## Guide
Instructions: NEPA Project Milestone Schedule
This template serves as a base for grantees to complete their NEPA Project Milestone Schedule. Only Column B must be complete by December 19th using the Planned Date to Submit (enter a date or N/A if not applicable). Upload the completed file under Letter of Credit in the Grant Application Contracting tab. One milestone schedule is required per contracted area. If multiple PAUs fall within the same county, upload one file per county. Grantees are expected to maintain and update this file as project milestones are achieved. ECD will gather the most recent version in each quarterly report.
Find an explanation of each column below:
Milestone: | This includes the major milestones required to complete each project's environmental review in compliance with NTIA's guidance. Please note, not every project will require the same permits depending on the area. ECD expects grantees to complete the relevant milestones and customize the template as needed for projects that require additional measures.
Planned Date to Submit: | The expected date the subgrantee intends to submit the item or trigger the action. Insert the date in the following format: MM/DD/YYYY
Date Sumbitted: | The date the subgrantee submitted the item or triggered the action, such as starting a consultation or submitting a permit application. Insert the date in the following format: MM/DD/YYYY
Date Accepted: | The date the milestone is formally cleared by the responsible agency or party. It marks the point when that review or permit is done and the subgrantee can move forward. Insert the date in the following format: MM/DD/YYYY
Notes: | Explain if there is a document accompanying this upload (for example, SHPO letter dated 1/16/2026 attached). If a milestone is not applicable, please explain why in the Notes column. Notes may also be used to communicated any issues or roadblocks to ECD.
Resources:
Link |  |  | Overview
NEPA for BEAD Frequently Asked Questions |  |  | Answers key environmental questions, including subgrantee and ESAPTT requirements
NTIA Permitting Resources |  |  | NTIA-provided resources and mapping tool that provides guidance on permits typically required for infrastructure deployment and related requirements of the BEAD program
USFWS IPaC Tool - Endangered Species Screening |  |  | Determines what impacts to sensitive natural resources are likely to occur from the project and provides suggestions for addressing them
FEMA Flood Map Service Center |  |  | Identifies floodplains
USFWS Wetlands Mapper |  |  | National Wetlands Inventory map that is used to screen for Clean Water Act/Section 404 triggers
Information on State Permits:
Agency Name |  | Division or Department |  | Permit Name | Permit Details
Tennessee Department of Transportation (TDOT) |  | Utilities Division |  | Use and Occupancy Permit (Fiber Optic on Freeways) | TDOT issues ROW occupancy permits for trenching, boring, or aerial fiber on state-maintained roads. Local municipalities and counties also require ROW permits for their roads.
Tennessee Dept of Environment and Conservation (TDEC) |  | Division of Water Resources |  | Hydrologic Determination (HD) | Determine whether a watercourse is legally classified as a stream or a wet weather conveyance (WWC) under Tennessee law.
Tennessee Dept of Environment and Conservation (TDEC) |  | Division of Water Resources |  | Aquatic Resource Alteration Permit (ARAP) | Fiber trenching or boring under waterways triggers these permits.
Tennessee Dept of Environment and Conservation (TDEC) |  | Division of Water Resources |  | Section 401 Water Quality Certification | When a project involves any discharge of dredged or fill material into waters of the United States/ Often paired with ARAP for projects affecting waters of the state.
Tennessee Dept of Environment and Conservation (TDEC) |  | Division of Water Resources |  | Tennessee Construction Stormwater General Permit | If your construction activities involve disturbing one acre or more of soil (e.g., trenching for underground fiber).
Railroad companies (various) |  |  |  | Railroad Crossing Permits | Fiber crossing railroad ROW.
Local electric cooperatives, municipal utilities, or private pole owners |  | Governed by FCC rules and Tennessee Valley Authority (TVA) agreements for co-op areas. |  | Utility Pole Attachment Permit | Using existing utility poles for aerial fiber.

## Project Milestone Schedule
Milestone | Planned Date to Submit | Actual Date Submitted | Date Accepted | Notes
Categorical Exclusion Review
Conduct Endangered Species Act (ESA) Section 7 obligations. This includes the use of the Information for Planning and Consultation (IPaC) tool and other relevant consultations
Conduct National Historic Preservation Act (NHPA) Section 106 Process. This includes any consultations required by Federal law, such as State Historic Preservation Office (SHPO)
Federal Agency Permits
Bureau of Land Management (BLM) ROW Authorization
Forest Service (FS) Special Uses
Clean Water Act Section (CWA) 404 / Rivers and Harbors Act (RHA) Section 10 - General Permit
Less Common Permits
National Park Service (NPS) ROW
U.S. Fish & Wildlife Service (USFWS) Special Uses Permit/ROW
Army Corps of Engineers (USACE) Section 408
Clean Water Act Section 401
Bureau of Indian Affairs (BIA) ROW
Bureau of Reclamation (BOR) ROW Authorization
State Permits (This list includes the most common state permits but is not exhaustive. Please add rows for any additional permits as needed.)
Use and Occupancy Permit (Fiber Optic on Freeways)
Hydrologic Determination (HD)
Aquatic Resource Alteration Permit (ARAP)
Section 401 Water Quality Certification
Tennessee Construction Stormwater General Permit
Railroad Crossing Permits
Utility Pole Attachment Permit
Local Permits (Please add rows to list the permit type, if applicable.)
Private Authorizations (Please add rows to list the permit type, if applicable.)

## Plan (hidden)
Environmental Compliance Monitoring Plan (Post-Construction/Active Construction) 1. Screening Approach Use updated project maps and plans to identify project location and proximity to sensitive features: wetlands, floodplains, habitats, cultural/historic areas. Check if the project has obtained a RoW access permit; this is considered a key indicator that some environmental evaluation has already occurred. 2. Project Category Names Enhanced Environmental Attention Projects in areas where sensitive environmental or historic features are present, especially those without a RoW permit. These locations may require closer monitoring, potentially including site inspections to verify compliance with all CPF environmental requirements and other relevant laws. Routine Environmental Review Projects with existing RoW permits and/or those located in areas where no major sensitive resources are present. These projects qualify for desktop checklist review—completion and submission of the CPF Environmental Questionnaire demonstrating compliance. 3. Monitoring Actions For Enhanced Environmental Attention Projects Conduct site inspections during construction or immediately post-construction. Review compliance with CPF and all applicable environmental permits, mitigations, and regulatory requirements. Document findings, non-compliance, corrective actions, and ongoing restoration efforts. For Routine Environmental Review Projects Require the completion and submission of the CPF Environmental Questionnaire as evidence of compliance. Desktop review includes verification of permit documentation, mapped project location, and answered compliance questions. Conduct periodic spot audits on a sampling basis, if deemed necessary. 4. Documentation and Reporting Centralize all project records including mapping analyses, category assignments, inspection reports, completed questionnaires, and corrective action logs. Prepare and submit summary reports for all projects, showing which category they fall into and how compliance has been verified.
| Category | Example Criteria | Monitoring Method
| Enhanced Environmental Attention | No RoW permit, near sensitive habitats | Site inspection and review
| Routine Environmental Review | Have RoW permit, standard location | Desktop checklist & audit
| Activity | Primary Responsible Stakeholder | Secondary Responsible Stakeholder
| Screening project maps and plans | Grantee | ECD
| Overlaying sensitive environmental data | Grantee | ECD
| CPF Environmental Checklist / Questionnaire completion | Grantee | ECD
| Desktop review of CPF Environmental Checklist | Accenture | ECD
| Identification of projects based on checklist response | Accenture | ECD
| Sensitive Projects - Environemental Assesment (Subject to ECD approval and review) | Grantee should hire an environmental experts to conduct assesment and provide results and permits to ECD | ECD
| Documenting findings and corrective actions | Accenture | ECD
| Centralizing compliance records | Accenture | ECD
| Preparing and submitting summary reports | Accenture | ECD

## Checklist (hidden)
Internal Checklist to Categorize Projects |  |  |  | Checklist to be filled by Grantee under Routine Environmental Review
Checkpoint | Yes / No | Notes / Action | Where to Check For | Has your project ensured compliance with the National Environmental Policy Act (NEPA), including required environmental assessments or impact statements, where applicable? ☐ Yes ☐ No ☐ Not Applicable Has the project obtained all necessary permits or clearances related to the Clean Water Act (CWA) concerning wetlands, waterbodies, and discharges? ☐ Yes ☐ No ☐ Not Applicable Have consultations been completed under the Endangered Species Act (ESA) and related services for threatened or endangered species? ☐ Yes ☐ No ☐ Not Applicable Have necessary reviews been conducted under the National Historic Preservation Act (NHPA) and any Tribal Historic Preservation obligations? ☐ Yes ☐ No ☐ Not Applicable Has the project addressed impacts related to the Rivers and Harbors Act, including work in navigable waters? ☐ Yes ☐ No ☐ Not Applicable Has compliance been ensured with the Clean Air Act (CAA) and related emission control programs? ☐ Yes ☐ No ☐ Not Applicable Has the project implemented proper handling or mitigation for hazardous materials consistent with RCRA, OSHA, and CERCLA? ☐ Yes ☐ No ☐ Not Applicable Has the project addressed concerns related to Superfund or contaminated sites? ☐ Yes ☐ No ☐ Not Applicable Has the project avoided or mitigated impacts to Wild and Scenic Rivers if applicable? ☐ Yes ☐ No ☐ Not Applicable Has compliance with the Safe Drinking Water Act (SDWA) been ensured for underground injections or water sources? ☐ Yes ☐ No ☐ Not Applicable Has the project taken steps consistent with the Farmland Protection Policy Act (FPPA) to minimize farmland conversion impacts? ☐ Yes ☐ No ☐ Not Applicable Has the project addressed Environmental Justice considerations under EO 12898, minimizing disproportionate impacts on minority or low-income communities? ☐ Yes ☐ No ☐ Not Applicable Has the project documented measures to prevent the introduction or spread of invasive species per EO 13112? ☐ Yes ☐ No ☐ Not Applicable Will the project avoid adverse impacts to migratory birds in accordance with EO 13186? ☐ Yes ☐ No ☐ Not Applicable Please describe any environmental incidents, non-compliance or mitigation measures taken during project activities (attach separate documentation if needed).
Does the project have an existing Right of Way (RoW) permit? |  | If Yes → Assign to Routine Environmental Review. Else, continue. | Ask Grantee to fill this information as part of their desktop review monitoring |  | Broadband Environmental Compliance Checklist For Middle Mile & Last Mile Grantees Step 1: Existing Infrastructure Check Are you ONLY using existing poles, conduit, or rights-of-way (ROW)? ☐ Yes → Likely no additional environmental compliance required (usually a categorical exclusion). STOP here. ☐ No → Proceed to Step 2. Step 2: Ground Disturbance Will your project involve new trenching, boring, or excavation (outside existing ROW or pole attachments)? ☐ Yes → Environmental review likely required. Continue checklist. ☐ No → Proceed to Step 3. Step 3: Water & Wetlands Will your project cross or impact: Wetlands Rivers, streams, or lakes Floodplains Coastal zones ☐ Yes → Permits/consultation required (Clean Water Act, CZM, floodplain management). ☐ No → Proceed to Step 4. Step 4: Protected Species & Habitats Could your project disturb threatened/endangered species or critical habitats? ☐ Yes → Consultation with U.S. Fish & Wildlife Service / NOAA / State Wildlife Agency required. ☐ No → Proceed to Step 5. Step 5: Cultural & Historic Resources Is your project near or within: Historic landmarks Tribal lands Archeological resources ☐ Yes → Consultation with SHPO/THPO required. ☐ No → Proceed to Step 6. Step 6: Railroad Crossings Will your project cross or run adjacent to a railroad ROW? ☐ Yes → Coordination with the railroad authority required; may trigger additional safety/environmental review. ☐ No → Proceed to Step 7. Step 7: Air, Noise, and Hazardous Materials Will construction cause significant noise, emissions, dust, or hazardous material disturbance? ☐ Yes → Compliance with Clean Air Act, OSHA/hazardous waste laws, and local ordinances required. ☐ No → Proceed to Step 8. Step 8: Mapping Potential Compliance Areas Upload a project route map showing: Green = Existing poles/ROW (low/no compliance) Yellow = Areas of new trenching/boring Orange = Sensitive areas (wetlands, historic sites, species habitat) Red = Railroad crossings or high-risk compliance areas Attach the map to funding documentation and keep for agency/consultant review. Step 9: Final Determination ✅ If all “No” after Step 2 → Minimal or no compliance required. ⚠️ If any “Yes” → Environmental consultation and permits needed before construction.
Does the project involve new trenching, boring, or excavation outside existing RoW or pole attachments? |  | If Yes → Assign to Enhanced Environmental Attention. Else, continue. | Ask Grantee to fill this information as part of their desktop review monitoring
Will the project occur in or near wetlands, rivers, streams, lakes, floodplains, or coastal zones? (CWA, CZMA, Floodplain Management, EO 11988, EO 11990) |  | If Yes → Enhanced Environmental Attention. | Screening Approach
Is the project located near or within threatened or endangered species habitats or critical habitats? (ESA, MSA, MMPA, EO 13112) |  | If Yes → Enhanced Environmental Attention. | Screening Approach
Does the project affect historic landmarks, tribal lands, cultural or archaeological resources? (NHPA, Tribal Historic Preservation Act) |  | If Yes → Enhanced Environmental Attention. | Screening Approach
Could the project involve work in, over, or under navigable waters? (Rivers & Harbors Act) |  | If Yes → Enhanced Environmental Attention. | Screening Approach
Will the project involve discharge or disposal of dredge or fill material into waters or wetlands? (CWA Section 404/401) |  | If Yes → Enhanced Environmental Attention. | Screening Approach
Will the project cause direct or indirect emissions in non-attainment areas for air quality? (CAA) |  | If Yes → Enhanced Environmental Attention. | Screening Approach
Will the project involve noise, hazardous material disturbance, or generate hazardous waste? (RCRA, OSHA, CERCLA) |  | If Yes → Enhanced Environmental Attention. | Screening Approach
Will the project involve storage or use of hazardous materials or petroleum products? (RCRA) |  | If Yes → Enhanced Environmental Attention. | Screening Approach
Will the project involve work in a Superfund or contaminated site? (CERCLA) |  | If Yes → Enhanced Environmental Attention. | Screening Approach
Is the project located within or adjacent to designated Wild and Scenic Rivers? (Wild and Scenic Rivers Act) |  | If Yes → Enhanced Environmental Attention. | Screening Approach
Will the project involve underground injection impacting drinking water sources? (Safe Drinking Water Act) |  | If Yes → Enhanced Environmental Attention. | Screening Approach
Will the project potentially impact farmland or agricultural lands? (Farmland Protection Policy Act) |  | If Yes → Enhanced Environmental Attention. | Screening Approach
Could the project impact coral reefs or marine sanctuaries? (EO 13089 – Coral Reef Protection) |  | If Yes → Enhanced Environmental Attention. | Screening Approach
Could the project introduce invasive species? (EO 13112 – Invasive Species) |  | If Yes → Enhanced Environmental Attention. | Screening Approach
Will the project likely disturb migratory birds during their season? (EO 13186) |  | If Yes → Enhanced Environmental Attention. | Screening Approach