## EXAMPLE TRACKER
Tennessee Department of Education Pathway Selection Tool |  |  |  | USE: Identify the overall project manager. (1) Determine your selected pathway. (2) The "Topic Area" section of the tracker is filled with the subjects from the toolkits. Districts can retain, add, or eliminate as needed. (3) Read and review all appropriate toolkits. (4) Determine the big-bucket categories that need to be addressed by the district from the toolkits, which may be listed in the checklist or startegies sections. (5) Using the toolkits, list the specific activities and actions that need to take place. (6) List the owners of the overall work and of each activity. (7) Idenitfy the deliverable date of acivities. Manage against this through reopening.
PATHWAY | CATEGORY | TOPIC AREA | DISTRICT OWNER | DESCRIPTION | LIST OF ACTIVITIES | ACTIVITY LEAD | SUGGESTED DELIVERABLE DATE: JUNE | [20 empty] | SUGGESTED DELIVERABLE DATE: JULY
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
[ex. TRADITIONAL RETURN] | PROGRAM | DISTRICT PLANNING GROUP |  | RE-OPENING TASK FORCE TO INCLUDE MULTIPLE STAKEHOLDERS
|  | BOARD RELATIONS |  | CALENDAR AND OPTIONS
BUDGET
REGULAR UPDATES
BOARD MEETING PLANNING
|  | ACADEMICS |  | ELEMENTARY PLAN
MIDDLE SCHOOL PLAN
HIGH SCHOOL PLAN
INSTRUCTIONAL MATERIALS
ASSESSMENT PLAN
|  | PROFESSIONAL DEVELOPMENT |  | STAFF - TECHNOLOGY
STAFF - REOPENING
FAMILIES AND STUDENTS - REOPENING
STAFF - PROCEDURES
STUDENTS - PROCEDURES
|  | SPECIAL POPULATIONS |  | ORGANIZE MEETING REQUIREMENTS
COMPENSATORY EDUCATION
STRATEGIC ALLOCATION OF SERVICES
DISTANCE PLAN
HOMELESS YOUTH
ENGLISH LEARNER PLANS
FOSTER YOUTH
MIGRANT AND HIGHLY MOBILE YOUTH
AT-RISK HEALTH YOUTH
|  | POST-SECONDARY TRANSITIONS |  | COORDINATION WITH COLLEGES
COORDINATION WITH TBR
DUAL CREDIT MANAGEMENT
PARTNERSHIPS
OTHER
|  | INSTRUCTIONAL STAFF |  | VERTICAL AND HORIZONTAL TEAMS
REVISED HR POLICIES
EMPLOYMENT OPTIONS FOR NON-SITE BASED
LICENSURE
RECRUITMENT
| OPERATIONS | NUTRITION |  | MEAL DISTRIBUTION PLANS
SUPPLY CHAIN ORDERING (INDIVIDUAL AND NON-PERISHABLE)
PLANS FOR CLOSURE
FINANCIAL MANAGEMENT
STAFF TRAINING AND SUPPORT
STUDENT TRAINING
|  | TRANSPORTATION |  | IDENTIFY TRANSPORTATION NEEDS
IDENTIFY SANITATION NEEDS
IDENTIFY BUDGET AND CAPACITY
IDENTIFY ALTERNATE ROUTES
CONTRACT MANAGEMENT
STAFFING MANAGEMENT
STAFF TRAINING AND SUPPORT
STUDENT PLANNING AND TRAINING
|  | FINANCE |  | IDENTIFY SOURCE OF FUNDS
REVISED BUDGET
FORECASTING
COVID TRACKING
OTHER
|  | CONSOLIDATED FUNDING |  | OVERALL
GRANT MANAGEMENT
MONITORING IN ALTERNATIVE SETTING
|  | TECHNOLOGY |  | PLANNING/NEEDS ASSESSMENT
BUDGETING - CARES AND LOCAL
DISTRIBUTION PLAN
TRACKING PLAN
STAFF TRAINING
STUDENT TRAINING
TROUBLESHOOTING
CALL CENTER
CONTENT DISTRIBUTION
REPLACEMENT AND INSURANCE
OTHER
|  | SAFETY |  | REVISE EMERGENCY OPERATIONS PLAN
CREATE PANDEMIC PLAN
POST-RECOVERY EVALUATION
UPDATES TO DRILLS AND EVACUATION PROCEDURES
OTHER
|  | COMMUNICATIONS |  | COMMUNICATIONS PLAN
SOCIAL MEDIA STRATEGY
PHONE COMMS STRATEGY
ONLINE AND EMAIL STRATEGY
COMMUNITY MEETING OR VIRTUAL MEETINGS
FEEDBACK FACILITATION
| HEALTH AND WELLNESS | MENTAL HEALTH |  | OPTIONAL SCREENER WITH PARENT PERMISSION
NEEDS ASSESSMENT AND SUPPORT PLAN
|  | PHYSICAL HEALTH |  | POSITIVE CASE MANAGEMENT AND COMMUNICATIONS
SCHOOL NURSE AND CSH TRAINING
QUARANTINE AND ILLNESS PROCEDURES
|  | SCHOOL CULTURE AND CLIMATE |  | DESIGN A WELCOME BACK FOR STUDENTS AND FAMILIES
DESIGN REVISED PROCEDURES FOR FIRST MONTH TO BUILD CULTURE
CREATE CULTURE AND CLIMATE TRACKER FOR STUDENT SUPPORT
|  | SOCIAL DISTANCING |  | DISTRICT POLICIES AND PROCEDURES
SCHOOL-BASED POLICY AND PROCEDURES
ORDERING AND PPE MANAGEMENT
MONITORING AND SUPPORT
|  | VIRUS MONITORING AND REPORTING |  | COORDINATION WITH STATE AND LOCAL OFFICIALS
| OTHER PROGRAMS | EARLY CHILDHOOD PROGRAMS AND VPK |  | ENROLLMENT TRACKING
STAFF TRAINING
FAMILY EXPECTATIONS
COMMUNICATION
OTHER
|  | COUNSELING |  | NEEDS ASSESSMENT
STAFFING REQUIREMENTS
CASELOAD MANAGEMENT SYSTEM
ANNUAL SCHEDULE
OTHER
|  | POLICY AND LEGAL |  | LEGAL REVIEW OF ALL CONTENT
NEW POLICY DEVELOPMENT
EXISTING POLICY REVISION
STATE BOARD REQUESTS
OTHER
|  | PUBLIC CHARTERS AND NON-PUBLICS |  | EQUITABLE SERVICES MANAGEMENT AND TRACKING
COMMUNICATIONS
OTHER
|  | SCHOOL IMPROVEMENT |  | SCHOOL PLANS
DATA TRACKING
COMPARABLE TRACKING
ADDITIONAL GAP ANALYSIS
ADDITIONAL RESOURCE MANAGEMENT
OTHER