## 2018_2019
STATE OF TENNESSEE
FY 2018~2019 OPERATIONAL CLOSE~OPEN CALENDAR
Due Date | Task | Responsibility Of
GENERATE FY18 EDISON ZERO BUDGET
2018-06-15 | Notify F&A Budget of changes to allotment codes to be effective Jul 1 | State Agencies
2018-06-29 | Generate FY19 zero budget entries | Accounts
2018-06-30 | Begin making additions or changes to FY19 zero budget entries | Accounts
BEGINNING OF NEW FISCAL YEAR
2018-06-22 | Notify Accounts of approved changes to allotment codes that must be made by Jul 1 | F&A Budget
2018-06-22 | Requests for new FY19 chartfields that must be established by Jul 1 | State Agencies
2018-06-22 | Requests for changes/new speedcharts for FY19 that must be completed by Jul 1 | State Agencies
2018-06-22 | Agencies request to Edison new iNovah allocations for FY19 | State Agencies
2018-06-22 | Agencies request to Edison to change existing allocations to a different speedchart | State Agencies
2018-07-01 | Edison ready for input of FY19 transactions | Edison
7/1-7/3 | Edison run Speedchart update for iNovah | Edison
TRAVEL
Expense Reports
2018-06-29 | Expense reports for FY18 must be submitted by employee or proxy | State Agencies
2018-07-01 | Delete FY18 expense reports created using a TA and not submitted by Jun 30 | Edison
2018-07-06 | Expense reports for FY18 approved by the HR Supervisor | State Agencies
2018-07-09 | Deny FY18 expense reports not approved by HR Supervisor | Edison
2018-07-11 | Expense reports for FY18 approved by the Fiscal Office | State Agencies
2018-07-12 | Deny FY18 expense reports not approved by Fiscal Office | Edison
Travel Authorizations
2018-07-11 | TAs submitted in FY18 for an FY19 trip must be approved for roll-over to FY19 | State Agencies
7/1-7/13 | Approved FY18 TAs not used on an expense report will be rolled to FY19 | Edison
2018-07-13 | Delete FY18 and prior year TAs not approved by HR supervisor | State Agencies
Cash Advances
2018-06-29 | Pay back any outstanding cash advances for trip taken in FY18 or prior | State Agencies
REQUISITIONS, PURCHASE ORDERS AND DISBURSEMENTS
2018-06-29 | Requisitions to be carried forward into FY19 must be associated with a non-budgeted account | State Agencies
2018-07-02 | Last June Pcard file loaded | Edison
2018-07-02 | Begin canceling open FY18 requisitions remaining associated with a budgeted account | Edison
2018-07-02 | Begin canceling FY19 receipts for FY18 POs (if they are created) | Edison
2018-07-06 | Pcard transactions must be reconciled for Billing Date 6/30/18 | State Agencies
2018-07-09 | Record FY18 receipts against POs for FY18 received merchandise | State Agencies
2018-07-09 | Create AP Vouchers for goods/services received in FY18 | State Agencies
2018-07-09 | Close or cancel all FY18 POs that should not be rolled to FY19 | State Agencies
2018-07-01 | Begin to delete any FY18 Vchrs with mismatched Acct/Budget Dates between PO and Vchr | Edison
2018-07-13 | Begin PO Roll-Over to FY19 for all qualified FY18 POs | Edison
2018-07-10 | AP Vouchers greater than $2,000 approved by agency | State Agencies
2018-07-12 | AP Vouchers less than $2,000 approved by agency | State Agencies
2018-07-12 | AP Vouchers greater than $2,000 approved by Accounts | Accounts
2018-07-13 | Delete all FY18 AP Vouchers not in approved status | Edison
WARRANT CANCELLATION AND REISSUES
2018-07-06 | Cutoff for Accounts receipt of cancellation and reissues from agencies | State Agencies
2018-07-11 | Warrant cancellations and reissues processed | Accounts
DEPOSITS
2018-06-30 | Deposit monies received on June 30 in time to make cutoff for deposits on June 30 | State Agencies
2018-07-06 | June batches in Inovah in close status | State Agencies
2018-07-09 | June deposits submitted in PeopleSoft | State Agencies
2018-07-11 | Deposits and related accounting recorded for all FY18 ACH and fedwire receipts | State Agencies
PREPAID GRANTS
2018-07-12 | Finalize billings/invoices for FY18 collected prepaids associated with grants (customer revenue contracts) | State Agencies
EDISON SUBMODULES
2018-07-12 | Edison submodules closed for FY18 except Customer Contract Module (revenue recognition) and automated indirect cost processing | Edison
2018-08-09 | Edison Customer Contract Module closed for FY18 (grants/projects revenue recognition for FY18 transactions no longer automated) | Edison
2018-08-09 | Grants/projects automated indirect cost processing for FY18 stopped | Edison
GENERAL LEDGER JOURNALS
Sales Tax Payment Journals (IU)
2018-07-05 | Entry (debit side) of IU journals paying sales tax to TDOR | State Agencies
2018-07-06 | Entry (credit side) and submission of IU journals paying sales tax | TDOR
2018-07-09 | Approval by creating agencies of IU journals paying sales tax | State Agencies
2018-07-11 | Approval of IU journals paying sales tax by Accounts | Accounts
Multi-Unit Journals (MU)
2018-07-16 | Entry/approval of multi-unit MU journals into Edison | State Agencies
2018-07-17 | Approval of multi-unit MU journals by Accounts | Accounts
Accrued Liability Journals (LA)
2018-07-27 | Entry of accrued liability LA journals into Edison | State Agencies
2018-07-30 | Approval by creating agency of accrued liability LA journals | State Agencies
2018-08-02 | Approval of accrued liability LA journals by Accounts | Accounts
Inter-Unit Journals (IU)
2018-07-30 | Entry of IU journals by the creating agency | State Agencies
2018-08-01 | Entry and submission by second agency on IU journals | State Agencies
2018-08-02 | Approval by the creating agency and the second agency for IU journals | State Agencies
2018-08-06 | Approval of IU journals by Accounts | Accounts
Other Journals Affecting Projects/Grants (JV/AG/EX)
2018-08-03 | Entry of miscellaneous JV/AG/EX journals to correct a previous FY18 transaction affecting projects/grants | State Agencies
2018-08-06 | Approval by creating agency of miscellaneous JV/AG/EX journals to correct a previous FY18 transaction affecting projects/grants | State Agencies
2018-08-08 | Approval of miscellaneous JV/AG/EX journals to correct a previous FY18 transaction affecting projects/grants by Accounts | Accounts
Other Journals NOT Affecting Projects/Grants (JV/AG/EX)
2018-08-21 | Entry of miscellaneous JV/AG/EX journals to correct a previous FY18 transaction NOT affecting projects/grants | State Agencies
2018-08-23 | Approval by creating agency of miscellaneous JV/AG/EX journals to correct a previous FY18 transaction NOT affecting projects/grants | State Agencies
2018-08-27 | Approval of miscellaneous JV/AG/EX journals to correct a previous FY18 transaction by Accounts NOT affecting projects/grants | Accounts
Accounts Receivable Against Accrued Liabilities Journals (RA)
2018-08-03 | Entry of accounts receivable against accrued liabilities RA journals | State Agencies
2018-08-06 | Approval by creating agency of accounts receivable against accrued liabilities RA journals | State Agencies
2018-08-08 | Accounts receivable against accrued liabilities RA journals approved by Accounts | Accounts
Accounts Receivable Not Against Accrued Liabilities Journals (RA)
2018-08-20 | Entry of accounts receivable not against accrued liabilities RA journals | State Agencies
2018-08-21 | Approval by creating agency of accounts receivable not against accrued liabilities RA journals | State Agencies
2018-08-23 | Accounts receivable not against accrued liabilities RA journals by Accounts | Accounts
COST ALLOCATION PROCESSING
2018-07-18 | Cost allocation processing begins for period 12 | Edison
2018-08-09 | Cost allocation processing begins for period 991 | Edison
2018-08-28 | Cost allocation processing begins for period 992 | Edison
EDISON CLOSING
2018-07-13 | Open period 991 for FY18 | Edison
2018-07-20 | Close period 12 for FY18 | Edison
2018-08-03 | Open period 992 for FY18 | Edison
2018-08-13 | Close period 991 for FY18 | Edison
2018-08-24 | Open period 993 for FY18 | Edison
2018-08-30 | Close period 992 for FY18 | Edison