## Cover Page
RFP Attachment 6.3 - Cost Proposal
Cost Proposal & Scoring Guide
SBC Project No.: |  | 361/000-03-2025
Project: |  | TEMA New EOC and Administrative Building
NOTICE: THIS COST PROPOSAL MUST BE COMPLETED EXACTLY AS REQUIRED
Please Complete All Yellow Shaded Areas
COST PROPOSAL SCHEDULE — The proposed cost and the submitted technical proposal associated with this cost must remain valid for at least 120 days subsequent to the date of the Cost Proposal opening and thereafter in accordance with any resulting contract between the Respondent and the State. All monetary amounts are United States currency and limited to two places right of the decimal point.
NOTICE: | The evaluation factors, GMP Months and GMP Target, do NOT and should NOT be construed as any type of guarantee. The evaluation factors shall NOT create rights, interests, or claims of entitlement in the Respondent.
The signatory must be in individual or company officer empowered to contractually bind the Respondent
RESPONDENT LEGAL ENTITY NAME:
RESPONDENT SIGNATURE:
PRINTED NAME & TITLE:
DATE:

## Section A
SECTION A
CM/GC CONSTRUCTION SERVICES PRE-CONSTRUCTION PHASE SERVICES LUMP SUM FEE
RESPONDENT LEGAL ENTITY NAME:
Provide the total lump sum fee for delivery of the Pre-Construction Phase Services for this Project as defined by CM/GC Scope of Services and Deliverables, Section 1. This fee must not include costs of printing the Designer’s design/construction documents, geotechnical investigations, environmental testing, and property surveys during the Design Phase. This fee will be paid upon successful completion of services and is not to be included as a part of the CM/GC construction services fixed fee.
The Pre-Construction Fee will be paid according to the following schedules
| • Schematic Design Phase: | 35%
| • Design Development Phase: | 35%
| • Construction Document Phase: | 20%
| • Conclusion of Trade Contractor Buy Out: | 10%
Pre-Construction Phase Services Lump Sum Fee (The State will insert value at RFP Attachment 6.3., Section G.1.) |  | 0

## Section B
SECTION B
CM/GC CONSTRUCTION SERVICES FEE PERCENTAGE
RESPONDENT LEGAL ENTITY NAME:
The proposed cost for the CM/GC construction services percent fee (the “Fee”) will be for providing the construction services defined in the CM/GC Scope of Services and Deliverables, Section 2 for the total contract time and project closeout. The Fee must be stated as a percentage of the Project construction cost that includes the following:
COST PROPOSAL SCHEDULE — The Cost Proposal, detailed below, shall indicate the proposed price for goods or services defined in the Scope of Services of the RFP Attachment 6.6., Pro Forma Contract and for the entire contract period. The Cost Proposal shall remain valid for at least one hundred twenty (120) days subsequent to the date of the Cost Proposal opening and thereafter in accordance with any contract resulting from this RFP. All monetary amounts shall be in U.S. currency and limited to two (2) places to the right of the decimal point. | • General company overhead and profit;
• Personnel not directly assigned to the Project such as accountants, clerks, secretaries, and personnel other than those listed under Construction Services General Conditions Budget (whether on site or in the office);
• Company officers and other personnel with supervisory status not listed under Construction Services General Conditions Budget;
• The cost of main office equipment and related supplies, maintenance and service not located on site; and
• THIS PERCENTAGE WILL BE MULTIPLIED BY THE PROJECT BUDGET CONSTRUCTION COST LISTED IN SECTION D FOR EVALUATION PURPOSES; HOWEVER, THE FINAL FEE WILL BE CALCULATED BASED UPON THE GUARANTEED MAXIMUM PRICE (GMP), EXCLUSIVE OF THE BOND AMOUNT AT THE SUBMISSION OF THE GMP
CM/GC Construction Services Fee Percentage (The State will insert value at RFP Attachment 6.3., Section G.2.) |  | 0%

## Section C
SECTION C
CM/GC CONSTRUCTION SERVICES GENERAL CONDITIONS MONTHLY RATE
RESPONDENT LEGAL ENTITY NAME:
Provide the proposed General Conditions Total Monthly Costs as described below for the construction scope and the construction services target duration identified in the RFP for the date of start of construction given in Section 1.7, shown below as a Total Monthly Rate. This rate will be multiplied by the duration of the project, in months, to determine a not to exceed amount for the Monthly General Conditions. General Conditions must be invoiced at actual cost.
The proposed amount must include all General Conditions monthly costs for personnel and equipment of the quantity and type required to accomplish the services as defined by the RFP and the scope of the project for the entire duration of the Contract Time defined by the Pro Forma General Conditions and the GMP. Monthly costs include, but are not limited to, the following:
• Personnel costs including Labor Burden of all personnel directly assigned to the Project including but not limited to:
|  | Superintendent; | Construction Documentation Manager/Coordinator
Assistant Superintendent;
|  | Project Manager; | Trades Coordinator
|  | BIM Manager | Project Scheduler
|  | Project Director | Clerk
|  | Project Engineer | Other supervisory personnel
Safety Director
• Photography and videography for normal documentation of the progress of the Work;
• Temporary utilities usage charges required for contractor support facilities;
• Project office trailers
• Storage trailer(s) for CM and general usage;
• Portable restroom facilities;
• Phones, pagers, faxes, e-mails, and other communications devices;
• Computers, copiers, printers, and other electronic office equipment;
• Software and subscription costs incurred by the CM/GC in the management of the project;
• Safety measures (including, but not limited to, personal protective equipment, fire protection, safety signage, and training);
• Vehicle costs including fuel, maintenance, rentals, leases, and other related items;
• Parking fees and shuttle services;
• Contractor support facility office furniture and equipment;
• Contractor support facility supplies and other expenses;
• Refuse dumpster rental and disposal (not including those dedicated to HPBr recyclables or demolition materials);
• Dust control for the whole Project (including, but not limited to, filtration material, and other measures to prevent damage to installed materials); and
• Daily, Weekly, and Monthly cleanup for the whole Project.
Note: All charges for the project as a direct expense of the Construction Manager must be included either as a Monthly General Conditions Rate or as a part of the General Conditions Total Lump Sum Cost. All other work must be competitively procured as a part of the GMP
CM/GC General Conditions Total Monthly Rate: (The State will insert value at RFP Attachment 6.3., Section G.3.)

## Section D
SECTION D
CM/GC CONSTRUCTION SERVICES GENERAL CONDITIONS TOTAL LUMP SUM COSTS
RESPONDENT LEGAL ENTITY NAME:
Provide the proposed General Conditions Total Lump Sum Costs as described below for the construction scope and the construction services target duration identified in the RFP for the date of start of construction given in Section 1.7, shown below as a Total Lump Sum Costs. This cost will be used as a not to exceed amount for the Lump Sum General Conditions. General Conditions must be invoiced at actual cost.
The proposed amount must include all General Conditions lump sum costs of the quantity and type required to accomplish the services as defined by the RFP and the scope of the project for the entire duration of the Contract Time defined by the Pro Forma General Conditions and the GMP. Lump sum costs include, but are not limited to, the following:
• Project mobilization and demobilization charges;
• Installation and deinstallation of conveyance systems for temporary utilities;
• Project layout and surveying;
• All required permits and related fees;
• Builder’s Risk insurance as required by the Pro Forma General Conditions;
• Temporary project signage;
• All general project testing if not procured as a part of a separate package;
• All temporary construction items not included as a Monthly cost;
• Reproduction of documents for sub trades;
• Trade contract bidding including advertising;
• Printing and record drawings;
• Substantial Completion;
• Project closeout;
• Project punch list work and final inspection;
• Warranty inspection; and
The following items are considered General Conditions but must be listed separately on the next page of this section and not included in the CM/GC General Conditions Total Lump Sum Costs on this page:
• Contract Bond;
• Subcontractor Default Insurance
• Contractor Controlled Insurance Program
Any additional costs in these three amounts during Buyout will be drawn against the Lump Sum General Conditions
Note: All charges for the project as a direct expense of the Construction Manager must be included either as a Monthly General Conditions Rate or as a part of the General Conditions Total Lump Sum Cost. All other work must be competitively procured as a part of the GMP.
CM/GC General Conditions Total Lump Sum Costs: Excluding Contract Bond, Subcontractor Default Insurance, and Contractor Controlled Insurance Program (The State will insert value at RFP Attachment 6.3., Section G.4.) |  | 0

## Section E
SECTION E
CM/GC CONSTRUCTION SERVICES PERCENTAGE BASED GENERAL CONDITIONS COSTS
RESPONDENT LEGAL ENTITY NAME:
The following items are considered General Conditions costs but must be listed here and calculated at the time of submission of the Guaranteed Maximum Price. Any overruns in the actual costs of these three items will be invoiced against the Lump Sum General Conditions. All rates must be provided in order to evaluate the respondent’s cost proposal, regardless of whether the respondent normally utilizes a Contractor Controlled Insurance Program or a Subcontractor Default Insurance program. The substitution of alternate solutions will occur during the pre-construction services phase according to the paragraphs below. Failure to list all rates will cause the entire cost submission to be deemed unresponsive.
Contract Bond Rate (Based on the total GMP target) (The State will insert value at RFP Attachment 6.3., Section G.5.) | 0%
Subcontractor Default Insurance Rate (The State will insert value at RFP Attachment 6.3., Section G.6.) | 0%
Contractor Controlled Insurance Program Rate: (The State will insert value at RFP Attachment 6.3., Section G.7.) | 0%
If a CM/GC elects to utilize bonding of individual trade subcontractors in lieu of providing Subcontractor Default Insurance, that election must be proposed to the State prior to the submission of the GMP. If proposed, the CM/GC must provide to the State an analysis of the costs demonstrating whether the bonding of individual trade subcontractors is less costly to the Owner than Subcontractor Default Insurance. If the option of bonding individual trade subcontractors is more costly and the CM/GC is still recommending that option as being in the best interest of the project, the CM/GC must provide to the State a written justification of such recommendation, including analysis of associated costs and intangible items contributing to this recommendation. The State reserves the right to determine the course of action that provides the best financial and practical benefit to the project.
If a CM/GC elects to utilize individual insurance programs for each trade subcontractor in lieu of providing a CCIP, that must be proposed prior to the submission of the GMP. To facilitate this, the CM/GC must provide an analysis of the costs demonstrating individual insurance programs are less costly to the Owner than a CCIP. If the CM/GC is recommending that the more costly option of using individual insurance programs would still be in the best interest of the project, the CM/GC must provide to the State written justification of such recommendation, including analysis of associated costs and intangible items contributing to this recommendation. The State reserves the right to determine the course of action that provides the best financial and practical benefit to the project.

## Section F
SECTION F
CM/GC CONSTRUCTION SERVICES GENERAL REQUIREMENTS
RESPONDENT LEGAL ENTITY NAME:
Below is a list of allowable General Requirements for this project. The Respondent is not required to provide any costs for these items at this time as these costs will be provided as part of the submission of the Guaranteed Maximum Price. General Requirements are defined as work performed by the CM/GC for the benefit of the Work but is not incorporated into the Work. The Owner prefers that General Requirements are directly procured by the CM/GC rather than procured in individual trade packages, however General Requirements will be limited to be a maximum of 3% of the total of all Trade Costs.
General requirements include but are not limited to the following:
• Scaffolding and lifts;
• Crane rental and operation;
• Erosion control measures;
• Project testing and special inspections;
• Project Final Cleaning including trade cleaning;
• Gross receipts tax;
• Other General Requirements identified by the Respondent:
•
•
•
•
•
•
•
•
•
•
•
•
•
•
Note: No items may be included as General Requirements that are listed on the proceeding pages as General Conditions.

## Section G
SECTION G
COST PROPOSAL SUMMARY & SCORING
RESPONDENT LEGAL ENTITY NAME:
1 | PRE-CONSTRUCTION PHASE SERVICES LUMP SUM FEE (SECTION A) |  |  |  |  | 0
Pre-Construction Phase Services Lump Sum Fee
(This form will insert value from RFP Attachment 6.3., Section A.)
2 | FEE PERCENTAGE (SECTION B) |  |  |  |  | 0
| Construction Services Fee |  | X | GMP Target
| 0% |  |  | 199050000
| Note: This figure is for evaluation purposes ONLY. See Section B for additional information regarding the final calculation for Construction Services. |  |  |  |  | (This form will insert value from RFP Attachment 6.3., Section B and multiply by GMP TARGET)
3 | GENERAL CONDTIONS MONTHLY RATE (SECTION C) |  |  |  |  | 0
| Construction Services General Conditions Budget – Monthly Cost Total |  | X | GMP Months
| 0 |  |  | 24 |  | (This form will insert value from RFP Attachment 6.3., Section C and multiply by GMP MONTHS)
Note: The months are for evaluation purposes only.
4 | GENERAL CONDTIONS TOTAL LUMP SUM COSTS (SECTION D) |  |  |  |  | 0
Construction Services General Conditions Budget – Lump Sum Total
(This form will insert value from RFP Attachment 6.3., Section D)
5 | CONTRACT BOND RATE (SECTION E) |  |  |  |  | 0
| Construction Bond Amount |  | X | GMP Target
| 0% |  |  | 199050000
| Note: This figure is for evaluation purposes only; the stated percentage rate will be calculated based on the submitted GMP. |  |  |  |  | (This form will insert value from RFP Attachment 6.3., Section E and multiply by GMP TARGET)
6 | SUBCONTRACTOR DEFAULT INSURANCE RATE (SECTION E) |  |  |  |  | 0
| Subcontractor Default Insurance Rate |  | X | 80% | GMP Target
| 0% |  |  |  | 199050000
| Note: This figure is for evaluation purposes only. The stated percentage rate will be calculated against the estimated value of subtrade csots at the time of GMP submission. |  |  |  |  | (This form will insert value from RFP Attachment 6.3., Section E and multiply by GMP TARGET)
7 | CONTRACTOR CONTROLLED INSURANCE PROGRAM (SECTION E) |  |  |  |  | 0
| Contractor Controlled Insurance Program |  | X | GMP Target
| 0% |  |  | 199050000
| Note: This figure is for evaluation purposes only. The stated percentage rate will be calculated against the estimated value of General Conditons, General Requirements, and subtrade costs as the time of GMP submission. |  |  |  |  | (This form will insert value from RFP Attachment 6.3., Section E and multiply by GMP TARGET)
TOTAL COST ITEMS 1 - 7 | [5 empty] | 0
Note: The Procurement Officer will use the above calculated total cost and the formula below to calculate the Cost Proposal Score. Numbers rounded to 2 places to the right of the decimal point will be standard for calculations.
Lowest Cost from All Proposals |  | X | 30 |  | = SCORE
Cost of this Proposal
Actual calculations for the GMP will be made using Attachment F – GMP Submission. This workbook contains instructions on how calculations are made with respect to rates provided above. A fillable workbook will be made available for the submission of the actual GMP.

## DATA (hidden)
| GMP TARGET | 199050000
| GMP MONTHS | 24
1 | PCP Lump Sum Fee | 0
2 | Fee Percentage | 0%
3 | GC Monthly Rate | 0
4 | GC Lump Sum | 0
5 | Contract Bond Rate | 0%
6 | SDI Rate | 0%
7 | CCIP Rate | 0%