Q1    April 1 2018 – June 30, 2018

Quarterly Report:

Tennessee Health Management, Inc.

Legal Name of Organization:

1971 Tennessee Avenue North

P.O. Box 10

Parsons, TN  38363

Mailing Address, City, State, and Zip:

621541543

212086

731-847-6343

Phone:		   	        	EIN:		     		Edison Vendor ID:

Mike  Bailey, CEO

CEO/Executive Director:

mbailey@thmgt.com

731-847-6343

Phone:					Email:

Heather Lansaw, Regional Director of Operations

Project Leader:

hlansaw@thmgt.com

731-695-8981

Phone:					Email:

Activities, Restorative, and Therapy in Sync (ARTS)

Program name:

Z18172268, Amendment:  Z18176942

Grant ID Number:

April 1, 2018 - March 31, 2021

Dates Covered by this Grant:

$493,550.87

Grant Amount:

The objective of the Activities, Restorative, and Therapy in Sync (ACTS) program is to provide the residents in our care an improved quality of life through the implementation of It’s Never 2 Late (iN2L) – fusing activities, restorative care, and therapy into a truly individualized approach.  By aligning the patients’ personal interests and functional limitations with activities, restorative programs, and therapy treatment in a computer-based format, we will improve or maintain the patients’ activities of daily living, increase the number of residents in activities, and increase the number of residents in the restorative program.  This movement to synchronize the different programs will have a direct impact on the culture in our communities and improve the quality of life for those we serve.

Summary of Grant Purpose:

The goals of the project are to 1) to improve or maintain ADL function, and 2) increase patient participation in person-centered recreational and rehabilitation activities.

The iN2L equipment was delivered and initial onsite training for the staff was completed.  Residents were also trained on the iN2L system through numerous resident council meetings and trainings.  Invitations to trainings and in-services were posted throughout the facilities for staff, residents and family members.  (Attachment #4 contains examples of invitations and training sessions).  The baseline data was obtained along with the data for the April – June 2018 quarter.  A press release was finalized and released June 2018 to promote the program to the public and stakeholders (Attachment #2).

| Project Tasks / Process Objectives | Timeline Month/Year | Responsible Party | Date Completed | Notes |
| --- | --- | --- | --- | --- |
| Grant Awarded—sign contract, workout logistics | Apr-18 | Regional Director of Operations | Apr-18 |  |
| Purchase iN2L equipment, schedule initial Onsite Activity-Specific and Therapy-Specific Trainings, System Installations and Program Rollouts for all 10 Memphis Region facilities | May-18 | Regional Director of Operations; THM-Memphis Region Administrators | May-18 |  |
| Collect and record MDS, Restorative Care Log, and Activity Log baseline data | May-18 | THM-Memphis Region Administrators | May-18 |  |
| Inform stakeholders of the project and explain the benefits through the newsletter, flyers, and meetings | Jun-18 | THM-Memphis Region Administrators | Jun-18 | Facilities completed staff meetings, spoke at Resident Council meetings to ensure staff was aware of the program and its benefits. Flyers posted for meetings throughout the facilities |
| Participate in Activities and Therapy-specific On-Site Trainings, System Installations and Program Rollouts | Jul-18 | Regional Director of Operations; THM-Memphis Region Administrators | Jun-18 | Training staff from April – May 15th. Rollout completed by June 2018 for all facilities. |
| Meeting with the Patients to educate on the New Program** | Jun-18 | Activities Directors | Jun-18 | Completed in Resident Council along with individual meetings for some patients. |

Baseline Data Obtained:

- ADL Function on the Minimum Data Set of study group.

- Number of Activities Attended by the study group.

- Total number of Residents participating in the restorative program

Other data:

- iN2L Usage Documentation from iN2L

- Resident Questionnaires (Attachment #2)

| List of Long Term Residents that had a decrease or anticipated decrease in ADL function prior to implementation of the program. # of pts. in study | Average Total ADL Score at Baseline for Self Assessment Section G Lines A-J Self Performance only. (April 2018) 7 or 8 counted as a 4. |  | 6/30/18 |
| --- | --- | --- | --- |
| Applingwood 20 | 24.55 |  | 24.15 |
| Bright Glade 19 | 30.18 |  | 30.23 |
| Covington Care 19 | 37.32 |  | 30.58 |
| Dyersburg 24 | 29.50 |  | 28.92 |
| Harbor View 20 | 31.85 |  | 32.01 |
| Humboldt 10 | 31.00 |  | 31.50 |
| McKenzie 19 | 29.05 |  | 29.05 |
| Paris 20 | 25.85 |  | 26.00 |
| Union City 24 | 24.80 |  | 25.25 |
| VanAyer 20 | 30.35 |  | 31.10 |
| Totals - Averaged 195 total patients in study | 29.45 |  | 31.10 |

Initial data obtained from the MDS Average Total ADL Score for Self Assessment  Section G Lines A-J (Self Performance only), indicate a slight increase in the Average score from the baseline.  Applingwood, Covington Care, Dyersburg, and McKenzie have improved or maintained the ADL scores for the study group.  4 of the 10 facilities produced positive results in maintaining or improving patients’ self-performance of Activities of Daily Living.

| Of the participants that are in the case study, how many activities did they attend per month in total? This number is averaged on this form. | 4/30/2018 | 05/31/18 | 06/30/18 |
| --- | --- | --- | --- |
| Applingwood | 19 | 13 | 23 |
| Bright Glade | 16 | 17 | 15 |
| Covington Care | 25 | 19 | 11 |
| Dyersburg | 13 | 14 | 15 |
| Harbor View | 8 | 8 | 6 |
| Humboldt | 30 | 30 | 40 |
| McKenzie | 9 | 10 | 10 |
| Paris | 16 | 21 | 22 |
| Union City | 16 | 19 | 15 |
| VanAyer | 40 | 46 | 39 |
| Totals | 19 | 20 | 19 |

This information is obtained by the number of Activities input into the computer per each resident.  During calls reviewing information, it has been determined that the Activities Directors will be inserviced regarding the input of each activity into the Vision charting system to ensure accurate charting of individual participation in Activities.  Several facilities did not understand that the ARTS/iN2L information did not transfer to the Vision medical record automatically.

| Total number of patients participating in Restorative Nursing Program | 4/30/2018 | 05/31/18 | 06/30/18 |
| --- | --- | --- | --- |
| Applingwood | 5 | 6 | 6 |
| Bright Glade | 14 | 12 | 10 |
| Covington Care | 6 | 6 | 6 |
| Dyersburg | 11 | 15 | 16 |
| Harbor View | 8 | 11 | 9 |
| Humboldt | 5 | 8 | 8 |
| McKenzie | 31 | 25 | 29 |
| Paris | 10 | 10 | 10 |
| Union City | 19 | 18 | 17 |
| VanAyer | 15 | 16 | 16 |
| Totals | 124 | 127 | 127 |

Total number of patients that participated in restorative improved overall since baseline was obtained.  Three facilities decreased the number of patients receiving the Restorative Nursing program.  Bright Glade, McKenzie, and Union City will be reviewed to ensure all qualifying patients are receiving restorative therapy and we will continue to monitor progress.  Seven of the ten facilities increased the number of patients receiving restorative care.

| IN2L Usage Report (in Minutes) |  |  |  |
| --- | --- | --- | --- |
|  | Apr2018 | May2018 | Jun2018 |
| Applingwood | 0.27 | 331.10 | 385.60 |
| Bright Glade | 0.07 | 362.04 | 633.91 |
| Covington Care | 0.07 | 236.49 | 239.33 |
| Dyersburg | 132.42 | 489.17 | 252.65 |
| Harbor View | 0.05 | 275.79 | 519.59 |
| Humboldt | 17.54 | 583.19 | 562.49 |
| McKenzie | 0.14 | 281.55 | 398.31 |
| Paris | 110.38 | 529.80 | 517.79 |
| Union City | 59.63 | 659.64 | 717.10 |
| VanAyer | 25.56 | 197.53 | 80.03 |
| Totals | 346.13 | 3946.30 | 4306.80 |

iN2L usage has increased in 6 out of 10 facilities every month.  Dyersburg, Humboldt, Paris, and VanAyer will be retrained on the system during the next quarter to ensure knowledge of the system.

| Alert patients complete the Questionnaire. Patients' scores are averaged per facility. |  |  | 6/30/2018 |
| --- | --- | --- | --- |
| Applingwood |  |  | 21.3 |
| Bright Glade |  |  | 21 |
| Covington Care |  |  | 22.6 |
| Dyersburg |  |  | 22.75 |
| Harbor View |  |  | 19.95 |
| Humboldt |  |  | 22.75 |
| McKenzie |  |  | 22 |
| Paris |  |  | 20.35 |
| Union City |  |  | 21.3 |
| VanAyer |  |  | 22.64 |
| Total Average |  |  | 21.66 |

The maximum score that can be achieved on the Patient Questionnaires is a 25 (Attachment #2).  The patients are adapting to the technology very quickly.  They feel they have been given training and it is easy to use.  Family involvement is the area of opportunity that we are focusing on the next quarter.

Groups making significant contributions:

iN2L made a significant contribution with the success of the program through on-site training and follow-up.  They are also monitoring usage minutes of the system and reporting to the facilities monthly.

Partnerships have developed in all facilities with the family members of the residents.  Through the process of creating My Page buttons and discussing the digital biographies that will be completed in the second quarter, the residents and families are more engaged with the staff.

An unexpected partner in one of the facilities is the local high school softball team.  The coach inquired about a special project to promote community service and reached out to a facility when they read the article in the local paper.  Upon resident\family approval, they have volunteered to work with our residents to complete the digital biographies.  This intergenerational volunteer program will be piloted in the Union City facility and attempt to replicate if proven successful.

Evidence of Effectiveness:

- 4 of the 10 facilities produced positive results in maintaining or improving patients’ self-performance of Activities of Daily Living.

- 7 of the 10 facilities increased the number of patients receiving restorative care.

- 6 out of 10 facilities have increased iN2L usage every month.

- Patient questionnaire scores averaged 21.66 out of a possible 25 points for the first quarter.  Over-all this is a very high score for the initial quarter of a program.

Although we cannot quantify comments from stakeholders, the comments below give valuable insight on how the program is affecting their daily lives.

Comments from the Staff include:

Dyersburg -  “We love it! No problems. Every discipline uses it. They had a patient flying a plane this morning. In use as I am typing. It never sits unused.”

Bright Glade -  “YES!!! We use it all day long with multiple patients. We have gotten excellent feedback and all (residents and therapists) LOVE it!!! We are so happy to have it!!”

Applingwood -  “We love it! Our patients are really enjoying all of the new activities we can do during therapy. We use it with most of our patients for at least part of a session. It has definitely been an improvement to our sessions. “

Harbor View  -  “We love it. We are using with all most all of our patients. They are really loving the programs on the computer. It is very easy to use.  Some of our patients have never used a computer before now. So far it has been awesome....”

Covington Care -  “We have patients that are doing so much more with standing as well as tolerating longer treatment times prior to rest. We have also utilized it for stimulation with a patient that has had a serious stroke and has not been responding well...EX: 2 weeks ago this patient was playing a guitar in a Rock N Roll band and now can hardly open his eyes. We used the iN2L to stimulate him with Rock music, his response was still quiet, however he responded accurately to questions asked such as, who is playing this song ? His response to the Beatles song was "George". What kind of guitar does George play? his response "Gibson" etc..”

Family comments:

Dyersburg – “We love coming in the door and seeing the men playing Chess and Family Feud at night”

Union City –  A patient’s wife stated, “You started having happy hour and slot machines after I got better  and went home.  I’m coming back.”

Paris Health Care – “We set up the skype as soon as we heard about it, this is exciting.”

VanAyer – “We are thrilled that we can enjoy this with them.”

Bright Glade – “I never thought she would use a computer.”

Patient comments:

Paris Health Care – “We love the Bingo.”

Union City – “I have a love hate relationship with that flower memory game. That otter comes out and moves the flowers on me!”

McKenzie - Ms. Ruth Wade a resident of McKenzie Healthcare is pictured.  Ms. Wade enjoys playing the slot machines; this reminds her of traveling to Tunica MS and Las-Vegas, art, bubble pop, and playing the piano and drums.  Ms. Wade enjoyed traveling over the last several years with her family; she enjoys watching the travel videos and the live webcam.  Prior to being admitted to McKenzie, Ms. Wade was in the hospital for over two months in the bed not able to get up or feed herself.  As her picture indicates, the IN2L has helped improve her mental and physical function.

Ms. Wade reported, “I enjoy playing so much I don’t want to get off of it.”

VanAyer – “I love to do the music, it feels like I am playing a guitar.”

Covington Care – “While the other residents are being brought in the dining room on Sunday mornings, I turn it on the gospel music so we all can sing while we are waiting on the food. It is so nice.”

Dyersburg – “I love looking at where I use to live.”

Applingwood – Patient interview on television news broadcast:    https://www.localmemphis.com/news/local-news/local-health-alert-technology-is-changing-the-way-skilled-nursing-patients-think-about-therapy/1305981782

Results Communication:

A press release was sent the THCA.  THM will report the results to the Tennessee Health Care Association.  The American Health Care Association Convention in October of 2018 is hosting a seminar on the iN2L system and the Team Leader for the ARTS project will speak about the program.

A press release was finalized and released June 2018 to promote the program to the public and stakeholders (Attachment #1).  The McKenzie, Martin, and Union City local newspapers ran the story.  Also, as a result of the press release, a Memphis television station visited Applingwood for an interview that aired on two stations morning, noon and evening.     https://www.localmemphis.com/news/local-news/local-health-alert-technology-is-changing-the-way-skilled-nursing-patients-think-about-therapy/1305981782

Problems/Delays:

The first few months, several facilities experienced issues with the internet connections being slow to download.  The IT department addressed all issues and reports from June 2018 were improved.   Streaming is successful with few, if any, interruptions.

The data being obtained is being reviewed to ensure we are using the right data to capture information that helps us determine if the program meets the goals.   A committee is reviewing and will report recommendations by October 2018.   Committee felt two quarters of data should be obtained before an evaluation is complete.  Also, the Committee will discuss possible data collection to determine how many total patients are in the facilities vs. how many patients are using the system.  This could help determine if we are engaging all patients to participate.

During calls reviewing information, it has been determined that the Activities Directors will be in-serviced regarding the input of each activity into the Vision charting system to ensure accurate charting of individual participation in Activities.  Several facilities did not understand that the ARTS/iN2L information did not transfer to the Vision medical record automatically.

Funding Information Summary below.

Attachment #2

1 of 2

Media Contact:                                                                                                 Address:

Cherryl Carlson                                                                                                  512 Autumn Springs Rd, Suite A

P: 615.905.5421                                                                                                Franklin, TN 37067

ccarlson@thmgt.com

10 SKILLED NURSING COMMUNITIES IN WEST TENNESSEE LAUNCH PROGRAM FOR RESIDENTS THAT IS MEASURABLY IMPROVING QUALITY OF LIFE

Memphis, Tenn – June 26, 2018 –Tennessee Health Management (THM), which operates 29 skilled nursing communities, recently launched an interactive program for patients and residents that combines online activities with restorative therapies to improve their quality of life. Approximately 770 skilled nursing patients in 10 THM facilities in Memphis and Northwest Tennessee can participate in the Activities, Restorative and Therapy in Sync (ARTS) program.

“This program is changing lives right before our eyes and in just two months’ time,” said Heather Lansaw, regional director of operations. “The examples are rolling in from all 10 centers. One patient has doubled the time he can stand for therapy. Others are awaking in cognitive ways we did not expect. It’s very inspiring.”

The ARTS program, which was funded by a $493,550 grant from the Tennessee Department of Health, uses the It’s Never Too Late (iN2L) computer-based system to engage residents in fun and meaningful activities. The iN2L touch-based technologies encourage users, even those unfamiliar with computers, to “touch their way” through programs to connect with loved ones via Skype, create “My Story” digital biographies, do simulated physical activities, and play brain games.

“For years, activities, restorative care and rehabilitative therapies have been separate departments in a residential nursing facility,” added Lansaw. “The ARTS program helps break down those divisions by creating individualized experiences for each patient. Using the iN2L platform has helped our therapy teams offer more personalized support for patients across all daily activities.”

As a requirement of the grant program, Lansaw and her team will be measuring and reporting on the program’s results over the next 36 months, beginning from the launch date of April 1, 2018.

So far, THM therapists are enthusiastic about the results they are seeing, Lansaw explained. At Applingwood Healthcare Center in Cordova, Tenn., the staff has incorporated the program into most patients’ therapy sessions and reports that patients are enjoying the new online activities. At Covington Care Nursing and Rehabilitation Center in Covington, Tenn., the therapists have found that patients who use the system are more active and tolerate longer treatment times prior to rest.   “We are so thankful for this grant,” Lansaw said. “One resident who had been in the hospital for two months before coming to our center uses iN2L to watch travel videos and the live webcam. Now she is

Attachment #2

2 of 2

feeling hope about going home again. She also loves the casino games. This was a woman who could not walk or feed herself just two months ago. You cannot put a premium on that.”

In addition to Applingwood Healthcare Center and Covington Care, the eight other THM skilled nursing facilities in west Tennessee that have implemented the ARTS program include: Bright Glade Health and Rehabilitation Center and Harbor View Nursing and Rehabilitation Center in Memphis; Dyersburg Nursing and Rehabilitation; Humboldt Healthcare and Rehab Center; McKenzie Healthcare and Rehabilitation Center; Paris Health Care Nursing and Rehabilitation Center; Union City Nursing and Rehabilitation Center; and VanAyer Healthcare and Rehab Center located in Martin, Tenn.

About Tennessee Health Management, Inc. Tennessee Health Management, Inc. (THM) operates 29 skilled nursing and rehabilitation centers throughout the state of Tennessee and north Alabama. In addition, the company provides home health services in 24 counties, hospice services in 31 counties, and operates five acute care psychiatric facilities for older adults needing mental health care. For more information visit thmgt.com.

About iN2L Founded in 1999, iN2L is dedicated to making technology and the Internet accessible and enjoyable for older adults — regardless of physical or cognitive limitations. A proprietary combination of adaptive hardware, software and content delivers a person-centered experience that engages, empowers and inspires. The engagement tools developed for older adults are currently used in 2,000 communities across all 50 states, Canada, Australia and Northern Ireland. The company is located in Centennial, CO. For more information, visit www.iN2L.com.

Attachment #3

1 of 1