## Table of Contents
Project Schedule Templates
Table of Contents
Type of Request
How to Begin: | Airport Planning
Choose the corresponding Type of Funding Request. Most project requests are Development category. Airport Planning is Planning category. Development (Method 1) is a 3 grant approach where the initial Preliminary Design/NEPA grant is not federally eligible. Development (Method 2) is a 2 grant approach where the Preliminary Design/NEPA is completed by the Airport Sponsor beforehand to ensure full federal eligibily of both grants. This same approach is applied to Land/Easement projects. Review your approved TDOT programmed ACIP to find out more information. Please contact the TDOT Project Manager if you are unsure which schedule template to utilize. | Development (Method 1)
Development (Method 2)
Land-Easement (Method 1)
Land-Easement (Method 2)
Equipment
Miscellaneous
Note on F7: Adam Guy: ALPs/Master Plans
Note on F8: Adam Guy: 3 Grants for completion
Note on F9: Adam Guy: 2 Grants for completion
Note on F10: Adam Guy: 2 Grants for completion
Note on F11: Adam Guy: 1 Grant for completion
Note on F12: Adam Guy: 1 Grant for completion
Note on F13: Adam Guy: Project that does not fit the others, use this one
Click the corresponding Type of Request to get started!

## Airport Planning
Airport Planning
Project Timeline
| Task ID | Description | Anticipated Schedule
Airport Layout Plan (Grant 1) | 1 | Scoping Meeting
| 2 | Submit ALP Project Funding Request
| 3 | TDOT Aeronautics Project Staff Review (PSR)
| 4 | Grant Execution
| 5 | Work Authorization Execution
| 6 | Kick-Off Meeting
| 7 | AGIS Survey Completed
| 8 | Aviation Forecast Submittal to TDOT
| 9 | TDOT Approval of Aviation Forecast
| 10 | 30% ALP Submittal
| 11 | 30% ALP Review Meeting
| 12 | RSAI and RSAD Submitted
| 13 | Modification of Standards (if applicable)
| 14 | 60% ALP Submittal
| 15 | 60% ALP Review Meeting
| 16 | 90% ALP Submittal
| 17 | 90% ALP Review Meeting
| 18 | 100% ALP Submittal
| 19 | Submission of ALP Documents into OE/AAA
| 20 | OE/AAA Complete
| 21 | Airport Sponsor Electronic ALP Signature
| 22 | TDOT Conditional Approval Letter and Electronic Signatures
| 23 | Final Deliverables Submitted to TDOT
| 24 | Final Invoices Submitted
| 25 | Grant End Date
| 26 | Project Closeout Letter Submitted to TDOT
| 27 | Project Closed
Created by:
Date:

## Development (Method 1)
Development (Method 1)
Project Timeline
| Task ID | Description | Anticipated Schedule
Preliminary Study/NEPA (Grant 1) | 1 | Scoping Meeting
| 2 | Environmental Determination Checklist for NEPA (EDC)
| 3 | Submit Planning Development Project Funding Request
| 4 | TDOT Aeronautics Project Staff Review (PSR)
| 5 | Grant Execution (via Adobe Sign)
| 6 | Professional Services Work Authorization Execution
| 7 | Preliminary Study Kickoff Meeting
| 8 | Survey Completion
| 9 | Geotechnical Completion
| 10 | Engineer's Opinion of Probable Construction Cost (EOPCC)
| 11 | 30% Preliminary Study Review Meeting
| 12 | Complete National Environmental Policy Act (NEPA) Requirements
| 13 | Grant Closeout
Final Design/Bidding (Grant 2) | 14 | Submit Design Project Funding Request
| 15 | TDOT Aeronautics Project Staff Review (PSR)
| 16 | Tennessee Aeronautics Commission (TAC, As Applicable)
| 17 | Grant Execution (via Adobe Sign)
| 18 | Professional Services Work Authorization Execution
| 19 | 60% Design Review Meeting
| 20 | 90% Design Review Meeting
| 21 | Issued for Bid (IFB) Plans and Specifications TDOT Aeronautics Review
| 22 | Advertise for Bids
| 23 | Pre-Bid Conference
| 24 | Engineer's Final EOPCC
| 25 | Bid Opening
| 26 | Bid Tabulation
| 27 | Engineer's Letter of Recommendation to Airport Sponsor
| 28 | Grant Closeout
Construction (Grant 3) | 29 | Submit Construction Project Funding Request
| 30 | TDOT Aeronautics Project Staff Review (PSR)
| 31 | Grant Execution (via Adobe Sign)
| 32 | Construction Contract Award & Execution
| 33 | Construction/Engineering Inspection (CEI) Professional Services Work Authorization Execution
| 34 | Issued for Construction (IFC) Plans and Specifications
| 35 | Pre-Construction Conference
| 36 | Material/Shop Submittals Completion
| 37 | Contractor's Notice to Proceed (NTP)
| 38 | Construction Substantial Completion
| 39 | Project Closeout Deliverables (i.e. Change Orders, DBE Final Certification, Release of Liens, Record Drawings…)
| 40 | Grant Closeout
Created by:
Date:

## Development (Method 2)
Development (Method 2)
Project Timeline
| Task ID | Description | Anticipated Schedule
Preliminary Study/NEPA (Cashflow) | 1 | Scoping Meeting
| 2 | Environmental Determination Checklist for NEPA (EDC)
| 3 | Professional Services Work Authorization Execution
| 4 | Preliminary Study Kickoff Meeting
| 5 | Survey Completion
| 6 | Geotechnical Completion
| 7 | Engineer's Opinion of Probable Construction Cost (EOPCC)
| 8 | 30% Preliminary Study Review Meeting
| 9 | Complete National Environmental Policy Act (NEPA) Requirements
Final Design/Bidding (Grant 1) | 10 | Submit Design Project Funding Request
| 11 | TDOT Aeronautics Project Staff Review (PSR)
| 12 | Tennessee Aeronautics Commission (TAC, As Applicable)
| 13 | Grant Execution (via Adobe Sign)
| 14 | Professional Services Work Authorization Execution
| 15 | 60% Design Review Meeting
| 16 | 90% Design Review Meeting
| 17 | Issued for Bid (IFB) Plans and Specifications TDOT Aeronautics Review
| 18 | Advertise for Bids
| 19 | Pre-Bid Conference
| 20 | Engineer's Final EOPCC
| 21 | Bid Opening
| 22 | Bid Tabulation
| 23 | Engineer's Letter of Recommendation to Airport Sponsor
| 24 | Grant Closeout
Construction (Grant 2) | 25 | Submit Construction Project Funding Request
| 26 | TDOT Aeronautics Project Staff Review (PSR)
| 27 | Grant Execution (via Adobe Sign)
| 28 | Construction Contract Award & Execution
| 29 | Construction/Engineering Inspection (CEI) Professional Services Work Authorization Execution
| 30 | Issued for Construction (IFC) Plans and Specifications
| 31 | Pre-Construction Conference
| 32 | Material/Shop Submittals Completion
| 33 | Contractor's Notice to Proceed (NTP)
| 34 | Construction Substantial Completion
| 35 | Project Closeout Deliverables (i.e. Change Orders, DBE Final Certification, Release of Liens, Record Drawings…)
| 36 | Grant Closeout
Created by:
Date:

## Land-Easement (Method 1)
Land/Easement (Method 1)
Project Timeline
| Task ID | Description | Anticipated Schedule
Land/Easement Study Phase (Grant 1) | 1 | Scoping Meeting
| 2 | Environmental Determination Checklist for NEPA (EDC)
| 3 | Submit Land/Easement Study Project Funding Request
| 4 | TDOT Aeronautics Project Staff Review (PSR)
| 5 | Tennessee Aeronautics Commission (TAC, As Applicable)
| 6 | Grant Execution (via Adobe Sign)
| 7 | Professional Services Work Authorization Execution (As Applicable)
| 8 | Notice of Proposed Acquisition (Obtain Right of Entry)
| 9 | Property Boundary Survey Complete
| 10 | Phase I ESA Complete
| 11 | Complete National Environmental Policy Act (NEPA) Requirements
| 12 | Title Search & Ownership and Encumbrances Verified
| 13 | Appraisal(s) Complete
| 14 | Appraisal Review(s) Complete
| 15 | Written Offer(s) Sent
| 16 | Written Purchase Agreement(s) in place
Land/Easement Acquisition Phase (Grant 2) | 17 | Submit Land/Easement Acquisition Project Funding Request
| 18 | TDOT Aeronautics Project Staff Review (PSR)
| 19 | Grant Execution (via Adobe Sign)
| 20 | Professional Services Work Authorization Execution (if applicable)
| 21 | Relocation(s) Complete (if applicable)
| 22 | New Warranty Deed and/or Easement Documentation Complete
| 23 | Close on Land and/or Easement (HUD-1 Settlement Statement)
| 24 | Update Exhibit A
| 25 | Grant Closeout
Created by:
Date:

## Land-Easement (Method 2)
Land/Easement (Method 2, Previous Acquisition(s) Reimbursement)
Project Timeline
| Task ID | Description | Anticipated Schedule
Land/Easement Acquisition Phase (Grant 1) | 1 | Close on Land and/or Easement (HUD-1 Settlement Statement)
| 2 | Compile and submit necessary Land and/or Easement Project Files to TAD
| 3 | Submit Land/Easement Acquisition Project Funding Request
| 4 | TDOT Aeronautics Project Staff Review (PSR)
| 5 | Tennessee Aeronautics Commission (TAC, As Applicable)
| 6 | Grant Execution (via Adobe Sign)
| 7 | Update Exhibit A
| 8 | Grant Closeout
Created by:
Date:

## Equipment
Equipment (Grounds Maintenance)
Project Timeline
| Task ID | Description | Anticipated Schedule
Grounds Maintenance Equipment (Grant 1) | 1 | Salvage existing Grounds Maintenance Equipment that is past useful life (As Applicable)
| 2 | Quote Acquisition (Two or More)
| 3 | Submit Grounds Maintenance Equipment Funding Request
| 4 | TDOT Aeronautics Project Staff Review (PSR)
| 5 | Grant Execution (via Adobe Sign)
| 6 | Submit Grounds Maintenance Equipment Order
| 7 | Grounds Maintenance Equipment Acquired
| 8 | Submit Invoice(s) in Grant Management System for TDOT Aeronautics Reimbursement
| 9 | Grant Closeout
Created by:
Date:

## Miscellaneous
Miscellaneous (Use this one if other templates don't fit)
Project Timeline
Task ID | Description | Anticipated Schedule
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
Created by:
Date:

## Option 1 - Per Project Type
| Airport Planning |  |  |  | Development (Method 1) |  |  |  | Development (Method 2) |  |  |  | Land/Easement (Method 1) |  |  |  | Land/Easement (Method 2, Previous Acquisition(s) Reimbursement) |  |  |  | Equipment (Grounds Maintenance) |  |  | Miscellaneous
| Project Timeline |  |  |  | Project Timeline |  |  |  | Project Timeline |  |  |  | Project Timeline |  |  |  | Project Timeline |  |  |  | Project Timeline |  |  | Project Timeline
| Task ID | Description | Anticipated Schedule |  | Task ID | Description | Anticipated Schedule |  | Task ID | Description | Anticipated Schedule |  | Task ID | Description | Anticipated Schedule |  | Task ID | Description | Anticipated Schedule |  | Task ID | Description | Anticipated Schedule | Task ID | Description | Anticipated Schedule
Airport Layout Plan (Grant 1) | 1 | Scoping Meeting |  | Preliminary Study/NEPA | 1 | Scoping Meeting |  | Preliminary Study/NEPA | 1 | Scoping Meeting |  | Land/Easement Study Phase (Grant 1) | 1 | Scoping Meeting |  | Land/Easement Acquisition Phase (Grant 1) | 1 | Close on Land and/or Easement (HUD-1 Settlement Statement) |  | Grounds Maintenance Equipment (Grant 1) | 1 | Salvage existing Grounds Maintenance Equipment that is past useful life (As Applicable) |  | 1
| 2 | Submit ALP Project Funding Request |  |  | 2 | Environmental Determination Checklist for NEPA (EDC) |  |  | 2 | Environmental Determination Checklist for NEPA (EDC) |  |  | 2 | Environmental Determination Checklist for NEPA (EDC) |  |  | 2 | Compile and submit necessary Land and/or Easement Project Files to TAD |  |  | 2 | Quote Acquisition (Two or More) |  | 2
| 3 | TDOT Aeronautics Project Staff Review (PSR) |  |  | 3 | Submit Planning Development Project Funding Request |  |  | 3 | Professional Services Work Authorization Execution |  |  | 3 | Submit Land/Easement Study Project Funding Request |  |  | 3 | Submit Land/Easement Acquisition Project Funding Request |  |  | 3 | Submit Grounds Maintenance Equipment Funding Request |  | 3
| 4 | Grant Execution |  |  | 4 | TDOT Aeronautics Project Staff Review (PSR) |  |  | 4 | Preliminary Study Kickoff Meeting |  |  | 4 | TDOT Aeronautics Project Staff Review (PSR) |  |  | 4 | TDOT Aeronautics Project Staff Review (PSR) |  |  | 4 | TDOT Aeronautics Project Staff Review (PSR) |  | 4
| 5 | Work Authorization Execution |  |  | 5 | Grant Execution (via Adobe Sign) |  |  | 5 | Survey Completion |  |  | 5 | Tennessee Aeronautics Commission (TAC, As Applicable) |  |  | 5 | Tennessee Aeronautics Commission (TAC, As Applicable) |  |  | 5 | Grant Execution (via Adobe Sign) |  | 5
| 6 | Kick-Off Meeting |  |  | 6 | Professional Services Work Authorization Execution |  |  | 6 | Geotechnical Completion |  |  | 6 | Grant Execution (via Adobe Sign) |  |  | 6 | Grant Execution (via Adobe Sign) |  |  | 6 | Submit Grounds Maintenance Equipment Order |  | 6
| 7 | AGIS Survey Completed |  |  | 7 | Preliminary Study Kickoff Meeting |  |  | 7 | Engineer's Opinion of Probable Construction Cost (EOPCC) |  |  | 7 | Professional Services Work Authorization Execution (As Applicable) |  |  | 7 | Update Exhibit A |  |  | 7 | Grounds Maintenance Equipment Acquired |  | 7
| 8 | Aviation Forecast Submittal to TDOT |  |  | 8 | Survey Completion |  |  | 8 | 30% Preliminary Study Review Meeting |  |  | 8 | Notice of Proposed Acquisition (Obtain Right of Entry) |  |  | 8 | Grant Closeout |  |  | 8 | Submit Invoice(s) in Grant Management System for TDOT Aeronautics Reimbursement |  | 8
| 9 | TDOT Approval of Aviation Forecast |  |  | 9 | Geotechnical Completion |  |  | 9 | Complete National Environmental Policy Act (NEPA) Requirements |  |  | 9 | Property Boundary Survey Complete | [6 empty] | 9 | Grant Closeout |  | 9
| 10 | 30% ALP Submittal |  |  | 10 | Engineer's Opinion of Probable Construction Cost (EOPCC) |  | Final Design/Bidding | 10 | Submit Design Project Funding Request |  |  | 10 | Phase I ESA Complete | [9 empty] | 10
| 11 | 30% ALP Review Meeting |  |  | 11 | 30% Preliminary Study Review Meeting |  |  | 11 | TDOT Aeronautics Project Staff Review (PSR) |  |  | 11 | Complete National Environmental Policy Act (NEPA) Requirements | [9 empty] | 11
| 12 | RSAI and RSAD Submitted |  |  | 12 | Complete National Environmental Policy Act (NEPA) Requirements |  |  | 12 | Tennessee Aeronautics Commission (TAC, As Applicable) |  |  | 12 | Title Search & Ownership and Encumbrances Verified | [9 empty] | 12
| 13 | Modification of Standards (if applicable) |  |  | 13 | Grant Closeout |  |  | 13 | Grant Execution (via Adobe Sign) |  |  | 13 | Appraisal(s) Complete | [9 empty] | 13
| 14 | 60% ALP Submittal |  | Final Design/Bidding | 14 | Submit Design Project Funding Request |  |  | 14 | Professional Services Work Authorization Execution |  |  | 14 | Appraisal Review(s) Complete | [9 empty] | 14
| 15 | 60% ALP Review Meeting |  |  | 15 | TDOT Aeronautics Project Staff Review (PSR) |  |  | 15 | 60% Design Review Meeting |  |  | 15 | Written Offer(s) Sent | [9 empty] | 15
| 16 | 90% ALP Submittal |  |  | 16 | Tennessee Aeronautics Commission (TAC, As Applicable) |  |  | 16 | 90% Design Review Meeting |  |  | 16 | Written Purchase Agreement(s) in place | [9 empty] | 16
| 17 | 90% ALP Review Meeting |  |  | 17 | Grant Execution (via Adobe Sign) |  |  | 17 | Issued for Bid (IFB) Plans and Specifications TDOT Aeronautics Review |  | Land/Easement Acquisition Phase (Grant 2) | 17 | Submit Land/Easement Acquisition Project Funding Request | [9 empty] | 17
| 18 | 100% ALP Submittal |  |  | 18 | Professional Services Work Authorization Execution |  |  | 18 | Advertise for Bids |  |  | 18 | TDOT Aeronautics Project Staff Review (PSR) | [9 empty] | 18
| 19 | Submission of ALP Documents into OE/AAA |  |  | 19 | 60% Design Review Meeting |  |  | 19 | Pre-Bid Conference |  |  | 19 | Grant Execution (via Adobe Sign) | [9 empty] | 19
| 20 | OE/AAA Complete |  |  | 20 | 90% Design Review Meeting |  |  | 20 | Engineer's Final EOPCC |  |  | 20 | Professional Services Work Authorization Execution (if applicable) | [9 empty] | 20
| 21 | Airport Sponsor Electronic ALP Signature |  |  | 21 | Issued for Bid (IFB) Plans and Specifications TDOT Aeronautics Review |  |  | 21 | Bid Opening |  |  | 21 | Relocation(s) Complete (if applicable) | [9 empty] | 21
| 22 | TDOT Conditional Approval Letter and Electronic Signatures |  |  | 22 | Advertise for Bids |  |  | 22 | Bid Tabulation |  |  | 22 | New Warranty Deed and/or Easement Documentation Complete | [9 empty] | 22
| 23 | Final Deliverables Submitted to TDOT |  |  | 23 | Pre-Bid Conference |  |  | 23 | Engineer's Letter of Recommendation to Airport Sponsor |  |  | 23 | Close on Land and/or Easement (HUD-1 Settlement Statement) | [9 empty] | 23
| 24 | Final Invoices Submitted |  |  | 24 | Engineer's Final EOPCC |  |  | 24 | Grant Closeout |  |  | 24 | Update Exhibit A | [9 empty] | 24
| 25 | Grant End Date |  |  | 25 | Bid Opening |  | Construction | 25 | Submit Construction Project Funding Request |  |  | 25 | Grant Closeout | [9 empty] | 25
| 26 | Project Closeout Letter Submitted to TDOT |  |  | 26 | Bid Tabulation |  |  | 26 | TDOT Aeronautics Project Staff Review (PSR) | [13 empty] | 26
| 27 | Project Closed |  |  | 27 | Engineer's Letter of Recommendation to Airport Sponsor |  |  | 27 | Grant Execution (via Adobe Sign) | [13 empty] | 27
[5 empty] | 28 | Grant Closeout |  |  | 28 | Construction Contract Award & Execution | [13 empty] | 28
|  |  |  | Construction | 29 | Submit Construction Project Funding Request |  |  | 29 | Construction/Engineering Inspection (CEI) Professional Services Work Authorization Execution
[5 empty] | 30 | TDOT Aeronautics Project Staff Review (PSR) |  |  | 30 | Issued for Construction (IFC) Plans and Specifications
[5 empty] | 31 | Grant Execution (via Adobe Sign) |  |  | 31 | Pre-Construction Conference
[5 empty] | 32 | Construction Contract Award & Execution |  |  | 32 | Material/Shop Submittals Completion
[5 empty] | 33 | Construction/Engineering Inspection (CEI) Professional Services Work Authorization Execution |  |  | 33 | Contractor's Notice to Proceed (NTP)
[5 empty] | 34 | Issued for Construction (IFC) Plans and Specifications |  |  | 34 | Construction Substantial Completion
[5 empty] | 35 | Pre-Construction Conference |  |  | 35 | Project Closeout Deliverables (i.e. Change Orders, DBE Final Certification, Release of Liens, Record Drawings…)
[5 empty] | 36 | Material/Shop Submittals Completion |  |  | 36 | Grant Closeout
[5 empty] | 37 | Contractor's Notice to Proceed (NTP)
[5 empty] | 38 | Construction Substantial Completion
[5 empty] | 39 | Project Closeout Deliverables (i.e. Change Orders, DBE Final Certification, Release of Liens, Record Drawings…)
[5 empty] | 40 | Grant Closeout

## Option 2 - Per Project Phase
Airport Planning - Request |  |  | Preliminary Study/NEPA - Request |  |  | Final Design/Bidding Services - Request |  |  | Full Design/Bidding Services - Request |  |  | Construction - Request |  |  | Land Easement/Acquisition - Request |  |  | Equipment - Request |  |  | Miscellaneous - Request
Project Timeline |  |  | Project Timeline |  |  | Project Timeline |  |  | Project Timeline |  |  | Project Timeline |  |  | Project Timeline |  |  | Project Timeline |  |  | Project Timeline
Task ID | Description | Anticipated Schedule | Task ID | Description | Anticipated Schedule | Task ID | Description | Anticipated Schedule | Task ID | Description | Anticipated Schedule | Task ID | Description | Anticipated Schedule | Task ID | Description | Anticipated Schedule | Task ID | Description | Anticipated Schedule | Task ID | Description | Anticipated Schedule
1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1
2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2
3 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3
4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4
5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5
6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6
7 |  |  | 7 |  |  | 7 |  |  | 7 |  |  | 7 |  |  | 7 |  |  | 7 |  |  | 7
8 |  |  | 8 |  |  | 8 |  |  | 8 |  |  | 8 |  |  | 8 |  |  | 8 |  |  | 8
9 |  |  | 9 |  |  | 9 |  |  | 9 |  |  | 9 |  |  | 9 |  |  | 9 |  |  | 9
10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10
11 |  |  | 11 |  |  | 11 |  |  | 11 |  |  | 11 |  |  | 11 |  |  | 11 |  |  | 11
12 |  |  | 12 |  |  | 12 |  |  | 12 |  |  | 12 |  |  | 12 |  |  | 12 |  |  | 12
13 |  |  | 13 |  |  | 13 |  |  | 13 |  |  | 13 |  |  | 13 |  |  | 13 |  |  | 13
14 |  |  | 14 |  |  | 14 |  |  | 14 |  |  | 14 |  |  | 14 |  |  | 14 |  |  | 14
15 |  |  | 15 |  |  | 15 |  |  | 15 |  |  | 15 |  |  | 15 |  |  | 15 |  |  | 15
16 |  |  | 16 |  |  | 16 |  |  | 16 |  |  | 16 |  |  | 16 |  |  | 16 |  |  | 16
17 |  |  | 17 |  |  | 17 |  |  | 17 |  |  | 17 |  |  | 17 |  |  | 17 |  |  | 17
18 |  |  | 18 |  |  | 18 |  |  | 18 |  |  | 18 |  |  | 18 |  |  | 18 |  |  | 18
19 |  |  | 19 |  |  | 19 |  |  | 19 |  |  | 19 |  |  | 19 |  |  | 19 |  |  | 19
20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20
21 |  |  | 21 |  |  | 21 |  |  | 21 |  |  | 21 |  |  | 21 |  |  | 21 |  |  | 21
22 |  |  | 22 |  |  | 22 |  |  | 22 |  |  | 22 |  |  | 22 |  |  | 22 |  |  | 22
23 |  |  | 23 |  |  | 23 |  |  | 23 |  |  | 23 |  |  | 23 |  |  | 23 |  |  | 23
24 |  |  | 24 |  |  | 24 |  |  | 24 |  |  | 24 |  |  | 24 |  |  | 24 |  |  | 24
25 |  |  | 25 |  |  | 25 |  |  | 25 |  |  | 25 |  |  | 25 |  |  | 25 |  |  | 25
26 |  |  | 26 |  |  | 26 |  |  | 26 |  |  | 26 |  |  | 26 |  |  | 26 |  |  | 26
27 |  |  | 27 |  |  | 27 |  |  | 27 |  |  | 27 |  |  | 27 |  |  | 27 |  |  | 27
28 |  |  | 28 |  |  | 28 |  |  | 28 |  |  | 28 |  |  | 28 |  |  | 28 |  |  | 28