{"text_format":"1","workbook":"xlsx","n_sheets":41,"sheets":["Visual Guidance","Tool","Haul Road","Typical Comparison","Finalize Items","Summary","Cost Estimate","Median","ROW_Old","AUP Library","Sheet1","Sign Quantities","Sign Schedule","Updated Quanities","Average Unit Price","Prelim Plans Est (STID Only)","IT CLASS","ROW Statistics","Housing Index","Update Notes","Projects","Guardrail","CLS","SUP 2022","Inflated Cost","Retaining Wall Data","AUP Data","PE","Clr&Grb","Estimate Process","ROW_New","Roadway","Drainage","Terrain","Bridges","Utilities","Traffic Control","Corridor_Proj_ROW","Bridges_Projects_ROW","ROW_Zillow","Const Index"],"not_rendered":{"charts":7,"images":132,"macros":1,"external_links":0,"defined_names":39,"comments":3,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Visual Guidance","index":0,"n_rows":5,"n_cols":2,"rows_kept":5,"cut":false,"hidden":false,"merged":[[0,0,0,1]]}
["DEFAULT SLOPE RATES"]
["FLAT:","6H:1V"]
["ROLLING:","4H:1V"]
["MOUNTAINOUS:","3H:1V"]
["HEAVY MOUNTAINOUS:","2H:1V"]

{"sheet":"Tool","index":1,"n_rows":242,"n_cols":46,"rows_kept":242,"cut":false,"hidden":false,"merged":[[238,3,238,7],[239,3,239,7],[240,3,240,7],[241,3,241,7],[205,11,206,16],[236,3,236,7],[237,3,237,7],[225,6,225,7],[230,6,230,7],[231,6,231,7],[228,2,228,3],[231,2,231,3],[227,2,227,4],[227,6,227,9],[235,2,235,7],[233,6,233,7],[220,2,220,9],[225,8,225,9],[226,8,226,9],[229,2,230,3],[225,2,226,4],[223,6,223,9],[226,6,226,7],[224,6,224,9],[208,42,209,45],[210,42,210,45],[154,2,154,5],[60,10,62,10],[119,2,119,3],[60,13,62,13],[95,2,95,8],[60,7,61,8],[60,2,60,5],[119,12,119,15],[119,8,119,10],[119,5,119,6],[94,2,94,9],[126,1,127,16],[60,9,61,9],[120,5,120,6],[208,2,208,3],[208,5,208,6],[178,2,178,6],[201,2,201,3],[60,15,62,15],[208,12,208,15],[154,7,154,9],[153,2,153,9],[21,1,21,16],[51,9,52,9],[50,6,50,9],[48,1,48,16],[53,9,54,9],[38,11,38,14],[42,3,42,5],[41,3,41,5],[39,12,39,14],[43,3,43,5],[51,8,52,8],[53,8,54,8],[35,2,35,4],[44,3,44,5],[45,3,45,5],[23,2,23,5],[23,7,23,9],[23,11,23,14],[25,11,25,14],[25,2,25,3],[24,12,24,14],[24,2,24,3],[26,2,26,3],[27,2,27,3],[56,1,56,16],[28,2,28,3],[29,2,29,3],[30,2,30,3],[31,2,31,3],[130,2,130,4],[120,2,120,3],[34,2,34,4],[37,2,37,4],[36,2,36,4],[59,2,59,9],[129,2,129,5],[58,2,58,15],[60,14,62,14],[59,10,59,12],[61,2,61,5],[59,13,59,15],[40,2,40,5],[33,2,33,5],[229,4,230,4],[232,2,232,3],[224,2,224,4],[223,2,223,4],[220,12,220,15],[221,12,221,15],[222,12,222,14],[223,12,223,14],[224,12,224,14],[225,12,225,14],[230,12,230,15],[231,12,231,13],[231,14,231,15],[232,12,232,13],[232,14,232,15],[201,4,203,6],[233,12,233,13],[233,14,233,15],[234,12,234,13],[234,14,234,15],[153,11,153,14],[178,8,178,10],[177,2,177,10],[209,12,209,13],[211,12,211,13],[212,12,212,13],[213,12,213,13],[214,12,214,13],[215,12,215,13],[216,12,216,13],[210,12,210,15],[209,14,209,15],[232,6,232,7],[219,2,219,9],[205,1,206,10],[228,6,228,7],[229,6,229,7],[209,2,209,3],[212,2,212,3]]}
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,null,null,null,null,null,null,null,null,0,null,null,null,null,2,0.05]
[null,null,null,null,null,null,null,null,null,null,null,null,0.1,null,null,null,null,3,0.1]
[null,null,null,null,null,null,null,null,null,null,null,null,0.2,null,null,null,null,4,0.15]
[null,null,null,null,null,null,null,null,null,null,null,null,0.3,null,null,null,null,5,0.2]
[null,null,null,null,null,null,null,null,null,null,null,null,0.4,null,null,null,null,6,0.25,null,"None","Tier 1 - Very Low Impacts",null,"Detour/New Location"]
[null,"Rural/Ditch","Both Sides","Yes","Flat","8\"","Local","Box Bridge","Land Only","Depressed Grass (RD11-TS-3A&5)",1,"None",0.5,"6H:1V",5,2,1,7,0.3,1,"Low","Tier 2 - Low Impacts",null,"ABC/CMGC"]
[null,"Urban/C&G","One Side","No","Rolling","9\"","SIA","Concrete I-Beam & Bulb-T","Residential","Raised Median (RD11-TS-6)",2,"One Side",0.6,"5H:1V",6,">=3",{"$f":"Q7+1","v":2},8,0.35,2,"Moderate","Tier 3 - Moderate Impacts",null,"Stage Construction"]
[null,null,null,null,"Mountainous","10\"","Collector","Concrete Box Beam","Commercial Industrial","Barrier Wall (RD11-TS-5B)",3,"Both Sides",0.7,"4H:1V",7,null,3,9,0.4,3,"High","Tier 4 - High Impacts"]
[null,null,null,null,"Heavy Mountainous","11\"","Arterial","Steel Beam",null,null,4,null,0.8,"3H:1V",8,null,4,10,0.45,4,null,"Tier 5 - Very High Impacts",null,"Bridge Construction"]
[null,null,null,null,null,null,"Freeway",null,null,null,5,null,0.9,"2H:1V",9,null,5,11,0.5,"Statewide",null,null,null,"Grade and Drain"]
[null,null,null,null,null,null,"Concrete",null,null,null,6,null,1,"1H:1V",10,null,6,12,0.55000000000000004,null,null,null,null,"Safety"]
[null,null,null,null,null,null,null,null,null,null,7,null,null,null,11,null,7,13,0.6,null,null,null,null,"Resurfacing"]
[null,null,null,null,null,null,null,null,null,null,8,null,null,null,12,null,8,14,0.65]
[null,null,null,null,null,null,null,null,null,null,9,null,null,null,13,null,9,15,0.7,null,null,null,null,"Average"]
[null,null,null,null,null,null,null,null,null,null,10,null,null,null,14,null,10,16,0.75,null,null,null,null,"High"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,17,0.8]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,18,0.85]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,19,0.9]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,20,0.95]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,"COST ESTIMATE TOOL - 2024"]
[]
[null,null,"Project Cost Summary",null,null,null,null,"Construction Estimate",null,null,null,"Pavement Calculator"]
[null,null,"Description",null,"Estimate","Contingency",null,"Category","Cost","Contribution",null,"Area (SQFT):"]
[null,null,"Construction:",null,{"$f":"'Cost Estimate'!J38","v":0},0.3,null,"Pavement Removal",{"$f":"'Cost Estimate'!J15","v":0},{"$f":"'Cost Estimate'!L15","v":0},null,"TRAVELED-WAY"]
[null,null,"Right-of-Way:",null,{"$f":"'Cost Estimate'!J50","v":0},null,null,"Asphalt Paving",{"$f":"'Cost Estimate'!J16","v":0},{"$f":"'Cost Estimate'!L16","v":0},null,"415-01.02","COLD PLANE","SqYd =",{"$f":"M25/9","v":0},"<- Resurfacing"]
[null,null,"Utility Relocation:",null,{"$f":"'Cost Estimate'!J51","v":0},null,null,"Concrete Pavement",{"$f":"'Cost Estimate'!J17","v":0},{"$f":"'Cost Estimate'!L17","v":0},null,"Item #","Description","Thickness (in)","Tons"]
[null,null,"Interchanges & Roundabouts:",null,{"$f":"'Cost Estimate'!J46+'Cost Estimate'!J47","v":0},null,null,"Drainage",{"$f":"'Cost Estimate'!J18","v":0},{"$f":"'Cost Estimate'!L18","v":0},null,"411-03.10","\"D\" mix",2,{"$f":"Roadway!AK55","v":0},"<- Resurfacing"]
[null,null,"Preliminary Engineering:",null,{"$f":"'Cost Estimate'!J54","v":0},null,null,"Appurtenances",{"$f":"'Cost Estimate'!J19","v":0},{"$f":"'Cost Estimate'!L19","v":0},null,"403-01","1st Layer - Tack","N/A",{"$f":"Roadway!AK56","v":0},"<- Resurfacing"]
[null,null,"Construction Engineering:",null,{"$f":"'Cost Estimate'!J37","v":0},0.15,null,"Structures",{"$f":"'Cost Estimate'!J20","v":0},{"$f":"'Cost Estimate'!L20","v":0},null,"307-02.08","\"BM-2\" mix",2,{"$f":"Roadway!AK57","v":0}]
[null,null,"Total Estimated Project Cost:",null,{"$f":"'Cost Estimate'!J57","v":0},null,null,"Fencing",{"$f":"'Cost Estimate'!J21","v":0},{"$f":"'Cost Estimate'!L21","v":0},null,"403-01","2nd Layer - Tack","N/A",{"$f":"Roadway!AK58","v":0}]
[null,null,null,null,null,null,null,"Signalization ",{"$f":"'Cost Estimate'!J22","v":0},{"$f":"'Cost Estimate'!L22","v":0},null,"307-02.01","\"A\" mix",3.5,{"$f":"Roadway!AK59","v":0}]
[null,null,"Additional Specifications",null,null,null,null,"RR X or Separation",{"$f":"'Cost Estimate'!J23","v":0},{"$f":"'Cost Estimate'!L23","v":0},null,"403-01","3rd Layer - Tack","N/A",{"$f":"Roadway!AK60","v":0}]
[null,null,"Graded Solid Rock:",null,null,"Low",null,"Earthwork",{"$f":"'Cost Estimate'!J24","v":0},{"$f":"'Cost Estimate'!L24","v":0},null,"307-02.21","GR \"A-S\" Mix",3,{"$f":"Roadway!AK61","v":0}]
[null,null,"Number of Traffic Signals:",null,null,null,null,"Clear & Grub",{"$f":"'Cost Estimate'!J25","v":0},{"$f":"'Cost Estimate'!L25","v":0},null,"402-01","Prime Coat","N/A",{"$f":"Roadway!AK63","v":0}]
[null,null,"Length of ITS Installation:",null,null,null,null,"Seeding & Sodding",{"$f":"'Cost Estimate'!J26","v":0},{"$f":"'Cost Estimate'!L26","v":0},null,"402-02","Agg. Cover","N/A",{"$f":"Roadway!AK64","v":0}]
[null,null,"Include Tool Generated Guardrail Quantities?",null,null,"No",null,"Rip-Rap or Slope Prot.",{"$f":"'Cost Estimate'!J27","v":0},{"$f":"'Cost Estimate'!L27","v":0},null,"303-01","Base Stone",4,{"$f":"Roadway!AK65","v":0}]
[null,null,null,null,null,null,null,"Guardrail ",{"$f":"'Cost Estimate'!J28","v":0},{"$f":"'Cost Estimate'!L28","v":0},null,"SHOULDERS"]
[null,null,null,null,null,null,null,"Signing ",{"$f":"'Cost Estimate'!J29","v":0},{"$f":"'Cost Estimate'!L29","v":0},null,"Area (SQFT):"]
[null,null,"Notifications",null,null,null,null,"Pavement Markings ",{"$f":"'Cost Estimate'!J30","v":0},{"$f":"'Cost Estimate'!L30","v":0},null,"Item #","Description","Thickness","Tons"]
[null,null,"Roadway:",{"$f":"IF(OR('Cost Estimate'!C5='Cost Estimate'!D116,'Cost Estimate'!C5='Cost Estimate'!D117),\"No Errors\",IF(OR(K52=\"Enter Begin L.M.\",K54=\"Enter End L.M.\"),\"Location Info Missing\",IF(D64<J52,\"Beginning Segment Doesn't Match Project Begin\",IF(AND(J52=\"\",J54=\"\"),\"No Errors\",IF(SUM(T64:T93)>0,\"Data Missing, See Roadway Table\",IF(SUM(E64:E93)=0,\"Enter Roadway Information\",IF(MAX(E64:E93)=J54,\"No Errors\",\"End Segment Does NOT Equal Project End (See Cell H55)\")))))))","v":"Location Info Missing"},null,null,null,"Maint. of Traffic",{"$f":"'Cost Estimate'!J31","v":0},{"$f":"'Cost Estimate'!L31","v":0},null,"411-01","\"E\" mix",1.5,{"$f":"Roadway!AK69","v":0}]
[null,null,"Median:",{"$f":"IF(SUM(S98:S117)>(J54-J52),\"Median Length is Greater than the Project Limits\",\"No Errors\")","v":"No Errors"},null,null,null,"Mobilization (5%)",{"$f":"'Cost Estimate'!J34","v":0},null,null,"403-01","Tack","N/A",{"$f":"Roadway!AK70","v":0}]
[null,null,"Right-of-Way:",{"$f":"IF(H53=\"\",\"Enter County, If using Tool for ROW Estimate\",\"No Errors\")","v":"Enter County, If using Tool for ROW Estimate"},null,null,null,"Other Items (25%)",{"$f":"'Cost Estimate'!J35","v":0},null,null,"307-02.08","\"BM-2\" mix",2,{"$f":"Roadway!AK71","v":0}]
[null,null,"Contingency:",{"$f":"IF(F26>0.5,\"Contingency Greater than 50%\",IF(F26<0.15,\"Contingency Less than 15%\",\"Default\"))","v":"Default"},null,null,null,"Contingency",{"$f":"'Cost Estimate'!J36","v":0},null,null,"402-01","Prime Coat","N/A",{"$f":"Roadway!AK72","v":0}]
[null,null,"General:",{"$f":"IF(OR('Cost Estimate'!C5='Cost Estimate'!D116,'Cost Estimate'!C5='Cost Estimate'!D117),\"No Errors\",IF(D42<>\"No Errors\",\"Invalid Inputs\",\"No Errors\"))","v":"Invalid Inputs"},null,null,null,"Total:",{"$f":"'Cost Estimate'!L75","v":0},null,null,"402-02","Agg. Cover","N/A",{"$f":"Roadway!AK73","v":0}]
[null,null,null,null,null,null,null,null,null,null,null,"303-01","Base Stone",20.25,{"$f":"Roadway!AK74","v":0}]
[]
[null,"Project Location and Termini"]
[]
[null,null,null,null,null,null,"Location Information"]
[null,null,null,null,null,null,"Route:",null,"Project Begin (mi):",null,{"$f":"IF(J52=\"\",\"Enter Begin L.M.\",IF(J52>J54,\"Beginning L.M. Greater than End L.M.\",\"\"))","v":"Enter Begin L.M."}]
[null,null,null,null,null,{"$f":"IF(H53=\"\",\"Enter County ->\",\"\")","v":"Enter County ->"},"County:"]
[null,null,null,null,null,null,"Project Type:","Statewide","Project End (mi):",null,{"$f":"IF(J54=\"\",\"Enter End L.M.\",\"\")","v":"Enter End L.M."}]
[null,null,null,null,null,{"$f":"IF(H55=\"\",\"Enter PIN ->\",\"\")","v":"Enter PIN ->"},"PIN:"]
[null,null,null,null,null,null,null,"."]
[null,"ROADWAY DESIGN"]
[]
[null,null,"INPUT ROAD SEGMENT CHARACTERISTICS"]
[null,null,"PAVEMENT",null,null,null,null,null,null,null,"ROADSIDE DESIGN",null,null,"TERRAIN"]
[null,null,"Construction Estimate:",null,null,null,{"$f":"E26","v":0},"How Many Segments (1-30)?",null,1,"Rural or Urban Drainage","Sidewalk Width (ft):",6,"Terrain Type","Widen to One Side or Both?","Foreslope H:V Rate"]
[null,null,"Total Estimated Project Cost:",null,null,null,{"$f":"'Cost Estimate'!J57","v":0},null,null,null,null,"Grass Strip Width (ft):",2.5]
[null,null,"Segment","Begin (mi)","End (mi)","Pavement Design (ft)","Proposed Full Depth Pavement Width (ft)","Outside Shldr Width (ft)","Existing Pavement Width","Replace Existing Full Depth Pavement?",null,"Urban Drainage on one side or both?","Sidewalk on One Side or Both Sides",null,null,null,null,1,"Urban Additional Info Check",null,{"$f":"IFERROR(IF(OR(C64=\"\",N64=\"\"),\"\",IF(N64=\"Flat\",$K$122,IF(N64=\"Rolling\",$K$123,IF(N64=\"Mountainous\",$K$124,IF(N64=\"Heavy Mountainous\",$K$125))))),\"\")","v":""},"<- Backup Formula"]
[null,{"$f":"IF(OR($J$52=\"\",$J$54=\"\"),\"\",IF(E64=$J$54,\"Complete - Last Segment\",IF(AND(E64<>\"\",E65=\"\",E64<$J$54),\"Not Complete - Enter More Segments\",\"\")))","v":""},{"$f":"IF(AND(J61>=1,J61<=30),1,\"\")","v":1},null,null,null,null,null,null,null,null,null,null,null,null,"",{"$f":"IF(S64<>\"\",\"Data Missing\",IF(OR($J$52=\"\",$J$54=\"\"),\"Location Info Missing\",IF(AND(E64<>\"\",OR(F64=\"\",G64=\"\",H64=\"\",I64=\"\",N64=\"\",J64=\"\",O64=\"\",K64=\"\",P64=\"\")),\"Data Missing\",\"\")))","v":"Location Info Missing"},{"$f":"IF(C64<>\"\",1,0)","v":1},{"$f":"IF(K64=$B$8,IF(OR(L64=\"\",M64=\"\"),\"Data Missing\",\"\"),\"\")","v":""},{"$f":"IF(Q64=\"Data Missing\",1,0)","v":0},{"$f":"IFERROR(IF(OR(C64=\"\",N64=\"\"),\"\",IF(N64=\"Flat\",$K$122,IF(N64=\"Rolling\",$K$123,IF(N64=\"Mountainous\",$K$124,IF(N64=\"Heavy Mountainous\",$K$125))))),\"\")","v":""}]
[null,{"$f":"IF(OR($J$52=\"\",$J$54=\"\"),\"\",IF(E65=$J$54,\"Complete - Last Segment\",IF(AND(E65<>\"\",E66=\"\",E65<$J$54),\"Not Complete - Enter More Segments\",\"\")))","v":""},{"$f":"IF(AND(J61>=2,J61<=30),2,\"\")","v":""},{"$f":"IF(E64=\"\",\"\",E64)","v":""},null,null,null,null,null,null,null,null,null,null,null,"",{"$f":"IF(S65<>\"\",\"Data Missing\",IF(OR($J$52=\"\",$J$54=\"\"),\"Location Info Missing\",IF(AND(E65<>\"\",OR(F65=\"\",G65=\"\",H65=\"\",I65=\"\",N65=\"\",J65=\"\",O65=\"\",K65=\"\",P65=\"\")),\"Data Missing\",\"\")))","v":"Location Info Missing"},0,{"$f":"IF(K65=$B$8,IF(OR(L65=\"\",M65=\"\"),\"Data Missing\",\"\"),\"\")","v":""},{"$f":"IF(Q65=\"Data Missing\",1,0)","v":0},{"$f":"IFERROR(IF(OR(C65=\"\",N65=\"\"),\"\",IF(N65=\"Flat\",$K$122,IF(N65=\"Rolling\",$K$123,IF(N65=\"Mountainous\",$K$124,IF(N65=\"Heavy Mountainous\",$K$125))))),\"\")","v":""}]
[null,"",{"$f":"IF(AND(J61>=3,J61<=30),3,\"\")","v":""},{"$f":"IF(E65=\"\",\"\",E65)","v":""},null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,{"$f":"IF(K66=$B$8,IF(OR(L66=\"\",M66=\"\"),\"Data Missing\",\"\"),\"\")","v":""},0,""]
[null,"",{"$f":"IF(AND(J61>=4,J61<=30),4,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,{"$f":"IF(K67=$B$8,IF(OR(L67=\"\",M67=\"\"),\"Data Missing\",\"\"),\"\")","v":""},0,""]
[null,"",{"$f":"IF(AND(J61>=5,J61<=30),5,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=6,J61<=30),6,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=7,J61<=30),7,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=8,J61<=30),8,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=9,J61<=30),9,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=10,J61<=30),10,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=11,J61<=30),11,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=12,J61<=30),12,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=13,J61<=30),13,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=14,J61<=30),14,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=15,J61<=30),15,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=16,J61<=30),16,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=17,J61<=30),17,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=18,J61<=30),18,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=19,J61<=30),19,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=20,J61<=30),20,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=21,J61<=30),21,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=22,J61<=30),22,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=23,J61<=30),23,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=24,J61<=30),24,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=25,J61<=30),25,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=26,J61<=30),26,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=27,J61<=30),27,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=28,J61<=30),28,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61>=29,J61<=30),29,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[null,"",{"$f":"IF(AND(J61=30),30,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,"","Location Info Missing",0,"",0,""]
[]
[null,null,"MEDIAN INPUTS"]
[null,null,"How Many Segments (1-20)?",null,null,null,null,null,null,1]
[null,null,"Segments","Begin (mi)","End (mi)","Median Type","# Travel Lanes in Each Direction","Terrain Type","Inside Shldr. Width (ft)","Interior Width (ft)",null,null,null,null,null,null,null,1]
[null,null,{"$f":"IF(AND(J96>=1,J96<=20),1,\"\")","v":1},null,null,null,null,null,{"$f":"IF(AND(F98=$J$7,G98=$P$7),4,IF(AND(F98=$J$7,G98=$P$8),10,IF(F98=$J$8,0,IF(F98=$J$9,0,\"\"))))","v":""},{"$f":"IF(AND(F98=$J$7,G98=$P$7),48-I98*2,IF(AND(F98=$J$7,G98=$P$8),68-I98*2,IF(F98=$J$8,14,IF(F98=$J$9,0,\"\"))))","v":""},{"$f":"IF(AND(D98<>\"\",E98<>\"\",OR(F98=\"\",I98=\"\",J98=\"\",H98=\"\")),\"Data Missing\",\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(AND(J96>=1,J96<=20),1,0)","v":1},null,{"$f":"IF(AND(D98<>\"\",E98<>\"\"),E98-D98,0)","v":0}]
[null,null,{"$f":"IF(AND(J96>=2,J96<=20),2,\"\")","v":""},{"$f":"IF(E98=\"\",\"\",E98)","v":""},null,null,null,null,{"$f":"IF(AND(F99=$J$7,G99=$P$7),4,IF(AND(F99=$J$7,G99=$P$8),10,IF(F99=$J$8,0,IF(F99=$J$9,0,\"\"))))","v":""},{"$f":"IF(AND(F99=$J$7,G99=$P$7),48-I99*2,IF(AND(F99=$J$7,G99=$P$8),68-I99*2,IF(F99=$J$8,14,IF(F99=$J$9,0,\"\"))))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=2,J96<=20),1,0)","v":0},{"$f":"IF(AND(D99<>\"\",E99<>\"\"),E99-D99,0)","v":0}]
[null,null,{"$f":"IF(AND(J96>=3,J96<=20),3,\"\")","v":""},{"$f":"IF(E99=\"\",\"\",E99)","v":""},null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=3,J96<=20),1,0)","v":0},0]
[null,null,{"$f":"IF(AND(J96>=4,J96<=20),4,\"\")","v":""},"",null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=4,J96<=20),1,0)","v":0},0]
[null,null,{"$f":"IF(AND(J96>=5,J96<=20),5,\"\")","v":""},"",null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=5,J96<=20),1,0)","v":0},0]
[null,null,{"$f":"IF(AND(J96>=6,J96<=20),6,\"\")","v":""},"",null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=6,J96<=20),1,0)","v":0},0]
[null,null,{"$f":"IF(AND(J96>=7,J96<=20),7,\"\")","v":""},"",null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=7,J96<=20),1,0)","v":0},0]
[null,null,{"$f":"IF(AND(J96>=8,J96<=20),8,\"\")","v":""},"",null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=8,J96<=20),1,0)","v":0},0]
[null,null,{"$f":"IF(AND(J96>=9,J96<=20),9,\"\")","v":""},"",null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=9,J96<=20),1,0)","v":0},0]
[null,null,{"$f":"IF(AND(J96>=10,J96<=20),10,\"\")","v":""},"",null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=10,J96<=20),1,0)","v":0},0]
[null,null,{"$f":"IF(AND(J96>=11,J96<=20),11,\"\")","v":""},"",null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=11,J96<=20),1,0)","v":0},0]
[null,null,{"$f":"IF(AND(J96>=12,J96<=20),12,\"\")","v":""},"",null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=12,J96<=20),1,0)","v":0},0]
[null,null,{"$f":"IF(AND(J96>=13,J96<=20),13,\"\")","v":""},"",null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=13,J96<=20),1,0)","v":0},0]
[null,null,{"$f":"IF(AND(J96>=14,J96<=20),14,\"\")","v":""},"",null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=14,J96<=20),1,0)","v":0},0]
[null,null,{"$f":"IF(AND(J96>=15,J96<=20),15,\"\")","v":""},"",null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=15,J96<=20),1,0)","v":0},0]
[null,null,{"$f":"IF(AND(J96>=16,J96<=20),16,\"\")","v":""},"",null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=16,J96<=20),1,0)","v":0},0]
[null,null,{"$f":"IF(AND(J96>=17,J96<=20),17,\"\")","v":""},"",null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=17,J96<=20),1,0)","v":0},0]
[null,null,{"$f":"IF(AND(J96>=18,J96<=20),18,\"\")","v":""},"",null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=18,J96<=20),1,0)","v":0},0]
[null,null,{"$f":"IF(AND(J96>=19,J96<=20),19,\"\")","v":""},"",null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96>=19,J96<=20),1,0)","v":0},0]
[null,null,{"$f":"IF(AND(J96=20),20,\"\")","v":""},"",null,null,null,null,"","",null,null,null,null,null,null,null,{"$f":"IF(AND(J96=20),1,0)","v":0},0]
[]
[]
[null,null,"Pavement Removal",null,null,"Concrete Islands",null,null,"Terrain Assumptions",null,null,null,"Shared Use Path"]
[null,null,"AREA OF PAVEMENT REMOVAL (SF)",null,null,"Total Concrete Island Area (SF)",null,null,"Terrain Type","Cut/Fill Depth","Foreslope Rate",null,"Terrain Type","Length (mi)","Grass Strip Width (ft)","Pav Width (8 - 12 ft)"]
[null,null,"Asphalt:",null,null,"SQFT:",null,null,"Flat (1 - 3ft):",3,"6H:1V",null,"Flat :"]
[null,null,"Concrete:",null,null,null,null,null,"Rolling (4 - 7 ft):",4.9804691576092077,"4H:1V",null,"Rolling:"]
[null,null,null,null,null,null,null,null,"Mountainous (8 - 11 ft):",9,"3H:1V",null,"Mountainous:"]
[null,null,null,null,null,null,null,null,"Heavy Mountainous (12 - 25 ft):",16.018039252929434,"2H:1V",null,"Heavy Mountainous:"]
[]
[null,"BRIDGES AND STRUCTURES"]
[]
[]
[null,null,"Structure Removal"]
[null,null,"How Many (1-20)?",null,null,1]
[null,null,"Number","Length","Width","Type",null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,{"$f":"IF(AND(F131>=1,F131<=20),1,\"\")","v":1},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=1,F131<=20),1,0)","v":1}]
[null,null,{"$f":"IF(AND(F131>=2,F131<=20),2,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=2,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131>=3,F131<=20),3,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=3,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131>=4,F131<=20),4,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=4,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131>=5,F131<=20),5,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=5,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131>=6,F131<=20),6,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=6,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131>=7,F131<=20),7,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=7,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131>=8,F131<=20),8,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=8,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131>=9,F131<=20),9,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=9,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131>=10,F131<=20),10,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=10,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131>=11,F131<=20),11,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=11,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131>=12,F131<=20),12,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=12,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131>=13,F131<=20),13,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=13,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131>=14,F131<=20),14,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=14,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131>=15,F131<=20),15,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=15,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131>=16,F131<=20),16,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=16,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131>=17,F131<=20),17,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=17,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131>=18,F131<=20),18,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=18,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131>=19,F131<=20),19,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=19,F131<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(F131=20),20,\"\")","v":""},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(F131>=20,E138<=20),1,0)","v":0}]
[]
[null,null,"New Structures",null,null,null,null,null,null,null,null,"New Structure Contingencies"]
[null,null,"How Many (1-20)?",null,null,null,1,null,null,null,null,"Box Bridge","Concrete I-Beam & Bulb-T","Concrete Box Beam","Steel Bridge"]
[null,null,"Number","Length","Width","Type","Construction Method","Foundation Contingency","Bridge Contingency","Feature Crossed / No Spans",null,{"$f":"Bridges!E18","v":0},{"$f":"Bridges!E19","v":0},{"$f":"Bridges!E20","v":0},{"$f":"Bridges!E21","v":0},null,null,1]
[null,null,{"$f":"IF(AND(G155>=1,G155<=20),1,\"\")","v":1},null,null,null,null,null,{"$f":"IF(OR(D157=\"\",E157=\"\",F157=\"\",G157=\"\",H157=\"\"),\"\",IF(OR(Bridges!AT65=\"\",Bridges!AT65=0),0,Bridges!AT65))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=1,G155<=20),1,0)","v":1}]
[null,null,{"$f":"IF(AND(G155>=2,G155<=20),2,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D158=\"\",E158=\"\",F158=\"\",G158=\"\",H158=\"\"),\"\",IF(OR(Bridges!AT66=\"\",Bridges!AT66=0),0,Bridges!AT66))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=2,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155>=3,G155<=20),3,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D159=\"\",E159=\"\",F159=\"\",G159=\"\",H159=\"\"),\"\",IF(OR(Bridges!AT67=\"\",Bridges!AT67=0),0,Bridges!AT67))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=3,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155>=4,G155<=20),4,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D160=\"\",E160=\"\",F160=\"\",G160=\"\",H160=\"\"),\"\",IF(OR(Bridges!AT68=\"\",Bridges!AT68=0),0,Bridges!AT68))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=4,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155>=5,G155<=20),5,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D161=\"\",E161=\"\",F161=\"\",G161=\"\",H161=\"\"),\"\",IF(OR(Bridges!AT69=\"\",Bridges!AT69=0),0,Bridges!AT69))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=5,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155>=6,G155<=20),6,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D162=\"\",E162=\"\",F162=\"\",G162=\"\",H162=\"\"),\"\",IF(OR(Bridges!AT70=\"\",Bridges!AT70=0),0,Bridges!AT70))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=6,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155>=7,G155<=20),7,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D163=\"\",E163=\"\",F163=\"\",G163=\"\",H163=\"\"),\"\",IF(OR(Bridges!AT71=\"\",Bridges!AT71=0),0,Bridges!AT71))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=7,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155>=8,G155<=20),8,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D164=\"\",E164=\"\",F164=\"\",G164=\"\",H164=\"\"),\"\",IF(OR(Bridges!AT72=\"\",Bridges!AT72=0),0,Bridges!AT72))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=8,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155>=9,G155<=20),9,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D165=\"\",E165=\"\",F165=\"\",G165=\"\",H165=\"\"),\"\",IF(OR(Bridges!AT73=\"\",Bridges!AT73=0),0,Bridges!AT73))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=9,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155>=10,G155<=20),10,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D166=\"\",E166=\"\",F166=\"\",G166=\"\",H166=\"\"),\"\",IF(OR(Bridges!AT74=\"\",Bridges!AT74=0),0,Bridges!AT74))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=10,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155>=11,G155<=20),11,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D167=\"\",E167=\"\",F167=\"\",G167=\"\",H167=\"\"),\"\",IF(OR(Bridges!AT75=\"\",Bridges!AT75=0),0,Bridges!AT75))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=11,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155>=12,G155<=20),12,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D168=\"\",E168=\"\",F168=\"\",G168=\"\",H168=\"\"),\"\",IF(OR(Bridges!AT76=\"\",Bridges!AT76=0),0,Bridges!AT76))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=12,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155>=13,G155<=20),13,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D169=\"\",E169=\"\",F169=\"\",G169=\"\",H169=\"\"),\"\",IF(OR(Bridges!AT77=\"\",Bridges!AT77=0),0,Bridges!AT77))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=13,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155>=14,G155<=20),14,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D170=\"\",E170=\"\",F170=\"\",G170=\"\",H170=\"\"),\"\",IF(OR(Bridges!AT78=\"\",Bridges!AT78=0),0,Bridges!AT78))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=14,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155>=15,G155<=20),15,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D171=\"\",E171=\"\",F171=\"\",G171=\"\",H171=\"\"),\"\",IF(OR(Bridges!AT79=\"\",Bridges!AT79=0),0,Bridges!AT79))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=15,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155>=16,G155<=20),16,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D172=\"\",E172=\"\",F172=\"\",G172=\"\",H172=\"\"),\"\",IF(OR(Bridges!AT80=\"\",Bridges!AT80=0),0,Bridges!AT80))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=16,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155>=17,G155<=20),17,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D173=\"\",E173=\"\",F173=\"\",G173=\"\",H173=\"\"),\"\",IF(OR(Bridges!AT81=\"\",Bridges!AT81=0),0,Bridges!AT81))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=17,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155>=18,G155<=20),18,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D174=\"\",E174=\"\",F174=\"\",G174=\"\",H174=\"\"),\"\",IF(OR(Bridges!AT82=\"\",Bridges!AT82=0),0,Bridges!AT82))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=18,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155>=19,G155<=20),19,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D175=\"\",E175=\"\",F175=\"\",G175=\"\",H175=\"\"),\"\",IF(OR(Bridges!AT83=\"\",Bridges!AT83=0),0,Bridges!AT83))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=19,G155<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(G155=20),20,\"\")","v":""},null,null,null,null,null,{"$f":"IF(OR(D176=\"\",E176=\"\",F176=\"\",G176=\"\",H176=\"\"),\"\",IF(OR(Bridges!AT84=\"\",Bridges!AT84=0),0,Bridges!AT84))","v":""},null,null,null,null,null,null,null,null,{"$f":"IF(AND(G155>=20,G155<=20),1,0)","v":0}]
[]
[null,null,"Structure Rehabilitation & Widenings"]
[null,null,"How Many (1-20)?",null,null,null,null,1]
[null,null,"Number","Length (ft)","Width (ft)","Type","Add'l Width","Construction Method","Foundation Risk","Bridge Contingency","Bridge Location",null,null,null,null,null,null,1]
[null,null,{"$f":"IF(AND(H179>=1,H179<=20),1,\"\")","v":1},null,null,null,null,null,null,{"$f":"IF(OR(D181=\"\",E181=\"\",F181=\"\",G181=\"\",H181=\"\",I181=\"\"),\"\",IF(Bridges!AU35=0,0,Bridges!AU35))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=1,H179<=20),1,0)","v":1}]
[null,null,{"$f":"IF(AND(H179>=2,H179<=20),2,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D182=\"\",E182=\"\",F182=\"\",G182=\"\",H182=\"\",I182=\"\"),\"\",IF(Bridges!AU36=0,0,Bridges!AU36))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=2,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179>=3,H179<=20),3,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D183=\"\",E183=\"\",F183=\"\",G183=\"\",H183=\"\",I183=\"\"),\"\",IF(Bridges!AU37=0,0,Bridges!AU37))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=3,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179>=4,H179<=20),4,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D184=\"\",E184=\"\",F184=\"\",G184=\"\",H184=\"\",I184=\"\"),\"\",IF(Bridges!AU38=0,0,Bridges!AU38))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=4,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179>=5,H179<=20),5,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D185=\"\",E185=\"\",F185=\"\",G185=\"\",H185=\"\",I185=\"\"),\"\",IF(Bridges!AU39=0,0,Bridges!AU39))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=5,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179>=6,H179<=20),6,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D186=\"\",E186=\"\",F186=\"\",G186=\"\",H186=\"\",I186=\"\"),\"\",IF(Bridges!AU40=0,0,Bridges!AU40))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=6,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179>=7,H179<=20),7,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D187=\"\",E187=\"\",F187=\"\",G187=\"\",H187=\"\",I187=\"\"),\"\",IF(Bridges!AU41=0,0,Bridges!AU41))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=7,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179>=8,H179<=20),8,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D188=\"\",E188=\"\",F188=\"\",G188=\"\",H188=\"\",I188=\"\"),\"\",IF(Bridges!AU42=0,0,Bridges!AU42))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=8,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179>=9,H179<=20),9,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D189=\"\",E189=\"\",F189=\"\",G189=\"\",H189=\"\",I189=\"\"),\"\",IF(Bridges!AU43=0,0,Bridges!AU43))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=9,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179>=10,H179<=20),10,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D190=\"\",E190=\"\",F190=\"\",G190=\"\",H190=\"\",I190=\"\"),\"\",IF(Bridges!AU44=0,0,Bridges!AU44))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=10,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179>=11,H179<=20),11,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D191=\"\",E191=\"\",F191=\"\",G191=\"\",H191=\"\",I191=\"\"),\"\",IF(Bridges!AU45=0,0,Bridges!AU45))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=11,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179>=12,H179<=20),12,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D192=\"\",E192=\"\",F192=\"\",G192=\"\",H192=\"\",I192=\"\"),\"\",IF(Bridges!AU46=0,0,Bridges!AU46))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=12,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179>=13,H179<=20),13,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D193=\"\",E193=\"\",F193=\"\",G193=\"\",H193=\"\",I193=\"\"),\"\",IF(Bridges!AU47=0,0,Bridges!AU47))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=13,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179>=14,H179<=20),14,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D194=\"\",E194=\"\",F194=\"\",G194=\"\",H194=\"\",I194=\"\"),\"\",IF(Bridges!AU48=0,0,Bridges!AU48))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=14,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179>=15,H179<=20),15,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D195=\"\",E195=\"\",F195=\"\",G195=\"\",H195=\"\",I195=\"\"),\"\",IF(Bridges!AU49=0,0,Bridges!AU49))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=15,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179>=16,H179<=20),16,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D196=\"\",E196=\"\",F196=\"\",G196=\"\",H196=\"\",I196=\"\"),\"\",IF(Bridges!AU50=0,0,Bridges!AU50))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=16,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179>=17,H179<=20),17,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D197=\"\",E197=\"\",F197=\"\",G197=\"\",H197=\"\",I197=\"\"),\"\",IF(Bridges!AU51=0,0,Bridges!AU51))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=17,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179>=18,H179<=20),18,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D198=\"\",E198=\"\",F198=\"\",G198=\"\",H198=\"\",I198=\"\"),\"\",IF(Bridges!AU52=0,0,Bridges!AU52))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=18,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179>=19,H179<=20),19,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D199=\"\",E199=\"\",F199=\"\",G199=\"\",H199=\"\",I199=\"\"),\"\",IF(Bridges!AU53=0,0,Bridges!AU53))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=19,H179<=20),1,0)","v":0}]
[null,null,{"$f":"IF(AND(H179=20),20,\"\")","v":""},null,null,null,null,null,null,{"$f":"IF(OR(D200=\"\",E200=\"\",F200=\"\",G200=\"\",H200=\"\",I200=\"\"),\"\",IF(Bridges!AU54=0,0,Bridges!AU54))","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(H179>=20,H179<=20),1,0)","v":0}]
[]
[null,null,"Retaining Walls",null,"If Conceptual Level Retaining Wall Information is known, then use the RETAINING WALL PROBABLE BID PRICE ESTIMATING TOOL"]
[null,null,"Average Height:"]
[null,null,"Total Length:"]
[]
[null,"RIGHT-OF-WAY AND UTILTIES",null,null,null,null,null,null,null,null,null,"MISCELLANEOUS"]
[]
[]
[null,null,"Utility Relocation",null,null,"Additional ROW & Utilities Cost",null,null,null,null,null,null,"CLEARING AND GRUBBING ASSUMPTIONS",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"PLANNING LEVEL INTERCHANGE COSTS"]
[null,null,"Overhead",null,null,"Right-of-Way:",null,null,null,null,null,null,"LENGTH OF IMPACTS (MILE):"]
[null,null,"Distribution (mi):",null,null,"Utilities:",null,null,null,null,null,null,"TYPE OF IMPACTS",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"New Interchanges"]
[null,null,"Transmission (mi):",null,null,null,null,null,null,null,null,null,"Very Low",null,0,{"$f":"$O$212*$O$210*'Clr&Grb'!N2","v":0},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Diamond","Par-Clo","Cloverleaf"]
[null,null,"Underground",null,null,null,null,null,null,null,null,null,"Low",null,0,{"$f":"$O213*$O$210*'Clr&Grb'!N3","v":0},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Rural"]
[null,null,"Power (mi):",null,null,null,null,null,null,null,null,null,"Moderate",null,0,{"$f":"$O214*$O$210*'Clr&Grb'!N4","v":0},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Diamond","TUDI","SPUI"]
[null,null,"Water (mi):",null,null,null,null,null,null,null,null,null,"High",null,0,{"$f":"$O215*$O$210*'Clr&Grb'!N5","v":0},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Urban"]
[null,null,"Gas (mi):",null,null,null,null,null,null,null,null,null,"Very High",null,0,{"$f":"$O216*$O$210*'Clr&Grb'!N6","v":0}]
[null,null,"Comm. (mi):",null,null,null,null,null,null,null,null,null,"TOTAL:",null,{"$f":"SUM(O212:O216)","v":0},{"$f":"SUM(P212:P216)","v":0}]
[null,null,"Sewer (mi):"]
[]
[null,null,"PLANNING LEVEL PER MILE RIGHT-OF-WAY ESTIMATE INPUTS"]
[null,null,"NOTICE: The purpose of this right-of-way estimate method is to provide a rough estimate of potential row costs for a project, and it should be used solely for early budgeting purposes. Please note that this method is not intended to provide cost projection with a high degree of accuracy, but rather to give an order of magnitude for planning purposes.  ",null,null,null,null,null,null,null,null,null,"Traffic Control"]
[null,null,null,null,null,null,null,null,null,null,null,null,"Enter Information"]
[null,null,null,null,null,null,null,null,null,null,null,null,"Project Type:",null,null,"Grade and Drain"]
[null,null,"STEP 1: CALIBRATE TO LOCAL CONDITIONS",null,null,null,"STEP 2: DEFINE PROJECT TYPE AND LEVEL OF IMPACTS",null,null,null,null,null,"Level of Traffic Control:",null,null,"Average"]
[null,null,"Zillow Home Value Index",null,null,null,"ROW IMPACT ASSUMPTIONS",null,null,null,null,null,"Recommended % Project Cost:",null,null,{"$f":"IF(P224=\"Average\",VLOOKUP(P223,'Traffic Control'!B:C,2,0),IF(P224=\"High\",VLOOKUP(P223,'Traffic Control'!B:D,3,0),\"\"))","v":0.05}]
[null,null,"USE THE LINK BELOW TO FIND THE CURRENT STATEWIDE AND LOCAL HOME VALUE INDEXES",null,null,null,"TYPE OF PROJECT:",null,"Corridor Project",null,null,null,"Traffic Control Cost",null,null,{"$f":"'Cost Estimate'!J31","v":0}]
[null,null,null,null,null,null,"LENGTH OF IMPACTS (mi):",null,1]
[null,null,"https://www.zillow.com/home-values/53/tn/",null,null,null,"TYPE OF IMPACTS"]
[null,null,"TN Average:",null,325653,null,"Very Low",null,0,{"$f":"IF($I$234<>1,\"\",IF($I$226=\"Bridge Replacement\",VLOOKUP(Tool!G229,ROW_New!$J$30:$M$34,4,0),IF($I$226=\"Corridor Project\",VLOOKUP(Tool!G229,ROW_New!$J$22:$M$26,4,0),\"\")))","v":""}]
[null,null,"Closest City to Project?:",null,null,null,"Low",null,0,{"$f":"IF($I$234<>1,\"\",IF($I$226=\"Bridge Replacement\",VLOOKUP(Tool!G230,ROW_New!$J$30:$M$34,4,0),IF($I$226=\"Corridor Project\",VLOOKUP(Tool!G230,ROW_New!$J$22:$M$26,4,0),\"\")))","v":""}]
[null,null,null,null,null,null,"Moderate",null,0,{"$f":"IF($I$234<>1,\"\",IF($I$226=\"Bridge Replacement\",VLOOKUP(Tool!G231,ROW_New!$J$30:$M$34,4,0),IF($I$226=\"Corridor Project\",VLOOKUP(Tool!G231,ROW_New!$J$22:$M$26,4,0),\"\")))","v":""},null,null,"Haul Road"]
[null,null,"Local Home Value Index:",null,325653,null,"High",null,0,{"$f":"IF($I$234<>1,\"\",IF($I$226=\"Bridge Replacement\",VLOOKUP(Tool!G232,ROW_New!$J$30:$M$34,4,0),IF($I$226=\"Corridor Project\",VLOOKUP(Tool!G232,ROW_New!$J$22:$M$26,4,0),\"\")))","v":""},null,null,"Estimated Top Layer Height (ft) (0.5' - 2')"]
[null,null,"Local Calibration Factor:",null,{"$f":"E232/E229","v":1},null,"Very High",null,0,{"$f":"IF($I$234<>1,\"\",IF($I$226=\"Bridge Replacement\",VLOOKUP(Tool!G233,ROW_New!$J$30:$M$34,4,0),IF($I$226=\"Corridor Project\",VLOOKUP(Tool!G233,ROW_New!$J$22:$M$26,4,0),\"\")))","v":""},null,null,"Estimated Bottom Layer Height (ft) (1' - 9')"]
[null,null,null,null,null,null,"TOTAL:",null,{"$f":"SUM(I229:I233)","v":0},{"$f":"SUM(J229:J233)","v":0},null,null,"Total Estimated Length (ft)"]
[null,null,null,null,null,null,null,null,null,null,null,null,"Total Cost",null,{"$f":"'Haul Road'!B27","v":0}]
[null,null,"LEVEL OF IMPACTS GUIDANCE"]
[null,null,"Impacts","Guidance"]
[null,null,"Very Low:","Minor Land Acquisition only.  Examples would be interstate widenings that occur mostly within existing ROW, or rural locations with very minimal impacts to property owners with no relocations."]
[null,null,"Low:","Mostly minor land acquisition in rural areas with 1 or 2 residential relocations per mile"]
[null,null,"Moderate:","A majority of the impacts will be land acquisition, but there will be several driveway impacts and relocations to home owners and/or small business owners."]
[null,null,"High:","High density of residential and/or commercial impacts and relocations"]
[null,null,"Very High:","Significant Heavy Industrial and/or Commercial Impacts, or Very High Density Impacts to Urban Residential Environment"]

{"sheet":"Haul Road","index":2,"n_rows":27,"n_cols":6,"rows_kept":27,"cut":false,"hidden":true,"merged":[[24,1,24,2],[25,1,25,2],[7,0,7,1],[7,3,7,4],[20,0,20,2],[21,1,21,2],[22,1,22,2],[23,1,23,2]]}
[]
[]
[]
["Haul #1 Road Cost Estimation",null,null,"*enter data in grey cells*"]
[]
["Total Length",{"$f":"Tool!O234","v":0}]
[]
["Top Layer ",null,null,"Bottom Layer"]
["Slope",2,":1","Slope",{"$f":"B9","v":2},":1"]
["Height",{"$f":"Tool!O232","v":0},"ft","Height",{"$f":"Tool!O233","v":0},"ft"]
["Top Width",22,"ft","Top Width",{"$f":"B12","v":22},"ft"]
["Bottom Width",{"$f":"(2*(B9*B10))+B11","v":22},"ft","Bottom Width",{"$f":"(2*(E9*E10))+E11","v":22},"ft"]
["Volume",{"$f":"(B6*(0.5*B10*(B11+B12)))/27","v":0},"CY","Volume",{"$f":"(B6*(0.5*E10*(E11+E12)))/27","v":0},"CY"]
["Density",1.75,"ton/CY","Density",1.8,"ton/CY"]
["Cost",64.22,"/ton","Cost",62,"/ton"]
[]
["Geotextile",2.91,"/SY"]
[]
["Removal Factor",1.5]
[]
["Totals (Installation)"]
["Top Layer",{"$f":"(B13*B14)*B15","v":0}]
["Bottom Layer",{"$f":"(E13*E14)*E15","v":0}]
["Geo",{"$f":"((B6*E12)/9)*B17","v":0}]
[null,{"$f":"SUM(B22:C24)","v":0}]
["w/Removal",{"$f":"B25*B19","v":0}]
[null,{"$f":"B26","v":0}]

{"sheet":"Typical Comparison","index":3,"n_rows":23,"n_cols":12,"rows_kept":23,"cut":false,"hidden":true,"merged":[[22,1,22,2],[14,1,14,4],[15,1,15,4],[16,1,16,2],[17,1,17,2],[7,1,7,2],[4,6,4,11],[19,1,19,4],[20,1,20,4],[21,1,21,2],[11,1,11,2],[12,1,12,2],[4,1,4,4],[9,1,9,4],[10,1,10,4],[5,1,5,4],[6,1,6,2]]}
[]
[null,"Begin (mi)","End (mi)","Pavement Design (ft)","Proposed Full Depth Pavement Width (ft)","Outside Shldr Width (ft)","Existing Pavement - If Widening","Terrain Type"]
[null,0,1,"Arterial",80,0,24,"Rolling"]
[]
[null,"Rural Ditch - Both Sides - Full Depth Pavement Removal",null,null,null,null,"Urban Typical Comparison"]
[null,"Project Cost Summary",null,null,null,null,"#","Widen to One Side or Both?","Curb and Gutter on one side or both?","5' Sidewalks","FDPR","Construction Cost"]
[null,"Description",null,"Estimate","Contingency",null,1,"Both Sides","Both Sides","Both Sides","Yes",13000000]
[null,"Construction:",null,11200000,0.3,null,2,"Both Sides","Both Sides","One Side","Yes",12500000]
[null,null,null,null,null,null,3,"Both Sides","Both Sides","None","Yes",12000000]
[null,"Rural Ditch - One Side - Full Depth Pavement Removal",null,null,null,null,4,"Both Sides","One Side","One Side","Yes",12100000]
[null,"Project Cost Summary",null,null,null,null,5,"Both Sides","One Side","None","Yes",11600000]
[null,"Description",null,"Estimate","Contingency",null,6,"One Side","Both Sides","Both Sides","Yes",11500000]
[null,"Construction:",null,9170000,0.3,null,7,"One Side","Both Sides","One Side","Yes",11000000]
[null,null,null,null,null,null,8,"One Side","Both Sides","None","Yes",10500000]
[null,"Rural Ditch - Both Sides",null,null,null,null,9,"One Side","One Side","One Side","Yes",10600000]
[null,"Project Cost Summary",null,null,null,null,10,"One Side","One Side","None","Yes",10100000]
[null,"Description",null,"Estimate","Contingency"]
[null,"Construction:",null,9010000,0.3]
[]
[null,"Rural Ditch - One Side"]
[null,"Project Cost Summary"]
[null,"Description",null,"Estimate","Contingency"]
[null,"Construction:",null,7020000,0.3]

{"sheet":"Finalize Items","index":4,"n_rows":804,"n_cols":10,"rows_kept":804,"cut":false,"hidden":false,"merged":[[15,2,15,7],[16,2,16,7],[758,2,758,7]]}
[0,"TN - 2005"]
[0,"TN -2006"]
[0,"TN - 2007"]
[0,"TN - 2008"]
[0,"TN - 2009"]
[0,"TN - 2010"]
[0,"TN - 2011"]
[0,"TN - 2012"]
[0,"TN - 2013"]
[0,"TN - 2014"]
[0,"Region 1 - 2016"]
[0,"Region 2 - 2016"]
[0,"Region 3 - 2016"]
[0,"Region 4 - 2016"]
[0,"Statewide - 2016"]
[1,null,"** DO NOT ADJUST COLUMN E **"]
[1,null,"** MAKE ALL ADJUSTMENTS TO QUANTITIES IN COLUMN F **"]
[1]
[1,"TDOT PAY ITEM","TDOT DESCRIPTION","UNIT","TOOL QUANTITIES","ADDITIONAL QUANTITIES","TOOL QUANTITIES + ADDITIONAL QUANTITIES","Unit Price","TOTAL COST"]
[1]
[1,"Pavment Removal"]
[{"$f":"IF(G22>0,1,0)","v":0},"202-03.01","REMOVAL OF ASPHALT PAVEMENT","SY",{"$f":"IF(Tool!$D$46=\"No Errors\",Roadway!O22,0)","v":0},null,{"$f":"E22+F22","v":0},{"$f":"VLOOKUP($B22,'AUP Data'!$A:$AF,25,0)","v":20.64},{"$f":"IF(G22<>\"\",G22*H22,\"\")","v":0}]
[{"$f":"IF(G23>0,1,0)","v":0},"202-03","REMOVAL OF RIGID PAVEMENT","CY",{"$f":"IF(Tool!$D$46=\"No Errors\",Roadway!O23,0)","v":0},null,{"$f":"E23+F23","v":0},{"$f":"VLOOKUP($B23,'AUP Data'!$A:$AF,25,0)","v":45.23},{"$f":"IF(G23<>\"\",G23*H23,\"\")","v":0}]
[0,"202-08.15","REMOVAL OF CURB AND GUTTER","LF",null,null,{"$f":"F24","v":0},29.94,0]
[0,"202-08.28","REMOVAL OF MEDIAN BARRIER","LF",null,null,0,85,0]
[0,"411-12.01","SCORING SHOULDERS (CONTINUOUS) (16IN WIDTH)","L.M.",null,null,0,1004.48,0]
[0,"411-12.02","SCORING SHOULDERS (NON-CONTINUOUS) (16IN WIDTH)","L.M.",null,null,0,1029.56,0]
[0,"411-12.03","SCORING FOR RUMBLE STRIPE (NON-CONTINUOUS) (8IN WIDTH)","L.M.",null,null,0,911.15,0]
[0,"411-12.04","SCORING FOR RUMBLE STRIPE (NON-CONTINUOUS) (4IN WIDTH)","L.M.",null,null,0,1078.8399999999999,0]
[0,"411-12.05","Scoring For Centerline Rumble (4\" Width)","L.M.",null,null,0,2976.63,0]
[0,"415-01.02","COLD PLANING BITUMINOUS PAVEMENT","SY",{"$f":"IF(Tool!$D$46=\"No Errors\",Roadway!O21,0)","v":0},null,{"$f":"E31+F31","v":0},{"$f":"VLOOKUP($B31,'AUP Data'!$A:$AF,25,0)","v":9.6},0]
[0,"415-01.03","COLD PLANING BITUMINOUS PAVEMENT","CY",null,null,{"$f":"E32+F32","v":0},63.24,0]
[1,null,null,null,null,null,null,"PAVEMENT REMOVAL TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(SUM(I22:I32),-2)<0,0,ROUNDUP(SUM(I22:I32),-2))","v":0}]
[1]
[1,"Asphalt Roads"]
[{"$f":"IF(G36>0,1,0)","v":0},"203-06","WATER","MG",null,null,{"$f":"F36","v":0},12.01,{"$f":"IF(G36<>\"\",G36*H36,\"\")","v":0}]
[{"$f":"IF(G37>0,1,0)","v":0},"303-01","MINERAL AGGREGATE, TYPE A BASE, GRADING D","TON",{"$f":"IF(Tool!$D$46=\"No Errors\",(Roadway!O17+Median!M13+Drainage!L19+Roadway!S14),0)","v":0},null,{"$f":"E37+F37","v":0},{"$f":"VLOOKUP($B37,'AUP Data'!$A:$AF,25,0)","v":40.6},{"$f":"G37*H37","v":0}]
[{"$f":"IF(G38>0,1,0)","v":0},"307-01.01","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING A","TON",null,null,{"$f":"F38","v":0},125.89,0]
[0,"307-01.02","ASPHALT CEMENT (PG64-22) (BPMB-HM) GRADING A-S","TON",null,null,0,750.3,0]
[0,"307-01.03","AGGREGATE (BPMB-HM) GRADING A-S MIX","TON",null,null,0,54.15,0]
[0,"307-01.07","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING B-M","TON",null,null,0,90,0]
[0,"307-01.08","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING B-M2","TON",null,null,0,101.83,0]
[0,"307-01.15","ASC MIX (PG64-22) (BPMLC-HM) GRADING CS","TON",null,null,0,128.71,0]
[0,"307-(01, 02, 03).01","ASPHALT CONCRETE MIX (All Grades) (BPMB-HM) GRADING A","TON",{"$f":"IF(Tool!$D$46=\"No Errors\",Roadway!O11,0)","v":0},null,{"$f":"E44+F44","v":0},{"$f":"VLOOKUP($B44,'AUP Data'!$A:$AF,25,0)","v":124.26208009204254},0]
[0,"307-01.(20 & 21 & 22)","AGGREGATE (BPMB-HM) GRADING A-S MIX","TON",{"$f":"IF(Tool!$D$46=\"No Errors\",Roadway!O12,0)","v":0},null,{"$f":"E45+F45","v":0},{"$f":"VLOOKUP($B45,'AUP Data'!$A:$AF,25,0)","v":124.26784422722803},0]
[0,"307-(01 & 02 & 03).08","ASPHALT CONCRETE MIX (ALL GRADES) (BPMB-HM) GRADING B-M2","TON",{"$f":"IF(Tool!$D$46=\"No Errors\",Roadway!O10+Median!M10+Roadway!S11,0)","v":0},null,{"$f":"E46+F46","v":0},{"$f":"VLOOKUP($B46,'AUP Data'!$A:$AF,25,0)","v":130.98531901543353},0]
[0,"307-03.01","ASPHALT CONCRETE MIX (PG76-22) (BPMB-HM) GRADING A","TON",null,null,{"$f":"F47","v":0},84.24,0]
[0,"307-03.02","PERF. GRADE ASPH. CEMENT(PG76-22)GRADING AS","TON",null,null,0,942.31,0]
[0,"307-03.03","AGGREGATE(BPMB-HM) GRADING AS","TON",null,null,0,67.48,0]
[0,"307-03.08","ASPHALT CONCRETE MIX (PG76-22) (BPMB-HM) GRADING B-M2","TON",null,null,0,82.68,0]
[0,"307-03.10","ASPHALT CONC MIX (PG76-22)(BPMB-HM) GR CS","TON",null,null,0,183.12,0]
[0,"309-01.01","MINERAL AGGREGATE (A-CBC)","TON",null,null,0,19.649999999999999,0]
[0,"309-01.02","PORTLAND CEMENT (A-CBC)","TON",null,null,0,283.82,0]
[0,"309-02","BITUMINOUS MATERIAL (A-CBC)","TON",null,null,0,743.04,0]
[0,"402-01","BITUMINOUS MATERIAL FOR PRIME COAT (PC)","TON",{"$f":"IF(Tool!$D$46=\"No Errors\",Roadway!O15+Median!M11+Roadway!S12,0)","v":0},null,{"$f":"E55+F55","v":0},{"$f":"VLOOKUP($B55,'AUP Data'!$A:$AF,25,0)","v":978.2},0]
[0,"402-02","AGGREGATE FOR COVER MATERIAL (PC)","TON",{"$f":"IF(Tool!$D$46=\"No Errors\",Roadway!O16+Median!M12+Roadway!S13,0)","v":0},null,{"$f":"E56+F56","v":0},{"$f":"VLOOKUP($B56,'AUP Data'!$A:$AF,25,0)","v":75.900000000000006},0]
[0,"403-01","BITUMINOUS MATERIAL FOR TACK COAT (TC)","TON",{"$f":"IF(Tool!$D$46=\"No Errors\",Roadway!O14+Median!M9+Roadway!S10,0)","v":0},null,{"$f":"E57+F57","v":0},{"$f":"VLOOKUP($B57,'AUP Data'!$A:$AF,25,0)","v":974.85},0]
[0,"404-01.01","BITUMINOUS MATERIAL (DBST)","TON",null,null,{"$f":"F58","v":0},1575,0]
[0,"404-01.02","MINERAL AGGREGATE (DBST)","TON",null,null,0,61.85,0]
[0,"405-01.01","BITUMINOUS MATERIAL (BSC)","TON",null,null,0,711.13,0]
[0,"405-01.02","MINERAL AGGREGATE (BSC)","TON",null,null,0,46.39,0]
[0,"406-04.02","High Friction Surface Treatment","SY",null,null,0,37.130000000000003,0]
[0,"406-04.03","High Friction Surface Treatment (Single Lift)","SY",null,null,0,44.13,0]
[0,"406-04.04","High Friction Surface Treatment (Double Lift)","SY",null,null,0,68.87,0]
[0,"407-02.11","Removal & Disposal Existing Asphalt Pavement","CY",null,null,0,10,0]
[0,"407-02.12","Removal & Disposal Existing Asphalt Pavement","TON",null,null,0,17.760000000000002,0]
[0,"407-02.13","Removal & Disposal Existing Asphalt Pavement","SY",null,null,0,4.3099999999999996,0]
[0,"407-20.05","SAW CUTTING ASPHALT PAVEMENT","LS",null,null,0,3.1,0]
[0,"411-01.07","ACS MIX (PG64-22) GRADING E SHOULDER","TON",{"$f":"IF(Tool!$D$46=\"No Errors\",Median!M8+Roadway!S9,0)","v":0},null,{"$f":"E69+F69","v":0},{"$f":"VLOOKUP($B69,'AUP Data'!$A:$AF,25,0)","v":128.63},0]
[0,"411-01.10","ACS MIX(PG64-22) GRADING D","TON",null,null,{"$f":"F70","v":0},134.28,0]
[0,"411-(01 & 02 & 03).10","ACS MIX(ALL GRADES) GRADING D","TON",{"$f":"IF(Tool!$D$46=\"No Errors\",Roadway!O9,0)","v":0},null,{"$f":"E71+F71","v":0},{"$f":"VLOOKUP($B71,'AUP Data'!$A:$AF,25,0)","v":146.95076747266484},0]
[0,"411-03.05","ACS Mix (PG64-22) Thing Lift CS Asphalt","SY",null,null,{"$f":"F72","v":0},3.1,0]
[0,"411-03.07","ASC Mix (PG64-22) Thin Lift CS Asphalt","TON",null,null,0,134.63,0]
[0,"411-03.08","ACS Mix (PG70-22) Thin Lift CS Asphalt","TON",null,null,0,96.75,0]
[0,"411-03.09","ACS Mix (PG76-22) Thin Lift CS Asphalt","TON",null,null,0,88.03,0]
[0,"411-03.10","ACS MIX(PG76-22) GRADING D","TON",null,null,0,144.91999999999999,0]
[0,"411-03.12","ACS MIX(PG64-22) THIN LIFT D ASPHALT","TON",null,null,0,125.77,0]
[0,"411-03.13","ACS Mix (PG70-22) Thin Lift D Asphalt","TON",null,null,0,145.63,0]
[0,"411-03.14","ACS Mix (PG76-22) Thin Lift D Asphalt","TON",null,null,0,100.86,0]
[0,"411-03.23","ASP Cem(PG76-22) For OGFC Mix","TON",null,null,0,167.47,0]
[0,"411-03.16","Aggregate for OGFC Mix","TON",null,null,0,54.05,0]
[0,"411-04","Crack Sealant","LB",null,null,0,1.61,0]
[0,"411-04.10","ACS Mix (PG82-22) Grading D","TON",null,null,0,175.44,0]
[0,"414-03.01","Emulsified Asphalt for Micro-Surfacing","TON",null,null,0,862.4,0]
[0,"414-03.02","Aggregate for Micro Surfacing","TON",null,null,0,99.36,0]
[0,"414-03.03","Micro Surfacing","SY",null,null,0,3.97,0]
[1,null,null,null,null,null,null,"PAVING TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(SUM(I36:I86),-2)<0,0,ROUNDUP(SUM(I36:I86),-2))","v":0}]
[1]
[1,"Concrete Roads"]
[{"$f":"IF(G90>0,1,0)","v":0},"303-01","MINERAL AGGREGATE, TYPE A BASE, GRADING D","TON",null,null,{"$f":"F90","v":0},21.76,{"$f":"IF(G90<>\"\",G90*H90,\"\")","v":0}]
[0,"313-03","TREATED PERMEABLE BASE","SY",{"$f":"IF(Tool!$D$46=\"No Errors\",Roadway!O19+Roadway!S16,0)","v":0},null,{"$f":"E91+F91","v":0},{"$f":"VLOOKUP($B91,'AUP Data'!$A:$AF,25,0)","v":32.69},0]
[0,"501-01.01","PORTLAND CEMENT CONCRETE PAVEMENT (PLAIN) 8\"","SY",null,null,{"$f":"F92","v":0},68.86,0]
[0,"501-01.02","PORTLAND CEMENT CONCRETE PVMT 9\"","SY",null,null,{"$f":"F93","v":0},85,0]
[0,"501-01.03","PORTLAND CEMENT CONCRETE PAVEMENT (PLAIN) 10\"","SY",{"$f":"IF(Tool!$D$46=\"No Errors\",Roadway!O18+Roadway!S15,0)","v":0},null,{"$f":"E94+F94","v":0},{"$f":"VLOOKUP($B94,'AUP Data'!$A:$AF,25,0)","v":155.51},0]
[0,"501-01.04","PORTLAND CEMENT CONCRETE PVMT 11\"","SY",null,null,{"$f":"F95","v":0},56.82,0]
[0,"502-03.01","CEMENT GROUTING","CF",null,null,0,11.58,0]
[0,"502-03.13","CONCRETE PAVEMENT REMOVAL","SY",null,null,0,18.82,0]
[0,"502-04.01","SAWING CONCRETE PAVEMENT (FULL DEPTH)","LF",null,null,0,16.98,0]
[0,"502-04.03","TRANSVERSE TIE-BARS","EACH",null,null,0,25.66,0]
[0,"502-08.01","RESEALING JOINTS (HOT POURED ELASTIC)","LF",null,null,0,2.9,0]
[0,"502-08.02","RESEALING JOINTS (SILICONE SEALANT)","LF",null,null,0,6.66,0]
[0,"503-01.01","MILLING CONCRETE PAVEMENT","SY",null,null,0,7.34,0]
[0,"504-01","CRACKING & SEATING CONCRETE PAVEMENT","SY",null,null,0,1.9,0]
[0,"604-01.01","CLASS A CONCRETE (ROADWAY)","CY",{"$f":"IF(Tool!$D$46=\"No Errors\",Roadway!S19,0)","v":0},null,{"$f":"E104+F104","v":0},{"$f":"VLOOKUP($B104,'AUP Data'!$A:$AF,25,0)","v":1333.8},0]
[0,"604-01.02","STEEL BAR REINFORCEMENT (ROADWAY)","LB",null,null,{"$f":"F105","v":0},1.65,0]
[1,null,null,null,null,null,null,"CONCRETE RAMPS AND ROADWAYS TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(SUM(I90:I105),-2)<0,0,ROUNDUP(SUM(I90:I105),-2))","v":0}]
[1]
[1,"Drainage"]
[{"$f":"IF(G109>0,1,0)","v":0},"202-01.13","REMOVAL OF PIPE","LF",null,null,{"$f":"F109","v":0},68.95281501340483,{"$f":"IF(G109<>\"\",G109*H109,\"\")","v":0}]
[{"$f":"IF(G110>0,1,0)","v":0},"209-01.31","TEMPORARY MULCH FILTER BERM","CY",null,null,0,16.38,{"$f":"IF(G110<>\"\",G110*H110,\"\")","v":0}]
[0,"209-02.03","8\" TEMPORARY SLOPE DRAIN","LF",null,null,0,27.109766637856527,0]
[0,"209-02.04","10\" TEMPORARY SLOPE DRAIN","LF",null,null,0,54.5,0]
[0,"209-02.05","12\" TEMPORARY SLOPE DRAIN","LF",null,null,0,38.692307692307693,0]
[0,"209-02.06","15\" TEMPORARY SLOPE DRAIN","LF",null,null,0,20,0]
[0,"209-02.07","18\" TEMPORARY SLOPE DRAIN","LF",null,null,0,32.86389796351294,0]
[0,"209-03","Check Dams","SF",null,null,0,8.5,0]
[0,"209-03.20","FILTER SOCK (8 INCH)","LF",null,null,0,4.0578680203045687,0]
[0,"209-03.21","FILTER SOCK (12 INCH)","LF",null,null,0,12.215841584158415,0]
[0,"209-03.22","FILTER SOCK (18 INCH)","LF",null,null,0,12.980655737704918,0]
[0,"209-03.23","FILTER SOCK (24 INCH)","LF",null,null,0,5.7022072788119642,0]
[0,"209-05","SEDIMENT REMOVAL","CY",null,null,0,12.69,0]
[0,"209-06","Baled Hay or Straw Erosion Checks","BALE",null,null,0,5,0]
[0,"209-06.01","Permeable Plastic Ditch Berm","LF",null,null,0,8,0]
[0,"209-06.02","12\" DIA COIR LOG (FOR LOW CHANNEL FLOW)","LF",null,null,0,12.36,0]
[0,"209-06.03","16\" Dia Coir Log (Description)","LF",null,null,0,16.690000000000001,0]
[0,"209-06.05","BALED HAY OR STRAW","BALE",null,null,0,10,0]
[0,"209-06.13","20\" Dia Coir Log (Description)","LF",null,null,0,40,0]
[0,"209-08.02","TEMPORARY SILT FENCE (WITH BACKING)","LF",null,null,0,5.6764193056610415,0]
[0,"209-08.03","TEMPORARY SILT FENCE (WITHOUT BACKING)","LF",null,null,0,2.3295158433646885,0]
[0,"209-08.05","ENHANCED SILT FENCE CHECK (V-DITCH)","EACH",null,null,0,459.99,0]
[0,"209-08.07","ROCK CHECK DAM PER","EACH",null,null,0,580.1677384351799,0]
[0,"209-08.08","ENHANCED ROCK CHECK DAM","EACH",null,null,0,942.34378868729982,0]
[0,"209-09.01","SANDBAGS","BAG",null,null,0,8.7669747938751481,0]
[0,"209-09.02","TEMPORARY SEDIMENT FILTER BAG (14'6\" X 2'0\" X 13'3\")","Bag",null,null,0,348.15,0]
[0,"209-09.03","SEDIMENT FILTER BAG (15' X 15')","EACH",null,null,0,965.96,0]
[0,"209-09.04","SEDIMENT FILTER BAG(15' X 10')","EACH",null,null,0,1533.25,0]
[0,"209-09.20","Polymer Flocculent","LB",null,null,0,8,0]
[0,"209-09.21","POLYACRYLAMIDE GEL LOGS","EA",null,null,0,184.79,0]
[0,"209-09.22","POLYACRYLAMIDE POWDER","LB",null,null,0,12.08,0]
[0,"209-09.23","POLYACRYLAMIDE LIQUID","LB",null,null,0,55.01,0]
[0,"209-09.24","JUTE MESH FABRIC","SY",null,null,{"$f":"F141","v":0},1.65,0]
[0,"209-09.40","CURB INLET PROTECTION (TYPE 1)","EACH",null,null,0,492.88,0]
[0,"209-09.41","CURB INLET PROTECTION (TYPE 2)","EACH",null,null,0,507.03125,0]
[0,"209-09.42","CURB INLET PROTECTION (TYPE 3)","EACH",null,null,0,270.83,0]
[0,"209-09.43","CURB INLET PROTECTION (TYPE 4)","EACH",null,null,0,259.62567035670355,0]
[0,"209-10.01","TEMPORARY DEWATERING STRUCTURE","CY",null,null,0,44.333333333333336,0]
[0,"209-10.02","8IN SKIMMER W/6IN HEAD","EACH",null,null,0,2500,0]
[0,"209-10.20","TEMPORARY SEDIMENT TRAP","CY",null,null,0,20.368857689853222,0]
[0,"209-11.01","SEDIMENT BASIN RISER (24\")","EACH",null,null,0,7982.3,0]
[0,"209-11.20","Sediment Basin Baffles","LF",null,null,0,32.520000000000003,0]
[0,"209-13.04","TURBIDITY CURTAIN(DESCRIPTION)","LF",null,null,0,35.477647058823528,0]
[0,"209-20.03","POLYETHYLENE SHEETING (6 MIL. MINIMUM)","SY",null,null,0,5.3434600627833966,0]
[0,"209-20.04","POLYETHYLENE SHEETING (10 MIL.)","SY",null,null,0,2.8453267162944584,0]
[0,"209-40.30","CATCH BASIN PROTECTION (TYPE A)","EACH",null,null,0,614.55500000000006,0]
[0,"209-40.31","CATCH BASIN PROTECTION (TYPE B)","EACH",null,null,0,616.66999999999996,0]
[0,"209-40.32","Catch Basin Protection (Type C)","EACH",null,null,0,501.41,0]
[0,"209-40.33","CATCH BASIN PROTECTION (TYPE D)","EACH",null,null,0,410.06556497175137,0]
[0,"209-40.34","CATCH BASIN PROTECTION (TYPE E)","EACH",null,null,0,385,0]
[0,"209-40.41","CATCH BASIN FILTER ASSEMBLY(TYPE 1)","EACH",null,null,0,738.54215909090908,0]
[{"$f":"IF(G160>0,1,0)","v":0},"209-40.42","CATCH BASIN FILTER ASSEMBLY(TYPE 2)","EACH",null,null,0,919.41714285714295,0]
[0,"209-40.43","CATCH BASIN FILTER ASSEMBLY(TYPE 3)","EACH",null,null,0,877.35294117647061,0]
[0,"209-40.44","CATCH BASIN FILTER ASSEMBLY(TYPE 4)","EACH",null,null,0,879.59,0]
[0,"209-40.45","CATCH BASIN FILTER ASSEMBLY(TYPE 5)","EACH",null,null,0,1000.1392857142857,{"$f":"IF(G163<>\"\",G163*H163,\"\")","v":0}]
[0,"209-40.46","CATCH BASIN FILTER ASSEMBLY(TYPE 6)","EACH",null,null,0,699.62192825112106,0]
[0,"209-40.47","CATCH BASIN FILTER ASSEMBLY(TYPE 7)","EACH",null,null,0,870.41846153846154,0]
[0,"209-40.48","CATCH BASIN FILTER ASSEMBLY(TYPE 8)","EACH",null,null,0,951.78,0]
[0,"209-40.50","CATCH BASIN FILTER ASSEMBLY(TYPE 10)","EACH",null,null,0,951.78,0]
[0,"209-65.01","TEMPORARY STREAM DIVERSION (DESCRIPTION)","LS",null,null,0,84000,0]
[0,"209-65.02","TEMPORARY STREAM DIVERSION (DESCRIPTION)","LS",null,null,0,15000,0]
[0,"209-65.03","TEMPORARY DIVERSION CHANNEL","LF",null,null,0,16.47,0]
[0,"209-65.04","TEMPORARY IN STREAM DIVERSION","LF",null,null,0,75.029518900343646,0]
[0,"209-65.14","TEMPORARY STREAM DIVERSION","LS",null,null,0,45000,0]
[0,"606-24.10","Sheet Piles","SF",null,null,{"$f":"F173","v":0},76.16,0]
[0,"606-24.12","TEMPORARY SHEET PILES","SF",null,null,0,32.435897435897438,0]
[0,"607-01.02","12\" Concrete Pipe Culvert (Class III)","LF",null,null,0,129.21,0]
[0,"607-02.02","15\" CONCRETE PIPE CULVERT(CLASS III)","LF",null,null,0,163.18181818181819,0]
[0,"607-03.02","18\" CONCRETE PIPE CULVERT (CLASS III)","LF",null,null,0,104.79779903131487,0]
[0,"607-03.30","18\" PIPE CULVERT","LF",null,null,0,145.54553383102262,0]
[0,"607-05.02","24\" CONCRETE PIPE CULVERT (CLASS III)","LF",{"$f":"IF(Tool!$D$46=\"No Errors\",Median!M15+Drainage!L13,0)","v":0},null,{"$f":"E179+F179","v":0},{"$f":"VLOOKUP($B179,'AUP Data'!$A:$AF,25,0)","v":137.55000000000001},0]
[0,"607-05.30","24\" PIPE CULVERT","LF",null,null,{"$f":"F180","v":0},208.48893877551018,0]
[0,"607-06.02","30\" CONCRETE PIPE CULVERT (CLASS III)","LF",null,null,0,138.15390211286442,0]
[0,"607-06.30","30\" PIPE CULVERT","LF",null,null,0,251.61714505381855,0]
[0,"607-07.02","36\" CONCRETE PIPE CULVERT (CLASS III)","LF",null,null,0,217.47581836418345,0]
[0,"607-07.30","36\" PIPE CULVERT","LF",null,null,0,182.0408163265306,0]
[0,"607-08.02","42\" CONCRETE PIPE CULVERT (CLASS III)","LF",null,null,0,257.99786081270429,0]
[0,"607-08.30","42\" PIPE CULVERT","LF",null,null,0,215,0]
[0,"607-09.02","48\" CONCRETE PIPE CULVERT (CLASS III)","LF",null,null,0,336.66132901134523,0]
[0,"607-09.30","48\" PIPE CULVERT","LF",null,null,0,281.46643109540634,0]
[0,"607-10.02","54\" CONCRETE PIPE CULVERT (CLASS III)","LF",null,null,0,505,0]
[0,"607-10.30","54\" PIPE CULVERT","LF",null,null,0,215,0]
[0,"607-11.03","60\" CONCRETE PIPE CULVERT (CLASS III)","LF",null,null,0,488.75438016528926,0]
[0,"607-16.01","23\"X 14\" HORIZONTAL OVAL CONCRETE PIPE CULVERT","LF",null,null,0,107.69230769230769,0]
[0,"607-16.02","30\"X 19\" HORIZONTAL OVAL CONCRETE PIPE CULVERT","LF",null,null,0,322.69,0]
[0,"607-16.04","38\"X 24\" HORIZONTAL OVAL CONCRETE PIPE CULVERT","LF",null,null,0,305.16000000000003,0]
[0,"607-16.05","45\"X 29\" HORIZONTAL OVAL CONCRETE PIPE CULVERT (CLASS__)","LF",null,null,0,455.93,0]
[0,"607-16.06","45\"X 29\" HORIZONTAL OVAL CONCRETE PIPE CULVERT","LF",null,null,0,227.59,0]
[0,"607-16.07","49\"X 32\" HORIZONTAL OVAL CONCRETE PIPE CULVERT","LF",null,null,0,126.71,0]
[0,"607-16.08","53\"X 34\" HORIZONTAL OVAL CONCRETE PIPE CULVERT","LF",null,null,0,137.97,0]
[0,"607-16.09","60\"X 38\" HORIZONTAL OVAL CONCRETE PIPE CULVERT","LF",null,null,0,165.54,0]
[0,"607-16.10","68\"X 43\"HORIZONTAL OVAL CNC PIPE CULVERT","LF",null,null,0,146.35,0]
[0,"607-16.11","76\"X 48\" HORIZONTAL OVAL CONCRETE PIPE CULVERT","LF",null,null,0,220,0]
[0,"607-37.01","15\" CORRUGATED METAL PIPE CULVERT","LF",null,null,0,32.130000000000003,0]
[0,"607-37.02","18\" CORRUGATED METAL PIPE CULVERT","LF",null,null,0,122.1,0]
[0,"607-37.03","24\" CORRUGATED METAL PIPE CULVERT","LF",null,null,0,301.83999999999997,0]
[0,"607-37.04","30\" CORRUGATED METAL PIPE CULVERT","LF",null,null,0,126.61,0]
[0,"607-37.05","36\" CORRUGATED METAL PIPE CULVERT","LF",null,null,0,65.23,0]
[0,"607-37.06","42\" CORRUGATED METAL PIPE CULVERT","LF",null,null,0,70.78,0]
[0,"607-37.07","48\" CORRUGATED METAL PIPE CULVERT","LF",null,null,0,190,0]
[0,"607-37.08","54\" CORRUGATED METAL PIPE CULVERT","LF",null,null,0,80,0]
[0,"607-37.09","60\" CORRUGATED METAL PIPE CULVERT","LF",null,null,0,97,0]
[0,"607-37.11","72\" CORRUGATED METAL PIPE CULVERT","LF",null,null,0,150,0]
[0,"607-37.12","78\" CORRUGATED METAL PIPE CULVERT","LF",null,null,{"$f":"F212","v":0},80,0]
[0,"607-37.13","84\" CORRUGATED METAL PIPE CULVERT","LF",null,null,0,218,0]
[0,"607-39.01","15\" PIPE CULVERT (SIDE DRAIN)","LF",null,null,0,122,0]
[0,"607-39.02","18\" PIPE CULVERT (SIDE DRAIN)","LF",null,null,0,73.972166617603776,0]
[0,"607-39.03","24\" PIPE CULVERT (SIDE DRAIN)","LF",null,null,0,86.765199161425571,0]
[0,"607-39.04","30\" PIPE CULVERT (SIDE DRAIN)","LF",null,null,0,120.62871287128714,0]
[0,"607-39.05","36\" PIPE CULVERT (SIDE DRAIN)","LF",null,null,0,112.37696335078535,0]
[0,"607-39.06","42\" PIPE CULVERT (SIDE DRAIN)","LF",null,null,0,155,0]
[0,"607-39.07","48\" PIPE CULVERT (SIDE DRAIN)","LF",null,null,0,95,0]
[0,"607-39.08","54\" Pipe Culvert (Side Drain)","LF",null,null,0,118.86,0]
[0,"607-39.09","60\" Pipe Culvert (Side Drain)","LF",null,null,0,468.68,0]
[0,"607-39.10","66\" Pipe Culvert (Side Drain)","LF",null,null,0,750,0]
[{"$f":"IF(G224>0,1,0)","v":0},"607-45.02","18\" SLOTTED DRAIN PIPE","LF",null,null,0,279,0]
[0,"607-57.01","Reinforced Concrete Pipe Arch (22\" x 13\")","LF",null,null,0,145.85,0]
[0,"607-57.02","Reinforced Concrete Pipe Arch (29\" x 18\")","LF",null,null,0,101.95737704918034,0]
[0,"607-57.07","Reinforced Concrete Pipe Arch (65\" x 40\")","LF",null,null,0,235,0]
[0,"610-07.03","18\" PIPE DRAIN (BRIDGE DRAIN)","LF",null,null,0,113.76,0]
[0,"611-01.02","MANHOLES, > 4' - 8' DEPTH","EA",null,null,0,7707.001923076923,0]
[0,"611-01.03","MANHOLES, > 8' - 12' DEPTH","EA",null,null,0,9339.2000000000007,0]
[0,"611-01.04","MANHOLES, > 12' - 16' DEPTH","EA",null,null,0,17135,0]
[0,"611-01.05","MANHOLES, > 16' - 20' DEPTH","EA",null,null,0,50000,0]
[0,"611-02.10","JUNCTION BOX, TYPE 1","EA",null,null,0,5176.086956521739,0]
[0,"611-02.11","JUNCTION BOX, TYPE 2","EA",null,null,0,6536.164615384615,0]
[0,"611-02.12","JUNCTION BOX, TYPE 3","EA",null,null,0,11433.333333333334,0]
[0,"611-02.13","JUNCTION BOX, TYPE 4","EA",null,null,0,17000,0]
[0,"611-02.14","JUNCTION BOX, TYPE 5","EA",null,null,0,56500,0]
[0,"611-07.01","CLASS A CONCRETE (PIPE ENDWALLS)","CY",{"$f":"IF(Tool!$D$46=\"No Errors\",Drainage!L14,0)","v":0},null,{"$f":"E238+F238","v":0},{"$f":"VLOOKUP($B238,'AUP Data'!$A:$AF,25,0)","v":2156.1799999999998},0]
[0,"611-07.02","STEEL BAR REINFORCEMENT (PIPE ENDWALLS)","LB",{"$f":"IF(Tool!$D$46=\"No Errors\",Drainage!L15,0)","v":0},null,{"$f":"E239+F239","v":0},{"$f":"VLOOKUP($B239,'AUP Data'!$A:$AF,25,0)","v":4.08},0]
[0,"611-07.03","STRUCTURAL STEEL (PIPE ENDWALLS)","LB",null,null,{"$f":"F240","v":0},4.7,0]
[0,"611-07.51","15IN ENDWALL (CROSS DRAIN) 3:1","EA",null,null,0,1937.27,0]
[0,"611-07.54","18IN ENDWALL (CROSS DRAIN) 3:1","EA",null,null,0,2471.8977333333337,0]
[0,"611-07.57","24IN ENDWALL (CROSS DRAIN) 3:1","EA",null,null,0,3432.2157692307692,0]
[0,"611-07.60","30IN ENDWALL (CROSS DRAIN) 3:1","EA",null,null,0,4590.473,0]
[0,"611-07.63","36IN ENDWALL (CROSS DRAIN) 3:1","EA",null,null,0,7415,0]
[0,"611-07.66","42IN ENDWALL (CROSS DRAIN) 3:1","EA",null,null,0,7322.5,0]
[0,"611-07.69","48IN ENDWALL (CROSS DRAIN) 3:1","EA",null,null,0,10212.92,0]
[0,"611-09.01","ADJUSTMENT OF EXISTING CATCHBASIN","EA",null,null,0,1758.3118840579709,0]
[0,"611-09.02","REWORK CATCHBASIN","EA",null,null,0,2630,0]
[0,"611-09.03","CAPPING EXISTING CATCHBASIN","EA",null,null,0,2500,0]
[0,"611-10.01","CATCH BASINS, TYPE 10, 0' - 4' DEPTH","EA",null,null,0,6000,0]
[0,"611-10.02","CATCH BASINS, TYPE 10, > 4' - 8' DEPTH","EA",null,null,0,6167.17,0]
[0,"611-12.01","CATCH BASINS, TYPE 12, 0' - 4' DEPTH","EA",null,null,0,5592.7092537313438,0]
[0,"611-12.02","CATCH BASINS, TYPE 12, > 4' - 8' DEPTH","EA",{"$f":"IF(Tool!$D$46=\"No Errors\",Median!M17+Drainage!L10,0)","v":0},null,{"$f":"E254+F254","v":0},{"$f":"VLOOKUP($B254,'AUP Data'!$A:$AF,25,0)","v":8113.47},0]
[0,"611-12.03","CATCH BASINS, TYPE 12, > 8' - 12' DEPTH","EA",null,null,{"$f":"F255","v":0},9971.7607272727273,0]
[0,"611-12.04","CATCH BASINS, TYPE 12, > 12' - 16' DEPTH","EA",null,null,{"$f":"F256","v":0},17980,0]
[0,"611-12.05","CATCH BASINS, TYPE 12, > 16' - 20' DEPTH","EA",null,null,{"$f":"F257","v":0},22825.78,{"$f":"IF(G257<>\"\",G257*H257,\"\")","v":0}]
[0,"611-12.06","Catch Basins, Type 12, > 20' - 24' Depth","EA",null,null,{"$f":"F258","v":0},17407.89,0]
[0,"611-14.01","CATCH BASINS, TYPE 14, 0' - 4' DEPTH","EA",null,null,{"$f":"F259","v":0},9986.753333333334,0]
[0,"611-14.02","CATCH BASINS, TYPE 14, > 4' - 8' DEPTH","EA",{"$f":"IF(Tool!$D$46=\"No Errors\",Drainage!L11,0)","v":0},null,{"$f":"E260+F260","v":0},{"$f":"VLOOKUP($B260,'AUP Data'!$A:$AF,25,0)","v":11628.28},0]
[0,"611-14.03","CATCH BASINS, TYPE 14, > 8' - 12' DEPTH","EA",null,null,{"$f":"F261","v":0},17428.599999999999,0]
[0,"611-14.04","CATCH BASINS, TYPE 14, > 12' - 16' DEPTH","EA",null,null,0,19000,0]
[0,"611-14.05","CATCH BASINS, TYPE 14, > 16' - 20' DEPTH","EA",null,null,0,28000,0]
[0,"611-16.01","Catch Basins, Type 16, > 0' - 4' Depth","EA",null,null,0,5573.02,0]
[0,"611-16.02","CATCH BASINS, TYPE 16, > 4' - 8' DEPTH","EA",null,null,0,10868.75,0]
[0,"611-16.03","Catch Basins, Type 16, > 8' - 12' Depth","EA",null,null,0,13900,0]
[0,"611-16.04","Catch Basins, Type 16, > 12' - 16' Depth","EA",null,null,0,21120,0]
[0,"611-25.01","CATCH BASINS, TYPE 25, 0' - 4' DEPTH","EA",null,null,0,7023.99,0]
[0,"611-25.02","CATCH BASINS, TYPE 25, > 4' - 8' DEPTH","EA",null,null,0,7703.54,0]
[0,"611-25.03","CATCH BASINS, TYPE 25, > 8' - 12' DEPTH","EA",null,null,0,11841.86,0]
[0,"611-25.04","Catch Basins, Type 25, > 12' - 16' Depth","EA",null,null,0,14860.5,0]
[0,"611-26.01","Catch Basins, Type 26, > 0' - 4' Depth","EA",null,null,0,9571.89,0]
[0,"611-26.02","CATCH BASINS, TYPE 26, > 4' - 8' DEPTH","EA",null,null,0,12512.65,0]
[0,"611-26.03","Catch Basin, Type 26, > 8' - 12' Depth","EA",null,null,0,5294.47,0]
[0,"611-26.04","Catch Basin, Type 26, > 12' - 16' Depth","EA",null,null,0,5294.47,0]
[0,"611-28.01","Catch Basin, Type 28, > 0' - 4' Depth","EA",null,null,0,5294.47,0]
[0,"611-28.02","Catch Basin, Type 28, > 4' - 8' Depth","EA",null,null,0,5294.47,0]
[0,"611-28.03","Catch Basin, Type 28, > 8' - 12' Depth","EA",null,null,0,5294.47,0]
[0,"611-28.04","Catch Basin, Type 28, > 12' - 16' Depth","EA",null,null,0,5294.47,0]
[0,"611-31.01","Catch Basins, Type 31, > 0' - 4' Depth","EA",null,null,0,5294.47,0]
[0,"611-31.02","CATCH BASINS, TYPE 31, > 4' - 8' DEPTH","EA",null,null,0,10000,0]
[0,"611-31.03","CATCH BASINS, TYPE 31, > 8' - 12' DEPTH","EA",null,null,0,15000,0]
[0,"611-31.04","CATCH BASINS, TYPE 31, > 12' - 16' DEPTH","EA",null,null,0,12762.04,0]
[0,"611-32.01","Catch Basins, Type 32, > 0' - 4' Depth","EA",null,null,0,4678.1899999999996,0]
[0,"611-32.02","Catch Basins, Type 32, > 4' - 6' Depth","EA",null,null,0,3304.07,0]
[0,"611-38.02","CATCH BASINS, TYPE 38, > 4' - 8' DEPTH","EA",null,null,0,6369.1404999999995,0]
[0,"611-39.01","CATCH BASINS, TYPE 39, 0' - 4' DEPTH","EA",null,null,0,6483.6012499999997,0]
[{"$f":"IF(G288>0,1,0)","v":0},"611-39.02","CATCH BASINS, TYPE 39, > 4' - 8' DEPTH","EA",null,null,0,10266.666666666666,0]
[0,"611-39.03","CATCH BASINS, TYPE 39, > 8' - 12' DEPTH","EA",null,null,0,14700,0]
[0,"611-39.04","CATCH BASINS, TYPE 39, > 12' - 16' DEPTH","EA",null,null,0,14800,0]
[0,"611-39.05","CATCH BASINS, TYPE 39, > 16' - 20' DEPTH","EA",null,null,0,14000,0]
[0,"611-40.01","CATCH BASINS, TYPE 40, 0' - 4' DEPTH","EA",null,null,0,12600,0]
[0,"611-40.02","CATCH BASINS, TYPE 40, > 4' - 8' DEPTH","EA",null,null,0,10000,0]
[0,"611-40.03","Catch Basins, Type 40, > 8' - 12' Depth","EA",null,null,0,6077.01,0]
[0,"611-40.04","Catch Basins, Type 40, > 12' - 16' Depth","EA",null,null,0,6077.01,0]
[0,"611-41.01","CATCH BASINS, TYPE 41, 0' - 4' DEPTH","EA",null,null,0,5137.5,0]
[0,"611-41.02","CATCH BASINS, TYPE 41, > 4' - 8' DEPTH","EA",null,null,0,12674.84,0]
[0,"611-41.03","CATCH BASINS, TYPE 41, > 8' - 12' DEPTH","EA",null,null,0,3620,0]
[0,"611-41.04","Catch Basins, Type 41, > 12' - 16'","EA",null,null,0,9880,0]
[0,"611-42.01","CATCH BASINS, TYPE 42, 0' - 4' DEPTH","EA",null,null,0,5858.2290789473682,0]
[0,"611-42.02","CATCH BASINS, TYPE 42, > 4' - 8' DEPTH","EA",{"$f":"IF(Tool!$D$46=\"No Errors\",Drainage!L12,0)","v":0},null,{"$f":"E301+F301","v":0},{"$f":"VLOOKUP($B301,'AUP Data'!$A:$AF,25,0)","v":8249.02},0]
[0,"611-42.03","CATCH BASINS, TYPE 42, > 8' - 12' DEPTH","EA",null,null,{"$f":"F302","v":0},13460.27,0]
[0,"611-42.04","CATCH BASINS, TYPE 42, > 12' - 16' DEPTH","EA",null,null,0,6051.93,0]
[0,"611-43.01","CATCH BASINS, TYPE 43, 0' - 4' DEPTH","EA",null,null,0,11200,0]
[0,"611-43.02","CATCH BASINS, TYPE 43, > 4' - 8' DEPTH","EA",null,null,0,11050.666666666666,0]
[0,"611-43.03","CATCH BASINS, TYPE 43, > 8' - 12' DEPTH","EA",null,null,0,12762.04,0]
[0,"611-43.04","Catch Basins, Type 43, > 12' - 16' Depth","EA",null,null,0,12762.04,0]
[0,"611-44.01","Catch Basins, Type 44, > 0' - 4' Depth","EA",null,null,0,13700,0]
[0,"611-44.02","CATCH BASINS, TYPE 44, > 4' - 8' DEPTH","EA",null,null,0,6100,0]
[0,"611-44.03","Catch Basins, Type 44, > 8' - 12' Depth","EA",null,null,0,12760.04,0]
[0,"611-44.04","CATCH BASINS, TYPE 44, > 12' - 16' DEPTH","EA",null,null,0,12760.04,0]
[0,"611-46.01","Catch Basins, Type 46, > 0' - 4' Depth","EA",null,null,0,18816.810000000001,0]
[0,"611-46.02","Catch Basins, Type 46, > 4' - 8' Depth","EA",null,null,0,20758.746666666666,0]
[0,"611-46.03","Catch Basins, Type 46, > 8' - 12' Depth","EA",null,null,0,25913.58,0]
[0,"611-46.04","Catch Basins, Type 46, > 12' - 16' Depth","EA",null,null,0,12500,0]
[0,"611-51.01","Catch Basins, Type 51, > 0' - 4' Depth","EA",null,null,0,9690,0]
[0,"611-51.02","CATCH BASINS, TYPE 51, > 4' - 8' DEPTH","EA",null,null,0,16544.54,0]
[0,"611-51.03","CATCH BASINS, TYPE 51, > 8' - 12' DEPTH","EA",null,null,0,14392,0]
[0,"611-51.04","CATCH BASINS, TYPE 51, > 12' - 16' DEPTH","EA",null,null,0,6196.26,0]
[0,"621-03.02","18\" TEMPORARY DRAINAGE PIPE","LF",null,null,0,60.992131219726993,0]
[0,"621-03.03","24\" TEMPORARY DRAINAGE PIPE","LF",null,null,0,66.677217613273768,{"$f":"IF(G321<>\"\",G321*H321,\"\")","v":0}]
[0,"621-03.04","30\" TEMPORARY DRAINAGE PIPE","LF",null,null,0,108.25443786982248,0]
[0,"621-03.05","36\" TEMPORARY DRAINAGE PIPE","LF",null,null,0,63.011659475605711,0]
[0,"621-03.06","42\" TEMPORARY DRAINAGE PIPE","LF",null,null,0,112.04285714285714,0]
[0,"621-03.07","48\" TEMPORARY DRAINAGE PIPE","LF",null,null,0,160.12730964467005,0]
[0,"621-03.08","54\" TEMPORARY DRAINAGE PIPE","LF",null,null,0,150,0]
[0,"621-03.09","60\" TEMPORARY DRAINAGE PIPE","LF",null,null,0,107.64004767580452,0]
[0,"621-03.10","66\" Temporary Drainage Pipe","LF",null,null,0,230,0]
[0,"621-03.11","72\" TEMPORARY DRAINAGE PIPE","LF",null,null,0,360,0]
[0,"621-05.01","TEMPORARY SHORING","SF",null,null,0,32.382425486764689,0]
[0,"703-01","CEMENT CONCRETE DITCH PAVING","CY",null,null,0,975.69832402234636,0]
[0,"703-02","CEMENT CONCRETE DITCH PAVING (REINFORCED)","CY",null,null,0,1200,0]
[0,"703-02.05","Cement Concrete Ditch Paving (Slotted Drains)","CY",null,null,0,700,0]
[0,"710-02","Aggregate Underdrains (with pipe)","LF",{"$f":"IF(Tool!$D$46=\"No Errors\",Roadway!O20,0)","v":0},null,{"$f":"E334+F334","v":0},{"$f":"VLOOKUP($B334,'AUP Data'!$A:$AF,25,0)","v":13.31},0]
[0,"710-04","Filter Cloth Underdrain (with pipe)","LF",null,null,{"$f":"F335","v":0},26.570578303900639,0]
[0,"710-05","LATERAL UNDERDRAIN","LF",null,null,0,10.340464243939822,0]
[0,"710-06.11","LATERAL UNDERDRAIN ENDWALL (2:1)","EA",null,null,0,1110.4870588235294,0]
[0,"710-06.12","LATERAL UNDERDRAIN ENDWALL (3:1)","EA",null,null,0,994.40329896907213,0]
[0,"710-06.13","LATERAL UNDERDRAIN ENDWALL (4:1)","EA",null,null,0,1064.3799118942732,0]
[0,"710-06.15","LATERAL UNDERDRAIN ENDWALL (6:1)","EA",null,null,0,1174.3847874720359,0]
[0,"710-09.01","6\" PERFORATED PIPE WITH VERTICAL DRAIN SYSTEM","LF",null,null,0,54.836919553962566,{"$f":"IF(G341<>\"\",G341*H341,\"\")","v":0}]
[0,"710-13.03","FILTER CLOTH","SY",null,null,0,3,0]
[0,"740-06.01","GEOMEMBRANE","SY",null,null,0,20.472776462631046,0]
[0,"740-07.01","GEO GRID REINFORCEMENT","SY",null,null,0,11.07967032967033,0]
[0,"740-07.02","Geogrid Reinforcement (Soil Slopes)","SY",null,null,0,7.33,0]
[0,"740-10.01","GEOTEXTILE (TYPE I)(SUBSURFACE DRAINAGE)","SY",null,null,0,18,0]
[0,"740-10.02","GEOTEXTILE (TYPE II)(SEDIMENT CONTROL)","SY",null,null,0,2.31,0]
[0,"740-10.03","GEOTEXTILE (TYPE III)(EROSION CONTROL)","SY",null,null,0,4.094523949407499,0]
[0,"740-10.04","GEOTEXTILE (TYPE IV)(STABILIZATION)","SY",null,null,0,2.8536472877887551,0]
[0,"740-11.01","TEMPORARY SEDIMENT TUBE 8IN (DESCRIPTION)","LF",null,null,0,5.1723660277039318,0]
[0,"740-11.02","TEMPORARY SEDIMENT TUBE 12IN (SEE PLANS)","LF",null,null,0,4.0387954945981148,0]
[0,"740-11.03","TEMPORARY SEDIMENT TUBE 18IN (18 IN)","LF",null,null,0,5.7983503903777169,0]
[{"$f":"IF(G353>0,1,0)","v":0},"740-11.04","TEMPORARY SEDIMENT TUBE 20IN (DESCRIPTION)","LF",null,null,0,4.5484843118630973,0]
[{"$f":"IF(G354>0,1,0)","v":0},"740-11.05","TEMPORARY SEDIMENT TUBE 24IN (DESCRIPTION)","LF",null,null,0,6.7147102526002973,0]
[1,null,null,null,null,null,null,"DRAINAGE TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(SUM(I109:I354),-2)<0,0,ROUNDUP(SUM(I109:I354),-2))","v":0}]
[1]
[1,"Appurtenances"]
[{"$f":"IF(G358>0,1,0)","v":0},"202-03","REMOVAL OF RIGID PAVEMENT, SIDEWALK, ETC.","SY",null,null,{"$f":"F358","v":0},26.726190157734528,{"$f":"IF(G358<>\"\",G358*H358,\"\")","v":0}]
[0,"202-08.15","REMOVAL OF CURB AND GUTTER","LF",null,null,{"$f":"F359","v":0},29.936700291414478,{"$f":"IF(G359<>\"\",G359*H359,\"\")","v":0}]
[0,"202-08.28","Removal of Median Barrier","LF",null,null,{"$f":"F360","v":0},44.99,0]
[0,"604-04.62","Clean and Texture Finish Concrete Barrier","LF",null,null,{"$f":"F361","v":0},7.38,0]
[0,"701-01.01","CONCRETE SIDEWALK (4 \")","SF",{"$f":"IF(Tool!$D$46=\"No Errors\",Median!M18+Drainage!L8,0)","v":0},null,{"$f":"E362+F362","v":0},{"$f":"VLOOKUP($B362,'AUP Data'!$A:$AF,25,0)","v":9.89},0]
[0,"701-01.02","CONCRETE SIDEWALK (6 \")","SF",null,null,{"$f":"F363","v":0},14.502031602708804,0]
[0,"701-02","CONCRETE DRIVEWAY","SF",null,null,0,12.654153594653396,0]
[0,"701-02.02","CONCRETE DRIVEWAY (8\")","SF",null,null,0,14.060219734660032,0]
[0,"701-02.01","CONCRETE CURB RAMP (RETROFIT)","SF",null,null,0,45.172921843450418,0]
[0,"701-02.03","CONCRETE CURB RAMP","SF",null,null,0,30.29559588657537,0]
[0,"702-01","CONCRETE CURB","CY",null,null,0,1051.2705113116256,0]
[0,"702-01.01","EXTRUDED MOUNTABLE CURB","LF",null,null,0,16.384728340675476,0]
[0,"702-01.02","CONCRETE CURB","LF",null,null,0,103,0]
[0,"702-01.03","MODULAR CURB W/DELINEATOR","LF",null,null,0,73,0]
[0,"702-03","CONCRETE COMBINED CURB & GUTTER","CY",{"$f":"IF(Tool!$D$46=\"No Errors\",Median!M16+Drainage!L9,0)","v":0},null,{"$f":"E372+F372","v":0},{"$f":"VLOOKUP($B372,'AUP Data'!$A:$AF,25,0)","v":603.04},0]
[0,"711-04.01","Concrete Glare Screen Median Barrier @ Bridge Piers","LF",null,null,{"$f":"F373","v":0},376.74,0]
[0,"711-05.01","REMOVAL & DISPOSAL OF CONCRETE MEDIAN BARRIER","LF",null,null,{"$f":"F374","v":0},152.55000000000001,0]
[0,"711-05.70","32IN SINGLE SLOPE CONCRETE BARRIER WALL","LF",null,null,{"$f":"F375","v":0},327.69,0]
[0,"711-05.71","51IN SINGLE SLOPE CONCRETE BARRIER WALL","LF",{"$f":"IF(Tool!$D$46=\"No Errors\",Summary!E40,0)","v":0},null,{"$f":"F376+E376","v":0},{"$f":"VLOOKUP($B376,'AUP Data'!$A:$AF,25,0)","v":281.13},0]
[1,null,null,null,null,null,null,"ROADWAY AND PAVEMENT APPURTENANCES TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(SUM(I358:I376),-2)<0,0,ROUNDUP(SUM(I358:I376),-2))","v":0}]
[1]
[1,"Earthwork & Mineral"]
[{"$f":"IF(G380>0,1,0)","v":0},"203-01","ROAD & DRAINAGE EXCAVATION (UNCLASSIFIED)","CY",{"$f":"IF(Tool!$D$46=\"No Errors\",Terrain!AC10,0)","v":0},null,{"$f":"E380+F380","v":0},{"$f":"VLOOKUP($B380,'AUP Data'!$A:$AF,25,0)","v":17.18},{"$f":"G380*H380","v":0}]
[0,"203-01.07","Rd & Drng (Acid Producing off Site)","CY",null,null,{"$f":"F381","v":0},53.5,0]
[0,"203-01.11","PRESPLITTING OF ROCK EXCAVATION","SY",null,null,{"$f":"F382","v":0},33.28,0]
[0,"203-01.29","ROCK EXCAVATION","CY",null,null,{"$f":"F383","v":0},250,0]
[0,"203-01.60","ROAD & DRAINAGE EXCAVATION (ROCK)","CY",null,null,{"$f":"F384","v":0},76.67,0]
[0,"203-01.79","EXCAVATION/BACKFILL","CY",null,null,{"$f":"F385","v":0},65,0]
[0,"203-02.01","BORROW EXCAVATION (GRADED SOLID ROCK)","TON",{"$f":"IF(Tool!$D$46=\"No Errors\",Terrain!AC12,0)*1.7636","v":0},null,{"$f":"F386+E386","v":0},{"$f":"VLOOKUP($B386,'AUP Data'!$A:$AF,25,0)","v":60.67},{"$f":"G386*H386","v":0}]
[0,"203-02.02","BORROW EXCAVATION (GRADED SOLID ROCK)","CY",null,null,{"$f":"F387","v":0},67.37,{"$f":"G387*H387","v":0}]
[0,"203-03","BORROW EXCAVATION (UNCLASSIFIED)","CY",{"$f":"IF(Tool!$D$46=\"No Errors\",Terrain!AC11,0)","v":0},null,{"$f":"E388+F388","v":0},{"$f":"VLOOKUP($B388,'AUP Data'!$A:$AF,25,0)","v":19.3},{"$f":"G388*H388","v":0}]
[0,"203-03.01","BORROW EXCAVATION (SELECT MATERIAL)","CY",null,null,{"$f":"F389","v":0},27.908979494972037,0]
[0,"203-03.10","SELECT GRANULAR MATERIAL","TON",null,null,0,19.78,0]
[0,"203-04","PLACING AND SPREADING TOPSOIL","CY",null,null,0,9.8347133927435113,0]
[0,"203-04.01","PLACING SPREADING SOIL FOR LANDSCAPING","CY",null,null,0,30,0]
[0,"203-04.02","Stripping and Stockpile Topsoil","CY",null,null,0,1.5,0]
[0,"203-05","UNDERCUTTING","CY",null,null,0,10.58051964166067,0]
[0,"203-06","WATER","MG",null,null,0,12.01395081580575,0]
[0,"203-07","FURNISHING & SPREADING TOPSOIL","CY",null,null,0,22.369607787596635,0]
[0,"203-08","CHANNEL EXCAVATION (UNCLASSIFIED)","CY",null,null,0,69.982742914979767,0]
[0,"203-10","EMBANKMENT (COMPACTED IN PLACE)","CY",null,null,0,19.2,0]
[0,"203-10.15","WASTE MATERIAL","CY",null,null,0,33,0]
[0,"203-11","SCALING AND TRIMMING","SY",null,null,0,33.25,0]
[0,"203-12.30","Wetland Materials Exc and Relocation","CY",null,null,0,25.25,0]
[0,"203-15.03","COMPACTED CLAY","CY",null,null,0,128.48536585365855,0]
[0,"203-40.02","ROCK ANCHORS (NON-TENSIONED)","LF",null,null,0,158.5,0]
[0,"203-40.05","Drilling","LF",null,null,0,50,0]
[1,"203-50","CONSTRUCTION OF HAUL ROAD","LS",1,null,{"$f":"E405+F405","v":1},{"$f":"Tool!O235","v":0},0]
[0,"203-50.01","Construction of Haul Road","LS",null,null,0,35000,0]
[0,"204-01","CULVERT EXCAVATION (UNCLASSIFIED)","CY",null,null,0,53.436313712945193,0]
[0,"204-02.01","DRY EXCAVATION (BRIDGES)","CY",null,null,0,28.013460316018886,0]
[0,"204-03.01","WET EXCAVATION (BRIDGES)","CY",null,null,0,42.166844919786094,0]
[0,"204-04.01","ROCK EXCAVATION (BRIDGES)","CY",null,null,0,175.70439814814816,0]
[0,"204-05","ROCK DRILLING (BRIDGES)","LF",null,null,0,45.486294416243652,0]
[0,"204-05.01","CORE DRILLING AND SAMPLING","LF",null,null,0,43.25,0]
[0,"204-05.20","GROUT CASING INSTALLATION","LF",null,null,0,46,0]
[0,"204-06.01","FLOWABLE FILL (GENERAL)","CY",null,null,0,288.59404844290657,0]
[0,"204-08","FOUNDATION FILL MATERIAL","CY",null,null,0,120.6680377259628,0]
[0,"204-08.01","BACKFILL MATERIAL (FLOWABLE FILL)","CY",null,null,0,394.42877955758962,0]
[0,"204-09.01","COFFERDAM","LS",null,null,0,83375.600000000006,0]
[0,"204-10.01","FOUNDATION PREPARATION","LS",null,null,0,49616.666666666664,0]
[{"$f":"IF(G419>0,1,0)","v":0},"204-11","BRIDGE EXCAVATION (UNCLASSIFIED)","CY",null,null,0,50.02,0]
[0,"204-14","CORE DRILLING FOR PILES(ROCK)","LF",null,null,0,287.87299703264097,0]
[0,"204-15","CORE DRILLING FOR PILES(SOIL)","LF",null,null,0,93.023959060246568,0]
[0,"303-01.01","GRANULAR BACKFILL (ROADWAY)","TON",null,null,0,48.41962478603218,0]
[0,"303-01.02","GRANULAR BACKFILL (BRIDGES)","TON",null,null,0,61.565266655009616,0]
[0,"303-01.03","GRANULAR BACKFILL (RETAINING WALLS)","TON",null,null,0,53,0]
[0,"303-01.09","MINERAL AGGREGATE, TYPE A BASE,GRADING D LIMESTONE","TON",null,null,0,47.10669331187875,0]
[0,"303-02","MINERAL AGGREGATE, TYPE B BASE, GRADING (D)","TON",null,null,0,30.046001808346947,0]
[0,"303-10.01","MINERAL AGGREGATE (SIZE 57)","TON",null,null,0,61.707962960449834,0]
[0,"303-10.03","MINERAL AGGREGATE (SIZE 68)","TON",null,null,0,63.55681818181818,0]
[0,"303-10.04","MINERAL AGGREGATE (SIZE   )","TON",null,null,0,59.116255547054323,{"$f":"G429*H429","v":0}]
[0,"303-20.02","RIVER GRAVEL","TON",null,null,0,40,{"$f":"G430*H430","v":0}]
[1,null,null,null,null,null,null,"EARTHWORK & MINERAL TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(SUM(I380:I430),-2)<0,0,ROUNDUP(SUM(I380:I430),-2))","v":0}]
[1]
[1,"Construction Lines and Stakes"]
[{"$f":"IF(G434>0,1,0)","v":1},"105-01","Construction Lines and Stakes","LS",1,null,{"$f":"E434","v":1},null,{"$f":"MROUND(IF(Tool!D46=\"No Errors\",0.00000000004*(J434^2)+0.0096*J434+16594,0),1000)","v":0},{"$f":"SUM('Cost Estimate'!J15:J31)+'Cost Estimate'!J34+'Cost Estimate'!J35+'Cost Estimate'!J36","v":0}]
[1,null,null,null,null,null,null,null,{"$f":"I434","v":0}]
[1]
[1,"Structures"]
[{"$f":"IF(G438>0,1,0)","v":0},"N/A","Removal of Bridge","SF",{"$f":"Bridges!E9","v":0},null,{"$f":"E438+F438","v":0},30,{"$f":"IF(G438<>\"\",G438*H438,\"\")","v":0}]
[0,"N/A","Widen Existing Bridge (Box):","SF",{"$f":"Bridges!E10","v":0},null,0,{"$f":"42*(1+0.07*7)","v":62.58},0]
[0,"N/A","Widen Existing Bridge (Concrete I-Beam & Bulb-T):","SF",{"$f":"Bridges!E11","v":0},null,0,{"$f":"48*(1+0.07*7)","v":71.52},0]
[0,"N/A","Widen Existing Bridge (Concrete Box Beam):","SF",{"$f":"Bridges!E12","v":0},null,0,{"$f":"48*(1+0.07*7)","v":71.52},0]
[0,"N/A","Widen Existing Bridge (Steel Girder):","SF",{"$f":"Bridges!E13","v":0},null,0,{"$f":"60*(1+0.07*7)","v":89.4},0]
[0,"N/A","New Bridge (Box):","SF",{"$f":"Bridges!E14","v":0},null,0,175,0]
[0,"N/A","New Bridge (Concrete I-Beam & Bulb-T):","SF",{"$f":"Bridges!E15","v":0},null,0,240,0]
[0,"N/A","New Bridge (Concrete Box Beam):","SF",{"$f":"Bridges!E16","v":0},null,0,300,0]
[0,"N/A","New Bridge (Steel Girder):","SF",{"$f":"Bridges!E17","v":0},null,0,350,0]
[0,"N/A","Contingency - New Bridge (Box):","%",{"$f":"Bridges!E18","v":0},null,0,{"$f":"E447","v":0},{"$f":"I443*H447","v":0}]
[0,"N/A","Contingency - New Bridge (Concrete I-Beam & Bulb-T):","%",{"$f":"Bridges!E19","v":0},null,0,{"$f":"E448","v":0},{"$f":"I444*H448","v":0}]
[0,"N/A","Contingency - New Bridge (Concrete Box Beam):","%",{"$f":"Bridges!E20","v":0},null,0,0,0]
[0,"N/A","Contingency - New Bridge (Steel Girder):","%",{"$f":"Bridges!E21","v":0},null,0,0,0]
[{"$f":"IF(G451>0,1,0)","v":0},"604-07.01","RETAINING WALL","SF",{"$f":"Bridges!E22","v":0},null,0,200,0]
[1,null,null,null,null,null,null,"STRUCTURES TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(SUM(I438:I451),-2)<0,0,ROUNDUP(SUM(I438:I451),-2))","v":0}]
[1]
[1,"Interchanges and Unique Intersections"]
[{"$f":"IF(G455>0,1,0)","v":0},"N/A","Roundabout","EA",null,null,{"$f":"E455+F455","v":0},1000000,{"$f":"IF(G455<>\"\",G455*H455,\"\")","v":0}]
[{"$f":"IF(G456>0,1,0)","v":0},"N/A","Urban Standard Diamond","EA",null,null,0,25000000,0]
[0,"N/A","Urban Tight Diamond","EA",null,null,0,30000000,0]
[0,"N/A","Urban - Single Point Urban Interchange","EA",null,null,0,35000000,0]
[0,"N/A","Rural - Diamond","EA",null,null,0,10000000,0]
[0,"N/A","Rural - Partial Cloverleaf","EA",null,null,0,12500000,0]
[0,"N/A","Rural - Cloverleaf","EA",null,null,0,15000000,0]
[1,null,null,null,null,null,null,"INTERCHANGES AND UNIQUE INTERSECTIONS TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(SUM(I455:I461),-2)<0,0,ROUNDUP(SUM(I455:I461),-2))","v":0}]
[1]
[1,"Lighting & Signalization"]
[{"$f":"IF(G465>0,1,0)","v":0},"N/A","Traffic Signal","EA",{"$f":"Tool!F36","v":0},null,{"$f":"E465+F465","v":0},{"$f":"250000*(1+0.05*5)","v":312500},{"$f":"IF(G465<>\"\",G465*H465,\"\")","v":0}]
[0,"730-40","TEMPORARY TRAFFIC SIGNAL SYSTEM","EA",null,null,{"$f":"F466","v":0},33475.14,{"$f":"IF(G466<>\"\",G466*H466,\"\")","v":0}]
[0,"N/A","HIGH MAST INTERCHANGE LIGHTING","LS",null,null,{"$f":"F467","v":0},2000000,{"$f":"(G467*H467)","v":0}]
[0,"714-01.38","Light Pole Relocation","EA",null,null,{"$f":"F468","v":0},3740,0]
[0,"714-08.06","Light Standards (Steel)","EA",null,null,0,{"$f":"3900*(1+0.05)^5","v":4977.4980937500004},0]
[0,"725-20.91","CCTV CAMERA SYSTEM (PAN, TILT & ZOOM)","EA",null,null,0,{"$f":"10000*(1+0.05)^5","v":12762.815625000001},0]
[0,"725-21.02","DYNAMIC MESSAGE SIGN (MULTI-COLOR)","EA",null,null,0,{"$f":"145000*(1+0.05)^5","v":185060.82656250001},0]
[0,"725-21.06","DYNAMIC MESSAGE SIGN REMOVE AND REPLACE","EA",null,null,0,{"$f":"20000*(1+0.05)^5","v":25525.631250000002},0]
[0,"N/A","ITS Installation","Mi",null,null,0,1000000,0]
[1,null,null,null,null,null,null,"LIGHTING & SIGNALIZATION TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(SUM(I465:I473),-2)<0,0,ROUNDUP(SUM(I465:I473),-2))","v":0}]
[1]
[1,"Guardrail"]
[{"$f":"IF(G477>0,1,0)","v":0},"705-01.01","GUARDRAIL AT BRIDGE ENDS","LF",{"$f":"IF(Tool!$D$46=\"No Errors\",25*4*SUM(Bridges!B10:B17),0)","v":0},null,{"$f":"E477+F477","v":0},{"$f":"VLOOKUP($B477,'AUP Data'!$A:$AF,25,0)","v":112.09},{"$f":"IF(G477<>\"\",G477*H477,\"\")","v":0}]
[0,"705-01.04","METAL BEAM GUARD FENCE","LF",null,null,0,101.71,{"$f":"IF(G478<>\"\",G478*H478,\"\")","v":0}]
[0,"705-06.01 ","W Beam GR (Type 2) Mash TL3","LF",{"$f":"IF(Tool!$D$46=\"No Errors\",Terrain!AC13,0)","v":0},null,0,{"$f":"VLOOKUP($B479,'AUP Data'!$A:$AF,25,0)","v":34.659999999999997},0]
[0,"705-02.03","SINGLE GUARDRAIL (TYPE 2) LONG POST","LF",null,null,0,40.25,0]
[0,"705-02.50","Shop Curved Guardrail","LF",null,null,0,46,0]
[0,"705-04.02","GUARDRAIL TERMINAL (TYPE 12)","EA",null,null,0,3301.25,0]
[0,"705-04.03","GUARDRAIL TERMINAL (TYPE 13)","EA",null,null,0,1758.7179487179487,0]
[0,"705-04.04","GUARDRAIL TERMINAL (TYPE 21)","EA",null,null,0,1813.42,0]
[0,"705-04.05","GUARDRAIL TERMINAL (TYPE-IN-LINE)","EA",null,null,0,1568.96,0]
[0,"705-06.20 ","Tangent Energy Absorbing Term Mash TL-3","EA",{"$f":"IF(Tool!$D$46=\"No Errors\",Terrain!AC14+Bridges!E30,0)","v":0},null,0,{"$f":"VLOOKUP($B486,'AUP Data'!$A:$AF,25,0)","v":3697.01},0]
[0,"705-04.09","EARTH PAD FOR TYPE 38 GR END TREATMENT","EA",null,null,0,1519.43,0]
[0,"705-04.21","GUARDRAIL DELINEATION ENHANCEMENT","LF",null,null,{"$f":"F488","v":0},4.8600000000000003,0]
[0,"705-08.13","Permanent Impact Attenuator NCHRP350 TL-3","EA",null,null,0,16750.169999999998,0]
[0,"705-08.21","Impact Attenuator (TAU-II Parallel)","EA",null,null,0,18793.34,0]
[0,"705-08.51","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3","EA",null,null,0,7937.5,0]
[0,"705-80.18","CABLE BARRIER TERMINAL","EA",null,null,0,2566.15,0]
[0,"705-80.21","Longitudinal Cable Barrier Cable","LF",null,null,0,82.84,0]
[0,"706-01","GUARDRAIL REMOVED","LF",null,null,0,3.44,0]
[0,"706-06.03","RADIUS RAIL","LF",null,null,0,38.76,0]
[0,"706.06.03","Radius Rail Long Post (6-9 ft)","LF",null,null,0,43.87,0]
[0,"706-06.06","RADIUS RAIL LONG POST (9-12 FT)","LF",null,null,0,46.07,0]
[0,"706-10.24","FLARED END ELEMENT","EA",null,null,0,44.3,0]
[0,"706-10.26","ROUNDED END ELEMENT","EA",null,null,0,162.52210300429186,0]
[0,"706-10.54","RE-ALIGN GUARDRAIL","LF",null,null,0,4.333333333333333,0]
[0,"706-10.56","BUFFER ENDS 88\"","EA",null,null,0,161.5,0]
[0,"706-10.71","HAZARD MARKERS","EA",null,null,0,48.70967741935484,0]
[0,"706-10.72","PULL AND RENSTALL GURDRAIL POST FOR VERI","EA",null,null,0,366.66666666666669,0]
[0,"706-10.73","REMOVAL OF GUARDRAIL & POST FOR REUSE","CY",null,null,0,30,0]
[0,"706-10.74","CONCRETE BARRIER WALL REPAIR","EA",null,null,0,4344.9367088607596,0]
[0,"706-10.80","MICHIGAN AND MODIFIED MICHIGAN END SHOE","EA",null,null,0,312.46606557377049,0]
[0,"706-10.81","GUARDRAIL REFLECTORS","EA",null,null,0,17.62148337595908,0]
[0,"706-10.82","CONC BR END OR PIER PROTECTION REPAIR","CY",null,null,0,3500,0]
[0,"706-10.83","DRILL BR. PAR. WALL, MICHIGAN END SHOE","EA",null,null,0,238.39285714285714,0]
[1,null,null,null,null,null,null,"GUARDRAIL TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(SUM(I477:I509),-2)<0,0,ROUNDUP(SUM(I477:I509),-2))","v":0}]
[1]
[1,"Seeding and Sodding"]
[{"$f":"IF(G513>0,1,0)","v":0},"801-01","SEEDING (WITH MULCH)","UNIT",{"$f":"IF(Tool!$D$46=\"No Errors\",Drainage!L16,0)","v":0},null,{"$f":"E513+F513","v":0},{"$f":"VLOOKUP($B513,'AUP Data'!$A:$AF,25,0)","v":65.16},{"$f":"IF(G513<>\"\",G513*H513,\"\")","v":0}]
[0,"801.01.02","Crown Vetch Mixture (with mulch)","UNIT",null,null,{"$f":"F514","v":0},97.14,{"$f":"IF(G514<>\"\",G514*H514,\"\")","v":0}]
[0,"801-01.07","TEMPORARY SEEDING (WITH MULCH)","UNIT",{"$f":"IF(Tool!$D$46=\"No Errors\",Drainage!L17,0)","v":0},null,{"$f":"E515+F515","v":0},{"$f":"VLOOKUP($B515,'AUP Data'!$A:$AF,25,0)","v":45.9},{"$f":"IF(G515<>\"\",G515*H515,\"\")","v":0}]
[0,"801-02","SEEDING (WITHOUT MULCH)","UNIT",{"$f":"IF(Tool!$D$46=\"No Errors\",Drainage!L18,0)","v":0},null,{"$f":"E516+F516","v":0},{"$f":"VLOOKUP($B516,'AUP Data'!$A:$AF,25,0)","v":42.23},0]
[0,"801-02.15","FERTILIZER","TON",null,null,{"$f":"F517","v":0},878.59259259259272,0]
[0,"801-03","WATER (SEEDING & SODDING)","MG",null,null,0,14.084555805310238,0]
[0,"801-07","SEED (SUPPLEMENTAL APPLICATION)","TON",null,null,0,14.56,0]
[0,"801-08","FERTILIZER (SUPPLEMENTAL APPLICATION)","TON",null,null,0,723.74107142857144,0]
[0,"802-01.10","TREES (Populus deltoides 1 1#4\"- 1 1#2\" Cal, B &B)","EA",null,null,0,150,0]
[0,"802-01.11","TREES (Quercus Falcata 1 1#4\"- 1 1#2\" Cal, B&B )","EA",null,null,0,448.47857142857146,0]
[0,"802-01.12","TREES (Fraxinus pennsylvanica 1 1#4\"- 1 1#2\" C al, B&B)","EA",null,null,0,368.67019607843139,0]
[0,"802-01.13","Tree","EA",null,null,0,502.48000000000008,0]
[0,"802-01.14","Tree","EA",null,null,0,573.55999999999995,0]
[0,"802-12.07","BETULA NIGRA (RIVER BIRCH SEEDLNG B.R.)","EA",null,null,0,15.18,0]
[0,"802-12.18","LIQUIDAMBER STYRACIFLUA (SWEETGUM SEEDLNG B.R.)","EA",null,null,0,12.03448275862069,0]
[0,"802-12.26","PLATANUS OCCIDENTALIS (SYCAMORE SEEDLNG B.R.)","EA",null,null,0,14.693627450980392,0]
[0,"802-12.38","Tree","EA",null,null,0,10.49,0]
[0,"802-12.42","Tree","EA",null,null,0,5.58,0]
[0,"803-01","SODDING (NEW SOD)","SY",null,null,0,4.3272983425752889,0]
[0,"805-01.03","TURF REINFORCEMENT MAT (CLASS III)","SY",null,null,0,4.8857044198895023,0]
[0,"805-12.01","EROSION CONTROL BLANKET (TYPE I)","SY",null,null,0,2.2255195233327636,0]
[0,"805-12.02","EROSION CONTROL BLANKET (TYPE II)","SY",null,null,0,1.4176929745238953,0]
[0,"805-12.03","EROSION CONTROL BLANKET (TYPE III)","SY",null,null,0,2.0156173707183549,0]
[0,"806-01","Mowing","Acre",null,null,0,66.868365938797211,0]
[0,"806-02.03","PROJECT MOWING","Cycl",null,null,0,3778.7849999999999,0]
[0,"806-02.05","Herbicide Application","Acre",null,null,0,1000,0]
[0,"806-02.10","Herbicide Application","LS",null,null,0,2000,0]
[0,"806-02.12","Mowing, Weedeating & Litter Pickup (Urban)","Cycl",null,null,0,11266.41,0]
[0,"806-02.13","Swath Mowing","Acre",null,null,0,69.820492764958942,0]
[0,"806-03.01","TREE CUTTING","LS",null,null,0,10500,0]
[1,null,null,null,null,null,null,"SODDING TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(SUM(I513:I542),-2)<0,0,ROUNDUP(SUM(I513:I542),-2))","v":0}]
[1]
[1,"Maintenace of Traffic"]
[{"$f":"IF(G546>0,1,0)","v":0},"N/A","Traffic Control Cost","LS",{"$f":"IF(Tool!$D$46=\"No Errors\",1,0)","v":0},null,{"$f":"E546+F546","v":0},null,{"$f":"J546*Tool!P225","v":0},{"$f":"SUM('Cost Estimate'!N15:N30,'Cost Estimate'!N32,'Cost Estimate'!N34:N36)","v":0}]
[0,"712-01","TRAFFIC CONTROL","LS",null,null,{"$f":"F547","v":0},null,{"$f":"G547*H547","v":0}]
[0,"712-09.01","Removable Pavement Marking Line","LF",null,null,{"$f":"F548","v":0},4.8,{"$f":"G548*H548","v":0}]
[0,"712-09.02","Removable Pavement Marking (8\" Barrier Line)","LF",null,null,0,4.62,0]
[0,"712-02.02","INTERCONNECTED PORTABLE BARRIER RAIL","LF",null,null,{"$f":"E550+F550","v":0},37.96,{"$f":"G550*H550","v":0}]
[1,null,null,null,null,null,null,"MAINTENANCE OF TRAFFIC TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(SUM(I546:I550),-2)<0,0,ROUNDUP(SUM(I546:I550),-2))","v":0}]
[1]
[1,"Signs"]
[{"$f":"IF(G554>0,1,0)","v":0},"713-01.01","CLASS A CONCRETE (FOUNDATION FOR SIGN SUPPORTS)","Cycl",null,null,{"$f":"F554","v":0},716.70589400039603,{"$f":"G554*H554","v":0}]
[0,"713-01.02","STEEL BAR REINFORCEMENT(FOUNDATION FOR SIGN SUPPORTS)","LB",null,null,0,3.2336077312213609,{"$f":"G555*H555","v":0}]
[0,"713-02.04","DELINEATOR (MILE MARKER) & STEEL POST","EA",null,null,0,257.84615384615387,0]
[0,"713-02.11","REMOVAL OF EXISTING DELINEATORS","EA",null,null,0,11.962578124999999,0]
[0,"713-02.14","FLEXIBLE DELINEATOR (WHITE)","EA",null,null,0,52.195697830163404,0]
[0,"713-02.15","FLEXIBLE DELINEATOR (YELLOW)","EA",null,null,0,46.848936170212767,0]
[0,"713-02.16","Flexible Type II Object Marker","EA",null,null,0,55,0]
[0,"713-02.20","Roadside Obstacle Delineation","SF",null,null,0,21.038009049773756,0]
[0,"713-02.21","SIGN POST DELINEATION ENHANCEMENT","LF",null,null,0,6.2,0]
[0,"713-02.22","Barrier Wall Delineation Enhancement","LF",null,null,0,8.69,0]
[0,"713-02.26","CONCRETE BARRIER/PARAPET DELINEATOR","EA",null,null,0,20.054744525547445,0]
[0,"713-02.33","FLEXIBLE DELINEATOR (RED)","EA",null,null,0,34.5,0]
[0,"713-02.34","DELINEATORS (ALL)","EA",null,null,0,32.340000000000003,0]
[0,"713-02.35","Barrier Delineation Sheeting","LF",null,null,0,8.89,0]
[0,"713-04.02","Steel I-Beams & W-F Beams-Sign Supports","LB",null,null,0,6.5152402807775376,0]
[0,"713-05","STEEL HOLLOW SQUARE POST (BREAKAWAY) SIGN SUPPORTS","LB",null,null,0,7.7931914893617025,0]
[0,"713-06","STEEL I-BEAMS & WF-BEAMS(BREAKAWAY) SIGN SUPPORT","LB",null,null,0,6.0134400758206716,0]
[0,"713-06.01","Steel I-BMs & WF-BMs (Brksafe) Sign Support","LB",null,null,0,5.5,0]
[0,"713-09.01","STEEL OVERHEAD SIGN STRUCTURE (SPAN 96' - 6\")","EA",null,null,0,151044.06666666668,0]
[0,"713-09.02","STEEL OVERHEAD SIGN STRUCTURE (SPAN 83' - 0\")","EA",null,null,0,128042.92,0]
[0,"713-09.03","STEEL OVERHEAD SIGN STRUCTURE (SPAN 90' - 0\")","EA",null,null,0,133299.12,0]
[0,"713-09.04","STEEL OVERHEAD SIGN STRUCTURE (SPAN 60' - 0\")","EA",null,null,0,147218.51999999999,0]
[0,"713-09.05","STEEL OVERHEAD SIGN STRUCTURE (SPAN 62' - 6\")","EA",null,null,0,168667.85,0]
[0,"713-09.06","STEEL OVERHEAD SIGN STRUCTURE (SPAN 81')","EA",null,null,0,181363.94,0]
[0,"713-09.07","STEEL OVERHEAD SIGN STRUCTURE (SPAN 97')","EA",null,null,0,178824.68,0]
[0,"713-09.08","STEEL OVERHEAD SIGN STRUCTURE (SPAN 99.5')","EA",null,null,0,158415,0]
[0,"713-09.09","STEEL OVERHEAD SIGN STRUCTURE (SPAN 92.50')","EA",null,null,0,165750,0]
[0,"713-09.10","STEEL OVERHEAD SIGN STRUCTURE (SPAN 92.50')","EA",null,null,0,195515,0]
[0,"713-09.11","STEEL OVERHEAD SIGN STRUCTURE (SPAN 165.50')","EA",null,null,0,147369.60000000001,0]
[0,"713-09.12","STEEL OVERHEAD SIGN STRUCTURE (SPAN 80.50')","EA",null,null,0,93250,0]
[0,"713-09.13","STEEL OVERHEAD SIGN STRUCTURE (SPAN 187')","EA",null,null,0,91250,0]
[0,"713-09.14","STEEL OVERHEAD SIGN STRUCTURE (SPAN 175')","EA",null,null,0,77000,0]
[0,"713-09.21","Steel Overhead Sign Structure","EA",null,null,{"$f":"F586","v":0},101750,0]
[0,"713-10.01","Steel Cntlv Sign Structure","EA",null,null,0,63140,0]
[0,"713-11.01","\"U\" SECTION STEEL POSTS","LB",null,null,0,4.7155234008255915,0]
[0,"713-11.02","PERFORATED/KNOCKOUT SQUARE TUBE POST","LB",null,null,0,5.3351479096915995,0]
[0,"713-11.03","2 1/2\" DIA ROUND STEEL TUBE SIGN POST","LB",null,null,0,9.6441192411924135,0]
[0,"713-11.05","SQUARE TUBE SIGN SUPPORT","LB",null,null,0,6.7033903301886806,0]
[0,"713-11.21","P POST SLIP BASE","EA",null,null,0,617.67131455399056,0]
[0,"713-11.22","U POST SLIP BASE","EA",null,null,0,420.47,0]
[0,"713-11.23","ROUND POST SLIP BASE","EA",null,null,0,616,0]
[0,"713-13.02","FLAT SHEET ALUMINUM SIGNS (0.080\" THICK)","SF",null,null,0,14.971478316623196,0]
[0,"713-13.03","FLAT SHEET ALUMINUM SIGNS (0.100\" THICK)","SF",null,null,0,16.25417353575477,0]
[0,"713-13.04","FLAT SHEET ALUMINUM SIGNS (0.125\" THICK)","SF",null,null,0,40,0]
[0,"713-13.12","Flat Sheet Alum Signs Overlay (0.080\" Thick)","SF",null,null,0,21.19,0]
[0,"713-13.14","Florescent Yellow Sign Sheeting","SF",null,null,0,5.156847133757962,0]
[0,"713-14","EXTRUDED ALUMINUM PANEL SIGNS","SF",null,null,0,28.636731665770125,0]
[0,"713-15","REMOVAL OF SIGNS, POSTS AND FOOTINGS","LS",null,null,0,2121.3331707317075,0]
[0,"713-15.01","REMOVAL OF EXISTING SIGN POST","EA",null,null,0,58.333333333333336,0]
[0,"713-15.02","REMOVAL & RELOCATION OF SIGN & SUPPORT","EA",null,null,0,437.70405063291133,0]
[0,"713-15.04","INSTALLATION OF LETTERS & ARROWS","LS",null,null,0,3300,0]
[0,"713-15.06","MILE POST SIGN","EA",null,null,0,234.91666666666666,0]
[0,"713-15.07","SUSPENDED FLAT SHEET ALUMINUM SIGN (0.080\" THICK)","EA",null,null,0,396.01372093023258,0]
[0,"713-15.35","METAL BARRICADE (TYPE III)","EA",null,null,0,1477.32,0]
[0,"713-15.36","REMOVE SIGN, SUPPORT & FOOTING","EA",null,null,0,43.018342440801462,0]
[0,"713-15.37","Installation of Sign Message (Letter, #, AR)","SF",null,null,0,42.4,0]
[0,"713-15.38","Extrd Alm Panels for Overlaying Bkground","SF",null,null,0,17.918918918918919,0]
[{"$f":"IF(G611>0,1,0)","v":0},"713-15.40","SIGN INSTALLATION (DESCRIPTION)","LS",null,null,0,2000.59,0]
[0,"713-15.41","SIGN REMOVAL (DESCRIPTION)","LS",null,null,0,403.33,{"$f":"G612*H612","v":0}]
[0,"713-16.01","CHANGEABLE MESSAGE SIGN UNIT","EA",null,null,0,6526.9857700650764,0]
[0,"713-16.02","Truck Mtd Imp Attn (w/ Flashing Arrow Board)","EA",null,null,0,26460,0]
[0,"713-16.05","RAILROAD CROSS-BUCK SIGN & SUPPORT","EA",null,null,0,477,0]
[0,"713-16.06","DEAD END SIGN AND SUPPORT","Ea",null,null,0,359.33333333333331,0]
[0,"713-16.07","END OF ROADWAY SIGN AND SUPPORT","EA",null,null,0,281,0]
[0,"713-16.09","RAILROAD ADVANCE WARNING SIGN AND SUPPORT","EA",null,null,{"$f":"F618","v":0},471.06461538461542,0]
[0,"713-16.20","SIGNS (PARK AND RIDE - LEFT (D4-2L)","EA",null,null,0,469.23692660550455,0]
[0,"713-16.21","SIGNS (PARK AND RIDE - RIGHT (D4-2R)","EA",null,null,0,410.65999999999997,0]
[0,"713-16.22","SIGNS (BUS STOP NO PARKING (R7-107A)","EA",null,null,0,250.78234375000002,0]
[0,"713-16.23","SIGNS (NO TRUCKS (R5-2A)","EA",null,null,0,410.02195121951212,0]
[0,"713-16.24","SIGNS (HANDICAP PARKING (SP-1)","EA",null,null,0,200.92037037037039,0]
[0,"713-16.25","SIGNS (STOP (R1-1)","EA",null,null,0,397.1370588235294,0]
[0,"713-16.26","SIGNS (OM4-1 - OBJECT MARKER)","EA",null,null,0,277.57666666666665,0]
[0,"713-16.27","SIGNS (OM1-1 - OBJECT MARKER)","EA",null,null,0,4571.9449999999997,0]
[0,"713-16.28","SIGNS (CLAIM CAR)","EA",null,null,0,955.30333333333328,0]
[0,"713-16.29","SIGNS (Bus Stop)","EA",null,null,0,235,0]
[0,"713-16.41","RELOCATE SIGN","LS",null,null,0,2847.13,0]
[0,"713-16.42","RELOCATE SIGN & REWIRE","LS",null,null,0,4000,0]
[0,"713-16.50","REMOVE AND REPLACE SIGN (DESCRIPTION)","EA",null,null,0,276.43,0]
[0,"713-16.60","Remove and Replace Sign (Description)","EA",null,null,0,225,0]
[0,"713-17.02","INSTALL AUXILIARY SUPPORT FOR EXIT NUMBER PANEL","EA",null,null,0,91.43,0]
[0,"713-17.50","SIGN MOUNTED ON BRIDGE PARAPET","EA",null,null,0,664.69,0]
[0,"713-20.01","Traf Sign Base","EA",null,null,0,350,0]
[0,"713-20.02","Architectural Traf Sign Pole & Frame","EA",null,null,0,940,0]
[0,"713-20.30","SIGN ADJUSTMENTS","EA",null,null,0,269.88636363636363,0]
[0,"713-30.09","BARRIER MOUNTED SIGN SUPPORT (SEE PLANS)","EA",null,null,0,706.61571428571426,0]
[0,"713-09.06","Steel Overhead Sign Structure","EA",null,null,0,159816.5,0]
[1,"Not Listed","Signs (Construction)","LS",1,null,{"$f":"E640+F640","v":1},0,{"$f":"MROUND((SUM('Cost Estimate'!J15:J28)+'Cost Estimate'!J30*0.0006)*0.001,100)","v":0}]
[1,null,null,null,null,null,null,"SIGNING TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(SUM(I554:I640),-2)<0,0,ROUNDUP(SUM(I554:I640),-2))","v":0}]
[1]
[1,"Pavement Markings"]
[{"$f":"IF(G644>0,1,0)","v":0},"N/A","Pavement Markings (Widening Projects)","LS",null,null,{"$f":"F644","v":0},null,{"$f":"G644*H644","v":0}]
[0,"716-01.05","Temporary Raised Pavement Marker","EA",null,null,0,14.598832206515057,{"$f":"G645*H645","v":0}]
[0,"716-01.06","Temporary Raised Pavement Marker, White","EA",null,null,0,14.657074340527577,0]
[0,"716-01.07","Temporary Raised Pavement Marker, Yellow","EA",null,null,0,13.255962769051774,0]
[0,"716-01.10","Snowplowable Reflective Marker","EA",null,null,0,323.91304347826087,0]
[0,"716-01.11","Raised Pvmt Markers (Bi-Dir, 1 Color)","EA",null,null,0,11.524036488027367,0]
[0,"716-01.12","Raised Pvmt Markers (Mono-Dir, 1 Color)","EA",null,null,0,9.5299999999999994,0]
[0,"716-01.13","Raised Pvmt Markers (Bi-Dir, 2 Color)","EA",null,null,0,25.839885714285714,0]
[0,"716-01.21","Snwplwble Pvmt Mrkrs (Bi-Dir)(1 Color)","EA",null,null,0,37.752882093693891,0]
[0,"716-01.22","Snwplwble Pvmt Mrkrs (Mono-Dir)(1 Color)","EA",null,null,0,41.370563815238015,0]
[0,"716-01.23","Snwplwble Pvmt Mrkrs (Bi-Dir)(2 Color)","EA",null,null,0,37.801822189294313,0]
[0,"716-02.01","PLASTIC PAVEMENT MARKING (4\" LINE)","LM",null,null,0,3172.32,0]
[0,"716-02.02","PLASTIC PAVEMENT MKG (8\" BARRIER LINE)","LF",null,null,0,2.95,0]
[0,"716-02.03","Plastic Pavement Marking (Cross-Walk)","LF",null,null,0,14.417187941117161,0]
[0,"716-02.04","Plastic Pavement Marking (Chnz Striping)","SY",null,null,0,27.038577630350197,0]
[0,"716-02.05","Plastic Pavement Marking (Stop Line)","LF",null,null,0,17.607780166621875,0]
[0,"716-02.06","Plastic Pavement Marking (Turn Lane Arrow)","EA",null,null,0,207.36228504516563,0]
[0,"716-02.07","Plastic Pavement Marking (24\" Barrier Line)","LF",null,null,0,12.99731136477852,0]
[0,"716-02.08","Plastic Pavement Marking (8\" Dotted Line)","LF",null,null,0,6.56,0]
[0,"716-02.09","Plastic Pavement Marking (Longitudinal X-Walk)","LF",null,null,0,35.079536445690856,0]
[0,"716-02.13","Plastic Pavement Marking (Cross-Walk)","SF",null,null,0,10.97,0]
[0,"716-03.01","Plastic Word Pavement Marking (Only)","EA",null,null,0,293.24153846153848,0]
[0,"716-03.02","Plastic Word Pavement Marking (RXR)","EA",null,null,0,688.83829787234049,0]
[0,"716-03.03","Plastic Word Pavement Marking (Stop Ahead)","EA",null,null,0,591.99074074074076,0]
[0,"716-03.04","Plastic Word Pavement Marking (School)","EA",null,null,0,364.7,0]
[0,"716-03.05","Plastic Word Pavement Marking (Bike Lane)","EA",null,null,0,354.16666666666669,0]
[0,"716-03.06","Plastic Word Pavement Marking (Signal Ahead)","EA",null,null,0,860.71818181818173,0]
[0,"716-03.07","Plastic Word Pavement Marking (Stop)","EA",null,null,0,403.22,0]
[0,"716-03.08","Plastic Word Pavement Marking (Ped-Xing)","EA",null,null,0,359.375,0]
[0,"716-04.01","Plastic Word Pavement Marking (Straight-Turn Arrow)","EA",null,null,0,364.50965277777783,0]
[0,"716-04.02","Plastic Pavment Marking (Double Turning Arrow)","EA",null,null,0,393.33673469387753,0]
[0,"716-04.03","Plastic Pavment Marking (4\" Dotted Line)","LF",null,null,0,3,0]
[0,"716-04.04","Plastic Pavment Marking (Transverse Shoulder)","LF",null,null,{"$f":"F676","v":0},17.79,0]
[0,"716-04.05","Plastic Pavement Marking (Straight Arrow)","EA",null,null,0,208.60143939393939,0]
[0,"716-04.06","Plastic Pavement Marking (Wrong Way Arrow)","EA",null,null,0,314.32333333333332,0]
[0,"716-04.07","Plastic Pavement Marking (Exit Only Arrow)","EA",null,null,0,434.13362068965517,0]
[0,"716-04.08","Plastic Pavement Marking (Option Lane Arrow)","EA",null,null,0,451.88461538461536,0]
[0,"716-04.09","Plastic Pavement Marking (H.O.V. Diamond)","EA",null,null,0,496.11521739130438,0]
[0,"716-04.10","Plastic Pavement Marking (Handicap Symbol)","EA",null,null,0,228.5,0]
[0,"716-04.12","Plastic Pavement Marking (Yield Line)","SF",null,null,0,82.84,0]
[0,"716-04.13","PLASTIC PAVEMENT MARKING(BLANE SY ARROW)","EA",null,null,0,482.19638766519824,0]
[0,"716-04.14","PLASTIC PAVEMENT MARKING(LANE RED ARROW)","EA",null,null,0,462.06884146341469,0]
[0,"716-04.15","PLASTIC PAVEMT MARKING-BIKE SYMBOL/AR SH","EA",null,null,0,437.62886597938143,0]
[0,"716-04.16","Painted Pavement Marking (Noise Strip)","LF",null,null,0,12.72011952191235,0]
[0,"716-04.17","Plastic Pavement Marking (Yield Symbol)","EA",null,null,0,210,0]
[0,"716-05.01","Painted Pavement Marking (4\" Line)","LM",null,null,0,1168.3020135480438,0]
[0,"716-05.02","Painted Pavement Marking (8\" Barrier Line)","LF",null,null,0,0.8321365409059962,0]
[0,"716-05.03","Painted Pavement Mkg (Cross-Walk)","LF",null,null,0,27.993945899527695,0]
[0,"716-05.04","Painted Pavement Mkg (Chnz Striping)","SY",null,null,0,13.245030581039755,0]
[0,"716-05.05","Painted Pavement Marking (Stop Line)","LF",null,null,0,12.443515857672814,0]
[0,"716-05.06","Painted Pavement Mkg (Turn Lane Arrow)","EA",null,null,0,149.19736346516009,0]
[0,"716-05.07","Painted Pavement Mkg (24\" Barrier Line)","LF",null,null,0,21.6944935111752,0]
[0,"716-05.08","Painted Pavement Marking (Parking Line)","LF",null,null,0,3.7535395506309635,0]
[0,"716-05.09","Painted Pavement Marking (Str-Turn Arrow)","EA",null,null,0,320.5418181818182,0]
[0,"716-05.10","Painted Pavement Marking (RXR)","EA",null,null,0,447.815,0]
[0,"716-05.11","Painted Pavement Marking (Str-Arrow)","EA",null,null,0,144.32666666666668,0]
[0,"716-05.20","Painted Pavement Marking (6\" Line)","LM",null,null,0,1422.4672865375878,0]
[0,"716-08.01","Removal of Pavement Marking (Line)","LF",null,null,0,1.2220955517176582,0]
[0,"716-08.03","Removal of Pavement Marking (Cross Walk)","LF",null,null,0,12.039702694332609,0]
[0,"716-08.04","Removal Pavement Marking (Chnz Striping)","SY",null,null,0,20.962503121098628,0]
[0,"716-08.05","Removal of Pavement Marking (Stop Line)","LF",null,null,0,12.757031249999999,0]
[0,"716-08.06","Removal of Pavement Marking (Turn Lane Arrow)","EA",null,null,0,120.57625418060202,0]
[0,"716-08.07","Removal Pavement Marking (Straight-Turn Arrow)","EA",null,null,0,129.36363636363637,0]
[0,"716-08.08","Removal Pavement Marking (Double Turning Arrow)","EA",null,null,0,229.54545454545453,0]
[0,"716-08.09","Removal of Pavement Marking (Dotted Line)","LF",null,null,{"$f":"F708","v":0},11.58,0]
[0,"716-08.10","Removal Pavement Marking (Transverse Shoulder)","LF",null,null,0,251.06,0]
[0,"716-08.11","Removal of Word Pavement Marking","EA",null,null,0,519.04999999999995,0]
[0,"716-08.30","Hyrdoblast Removal of Pavement Marking (Line)","LF",null,null,0,4793.950143815915,0]
[0,"716-09.03","WET REFLECTIVE PAVEMENT MARKING(6\" LINE)","LM",null,null,0,34584.615384615383,0]
[0,"716-09.31","STOP LINE","LF",null,null,0,16.649999999999999,0]
[0,"716-09.33","6 INCH DOTTED LINE","LF",null,null,0,1.1000000000000001,0]
[0,"716-09.72","WET REFLEC PAVEMEMT MARKING (4\"LINE)","LM",null,null,0,47141.919999999998,0]
[0,"716-10.50","Preformed Plastic Pavement Marking (Interstate Shield)","EA",null,null,0,1904.8780487804879,0]
[{"$f":"IF(G717>0,1,0)","v":0},"716-12.01","Enhanced Flat Thermo P.M. (4\")","LM",null,null,0,3825,0]
[0,"716-12.02","Enhanced Flat Thermo P.M. (6\")","LM",null,null,0,7576.4906215078836,{"$f":"G718*H718","v":0}]
[0,"716-12.03","Enhanced Flat Thermo P.M. (8\" Barrier)","LF",null,null,0,2.6729000589374423,0]
[0,"716-12.04","Enhanced Flat Thermo (4\" Dotted)","LF",null,null,0,1.52,0]
[0,"716-12.05","Enhanced Flat Thermo (6\" Dotted)","LF",null,null,0,2.4015182022971886,0]
[0,"716-12.06","Enhanced Flat Thermo (8\" Line)","LF",null,null,0,12.77,0]
[0,"716-12.07","Enhanced Flat Thermo (8\" Broken Line)","LF",null,null,0,20.51,0]
[0,"716-12.08","Enhanced Flat Thermo (12\" Barrier)","LF",null,null,0,4.250261298751572,0]
[0,"716-12.09","Enhanced Flat Thermo (12\" Line)","LF",null,null,0,5.3834199194332539,0]
[0,"716-12.10","Enhanced Flat Thermo (12\" Dotted)","LF",null,null,0,5.3513730082472568,0]
[0,"716-13.01","Spray Thermo P.M. (60 Mil 4\")","LM",null,null,0,1948.24,0]
[0,"716-13.02","Spray Thermo P.M. (60 mil 6\")","LM",null,null,0,3473.2913886351175,0]
[0,"716-13.03","Spray Thermo P.M. (60 mil 8\" Barrier)","LF",null,null,0,2.35,0]
[0,"716-13.04","Spray Thermo (60 Mil 4\" Dotted)","LF",null,null,0,1.55,0]
[0,"716-13.05","Spray Thermo P.M. (60 mil 6\" Dotted)","LF",null,null,0,2.15,0]
[0,"716-13.06","Spray Thermo P.M. (40 mil 4\")","LM",null,null,{"$f":"E732+F732","v":0},1654.2273950855883,0]
[0,"716-12.02","ENHANCED FLAT THERMO P.M. (6IN)","LM",{"$f":"IF(Tool!$D$46=\"No Errors\",((2+Roadway!S41/5)*Roadway!D2),0)","v":0},null,{"$f":"F733+E733","v":0},{"$f":"VLOOKUP($B733,'AUP Data'!$A:$AF,25,0)","v":7529.96},0]
[0,"716-12.02","Enhanced Flat Thermo P.M. (6\")","LM",null,null,{"$f":"F734","v":0},7576.4906215078836,0]
[0,"716-01.23","Snwplwble Pvmt Mrkrs (Bi-Dir)(2 Color)","EA",null,null,0,37.801822189294313,0]
[0,"716-13.10","Spray Thermo P.M. (40 mil 6\" Dotted)","LF",null,null,{"$f":"F736","v":0},568.71,0]
[1,null,null,null,null,null,null,"PAVEMENT MARKINGS TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(SUM(I644:I736),-2)<0,0,ROUNDUP(SUM(I644:I736),-2))","v":0}]
[1]
[1,"Fencing"]
[{"$f":"IF(G740>0,1,0)","v":0},"707-01.01","Chain Link Fence (4 Foot)","LF",null,null,{"$f":"F740","v":0},12.5,{"$f":"G740*H740","v":0}]
[0,"707-01.02","End & Corner Post Assembly (CL Fence 4')","EA",null,null,0,310,{"$f":"G741*H741","v":0}]
[0,"707-01.11","Chain Link Fence (6 Foot)","LF",null,null,0,16.781287624358406,0]
[0,"707-01.12","End & Corner Post ASM(CL Fence 6')","EA",null,null,0,380.30620689655171,0]
[0,"707-01.13","Gate -CL Fence-6 Foot","EA",null,null,0,3928.65,0]
[0,"707-01.14","Gate-CL Fence - 6 Foot","EA",null,null,0,3000,0]
[0,"707-01.20","Temp 6ft Chainlink W/3 Strand B. Wire","LF",null,null,0,10,0]
[0,"707-01.23","Chain-Link (6FT)(Vinyl CTD) W/3 STR B.W.","LF",null,null,0,19.350000000000001,0]
[0,"707-01.28","End & Corner Post Assembly (Description)","EA",null,null,0,112,0]
[0,"707-01.50","Chain-Link Fence","LF",null,null,0,10.58,0]
[0,"707-01.51","End and Corner Post Assembly (Chain-Link Fence 6\")","EA",null,null,0,172.5,0]
[0,"707-01.52","Gate - CL Fence","EA",null,null,0,700,0]
[0,"707-06.01","Removal of Fence","LF",null,null,0,6.1377516258903686,0]
[0,"707-06.03","Removal and Reset Fence","LF",null,null,0,120,0]
[0,"707-07.01","Chain-Link Fence (Bridges)","LF",null,null,0,38.571428571428569,0]
[0,"707-08.01 ","High Visibility Construction Fence","LF",null,null,0,16.600000000000001,0]
[0,"707-08.02 ","Gate","EA",null,null,0,8313.76,0]
[0,"707-08.11","High Visibility Construction Fence","LF",null,null,0,3.0165477317813272,0]
[0,"708-02.01","Markers (Concrete ROW Posts)","EA",null,null,0,356.85617231638417,0]
[1,null,"FENCE TOTAL (ROUNDED)",null,null,null,null,null,{"$f":"IF(ROUNDUP(SUM(I740:I758),-2)<0,0,ROUNDUP(SUM(I740:I758),-2))","v":0}]
[1]
[1,"Rip-Rap"]
[{"$f":"IF(G762>0,1,0)","v":0},"709-01.01","Rubble Stone Rip-Rap","CY",null,null,{"$f":"F762","v":0},315.74,{"$f":"G762*H762","v":0}]
[0,"709-01.02","Rubble Stone Rip-Rap","TON",null,null,0,83.63,{"$f":"G763*H763","v":0}]
[0,"709-02.01","Rubble Stone Rip-Rap (Grouted)","CY",null,null,0,384,0]
[0,"709-04","Reinforced Concrete Slope Pavement","CY",null,null,0,1720.93,0]
[0,"709-05.02","Machined Rip-Rap (Rubble Stone)","CY",null,null,0,475,0]
[0,"709-05.05","Machined Rip-Rap (Class A-3)","TON",{"$f":"Bridges!E28","v":0},null,{"$f":"F767+E767","v":0},{"$f":"VLOOKUP($B767,'AUP Data'!$A:$AF,25,0)","v":67.8},0]
[0,"709-05.06","Machined Rip-Rap (Class A-1)","TON",null,null,0,67.933131833247259,0]
[0,"709-05.07","Machined Rip-Rap (Class A-2)","TON",null,null,0,63.34,0]
[0,"709-05.08","Machined Rip-Rap (Class B)","TON",null,null,0,57.156190471986264,0]
[0,"709-05.09","Machined Rip-Rap (Class C)","TON",null,null,0,63.193258099745172,0]
[0,"709-05.10","Machined Rip-Rap","CY",null,null,0,150,0]
[0,"709-05.12","Machined Rip-Rap","TON",null,null,0,40,0]
[0,"709-05.81","Rock Riffles","LS",null,null,0,9700,0]
[0,"709-05.83","Embedded Riprap","TON",null,null,0,32.32,0]
[0,"709-10.01","Gabions","CY",null,null,0,406,0]
[0,"709-10.02","Gabions","CY",null,null,0,170,0]
[1,null,null,null,null,null,null,"RIP-RAP & SLOPE PROTECTION TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(SUM(I762:I777),-2)<0,0,ROUNDUP(SUM(I762:I777),-2))","v":0}]
[1]
[1,"Clearing and Grubing"]
[{"$f":"IF(G781>0,1,0)","v":1},"201-01","Clearing and Grubbing","LS",null,null,{"$f":"F781+1","v":1},{"$f":"Tool!P217","v":0},{"$f":"G781*H781","v":0}]
[1,null,null,null,null,null,null,"CLEAR AND GRUBBING TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(SUM(I781),-2)<0,0,ROUNDUP(SUM(I781),-2))","v":0}]
[1]
[1,"Railroad At-Grade Crossing"]
[{"$f":"IF(G785>0,1,0)","v":0},"N/A","Railroad Cross Lights and Gates","LS",null,null,{"$f":"F785","v":0},350000,{"$f":"G785*H785","v":0}]
[1,null,null,null,null,null,null,"RAILROAD CROSSING OR SEPARATION TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(I785,-2)<0,0,ROUNDUP(I785,-2))","v":0}]
[1]
[1,"Utilties"]
[{"$f":"IF(G789>0,1,0)","v":0},"N/A","Overhead Distribution","LM",{"$f":"Tool!D211","v":0},null,{"$f":"E789+F789","v":0},{"$f":"1650000*1.2","v":1980000},{"$f":"IF(G789<>\"\",G789*H789,\"\")","v":0}]
[0,"N/A","Overhead Transmission","LM",{"$f":"Tool!D212","v":0},null,0,{"$f":"8110000*(1.2)","v":9732000},0]
[0,"N/A","Underground Power","LM",{"$f":"Tool!D214","v":0},null,0,{"$f":"1650000*1.2","v":1980000},0]
[0,"N/A","Underground Communication","LM",{"$f":"Tool!D217","v":0},null,0,{"$f":"1660000*1.2","v":1992000},0]
[0,"N/A","Underground Gas","LM",{"$f":"Tool!D216","v":0},null,0,{"$f":"1740000*1.2","v":2088000},0]
[0,"N/A","Underground Water","LM",{"$f":"Tool!D215","v":0},null,0,{"$f":"2200000*1.2","v":2640000},0]
[0,"N/A","Underground Sewer","LM",{"$f":"Tool!D218","v":0},null,0,{"$f":"1390000*1.2","v":1668000},0]
[0,"N/A","Early Utilities Estimate from Construction Division","LS",null,null,{"$f":"F796","v":0},{"$f":"Tool!G211","v":0},{"$f":"H796","v":0}]
[1,null,null,null,null,null,null,"UTILITIES TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(SUM(I789:I796),-2)<0,0,ROUNDUP(SUM(I789:I796),-2))","v":0}]
[1]
[1,"Right-of-Way"]
[{"$f":"IF(G800>0,1,0)","v":0},"N/A","Right-of-Way","LS",{"$f":"IF(Tool!D44=\"No Errors\",1,0)","v":0},null,{"$f":"E800+F800","v":0},{"$f":"Tool!G210+Tool!J234","v":0},{"$f":"H800","v":0}]
[1,null,null,null,null,null,null,"RIGHT-OF-WAY TOTAL (ROUNDED)",{"$f":"IF(ROUNDUP(I800,-2)<0,0,ROUNDUP(I800,-2))","v":0}]
[1]
[1]
[1]

{"sheet":"Summary","index":5,"n_rows":69,"n_cols":18,"rows_kept":69,"cut":false,"hidden":true,"merged":[[2,7,3,7],[2,1,3,6],[34,14,34,17],[49,15,49,16],[37,15,37,16],[38,15,38,16],[39,15,39,16],[41,15,41,16],[42,15,42,16],[43,15,43,16],[40,15,40,16],[44,15,44,16],[46,15,46,16],[47,15,47,16],[48,15,48,16],[45,14,45,17],[38,9,38,12],[23,9,23,12],[36,15,36,16],[35,14,35,17],[2,9,2,17]]}
[]
[]
[null,"TOOL ITEM SUMMARY",null,null,null,null,null,{"$f":"IF(Tool!Z23=\"ON\",\"ON\",\"OFF\")","v":"OFF"}]
[]
[null,"ITEM NUMBER","DESCRIPTION","UNIT","QUANTITY","UNIT PRICE","COST",null,null,"Roadway Summary (Travel Lanes)",null,null,null,null,"Roadway Summary (Shoulder)"]
[null,"105-01","Construction Stakes, Lines, and Grades","LS",{"$f":"IF(SUM(Terrain!AB25:AB28)>=0,IF(H3=\"ON\",IF(Tool!J54-Tool!J52>0,1,0),0),0)","v":0},null,{"$f":"E6*F6","v":0},null,null,"Item Summary",null,null,null,null,"Item Summary"]
[null,"203-01","Road & Drainage Excavation (Unclassified)","C.Y.",{"$f":"IF(AND(SUM(Terrain!AB25:AB28)>=0,H3=\"ON\"),Q27,0)","v":0},{"$f":"'Finalize Items'!H380","v":17.18},{"$f":"E7*F7","v":0},null,null,"Item #","Description","Quantity","% Cost",null,"Item #","Description","Quantity","% Cost"]
[null,"203-03","Borrow Excavation (Unclassified)","C.Y.",{"$f":"IF(AND(SUM(Terrain!AB25:AB28)>=0,H3=\"ON\"),Q28,0)","v":0},{"$f":"'Finalize Items'!H388","v":19.3},{"$f":"E8*F8","v":0},null,null,"411-03.10","\"D\" mix (TON)",{"$f":"Roadway!O9","v":0},null,null,"411-01","\"E\" mix (TON)",{"$f":"Roadway!S9","v":0}]
[null,"203-02.01","Borrow Excavation (Graded Solid Rock)","TON",{"$f":"Terrain!AC12","v":0},{"$f":"'Finalize Items'!H386","v":60.67},null,null,null,"307-02.08","\"BM-2\" mix (TON)",{"$f":"Roadway!O10","v":0},null,null,"403-01","Tack (TON)",{"$f":"Roadway!S10","v":0}]
[null,"303-01","Mineral Aggregate, Type A Base, Grading D","TON",{"$f":"IF(H3=\"ON\",L16+L32+Q13+L53,0)","v":0},{"$f":"'Finalize Items'!H37","v":40.6},{"$f":"E10*F10","v":0},null,null,"307-02.01","\"A\" mix (TON)",{"$f":"Roadway!O11","v":0},null,null,"307-02.08","\"BM-2\" mix (TON)",{"$f":"Roadway!S11","v":0}]
[null,"307-02.01","Asphalt Concrete Mix (PG70-22) (BPMB-HM) Grading A","TON",{"$f":"IF(H3=\"ON\",L10,0)","v":0},{"$f":"'Finalize Items'!H44","v":124.26208009204254},0,null,null,"307-02.03","GR \"A-S\" Mix (TON)",{"$f":"Roadway!O12","v":0},null,null,"402-01","Prime Coat (TON)",{"$f":"Roadway!S12","v":0}]
[null,"307-02.02","Asphalt Cement (PG70-22)(BPMB-HM) Grading A-S","TON",{"$f":"IF(H3=\"ON\",L12,0)","v":0},{"$f":"'Finalize Items'!#REF!","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,null,"307-02.02","GR \"A-S\" Cement (TON)",{"$f":"Roadway!O13","v":0},null,null,"402-02","Agg. Cover (TON)",{"$f":"Roadway!S13","v":0}]
[null,"307-02.03","Aggregate (BPMB-HM) Grading A-S Mix","TON",{"$f":"IF(H3=\"ON\",L11,0)","v":0},{"$f":"'Finalize Items'!H45","v":124.26784422722803},0,null,null,"403-01","Tack (TON)",{"$f":"Roadway!O14","v":0},null,null,"303-01","Stone (Asphalt) (TON)",{"$f":"Roadway!S14","v":0}]
[null,"307-02.08","Asphalt Concrete Mix (PG70-22) (BPMB-HM) Grading B-M2","TON",{"$f":"IF(H3=\"ON\",L9+L29+Q10,0)","v":0},{"$f":"'Finalize Items'!H46","v":130.98531901543353},0,null,null,"402-01","Prime Coat (TON)",{"$f":"Roadway!O15","v":0},null,null,"501-01.03","Concrete Pvmt 10\" (SY)",{"$f":"Roadway!S15","v":0}]
[null,"402-01","Bituminous Material For Prime Coat (PC)","TON",{"$f":"IF(H3=\"ON\",L14+Q11+L30,0)","v":0},{"$f":"'Finalize Items'!H55","v":978.2},0,null,null,"402-02","Agg. Cover (TON)",{"$f":"Roadway!O16","v":0},null,null,"313-03","Treated Permeable Base",{"$f":"Roadway!S16","v":0}]
[null,"402-02","Aggregate For Cover Material (PC)","TON",{"$f":"IF(H3=\"ON\",L15+Q12+L31,0)","v":0},{"$f":"'Finalize Items'!H56","v":75.900000000000006},0,null,null,"303-01","Stone (Asphalt) (TON)",{"$f":"Roadway!O17","v":0}]
[null,"403-01","Bituminous Material For Tack Coat (TC)","TON",{"$f":"IF(H3=\"ON\",L13+L28+Q9,0)","v":0},{"$f":"'Finalize Items'!H57","v":974.85},0,null,null,"501-01.03","Concrete Pvmt 10\" (SY)",{"$f":"Roadway!O18","v":0}]
[null,"411-01.07","ACS (PG64-22) GR \"E\"","TON",{"$f":"IF(H3=\"ON\",Q8+L27,0)","v":0},{"$f":"'Finalize Items'!H69","v":128.63},0,null,null,"313-03","Treated Permeable Base",{"$f":"Roadway!O19+Roadway!S16","v":0}]
[null,"411-02.10","ACS Mix(PG70-22) Grading D","TON",{"$f":"IF(H3=\"ON\",L8,0)","v":0},{"$f":"'Finalize Items'!H71","v":146.95076747266484},0,null,null,"71-02","Agg. Underdrains (LF)",{"$f":"Roadway!O20","v":0}]
[null,"313-03","Treated Permeable Base","SY",{"$f":"IF(H3=\"ON\",L18+Q15,0)","v":0},{"$f":"'Finalize Items'!H91","v":32.69},0,null,null,"415-01.01","Cold Planing (SY)",{"$f":"Roadway!O21","v":0}]
[null,"501-01.03","Portland Cement Concrete 10\"","SY",{"$f":"IF(H3=\"ON\",Q14+L17,0)","v":0},{"$f":"'Finalize Items'!H94","v":155.51},0,null,null,"202-03.01","Asphalt Removal (SY)",{"$f":"Roadway!O22","v":0}]
[null,"604-01.01","CLASS A CONCRETE (ROADWAY)","CY",{"$f":"IF(H3=\"ON\",Roadway!S19,0)","v":0},{"$f":"'Finalize Items'!H104","v":1333.8},0,null,null,"202-03.02","Concrete Removal (CY)",{"$f":"Roadway!O23","v":0}]
[null,"415-01.02","Cold Planning Bituminous Pavement","S.Y.",{"$f":"IF(H3=\"ON\",L20,0)","v":0},{"$f":"'Finalize Items'!H31","v":9.6},{"$f":"E23*F23","v":0}]
[null,"202-03.01","Asphalt Removal (SY)","SY",{"$f":"IF(H3=\"ON\",L21,0)","v":0},{"$f":"'Finalize Items'!H22","v":20.64},0,null,null,"Median Summary",null,null,null,null,"Terrain Summary"]
[null,"202-03.02","Concrete Removal (CY)","CY",{"$f":"IF(H3=\"ON\",L22,0)","v":0},{"$f":"'Finalize Items'!H23","v":45.23},0,null,null,"Item Summary",null,null,null,null,"Item Summary"]
[null,"502-04.01","Sawing Concrete Pvmt","L.F.",{"$f":"Roadway!U28/10","v":0},{"$f":"'Finalize Items'!H98","v":16.98},0,null,null,"Item #","Description","Quantity","% Cost",null,"Item #","Description","Quantity","% Cost"]
[null,"607-05.02","24\" Concrete Pipe Culvert (Class III)","L.F.",{"$f":"IF(H3=\"ON\",L47+L34,0)","v":0},{"$f":"'Finalize Items'!H179","v":137.55000000000001},0,null,null,"411-01","\"E\" mix (TON)",{"$f":"Median!M8","v":0},null,null,"203-01","R&D Excav. (UnC)",{"$f":"Terrain!AC10","v":0}]
[null,"611-07.01","Class A Concrete (Pipe Endwalls)","C.Y.",{"$f":"IF(H3=\"ON\",L48,0)","v":0},{"$f":"'Finalize Items'!H238","v":2156.1799999999998},0,null,null,"403-01","Tack (TON)",{"$f":"Median!M9","v":0},null,null,"203-03","Borrow Excav. (UnC)",{"$f":"Terrain!AC11","v":0}]
[null,"611-07.02","Steel Bar Reinforcement (Pipe Endwalls)","LB.",{"$f":"IF(H3=\"ON\",L49,0)","v":0},{"$f":"'Finalize Items'!H239","v":4.08},0,null,null,"307-02.08","\"BM-2\" mix (TON)",{"$f":"Median!M10","v":0},null,null,"705-02.02","Single Guardrail (Type 2)",{"$f":"Terrain!AC13","v":0}]
[null,"611-12.02","Catch Basins, Type 12, > 4' - 8' Depth","EACH",{"$f":"IF(H3=\"ON\",L44+L36,0)","v":0},{"$f":"'Finalize Items'!H254","v":8113.47},0,null,null,"402-01","Prime Coat (TON)",{"$f":"Median!M11","v":0},null,null,"705-04.07","Type 38",{"$f":"Terrain!AC14","v":0}]
[null,"611-14.02","Catch Basins, Type 14, > 4' - 8' Depth","EACH",{"$f":"IF(H3=\"ON\",L45,0)","v":0},{"$f":"'Finalize Items'!H260","v":11628.28},0,null,null,"402-02","Agg. Cover (TON)",{"$f":"Median!M12","v":0},null,null,"705-04.09","Earth Pad For Type 38",{"$f":"Terrain!AC15","v":0}]
[null,"611-42.02","Catch Basins, Type 42, > 4' - 8' Depth","EACH",{"$f":"IF(H3=\"ON\",L46,0)","v":0},{"$f":"'Finalize Items'!H301","v":8249.02},0,null,null,"303-01","Stone ",{"$f":"Median!M13","v":0}]
[null,"701-01.01","Concrete Sidewalk (4\")","S.F.",{"$f":"IF(H3=\"ON\",L42+L37,0)","v":0},{"$f":"'Finalize Items'!H362","v":9.89},0,null,null,"711-05.71","Barrier Wall",{"$f":"Median!M14","v":0}]
[null,"702-03","Concrete Combined Curb & Gutter","C.Y.",{"$f":"IF(H3=\"ON\",L43+L35,0)","v":0},{"$f":"'Finalize Items'!H372","v":603.04},0,null,null,"607-05.02","24\" Concrete Pipe Culvert (Class III)",{"$f":"Median!M15","v":0}]
[null,"705-02.02","Single Guardrail (Type 2)","L.F.",{"$f":"IF(H3=\"ON\",Q29,0)","v":0},{"$f":"'Finalize Items'!H479","v":34.659999999999997},0,null,null,"702-03","Concrete Combined Curb & Gutter",{"$f":"Median!M16","v":0},null,null,"Bridge & Structure Summary"]
[null,"705-04.07","Tan Energy Absg Term (NCHRP, 350, TL3)","EACH      ",{"$f":"IF(H3=\"ON\",Q30+R49,0)","v":0},{"$f":"'Finalize Items'!H486","v":3697.01},0,null,null,"611-12.02","Catch Basins, Type 12, > 8' - 12' Depth",{"$f":"Median!M17","v":0},null,null,"Item Summary"]
[null,"705-04.09","Earth Pad for Type 38 GR End Treatment","EACH",{"$f":"IF(H3=\"ON\",Q31+R50,0)","v":0},{"$f":"'Finalize Items'!H487","v":1519.43},0,null,null,"701-01.01 ","4\" Concrete",{"$f":"Median!M18","v":0},null,null,"Number","Description",null,"Area (SF)"]
[null,"705-01.01","Guardrail @ Bridge Ends (LF)","L.F.",{"$f":"IF(H3=\"ON\",R48,0)","v":0},{"$f":"'Finalize Items'!H477","v":112.09},0,null,null,null,null,null,null,null,{"$f":"Bridges!B9","v":0},"Bridge Removal:",null,{"$f":"Bridges!E9","v":0}]
[null,710.02,"Aggregate Underdrains (with pipe)","L.F.",{"$f":"IF(H3=\"ON\",L19,0)","v":0},{"$f":"'Finalize Items'!H334","v":13.31},0,null,null,"Drainage Summary",null,null,null,null,{"$f":"Bridges!B10","v":0},"Widen Existing Bridge (Box):",null,{"$f":"Bridges!E10","v":0}]
[null,"711-05.71","Barrier Wall","L.F.",{"$f":"L33","v":0},null,null,null,null,"Item Summary",null,null,null,null,{"$f":"Bridges!B11","v":0},"Widen Existing Bridge (Concrete Girder):",null,{"$f":"Bridges!E11","v":0}]
[null,"712-01","Traffic Control","LS",{"$f":"IF(H3=\"ON\",1,0)","v":0},{"$f":"0.1*(SUM(G6:G39)+SUM(G42:G65))","v":{"$error":"#REF!"}},{"$f":"E41*F41","v":{"$error":"#REF!"}},null,null,"Item #","Description","Quantity","% Cost",null,{"$f":"Bridges!B13","v":0},"Widen Existing Bridge (Steel Girder):",null,{"$f":"Bridges!E13","v":0}]
[null,"712-02.02","Interconnected Portable Barrier Rail","L.F.",{"$f":"IF(E19=0,0,IF(H3=\"ON\",G69*0.05*5280,0))","v":0},{"$f":"'Finalize Items'!H550","v":37.96},{"$f":"E42*F42","v":0},null,null,"701-01.01","Concrete Sidewalk (4\")",{"$f":"Drainage!L8","v":0},null,null,{"$f":"Bridges!B14","v":0},"New Bridge (Box):",null,{"$f":"Bridges!E14","v":0}]
[null,"713-16.20","Signs","EACH",{"$f":"IF(H3=\"ON\",G69*(Drainage!K27*40+Drainage!K28*100),0)","v":0},150,{"$f":"E43*F43","v":0},null,null,"702-03","Concrete Combined Curb & Gutter",{"$f":"Drainage!L9","v":0},null,null,{"$f":"Bridges!B15","v":0},"New Bridge (Concrete Girder):",null,{"$f":"Bridges!E15","v":0}]
[null,"716-13.06","Spray Thermo P.M. (40 mil 4\")","L.M.",{"$f":"IF(E19=0,0,IF(H3=\"ON\",((2+Roadway!S41/5)*G69),0))","v":0},{"$f":"'Finalize Items'!H732","v":1654.2273950855883},0,null,null,"611-12.03","Catch Basins, Type 12, > 8' - 12' Depth",{"$f":"Drainage!L10","v":0},null,null,{"$f":"Bridges!B17","v":0},"New Bridge (Steel Girder):",null,{"$f":"Bridges!E17","v":0}]
[null,"801-01","Seeding (With Mulch)","UNIT",{"$f":"IF(H3=\"ON\",L50,0)","v":0},{"$f":"'Finalize Items'!H513","v":65.16},0,null,null,"611-14.03","Catch Basins, Type 14, > 8' - 12' Depth",{"$f":"Drainage!L11","v":0},null,null,null,"Retaining Wall",null,{"$f":"Bridges!E22","v":0}]
[null,"801-01.07","Temporary Seeding (With Mulch)","UNIT",{"$f":"IF(H3=\"ON\",L51,0)","v":0},{"$f":"'Finalize Items'!H515","v":45.9},0,null,null,"611-42.02","Catch Basins, Type 42, > 4' - 8' Depth",{"$f":"Drainage!L12","v":0},null,null,"Additional Safety Features"]
[null,"801-02","Seeding (Without Mulch)","UNIT",{"$f":"IF(H3=\"ON\",L52,0)","v":0},{"$f":"'Finalize Items'!H516","v":42.23},0,null,null,"607-05.02","24\" Concrete Pipe Culvert (Class III)",{"$f":"Drainage!L13","v":0},null,null,"Item #","Description",null,"Quantity"]
[null,"N/A","Traffic Signal","EACH",{"$f":"IF(AND(Tool!F36>0,H3=\"ON\"),Tool!F36,0)","v":0},120000,0,null,null,"611-07.01","Class A Concrete (Pipe Endwalls)",{"$f":"Drainage!L14","v":0},null,null,"705-01.01","Guardrail @ Bridge Ends (LF)",null,{"$f":"25*4*(O39+O40+O41+O42+O43+O44)","v":0}]
[null,"N/A","ITS","L.M.",{"$f":"IF(AND(Tool!F37>0,H3=\"ON\"),Tool!F37,0)","v":0},200000,0,null,null,"611-07.02","Steel Bar Reinforcement (Pipe Endwalls)",{"$f":"Drainage!L15","v":0},null,null,"705-04.07","Type 38 Guadrail End Treatment (EACH)",null,{"$f":"4*(O39+O40+O41+O42+O43+O44)","v":0}]
[null,"N/A","SHARED-USE PATH","L.M.",{"$f":"IF(AND(Tool!#REF!>0,H3=\"ON\"),Tool!#REF!,0)","v":{"$error":"#REF!"}},250000,{"$error":"#REF!"},null,null,"801-01","Seeding (With Mulch)",{"$f":"Drainage!L16","v":0},null,null,"705-04.09","Earth Pad-Type 38 Guadrail End Treatment (EACH)",null,{"$f":"4*(O39+O40+O41+O42+O43+O44)","v":0}]
[null,"N/A","ROUNDABOUT","EACH",{"$f":"IF(AND(Tool!#REF!>0,H3=\"ON\"),Tool!#REF!,0)","v":{"$error":"#REF!"}},1100000,{"$error":"#REF!"},null,null,"801-01.07","Temporary Seeding (With Mulch)",{"$f":"Drainage!L17","v":0}]
[null,"N/A","Bridge Removal:","S.F.",{"$f":"R38","v":0},20,0,null,null,"801-02","Seeding (Without Mulch)",{"$f":"Drainage!L18","v":0},null,null,{"$f":"Median!M17+Drainage!L10","v":0}]
[null,"N/A","Widen Existing Bridge (Box):","S.F.",{"$f":"R39","v":0},42,0,null,null,"303-01","Stone CY)",{"$f":"Drainage!L19","v":0},null,null,{"$f":"Terrain!AC14","v":0}]
[null,"N/A","Widen Existing Bridge (Concrete Girder):","S.F.",0,48,0]
[null,"N/A","Widen Existing Bridge (Steel Girder):","S.F.",0,60,0]
[null,"N/A","New Bridge (Box):","S.F.",0,105,0]
[null,"N/A","New Bridge (Concrete Girder):","S.F.",0,125,0]
[null,"N/A","New Bridge (Steel Girder):","S.F.",0,150,0]
[null,"N/A","Retaining Wall","S.F.",{"$f":"R45","v":0},75,0]
[null,"N/A","Urban Standard Diamond","EACH",{"$f":"IF(H3=\"ON\",Tool!AR215,0)","v":0},25000000,0]
[null,"N/A","Urban - Tight Diamond","EACH",{"$f":"IF(H3=\"ON\",Tool!AS215,0)","v":0},30000000,0]
[null,"N/A","Urban - Single Point Urban Interchange (SPUI)","EACH",{"$f":"IF(H3=\"ON\",Tool!AT215,0)","v":0},35000000,0]
[null,"N/A","Rural - Diamond","EACH",{"$f":"IF(H3=\"ON\",Tool!AR213,0)","v":0},12500000,0]
[null,"N/A","Rural - Partial Cloverleaf","EACH",{"$f":"IF(H3=\"ON\",Tool!AS213,0)","v":0},15000000,0]
[null,"N/A","Rural - Full Cloverleaf","EACH",{"$f":"IF(H3=\"ON\",Tool!AT213,0)","v":0},17500000,0]
[null,"709-05.05","Machined Rip-Rap (Class A-3)","TON",{"$f":"IF(G69>0,IF(AND((Tool!E64-Tool!D64)>0,Tool!F64<>\"\",H3=\"ON\"),Bridges!E28,0),0)","v":0}]
[]
[]
[null,null,null,null,null,"Project Length:",{"$f":"IF(Roadway!B9<>\"\",IF((Tool!$J$54-Tool!$J$52)>0,(Tool!$J$54-Tool!$J$52),0),0)","v":0}]

{"sheet":"Cost Estimate","index":6,"n_rows":174,"n_cols":20,"rows_kept":174,"cut":false,"hidden":false,"merged":[[3,2,3,8],[11,1,12,2],[4,2,4,7],[5,2,5,7],[8,2,8,7],[56,11,56,12],[56,1,56,2],[47,1,48,2],[15,1,15,2],[16,1,16,2],[17,1,17,2],[18,1,18,2],[19,1,19,2],[20,1,20,2],[51,9,52,9],[31,1,31,2],[13,1,13,2],[14,1,14,2],[11,9,13,9],[23,1,23,2],[24,1,24,2],[0,11,0,12],[0,1,0,9],[57,1,57,2],[22,1,22,2],[57,11,57,12],[11,11,13,11],[11,12,13,12],[7,9,9,9],[50,1,50,2],[49,1,49,2],[21,1,21,2],[1,2,1,7],[7,2,7,7],[2,2,2,8],[55,11,55,12],[54,11,54,12],[58,1,58,2],[51,1,52,2],[25,1,25,2],[26,1,26,2],[27,1,27,2],[28,1,28,2],[29,1,29,2],[30,1,30,2],[37,1,37,2],[43,1,43,2],[32,1,32,9],[38,1,38,9],[58,11,58,12],[47,9,48,9]]}
[1,"COST ESTIMATE SUMMARY"]
[1,"Route:"]
[1,"Termini:"]
[1,"Scope of Work:"]
[1,"Project Type of Work:"]
[1,"County:",null,null,null,null,null,null,null,"Estimate Developed By"]
[1,"Length:",{"$f":"Tool!J54-Tool!J52","v":0},"Miles",null,null,null,null,null,"Initial/Organization"]
[1,"Date:",{"$f":"TODAY()","v":"2025-04-03"}]
[1,"Estimate Type:","Design-Bid-Build"]
[1,"Years Inflated:"]
[1]
[1,"DESCRIPTION",null,"LOCAL",null,"STATE",null,"FEDERAL",null,"TOTAL",null,"DBB & DB % Constributions","CMGC % Contributions"]
[1,null,null,0,null,0,null,0]
[1,"Construction Items",null,null,null,null,null,null,null,null,null,null,null,{"$f":"(1+'Inflated Cost'!$D$57)^'Cost Estimate'!$C$10","v":1},null,null,null,"Threshold","Round to"]
[1,"Removal Items",null,{"$f":"MROUND($J15*E15,100)","v":0},{"$f":"$D$13","v":0},{"$f":"MROUND($J15*G15,100)","v":0},{"$f":"$F$13","v":0},{"$f":"MROUND($J15*I15,100)","v":0},{"$f":"$H$13","v":0},{"$f":"IF(N15<$R$15,MROUND(N15,$S$15),IF(AND(N15>=$R$15,N15<$R$16),MROUND(N15,$S$16),IF(AND(N15>=$R$16,N15<$R$17),MROUND(N15,$S$17),IF(AND(N15>=$R$17,N15<$R$18),MROUND(N15,$S$18),IF(AND(N15>=$R$18,N15<$R$19),MROUND(N15,$S$19),IF(AND(N15>=$R$19,N15<$R$20),MROUND(N15,$S$20),IF(N15>=$R$21,MROUND(N15,$S$21))))))))","v":0},null,{"$f":"IF(SUM($J$15:$J$37)>0,J15/SUM($J$15:$J$37),0)","v":0},{"$f":"IF((SUM($J$15:$J$32)+SUM($J$40:$J$43))>0,J15/(SUM($J$15:$J$32)+SUM($J$40:$J$43)),0)","v":0},{"$f":"'Finalize Items'!I33*$N$14","v":0},null,"TIER 1","<",1000,1]
[1,"Asphalt Paving",null,{"$f":"MROUND($J16*E16,100)","v":0},{"$f":"$D$13","v":0},{"$f":"MROUND($J16*G16,100)","v":0},{"$f":"$F$13","v":0},{"$f":"MROUND($J16*I16,100)","v":0},{"$f":"$H$13","v":0},0,null,0,0,{"$f":"'Finalize Items'!I87*$N$14","v":0},null,"TIER 2","<",10000,10]
[1,"Concrete Pavement",null,0,0,0,{"$f":"$F$13","v":0},0,0,0,null,0,0,{"$f":"'Finalize Items'!I106*$N$14","v":0},null,"TIER 3","<",100000,100]
[1,"Drainage",null,0,0,0,0,0,0,0,null,0,0,{"$f":"'Finalize Items'!I355*$N$14","v":0},null,"TIER 4","<",1000000,1000]
[1,"Appurtenances",null,0,0,0,0,0,0,0,null,0,0,{"$f":"'Finalize Items'!I377*$N$14","v":0},null,"TIER 5","<",10000000,10000]
[1,"Structures & Contingency",null,0,0,0,0,0,0,0,null,0,0,{"$f":"'Finalize Items'!I452*$N$14","v":0},null,"TIER 6","<",100000000,100000]
[1,"Fencing",null,0,0,0,0,0,0,0,null,0,0,{"$f":"'Finalize Items'!I759*$N$14","v":0},null,"TIER 7",">",100000000,1000000]
[1,"Signalization & Lighting",null,0,0,0,0,0,0,0,null,0,0,{"$f":"'Finalize Items'!I474*$N$14","v":0}]
[1,"Railroad Crossing",null,0,0,0,0,0,0,0,null,0,0,{"$f":"'Finalize Items'!I786*$N$14","v":0}]
[1,"Earthwork",null,0,0,0,0,0,0,0,null,0,0,{"$f":"'Finalize Items'!I431*$N$14","v":0}]
[1,"Clearing and Grubbing",null,0,0,0,0,0,0,0,null,0,0,{"$f":"'Finalize Items'!I782*$N$14","v":0}]
[1,"Seeding & Sodding",null,0,0,0,0,0,0,0,null,0,0,{"$f":"'Finalize Items'!I543*$N$14","v":0}]
[1,"Rip-Rap or Slope Protection",null,0,0,0,0,0,0,0,null,0,0,{"$f":"'Finalize Items'!I778*$N$14","v":0}]
[1,"Guardrail ",null,0,0,0,0,0,0,0,null,0,0,{"$f":"'Finalize Items'!I510*$N$14","v":0}]
[1,"Signing ",null,0,0,0,0,0,0,0,null,0,0,{"$f":"'Finalize Items'!I641*$N$14","v":0}]
[1,"Pavement Markings ",null,0,0,0,0,0,0,0,null,0,0,{"$f":"'Finalize Items'!I737*$N$14","v":0}]
[1,"Traffic Control",null,0,0,0,0,{"$f":"MROUND($J31*I31,100)","v":0},0,0,null,0,0,{"$f":"'Finalize Items'!I551*$N$14","v":0}]
[1,"Construction Lines and Stakes",null,0,0,0,0,{"$f":"MROUND($J32*I32,100)","v":0},0,{"$f":"'Finalize Items'!I435","v":0},null,0,0]
[{"$f":"IF($C$9=$H$92,1,IF(OR($C$9=$H$89,$C$9=$H$90),1,0))","v":1},"DESIGN-BID-BUILD & DESIGN-BUILD PERCENTAGES"]
[1,"Mobilization ","5%",0,0,0,0,0,0,{"$f":"IF(N34<$R$15,MROUND(N34,$S$15),IF(AND(N34>=$R$15,N34<$R$16),MROUND(N34,$S$16),IF(AND(N34>=$R$16,N34<$R$17),MROUND(N34,$S$17),IF(AND(N34>=$R$17,N34<$R$18),MROUND(N34,$S$18),IF(AND(N34>=$R$18,N34<$R$19),MROUND(N34,$S$19),IF(AND(N34>=$R$19,N34<$R$20),MROUND(N34,$S$20),IF(N34>=$R$21,MROUND(N34,$S$21))))))))","v":0},null,{"$f":"IF(SUM($J$15:$J$37)>0,J34/SUM($J$15:$J$37),0)","v":0},null,{"$f":"SUM(J15:J30)*C34","v":0},null,null,null,"Min PE Percent",{"$f":"3/100","v":0.03}]
[1,"Allowances",0.1,0,0,0,0,0,0,0,null,{"$f":"IF(SUM($J$15:$J$37)>0,J35/SUM($J$15:$J$37),0)","v":0},null,{"$f":"(SUM(J15:J30))*C35","v":0},null,null,null,"Max PE Percent",0.1]
[1,"Const. Contingency (Structures Not Included)",0.3,0,0,0,0,0,0,0,null,{"$f":"IF(SUM($J$15:$J$37)>0,J36/SUM($J$15:$J$37),0)","v":0},null,{"$f":"(SUM(J15:J19)+SUM(J21:J30)+SUM(J34:J35))*C36","v":0}]
[1,"  Const. Eng. & Inspec.",0.1,0,{"$f":"$D$13","v":0},0,0,{"$f":"MROUND($J37*I37,100)","v":0},0,0,null,{"$f":"IF(SUM($J$15:$J$37)>0,J37/SUM($J$15:$J$37),0)","v":0},null,{"$f":"((SUM(J15:J32)+SUM(J34:J36)+SUM(J46:J47))*C37)","v":0}]
[1,"   Construction Estimate - DBB & DB",null,{"$f":"L75*E38","v":0},0,{"$f":"J38*G38","v":0},{"$f":"$F$13","v":0},{"$f":"MROUND(J38*I38,100)","v":0},{"$f":"$H$13","v":0},{"$f":"IF(N38<$R$15,MROUND(N38,$S$15),IF(AND(N38>=$R$15,N38<$R$16),MROUND(N38,$S$16),IF(AND(N38>=$R$16,N38<$R$17),MROUND(N38,$S$17),IF(AND(N38>=$R$17,N38<$R$18),MROUND(N38,$S$18),IF(AND(N38>=$R$18,N38<$R$19),MROUND(N38,$S$19),IF(AND(N38>=$R$19,N38<$R$20),MROUND(N38,$S$20),IF(N38>=$R$21,MROUND(N38,$S$21))))))))","v":0},null,null,null,{"$f":"SUM(J15:J37)","v":0}]
[{"$f":"IF($C$9=$H$92,1,IF($C$9=$H$91,1,0))","v":0},"CMGC (HIGH RISK) PERCENTAGES"]
[0,"Mobilization & CM/GC Risk Fees",0.1,{"$f":"MROUND($J40*E40,100)","v":0},0,{"$f":"MROUND($J40*G40,100)","v":0},{"$f":"$F$13","v":0},{"$f":"MROUND($J40*I40,100)","v":0},{"$f":"$H$13","v":0},{"$f":"IF(N40<$R$15,MROUND(N40,$S$15),IF(AND(N40>=$R$15,N40<$R$16),MROUND(N40,$S$16),IF(AND(N40>=$R$16,N40<$R$17),MROUND(N40,$S$17),IF(AND(N40>=$R$17,N40<$R$18),MROUND(N40,$S$18),IF(AND(N40>=$R$18,N40<$R$19),MROUND(N40,$S$19),IF(AND(N40>=$R$19,N40<$R$20),MROUND(N40,$S$20),IF(N40>=$R$21,MROUND(N40,$S$21))))))))","v":0},null,null,{"$f":"IF((SUM($J$15:$J$32)+SUM($J$40:$J$43))>0,J40/(SUM($J$15:$J$32)+SUM($J$40:$J$43)),0)","v":0},{"$f":"SUM(J15:J31)*C40","v":0}]
[0,"Additional Items",0.1,0,0,0,0,{"$f":"MROUND($J41*I41,100)","v":0},0,{"$f":"IF(N41<$R$15,MROUND(N41,$S$15),IF(AND(N41>=$R$15,N41<$R$16),MROUND(N41,$S$16),IF(AND(N41>=$R$16,N41<$R$17),MROUND(N41,$S$17),IF(AND(N41>=$R$17,N41<$R$18),MROUND(N41,$S$18),IF(AND(N41>=$R$18,N41<$R$19),MROUND(N41,$S$19),IF(AND(N41>=$R$19,N41<$R$20),MROUND(N41,$S$20),IF(N41>=$R$21,MROUND(N41,$S$21))))))))","v":0},null,null,{"$f":"IF((SUM($J$15:$J$32)+SUM($J$40:$J$43))>0,J41/(SUM($J$15:$J$32)+SUM($J$40:$J$43)),0)","v":0},{"$f":"(SUM(J15:J31))*C41","v":0}]
[0,"Const. Contingency (Structures Not Included)",0.3,0,0,0,0,0,0,0,null,null,{"$f":"IF((SUM($J$15:$J$32)+SUM($J$40:$J$43))>0,J42/(SUM($J$15:$J$32)+SUM($J$40:$J$43)),0)","v":0},{"$f":"(SUM(J15:J19)+SUM(J21:J31)+SUM(J34:J35))*C42","v":0}]
[0,"  Const. Eng. & Inspec.",0.1,0,{"$f":"$D$13","v":0},0,0,0,0,{"$f":"IF(N43<$R$15,MROUND(N43,$S$15),IF(AND(N43>=$R$15,N43<$R$16),MROUND(N43,$S$16),IF(AND(N43>=$R$16,N43<$R$17),MROUND(N43,$S$17),IF(AND(N43>=$R$17,N43<$R$18),MROUND(N43,$S$18),IF(AND(N43>=$R$18,N43<$R$19),MROUND(N43,$S$19),IF(AND(N43>=$R$19,N43<$R$20),MROUND(N43,$S$20),IF(N43>=$R$21,MROUND(N43,$S$21))))))))","v":0},null,null,{"$f":"IF((SUM($J$15:$J$32)+SUM($J$40:$J$43))>0,J43/(SUM($J$15:$J$32)+SUM($J$40:$J$43)),0)","v":0},{"$f":"((SUM(J15:J31)+SUM(J40:J42)+SUM(J46:J47))*C43)","v":0}]
[0,"   Construction Estimate - CMGC",null,{"$f":"L81*E44","v":0},0,{"$f":"J44*G44","v":0},{"$f":"$F$13","v":0},{"$f":"MROUND(J44*I44,100)","v":0},{"$f":"$H$13","v":0},{"$f":"IF(N44<$R$15,MROUND(N44,$S$15),IF(AND(N44>=$R$15,N44<$R$16),MROUND(N44,$S$16),IF(AND(N44>=$R$16,N44<$R$17),MROUND(N44,$S$17),IF(AND(N44>=$R$17,N44<$R$18),MROUND(N44,$S$18),IF(AND(N44>=$R$18,N44<$R$19),MROUND(N44,$S$19),IF(AND(N44>=$R$19,N44<$R$20),MROUND(N44,$S$20),IF(N44>=$R$21,MROUND(N44,$S$21))))))))","v":0},null,null,null,{"$f":"(SUM(J15:J32)+SUM(J40:J43))","v":0}]
[0,"Interchanges & Unique Intersections"]
[0,"Roundabouts",null,{"$f":"MROUND($J46*$D$13,100)","v":0},{"$f":"$D$13","v":0},{"$f":"MROUND($J46*G46,100)","v":0},{"$f":"$F$13","v":0},{"$f":"MROUND($J46*I46,100)","v":0},{"$f":"$H$13","v":0},{"$f":"IF(N46<$R$15,MROUND(N46,$S$15),IF(AND(N46>=$R$15,N46<$R$16),MROUND(N46,$S$16),IF(AND(N46>=$R$16,N46<$R$17),MROUND(N46,$S$17),IF(AND(N46>=$R$17,N46<$R$18),MROUND(N46,$S$18),IF(AND(N46>=$R$18,N46<$R$19),MROUND(N46,$S$19),IF(AND(N46>=$R$19,N46<$R$20),MROUND(N46,$S$20),IF(N46>=$R$21,MROUND(N46,$S$21))))))))","v":0},null,null,null,{"$f":"IF('Finalize Items'!I455<>\"\",'Finalize Items'!I455,0)*(1+'Inflated Cost'!$D$57)^'Cost Estimate'!$C$10","v":0}]
[0,"Interchanges",null,{"$f":"MROUND($J47*$D$13,100)","v":0},{"$f":"$D$13","v":0},{"$f":"MROUND($J47*G47,100)","v":0},{"$f":"$F$13","v":0},{"$f":"MROUND($J47*I47,100)","v":0},{"$f":"$H$13","v":0},{"$f":"IF(N47<$R$15,MROUND(N47,$S$15),IF(AND(N47>=$R$15,N47<$R$16),MROUND(N47,$S$16),IF(AND(N47>=$R$16,N47<$R$17),MROUND(N47,$S$17),IF(AND(N47>=$R$17,N47<$R$18),MROUND(N47,$S$18),IF(AND(N47>=$R$18,N47<$R$19),MROUND(N47,$S$19),IF(AND(N47>=$R$19,N47<$R$20),MROUND(N47,$S$20),IF(N47>=$R$21,MROUND(N47,$S$21))))))))","v":0},null,null,null,{"$f":"SUM('Finalize Items'!I456:I460)*(1+'Inflated Cost'!$D$57)^'Cost Estimate'!$C$10","v":0}]
[1,"Right-of-Way & Utilties",null,"LOCAL",null,"STATE",null,"FEDERAL",null,"TOTAL"]
[1,null,null,0,null,0,null,0]
[1,"Right-of-Way ",null,{"$f":"J50*E50","v":0},{"$f":"$D$49","v":0},{"$f":"J50*G50","v":0},{"$f":"$F$49","v":0},{"$f":"J50*I50","v":0},{"$f":"$H$49","v":0},{"$f":"IF(N50<$R$15,MROUND(N50,$S$15),IF(AND(N50>=$R$15,N50<$R$16),MROUND(N50,$S$16),IF(AND(N50>=$R$16,N50<$R$17),MROUND(N50,$S$17),IF(AND(N50>=$R$17,N50<$R$18),MROUND(N50,$S$18),IF(AND(N50>=$R$18,N50<$R$19),MROUND(N50,$S$19),IF(AND(N50>=$R$19,N50<$R$20),MROUND(N50,$S$20),IF(N50>=$R$21,MROUND(N50,$S$21))))))))","v":0},null,null,null,{"$f":"'Finalize Items'!I801","v":0}]
[1,"Utilities",null,{"$f":"J51*E51","v":0},{"$f":"$D$49","v":0},{"$f":"J51*G51","v":0},{"$f":"$F$49","v":0},{"$f":"J51*I51","v":0},{"$f":"$H$49","v":0},{"$f":"IF(N51<$R$15,MROUND(N51,$S$15),IF(AND(N51>=$R$15,N51<$R$16),MROUND(N51,$S$16),IF(AND(N51>=$R$16,N51<$R$17),MROUND(N51,$S$17),IF(AND(N51>=$R$17,N51<$R$18),MROUND(N51,$S$18),IF(AND(N51>=$R$18,N51<$R$19),MROUND(N51,$S$19),IF(AND(N51>=$R$19,N51<$R$20),MROUND(N51,$S$20),IF(N51>=$R$21,MROUND(N51,$S$21))))))))","v":0},null,null,null,{"$f":"'Finalize Items'!I797","v":0}]
[1,"Preliminary Engineering",null,"LOCAL",null,"STATE",null,"FEDERAL",null,"TOTAL"]
[1,null,null,0,null,0,null,0]
[{"$f":"IF($C$9=$H$92,1,IF($C$9=$H$89,1,0))","v":1},"  Prelim. Eng. ",0.1,{"$f":"$J54*D$53","v":0},null,{"$f":"$J54*F$53","v":0},null,{"$f":"$J54*H$53","v":0},null,{"$f":"IF(N54<$R$15,MROUND(N54,$S$15),IF(AND(N54>=$R$15,N54<$R$16),MROUND(N54,$S$16),IF(AND(N54>=$R$16,N54<$R$17),MROUND(N54,$S$17),IF(AND(N54>=$R$17,N54<$R$18),MROUND(N54,$S$18),IF(AND(N54>=$R$18,N54<$R$19),MROUND(N54,$S$19),IF(AND(N54>=$R$19,N54<$R$20),MROUND(N54,$S$20),IF(N54>=$R$21,MROUND(N54,$S$21))))))))","v":0},null,null,null,{"$f":"IF(IF(C5=$D$116,$J$76,IF(C5=$D$117,J77,(SUM(J15:J36))*C54))>O54,O54,(IF(C5=$D$116,$J$76,IF(C5=$D$117,J77,(SUM(J15:J36))*C54))))","v":0},5500000,"Design-Bid-Build"]
[{"$f":"IF($C$9=$H$92,1,IF($C$9=$H$90,1,0))","v":0},"  Prelim. Eng. (Design-Build)",0.1,{"$f":"$J55*D$53","v":0},null,0,null,{"$f":"$J55*H$53","v":0},null,{"$f":"IF(N55<$R$15,MROUND(N55,$S$15),IF(AND(N55>=$R$15,N55<$R$16),MROUND(N55,$S$16),IF(AND(N55>=$R$16,N55<$R$17),MROUND(N55,$S$17),IF(AND(N55>=$R$17,N55<$R$18),MROUND(N55,$S$18),IF(AND(N55>=$R$18,N55<$R$19),MROUND(N55,$S$19),IF(AND(N55>=$R$19,N55<$R$20),MROUND(N55,$S$20),IF(N55>=$R$21,MROUND(N55,$S$21))))))))","v":0},null,{"$f":"IF(N55>=O55,\"Discuss PE Cost w/ Alt Delivery\",\"\")","v":""},null,{"$f":"IF(IF(C5=$D$116,$J$76,IF(C5=$D$117,J77,(SUM(J15:J36))*C55))>O55,O55,IF(C5=$D$116,$J$76,IF(C5=$D$117,J77,(SUM(J15:J36))*C55)))","v":0},8000000,"Design-Build"]
[{"$f":"IF($C$9=$H$92,1,IF($C$9=$H$91,1,0))","v":0},"  Prelim. Eng. (CMGC/PDB)",0.1,0,null,0,null,0,null,{"$f":"IF(N56<$R$15,MROUND(N56,$S$15),IF(AND(N56>=$R$15,N56<$R$16),MROUND(N56,$S$16),IF(AND(N56>=$R$16,N56<$R$17),MROUND(N56,$S$17),IF(AND(N56>=$R$17,N56<$R$18),MROUND(N56,$S$18),IF(AND(N56>=$R$18,N56<$R$19),MROUND(N56,$S$19),IF(AND(N56>=$R$19,N56<$R$20),MROUND(N56,$S$20),IF(N56>=$R$21,MROUND(N56,$S$21))))))))","v":0},null,{"$f":"IF(N56>=O56,\"Discuss PE Cost w/ Alt Delivery\",\"\")","v":""},null,{"$f":"IF(IF(C5=$D$116,$J$76,IF(C5=$D$117,J77,(SUM(J15:J32)+SUM(J40:J42))*C56))>O56,O56,IF(C5=$D$116,$J$76,IF(C5=$D$117,J77,(SUM(J15:J32)+SUM(J40:J42))*C56)))","v":0},10000000,"CMGC"]
[{"$f":"IF($C$9=$H$92,1,IF($C$9=$H$89,1,0))","v":1},"Design-Bid-Build Project Cost",null,{"$f":"$M$76-($M$76-SUM(D38,D46,D47,D50,D51,D54))","v":0},null,{"$f":"$M$76-($M$76-SUM(F38,F46,F47,F50,F51,F54))","v":0},null,{"$f":"$M$76-($M$76-SUM(H38,H46,H47,H50,H51,H54))","v":0},null,{"$f":"IF(N57<$R$15,MROUND(N57,$S$15),IF(AND(N57>=$R$15,N57<$R$16),MROUND(N57,$S$16),IF(AND(N57>=$R$16,N57<$R$17),MROUND(N57,$S$17),IF(AND(N57>=$R$17,N57<$R$18),MROUND(N57,$S$18),IF(AND(N57>=$R$18,N57<$R$19),MROUND(N57,$S$19),IF(AND(N57>=$R$19,N57<$R$20),MROUND(N57,$S$20),IF(N57>=$R$21,MROUND(N57,$S$21))))))))","v":0},null,{"$f":"IF(J57>0,J57/Summary!$G$69,0)","v":0},null,{"$f":"(J38+SUM(J46:J47)+SUM(J50:J51)+J54)","v":0},null,null,null,null,null,"Per Mile Cost"]
[{"$f":"IF($C$9=$H$92,1,IF($C$9=$H$90,1,0))","v":0},"Design-Build Project Cost",null,{"$f":"$M$76-($M$76-SUM(D38,D46,D47,D50,D51,D55))","v":0},null,{"$f":"$M$76-($M$76-SUM(F38,F46,F47,F50,F51,F55))","v":0},null,{"$f":"$M$76-($M$76-SUM(H38,H46,H47,H50,H51,H55))","v":0},null,{"$f":"IF(N58<$R$15,MROUND(N58,$S$15),IF(AND(N58>=$R$15,N58<$R$16),MROUND(N58,$S$16),IF(AND(N58>=$R$16,N58<$R$17),MROUND(N58,$S$17),IF(AND(N58>=$R$17,N58<$R$18),MROUND(N58,$S$18),IF(AND(N58>=$R$18,N58<$R$19),MROUND(N58,$S$19),IF(AND(N58>=$R$19,N58<$R$20),MROUND(N58,$S$20),IF(N58>=$R$21,MROUND(N58,$S$21))))))))","v":0},null,{"$f":"IF(J58>0,J58/Summary!$G$69,0)","v":0},null,{"$f":"(J38+SUM(J46:J47)+SUM(J50:J51)+J55)","v":0},null,null,null,null,null,"Per Mile Cost"]
[{"$f":"IF($C$9=$H$92,1,IF($C$9=$H$91,1,0))","v":0},"CMGC/PDB Cost",null,{"$f":"$M$76-($M$76-SUM(D44,D46,D47,D50,D51,D56))","v":0},null,{"$f":"$M$76-($M$76-SUM(F44,F46,F47,F50,F51,F56))","v":0},null,{"$f":"$M$76-($M$76-SUM(H44,H46,H47,H50,H51,H56))","v":0},null,{"$f":"IF(N59<$R$15,MROUND(N59,$S$15),IF(AND(N59>=$R$15,N59<$R$16),MROUND(N59,$S$16),IF(AND(N59>=$R$16,N59<$R$17),MROUND(N59,$S$17),IF(AND(N59>=$R$17,N59<$R$18),MROUND(N59,$S$18),IF(AND(N59>=$R$18,N59<$R$19),MROUND(N59,$S$19),IF(AND(N59>=$R$19,N59<$R$20),MROUND(N59,$S$20),IF(N59>=$R$21,MROUND(N59,$S$21))))))))","v":0},null,{"$f":"IF(J59>0,J59/Summary!$G$69,0)","v":0},null,{"$f":"(J44+SUM(J46:J47)+SUM(J50:J51)+J56)","v":0},null,null,null,null,null,"Per Mile Cost"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Construction Cost","Total Cost - TEXT Format"]
[null,null,null,null,null,null,null,null,null,null,null,{"$f":"TEXT(SUM(J15:J37)*(1+'Inflated Cost'!$D$57)^'Cost Estimate'!$C$10,\"$#,##0\")","v":"$0"},{"$f":"TEXT((SUM(J15:J37)+J46+J47+J50+J51+J54)*(1+0.05)^C10,\"$#,##0\")","v":"$0"}]
[null,null,null,"Report Type",null,"Report",null,"NEPA",null,"Total",null,{"$f":"IF(N45<$R$15,MROUND(N45,$S$15),IF(AND(N45>=$R$15,N45<$R$16),MROUND(N45,$S$16),IF(AND(N45>=$R$16,N45<$R$17),MROUND(N45,$S$17),IF(AND(N45>=$R$17,N45<$R$18),MROUND(N45,$S$18),IF(AND(N45>=$R$18,N45<$R$19),MROUND(N45,$S$19),IF(AND(N45>=$R$19,N45<$R$20),MROUND(N45,$S$20),IF(N45>=$R$21,MROUND(N45,$S$21))))))))","v":0},{"$f":"(SUM(J15:J37)+J46+J47+J50+J51+J54)*(1+0.05)^C10","v":0}]
[null,null,null,"No Plans RSA",null,45000,null,null,null,{"$f":"F76+H76","v":45000},null,{"$f":"IF(L75>1000000000,TEXT(L75/1000000000,\"$#,##0.0\"),IF(AND(L75>=1000000,L75<1000000000),TEXT(L75/1000000,\"$#,##0\"), IF(L75<1000000,TEXT(L75/1000,\"$#,##0\"),\"\")))","v":"$0"},{"$f":"IF(M75<$R$15,MROUND(M75,$S$15),IF(AND(M75>=$R$15,M75<$R$16),MROUND(M75,$S$16),IF(AND(M75>=$R$16,M75<$R$17),MROUND(M75,$S$17),IF(AND(M75>=$R$17,M75<$R$18),MROUND(M75,$S$18),IF(AND(M75>=$R$18,M75<$R$19),MROUND(M75,$S$19),IF(AND(M75>=$R$19,M75<$R$20),MROUND(M75,$S$20),IF(M75>=$R$21,MROUND(M75,$S$21))))))))","v":0}]
[null,null,null,"LRSI",null,65000,null,null,null,{"$f":"F77+H77","v":65000},null,null,{"$f":"IF(M76>1000000000,TEXT(MROUND(M76/1000000000,1),\"$#,##0\"),IF(AND(M76>=1000000,M76<1000000000),TEXT(MROUND(M76/1000000,1),\"$#,##0\"), IF(M76<1000000,TEXT(MROUND(M76/1000,1),\"$#,##0\"),\"\")))","v":"$0"}]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,"Filter","List"]
[null,null,1,"Bicycles and Pedestrian Facility",null,null,null,"Design-Bid-Build"]
[null,null,1,"Bridge-New Construction",null,null,null,"Design-Build"]
[null,null,1,"Intersection Improvements",null,null,null,"CMGC"]
[null,null,1,"Intersection Improvements and Signals",null,null,null,"Show All"]
[null,null,1,"Modify Interchange"]
[null,null,1,"New Interchange"]
[null,null,1,"New Interchange-Connector"]
[null,null,1,"Bridge Replacement"]
[null,null,1,"Construction-New"]
[null,null,1,"Intelligent Transportation System"]
[null,null,1,"Noise Barrier Walls"]
[null,null,1,"Ramp Improvements"]
[null,null,1,"Realign and Widen"]
[null,null,1,"Realignment"]
[null,null,1,"Reconstruction"]
[null,null,1,"Resurface & Safety"]
[null,null,1,"Mitigation - Rockfall"]
[null,null,1,"RSAR"]
[null,null,1,"Safety"]
[null,null,1,"Sidewalk Improvements"]
[null,null,1,"Signalization"]
[null,null,1,"Truck Climbing Lane(s)"]
[null,null,1,"Widen"]
[null,null,1,"Widen and Resurfacing"]
[null,null,1,"Roundabout"]
[null,null,1,"Turn Lanes"]
[null,null,1,"Turn Lanes with Signal"]
[null,null,1,"No Plans RSA"]
[null,null,1,"LRSI"]
[null,null,null,"Culvert Replacement"]
[null,null,null,"Demo and Site Preparation"]
[null,null,null,"Enhancement (Misc.)"]
[null,null,null,"Env Mitigation and Wildlife Connectivity"]
[null,null,null,"Environmental Studies"]
[null,null,null,"Flashing Beacon"]
[null,null,null,"Flashing School Sign"]
[null,null,null,"GHSP"]
[null,null,null,"Guardrail"]
[null,null,null,"Historic Preservation"]
[null,null,null,"Historic Rehabilation"]
[null,null,null,"Interchange Lighting"]
[null,null,null,"Acq of Scenic or Historical Sites"]
[null,null,null,"Arch. Planning and Research"]
[null,null,null,"Bi-Ped Safety Activities"]
[null,null,null,"Bridge Rehabilitation"]
[null,null,null,"Bridge Repair"]
[null,null,null,"Intermodal Transportation Center"]
[null,null,null,"Landscaping and Scenic Beautification"]
[null,null,null,"Lighting"]
[null,null,null,"Location and Environmental Study"]
[null,null,null,"Maintenance"]
[null,null,null,"Median Barrier Wall"]
[null,null,null,"Microsurface"]
[null,null,null,"Miscellaneous Improvements"]
[null,null,null,"Miscellaneous Safety Improvements"]
[null,null,null,"Mowing/Litter"]
[null,null,null,"Other"]
[null,null,null,"Outdoor Advertising Control"]
[null,null,null,"Pavement Marking"]
[null,null,null,"Paving"]
[null,null,null,"Preliminary Engineering"]
[null,null,null,"Public Transportation"]
[null,null,null,"Purchase Hybrid Vehicles"]
[null,null,null,"Purchase Vans For Vanpool"]
[null,null,null,"Railroad Crossing Improvement"]
[null,null,null,"Rail-To or with Trails"]
[null,null,null,"Resurfacing"]
[null,null,null,"Rideshare"]
[null,null,null,"Right-of-Way"]
[null,null,null,"Roadscapes"]
[null,null,null,"Scenic By-Way"]
[null,null,null,"Scenic or Hist Hwy Prog Activities or Vi"]
[null,null,null,"Signal Timing Upgrade"]
[null,null,null,"Signs"]
[null,null,null,"Mitigation - Slide"]
[null,null,null,"SPR"]
[null,null,null,"Stage Construction-New"]
[null,null,null,"Mitigation - Stream"]
[null,null,null,"STIP Grouping"]
[null,null,null,"Study"]
[null,null,null,"Training"]
[null,null,null,"TIP Grouping"]
[null,null,null,"Transportation Museums"]
[null,null,null,"Utilities"]
[null,null,null,"Weigh Station or Rest Area Improvements"]
[null,null,null,"Resurf, Safety & Br Repair"]

{"sheet":"Median","index":7,"n_rows":114,"n_cols":21,"rows_kept":114,"cut":false,"hidden":true,"merged":[[111,15,117,21],[5,10,5,12],[19,10,19,11],[22,10,22,20],[87,1,87,2],[35,10,35,12],[39,10,39,14],[43,10,43,18],[47,10,47,12],[52,10,52,16],[88,1,88,2],[60,1,60,2],[4,1,4,2],[3,1,3,2],[31,1,31,2],[32,1,32,2],[59,1,59,2]]}
[]
[null,"Project Length:",{"$f":"IF((Tool!$J$54-Tool!$J$52)>0,(Tool!$J$54-Tool!$J$52),0)","v":0}]
[]
[null,"Depressed Grass"]
[null,"Segments:",null,{"$f":"Tool!$J$96","v":1}]
[null,"Segments","Begin","End","Type","Inside Shldr. Width (ft)","Interior Width (ft)","Length (ft)",null,null,"Overall Item Summary"]
[null,{"$f":"IF(AND(D5>=1,D5<=20),1,\"\")","v":1},{"$f":"IF(Tool!D98<>\"\",IF(B7<>\"\",IF(Tool!D98=0,Tool!D98,Tool!D98-Tool!D98),\"\"),\"\")","v":""},{"$f":"IF(C7=\"\",\"\",IF(Tool!E98<>\"\",IF(B7=1,IF($C$2<(Tool!E98-Tool!$D$98),$C$2,IF(Tool!D98<>0,(Tool!E98-Tool!D98),Tool!E98)),\"\")))","v":""},{"$f":"IF(D7<=0,\"\",IF(AND(B7<>\"\",D7<>\"\",Tool!F98=\"Depressed Grass\"),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E7=\"TRUE\",Tool!I98>0),Tool!I98,\"\")","v":""},{"$f":"IF(AND(E7=\"TRUE\",Tool!$J$98>0),Tool!$J$98,\"\")","v":""},{"$f":"IF(OR(C7=\"\",D7=\"\"),\"\",IF(E7=\"TRUE\",D7-C7,\"\"))","v":""},null,null,"Item #","Description","Quantity"]
[null,{"$f":"IF(AND(D5>=2,D5<=20),2,\"\")","v":""},{"$f":"IF(D7>=$C$2,\"\",IF(B8<>\"\",IF($C$2<(Tool!E98-Tool!$D$98),\"\",IF(Tool!D99<>\"\",IF(Tool!$D$98<>0,Tool!E98-Tool!$D$98,Tool!E98),\"\")),\"\"))","v":""},{"$f":"IF(C8>=$C$2,\"\",IF(C8=\"\",\"\",IF((Tool!E99-Tool!$D$98)>$C$2,$C$2,IF(C8=\"\",\"\",IF(Tool!E98<>\"\",IF(AND($C$2>=(Tool!E99-Tool!$D$98),(Tool!E100-Tool!$D$98)>=(Tool!E99-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E99-Tool!$D$98,Tool!E99),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B8<>\"\",D8<>\"\",Tool!F99=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E8=\"TRUE\",Tool!I99>0),Tool!I99,\"\")","v":""},{"$f":"IF(AND(E8=\"TRUE\",Tool!J99>0),Tool!J99,\"\")","v":""},{"$f":"IF(OR(C8=\"\",D8=\"\"),\"\",IF(E8=\"TRUE\",D8-C8,\"\"))","v":""},null,null,"411-01","\"E\" mix",{"$f":"U25","v":0}]
[null,{"$f":"IF(AND(D5>=3,D5<=20),3,\"\")","v":""},{"$f":"IF(D8>=$C$2,\"\",IF(B9<>\"\",IF($C$2<(Tool!E99-Tool!$D$98),\"\",IF(Tool!D100<>\"\",IF(Tool!$D$98<>0,Tool!E99-Tool!$D$98,Tool!E99),\"\")),\"\"))","v":""},{"$f":"IF(C9>=$C$2,\"\",IF(C9=\"\",\"\",IF((Tool!E100-Tool!$D$98)>$C$2,$C$2,IF(C9=\"\",\"\",IF(Tool!E99<>\"\",IF(AND($C$2>=(Tool!E100-Tool!$D$98),(Tool!E101-Tool!$D$98)>=(Tool!E100-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E100-Tool!$D$98,Tool!E100),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B9<>\"\",D9<>\"\",Tool!F100=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E9=\"TRUE\",Tool!I100>0),Tool!I100,\"\")","v":""},{"$f":"IF(AND(E9=\"TRUE\",Tool!J100>0),Tool!J100,\"\")","v":""},"",null,null,"403-01","Tack",{"$f":"U26","v":0}]
[null,{"$f":"IF(AND(D5>=4,D5<=20),4,\"\")","v":""},{"$f":"IF(D9>=$C$2,\"\",IF(B10<>\"\",IF($C$2<(Tool!E100-Tool!$D$98),\"\",IF(Tool!D101<>\"\",IF(Tool!$D$98<>0,Tool!E100-Tool!$D$98,Tool!E100),\"\")),\"\"))","v":""},{"$f":"IF(C10>=$C$2,\"\",IF(C10=\"\",\"\",IF((Tool!E101-Tool!$D$98)>$C$2,$C$2,IF(C10=\"\",\"\",IF(Tool!E100<>\"\",IF(AND($C$2>=(Tool!E101-Tool!$D$98),(Tool!E102-Tool!$D$98)>=(Tool!E101-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E101-Tool!$D$98,Tool!E101),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B10<>\"\",D10<>\"\",Tool!F101=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E10=\"TRUE\",Tool!I101>0),Tool!I101,\"\")","v":""},{"$f":"IF(AND(E10=\"TRUE\",Tool!J101>0),Tool!J101,\"\")","v":""},"",null,null,"307-02.08","\"BM-2\" mix",{"$f":"U27","v":0}]
[null,{"$f":"IF(AND(D5>=5,D5<=20),5,\"\")","v":""},{"$f":"IF(D10>=$C$2,\"\",IF(B11<>\"\",IF($C$2<(Tool!E101-Tool!$D$98),\"\",IF(Tool!D102<>\"\",IF(Tool!$D$98<>0,Tool!E101-Tool!$D$98,Tool!E101),\"\")),\"\"))","v":""},{"$f":"IF(C11>=$C$2,\"\",IF(C11=\"\",\"\",IF((Tool!E102-Tool!$D$98)>$C$2,$C$2,IF(C11=\"\",\"\",IF(Tool!E101<>\"\",IF(AND($C$2>=(Tool!E102-Tool!$D$98),(Tool!E103-Tool!$D$98)>=(Tool!E102-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E102-Tool!$D$98,Tool!E102),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B11<>\"\",D11<>\"\",Tool!F102=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E11=\"TRUE\",Tool!I102>0),Tool!I102,\"\")","v":""},{"$f":"IF(AND(E11=\"TRUE\",Tool!J102>0),Tool!J102,\"\")","v":""},"",null,null,"402-01","Prime Coat",{"$f":"U28","v":0}]
[null,{"$f":"IF(AND(D5>=6,D5<=20),6,\"\")","v":""},{"$f":"IF(D11>=$C$2,\"\",IF(B12<>\"\",IF($C$2<(Tool!E102-Tool!$D$98),\"\",IF(Tool!D103<>\"\",IF(Tool!$D$98<>0,Tool!E102-Tool!$D$98,Tool!E102),\"\")),\"\"))","v":""},{"$f":"IF(C12>=$C$2,\"\",IF(C12=\"\",\"\",IF((Tool!E103-Tool!$D$98)>$C$2,$C$2,IF(C12=\"\",\"\",IF(Tool!E102<>\"\",IF(AND($C$2>=(Tool!E103-Tool!$D$98),(Tool!E104-Tool!$D$98)>=(Tool!E103-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E103-Tool!$D$98,Tool!E103),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B12<>\"\",D12<>\"\",Tool!F103=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E12=\"TRUE\",Tool!I103>0),Tool!I103,\"\")","v":""},{"$f":"IF(AND(E12=\"TRUE\",Tool!J103>0),Tool!J103,\"\")","v":""},"",null,null,"402-02","Agg. Cover",{"$f":"U29","v":0}]
[null,{"$f":"IF(AND(D5>=7,D5<=20),7,\"\")","v":""},{"$f":"IF(D12>=$C$2,\"\",IF(B13<>\"\",IF($C$2<(Tool!E103-Tool!$D$98),\"\",IF(Tool!D104<>\"\",IF(Tool!$D$98<>0,Tool!E103-Tool!$D$98,Tool!E103),\"\")),\"\"))","v":""},{"$f":"IF(C13>=$C$2,\"\",IF(C13=\"\",\"\",IF((Tool!E104-Tool!$D$98)>$C$2,$C$2,IF(C13=\"\",\"\",IF(Tool!E103<>\"\",IF(AND($C$2>=(Tool!E104-Tool!$D$98),(Tool!E105-Tool!$D$98)>=(Tool!E104-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E104-Tool!$D$98,Tool!E104),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B13<>\"\",D13<>\"\",Tool!F104=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E13=\"TRUE\",Tool!I104>0),Tool!I104,\"\")","v":""},{"$f":"IF(AND(E13=\"TRUE\",Tool!J104>0),Tool!J104,\"\")","v":""},"",null,null,"303-01","Stone ",{"$f":"U30+T33+T34+P46+M50","v":0}]
[null,{"$f":"IF(AND(D5>=8,D5<=20),8,\"\")","v":""},{"$f":"IF(D13>=$C$2,\"\",IF(B14<>\"\",IF($C$2<(Tool!E104-Tool!$D$98),\"\",IF(Tool!D105<>\"\",IF(Tool!$D$98<>0,Tool!E104-Tool!$D$98,Tool!E104),\"\")),\"\"))","v":""},{"$f":"IF(C14>=$C$2,\"\",IF(C14=\"\",\"\",IF((Tool!E105-Tool!$D$98)>$C$2,$C$2,IF(C14=\"\",\"\",IF(Tool!E104<>\"\",IF(AND($C$2>=(Tool!E105-Tool!$D$98),(Tool!E106-Tool!$D$98)>=(Tool!E105-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E105-Tool!$D$98,Tool!E105),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B14<>\"\",D14<>\"\",Tool!F105=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E14=\"TRUE\",Tool!I105>0),Tool!I105,\"\")","v":""},{"$f":"IF(AND(E14=\"TRUE\",Tool!J105>0),Tool!J105,\"\")","v":""},"",null,null,"711-05.71","Barrier Wall",{"$f":"K50","v":0}]
[null,{"$f":"IF(AND(D5>=9,D5<=20),9,\"\")","v":""},{"$f":"IF(D14>=$C$2,\"\",IF(B15<>\"\",IF($C$2<(Tool!E105-Tool!$D$98),\"\",IF(Tool!D106<>\"\",IF(Tool!$D$98<>0,Tool!E105-Tool!$D$98,Tool!E105),\"\")),\"\"))","v":""},{"$f":"IF(C15>=$C$2,\"\",IF(C15=\"\",\"\",IF((Tool!E106-Tool!$D$98)>$C$2,$C$2,IF(C15=\"\",\"\",IF(Tool!E105<>\"\",IF(AND($C$2>=(Tool!E106-Tool!$D$98),(Tool!E107-Tool!$D$98)>=(Tool!E106-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E106-Tool!$D$98,Tool!E106),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B15<>\"\",D15<>\"\",Tool!F106=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E15=\"TRUE\",Tool!I106>0),Tool!I106,\"\")","v":""},{"$f":"IF(AND(E15=\"TRUE\",Tool!J106>0),Tool!J106,\"\")","v":""},"",null,null,"607-05.02","24\" RCP",{"$f":"N42+R46+K50","v":0}]
[null,{"$f":"IF(AND(D5>=10,D5<=20),10,\"\")","v":""},{"$f":"IF(D15>=$C$2,\"\",IF(B16<>\"\",IF($C$2<(Tool!E106-Tool!$D$98),\"\",IF(Tool!D107<>\"\",IF(Tool!$D$98<>0,Tool!E106-Tool!$D$98,Tool!E106),\"\")),\"\"))","v":""},{"$f":"IF(C16>=$C$2,\"\",IF(C16=\"\",\"\",IF((Tool!E107-Tool!$D$98)>$C$2,$C$2,IF(C16=\"\",\"\",IF(Tool!E106<>\"\",IF(AND($C$2>=(Tool!E107-Tool!$D$98),(Tool!E108-Tool!$D$98)>=(Tool!E107-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E107-Tool!$D$98,Tool!E107),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B16<>\"\",D16<>\"\",Tool!F107=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E16=\"TRUE\",Tool!I107>0),Tool!I107,\"\")","v":""},{"$f":"IF(AND(E16=\"TRUE\",Tool!J107>0),Tool!J107,\"\")","v":""},{"$f":"IF(OR(C16=\"\",D16=\"\"),\"\",IF(E16=\"TRUE\",D16-C16,\"\"))","v":""},null,null,"702-03","Combined C&G",{"$f":"N42+R46*0.07953","v":0}]
[null,{"$f":"IF(AND(D5>=11,D5<=20),11,\"\")","v":""},{"$f":"IF(D16>=$C$2,\"\",IF(B17<>\"\",IF($C$2<(Tool!E107-Tool!$D$98),\"\",IF(Tool!D108<>\"\",IF(Tool!$D$98<>0,Tool!E107-Tool!$D$98,Tool!E107),\"\")),\"\"))","v":""},{"$f":"IF(C17>=$C$2,\"\",IF(C17=\"\",\"\",IF((Tool!E108-Tool!$D$98)>$C$2,$C$2,IF(C17=\"\",\"\",IF(Tool!E107<>\"\",IF(AND($C$2>=(Tool!E108-Tool!$D$98),(Tool!E109-Tool!$D$98)>=(Tool!E108-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E108-Tool!$D$98,Tool!E108),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B17<>\"\",D17<>\"\",Tool!F108=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E17=\"TRUE\",Tool!I108>0),Tool!I108,\"\")","v":""},{"$f":"IF(AND(E17=\"TRUE\",Tool!J108>0),Tool!J108,\"\")","v":""},"",null,null,"611-12.02","CB Type 12",{"$f":"O42+S46+(K50/300)","v":0}]
[null,{"$f":"IF(AND(D5>=12,D5<=20),12,\"\")","v":""},{"$f":"IF(D17>=$C$2,\"\",IF(B18<>\"\",IF($C$2<(Tool!E108-Tool!$D$98),\"\",IF(Tool!D109<>\"\",IF(Tool!$D$98<>0,Tool!E108-Tool!$D$98,Tool!E108),\"\")),\"\"))","v":""},{"$f":"IF(C18>=$C$2,\"\",IF(C18=\"\",\"\",IF((Tool!E109-Tool!$D$98)>$C$2,$C$2,IF(C18=\"\",\"\",IF(Tool!E108<>\"\",IF(AND($C$2>=(Tool!E109-Tool!$D$98),(Tool!E110-Tool!$D$98)>=(Tool!E109-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E109-Tool!$D$98,Tool!E109),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B18<>\"\",D18<>\"\",Tool!F109=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E18=\"TRUE\",Tool!I109>0),Tool!I109,\"\")","v":""},{"$f":"IF(AND(E18=\"TRUE\",Tool!J109>0),Tool!J109,\"\")","v":""},"",null,null,"701-01.01 ","4\" Concrete",{"$f":"Q46","v":0}]
[null,{"$f":"IF(AND(D5>=13,D5<=20),13,\"\")","v":""},{"$f":"IF(D18>=$C$2,\"\",IF(B19<>\"\",IF($C$2<(Tool!E109-Tool!$D$98),\"\",IF(Tool!D110<>\"\",IF(Tool!$D$98<>0,Tool!E109-Tool!$D$98,Tool!E109),\"\")),\"\"))","v":""},{"$f":"IF(C19>=$C$2,\"\",IF(C19=\"\",\"\",IF((Tool!E110-Tool!$D$98)>$C$2,$C$2,IF(C19=\"\",\"\",IF(Tool!E109<>\"\",IF(AND($C$2>=(Tool!E110-Tool!$D$98),(Tool!E111-Tool!$D$98)>=(Tool!E110-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E110-Tool!$D$98,Tool!E110),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B19<>\"\",D19<>\"\",Tool!F110=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E19=\"TRUE\",Tool!I110>0),Tool!I110,\"\")","v":""},{"$f":"IF(AND(E19=\"TRUE\",Tool!J110>0),Tool!J110,\"\")","v":""},""]
[null,{"$f":"IF(AND(D5>=14,D5<=20),14,\"\")","v":""},{"$f":"IF(D19>=$C$2,\"\",IF(B20<>\"\",IF($C$2<(Tool!E110-Tool!$D$98),\"\",IF(Tool!D111<>\"\",IF(Tool!$D$98<>0,Tool!E110-Tool!$D$98,Tool!E110),\"\")),\"\"))","v":""},{"$f":"IF(C20>=$C$2,\"\",IF(C20=\"\",\"\",IF((Tool!E111-Tool!$D$98)>$C$2,$C$2,IF(C20=\"\",\"\",IF(Tool!E110<>\"\",IF(AND($C$2>=(Tool!E111-Tool!$D$98),(Tool!E112-Tool!$D$98)>=(Tool!E111-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E111-Tool!$D$98,Tool!E111),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B20<>\"\",D20<>\"\",Tool!F111=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E20=\"TRUE\",Tool!I111>0),Tool!I111,\"\")","v":""},{"$f":"IF(AND(E20=\"TRUE\",Tool!J111>0),Tool!J111,\"\")","v":""},"",null,null,"For Drainage Calcs"]
[null,{"$f":"IF(AND(D5>=15,D5<=20),15,\"\")","v":""},{"$f":"IF(D20>=$C$2,\"\",IF(B21<>\"\",IF($C$2<(Tool!E111-Tool!$D$98),\"\",IF(Tool!D112<>\"\",IF(Tool!$D$98<>0,Tool!E111-Tool!$D$98,Tool!E111),\"\")),\"\"))","v":""},{"$f":"IF(C21>=$C$2,\"\",IF(C21=\"\",\"\",IF((Tool!E112-Tool!$D$98)>$C$2,$C$2,IF(C21=\"\",\"\",IF(Tool!E111<>\"\",IF(AND($C$2>=(Tool!E112-Tool!$D$98),(Tool!E113-Tool!$D$98)>=(Tool!E112-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E112-Tool!$D$98,Tool!E112),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B21<>\"\",D21<>\"\",Tool!F112=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E21=\"TRUE\",Tool!I112>0),Tool!I112,\"\")","v":""},{"$f":"IF(AND(E21=\"TRUE\",Tool!J112>0),Tool!J112,\"\")","v":""},"",null,null,"Avg Med. Width:",{"$f":"N59","v":0}]
[null,{"$f":"IF(AND(D5>=16,D5<=20),16,\"\")","v":""},{"$f":"IF(D21>=$C$2,\"\",IF(B22<>\"\",IF($C$2<(Tool!E112-Tool!$D$98),\"\",IF(Tool!D113<>\"\",IF(Tool!$D$98<>0,Tool!E112-Tool!$D$98,Tool!E112),\"\")),\"\"))","v":""},{"$f":"IF(C22>=$C$2,\"\",IF(C22=\"\",\"\",IF((Tool!E113-Tool!$D$98)>$C$2,$C$2,IF(C22=\"\",\"\",IF(Tool!E112<>\"\",IF(AND($C$2>=(Tool!E113-Tool!$D$98),(Tool!E114-Tool!$D$98)>=(Tool!E113-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E113-Tool!$D$98,Tool!E113),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B22<>\"\",D22<>\"\",Tool!F113=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E22=\"TRUE\",Tool!I113>0),Tool!I113,\"\")","v":""},{"$f":"IF(AND(E22=\"TRUE\",Tool!J113>0),Tool!J113,\"\")","v":""},""]
[null,{"$f":"IF(AND(D5>=17,D5<=20),17,\"\")","v":""},{"$f":"IF(D22>=$C$2,\"\",IF(B23<>\"\",IF($C$2<(Tool!E113-Tool!$D$98),\"\",IF(Tool!D114<>\"\",IF(Tool!$D$98<>0,Tool!E113-Tool!$D$98,Tool!E113),\"\")),\"\"))","v":""},{"$f":"IF(C23>=$C$2,\"\",IF(C23=\"\",\"\",IF((Tool!E114-Tool!$D$98)>$C$2,$C$2,IF(C23=\"\",\"\",IF(Tool!E113<>\"\",IF(AND($C$2>=(Tool!E114-Tool!$D$98),(Tool!E115-Tool!$D$98)>=(Tool!E114-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E114-Tool!$D$98,Tool!E114),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B23<>\"\",D23<>\"\",Tool!F114=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E23=\"TRUE\",Tool!I114>0),Tool!I114,\"\")","v":""},{"$f":"IF(AND(E23=\"TRUE\",Tool!J114>0),Tool!J114,\"\")","v":""},"",null,null,"Paved Shoulder Calculations"]
[null,{"$f":"IF(AND(D5>=18,D5<=20),18,\"\")","v":""},{"$f":"IF(D23>=$C$2,\"\",IF(B24<>\"\",IF($C$2<(Tool!E114-Tool!$D$98),\"\",IF(Tool!D115<>\"\",IF(Tool!$D$98<>0,Tool!E114-Tool!$D$98,Tool!E114),\"\")),\"\"))","v":""},{"$f":"IF(C24>=$C$2,\"\",IF(C24=\"\",\"\",IF((Tool!E115-Tool!$D$98)>$C$2,$C$2,IF(C24=\"\",\"\",IF(Tool!E114<>\"\",IF(AND($C$2>=(Tool!E115-Tool!$D$98),(Tool!E116-Tool!$D$98)>=(Tool!E115-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E115-Tool!$D$98,Tool!E115),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B24<>\"\",D24<>\"\",Tool!F115=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E24=\"TRUE\",Tool!I115>0),Tool!I115,\"\")","v":""},{"$f":"IF(AND(E24=\"TRUE\",Tool!J115>0),Tool!J115,\"\")","v":""},"",null,null,"Pay Item #","Description","Area (s.f.)","Thk (in.)","Thk. (ft.)","CF","S.Y.","C.Y.","CF","lb/ton","Tons"]
[null,{"$f":"IF(AND(D5>=19,D5<=20),19,\"\")","v":""},{"$f":"IF(D24>=$C$2,\"\",IF(B25<>\"\",IF($C$2<(Tool!E115-Tool!$D$98),\"\",IF(Tool!D116<>\"\",IF(Tool!$D$98<>0,Tool!E115-Tool!$D$98,Tool!E115),\"\")),\"\"))","v":""},{"$f":"IF(C25>=$C$2,\"\",IF(C25=\"\",\"\",IF((Tool!E116-Tool!$D$98)>$C$2,$C$2,IF(C25=\"\",\"\",IF(Tool!E115<>\"\",IF(AND($C$2>=(Tool!E116-Tool!$D$98),(Tool!E117-Tool!$D$98)>=(Tool!E116-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E116-Tool!$D$98,Tool!E116),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B25<>\"\",D25<>\"\",Tool!F116=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E25=\"TRUE\",Tool!I116>0),Tool!I116,\"\")","v":""},{"$f":"IF(AND(E25=\"TRUE\",Tool!J116>0),Tool!J116,\"\")","v":""},"",null,null,"411-01","\"E\" mix",{"$f":"O59*5280*M59*2","v":0},1.5,{"$f":"N25/12","v":0.125},27,null,{"$f":"(M25*O25)/P25","v":0},3870,2000,{"$f":"(R25*S25)/T25","v":0}]
[null,{"$f":"IF(AND(D5=20),20,\"\")","v":""},{"$f":"IF(D25>=$C$2,\"\",IF(B26<>\"\",IF($C$2<(Tool!E116-Tool!$D$98),\"\",IF(Tool!D117<>\"\",IF(Tool!$D$98<>0,Tool!E116-Tool!$D$98,Tool!E116),\"\")),\"\"))","v":""},{"$f":"IF(C26>=$C$2,\"\",IF(C26=\"\",\"\",IF((Tool!E117-Tool!$D$98)>$C$2,$C$2,IF(C26=\"\",\"\",IF(Tool!E116<>\"\",IF(AND($C$2>=(Tool!E117-Tool!$D$98),(Tool!E118-Tool!$D$98)>=(Tool!E117-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E117-Tool!$D$98,Tool!E117),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B26<>\"\",D26<>\"\",Tool!F117=\"Depressed Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E26=\"TRUE\",Tool!I117>0),Tool!I117,\"\")","v":""},{"$f":"IF(AND(E26=\"TRUE\",Tool!J117>0),Tool!J117,\"\")","v":""},"",null,null,"403-01","Tack",{"$f":"O59*5280*M59*2","v":0},null,null,9,{"$f":"M26/P26","v":0},null,7.0000000000000007E-2,231,{"$f":"(Q26*S26)/T26","v":0}]
[null,null,null,null,null,null,null,null,null,null,"307-02.08","\"BM-2\" mix",{"$f":"O59*5280*M59*2","v":0},2,{"$f":"N27/12","v":0.16666666666666666},27,null,{"$f":"(M27*O27)/P27","v":0},4068,2000,{"$f":"(R27*S27)/T27","v":0}]
[null,null,null,null,null,null,"Average Interior Width:",{"$f":"IF(AND(SUM(H7:H26)>0,SUM(G7:G26)>0),SUMPRODUCT(G7:G26,H7:H26)/SUM(H7:H26),0)","v":0},null,null,"402-01","Prime Coat",{"$f":"O59*5280*M59*2","v":0},null,null,9,{"$f":"M28/P28","v":0},null,0.32,231,{"$f":"(Q28*S28)/T28","v":0}]
[null,null,null,null,null,null,"Avg. Inside Shoulder:",{"$f":"IF(SUM(H7:H26)>0,SUMPRODUCT(F7:F26,H7:H26)/SUM(H7:H26),0)","v":0},null,null,"402-02","Agg. Cover",{"$f":"O59*5280*M59*2","v":0},null,null,9,{"$f":"M29/P29","v":0},null,10,2000,{"$f":"(Q29*S29)/T29","v":0}]
[null,null,null,null,null,null,"Length:",{"$f":"SUM(H7:H26)","v":0},null,null,"303-01","Stone (Asphalt)",{"$f":"O59*5280*M59*2","v":0},20.25,{"$f":"N30/12","v":1.6875},27,null,{"$f":"(M30*O30)/27","v":0},2.0299999999999998,null,{"$f":"R30*S30","v":0}]
[null,null,null,null,null,null,"Avg. Interior Area:",{"$f":"H28*SUM(H7:H26)*5280","v":0}]
[null,"Raised Grass",null,null,null,null,null,null,null,null,"Pay Item #","Description","Width (ft.)","Thk (inches)","Thk. (ft.)","Conversion Factor","S.Y.","C.Y.","Conversion Factor","Tons"]
[null,"Segments:",null,{"$f":"Tool!$J$96","v":1},null,null,null,null,null,null,"303-01","Stone (2' Grv. Shldr)",{"$f":"O33*6*0.5","v":5.0625},20.25,{"$f":"N33/12","v":1.6875},27,null,{"$f":"(M33*O33*$L$57)/P33","v":0},2.0299999999999998,{"$f":"R33*S33","v":0}]
[null,"Segments","Begin","End","Type","Inside Shldr. Width (ft)","Interior Width (ft)","Length (ft)",null,null,"303-01","Stone (6:1 Agg. Slp.)",{"$f":"O34*6*0.5","v":5.0625},20.25,{"$f":"N34/12","v":1.6875},27,null,{"$f":"(M34*O34*$L$57)/P34","v":0},2.0299999999999998,{"$f":"R34*S34","v":0}]
[null,{"$f":"IF(AND(D33>=1,D33<=20),1,\"\")","v":1},{"$f":"IF(Tool!D98<>\"\",IF(B7<>\"\",IF(Tool!D98=0,Tool!D98,Tool!D98-Tool!D98),\"\"),\"\")","v":""},{"$f":"IF(C35=\"\",\"\",IF(Tool!E98<>\"\",IF(B7=1,IF($C$2<(Tool!E98-Tool!$D$98),$C$2,IF(Tool!D98<>0,(Tool!E98-Tool!D98),Tool!E98)),\"\")))","v":""},{"$f":"IF(D35<=0,\"\",IF(AND(B35<>\"\",Tool!F98=\"Raised Grass\"),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E35=\"TRUE\",Tool!I98>0),Tool!I98,\"\")","v":""},{"$f":"IF(AND(E35=\"TRUE\",Tool!J98>0),Tool!J98,\"\")","v":""},{"$f":"IF(OR(C35=\"\",D35=\"\"),\"\",IF(E35=\"TRUE\",D35-C35,\"\"))","v":""}]
[null,{"$f":"IF(AND(D33>=2,D33<=20),2,\"\")","v":""},{"$f":"IF(D35>=$C$2,\"\",IF(B36<>\"\",IF($C$2<(Tool!E98-Tool!$D$98),\"\",IF(Tool!D99<>\"\",IF(Tool!$D$98<>0,Tool!E98-Tool!$D$98,Tool!E98),\"\")),\"\"))","v":""},{"$f":"IF(C8>=$C$2,\"\",IF(C8=\"\",\"\",IF((Tool!E99-Tool!$D$98)>$C$2,$C$2,IF(C8=\"\",\"\",IF(Tool!E98<>\"\",IF(AND($C$2>=(Tool!E99-Tool!$D$98),(Tool!E100-Tool!$D$98)>=(Tool!E99-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E99-Tool!$D$98,Tool!E99),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B36<>\"\",D36<>\"\",Tool!F99=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E36=\"TRUE\",Tool!I99>0),Tool!I99,\"\")","v":""},{"$f":"IF(AND(E36=\"TRUE\",Tool!J99>0),Tool!J99,\"\")","v":""},{"$f":"IF(OR(C36=\"\",D36=\"\"),\"\",IF(E36=\"TRUE\",D36-C36,\"\"))","v":""},null,null,"Depressed Median Calcs."]
[null,{"$f":"IF(AND(D33>=3,D33<=20),3,\"\")","v":""},{"$f":"IF(D36>=$C$2,\"\",IF(B37<>\"\",IF($C$2<(Tool!E99-Tool!$D$98),\"\",IF(Tool!D100<>\"\",IF(Tool!$D$98<>0,Tool!E99-Tool!$D$98,Tool!E99),\"\")),\"\"))","v":""},{"$f":"IF(C9>=$C$2,\"\",IF(C9=\"\",\"\",IF((Tool!E100-Tool!$D$98)>$C$2,$C$2,IF(C9=\"\",\"\",IF(Tool!E99<>\"\",IF(AND($C$2>=(Tool!E100-Tool!$D$98),(Tool!E101-Tool!$D$98)>=(Tool!E100-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E100-Tool!$D$98,Tool!E100),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B37<>\"\",D37<>\"\",Tool!F100=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E37=\"TRUE\",Tool!I100>0),Tool!I100,\"\")","v":""},{"$f":"IF(AND(E37=\"TRUE\",Tool!J100>0),Tool!J100,\"\")","v":""},"",null,null,"Length","Width","Depth"]
[null,{"$f":"IF(AND(D33>=4,D33<=20),4,\"\")","v":""},{"$f":"IF(D37>=$C$2,\"\",IF(B38<>\"\",IF($C$2<(Tool!E100-Tool!$D$98),\"\",IF(Tool!D101<>\"\",IF(Tool!$D$98<>0,Tool!E100-Tool!$D$98,Tool!E100),\"\")),\"\"))","v":""},{"$f":"IF(C10>=$C$2,\"\",IF(C10=\"\",\"\",IF((Tool!E101-Tool!$D$98)>$C$2,$C$2,IF(C10=\"\",\"\",IF(Tool!E100<>\"\",IF(AND($C$2>=(Tool!E101-Tool!$D$98),(Tool!E102-Tool!$D$98)>=(Tool!E101-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E101-Tool!$D$98,Tool!E101),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B38<>\"\",D38<>\"\",Tool!F101=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E38=\"TRUE\",Tool!I101>0),Tool!I101,\"\")","v":""},{"$f":"IF(AND(E38=\"TRUE\",Tool!J101>0),Tool!J101,\"\")","v":""},"",null,null,{"$f":"H30*5280","v":0},{"$f":"H28","v":0},3]
[null,{"$f":"IF(AND(D33>=5,D33<=20),5,\"\")","v":""},{"$f":"IF(D38>=$C$2,\"\",IF(B39<>\"\",IF($C$2<(Tool!E101-Tool!$D$98),\"\",IF(Tool!D102<>\"\",IF(Tool!$D$98<>0,Tool!E101-Tool!$D$98,Tool!E101),\"\")),\"\"))","v":""},{"$f":"IF(C11>=$C$2,\"\",IF(C11=\"\",\"\",IF((Tool!E102-Tool!$D$98)>$C$2,$C$2,IF(C11=\"\",\"\",IF(Tool!E101<>\"\",IF(AND($C$2>=(Tool!E102-Tool!$D$98),(Tool!E103-Tool!$D$98)>=(Tool!E102-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E102-Tool!$D$98,Tool!E102),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B39<>\"\",D39<>\"\",Tool!F102=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E39=\"TRUE\",Tool!I102>0),Tool!I102,\"\")","v":""},{"$f":"IF(AND(E39=\"TRUE\",Tool!J102>0),Tool!J102,\"\")","v":""},""]
[null,{"$f":"IF(AND(D33>=6,D33<=20),6,\"\")","v":""},{"$f":"IF(D39>=$C$2,\"\",IF(B40<>\"\",IF($C$2<(Tool!E102-Tool!$D$98),\"\",IF(Tool!D103<>\"\",IF(Tool!$D$98<>0,Tool!E102-Tool!$D$98,Tool!E102),\"\")),\"\"))","v":""},{"$f":"IF(C12>=$C$2,\"\",IF(C12=\"\",\"\",IF((Tool!E103-Tool!$D$98)>$C$2,$C$2,IF(C12=\"\",\"\",IF(Tool!E102<>\"\",IF(AND($C$2>=(Tool!E103-Tool!$D$98),(Tool!E104-Tool!$D$98)>=(Tool!E103-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E103-Tool!$D$98,Tool!E103),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B40<>\"\",D40<>\"\",Tool!F103=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E40=\"TRUE\",Tool!I103>0),Tool!I103,\"\")","v":""},{"$f":"IF(AND(E40=\"TRUE\",Tool!J103>0),Tool!J103,\"\")","v":""},"",null,null,"Raised Grass Median Calcs."]
[null,{"$f":"IF(AND(D33>=7,D33<=20),7,\"\")","v":""},{"$f":"IF(D40>=$C$2,\"\",IF(B41<>\"\",IF($C$2<(Tool!E103-Tool!$D$98),\"\",IF(Tool!D104<>\"\",IF(Tool!$D$98<>0,Tool!E103-Tool!$D$98,Tool!E103),\"\")),\"\"))","v":""},{"$f":"IF(C13>=$C$2,\"\",IF(C13=\"\",\"\",IF((Tool!E104-Tool!$D$98)>$C$2,$C$2,IF(C13=\"\",\"\",IF(Tool!E103<>\"\",IF(AND($C$2>=(Tool!E104-Tool!$D$98),(Tool!E105-Tool!$D$98)>=(Tool!E104-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E104-Tool!$D$98,Tool!E104),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B41<>\"\",D41<>\"\",Tool!F104=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E41=\"TRUE\",Tool!I104>0),Tool!I104,\"\")","v":""},{"$f":"IF(AND(E41=\"TRUE\",Tool!J104>0),Tool!J104,\"\")","v":""},"",null,null,"Length","Width","Depth","C/G - RCP Length","Type 12 CB"]
[null,{"$f":"IF(AND(D33>=8,D33<=20),8,\"\")","v":""},{"$f":"IF(D41>=$C$2,\"\",IF(B42<>\"\",IF($C$2<(Tool!E104-Tool!$D$98),\"\",IF(Tool!D105<>\"\",IF(Tool!$D$98<>0,Tool!E104-Tool!$D$98,Tool!E104),\"\")),\"\"))","v":""},{"$f":"IF(C14>=$C$2,\"\",IF(C14=\"\",\"\",IF((Tool!E105-Tool!$D$98)>$C$2,$C$2,IF(C14=\"\",\"\",IF(Tool!E104<>\"\",IF(AND($C$2>=(Tool!E105-Tool!$D$98),(Tool!E106-Tool!$D$98)>=(Tool!E105-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E105-Tool!$D$98,Tool!E105),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B42<>\"\",D42<>\"\",Tool!F105=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E42=\"TRUE\",Tool!I105>0),Tool!I105,\"\")","v":""},{"$f":"IF(AND(E42=\"TRUE\",Tool!J105>0),Tool!J105,\"\")","v":""},"",null,null,{"$f":"H58*5280","v":0},{"$f":"H56","v":0},6,{"$f":"H58*2","v":0},{"$f":"(N42/300)","v":0}]
[null,{"$f":"IF(AND(D33>=9,D33<=20),9,\"\")","v":""},{"$f":"IF(D42>=$C$2,\"\",IF(B43<>\"\",IF($C$2<(Tool!E105-Tool!$D$98),\"\",IF(Tool!D106<>\"\",IF(Tool!$D$98<>0,Tool!E105-Tool!$D$98,Tool!E105),\"\")),\"\"))","v":""},{"$f":"IF(C15>=$C$2,\"\",IF(C15=\"\",\"\",IF((Tool!E106-Tool!$D$98)>$C$2,$C$2,IF(C15=\"\",\"\",IF(Tool!E105<>\"\",IF(AND($C$2>=(Tool!E106-Tool!$D$98),(Tool!E107-Tool!$D$98)>=(Tool!E106-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E106-Tool!$D$98,Tool!E106),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B43<>\"\",D43<>\"\",Tool!F106=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E43=\"TRUE\",Tool!I106>0),Tool!I106,\"\")","v":""},{"$f":"IF(AND(E43=\"TRUE\",Tool!J106>0),Tool!J106,\"\")","v":""},""]
[null,{"$f":"IF(AND(D33>=10,D33<=20),10,\"\")","v":""},{"$f":"IF(D43>=$C$2,\"\",IF(B44<>\"\",IF($C$2<(Tool!E106-Tool!$D$98),\"\",IF(Tool!D107<>\"\",IF(Tool!$D$98<>0,Tool!E106-Tool!$D$98,Tool!E106),\"\")),\"\"))","v":""},{"$f":"IF(C16>=$C$2,\"\",IF(C16=\"\",\"\",IF((Tool!E107-Tool!$D$98)>$C$2,$C$2,IF(C16=\"\",\"\",IF(Tool!E106<>\"\",IF(AND($C$2>=(Tool!E107-Tool!$D$98),(Tool!E108-Tool!$D$98)>=(Tool!E107-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E107-Tool!$D$98,Tool!E107),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B44<>\"\",D44<>\"\",Tool!F107=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E44=\"TRUE\",Tool!I107>0),Tool!I107,\"\")","v":""},{"$f":"IF(AND(E44=\"TRUE\",Tool!J107>0),Tool!J107,\"\")","v":""},"",null,null,"Raised Concrete Median Calcs"]
[null,{"$f":"IF(AND(D33>=11,D33<=20),11,\"\")","v":""},{"$f":"IF(D44>=$C$2,\"\",IF(B45<>\"\",IF($C$2<(Tool!E107-Tool!$D$98),\"\",IF(Tool!D108<>\"\",IF(Tool!$D$98<>0,Tool!E107-Tool!$D$98,Tool!E107),\"\")),\"\"))","v":""},{"$f":"IF(C17>=$C$2,\"\",IF(C17=\"\",\"\",IF((Tool!E108-Tool!$D$98)>$C$2,$C$2,IF(C17=\"\",\"\",IF(Tool!E107<>\"\",IF(AND($C$2>=(Tool!E108-Tool!$D$98),(Tool!E109-Tool!$D$98)>=(Tool!E108-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E108-Tool!$D$98,Tool!E108),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B45<>\"\",D45<>\"\",Tool!F108=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E45=\"TRUE\",Tool!I108>0),Tool!I108,\"\")","v":""},{"$f":"IF(AND(E45=\"TRUE\",Tool!J108>0),Tool!J108,\"\")","v":""},"",null,null,"Length","Width (ft)","Interior Width (ft)","Interior Area (sqft)","Stone Depth (10\")","Stone (CY)","Class A Concrete 4\"","C/G - RCP Length","Type 12 CB"]
[null,{"$f":"IF(AND(D33>=12,D33<=20),12,\"\")","v":""},{"$f":"IF(D45>=$C$2,\"\",IF(B46<>\"\",IF($C$2<(Tool!E108-Tool!$D$98),\"\",IF(Tool!D109<>\"\",IF(Tool!$D$98<>0,Tool!E108-Tool!$D$98,Tool!E108),\"\")),\"\"))","v":""},{"$f":"IF(C18>=$C$2,\"\",IF(C18=\"\",\"\",IF((Tool!E109-Tool!$D$98)>$C$2,$C$2,IF(C18=\"\",\"\",IF(Tool!E108<>\"\",IF(AND($C$2>=(Tool!E109-Tool!$D$98),(Tool!E110-Tool!$D$98)>=(Tool!E109-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E109-Tool!$D$98,Tool!E109),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B46<>\"\",D46<>\"\",Tool!F109=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E46=\"TRUE\",Tool!I109>0),Tool!I109,\"\")","v":""},{"$f":"IF(AND(E46=\"TRUE\",Tool!J109>0),Tool!J109,\"\")","v":""},"",null,null,{"$f":"H86*5280","v":0},{"$f":"H84","v":0},{"$f":"L46-H85","v":0},{"$f":"M46*K46","v":0},{"$f":"10/12","v":0.83333333333333337},null,null,{"$f":"K46*0.5","v":0},{"$f":"(K46/600)","v":0}]
[null,{"$f":"IF(AND(D33>=13,D33<=20),13,\"\")","v":""},{"$f":"IF(D46>=$C$2,\"\",IF(B47<>\"\",IF($C$2<(Tool!E109-Tool!$D$98),\"\",IF(Tool!D110<>\"\",IF(Tool!$D$98<>0,Tool!E109-Tool!$D$98,Tool!E109),\"\")),\"\"))","v":""},{"$f":"IF(C19>=$C$2,\"\",IF(C19=\"\",\"\",IF((Tool!E110-Tool!$D$98)>$C$2,$C$2,IF(C19=\"\",\"\",IF(Tool!E109<>\"\",IF(AND($C$2>=(Tool!E110-Tool!$D$98),(Tool!E111-Tool!$D$98)>=(Tool!E110-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E110-Tool!$D$98,Tool!E110),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B47<>\"\",D47<>\"\",Tool!F110=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E47=\"TRUE\",Tool!I110>0),Tool!I110,\"\")","v":""},{"$f":"IF(AND(E47=\"TRUE\",Tool!J110>0),Tool!J110,\"\")","v":""},""]
[null,{"$f":"IF(AND(D33>=14,D33<=20),14,\"\")","v":""},{"$f":"IF(D47>=$C$2,\"\",IF(B48<>\"\",IF($C$2<(Tool!E110-Tool!$D$98),\"\",IF(Tool!D111<>\"\",IF(Tool!$D$98<>0,Tool!E110-Tool!$D$98,Tool!E110),\"\")),\"\"))","v":""},{"$f":"IF(C20>=$C$2,\"\",IF(C20=\"\",\"\",IF((Tool!E111-Tool!$D$98)>$C$2,$C$2,IF(C20=\"\",\"\",IF(Tool!E110<>\"\",IF(AND($C$2>=(Tool!E111-Tool!$D$98),(Tool!E112-Tool!$D$98)>=(Tool!E111-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E111-Tool!$D$98,Tool!E111),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B48<>\"\",D48<>\"\",Tool!F111=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E48=\"TRUE\",Tool!I111>0),Tool!I111,\"\")","v":""},{"$f":"IF(AND(E48=\"TRUE\",Tool!J111>0),Tool!J111,\"\")","v":""},"",null,null,"Median Barrier Wall Calcs"]
[null,{"$f":"IF(AND(D33>=15,D33<=20),15,\"\")","v":""},{"$f":"IF(D48>=$C$2,\"\",IF(B49<>\"\",IF($C$2<(Tool!E111-Tool!$D$98),\"\",IF(Tool!D112<>\"\",IF(Tool!$D$98<>0,Tool!E111-Tool!$D$98,Tool!E111),\"\")),\"\"))","v":""},{"$f":"IF(C21>=$C$2,\"\",IF(C21=\"\",\"\",IF((Tool!E112-Tool!$D$98)>$C$2,$C$2,IF(C21=\"\",\"\",IF(Tool!E111<>\"\",IF(AND($C$2>=(Tool!E112-Tool!$D$98),(Tool!E113-Tool!$D$98)>=(Tool!E112-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E112-Tool!$D$98,Tool!E112),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B49<>\"\",D49<>\"\",Tool!F112=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E49=\"TRUE\",Tool!I112>0),Tool!I112,\"\")","v":""},{"$f":"IF(AND(E49=\"TRUE\",Tool!J112>0),Tool!J112,\"\")","v":""},"",null,null,"Length","Width","Stone Depth(20.25\")"]
[null,{"$f":"IF(AND(D33>=16,D33<=20),16,\"\")","v":""},{"$f":"IF(D49>=$C$2,\"\",IF(B50<>\"\",IF($C$2<(Tool!E112-Tool!$D$98),\"\",IF(Tool!D113<>\"\",IF(Tool!$D$98<>0,Tool!E112-Tool!$D$98,Tool!E112),\"\")),\"\"))","v":""},{"$f":"IF(C22>=$C$2,\"\",IF(C22=\"\",\"\",IF((Tool!E113-Tool!$D$98)>$C$2,$C$2,IF(C22=\"\",\"\",IF(Tool!E112<>\"\",IF(AND($C$2>=(Tool!E113-Tool!$D$98),(Tool!E114-Tool!$D$98)>=(Tool!E113-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E113-Tool!$D$98,Tool!E113),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B50<>\"\",D50<>\"\",Tool!F113=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E50=\"TRUE\",Tool!I113>0),Tool!I113,\"\")","v":""},{"$f":"IF(AND(E50=\"TRUE\",Tool!J113>0),Tool!J113,\"\")","v":""},"",null,null,{"$f":"H114*5280","v":0},2,{"$f":"(K50*L50*O34)/27","v":0}]
[null,{"$f":"IF(AND(D33>=17,D33<=20),17,\"\")","v":""},{"$f":"IF(D50>=$C$2,\"\",IF(B51<>\"\",IF($C$2<(Tool!E113-Tool!$D$98),\"\",IF(Tool!D114<>\"\",IF(Tool!$D$98<>0,Tool!E113-Tool!$D$98,Tool!E113),\"\")),\"\"))","v":""},{"$f":"IF(C23>=$C$2,\"\",IF(C23=\"\",\"\",IF((Tool!E114-Tool!$D$98)>$C$2,$C$2,IF(C23=\"\",\"\",IF(Tool!E113<>\"\",IF(AND($C$2>=(Tool!E114-Tool!$D$98),(Tool!E115-Tool!$D$98)>=(Tool!E114-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E114-Tool!$D$98,Tool!E114),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B51<>\"\",D51<>\"\",Tool!F114=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E51=\"TRUE\",Tool!I114>0),Tool!I114,\"\")","v":""},{"$f":"IF(AND(E51=\"TRUE\",Tool!J114>0),Tool!J114,\"\")","v":""},""]
[null,{"$f":"IF(AND(D33>=18,D33<=20),18,\"\")","v":""},{"$f":"IF(D51>=$C$2,\"\",IF(B52<>\"\",IF($C$2<(Tool!E114-Tool!$D$98),\"\",IF(Tool!D115<>\"\",IF(Tool!$D$98<>0,Tool!E114-Tool!$D$98,Tool!E114),\"\")),\"\"))","v":""},{"$f":"IF(C24>=$C$2,\"\",IF(C24=\"\",\"\",IF((Tool!E115-Tool!$D$98)>$C$2,$C$2,IF(C24=\"\",\"\",IF(Tool!E114<>\"\",IF(AND($C$2>=(Tool!E115-Tool!$D$98),(Tool!E116-Tool!$D$98)>=(Tool!E115-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E115-Tool!$D$98,Tool!E115),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B52<>\"\",D52<>\"\",Tool!F115=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E52=\"TRUE\",Tool!I115>0),Tool!I115,\"\")","v":""},{"$f":"IF(AND(E52=\"TRUE\",Tool!J115>0),Tool!J115,\"\")","v":""},""]
[null,{"$f":"IF(AND(D33>=19,D33<=20),19,\"\")","v":""},{"$f":"IF(D52>=$C$2,\"\",IF(B53<>\"\",IF($C$2<(Tool!E115-Tool!$D$98),\"\",IF(Tool!D116<>\"\",IF(Tool!$D$98<>0,Tool!E115-Tool!$D$98,Tool!E115),\"\")),\"\"))","v":""},{"$f":"IF(C25>=$C$2,\"\",IF(C25=\"\",\"\",IF((Tool!E116-Tool!$D$98)>$C$2,$C$2,IF(C25=\"\",\"\",IF(Tool!E115<>\"\",IF(AND($C$2>=(Tool!E116-Tool!$D$98),(Tool!E117-Tool!$D$98)>=(Tool!E116-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E116-Tool!$D$98,Tool!E116),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B53<>\"\",D53<>\"\",Tool!F116=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E53=\"TRUE\",Tool!I116>0),Tool!I116,\"\")","v":""},{"$f":"IF(AND(E53=\"TRUE\",Tool!J116>0),Tool!J116,\"\")","v":""},"",null,null,"Median Properties Table"]
[null,{"$f":"IF(AND(D33=20),20,\"\")","v":""},{"$f":"IF(D53>=$C$2,\"\",IF(B54<>\"\",IF($C$2<(Tool!E116-Tool!$D$98),\"\",IF(Tool!D117<>\"\",IF(Tool!$D$98<>0,Tool!E116-Tool!$D$98,Tool!E116),\"\")),\"\"))","v":""},{"$f":"IF(C26>=$C$2,\"\",IF(C26=\"\",\"\",IF((Tool!E117-Tool!$D$98)>$C$2,$C$2,IF(C26=\"\",\"\",IF(Tool!E116<>\"\",IF(AND($C$2>=(Tool!E117-Tool!$D$98),(Tool!E118-Tool!$D$98)>=(Tool!E117-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E117-Tool!$D$98,Tool!E117),$C$2),\"\")))))","v":""},{"$f":"IF(AND(B54<>\"\",D54<>\"\",Tool!F117=\"Raised Grass\"),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(E54=\"TRUE\",Tool!I117>0),Tool!I117,\"\")","v":""},{"$f":"IF(AND(E54=\"TRUE\",Tool!J117>0),Tool!J117,\"\")","v":""},"",null,null,null,"Avg. Interior Width:","Avg. I'Shldr Width:","Av Med. Width","Total Length:","Avg Median Area","Percent Type"]
[null,null,null,null,null,null,null,null,null,null,"Depressed Grass:",{"$f":"H28","v":0},{"$f":"H29","v":0},{"$f":"L55+M55*2","v":0},{"$f":"H30","v":0},{"$f":"N55*O55*5280","v":0},{"$f":"IF($P$59>0,P55/$P$59,0)","v":0}]
[null,null,null,null,null,null,"Average Interior Width:",{"$f":"IF(AND(SUM(H35:H54)>0,SUM(G35:G54)>0),SUMPRODUCT(G35:G54,H35:H54)/SUM(H35:H54),0)","v":0},null,null,"Raised Grass:",{"$f":"H56","v":0},{"$f":"H57","v":0},{"$f":"L56+M56*2","v":0},{"$f":"H58","v":0},{"$f":"N56*O56*5280","v":0},{"$f":"IF($P$59>0,P56/$P$59,0)","v":0}]
[null,null,null,null,null,null,"Avg. Inside Shoulder:",{"$f":"IF(SUM(H35:H54)>0,SUMPRODUCT(F35:F54,H35:H54)/SUM(H35:H54),0)","v":0},null,null,"Raised Concrete:",{"$f":"H84","v":0},{"$f":"H85","v":0},{"$f":"L57+M57*2","v":0},{"$f":"H86","v":0},{"$f":"N57*O57*5280","v":0},{"$f":"IF($P$59>0,P57/$P$59,0)","v":0}]
[null,null,null,null,null,null,"Length:",{"$f":"SUM(H35:H54)","v":0},null,null,"Barrier Wall:",{"$f":"H112","v":0},{"$f":"H113","v":0},{"$f":"L58+M58*2","v":0},{"$f":"H114","v":0},{"$f":"N58*O58*5280","v":0},{"$f":"IF($P$59>0,P58/$P$59,0)","v":0}]
[null,null,null,null,null,null,"Avg. Interior Area:",{"$f":"H56*SUM(H35:H54)*5280","v":0},null,null,"Overall:",{"$f":"IF(SUM($O$55:$O$58)>0,SUMPRODUCT(L55:L58,$O$55:$O$58)/SUM($O$55:$O$58),0)","v":0},{"$f":"IF(SUM($O$55:$O$58)>0,SUMPRODUCT(M55:M58,$O$55:$O$58)/SUM($O$55:$O$58),0)","v":0},{"$f":"IF(SUM($O$55:$O$58)>0,SUMPRODUCT(N55:N58,$O$55:$O$58)/SUM($O$55:$O$58),0)","v":0},{"$f":"SUM(O55:O58)","v":0},{"$f":"SUM(P55:P58)","v":0},{"$f":"SUM(Q55:Q58)","v":0}]
[null,"Raised Concrete"]
[null,"Segments:",null,{"$f":"Tool!$J$96","v":1}]
[null,"Segments","Begin","End","Type","Inside Shldr. Width (ft)","Interior Width (ft)","Length (ft)"]
[null,{"$f":"IF(AND(D61>=1,D61<=20),1,\"\")","v":1},{"$f":"IF(Tool!D98<>\"\",IF(B7<>\"\",IF(Tool!D98=0,Tool!D98,Tool!D98-Tool!D98),\"\"),\"\")","v":""},{"$f":"IF(C63=\"\",\"\",IF(Tool!E98<>\"\",IF(B7=1,IF($C$2<(Tool!E98-Tool!$D$98),$C$2,IF(Tool!D98<>0,(Tool!E98-Tool!D98),Tool!E98)),\"\")))","v":""},{"$f":"IF(D63<=0,\"\",IF(AND(B63<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E63=\"TRUE\",Tool!$I$98>0),Tool!$I$98,\"\")","v":""},{"$f":"IF(AND(E63=\"TRUE\",Tool!J98>0),Tool!J98,\"\")","v":""},{"$f":"IF(OR(C63=\"\",D63=\"\"),\"\",IF(E63=\"TRUE\",D63-C63,\"\"))","v":""}]
[null,{"$f":"IF(AND(D61>=2,D61<=20),2,\"\")","v":""},{"$f":"IF(D35>=$C$2,\"\",IF(B36<>\"\",IF($C$2<(Tool!E98-Tool!$D$98),\"\",IF(Tool!D99<>\"\",IF(Tool!$D$98<>0,Tool!E98-Tool!$D$98,Tool!E98),\"\")),\"\"))","v":""},{"$f":"IF(C8>=$C$2,\"\",IF(C8=\"\",\"\",IF((Tool!E99-Tool!$D$98)>$C$2,$C$2,IF(C8=\"\",\"\",IF(Tool!E98<>\"\",IF(AND($C$2>=(Tool!E99-Tool!$D$98),(Tool!E100-Tool!$D$98)>=(Tool!E99-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E99-Tool!$D$98,Tool!E99),$C$2),\"\")))))","v":""},{"$f":"IF(D64<=0,\"\",IF(AND(B64<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E64=\"TRUE\",Tool!I99>0),Tool!I99,\"\")","v":""},{"$f":"IF(AND(E64=\"TRUE\",Tool!J99>0),Tool!J99,\"\")","v":""},{"$f":"IF(OR(C64=\"\",D64=\"\"),\"\",IF(E64=\"TRUE\",D64-C64,\"\"))","v":""}]
[null,{"$f":"IF(AND(D61>=3,D61<=20),3,\"\")","v":""},{"$f":"IF(D36>=$C$2,\"\",IF(B37<>\"\",IF($C$2<(Tool!E99-Tool!$D$98),\"\",IF(Tool!D100<>\"\",IF(Tool!$D$98<>0,Tool!E99-Tool!$D$98,Tool!E99),\"\")),\"\"))","v":""},{"$f":"IF(C9>=$C$2,\"\",IF(C9=\"\",\"\",IF((Tool!E100-Tool!$D$98)>$C$2,$C$2,IF(C9=\"\",\"\",IF(Tool!E99<>\"\",IF(AND($C$2>=(Tool!E100-Tool!$D$98),(Tool!E101-Tool!$D$98)>=(Tool!E100-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E100-Tool!$D$98,Tool!E100),$C$2),\"\")))))","v":""},{"$f":"IF(D65<=0,\"\",IF(AND(B65<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E65=\"TRUE\",Tool!I100>0),Tool!I100,\"\")","v":""},{"$f":"IF(AND(E65=\"TRUE\",Tool!J100>0),Tool!J100,\"\")","v":""},""]
[null,{"$f":"IF(AND(D61>=4,D61<=20),4,\"\")","v":""},{"$f":"IF(D37>=$C$2,\"\",IF(B38<>\"\",IF($C$2<(Tool!E100-Tool!$D$98),\"\",IF(Tool!D101<>\"\",IF(Tool!$D$98<>0,Tool!E100-Tool!$D$98,Tool!E100),\"\")),\"\"))","v":""},{"$f":"IF(C10>=$C$2,\"\",IF(C10=\"\",\"\",IF((Tool!E101-Tool!$D$98)>$C$2,$C$2,IF(C10=\"\",\"\",IF(Tool!E100<>\"\",IF(AND($C$2>=(Tool!E101-Tool!$D$98),(Tool!E102-Tool!$D$98)>=(Tool!E101-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E101-Tool!$D$98,Tool!E101),$C$2),\"\")))))","v":""},{"$f":"IF(D66<=0,\"\",IF(AND(B66<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E66=\"TRUE\",Tool!I101>0),Tool!I101,\"\")","v":""},{"$f":"IF(AND(E66=\"TRUE\",Tool!J101>0),Tool!J101,\"\")","v":""},""]
[null,{"$f":"IF(AND(D61>=5,D61<=20),5,\"\")","v":""},{"$f":"IF(D38>=$C$2,\"\",IF(B39<>\"\",IF($C$2<(Tool!E101-Tool!$D$98),\"\",IF(Tool!D102<>\"\",IF(Tool!$D$98<>0,Tool!E101-Tool!$D$98,Tool!E101),\"\")),\"\"))","v":""},{"$f":"IF(C11>=$C$2,\"\",IF(C11=\"\",\"\",IF((Tool!E102-Tool!$D$98)>$C$2,$C$2,IF(C11=\"\",\"\",IF(Tool!E101<>\"\",IF(AND($C$2>=(Tool!E102-Tool!$D$98),(Tool!E103-Tool!$D$98)>=(Tool!E102-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E102-Tool!$D$98,Tool!E102),$C$2),\"\")))))","v":""},{"$f":"IF(D67<=0,\"\",IF(AND(B67<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E67=\"TRUE\",Tool!I102>0),Tool!I102,\"\")","v":""},{"$f":"IF(AND(E67=\"TRUE\",Tool!J102>0),Tool!J102,\"\")","v":""},""]
[null,{"$f":"IF(AND(D61>=6,D61<=20),6,\"\")","v":""},{"$f":"IF(D39>=$C$2,\"\",IF(B40<>\"\",IF($C$2<(Tool!E102-Tool!$D$98),\"\",IF(Tool!D103<>\"\",IF(Tool!$D$98<>0,Tool!E102-Tool!$D$98,Tool!E102),\"\")),\"\"))","v":""},{"$f":"IF(C12>=$C$2,\"\",IF(C12=\"\",\"\",IF((Tool!E103-Tool!$D$98)>$C$2,$C$2,IF(C12=\"\",\"\",IF(Tool!E102<>\"\",IF(AND($C$2>=(Tool!E103-Tool!$D$98),(Tool!E104-Tool!$D$98)>=(Tool!E103-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E103-Tool!$D$98,Tool!E103),$C$2),\"\")))))","v":""},{"$f":"IF(D68<=0,\"\",IF(AND(B68<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E68=\"TRUE\",Tool!I103>0),Tool!I103,\"\")","v":""},{"$f":"IF(AND(E68=\"TRUE\",Tool!J103>0),Tool!J103,\"\")","v":""},""]
[null,{"$f":"IF(AND(D61>=7,D61<=20),7,\"\")","v":""},{"$f":"IF(D40>=$C$2,\"\",IF(B41<>\"\",IF($C$2<(Tool!E103-Tool!$D$98),\"\",IF(Tool!D104<>\"\",IF(Tool!$D$98<>0,Tool!E103-Tool!$D$98,Tool!E103),\"\")),\"\"))","v":""},{"$f":"IF(C13>=$C$2,\"\",IF(C13=\"\",\"\",IF((Tool!E104-Tool!$D$98)>$C$2,$C$2,IF(C13=\"\",\"\",IF(Tool!E103<>\"\",IF(AND($C$2>=(Tool!E104-Tool!$D$98),(Tool!E105-Tool!$D$98)>=(Tool!E104-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E104-Tool!$D$98,Tool!E104),$C$2),\"\")))))","v":""},{"$f":"IF(D69<=0,\"\",IF(AND(B69<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E69=\"TRUE\",Tool!I104>0),Tool!I104,\"\")","v":""},{"$f":"IF(AND(E69=\"TRUE\",Tool!J104>0),Tool!J104,\"\")","v":""},""]
[null,{"$f":"IF(AND(D61>=8,D61<=20),8,\"\")","v":""},{"$f":"IF(D41>=$C$2,\"\",IF(B42<>\"\",IF($C$2<(Tool!E104-Tool!$D$98),\"\",IF(Tool!D105<>\"\",IF(Tool!$D$98<>0,Tool!E104-Tool!$D$98,Tool!E104),\"\")),\"\"))","v":""},{"$f":"IF(C14>=$C$2,\"\",IF(C14=\"\",\"\",IF((Tool!E105-Tool!$D$98)>$C$2,$C$2,IF(C14=\"\",\"\",IF(Tool!E104<>\"\",IF(AND($C$2>=(Tool!E105-Tool!$D$98),(Tool!E106-Tool!$D$98)>=(Tool!E105-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E105-Tool!$D$98,Tool!E105),$C$2),\"\")))))","v":""},{"$f":"IF(D70<=0,\"\",IF(AND(B70<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E70=\"TRUE\",Tool!I105>0),Tool!I105,\"\")","v":""},{"$f":"IF(AND(E70=\"TRUE\",Tool!J105>0),Tool!J105,\"\")","v":""},""]
[null,{"$f":"IF(AND(D61>=9,D61<=20),9,\"\")","v":""},{"$f":"IF(D42>=$C$2,\"\",IF(B43<>\"\",IF($C$2<(Tool!E105-Tool!$D$98),\"\",IF(Tool!D106<>\"\",IF(Tool!$D$98<>0,Tool!E105-Tool!$D$98,Tool!E105),\"\")),\"\"))","v":""},{"$f":"IF(C15>=$C$2,\"\",IF(C15=\"\",\"\",IF((Tool!E106-Tool!$D$98)>$C$2,$C$2,IF(C15=\"\",\"\",IF(Tool!E105<>\"\",IF(AND($C$2>=(Tool!E106-Tool!$D$98),(Tool!E107-Tool!$D$98)>=(Tool!E106-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E106-Tool!$D$98,Tool!E106),$C$2),\"\")))))","v":""},{"$f":"IF(D71<=0,\"\",IF(AND(B71<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E71=\"TRUE\",Tool!I106>0),Tool!I106,\"\")","v":""},{"$f":"IF(AND(E71=\"TRUE\",Tool!J106>0),Tool!J106,\"\")","v":""},""]
[null,{"$f":"IF(AND(D61>=10,D61<=20),10,\"\")","v":""},{"$f":"IF(D43>=$C$2,\"\",IF(B44<>\"\",IF($C$2<(Tool!E106-Tool!$D$98),\"\",IF(Tool!D107<>\"\",IF(Tool!$D$98<>0,Tool!E106-Tool!$D$98,Tool!E106),\"\")),\"\"))","v":""},{"$f":"IF(C16>=$C$2,\"\",IF(C16=\"\",\"\",IF((Tool!E107-Tool!$D$98)>$C$2,$C$2,IF(C16=\"\",\"\",IF(Tool!E106<>\"\",IF(AND($C$2>=(Tool!E107-Tool!$D$98),(Tool!E108-Tool!$D$98)>=(Tool!E107-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E107-Tool!$D$98,Tool!E107),$C$2),\"\")))))","v":""},{"$f":"IF(D72<=0,\"\",IF(AND(B72<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E72=\"TRUE\",Tool!I107>0),Tool!I107,\"\")","v":""},{"$f":"IF(AND(E72=\"TRUE\",Tool!J107>0),Tool!J107,\"\")","v":""},""]
[null,{"$f":"IF(AND(D61>=11,D61<=20),11,\"\")","v":""},{"$f":"IF(D44>=$C$2,\"\",IF(B45<>\"\",IF($C$2<(Tool!E107-Tool!$D$98),\"\",IF(Tool!D108<>\"\",IF(Tool!$D$98<>0,Tool!E107-Tool!$D$98,Tool!E107),\"\")),\"\"))","v":""},{"$f":"IF(C17>=$C$2,\"\",IF(C17=\"\",\"\",IF((Tool!E108-Tool!$D$98)>$C$2,$C$2,IF(C17=\"\",\"\",IF(Tool!E107<>\"\",IF(AND($C$2>=(Tool!E108-Tool!$D$98),(Tool!E109-Tool!$D$98)>=(Tool!E108-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E108-Tool!$D$98,Tool!E108),$C$2),\"\")))))","v":""},{"$f":"IF(D73<=0,\"\",IF(AND(B73<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E73=\"TRUE\",Tool!I108>0),Tool!I108,\"\")","v":""},{"$f":"IF(AND(E73=\"TRUE\",Tool!J108>0),Tool!J108,\"\")","v":""},""]
[null,{"$f":"IF(AND(D61>=12,D61<=20),12,\"\")","v":""},{"$f":"IF(D45>=$C$2,\"\",IF(B46<>\"\",IF($C$2<(Tool!E108-Tool!$D$98),\"\",IF(Tool!D109<>\"\",IF(Tool!$D$98<>0,Tool!E108-Tool!$D$98,Tool!E108),\"\")),\"\"))","v":""},{"$f":"IF(C18>=$C$2,\"\",IF(C18=\"\",\"\",IF((Tool!E109-Tool!$D$98)>$C$2,$C$2,IF(C18=\"\",\"\",IF(Tool!E108<>\"\",IF(AND($C$2>=(Tool!E109-Tool!$D$98),(Tool!E110-Tool!$D$98)>=(Tool!E109-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E109-Tool!$D$98,Tool!E109),$C$2),\"\")))))","v":""},{"$f":"IF(D74<=0,\"\",IF(AND(B74<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E74=\"TRUE\",Tool!I109>0),Tool!I109,\"\")","v":""},{"$f":"IF(AND(E74=\"TRUE\",Tool!J109>0),Tool!J109,\"\")","v":""},""]
[null,{"$f":"IF(AND(D61>=13,D61<=20),13,\"\")","v":""},{"$f":"IF(D46>=$C$2,\"\",IF(B47<>\"\",IF($C$2<(Tool!E109-Tool!$D$98),\"\",IF(Tool!D110<>\"\",IF(Tool!$D$98<>0,Tool!E109-Tool!$D$98,Tool!E109),\"\")),\"\"))","v":""},{"$f":"IF(C19>=$C$2,\"\",IF(C19=\"\",\"\",IF((Tool!E110-Tool!$D$98)>$C$2,$C$2,IF(C19=\"\",\"\",IF(Tool!E109<>\"\",IF(AND($C$2>=(Tool!E110-Tool!$D$98),(Tool!E111-Tool!$D$98)>=(Tool!E110-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E110-Tool!$D$98,Tool!E110),$C$2),\"\")))))","v":""},{"$f":"IF(D75<=0,\"\",IF(AND(B75<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E75=\"TRUE\",Tool!I110>0),Tool!I110,\"\")","v":""},{"$f":"IF(AND(E75=\"TRUE\",Tool!J110>0),Tool!J110,\"\")","v":""},""]
[null,{"$f":"IF(AND(D61>=14,D61<=20),14,\"\")","v":""},{"$f":"IF(D47>=$C$2,\"\",IF(B48<>\"\",IF($C$2<(Tool!E110-Tool!$D$98),\"\",IF(Tool!D111<>\"\",IF(Tool!$D$98<>0,Tool!E110-Tool!$D$98,Tool!E110),\"\")),\"\"))","v":""},{"$f":"IF(C20>=$C$2,\"\",IF(C20=\"\",\"\",IF((Tool!E111-Tool!$D$98)>$C$2,$C$2,IF(C20=\"\",\"\",IF(Tool!E110<>\"\",IF(AND($C$2>=(Tool!E111-Tool!$D$98),(Tool!E112-Tool!$D$98)>=(Tool!E111-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E111-Tool!$D$98,Tool!E111),$C$2),\"\")))))","v":""},{"$f":"IF(D76<=0,\"\",IF(AND(B76<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E76=\"TRUE\",Tool!I111>0),Tool!I111,\"\")","v":""},{"$f":"IF(AND(E76=\"TRUE\",Tool!J111>0),Tool!J111,\"\")","v":""},""]
[null,{"$f":"IF(AND(D61>=15,D61<=20),15,\"\")","v":""},{"$f":"IF(D48>=$C$2,\"\",IF(B49<>\"\",IF($C$2<(Tool!E111-Tool!$D$98),\"\",IF(Tool!D112<>\"\",IF(Tool!$D$98<>0,Tool!E111-Tool!$D$98,Tool!E111),\"\")),\"\"))","v":""},{"$f":"IF(C21>=$C$2,\"\",IF(C21=\"\",\"\",IF((Tool!E112-Tool!$D$98)>$C$2,$C$2,IF(C21=\"\",\"\",IF(Tool!E111<>\"\",IF(AND($C$2>=(Tool!E112-Tool!$D$98),(Tool!E113-Tool!$D$98)>=(Tool!E112-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E112-Tool!$D$98,Tool!E112),$C$2),\"\")))))","v":""},{"$f":"IF(D77<=0,\"\",IF(AND(B77<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E77=\"TRUE\",Tool!I112>0),Tool!I112,\"\")","v":""},{"$f":"IF(AND(E77=\"TRUE\",Tool!J112>0),Tool!J112,\"\")","v":""},""]
[null,{"$f":"IF(AND(D61>=16,D61<=20),16,\"\")","v":""},{"$f":"IF(D49>=$C$2,\"\",IF(B50<>\"\",IF($C$2<(Tool!E112-Tool!$D$98),\"\",IF(Tool!D113<>\"\",IF(Tool!$D$98<>0,Tool!E112-Tool!$D$98,Tool!E112),\"\")),\"\"))","v":""},{"$f":"IF(C22>=$C$2,\"\",IF(C22=\"\",\"\",IF((Tool!E113-Tool!$D$98)>$C$2,$C$2,IF(C22=\"\",\"\",IF(Tool!E112<>\"\",IF(AND($C$2>=(Tool!E113-Tool!$D$98),(Tool!E114-Tool!$D$98)>=(Tool!E113-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E113-Tool!$D$98,Tool!E113),$C$2),\"\")))))","v":""},{"$f":"IF(D78<=0,\"\",IF(AND(B78<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E78=\"TRUE\",Tool!I113>0),Tool!I113,\"\")","v":""},{"$f":"IF(AND(E78=\"TRUE\",Tool!J113>0),Tool!J113,\"\")","v":""},""]
[null,{"$f":"IF(AND(D61>=17,D61<=20),17,\"\")","v":""},{"$f":"IF(D50>=$C$2,\"\",IF(B51<>\"\",IF($C$2<(Tool!E113-Tool!$D$98),\"\",IF(Tool!D114<>\"\",IF(Tool!$D$98<>0,Tool!E113-Tool!$D$98,Tool!E113),\"\")),\"\"))","v":""},{"$f":"IF(C23>=$C$2,\"\",IF(C23=\"\",\"\",IF((Tool!E114-Tool!$D$98)>$C$2,$C$2,IF(C23=\"\",\"\",IF(Tool!E113<>\"\",IF(AND($C$2>=(Tool!E114-Tool!$D$98),(Tool!E115-Tool!$D$98)>=(Tool!E114-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E114-Tool!$D$98,Tool!E114),$C$2),\"\")))))","v":""},{"$f":"IF(D79<=0,\"\",IF(AND(B79<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E79=\"TRUE\",Tool!I114>0),Tool!I114,\"\")","v":""},{"$f":"IF(AND(E79=\"TRUE\",Tool!J114>0),Tool!J114,\"\")","v":""},""]
[null,{"$f":"IF(AND(D61>=18,D61<=20),18,\"\")","v":""},{"$f":"IF(D51>=$C$2,\"\",IF(B52<>\"\",IF($C$2<(Tool!E114-Tool!$D$98),\"\",IF(Tool!D115<>\"\",IF(Tool!$D$98<>0,Tool!E114-Tool!$D$98,Tool!E114),\"\")),\"\"))","v":""},{"$f":"IF(C24>=$C$2,\"\",IF(C24=\"\",\"\",IF((Tool!E115-Tool!$D$98)>$C$2,$C$2,IF(C24=\"\",\"\",IF(Tool!E114<>\"\",IF(AND($C$2>=(Tool!E115-Tool!$D$98),(Tool!E116-Tool!$D$98)>=(Tool!E115-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E115-Tool!$D$98,Tool!E115),$C$2),\"\")))))","v":""},{"$f":"IF(D80<=0,\"\",IF(AND(B80<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E80=\"TRUE\",Tool!I115>0),Tool!I115,\"\")","v":""},{"$f":"IF(AND(E80=\"TRUE\",Tool!J115>0),Tool!J115,\"\")","v":""},""]
[null,{"$f":"IF(AND(D61>=19,D61<=20),19,\"\")","v":""},{"$f":"IF(D52>=$C$2,\"\",IF(B53<>\"\",IF($C$2<(Tool!E115-Tool!$D$98),\"\",IF(Tool!D116<>\"\",IF(Tool!$D$98<>0,Tool!E115-Tool!$D$98,Tool!E115),\"\")),\"\"))","v":""},{"$f":"IF(C25>=$C$2,\"\",IF(C25=\"\",\"\",IF((Tool!E116-Tool!$D$98)>$C$2,$C$2,IF(C25=\"\",\"\",IF(Tool!E115<>\"\",IF(AND($C$2>=(Tool!E116-Tool!$D$98),(Tool!E117-Tool!$D$98)>=(Tool!E116-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E116-Tool!$D$98,Tool!E116),$C$2),\"\")))))","v":""},{"$f":"IF(D81<=0,\"\",IF(AND(B81<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E81=\"TRUE\",Tool!I116>0),Tool!I116,\"\")","v":""},{"$f":"IF(AND(E81=\"TRUE\",Tool!J116>0),Tool!J116,\"\")","v":""},""]
[null,{"$f":"IF(AND(D61=20),20,\"\")","v":""},{"$f":"IF(D53>=$C$2,\"\",IF(B54<>\"\",IF($C$2<(Tool!E116-Tool!$D$98),\"\",IF(Tool!D117<>\"\",IF(Tool!$D$98<>0,Tool!E116-Tool!$D$98,Tool!E116),\"\")),\"\"))","v":""},{"$f":"IF(C26>=$C$2,\"\",IF(C26=\"\",\"\",IF((Tool!E117-Tool!$D$98)>$C$2,$C$2,IF(C26=\"\",\"\",IF(Tool!E116<>\"\",IF(AND($C$2>=(Tool!E117-Tool!$D$98),(Tool!E118-Tool!$D$98)>=(Tool!E117-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E117-Tool!$D$98,Tool!E117),$C$2),\"\")))))","v":""},{"$f":"IF(D82<=0,\"\",IF(AND(B82<>\"\",Tool!$F$98=Tool!$J$8),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E82=\"TRUE\",Tool!I117>0),Tool!I117,\"\")","v":""},{"$f":"IF(AND(E82=\"TRUE\",Tool!J117>0),Tool!J117,\"\")","v":""},""]
[]
[null,null,null,null,null,null,"Average Interior Width:",{"$f":"IF(AND(SUM(H63:H82)>0,SUM(G63:G82)>0),SUMPRODUCT(G63:G82,H63:H82)/SUM(H63:H82),0)","v":0}]
[null,null,null,null,null,null,"Avg. Inside Shoulder:",{"$f":"IF(SUM(H63:H82)>0,SUMPRODUCT(F63:F82,H63:H82)/SUM(H63:H82),0)","v":0}]
[null,null,null,null,null,null,"Length:",{"$f":"SUM(H63:H82)","v":0}]
[]
[null,"Barrier Wall"]
[null,"Segments:",null,{"$f":"Tool!$J$96","v":1}]
[null,"Segments","Begin","End","Type","Inside Shldr. Width (ft)","Interior Width (ft)","Length (ft)"]
[null,{"$f":"IF(AND(D89>=1,D89<=20),1,\"\")","v":1},{"$f":"IF(Tool!D98<>\"\",IF(B7<>\"\",IF(Tool!D98=0,Tool!D98,Tool!D98-Tool!D98),\"\"),\"\")","v":""},{"$f":"IF(C91=\"\",\"\",IF(Tool!E98<>\"\",IF(B7=1,IF($C$2<(Tool!E98-Tool!$D$98),$C$2,IF(Tool!D98<>0,(Tool!E98-Tool!D98),Tool!E98)),\"\")))","v":""},{"$f":"IF(D91<=0,\"\",IF(AND(B91<>\"\",Tool!F98=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E91=\"TRUE\",Tool!I98>0),Tool!I98,\"\")","v":""},{"$f":"IF(AND(E91=\"TRUE\",D91<>\"\",C91<>\"\"),3,\"\")","v":""},{"$f":"IF(OR(C91=\"\",D91=\"\"),\"\",IF(E91=\"TRUE\",D91-C91,\"\"))","v":""}]
[null,{"$f":"IF(AND(D89>=2,D89<=20),2,\"\")","v":""},{"$f":"IF(D35>=$C$2,\"\",IF(B36<>\"\",IF($C$2<(Tool!E98-Tool!$D$98),\"\",IF(Tool!D99<>\"\",IF(Tool!$D$98<>0,Tool!E98-Tool!$D$98,Tool!E98),\"\")),\"\"))","v":""},{"$f":"IF(C8>=$C$2,\"\",IF(C8=\"\",\"\",IF((Tool!E99-Tool!$D$98)>$C$2,$C$2,IF(C8=\"\",\"\",IF(Tool!E98<>\"\",IF(AND($C$2>=(Tool!E99-Tool!$D$98),(Tool!E100-Tool!$D$98)>=(Tool!E99-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E99-Tool!$D$98,Tool!E99),$C$2),\"\")))))","v":""},{"$f":"IF(D92<=0,\"\",IF(AND(B92<>\"\",Tool!F99=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E92=\"TRUE\",Tool!I99>0),Tool!I99,\"\")","v":""},{"$f":"IF(AND(E92=\"TRUE\",D92<>\"\",C92<>\"\"),3,\"\")","v":""},{"$f":"IF(OR(C92=\"\",D92=\"\"),\"\",IF(E92=\"TRUE\",D92-C92,\"\"))","v":""}]
[null,{"$f":"IF(AND(D89>=3,D89<=20),3,\"\")","v":""},{"$f":"IF(D36>=$C$2,\"\",IF(B37<>\"\",IF($C$2<(Tool!E99-Tool!$D$98),\"\",IF(Tool!D100<>\"\",IF(Tool!$D$98<>0,Tool!E99-Tool!$D$98,Tool!E99),\"\")),\"\"))","v":""},{"$f":"IF(C9>=$C$2,\"\",IF(C9=\"\",\"\",IF((Tool!E100-Tool!$D$98)>$C$2,$C$2,IF(C9=\"\",\"\",IF(Tool!E99<>\"\",IF(AND($C$2>=(Tool!E100-Tool!$D$98),(Tool!E101-Tool!$D$98)>=(Tool!E100-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E100-Tool!$D$98,Tool!E100),$C$2),\"\")))))","v":""},{"$f":"IF(D93<=0,\"\",IF(AND(B93<>\"\",Tool!F100=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E93=\"TRUE\",Tool!I100>0),Tool!I100,\"\")","v":""},"",""]
[null,{"$f":"IF(AND(D89>=4,D89<=20),4,\"\")","v":""},{"$f":"IF(D37>=$C$2,\"\",IF(B38<>\"\",IF($C$2<(Tool!E100-Tool!$D$98),\"\",IF(Tool!D101<>\"\",IF(Tool!$D$98<>0,Tool!E100-Tool!$D$98,Tool!E100),\"\")),\"\"))","v":""},{"$f":"IF(C10>=$C$2,\"\",IF(C10=\"\",\"\",IF((Tool!E101-Tool!$D$98)>$C$2,$C$2,IF(C10=\"\",\"\",IF(Tool!E100<>\"\",IF(AND($C$2>=(Tool!E101-Tool!$D$98),(Tool!E102-Tool!$D$98)>=(Tool!E101-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E101-Tool!$D$98,Tool!E101),$C$2),\"\")))))","v":""},{"$f":"IF(D94<=0,\"\",IF(AND(B94<>\"\",Tool!F101=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E94=\"TRUE\",Tool!I101>0),Tool!I101,\"\")","v":""},"",""]
[null,{"$f":"IF(AND(D89>=5,D89<=20),5,\"\")","v":""},{"$f":"IF(D38>=$C$2,\"\",IF(B39<>\"\",IF($C$2<(Tool!E101-Tool!$D$98),\"\",IF(Tool!D102<>\"\",IF(Tool!$D$98<>0,Tool!E101-Tool!$D$98,Tool!E101),\"\")),\"\"))","v":""},{"$f":"IF(C11>=$C$2,\"\",IF(C11=\"\",\"\",IF((Tool!E102-Tool!$D$98)>$C$2,$C$2,IF(C11=\"\",\"\",IF(Tool!E101<>\"\",IF(AND($C$2>=(Tool!E102-Tool!$D$98),(Tool!E103-Tool!$D$98)>=(Tool!E102-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E102-Tool!$D$98,Tool!E102),$C$2),\"\")))))","v":""},{"$f":"IF(D95<=0,\"\",IF(AND(B95<>\"\",Tool!F102=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E95=\"TRUE\",Tool!I102>0),Tool!I102,\"\")","v":""},"",""]
[null,{"$f":"IF(AND(D89>=6,D89<=20),6,\"\")","v":""},{"$f":"IF(D39>=$C$2,\"\",IF(B40<>\"\",IF($C$2<(Tool!E102-Tool!$D$98),\"\",IF(Tool!D103<>\"\",IF(Tool!$D$98<>0,Tool!E102-Tool!$D$98,Tool!E102),\"\")),\"\"))","v":""},{"$f":"IF(C12>=$C$2,\"\",IF(C12=\"\",\"\",IF((Tool!E103-Tool!$D$98)>$C$2,$C$2,IF(C12=\"\",\"\",IF(Tool!E102<>\"\",IF(AND($C$2>=(Tool!E103-Tool!$D$98),(Tool!E104-Tool!$D$98)>=(Tool!E103-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E103-Tool!$D$98,Tool!E103),$C$2),\"\")))))","v":""},{"$f":"IF(D96<=0,\"\",IF(AND(B96<>\"\",Tool!F103=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E96=\"TRUE\",Tool!I103>0),Tool!I103,\"\")","v":""},"",""]
[null,{"$f":"IF(AND(D89>=7,D89<=20),7,\"\")","v":""},{"$f":"IF(D40>=$C$2,\"\",IF(B41<>\"\",IF($C$2<(Tool!E103-Tool!$D$98),\"\",IF(Tool!D104<>\"\",IF(Tool!$D$98<>0,Tool!E103-Tool!$D$98,Tool!E103),\"\")),\"\"))","v":""},{"$f":"IF(C13>=$C$2,\"\",IF(C13=\"\",\"\",IF((Tool!E104-Tool!$D$98)>$C$2,$C$2,IF(C13=\"\",\"\",IF(Tool!E103<>\"\",IF(AND($C$2>=(Tool!E104-Tool!$D$98),(Tool!E105-Tool!$D$98)>=(Tool!E104-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E104-Tool!$D$98,Tool!E104),$C$2),\"\")))))","v":""},{"$f":"IF(D97<=0,\"\",IF(AND(B97<>\"\",Tool!F104=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E97=\"TRUE\",Tool!I104>0),Tool!I104,\"\")","v":""},"",""]
[null,{"$f":"IF(AND(D89>=8,D89<=20),8,\"\")","v":""},{"$f":"IF(D41>=$C$2,\"\",IF(B42<>\"\",IF($C$2<(Tool!E104-Tool!$D$98),\"\",IF(Tool!D105<>\"\",IF(Tool!$D$98<>0,Tool!E104-Tool!$D$98,Tool!E104),\"\")),\"\"))","v":""},{"$f":"IF(C14>=$C$2,\"\",IF(C14=\"\",\"\",IF((Tool!E105-Tool!$D$98)>$C$2,$C$2,IF(C14=\"\",\"\",IF(Tool!E104<>\"\",IF(AND($C$2>=(Tool!E105-Tool!$D$98),(Tool!E106-Tool!$D$98)>=(Tool!E105-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E105-Tool!$D$98,Tool!E105),$C$2),\"\")))))","v":""},{"$f":"IF(D98<=0,\"\",IF(AND(B98<>\"\",Tool!F105=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E98=\"TRUE\",Tool!I105>0),Tool!I105,\"\")","v":""},"",""]
[null,{"$f":"IF(AND(D89>=9,D89<=20),9,\"\")","v":""},{"$f":"IF(D42>=$C$2,\"\",IF(B43<>\"\",IF($C$2<(Tool!E105-Tool!$D$98),\"\",IF(Tool!D106<>\"\",IF(Tool!$D$98<>0,Tool!E105-Tool!$D$98,Tool!E105),\"\")),\"\"))","v":""},{"$f":"IF(C15>=$C$2,\"\",IF(C15=\"\",\"\",IF((Tool!E106-Tool!$D$98)>$C$2,$C$2,IF(C15=\"\",\"\",IF(Tool!E105<>\"\",IF(AND($C$2>=(Tool!E106-Tool!$D$98),(Tool!E107-Tool!$D$98)>=(Tool!E106-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E106-Tool!$D$98,Tool!E106),$C$2),\"\")))))","v":""},{"$f":"IF(D99<=0,\"\",IF(AND(B99<>\"\",Tool!F106=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E99=\"TRUE\",Tool!I106>0),Tool!I106,\"\")","v":""},"",""]
[null,{"$f":"IF(AND(D89>=10,D89<=20),10,\"\")","v":""},{"$f":"IF(D43>=$C$2,\"\",IF(B44<>\"\",IF($C$2<(Tool!E106-Tool!$D$98),\"\",IF(Tool!D107<>\"\",IF(Tool!$D$98<>0,Tool!E106-Tool!$D$98,Tool!E106),\"\")),\"\"))","v":""},{"$f":"IF(C16>=$C$2,\"\",IF(C16=\"\",\"\",IF((Tool!E107-Tool!$D$98)>$C$2,$C$2,IF(C16=\"\",\"\",IF(Tool!E106<>\"\",IF(AND($C$2>=(Tool!E107-Tool!$D$98),(Tool!E108-Tool!$D$98)>=(Tool!E107-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E107-Tool!$D$98,Tool!E107),$C$2),\"\")))))","v":""},{"$f":"IF(D100<=0,\"\",IF(AND(B100<>\"\",Tool!F107=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E100=\"TRUE\",Tool!I107>0),Tool!I107,\"\")","v":""},"",""]
[null,{"$f":"IF(AND(D89>=11,D89<=20),11,\"\")","v":""},{"$f":"IF(D44>=$C$2,\"\",IF(B45<>\"\",IF($C$2<(Tool!E107-Tool!$D$98),\"\",IF(Tool!D108<>\"\",IF(Tool!$D$98<>0,Tool!E107-Tool!$D$98,Tool!E107),\"\")),\"\"))","v":""},{"$f":"IF(C17>=$C$2,\"\",IF(C17=\"\",\"\",IF((Tool!E108-Tool!$D$98)>$C$2,$C$2,IF(C17=\"\",\"\",IF(Tool!E107<>\"\",IF(AND($C$2>=(Tool!E108-Tool!$D$98),(Tool!E109-Tool!$D$98)>=(Tool!E108-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E108-Tool!$D$98,Tool!E108),$C$2),\"\")))))","v":""},{"$f":"IF(D101<=0,\"\",IF(AND(B101<>\"\",Tool!F108=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E101=\"TRUE\",Tool!I108>0),Tool!I108,\"\")","v":""},"",""]
[null,{"$f":"IF(AND(D89>=12,D89<=20),12,\"\")","v":""},{"$f":"IF(D45>=$C$2,\"\",IF(B46<>\"\",IF($C$2<(Tool!E108-Tool!$D$98),\"\",IF(Tool!D109<>\"\",IF(Tool!$D$98<>0,Tool!E108-Tool!$D$98,Tool!E108),\"\")),\"\"))","v":""},{"$f":"IF(C18>=$C$2,\"\",IF(C18=\"\",\"\",IF((Tool!E109-Tool!$D$98)>$C$2,$C$2,IF(C18=\"\",\"\",IF(Tool!E108<>\"\",IF(AND($C$2>=(Tool!E109-Tool!$D$98),(Tool!E110-Tool!$D$98)>=(Tool!E109-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E109-Tool!$D$98,Tool!E109),$C$2),\"\")))))","v":""},{"$f":"IF(D102<=0,\"\",IF(AND(B102<>\"\",Tool!F109=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E102=\"TRUE\",Tool!I109>0),Tool!I109,\"\")","v":""},"",""]
[null,{"$f":"IF(AND(D89>=13,D89<=20),13,\"\")","v":""},{"$f":"IF(D46>=$C$2,\"\",IF(B47<>\"\",IF($C$2<(Tool!E109-Tool!$D$98),\"\",IF(Tool!D110<>\"\",IF(Tool!$D$98<>0,Tool!E109-Tool!$D$98,Tool!E109),\"\")),\"\"))","v":""},{"$f":"IF(C19>=$C$2,\"\",IF(C19=\"\",\"\",IF((Tool!E110-Tool!$D$98)>$C$2,$C$2,IF(C19=\"\",\"\",IF(Tool!E109<>\"\",IF(AND($C$2>=(Tool!E110-Tool!$D$98),(Tool!E111-Tool!$D$98)>=(Tool!E110-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E110-Tool!$D$98,Tool!E110),$C$2),\"\")))))","v":""},{"$f":"IF(D103<=0,\"\",IF(AND(B103<>\"\",Tool!F110=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E103=\"TRUE\",Tool!I110>0),Tool!I110,\"\")","v":""},"",""]
[null,{"$f":"IF(AND(D89>=14,D89<=20),14,\"\")","v":""},{"$f":"IF(D47>=$C$2,\"\",IF(B48<>\"\",IF($C$2<(Tool!E110-Tool!$D$98),\"\",IF(Tool!D111<>\"\",IF(Tool!$D$98<>0,Tool!E110-Tool!$D$98,Tool!E110),\"\")),\"\"))","v":""},{"$f":"IF(C20>=$C$2,\"\",IF(C20=\"\",\"\",IF((Tool!E111-Tool!$D$98)>$C$2,$C$2,IF(C20=\"\",\"\",IF(Tool!E110<>\"\",IF(AND($C$2>=(Tool!E111-Tool!$D$98),(Tool!E112-Tool!$D$98)>=(Tool!E111-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E111-Tool!$D$98,Tool!E111),$C$2),\"\")))))","v":""},{"$f":"IF(D104<=0,\"\",IF(AND(B104<>\"\",Tool!F111=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E104=\"TRUE\",Tool!I111>0),Tool!I111,\"\")","v":""},"",""]
[null,{"$f":"IF(AND(D89>=15,D89<=20),15,\"\")","v":""},{"$f":"IF(D48>=$C$2,\"\",IF(B49<>\"\",IF($C$2<(Tool!E111-Tool!$D$98),\"\",IF(Tool!D112<>\"\",IF(Tool!$D$98<>0,Tool!E111-Tool!$D$98,Tool!E111),\"\")),\"\"))","v":""},{"$f":"IF(C21>=$C$2,\"\",IF(C21=\"\",\"\",IF((Tool!E112-Tool!$D$98)>$C$2,$C$2,IF(C21=\"\",\"\",IF(Tool!E111<>\"\",IF(AND($C$2>=(Tool!E112-Tool!$D$98),(Tool!E113-Tool!$D$98)>=(Tool!E112-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E112-Tool!$D$98,Tool!E112),$C$2),\"\")))))","v":""},{"$f":"IF(D105<=0,\"\",IF(AND(B105<>\"\",Tool!F112=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E105=\"TRUE\",Tool!I112>0),Tool!I112,\"\")","v":""},"",""]
[null,{"$f":"IF(AND(D89>=16,D89<=20),16,\"\")","v":""},{"$f":"IF(D49>=$C$2,\"\",IF(B50<>\"\",IF($C$2<(Tool!E112-Tool!$D$98),\"\",IF(Tool!D113<>\"\",IF(Tool!$D$98<>0,Tool!E112-Tool!$D$98,Tool!E112),\"\")),\"\"))","v":""},{"$f":"IF(C22>=$C$2,\"\",IF(C22=\"\",\"\",IF((Tool!E113-Tool!$D$98)>$C$2,$C$2,IF(C22=\"\",\"\",IF(Tool!E112<>\"\",IF(AND($C$2>=(Tool!E113-Tool!$D$98),(Tool!E114-Tool!$D$98)>=(Tool!E113-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E113-Tool!$D$98,Tool!E113),$C$2),\"\")))))","v":""},{"$f":"IF(D106<=0,\"\",IF(AND(B106<>\"\",Tool!F113=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E106=\"TRUE\",Tool!I113>0),Tool!I113,\"\")","v":""},"",""]
[null,{"$f":"IF(AND(D89>=17,D89<=20),17,\"\")","v":""},{"$f":"IF(D50>=$C$2,\"\",IF(B51<>\"\",IF($C$2<(Tool!E113-Tool!$D$98),\"\",IF(Tool!D114<>\"\",IF(Tool!$D$98<>0,Tool!E113-Tool!$D$98,Tool!E113),\"\")),\"\"))","v":""},{"$f":"IF(C23>=$C$2,\"\",IF(C23=\"\",\"\",IF((Tool!E114-Tool!$D$98)>$C$2,$C$2,IF(C23=\"\",\"\",IF(Tool!E113<>\"\",IF(AND($C$2>=(Tool!E114-Tool!$D$98),(Tool!E115-Tool!$D$98)>=(Tool!E114-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E114-Tool!$D$98,Tool!E114),$C$2),\"\")))))","v":""},{"$f":"IF(D107<=0,\"\",IF(AND(B107<>\"\",Tool!F114=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E107=\"TRUE\",Tool!I114>0),Tool!I114,\"\")","v":""},"",""]
[null,{"$f":"IF(AND(D89>=18,D89<=20),18,\"\")","v":""},{"$f":"IF(D51>=$C$2,\"\",IF(B52<>\"\",IF($C$2<(Tool!E114-Tool!$D$98),\"\",IF(Tool!D115<>\"\",IF(Tool!$D$98<>0,Tool!E114-Tool!$D$98,Tool!E114),\"\")),\"\"))","v":""},{"$f":"IF(C24>=$C$2,\"\",IF(C24=\"\",\"\",IF((Tool!E115-Tool!$D$98)>$C$2,$C$2,IF(C24=\"\",\"\",IF(Tool!E114<>\"\",IF(AND($C$2>=(Tool!E115-Tool!$D$98),(Tool!E116-Tool!$D$98)>=(Tool!E115-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E115-Tool!$D$98,Tool!E115),$C$2),\"\")))))","v":""},{"$f":"IF(D108<=0,\"\",IF(AND(B108<>\"\",Tool!F115=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E108=\"TRUE\",Tool!I115>0),Tool!I115,\"\")","v":""},"",""]
[null,{"$f":"IF(AND(D89>=19,D89<=20),19,\"\")","v":""},{"$f":"IF(D52>=$C$2,\"\",IF(B53<>\"\",IF($C$2<(Tool!E115-Tool!$D$98),\"\",IF(Tool!D116<>\"\",IF(Tool!$D$98<>0,Tool!E115-Tool!$D$98,Tool!E115),\"\")),\"\"))","v":""},{"$f":"IF(C25>=$C$2,\"\",IF(C25=\"\",\"\",IF((Tool!E116-Tool!$D$98)>$C$2,$C$2,IF(C25=\"\",\"\",IF(Tool!E115<>\"\",IF(AND($C$2>=(Tool!E116-Tool!$D$98),(Tool!E117-Tool!$D$98)>=(Tool!E116-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E116-Tool!$D$98,Tool!E116),$C$2),\"\")))))","v":""},{"$f":"IF(D109<=0,\"\",IF(AND(B109<>\"\",Tool!F116=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E109=\"TRUE\",Tool!I116>0),Tool!I116,\"\")","v":""},"",""]
[null,{"$f":"IF(AND(D89=20),20,\"\")","v":""},{"$f":"IF(D53>=$C$2,\"\",IF(B54<>\"\",IF($C$2<(Tool!E116-Tool!$D$98),\"\",IF(Tool!D117<>\"\",IF(Tool!$D$98<>0,Tool!E116-Tool!$D$98,Tool!E116),\"\")),\"\"))","v":""},{"$f":"IF(C26>=$C$2,\"\",IF(C26=\"\",\"\",IF((Tool!E117-Tool!$D$98)>$C$2,$C$2,IF(C26=\"\",\"\",IF(Tool!E116<>\"\",IF(AND($C$2>=(Tool!E117-Tool!$D$98),(Tool!E118-Tool!$D$98)>=(Tool!E117-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E117-Tool!$D$98,Tool!E117),$C$2),\"\")))))","v":""},{"$f":"IF(D110<=0,\"\",IF(AND(B110<>\"\",Tool!F117=Tool!$J$9),\"TRUE\",\"\"))","v":""},{"$f":"IF(AND(E110=\"TRUE\",Tool!I117>0),Tool!I117,\"\")","v":""},"",""]
[]
[null,null,null,null,null,null,"Average Interior Width:",{"$f":"IF(AND(SUM(H91:H110)>0,SUM(G91:G110)>0),SUMPRODUCT(G91:G110,H91:H110)/SUM(H91:H110),0)","v":0},null,null,null,null,null,null,null,"Median Design"]
[null,null,null,null,null,null,"Avg. Inside Shoulder:",{"$f":"IF(SUM(H91:H110)>0,SUMPRODUCT(F91:F110,H91:H110)/SUM(H91:H110),0)","v":0}]
[null,null,null,null,null,null,"Length:",{"$f":"SUM(H91:H110)","v":0}]

{"sheet":"ROW_Old","index":8,"n_rows":113,"n_cols":19,"rows_kept":113,"cut":false,"hidden":true,"merged":[[5,1,5,2],[33,1,33,2],[61,1,61,2],[6,9,6,16],[112,16,117,19]]}
[]
[null,null,"Project Length:",{"$f":"IF((Tool!$J$54-Tool!$J$52)>0,(Tool!$J$54-Tool!$J$52),0)","v":0},null,"County:",{"$f":"Tool!H53","v":0}]
[]
[]
[null,"Segments:",{"$f":"Tool!#REF!","v":{"$error":"#REF!"}}]
[null,"Land Only"]
[null,"Segments","Begin","End","Land Use","Existing Width (ft)","Proposed Width (ft)","Length",null,"Properties Table"]
[null,{"$f":"IF(AND(C5>=1,C5<=20),1,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(Tool!H228<>\"\",IF(B8<>\"\",IF(Tool!H228=0,Tool!H228,Tool!H228-Tool!H228),\"\"),\"\")","v":""},{"$f":"IF(C8=\"\",\"\",IF((Tool!#REF!-Tool!H228)<(Tool!I228-Tool!H228),D2,IF(B8<>\"\",IF(Tool!I228<>\"\",IF(AND(B9=\"\",Tool!I228-Tool!H228<$D$2),$D$2,IF(B8=1,IF($D$2<(Tool!I228-Tool!$H$228),$D$2,IF(Tool!H228<>0,(Tool!I228-Tool!H228),Tool!I228)),\"\")),\"\"),\"\")))","v":""},{"$f":"IF(B8=\"\",\"\",IF(C8<>\"\",IF(Tool!J228=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E8=\"Land Only\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E8=\"Land Only\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(OR(C8=\"\",D8=\"\"),\"\",IF(E8=\"Land Only\",D8-C8,\"\"))","v":""},null,null,"Avg Width Existing","Avg. Width Proposed","Length","Area (sf)","Area (Acre)","Cost/Acre","Cost"]
[null,{"$f":"IF(AND(C5>=2,C5<=20),2,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B9<>\"\",IF(D8>=$D$2,\"\",IF($D$2<(Tool!I228-Tool!$H$228),\"\",IF(Tool!H229<>\"\",IF(Tool!$H$228<>0,Tool!I228-Tool!$H$228,Tool!I228),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C9=\"\",\"\",IF(B9=\"\",$D$2,IF((D8-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!I230-Tool!$H$228)>=(Tool!#REF!-Tool!H228)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B9=\"\",\"\",IF(C9<>\"\",IF(Tool!I229=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E9=\"Land Only\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E9=\"Land Only\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(F9<>\"\",IF(OR(C9=\"\",D9=\"\"),\"\",IF(E9=\"Land Only\",D9-C9,\"\")),\"\")","v":{"$error":"#REF!"}},null,"Land Only:",{"$f":"F29","v":{"$error":"#REF!"}},{"$f":"F30","v":{"$error":"#REF!"}},{"$f":"F31","v":{"$error":"#REF!"}},{"$f":"(L9*M9*5280)-(K9*M9*5280)","v":{"$error":"#REF!"}},{"$f":"N9/43560","v":{"$error":"#REF!"}},{"$f":"IF(Tool!H53<>\"\",VLOOKUP(G2,J16:N110,4,0),0)","v":0},{"$f":"O9*P9","v":{"$error":"#REF!"}}]
[null,{"$f":"IF(AND(C5>=3,C5<=20),3,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B10<>\"\",IF(D9>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!H230<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C10=\"\",\"\",IF(B10=\"\",$D$2,IF((D9-$C$8)>=$D$2,\"\",IF(Tool!I230<>\"\",IF(AND($D$2>=(Tool!I230-Tool!$H$228),(Tool!I231-Tool!$H$228)>=(Tool!I230-Tool!H229)),IF(Tool!$H$228<>\"\",Tool!I230-Tool!$H$228,Tool!I230),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B10=\"\",\"\",IF(C10<>\"\",IF(Tool!J230=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E10=\"Land Only\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E10=\"Land Only\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Residential:",{"$f":"F57","v":{"$error":"#REF!"}},{"$f":"F58","v":{"$error":"#REF!"}},{"$f":"F59","v":{"$error":"#REF!"}},{"$f":"(L10*M10*5280)-(K10*M10*5280)","v":{"$error":"#REF!"}},{"$f":"N10/43560","v":{"$error":"#REF!"}},{"$f":"IF(Tool!H53<>\"\",VLOOKUP(G2,J16:N110,3,0),0)","v":0},{"$f":"O10*P10","v":{"$error":"#REF!"}}]
[null,{"$f":"IF(AND(C5>=4,C5<=20),4,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B11<>\"\",IF(D10>=$D$2,\"\",IF($D$2<(Tool!I230-Tool!$H$228),\"\",IF(Tool!H231<>\"\",IF(Tool!$H$228<>0,Tool!I230-Tool!$H$228,Tool!I230),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C11=\"\",\"\",IF(B11=\"\",$D$2,IF((D10-$C$8)>=$D$2,\"\",IF(Tool!I231<>\"\",IF(AND($D$2>=(Tool!I231-Tool!$H$228),(Tool!I232-Tool!$H$228)>=(Tool!I231-Tool!H230)),IF(Tool!$H$228<>\"\",Tool!I231-Tool!$H$228,Tool!I231),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B11=\"\",\"\",IF(C11<>\"\",IF(Tool!J231=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E11=\"Land Only\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E11=\"Land Only\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Com/Ind:",{"$f":"F85","v":{"$error":"#REF!"}},{"$f":"F86","v":{"$error":"#REF!"}},{"$f":"F87","v":{"$error":"#REF!"}},{"$f":"(L11*M11*5280)-(K11*M11*5280)","v":{"$error":"#REF!"}},{"$f":"N11/43560","v":{"$error":"#REF!"}},{"$f":"IF(Tool!H53<>\"\",VLOOKUP(G2,J16:N110,5,0),0)","v":0},{"$f":"O11*P11","v":{"$error":"#REF!"}}]
[null,{"$f":"IF(AND(C5>=5,C5<=20),5,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B12<>\"\",IF(D11>=$D$2,\"\",IF($D$2<(Tool!I231-Tool!$H$228),\"\",IF(Tool!H232<>\"\",IF(Tool!$H$228<>0,Tool!I231-Tool!$H$228,Tool!I231),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C12=\"\",\"\",IF(B12=\"\",$D$2,IF((D11-$C$8)>=$D$2,\"\",IF(Tool!I232<>\"\",IF(AND($D$2>=(Tool!I232-Tool!$H$228),(Tool!I233-Tool!$H$228)>=(Tool!I232-Tool!H231)),IF(Tool!$H$228<>\"\",Tool!I232-Tool!$H$228,Tool!I232),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B12=\"\",\"\",IF(C12<>\"\",IF(Tool!J232=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E12=\"Land Only\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E12=\"Land Only\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,null,null,null,null,null,null,"Total:",{"$f":"SUM(Q9:Q11)","v":{"$error":"#REF!"}}]
[null,{"$f":"IF(AND(C5>=6,C5<=20),6,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B13<>\"\",IF(D12>=$D$2,\"\",IF($D$2<(Tool!I232-Tool!$H$228),\"\",IF(Tool!H233<>\"\",IF(Tool!$H$228<>0,Tool!I232-Tool!$H$228,Tool!I232),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C13=\"\",\"\",IF(B13=\"\",$D$2,IF((D12-$C$8)>=$D$2,\"\",IF(Tool!I233<>\"\",IF(AND($D$2>=(Tool!I233-Tool!$H$228),(Tool!E234-Tool!$H$228)>=(Tool!I233-Tool!H232)),IF(Tool!$H$228<>\"\",Tool!I233-Tool!$H$228,Tool!I233),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B13=\"\",\"\",IF(C13<>\"\",IF(Tool!J233=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E13=\"Land Only\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E13=\"Land Only\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"}]
[null,{"$f":"IF(AND(C5>=7,C5<=20),7,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B14<>\"\",IF(D13>=$D$2,\"\",IF($D$2<(Tool!I233-Tool!$H$228),\"\",IF(Tool!D234<>\"\",IF(Tool!$H$228<>0,Tool!I233-Tool!$H$228,Tool!I233),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C14=\"\",\"\",IF(B14=\"\",$D$2,IF((D13-$C$8)>=$D$2,\"\",IF(Tool!E234<>\"\",IF(AND($D$2>=(Tool!E234-Tool!$H$228),(Tool!E235-Tool!$H$228)>=(Tool!E234-Tool!H233)),IF(Tool!$H$228<>\"\",Tool!E234-Tool!$H$228,Tool!E234),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B14=\"\",\"\",IF(C14<>\"\",IF(Tool!F234=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E14=\"Land Only\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E14=\"Land Only\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"}]
[null,{"$f":"IF(AND(C5>=8,C5<=20),8,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B15<>\"\",IF(D14>=$D$2,\"\",IF($D$2<(Tool!E234-Tool!$H$228),\"\",IF(Tool!D235<>\"\",IF(Tool!$H$228<>0,Tool!E234-Tool!$H$228,Tool!E234),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C15=\"\",\"\",IF(B15=\"\",$D$2,IF((D14-$C$8)>=$D$2,\"\",IF(Tool!E235<>\"\",IF(AND($D$2>=(Tool!E235-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!E235-Tool!D234)),IF(Tool!$H$228<>\"\",Tool!E235-Tool!$H$228,Tool!E235),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B15=\"\",\"\",IF(C15<>\"\",IF(Tool!F235=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E15=\"Land Only\",Tool!G235>=0),Tool!G235,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E15=\"Land Only\",IF(Tool!G235>Tool!H235,Tool!G235,IF(Tool!G235>=0,Tool!H235)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"County","MSA County","Residential","Land Only","Com/Ind",null,null,"Residential","Agricultural","Comm/Ind"]
[null,{"$f":"IF(AND(C5>=9,C5<=20),9,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B16<>\"\",IF(D15>=$D$2,\"\",IF($D$2<(Tool!E235-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!E235-Tool!$H$228,Tool!E235),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C16=\"\",\"\",IF(B16=\"\",$D$2,IF((D15-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!D235)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B16=\"\",\"\",IF(C16<>\"\",IF(Tool!#REF!=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E16=\"Land Only\",Tool!G237>=0),Tool!G237,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E16=\"Land Only\",IF(Tool!G237>Tool!H237,Tool!G237,IF(Tool!G237>=0,Tool!H237)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Anderson ","Knox",{"$f":"Q22","v":315000},{"$f":"R22","v":59000},{"$f":"S22","v":372272.72727272729},null,"Hamilton",215000,30500,757461.5384615385]
[null,{"$f":"IF(AND(C5>=10,C5<=20),10,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B17<>\"\",IF(D16>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C17=\"\",\"\",IF(B17=\"\",$D$2,IF((D16-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B17=\"\",\"\",IF(C17<>\"\",IF(Tool!#REF!=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E17=\"Land Only\",Tool!G238>=0),Tool!G238,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E17=\"Land Only\",IF(Tool!G238>Tool!H238,Tool!G238,IF(Tool!G238>=0,Tool!H238)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Bedford","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284},null,"Montgomery",185000,14000,700357.14285714284]
[null,{"$f":"IF(AND(C5>=11,C5<=20),11,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B18<>\"\",IF(D17>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C18=\"\",\"\",IF(B18=\"\",$D$2,IF((D17-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B18=\"\",\"\",IF(C18<>\"\",IF(Tool!#REF!=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E18=\"Land Only\",Tool!G239>=0),Tool!G239,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E18=\"Land Only\",IF(Tool!G239>Tool!H239,Tool!G239,IF(Tool!G239>=0,Tool!H239)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Benton","Madison",{"$f":"Q19","v":180000},{"$f":"R19","v":10000},{"$f":"S19","v":375000},null,"Bradley",180000,6500,330000]
[null,{"$f":"IF(AND(C5>=12,C5<=20),12,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B19<>\"\",IF(D18>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C19=\"\",\"\",IF(B19=\"\",$D$2,IF((D18-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B19=\"\",\"\",IF(C19<>\"\",IF(Tool!#REF!=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E19=\"Land Only\",Tool!G240>=0),Tool!G240,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E19=\"Land Only\",IF(Tool!G240>Tool!H240,Tool!G240,IF(Tool!G240>=0,Tool!H240)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Bledsoe ","Bradley",{"$f":"Q18","v":180000},{"$f":"R18","v":6500},{"$f":"S18","v":330000},null,"Madison",180000,10000,375000]
[null,{"$f":"IF(AND(C5>=13,C5<=20),13,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B20<>\"\",IF(D19>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C20=\"\",\"\",IF(B20=\"\",$D$2,IF((D19-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B20=\"\",\"\",IF(C20<>\"\",IF(Tool!#REF!=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E20=\"Land Only\",Tool!G241>=0),Tool!G241,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E20=\"Land Only\",IF(Tool!G241>Tool!H241,Tool!G241,IF(Tool!G241>=0,Tool!H241)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Blount ","Knox",{"$f":"Q22","v":315000},{"$f":"R22","v":59000},{"$f":"S22","v":372272.72727272729},null,"Washington",195000,18000,281666.66666666669]
[null,{"$f":"IF(AND(C5>=14,C5<=20),14,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B21<>\"\",IF(D20>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C21=\"\",\"\",IF(B21=\"\",$D$2,IF((D20-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B21=\"\",\"\",IF(C21<>\"\",IF(Tool!#REF!=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E21=\"Land Only\",Tool!G242>=0),Tool!G242,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E21=\"Land Only\",IF(Tool!G242>Tool!H242,Tool!G242,IF(Tool!G242>=0,Tool!H242)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Bradley ","Bradley",{"$f":"Q18","v":180000},{"$f":"R18","v":6500},{"$f":"S18","v":330000},null,"Sullivan",205000,16500,205000]
[null,{"$f":"IF(AND(C5>=15,C5<=20),15,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B22<>\"\",IF(D21>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C22=\"\",\"\",IF(B22=\"\",$D$2,IF((D21-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!E243-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B22=\"\",\"\",IF(C22<>\"\",IF(Tool!#REF!=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E22=\"Land Only\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E22=\"Land Only\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Campbell ","Knox",{"$f":"Q22","v":315000},{"$f":"R22","v":59000},{"$f":"S22","v":372272.72727272729},null,"Knox",315000,59000,372272.72727272729]
[null,{"$f":"IF(AND(C5>=16,C5<=20),16,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B23<>\"\",IF(D22>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!D243<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C23=\"\",\"\",IF(B23=\"\",$D$2,IF((D22-$C$8)>=$D$2,\"\",IF(Tool!E243<>\"\",IF(AND($D$2>=(Tool!E243-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!E243-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!E243-Tool!$H$228,Tool!E243),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B23=\"\",\"\",IF(C23<>\"\",IF(Tool!F243=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E23=\"Land Only\",Tool!G243>=0),Tool!G243,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E23=\"Land Only\",IF(Tool!G243>Tool!H243,Tool!G243,IF(Tool!G243>=0,Tool!H243)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Cannon","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284},null,"Shelby",275000,32500,236500]
[null,{"$f":"IF(AND(C5>=17,C5<=20),17,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B24<>\"\",IF(D23>=$D$2,\"\",IF($D$2<(Tool!E243-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!E243-Tool!$H$228,Tool!E243),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C24=\"\",\"\",IF(B24=\"\",$D$2,IF((D23-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!D243)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B24=\"\",\"\",IF(C24<>\"\",IF(Tool!#REF!=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E24=\"Land Only\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E24=\"Land Only\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Carroll","Madison",{"$f":"Q19","v":180000},10000,375000,null,"Hamblen",213000,11000,287380.95238095243]
[null,{"$f":"IF(AND(C5>=18,C5<=20),18,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B25<>\"\",IF(D24>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C25=\"\",\"\",IF(B25=\"\",$D$2,IF((D24-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B25=\"\",\"\",IF(C25<>\"\",IF(Tool!#REF!=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E25=\"Land Only\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E25=\"Land Only\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Carter","Washington",195000,18000,281666.66666666669,null,"Davidson",290000,30000,310714.28571428568]
[null,{"$f":"IF(AND(C5>=19,C5<=20),19,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B26<>\"\",IF(D25>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C26=\"\",\"\",IF(B26=\"\",$D$2,IF((D25-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B26=\"\",\"\",IF(C26<>\"\",IF(Tool!#REF!=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E26=\"Land Only\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E26=\"Land Only\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Cheatham","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284},null,"Rutherford",223000,26000,687328.76712328766]
[null,{"$f":"IF(AND(C5=20),20,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B27<>\"\",IF(D26>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C27=\"\",\"\",IF(B27=\"\",$D$2,IF((D26-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B27=\"\",\"\",IF(C27<>\"\",IF(Tool!#REF!=Tool!$I$7,\"Land Only\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E27=\"Land Only\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E27=\"Land Only\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Chester","Madison",{"$f":"Q19","v":180000},{"$f":"R19","v":10000},{"$f":"S19","v":375000},null,"Williamson",275000,25000,577500]
[null,null,null,null,null,null,null,null,null,"Claiborne ","Sullivan",{"$f":"Q21","v":205000},{"$f":"R21","v":16500},{"$f":"S21","v":205000}]
[null,null,null,null,"Average Existing Width:",{"$f":"IF(SUM(H8:H27)>0,SUMPRODUCT(F8:F27,H8:H27)/SUM(H8:H27),0)","v":{"$error":"#REF!"}},null,null,null,"Clay","Bradley",{"$f":"Q18","v":180000},{"$f":"R18","v":6500},{"$f":"S18","v":330000}]
[null,null,null,null,"Average Proposed Width:",{"$f":"IF(SUM(H8:H27)>0,SUMPRODUCT(G8:G27,H8:H27)/SUM(H8:H27),0)","v":{"$error":"#REF!"}},null,null,null,"Cocke","Hamblen",{"$f":"Q24","v":213000},{"$f":"R24","v":11000},{"$f":"S24","v":287380.95238095243}]
[null,null,null,null,"Length:",{"$f":"SUM(H8:H27)","v":{"$error":"#REF!"}},null,null,null,"Coffee ","Bradley",{"$f":"Q18","v":180000},6500,330000]
[null,null,null,null,null,null,null,null,null,"Crockett","Madison",180000,10000,375000]
[null,"Segments:",{"$f":"Tool!#REF!","v":{"$error":"#REF!"}},null,null,null,null,null,null,"Cumberland","Bradley",{"$f":"Q18","v":180000},{"$f":"R18","v":6500},{"$f":"S18","v":330000}]
[null,"Residential",null,null,null,null,null,null,null,"Davidson","Davidson",{"$f":"Q25","v":290000},{"$f":"R25","v":30000},{"$f":"S25","v":310714.28571428568}]
[null,"Segments","Begin","End","Land Use","Width (ft)","Proposed Width (ft)","Length",null,"Decatur","Madison",{"$f":"Q19","v":180000},{"$f":"R19","v":10000},{"$f":"S19","v":375000}]
[null,{"$f":"IF(AND(C33>=1,C33<=20),1,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(Tool!H228<>\"\",IF(B8<>\"\",IF(Tool!H228=0,Tool!H228,Tool!H228-Tool!H228),\"\"),\"\")","v":""},{"$f":"IF(C8=\"\",\"\",IF((Tool!#REF!-Tool!H228)<(Tool!I228-Tool!H228),D2,IF(B8<>\"\",IF(Tool!I228<>\"\",IF(AND(B9=\"\",Tool!I228-Tool!H228<$D$2),$D$2,IF(B8=1,IF($D$2<(Tool!I228-Tool!$H$228),$D$2,IF(Tool!H228<>0,(Tool!I228-Tool!H228),Tool!I228)),\"\")),\"\"),\"\")))","v":""},{"$f":"IF(B36=\"\",\"\",IF(C36<>\"\",IF(Tool!J228=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E36=\"Residential\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E36=\"Residential\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(F36<>\"\",IF(OR(C36=\"\",D36=\"\"),\"\",IF(E36=\"Residential\",D36-C36,\"\")),\"\")","v":{"$error":"#REF!"}},null,"DeKalb ","Bradley",{"$f":"Q18","v":180000},{"$f":"R18","v":6500},{"$f":"S18","v":330000}]
[null,{"$f":"IF(AND(C33>=2,C33<=20),2,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B9<>\"\",IF(D8>=$D$2,\"\",IF($D$2<(Tool!I228-Tool!$H$228),\"\",IF(Tool!H229<>\"\",IF(Tool!$H$228<>0,Tool!I228-Tool!$H$228,Tool!I228),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C9=\"\",\"\",IF(B37=\"\",$D$2,IF((D8-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!I230-Tool!$H$228)>=(Tool!#REF!-Tool!H228)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B37=\"\",\"\",IF(C37<>\"\",IF(Tool!I229=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E37=\"Residential\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E37=\"Residential\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(F37<>\"\",IF(OR(C37=\"\",D37=\"\"),\"\",IF(E37=\"Residential\",D37-C37,\"\")),\"\")","v":{"$error":"#REF!"}},null,"Dickson ","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[null,{"$f":"IF(AND(C33>=3,C33<=20),3,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B10<>\"\",IF(D9>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!H230<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C10=\"\",\"\",IF(B38=\"\",$D$2,IF((D9-$C$8)>=$D$2,\"\",IF(Tool!I230<>\"\",IF(AND($D$2>=(Tool!I230-Tool!$H$228),(Tool!I231-Tool!$H$228)>=(Tool!I230-Tool!H229)),IF(Tool!$H$228<>\"\",Tool!I230-Tool!$H$228,Tool!I230),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B38=\"\",\"\",IF(C38<>\"\",IF(Tool!J230=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E38=\"Residential\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E38=\"Residential\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Dyer","Madison",{"$f":"Q19","v":180000},{"$f":"R19","v":10000},{"$f":"S19","v":375000}]
[null,{"$f":"IF(AND(C33>=4,C33<=20),4,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B11<>\"\",IF(D10>=$D$2,\"\",IF($D$2<(Tool!I230-Tool!$H$228),\"\",IF(Tool!H231<>\"\",IF(Tool!$H$228<>0,Tool!I230-Tool!$H$228,Tool!I230),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C11=\"\",\"\",IF(B39=\"\",$D$2,IF((D10-$C$8)>=$D$2,\"\",IF(Tool!I231<>\"\",IF(AND($D$2>=(Tool!I231-Tool!$H$228),(Tool!I232-Tool!$H$228)>=(Tool!I231-Tool!H230)),IF(Tool!$H$228<>\"\",Tool!I231-Tool!$H$228,Tool!I231),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B39=\"\",\"\",IF(C39<>\"\",IF(Tool!J231=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E39=\"Residential\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E39=\"Residential\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Fayette","Shelby",{"$f":"Q23","v":275000},{"$f":"R23","v":32500},{"$f":"S23","v":236500}]
[null,{"$f":"IF(AND(C33>=5,C33<=20),5,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B12<>\"\",IF(D11>=$D$2,\"\",IF($D$2<(Tool!I231-Tool!$H$228),\"\",IF(Tool!H232<>\"\",IF(Tool!$H$228<>0,Tool!I231-Tool!$H$228,Tool!I231),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C12=\"\",\"\",IF(B40=\"\",$D$2,IF((D11-$C$8)>=$D$2,\"\",IF(Tool!I232<>\"\",IF(AND($D$2>=(Tool!I232-Tool!$H$228),(Tool!I233-Tool!$H$228)>=(Tool!I232-Tool!H231)),IF(Tool!$H$228<>\"\",Tool!I232-Tool!$H$228,Tool!I232),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B40=\"\",\"\",IF(C40<>\"\",IF(Tool!J232=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E40=\"Residential\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E40=\"Residential\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Fentress ","Bradley",{"$f":"Q18","v":180000},{"$f":"R18","v":6500},{"$f":"S18","v":330000}]
[null,{"$f":"IF(AND(C33>=6,C33<=20),6,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B13<>\"\",IF(D12>=$D$2,\"\",IF($D$2<(Tool!I232-Tool!$H$228),\"\",IF(Tool!H233<>\"\",IF(Tool!$H$228<>0,Tool!I232-Tool!$H$228,Tool!I232),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C13=\"\",\"\",IF(B41=\"\",$D$2,IF((D12-$C$8)>=$D$2,\"\",IF(Tool!I233<>\"\",IF(AND($D$2>=(Tool!I233-Tool!$H$228),(Tool!E234-Tool!$H$228)>=(Tool!I233-Tool!H232)),IF(Tool!$H$228<>\"\",Tool!I233-Tool!$H$228,Tool!I233),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B41=\"\",\"\",IF(C41<>\"\",IF(Tool!J233=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E41=\"Residential\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E41=\"Residential\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Franklin","Bradley",{"$f":"Q18","v":180000},6500,330000]
[null,{"$f":"IF(AND(C33>=7,C33<=20),7,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B14<>\"\",IF(D13>=$D$2,\"\",IF($D$2<(Tool!I233-Tool!$H$228),\"\",IF(Tool!D234<>\"\",IF(Tool!$H$228<>0,Tool!I233-Tool!$H$228,Tool!I233),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C14=\"\",\"\",IF(B42=\"\",$D$2,IF((D13-$C$8)>=$D$2,\"\",IF(Tool!E234<>\"\",IF(AND($D$2>=(Tool!E234-Tool!$H$228),(Tool!E235-Tool!$H$228)>=(Tool!E234-Tool!H233)),IF(Tool!$H$228<>\"\",Tool!E234-Tool!$H$228,Tool!E234),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B42=\"\",\"\",IF(C42<>\"\",IF(Tool!F234=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E42=\"Residential\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E42=\"Residential\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Gibson","Madison",180000,10000,375000]
[null,{"$f":"IF(AND(C33>=8,C33<=20),8,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B15<>\"\",IF(D14>=$D$2,\"\",IF($D$2<(Tool!E234-Tool!$H$228),\"\",IF(Tool!D235<>\"\",IF(Tool!$H$228<>0,Tool!E234-Tool!$H$228,Tool!E234),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C15=\"\",\"\",IF(B43=\"\",$D$2,IF((D14-$C$8)>=$D$2,\"\",IF(Tool!E235<>\"\",IF(AND($D$2>=(Tool!E235-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!E235-Tool!D234)),IF(Tool!$H$228<>\"\",Tool!E235-Tool!$H$228,Tool!E235),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B43=\"\",\"\",IF(C43<>\"\",IF(Tool!F235=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E43=\"Residential\",Tool!G235>=0),Tool!G235,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E43=\"Residential\",IF(Tool!G235>Tool!H235,Tool!G235,IF(Tool!G235>=0,Tool!H235)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Giles","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[null,{"$f":"IF(AND(C33>=9,C33<=20),9,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B16<>\"\",IF(D15>=$D$2,\"\",IF($D$2<(Tool!E235-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!E235-Tool!$H$228,Tool!E235),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C16=\"\",\"\",IF(B44=\"\",$D$2,IF((D15-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!D235)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B44=\"\",\"\",IF(C44<>\"\",IF(Tool!#REF!=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E44=\"Residential\",Tool!G237>=0),Tool!G237,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E44=\"Residential\",IF(Tool!G237>Tool!H237,Tool!G237,IF(Tool!G237>=0,Tool!H237)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Grainger","Knox",{"$f":"Q22","v":315000},{"$f":"R22","v":59000},{"$f":"S22","v":372272.72727272729}]
[null,{"$f":"IF(AND(C33>=10,C33<=20),10,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B17<>\"\",IF(D16>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C17=\"\",\"\",IF(B45=\"\",$D$2,IF((D16-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B45=\"\",\"\",IF(C45<>\"\",IF(Tool!#REF!=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E45=\"Residential\",Tool!G238>=0),Tool!G238,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E45=\"Residential\",IF(Tool!G238>Tool!H238,Tool!G238,IF(Tool!G238>=0,Tool!H238)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Greene ","Washington",{"$f":"Q20","v":195000},{"$f":"R20","v":18000},{"$f":"S20","v":281666.66666666669}]
[null,{"$f":"IF(AND(C33>=11,C33<=20),11,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B18<>\"\",IF(D17>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C18=\"\",\"\",IF(B46=\"\",$D$2,IF((D17-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B46=\"\",\"\",IF(C46<>\"\",IF(Tool!#REF!=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E46=\"Residential\",Tool!G239>=0),Tool!G239,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E46=\"Residential\",IF(Tool!G239>Tool!H239,Tool!G239,IF(Tool!G239>=0,Tool!H239)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Grundy","Bradley",{"$f":"Q18","v":180000},{"$f":"R18","v":6500},{"$f":"S18","v":330000}]
[null,{"$f":"IF(AND(C33>=12,C33<=20),12,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B19<>\"\",IF(D18>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C19=\"\",\"\",IF(B47=\"\",$D$2,IF((D18-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B47=\"\",\"\",IF(C47<>\"\",IF(Tool!#REF!=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E47=\"Residential\",Tool!G240>=0),Tool!G240,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E47=\"Residential\",IF(Tool!G240>Tool!H240,Tool!G240,IF(Tool!G240>=0,Tool!H240)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Hamblen ","Hamblen",{"$f":"Q24","v":213000},{"$f":"R24","v":11000},{"$f":"S24","v":287380.95238095243}]
[null,{"$f":"IF(AND(C33>=13,C33<=20),13,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B20<>\"\",IF(D19>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C20=\"\",\"\",IF(B48=\"\",$D$2,IF((D19-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B48=\"\",\"\",IF(C48<>\"\",IF(Tool!#REF!=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E48=\"Residential\",Tool!G241>=0),Tool!G241,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E48=\"Residential\",IF(Tool!G241>Tool!H241,Tool!G241,IF(Tool!G241>=0,Tool!H241)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Hamilton ","Hamilton",{"$f":"Q16","v":215000},{"$f":"R16","v":30500},{"$f":"S16","v":757461.5384615385}]
[null,{"$f":"IF(AND(C33>=14,C33<=20),14,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B21<>\"\",IF(D20>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C21=\"\",\"\",IF(B49=\"\",$D$2,IF((D20-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B49=\"\",\"\",IF(C49<>\"\",IF(Tool!#REF!=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E49=\"Residential\",Tool!G242>=0),Tool!G242,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E49=\"Residential\",IF(Tool!G242>Tool!H242,Tool!G242,IF(Tool!G242>=0,Tool!H242)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Hancock","Sullivan",{"$f":"Q21","v":205000},{"$f":"R21","v":16500},{"$f":"S21","v":205000}]
[null,{"$f":"IF(AND(C33>=15,C33<=20),15,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B22<>\"\",IF(D21>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C22=\"\",\"\",IF(B50=\"\",$D$2,IF((D21-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!E243-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B50=\"\",\"\",IF(C50<>\"\",IF(Tool!#REF!=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E50=\"Residential\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E50=\"Residential\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Hardeman","Madison",{"$f":"Q19","v":180000},{"$f":"R19","v":10000},{"$f":"S19","v":375000}]
[null,{"$f":"IF(AND(C33>=16,C33<=20),16,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B23<>\"\",IF(D22>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!D243<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C23=\"\",\"\",IF(B51=\"\",$D$2,IF((D22-$C$8)>=$D$2,\"\",IF(Tool!E243<>\"\",IF(AND($D$2>=(Tool!E243-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!E243-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!E243-Tool!$H$228,Tool!E243),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B51=\"\",\"\",IF(C51<>\"\",IF(Tool!F243=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E51=\"Residential\",Tool!G243>=0),Tool!G243,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E51=\"Residential\",IF(Tool!G243>Tool!H243,Tool!G243,IF(Tool!G243>=0,Tool!H243)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Hardin ","Madison",{"$f":"Q19","v":180000},{"$f":"R19","v":10000},{"$f":"S19","v":375000}]
[null,{"$f":"IF(AND(C33>=17,C33<=20),17,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B24<>\"\",IF(D23>=$D$2,\"\",IF($D$2<(Tool!E243-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!E243-Tool!$H$228,Tool!E243),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C24=\"\",\"\",IF(B52=\"\",$D$2,IF((D23-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!D243)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B52=\"\",\"\",IF(C52<>\"\",IF(Tool!#REF!=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E52=\"Residential\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E52=\"Residential\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Hawkins","Sullivan",{"$f":"Q21","v":205000},{"$f":"R21","v":16500},{"$f":"S21","v":205000}]
[null,{"$f":"IF(AND(C33>=18,C33<=20),18,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B25<>\"\",IF(D24>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C25=\"\",\"\",IF(B53=\"\",$D$2,IF((D24-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B53=\"\",\"\",IF(C53<>\"\",IF(Tool!#REF!=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E53=\"Residential\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E53=\"Residential\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Haywood","Madison",{"$f":"Q19","v":180000},{"$f":"R19","v":10000},{"$f":"S19","v":375000}]
[null,{"$f":"IF(AND(C33>=19,C33<=20),19,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B26<>\"\",IF(D25>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C26=\"\",\"\",IF(B54=\"\",$D$2,IF((D25-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B54=\"\",\"\",IF(C54<>\"\",IF(Tool!#REF!=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E54=\"Residential\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E54=\"Residential\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Henderson","Madison",{"$f":"Q19","v":180000},{"$f":"R19","v":10000},{"$f":"S19","v":375000}]
[null,{"$f":"IF(AND(C33=20),20,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B27<>\"\",IF(D26>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C27=\"\",\"\",IF(B55=\"\",$D$2,IF((D26-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B55=\"\",\"\",IF(C55<>\"\",IF(Tool!#REF!=Tool!$I$8,\"Residential\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E55=\"Residential\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E55=\"Residential\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Henry ","Madison",{"$f":"Q19","v":180000},{"$f":"R19","v":10000},{"$f":"S19","v":375000}]
[null,null,null,null,null,null,null,null,null,"Hickman","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[null,null,null,null,"Average Existing Width:",{"$f":"IF(SUM(H36:H55)>0,SUMPRODUCT(F36:F55,H36:H55)/SUM(H36:H55),0)","v":{"$error":"#REF!"}},null,null,null,"Houston","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[null,null,null,null,"Average Proposed Width:",{"$f":"IF(SUM(H36:H55)>0,SUMPRODUCT(G36:G55,H36:H55)/SUM(H36:H55),0)","v":{"$error":"#REF!"}},null,null,null,"Humphreys","Montgomery",{"$f":"Q17","v":185000},14000,700357.14285714284]
[null,null,null,null,"Length:",{"$f":"SUM(H36:H55)","v":{"$error":"#REF!"}},null,null,null,"Jackson","Bradley",180000,6500,330000]
[null,null,null,null,null,null,null,null,null,"Jefferson ","Hamblen",{"$f":"Q24","v":213000},{"$f":"R24","v":11000},{"$f":"S24","v":287380.95238095243}]
[null,"Segments:",{"$f":"Tool!#REF!","v":{"$error":"#REF!"}},null,null,null,null,null,null,"Johnson ","Sullivan",{"$f":"Q21","v":205000},16500,205000]
[null,"Commercial/Industrial",null,null,null,null,null,null,null,"Knox ","Knox",315000,59000,372272.72727272729]
[null,"Segments","Begin","End","Land Use","Width (ft)","Proposed Width (ft)","Length",null,"Lake","Madison",{"$f":"Q19","v":180000},{"$f":"R19","v":10000},{"$f":"S19","v":375000}]
[null,{"$f":"IF(AND(C61>=1,C61<=20),1,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(Tool!H228<>\"\",IF(B8<>\"\",IF(Tool!H228=0,Tool!H228,Tool!H228-Tool!H228),\"\"),\"\")","v":""},{"$f":"IF(C8=\"\",\"\",IF((Tool!#REF!-Tool!H228)<(Tool!I228-Tool!H228),D2,IF(B8<>\"\",IF(Tool!I228<>\"\",IF(AND(B9=\"\",Tool!I228-Tool!H228<$D$2),$D$2,IF(B8=1,IF($D$2<(Tool!I228-Tool!$H$228),$D$2,IF(Tool!H228<>0,(Tool!I228-Tool!H228),Tool!I228)),\"\")),\"\"),\"\")))","v":""},{"$f":"IF(B64=\"\",\"\",IF(C64<>\"\",IF(Tool!J228=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E64=\"Com/Ind\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E64=\"Com/Ind\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(F64<>\"\",IF(OR(C64=\"\",D64=\"\"),\"\",IF(E64=\"Com/Ind\",D64-C64,\"\")),\"\")","v":{"$error":"#REF!"}},null,"Lauderdale","Madison",{"$f":"Q19","v":180000},{"$f":"R19","v":10000},{"$f":"S19","v":375000}]
[null,{"$f":"IF(AND(C61>=2,C61<=20),2,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B9<>\"\",IF(D8>=$D$2,\"\",IF($D$2<(Tool!I228-Tool!$H$228),\"\",IF(Tool!H229<>\"\",IF(Tool!$H$228<>0,Tool!I228-Tool!$H$228,Tool!I228),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C9=\"\",\"\",IF(B65=\"\",$D$2,IF((D8-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!I230-Tool!$H$228)>=(Tool!#REF!-Tool!H228)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B65=\"\",\"\",IF(C65<>\"\",IF(Tool!I229=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E65=\"Com/Ind\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E65=\"Com/Ind\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(F65<>\"\",IF(OR(C65=\"\",D65=\"\"),\"\",IF(E65=\"Com/Ind\",D65-C65,\"\")),\"\")","v":{"$error":"#REF!"}},null,"Lawrence","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[null,{"$f":"IF(AND(C61>=3,C61<=20),3,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B10<>\"\",IF(D9>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!H230<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C10=\"\",\"\",IF(B66=\"\",$D$2,IF((D9-$C$8)>=$D$2,\"\",IF(Tool!I230<>\"\",IF(AND($D$2>=(Tool!I230-Tool!$H$228),(Tool!I231-Tool!$H$228)>=(Tool!I230-Tool!H229)),IF(Tool!$H$228<>\"\",Tool!I230-Tool!$H$228,Tool!I230),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B66=\"\",\"\",IF(C66<>\"\",IF(Tool!J230=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E66=\"Com/Ind\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E66=\"Com/Ind\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Lewis","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[null,{"$f":"IF(AND(C61>=4,C61<=20),4,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B11<>\"\",IF(D10>=$D$2,\"\",IF($D$2<(Tool!I230-Tool!$H$228),\"\",IF(Tool!H231<>\"\",IF(Tool!$H$228<>0,Tool!I230-Tool!$H$228,Tool!I230),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C11=\"\",\"\",IF(B67=\"\",$D$2,IF((D10-$C$8)>=$D$2,\"\",IF(Tool!I231<>\"\",IF(AND($D$2>=(Tool!I231-Tool!$H$228),(Tool!I232-Tool!$H$228)>=(Tool!I231-Tool!H230)),IF(Tool!$H$228<>\"\",Tool!I231-Tool!$H$228,Tool!I231),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B67=\"\",\"\",IF(C67<>\"\",IF(Tool!J231=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E67=\"Com/Ind\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E67=\"Com/Ind\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Lincoln","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[null,{"$f":"IF(AND(C61>=5,C61<=20),5,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B12<>\"\",IF(D11>=$D$2,\"\",IF($D$2<(Tool!I231-Tool!$H$228),\"\",IF(Tool!H232<>\"\",IF(Tool!$H$228<>0,Tool!I231-Tool!$H$228,Tool!I231),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C12=\"\",\"\",IF(B68=\"\",$D$2,IF((D11-$C$8)>=$D$2,\"\",IF(Tool!I232<>\"\",IF(AND($D$2>=(Tool!I232-Tool!$H$228),(Tool!I233-Tool!$H$228)>=(Tool!I232-Tool!H231)),IF(Tool!$H$228<>\"\",Tool!I232-Tool!$H$228,Tool!I232),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B68=\"\",\"\",IF(C68<>\"\",IF(Tool!J232=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E68=\"Com/Ind\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E68=\"Com/Ind\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Loudon ","Knox",{"$f":"Q22","v":315000},{"$f":"R22","v":59000},{"$f":"S22","v":372272.72727272729}]
[null,{"$f":"IF(AND(C61>=6,C61<=20),6,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B13<>\"\",IF(D12>=$D$2,\"\",IF($D$2<(Tool!I232-Tool!$H$228),\"\",IF(Tool!H233<>\"\",IF(Tool!$H$228<>0,Tool!I232-Tool!$H$228,Tool!I232),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C13=\"\",\"\",IF(B69=\"\",$D$2,IF((D12-$C$8)>=$D$2,\"\",IF(Tool!I233<>\"\",IF(AND($D$2>=(Tool!I233-Tool!$H$228),(Tool!E234-Tool!$H$228)>=(Tool!I233-Tool!H232)),IF(Tool!$H$228<>\"\",Tool!I233-Tool!$H$228,Tool!I233),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B69=\"\",\"\",IF(C69<>\"\",IF(Tool!J233=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E69=\"Com/Ind\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E69=\"Com/Ind\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Macon","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[null,{"$f":"IF(AND(C61>=7,C61<=20),7,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B14<>\"\",IF(D13>=$D$2,\"\",IF($D$2<(Tool!I233-Tool!$H$228),\"\",IF(Tool!D234<>\"\",IF(Tool!$H$228<>0,Tool!I233-Tool!$H$228,Tool!I233),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C14=\"\",\"\",IF(B70=\"\",$D$2,IF((D13-$C$8)>=$D$2,\"\",IF(Tool!E234<>\"\",IF(AND($D$2>=(Tool!E234-Tool!$H$228),(Tool!E235-Tool!$H$228)>=(Tool!E234-Tool!H233)),IF(Tool!$H$228<>\"\",Tool!E234-Tool!$H$228,Tool!E234),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B70=\"\",\"\",IF(C70<>\"\",IF(Tool!F234=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E70=\"Com/Ind\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E70=\"Com/Ind\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Madison","Madison",{"$f":"Q19","v":180000},{"$f":"R19","v":10000},{"$f":"S19","v":375000}]
[null,{"$f":"IF(AND(C61>=8,C61<=20),8,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B15<>\"\",IF(D14>=$D$2,\"\",IF($D$2<(Tool!E234-Tool!$H$228),\"\",IF(Tool!D235<>\"\",IF(Tool!$H$228<>0,Tool!E234-Tool!$H$228,Tool!E234),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C15=\"\",\"\",IF(B71=\"\",$D$2,IF((D14-$C$8)>=$D$2,\"\",IF(Tool!E235<>\"\",IF(AND($D$2>=(Tool!E235-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!E235-Tool!D234)),IF(Tool!$H$228<>\"\",Tool!E235-Tool!$H$228,Tool!E235),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B71=\"\",\"\",IF(C71<>\"\",IF(Tool!F235=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E71=\"Com/Ind\",Tool!G235>=0),Tool!G235,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E71=\"Com/Ind\",IF(Tool!G235>Tool!H235,Tool!G235,IF(Tool!G235>=0,Tool!H235)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Marion ","Hamilton",{"$f":"Q24","v":213000},{"$f":"R24","v":11000},{"$f":"S24","v":287380.95238095243}]
[null,{"$f":"IF(AND(C61>=9,C61<=20),9,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B16<>\"\",IF(D15>=$D$2,\"\",IF($D$2<(Tool!E235-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!E235-Tool!$H$228,Tool!E235),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C16=\"\",\"\",IF(B72=\"\",$D$2,IF((D15-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!D235)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B72=\"\",\"\",IF(C72<>\"\",IF(Tool!#REF!=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E72=\"Com/Ind\",Tool!G237>=0),Tool!G237,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E72=\"Com/Ind\",IF(Tool!G237>Tool!H237,Tool!G237,IF(Tool!G237>=0,Tool!H237)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Marshall","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[null,{"$f":"IF(AND(C61>=10,C61<=20),10,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B17<>\"\",IF(D16>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C17=\"\",\"\",IF(B73=\"\",$D$2,IF((D16-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B73=\"\",\"\",IF(C73<>\"\",IF(Tool!#REF!=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E73=\"Com/Ind\",Tool!G238>=0),Tool!G238,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E73=\"Com/Ind\",IF(Tool!G238>Tool!H238,Tool!G238,IF(Tool!G238>=0,Tool!H238)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Maury","Montgomery",{"$f":"Q17","v":185000},14000,700357.14285714284]
[null,{"$f":"IF(AND(C61>=11,C61<=20),11,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B18<>\"\",IF(D17>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C18=\"\",\"\",IF(B74=\"\",$D$2,IF((D17-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B74=\"\",\"\",IF(C74<>\"\",IF(Tool!#REF!=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E74=\"Com/Ind\",Tool!G239>=0),Tool!G239,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E74=\"Com/Ind\",IF(Tool!G239>Tool!H239,Tool!G239,IF(Tool!G239>=0,Tool!H239)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"McMinn ","Bradley",180000,6500,330000]
[null,{"$f":"IF(AND(C61>=12,C61<=20),12,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B19<>\"\",IF(D18>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C19=\"\",\"\",IF(B75=\"\",$D$2,IF((D18-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B75=\"\",\"\",IF(C75<>\"\",IF(Tool!#REF!=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E75=\"Com/Ind\",Tool!G240>=0),Tool!G240,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E75=\"Com/Ind\",IF(Tool!G240>Tool!H240,Tool!G240,IF(Tool!G240>=0,Tool!H240)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"McNairy","Madison",180000,10000,375000]
[null,{"$f":"IF(AND(C61>=13,C61<=20),13,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B20<>\"\",IF(D19>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C20=\"\",\"\",IF(B76=\"\",$D$2,IF((D19-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B76=\"\",\"\",IF(C76<>\"\",IF(Tool!#REF!=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E76=\"Com/Ind\",Tool!G241>=0),Tool!G241,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E76=\"Com/Ind\",IF(Tool!G241>Tool!H241,Tool!G241,IF(Tool!G241>=0,Tool!H241)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Meigs","Bradley",{"$f":"Q18","v":180000},{"$f":"R18","v":6500},{"$f":"S18","v":330000}]
[null,{"$f":"IF(AND(C61>=14,C61<=20),14,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B21<>\"\",IF(D20>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C21=\"\",\"\",IF(B77=\"\",$D$2,IF((D20-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B77=\"\",\"\",IF(C77<>\"\",IF(Tool!#REF!=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E77=\"Com/Ind\",Tool!G242>=0),Tool!G242,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E77=\"Com/Ind\",IF(Tool!G242>Tool!H242,Tool!G242,IF(Tool!G242>=0,Tool!H242)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Monroe ","Bradley",{"$f":"Q18","v":180000},{"$f":"R18","v":6500},{"$f":"S18","v":330000}]
[null,{"$f":"IF(AND(C61>=15,C61<=20),15,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B22<>\"\",IF(D21>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C22=\"\",\"\",IF(B78=\"\",$D$2,IF((D21-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!E243-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B78=\"\",\"\",IF(C78<>\"\",IF(Tool!#REF!=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E78=\"Com/Ind\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E78=\"Com/Ind\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Montgomery","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[null,{"$f":"IF(AND(C61>=16,C61<=20),16,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B23<>\"\",IF(D22>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!D243<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C23=\"\",\"\",IF(B79=\"\",$D$2,IF((D22-$C$8)>=$D$2,\"\",IF(Tool!E243<>\"\",IF(AND($D$2>=(Tool!E243-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!E243-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!E243-Tool!$H$228,Tool!E243),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B79=\"\",\"\",IF(C79<>\"\",IF(Tool!F243=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E79=\"Com/Ind\",Tool!G243>=0),Tool!G243,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E79=\"Com/Ind\",IF(Tool!G243>Tool!H243,Tool!G243,IF(Tool!G243>=0,Tool!H243)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Moore","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[null,{"$f":"IF(AND(C61>=17,C61<=20),17,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B24<>\"\",IF(D23>=$D$2,\"\",IF($D$2<(Tool!E243-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!E243-Tool!$H$228,Tool!E243),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C24=\"\",\"\",IF(B80=\"\",$D$2,IF((D23-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!D243)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B80=\"\",\"\",IF(C80<>\"\",IF(Tool!#REF!=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E80=\"Com/Ind\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E80=\"Com/Ind\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Morgan ","Knox",{"$f":"Q22","v":315000},{"$f":"R22","v":59000},{"$f":"S22","v":372272.72727272729}]
[null,{"$f":"IF(AND(C61>=18,C61<=20),18,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B25<>\"\",IF(D24>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C25=\"\",\"\",IF(B81=\"\",$D$2,IF((D24-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B81=\"\",\"\",IF(C81<>\"\",IF(Tool!#REF!=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E81=\"Com/Ind\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E81=\"Com/Ind\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Obion","Madison",{"$f":"Q19","v":180000},{"$f":"R19","v":10000},{"$f":"S19","v":375000}]
[null,{"$f":"IF(AND(C61>=19,C61<=20),19,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B26<>\"\",IF(D25>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C26=\"\",\"\",IF(B82=\"\",$D$2,IF((D25-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B82=\"\",\"\",IF(C82<>\"\",IF(Tool!#REF!=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E82=\"Com/Ind\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E82=\"Com/Ind\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Overton ","Bradley",{"$f":"Q18","v":180000},{"$f":"R18","v":6500},{"$f":"S18","v":330000}]
[null,{"$f":"IF(AND(C61=20),20,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(B27<>\"\",IF(D26>=$D$2,\"\",IF($D$2<(Tool!#REF!-Tool!$H$228),\"\",IF(Tool!#REF!<>\"\",IF(Tool!$H$228<>0,Tool!#REF!-Tool!$H$228,Tool!#REF!),\"\"))),\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C27=\"\",\"\",IF(B83=\"\",$D$2,IF((D26-$C$8)>=$D$2,\"\",IF(Tool!#REF!<>\"\",IF(AND($D$2>=(Tool!#REF!-Tool!$H$228),(Tool!#REF!-Tool!$H$228)>=(Tool!#REF!-Tool!#REF!)),IF(Tool!$H$228<>\"\",Tool!#REF!-Tool!$H$228,Tool!#REF!),$D$2),\"\"))))","v":{"$error":"#REF!"}},{"$f":"IF(B83=\"\",\"\",IF(C83<>\"\",IF(Tool!#REF!=Tool!$I$9,\"Com/Ind\",\"\"),\"\"))","v":{"$error":"#REF!"}},{"$f":"IF(AND(E83=\"Com/Ind\",Tool!#REF!>=0),Tool!#REF!,\"\")","v":{"$error":"#REF!"}},{"$f":"IF(E83=\"Com/Ind\",IF(Tool!#REF!>Tool!#REF!,Tool!#REF!,IF(Tool!#REF!>=0,Tool!#REF!)),\"\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},null,"Perry","Montgomery",{"$f":"Q17","v":185000},14000,700357.14285714284]
[null,null,null,null,null,null,null,null,null,"Pickett","Bradley",180000,6500,330000]
[null,null,null,null,"Average Existing Width:",{"$f":"IF(SUM(H64:H83)>0,SUMPRODUCT(F64:F83,H64:H83)/SUM(H64:H83),0)","v":{"$error":"#REF!"}},null,null,null,"Polk ","Bradley",{"$f":"Q18","v":180000},{"$f":"R18","v":6500},{"$f":"S18","v":330000}]
[null,null,null,null,"Average Proposed Width:",{"$f":"IF(SUM(H64:H83)>0,SUMPRODUCT(G64:G83,H64:H83)/SUM(H64:H83),0)","v":{"$error":"#REF!"}},null,null,null,"Putnam","Bradley",{"$f":"Q18","v":180000},{"$f":"R18","v":6500},{"$f":"S18","v":330000}]
[null,null,null,null,"Length:",{"$f":"SUM(H64:H83)","v":{"$error":"#REF!"}},null,null,null,"Rhea ","Bradley",{"$f":"Q18","v":180000},{"$f":"R18","v":6500},{"$f":"S18","v":330000}]
[null,null,null,null,null,null,null,null,null,"Roane ","Knox",{"$f":"Q22","v":315000},{"$f":"R22","v":59000},{"$f":"S22","v":372272.72727272729}]
[null,null,null,null,null,null,null,null,null,"Robertson ","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[null,null,null,null,null,null,null,null,null,"Rutherford ","Rutherford",{"$f":"Q26","v":223000},{"$f":"R26","v":26000},{"$f":"S26","v":687328.76712328766}]
[null,null,null,null,null,null,null,null,null,"Scott ","Washington",{"$f":"Q20","v":195000},{"$f":"R20","v":18000},{"$f":"S20","v":281666.66666666669}]
[null,null,null,null,null,null,null,null,null,"Sequatchie","Hamilton",{"$f":"Q24","v":213000},{"$f":"R24","v":11000},{"$f":"S24","v":287380.95238095243}]
[null,null,null,null,null,null,null,null,null,"Sevier ","Knox",{"$f":"Q22","v":315000},59000,372272.72727272729]
[null,null,null,null,null,null,null,null,null,"Shelby ","Shelby",275000,32500,236500]
[null,null,null,null,null,null,null,null,null,"Smith","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[null,null,null,null,null,null,null,null,null,"Stewart","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[null,null,null,null,null,null,null,null,null,"Sullivan ","Sullivan",{"$f":"Q21","v":205000},{"$f":"R21","v":16500},{"$f":"S21","v":205000}]
[null,null,null,null,null,null,null,null,null,"Sumner ","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[null,null,null,null,null,null,null,null,null,"Tipton","Shelby",{"$f":"Q23","v":275000},{"$f":"R23","v":32500},{"$f":"S23","v":236500}]
[null,null,null,null,null,null,null,null,null,"Trousdale","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[null,null,null,null,null,null,null,null,null,"Unicoi","Washington",{"$f":"Q20","v":195000},{"$f":"R20","v":18000},{"$f":"S20","v":281666.66666666669}]
[null,null,null,null,null,null,null,null,null,"Union ","Knox",{"$f":"Q22","v":315000},{"$f":"R22","v":59000},{"$f":"S22","v":372272.72727272729}]
[null,null,null,null,null,null,null,null,null,"Van Buren ","Bradley",{"$f":"Q18","v":180000},{"$f":"R18","v":6500},{"$f":"S18","v":330000}]
[null,null,null,null,null,null,null,null,null,"Warren","Bradley",{"$f":"Q18","v":180000},{"$f":"R18","v":6500},{"$f":"S18","v":330000}]
[null,null,null,null,null,null,null,null,null,"Washington","Washington",{"$f":"Q20","v":195000},{"$f":"R20","v":18000},{"$f":"S20","v":281666.66666666669}]
[null,null,null,null,null,null,null,null,null,"Wayne","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[null,null,null,null,null,null,null,null,null,"Weakley","Madison",{"$f":"Q19","v":180000},{"$f":"R19","v":10000},{"$f":"S19","v":375000}]
[null,null,null,null,null,null,null,null,null,"White ","Bradley",{"$f":"Q18","v":180000},{"$f":"R18","v":6500},{"$f":"S18","v":330000}]
[null,null,null,null,null,null,null,null,null,"Williamson ","Williamson",{"$f":"Q27","v":275000},{"$f":"R27","v":25000},{"$f":"S27","v":577500}]
[null,null,null,null,null,null,null,null,null,"Wilson ","Montgomery",{"$f":"Q17","v":185000},{"$f":"R17","v":14000},{"$f":"S17","v":700357.14285714284}]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Right-of-Way"]

{"sheet":"AUP Library","index":9,"n_rows":1129,"n_cols":22,"rows_kept":1129,"cut":false,"hidden":true,"merged":[[1108,1,1108,2],[1089,1,1089,2]]}
["TDOT PAY ITEM","TDOT DESCRIPTION","UNIT",2005,2006,2007,2008,2009,2010,2011,2012,2013,2014,"Region 1 - 2016","Region 2 - 2016","Region 3 - 2016","Region 4 - 2016","Statewide - 2016","Statewide 3-Year","Statistical"]
[]
["Pavment Removal",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"TN - 2005",4]
["202-03.01","Removal of Asphalt Pavement","SY",2.71,1.52,3.88,2.56,2.56,3.86,9.48,6.81,4.22,10.56,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A4,'Updated Quanities'!F:I,4,0),R4)=\"\",R4,IFERROR(VLOOKUP('AUP Library'!A4,'Updated Quanities'!F:I,4,0),R4))","v":15.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A4,'Updated Quanities'!F:I,5,0),R4)=\"\",R4,IFERROR(VLOOKUP('AUP Library'!A4,'Updated Quanities'!F:I,5,0),R4))","v":15.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A4,'Updated Quanities'!F:I,6,0),R4)=\"\",R4,IFERROR(VLOOKUP('AUP Library'!A4,'Updated Quanities'!F:I,6,0),R4))","v":15.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A4,'Updated Quanities'!F:I,7,0),R4)=\"\",R4,IFERROR(VLOOKUP('AUP Library'!A4,'Updated Quanities'!F:I,7,0),R4))","v":15.32},15.32,{"$f":"IFERROR(VLOOKUP('AUP Library'!A4,'Updated Quanities'!F:G,4,0),R4)","v":15.32},null,"TN -2006",5]
["202-03.02","Removal of Rigid Pavement","CY",18.760000000000002,175,17.149999999999999,48.17,48.17,11.31,12,28.08,12.36,39.64,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A5,'Updated Quanities'!F:I,4,0),R5)=\"\",R5,IFERROR(VLOOKUP('AUP Library'!A5,'Updated Quanities'!F:I,4,0),R5))","v":14.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A5,'Updated Quanities'!F:I,5,0),R5)=\"\",R5,IFERROR(VLOOKUP('AUP Library'!A5,'Updated Quanities'!F:I,5,0),R5))","v":14.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A5,'Updated Quanities'!F:I,6,0),R5)=\"\",R5,IFERROR(VLOOKUP('AUP Library'!A5,'Updated Quanities'!F:I,6,0),R5))","v":14.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A5,'Updated Quanities'!F:I,7,0),R5)=\"\",R5,IFERROR(VLOOKUP('AUP Library'!A5,'Updated Quanities'!F:I,7,0),R5))","v":14.81},14.81,{"$f":"IFERROR(VLOOKUP('AUP Library'!A5,'Updated Quanities'!F:G,4,0),R5)","v":14.81},null,"TN - 2007",6]
["202-08.15","Removal of Curb and Gutter","LF",3.38,3.38,3.38,3.38,3.38,3.38,3.38,3.38,3.38,3.38,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A6,'Updated Quanities'!F:I,4,0),R6)=\"\",R6,IFERROR(VLOOKUP('AUP Library'!A6,'Updated Quanities'!F:I,4,0),R6))","v":3.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A6,'Updated Quanities'!F:I,5,0),R6)=\"\",R6,IFERROR(VLOOKUP('AUP Library'!A6,'Updated Quanities'!F:I,5,0),R6))","v":3.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A6,'Updated Quanities'!F:I,6,0),R6)=\"\",R6,IFERROR(VLOOKUP('AUP Library'!A6,'Updated Quanities'!F:I,6,0),R6))","v":3.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A6,'Updated Quanities'!F:I,7,0),R6)=\"\",R6,IFERROR(VLOOKUP('AUP Library'!A6,'Updated Quanities'!F:I,7,0),R6))","v":3.38},3.38,{"$f":"IFERROR(VLOOKUP('AUP Library'!A6,'Updated Quanities'!F:G,4,0),R6)","v":3.38},null,"TN - 2008",7]
["202-08.28","Removal of Median Barrier","LF",85,85,85,85,85,85,85,85,85,85,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A7,'Updated Quanities'!F:I,4,0),R7)=\"\",R7,IFERROR(VLOOKUP('AUP Library'!A7,'Updated Quanities'!F:I,4,0),R7))","v":85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A7,'Updated Quanities'!F:I,5,0),R7)=\"\",R7,IFERROR(VLOOKUP('AUP Library'!A7,'Updated Quanities'!F:I,5,0),R7))","v":85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A7,'Updated Quanities'!F:I,6,0),R7)=\"\",R7,IFERROR(VLOOKUP('AUP Library'!A7,'Updated Quanities'!F:I,6,0),R7))","v":85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A7,'Updated Quanities'!F:I,7,0),R7)=\"\",R7,IFERROR(VLOOKUP('AUP Library'!A7,'Updated Quanities'!F:I,7,0),R7))","v":85},85,{"$f":"IFERROR(VLOOKUP('AUP Library'!A7,'Updated Quanities'!F:G,4,0),R7)","v":85},null,"TN - 2009",8]
["411-12.01","Scoring Shoulders (Cont. 16\")","L.M.",526.25,526.25,526.25,526.25,526.25,526.25,526.25,526.25,526.25,526.25,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A8,'Updated Quanities'!F:I,4,0),R8)=\"\",R8,IFERROR(VLOOKUP('AUP Library'!A8,'Updated Quanities'!F:I,4,0),R8))","v":526.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A8,'Updated Quanities'!F:I,5,0),R8)=\"\",R8,IFERROR(VLOOKUP('AUP Library'!A8,'Updated Quanities'!F:I,5,0),R8))","v":526.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A8,'Updated Quanities'!F:I,6,0),R8)=\"\",R8,IFERROR(VLOOKUP('AUP Library'!A8,'Updated Quanities'!F:I,6,0),R8))","v":526.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A8,'Updated Quanities'!F:I,7,0),R8)=\"\",R8,IFERROR(VLOOKUP('AUP Library'!A8,'Updated Quanities'!F:I,7,0),R8))","v":526.25},526.25,{"$f":"IFERROR(VLOOKUP('AUP Library'!A8,'Updated Quanities'!F:G,4,0),R8)","v":526.25},null,"TN - 2010",9]
["411-12.02","Scoring Shoulders (Non- Cont. 16\")","L.M.",848.51,848.51,848.51,848.51,848.51,848.51,848.51,848.51,848.51,848.51,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A9,'Updated Quanities'!F:I,4,0),R9)=\"\",R9,IFERROR(VLOOKUP('AUP Library'!A9,'Updated Quanities'!F:I,4,0),R9))","v":848.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A9,'Updated Quanities'!F:I,5,0),R9)=\"\",R9,IFERROR(VLOOKUP('AUP Library'!A9,'Updated Quanities'!F:I,5,0),R9))","v":848.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A9,'Updated Quanities'!F:I,6,0),R9)=\"\",R9,IFERROR(VLOOKUP('AUP Library'!A9,'Updated Quanities'!F:I,6,0),R9))","v":848.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A9,'Updated Quanities'!F:I,7,0),R9)=\"\",R9,IFERROR(VLOOKUP('AUP Library'!A9,'Updated Quanities'!F:I,7,0),R9))","v":848.51},848.51,{"$f":"IFERROR(VLOOKUP('AUP Library'!A9,'Updated Quanities'!F:G,4,0),R9)","v":848.51},null,"TN - 2011",10]
["411-12.03","Scoring Shoulder (Non-Cont. 8\")","L.M.",594.86,594.86,594.86,594.86,594.86,594.86,594.86,594.86,594.86,594.86,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A10,'Updated Quanities'!F:I,4,0),R10)=\"\",R10,IFERROR(VLOOKUP('AUP Library'!A10,'Updated Quanities'!F:I,4,0),R10))","v":594.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A10,'Updated Quanities'!F:I,5,0),R10)=\"\",R10,IFERROR(VLOOKUP('AUP Library'!A10,'Updated Quanities'!F:I,5,0),R10))","v":594.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A10,'Updated Quanities'!F:I,6,0),R10)=\"\",R10,IFERROR(VLOOKUP('AUP Library'!A10,'Updated Quanities'!F:I,6,0),R10))","v":594.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A10,'Updated Quanities'!F:I,7,0),R10)=\"\",R10,IFERROR(VLOOKUP('AUP Library'!A10,'Updated Quanities'!F:I,7,0),R10))","v":594.86},594.86,{"$f":"IFERROR(VLOOKUP('AUP Library'!A10,'Updated Quanities'!F:G,4,0),R10)","v":594.86},null,"TN - 2012",11]
["411-12.04","Scoring Shoulder (Non-Cont. 4\")","L.M.",580.49,580.49,580.49,580.49,580.49,580.49,580.49,580.49,580.49,580.49,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A11,'Updated Quanities'!F:I,4,0),R11)=\"\",R11,IFERROR(VLOOKUP('AUP Library'!A11,'Updated Quanities'!F:I,4,0),R11))","v":580.49},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A11,'Updated Quanities'!F:I,5,0),R11)=\"\",R11,IFERROR(VLOOKUP('AUP Library'!A11,'Updated Quanities'!F:I,5,0),R11))","v":580.49},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A11,'Updated Quanities'!F:I,6,0),R11)=\"\",R11,IFERROR(VLOOKUP('AUP Library'!A11,'Updated Quanities'!F:I,6,0),R11))","v":580.49},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A11,'Updated Quanities'!F:I,7,0),R11)=\"\",R11,IFERROR(VLOOKUP('AUP Library'!A11,'Updated Quanities'!F:I,7,0),R11))","v":580.49},580.49,{"$f":"IFERROR(VLOOKUP('AUP Library'!A11,'Updated Quanities'!F:G,4,0),R11)","v":580.49},null,"TN - 2013",12]
["411-12.05","Scoring For Centerline Rumble (4\" Width)","L.M.",563.51,563.51,563.51,563.51,563.51,563.51,563.51,563.51,563.51,563.51,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A12,'Updated Quanities'!F:I,4,0),R12)=\"\",R12,IFERROR(VLOOKUP('AUP Library'!A12,'Updated Quanities'!F:I,4,0),R12))","v":563.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A12,'Updated Quanities'!F:I,5,0),R12)=\"\",R12,IFERROR(VLOOKUP('AUP Library'!A12,'Updated Quanities'!F:I,5,0),R12))","v":563.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A12,'Updated Quanities'!F:I,6,0),R12)=\"\",R12,IFERROR(VLOOKUP('AUP Library'!A12,'Updated Quanities'!F:I,6,0),R12))","v":563.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A12,'Updated Quanities'!F:I,7,0),R12)=\"\",R12,IFERROR(VLOOKUP('AUP Library'!A12,'Updated Quanities'!F:I,7,0),R12))","v":563.51},563.51,{"$f":"IFERROR(VLOOKUP('AUP Library'!A12,'Updated Quanities'!F:G,4,0),R12)","v":563.51},null,"TN - 2014",13]
["415-01.02","Cold Planning Bituminous Pavement","SY",1.26,1.67,1.25,1.25,1.25,1.03,0.95,0.93,1.3,1.47,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A13,'Updated Quanities'!F:I,4,0),R13)=\"\",R13,IFERROR(VLOOKUP('AUP Library'!A13,'Updated Quanities'!F:I,4,0),R13))","v":1.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A13,'Updated Quanities'!F:I,5,0),R13)=\"\",R13,IFERROR(VLOOKUP('AUP Library'!A13,'Updated Quanities'!F:I,5,0),R13))","v":1.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A13,'Updated Quanities'!F:I,6,0),R13)=\"\",R13,IFERROR(VLOOKUP('AUP Library'!A13,'Updated Quanities'!F:I,6,0),R13))","v":1.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A13,'Updated Quanities'!F:I,7,0),R13)=\"\",R13,IFERROR(VLOOKUP('AUP Library'!A13,'Updated Quanities'!F:I,7,0),R13))","v":1.74},1.74,{"$f":"IFERROR(VLOOKUP('AUP Library'!A13,'Updated Quanities'!F:G,4,0),R13)","v":1.74},null,"Statewide - 2016",18]
["415-01.03","Cold Planning Bituminous Pavement","CY",59.06,59.06,59.06,59.06,59.06,59.06,59.06,59.06,59.06,59.06,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A14,'Updated Quanities'!F:I,4,0),R14)=\"\",R14,IFERROR(VLOOKUP('AUP Library'!A14,'Updated Quanities'!F:I,4,0),R14))","v":59.06},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A14,'Updated Quanities'!F:I,5,0),R14)=\"\",R14,IFERROR(VLOOKUP('AUP Library'!A14,'Updated Quanities'!F:I,5,0),R14))","v":59.06},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A14,'Updated Quanities'!F:I,6,0),R14)=\"\",R14,IFERROR(VLOOKUP('AUP Library'!A14,'Updated Quanities'!F:I,6,0),R14))","v":59.06},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A14,'Updated Quanities'!F:I,7,0),R14)=\"\",R14,IFERROR(VLOOKUP('AUP Library'!A14,'Updated Quanities'!F:I,7,0),R14))","v":59.06},59.06,{"$f":"IFERROR(VLOOKUP('AUP Library'!A14,'Updated Quanities'!F:G,4,0),R14)","v":59.06},null,"Region 1",14]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Region 2",15]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Region 3",16]
["Asphalt Roads",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Region 4",17]
["203-06","Water","MG",10.27,10.27,10.27,10.27,10.27,10.27,10.27,10.27,10.27,10.27,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A18,'Updated Quanities'!F:I,4,0),R18)=\"\",R18,IFERROR(VLOOKUP('AUP Library'!A18,'Updated Quanities'!F:I,4,0),R18))","v":10.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A18,'Updated Quanities'!F:I,5,0),R18)=\"\",R18,IFERROR(VLOOKUP('AUP Library'!A18,'Updated Quanities'!F:I,5,0),R18))","v":10.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A18,'Updated Quanities'!F:I,6,0),R18)=\"\",R18,IFERROR(VLOOKUP('AUP Library'!A18,'Updated Quanities'!F:I,6,0),R18))","v":10.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A18,'Updated Quanities'!F:I,7,0),R18)=\"\",R18,IFERROR(VLOOKUP('AUP Library'!A18,'Updated Quanities'!F:I,7,0),R18))","v":10.27},10.27,{"$f":"IFERROR(VLOOKUP('AUP Library'!A18,'Updated Quanities'!F:G,4,0),R18)","v":10.27},null,"Statewide",19]
["303-01","Mineral Aggregate, Type A Base, Grading D","TON",13.09,14.11,14.18,15.33,15.33,14.93,16.13,18.079999999999998,15.56,19,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A19,'Updated Quanities'!F:I,4,0),R19)=\"\",R19,IFERROR(VLOOKUP('AUP Library'!A19,'Updated Quanities'!F:I,4,0),R19))","v":21.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A19,'Updated Quanities'!F:I,5,0),R19)=\"\",R19,IFERROR(VLOOKUP('AUP Library'!A19,'Updated Quanities'!F:I,5,0),R19))","v":21.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A19,'Updated Quanities'!F:I,6,0),R19)=\"\",R19,IFERROR(VLOOKUP('AUP Library'!A19,'Updated Quanities'!F:I,6,0),R19))","v":21.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A19,'Updated Quanities'!F:I,7,0),R19)=\"\",R19,IFERROR(VLOOKUP('AUP Library'!A19,'Updated Quanities'!F:I,7,0),R19))","v":21.76},21.76,{"$f":"IFERROR(VLOOKUP('AUP Library'!A19,'Updated Quanities'!F:G,4,0),R19)","v":21.76}]
["307-01.01","Asphalt Concrete Mix (PG64-22) (BPMB-HM) Grading A","TON",78.760000000000005,78.760000000000005,78.760000000000005,78.760000000000005,78.760000000000005,78.760000000000005,78.760000000000005,78.760000000000005,78.760000000000005,78.760000000000005,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A20,'Updated Quanities'!F:I,4,0),R20)=\"\",R20,IFERROR(VLOOKUP('AUP Library'!A20,'Updated Quanities'!F:I,4,0),R20))","v":78.760000000000005},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A20,'Updated Quanities'!F:I,5,0),R20)=\"\",R20,IFERROR(VLOOKUP('AUP Library'!A20,'Updated Quanities'!F:I,5,0),R20))","v":78.760000000000005},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A20,'Updated Quanities'!F:I,6,0),R20)=\"\",R20,IFERROR(VLOOKUP('AUP Library'!A20,'Updated Quanities'!F:I,6,0),R20))","v":78.760000000000005},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A20,'Updated Quanities'!F:I,7,0),R20)=\"\",R20,IFERROR(VLOOKUP('AUP Library'!A20,'Updated Quanities'!F:I,7,0),R20))","v":78.760000000000005},78.760000000000005,{"$f":"IFERROR(VLOOKUP('AUP Library'!A20,'Updated Quanities'!F:G,4,0),R20)","v":78.760000000000005}]
["307-01.02","Asphalt Cem. (PG64-22)(BPMB-HM) GR. A-S","TON",750.3,750.3,750.3,750.3,750.3,750.3,750.3,750.3,750.3,750.3,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A21,'Updated Quanities'!F:I,4,0),R21)=\"\",R21,IFERROR(VLOOKUP('AUP Library'!A21,'Updated Quanities'!F:I,4,0),R21))","v":750.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A21,'Updated Quanities'!F:I,5,0),R21)=\"\",R21,IFERROR(VLOOKUP('AUP Library'!A21,'Updated Quanities'!F:I,5,0),R21))","v":750.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A21,'Updated Quanities'!F:I,6,0),R21)=\"\",R21,IFERROR(VLOOKUP('AUP Library'!A21,'Updated Quanities'!F:I,6,0),R21))","v":750.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A21,'Updated Quanities'!F:I,7,0),R21)=\"\",R21,IFERROR(VLOOKUP('AUP Library'!A21,'Updated Quanities'!F:I,7,0),R21))","v":750.3},750.3,{"$f":"IFERROR(VLOOKUP('AUP Library'!A21,'Updated Quanities'!F:G,4,0),R21)","v":750.3}]
["307-01.03","Aggregate (BPMB-HM) Grading A-S Mix","TON",54.15,54.15,54.15,54.15,54.15,54.15,54.15,54.15,54.15,54.15,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A22,'Updated Quanities'!F:I,4,0),R22)=\"\",R22,IFERROR(VLOOKUP('AUP Library'!A22,'Updated Quanities'!F:I,4,0),R22))","v":54.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A22,'Updated Quanities'!F:I,5,0),R22)=\"\",R22,IFERROR(VLOOKUP('AUP Library'!A22,'Updated Quanities'!F:I,5,0),R22))","v":54.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A22,'Updated Quanities'!F:I,6,0),R22)=\"\",R22,IFERROR(VLOOKUP('AUP Library'!A22,'Updated Quanities'!F:I,6,0),R22))","v":54.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A22,'Updated Quanities'!F:I,7,0),R22)=\"\",R22,IFERROR(VLOOKUP('AUP Library'!A22,'Updated Quanities'!F:I,7,0),R22))","v":54.15},54.15,{"$f":"IFERROR(VLOOKUP('AUP Library'!A22,'Updated Quanities'!F:G,4,0),R22)","v":54.15}]
["307-01.07","Asphalt Conc Mix (PG64-22) (BPMB-HM) GR B-M","TON",85.88,85.88,85.88,85.88,85.88,85.88,85.88,85.88,85.88,85.88,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A23,'Updated Quanities'!F:I,4,0),R23)=\"\",R23,IFERROR(VLOOKUP('AUP Library'!A23,'Updated Quanities'!F:I,4,0),R23))","v":85.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A23,'Updated Quanities'!F:I,5,0),R23)=\"\",R23,IFERROR(VLOOKUP('AUP Library'!A23,'Updated Quanities'!F:I,5,0),R23))","v":85.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A23,'Updated Quanities'!F:I,6,0),R23)=\"\",R23,IFERROR(VLOOKUP('AUP Library'!A23,'Updated Quanities'!F:I,6,0),R23))","v":85.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A23,'Updated Quanities'!F:I,7,0),R23)=\"\",R23,IFERROR(VLOOKUP('AUP Library'!A23,'Updated Quanities'!F:I,7,0),R23))","v":85.88},85.88,{"$f":"IFERROR(VLOOKUP('AUP Library'!A23,'Updated Quanities'!F:G,4,0),R23)","v":85.88}]
["307-01.08","Asphalt Conc MIX (PG64-22) (BPMB-HM) GR B-M2","TON",81.760000000000005,81.760000000000005,81.760000000000005,81.760000000000005,81.760000000000005,81.760000000000005,81.760000000000005,81.760000000000005,81.760000000000005,81.760000000000005,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A24,'Updated Quanities'!F:I,4,0),R24)=\"\",R24,IFERROR(VLOOKUP('AUP Library'!A24,'Updated Quanities'!F:I,4,0),R24))","v":81.760000000000005},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A24,'Updated Quanities'!F:I,5,0),R24)=\"\",R24,IFERROR(VLOOKUP('AUP Library'!A24,'Updated Quanities'!F:I,5,0),R24))","v":81.760000000000005},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A24,'Updated Quanities'!F:I,6,0),R24)=\"\",R24,IFERROR(VLOOKUP('AUP Library'!A24,'Updated Quanities'!F:I,6,0),R24))","v":81.760000000000005},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A24,'Updated Quanities'!F:I,7,0),R24)=\"\",R24,IFERROR(VLOOKUP('AUP Library'!A24,'Updated Quanities'!F:I,7,0),R24))","v":81.760000000000005},81.760000000000005,{"$f":"IFERROR(VLOOKUP('AUP Library'!A24,'Updated Quanities'!F:G,4,0),R24)","v":81.760000000000005}]
["307-01.10","Asphalt Conc Mix (PG64-22)(BPMB-HM) GR C-W","TON",91,91,91,91,91,91,91,91,91,91,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A25,'Updated Quanities'!F:I,4,0),R25)=\"\",R25,IFERROR(VLOOKUP('AUP Library'!A25,'Updated Quanities'!F:I,4,0),R25))","v":91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A25,'Updated Quanities'!F:I,5,0),R25)=\"\",R25,IFERROR(VLOOKUP('AUP Library'!A25,'Updated Quanities'!F:I,5,0),R25))","v":91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A25,'Updated Quanities'!F:I,6,0),R25)=\"\",R25,IFERROR(VLOOKUP('AUP Library'!A25,'Updated Quanities'!F:I,6,0),R25))","v":91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A25,'Updated Quanities'!F:I,7,0),R25)=\"\",R25,IFERROR(VLOOKUP('AUP Library'!A25,'Updated Quanities'!F:I,7,0),R25))","v":91},91,{"$f":"IFERROR(VLOOKUP('AUP Library'!A25,'Updated Quanities'!F:G,4,0),R25)","v":91}]
["307-01.15","ASC Mix (PG64-22)(BPMLC-HM) GR.CS","TON",98.66,98.66,98.66,98.66,98.66,98.66,98.66,98.66,98.66,98.66,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A26,'Updated Quanities'!F:I,4,0),R26)=\"\",R26,IFERROR(VLOOKUP('AUP Library'!A26,'Updated Quanities'!F:I,4,0),R26))","v":98.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A26,'Updated Quanities'!F:I,5,0),R26)=\"\",R26,IFERROR(VLOOKUP('AUP Library'!A26,'Updated Quanities'!F:I,5,0),R26))","v":98.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A26,'Updated Quanities'!F:I,6,0),R26)=\"\",R26,IFERROR(VLOOKUP('AUP Library'!A26,'Updated Quanities'!F:I,6,0),R26))","v":98.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A26,'Updated Quanities'!F:I,7,0),R26)=\"\",R26,IFERROR(VLOOKUP('AUP Library'!A26,'Updated Quanities'!F:I,7,0),R26))","v":98.66},98.66,{"$f":"IFERROR(VLOOKUP('AUP Library'!A26,'Updated Quanities'!F:G,4,0),R26)","v":98.66}]
["307-02.01","Asphalt Concrete Mix (PG70-22) (BPMB-HM) Grading A","TON",40.08,52.88,55.79,69.150000000000006,69.150000000000006,66.760000000000005,77.459999999999994,72.81,59.92,78.760000000000005,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A27,'Updated Quanities'!F:I,4,0),R27)=\"\",R27,IFERROR(VLOOKUP('AUP Library'!A27,'Updated Quanities'!F:I,4,0),R27))","v":65.48},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A27,'Updated Quanities'!F:I,5,0),R27)=\"\",R27,IFERROR(VLOOKUP('AUP Library'!A27,'Updated Quanities'!F:I,5,0),R27))","v":65.48},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A27,'Updated Quanities'!F:I,6,0),R27)=\"\",R27,IFERROR(VLOOKUP('AUP Library'!A27,'Updated Quanities'!F:I,6,0),R27))","v":65.48},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A27,'Updated Quanities'!F:I,7,0),R27)=\"\",R27,IFERROR(VLOOKUP('AUP Library'!A27,'Updated Quanities'!F:I,7,0),R27))","v":65.48},65.48,{"$f":"IFERROR(VLOOKUP('AUP Library'!A27,'Updated Quanities'!F:G,4,0),R27)","v":65.48}]
["307-02.02","Asphalt Cement (PG70-22)(BPMB-HM) Grading A-S","TON",330.41,462.54,492.3,763.2,763.2,688.28,849.06,888.11,526.78,842.76,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A28,'Updated Quanities'!F:I,4,0),R28)=\"\",R28,IFERROR(VLOOKUP('AUP Library'!A28,'Updated Quanities'!F:I,4,0),R28))","v":769.56},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A28,'Updated Quanities'!F:I,5,0),R28)=\"\",R28,IFERROR(VLOOKUP('AUP Library'!A28,'Updated Quanities'!F:I,5,0),R28))","v":769.56},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A28,'Updated Quanities'!F:I,6,0),R28)=\"\",R28,IFERROR(VLOOKUP('AUP Library'!A28,'Updated Quanities'!F:I,6,0),R28))","v":769.56},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A28,'Updated Quanities'!F:I,7,0),R28)=\"\",R28,IFERROR(VLOOKUP('AUP Library'!A28,'Updated Quanities'!F:I,7,0),R28))","v":769.56},769.56,{"$f":"IFERROR(VLOOKUP('AUP Library'!A28,'Updated Quanities'!F:G,4,0),R28)","v":769.56}]
["307-02.03","Aggregate (BPMB-HM) Grading A-S Mix","TON",28.26,34.31,39.880000000000003,37.130000000000003,37.130000000000003,46.54,48.88,42.27,45.77,49.99,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A29,'Updated Quanities'!F:I,4,0),R29)=\"\",R29,IFERROR(VLOOKUP('AUP Library'!A29,'Updated Quanities'!F:I,4,0),R29))","v":49.56},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A29,'Updated Quanities'!F:I,5,0),R29)=\"\",R29,IFERROR(VLOOKUP('AUP Library'!A29,'Updated Quanities'!F:I,5,0),R29))","v":49.56},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A29,'Updated Quanities'!F:I,6,0),R29)=\"\",R29,IFERROR(VLOOKUP('AUP Library'!A29,'Updated Quanities'!F:I,6,0),R29))","v":49.56},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A29,'Updated Quanities'!F:I,7,0),R29)=\"\",R29,IFERROR(VLOOKUP('AUP Library'!A29,'Updated Quanities'!F:I,7,0),R29))","v":49.56},49.56,{"$f":"IFERROR(VLOOKUP('AUP Library'!A29,'Updated Quanities'!F:G,4,0),R29)","v":49.56}]
["307-02.08","Asphalt Concrete Mix (PG70-22) (BPMB-HM) Grading B-M2","TON",39.950000000000003,56.55,57.47,71.94,71.94,69.430000000000007,80.78,77.650000000000006,64.459999999999994,78.989999999999995,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A30,'Updated Quanities'!F:I,4,0),R30)=\"\",R30,IFERROR(VLOOKUP('AUP Library'!A30,'Updated Quanities'!F:I,4,0),R30))","v":87.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A30,'Updated Quanities'!F:I,5,0),R30)=\"\",R30,IFERROR(VLOOKUP('AUP Library'!A30,'Updated Quanities'!F:I,5,0),R30))","v":87.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A30,'Updated Quanities'!F:I,6,0),R30)=\"\",R30,IFERROR(VLOOKUP('AUP Library'!A30,'Updated Quanities'!F:I,6,0),R30))","v":87.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A30,'Updated Quanities'!F:I,7,0),R30)=\"\",R30,IFERROR(VLOOKUP('AUP Library'!A30,'Updated Quanities'!F:I,7,0),R30))","v":87.13},87.13,{"$f":"IFERROR(VLOOKUP('AUP Library'!A30,'Updated Quanities'!F:G,4,0),R30)","v":87.13}]
["307-03.01","Asphalt Conc Mix (PG76-22)(BPMB-HM) GR A","TON",84.24,84.24,84.24,84.24,84.24,84.24,84.24,84.24,84.24,84.24,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A31,'Updated Quanities'!F:I,4,0),R31)=\"\",R31,IFERROR(VLOOKUP('AUP Library'!A31,'Updated Quanities'!F:I,4,0),R31))","v":84.24},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A31,'Updated Quanities'!F:I,5,0),R31)=\"\",R31,IFERROR(VLOOKUP('AUP Library'!A31,'Updated Quanities'!F:I,5,0),R31))","v":84.24},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A31,'Updated Quanities'!F:I,6,0),R31)=\"\",R31,IFERROR(VLOOKUP('AUP Library'!A31,'Updated Quanities'!F:I,6,0),R31))","v":84.24},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A31,'Updated Quanities'!F:I,7,0),R31)=\"\",R31,IFERROR(VLOOKUP('AUP Library'!A31,'Updated Quanities'!F:I,7,0),R31))","v":84.24},84.24,{"$f":"IFERROR(VLOOKUP('AUP Library'!A31,'Updated Quanities'!F:G,4,0),R31)","v":84.24}]
["307-03.02","Perf. Grade Asph. Cement (PG76-22) GR AS","TON",942.31,942.31,942.31,942.31,942.31,942.31,942.31,942.31,942.31,942.31,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A32,'Updated Quanities'!F:I,4,0),R32)=\"\",R32,IFERROR(VLOOKUP('AUP Library'!A32,'Updated Quanities'!F:I,4,0),R32))","v":942.31},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A32,'Updated Quanities'!F:I,5,0),R32)=\"\",R32,IFERROR(VLOOKUP('AUP Library'!A32,'Updated Quanities'!F:I,5,0),R32))","v":942.31},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A32,'Updated Quanities'!F:I,6,0),R32)=\"\",R32,IFERROR(VLOOKUP('AUP Library'!A32,'Updated Quanities'!F:I,6,0),R32))","v":942.31},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A32,'Updated Quanities'!F:I,7,0),R32)=\"\",R32,IFERROR(VLOOKUP('AUP Library'!A32,'Updated Quanities'!F:I,7,0),R32))","v":942.31},942.31,{"$f":"IFERROR(VLOOKUP('AUP Library'!A32,'Updated Quanities'!F:G,4,0),R32)","v":942.31}]
["307-03.03","Aggregate (BPMB-HM) Grading AS","TON",67.48,67.48,67.48,67.48,67.48,67.48,67.48,67.48,67.48,67.48,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A33,'Updated Quanities'!F:I,4,0),R33)=\"\",R33,IFERROR(VLOOKUP('AUP Library'!A33,'Updated Quanities'!F:I,4,0),R33))","v":67.48},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A33,'Updated Quanities'!F:I,5,0),R33)=\"\",R33,IFERROR(VLOOKUP('AUP Library'!A33,'Updated Quanities'!F:I,5,0),R33))","v":67.48},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A33,'Updated Quanities'!F:I,6,0),R33)=\"\",R33,IFERROR(VLOOKUP('AUP Library'!A33,'Updated Quanities'!F:I,6,0),R33))","v":67.48},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A33,'Updated Quanities'!F:I,7,0),R33)=\"\",R33,IFERROR(VLOOKUP('AUP Library'!A33,'Updated Quanities'!F:I,7,0),R33))","v":67.48},67.48,{"$f":"IFERROR(VLOOKUP('AUP Library'!A33,'Updated Quanities'!F:G,4,0),R33)","v":67.48}]
["307-03.08","Asphalt Conc MX (PG76-22)(BPMB-HM) GR B-M2","TON",79.28,79.28,79.28,79.28,79.28,79.28,79.28,79.28,79.28,79.28,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A34,'Updated Quanities'!F:I,4,0),R34)=\"\",R34,IFERROR(VLOOKUP('AUP Library'!A34,'Updated Quanities'!F:I,4,0),R34))","v":79.28},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A34,'Updated Quanities'!F:I,5,0),R34)=\"\",R34,IFERROR(VLOOKUP('AUP Library'!A34,'Updated Quanities'!F:I,5,0),R34))","v":79.28},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A34,'Updated Quanities'!F:I,6,0),R34)=\"\",R34,IFERROR(VLOOKUP('AUP Library'!A34,'Updated Quanities'!F:I,6,0),R34))","v":79.28},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A34,'Updated Quanities'!F:I,7,0),R34)=\"\",R34,IFERROR(VLOOKUP('AUP Library'!A34,'Updated Quanities'!F:I,7,0),R34))","v":79.28},79.28,{"$f":"IFERROR(VLOOKUP('AUP Library'!A34,'Updated Quanities'!F:G,4,0),R34)","v":79.28}]
["307-03.10","Asphalt Conc Mix (PG76-22) (BPMB-HM) GR CS","TON",89.8,89.8,89.8,89.8,89.8,89.8,89.8,89.8,89.8,89.8,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A35,'Updated Quanities'!F:I,4,0),R35)=\"\",R35,IFERROR(VLOOKUP('AUP Library'!A35,'Updated Quanities'!F:I,4,0),R35))","v":89.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A35,'Updated Quanities'!F:I,5,0),R35)=\"\",R35,IFERROR(VLOOKUP('AUP Library'!A35,'Updated Quanities'!F:I,5,0),R35))","v":89.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A35,'Updated Quanities'!F:I,6,0),R35)=\"\",R35,IFERROR(VLOOKUP('AUP Library'!A35,'Updated Quanities'!F:I,6,0),R35))","v":89.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A35,'Updated Quanities'!F:I,7,0),R35)=\"\",R35,IFERROR(VLOOKUP('AUP Library'!A35,'Updated Quanities'!F:I,7,0),R35))","v":89.8},89.8,{"$f":"IFERROR(VLOOKUP('AUP Library'!A35,'Updated Quanities'!F:G,4,0),R35)","v":89.8}]
["309-01.01","Mineral Aggregate (A-CBC)","TON",18.37,18.37,18.37,18.37,18.37,18.37,18.37,18.37,18.37,18.37,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A36,'Updated Quanities'!F:I,4,0),R36)=\"\",R36,IFERROR(VLOOKUP('AUP Library'!A36,'Updated Quanities'!F:I,4,0),R36))","v":18.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A36,'Updated Quanities'!F:I,5,0),R36)=\"\",R36,IFERROR(VLOOKUP('AUP Library'!A36,'Updated Quanities'!F:I,5,0),R36))","v":18.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A36,'Updated Quanities'!F:I,6,0),R36)=\"\",R36,IFERROR(VLOOKUP('AUP Library'!A36,'Updated Quanities'!F:I,6,0),R36))","v":18.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A36,'Updated Quanities'!F:I,7,0),R36)=\"\",R36,IFERROR(VLOOKUP('AUP Library'!A36,'Updated Quanities'!F:I,7,0),R36))","v":18.37},18.37,{"$f":"IFERROR(VLOOKUP('AUP Library'!A36,'Updated Quanities'!F:G,4,0),R36)","v":18.37}]
["309-01.02","Portland Cement (A-CBC)","TON",187.3,187.3,187.3,187.3,187.3,187.3,187.3,187.3,187.3,187.3,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A37,'Updated Quanities'!F:I,4,0),R37)=\"\",R37,IFERROR(VLOOKUP('AUP Library'!A37,'Updated Quanities'!F:I,4,0),R37))","v":187.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A37,'Updated Quanities'!F:I,5,0),R37)=\"\",R37,IFERROR(VLOOKUP('AUP Library'!A37,'Updated Quanities'!F:I,5,0),R37))","v":187.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A37,'Updated Quanities'!F:I,6,0),R37)=\"\",R37,IFERROR(VLOOKUP('AUP Library'!A37,'Updated Quanities'!F:I,6,0),R37))","v":187.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A37,'Updated Quanities'!F:I,7,0),R37)=\"\",R37,IFERROR(VLOOKUP('AUP Library'!A37,'Updated Quanities'!F:I,7,0),R37))","v":187.3},187.3,{"$f":"IFERROR(VLOOKUP('AUP Library'!A37,'Updated Quanities'!F:G,4,0),R37)","v":187.3}]
["309-02","Bituminous Material (A-CBC)","TON",673.26,673.26,673.26,673.26,673.26,673.26,673.26,673.26,673.26,673.26,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A38,'Updated Quanities'!F:I,4,0),R38)=\"\",R38,IFERROR(VLOOKUP('AUP Library'!A38,'Updated Quanities'!F:I,4,0),R38))","v":673.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A38,'Updated Quanities'!F:I,5,0),R38)=\"\",R38,IFERROR(VLOOKUP('AUP Library'!A38,'Updated Quanities'!F:I,5,0),R38))","v":673.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A38,'Updated Quanities'!F:I,6,0),R38)=\"\",R38,IFERROR(VLOOKUP('AUP Library'!A38,'Updated Quanities'!F:I,6,0),R38))","v":673.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A38,'Updated Quanities'!F:I,7,0),R38)=\"\",R38,IFERROR(VLOOKUP('AUP Library'!A38,'Updated Quanities'!F:I,7,0),R38))","v":673.26},673.26,{"$f":"IFERROR(VLOOKUP('AUP Library'!A38,'Updated Quanities'!F:G,4,0),R38)","v":673.26}]
["402-01","Bituminous Material For Prime Coat (PC)","TON",231.71,337.5,382.39,491.95,491.95,472.5,558.36,508.44,452.98,497.96,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A39,'Updated Quanities'!F:I,4,0),R39)=\"\",R39,IFERROR(VLOOKUP('AUP Library'!A39,'Updated Quanities'!F:I,4,0),R39))","v":535.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A39,'Updated Quanities'!F:I,5,0),R39)=\"\",R39,IFERROR(VLOOKUP('AUP Library'!A39,'Updated Quanities'!F:I,5,0),R39))","v":535.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A39,'Updated Quanities'!F:I,6,0),R39)=\"\",R39,IFERROR(VLOOKUP('AUP Library'!A39,'Updated Quanities'!F:I,6,0),R39))","v":535.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A39,'Updated Quanities'!F:I,7,0),R39)=\"\",R39,IFERROR(VLOOKUP('AUP Library'!A39,'Updated Quanities'!F:I,7,0),R39))","v":535.72},535.72,{"$f":"IFERROR(VLOOKUP('AUP Library'!A39,'Updated Quanities'!F:G,4,0),R39)","v":535.72}]
["402-02","Aggregate For Cover Material (PC)","TON",16.38,16.14,18.190000000000001,23.67,23.67,18.059999999999999,20.81,23.27,24.74,23.81,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A40,'Updated Quanities'!F:I,4,0),R40)=\"\",R40,IFERROR(VLOOKUP('AUP Library'!A40,'Updated Quanities'!F:I,4,0),R40))","v":34.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A40,'Updated Quanities'!F:I,5,0),R40)=\"\",R40,IFERROR(VLOOKUP('AUP Library'!A40,'Updated Quanities'!F:I,5,0),R40))","v":34.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A40,'Updated Quanities'!F:I,6,0),R40)=\"\",R40,IFERROR(VLOOKUP('AUP Library'!A40,'Updated Quanities'!F:I,6,0),R40))","v":34.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A40,'Updated Quanities'!F:I,7,0),R40)=\"\",R40,IFERROR(VLOOKUP('AUP Library'!A40,'Updated Quanities'!F:I,7,0),R40))","v":34.19},34.19,{"$f":"IFERROR(VLOOKUP('AUP Library'!A40,'Updated Quanities'!F:G,4,0),R40)","v":34.19}]
["403-01","Bituminous Material For Tack Coat (TC)","TON",260.45,327.14999999999998,339.5,413.86,413.86,453.48,517.73,571.21,561.91,626.54999999999995,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A41,'Updated Quanities'!F:I,4,0),R41)=\"\",R41,IFERROR(VLOOKUP('AUP Library'!A41,'Updated Quanities'!F:I,4,0),R41))","v":589.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A41,'Updated Quanities'!F:I,5,0),R41)=\"\",R41,IFERROR(VLOOKUP('AUP Library'!A41,'Updated Quanities'!F:I,5,0),R41))","v":589.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A41,'Updated Quanities'!F:I,6,0),R41)=\"\",R41,IFERROR(VLOOKUP('AUP Library'!A41,'Updated Quanities'!F:I,6,0),R41))","v":589.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A41,'Updated Quanities'!F:I,7,0),R41)=\"\",R41,IFERROR(VLOOKUP('AUP Library'!A41,'Updated Quanities'!F:I,7,0),R41))","v":589.1},589.1,{"$f":"IFERROR(VLOOKUP('AUP Library'!A41,'Updated Quanities'!F:G,4,0),R41)","v":589.1}]
["404-01.01","Bituminous Material (DBST)","TON",1575,1575,1575,1575,1575,1575,1575,1575,1575,1575,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A42,'Updated Quanities'!F:I,4,0),R42)=\"\",R42,IFERROR(VLOOKUP('AUP Library'!A42,'Updated Quanities'!F:I,4,0),R42))","v":1575},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A42,'Updated Quanities'!F:I,5,0),R42)=\"\",R42,IFERROR(VLOOKUP('AUP Library'!A42,'Updated Quanities'!F:I,5,0),R42))","v":1575},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A42,'Updated Quanities'!F:I,6,0),R42)=\"\",R42,IFERROR(VLOOKUP('AUP Library'!A42,'Updated Quanities'!F:I,6,0),R42))","v":1575},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A42,'Updated Quanities'!F:I,7,0),R42)=\"\",R42,IFERROR(VLOOKUP('AUP Library'!A42,'Updated Quanities'!F:I,7,0),R42))","v":1575},1575,{"$f":"IFERROR(VLOOKUP('AUP Library'!A42,'Updated Quanities'!F:G,4,0),R42)","v":1575}]
["404-01.02","Mineral Aggregate (DBST)","TON",61.85,61.85,61.85,61.85,61.85,61.85,61.85,61.85,61.85,61.85,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A43,'Updated Quanities'!F:I,4,0),R43)=\"\",R43,IFERROR(VLOOKUP('AUP Library'!A43,'Updated Quanities'!F:I,4,0),R43))","v":61.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A43,'Updated Quanities'!F:I,5,0),R43)=\"\",R43,IFERROR(VLOOKUP('AUP Library'!A43,'Updated Quanities'!F:I,5,0),R43))","v":61.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A43,'Updated Quanities'!F:I,6,0),R43)=\"\",R43,IFERROR(VLOOKUP('AUP Library'!A43,'Updated Quanities'!F:I,6,0),R43))","v":61.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A43,'Updated Quanities'!F:I,7,0),R43)=\"\",R43,IFERROR(VLOOKUP('AUP Library'!A43,'Updated Quanities'!F:I,7,0),R43))","v":61.85},61.85,{"$f":"IFERROR(VLOOKUP('AUP Library'!A43,'Updated Quanities'!F:G,4,0),R43)","v":61.85}]
["405-01.01","Bituminous Material (BSC)","TON",668.02,668.02,668.02,668.02,668.02,668.02,668.02,668.02,668.02,668.02,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A44,'Updated Quanities'!F:I,4,0),R44)=\"\",R44,IFERROR(VLOOKUP('AUP Library'!A44,'Updated Quanities'!F:I,4,0),R44))","v":668.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A44,'Updated Quanities'!F:I,5,0),R44)=\"\",R44,IFERROR(VLOOKUP('AUP Library'!A44,'Updated Quanities'!F:I,5,0),R44))","v":668.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A44,'Updated Quanities'!F:I,6,0),R44)=\"\",R44,IFERROR(VLOOKUP('AUP Library'!A44,'Updated Quanities'!F:I,6,0),R44))","v":668.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A44,'Updated Quanities'!F:I,7,0),R44)=\"\",R44,IFERROR(VLOOKUP('AUP Library'!A44,'Updated Quanities'!F:I,7,0),R44))","v":668.02},668.02,{"$f":"IFERROR(VLOOKUP('AUP Library'!A44,'Updated Quanities'!F:G,4,0),R44)","v":668.02}]
["405-01.02","Mineral Aggregate (BSC)","TON",38.32,38.32,38.32,38.32,38.32,38.32,38.32,38.32,38.32,38.32,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A45,'Updated Quanities'!F:I,4,0),R45)=\"\",R45,IFERROR(VLOOKUP('AUP Library'!A45,'Updated Quanities'!F:I,4,0),R45))","v":38.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A45,'Updated Quanities'!F:I,5,0),R45)=\"\",R45,IFERROR(VLOOKUP('AUP Library'!A45,'Updated Quanities'!F:I,5,0),R45))","v":38.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A45,'Updated Quanities'!F:I,6,0),R45)=\"\",R45,IFERROR(VLOOKUP('AUP Library'!A45,'Updated Quanities'!F:I,6,0),R45))","v":38.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A45,'Updated Quanities'!F:I,7,0),R45)=\"\",R45,IFERROR(VLOOKUP('AUP Library'!A45,'Updated Quanities'!F:I,7,0),R45))","v":38.32},38.32,{"$f":"IFERROR(VLOOKUP('AUP Library'!A45,'Updated Quanities'!F:G,4,0),R45)","v":38.32}]
["406-04.01","Polymer Modfified Epoxy Pavement Overlay","SY",22,22,22,22,22,22,22,22,22,22,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A46,'Updated Quanities'!F:I,4,0),R46)=\"\",R46,IFERROR(VLOOKUP('AUP Library'!A46,'Updated Quanities'!F:I,4,0),R46))","v":22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A46,'Updated Quanities'!F:I,5,0),R46)=\"\",R46,IFERROR(VLOOKUP('AUP Library'!A46,'Updated Quanities'!F:I,5,0),R46))","v":22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A46,'Updated Quanities'!F:I,6,0),R46)=\"\",R46,IFERROR(VLOOKUP('AUP Library'!A46,'Updated Quanities'!F:I,6,0),R46))","v":22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A46,'Updated Quanities'!F:I,7,0),R46)=\"\",R46,IFERROR(VLOOKUP('AUP Library'!A46,'Updated Quanities'!F:I,7,0),R46))","v":22},22,{"$f":"IFERROR(VLOOKUP('AUP Library'!A46,'Updated Quanities'!F:G,4,0),R46)","v":22}]
["406-04.02","High Friction Surface Treatment","SY",20.94,20.94,20.94,20.94,20.94,20.94,20.94,20.94,20.94,20.94,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A47,'Updated Quanities'!F:I,4,0),R47)=\"\",R47,IFERROR(VLOOKUP('AUP Library'!A47,'Updated Quanities'!F:I,4,0),R47))","v":20.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A47,'Updated Quanities'!F:I,5,0),R47)=\"\",R47,IFERROR(VLOOKUP('AUP Library'!A47,'Updated Quanities'!F:I,5,0),R47))","v":20.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A47,'Updated Quanities'!F:I,6,0),R47)=\"\",R47,IFERROR(VLOOKUP('AUP Library'!A47,'Updated Quanities'!F:I,6,0),R47))","v":20.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A47,'Updated Quanities'!F:I,7,0),R47)=\"\",R47,IFERROR(VLOOKUP('AUP Library'!A47,'Updated Quanities'!F:I,7,0),R47))","v":20.94},20.94,{"$f":"IFERROR(VLOOKUP('AUP Library'!A47,'Updated Quanities'!F:G,4,0),R47)","v":20.94}]
["406-04.03","High Friction Surface Treatment (Single Lift)","SY",18.54,18.54,18.54,18.54,18.54,18.54,18.54,18.54,18.54,18.54,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A48,'Updated Quanities'!F:I,4,0),R48)=\"\",R48,IFERROR(VLOOKUP('AUP Library'!A48,'Updated Quanities'!F:I,4,0),R48))","v":18.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A48,'Updated Quanities'!F:I,5,0),R48)=\"\",R48,IFERROR(VLOOKUP('AUP Library'!A48,'Updated Quanities'!F:I,5,0),R48))","v":18.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A48,'Updated Quanities'!F:I,6,0),R48)=\"\",R48,IFERROR(VLOOKUP('AUP Library'!A48,'Updated Quanities'!F:I,6,0),R48))","v":18.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A48,'Updated Quanities'!F:I,7,0),R48)=\"\",R48,IFERROR(VLOOKUP('AUP Library'!A48,'Updated Quanities'!F:I,7,0),R48))","v":18.54},18.54,{"$f":"IFERROR(VLOOKUP('AUP Library'!A48,'Updated Quanities'!F:G,4,0),R48)","v":18.54}]
["406-04.04","High Friction Surface Treatment (Double Lift)","SY",36.85,36.85,36.85,36.85,36.85,36.85,36.85,36.85,36.85,36.85,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A49,'Updated Quanities'!F:I,4,0),R49)=\"\",R49,IFERROR(VLOOKUP('AUP Library'!A49,'Updated Quanities'!F:I,4,0),R49))","v":36.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A49,'Updated Quanities'!F:I,5,0),R49)=\"\",R49,IFERROR(VLOOKUP('AUP Library'!A49,'Updated Quanities'!F:I,5,0),R49))","v":36.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A49,'Updated Quanities'!F:I,6,0),R49)=\"\",R49,IFERROR(VLOOKUP('AUP Library'!A49,'Updated Quanities'!F:I,6,0),R49))","v":36.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A49,'Updated Quanities'!F:I,7,0),R49)=\"\",R49,IFERROR(VLOOKUP('AUP Library'!A49,'Updated Quanities'!F:I,7,0),R49))","v":36.85},36.85,{"$f":"IFERROR(VLOOKUP('AUP Library'!A49,'Updated Quanities'!F:G,4,0),R49)","v":36.85}]
["407-02.11","Removal & Disposal Existing Asphalt Pavement","CY",10,10,10,10,10,10,10,10,10,10,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A50,'Updated Quanities'!F:I,4,0),R50)=\"\",R50,IFERROR(VLOOKUP('AUP Library'!A50,'Updated Quanities'!F:I,4,0),R50))","v":10},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A50,'Updated Quanities'!F:I,5,0),R50)=\"\",R50,IFERROR(VLOOKUP('AUP Library'!A50,'Updated Quanities'!F:I,5,0),R50))","v":10},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A50,'Updated Quanities'!F:I,6,0),R50)=\"\",R50,IFERROR(VLOOKUP('AUP Library'!A50,'Updated Quanities'!F:I,6,0),R50))","v":10},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A50,'Updated Quanities'!F:I,7,0),R50)=\"\",R50,IFERROR(VLOOKUP('AUP Library'!A50,'Updated Quanities'!F:I,7,0),R50))","v":10},10,{"$f":"IFERROR(VLOOKUP('AUP Library'!A50,'Updated Quanities'!F:G,4,0),R50)","v":10}]
["407-02.12","Removal & Disposal Existing Asphalt Pavement","TON",17.760000000000002,17.760000000000002,17.760000000000002,17.760000000000002,17.760000000000002,17.760000000000002,17.760000000000002,17.760000000000002,17.760000000000002,17.760000000000002,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A51,'Updated Quanities'!F:I,4,0),R51)=\"\",R51,IFERROR(VLOOKUP('AUP Library'!A51,'Updated Quanities'!F:I,4,0),R51))","v":17.760000000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A51,'Updated Quanities'!F:I,5,0),R51)=\"\",R51,IFERROR(VLOOKUP('AUP Library'!A51,'Updated Quanities'!F:I,5,0),R51))","v":17.760000000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A51,'Updated Quanities'!F:I,6,0),R51)=\"\",R51,IFERROR(VLOOKUP('AUP Library'!A51,'Updated Quanities'!F:I,6,0),R51))","v":17.760000000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A51,'Updated Quanities'!F:I,7,0),R51)=\"\",R51,IFERROR(VLOOKUP('AUP Library'!A51,'Updated Quanities'!F:I,7,0),R51))","v":17.760000000000002},17.760000000000002,{"$f":"IFERROR(VLOOKUP('AUP Library'!A51,'Updated Quanities'!F:G,4,0),R51)","v":17.760000000000002}]
["407-02.13","Removal & Disposal Existing Asphalt Pavement","SY",4.3099999999999996,4.3099999999999996,4.3099999999999996,4.3099999999999996,4.3099999999999996,4.3099999999999996,4.3099999999999996,4.3099999999999996,4.3099999999999996,4.3099999999999996,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A52,'Updated Quanities'!F:I,4,0),R52)=\"\",R52,IFERROR(VLOOKUP('AUP Library'!A52,'Updated Quanities'!F:I,4,0),R52))","v":4.3099999999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A52,'Updated Quanities'!F:I,5,0),R52)=\"\",R52,IFERROR(VLOOKUP('AUP Library'!A52,'Updated Quanities'!F:I,5,0),R52))","v":4.3099999999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A52,'Updated Quanities'!F:I,6,0),R52)=\"\",R52,IFERROR(VLOOKUP('AUP Library'!A52,'Updated Quanities'!F:I,6,0),R52))","v":4.3099999999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A52,'Updated Quanities'!F:I,7,0),R52)=\"\",R52,IFERROR(VLOOKUP('AUP Library'!A52,'Updated Quanities'!F:I,7,0),R52))","v":4.3099999999999996},4.3099999999999996,{"$f":"IFERROR(VLOOKUP('AUP Library'!A52,'Updated Quanities'!F:G,4,0),R52)","v":4.3099999999999996}]
["407-02.14","Asphalt Pavement Repair","SY",60,60,60,60,60,60,60,60,60,60,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A53,'Updated Quanities'!F:I,4,0),R53)=\"\",R53,IFERROR(VLOOKUP('AUP Library'!A53,'Updated Quanities'!F:I,4,0),R53))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A53,'Updated Quanities'!F:I,5,0),R53)=\"\",R53,IFERROR(VLOOKUP('AUP Library'!A53,'Updated Quanities'!F:I,5,0),R53))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A53,'Updated Quanities'!F:I,6,0),R53)=\"\",R53,IFERROR(VLOOKUP('AUP Library'!A53,'Updated Quanities'!F:I,6,0),R53))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A53,'Updated Quanities'!F:I,7,0),R53)=\"\",R53,IFERROR(VLOOKUP('AUP Library'!A53,'Updated Quanities'!F:I,7,0),R53))","v":60},60,{"$f":"IFERROR(VLOOKUP('AUP Library'!A53,'Updated Quanities'!F:G,4,0),R53)","v":60}]
["407-07.01","Intelligent Compaction Equipment","LS",90930,90930,90930,90930,90930,90930,90930,90930,90930,90930,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A54,'Updated Quanities'!F:I,4,0),R54)=\"\",R54,IFERROR(VLOOKUP('AUP Library'!A54,'Updated Quanities'!F:I,4,0),R54))","v":90930},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A54,'Updated Quanities'!F:I,5,0),R54)=\"\",R54,IFERROR(VLOOKUP('AUP Library'!A54,'Updated Quanities'!F:I,5,0),R54))","v":90930},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A54,'Updated Quanities'!F:I,6,0),R54)=\"\",R54,IFERROR(VLOOKUP('AUP Library'!A54,'Updated Quanities'!F:I,6,0),R54))","v":90930},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A54,'Updated Quanities'!F:I,7,0),R54)=\"\",R54,IFERROR(VLOOKUP('AUP Library'!A54,'Updated Quanities'!F:I,7,0),R54))","v":90930},90930,{"$f":"IFERROR(VLOOKUP('AUP Library'!A54,'Updated Quanities'!F:G,4,0),R54)","v":90930}]
["407-10.03","Fiber Glass Mat (Pavement Reinforcing)","SY",1.8,1.8,1.8,1.8,1.8,1.8,1.8,1.8,1.8,1.8,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A55,'Updated Quanities'!F:I,4,0),R55)=\"\",R55,IFERROR(VLOOKUP('AUP Library'!A55,'Updated Quanities'!F:I,4,0),R55))","v":1.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A55,'Updated Quanities'!F:I,5,0),R55)=\"\",R55,IFERROR(VLOOKUP('AUP Library'!A55,'Updated Quanities'!F:I,5,0),R55))","v":1.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A55,'Updated Quanities'!F:I,6,0),R55)=\"\",R55,IFERROR(VLOOKUP('AUP Library'!A55,'Updated Quanities'!F:I,6,0),R55))","v":1.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A55,'Updated Quanities'!F:I,7,0),R55)=\"\",R55,IFERROR(VLOOKUP('AUP Library'!A55,'Updated Quanities'!F:I,7,0),R55))","v":1.8},1.8,{"$f":"IFERROR(VLOOKUP('AUP Library'!A55,'Updated Quanities'!F:G,4,0),R55)","v":1.8}]
["407-10.05","Asphalt Overlay Reinforcement (Installation)","LS",20000,20000,20000,20000,20000,20000,20000,20000,20000,20000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A56,'Updated Quanities'!F:I,4,0),R56)=\"\",R56,IFERROR(VLOOKUP('AUP Library'!A56,'Updated Quanities'!F:I,4,0),R56))","v":20000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A56,'Updated Quanities'!F:I,5,0),R56)=\"\",R56,IFERROR(VLOOKUP('AUP Library'!A56,'Updated Quanities'!F:I,5,0),R56))","v":20000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A56,'Updated Quanities'!F:I,6,0),R56)=\"\",R56,IFERROR(VLOOKUP('AUP Library'!A56,'Updated Quanities'!F:I,6,0),R56))","v":20000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A56,'Updated Quanities'!F:I,7,0),R56)=\"\",R56,IFERROR(VLOOKUP('AUP Library'!A56,'Updated Quanities'!F:I,7,0),R56))","v":20000},20000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A56,'Updated Quanities'!F:G,4,0),R56)","v":20000}]
["407-10.50","Design-Build Bituminous Pavement","LS",57827.5,57827.5,57827.5,57827.5,57827.5,57827.5,57827.5,57827.5,57827.5,57827.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A57,'Updated Quanities'!F:I,4,0),R57)=\"\",R57,IFERROR(VLOOKUP('AUP Library'!A57,'Updated Quanities'!F:I,4,0),R57))","v":57827.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A57,'Updated Quanities'!F:I,5,0),R57)=\"\",R57,IFERROR(VLOOKUP('AUP Library'!A57,'Updated Quanities'!F:I,5,0),R57))","v":57827.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A57,'Updated Quanities'!F:I,6,0),R57)=\"\",R57,IFERROR(VLOOKUP('AUP Library'!A57,'Updated Quanities'!F:I,6,0),R57))","v":57827.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A57,'Updated Quanities'!F:I,7,0),R57)=\"\",R57,IFERROR(VLOOKUP('AUP Library'!A57,'Updated Quanities'!F:I,7,0),R57))","v":57827.5},57827.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A57,'Updated Quanities'!F:G,4,0),R57)","v":57827.5}]
["407-20.05","Saw Cutting Asphalt Pavement","LS",3.1,3.1,3.1,3.1,3.1,3.1,3.1,3.1,3.1,3.1,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A58,'Updated Quanities'!F:I,4,0),R58)=\"\",R58,IFERROR(VLOOKUP('AUP Library'!A58,'Updated Quanities'!F:I,4,0),R58))","v":3.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A58,'Updated Quanities'!F:I,5,0),R58)=\"\",R58,IFERROR(VLOOKUP('AUP Library'!A58,'Updated Quanities'!F:I,5,0),R58))","v":3.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A58,'Updated Quanities'!F:I,6,0),R58)=\"\",R58,IFERROR(VLOOKUP('AUP Library'!A58,'Updated Quanities'!F:I,6,0),R58))","v":3.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A58,'Updated Quanities'!F:I,7,0),R58)=\"\",R58,IFERROR(VLOOKUP('AUP Library'!A58,'Updated Quanities'!F:I,7,0),R58))","v":3.1},3.1,{"$f":"IFERROR(VLOOKUP('AUP Library'!A58,'Updated Quanities'!F:G,4,0),R58)","v":3.1}]
["411-01.07","ACS (PG64-22) GR \"E\"","TON",40.4,52.14,56.92,73.650000000000006,73.650000000000006,73.36,75.77,82.94,75.56,92.37,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A59,'Updated Quanities'!F:I,4,0),R59)=\"\",R59,IFERROR(VLOOKUP('AUP Library'!A59,'Updated Quanities'!F:I,4,0),R59))","v":84.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A59,'Updated Quanities'!F:I,5,0),R59)=\"\",R59,IFERROR(VLOOKUP('AUP Library'!A59,'Updated Quanities'!F:I,5,0),R59))","v":84.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A59,'Updated Quanities'!F:I,6,0),R59)=\"\",R59,IFERROR(VLOOKUP('AUP Library'!A59,'Updated Quanities'!F:I,6,0),R59))","v":84.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A59,'Updated Quanities'!F:I,7,0),R59)=\"\",R59,IFERROR(VLOOKUP('AUP Library'!A59,'Updated Quanities'!F:I,7,0),R59))","v":84.51},84.51,{"$f":"IFERROR(VLOOKUP('AUP Library'!A59,'Updated Quanities'!F:G,4,0),R59)","v":84.51}]
["411-01.10","ACS Mix(PG64-22) Grading D","TON",93.96,93.96,93.96,93.96,93.96,93.96,93.96,93.96,93.96,93.96,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A60,'Updated Quanities'!F:I,4,0),R60)=\"\",R60,IFERROR(VLOOKUP('AUP Library'!A60,'Updated Quanities'!F:I,4,0),R60))","v":94.96},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A60,'Updated Quanities'!F:I,5,0),R60)=\"\",R60,IFERROR(VLOOKUP('AUP Library'!A60,'Updated Quanities'!F:I,5,0),R60))","v":94.96},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A60,'Updated Quanities'!F:I,6,0),R60)=\"\",R60,IFERROR(VLOOKUP('AUP Library'!A60,'Updated Quanities'!F:I,6,0),R60))","v":94.96},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A60,'Updated Quanities'!F:I,7,0),R60)=\"\",R60,IFERROR(VLOOKUP('AUP Library'!A60,'Updated Quanities'!F:I,7,0),R60))","v":94.96},94.96,{"$f":"IFERROR(VLOOKUP('AUP Library'!A60,'Updated Quanities'!F:G,4,0),R60)","v":94.96}]
["411-01.11","ACS Mix (PG64-22) Grading E Rdwy","TON",85.61,85.61,85.61,85.61,85.61,85.61,85.61,85.61,85.61,85.61,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A61,'Updated Quanities'!F:I,4,0),R61)=\"\",R61,IFERROR(VLOOKUP('AUP Library'!A61,'Updated Quanities'!F:I,4,0),R61))","v":85.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A61,'Updated Quanities'!F:I,5,0),R61)=\"\",R61,IFERROR(VLOOKUP('AUP Library'!A61,'Updated Quanities'!F:I,5,0),R61))","v":85.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A61,'Updated Quanities'!F:I,6,0),R61)=\"\",R61,IFERROR(VLOOKUP('AUP Library'!A61,'Updated Quanities'!F:I,6,0),R61))","v":85.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A61,'Updated Quanities'!F:I,7,0),R61)=\"\",R61,IFERROR(VLOOKUP('AUP Library'!A61,'Updated Quanities'!F:I,7,0),R61))","v":85.61},85.61,{"$f":"IFERROR(VLOOKUP('AUP Library'!A61,'Updated Quanities'!F:G,4,0),R61)","v":85.61}]
["411-01.12","Longitudinal Joint Stabilization","SF",0.09,0.09,0.09,0.09,0.09,0.09,0.09,0.09,0.09,0.09,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A62,'Updated Quanities'!F:I,4,0),R62)=\"\",R62,IFERROR(VLOOKUP('AUP Library'!A62,'Updated Quanities'!F:I,4,0),R62))","v":0.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A62,'Updated Quanities'!F:I,5,0),R62)=\"\",R62,IFERROR(VLOOKUP('AUP Library'!A62,'Updated Quanities'!F:I,5,0),R62))","v":0.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A62,'Updated Quanities'!F:I,6,0),R62)=\"\",R62,IFERROR(VLOOKUP('AUP Library'!A62,'Updated Quanities'!F:I,6,0),R62))","v":0.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A62,'Updated Quanities'!F:I,7,0),R62)=\"\",R62,IFERROR(VLOOKUP('AUP Library'!A62,'Updated Quanities'!F:I,7,0),R62))","v":0.09},0.09,{"$f":"IFERROR(VLOOKUP('AUP Library'!A62,'Updated Quanities'!F:G,4,0),R62)","v":0.09}]
["411-02.10","ACS Mix(PG70-22) Grading D","TON",44.51,58.53,60.66,75.61,75.61,80.459999999999994,84.45,86.65,85.98,93.96,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A63,'Updated Quanities'!F:I,4,0),R63)=\"\",R63,IFERROR(VLOOKUP('AUP Library'!A63,'Updated Quanities'!F:I,4,0),R63))","v":85.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A63,'Updated Quanities'!F:I,5,0),R63)=\"\",R63,IFERROR(VLOOKUP('AUP Library'!A63,'Updated Quanities'!F:I,5,0),R63))","v":85.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A63,'Updated Quanities'!F:I,6,0),R63)=\"\",R63,IFERROR(VLOOKUP('AUP Library'!A63,'Updated Quanities'!F:I,6,0),R63))","v":85.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A63,'Updated Quanities'!F:I,7,0),R63)=\"\",R63,IFERROR(VLOOKUP('AUP Library'!A63,'Updated Quanities'!F:I,7,0),R63))","v":85.82},85.82,{"$f":"IFERROR(VLOOKUP('AUP Library'!A63,'Updated Quanities'!F:G,4,0),R63)","v":85.82}]
["411-03.05","ACS Mix (PG64-22) Thing Lift CS Asphalt","SY",3.1,3.1,3.1,3.1,3.1,3.1,3.1,3.1,3.1,3.1,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A64,'Updated Quanities'!F:I,4,0),R64)=\"\",R64,IFERROR(VLOOKUP('AUP Library'!A64,'Updated Quanities'!F:I,4,0),R64))","v":3.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A64,'Updated Quanities'!F:I,5,0),R64)=\"\",R64,IFERROR(VLOOKUP('AUP Library'!A64,'Updated Quanities'!F:I,5,0),R64))","v":3.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A64,'Updated Quanities'!F:I,6,0),R64)=\"\",R64,IFERROR(VLOOKUP('AUP Library'!A64,'Updated Quanities'!F:I,6,0),R64))","v":3.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A64,'Updated Quanities'!F:I,7,0),R64)=\"\",R64,IFERROR(VLOOKUP('AUP Library'!A64,'Updated Quanities'!F:I,7,0),R64))","v":3.1},3.1,{"$f":"IFERROR(VLOOKUP('AUP Library'!A64,'Updated Quanities'!F:G,4,0),R64)","v":3.1}]
["411-03.07","ASC Mix (PG64-22) Thin Lift CS Asphalt","TON",64.91,64.91,64.91,64.91,64.91,64.91,64.91,64.91,64.91,64.91,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A65,'Updated Quanities'!F:I,4,0),R65)=\"\",R65,IFERROR(VLOOKUP('AUP Library'!A65,'Updated Quanities'!F:I,4,0),R65))","v":64.91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A65,'Updated Quanities'!F:I,5,0),R65)=\"\",R65,IFERROR(VLOOKUP('AUP Library'!A65,'Updated Quanities'!F:I,5,0),R65))","v":64.91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A65,'Updated Quanities'!F:I,6,0),R65)=\"\",R65,IFERROR(VLOOKUP('AUP Library'!A65,'Updated Quanities'!F:I,6,0),R65))","v":64.91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A65,'Updated Quanities'!F:I,7,0),R65)=\"\",R65,IFERROR(VLOOKUP('AUP Library'!A65,'Updated Quanities'!F:I,7,0),R65))","v":64.91},64.91,{"$f":"IFERROR(VLOOKUP('AUP Library'!A65,'Updated Quanities'!F:G,4,0),R65)","v":64.91}]
["411-03.08","ACS Mix (PG70-22) Thin Lift CS Asphalt","TON",96.75,96.75,96.75,96.75,96.75,96.75,96.75,96.75,96.75,96.75,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A66,'Updated Quanities'!F:I,4,0),R66)=\"\",R66,IFERROR(VLOOKUP('AUP Library'!A66,'Updated Quanities'!F:I,4,0),R66))","v":96.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A66,'Updated Quanities'!F:I,5,0),R66)=\"\",R66,IFERROR(VLOOKUP('AUP Library'!A66,'Updated Quanities'!F:I,5,0),R66))","v":96.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A66,'Updated Quanities'!F:I,6,0),R66)=\"\",R66,IFERROR(VLOOKUP('AUP Library'!A66,'Updated Quanities'!F:I,6,0),R66))","v":96.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A66,'Updated Quanities'!F:I,7,0),R66)=\"\",R66,IFERROR(VLOOKUP('AUP Library'!A66,'Updated Quanities'!F:I,7,0),R66))","v":96.75},96.75,{"$f":"IFERROR(VLOOKUP('AUP Library'!A66,'Updated Quanities'!F:G,4,0),R66)","v":96.75}]
["411-03.09","ACS Mix (PG76-22) Thin Lift CS Asphalt","TON",88.03,88.03,88.03,88.03,88.03,88.03,88.03,88.03,88.03,88.03,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A67,'Updated Quanities'!F:I,4,0),R67)=\"\",R67,IFERROR(VLOOKUP('AUP Library'!A67,'Updated Quanities'!F:I,4,0),R67))","v":88.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A67,'Updated Quanities'!F:I,5,0),R67)=\"\",R67,IFERROR(VLOOKUP('AUP Library'!A67,'Updated Quanities'!F:I,5,0),R67))","v":88.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A67,'Updated Quanities'!F:I,6,0),R67)=\"\",R67,IFERROR(VLOOKUP('AUP Library'!A67,'Updated Quanities'!F:I,6,0),R67))","v":88.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A67,'Updated Quanities'!F:I,7,0),R67)=\"\",R67,IFERROR(VLOOKUP('AUP Library'!A67,'Updated Quanities'!F:I,7,0),R67))","v":88.03},88.03,{"$f":"IFERROR(VLOOKUP('AUP Library'!A67,'Updated Quanities'!F:G,4,0),R67)","v":88.03}]
["411-03.10","ACS Mix (PG76-22) Grading D","TON",72.44,72.44,72.44,72.44,72.44,72.44,72.44,72.44,72.44,72.44,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A68,'Updated Quanities'!F:I,4,0),R68)=\"\",R68,IFERROR(VLOOKUP('AUP Library'!A68,'Updated Quanities'!F:I,4,0),R68))","v":72.44},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A68,'Updated Quanities'!F:I,5,0),R68)=\"\",R68,IFERROR(VLOOKUP('AUP Library'!A68,'Updated Quanities'!F:I,5,0),R68))","v":72.44},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A68,'Updated Quanities'!F:I,6,0),R68)=\"\",R68,IFERROR(VLOOKUP('AUP Library'!A68,'Updated Quanities'!F:I,6,0),R68))","v":72.44},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A68,'Updated Quanities'!F:I,7,0),R68)=\"\",R68,IFERROR(VLOOKUP('AUP Library'!A68,'Updated Quanities'!F:I,7,0),R68))","v":72.44},72.44,{"$f":"IFERROR(VLOOKUP('AUP Library'!A68,'Updated Quanities'!F:G,4,0),R68)","v":72.44}]
["411-03.12","ACS Mix (PG64-22) Thin Lift D Asphalt","TON",0.31,0.31,0.31,0.31,0.31,0.31,0.31,0.31,0.31,0.31,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A69,'Updated Quanities'!F:I,4,0),R69)=\"\",R69,IFERROR(VLOOKUP('AUP Library'!A69,'Updated Quanities'!F:I,4,0),R69))","v":0.31},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A69,'Updated Quanities'!F:I,5,0),R69)=\"\",R69,IFERROR(VLOOKUP('AUP Library'!A69,'Updated Quanities'!F:I,5,0),R69))","v":0.31},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A69,'Updated Quanities'!F:I,6,0),R69)=\"\",R69,IFERROR(VLOOKUP('AUP Library'!A69,'Updated Quanities'!F:I,6,0),R69))","v":0.31},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A69,'Updated Quanities'!F:I,7,0),R69)=\"\",R69,IFERROR(VLOOKUP('AUP Library'!A69,'Updated Quanities'!F:I,7,0),R69))","v":0.31},0.31,{"$f":"IFERROR(VLOOKUP('AUP Library'!A69,'Updated Quanities'!F:G,4,0),R69)","v":0.31}]
["411-03.13","ACS Mix (PG70-22) Thin Lift D Asphalt","TON",82.15,82.15,82.15,82.15,82.15,82.15,82.15,82.15,82.15,82.15,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A70,'Updated Quanities'!F:I,4,0),R70)=\"\",R70,IFERROR(VLOOKUP('AUP Library'!A70,'Updated Quanities'!F:I,4,0),R70))","v":82.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A70,'Updated Quanities'!F:I,5,0),R70)=\"\",R70,IFERROR(VLOOKUP('AUP Library'!A70,'Updated Quanities'!F:I,5,0),R70))","v":82.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A70,'Updated Quanities'!F:I,6,0),R70)=\"\",R70,IFERROR(VLOOKUP('AUP Library'!A70,'Updated Quanities'!F:I,6,0),R70))","v":82.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A70,'Updated Quanities'!F:I,7,0),R70)=\"\",R70,IFERROR(VLOOKUP('AUP Library'!A70,'Updated Quanities'!F:I,7,0),R70))","v":82.15},82.15,{"$f":"IFERROR(VLOOKUP('AUP Library'!A70,'Updated Quanities'!F:G,4,0),R70)","v":82.15}]
["411-03.14","ACS Mix (PG76-22) Thin Lift D Asphalt","TON",100.86,100.86,100.86,100.86,100.86,100.86,100.86,100.86,100.86,100.86,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A71,'Updated Quanities'!F:I,4,0),R71)=\"\",R71,IFERROR(VLOOKUP('AUP Library'!A71,'Updated Quanities'!F:I,4,0),R71))","v":100.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A71,'Updated Quanities'!F:I,5,0),R71)=\"\",R71,IFERROR(VLOOKUP('AUP Library'!A71,'Updated Quanities'!F:I,5,0),R71))","v":100.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A71,'Updated Quanities'!F:I,6,0),R71)=\"\",R71,IFERROR(VLOOKUP('AUP Library'!A71,'Updated Quanities'!F:I,6,0),R71))","v":100.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A71,'Updated Quanities'!F:I,7,0),R71)=\"\",R71,IFERROR(VLOOKUP('AUP Library'!A71,'Updated Quanities'!F:I,7,0),R71))","v":100.86},100.86,{"$f":"IFERROR(VLOOKUP('AUP Library'!A71,'Updated Quanities'!F:G,4,0),R71)","v":100.86}]
["411-03.15","ASP Cem(PG76-22) For OGFC Mix","TON",935.84,935.84,935.84,935.84,935.84,935.84,935.84,935.84,935.84,935.84,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A72,'Updated Quanities'!F:I,4,0),R72)=\"\",R72,IFERROR(VLOOKUP('AUP Library'!A72,'Updated Quanities'!F:I,4,0),R72))","v":935.84},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A72,'Updated Quanities'!F:I,5,0),R72)=\"\",R72,IFERROR(VLOOKUP('AUP Library'!A72,'Updated Quanities'!F:I,5,0),R72))","v":935.84},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A72,'Updated Quanities'!F:I,6,0),R72)=\"\",R72,IFERROR(VLOOKUP('AUP Library'!A72,'Updated Quanities'!F:I,6,0),R72))","v":935.84},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A72,'Updated Quanities'!F:I,7,0),R72)=\"\",R72,IFERROR(VLOOKUP('AUP Library'!A72,'Updated Quanities'!F:I,7,0),R72))","v":935.84},935.84,{"$f":"IFERROR(VLOOKUP('AUP Library'!A72,'Updated Quanities'!F:G,4,0),R72)","v":935.84}]
["411-03.16","Aggregate for OGFC Mix","TON",54.05,54.05,54.05,54.05,54.05,54.05,54.05,54.05,54.05,54.05,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A73,'Updated Quanities'!F:I,4,0),R73)=\"\",R73,IFERROR(VLOOKUP('AUP Library'!A73,'Updated Quanities'!F:I,4,0),R73))","v":54.05},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A73,'Updated Quanities'!F:I,5,0),R73)=\"\",R73,IFERROR(VLOOKUP('AUP Library'!A73,'Updated Quanities'!F:I,5,0),R73))","v":54.05},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A73,'Updated Quanities'!F:I,6,0),R73)=\"\",R73,IFERROR(VLOOKUP('AUP Library'!A73,'Updated Quanities'!F:I,6,0),R73))","v":54.05},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A73,'Updated Quanities'!F:I,7,0),R73)=\"\",R73,IFERROR(VLOOKUP('AUP Library'!A73,'Updated Quanities'!F:I,7,0),R73))","v":54.05},54.05,{"$f":"IFERROR(VLOOKUP('AUP Library'!A73,'Updated Quanities'!F:G,4,0),R73)","v":54.05}]
["411-04","Crack Sealant","LB",1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A74,'Updated Quanities'!F:I,4,0),R74)=\"\",R74,IFERROR(VLOOKUP('AUP Library'!A74,'Updated Quanities'!F:I,4,0),R74))","v":1.1000000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A74,'Updated Quanities'!F:I,5,0),R74)=\"\",R74,IFERROR(VLOOKUP('AUP Library'!A74,'Updated Quanities'!F:I,5,0),R74))","v":1.1000000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A74,'Updated Quanities'!F:I,6,0),R74)=\"\",R74,IFERROR(VLOOKUP('AUP Library'!A74,'Updated Quanities'!F:I,6,0),R74))","v":1.1000000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A74,'Updated Quanities'!F:I,7,0),R74)=\"\",R74,IFERROR(VLOOKUP('AUP Library'!A74,'Updated Quanities'!F:I,7,0),R74))","v":1.1000000000000001},1.1000000000000001,{"$f":"IFERROR(VLOOKUP('AUP Library'!A74,'Updated Quanities'!F:G,4,0),R74)","v":1.1000000000000001}]
["411-04.10","ACS Mix (PG82-22) Grading D","TON",90,90,90,90,90,90,90,90,90,90,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A75,'Updated Quanities'!F:I,4,0),R75)=\"\",R75,IFERROR(VLOOKUP('AUP Library'!A75,'Updated Quanities'!F:I,4,0),R75))","v":90},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A75,'Updated Quanities'!F:I,5,0),R75)=\"\",R75,IFERROR(VLOOKUP('AUP Library'!A75,'Updated Quanities'!F:I,5,0),R75))","v":90},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A75,'Updated Quanities'!F:I,6,0),R75)=\"\",R75,IFERROR(VLOOKUP('AUP Library'!A75,'Updated Quanities'!F:I,6,0),R75))","v":90},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A75,'Updated Quanities'!F:I,7,0),R75)=\"\",R75,IFERROR(VLOOKUP('AUP Library'!A75,'Updated Quanities'!F:I,7,0),R75))","v":90},90,{"$f":"IFERROR(VLOOKUP('AUP Library'!A75,'Updated Quanities'!F:G,4,0),R75)","v":90}]
["414-03.01","Emulsified Asphalt for Micro-Surfacing","TON",722.07,722.07,722.07,722.07,722.07,722.07,722.07,722.07,722.07,722.07,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A76,'Updated Quanities'!F:I,4,0),R76)=\"\",R76,IFERROR(VLOOKUP('AUP Library'!A76,'Updated Quanities'!F:I,4,0),R76))","v":722.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A76,'Updated Quanities'!F:I,5,0),R76)=\"\",R76,IFERROR(VLOOKUP('AUP Library'!A76,'Updated Quanities'!F:I,5,0),R76))","v":722.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A76,'Updated Quanities'!F:I,6,0),R76)=\"\",R76,IFERROR(VLOOKUP('AUP Library'!A76,'Updated Quanities'!F:I,6,0),R76))","v":722.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A76,'Updated Quanities'!F:I,7,0),R76)=\"\",R76,IFERROR(VLOOKUP('AUP Library'!A76,'Updated Quanities'!F:I,7,0),R76))","v":722.07},722.07,{"$f":"IFERROR(VLOOKUP('AUP Library'!A76,'Updated Quanities'!F:G,4,0),R76)","v":722.07}]
["414-03.02","Aggregate for Micro Surfacing","TON",99.36,99.36,99.36,99.36,99.36,99.36,99.36,99.36,99.36,99.36,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A77,'Updated Quanities'!F:I,4,0),R77)=\"\",R77,IFERROR(VLOOKUP('AUP Library'!A77,'Updated Quanities'!F:I,4,0),R77))","v":99.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A77,'Updated Quanities'!F:I,5,0),R77)=\"\",R77,IFERROR(VLOOKUP('AUP Library'!A77,'Updated Quanities'!F:I,5,0),R77))","v":99.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A77,'Updated Quanities'!F:I,6,0),R77)=\"\",R77,IFERROR(VLOOKUP('AUP Library'!A77,'Updated Quanities'!F:I,6,0),R77))","v":99.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A77,'Updated Quanities'!F:I,7,0),R77)=\"\",R77,IFERROR(VLOOKUP('AUP Library'!A77,'Updated Quanities'!F:I,7,0),R77))","v":99.36},99.36,{"$f":"IFERROR(VLOOKUP('AUP Library'!A77,'Updated Quanities'!F:G,4,0),R77)","v":99.36}]
["414-03.03","Micro Surfacing","SY",2.15,2.15,2.15,2.15,2.15,2.15,2.15,2.15,2.15,2.15,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A78,'Updated Quanities'!F:I,4,0),R78)=\"\",R78,IFERROR(VLOOKUP('AUP Library'!A78,'Updated Quanities'!F:I,4,0),R78))","v":2.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A78,'Updated Quanities'!F:I,5,0),R78)=\"\",R78,IFERROR(VLOOKUP('AUP Library'!A78,'Updated Quanities'!F:I,5,0),R78))","v":2.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A78,'Updated Quanities'!F:I,6,0),R78)=\"\",R78,IFERROR(VLOOKUP('AUP Library'!A78,'Updated Quanities'!F:I,6,0),R78))","v":2.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A78,'Updated Quanities'!F:I,7,0),R78)=\"\",R78,IFERROR(VLOOKUP('AUP Library'!A78,'Updated Quanities'!F:I,7,0),R78))","v":2.15},2.15,{"$f":"IFERROR(VLOOKUP('AUP Library'!A78,'Updated Quanities'!F:G,4,0),R78)","v":2.15}]
[]
[]
["Concrete Roads"]
["303-01","Mineral Aggregate, Type A Base, Grading D","TON",19,19,19,19,19,19,19,19,19,19,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A82,'Updated Quanities'!F:I,4,0),R82)=\"\",R82,IFERROR(VLOOKUP('AUP Library'!A82,'Updated Quanities'!F:I,4,0),R82))","v":19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A82,'Updated Quanities'!F:I,5,0),R82)=\"\",R82,IFERROR(VLOOKUP('AUP Library'!A82,'Updated Quanities'!F:I,5,0),R82))","v":19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A82,'Updated Quanities'!F:I,6,0),R82)=\"\",R82,IFERROR(VLOOKUP('AUP Library'!A82,'Updated Quanities'!F:I,6,0),R82))","v":19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A82,'Updated Quanities'!F:I,7,0),R82)=\"\",R82,IFERROR(VLOOKUP('AUP Library'!A82,'Updated Quanities'!F:I,7,0),R82))","v":19},19,{"$f":"IFERROR(VLOOKUP('AUP Library'!A82,'Updated Quanities'!F:G,4,0),R82)","v":19}]
["313-03","Treated Permeable Base","SY",9.4,9.33,9.6300000000000008,11.58,11.58,14.47,16.47,12.88,15.82,18.309999999999999,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A83,'Updated Quanities'!F:I,4,0),R83)=\"\",R83,IFERROR(VLOOKUP('AUP Library'!A83,'Updated Quanities'!F:I,4,0),R83))","v":17.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A83,'Updated Quanities'!F:I,5,0),R83)=\"\",R83,IFERROR(VLOOKUP('AUP Library'!A83,'Updated Quanities'!F:I,5,0),R83))","v":17.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A83,'Updated Quanities'!F:I,6,0),R83)=\"\",R83,IFERROR(VLOOKUP('AUP Library'!A83,'Updated Quanities'!F:I,6,0),R83))","v":17.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A83,'Updated Quanities'!F:I,7,0),R83)=\"\",R83,IFERROR(VLOOKUP('AUP Library'!A83,'Updated Quanities'!F:I,7,0),R83))","v":17.88},17.88,{"$f":"IFERROR(VLOOKUP('AUP Library'!A83,'Updated Quanities'!F:G,4,0),R83)","v":17.88}]
["501-01.01","Portland Cement Concrete Pvmt 8\"","SY",68.86,68.86,68.86,68.86,68.86,68.86,68.86,68.86,68.86,68.86,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A84,'Updated Quanities'!F:I,4,0),R84)=\"\",R84,IFERROR(VLOOKUP('AUP Library'!A84,'Updated Quanities'!F:I,4,0),R84))","v":68.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A84,'Updated Quanities'!F:I,5,0),R84)=\"\",R84,IFERROR(VLOOKUP('AUP Library'!A84,'Updated Quanities'!F:I,5,0),R84))","v":68.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A84,'Updated Quanities'!F:I,6,0),R84)=\"\",R84,IFERROR(VLOOKUP('AUP Library'!A84,'Updated Quanities'!F:I,6,0),R84))","v":68.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A84,'Updated Quanities'!F:I,7,0),R84)=\"\",R84,IFERROR(VLOOKUP('AUP Library'!A84,'Updated Quanities'!F:I,7,0),R84))","v":68.86},68.86,{"$f":"IFERROR(VLOOKUP('AUP Library'!A84,'Updated Quanities'!F:G,4,0),R84)","v":68.86}]
["501-01.02","Portland Cement Concrete Pvmt 9\"","SY",85,85,85,85,85,85,85,85,85,85,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A85,'Updated Quanities'!F:I,4,0),R85)=\"\",R85,IFERROR(VLOOKUP('AUP Library'!A85,'Updated Quanities'!F:I,4,0),R85))","v":85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A85,'Updated Quanities'!F:I,5,0),R85)=\"\",R85,IFERROR(VLOOKUP('AUP Library'!A85,'Updated Quanities'!F:I,5,0),R85))","v":85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A85,'Updated Quanities'!F:I,6,0),R85)=\"\",R85,IFERROR(VLOOKUP('AUP Library'!A85,'Updated Quanities'!F:I,6,0),R85))","v":85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A85,'Updated Quanities'!F:I,7,0),R85)=\"\",R85,IFERROR(VLOOKUP('AUP Library'!A85,'Updated Quanities'!F:I,7,0),R85))","v":85},85,{"$f":"IFERROR(VLOOKUP('AUP Library'!A85,'Updated Quanities'!F:G,4,0),R85)","v":85}]
["501-01.03","Portland Cement Concrete Pvmt 10\"","SY",46.75,45.24,41.91,46.36,46.36,45.55,46.82,53.43,56.13,61.06,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A86,'Updated Quanities'!F:I,4,0),R86)=\"\",R86,IFERROR(VLOOKUP('AUP Library'!A86,'Updated Quanities'!F:I,4,0),R86))","v":38.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A86,'Updated Quanities'!F:I,5,0),R86)=\"\",R86,IFERROR(VLOOKUP('AUP Library'!A86,'Updated Quanities'!F:I,5,0),R86))","v":38.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A86,'Updated Quanities'!F:I,6,0),R86)=\"\",R86,IFERROR(VLOOKUP('AUP Library'!A86,'Updated Quanities'!F:I,6,0),R86))","v":38.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A86,'Updated Quanities'!F:I,7,0),R86)=\"\",R86,IFERROR(VLOOKUP('AUP Library'!A86,'Updated Quanities'!F:I,7,0),R86))","v":38.53},38.53,{"$f":"IFERROR(VLOOKUP('AUP Library'!A86,'Updated Quanities'!F:G,4,0),R86)","v":38.53}]
["501-01.04","Portland Cement Concrete Pvmt 11\"","SY",56.82,56.82,56.82,56.82,56.82,56.82,56.82,56.82,56.82,56.82,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A87,'Updated Quanities'!F:I,4,0),R87)=\"\",R87,IFERROR(VLOOKUP('AUP Library'!A87,'Updated Quanities'!F:I,4,0),R87))","v":56.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A87,'Updated Quanities'!F:I,5,0),R87)=\"\",R87,IFERROR(VLOOKUP('AUP Library'!A87,'Updated Quanities'!F:I,5,0),R87))","v":56.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A87,'Updated Quanities'!F:I,6,0),R87)=\"\",R87,IFERROR(VLOOKUP('AUP Library'!A87,'Updated Quanities'!F:I,6,0),R87))","v":56.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A87,'Updated Quanities'!F:I,7,0),R87)=\"\",R87,IFERROR(VLOOKUP('AUP Library'!A87,'Updated Quanities'!F:I,7,0),R87))","v":56.82},56.82,{"$f":"IFERROR(VLOOKUP('AUP Library'!A87,'Updated Quanities'!F:G,4,0),R87)","v":56.82}]
["502-01","CLEANING AND SEALING JOINTS","LF",3.76,3.76,3.76,3.76,3.76,3.76,3.76,3.76,3.76,3.76,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A88,'Updated Quanities'!F:I,4,0),R88)=\"\",R88,IFERROR(VLOOKUP('AUP Library'!A88,'Updated Quanities'!F:I,4,0),R88))","v":3.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A88,'Updated Quanities'!F:I,5,0),R88)=\"\",R88,IFERROR(VLOOKUP('AUP Library'!A88,'Updated Quanities'!F:I,5,0),R88))","v":3.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A88,'Updated Quanities'!F:I,6,0),R88)=\"\",R88,IFERROR(VLOOKUP('AUP Library'!A88,'Updated Quanities'!F:I,6,0),R88))","v":3.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A88,'Updated Quanities'!F:I,7,0),R88)=\"\",R88,IFERROR(VLOOKUP('AUP Library'!A88,'Updated Quanities'!F:I,7,0),R88))","v":3.76},3.76,{"$f":"IFERROR(VLOOKUP('AUP Library'!A88,'Updated Quanities'!F:G,4,0),R88)","v":3.76}]
["502-03.01","CEMENT GROUTING","CF",11.58,11.58,11.58,11.58,11.58,11.58,11.58,11.58,11.58,11.58,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A89,'Updated Quanities'!F:I,4,0),R89)=\"\",R89,IFERROR(VLOOKUP('AUP Library'!A89,'Updated Quanities'!F:I,4,0),R89))","v":11.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A89,'Updated Quanities'!F:I,5,0),R89)=\"\",R89,IFERROR(VLOOKUP('AUP Library'!A89,'Updated Quanities'!F:I,5,0),R89))","v":11.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A89,'Updated Quanities'!F:I,6,0),R89)=\"\",R89,IFERROR(VLOOKUP('AUP Library'!A89,'Updated Quanities'!F:I,6,0),R89))","v":11.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A89,'Updated Quanities'!F:I,7,0),R89)=\"\",R89,IFERROR(VLOOKUP('AUP Library'!A89,'Updated Quanities'!F:I,7,0),R89))","v":11.58},11.58,{"$f":"IFERROR(VLOOKUP('AUP Library'!A89,'Updated Quanities'!F:G,4,0),R89)","v":11.58}]
["502-03.10","FULL DEPTH P.C.C. PAVEMENT REPAIR","SY",340,340,340,340,340,340,340,340,340,340,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A90,'Updated Quanities'!F:I,4,0),R90)=\"\",R90,IFERROR(VLOOKUP('AUP Library'!A90,'Updated Quanities'!F:I,4,0),R90))","v":340},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A90,'Updated Quanities'!F:I,5,0),R90)=\"\",R90,IFERROR(VLOOKUP('AUP Library'!A90,'Updated Quanities'!F:I,5,0),R90))","v":340},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A90,'Updated Quanities'!F:I,6,0),R90)=\"\",R90,IFERROR(VLOOKUP('AUP Library'!A90,'Updated Quanities'!F:I,6,0),R90))","v":340},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A90,'Updated Quanities'!F:I,7,0),R90)=\"\",R90,IFERROR(VLOOKUP('AUP Library'!A90,'Updated Quanities'!F:I,7,0),R90))","v":340},340,{"$f":"IFERROR(VLOOKUP('AUP Library'!A90,'Updated Quanities'!F:G,4,0),R90)","v":340}]
["502-03.13","CONCRETE PAVEMENT REMOVAL","SY",7,7,7,7,7,7,7,7,7,7,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A91,'Updated Quanities'!F:I,4,0),R91)=\"\",R91,IFERROR(VLOOKUP('AUP Library'!A91,'Updated Quanities'!F:I,4,0),R91))","v":7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A91,'Updated Quanities'!F:I,5,0),R91)=\"\",R91,IFERROR(VLOOKUP('AUP Library'!A91,'Updated Quanities'!F:I,5,0),R91))","v":7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A91,'Updated Quanities'!F:I,6,0),R91)=\"\",R91,IFERROR(VLOOKUP('AUP Library'!A91,'Updated Quanities'!F:I,6,0),R91))","v":7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A91,'Updated Quanities'!F:I,7,0),R91)=\"\",R91,IFERROR(VLOOKUP('AUP Library'!A91,'Updated Quanities'!F:I,7,0),R91))","v":7},7,{"$f":"IFERROR(VLOOKUP('AUP Library'!A91,'Updated Quanities'!F:G,4,0),R91)","v":7}]
["502-04.01","SAWING CONCRETE PAVEMENT (FULL DEPTH)","LF",6.4,6.4,6.4,6.4,6.4,6.4,6.4,6.4,6.4,6.4,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A92,'Updated Quanities'!F:I,4,0),R92)=\"\",R92,IFERROR(VLOOKUP('AUP Library'!A92,'Updated Quanities'!F:I,4,0),R92))","v":6.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A92,'Updated Quanities'!F:I,5,0),R92)=\"\",R92,IFERROR(VLOOKUP('AUP Library'!A92,'Updated Quanities'!F:I,5,0),R92))","v":6.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A92,'Updated Quanities'!F:I,6,0),R92)=\"\",R92,IFERROR(VLOOKUP('AUP Library'!A92,'Updated Quanities'!F:I,6,0),R92))","v":6.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A92,'Updated Quanities'!F:I,7,0),R92)=\"\",R92,IFERROR(VLOOKUP('AUP Library'!A92,'Updated Quanities'!F:I,7,0),R92))","v":6.4},6.4,{"$f":"IFERROR(VLOOKUP('AUP Library'!A92,'Updated Quanities'!F:G,4,0),R92)","v":6.4}]
["502-04.02","LOAD TRANSFER DOWELS","EACH",9.6300000000000008,9.6300000000000008,9.6300000000000008,9.6300000000000008,9.6300000000000008,9.6300000000000008,9.6300000000000008,9.6300000000000008,9.6300000000000008,9.6300000000000008,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A93,'Updated Quanities'!F:I,4,0),R93)=\"\",R93,IFERROR(VLOOKUP('AUP Library'!A93,'Updated Quanities'!F:I,4,0),R93))","v":9.6300000000000008},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A93,'Updated Quanities'!F:I,5,0),R93)=\"\",R93,IFERROR(VLOOKUP('AUP Library'!A93,'Updated Quanities'!F:I,5,0),R93))","v":9.6300000000000008},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A93,'Updated Quanities'!F:I,6,0),R93)=\"\",R93,IFERROR(VLOOKUP('AUP Library'!A93,'Updated Quanities'!F:I,6,0),R93))","v":9.6300000000000008},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A93,'Updated Quanities'!F:I,7,0),R93)=\"\",R93,IFERROR(VLOOKUP('AUP Library'!A93,'Updated Quanities'!F:I,7,0),R93))","v":9.6300000000000008},9.6300000000000008,{"$f":"IFERROR(VLOOKUP('AUP Library'!A93,'Updated Quanities'!F:G,4,0),R93)","v":9.6300000000000008}]
["502-04.03","TRANSVERSE TIE-BARS","EACH",8.67,8.67,8.67,8.67,8.67,8.67,8.67,8.67,8.67,8.67,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A94,'Updated Quanities'!F:I,4,0),R94)=\"\",R94,IFERROR(VLOOKUP('AUP Library'!A94,'Updated Quanities'!F:I,4,0),R94))","v":8.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A94,'Updated Quanities'!F:I,5,0),R94)=\"\",R94,IFERROR(VLOOKUP('AUP Library'!A94,'Updated Quanities'!F:I,5,0),R94))","v":8.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A94,'Updated Quanities'!F:I,6,0),R94)=\"\",R94,IFERROR(VLOOKUP('AUP Library'!A94,'Updated Quanities'!F:I,6,0),R94))","v":8.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A94,'Updated Quanities'!F:I,7,0),R94)=\"\",R94,IFERROR(VLOOKUP('AUP Library'!A94,'Updated Quanities'!F:I,7,0),R94))","v":8.67},8.67,{"$f":"IFERROR(VLOOKUP('AUP Library'!A94,'Updated Quanities'!F:G,4,0),R94)","v":8.67}]
["502-07","SPALL REPAIR","SY",115,115,115,115,115,115,115,115,115,115,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A95,'Updated Quanities'!F:I,4,0),R95)=\"\",R95,IFERROR(VLOOKUP('AUP Library'!A95,'Updated Quanities'!F:I,4,0),R95))","v":115},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A95,'Updated Quanities'!F:I,5,0),R95)=\"\",R95,IFERROR(VLOOKUP('AUP Library'!A95,'Updated Quanities'!F:I,5,0),R95))","v":115},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A95,'Updated Quanities'!F:I,6,0),R95)=\"\",R95,IFERROR(VLOOKUP('AUP Library'!A95,'Updated Quanities'!F:I,6,0),R95))","v":115},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A95,'Updated Quanities'!F:I,7,0),R95)=\"\",R95,IFERROR(VLOOKUP('AUP Library'!A95,'Updated Quanities'!F:I,7,0),R95))","v":115},115,{"$f":"IFERROR(VLOOKUP('AUP Library'!A95,'Updated Quanities'!F:G,4,0),R95)","v":115}]
["502-08.01","RESEALING JOINTS (HOT POURED ELASTIC)","LF",1.42,1.42,1.42,1.42,1.42,1.42,1.42,1.42,1.42,1.42,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A96,'Updated Quanities'!F:I,4,0),R96)=\"\",R96,IFERROR(VLOOKUP('AUP Library'!A96,'Updated Quanities'!F:I,4,0),R96))","v":1.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A96,'Updated Quanities'!F:I,5,0),R96)=\"\",R96,IFERROR(VLOOKUP('AUP Library'!A96,'Updated Quanities'!F:I,5,0),R96))","v":1.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A96,'Updated Quanities'!F:I,6,0),R96)=\"\",R96,IFERROR(VLOOKUP('AUP Library'!A96,'Updated Quanities'!F:I,6,0),R96))","v":1.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A96,'Updated Quanities'!F:I,7,0),R96)=\"\",R96,IFERROR(VLOOKUP('AUP Library'!A96,'Updated Quanities'!F:I,7,0),R96))","v":1.42},1.42,{"$f":"IFERROR(VLOOKUP('AUP Library'!A96,'Updated Quanities'!F:G,4,0),R96)","v":1.42}]
["502-08.02","RESEALING JOINTS (SILICONE SEALANT)","LF",1.73,1.73,1.73,1.73,1.73,1.73,1.73,1.73,1.73,1.73,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A97,'Updated Quanities'!F:I,4,0),R97)=\"\",R97,IFERROR(VLOOKUP('AUP Library'!A97,'Updated Quanities'!F:I,4,0),R97))","v":1.73},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A97,'Updated Quanities'!F:I,5,0),R97)=\"\",R97,IFERROR(VLOOKUP('AUP Library'!A97,'Updated Quanities'!F:I,5,0),R97))","v":1.73},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A97,'Updated Quanities'!F:I,6,0),R97)=\"\",R97,IFERROR(VLOOKUP('AUP Library'!A97,'Updated Quanities'!F:I,6,0),R97))","v":1.73},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A97,'Updated Quanities'!F:I,7,0),R97)=\"\",R97,IFERROR(VLOOKUP('AUP Library'!A97,'Updated Quanities'!F:I,7,0),R97))","v":1.73},1.73,{"$f":"IFERROR(VLOOKUP('AUP Library'!A97,'Updated Quanities'!F:G,4,0),R97)","v":1.73}]
["502-08.03","SEALING SHOULDER JOINTS","LF",1.36,1.36,1.36,1.36,1.36,1.36,1.36,1.36,1.36,1.36,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A98,'Updated Quanities'!F:I,4,0),R98)=\"\",R98,IFERROR(VLOOKUP('AUP Library'!A98,'Updated Quanities'!F:I,4,0),R98))","v":1.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A98,'Updated Quanities'!F:I,5,0),R98)=\"\",R98,IFERROR(VLOOKUP('AUP Library'!A98,'Updated Quanities'!F:I,5,0),R98))","v":1.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A98,'Updated Quanities'!F:I,6,0),R98)=\"\",R98,IFERROR(VLOOKUP('AUP Library'!A98,'Updated Quanities'!F:I,6,0),R98))","v":1.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A98,'Updated Quanities'!F:I,7,0),R98)=\"\",R98,IFERROR(VLOOKUP('AUP Library'!A98,'Updated Quanities'!F:I,7,0),R98))","v":1.36},1.36,{"$f":"IFERROR(VLOOKUP('AUP Library'!A98,'Updated Quanities'!F:G,4,0),R98)","v":1.36}]
["502-08.04","SEALING RANDOM CRCK (HOT POURED ELASTIC)","LF",1.8,1.8,1.8,1.8,1.8,1.8,1.8,1.8,1.8,1.8,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A99,'Updated Quanities'!F:I,4,0),R99)=\"\",R99,IFERROR(VLOOKUP('AUP Library'!A99,'Updated Quanities'!F:I,4,0),R99))","v":1.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A99,'Updated Quanities'!F:I,5,0),R99)=\"\",R99,IFERROR(VLOOKUP('AUP Library'!A99,'Updated Quanities'!F:I,5,0),R99))","v":1.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A99,'Updated Quanities'!F:I,6,0),R99)=\"\",R99,IFERROR(VLOOKUP('AUP Library'!A99,'Updated Quanities'!F:I,6,0),R99))","v":1.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A99,'Updated Quanities'!F:I,7,0),R99)=\"\",R99,IFERROR(VLOOKUP('AUP Library'!A99,'Updated Quanities'!F:I,7,0),R99))","v":1.8},1.8,{"$f":"IFERROR(VLOOKUP('AUP Library'!A99,'Updated Quanities'!F:G,4,0),R99)","v":1.8}]
["502-08.07","SEALING RANDOM CRACKS (SILICONE SEALANT)","LF",3.64,3.64,3.64,3.64,3.64,3.64,3.64,3.64,3.64,3.64,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A100,'Updated Quanities'!F:I,4,0),R100)=\"\",R100,IFERROR(VLOOKUP('AUP Library'!A100,'Updated Quanities'!F:I,4,0),R100))","v":3.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A100,'Updated Quanities'!F:I,5,0),R100)=\"\",R100,IFERROR(VLOOKUP('AUP Library'!A100,'Updated Quanities'!F:I,5,0),R100))","v":3.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A100,'Updated Quanities'!F:I,6,0),R100)=\"\",R100,IFERROR(VLOOKUP('AUP Library'!A100,'Updated Quanities'!F:I,6,0),R100))","v":3.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A100,'Updated Quanities'!F:I,7,0),R100)=\"\",R100,IFERROR(VLOOKUP('AUP Library'!A100,'Updated Quanities'!F:I,7,0),R100))","v":3.64},3.64,{"$f":"IFERROR(VLOOKUP('AUP Library'!A100,'Updated Quanities'!F:G,4,0),R100)","v":3.64}]
["502-08.10","SAWING & RESEAL JOINTS (SILICONE SLNT)","LF",1.8,1.8,1.8,1.8,1.8,1.8,1.8,1.8,1.8,1.8,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A101,'Updated Quanities'!F:I,4,0),R101)=\"\",R101,IFERROR(VLOOKUP('AUP Library'!A101,'Updated Quanities'!F:I,4,0),R101))","v":1.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A101,'Updated Quanities'!F:I,5,0),R101)=\"\",R101,IFERROR(VLOOKUP('AUP Library'!A101,'Updated Quanities'!F:I,5,0),R101))","v":1.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A101,'Updated Quanities'!F:I,6,0),R101)=\"\",R101,IFERROR(VLOOKUP('AUP Library'!A101,'Updated Quanities'!F:I,6,0),R101))","v":1.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A101,'Updated Quanities'!F:I,7,0),R101)=\"\",R101,IFERROR(VLOOKUP('AUP Library'!A101,'Updated Quanities'!F:I,7,0),R101))","v":1.8},1.8,{"$f":"IFERROR(VLOOKUP('AUP Library'!A101,'Updated Quanities'!F:G,4,0),R101)","v":1.8}]
["502-08.23","CLEANING AND RESEALING JOINTS AND CRACKS","LF",2.25,2.25,2.25,2.25,2.25,2.25,2.25,2.25,2.25,2.25,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A102,'Updated Quanities'!F:I,4,0),R102)=\"\",R102,IFERROR(VLOOKUP('AUP Library'!A102,'Updated Quanities'!F:I,4,0),R102))","v":2.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A102,'Updated Quanities'!F:I,5,0),R102)=\"\",R102,IFERROR(VLOOKUP('AUP Library'!A102,'Updated Quanities'!F:I,5,0),R102))","v":2.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A102,'Updated Quanities'!F:I,6,0),R102)=\"\",R102,IFERROR(VLOOKUP('AUP Library'!A102,'Updated Quanities'!F:I,6,0),R102))","v":2.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A102,'Updated Quanities'!F:I,7,0),R102)=\"\",R102,IFERROR(VLOOKUP('AUP Library'!A102,'Updated Quanities'!F:I,7,0),R102))","v":2.25},2.25,{"$f":"IFERROR(VLOOKUP('AUP Library'!A102,'Updated Quanities'!F:G,4,0),R102)","v":2.25}]
["503-01","GRINDING CONCRETE PAVEMENT","SY",1.94,1.94,1.94,1.94,1.94,1.94,1.94,1.94,1.94,1.94,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A103,'Updated Quanities'!F:I,4,0),R103)=\"\",R103,IFERROR(VLOOKUP('AUP Library'!A103,'Updated Quanities'!F:I,4,0),R103))","v":1.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A103,'Updated Quanities'!F:I,5,0),R103)=\"\",R103,IFERROR(VLOOKUP('AUP Library'!A103,'Updated Quanities'!F:I,5,0),R103))","v":1.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A103,'Updated Quanities'!F:I,6,0),R103)=\"\",R103,IFERROR(VLOOKUP('AUP Library'!A103,'Updated Quanities'!F:I,6,0),R103))","v":1.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A103,'Updated Quanities'!F:I,7,0),R103)=\"\",R103,IFERROR(VLOOKUP('AUP Library'!A103,'Updated Quanities'!F:I,7,0),R103))","v":1.94},1.94,{"$f":"IFERROR(VLOOKUP('AUP Library'!A103,'Updated Quanities'!F:G,4,0),R103)","v":1.94}]
["503-01.01","MILLING CONCRETE PAVEMENT","SY",1.94,1.94,1.94,1.94,1.94,1.94,1.94,1.94,1.94,1.94,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A104,'Updated Quanities'!F:I,4,0),R104)=\"\",R104,IFERROR(VLOOKUP('AUP Library'!A104,'Updated Quanities'!F:I,4,0),R104))","v":1.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A104,'Updated Quanities'!F:I,5,0),R104)=\"\",R104,IFERROR(VLOOKUP('AUP Library'!A104,'Updated Quanities'!F:I,5,0),R104))","v":1.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A104,'Updated Quanities'!F:I,6,0),R104)=\"\",R104,IFERROR(VLOOKUP('AUP Library'!A104,'Updated Quanities'!F:I,6,0),R104))","v":1.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A104,'Updated Quanities'!F:I,7,0),R104)=\"\",R104,IFERROR(VLOOKUP('AUP Library'!A104,'Updated Quanities'!F:I,7,0),R104))","v":1.94},1.94,{"$f":"IFERROR(VLOOKUP('AUP Library'!A104,'Updated Quanities'!F:G,4,0),R104)","v":1.94}]
["503-60","RETROFIT DOWEL BAR","EACH",45.24,45.24,45.24,45.24,45.24,45.24,45.24,45.24,45.24,45.24,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A105,'Updated Quanities'!F:I,4,0),R105)=\"\",R105,IFERROR(VLOOKUP('AUP Library'!A105,'Updated Quanities'!F:I,4,0),R105))","v":45.24},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A105,'Updated Quanities'!F:I,5,0),R105)=\"\",R105,IFERROR(VLOOKUP('AUP Library'!A105,'Updated Quanities'!F:I,5,0),R105))","v":45.24},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A105,'Updated Quanities'!F:I,6,0),R105)=\"\",R105,IFERROR(VLOOKUP('AUP Library'!A105,'Updated Quanities'!F:I,6,0),R105))","v":45.24},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A105,'Updated Quanities'!F:I,7,0),R105)=\"\",R105,IFERROR(VLOOKUP('AUP Library'!A105,'Updated Quanities'!F:I,7,0),R105))","v":45.24},45.24,{"$f":"IFERROR(VLOOKUP('AUP Library'!A105,'Updated Quanities'!F:G,4,0),R105)","v":45.24}]
["504-01","CRACKING & SEATING CONCRETE PAVEMENT","SY",1.9,1.9,1.9,1.9,1.9,1.9,1.9,1.9,1.9,1.9,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A106,'Updated Quanities'!F:I,4,0),R106)=\"\",R106,IFERROR(VLOOKUP('AUP Library'!A106,'Updated Quanities'!F:I,4,0),R106))","v":1.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A106,'Updated Quanities'!F:I,5,0),R106)=\"\",R106,IFERROR(VLOOKUP('AUP Library'!A106,'Updated Quanities'!F:I,5,0),R106))","v":1.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A106,'Updated Quanities'!F:I,6,0),R106)=\"\",R106,IFERROR(VLOOKUP('AUP Library'!A106,'Updated Quanities'!F:I,6,0),R106))","v":1.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A106,'Updated Quanities'!F:I,7,0),R106)=\"\",R106,IFERROR(VLOOKUP('AUP Library'!A106,'Updated Quanities'!F:I,7,0),R106))","v":1.9},1.9,{"$f":"IFERROR(VLOOKUP('AUP Library'!A106,'Updated Quanities'!F:G,4,0),R106)","v":1.9}]
["604-01.01","Class A Concrete (Roadway)","CY",450.86,450.86,450.86,450.86,450.86,450.86,450.86,450.86,450.86,450.86,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A107,'Updated Quanities'!F:I,4,0),R107)=\"\",R107,IFERROR(VLOOKUP('AUP Library'!A107,'Updated Quanities'!F:I,4,0),R107))","v":450.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A107,'Updated Quanities'!F:I,5,0),R107)=\"\",R107,IFERROR(VLOOKUP('AUP Library'!A107,'Updated Quanities'!F:I,5,0),R107))","v":450.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A107,'Updated Quanities'!F:I,6,0),R107)=\"\",R107,IFERROR(VLOOKUP('AUP Library'!A107,'Updated Quanities'!F:I,6,0),R107))","v":450.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A107,'Updated Quanities'!F:I,7,0),R107)=\"\",R107,IFERROR(VLOOKUP('AUP Library'!A107,'Updated Quanities'!F:I,7,0),R107))","v":450.86},450.86,{"$f":"IFERROR(VLOOKUP('AUP Library'!A107,'Updated Quanities'!F:G,4,0),R107)","v":450.86}]
["604-01.02","Steel Bar Reinforcement (Roadway)","LB",0.93,0.93,0.93,0.93,0.93,0.93,0.93,0.93,0.93,0.93,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A108,'Updated Quanities'!F:I,4,0),R108)=\"\",R108,IFERROR(VLOOKUP('AUP Library'!A108,'Updated Quanities'!F:I,4,0),R108))","v":0.93},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A108,'Updated Quanities'!F:I,5,0),R108)=\"\",R108,IFERROR(VLOOKUP('AUP Library'!A108,'Updated Quanities'!F:I,5,0),R108))","v":0.93},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A108,'Updated Quanities'!F:I,6,0),R108)=\"\",R108,IFERROR(VLOOKUP('AUP Library'!A108,'Updated Quanities'!F:I,6,0),R108))","v":0.93},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A108,'Updated Quanities'!F:I,7,0),R108)=\"\",R108,IFERROR(VLOOKUP('AUP Library'!A108,'Updated Quanities'!F:I,7,0),R108))","v":0.93},0.93,{"$f":"IFERROR(VLOOKUP('AUP Library'!A108,'Updated Quanities'!F:G,4,0),R108)","v":0.93}]
[]
[]
["Drainage"]
["202-01.13","Removal of Pipe","LF",15,15,15,15,15,15,15,15,15,15,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A112,'Updated Quanities'!F:I,4,0),R112)=\"\",R112,IFERROR(VLOOKUP('AUP Library'!A112,'Updated Quanities'!F:I,4,0),R112))","v":15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A112,'Updated Quanities'!F:I,5,0),R112)=\"\",R112,IFERROR(VLOOKUP('AUP Library'!A112,'Updated Quanities'!F:I,5,0),R112))","v":15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A112,'Updated Quanities'!F:I,6,0),R112)=\"\",R112,IFERROR(VLOOKUP('AUP Library'!A112,'Updated Quanities'!F:I,6,0),R112))","v":15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A112,'Updated Quanities'!F:I,7,0),R112)=\"\",R112,IFERROR(VLOOKUP('AUP Library'!A112,'Updated Quanities'!F:I,7,0),R112))","v":15},15,{"$f":"IFERROR(VLOOKUP('AUP Library'!A112,'Updated Quanities'!F:G,4,0),R112)","v":15}]
["202-02.01","Removal of Pipe","LF",23.65,23.65,23.65,23.65,23.65,23.65,23.65,23.65,23.65,23.65,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A113,'Updated Quanities'!F:I,4,0),R113)=\"\",R113,IFERROR(VLOOKUP('AUP Library'!A113,'Updated Quanities'!F:I,4,0),R113))","v":23.65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A113,'Updated Quanities'!F:I,5,0),R113)=\"\",R113,IFERROR(VLOOKUP('AUP Library'!A113,'Updated Quanities'!F:I,5,0),R113))","v":23.65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A113,'Updated Quanities'!F:I,6,0),R113)=\"\",R113,IFERROR(VLOOKUP('AUP Library'!A113,'Updated Quanities'!F:I,6,0),R113))","v":23.65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A113,'Updated Quanities'!F:I,7,0),R113)=\"\",R113,IFERROR(VLOOKUP('AUP Library'!A113,'Updated Quanities'!F:I,7,0),R113))","v":23.65},23.65,{"$f":"IFERROR(VLOOKUP('AUP Library'!A113,'Updated Quanities'!F:G,4,0),R113)","v":23.65}]
["202-02.02","Removal of Pipe","LF",12.43,12.43,12.43,12.43,12.43,12.43,12.43,12.43,12.43,12.43,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A114,'Updated Quanities'!F:I,4,0),R114)=\"\",R114,IFERROR(VLOOKUP('AUP Library'!A114,'Updated Quanities'!F:I,4,0),R114))","v":12.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A114,'Updated Quanities'!F:I,5,0),R114)=\"\",R114,IFERROR(VLOOKUP('AUP Library'!A114,'Updated Quanities'!F:I,5,0),R114))","v":12.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A114,'Updated Quanities'!F:I,6,0),R114)=\"\",R114,IFERROR(VLOOKUP('AUP Library'!A114,'Updated Quanities'!F:I,6,0),R114))","v":12.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A114,'Updated Quanities'!F:I,7,0),R114)=\"\",R114,IFERROR(VLOOKUP('AUP Library'!A114,'Updated Quanities'!F:I,7,0),R114))","v":12.43},12.43,{"$f":"IFERROR(VLOOKUP('AUP Library'!A114,'Updated Quanities'!F:G,4,0),R114)","v":12.43}]
["202-02.03","Removal of Pipe","LF",10.4,10.4,10.4,10.4,10.4,10.4,10.4,10.4,10.4,10.4,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A115,'Updated Quanities'!F:I,4,0),R115)=\"\",R115,IFERROR(VLOOKUP('AUP Library'!A115,'Updated Quanities'!F:I,4,0),R115))","v":10.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A115,'Updated Quanities'!F:I,5,0),R115)=\"\",R115,IFERROR(VLOOKUP('AUP Library'!A115,'Updated Quanities'!F:I,5,0),R115))","v":10.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A115,'Updated Quanities'!F:I,6,0),R115)=\"\",R115,IFERROR(VLOOKUP('AUP Library'!A115,'Updated Quanities'!F:I,6,0),R115))","v":10.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A115,'Updated Quanities'!F:I,7,0),R115)=\"\",R115,IFERROR(VLOOKUP('AUP Library'!A115,'Updated Quanities'!F:I,7,0),R115))","v":10.4},10.4,{"$f":"IFERROR(VLOOKUP('AUP Library'!A115,'Updated Quanities'!F:G,4,0),R115)","v":10.4}]
["202-02.04","Removal of Pipe","LF",12.5,12.5,12.5,12.5,12.5,12.5,12.5,12.5,12.5,12.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A116,'Updated Quanities'!F:I,4,0),R116)=\"\",R116,IFERROR(VLOOKUP('AUP Library'!A116,'Updated Quanities'!F:I,4,0),R116))","v":12.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A116,'Updated Quanities'!F:I,5,0),R116)=\"\",R116,IFERROR(VLOOKUP('AUP Library'!A116,'Updated Quanities'!F:I,5,0),R116))","v":12.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A116,'Updated Quanities'!F:I,6,0),R116)=\"\",R116,IFERROR(VLOOKUP('AUP Library'!A116,'Updated Quanities'!F:I,6,0),R116))","v":12.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A116,'Updated Quanities'!F:I,7,0),R116)=\"\",R116,IFERROR(VLOOKUP('AUP Library'!A116,'Updated Quanities'!F:I,7,0),R116))","v":12.5},12.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A116,'Updated Quanities'!F:G,4,0),R116)","v":12.5}]
["202-02.05","Removal of Pipe","LF",12.65,12.65,12.65,12.65,12.65,12.65,12.65,12.65,12.65,12.65,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A117,'Updated Quanities'!F:I,4,0),R117)=\"\",R117,IFERROR(VLOOKUP('AUP Library'!A117,'Updated Quanities'!F:I,4,0),R117))","v":12.65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A117,'Updated Quanities'!F:I,5,0),R117)=\"\",R117,IFERROR(VLOOKUP('AUP Library'!A117,'Updated Quanities'!F:I,5,0),R117))","v":12.65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A117,'Updated Quanities'!F:I,6,0),R117)=\"\",R117,IFERROR(VLOOKUP('AUP Library'!A117,'Updated Quanities'!F:I,6,0),R117))","v":12.65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A117,'Updated Quanities'!F:I,7,0),R117)=\"\",R117,IFERROR(VLOOKUP('AUP Library'!A117,'Updated Quanities'!F:I,7,0),R117))","v":12.65},12.65,{"$f":"IFERROR(VLOOKUP('AUP Library'!A117,'Updated Quanities'!F:G,4,0),R117)","v":12.65}]
["202-02.06","Removal of Pipe","LF",9.4700000000000006,9.4700000000000006,9.4700000000000006,9.4700000000000006,9.4700000000000006,9.4700000000000006,9.4700000000000006,9.4700000000000006,9.4700000000000006,9.4700000000000006,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A118,'Updated Quanities'!F:I,4,0),R118)=\"\",R118,IFERROR(VLOOKUP('AUP Library'!A118,'Updated Quanities'!F:I,4,0),R118))","v":9.4700000000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A118,'Updated Quanities'!F:I,5,0),R118)=\"\",R118,IFERROR(VLOOKUP('AUP Library'!A118,'Updated Quanities'!F:I,5,0),R118))","v":9.4700000000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A118,'Updated Quanities'!F:I,6,0),R118)=\"\",R118,IFERROR(VLOOKUP('AUP Library'!A118,'Updated Quanities'!F:I,6,0),R118))","v":9.4700000000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A118,'Updated Quanities'!F:I,7,0),R118)=\"\",R118,IFERROR(VLOOKUP('AUP Library'!A118,'Updated Quanities'!F:I,7,0),R118))","v":9.4700000000000006},9.4700000000000006,{"$f":"IFERROR(VLOOKUP('AUP Library'!A118,'Updated Quanities'!F:G,4,0),R118)","v":9.4700000000000006}]
["202-02.07","Removal of Pipe","LF",10.88,10.88,10.88,10.88,10.88,10.88,10.88,10.88,10.88,10.88,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A119,'Updated Quanities'!F:I,4,0),R119)=\"\",R119,IFERROR(VLOOKUP('AUP Library'!A119,'Updated Quanities'!F:I,4,0),R119))","v":10.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A119,'Updated Quanities'!F:I,5,0),R119)=\"\",R119,IFERROR(VLOOKUP('AUP Library'!A119,'Updated Quanities'!F:I,5,0),R119))","v":10.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A119,'Updated Quanities'!F:I,6,0),R119)=\"\",R119,IFERROR(VLOOKUP('AUP Library'!A119,'Updated Quanities'!F:I,6,0),R119))","v":10.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A119,'Updated Quanities'!F:I,7,0),R119)=\"\",R119,IFERROR(VLOOKUP('AUP Library'!A119,'Updated Quanities'!F:I,7,0),R119))","v":10.88},10.88,{"$f":"IFERROR(VLOOKUP('AUP Library'!A119,'Updated Quanities'!F:G,4,0),R119)","v":10.88}]
["202-02.08","Removal of Pipe","LF",11.51,11.51,11.51,11.51,11.51,11.51,11.51,11.51,11.51,11.51,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A120,'Updated Quanities'!F:I,4,0),R120)=\"\",R120,IFERROR(VLOOKUP('AUP Library'!A120,'Updated Quanities'!F:I,4,0),R120))","v":11.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A120,'Updated Quanities'!F:I,5,0),R120)=\"\",R120,IFERROR(VLOOKUP('AUP Library'!A120,'Updated Quanities'!F:I,5,0),R120))","v":11.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A120,'Updated Quanities'!F:I,6,0),R120)=\"\",R120,IFERROR(VLOOKUP('AUP Library'!A120,'Updated Quanities'!F:I,6,0),R120))","v":11.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A120,'Updated Quanities'!F:I,7,0),R120)=\"\",R120,IFERROR(VLOOKUP('AUP Library'!A120,'Updated Quanities'!F:I,7,0),R120))","v":11.51},11.51,{"$f":"IFERROR(VLOOKUP('AUP Library'!A120,'Updated Quanities'!F:G,4,0),R120)","v":11.51}]
["202-02.09","Removal of Pipe","LF",16.170000000000002,16.170000000000002,16.170000000000002,16.170000000000002,16.170000000000002,16.170000000000002,16.170000000000002,16.170000000000002,16.170000000000002,16.170000000000002,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A121,'Updated Quanities'!F:I,4,0),R121)=\"\",R121,IFERROR(VLOOKUP('AUP Library'!A121,'Updated Quanities'!F:I,4,0),R121))","v":16.170000000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A121,'Updated Quanities'!F:I,5,0),R121)=\"\",R121,IFERROR(VLOOKUP('AUP Library'!A121,'Updated Quanities'!F:I,5,0),R121))","v":16.170000000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A121,'Updated Quanities'!F:I,6,0),R121)=\"\",R121,IFERROR(VLOOKUP('AUP Library'!A121,'Updated Quanities'!F:I,6,0),R121))","v":16.170000000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A121,'Updated Quanities'!F:I,7,0),R121)=\"\",R121,IFERROR(VLOOKUP('AUP Library'!A121,'Updated Quanities'!F:I,7,0),R121))","v":16.170000000000002},16.170000000000002,{"$f":"IFERROR(VLOOKUP('AUP Library'!A121,'Updated Quanities'!F:G,4,0),R121)","v":16.170000000000002}]
["202-02.10","Removal of Pipe","LF",15.6,15.6,15.6,15.6,15.6,15.6,15.6,15.6,15.6,15.6,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A122,'Updated Quanities'!F:I,4,0),R122)=\"\",R122,IFERROR(VLOOKUP('AUP Library'!A122,'Updated Quanities'!F:I,4,0),R122))","v":15.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A122,'Updated Quanities'!F:I,5,0),R122)=\"\",R122,IFERROR(VLOOKUP('AUP Library'!A122,'Updated Quanities'!F:I,5,0),R122))","v":15.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A122,'Updated Quanities'!F:I,6,0),R122)=\"\",R122,IFERROR(VLOOKUP('AUP Library'!A122,'Updated Quanities'!F:I,6,0),R122))","v":15.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A122,'Updated Quanities'!F:I,7,0),R122)=\"\",R122,IFERROR(VLOOKUP('AUP Library'!A122,'Updated Quanities'!F:I,7,0),R122))","v":15.6},15.6,{"$f":"IFERROR(VLOOKUP('AUP Library'!A122,'Updated Quanities'!F:G,4,0),R122)","v":15.6}]
["202-02.11","Removal of Pipe","LF",21.5,21.5,21.5,21.5,21.5,21.5,21.5,21.5,21.5,21.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A123,'Updated Quanities'!F:I,4,0),R123)=\"\",R123,IFERROR(VLOOKUP('AUP Library'!A123,'Updated Quanities'!F:I,4,0),R123))","v":21.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A123,'Updated Quanities'!F:I,5,0),R123)=\"\",R123,IFERROR(VLOOKUP('AUP Library'!A123,'Updated Quanities'!F:I,5,0),R123))","v":21.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A123,'Updated Quanities'!F:I,6,0),R123)=\"\",R123,IFERROR(VLOOKUP('AUP Library'!A123,'Updated Quanities'!F:I,6,0),R123))","v":21.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A123,'Updated Quanities'!F:I,7,0),R123)=\"\",R123,IFERROR(VLOOKUP('AUP Library'!A123,'Updated Quanities'!F:I,7,0),R123))","v":21.5},21.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A123,'Updated Quanities'!F:G,4,0),R123)","v":21.5}]
["202-02.12","Removal of Pipe","LF",13.36,13.36,13.36,13.36,13.36,13.36,13.36,13.36,13.36,13.36,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A124,'Updated Quanities'!F:I,4,0),R124)=\"\",R124,IFERROR(VLOOKUP('AUP Library'!A124,'Updated Quanities'!F:I,4,0),R124))","v":13.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A124,'Updated Quanities'!F:I,5,0),R124)=\"\",R124,IFERROR(VLOOKUP('AUP Library'!A124,'Updated Quanities'!F:I,5,0),R124))","v":13.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A124,'Updated Quanities'!F:I,6,0),R124)=\"\",R124,IFERROR(VLOOKUP('AUP Library'!A124,'Updated Quanities'!F:I,6,0),R124))","v":13.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A124,'Updated Quanities'!F:I,7,0),R124)=\"\",R124,IFERROR(VLOOKUP('AUP Library'!A124,'Updated Quanities'!F:I,7,0),R124))","v":13.36},13.36,{"$f":"IFERROR(VLOOKUP('AUP Library'!A124,'Updated Quanities'!F:G,4,0),R124)","v":13.36}]
["202-02.13","Removal of Pipe","LF",14.5,14.5,14.5,14.5,14.5,14.5,14.5,14.5,14.5,14.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A125,'Updated Quanities'!F:I,4,0),R125)=\"\",R125,IFERROR(VLOOKUP('AUP Library'!A125,'Updated Quanities'!F:I,4,0),R125))","v":14.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A125,'Updated Quanities'!F:I,5,0),R125)=\"\",R125,IFERROR(VLOOKUP('AUP Library'!A125,'Updated Quanities'!F:I,5,0),R125))","v":14.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A125,'Updated Quanities'!F:I,6,0),R125)=\"\",R125,IFERROR(VLOOKUP('AUP Library'!A125,'Updated Quanities'!F:I,6,0),R125))","v":14.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A125,'Updated Quanities'!F:I,7,0),R125)=\"\",R125,IFERROR(VLOOKUP('AUP Library'!A125,'Updated Quanities'!F:I,7,0),R125))","v":14.5},14.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A125,'Updated Quanities'!F:G,4,0),R125)","v":14.5}]
["202-02.14","Removal of Pipe","LF",7.5,7.5,7.5,7.5,7.5,7.5,7.5,7.5,7.5,7.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A126,'Updated Quanities'!F:I,4,0),R126)=\"\",R126,IFERROR(VLOOKUP('AUP Library'!A126,'Updated Quanities'!F:I,4,0),R126))","v":7.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A126,'Updated Quanities'!F:I,5,0),R126)=\"\",R126,IFERROR(VLOOKUP('AUP Library'!A126,'Updated Quanities'!F:I,5,0),R126))","v":7.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A126,'Updated Quanities'!F:I,6,0),R126)=\"\",R126,IFERROR(VLOOKUP('AUP Library'!A126,'Updated Quanities'!F:I,6,0),R126))","v":7.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A126,'Updated Quanities'!F:I,7,0),R126)=\"\",R126,IFERROR(VLOOKUP('AUP Library'!A126,'Updated Quanities'!F:I,7,0),R126))","v":7.5},7.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A126,'Updated Quanities'!F:G,4,0),R126)","v":7.5}]
["202-02.15","Removal of Pipe","LF",11.73,11.73,11.73,11.73,11.73,11.73,11.73,11.73,11.73,11.73,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A127,'Updated Quanities'!F:I,4,0),R127)=\"\",R127,IFERROR(VLOOKUP('AUP Library'!A127,'Updated Quanities'!F:I,4,0),R127))","v":11.73},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A127,'Updated Quanities'!F:I,5,0),R127)=\"\",R127,IFERROR(VLOOKUP('AUP Library'!A127,'Updated Quanities'!F:I,5,0),R127))","v":11.73},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A127,'Updated Quanities'!F:I,6,0),R127)=\"\",R127,IFERROR(VLOOKUP('AUP Library'!A127,'Updated Quanities'!F:I,6,0),R127))","v":11.73},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A127,'Updated Quanities'!F:I,7,0),R127)=\"\",R127,IFERROR(VLOOKUP('AUP Library'!A127,'Updated Quanities'!F:I,7,0),R127))","v":11.73},11.73,{"$f":"IFERROR(VLOOKUP('AUP Library'!A127,'Updated Quanities'!F:G,4,0),R127)","v":11.73}]
["202-02.16","Removal of Pipe","LF",11.74,11.74,11.74,11.74,11.74,11.74,11.74,11.74,11.74,11.74,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A128,'Updated Quanities'!F:I,4,0),R128)=\"\",R128,IFERROR(VLOOKUP('AUP Library'!A128,'Updated Quanities'!F:I,4,0),R128))","v":11.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A128,'Updated Quanities'!F:I,5,0),R128)=\"\",R128,IFERROR(VLOOKUP('AUP Library'!A128,'Updated Quanities'!F:I,5,0),R128))","v":11.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A128,'Updated Quanities'!F:I,6,0),R128)=\"\",R128,IFERROR(VLOOKUP('AUP Library'!A128,'Updated Quanities'!F:I,6,0),R128))","v":11.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A128,'Updated Quanities'!F:I,7,0),R128)=\"\",R128,IFERROR(VLOOKUP('AUP Library'!A128,'Updated Quanities'!F:I,7,0),R128))","v":11.74},11.74,{"$f":"IFERROR(VLOOKUP('AUP Library'!A128,'Updated Quanities'!F:G,4,0),R128)","v":11.74}]
["202-02.17","Removal of Pipe","LF",11.74,11.74,11.74,11.74,11.74,11.74,11.74,11.74,11.74,11.74,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A129,'Updated Quanities'!F:I,4,0),R129)=\"\",R129,IFERROR(VLOOKUP('AUP Library'!A129,'Updated Quanities'!F:I,4,0),R129))","v":11.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A129,'Updated Quanities'!F:I,5,0),R129)=\"\",R129,IFERROR(VLOOKUP('AUP Library'!A129,'Updated Quanities'!F:I,5,0),R129))","v":11.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A129,'Updated Quanities'!F:I,6,0),R129)=\"\",R129,IFERROR(VLOOKUP('AUP Library'!A129,'Updated Quanities'!F:I,6,0),R129))","v":11.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A129,'Updated Quanities'!F:I,7,0),R129)=\"\",R129,IFERROR(VLOOKUP('AUP Library'!A129,'Updated Quanities'!F:I,7,0),R129))","v":11.74},11.74,{"$f":"IFERROR(VLOOKUP('AUP Library'!A129,'Updated Quanities'!F:G,4,0),R129)","v":11.74}]
["202-02.18","Removal of Pipe","LF",11.72,11.72,11.72,11.72,11.72,11.72,11.72,11.72,11.72,11.72,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A130,'Updated Quanities'!F:I,4,0),R130)=\"\",R130,IFERROR(VLOOKUP('AUP Library'!A130,'Updated Quanities'!F:I,4,0),R130))","v":11.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A130,'Updated Quanities'!F:I,5,0),R130)=\"\",R130,IFERROR(VLOOKUP('AUP Library'!A130,'Updated Quanities'!F:I,5,0),R130))","v":11.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A130,'Updated Quanities'!F:I,6,0),R130)=\"\",R130,IFERROR(VLOOKUP('AUP Library'!A130,'Updated Quanities'!F:I,6,0),R130))","v":11.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A130,'Updated Quanities'!F:I,7,0),R130)=\"\",R130,IFERROR(VLOOKUP('AUP Library'!A130,'Updated Quanities'!F:I,7,0),R130))","v":11.72},11.72,{"$f":"IFERROR(VLOOKUP('AUP Library'!A130,'Updated Quanities'!F:G,4,0),R130)","v":11.72}]
["202-02.19","Removal of Pipe","LF",60,60,60,60,60,60,60,60,60,60,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A131,'Updated Quanities'!F:I,4,0),R131)=\"\",R131,IFERROR(VLOOKUP('AUP Library'!A131,'Updated Quanities'!F:I,4,0),R131))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A131,'Updated Quanities'!F:I,5,0),R131)=\"\",R131,IFERROR(VLOOKUP('AUP Library'!A131,'Updated Quanities'!F:I,5,0),R131))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A131,'Updated Quanities'!F:I,6,0),R131)=\"\",R131,IFERROR(VLOOKUP('AUP Library'!A131,'Updated Quanities'!F:I,6,0),R131))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A131,'Updated Quanities'!F:I,7,0),R131)=\"\",R131,IFERROR(VLOOKUP('AUP Library'!A131,'Updated Quanities'!F:I,7,0),R131))","v":60},60,{"$f":"IFERROR(VLOOKUP('AUP Library'!A131,'Updated Quanities'!F:G,4,0),R131)","v":60}]
["202-02.20","Removal of Pipe","LF",60,60,60,60,60,60,60,60,60,60,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A132,'Updated Quanities'!F:I,4,0),R132)=\"\",R132,IFERROR(VLOOKUP('AUP Library'!A132,'Updated Quanities'!F:I,4,0),R132))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A132,'Updated Quanities'!F:I,5,0),R132)=\"\",R132,IFERROR(VLOOKUP('AUP Library'!A132,'Updated Quanities'!F:I,5,0),R132))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A132,'Updated Quanities'!F:I,6,0),R132)=\"\",R132,IFERROR(VLOOKUP('AUP Library'!A132,'Updated Quanities'!F:I,6,0),R132))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A132,'Updated Quanities'!F:I,7,0),R132)=\"\",R132,IFERROR(VLOOKUP('AUP Library'!A132,'Updated Quanities'!F:I,7,0),R132))","v":60},60,{"$f":"IFERROR(VLOOKUP('AUP Library'!A132,'Updated Quanities'!F:G,4,0),R132)","v":60}]
["202-02.21","Removal of Pipe","LF",60,60,60,60,60,60,60,60,60,60,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A133,'Updated Quanities'!F:I,4,0),R133)=\"\",R133,IFERROR(VLOOKUP('AUP Library'!A133,'Updated Quanities'!F:I,4,0),R133))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A133,'Updated Quanities'!F:I,5,0),R133)=\"\",R133,IFERROR(VLOOKUP('AUP Library'!A133,'Updated Quanities'!F:I,5,0),R133))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A133,'Updated Quanities'!F:I,6,0),R133)=\"\",R133,IFERROR(VLOOKUP('AUP Library'!A133,'Updated Quanities'!F:I,6,0),R133))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A133,'Updated Quanities'!F:I,7,0),R133)=\"\",R133,IFERROR(VLOOKUP('AUP Library'!A133,'Updated Quanities'!F:I,7,0),R133))","v":60},60,{"$f":"IFERROR(VLOOKUP('AUP Library'!A133,'Updated Quanities'!F:G,4,0),R133)","v":60}]
["202-02.22","Removal of Pipe","LF",60,60,60,60,60,60,60,60,60,60,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A134,'Updated Quanities'!F:I,4,0),R134)=\"\",R134,IFERROR(VLOOKUP('AUP Library'!A134,'Updated Quanities'!F:I,4,0),R134))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A134,'Updated Quanities'!F:I,5,0),R134)=\"\",R134,IFERROR(VLOOKUP('AUP Library'!A134,'Updated Quanities'!F:I,5,0),R134))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A134,'Updated Quanities'!F:I,6,0),R134)=\"\",R134,IFERROR(VLOOKUP('AUP Library'!A134,'Updated Quanities'!F:I,6,0),R134))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A134,'Updated Quanities'!F:I,7,0),R134)=\"\",R134,IFERROR(VLOOKUP('AUP Library'!A134,'Updated Quanities'!F:I,7,0),R134))","v":60},60,{"$f":"IFERROR(VLOOKUP('AUP Library'!A134,'Updated Quanities'!F:G,4,0),R134)","v":60}]
["202-02.23","Removal of Pipe","LF",60,60,60,60,60,60,60,60,60,60,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A135,'Updated Quanities'!F:I,4,0),R135)=\"\",R135,IFERROR(VLOOKUP('AUP Library'!A135,'Updated Quanities'!F:I,4,0),R135))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A135,'Updated Quanities'!F:I,5,0),R135)=\"\",R135,IFERROR(VLOOKUP('AUP Library'!A135,'Updated Quanities'!F:I,5,0),R135))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A135,'Updated Quanities'!F:I,6,0),R135)=\"\",R135,IFERROR(VLOOKUP('AUP Library'!A135,'Updated Quanities'!F:I,6,0),R135))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A135,'Updated Quanities'!F:I,7,0),R135)=\"\",R135,IFERROR(VLOOKUP('AUP Library'!A135,'Updated Quanities'!F:I,7,0),R135))","v":60},60,{"$f":"IFERROR(VLOOKUP('AUP Library'!A135,'Updated Quanities'!F:G,4,0),R135)","v":60}]
["202-02.51","Remove Concrete Endwall & Pipe From Existing Driveway","LS",500,500,500,500,500,500,500,500,500,500,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A136,'Updated Quanities'!F:I,4,0),R136)=\"\",R136,IFERROR(VLOOKUP('AUP Library'!A136,'Updated Quanities'!F:I,4,0),R136))","v":500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A136,'Updated Quanities'!F:I,5,0),R136)=\"\",R136,IFERROR(VLOOKUP('AUP Library'!A136,'Updated Quanities'!F:I,5,0),R136))","v":500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A136,'Updated Quanities'!F:I,6,0),R136)=\"\",R136,IFERROR(VLOOKUP('AUP Library'!A136,'Updated Quanities'!F:I,6,0),R136))","v":500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A136,'Updated Quanities'!F:I,7,0),R136)=\"\",R136,IFERROR(VLOOKUP('AUP Library'!A136,'Updated Quanities'!F:I,7,0),R136))","v":500},500,{"$f":"IFERROR(VLOOKUP('AUP Library'!A136,'Updated Quanities'!F:G,4,0),R136)","v":500}]
["209-01.10","Erosion and Silt Control (Description)","LS",2500,2500,2500,2500,2500,2500,2500,2500,2500,2500,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A137,'Updated Quanities'!F:I,4,0),R137)=\"\",R137,IFERROR(VLOOKUP('AUP Library'!A137,'Updated Quanities'!F:I,4,0),R137))","v":2500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A137,'Updated Quanities'!F:I,5,0),R137)=\"\",R137,IFERROR(VLOOKUP('AUP Library'!A137,'Updated Quanities'!F:I,5,0),R137))","v":2500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A137,'Updated Quanities'!F:I,6,0),R137)=\"\",R137,IFERROR(VLOOKUP('AUP Library'!A137,'Updated Quanities'!F:I,6,0),R137))","v":2500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A137,'Updated Quanities'!F:I,7,0),R137)=\"\",R137,IFERROR(VLOOKUP('AUP Library'!A137,'Updated Quanities'!F:I,7,0),R137))","v":2500},2500,{"$f":"IFERROR(VLOOKUP('AUP Library'!A137,'Updated Quanities'!F:G,4,0),R137)","v":2500}]
["209-01.11","Construction Access","LS",10710,10710,10710,10710,10710,10710,10710,10710,10710,10710,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A138,'Updated Quanities'!F:I,4,0),R138)=\"\",R138,IFERROR(VLOOKUP('AUP Library'!A138,'Updated Quanities'!F:I,4,0),R138))","v":10710},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A138,'Updated Quanities'!F:I,5,0),R138)=\"\",R138,IFERROR(VLOOKUP('AUP Library'!A138,'Updated Quanities'!F:I,5,0),R138))","v":10710},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A138,'Updated Quanities'!F:I,6,0),R138)=\"\",R138,IFERROR(VLOOKUP('AUP Library'!A138,'Updated Quanities'!F:I,6,0),R138))","v":10710},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A138,'Updated Quanities'!F:I,7,0),R138)=\"\",R138,IFERROR(VLOOKUP('AUP Library'!A138,'Updated Quanities'!F:I,7,0),R138))","v":10710},10710,{"$f":"IFERROR(VLOOKUP('AUP Library'!A138,'Updated Quanities'!F:G,4,0),R138)","v":10710}]
["209-01.30","Temporary Compost Filter Berm","CY",16.59,16.59,16.59,16.59,16.59,16.59,16.59,16.59,16.59,16.59,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A139,'Updated Quanities'!F:I,4,0),R139)=\"\",R139,IFERROR(VLOOKUP('AUP Library'!A139,'Updated Quanities'!F:I,4,0),R139))","v":16.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A139,'Updated Quanities'!F:I,5,0),R139)=\"\",R139,IFERROR(VLOOKUP('AUP Library'!A139,'Updated Quanities'!F:I,5,0),R139))","v":16.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A139,'Updated Quanities'!F:I,6,0),R139)=\"\",R139,IFERROR(VLOOKUP('AUP Library'!A139,'Updated Quanities'!F:I,6,0),R139))","v":16.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A139,'Updated Quanities'!F:I,7,0),R139)=\"\",R139,IFERROR(VLOOKUP('AUP Library'!A139,'Updated Quanities'!F:I,7,0),R139))","v":16.59},16.59,{"$f":"IFERROR(VLOOKUP('AUP Library'!A139,'Updated Quanities'!F:G,4,0),R139)","v":16.59}]
["209-01.31","Temporary Mulch Filter Berm","CY",16.38,16.38,16.38,16.38,16.38,16.38,16.38,16.38,16.38,16.38,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A140,'Updated Quanities'!F:I,4,0),R140)=\"\",R140,IFERROR(VLOOKUP('AUP Library'!A140,'Updated Quanities'!F:I,4,0),R140))","v":16.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A140,'Updated Quanities'!F:I,5,0),R140)=\"\",R140,IFERROR(VLOOKUP('AUP Library'!A140,'Updated Quanities'!F:I,5,0),R140))","v":16.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A140,'Updated Quanities'!F:I,6,0),R140)=\"\",R140,IFERROR(VLOOKUP('AUP Library'!A140,'Updated Quanities'!F:I,6,0),R140))","v":16.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A140,'Updated Quanities'!F:I,7,0),R140)=\"\",R140,IFERROR(VLOOKUP('AUP Library'!A140,'Updated Quanities'!F:I,7,0),R140))","v":16.38},16.38,{"$f":"IFERROR(VLOOKUP('AUP Library'!A140,'Updated Quanities'!F:G,4,0),R140)","v":16.38}]
["209-02.02","6\" Temporary Slope Drain","LF",12,12,12,12,12,12,12,12,12,12,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A141,'Updated Quanities'!F:I,4,0),R141)=\"\",R141,IFERROR(VLOOKUP('AUP Library'!A141,'Updated Quanities'!F:I,4,0),R141))","v":12},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A141,'Updated Quanities'!F:I,5,0),R141)=\"\",R141,IFERROR(VLOOKUP('AUP Library'!A141,'Updated Quanities'!F:I,5,0),R141))","v":12},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A141,'Updated Quanities'!F:I,6,0),R141)=\"\",R141,IFERROR(VLOOKUP('AUP Library'!A141,'Updated Quanities'!F:I,6,0),R141))","v":12},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A141,'Updated Quanities'!F:I,7,0),R141)=\"\",R141,IFERROR(VLOOKUP('AUP Library'!A141,'Updated Quanities'!F:I,7,0),R141))","v":12},12,{"$f":"IFERROR(VLOOKUP('AUP Library'!A141,'Updated Quanities'!F:G,4,0),R141)","v":12}]
["209-02.03","8\" Temporary Slope Drain","LF",9.9600000000000009,9.9600000000000009,9.9600000000000009,9.9600000000000009,9.9600000000000009,9.9600000000000009,9.9600000000000009,9.9600000000000009,9.9600000000000009,9.9600000000000009,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A142,'Updated Quanities'!F:I,4,0),R142)=\"\",R142,IFERROR(VLOOKUP('AUP Library'!A142,'Updated Quanities'!F:I,4,0),R142))","v":9.9600000000000009},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A142,'Updated Quanities'!F:I,5,0),R142)=\"\",R142,IFERROR(VLOOKUP('AUP Library'!A142,'Updated Quanities'!F:I,5,0),R142))","v":9.9600000000000009},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A142,'Updated Quanities'!F:I,6,0),R142)=\"\",R142,IFERROR(VLOOKUP('AUP Library'!A142,'Updated Quanities'!F:I,6,0),R142))","v":9.9600000000000009},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A142,'Updated Quanities'!F:I,7,0),R142)=\"\",R142,IFERROR(VLOOKUP('AUP Library'!A142,'Updated Quanities'!F:I,7,0),R142))","v":9.9600000000000009},9.9600000000000009,{"$f":"IFERROR(VLOOKUP('AUP Library'!A142,'Updated Quanities'!F:G,4,0),R142)","v":9.9600000000000009}]
["209-02.04","10\" Temporary Slope Drain","LF",15.99,15.99,15.99,15.99,15.99,15.99,15.99,15.99,15.99,15.99,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A143,'Updated Quanities'!F:I,4,0),R143)=\"\",R143,IFERROR(VLOOKUP('AUP Library'!A143,'Updated Quanities'!F:I,4,0),R143))","v":15.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A143,'Updated Quanities'!F:I,5,0),R143)=\"\",R143,IFERROR(VLOOKUP('AUP Library'!A143,'Updated Quanities'!F:I,5,0),R143))","v":15.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A143,'Updated Quanities'!F:I,6,0),R143)=\"\",R143,IFERROR(VLOOKUP('AUP Library'!A143,'Updated Quanities'!F:I,6,0),R143))","v":15.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A143,'Updated Quanities'!F:I,7,0),R143)=\"\",R143,IFERROR(VLOOKUP('AUP Library'!A143,'Updated Quanities'!F:I,7,0),R143))","v":15.99},15.99,{"$f":"IFERROR(VLOOKUP('AUP Library'!A143,'Updated Quanities'!F:G,4,0),R143)","v":15.99}]
["209-02.05","12\" Temporary Slope Drain","LF",11.77,11.77,11.77,11.77,11.77,11.77,11.77,11.77,11.77,11.77,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A144,'Updated Quanities'!F:I,4,0),R144)=\"\",R144,IFERROR(VLOOKUP('AUP Library'!A144,'Updated Quanities'!F:I,4,0),R144))","v":11.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A144,'Updated Quanities'!F:I,5,0),R144)=\"\",R144,IFERROR(VLOOKUP('AUP Library'!A144,'Updated Quanities'!F:I,5,0),R144))","v":11.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A144,'Updated Quanities'!F:I,6,0),R144)=\"\",R144,IFERROR(VLOOKUP('AUP Library'!A144,'Updated Quanities'!F:I,6,0),R144))","v":11.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A144,'Updated Quanities'!F:I,7,0),R144)=\"\",R144,IFERROR(VLOOKUP('AUP Library'!A144,'Updated Quanities'!F:I,7,0),R144))","v":11.77},11.77,{"$f":"IFERROR(VLOOKUP('AUP Library'!A144,'Updated Quanities'!F:G,4,0),R144)","v":11.77}]
["209-02.06","15\" Temporary Slope Drain","LF",13.94,13.94,13.94,13.94,13.94,13.94,13.94,13.94,13.94,13.94,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A145,'Updated Quanities'!F:I,4,0),R145)=\"\",R145,IFERROR(VLOOKUP('AUP Library'!A145,'Updated Quanities'!F:I,4,0),R145))","v":13.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A145,'Updated Quanities'!F:I,5,0),R145)=\"\",R145,IFERROR(VLOOKUP('AUP Library'!A145,'Updated Quanities'!F:I,5,0),R145))","v":13.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A145,'Updated Quanities'!F:I,6,0),R145)=\"\",R145,IFERROR(VLOOKUP('AUP Library'!A145,'Updated Quanities'!F:I,6,0),R145))","v":13.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A145,'Updated Quanities'!F:I,7,0),R145)=\"\",R145,IFERROR(VLOOKUP('AUP Library'!A145,'Updated Quanities'!F:I,7,0),R145))","v":13.94},13.94,{"$f":"IFERROR(VLOOKUP('AUP Library'!A145,'Updated Quanities'!F:G,4,0),R145)","v":13.94}]
["209-02.07","18\" Temporary Slope Drain","LF",10.220000000000001,10.220000000000001,10.220000000000001,10.220000000000001,10.220000000000001,10.220000000000001,10.220000000000001,10.220000000000001,10.220000000000001,10.220000000000001,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A146,'Updated Quanities'!F:I,4,0),R146)=\"\",R146,IFERROR(VLOOKUP('AUP Library'!A146,'Updated Quanities'!F:I,4,0),R146))","v":10.220000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A146,'Updated Quanities'!F:I,5,0),R146)=\"\",R146,IFERROR(VLOOKUP('AUP Library'!A146,'Updated Quanities'!F:I,5,0),R146))","v":10.220000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A146,'Updated Quanities'!F:I,6,0),R146)=\"\",R146,IFERROR(VLOOKUP('AUP Library'!A146,'Updated Quanities'!F:I,6,0),R146))","v":10.220000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A146,'Updated Quanities'!F:I,7,0),R146)=\"\",R146,IFERROR(VLOOKUP('AUP Library'!A146,'Updated Quanities'!F:I,7,0),R146))","v":10.220000000000001},10.220000000000001,{"$f":"IFERROR(VLOOKUP('AUP Library'!A146,'Updated Quanities'!F:G,4,0),R146)","v":10.220000000000001}]
["209-03","Check Dams","SF",8.5,8.5,8.5,8.5,8.5,8.5,8.5,8.5,8.5,8.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A147,'Updated Quanities'!F:I,4,0),R147)=\"\",R147,IFERROR(VLOOKUP('AUP Library'!A147,'Updated Quanities'!F:I,4,0),R147))","v":8.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A147,'Updated Quanities'!F:I,5,0),R147)=\"\",R147,IFERROR(VLOOKUP('AUP Library'!A147,'Updated Quanities'!F:I,5,0),R147))","v":8.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A147,'Updated Quanities'!F:I,6,0),R147)=\"\",R147,IFERROR(VLOOKUP('AUP Library'!A147,'Updated Quanities'!F:I,6,0),R147))","v":8.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A147,'Updated Quanities'!F:I,7,0),R147)=\"\",R147,IFERROR(VLOOKUP('AUP Library'!A147,'Updated Quanities'!F:I,7,0),R147))","v":8.5},8.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A147,'Updated Quanities'!F:G,4,0),R147)","v":8.5}]
["209-03.20","Filter Sock (8 inch)","LF",4.03,4.03,4.03,4.03,4.03,4.03,4.03,4.03,4.03,4.03,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A148,'Updated Quanities'!F:I,4,0),R148)=\"\",R148,IFERROR(VLOOKUP('AUP Library'!A148,'Updated Quanities'!F:I,4,0),R148))","v":4.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A148,'Updated Quanities'!F:I,5,0),R148)=\"\",R148,IFERROR(VLOOKUP('AUP Library'!A148,'Updated Quanities'!F:I,5,0),R148))","v":4.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A148,'Updated Quanities'!F:I,6,0),R148)=\"\",R148,IFERROR(VLOOKUP('AUP Library'!A148,'Updated Quanities'!F:I,6,0),R148))","v":4.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A148,'Updated Quanities'!F:I,7,0),R148)=\"\",R148,IFERROR(VLOOKUP('AUP Library'!A148,'Updated Quanities'!F:I,7,0),R148))","v":4.03},4.03,{"$f":"IFERROR(VLOOKUP('AUP Library'!A148,'Updated Quanities'!F:G,4,0),R148)","v":4.03}]
["209-03.21","Filter Sock (12 inch)","LF",4.04,4.04,4.04,4.04,4.04,4.04,4.04,4.04,4.04,4.04,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A149,'Updated Quanities'!F:I,4,0),R149)=\"\",R149,IFERROR(VLOOKUP('AUP Library'!A149,'Updated Quanities'!F:I,4,0),R149))","v":4.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A149,'Updated Quanities'!F:I,5,0),R149)=\"\",R149,IFERROR(VLOOKUP('AUP Library'!A149,'Updated Quanities'!F:I,5,0),R149))","v":4.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A149,'Updated Quanities'!F:I,6,0),R149)=\"\",R149,IFERROR(VLOOKUP('AUP Library'!A149,'Updated Quanities'!F:I,6,0),R149))","v":4.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A149,'Updated Quanities'!F:I,7,0),R149)=\"\",R149,IFERROR(VLOOKUP('AUP Library'!A149,'Updated Quanities'!F:I,7,0),R149))","v":4.04},4.04,{"$f":"IFERROR(VLOOKUP('AUP Library'!A149,'Updated Quanities'!F:G,4,0),R149)","v":4.04}]
["209-03.22","Filter Sock (18 inch)","LF",5.0199999999999996,5.0199999999999996,5.0199999999999996,5.0199999999999996,5.0199999999999996,5.0199999999999996,5.0199999999999996,5.0199999999999996,5.0199999999999996,5.0199999999999996,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A150,'Updated Quanities'!F:I,4,0),R150)=\"\",R150,IFERROR(VLOOKUP('AUP Library'!A150,'Updated Quanities'!F:I,4,0),R150))","v":5.0199999999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A150,'Updated Quanities'!F:I,5,0),R150)=\"\",R150,IFERROR(VLOOKUP('AUP Library'!A150,'Updated Quanities'!F:I,5,0),R150))","v":5.0199999999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A150,'Updated Quanities'!F:I,6,0),R150)=\"\",R150,IFERROR(VLOOKUP('AUP Library'!A150,'Updated Quanities'!F:I,6,0),R150))","v":5.0199999999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A150,'Updated Quanities'!F:I,7,0),R150)=\"\",R150,IFERROR(VLOOKUP('AUP Library'!A150,'Updated Quanities'!F:I,7,0),R150))","v":5.0199999999999996},5.0199999999999996,{"$f":"IFERROR(VLOOKUP('AUP Library'!A150,'Updated Quanities'!F:G,4,0),R150)","v":5.0199999999999996}]
["209-03.23","Filter Sock (24 inch)","LF",5.63,5.63,5.63,5.63,5.63,5.63,5.63,5.63,5.63,5.63,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A151,'Updated Quanities'!F:I,4,0),R151)=\"\",R151,IFERROR(VLOOKUP('AUP Library'!A151,'Updated Quanities'!F:I,4,0),R151))","v":5.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A151,'Updated Quanities'!F:I,5,0),R151)=\"\",R151,IFERROR(VLOOKUP('AUP Library'!A151,'Updated Quanities'!F:I,5,0),R151))","v":5.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A151,'Updated Quanities'!F:I,6,0),R151)=\"\",R151,IFERROR(VLOOKUP('AUP Library'!A151,'Updated Quanities'!F:I,6,0),R151))","v":5.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A151,'Updated Quanities'!F:I,7,0),R151)=\"\",R151,IFERROR(VLOOKUP('AUP Library'!A151,'Updated Quanities'!F:I,7,0),R151))","v":5.63},5.63,{"$f":"IFERROR(VLOOKUP('AUP Library'!A151,'Updated Quanities'!F:G,4,0),R151)","v":5.63}]
["209-05","Sediment Removal","CY",7.6,7.6,7.6,7.6,7.6,7.6,7.6,7.6,7.6,7.6,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A152,'Updated Quanities'!F:I,4,0),R152)=\"\",R152,IFERROR(VLOOKUP('AUP Library'!A152,'Updated Quanities'!F:I,4,0),R152))","v":7.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A152,'Updated Quanities'!F:I,5,0),R152)=\"\",R152,IFERROR(VLOOKUP('AUP Library'!A152,'Updated Quanities'!F:I,5,0),R152))","v":7.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A152,'Updated Quanities'!F:I,6,0),R152)=\"\",R152,IFERROR(VLOOKUP('AUP Library'!A152,'Updated Quanities'!F:I,6,0),R152))","v":7.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A152,'Updated Quanities'!F:I,7,0),R152)=\"\",R152,IFERROR(VLOOKUP('AUP Library'!A152,'Updated Quanities'!F:I,7,0),R152))","v":7.6},7.6,{"$f":"IFERROR(VLOOKUP('AUP Library'!A152,'Updated Quanities'!F:G,4,0),R152)","v":7.6}]
["209-06","Baled Hay or Straw Erosion Checks","BALE",5,5,5,5,5,5,5,5,5,5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A153,'Updated Quanities'!F:I,4,0),R153)=\"\",R153,IFERROR(VLOOKUP('AUP Library'!A153,'Updated Quanities'!F:I,4,0),R153))","v":5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A153,'Updated Quanities'!F:I,5,0),R153)=\"\",R153,IFERROR(VLOOKUP('AUP Library'!A153,'Updated Quanities'!F:I,5,0),R153))","v":5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A153,'Updated Quanities'!F:I,6,0),R153)=\"\",R153,IFERROR(VLOOKUP('AUP Library'!A153,'Updated Quanities'!F:I,6,0),R153))","v":5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A153,'Updated Quanities'!F:I,7,0),R153)=\"\",R153,IFERROR(VLOOKUP('AUP Library'!A153,'Updated Quanities'!F:I,7,0),R153))","v":5},5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A153,'Updated Quanities'!F:G,4,0),R153)","v":5}]
["209-06.01","Permeable Plastic Ditch Berm","LF",8,8,8,8,8,8,8,8,8,8,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A154,'Updated Quanities'!F:I,4,0),R154)=\"\",R154,IFERROR(VLOOKUP('AUP Library'!A154,'Updated Quanities'!F:I,4,0),R154))","v":8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A154,'Updated Quanities'!F:I,5,0),R154)=\"\",R154,IFERROR(VLOOKUP('AUP Library'!A154,'Updated Quanities'!F:I,5,0),R154))","v":8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A154,'Updated Quanities'!F:I,6,0),R154)=\"\",R154,IFERROR(VLOOKUP('AUP Library'!A154,'Updated Quanities'!F:I,6,0),R154))","v":8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A154,'Updated Quanities'!F:I,7,0),R154)=\"\",R154,IFERROR(VLOOKUP('AUP Library'!A154,'Updated Quanities'!F:I,7,0),R154))","v":8},8,{"$f":"IFERROR(VLOOKUP('AUP Library'!A154,'Updated Quanities'!F:G,4,0),R154)","v":8}]
["209-06.02","12\" Dia Coir Log (Description)","LF",12.36,12.36,12.36,12.36,12.36,12.36,12.36,12.36,12.36,12.36,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A155,'Updated Quanities'!F:I,4,0),R155)=\"\",R155,IFERROR(VLOOKUP('AUP Library'!A155,'Updated Quanities'!F:I,4,0),R155))","v":12.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A155,'Updated Quanities'!F:I,5,0),R155)=\"\",R155,IFERROR(VLOOKUP('AUP Library'!A155,'Updated Quanities'!F:I,5,0),R155))","v":12.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A155,'Updated Quanities'!F:I,6,0),R155)=\"\",R155,IFERROR(VLOOKUP('AUP Library'!A155,'Updated Quanities'!F:I,6,0),R155))","v":12.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A155,'Updated Quanities'!F:I,7,0),R155)=\"\",R155,IFERROR(VLOOKUP('AUP Library'!A155,'Updated Quanities'!F:I,7,0),R155))","v":12.36},12.36,{"$f":"IFERROR(VLOOKUP('AUP Library'!A155,'Updated Quanities'!F:G,4,0),R155)","v":12.36}]
["209-06.03","16\" Dia Coir Log (Description)","LF",16.690000000000001,16.690000000000001,16.690000000000001,16.690000000000001,16.690000000000001,16.690000000000001,16.690000000000001,16.690000000000001,16.690000000000001,16.690000000000001,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A156,'Updated Quanities'!F:I,4,0),R156)=\"\",R156,IFERROR(VLOOKUP('AUP Library'!A156,'Updated Quanities'!F:I,4,0),R156))","v":16.690000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A156,'Updated Quanities'!F:I,5,0),R156)=\"\",R156,IFERROR(VLOOKUP('AUP Library'!A156,'Updated Quanities'!F:I,5,0),R156))","v":16.690000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A156,'Updated Quanities'!F:I,6,0),R156)=\"\",R156,IFERROR(VLOOKUP('AUP Library'!A156,'Updated Quanities'!F:I,6,0),R156))","v":16.690000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A156,'Updated Quanities'!F:I,7,0),R156)=\"\",R156,IFERROR(VLOOKUP('AUP Library'!A156,'Updated Quanities'!F:I,7,0),R156))","v":16.690000000000001},16.690000000000001,{"$f":"IFERROR(VLOOKUP('AUP Library'!A156,'Updated Quanities'!F:G,4,0),R156)","v":16.690000000000001}]
["209-06.05","Bailed Hay or Straw","BALE",10,10,10,10,10,10,10,10,10,10,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A157,'Updated Quanities'!F:I,4,0),R157)=\"\",R157,IFERROR(VLOOKUP('AUP Library'!A157,'Updated Quanities'!F:I,4,0),R157))","v":10},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A157,'Updated Quanities'!F:I,5,0),R157)=\"\",R157,IFERROR(VLOOKUP('AUP Library'!A157,'Updated Quanities'!F:I,5,0),R157))","v":10},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A157,'Updated Quanities'!F:I,6,0),R157)=\"\",R157,IFERROR(VLOOKUP('AUP Library'!A157,'Updated Quanities'!F:I,6,0),R157))","v":10},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A157,'Updated Quanities'!F:I,7,0),R157)=\"\",R157,IFERROR(VLOOKUP('AUP Library'!A157,'Updated Quanities'!F:I,7,0),R157))","v":10},10,{"$f":"IFERROR(VLOOKUP('AUP Library'!A157,'Updated Quanities'!F:G,4,0),R157)","v":10}]
["209-06.10","20 \" Wattle (Description)","LF",4,4,4,4,4,4,4,4,4,4,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A158,'Updated Quanities'!F:I,4,0),R158)=\"\",R158,IFERROR(VLOOKUP('AUP Library'!A158,'Updated Quanities'!F:I,4,0),R158))","v":4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A158,'Updated Quanities'!F:I,5,0),R158)=\"\",R158,IFERROR(VLOOKUP('AUP Library'!A158,'Updated Quanities'!F:I,5,0),R158))","v":4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A158,'Updated Quanities'!F:I,6,0),R158)=\"\",R158,IFERROR(VLOOKUP('AUP Library'!A158,'Updated Quanities'!F:I,6,0),R158))","v":4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A158,'Updated Quanities'!F:I,7,0),R158)=\"\",R158,IFERROR(VLOOKUP('AUP Library'!A158,'Updated Quanities'!F:I,7,0),R158))","v":4},4,{"$f":"IFERROR(VLOOKUP('AUP Library'!A158,'Updated Quanities'!F:G,4,0),R158)","v":4}]
["209-06.11","Wattle (Size)","LF",4.5,4.5,4.5,4.5,4.5,4.5,4.5,4.5,4.5,4.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A159,'Updated Quanities'!F:I,4,0),R159)=\"\",R159,IFERROR(VLOOKUP('AUP Library'!A159,'Updated Quanities'!F:I,4,0),R159))","v":4.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A159,'Updated Quanities'!F:I,5,0),R159)=\"\",R159,IFERROR(VLOOKUP('AUP Library'!A159,'Updated Quanities'!F:I,5,0),R159))","v":4.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A159,'Updated Quanities'!F:I,6,0),R159)=\"\",R159,IFERROR(VLOOKUP('AUP Library'!A159,'Updated Quanities'!F:I,6,0),R159))","v":4.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A159,'Updated Quanities'!F:I,7,0),R159)=\"\",R159,IFERROR(VLOOKUP('AUP Library'!A159,'Updated Quanities'!F:I,7,0),R159))","v":4.5},4.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A159,'Updated Quanities'!F:G,4,0),R159)","v":4.5}]
["209-06.12","9 IN Dia Coir Log (Description)","LF",20,20,20,20,20,20,20,20,20,20,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A160,'Updated Quanities'!F:I,4,0),R160)=\"\",R160,IFERROR(VLOOKUP('AUP Library'!A160,'Updated Quanities'!F:I,4,0),R160))","v":20},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A160,'Updated Quanities'!F:I,5,0),R160)=\"\",R160,IFERROR(VLOOKUP('AUP Library'!A160,'Updated Quanities'!F:I,5,0),R160))","v":20},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A160,'Updated Quanities'!F:I,6,0),R160)=\"\",R160,IFERROR(VLOOKUP('AUP Library'!A160,'Updated Quanities'!F:I,6,0),R160))","v":20},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A160,'Updated Quanities'!F:I,7,0),R160)=\"\",R160,IFERROR(VLOOKUP('AUP Library'!A160,'Updated Quanities'!F:I,7,0),R160))","v":20},20,{"$f":"IFERROR(VLOOKUP('AUP Library'!A160,'Updated Quanities'!F:G,4,0),R160)","v":20}]
["209-06.13","20\" Dia Coir Log (Description)","LF",40,40,40,40,40,40,40,40,40,40,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A161,'Updated Quanities'!F:I,4,0),R161)=\"\",R161,IFERROR(VLOOKUP('AUP Library'!A161,'Updated Quanities'!F:I,4,0),R161))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A161,'Updated Quanities'!F:I,5,0),R161)=\"\",R161,IFERROR(VLOOKUP('AUP Library'!A161,'Updated Quanities'!F:I,5,0),R161))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A161,'Updated Quanities'!F:I,6,0),R161)=\"\",R161,IFERROR(VLOOKUP('AUP Library'!A161,'Updated Quanities'!F:I,6,0),R161))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A161,'Updated Quanities'!F:I,7,0),R161)=\"\",R161,IFERROR(VLOOKUP('AUP Library'!A161,'Updated Quanities'!F:I,7,0),R161))","v":40},40,{"$f":"IFERROR(VLOOKUP('AUP Library'!A161,'Updated Quanities'!F:G,4,0),R161)","v":40}]
["209-08.02","Temporary Silt Fence (With Backing)","LF",3.52,3.52,3.52,3.52,3.52,3.52,3.52,3.52,3.52,3.52,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A162,'Updated Quanities'!F:I,4,0),R162)=\"\",R162,IFERROR(VLOOKUP('AUP Library'!A162,'Updated Quanities'!F:I,4,0),R162))","v":3.52},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A162,'Updated Quanities'!F:I,5,0),R162)=\"\",R162,IFERROR(VLOOKUP('AUP Library'!A162,'Updated Quanities'!F:I,5,0),R162))","v":3.52},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A162,'Updated Quanities'!F:I,6,0),R162)=\"\",R162,IFERROR(VLOOKUP('AUP Library'!A162,'Updated Quanities'!F:I,6,0),R162))","v":3.52},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A162,'Updated Quanities'!F:I,7,0),R162)=\"\",R162,IFERROR(VLOOKUP('AUP Library'!A162,'Updated Quanities'!F:I,7,0),R162))","v":3.52},3.52,{"$f":"IFERROR(VLOOKUP('AUP Library'!A162,'Updated Quanities'!F:G,4,0),R162)","v":3.52}]
["209-08.03","Temporary Silt Fence (Without Backing)","LF",1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A163,'Updated Quanities'!F:I,4,0),R163)=\"\",R163,IFERROR(VLOOKUP('AUP Library'!A163,'Updated Quanities'!F:I,4,0),R163))","v":1.1000000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A163,'Updated Quanities'!F:I,5,0),R163)=\"\",R163,IFERROR(VLOOKUP('AUP Library'!A163,'Updated Quanities'!F:I,5,0),R163))","v":1.1000000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A163,'Updated Quanities'!F:I,6,0),R163)=\"\",R163,IFERROR(VLOOKUP('AUP Library'!A163,'Updated Quanities'!F:I,6,0),R163))","v":1.1000000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A163,'Updated Quanities'!F:I,7,0),R163)=\"\",R163,IFERROR(VLOOKUP('AUP Library'!A163,'Updated Quanities'!F:I,7,0),R163))","v":1.1000000000000001},1.1000000000000001,{"$f":"IFERROR(VLOOKUP('AUP Library'!A163,'Updated Quanities'!F:G,4,0),R163)","v":1.1000000000000001}]
["209-08.05","Enhanced Silt Fence Check (V-Ditch)","EA",459.99,459.99,459.99,459.99,459.99,459.99,459.99,459.99,459.99,459.99,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A164,'Updated Quanities'!F:I,4,0),R164)=\"\",R164,IFERROR(VLOOKUP('AUP Library'!A164,'Updated Quanities'!F:I,4,0),R164))","v":459.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A164,'Updated Quanities'!F:I,5,0),R164)=\"\",R164,IFERROR(VLOOKUP('AUP Library'!A164,'Updated Quanities'!F:I,5,0),R164))","v":459.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A164,'Updated Quanities'!F:I,6,0),R164)=\"\",R164,IFERROR(VLOOKUP('AUP Library'!A164,'Updated Quanities'!F:I,6,0),R164))","v":459.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A164,'Updated Quanities'!F:I,7,0),R164)=\"\",R164,IFERROR(VLOOKUP('AUP Library'!A164,'Updated Quanities'!F:I,7,0),R164))","v":459.99},459.99,{"$f":"IFERROR(VLOOKUP('AUP Library'!A164,'Updated Quanities'!F:G,4,0),R164)","v":459.99}]
["209-08.07","Rock Check Dam","EA",186.64,186.64,186.64,186.64,186.64,186.64,186.64,186.64,186.64,186.64,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A165,'Updated Quanities'!F:I,4,0),R165)=\"\",R165,IFERROR(VLOOKUP('AUP Library'!A165,'Updated Quanities'!F:I,4,0),R165))","v":186.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A165,'Updated Quanities'!F:I,5,0),R165)=\"\",R165,IFERROR(VLOOKUP('AUP Library'!A165,'Updated Quanities'!F:I,5,0),R165))","v":186.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A165,'Updated Quanities'!F:I,6,0),R165)=\"\",R165,IFERROR(VLOOKUP('AUP Library'!A165,'Updated Quanities'!F:I,6,0),R165))","v":186.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A165,'Updated Quanities'!F:I,7,0),R165)=\"\",R165,IFERROR(VLOOKUP('AUP Library'!A165,'Updated Quanities'!F:I,7,0),R165))","v":186.64},186.64,{"$f":"IFERROR(VLOOKUP('AUP Library'!A165,'Updated Quanities'!F:G,4,0),R165)","v":186.64}]
["209-08.08","Enhanced Rock Check Dam","EA",492.59,492.59,492.59,492.59,492.59,492.59,492.59,492.59,492.59,492.59,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A166,'Updated Quanities'!F:I,4,0),R166)=\"\",R166,IFERROR(VLOOKUP('AUP Library'!A166,'Updated Quanities'!F:I,4,0),R166))","v":492.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A166,'Updated Quanities'!F:I,5,0),R166)=\"\",R166,IFERROR(VLOOKUP('AUP Library'!A166,'Updated Quanities'!F:I,5,0),R166))","v":492.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A166,'Updated Quanities'!F:I,6,0),R166)=\"\",R166,IFERROR(VLOOKUP('AUP Library'!A166,'Updated Quanities'!F:I,6,0),R166))","v":492.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A166,'Updated Quanities'!F:I,7,0),R166)=\"\",R166,IFERROR(VLOOKUP('AUP Library'!A166,'Updated Quanities'!F:I,7,0),R166))","v":492.59},492.59,{"$f":"IFERROR(VLOOKUP('AUP Library'!A166,'Updated Quanities'!F:G,4,0),R166)","v":492.59}]
["209-09.01","Sandbags","BAG",3.44,3.44,3.44,3.44,3.44,3.44,3.44,3.44,3.44,3.44,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A167,'Updated Quanities'!F:I,4,0),R167)=\"\",R167,IFERROR(VLOOKUP('AUP Library'!A167,'Updated Quanities'!F:I,4,0),R167))","v":3.44},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A167,'Updated Quanities'!F:I,5,0),R167)=\"\",R167,IFERROR(VLOOKUP('AUP Library'!A167,'Updated Quanities'!F:I,5,0),R167))","v":3.44},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A167,'Updated Quanities'!F:I,6,0),R167)=\"\",R167,IFERROR(VLOOKUP('AUP Library'!A167,'Updated Quanities'!F:I,6,0),R167))","v":3.44},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A167,'Updated Quanities'!F:I,7,0),R167)=\"\",R167,IFERROR(VLOOKUP('AUP Library'!A167,'Updated Quanities'!F:I,7,0),R167))","v":3.44},3.44,{"$f":"IFERROR(VLOOKUP('AUP Library'!A167,'Updated Quanities'!F:G,4,0),R167)","v":3.44}]
["209-09.02","Temporary Sediment Filter Bag (14'6\" x 2' x 13'3\")","Bag",348.15,348.15,348.15,348.15,348.15,348.15,348.15,348.15,348.15,348.15,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A168,'Updated Quanities'!F:I,4,0),R168)=\"\",R168,IFERROR(VLOOKUP('AUP Library'!A168,'Updated Quanities'!F:I,4,0),R168))","v":348.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A168,'Updated Quanities'!F:I,5,0),R168)=\"\",R168,IFERROR(VLOOKUP('AUP Library'!A168,'Updated Quanities'!F:I,5,0),R168))","v":348.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A168,'Updated Quanities'!F:I,6,0),R168)=\"\",R168,IFERROR(VLOOKUP('AUP Library'!A168,'Updated Quanities'!F:I,6,0),R168))","v":348.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A168,'Updated Quanities'!F:I,7,0),R168)=\"\",R168,IFERROR(VLOOKUP('AUP Library'!A168,'Updated Quanities'!F:I,7,0),R168))","v":348.15},348.15,{"$f":"IFERROR(VLOOKUP('AUP Library'!A168,'Updated Quanities'!F:G,4,0),R168)","v":348.15}]
["209-09.03","Sediment Filter Bag (15' x15')","EACH",472.59,472.59,472.59,472.59,472.59,472.59,472.59,472.59,472.59,472.59,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A169,'Updated Quanities'!F:I,4,0),R169)=\"\",R169,IFERROR(VLOOKUP('AUP Library'!A169,'Updated Quanities'!F:I,4,0),R169))","v":472.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A169,'Updated Quanities'!F:I,5,0),R169)=\"\",R169,IFERROR(VLOOKUP('AUP Library'!A169,'Updated Quanities'!F:I,5,0),R169))","v":472.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A169,'Updated Quanities'!F:I,6,0),R169)=\"\",R169,IFERROR(VLOOKUP('AUP Library'!A169,'Updated Quanities'!F:I,6,0),R169))","v":472.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A169,'Updated Quanities'!F:I,7,0),R169)=\"\",R169,IFERROR(VLOOKUP('AUP Library'!A169,'Updated Quanities'!F:I,7,0),R169))","v":472.59},472.59,{"$f":"IFERROR(VLOOKUP('AUP Library'!A169,'Updated Quanities'!F:G,4,0),R169)","v":472.59}]
["209-09.04","Sediment Filter Bag (15' x 10')","EACH",604.27,604.27,604.27,604.27,604.27,604.27,604.27,604.27,604.27,604.27,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A170,'Updated Quanities'!F:I,4,0),R170)=\"\",R170,IFERROR(VLOOKUP('AUP Library'!A170,'Updated Quanities'!F:I,4,0),R170))","v":604.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A170,'Updated Quanities'!F:I,5,0),R170)=\"\",R170,IFERROR(VLOOKUP('AUP Library'!A170,'Updated Quanities'!F:I,5,0),R170))","v":604.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A170,'Updated Quanities'!F:I,6,0),R170)=\"\",R170,IFERROR(VLOOKUP('AUP Library'!A170,'Updated Quanities'!F:I,6,0),R170))","v":604.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A170,'Updated Quanities'!F:I,7,0),R170)=\"\",R170,IFERROR(VLOOKUP('AUP Library'!A170,'Updated Quanities'!F:I,7,0),R170))","v":604.27},604.27,{"$f":"IFERROR(VLOOKUP('AUP Library'!A170,'Updated Quanities'!F:G,4,0),R170)","v":604.27}]
["209-09.20","Polymer Flocculent","LB",8,8,8,8,8,8,8,8,8,8,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A171,'Updated Quanities'!F:I,4,0),R171)=\"\",R171,IFERROR(VLOOKUP('AUP Library'!A171,'Updated Quanities'!F:I,4,0),R171))","v":8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A171,'Updated Quanities'!F:I,5,0),R171)=\"\",R171,IFERROR(VLOOKUP('AUP Library'!A171,'Updated Quanities'!F:I,5,0),R171))","v":8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A171,'Updated Quanities'!F:I,6,0),R171)=\"\",R171,IFERROR(VLOOKUP('AUP Library'!A171,'Updated Quanities'!F:I,6,0),R171))","v":8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A171,'Updated Quanities'!F:I,7,0),R171)=\"\",R171,IFERROR(VLOOKUP('AUP Library'!A171,'Updated Quanities'!F:I,7,0),R171))","v":8},8,{"$f":"IFERROR(VLOOKUP('AUP Library'!A171,'Updated Quanities'!F:G,4,0),R171)","v":8}]
["209-09.21","Polyachlamide Gel Logs","EA",184.79,184.79,184.79,184.79,184.79,184.79,184.79,184.79,184.79,184.79,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A172,'Updated Quanities'!F:I,4,0),R172)=\"\",R172,IFERROR(VLOOKUP('AUP Library'!A172,'Updated Quanities'!F:I,4,0),R172))","v":184.79},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A172,'Updated Quanities'!F:I,5,0),R172)=\"\",R172,IFERROR(VLOOKUP('AUP Library'!A172,'Updated Quanities'!F:I,5,0),R172))","v":184.79},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A172,'Updated Quanities'!F:I,6,0),R172)=\"\",R172,IFERROR(VLOOKUP('AUP Library'!A172,'Updated Quanities'!F:I,6,0),R172))","v":184.79},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A172,'Updated Quanities'!F:I,7,0),R172)=\"\",R172,IFERROR(VLOOKUP('AUP Library'!A172,'Updated Quanities'!F:I,7,0),R172))","v":184.79},184.79,{"$f":"IFERROR(VLOOKUP('AUP Library'!A172,'Updated Quanities'!F:G,4,0),R172)","v":184.79}]
["209-09.22","Polyachlamide Powder","LB",12.08,12.08,12.08,12.08,12.08,12.08,12.08,12.08,12.08,12.08,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A173,'Updated Quanities'!F:I,4,0),R173)=\"\",R173,IFERROR(VLOOKUP('AUP Library'!A173,'Updated Quanities'!F:I,4,0),R173))","v":12.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A173,'Updated Quanities'!F:I,5,0),R173)=\"\",R173,IFERROR(VLOOKUP('AUP Library'!A173,'Updated Quanities'!F:I,5,0),R173))","v":12.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A173,'Updated Quanities'!F:I,6,0),R173)=\"\",R173,IFERROR(VLOOKUP('AUP Library'!A173,'Updated Quanities'!F:I,6,0),R173))","v":12.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A173,'Updated Quanities'!F:I,7,0),R173)=\"\",R173,IFERROR(VLOOKUP('AUP Library'!A173,'Updated Quanities'!F:I,7,0),R173))","v":12.08},12.08,{"$f":"IFERROR(VLOOKUP('AUP Library'!A173,'Updated Quanities'!F:G,4,0),R173)","v":12.08}]
["209-09.23","Polyacrylamide Liquid","LB",55.01,55.01,55.01,55.01,55.01,55.01,55.01,55.01,55.01,55.01,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A174,'Updated Quanities'!F:I,4,0),R174)=\"\",R174,IFERROR(VLOOKUP('AUP Library'!A174,'Updated Quanities'!F:I,4,0),R174))","v":55.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A174,'Updated Quanities'!F:I,5,0),R174)=\"\",R174,IFERROR(VLOOKUP('AUP Library'!A174,'Updated Quanities'!F:I,5,0),R174))","v":55.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A174,'Updated Quanities'!F:I,6,0),R174)=\"\",R174,IFERROR(VLOOKUP('AUP Library'!A174,'Updated Quanities'!F:I,6,0),R174))","v":55.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A174,'Updated Quanities'!F:I,7,0),R174)=\"\",R174,IFERROR(VLOOKUP('AUP Library'!A174,'Updated Quanities'!F:I,7,0),R174))","v":55.01},55.01,{"$f":"IFERROR(VLOOKUP('AUP Library'!A174,'Updated Quanities'!F:G,4,0),R174)","v":55.01}]
["209-09.24","Jute Mesh Fabric","SY",1.65,1.65,1.65,1.65,1.65,1.65,1.65,1.65,1.65,1.65,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A175,'Updated Quanities'!F:I,4,0),R175)=\"\",R175,IFERROR(VLOOKUP('AUP Library'!A175,'Updated Quanities'!F:I,4,0),R175))","v":1.65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A175,'Updated Quanities'!F:I,5,0),R175)=\"\",R175,IFERROR(VLOOKUP('AUP Library'!A175,'Updated Quanities'!F:I,5,0),R175))","v":1.65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A175,'Updated Quanities'!F:I,6,0),R175)=\"\",R175,IFERROR(VLOOKUP('AUP Library'!A175,'Updated Quanities'!F:I,6,0),R175))","v":1.65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A175,'Updated Quanities'!F:I,7,0),R175)=\"\",R175,IFERROR(VLOOKUP('AUP Library'!A175,'Updated Quanities'!F:I,7,0),R175))","v":1.65},1.65,{"$f":"IFERROR(VLOOKUP('AUP Library'!A175,'Updated Quanities'!F:G,4,0),R175)","v":1.65}]
["209-09.35","Silt Saver Inlet Protection","EACH",500,500,500,500,500,500,500,500,500,500,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A176,'Updated Quanities'!F:I,4,0),R176)=\"\",R176,IFERROR(VLOOKUP('AUP Library'!A176,'Updated Quanities'!F:I,4,0),R176))","v":500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A176,'Updated Quanities'!F:I,5,0),R176)=\"\",R176,IFERROR(VLOOKUP('AUP Library'!A176,'Updated Quanities'!F:I,5,0),R176))","v":500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A176,'Updated Quanities'!F:I,6,0),R176)=\"\",R176,IFERROR(VLOOKUP('AUP Library'!A176,'Updated Quanities'!F:I,6,0),R176))","v":500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A176,'Updated Quanities'!F:I,7,0),R176)=\"\",R176,IFERROR(VLOOKUP('AUP Library'!A176,'Updated Quanities'!F:I,7,0),R176))","v":500},500,{"$f":"IFERROR(VLOOKUP('AUP Library'!A176,'Updated Quanities'!F:G,4,0),R176)","v":500}]
["209-09.40","Curb Inlet Protection (Type 1)","EACH",492.88,492.88,492.88,492.88,492.88,492.88,492.88,492.88,492.88,492.88,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A177,'Updated Quanities'!F:I,4,0),R177)=\"\",R177,IFERROR(VLOOKUP('AUP Library'!A177,'Updated Quanities'!F:I,4,0),R177))","v":492.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A177,'Updated Quanities'!F:I,5,0),R177)=\"\",R177,IFERROR(VLOOKUP('AUP Library'!A177,'Updated Quanities'!F:I,5,0),R177))","v":492.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A177,'Updated Quanities'!F:I,6,0),R177)=\"\",R177,IFERROR(VLOOKUP('AUP Library'!A177,'Updated Quanities'!F:I,6,0),R177))","v":492.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A177,'Updated Quanities'!F:I,7,0),R177)=\"\",R177,IFERROR(VLOOKUP('AUP Library'!A177,'Updated Quanities'!F:I,7,0),R177))","v":492.88},492.88,{"$f":"IFERROR(VLOOKUP('AUP Library'!A177,'Updated Quanities'!F:G,4,0),R177)","v":492.88}]
["209-09.41","Curb Inlet Protection (Type 2)","EACH",261.25,261.25,261.25,261.25,261.25,261.25,261.25,261.25,261.25,261.25,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A178,'Updated Quanities'!F:I,4,0),R178)=\"\",R178,IFERROR(VLOOKUP('AUP Library'!A178,'Updated Quanities'!F:I,4,0),R178))","v":261.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A178,'Updated Quanities'!F:I,5,0),R178)=\"\",R178,IFERROR(VLOOKUP('AUP Library'!A178,'Updated Quanities'!F:I,5,0),R178))","v":261.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A178,'Updated Quanities'!F:I,6,0),R178)=\"\",R178,IFERROR(VLOOKUP('AUP Library'!A178,'Updated Quanities'!F:I,6,0),R178))","v":261.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A178,'Updated Quanities'!F:I,7,0),R178)=\"\",R178,IFERROR(VLOOKUP('AUP Library'!A178,'Updated Quanities'!F:I,7,0),R178))","v":261.25},261.25,{"$f":"IFERROR(VLOOKUP('AUP Library'!A178,'Updated Quanities'!F:G,4,0),R178)","v":261.25}]
["209-09.42","Curb Inlet Protection (Type 3)","EACH",249,249,249,249,249,249,249,249,249,249,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A179,'Updated Quanities'!F:I,4,0),R179)=\"\",R179,IFERROR(VLOOKUP('AUP Library'!A179,'Updated Quanities'!F:I,4,0),R179))","v":249},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A179,'Updated Quanities'!F:I,5,0),R179)=\"\",R179,IFERROR(VLOOKUP('AUP Library'!A179,'Updated Quanities'!F:I,5,0),R179))","v":249},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A179,'Updated Quanities'!F:I,6,0),R179)=\"\",R179,IFERROR(VLOOKUP('AUP Library'!A179,'Updated Quanities'!F:I,6,0),R179))","v":249},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A179,'Updated Quanities'!F:I,7,0),R179)=\"\",R179,IFERROR(VLOOKUP('AUP Library'!A179,'Updated Quanities'!F:I,7,0),R179))","v":249},249,{"$f":"IFERROR(VLOOKUP('AUP Library'!A179,'Updated Quanities'!F:G,4,0),R179)","v":249}]
["209-09.43","Curb Inlet Protection (Type 4)","EACH",154.77000000000001,154.77000000000001,154.77000000000001,154.77000000000001,154.77000000000001,154.77000000000001,154.77000000000001,154.77000000000001,154.77000000000001,154.77000000000001,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A180,'Updated Quanities'!F:I,4,0),R180)=\"\",R180,IFERROR(VLOOKUP('AUP Library'!A180,'Updated Quanities'!F:I,4,0),R180))","v":154.77000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A180,'Updated Quanities'!F:I,5,0),R180)=\"\",R180,IFERROR(VLOOKUP('AUP Library'!A180,'Updated Quanities'!F:I,5,0),R180))","v":154.77000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A180,'Updated Quanities'!F:I,6,0),R180)=\"\",R180,IFERROR(VLOOKUP('AUP Library'!A180,'Updated Quanities'!F:I,6,0),R180))","v":154.77000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A180,'Updated Quanities'!F:I,7,0),R180)=\"\",R180,IFERROR(VLOOKUP('AUP Library'!A180,'Updated Quanities'!F:I,7,0),R180))","v":154.77000000000001},154.77000000000001,{"$f":"IFERROR(VLOOKUP('AUP Library'!A180,'Updated Quanities'!F:G,4,0),R180)","v":154.77000000000001}]
["209-10.01","Temporary Dewatering Structure","CY",25,25,25,25,25,25,25,25,25,25,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A181,'Updated Quanities'!F:I,4,0),R181)=\"\",R181,IFERROR(VLOOKUP('AUP Library'!A181,'Updated Quanities'!F:I,4,0),R181))","v":25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A181,'Updated Quanities'!F:I,5,0),R181)=\"\",R181,IFERROR(VLOOKUP('AUP Library'!A181,'Updated Quanities'!F:I,5,0),R181))","v":25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A181,'Updated Quanities'!F:I,6,0),R181)=\"\",R181,IFERROR(VLOOKUP('AUP Library'!A181,'Updated Quanities'!F:I,6,0),R181))","v":25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A181,'Updated Quanities'!F:I,7,0),R181)=\"\",R181,IFERROR(VLOOKUP('AUP Library'!A181,'Updated Quanities'!F:I,7,0),R181))","v":25},25,{"$f":"IFERROR(VLOOKUP('AUP Library'!A181,'Updated Quanities'!F:G,4,0),R181)","v":25}]
["209-10.02","8 IN Skimmer w/ 6IN Head","EACH",2500,2500,2500,2500,2500,2500,2500,2500,2500,2500,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A182,'Updated Quanities'!F:I,4,0),R182)=\"\",R182,IFERROR(VLOOKUP('AUP Library'!A182,'Updated Quanities'!F:I,4,0),R182))","v":2500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A182,'Updated Quanities'!F:I,5,0),R182)=\"\",R182,IFERROR(VLOOKUP('AUP Library'!A182,'Updated Quanities'!F:I,5,0),R182))","v":2500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A182,'Updated Quanities'!F:I,6,0),R182)=\"\",R182,IFERROR(VLOOKUP('AUP Library'!A182,'Updated Quanities'!F:I,6,0),R182))","v":2500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A182,'Updated Quanities'!F:I,7,0),R182)=\"\",R182,IFERROR(VLOOKUP('AUP Library'!A182,'Updated Quanities'!F:I,7,0),R182))","v":2500},2500,{"$f":"IFERROR(VLOOKUP('AUP Library'!A182,'Updated Quanities'!F:G,4,0),R182)","v":2500}]
["209-10.03","Portable Water/Sediment Barrier","LF",224,224,224,224,224,224,224,224,224,224,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A183,'Updated Quanities'!F:I,4,0),R183)=\"\",R183,IFERROR(VLOOKUP('AUP Library'!A183,'Updated Quanities'!F:I,4,0),R183))","v":224},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A183,'Updated Quanities'!F:I,5,0),R183)=\"\",R183,IFERROR(VLOOKUP('AUP Library'!A183,'Updated Quanities'!F:I,5,0),R183))","v":224},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A183,'Updated Quanities'!F:I,6,0),R183)=\"\",R183,IFERROR(VLOOKUP('AUP Library'!A183,'Updated Quanities'!F:I,6,0),R183))","v":224},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A183,'Updated Quanities'!F:I,7,0),R183)=\"\",R183,IFERROR(VLOOKUP('AUP Library'!A183,'Updated Quanities'!F:I,7,0),R183))","v":224},224,{"$f":"IFERROR(VLOOKUP('AUP Library'!A183,'Updated Quanities'!F:G,4,0),R183)","v":224}]
["209-10.20","Temporary Sediment Trap","CY",6.64,6.64,6.64,6.64,6.64,6.64,6.64,6.64,6.64,6.64,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A184,'Updated Quanities'!F:I,4,0),R184)=\"\",R184,IFERROR(VLOOKUP('AUP Library'!A184,'Updated Quanities'!F:I,4,0),R184))","v":6.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A184,'Updated Quanities'!F:I,5,0),R184)=\"\",R184,IFERROR(VLOOKUP('AUP Library'!A184,'Updated Quanities'!F:I,5,0),R184))","v":6.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A184,'Updated Quanities'!F:I,6,0),R184)=\"\",R184,IFERROR(VLOOKUP('AUP Library'!A184,'Updated Quanities'!F:I,6,0),R184))","v":6.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A184,'Updated Quanities'!F:I,7,0),R184)=\"\",R184,IFERROR(VLOOKUP('AUP Library'!A184,'Updated Quanities'!F:I,7,0),R184))","v":6.64},6.64,{"$f":"IFERROR(VLOOKUP('AUP Library'!A184,'Updated Quanities'!F:G,4,0),R184)","v":6.64}]
["209-11.01","Sediment Basin Riser","EACH",3235.71,3235.71,3235.71,3235.71,3235.71,3235.71,3235.71,3235.71,3235.71,3235.71,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A185,'Updated Quanities'!F:I,4,0),R185)=\"\",R185,IFERROR(VLOOKUP('AUP Library'!A185,'Updated Quanities'!F:I,4,0),R185))","v":3235.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A185,'Updated Quanities'!F:I,5,0),R185)=\"\",R185,IFERROR(VLOOKUP('AUP Library'!A185,'Updated Quanities'!F:I,5,0),R185))","v":3235.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A185,'Updated Quanities'!F:I,6,0),R185)=\"\",R185,IFERROR(VLOOKUP('AUP Library'!A185,'Updated Quanities'!F:I,6,0),R185))","v":3235.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A185,'Updated Quanities'!F:I,7,0),R185)=\"\",R185,IFERROR(VLOOKUP('AUP Library'!A185,'Updated Quanities'!F:I,7,0),R185))","v":3235.71},3235.71,{"$f":"IFERROR(VLOOKUP('AUP Library'!A185,'Updated Quanities'!F:G,4,0),R185)","v":3235.71}]
["209-11.02","Sediment Basin Riser","EACH",3200,3200,3200,3200,3200,3200,3200,3200,3200,3200,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A186,'Updated Quanities'!F:I,4,0),R186)=\"\",R186,IFERROR(VLOOKUP('AUP Library'!A186,'Updated Quanities'!F:I,4,0),R186))","v":3200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A186,'Updated Quanities'!F:I,5,0),R186)=\"\",R186,IFERROR(VLOOKUP('AUP Library'!A186,'Updated Quanities'!F:I,5,0),R186))","v":3200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A186,'Updated Quanities'!F:I,6,0),R186)=\"\",R186,IFERROR(VLOOKUP('AUP Library'!A186,'Updated Quanities'!F:I,6,0),R186))","v":3200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A186,'Updated Quanities'!F:I,7,0),R186)=\"\",R186,IFERROR(VLOOKUP('AUP Library'!A186,'Updated Quanities'!F:I,7,0),R186))","v":3200},3200,{"$f":"IFERROR(VLOOKUP('AUP Library'!A186,'Updated Quanities'!F:G,4,0),R186)","v":3200}]
["209-11.03","Sediment Basin Riser","EACH",4000,4000,4000,4000,4000,4000,4000,4000,4000,4000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A187,'Updated Quanities'!F:I,4,0),R187)=\"\",R187,IFERROR(VLOOKUP('AUP Library'!A187,'Updated Quanities'!F:I,4,0),R187))","v":4000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A187,'Updated Quanities'!F:I,5,0),R187)=\"\",R187,IFERROR(VLOOKUP('AUP Library'!A187,'Updated Quanities'!F:I,5,0),R187))","v":4000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A187,'Updated Quanities'!F:I,6,0),R187)=\"\",R187,IFERROR(VLOOKUP('AUP Library'!A187,'Updated Quanities'!F:I,6,0),R187))","v":4000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A187,'Updated Quanities'!F:I,7,0),R187)=\"\",R187,IFERROR(VLOOKUP('AUP Library'!A187,'Updated Quanities'!F:I,7,0),R187))","v":4000},4000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A187,'Updated Quanities'!F:G,4,0),R187)","v":4000}]
["209-11.04","Sediment Basin Riser","EACH",7800,7800,7800,7800,7800,7800,7800,7800,7800,7800,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A188,'Updated Quanities'!F:I,4,0),R188)=\"\",R188,IFERROR(VLOOKUP('AUP Library'!A188,'Updated Quanities'!F:I,4,0),R188))","v":7800},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A188,'Updated Quanities'!F:I,5,0),R188)=\"\",R188,IFERROR(VLOOKUP('AUP Library'!A188,'Updated Quanities'!F:I,5,0),R188))","v":7800},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A188,'Updated Quanities'!F:I,6,0),R188)=\"\",R188,IFERROR(VLOOKUP('AUP Library'!A188,'Updated Quanities'!F:I,6,0),R188))","v":7800},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A188,'Updated Quanities'!F:I,7,0),R188)=\"\",R188,IFERROR(VLOOKUP('AUP Library'!A188,'Updated Quanities'!F:I,7,0),R188))","v":7800},7800,{"$f":"IFERROR(VLOOKUP('AUP Library'!A188,'Updated Quanities'!F:G,4,0),R188)","v":7800}]
["209-11.20","Sediment Basin Baffles","LF",32.520000000000003,32.520000000000003,32.520000000000003,32.520000000000003,32.520000000000003,32.520000000000003,32.520000000000003,32.520000000000003,32.520000000000003,32.520000000000003,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A189,'Updated Quanities'!F:I,4,0),R189)=\"\",R189,IFERROR(VLOOKUP('AUP Library'!A189,'Updated Quanities'!F:I,4,0),R189))","v":32.520000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A189,'Updated Quanities'!F:I,5,0),R189)=\"\",R189,IFERROR(VLOOKUP('AUP Library'!A189,'Updated Quanities'!F:I,5,0),R189))","v":32.520000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A189,'Updated Quanities'!F:I,6,0),R189)=\"\",R189,IFERROR(VLOOKUP('AUP Library'!A189,'Updated Quanities'!F:I,6,0),R189))","v":32.520000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A189,'Updated Quanities'!F:I,7,0),R189)=\"\",R189,IFERROR(VLOOKUP('AUP Library'!A189,'Updated Quanities'!F:I,7,0),R189))","v":32.520000000000003},32.520000000000003,{"$f":"IFERROR(VLOOKUP('AUP Library'!A189,'Updated Quanities'!F:G,4,0),R189)","v":32.520000000000003}]
["209-13.04","Turbidity Curtain","LF",8.7899999999999991,8.7899999999999991,8.7899999999999991,8.7899999999999991,8.7899999999999991,8.7899999999999991,8.7899999999999991,8.7899999999999991,8.7899999999999991,8.7899999999999991,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A190,'Updated Quanities'!F:I,4,0),R190)=\"\",R190,IFERROR(VLOOKUP('AUP Library'!A190,'Updated Quanities'!F:I,4,0),R190))","v":8.7899999999999991},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A190,'Updated Quanities'!F:I,5,0),R190)=\"\",R190,IFERROR(VLOOKUP('AUP Library'!A190,'Updated Quanities'!F:I,5,0),R190))","v":8.7899999999999991},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A190,'Updated Quanities'!F:I,6,0),R190)=\"\",R190,IFERROR(VLOOKUP('AUP Library'!A190,'Updated Quanities'!F:I,6,0),R190))","v":8.7899999999999991},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A190,'Updated Quanities'!F:I,7,0),R190)=\"\",R190,IFERROR(VLOOKUP('AUP Library'!A190,'Updated Quanities'!F:I,7,0),R190))","v":8.7899999999999991},8.7899999999999991,{"$f":"IFERROR(VLOOKUP('AUP Library'!A190,'Updated Quanities'!F:G,4,0),R190)","v":8.7899999999999991}]
["209-13.05","Turbidity Curtain","LF",40,40,40,40,40,40,40,40,40,40,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A191,'Updated Quanities'!F:I,4,0),R191)=\"\",R191,IFERROR(VLOOKUP('AUP Library'!A191,'Updated Quanities'!F:I,4,0),R191))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A191,'Updated Quanities'!F:I,5,0),R191)=\"\",R191,IFERROR(VLOOKUP('AUP Library'!A191,'Updated Quanities'!F:I,5,0),R191))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A191,'Updated Quanities'!F:I,6,0),R191)=\"\",R191,IFERROR(VLOOKUP('AUP Library'!A191,'Updated Quanities'!F:I,6,0),R191))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A191,'Updated Quanities'!F:I,7,0),R191)=\"\",R191,IFERROR(VLOOKUP('AUP Library'!A191,'Updated Quanities'!F:I,7,0),R191))","v":40},40,{"$f":"IFERROR(VLOOKUP('AUP Library'!A191,'Updated Quanities'!F:G,4,0),R191)","v":40}]
["209-13.06","Turbidity Curtain","LF",40,40,40,40,40,40,40,40,40,40,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A192,'Updated Quanities'!F:I,4,0),R192)=\"\",R192,IFERROR(VLOOKUP('AUP Library'!A192,'Updated Quanities'!F:I,4,0),R192))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A192,'Updated Quanities'!F:I,5,0),R192)=\"\",R192,IFERROR(VLOOKUP('AUP Library'!A192,'Updated Quanities'!F:I,5,0),R192))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A192,'Updated Quanities'!F:I,6,0),R192)=\"\",R192,IFERROR(VLOOKUP('AUP Library'!A192,'Updated Quanities'!F:I,6,0),R192))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A192,'Updated Quanities'!F:I,7,0),R192)=\"\",R192,IFERROR(VLOOKUP('AUP Library'!A192,'Updated Quanities'!F:I,7,0),R192))","v":40},40,{"$f":"IFERROR(VLOOKUP('AUP Library'!A192,'Updated Quanities'!F:G,4,0),R192)","v":40}]
["209-13.07","Turbidity Curtain","LF",40,40,40,40,40,40,40,40,40,40,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A193,'Updated Quanities'!F:I,4,0),R193)=\"\",R193,IFERROR(VLOOKUP('AUP Library'!A193,'Updated Quanities'!F:I,4,0),R193))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A193,'Updated Quanities'!F:I,5,0),R193)=\"\",R193,IFERROR(VLOOKUP('AUP Library'!A193,'Updated Quanities'!F:I,5,0),R193))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A193,'Updated Quanities'!F:I,6,0),R193)=\"\",R193,IFERROR(VLOOKUP('AUP Library'!A193,'Updated Quanities'!F:I,6,0),R193))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A193,'Updated Quanities'!F:I,7,0),R193)=\"\",R193,IFERROR(VLOOKUP('AUP Library'!A193,'Updated Quanities'!F:I,7,0),R193))","v":40},40,{"$f":"IFERROR(VLOOKUP('AUP Library'!A193,'Updated Quanities'!F:G,4,0),R193)","v":40}]
["209-20.03","Polyethylene Sheeting (6 Mil. Minimum)","SY",2.64,2.64,2.64,2.64,2.64,2.64,2.64,2.64,2.64,2.64,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A194,'Updated Quanities'!F:I,4,0),R194)=\"\",R194,IFERROR(VLOOKUP('AUP Library'!A194,'Updated Quanities'!F:I,4,0),R194))","v":2.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A194,'Updated Quanities'!F:I,5,0),R194)=\"\",R194,IFERROR(VLOOKUP('AUP Library'!A194,'Updated Quanities'!F:I,5,0),R194))","v":2.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A194,'Updated Quanities'!F:I,6,0),R194)=\"\",R194,IFERROR(VLOOKUP('AUP Library'!A194,'Updated Quanities'!F:I,6,0),R194))","v":2.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A194,'Updated Quanities'!F:I,7,0),R194)=\"\",R194,IFERROR(VLOOKUP('AUP Library'!A194,'Updated Quanities'!F:I,7,0),R194))","v":2.64},2.64,{"$f":"IFERROR(VLOOKUP('AUP Library'!A194,'Updated Quanities'!F:G,4,0),R194)","v":2.64}]
["209-20.04","Polyethylene Sheeting (10 Mil. Minimum)","SY",1.55,1.55,1.55,1.55,1.55,1.55,1.55,1.55,1.55,1.55,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A195,'Updated Quanities'!F:I,4,0),R195)=\"\",R195,IFERROR(VLOOKUP('AUP Library'!A195,'Updated Quanities'!F:I,4,0),R195))","v":1.55},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A195,'Updated Quanities'!F:I,5,0),R195)=\"\",R195,IFERROR(VLOOKUP('AUP Library'!A195,'Updated Quanities'!F:I,5,0),R195))","v":1.55},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A195,'Updated Quanities'!F:I,6,0),R195)=\"\",R195,IFERROR(VLOOKUP('AUP Library'!A195,'Updated Quanities'!F:I,6,0),R195))","v":1.55},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A195,'Updated Quanities'!F:I,7,0),R195)=\"\",R195,IFERROR(VLOOKUP('AUP Library'!A195,'Updated Quanities'!F:I,7,0),R195))","v":1.55},1.55,{"$f":"IFERROR(VLOOKUP('AUP Library'!A195,'Updated Quanities'!F:G,4,0),R195)","v":1.55}]
["209-20.50","Sediment Basin (Description)","EACH",5000,5000,5000,5000,5000,5000,5000,5000,5000,5000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A196,'Updated Quanities'!F:I,4,0),R196)=\"\",R196,IFERROR(VLOOKUP('AUP Library'!A196,'Updated Quanities'!F:I,4,0),R196))","v":5000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A196,'Updated Quanities'!F:I,5,0),R196)=\"\",R196,IFERROR(VLOOKUP('AUP Library'!A196,'Updated Quanities'!F:I,5,0),R196))","v":5000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A196,'Updated Quanities'!F:I,6,0),R196)=\"\",R196,IFERROR(VLOOKUP('AUP Library'!A196,'Updated Quanities'!F:I,6,0),R196))","v":5000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A196,'Updated Quanities'!F:I,7,0),R196)=\"\",R196,IFERROR(VLOOKUP('AUP Library'!A196,'Updated Quanities'!F:I,7,0),R196))","v":5000},5000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A196,'Updated Quanities'!F:G,4,0),R196)","v":5000}]
["209-40.30","Catch Basin Protection (Type A)","EACH",542.38,542.38,542.38,542.38,542.38,542.38,542.38,542.38,542.38,542.38,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A197,'Updated Quanities'!F:I,4,0),R197)=\"\",R197,IFERROR(VLOOKUP('AUP Library'!A197,'Updated Quanities'!F:I,4,0),R197))","v":542.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A197,'Updated Quanities'!F:I,5,0),R197)=\"\",R197,IFERROR(VLOOKUP('AUP Library'!A197,'Updated Quanities'!F:I,5,0),R197))","v":542.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A197,'Updated Quanities'!F:I,6,0),R197)=\"\",R197,IFERROR(VLOOKUP('AUP Library'!A197,'Updated Quanities'!F:I,6,0),R197))","v":542.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A197,'Updated Quanities'!F:I,7,0),R197)=\"\",R197,IFERROR(VLOOKUP('AUP Library'!A197,'Updated Quanities'!F:I,7,0),R197))","v":542.38},542.38,{"$f":"IFERROR(VLOOKUP('AUP Library'!A197,'Updated Quanities'!F:G,4,0),R197)","v":542.38}]
["209-40.31","Catch Basin Protection (Type B)","EACH",246.88,246.88,246.88,246.88,246.88,246.88,246.88,246.88,246.88,246.88,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A198,'Updated Quanities'!F:I,4,0),R198)=\"\",R198,IFERROR(VLOOKUP('AUP Library'!A198,'Updated Quanities'!F:I,4,0),R198))","v":246.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A198,'Updated Quanities'!F:I,5,0),R198)=\"\",R198,IFERROR(VLOOKUP('AUP Library'!A198,'Updated Quanities'!F:I,5,0),R198))","v":246.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A198,'Updated Quanities'!F:I,6,0),R198)=\"\",R198,IFERROR(VLOOKUP('AUP Library'!A198,'Updated Quanities'!F:I,6,0),R198))","v":246.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A198,'Updated Quanities'!F:I,7,0),R198)=\"\",R198,IFERROR(VLOOKUP('AUP Library'!A198,'Updated Quanities'!F:I,7,0),R198))","v":246.88},246.88,{"$f":"IFERROR(VLOOKUP('AUP Library'!A198,'Updated Quanities'!F:G,4,0),R198)","v":246.88}]
["209-40.32","Catch Basin Protection (Type C)","EACH",501.41,501.41,501.41,501.41,501.41,501.41,501.41,501.41,501.41,501.41,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A199,'Updated Quanities'!F:I,4,0),R199)=\"\",R199,IFERROR(VLOOKUP('AUP Library'!A199,'Updated Quanities'!F:I,4,0),R199))","v":501.41},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A199,'Updated Quanities'!F:I,5,0),R199)=\"\",R199,IFERROR(VLOOKUP('AUP Library'!A199,'Updated Quanities'!F:I,5,0),R199))","v":501.41},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A199,'Updated Quanities'!F:I,6,0),R199)=\"\",R199,IFERROR(VLOOKUP('AUP Library'!A199,'Updated Quanities'!F:I,6,0),R199))","v":501.41},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A199,'Updated Quanities'!F:I,7,0),R199)=\"\",R199,IFERROR(VLOOKUP('AUP Library'!A199,'Updated Quanities'!F:I,7,0),R199))","v":501.41},501.41,{"$f":"IFERROR(VLOOKUP('AUP Library'!A199,'Updated Quanities'!F:G,4,0),R199)","v":501.41}]
["209-40.33","Catch Basin Protection (Type D)","EACH",237.16,237.16,237.16,237.16,237.16,237.16,237.16,237.16,237.16,237.16,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A200,'Updated Quanities'!F:I,4,0),R200)=\"\",R200,IFERROR(VLOOKUP('AUP Library'!A200,'Updated Quanities'!F:I,4,0),R200))","v":237.16},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A200,'Updated Quanities'!F:I,5,0),R200)=\"\",R200,IFERROR(VLOOKUP('AUP Library'!A200,'Updated Quanities'!F:I,5,0),R200))","v":237.16},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A200,'Updated Quanities'!F:I,6,0),R200)=\"\",R200,IFERROR(VLOOKUP('AUP Library'!A200,'Updated Quanities'!F:I,6,0),R200))","v":237.16},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A200,'Updated Quanities'!F:I,7,0),R200)=\"\",R200,IFERROR(VLOOKUP('AUP Library'!A200,'Updated Quanities'!F:I,7,0),R200))","v":237.16},237.16,{"$f":"IFERROR(VLOOKUP('AUP Library'!A200,'Updated Quanities'!F:G,4,0),R200)","v":237.16}]
["209-40.34","Catch Basin Protection (Type E)","EACH",256.86,256.86,256.86,256.86,256.86,256.86,256.86,256.86,256.86,256.86,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A201,'Updated Quanities'!F:I,4,0),R201)=\"\",R201,IFERROR(VLOOKUP('AUP Library'!A201,'Updated Quanities'!F:I,4,0),R201))","v":256.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A201,'Updated Quanities'!F:I,5,0),R201)=\"\",R201,IFERROR(VLOOKUP('AUP Library'!A201,'Updated Quanities'!F:I,5,0),R201))","v":256.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A201,'Updated Quanities'!F:I,6,0),R201)=\"\",R201,IFERROR(VLOOKUP('AUP Library'!A201,'Updated Quanities'!F:I,6,0),R201))","v":256.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A201,'Updated Quanities'!F:I,7,0),R201)=\"\",R201,IFERROR(VLOOKUP('AUP Library'!A201,'Updated Quanities'!F:I,7,0),R201))","v":256.86},256.86,{"$f":"IFERROR(VLOOKUP('AUP Library'!A201,'Updated Quanities'!F:G,4,0),R201)","v":256.86}]
["209-40.41","Catch Basin Filter Assembly (Type 1)","EACH",454.47,454.47,454.47,454.47,454.47,454.47,454.47,454.47,454.47,454.47,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A202,'Updated Quanities'!F:I,4,0),R202)=\"\",R202,IFERROR(VLOOKUP('AUP Library'!A202,'Updated Quanities'!F:I,4,0),R202))","v":454.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A202,'Updated Quanities'!F:I,5,0),R202)=\"\",R202,IFERROR(VLOOKUP('AUP Library'!A202,'Updated Quanities'!F:I,5,0),R202))","v":454.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A202,'Updated Quanities'!F:I,6,0),R202)=\"\",R202,IFERROR(VLOOKUP('AUP Library'!A202,'Updated Quanities'!F:I,6,0),R202))","v":454.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A202,'Updated Quanities'!F:I,7,0),R202)=\"\",R202,IFERROR(VLOOKUP('AUP Library'!A202,'Updated Quanities'!F:I,7,0),R202))","v":454.47},454.47,{"$f":"IFERROR(VLOOKUP('AUP Library'!A202,'Updated Quanities'!F:G,4,0),R202)","v":454.47}]
["209-40.42","Catch Basin Filter Assembly (Type 2)","EACH",453.1,453.1,453.1,453.1,453.1,453.1,453.1,453.1,453.1,453.1,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A203,'Updated Quanities'!F:I,4,0),R203)=\"\",R203,IFERROR(VLOOKUP('AUP Library'!A203,'Updated Quanities'!F:I,4,0),R203))","v":453.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A203,'Updated Quanities'!F:I,5,0),R203)=\"\",R203,IFERROR(VLOOKUP('AUP Library'!A203,'Updated Quanities'!F:I,5,0),R203))","v":453.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A203,'Updated Quanities'!F:I,6,0),R203)=\"\",R203,IFERROR(VLOOKUP('AUP Library'!A203,'Updated Quanities'!F:I,6,0),R203))","v":453.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A203,'Updated Quanities'!F:I,7,0),R203)=\"\",R203,IFERROR(VLOOKUP('AUP Library'!A203,'Updated Quanities'!F:I,7,0),R203))","v":453.1},453.1,{"$f":"IFERROR(VLOOKUP('AUP Library'!A203,'Updated Quanities'!F:G,4,0),R203)","v":453.1}]
["209-40.43","Catch Basin Filter Assembly (Type 3)","EACH",810,810,810,810,810,810,810,810,810,810,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A204,'Updated Quanities'!F:I,4,0),R204)=\"\",R204,IFERROR(VLOOKUP('AUP Library'!A204,'Updated Quanities'!F:I,4,0),R204))","v":810},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A204,'Updated Quanities'!F:I,5,0),R204)=\"\",R204,IFERROR(VLOOKUP('AUP Library'!A204,'Updated Quanities'!F:I,5,0),R204))","v":810},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A204,'Updated Quanities'!F:I,6,0),R204)=\"\",R204,IFERROR(VLOOKUP('AUP Library'!A204,'Updated Quanities'!F:I,6,0),R204))","v":810},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A204,'Updated Quanities'!F:I,7,0),R204)=\"\",R204,IFERROR(VLOOKUP('AUP Library'!A204,'Updated Quanities'!F:I,7,0),R204))","v":810},810,{"$f":"IFERROR(VLOOKUP('AUP Library'!A204,'Updated Quanities'!F:G,4,0),R204)","v":810}]
["209-40.44","Catch Basin Filter Assembly (Type 4)","EACH",879.59,879.59,879.59,879.59,879.59,879.59,879.59,879.59,879.59,879.59,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A205,'Updated Quanities'!F:I,4,0),R205)=\"\",R205,IFERROR(VLOOKUP('AUP Library'!A205,'Updated Quanities'!F:I,4,0),R205))","v":879.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A205,'Updated Quanities'!F:I,5,0),R205)=\"\",R205,IFERROR(VLOOKUP('AUP Library'!A205,'Updated Quanities'!F:I,5,0),R205))","v":879.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A205,'Updated Quanities'!F:I,6,0),R205)=\"\",R205,IFERROR(VLOOKUP('AUP Library'!A205,'Updated Quanities'!F:I,6,0),R205))","v":879.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A205,'Updated Quanities'!F:I,7,0),R205)=\"\",R205,IFERROR(VLOOKUP('AUP Library'!A205,'Updated Quanities'!F:I,7,0),R205))","v":879.59},879.59,{"$f":"IFERROR(VLOOKUP('AUP Library'!A205,'Updated Quanities'!F:G,4,0),R205)","v":879.59}]
["209-40.45","Catch Basin Filter Assembly (Type 5)","EACH",866.67,866.67,866.67,866.67,866.67,866.67,866.67,866.67,866.67,866.67,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A206,'Updated Quanities'!F:I,4,0),R206)=\"\",R206,IFERROR(VLOOKUP('AUP Library'!A206,'Updated Quanities'!F:I,4,0),R206))","v":866.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A206,'Updated Quanities'!F:I,5,0),R206)=\"\",R206,IFERROR(VLOOKUP('AUP Library'!A206,'Updated Quanities'!F:I,5,0),R206))","v":866.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A206,'Updated Quanities'!F:I,6,0),R206)=\"\",R206,IFERROR(VLOOKUP('AUP Library'!A206,'Updated Quanities'!F:I,6,0),R206))","v":866.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A206,'Updated Quanities'!F:I,7,0),R206)=\"\",R206,IFERROR(VLOOKUP('AUP Library'!A206,'Updated Quanities'!F:I,7,0),R206))","v":866.67},866.67,{"$f":"IFERROR(VLOOKUP('AUP Library'!A206,'Updated Quanities'!F:G,4,0),R206)","v":866.67}]
["209-40.46","Catch Basin Filter Assembly (Type 6)","EACH",454.55,454.55,454.55,454.55,454.55,454.55,454.55,454.55,454.55,454.55,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A207,'Updated Quanities'!F:I,4,0),R207)=\"\",R207,IFERROR(VLOOKUP('AUP Library'!A207,'Updated Quanities'!F:I,4,0),R207))","v":454.55},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A207,'Updated Quanities'!F:I,5,0),R207)=\"\",R207,IFERROR(VLOOKUP('AUP Library'!A207,'Updated Quanities'!F:I,5,0),R207))","v":454.55},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A207,'Updated Quanities'!F:I,6,0),R207)=\"\",R207,IFERROR(VLOOKUP('AUP Library'!A207,'Updated Quanities'!F:I,6,0),R207))","v":454.55},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A207,'Updated Quanities'!F:I,7,0),R207)=\"\",R207,IFERROR(VLOOKUP('AUP Library'!A207,'Updated Quanities'!F:I,7,0),R207))","v":454.55},454.55,{"$f":"IFERROR(VLOOKUP('AUP Library'!A207,'Updated Quanities'!F:G,4,0),R207)","v":454.55}]
["209-40.47","Catch Basin Filter Assembly (Type 7)","EACH",745.72,745.72,745.72,745.72,745.72,745.72,745.72,745.72,745.72,745.72,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A208,'Updated Quanities'!F:I,4,0),R208)=\"\",R208,IFERROR(VLOOKUP('AUP Library'!A208,'Updated Quanities'!F:I,4,0),R208))","v":745.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A208,'Updated Quanities'!F:I,5,0),R208)=\"\",R208,IFERROR(VLOOKUP('AUP Library'!A208,'Updated Quanities'!F:I,5,0),R208))","v":745.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A208,'Updated Quanities'!F:I,6,0),R208)=\"\",R208,IFERROR(VLOOKUP('AUP Library'!A208,'Updated Quanities'!F:I,6,0),R208))","v":745.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A208,'Updated Quanities'!F:I,7,0),R208)=\"\",R208,IFERROR(VLOOKUP('AUP Library'!A208,'Updated Quanities'!F:I,7,0),R208))","v":745.72},745.72,{"$f":"IFERROR(VLOOKUP('AUP Library'!A208,'Updated Quanities'!F:G,4,0),R208)","v":745.72}]
["209-40.48","Catch Basin Filter Assembly (Type 8)","EACH",951.78,951.78,951.78,951.78,951.78,951.78,951.78,951.78,951.78,951.78,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A209,'Updated Quanities'!F:I,4,0),R209)=\"\",R209,IFERROR(VLOOKUP('AUP Library'!A209,'Updated Quanities'!F:I,4,0),R209))","v":951.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A209,'Updated Quanities'!F:I,5,0),R209)=\"\",R209,IFERROR(VLOOKUP('AUP Library'!A209,'Updated Quanities'!F:I,5,0),R209))","v":951.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A209,'Updated Quanities'!F:I,6,0),R209)=\"\",R209,IFERROR(VLOOKUP('AUP Library'!A209,'Updated Quanities'!F:I,6,0),R209))","v":951.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A209,'Updated Quanities'!F:I,7,0),R209)=\"\",R209,IFERROR(VLOOKUP('AUP Library'!A209,'Updated Quanities'!F:I,7,0),R209))","v":951.78},951.78,{"$f":"IFERROR(VLOOKUP('AUP Library'!A209,'Updated Quanities'!F:G,4,0),R209)","v":951.78}]
["209-40.50","Catch Basin Filter Assembly (Type 10)","EACH",951.78,951.78,951.78,951.78,951.78,951.78,951.78,951.78,951.78,951.78,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A210,'Updated Quanities'!F:I,4,0),R210)=\"\",R210,IFERROR(VLOOKUP('AUP Library'!A210,'Updated Quanities'!F:I,4,0),R210))","v":951.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A210,'Updated Quanities'!F:I,5,0),R210)=\"\",R210,IFERROR(VLOOKUP('AUP Library'!A210,'Updated Quanities'!F:I,5,0),R210))","v":951.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A210,'Updated Quanities'!F:I,6,0),R210)=\"\",R210,IFERROR(VLOOKUP('AUP Library'!A210,'Updated Quanities'!F:I,6,0),R210))","v":951.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A210,'Updated Quanities'!F:I,7,0),R210)=\"\",R210,IFERROR(VLOOKUP('AUP Library'!A210,'Updated Quanities'!F:I,7,0),R210))","v":951.78},951.78,{"$f":"IFERROR(VLOOKUP('AUP Library'!A210,'Updated Quanities'!F:G,4,0),R210)","v":951.78}]
["209-65.01","Temporary Diversion Channel","LS",34600,34600,34600,34600,34600,34600,34600,34600,34600,34600,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A211,'Updated Quanities'!F:I,4,0),R211)=\"\",R211,IFERROR(VLOOKUP('AUP Library'!A211,'Updated Quanities'!F:I,4,0),R211))","v":34600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A211,'Updated Quanities'!F:I,5,0),R211)=\"\",R211,IFERROR(VLOOKUP('AUP Library'!A211,'Updated Quanities'!F:I,5,0),R211))","v":34600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A211,'Updated Quanities'!F:I,6,0),R211)=\"\",R211,IFERROR(VLOOKUP('AUP Library'!A211,'Updated Quanities'!F:I,6,0),R211))","v":34600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A211,'Updated Quanities'!F:I,7,0),R211)=\"\",R211,IFERROR(VLOOKUP('AUP Library'!A211,'Updated Quanities'!F:I,7,0),R211))","v":34600},34600,{"$f":"IFERROR(VLOOKUP('AUP Library'!A211,'Updated Quanities'!F:G,4,0),R211)","v":34600}]
["209-65.02","Temporary Diversion Channel","LS",15000,15000,15000,15000,15000,15000,15000,15000,15000,15000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A212,'Updated Quanities'!F:I,4,0),R212)=\"\",R212,IFERROR(VLOOKUP('AUP Library'!A212,'Updated Quanities'!F:I,4,0),R212))","v":15000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A212,'Updated Quanities'!F:I,5,0),R212)=\"\",R212,IFERROR(VLOOKUP('AUP Library'!A212,'Updated Quanities'!F:I,5,0),R212))","v":15000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A212,'Updated Quanities'!F:I,6,0),R212)=\"\",R212,IFERROR(VLOOKUP('AUP Library'!A212,'Updated Quanities'!F:I,6,0),R212))","v":15000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A212,'Updated Quanities'!F:I,7,0),R212)=\"\",R212,IFERROR(VLOOKUP('AUP Library'!A212,'Updated Quanities'!F:I,7,0),R212))","v":15000},15000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A212,'Updated Quanities'!F:G,4,0),R212)","v":15000}]
["209-65.03","Temporary Diversion Channel","LF",16.47,16.47,16.47,16.47,16.47,16.47,16.47,16.47,16.47,16.47,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A213,'Updated Quanities'!F:I,4,0),R213)=\"\",R213,IFERROR(VLOOKUP('AUP Library'!A213,'Updated Quanities'!F:I,4,0),R213))","v":16.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A213,'Updated Quanities'!F:I,5,0),R213)=\"\",R213,IFERROR(VLOOKUP('AUP Library'!A213,'Updated Quanities'!F:I,5,0),R213))","v":16.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A213,'Updated Quanities'!F:I,6,0),R213)=\"\",R213,IFERROR(VLOOKUP('AUP Library'!A213,'Updated Quanities'!F:I,6,0),R213))","v":16.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A213,'Updated Quanities'!F:I,7,0),R213)=\"\",R213,IFERROR(VLOOKUP('AUP Library'!A213,'Updated Quanities'!F:I,7,0),R213))","v":16.47},16.47,{"$f":"IFERROR(VLOOKUP('AUP Library'!A213,'Updated Quanities'!F:G,4,0),R213)","v":16.47}]
["209-65.04","Temporary Diversion Channel","LF",50,50,50,50,50,50,50,50,50,50,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A214,'Updated Quanities'!F:I,4,0),R214)=\"\",R214,IFERROR(VLOOKUP('AUP Library'!A214,'Updated Quanities'!F:I,4,0),R214))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A214,'Updated Quanities'!F:I,5,0),R214)=\"\",R214,IFERROR(VLOOKUP('AUP Library'!A214,'Updated Quanities'!F:I,5,0),R214))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A214,'Updated Quanities'!F:I,6,0),R214)=\"\",R214,IFERROR(VLOOKUP('AUP Library'!A214,'Updated Quanities'!F:I,6,0),R214))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A214,'Updated Quanities'!F:I,7,0),R214)=\"\",R214,IFERROR(VLOOKUP('AUP Library'!A214,'Updated Quanities'!F:I,7,0),R214))","v":50},50,{"$f":"IFERROR(VLOOKUP('AUP Library'!A214,'Updated Quanities'!F:G,4,0),R214)","v":50}]
["209-65.14","Temporary Diversion Channel","LS",30537.5,30537.5,30537.5,30537.5,30537.5,30537.5,30537.5,30537.5,30537.5,30537.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A215,'Updated Quanities'!F:I,4,0),R215)=\"\",R215,IFERROR(VLOOKUP('AUP Library'!A215,'Updated Quanities'!F:I,4,0),R215))","v":30537.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A215,'Updated Quanities'!F:I,5,0),R215)=\"\",R215,IFERROR(VLOOKUP('AUP Library'!A215,'Updated Quanities'!F:I,5,0),R215))","v":30537.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A215,'Updated Quanities'!F:I,6,0),R215)=\"\",R215,IFERROR(VLOOKUP('AUP Library'!A215,'Updated Quanities'!F:I,6,0),R215))","v":30537.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A215,'Updated Quanities'!F:I,7,0),R215)=\"\",R215,IFERROR(VLOOKUP('AUP Library'!A215,'Updated Quanities'!F:I,7,0),R215))","v":30537.5},30537.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A215,'Updated Quanities'!F:G,4,0),R215)","v":30537.5}]
["606-24.10","Sheet Piles","SF",36.18,36.18,36.18,36.18,36.18,36.18,36.18,36.18,36.18,36.18,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A216,'Updated Quanities'!F:I,4,0),R216)=\"\",R216,IFERROR(VLOOKUP('AUP Library'!A216,'Updated Quanities'!F:I,4,0),R216))","v":36.18},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A216,'Updated Quanities'!F:I,5,0),R216)=\"\",R216,IFERROR(VLOOKUP('AUP Library'!A216,'Updated Quanities'!F:I,5,0),R216))","v":36.18},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A216,'Updated Quanities'!F:I,6,0),R216)=\"\",R216,IFERROR(VLOOKUP('AUP Library'!A216,'Updated Quanities'!F:I,6,0),R216))","v":36.18},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A216,'Updated Quanities'!F:I,7,0),R216)=\"\",R216,IFERROR(VLOOKUP('AUP Library'!A216,'Updated Quanities'!F:I,7,0),R216))","v":36.18},36.18,{"$f":"IFERROR(VLOOKUP('AUP Library'!A216,'Updated Quanities'!F:G,4,0),R216)","v":36.18}]
["606-24.12","Temporary Sheet Piles","SF",20.76,20.76,20.76,20.76,20.76,20.76,20.76,20.76,20.76,20.76,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A217,'Updated Quanities'!F:I,4,0),R217)=\"\",R217,IFERROR(VLOOKUP('AUP Library'!A217,'Updated Quanities'!F:I,4,0),R217))","v":20.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A217,'Updated Quanities'!F:I,5,0),R217)=\"\",R217,IFERROR(VLOOKUP('AUP Library'!A217,'Updated Quanities'!F:I,5,0),R217))","v":20.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A217,'Updated Quanities'!F:I,6,0),R217)=\"\",R217,IFERROR(VLOOKUP('AUP Library'!A217,'Updated Quanities'!F:I,6,0),R217))","v":20.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A217,'Updated Quanities'!F:I,7,0),R217)=\"\",R217,IFERROR(VLOOKUP('AUP Library'!A217,'Updated Quanities'!F:I,7,0),R217))","v":20.76},20.76,{"$f":"IFERROR(VLOOKUP('AUP Library'!A217,'Updated Quanities'!F:G,4,0),R217)","v":20.76}]
["607-01.02","12\" Concrete Pipe Culvert (Class III)","LF",60,60,60,60,60,60,60,60,60,60,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A218,'Updated Quanities'!F:I,4,0),R218)=\"\",R218,IFERROR(VLOOKUP('AUP Library'!A218,'Updated Quanities'!F:I,4,0),R218))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A218,'Updated Quanities'!F:I,5,0),R218)=\"\",R218,IFERROR(VLOOKUP('AUP Library'!A218,'Updated Quanities'!F:I,5,0),R218))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A218,'Updated Quanities'!F:I,6,0),R218)=\"\",R218,IFERROR(VLOOKUP('AUP Library'!A218,'Updated Quanities'!F:I,6,0),R218))","v":60},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A218,'Updated Quanities'!F:I,7,0),R218)=\"\",R218,IFERROR(VLOOKUP('AUP Library'!A218,'Updated Quanities'!F:I,7,0),R218))","v":60},60,{"$f":"IFERROR(VLOOKUP('AUP Library'!A218,'Updated Quanities'!F:G,4,0),R218)","v":60}]
["607-02.02","15\" Concrete Pipe Culvert (Class III)","LF",95.18,95.18,95.18,95.18,95.18,95.18,95.18,95.18,95.18,95.18,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A219,'Updated Quanities'!F:I,4,0),R219)=\"\",R219,IFERROR(VLOOKUP('AUP Library'!A219,'Updated Quanities'!F:I,4,0),R219))","v":95.18},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A219,'Updated Quanities'!F:I,5,0),R219)=\"\",R219,IFERROR(VLOOKUP('AUP Library'!A219,'Updated Quanities'!F:I,5,0),R219))","v":95.18},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A219,'Updated Quanities'!F:I,6,0),R219)=\"\",R219,IFERROR(VLOOKUP('AUP Library'!A219,'Updated Quanities'!F:I,6,0),R219))","v":95.18},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A219,'Updated Quanities'!F:I,7,0),R219)=\"\",R219,IFERROR(VLOOKUP('AUP Library'!A219,'Updated Quanities'!F:I,7,0),R219))","v":95.18},95.18,{"$f":"IFERROR(VLOOKUP('AUP Library'!A219,'Updated Quanities'!F:G,4,0),R219)","v":95.18}]
["607-03.02","18\" Concrete Pipe Culvert (Class III)","LF",46.74,46.74,46.74,46.74,46.74,46.74,46.74,46.74,46.74,46.74,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A220,'Updated Quanities'!F:I,4,0),R220)=\"\",R220,IFERROR(VLOOKUP('AUP Library'!A220,'Updated Quanities'!F:I,4,0),R220))","v":46.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A220,'Updated Quanities'!F:I,5,0),R220)=\"\",R220,IFERROR(VLOOKUP('AUP Library'!A220,'Updated Quanities'!F:I,5,0),R220))","v":46.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A220,'Updated Quanities'!F:I,6,0),R220)=\"\",R220,IFERROR(VLOOKUP('AUP Library'!A220,'Updated Quanities'!F:I,6,0),R220))","v":46.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A220,'Updated Quanities'!F:I,7,0),R220)=\"\",R220,IFERROR(VLOOKUP('AUP Library'!A220,'Updated Quanities'!F:I,7,0),R220))","v":46.74},46.74,{"$f":"IFERROR(VLOOKUP('AUP Library'!A220,'Updated Quanities'!F:G,4,0),R220)","v":46.74}]
["607-03.30","18\" Pipe Culvert","LF",53.22,53.22,53.22,53.22,53.22,53.22,53.22,53.22,53.22,53.22,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A221,'Updated Quanities'!F:I,4,0),R221)=\"\",R221,IFERROR(VLOOKUP('AUP Library'!A221,'Updated Quanities'!F:I,4,0),R221))","v":53.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A221,'Updated Quanities'!F:I,5,0),R221)=\"\",R221,IFERROR(VLOOKUP('AUP Library'!A221,'Updated Quanities'!F:I,5,0),R221))","v":53.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A221,'Updated Quanities'!F:I,6,0),R221)=\"\",R221,IFERROR(VLOOKUP('AUP Library'!A221,'Updated Quanities'!F:I,6,0),R221))","v":53.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A221,'Updated Quanities'!F:I,7,0),R221)=\"\",R221,IFERROR(VLOOKUP('AUP Library'!A221,'Updated Quanities'!F:I,7,0),R221))","v":53.22},53.22,{"$f":"IFERROR(VLOOKUP('AUP Library'!A221,'Updated Quanities'!F:G,4,0),R221)","v":53.22}]
["607-05.02","24\" Concrete Pipe Culvert (Class III)","LF",57.79,42.12,44.220999999999997,51.62,51.62,49.14,56.59,52.65,53.08,63.38,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A222,'Updated Quanities'!F:I,4,0),R222)=\"\",R222,IFERROR(VLOOKUP('AUP Library'!A222,'Updated Quanities'!F:I,4,0),R222))","v":67.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A222,'Updated Quanities'!F:I,5,0),R222)=\"\",R222,IFERROR(VLOOKUP('AUP Library'!A222,'Updated Quanities'!F:I,5,0),R222))","v":67.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A222,'Updated Quanities'!F:I,6,0),R222)=\"\",R222,IFERROR(VLOOKUP('AUP Library'!A222,'Updated Quanities'!F:I,6,0),R222))","v":67.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A222,'Updated Quanities'!F:I,7,0),R222)=\"\",R222,IFERROR(VLOOKUP('AUP Library'!A222,'Updated Quanities'!F:I,7,0),R222))","v":67.23},67.23,{"$f":"IFERROR(VLOOKUP('AUP Library'!A222,'Updated Quanities'!F:G,4,0),R222)","v":67.23}]
["607-05.30","24\" Pipe Culvert","LF",66.430000000000007,66.430000000000007,66.430000000000007,66.430000000000007,66.430000000000007,66.430000000000007,66.430000000000007,66.430000000000007,66.430000000000007,66.430000000000007,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A223,'Updated Quanities'!F:I,4,0),R223)=\"\",R223,IFERROR(VLOOKUP('AUP Library'!A223,'Updated Quanities'!F:I,4,0),R223))","v":66.430000000000007},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A223,'Updated Quanities'!F:I,5,0),R223)=\"\",R223,IFERROR(VLOOKUP('AUP Library'!A223,'Updated Quanities'!F:I,5,0),R223))","v":66.430000000000007},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A223,'Updated Quanities'!F:I,6,0),R223)=\"\",R223,IFERROR(VLOOKUP('AUP Library'!A223,'Updated Quanities'!F:I,6,0),R223))","v":66.430000000000007},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A223,'Updated Quanities'!F:I,7,0),R223)=\"\",R223,IFERROR(VLOOKUP('AUP Library'!A223,'Updated Quanities'!F:I,7,0),R223))","v":66.430000000000007},66.430000000000007,{"$f":"IFERROR(VLOOKUP('AUP Library'!A223,'Updated Quanities'!F:G,4,0),R223)","v":66.430000000000007}]
["607-06.02","30\" Concrete Pipe Culvert (Class III)","LF",89.04,89.04,89.04,89.04,89.04,89.04,89.04,89.04,89.04,89.04,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A224,'Updated Quanities'!F:I,4,0),R224)=\"\",R224,IFERROR(VLOOKUP('AUP Library'!A224,'Updated Quanities'!F:I,4,0),R224))","v":89.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A224,'Updated Quanities'!F:I,5,0),R224)=\"\",R224,IFERROR(VLOOKUP('AUP Library'!A224,'Updated Quanities'!F:I,5,0),R224))","v":89.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A224,'Updated Quanities'!F:I,6,0),R224)=\"\",R224,IFERROR(VLOOKUP('AUP Library'!A224,'Updated Quanities'!F:I,6,0),R224))","v":89.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A224,'Updated Quanities'!F:I,7,0),R224)=\"\",R224,IFERROR(VLOOKUP('AUP Library'!A224,'Updated Quanities'!F:I,7,0),R224))","v":89.04},89.04,{"$f":"IFERROR(VLOOKUP('AUP Library'!A224,'Updated Quanities'!F:G,4,0),R224)","v":89.04}]
["607-06.30","30\" Pipe Culvert","LF",81.96,81.96,81.96,81.96,81.96,81.96,81.96,81.96,81.96,81.96,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A225,'Updated Quanities'!F:I,4,0),R225)=\"\",R225,IFERROR(VLOOKUP('AUP Library'!A225,'Updated Quanities'!F:I,4,0),R225))","v":81.96},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A225,'Updated Quanities'!F:I,5,0),R225)=\"\",R225,IFERROR(VLOOKUP('AUP Library'!A225,'Updated Quanities'!F:I,5,0),R225))","v":81.96},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A225,'Updated Quanities'!F:I,6,0),R225)=\"\",R225,IFERROR(VLOOKUP('AUP Library'!A225,'Updated Quanities'!F:I,6,0),R225))","v":81.96},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A225,'Updated Quanities'!F:I,7,0),R225)=\"\",R225,IFERROR(VLOOKUP('AUP Library'!A225,'Updated Quanities'!F:I,7,0),R225))","v":81.96},81.96,{"$f":"IFERROR(VLOOKUP('AUP Library'!A225,'Updated Quanities'!F:G,4,0),R225)","v":81.96}]
["607-07.02","36\" Concrete Pipe Culvert (Class III)","LF",103.71,103.71,103.71,103.71,103.71,103.71,103.71,103.71,103.71,103.71,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A226,'Updated Quanities'!F:I,4,0),R226)=\"\",R226,IFERROR(VLOOKUP('AUP Library'!A226,'Updated Quanities'!F:I,4,0),R226))","v":103.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A226,'Updated Quanities'!F:I,5,0),R226)=\"\",R226,IFERROR(VLOOKUP('AUP Library'!A226,'Updated Quanities'!F:I,5,0),R226))","v":103.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A226,'Updated Quanities'!F:I,6,0),R226)=\"\",R226,IFERROR(VLOOKUP('AUP Library'!A226,'Updated Quanities'!F:I,6,0),R226))","v":103.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A226,'Updated Quanities'!F:I,7,0),R226)=\"\",R226,IFERROR(VLOOKUP('AUP Library'!A226,'Updated Quanities'!F:I,7,0),R226))","v":103.71},103.71,{"$f":"IFERROR(VLOOKUP('AUP Library'!A226,'Updated Quanities'!F:G,4,0),R226)","v":103.71}]
["607-07.30","36\" Pipe Culvert","LF",73.260000000000005,73.260000000000005,73.260000000000005,73.260000000000005,73.260000000000005,73.260000000000005,73.260000000000005,73.260000000000005,73.260000000000005,73.260000000000005,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A227,'Updated Quanities'!F:I,4,0),R227)=\"\",R227,IFERROR(VLOOKUP('AUP Library'!A227,'Updated Quanities'!F:I,4,0),R227))","v":73.260000000000005},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A227,'Updated Quanities'!F:I,5,0),R227)=\"\",R227,IFERROR(VLOOKUP('AUP Library'!A227,'Updated Quanities'!F:I,5,0),R227))","v":73.260000000000005},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A227,'Updated Quanities'!F:I,6,0),R227)=\"\",R227,IFERROR(VLOOKUP('AUP Library'!A227,'Updated Quanities'!F:I,6,0),R227))","v":73.260000000000005},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A227,'Updated Quanities'!F:I,7,0),R227)=\"\",R227,IFERROR(VLOOKUP('AUP Library'!A227,'Updated Quanities'!F:I,7,0),R227))","v":73.260000000000005},73.260000000000005,{"$f":"IFERROR(VLOOKUP('AUP Library'!A227,'Updated Quanities'!F:G,4,0),R227)","v":73.260000000000005}]
["607-08.02","42\" Concrete Pipe Culvert (Class III)","LF",111.46,111.46,111.46,111.46,111.46,111.46,111.46,111.46,111.46,111.46,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A228,'Updated Quanities'!F:I,4,0),R228)=\"\",R228,IFERROR(VLOOKUP('AUP Library'!A228,'Updated Quanities'!F:I,4,0),R228))","v":111.46},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A228,'Updated Quanities'!F:I,5,0),R228)=\"\",R228,IFERROR(VLOOKUP('AUP Library'!A228,'Updated Quanities'!F:I,5,0),R228))","v":111.46},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A228,'Updated Quanities'!F:I,6,0),R228)=\"\",R228,IFERROR(VLOOKUP('AUP Library'!A228,'Updated Quanities'!F:I,6,0),R228))","v":111.46},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A228,'Updated Quanities'!F:I,7,0),R228)=\"\",R228,IFERROR(VLOOKUP('AUP Library'!A228,'Updated Quanities'!F:I,7,0),R228))","v":111.46},111.46,{"$f":"IFERROR(VLOOKUP('AUP Library'!A228,'Updated Quanities'!F:G,4,0),R228)","v":111.46}]
["607-08.30","42\" Pipe Culvert","LF",208.78,208.78,208.78,208.78,208.78,208.78,208.78,208.78,208.78,208.78,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A229,'Updated Quanities'!F:I,4,0),R229)=\"\",R229,IFERROR(VLOOKUP('AUP Library'!A229,'Updated Quanities'!F:I,4,0),R229))","v":208.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A229,'Updated Quanities'!F:I,5,0),R229)=\"\",R229,IFERROR(VLOOKUP('AUP Library'!A229,'Updated Quanities'!F:I,5,0),R229))","v":208.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A229,'Updated Quanities'!F:I,6,0),R229)=\"\",R229,IFERROR(VLOOKUP('AUP Library'!A229,'Updated Quanities'!F:I,6,0),R229))","v":208.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A229,'Updated Quanities'!F:I,7,0),R229)=\"\",R229,IFERROR(VLOOKUP('AUP Library'!A229,'Updated Quanities'!F:I,7,0),R229))","v":208.78},208.78,{"$f":"IFERROR(VLOOKUP('AUP Library'!A229,'Updated Quanities'!F:G,4,0),R229)","v":208.78}]
["607-09.02","48\" Concrete Pipe Culvert (Class III)","LF",143.27000000000001,143.27000000000001,143.27000000000001,143.27000000000001,143.27000000000001,143.27000000000001,143.27000000000001,143.27000000000001,143.27000000000001,143.27000000000001,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A230,'Updated Quanities'!F:I,4,0),R230)=\"\",R230,IFERROR(VLOOKUP('AUP Library'!A230,'Updated Quanities'!F:I,4,0),R230))","v":143.27000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A230,'Updated Quanities'!F:I,5,0),R230)=\"\",R230,IFERROR(VLOOKUP('AUP Library'!A230,'Updated Quanities'!F:I,5,0),R230))","v":143.27000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A230,'Updated Quanities'!F:I,6,0),R230)=\"\",R230,IFERROR(VLOOKUP('AUP Library'!A230,'Updated Quanities'!F:I,6,0),R230))","v":143.27000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A230,'Updated Quanities'!F:I,7,0),R230)=\"\",R230,IFERROR(VLOOKUP('AUP Library'!A230,'Updated Quanities'!F:I,7,0),R230))","v":143.27000000000001},143.27000000000001,{"$f":"IFERROR(VLOOKUP('AUP Library'!A230,'Updated Quanities'!F:G,4,0),R230)","v":143.27000000000001}]
["607-09.30","48\" Pipe Culvert","LF",140,140,140,140,140,140,140,140,140,140,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A231,'Updated Quanities'!F:I,4,0),R231)=\"\",R231,IFERROR(VLOOKUP('AUP Library'!A231,'Updated Quanities'!F:I,4,0),R231))","v":140},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A231,'Updated Quanities'!F:I,5,0),R231)=\"\",R231,IFERROR(VLOOKUP('AUP Library'!A231,'Updated Quanities'!F:I,5,0),R231))","v":140},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A231,'Updated Quanities'!F:I,6,0),R231)=\"\",R231,IFERROR(VLOOKUP('AUP Library'!A231,'Updated Quanities'!F:I,6,0),R231))","v":140},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A231,'Updated Quanities'!F:I,7,0),R231)=\"\",R231,IFERROR(VLOOKUP('AUP Library'!A231,'Updated Quanities'!F:I,7,0),R231))","v":140},140,{"$f":"IFERROR(VLOOKUP('AUP Library'!A231,'Updated Quanities'!F:G,4,0),R231)","v":140}]
["607-10.02","54\" Concrete Pipe Culvert (Class III)","LF",145.27000000000001,145.27000000000001,145.27000000000001,145.27000000000001,145.27000000000001,145.27000000000001,145.27000000000001,145.27000000000001,145.27000000000001,145.27000000000001,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A232,'Updated Quanities'!F:I,4,0),R232)=\"\",R232,IFERROR(VLOOKUP('AUP Library'!A232,'Updated Quanities'!F:I,4,0),R232))","v":145.27000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A232,'Updated Quanities'!F:I,5,0),R232)=\"\",R232,IFERROR(VLOOKUP('AUP Library'!A232,'Updated Quanities'!F:I,5,0),R232))","v":145.27000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A232,'Updated Quanities'!F:I,6,0),R232)=\"\",R232,IFERROR(VLOOKUP('AUP Library'!A232,'Updated Quanities'!F:I,6,0),R232))","v":145.27000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A232,'Updated Quanities'!F:I,7,0),R232)=\"\",R232,IFERROR(VLOOKUP('AUP Library'!A232,'Updated Quanities'!F:I,7,0),R232))","v":145.27000000000001},145.27000000000001,{"$f":"IFERROR(VLOOKUP('AUP Library'!A232,'Updated Quanities'!F:G,4,0),R232)","v":145.27000000000001}]
["607-10.30","54\" Pipe Culvert","LF",145.27000000000001,145.27000000000001,145.27000000000001,145.27000000000001,145.27000000000001,145.27000000000001,145.27000000000001,145.27000000000001,145.27000000000001,145.27000000000001,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A233,'Updated Quanities'!F:I,4,0),R233)=\"\",R233,IFERROR(VLOOKUP('AUP Library'!A233,'Updated Quanities'!F:I,4,0),R233))","v":145.27000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A233,'Updated Quanities'!F:I,5,0),R233)=\"\",R233,IFERROR(VLOOKUP('AUP Library'!A233,'Updated Quanities'!F:I,5,0),R233))","v":145.27000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A233,'Updated Quanities'!F:I,6,0),R233)=\"\",R233,IFERROR(VLOOKUP('AUP Library'!A233,'Updated Quanities'!F:I,6,0),R233))","v":145.27000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A233,'Updated Quanities'!F:I,7,0),R233)=\"\",R233,IFERROR(VLOOKUP('AUP Library'!A233,'Updated Quanities'!F:I,7,0),R233))","v":145.27000000000001},145.27000000000001,{"$f":"IFERROR(VLOOKUP('AUP Library'!A233,'Updated Quanities'!F:G,4,0),R233)","v":145.27000000000001}]
["607-11.03","60\" Concrete Pipe Culvert (Class III)","LF",214.6,214.6,214.6,214.6,214.6,214.6,214.6,214.6,214.6,214.6,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A234,'Updated Quanities'!F:I,4,0),R234)=\"\",R234,IFERROR(VLOOKUP('AUP Library'!A234,'Updated Quanities'!F:I,4,0),R234))","v":214.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A234,'Updated Quanities'!F:I,5,0),R234)=\"\",R234,IFERROR(VLOOKUP('AUP Library'!A234,'Updated Quanities'!F:I,5,0),R234))","v":214.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A234,'Updated Quanities'!F:I,6,0),R234)=\"\",R234,IFERROR(VLOOKUP('AUP Library'!A234,'Updated Quanities'!F:I,6,0),R234))","v":214.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A234,'Updated Quanities'!F:I,7,0),R234)=\"\",R234,IFERROR(VLOOKUP('AUP Library'!A234,'Updated Quanities'!F:I,7,0),R234))","v":214.6},214.6,{"$f":"IFERROR(VLOOKUP('AUP Library'!A234,'Updated Quanities'!F:G,4,0),R234)","v":214.6}]
["607-16.01","23\"X 14\"HORIZONTAL OVAL CNC PIPE CULVERT","LF",50.41,50.41,50.41,50.41,50.41,50.41,50.41,50.41,50.41,50.41,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A235,'Updated Quanities'!F:I,4,0),R235)=\"\",R235,IFERROR(VLOOKUP('AUP Library'!A235,'Updated Quanities'!F:I,4,0),R235))","v":50.41},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A235,'Updated Quanities'!F:I,5,0),R235)=\"\",R235,IFERROR(VLOOKUP('AUP Library'!A235,'Updated Quanities'!F:I,5,0),R235))","v":50.41},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A235,'Updated Quanities'!F:I,6,0),R235)=\"\",R235,IFERROR(VLOOKUP('AUP Library'!A235,'Updated Quanities'!F:I,6,0),R235))","v":50.41},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A235,'Updated Quanities'!F:I,7,0),R235)=\"\",R235,IFERROR(VLOOKUP('AUP Library'!A235,'Updated Quanities'!F:I,7,0),R235))","v":50.41},50.41,{"$f":"IFERROR(VLOOKUP('AUP Library'!A235,'Updated Quanities'!F:G,4,0),R235)","v":50.41}]
["607-16.02","30\"X 19\"HORIZONTAL OVAL CNC PIPE CULVERT","LF",63.72,63.72,63.72,63.72,63.72,63.72,63.72,63.72,63.72,63.72,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A236,'Updated Quanities'!F:I,4,0),R236)=\"\",R236,IFERROR(VLOOKUP('AUP Library'!A236,'Updated Quanities'!F:I,4,0),R236))","v":63.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A236,'Updated Quanities'!F:I,5,0),R236)=\"\",R236,IFERROR(VLOOKUP('AUP Library'!A236,'Updated Quanities'!F:I,5,0),R236))","v":63.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A236,'Updated Quanities'!F:I,6,0),R236)=\"\",R236,IFERROR(VLOOKUP('AUP Library'!A236,'Updated Quanities'!F:I,6,0),R236))","v":63.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A236,'Updated Quanities'!F:I,7,0),R236)=\"\",R236,IFERROR(VLOOKUP('AUP Library'!A236,'Updated Quanities'!F:I,7,0),R236))","v":63.72},63.72,{"$f":"IFERROR(VLOOKUP('AUP Library'!A236,'Updated Quanities'!F:G,4,0),R236)","v":63.72}]
["607-16.04","38\"X 24\"HORIZONTAL OVAL CNC PIPE CULVERT","LF",80.77,80.77,80.77,80.77,80.77,80.77,80.77,80.77,80.77,80.77,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A237,'Updated Quanities'!F:I,4,0),R237)=\"\",R237,IFERROR(VLOOKUP('AUP Library'!A237,'Updated Quanities'!F:I,4,0),R237))","v":80.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A237,'Updated Quanities'!F:I,5,0),R237)=\"\",R237,IFERROR(VLOOKUP('AUP Library'!A237,'Updated Quanities'!F:I,5,0),R237))","v":80.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A237,'Updated Quanities'!F:I,6,0),R237)=\"\",R237,IFERROR(VLOOKUP('AUP Library'!A237,'Updated Quanities'!F:I,6,0),R237))","v":80.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A237,'Updated Quanities'!F:I,7,0),R237)=\"\",R237,IFERROR(VLOOKUP('AUP Library'!A237,'Updated Quanities'!F:I,7,0),R237))","v":80.77},80.77,{"$f":"IFERROR(VLOOKUP('AUP Library'!A237,'Updated Quanities'!F:G,4,0),R237)","v":80.77}]
["607-16.05","45\"X29\"HORIZ OVAL CNC PIPE CULV (CL __)","LF",128.13999999999999,128.13999999999999,128.13999999999999,128.13999999999999,128.13999999999999,128.13999999999999,128.13999999999999,128.13999999999999,128.13999999999999,128.13999999999999,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A238,'Updated Quanities'!F:I,4,0),R238)=\"\",R238,IFERROR(VLOOKUP('AUP Library'!A238,'Updated Quanities'!F:I,4,0),R238))","v":128.13999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A238,'Updated Quanities'!F:I,5,0),R238)=\"\",R238,IFERROR(VLOOKUP('AUP Library'!A238,'Updated Quanities'!F:I,5,0),R238))","v":128.13999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A238,'Updated Quanities'!F:I,6,0),R238)=\"\",R238,IFERROR(VLOOKUP('AUP Library'!A238,'Updated Quanities'!F:I,6,0),R238))","v":128.13999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A238,'Updated Quanities'!F:I,7,0),R238)=\"\",R238,IFERROR(VLOOKUP('AUP Library'!A238,'Updated Quanities'!F:I,7,0),R238))","v":128.13999999999999},128.13999999999999,{"$f":"IFERROR(VLOOKUP('AUP Library'!A238,'Updated Quanities'!F:G,4,0),R238)","v":128.13999999999999}]
["607-16.06","45\"X 29\"HORIZONTAL OVAL CNC PIPE CULVERT","LF",105.63,105.63,105.63,105.63,105.63,105.63,105.63,105.63,105.63,105.63,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A239,'Updated Quanities'!F:I,4,0),R239)=\"\",R239,IFERROR(VLOOKUP('AUP Library'!A239,'Updated Quanities'!F:I,4,0),R239))","v":105.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A239,'Updated Quanities'!F:I,5,0),R239)=\"\",R239,IFERROR(VLOOKUP('AUP Library'!A239,'Updated Quanities'!F:I,5,0),R239))","v":105.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A239,'Updated Quanities'!F:I,6,0),R239)=\"\",R239,IFERROR(VLOOKUP('AUP Library'!A239,'Updated Quanities'!F:I,6,0),R239))","v":105.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A239,'Updated Quanities'!F:I,7,0),R239)=\"\",R239,IFERROR(VLOOKUP('AUP Library'!A239,'Updated Quanities'!F:I,7,0),R239))","v":105.63},105.63,{"$f":"IFERROR(VLOOKUP('AUP Library'!A239,'Updated Quanities'!F:G,4,0),R239)","v":105.63}]
["607-16.07","49\"X 32\"HORIZONTAL OVAL CNC PIPE CULVERT","LF",126.71,126.71,126.71,126.71,126.71,126.71,126.71,126.71,126.71,126.71,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A240,'Updated Quanities'!F:I,4,0),R240)=\"\",R240,IFERROR(VLOOKUP('AUP Library'!A240,'Updated Quanities'!F:I,4,0),R240))","v":126.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A240,'Updated Quanities'!F:I,5,0),R240)=\"\",R240,IFERROR(VLOOKUP('AUP Library'!A240,'Updated Quanities'!F:I,5,0),R240))","v":126.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A240,'Updated Quanities'!F:I,6,0),R240)=\"\",R240,IFERROR(VLOOKUP('AUP Library'!A240,'Updated Quanities'!F:I,6,0),R240))","v":126.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A240,'Updated Quanities'!F:I,7,0),R240)=\"\",R240,IFERROR(VLOOKUP('AUP Library'!A240,'Updated Quanities'!F:I,7,0),R240))","v":126.71},126.71,{"$f":"IFERROR(VLOOKUP('AUP Library'!A240,'Updated Quanities'!F:G,4,0),R240)","v":126.71}]
["607-16.08","53\"X 34\"HORIZONTAL OVAL CNC PIPE CULVERT","LF",137.97,137.97,137.97,137.97,137.97,137.97,137.97,137.97,137.97,137.97,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A241,'Updated Quanities'!F:I,4,0),R241)=\"\",R241,IFERROR(VLOOKUP('AUP Library'!A241,'Updated Quanities'!F:I,4,0),R241))","v":137.97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A241,'Updated Quanities'!F:I,5,0),R241)=\"\",R241,IFERROR(VLOOKUP('AUP Library'!A241,'Updated Quanities'!F:I,5,0),R241))","v":137.97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A241,'Updated Quanities'!F:I,6,0),R241)=\"\",R241,IFERROR(VLOOKUP('AUP Library'!A241,'Updated Quanities'!F:I,6,0),R241))","v":137.97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A241,'Updated Quanities'!F:I,7,0),R241)=\"\",R241,IFERROR(VLOOKUP('AUP Library'!A241,'Updated Quanities'!F:I,7,0),R241))","v":137.97},137.97,{"$f":"IFERROR(VLOOKUP('AUP Library'!A241,'Updated Quanities'!F:G,4,0),R241)","v":137.97}]
["607-16.09","60\"X 38\"HORIZONTAL OVAL CNC PIPE CULVERT","LF",165.54,165.54,165.54,165.54,165.54,165.54,165.54,165.54,165.54,165.54,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A242,'Updated Quanities'!F:I,4,0),R242)=\"\",R242,IFERROR(VLOOKUP('AUP Library'!A242,'Updated Quanities'!F:I,4,0),R242))","v":165.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A242,'Updated Quanities'!F:I,5,0),R242)=\"\",R242,IFERROR(VLOOKUP('AUP Library'!A242,'Updated Quanities'!F:I,5,0),R242))","v":165.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A242,'Updated Quanities'!F:I,6,0),R242)=\"\",R242,IFERROR(VLOOKUP('AUP Library'!A242,'Updated Quanities'!F:I,6,0),R242))","v":165.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A242,'Updated Quanities'!F:I,7,0),R242)=\"\",R242,IFERROR(VLOOKUP('AUP Library'!A242,'Updated Quanities'!F:I,7,0),R242))","v":165.54},165.54,{"$f":"IFERROR(VLOOKUP('AUP Library'!A242,'Updated Quanities'!F:G,4,0),R242)","v":165.54}]
["607-16.10","68\"X 43\"HORIZONTAL OVAL CNC PIPE CULVERT","LF",146.35,146.35,146.35,146.35,146.35,146.35,146.35,146.35,146.35,146.35,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A243,'Updated Quanities'!F:I,4,0),R243)=\"\",R243,IFERROR(VLOOKUP('AUP Library'!A243,'Updated Quanities'!F:I,4,0),R243))","v":146.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A243,'Updated Quanities'!F:I,5,0),R243)=\"\",R243,IFERROR(VLOOKUP('AUP Library'!A243,'Updated Quanities'!F:I,5,0),R243))","v":146.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A243,'Updated Quanities'!F:I,6,0),R243)=\"\",R243,IFERROR(VLOOKUP('AUP Library'!A243,'Updated Quanities'!F:I,6,0),R243))","v":146.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A243,'Updated Quanities'!F:I,7,0),R243)=\"\",R243,IFERROR(VLOOKUP('AUP Library'!A243,'Updated Quanities'!F:I,7,0),R243))","v":146.35},146.35,{"$f":"IFERROR(VLOOKUP('AUP Library'!A243,'Updated Quanities'!F:G,4,0),R243)","v":146.35}]
["607-16.11","76\"X 48\"HORIZONTAL OVAL CNC PIPE CULVERT","LF",220,220,220,220,220,220,220,220,220,220,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A244,'Updated Quanities'!F:I,4,0),R244)=\"\",R244,IFERROR(VLOOKUP('AUP Library'!A244,'Updated Quanities'!F:I,4,0),R244))","v":220},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A244,'Updated Quanities'!F:I,5,0),R244)=\"\",R244,IFERROR(VLOOKUP('AUP Library'!A244,'Updated Quanities'!F:I,5,0),R244))","v":220},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A244,'Updated Quanities'!F:I,6,0),R244)=\"\",R244,IFERROR(VLOOKUP('AUP Library'!A244,'Updated Quanities'!F:I,6,0),R244))","v":220},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A244,'Updated Quanities'!F:I,7,0),R244)=\"\",R244,IFERROR(VLOOKUP('AUP Library'!A244,'Updated Quanities'!F:I,7,0),R244))","v":220},220,{"$f":"IFERROR(VLOOKUP('AUP Library'!A244,'Updated Quanities'!F:G,4,0),R244)","v":220}]
["607-37.01","15\" CORRUGATED METAL PIPE CULVERT","LF",32.130000000000003,32.130000000000003,32.130000000000003,32.130000000000003,32.130000000000003,32.130000000000003,32.130000000000003,32.130000000000003,32.130000000000003,32.130000000000003,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A245,'Updated Quanities'!F:I,4,0),R245)=\"\",R245,IFERROR(VLOOKUP('AUP Library'!A245,'Updated Quanities'!F:I,4,0),R245))","v":32.130000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A245,'Updated Quanities'!F:I,5,0),R245)=\"\",R245,IFERROR(VLOOKUP('AUP Library'!A245,'Updated Quanities'!F:I,5,0),R245))","v":32.130000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A245,'Updated Quanities'!F:I,6,0),R245)=\"\",R245,IFERROR(VLOOKUP('AUP Library'!A245,'Updated Quanities'!F:I,6,0),R245))","v":32.130000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A245,'Updated Quanities'!F:I,7,0),R245)=\"\",R245,IFERROR(VLOOKUP('AUP Library'!A245,'Updated Quanities'!F:I,7,0),R245))","v":32.130000000000003},32.130000000000003,{"$f":"IFERROR(VLOOKUP('AUP Library'!A245,'Updated Quanities'!F:G,4,0),R245)","v":32.130000000000003}]
["607-37.02","18\" CORRUGATED METAL PIPE CULVERT","LF",33.04,33.04,33.04,33.04,33.04,33.04,33.04,33.04,33.04,33.04,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A246,'Updated Quanities'!F:I,4,0),R246)=\"\",R246,IFERROR(VLOOKUP('AUP Library'!A246,'Updated Quanities'!F:I,4,0),R246))","v":33.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A246,'Updated Quanities'!F:I,5,0),R246)=\"\",R246,IFERROR(VLOOKUP('AUP Library'!A246,'Updated Quanities'!F:I,5,0),R246))","v":33.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A246,'Updated Quanities'!F:I,6,0),R246)=\"\",R246,IFERROR(VLOOKUP('AUP Library'!A246,'Updated Quanities'!F:I,6,0),R246))","v":33.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A246,'Updated Quanities'!F:I,7,0),R246)=\"\",R246,IFERROR(VLOOKUP('AUP Library'!A246,'Updated Quanities'!F:I,7,0),R246))","v":33.04},33.04,{"$f":"IFERROR(VLOOKUP('AUP Library'!A246,'Updated Quanities'!F:G,4,0),R246)","v":33.04}]
["607-37.03","24\" CORRUGATED METAL PIPE CULVERT","LF",36.119999999999997,36.119999999999997,36.119999999999997,36.119999999999997,36.119999999999997,36.119999999999997,36.119999999999997,36.119999999999997,36.119999999999997,36.119999999999997,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A247,'Updated Quanities'!F:I,4,0),R247)=\"\",R247,IFERROR(VLOOKUP('AUP Library'!A247,'Updated Quanities'!F:I,4,0),R247))","v":36.119999999999997},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A247,'Updated Quanities'!F:I,5,0),R247)=\"\",R247,IFERROR(VLOOKUP('AUP Library'!A247,'Updated Quanities'!F:I,5,0),R247))","v":36.119999999999997},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A247,'Updated Quanities'!F:I,6,0),R247)=\"\",R247,IFERROR(VLOOKUP('AUP Library'!A247,'Updated Quanities'!F:I,6,0),R247))","v":36.119999999999997},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A247,'Updated Quanities'!F:I,7,0),R247)=\"\",R247,IFERROR(VLOOKUP('AUP Library'!A247,'Updated Quanities'!F:I,7,0),R247))","v":36.119999999999997},36.119999999999997,{"$f":"IFERROR(VLOOKUP('AUP Library'!A247,'Updated Quanities'!F:G,4,0),R247)","v":36.119999999999997}]
["607-37.04","30\" CORRUGATED METAL PIPE CULVERT","LF",59.36,59.36,59.36,59.36,59.36,59.36,59.36,59.36,59.36,59.36,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A248,'Updated Quanities'!F:I,4,0),R248)=\"\",R248,IFERROR(VLOOKUP('AUP Library'!A248,'Updated Quanities'!F:I,4,0),R248))","v":59.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A248,'Updated Quanities'!F:I,5,0),R248)=\"\",R248,IFERROR(VLOOKUP('AUP Library'!A248,'Updated Quanities'!F:I,5,0),R248))","v":59.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A248,'Updated Quanities'!F:I,6,0),R248)=\"\",R248,IFERROR(VLOOKUP('AUP Library'!A248,'Updated Quanities'!F:I,6,0),R248))","v":59.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A248,'Updated Quanities'!F:I,7,0),R248)=\"\",R248,IFERROR(VLOOKUP('AUP Library'!A248,'Updated Quanities'!F:I,7,0),R248))","v":59.36},59.36,{"$f":"IFERROR(VLOOKUP('AUP Library'!A248,'Updated Quanities'!F:G,4,0),R248)","v":59.36}]
["607-37.05","36\" CORRUGATED METAL PIPE CULVERT","LF",65.23,65.23,65.23,65.23,65.23,65.23,65.23,65.23,65.23,65.23,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A249,'Updated Quanities'!F:I,4,0),R249)=\"\",R249,IFERROR(VLOOKUP('AUP Library'!A249,'Updated Quanities'!F:I,4,0),R249))","v":65.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A249,'Updated Quanities'!F:I,5,0),R249)=\"\",R249,IFERROR(VLOOKUP('AUP Library'!A249,'Updated Quanities'!F:I,5,0),R249))","v":65.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A249,'Updated Quanities'!F:I,6,0),R249)=\"\",R249,IFERROR(VLOOKUP('AUP Library'!A249,'Updated Quanities'!F:I,6,0),R249))","v":65.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A249,'Updated Quanities'!F:I,7,0),R249)=\"\",R249,IFERROR(VLOOKUP('AUP Library'!A249,'Updated Quanities'!F:I,7,0),R249))","v":65.23},65.23,{"$f":"IFERROR(VLOOKUP('AUP Library'!A249,'Updated Quanities'!F:G,4,0),R249)","v":65.23}]
["607-37.06","42\" CORRUGATED METAL PIPE CULVERT","LF",70.78,70.78,70.78,70.78,70.78,70.78,70.78,70.78,70.78,70.78,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A250,'Updated Quanities'!F:I,4,0),R250)=\"\",R250,IFERROR(VLOOKUP('AUP Library'!A250,'Updated Quanities'!F:I,4,0),R250))","v":70.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A250,'Updated Quanities'!F:I,5,0),R250)=\"\",R250,IFERROR(VLOOKUP('AUP Library'!A250,'Updated Quanities'!F:I,5,0),R250))","v":70.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A250,'Updated Quanities'!F:I,6,0),R250)=\"\",R250,IFERROR(VLOOKUP('AUP Library'!A250,'Updated Quanities'!F:I,6,0),R250))","v":70.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A250,'Updated Quanities'!F:I,7,0),R250)=\"\",R250,IFERROR(VLOOKUP('AUP Library'!A250,'Updated Quanities'!F:I,7,0),R250))","v":70.78},70.78,{"$f":"IFERROR(VLOOKUP('AUP Library'!A250,'Updated Quanities'!F:G,4,0),R250)","v":70.78}]
["607-37.07","48\" CORRUGATED METAL PIPE CULVERT","LF",94.67,94.67,94.67,94.67,94.67,94.67,94.67,94.67,94.67,94.67,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A251,'Updated Quanities'!F:I,4,0),R251)=\"\",R251,IFERROR(VLOOKUP('AUP Library'!A251,'Updated Quanities'!F:I,4,0),R251))","v":94.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A251,'Updated Quanities'!F:I,5,0),R251)=\"\",R251,IFERROR(VLOOKUP('AUP Library'!A251,'Updated Quanities'!F:I,5,0),R251))","v":94.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A251,'Updated Quanities'!F:I,6,0),R251)=\"\",R251,IFERROR(VLOOKUP('AUP Library'!A251,'Updated Quanities'!F:I,6,0),R251))","v":94.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A251,'Updated Quanities'!F:I,7,0),R251)=\"\",R251,IFERROR(VLOOKUP('AUP Library'!A251,'Updated Quanities'!F:I,7,0),R251))","v":94.67},94.67,{"$f":"IFERROR(VLOOKUP('AUP Library'!A251,'Updated Quanities'!F:G,4,0),R251)","v":94.67}]
["607-37.08","54\" CORRUGATED METAL PIPE CULVERT","LF",80,80,80,80,80,80,80,80,80,80,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A252,'Updated Quanities'!F:I,4,0),R252)=\"\",R252,IFERROR(VLOOKUP('AUP Library'!A252,'Updated Quanities'!F:I,4,0),R252))","v":80},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A252,'Updated Quanities'!F:I,5,0),R252)=\"\",R252,IFERROR(VLOOKUP('AUP Library'!A252,'Updated Quanities'!F:I,5,0),R252))","v":80},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A252,'Updated Quanities'!F:I,6,0),R252)=\"\",R252,IFERROR(VLOOKUP('AUP Library'!A252,'Updated Quanities'!F:I,6,0),R252))","v":80},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A252,'Updated Quanities'!F:I,7,0),R252)=\"\",R252,IFERROR(VLOOKUP('AUP Library'!A252,'Updated Quanities'!F:I,7,0),R252))","v":80},80,{"$f":"IFERROR(VLOOKUP('AUP Library'!A252,'Updated Quanities'!F:G,4,0),R252)","v":80}]
["607-37.09","60\" CORRUGATED METAL PIPE CULVERT","LF",97,97,97,97,97,97,97,97,97,97,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A253,'Updated Quanities'!F:I,4,0),R253)=\"\",R253,IFERROR(VLOOKUP('AUP Library'!A253,'Updated Quanities'!F:I,4,0),R253))","v":97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A253,'Updated Quanities'!F:I,5,0),R253)=\"\",R253,IFERROR(VLOOKUP('AUP Library'!A253,'Updated Quanities'!F:I,5,0),R253))","v":97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A253,'Updated Quanities'!F:I,6,0),R253)=\"\",R253,IFERROR(VLOOKUP('AUP Library'!A253,'Updated Quanities'!F:I,6,0),R253))","v":97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A253,'Updated Quanities'!F:I,7,0),R253)=\"\",R253,IFERROR(VLOOKUP('AUP Library'!A253,'Updated Quanities'!F:I,7,0),R253))","v":97},97,{"$f":"IFERROR(VLOOKUP('AUP Library'!A253,'Updated Quanities'!F:G,4,0),R253)","v":97}]
["607-37.11","72\" CORRUGATED METAL PIPE CULVERT","LF",150,150,150,150,150,150,150,150,150,150,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A254,'Updated Quanities'!F:I,4,0),R254)=\"\",R254,IFERROR(VLOOKUP('AUP Library'!A254,'Updated Quanities'!F:I,4,0),R254))","v":150},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A254,'Updated Quanities'!F:I,5,0),R254)=\"\",R254,IFERROR(VLOOKUP('AUP Library'!A254,'Updated Quanities'!F:I,5,0),R254))","v":150},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A254,'Updated Quanities'!F:I,6,0),R254)=\"\",R254,IFERROR(VLOOKUP('AUP Library'!A254,'Updated Quanities'!F:I,6,0),R254))","v":150},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A254,'Updated Quanities'!F:I,7,0),R254)=\"\",R254,IFERROR(VLOOKUP('AUP Library'!A254,'Updated Quanities'!F:I,7,0),R254))","v":150},150,{"$f":"IFERROR(VLOOKUP('AUP Library'!A254,'Updated Quanities'!F:G,4,0),R254)","v":150}]
["607-37.12","78\" CORRUGATED METAL PIPE CULVERT","LF",80,80,80,80,80,80,80,80,80,80,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A255,'Updated Quanities'!F:I,4,0),R255)=\"\",R255,IFERROR(VLOOKUP('AUP Library'!A255,'Updated Quanities'!F:I,4,0),R255))","v":80},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A255,'Updated Quanities'!F:I,5,0),R255)=\"\",R255,IFERROR(VLOOKUP('AUP Library'!A255,'Updated Quanities'!F:I,5,0),R255))","v":80},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A255,'Updated Quanities'!F:I,6,0),R255)=\"\",R255,IFERROR(VLOOKUP('AUP Library'!A255,'Updated Quanities'!F:I,6,0),R255))","v":80},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A255,'Updated Quanities'!F:I,7,0),R255)=\"\",R255,IFERROR(VLOOKUP('AUP Library'!A255,'Updated Quanities'!F:I,7,0),R255))","v":80},80,{"$f":"IFERROR(VLOOKUP('AUP Library'!A255,'Updated Quanities'!F:G,4,0),R255)","v":80}]
["607-37.13","84\" CORRUGATED METAL PIPE CULVERT","LF",218,218,218,218,218,218,218,218,218,218,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A256,'Updated Quanities'!F:I,4,0),R256)=\"\",R256,IFERROR(VLOOKUP('AUP Library'!A256,'Updated Quanities'!F:I,4,0),R256))","v":218},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A256,'Updated Quanities'!F:I,5,0),R256)=\"\",R256,IFERROR(VLOOKUP('AUP Library'!A256,'Updated Quanities'!F:I,5,0),R256))","v":218},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A256,'Updated Quanities'!F:I,6,0),R256)=\"\",R256,IFERROR(VLOOKUP('AUP Library'!A256,'Updated Quanities'!F:I,6,0),R256))","v":218},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A256,'Updated Quanities'!F:I,7,0),R256)=\"\",R256,IFERROR(VLOOKUP('AUP Library'!A256,'Updated Quanities'!F:I,7,0),R256))","v":218},218,{"$f":"IFERROR(VLOOKUP('AUP Library'!A256,'Updated Quanities'!F:G,4,0),R256)","v":218}]
["607-39.01","15\" Pipe Culvert (Side Drain)","LF",32.99,32.99,32.99,32.99,32.99,32.99,32.99,32.99,32.99,32.99,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A257,'Updated Quanities'!F:I,4,0),R257)=\"\",R257,IFERROR(VLOOKUP('AUP Library'!A257,'Updated Quanities'!F:I,4,0),R257))","v":32.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A257,'Updated Quanities'!F:I,5,0),R257)=\"\",R257,IFERROR(VLOOKUP('AUP Library'!A257,'Updated Quanities'!F:I,5,0),R257))","v":32.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A257,'Updated Quanities'!F:I,6,0),R257)=\"\",R257,IFERROR(VLOOKUP('AUP Library'!A257,'Updated Quanities'!F:I,6,0),R257))","v":32.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A257,'Updated Quanities'!F:I,7,0),R257)=\"\",R257,IFERROR(VLOOKUP('AUP Library'!A257,'Updated Quanities'!F:I,7,0),R257))","v":32.99},32.99,{"$f":"IFERROR(VLOOKUP('AUP Library'!A257,'Updated Quanities'!F:G,4,0),R257)","v":32.99}]
["607-39.02","18\" Pipe Culvert (Side Drain)","LF",32.99,32.99,32.99,32.99,32.99,32.99,32.99,32.99,32.99,32.99,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A258,'Updated Quanities'!F:I,4,0),R258)=\"\",R258,IFERROR(VLOOKUP('AUP Library'!A258,'Updated Quanities'!F:I,4,0),R258))","v":32.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A258,'Updated Quanities'!F:I,5,0),R258)=\"\",R258,IFERROR(VLOOKUP('AUP Library'!A258,'Updated Quanities'!F:I,5,0),R258))","v":32.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A258,'Updated Quanities'!F:I,6,0),R258)=\"\",R258,IFERROR(VLOOKUP('AUP Library'!A258,'Updated Quanities'!F:I,6,0),R258))","v":32.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A258,'Updated Quanities'!F:I,7,0),R258)=\"\",R258,IFERROR(VLOOKUP('AUP Library'!A258,'Updated Quanities'!F:I,7,0),R258))","v":32.99},32.99,{"$f":"IFERROR(VLOOKUP('AUP Library'!A258,'Updated Quanities'!F:G,4,0),R258)","v":32.99}]
["607-39.03","24\" Pipe Culvert (Side Drain)","LF",42.76,42.76,42.76,42.76,42.76,42.76,42.76,42.76,42.76,42.76,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A259,'Updated Quanities'!F:I,4,0),R259)=\"\",R259,IFERROR(VLOOKUP('AUP Library'!A259,'Updated Quanities'!F:I,4,0),R259))","v":42.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A259,'Updated Quanities'!F:I,5,0),R259)=\"\",R259,IFERROR(VLOOKUP('AUP Library'!A259,'Updated Quanities'!F:I,5,0),R259))","v":42.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A259,'Updated Quanities'!F:I,6,0),R259)=\"\",R259,IFERROR(VLOOKUP('AUP Library'!A259,'Updated Quanities'!F:I,6,0),R259))","v":42.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A259,'Updated Quanities'!F:I,7,0),R259)=\"\",R259,IFERROR(VLOOKUP('AUP Library'!A259,'Updated Quanities'!F:I,7,0),R259))","v":42.76},42.76,{"$f":"IFERROR(VLOOKUP('AUP Library'!A259,'Updated Quanities'!F:G,4,0),R259)","v":42.76}]
["607-39.04","30\" Pipe Culvert (Side Drain)","LF",55.2,55.2,55.2,55.2,55.2,55.2,55.2,55.2,55.2,55.2,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A260,'Updated Quanities'!F:I,4,0),R260)=\"\",R260,IFERROR(VLOOKUP('AUP Library'!A260,'Updated Quanities'!F:I,4,0),R260))","v":55.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A260,'Updated Quanities'!F:I,5,0),R260)=\"\",R260,IFERROR(VLOOKUP('AUP Library'!A260,'Updated Quanities'!F:I,5,0),R260))","v":55.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A260,'Updated Quanities'!F:I,6,0),R260)=\"\",R260,IFERROR(VLOOKUP('AUP Library'!A260,'Updated Quanities'!F:I,6,0),R260))","v":55.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A260,'Updated Quanities'!F:I,7,0),R260)=\"\",R260,IFERROR(VLOOKUP('AUP Library'!A260,'Updated Quanities'!F:I,7,0),R260))","v":55.2},55.2,{"$f":"IFERROR(VLOOKUP('AUP Library'!A260,'Updated Quanities'!F:G,4,0),R260)","v":55.2}]
["607-39.05","36\" Pipe Culvert (Side Drain)","LF",84.03,84.03,84.03,84.03,84.03,84.03,84.03,84.03,84.03,84.03,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A261,'Updated Quanities'!F:I,4,0),R261)=\"\",R261,IFERROR(VLOOKUP('AUP Library'!A261,'Updated Quanities'!F:I,4,0),R261))","v":84.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A261,'Updated Quanities'!F:I,5,0),R261)=\"\",R261,IFERROR(VLOOKUP('AUP Library'!A261,'Updated Quanities'!F:I,5,0),R261))","v":84.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A261,'Updated Quanities'!F:I,6,0),R261)=\"\",R261,IFERROR(VLOOKUP('AUP Library'!A261,'Updated Quanities'!F:I,6,0),R261))","v":84.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A261,'Updated Quanities'!F:I,7,0),R261)=\"\",R261,IFERROR(VLOOKUP('AUP Library'!A261,'Updated Quanities'!F:I,7,0),R261))","v":84.03},84.03,{"$f":"IFERROR(VLOOKUP('AUP Library'!A261,'Updated Quanities'!F:G,4,0),R261)","v":84.03}]
["607-39.06","42\" Pipe Culvert (Side Drain)","LF",74.45,74.45,74.45,74.45,74.45,74.45,74.45,74.45,74.45,74.45,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A262,'Updated Quanities'!F:I,4,0),R262)=\"\",R262,IFERROR(VLOOKUP('AUP Library'!A262,'Updated Quanities'!F:I,4,0),R262))","v":74.45},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A262,'Updated Quanities'!F:I,5,0),R262)=\"\",R262,IFERROR(VLOOKUP('AUP Library'!A262,'Updated Quanities'!F:I,5,0),R262))","v":74.45},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A262,'Updated Quanities'!F:I,6,0),R262)=\"\",R262,IFERROR(VLOOKUP('AUP Library'!A262,'Updated Quanities'!F:I,6,0),R262))","v":74.45},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A262,'Updated Quanities'!F:I,7,0),R262)=\"\",R262,IFERROR(VLOOKUP('AUP Library'!A262,'Updated Quanities'!F:I,7,0),R262))","v":74.45},74.45,{"$f":"IFERROR(VLOOKUP('AUP Library'!A262,'Updated Quanities'!F:G,4,0),R262)","v":74.45}]
["607-39.07","48\" Pipe Culvert (Side Drain)","LF",91.42,91.42,91.42,91.42,91.42,91.42,91.42,91.42,91.42,91.42,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A263,'Updated Quanities'!F:I,4,0),R263)=\"\",R263,IFERROR(VLOOKUP('AUP Library'!A263,'Updated Quanities'!F:I,4,0),R263))","v":91.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A263,'Updated Quanities'!F:I,5,0),R263)=\"\",R263,IFERROR(VLOOKUP('AUP Library'!A263,'Updated Quanities'!F:I,5,0),R263))","v":91.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A263,'Updated Quanities'!F:I,6,0),R263)=\"\",R263,IFERROR(VLOOKUP('AUP Library'!A263,'Updated Quanities'!F:I,6,0),R263))","v":91.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A263,'Updated Quanities'!F:I,7,0),R263)=\"\",R263,IFERROR(VLOOKUP('AUP Library'!A263,'Updated Quanities'!F:I,7,0),R263))","v":91.42},91.42,{"$f":"IFERROR(VLOOKUP('AUP Library'!A263,'Updated Quanities'!F:G,4,0),R263)","v":91.42}]
["607-39.08","54\" Pipe Culvert (Side Drain)","LF",118.86,118.86,118.86,118.86,118.86,118.86,118.86,118.86,118.86,118.86,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A264,'Updated Quanities'!F:I,4,0),R264)=\"\",R264,IFERROR(VLOOKUP('AUP Library'!A264,'Updated Quanities'!F:I,4,0),R264))","v":118.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A264,'Updated Quanities'!F:I,5,0),R264)=\"\",R264,IFERROR(VLOOKUP('AUP Library'!A264,'Updated Quanities'!F:I,5,0),R264))","v":118.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A264,'Updated Quanities'!F:I,6,0),R264)=\"\",R264,IFERROR(VLOOKUP('AUP Library'!A264,'Updated Quanities'!F:I,6,0),R264))","v":118.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A264,'Updated Quanities'!F:I,7,0),R264)=\"\",R264,IFERROR(VLOOKUP('AUP Library'!A264,'Updated Quanities'!F:I,7,0),R264))","v":118.86},118.86,{"$f":"IFERROR(VLOOKUP('AUP Library'!A264,'Updated Quanities'!F:G,4,0),R264)","v":118.86}]
["607-39.09","60\" Pipe Culvert (Side Drain)","LF",91.42,91.42,91.42,91.42,91.42,91.42,91.42,91.42,91.42,91.42,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A265,'Updated Quanities'!F:I,4,0),R265)=\"\",R265,IFERROR(VLOOKUP('AUP Library'!A265,'Updated Quanities'!F:I,4,0),R265))","v":91.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A265,'Updated Quanities'!F:I,5,0),R265)=\"\",R265,IFERROR(VLOOKUP('AUP Library'!A265,'Updated Quanities'!F:I,5,0),R265))","v":91.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A265,'Updated Quanities'!F:I,6,0),R265)=\"\",R265,IFERROR(VLOOKUP('AUP Library'!A265,'Updated Quanities'!F:I,6,0),R265))","v":91.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A265,'Updated Quanities'!F:I,7,0),R265)=\"\",R265,IFERROR(VLOOKUP('AUP Library'!A265,'Updated Quanities'!F:I,7,0),R265))","v":91.42},91.42,{"$f":"IFERROR(VLOOKUP('AUP Library'!A265,'Updated Quanities'!F:G,4,0),R265)","v":91.42}]
["607-39.10","66\" Pipe Culvert (Side Drain)","LF",97,97,97,97,97,97,97,97,97,97,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A266,'Updated Quanities'!F:I,4,0),R266)=\"\",R266,IFERROR(VLOOKUP('AUP Library'!A266,'Updated Quanities'!F:I,4,0),R266))","v":97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A266,'Updated Quanities'!F:I,5,0),R266)=\"\",R266,IFERROR(VLOOKUP('AUP Library'!A266,'Updated Quanities'!F:I,5,0),R266))","v":97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A266,'Updated Quanities'!F:I,6,0),R266)=\"\",R266,IFERROR(VLOOKUP('AUP Library'!A266,'Updated Quanities'!F:I,6,0),R266))","v":97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A266,'Updated Quanities'!F:I,7,0),R266)=\"\",R266,IFERROR(VLOOKUP('AUP Library'!A266,'Updated Quanities'!F:I,7,0),R266))","v":97},97,{"$f":"IFERROR(VLOOKUP('AUP Library'!A266,'Updated Quanities'!F:G,4,0),R266)","v":97}]
["607-45.02","18\" Slotted Drain Pipe","LF",186.95,186.95,186.95,186.95,186.95,186.95,186.95,186.95,186.95,186.95,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A267,'Updated Quanities'!F:I,4,0),R267)=\"\",R267,IFERROR(VLOOKUP('AUP Library'!A267,'Updated Quanities'!F:I,4,0),R267))","v":186.95},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A267,'Updated Quanities'!F:I,5,0),R267)=\"\",R267,IFERROR(VLOOKUP('AUP Library'!A267,'Updated Quanities'!F:I,5,0),R267))","v":186.95},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A267,'Updated Quanities'!F:I,6,0),R267)=\"\",R267,IFERROR(VLOOKUP('AUP Library'!A267,'Updated Quanities'!F:I,6,0),R267))","v":186.95},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A267,'Updated Quanities'!F:I,7,0),R267)=\"\",R267,IFERROR(VLOOKUP('AUP Library'!A267,'Updated Quanities'!F:I,7,0),R267))","v":186.95},186.95,{"$f":"IFERROR(VLOOKUP('AUP Library'!A267,'Updated Quanities'!F:G,4,0),R267)","v":186.95}]
["607-57.01","Reinforced Concrete Pipe Arch (22\" x 13\")","LF",145.85,145.85,145.85,145.85,145.85,145.85,145.85,145.85,145.85,145.85,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A268,'Updated Quanities'!F:I,4,0),R268)=\"\",R268,IFERROR(VLOOKUP('AUP Library'!A268,'Updated Quanities'!F:I,4,0),R268))","v":145.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A268,'Updated Quanities'!F:I,5,0),R268)=\"\",R268,IFERROR(VLOOKUP('AUP Library'!A268,'Updated Quanities'!F:I,5,0),R268))","v":145.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A268,'Updated Quanities'!F:I,6,0),R268)=\"\",R268,IFERROR(VLOOKUP('AUP Library'!A268,'Updated Quanities'!F:I,6,0),R268))","v":145.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A268,'Updated Quanities'!F:I,7,0),R268)=\"\",R268,IFERROR(VLOOKUP('AUP Library'!A268,'Updated Quanities'!F:I,7,0),R268))","v":145.85},145.85,{"$f":"IFERROR(VLOOKUP('AUP Library'!A268,'Updated Quanities'!F:G,4,0),R268)","v":145.85}]
["607-57.02","Reinforced Concrete Pipe Arch (29\" x 18\")","LF",75,75,75,75,75,75,75,75,75,75,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A269,'Updated Quanities'!F:I,4,0),R269)=\"\",R269,IFERROR(VLOOKUP('AUP Library'!A269,'Updated Quanities'!F:I,4,0),R269))","v":75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A269,'Updated Quanities'!F:I,5,0),R269)=\"\",R269,IFERROR(VLOOKUP('AUP Library'!A269,'Updated Quanities'!F:I,5,0),R269))","v":75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A269,'Updated Quanities'!F:I,6,0),R269)=\"\",R269,IFERROR(VLOOKUP('AUP Library'!A269,'Updated Quanities'!F:I,6,0),R269))","v":75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A269,'Updated Quanities'!F:I,7,0),R269)=\"\",R269,IFERROR(VLOOKUP('AUP Library'!A269,'Updated Quanities'!F:I,7,0),R269))","v":75},75,{"$f":"IFERROR(VLOOKUP('AUP Library'!A269,'Updated Quanities'!F:G,4,0),R269)","v":75}]
["607-57.07","Reinforced Concrete Pipe Arch (65\" x 40\")","LF",235,235,235,235,235,235,235,235,235,235,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A270,'Updated Quanities'!F:I,4,0),R270)=\"\",R270,IFERROR(VLOOKUP('AUP Library'!A270,'Updated Quanities'!F:I,4,0),R270))","v":235},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A270,'Updated Quanities'!F:I,5,0),R270)=\"\",R270,IFERROR(VLOOKUP('AUP Library'!A270,'Updated Quanities'!F:I,5,0),R270))","v":235},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A270,'Updated Quanities'!F:I,6,0),R270)=\"\",R270,IFERROR(VLOOKUP('AUP Library'!A270,'Updated Quanities'!F:I,6,0),R270))","v":235},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A270,'Updated Quanities'!F:I,7,0),R270)=\"\",R270,IFERROR(VLOOKUP('AUP Library'!A270,'Updated Quanities'!F:I,7,0),R270))","v":235},235,{"$f":"IFERROR(VLOOKUP('AUP Library'!A270,'Updated Quanities'!F:G,4,0),R270)","v":235}]
["610-07.03","15\" Pipe Drain (Bridge Drain)","LF",31.22,31.22,31.22,31.22,31.22,31.22,31.22,31.22,31.22,31.22,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A271,'Updated Quanities'!F:I,4,0),R271)=\"\",R271,IFERROR(VLOOKUP('AUP Library'!A271,'Updated Quanities'!F:I,4,0),R271))","v":31.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A271,'Updated Quanities'!F:I,5,0),R271)=\"\",R271,IFERROR(VLOOKUP('AUP Library'!A271,'Updated Quanities'!F:I,5,0),R271))","v":31.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A271,'Updated Quanities'!F:I,6,0),R271)=\"\",R271,IFERROR(VLOOKUP('AUP Library'!A271,'Updated Quanities'!F:I,6,0),R271))","v":31.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A271,'Updated Quanities'!F:I,7,0),R271)=\"\",R271,IFERROR(VLOOKUP('AUP Library'!A271,'Updated Quanities'!F:I,7,0),R271))","v":31.22},31.22,{"$f":"IFERROR(VLOOKUP('AUP Library'!A271,'Updated Quanities'!F:G,4,0),R271)","v":31.22}]
["611-01.02","Manholes, >4'-8' Depth","EACH",3787.33,3787.33,3787.33,3787.33,3787.33,3787.33,3787.33,3787.33,3787.33,3787.33,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A272,'Updated Quanities'!F:I,4,0),R272)=\"\",R272,IFERROR(VLOOKUP('AUP Library'!A272,'Updated Quanities'!F:I,4,0),R272))","v":3787.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A272,'Updated Quanities'!F:I,5,0),R272)=\"\",R272,IFERROR(VLOOKUP('AUP Library'!A272,'Updated Quanities'!F:I,5,0),R272))","v":3787.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A272,'Updated Quanities'!F:I,6,0),R272)=\"\",R272,IFERROR(VLOOKUP('AUP Library'!A272,'Updated Quanities'!F:I,6,0),R272))","v":3787.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A272,'Updated Quanities'!F:I,7,0),R272)=\"\",R272,IFERROR(VLOOKUP('AUP Library'!A272,'Updated Quanities'!F:I,7,0),R272))","v":3787.33},3787.33,{"$f":"IFERROR(VLOOKUP('AUP Library'!A272,'Updated Quanities'!F:G,4,0),R272)","v":3787.33}]
["611-01.03","Manholes, >8'-12' Depth","EACH",5454.05,5454.05,5454.05,5454.05,5454.05,5454.05,5454.05,5454.05,5454.05,5454.05,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A273,'Updated Quanities'!F:I,4,0),R273)=\"\",R273,IFERROR(VLOOKUP('AUP Library'!A273,'Updated Quanities'!F:I,4,0),R273))","v":5454.05},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A273,'Updated Quanities'!F:I,5,0),R273)=\"\",R273,IFERROR(VLOOKUP('AUP Library'!A273,'Updated Quanities'!F:I,5,0),R273))","v":5454.05},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A273,'Updated Quanities'!F:I,6,0),R273)=\"\",R273,IFERROR(VLOOKUP('AUP Library'!A273,'Updated Quanities'!F:I,6,0),R273))","v":5454.05},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A273,'Updated Quanities'!F:I,7,0),R273)=\"\",R273,IFERROR(VLOOKUP('AUP Library'!A273,'Updated Quanities'!F:I,7,0),R273))","v":5454.05},5454.05,{"$f":"IFERROR(VLOOKUP('AUP Library'!A273,'Updated Quanities'!F:G,4,0),R273)","v":5454.05}]
["611-01.04","Manholes, >12'-16' Depth","EACH",6384.25,6384.25,6384.25,6384.25,6384.25,6384.25,6384.25,6384.25,6384.25,6384.25,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A274,'Updated Quanities'!F:I,4,0),R274)=\"\",R274,IFERROR(VLOOKUP('AUP Library'!A274,'Updated Quanities'!F:I,4,0),R274))","v":6384.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A274,'Updated Quanities'!F:I,5,0),R274)=\"\",R274,IFERROR(VLOOKUP('AUP Library'!A274,'Updated Quanities'!F:I,5,0),R274))","v":6384.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A274,'Updated Quanities'!F:I,6,0),R274)=\"\",R274,IFERROR(VLOOKUP('AUP Library'!A274,'Updated Quanities'!F:I,6,0),R274))","v":6384.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A274,'Updated Quanities'!F:I,7,0),R274)=\"\",R274,IFERROR(VLOOKUP('AUP Library'!A274,'Updated Quanities'!F:I,7,0),R274))","v":6384.25},6384.25,{"$f":"IFERROR(VLOOKUP('AUP Library'!A274,'Updated Quanities'!F:G,4,0),R274)","v":6384.25}]
["611-01.05","Manholes, >16'-20' Depth","EACH",18038.5,18038.5,18038.5,18038.5,18038.5,18038.5,18038.5,18038.5,18038.5,18038.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A275,'Updated Quanities'!F:I,4,0),R275)=\"\",R275,IFERROR(VLOOKUP('AUP Library'!A275,'Updated Quanities'!F:I,4,0),R275))","v":18038.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A275,'Updated Quanities'!F:I,5,0),R275)=\"\",R275,IFERROR(VLOOKUP('AUP Library'!A275,'Updated Quanities'!F:I,5,0),R275))","v":18038.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A275,'Updated Quanities'!F:I,6,0),R275)=\"\",R275,IFERROR(VLOOKUP('AUP Library'!A275,'Updated Quanities'!F:I,6,0),R275))","v":18038.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A275,'Updated Quanities'!F:I,7,0),R275)=\"\",R275,IFERROR(VLOOKUP('AUP Library'!A275,'Updated Quanities'!F:I,7,0),R275))","v":18038.5},18038.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A275,'Updated Quanities'!F:G,4,0),R275)","v":18038.5}]
["611-02.10","Junction Box, Type 1","EACH",2548.5300000000002,2548.5300000000002,2548.5300000000002,2548.5300000000002,2548.5300000000002,2548.5300000000002,2548.5300000000002,2548.5300000000002,2548.5300000000002,2548.5300000000002,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A276,'Updated Quanities'!F:I,4,0),R276)=\"\",R276,IFERROR(VLOOKUP('AUP Library'!A276,'Updated Quanities'!F:I,4,0),R276))","v":2548.5300000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A276,'Updated Quanities'!F:I,5,0),R276)=\"\",R276,IFERROR(VLOOKUP('AUP Library'!A276,'Updated Quanities'!F:I,5,0),R276))","v":2548.5300000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A276,'Updated Quanities'!F:I,6,0),R276)=\"\",R276,IFERROR(VLOOKUP('AUP Library'!A276,'Updated Quanities'!F:I,6,0),R276))","v":2548.5300000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A276,'Updated Quanities'!F:I,7,0),R276)=\"\",R276,IFERROR(VLOOKUP('AUP Library'!A276,'Updated Quanities'!F:I,7,0),R276))","v":2548.5300000000002},2548.5300000000002,{"$f":"IFERROR(VLOOKUP('AUP Library'!A276,'Updated Quanities'!F:G,4,0),R276)","v":2548.5300000000002}]
["611-02.11","Junction Box, Type 2","EACH",4262.26,4262.26,4262.26,4262.26,4262.26,4262.26,4262.26,4262.26,4262.26,4262.26,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A277,'Updated Quanities'!F:I,4,0),R277)=\"\",R277,IFERROR(VLOOKUP('AUP Library'!A277,'Updated Quanities'!F:I,4,0),R277))","v":4262.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A277,'Updated Quanities'!F:I,5,0),R277)=\"\",R277,IFERROR(VLOOKUP('AUP Library'!A277,'Updated Quanities'!F:I,5,0),R277))","v":4262.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A277,'Updated Quanities'!F:I,6,0),R277)=\"\",R277,IFERROR(VLOOKUP('AUP Library'!A277,'Updated Quanities'!F:I,6,0),R277))","v":4262.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A277,'Updated Quanities'!F:I,7,0),R277)=\"\",R277,IFERROR(VLOOKUP('AUP Library'!A277,'Updated Quanities'!F:I,7,0),R277))","v":4262.26},4262.26,{"$f":"IFERROR(VLOOKUP('AUP Library'!A277,'Updated Quanities'!F:G,4,0),R277)","v":4262.26}]
["611-02.12","Junction Box, Type 3","EACH",5980.78,5980.78,5980.78,5980.78,5980.78,5980.78,5980.78,5980.78,5980.78,5980.78,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A278,'Updated Quanities'!F:I,4,0),R278)=\"\",R278,IFERROR(VLOOKUP('AUP Library'!A278,'Updated Quanities'!F:I,4,0),R278))","v":5980.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A278,'Updated Quanities'!F:I,5,0),R278)=\"\",R278,IFERROR(VLOOKUP('AUP Library'!A278,'Updated Quanities'!F:I,5,0),R278))","v":5980.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A278,'Updated Quanities'!F:I,6,0),R278)=\"\",R278,IFERROR(VLOOKUP('AUP Library'!A278,'Updated Quanities'!F:I,6,0),R278))","v":5980.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A278,'Updated Quanities'!F:I,7,0),R278)=\"\",R278,IFERROR(VLOOKUP('AUP Library'!A278,'Updated Quanities'!F:I,7,0),R278))","v":5980.78},5980.78,{"$f":"IFERROR(VLOOKUP('AUP Library'!A278,'Updated Quanities'!F:G,4,0),R278)","v":5980.78}]
["611-02.13","Junction Box, Type 4","EACH",9504.81,9504.81,9504.81,9504.81,9504.81,9504.81,9504.81,9504.81,9504.81,9504.81,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A279,'Updated Quanities'!F:I,4,0),R279)=\"\",R279,IFERROR(VLOOKUP('AUP Library'!A279,'Updated Quanities'!F:I,4,0),R279))","v":9504.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A279,'Updated Quanities'!F:I,5,0),R279)=\"\",R279,IFERROR(VLOOKUP('AUP Library'!A279,'Updated Quanities'!F:I,5,0),R279))","v":9504.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A279,'Updated Quanities'!F:I,6,0),R279)=\"\",R279,IFERROR(VLOOKUP('AUP Library'!A279,'Updated Quanities'!F:I,6,0),R279))","v":9504.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A279,'Updated Quanities'!F:I,7,0),R279)=\"\",R279,IFERROR(VLOOKUP('AUP Library'!A279,'Updated Quanities'!F:I,7,0),R279))","v":9504.81},9504.81,{"$f":"IFERROR(VLOOKUP('AUP Library'!A279,'Updated Quanities'!F:G,4,0),R279)","v":9504.81}]
["611-02.14","Junction Box, Type 5","EACH",30385,30385,30385,30385,30385,30385,30385,30385,30385,30385,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A280,'Updated Quanities'!F:I,4,0),R280)=\"\",R280,IFERROR(VLOOKUP('AUP Library'!A280,'Updated Quanities'!F:I,4,0),R280))","v":30385},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A280,'Updated Quanities'!F:I,5,0),R280)=\"\",R280,IFERROR(VLOOKUP('AUP Library'!A280,'Updated Quanities'!F:I,5,0),R280))","v":30385},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A280,'Updated Quanities'!F:I,6,0),R280)=\"\",R280,IFERROR(VLOOKUP('AUP Library'!A280,'Updated Quanities'!F:I,6,0),R280))","v":30385},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A280,'Updated Quanities'!F:I,7,0),R280)=\"\",R280,IFERROR(VLOOKUP('AUP Library'!A280,'Updated Quanities'!F:I,7,0),R280))","v":30385},30385,{"$f":"IFERROR(VLOOKUP('AUP Library'!A280,'Updated Quanities'!F:G,4,0),R280)","v":30385}]
["611-07.01","Class A Concrete (Pipe Endwalls)","CY","561.5","508.82","572.96","632.53","632.53",571.42999999999995,614.71,659.74,591.11,786.17,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A281,'Updated Quanities'!F:I,4,0),R281)=\"\",R281,IFERROR(VLOOKUP('AUP Library'!A281,'Updated Quanities'!F:I,4,0),R281))","v":780.14},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A281,'Updated Quanities'!F:I,5,0),R281)=\"\",R281,IFERROR(VLOOKUP('AUP Library'!A281,'Updated Quanities'!F:I,5,0),R281))","v":780.14},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A281,'Updated Quanities'!F:I,6,0),R281)=\"\",R281,IFERROR(VLOOKUP('AUP Library'!A281,'Updated Quanities'!F:I,6,0),R281))","v":780.14},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A281,'Updated Quanities'!F:I,7,0),R281)=\"\",R281,IFERROR(VLOOKUP('AUP Library'!A281,'Updated Quanities'!F:I,7,0),R281))","v":780.14},780.14,{"$f":"IFERROR(VLOOKUP('AUP Library'!A281,'Updated Quanities'!F:G,4,0),R281)","v":780.14}]
["611-07.02","Steel Bar Reinforcement (Pipe Endwalls)","LB",1.27,1.29,1.24,1.41,1.41,1.2,1.18,1.25,1.61,1.61,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A282,'Updated Quanities'!F:I,4,0),R282)=\"\",R282,IFERROR(VLOOKUP('AUP Library'!A282,'Updated Quanities'!F:I,4,0),R282))","v":1.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A282,'Updated Quanities'!F:I,5,0),R282)=\"\",R282,IFERROR(VLOOKUP('AUP Library'!A282,'Updated Quanities'!F:I,5,0),R282))","v":1.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A282,'Updated Quanities'!F:I,6,0),R282)=\"\",R282,IFERROR(VLOOKUP('AUP Library'!A282,'Updated Quanities'!F:I,6,0),R282))","v":1.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A282,'Updated Quanities'!F:I,7,0),R282)=\"\",R282,IFERROR(VLOOKUP('AUP Library'!A282,'Updated Quanities'!F:I,7,0),R282))","v":1.54},1.54,{"$f":"IFERROR(VLOOKUP('AUP Library'!A282,'Updated Quanities'!F:G,4,0),R282)","v":1.54}]
["611-07.03","Structural Steel (Pipe Endwalls)","LB",4.7,4.7,4.7,4.7,4.7,4.7,4.7,4.7,4.7,4.7,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A283,'Updated Quanities'!F:I,4,0),R283)=\"\",R283,IFERROR(VLOOKUP('AUP Library'!A283,'Updated Quanities'!F:I,4,0),R283))","v":4.7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A283,'Updated Quanities'!F:I,5,0),R283)=\"\",R283,IFERROR(VLOOKUP('AUP Library'!A283,'Updated Quanities'!F:I,5,0),R283))","v":4.7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A283,'Updated Quanities'!F:I,6,0),R283)=\"\",R283,IFERROR(VLOOKUP('AUP Library'!A283,'Updated Quanities'!F:I,6,0),R283))","v":4.7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A283,'Updated Quanities'!F:I,7,0),R283)=\"\",R283,IFERROR(VLOOKUP('AUP Library'!A283,'Updated Quanities'!F:I,7,0),R283))","v":4.7},4.7,{"$f":"IFERROR(VLOOKUP('AUP Library'!A283,'Updated Quanities'!F:G,4,0),R283)","v":4.7}]
["611-07.51","15\" Endwall (Cross Drain) 3:1","EA",1937.27,1937.27,1937.27,1937.27,1937.27,1937.27,1937.27,1937.27,1937.27,1937.27,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A284,'Updated Quanities'!F:I,4,0),R284)=\"\",R284,IFERROR(VLOOKUP('AUP Library'!A284,'Updated Quanities'!F:I,4,0),R284))","v":1937.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A284,'Updated Quanities'!F:I,5,0),R284)=\"\",R284,IFERROR(VLOOKUP('AUP Library'!A284,'Updated Quanities'!F:I,5,0),R284))","v":1937.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A284,'Updated Quanities'!F:I,6,0),R284)=\"\",R284,IFERROR(VLOOKUP('AUP Library'!A284,'Updated Quanities'!F:I,6,0),R284))","v":1937.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A284,'Updated Quanities'!F:I,7,0),R284)=\"\",R284,IFERROR(VLOOKUP('AUP Library'!A284,'Updated Quanities'!F:I,7,0),R284))","v":1937.27},1937.27,{"$f":"IFERROR(VLOOKUP('AUP Library'!A284,'Updated Quanities'!F:G,4,0),R284)","v":1937.27}]
["611-07.54","18\" Endwall (Cross Drain) 3:1","EA",1483.09,1483.09,1483.09,1483.09,1483.09,1483.09,1483.09,1483.09,1483.09,1483.09,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A285,'Updated Quanities'!F:I,4,0),R285)=\"\",R285,IFERROR(VLOOKUP('AUP Library'!A285,'Updated Quanities'!F:I,4,0),R285))","v":1483.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A285,'Updated Quanities'!F:I,5,0),R285)=\"\",R285,IFERROR(VLOOKUP('AUP Library'!A285,'Updated Quanities'!F:I,5,0),R285))","v":1483.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A285,'Updated Quanities'!F:I,6,0),R285)=\"\",R285,IFERROR(VLOOKUP('AUP Library'!A285,'Updated Quanities'!F:I,6,0),R285))","v":1483.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A285,'Updated Quanities'!F:I,7,0),R285)=\"\",R285,IFERROR(VLOOKUP('AUP Library'!A285,'Updated Quanities'!F:I,7,0),R285))","v":1483.09},1483.09,{"$f":"IFERROR(VLOOKUP('AUP Library'!A285,'Updated Quanities'!F:G,4,0),R285)","v":1483.09}]
["611-07.57","24\" Endwall (Cross Drain) 3:1","EA",2262.71,2262.71,2262.71,2262.71,2262.71,2262.71,2262.71,2262.71,2262.71,2262.71,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A286,'Updated Quanities'!F:I,4,0),R286)=\"\",R286,IFERROR(VLOOKUP('AUP Library'!A286,'Updated Quanities'!F:I,4,0),R286))","v":2262.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A286,'Updated Quanities'!F:I,5,0),R286)=\"\",R286,IFERROR(VLOOKUP('AUP Library'!A286,'Updated Quanities'!F:I,5,0),R286))","v":2262.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A286,'Updated Quanities'!F:I,6,0),R286)=\"\",R286,IFERROR(VLOOKUP('AUP Library'!A286,'Updated Quanities'!F:I,6,0),R286))","v":2262.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A286,'Updated Quanities'!F:I,7,0),R286)=\"\",R286,IFERROR(VLOOKUP('AUP Library'!A286,'Updated Quanities'!F:I,7,0),R286))","v":2262.71},2262.71,{"$f":"IFERROR(VLOOKUP('AUP Library'!A286,'Updated Quanities'!F:G,4,0),R286)","v":2262.71}]
["611-07.60","30\" Endwall (Cross Drain) 3:1","EA",2686.78,2686.78,2686.78,2686.78,2686.78,2686.78,2686.78,2686.78,2686.78,2686.78,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A287,'Updated Quanities'!F:I,4,0),R287)=\"\",R287,IFERROR(VLOOKUP('AUP Library'!A287,'Updated Quanities'!F:I,4,0),R287))","v":2686.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A287,'Updated Quanities'!F:I,5,0),R287)=\"\",R287,IFERROR(VLOOKUP('AUP Library'!A287,'Updated Quanities'!F:I,5,0),R287))","v":2686.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A287,'Updated Quanities'!F:I,6,0),R287)=\"\",R287,IFERROR(VLOOKUP('AUP Library'!A287,'Updated Quanities'!F:I,6,0),R287))","v":2686.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A287,'Updated Quanities'!F:I,7,0),R287)=\"\",R287,IFERROR(VLOOKUP('AUP Library'!A287,'Updated Quanities'!F:I,7,0),R287))","v":2686.78},2686.78,{"$f":"IFERROR(VLOOKUP('AUP Library'!A287,'Updated Quanities'!F:G,4,0),R287)","v":2686.78}]
["611-07.63","36\" Endwall (Cross Drain) 3:1","EA",2466.09,2466.09,2466.09,2466.09,2466.09,2466.09,2466.09,2466.09,2466.09,2466.09,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A288,'Updated Quanities'!F:I,4,0),R288)=\"\",R288,IFERROR(VLOOKUP('AUP Library'!A288,'Updated Quanities'!F:I,4,0),R288))","v":2466.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A288,'Updated Quanities'!F:I,5,0),R288)=\"\",R288,IFERROR(VLOOKUP('AUP Library'!A288,'Updated Quanities'!F:I,5,0),R288))","v":2466.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A288,'Updated Quanities'!F:I,6,0),R288)=\"\",R288,IFERROR(VLOOKUP('AUP Library'!A288,'Updated Quanities'!F:I,6,0),R288))","v":2466.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A288,'Updated Quanities'!F:I,7,0),R288)=\"\",R288,IFERROR(VLOOKUP('AUP Library'!A288,'Updated Quanities'!F:I,7,0),R288))","v":2466.09},2466.09,{"$f":"IFERROR(VLOOKUP('AUP Library'!A288,'Updated Quanities'!F:G,4,0),R288)","v":2466.09}]
["611-07.66","42\" Endwall (Cross Drain) 3:1","EA",4275.0600000000004,4275.0600000000004,4275.0600000000004,4275.0600000000004,4275.0600000000004,4275.0600000000004,4275.0600000000004,4275.0600000000004,4275.0600000000004,4275.0600000000004,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A289,'Updated Quanities'!F:I,4,0),R289)=\"\",R289,IFERROR(VLOOKUP('AUP Library'!A289,'Updated Quanities'!F:I,4,0),R289))","v":4275.0600000000004},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A289,'Updated Quanities'!F:I,5,0),R289)=\"\",R289,IFERROR(VLOOKUP('AUP Library'!A289,'Updated Quanities'!F:I,5,0),R289))","v":4275.0600000000004},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A289,'Updated Quanities'!F:I,6,0),R289)=\"\",R289,IFERROR(VLOOKUP('AUP Library'!A289,'Updated Quanities'!F:I,6,0),R289))","v":4275.0600000000004},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A289,'Updated Quanities'!F:I,7,0),R289)=\"\",R289,IFERROR(VLOOKUP('AUP Library'!A289,'Updated Quanities'!F:I,7,0),R289))","v":4275.0600000000004},4275.0600000000004,{"$f":"IFERROR(VLOOKUP('AUP Library'!A289,'Updated Quanities'!F:G,4,0),R289)","v":4275.0600000000004}]
["611-07.69","48\" Endwall (Cross Drain) 3:1","EA",3505.78,3505.78,3505.78,3505.78,3505.78,3505.78,3505.78,3505.78,3505.78,3505.78,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A290,'Updated Quanities'!F:I,4,0),R290)=\"\",R290,IFERROR(VLOOKUP('AUP Library'!A290,'Updated Quanities'!F:I,4,0),R290))","v":3505.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A290,'Updated Quanities'!F:I,5,0),R290)=\"\",R290,IFERROR(VLOOKUP('AUP Library'!A290,'Updated Quanities'!F:I,5,0),R290))","v":3505.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A290,'Updated Quanities'!F:I,6,0),R290)=\"\",R290,IFERROR(VLOOKUP('AUP Library'!A290,'Updated Quanities'!F:I,6,0),R290))","v":3505.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A290,'Updated Quanities'!F:I,7,0),R290)=\"\",R290,IFERROR(VLOOKUP('AUP Library'!A290,'Updated Quanities'!F:I,7,0),R290))","v":3505.78},3505.78,{"$f":"IFERROR(VLOOKUP('AUP Library'!A290,'Updated Quanities'!F:G,4,0),R290)","v":3505.78}]
["611-09.01","ADJUSTMENT OF EXISTING CATCHBASIN","EA",394.42,394.42,394.42,394.42,394.42,394.42,394.42,394.42,394.42,394.42,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A291,'Updated Quanities'!F:I,4,0),R291)=\"\",R291,IFERROR(VLOOKUP('AUP Library'!A291,'Updated Quanities'!F:I,4,0),R291))","v":394.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A291,'Updated Quanities'!F:I,5,0),R291)=\"\",R291,IFERROR(VLOOKUP('AUP Library'!A291,'Updated Quanities'!F:I,5,0),R291))","v":394.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A291,'Updated Quanities'!F:I,6,0),R291)=\"\",R291,IFERROR(VLOOKUP('AUP Library'!A291,'Updated Quanities'!F:I,6,0),R291))","v":394.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A291,'Updated Quanities'!F:I,7,0),R291)=\"\",R291,IFERROR(VLOOKUP('AUP Library'!A291,'Updated Quanities'!F:I,7,0),R291))","v":394.42},394.42,{"$f":"IFERROR(VLOOKUP('AUP Library'!A291,'Updated Quanities'!F:G,4,0),R291)","v":394.42}]
["611-09.02","REWORK CATCHBASIN","EA",1116.58,1116.58,1116.58,1116.58,1116.58,1116.58,1116.58,1116.58,1116.58,1116.58,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A292,'Updated Quanities'!F:I,4,0),R292)=\"\",R292,IFERROR(VLOOKUP('AUP Library'!A292,'Updated Quanities'!F:I,4,0),R292))","v":1116.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A292,'Updated Quanities'!F:I,5,0),R292)=\"\",R292,IFERROR(VLOOKUP('AUP Library'!A292,'Updated Quanities'!F:I,5,0),R292))","v":1116.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A292,'Updated Quanities'!F:I,6,0),R292)=\"\",R292,IFERROR(VLOOKUP('AUP Library'!A292,'Updated Quanities'!F:I,6,0),R292))","v":1116.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A292,'Updated Quanities'!F:I,7,0),R292)=\"\",R292,IFERROR(VLOOKUP('AUP Library'!A292,'Updated Quanities'!F:I,7,0),R292))","v":1116.58},1116.58,{"$f":"IFERROR(VLOOKUP('AUP Library'!A292,'Updated Quanities'!F:G,4,0),R292)","v":1116.58}]
["611-09.03","CAPPING EXISTING CATCHBASIN","EA",559.22,559.22,559.22,559.22,559.22,559.22,559.22,559.22,559.22,559.22,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A293,'Updated Quanities'!F:I,4,0),R293)=\"\",R293,IFERROR(VLOOKUP('AUP Library'!A293,'Updated Quanities'!F:I,4,0),R293))","v":559.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A293,'Updated Quanities'!F:I,5,0),R293)=\"\",R293,IFERROR(VLOOKUP('AUP Library'!A293,'Updated Quanities'!F:I,5,0),R293))","v":559.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A293,'Updated Quanities'!F:I,6,0),R293)=\"\",R293,IFERROR(VLOOKUP('AUP Library'!A293,'Updated Quanities'!F:I,6,0),R293))","v":559.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A293,'Updated Quanities'!F:I,7,0),R293)=\"\",R293,IFERROR(VLOOKUP('AUP Library'!A293,'Updated Quanities'!F:I,7,0),R293))","v":559.22},559.22,{"$f":"IFERROR(VLOOKUP('AUP Library'!A293,'Updated Quanities'!F:G,4,0),R293)","v":559.22}]
["611-10.01","Catch Basins, Type 10, 0' -4' Depth","EA",2973.64,2973.64,2973.64,2973.64,2973.64,2973.64,2973.64,2973.64,2973.64,2973.64,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A294,'Updated Quanities'!F:I,4,0),R294)=\"\",R294,IFERROR(VLOOKUP('AUP Library'!A294,'Updated Quanities'!F:I,4,0),R294))","v":2973.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A294,'Updated Quanities'!F:I,5,0),R294)=\"\",R294,IFERROR(VLOOKUP('AUP Library'!A294,'Updated Quanities'!F:I,5,0),R294))","v":2973.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A294,'Updated Quanities'!F:I,6,0),R294)=\"\",R294,IFERROR(VLOOKUP('AUP Library'!A294,'Updated Quanities'!F:I,6,0),R294))","v":2973.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A294,'Updated Quanities'!F:I,7,0),R294)=\"\",R294,IFERROR(VLOOKUP('AUP Library'!A294,'Updated Quanities'!F:I,7,0),R294))","v":2973.64},2973.64,{"$f":"IFERROR(VLOOKUP('AUP Library'!A294,'Updated Quanities'!F:G,4,0),R294)","v":2973.64}]
["611-10.02","Catch Basins, Type 10, > 4' - 8' Depth","EA",3001.37,3001.37,3001.37,3001.37,3001.37,3001.37,3001.37,3001.37,3001.37,3001.37,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A295,'Updated Quanities'!F:I,4,0),R295)=\"\",R295,IFERROR(VLOOKUP('AUP Library'!A295,'Updated Quanities'!F:I,4,0),R295))","v":3001.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A295,'Updated Quanities'!F:I,5,0),R295)=\"\",R295,IFERROR(VLOOKUP('AUP Library'!A295,'Updated Quanities'!F:I,5,0),R295))","v":3001.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A295,'Updated Quanities'!F:I,6,0),R295)=\"\",R295,IFERROR(VLOOKUP('AUP Library'!A295,'Updated Quanities'!F:I,6,0),R295))","v":3001.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A295,'Updated Quanities'!F:I,7,0),R295)=\"\",R295,IFERROR(VLOOKUP('AUP Library'!A295,'Updated Quanities'!F:I,7,0),R295))","v":3001.37},3001.37,{"$f":"IFERROR(VLOOKUP('AUP Library'!A295,'Updated Quanities'!F:G,4,0),R295)","v":3001.37}]
["611-12.01","Catch Basins, Type 12, 0' -4' Depth","EA",2780.54,2780.54,2780.54,2780.54,2780.54,2780.54,2780.54,2780.54,2780.54,2780.54,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A296,'Updated Quanities'!F:I,4,0),R296)=\"\",R296,IFERROR(VLOOKUP('AUP Library'!A296,'Updated Quanities'!F:I,4,0),R296))","v":2780.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A296,'Updated Quanities'!F:I,5,0),R296)=\"\",R296,IFERROR(VLOOKUP('AUP Library'!A296,'Updated Quanities'!F:I,5,0),R296))","v":2780.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A296,'Updated Quanities'!F:I,6,0),R296)=\"\",R296,IFERROR(VLOOKUP('AUP Library'!A296,'Updated Quanities'!F:I,6,0),R296))","v":2780.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A296,'Updated Quanities'!F:I,7,0),R296)=\"\",R296,IFERROR(VLOOKUP('AUP Library'!A296,'Updated Quanities'!F:I,7,0),R296))","v":2780.54},2780.54,{"$f":"IFERROR(VLOOKUP('AUP Library'!A296,'Updated Quanities'!F:G,4,0),R296)","v":2780.54}]
["611-12.02","Catch Basins, Type 12, > 4' - 8' Depth","EA",2552.19,2117.79,2691.27,2504.83,2504.83,1936.55,2682.51,3076.19,3092.57,3912.72,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A297,'Updated Quanities'!F:I,4,0),R297)=\"\",R297,IFERROR(VLOOKUP('AUP Library'!A297,'Updated Quanities'!F:I,4,0),R297))","v":4775.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A297,'Updated Quanities'!F:I,5,0),R297)=\"\",R297,IFERROR(VLOOKUP('AUP Library'!A297,'Updated Quanities'!F:I,5,0),R297))","v":4775.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A297,'Updated Quanities'!F:I,6,0),R297)=\"\",R297,IFERROR(VLOOKUP('AUP Library'!A297,'Updated Quanities'!F:I,6,0),R297))","v":4775.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A297,'Updated Quanities'!F:I,7,0),R297)=\"\",R297,IFERROR(VLOOKUP('AUP Library'!A297,'Updated Quanities'!F:I,7,0),R297))","v":4775.34},4775.34,{"$f":"IFERROR(VLOOKUP('AUP Library'!A297,'Updated Quanities'!F:G,4,0),R297)","v":4775.34}]
["611-12.03","Catch Basins, Type 12, > 8' - 12' Depth","EA",6068.78,6068.78,6068.78,6068.78,6068.78,6068.78,6068.78,6068.78,6068.78,6068.78,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A298,'Updated Quanities'!F:I,4,0),R298)=\"\",R298,IFERROR(VLOOKUP('AUP Library'!A298,'Updated Quanities'!F:I,4,0),R298))","v":6068.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A298,'Updated Quanities'!F:I,5,0),R298)=\"\",R298,IFERROR(VLOOKUP('AUP Library'!A298,'Updated Quanities'!F:I,5,0),R298))","v":6068.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A298,'Updated Quanities'!F:I,6,0),R298)=\"\",R298,IFERROR(VLOOKUP('AUP Library'!A298,'Updated Quanities'!F:I,6,0),R298))","v":6068.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A298,'Updated Quanities'!F:I,7,0),R298)=\"\",R298,IFERROR(VLOOKUP('AUP Library'!A298,'Updated Quanities'!F:I,7,0),R298))","v":6068.78},6068.78,{"$f":"IFERROR(VLOOKUP('AUP Library'!A298,'Updated Quanities'!F:G,4,0),R298)","v":6068.78}]
["611-12.04","Catch Basins, Type 12, > 12' - 16' Depth","EA",8574.17,8574.17,8574.17,8574.17,8574.17,8574.17,8574.17,8574.17,8574.17,8574.17,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A299,'Updated Quanities'!F:I,4,0),R299)=\"\",R299,IFERROR(VLOOKUP('AUP Library'!A299,'Updated Quanities'!F:I,4,0),R299))","v":8574.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A299,'Updated Quanities'!F:I,5,0),R299)=\"\",R299,IFERROR(VLOOKUP('AUP Library'!A299,'Updated Quanities'!F:I,5,0),R299))","v":8574.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A299,'Updated Quanities'!F:I,6,0),R299)=\"\",R299,IFERROR(VLOOKUP('AUP Library'!A299,'Updated Quanities'!F:I,6,0),R299))","v":8574.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A299,'Updated Quanities'!F:I,7,0),R299)=\"\",R299,IFERROR(VLOOKUP('AUP Library'!A299,'Updated Quanities'!F:I,7,0),R299))","v":8574.17},8574.17,{"$f":"IFERROR(VLOOKUP('AUP Library'!A299,'Updated Quanities'!F:G,4,0),R299)","v":8574.17}]
["611-12.05","Catch Basins, Type 12, 16' - 20' Depth","EA",3633.77,3633.77,3633.77,3633.77,3633.77,3633.77,3633.77,3633.77,3633.77,3633.77,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A300,'Updated Quanities'!F:I,4,0),R300)=\"\",R300,IFERROR(VLOOKUP('AUP Library'!A300,'Updated Quanities'!F:I,4,0),R300))","v":3633.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A300,'Updated Quanities'!F:I,5,0),R300)=\"\",R300,IFERROR(VLOOKUP('AUP Library'!A300,'Updated Quanities'!F:I,5,0),R300))","v":3633.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A300,'Updated Quanities'!F:I,6,0),R300)=\"\",R300,IFERROR(VLOOKUP('AUP Library'!A300,'Updated Quanities'!F:I,6,0),R300))","v":3633.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A300,'Updated Quanities'!F:I,7,0),R300)=\"\",R300,IFERROR(VLOOKUP('AUP Library'!A300,'Updated Quanities'!F:I,7,0),R300))","v":3633.77},3633.77,{"$f":"IFERROR(VLOOKUP('AUP Library'!A300,'Updated Quanities'!F:G,4,0),R300)","v":3633.77}]
["611-12.06","Catch Basins, Type 12, > 20' - 24' Depth","EA",4161.9399999999996,4161.9399999999996,4161.9399999999996,4161.9399999999996,4161.9399999999996,4161.9399999999996,4161.9399999999996,4161.9399999999996,4161.9399999999996,4161.9399999999996,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A301,'Updated Quanities'!F:I,4,0),R301)=\"\",R301,IFERROR(VLOOKUP('AUP Library'!A301,'Updated Quanities'!F:I,4,0),R301))","v":4161.9399999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A301,'Updated Quanities'!F:I,5,0),R301)=\"\",R301,IFERROR(VLOOKUP('AUP Library'!A301,'Updated Quanities'!F:I,5,0),R301))","v":4161.9399999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A301,'Updated Quanities'!F:I,6,0),R301)=\"\",R301,IFERROR(VLOOKUP('AUP Library'!A301,'Updated Quanities'!F:I,6,0),R301))","v":4161.9399999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A301,'Updated Quanities'!F:I,7,0),R301)=\"\",R301,IFERROR(VLOOKUP('AUP Library'!A301,'Updated Quanities'!F:I,7,0),R301))","v":4161.9399999999996},4161.9399999999996,{"$f":"IFERROR(VLOOKUP('AUP Library'!A301,'Updated Quanities'!F:G,4,0),R301)","v":4161.9399999999996}]
["611-14.01","Catch Basins, Type 14, 0' -4' Depth","EA",5540.53,5540.53,5540.53,5540.53,5540.53,5540.53,5540.53,5540.53,5540.53,5540.53,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A302,'Updated Quanities'!F:I,4,0),R302)=\"\",R302,IFERROR(VLOOKUP('AUP Library'!A302,'Updated Quanities'!F:I,4,0),R302))","v":5540.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A302,'Updated Quanities'!F:I,5,0),R302)=\"\",R302,IFERROR(VLOOKUP('AUP Library'!A302,'Updated Quanities'!F:I,5,0),R302))","v":5540.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A302,'Updated Quanities'!F:I,6,0),R302)=\"\",R302,IFERROR(VLOOKUP('AUP Library'!A302,'Updated Quanities'!F:I,6,0),R302))","v":5540.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A302,'Updated Quanities'!F:I,7,0),R302)=\"\",R302,IFERROR(VLOOKUP('AUP Library'!A302,'Updated Quanities'!F:I,7,0),R302))","v":5540.53},5540.53,{"$f":"IFERROR(VLOOKUP('AUP Library'!A302,'Updated Quanities'!F:G,4,0),R302)","v":5540.53}]
["611-14.02","Catch Basins, Type 14, > 4' - 8' Depth","EA",4523.84,3308.92,3680.65,4292.3599999999997,4292.3599999999997,3001.58,7237.09,5607.5,5515.55,5975.89,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A303,'Updated Quanities'!F:I,4,0),R303)=\"\",R303,IFERROR(VLOOKUP('AUP Library'!A303,'Updated Quanities'!F:I,4,0),R303))","v":6594.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A303,'Updated Quanities'!F:I,5,0),R303)=\"\",R303,IFERROR(VLOOKUP('AUP Library'!A303,'Updated Quanities'!F:I,5,0),R303))","v":6594.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A303,'Updated Quanities'!F:I,6,0),R303)=\"\",R303,IFERROR(VLOOKUP('AUP Library'!A303,'Updated Quanities'!F:I,6,0),R303))","v":6594.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A303,'Updated Quanities'!F:I,7,0),R303)=\"\",R303,IFERROR(VLOOKUP('AUP Library'!A303,'Updated Quanities'!F:I,7,0),R303))","v":6594.36},6594.36,{"$f":"IFERROR(VLOOKUP('AUP Library'!A303,'Updated Quanities'!F:G,4,0),R303)","v":6594.36}]
["611-14.03","Catch Basins, Type 14, > 8' - 12' Depth","EA",6385.71,6385.71,6385.71,6385.71,6385.71,6385.71,6385.71,6385.71,6385.71,6385.71,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A304,'Updated Quanities'!F:I,4,0),R304)=\"\",R304,IFERROR(VLOOKUP('AUP Library'!A304,'Updated Quanities'!F:I,4,0),R304))","v":6385.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A304,'Updated Quanities'!F:I,5,0),R304)=\"\",R304,IFERROR(VLOOKUP('AUP Library'!A304,'Updated Quanities'!F:I,5,0),R304))","v":6385.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A304,'Updated Quanities'!F:I,6,0),R304)=\"\",R304,IFERROR(VLOOKUP('AUP Library'!A304,'Updated Quanities'!F:I,6,0),R304))","v":6385.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A304,'Updated Quanities'!F:I,7,0),R304)=\"\",R304,IFERROR(VLOOKUP('AUP Library'!A304,'Updated Quanities'!F:I,7,0),R304))","v":6385.71},6385.71,{"$f":"IFERROR(VLOOKUP('AUP Library'!A304,'Updated Quanities'!F:G,4,0),R304)","v":6385.71}]
["611-14.04","Catch Basins, Type 14, > 12' - 16' Depth","EA",13996.37,13996.37,13996.37,13996.37,13996.37,13996.37,13996.37,13996.37,13996.37,13996.37,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A305,'Updated Quanities'!F:I,4,0),R305)=\"\",R305,IFERROR(VLOOKUP('AUP Library'!A305,'Updated Quanities'!F:I,4,0),R305))","v":13996.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A305,'Updated Quanities'!F:I,5,0),R305)=\"\",R305,IFERROR(VLOOKUP('AUP Library'!A305,'Updated Quanities'!F:I,5,0),R305))","v":13996.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A305,'Updated Quanities'!F:I,6,0),R305)=\"\",R305,IFERROR(VLOOKUP('AUP Library'!A305,'Updated Quanities'!F:I,6,0),R305))","v":13996.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A305,'Updated Quanities'!F:I,7,0),R305)=\"\",R305,IFERROR(VLOOKUP('AUP Library'!A305,'Updated Quanities'!F:I,7,0),R305))","v":13996.37},13996.37,{"$f":"IFERROR(VLOOKUP('AUP Library'!A305,'Updated Quanities'!F:G,4,0),R305)","v":13996.37}]
["611-14.05","Catch Basins, Type 14, > 16' - 20' Depth","EA",14232.38,14232.38,14232.38,14232.38,14232.38,14232.38,14232.38,14232.38,14232.38,14232.38,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A306,'Updated Quanities'!F:I,4,0),R306)=\"\",R306,IFERROR(VLOOKUP('AUP Library'!A306,'Updated Quanities'!F:I,4,0),R306))","v":14232.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A306,'Updated Quanities'!F:I,5,0),R306)=\"\",R306,IFERROR(VLOOKUP('AUP Library'!A306,'Updated Quanities'!F:I,5,0),R306))","v":14232.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A306,'Updated Quanities'!F:I,6,0),R306)=\"\",R306,IFERROR(VLOOKUP('AUP Library'!A306,'Updated Quanities'!F:I,6,0),R306))","v":14232.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A306,'Updated Quanities'!F:I,7,0),R306)=\"\",R306,IFERROR(VLOOKUP('AUP Library'!A306,'Updated Quanities'!F:I,7,0),R306))","v":14232.38},14232.38,{"$f":"IFERROR(VLOOKUP('AUP Library'!A306,'Updated Quanities'!F:G,4,0),R306)","v":14232.38}]
["611-16.01","Catch Basins, Type 16, > 0' - 4' Depth","EA",5573.02,5573.02,5573.02,5573.02,5573.02,5573.02,5573.02,5573.02,5573.02,5573.02,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A307,'Updated Quanities'!F:I,4,0),R307)=\"\",R307,IFERROR(VLOOKUP('AUP Library'!A307,'Updated Quanities'!F:I,4,0),R307))","v":5573.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A307,'Updated Quanities'!F:I,5,0),R307)=\"\",R307,IFERROR(VLOOKUP('AUP Library'!A307,'Updated Quanities'!F:I,5,0),R307))","v":5573.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A307,'Updated Quanities'!F:I,6,0),R307)=\"\",R307,IFERROR(VLOOKUP('AUP Library'!A307,'Updated Quanities'!F:I,6,0),R307))","v":5573.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A307,'Updated Quanities'!F:I,7,0),R307)=\"\",R307,IFERROR(VLOOKUP('AUP Library'!A307,'Updated Quanities'!F:I,7,0),R307))","v":5573.02},5573.02,{"$f":"IFERROR(VLOOKUP('AUP Library'!A307,'Updated Quanities'!F:G,4,0),R307)","v":5573.02}]
["611-16.02","Catch Basins, Type 16, > 4' - 8' Depth","EA",5573.02,5573.02,5573.02,5573.02,5573.02,5573.02,5573.02,5573.02,5573.02,5573.02,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A308,'Updated Quanities'!F:I,4,0),R308)=\"\",R308,IFERROR(VLOOKUP('AUP Library'!A308,'Updated Quanities'!F:I,4,0),R308))","v":5573.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A308,'Updated Quanities'!F:I,5,0),R308)=\"\",R308,IFERROR(VLOOKUP('AUP Library'!A308,'Updated Quanities'!F:I,5,0),R308))","v":5573.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A308,'Updated Quanities'!F:I,6,0),R308)=\"\",R308,IFERROR(VLOOKUP('AUP Library'!A308,'Updated Quanities'!F:I,6,0),R308))","v":5573.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A308,'Updated Quanities'!F:I,7,0),R308)=\"\",R308,IFERROR(VLOOKUP('AUP Library'!A308,'Updated Quanities'!F:I,7,0),R308))","v":5573.02},5573.02,{"$f":"IFERROR(VLOOKUP('AUP Library'!A308,'Updated Quanities'!F:G,4,0),R308)","v":5573.02}]
["611-16.03","Catch Basins, Type 16, > 8' - 12' Depth","EA",4600,4600,4600,4600,4600,4600,4600,4600,4600,4600,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A309,'Updated Quanities'!F:I,4,0),R309)=\"\",R309,IFERROR(VLOOKUP('AUP Library'!A309,'Updated Quanities'!F:I,4,0),R309))","v":4600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A309,'Updated Quanities'!F:I,5,0),R309)=\"\",R309,IFERROR(VLOOKUP('AUP Library'!A309,'Updated Quanities'!F:I,5,0),R309))","v":4600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A309,'Updated Quanities'!F:I,6,0),R309)=\"\",R309,IFERROR(VLOOKUP('AUP Library'!A309,'Updated Quanities'!F:I,6,0),R309))","v":4600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A309,'Updated Quanities'!F:I,7,0),R309)=\"\",R309,IFERROR(VLOOKUP('AUP Library'!A309,'Updated Quanities'!F:I,7,0),R309))","v":4600},4600,{"$f":"IFERROR(VLOOKUP('AUP Library'!A309,'Updated Quanities'!F:G,4,0),R309)","v":4600}]
["611-16.04","Catch Basins, Type 16, > 12' - 16' Depth","EA",3397,3397,3397,3397,3397,3397,3397,3397,3397,3397,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A310,'Updated Quanities'!F:I,4,0),R310)=\"\",R310,IFERROR(VLOOKUP('AUP Library'!A310,'Updated Quanities'!F:I,4,0),R310))","v":3397},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A310,'Updated Quanities'!F:I,5,0),R310)=\"\",R310,IFERROR(VLOOKUP('AUP Library'!A310,'Updated Quanities'!F:I,5,0),R310))","v":3397},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A310,'Updated Quanities'!F:I,6,0),R310)=\"\",R310,IFERROR(VLOOKUP('AUP Library'!A310,'Updated Quanities'!F:I,6,0),R310))","v":3397},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A310,'Updated Quanities'!F:I,7,0),R310)=\"\",R310,IFERROR(VLOOKUP('AUP Library'!A310,'Updated Quanities'!F:I,7,0),R310))","v":3397},3397,{"$f":"IFERROR(VLOOKUP('AUP Library'!A310,'Updated Quanities'!F:G,4,0),R310)","v":3397}]
["611-25.01","Catch Basins, Type 25, > 0' - 4' Depth","EA",3397,3397,3397,3397,3397,3397,3397,3397,3397,3397,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A311,'Updated Quanities'!F:I,4,0),R311)=\"\",R311,IFERROR(VLOOKUP('AUP Library'!A311,'Updated Quanities'!F:I,4,0),R311))","v":3397},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A311,'Updated Quanities'!F:I,5,0),R311)=\"\",R311,IFERROR(VLOOKUP('AUP Library'!A311,'Updated Quanities'!F:I,5,0),R311))","v":3397},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A311,'Updated Quanities'!F:I,6,0),R311)=\"\",R311,IFERROR(VLOOKUP('AUP Library'!A311,'Updated Quanities'!F:I,6,0),R311))","v":3397},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A311,'Updated Quanities'!F:I,7,0),R311)=\"\",R311,IFERROR(VLOOKUP('AUP Library'!A311,'Updated Quanities'!F:I,7,0),R311))","v":3397},3397,{"$f":"IFERROR(VLOOKUP('AUP Library'!A311,'Updated Quanities'!F:G,4,0),R311)","v":3397}]
["611-25.02","Catch Basins, Type 25, > 4' - 8' Depth","EA",3397,3397,3397,3397,3397,3397,3397,3397,3397,3397,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A312,'Updated Quanities'!F:I,4,0),R312)=\"\",R312,IFERROR(VLOOKUP('AUP Library'!A312,'Updated Quanities'!F:I,4,0),R312))","v":3397},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A312,'Updated Quanities'!F:I,5,0),R312)=\"\",R312,IFERROR(VLOOKUP('AUP Library'!A312,'Updated Quanities'!F:I,5,0),R312))","v":3397},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A312,'Updated Quanities'!F:I,6,0),R312)=\"\",R312,IFERROR(VLOOKUP('AUP Library'!A312,'Updated Quanities'!F:I,6,0),R312))","v":3397},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A312,'Updated Quanities'!F:I,7,0),R312)=\"\",R312,IFERROR(VLOOKUP('AUP Library'!A312,'Updated Quanities'!F:I,7,0),R312))","v":3397},3397,{"$f":"IFERROR(VLOOKUP('AUP Library'!A312,'Updated Quanities'!F:G,4,0),R312)","v":3397}]
["611-25.03","Catch Basins, Type 25, > 8' - 12' Depth","EA",4678,4678,4678,4678,4678,4678,4678,4678,4678,4678,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A313,'Updated Quanities'!F:I,4,0),R313)=\"\",R313,IFERROR(VLOOKUP('AUP Library'!A313,'Updated Quanities'!F:I,4,0),R313))","v":4678},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A313,'Updated Quanities'!F:I,5,0),R313)=\"\",R313,IFERROR(VLOOKUP('AUP Library'!A313,'Updated Quanities'!F:I,5,0),R313))","v":4678},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A313,'Updated Quanities'!F:I,6,0),R313)=\"\",R313,IFERROR(VLOOKUP('AUP Library'!A313,'Updated Quanities'!F:I,6,0),R313))","v":4678},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A313,'Updated Quanities'!F:I,7,0),R313)=\"\",R313,IFERROR(VLOOKUP('AUP Library'!A313,'Updated Quanities'!F:I,7,0),R313))","v":4678},4678,{"$f":"IFERROR(VLOOKUP('AUP Library'!A313,'Updated Quanities'!F:G,4,0),R313)","v":4678}]
["611-25.04","Catch Basins, Type 25, > 12' - 16' Depth","EA",4678,4678,4678,4678,4678,4678,4678,4678,4678,4678,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A314,'Updated Quanities'!F:I,4,0),R314)=\"\",R314,IFERROR(VLOOKUP('AUP Library'!A314,'Updated Quanities'!F:I,4,0),R314))","v":4678},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A314,'Updated Quanities'!F:I,5,0),R314)=\"\",R314,IFERROR(VLOOKUP('AUP Library'!A314,'Updated Quanities'!F:I,5,0),R314))","v":4678},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A314,'Updated Quanities'!F:I,6,0),R314)=\"\",R314,IFERROR(VLOOKUP('AUP Library'!A314,'Updated Quanities'!F:I,6,0),R314))","v":4678},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A314,'Updated Quanities'!F:I,7,0),R314)=\"\",R314,IFERROR(VLOOKUP('AUP Library'!A314,'Updated Quanities'!F:I,7,0),R314))","v":4678},4678,{"$f":"IFERROR(VLOOKUP('AUP Library'!A314,'Updated Quanities'!F:G,4,0),R314)","v":4678}]
["611-26.01","Catch Basins, Type 26, > 0' - 4' Depth","EA",3895,3895,3895,3895,3895,3895,3895,3895,3895,3895,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A315,'Updated Quanities'!F:I,4,0),R315)=\"\",R315,IFERROR(VLOOKUP('AUP Library'!A315,'Updated Quanities'!F:I,4,0),R315))","v":3895},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A315,'Updated Quanities'!F:I,5,0),R315)=\"\",R315,IFERROR(VLOOKUP('AUP Library'!A315,'Updated Quanities'!F:I,5,0),R315))","v":3895},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A315,'Updated Quanities'!F:I,6,0),R315)=\"\",R315,IFERROR(VLOOKUP('AUP Library'!A315,'Updated Quanities'!F:I,6,0),R315))","v":3895},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A315,'Updated Quanities'!F:I,7,0),R315)=\"\",R315,IFERROR(VLOOKUP('AUP Library'!A315,'Updated Quanities'!F:I,7,0),R315))","v":3895},3895,{"$f":"IFERROR(VLOOKUP('AUP Library'!A315,'Updated Quanities'!F:G,4,0),R315)","v":3895}]
["611-26.02","Catch Basins, Type 26, > 4' - 8' Depth","EA",5686.69,5686.69,5686.69,5686.69,5686.69,5686.69,5686.69,5686.69,5686.69,5686.69,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A316,'Updated Quanities'!F:I,4,0),R316)=\"\",R316,IFERROR(VLOOKUP('AUP Library'!A316,'Updated Quanities'!F:I,4,0),R316))","v":5686.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A316,'Updated Quanities'!F:I,5,0),R316)=\"\",R316,IFERROR(VLOOKUP('AUP Library'!A316,'Updated Quanities'!F:I,5,0),R316))","v":5686.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A316,'Updated Quanities'!F:I,6,0),R316)=\"\",R316,IFERROR(VLOOKUP('AUP Library'!A316,'Updated Quanities'!F:I,6,0),R316))","v":5686.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A316,'Updated Quanities'!F:I,7,0),R316)=\"\",R316,IFERROR(VLOOKUP('AUP Library'!A316,'Updated Quanities'!F:I,7,0),R316))","v":5686.69},5686.69,{"$f":"IFERROR(VLOOKUP('AUP Library'!A316,'Updated Quanities'!F:G,4,0),R316)","v":5686.69}]
["611-26.03","Catch Basin, Type 26, > 8' - 12' Depth","EA",5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A317,'Updated Quanities'!F:I,4,0),R317)=\"\",R317,IFERROR(VLOOKUP('AUP Library'!A317,'Updated Quanities'!F:I,4,0),R317))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A317,'Updated Quanities'!F:I,5,0),R317)=\"\",R317,IFERROR(VLOOKUP('AUP Library'!A317,'Updated Quanities'!F:I,5,0),R317))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A317,'Updated Quanities'!F:I,6,0),R317)=\"\",R317,IFERROR(VLOOKUP('AUP Library'!A317,'Updated Quanities'!F:I,6,0),R317))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A317,'Updated Quanities'!F:I,7,0),R317)=\"\",R317,IFERROR(VLOOKUP('AUP Library'!A317,'Updated Quanities'!F:I,7,0),R317))","v":5294.47},5294.47,{"$f":"IFERROR(VLOOKUP('AUP Library'!A317,'Updated Quanities'!F:G,4,0),R317)","v":5294.47}]
["611-26.04","Catch Basin, Type 26, > 12' - 16' Depth","EA",5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A318,'Updated Quanities'!F:I,4,0),R318)=\"\",R318,IFERROR(VLOOKUP('AUP Library'!A318,'Updated Quanities'!F:I,4,0),R318))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A318,'Updated Quanities'!F:I,5,0),R318)=\"\",R318,IFERROR(VLOOKUP('AUP Library'!A318,'Updated Quanities'!F:I,5,0),R318))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A318,'Updated Quanities'!F:I,6,0),R318)=\"\",R318,IFERROR(VLOOKUP('AUP Library'!A318,'Updated Quanities'!F:I,6,0),R318))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A318,'Updated Quanities'!F:I,7,0),R318)=\"\",R318,IFERROR(VLOOKUP('AUP Library'!A318,'Updated Quanities'!F:I,7,0),R318))","v":5294.47},5294.47,{"$f":"IFERROR(VLOOKUP('AUP Library'!A318,'Updated Quanities'!F:G,4,0),R318)","v":5294.47}]
["611-28.01","Catch Basin, Type 28, > 0' - 4' Depth","EA",5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A319,'Updated Quanities'!F:I,4,0),R319)=\"\",R319,IFERROR(VLOOKUP('AUP Library'!A319,'Updated Quanities'!F:I,4,0),R319))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A319,'Updated Quanities'!F:I,5,0),R319)=\"\",R319,IFERROR(VLOOKUP('AUP Library'!A319,'Updated Quanities'!F:I,5,0),R319))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A319,'Updated Quanities'!F:I,6,0),R319)=\"\",R319,IFERROR(VLOOKUP('AUP Library'!A319,'Updated Quanities'!F:I,6,0),R319))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A319,'Updated Quanities'!F:I,7,0),R319)=\"\",R319,IFERROR(VLOOKUP('AUP Library'!A319,'Updated Quanities'!F:I,7,0),R319))","v":5294.47},5294.47,{"$f":"IFERROR(VLOOKUP('AUP Library'!A319,'Updated Quanities'!F:G,4,0),R319)","v":5294.47}]
["611-28.02","Catch Basin, Type 28, > 4' - 8' Depth","EA",5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A320,'Updated Quanities'!F:I,4,0),R320)=\"\",R320,IFERROR(VLOOKUP('AUP Library'!A320,'Updated Quanities'!F:I,4,0),R320))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A320,'Updated Quanities'!F:I,5,0),R320)=\"\",R320,IFERROR(VLOOKUP('AUP Library'!A320,'Updated Quanities'!F:I,5,0),R320))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A320,'Updated Quanities'!F:I,6,0),R320)=\"\",R320,IFERROR(VLOOKUP('AUP Library'!A320,'Updated Quanities'!F:I,6,0),R320))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A320,'Updated Quanities'!F:I,7,0),R320)=\"\",R320,IFERROR(VLOOKUP('AUP Library'!A320,'Updated Quanities'!F:I,7,0),R320))","v":5294.47},5294.47,{"$f":"IFERROR(VLOOKUP('AUP Library'!A320,'Updated Quanities'!F:G,4,0),R320)","v":5294.47}]
["611-28.03","Catch Basin, Type 28, > 8' - 12' Depth","EA",5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A321,'Updated Quanities'!F:I,4,0),R321)=\"\",R321,IFERROR(VLOOKUP('AUP Library'!A321,'Updated Quanities'!F:I,4,0),R321))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A321,'Updated Quanities'!F:I,5,0),R321)=\"\",R321,IFERROR(VLOOKUP('AUP Library'!A321,'Updated Quanities'!F:I,5,0),R321))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A321,'Updated Quanities'!F:I,6,0),R321)=\"\",R321,IFERROR(VLOOKUP('AUP Library'!A321,'Updated Quanities'!F:I,6,0),R321))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A321,'Updated Quanities'!F:I,7,0),R321)=\"\",R321,IFERROR(VLOOKUP('AUP Library'!A321,'Updated Quanities'!F:I,7,0),R321))","v":5294.47},5294.47,{"$f":"IFERROR(VLOOKUP('AUP Library'!A321,'Updated Quanities'!F:G,4,0),R321)","v":5294.47}]
["611-28.04","Catch Basin, Type 28, > 12' - 16' Depth","EA",5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A322,'Updated Quanities'!F:I,4,0),R322)=\"\",R322,IFERROR(VLOOKUP('AUP Library'!A322,'Updated Quanities'!F:I,4,0),R322))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A322,'Updated Quanities'!F:I,5,0),R322)=\"\",R322,IFERROR(VLOOKUP('AUP Library'!A322,'Updated Quanities'!F:I,5,0),R322))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A322,'Updated Quanities'!F:I,6,0),R322)=\"\",R322,IFERROR(VLOOKUP('AUP Library'!A322,'Updated Quanities'!F:I,6,0),R322))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A322,'Updated Quanities'!F:I,7,0),R322)=\"\",R322,IFERROR(VLOOKUP('AUP Library'!A322,'Updated Quanities'!F:I,7,0),R322))","v":5294.47},5294.47,{"$f":"IFERROR(VLOOKUP('AUP Library'!A322,'Updated Quanities'!F:G,4,0),R322)","v":5294.47}]
["611-31.01","Catch Basins, Type 31, > 0' - 4' Depth","EA",5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,5294.47,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A323,'Updated Quanities'!F:I,4,0),R323)=\"\",R323,IFERROR(VLOOKUP('AUP Library'!A323,'Updated Quanities'!F:I,4,0),R323))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A323,'Updated Quanities'!F:I,5,0),R323)=\"\",R323,IFERROR(VLOOKUP('AUP Library'!A323,'Updated Quanities'!F:I,5,0),R323))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A323,'Updated Quanities'!F:I,6,0),R323)=\"\",R323,IFERROR(VLOOKUP('AUP Library'!A323,'Updated Quanities'!F:I,6,0),R323))","v":5294.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A323,'Updated Quanities'!F:I,7,0),R323)=\"\",R323,IFERROR(VLOOKUP('AUP Library'!A323,'Updated Quanities'!F:I,7,0),R323))","v":5294.47},5294.47,{"$f":"IFERROR(VLOOKUP('AUP Library'!A323,'Updated Quanities'!F:G,4,0),R323)","v":5294.47}]
["611-31.02","Catch Basins, Type 31, > 4' - 8' Depth","EA",7287.3,7287.3,7287.3,7287.3,7287.3,7287.3,7287.3,7287.3,7287.3,7287.3,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A324,'Updated Quanities'!F:I,4,0),R324)=\"\",R324,IFERROR(VLOOKUP('AUP Library'!A324,'Updated Quanities'!F:I,4,0),R324))","v":7287.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A324,'Updated Quanities'!F:I,5,0),R324)=\"\",R324,IFERROR(VLOOKUP('AUP Library'!A324,'Updated Quanities'!F:I,5,0),R324))","v":7287.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A324,'Updated Quanities'!F:I,6,0),R324)=\"\",R324,IFERROR(VLOOKUP('AUP Library'!A324,'Updated Quanities'!F:I,6,0),R324))","v":7287.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A324,'Updated Quanities'!F:I,7,0),R324)=\"\",R324,IFERROR(VLOOKUP('AUP Library'!A324,'Updated Quanities'!F:I,7,0),R324))","v":7287.3},7287.3,{"$f":"IFERROR(VLOOKUP('AUP Library'!A324,'Updated Quanities'!F:G,4,0),R324)","v":7287.3}]
["611-31.03","Catch Basins, Type 31, > 8' - 12' Depth","EA",10365.030000000001,10365.030000000001,10365.030000000001,10365.030000000001,10365.030000000001,10365.030000000001,10365.030000000001,10365.030000000001,10365.030000000001,10365.030000000001,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A325,'Updated Quanities'!F:I,4,0),R325)=\"\",R325,IFERROR(VLOOKUP('AUP Library'!A325,'Updated Quanities'!F:I,4,0),R325))","v":10365.030000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A325,'Updated Quanities'!F:I,5,0),R325)=\"\",R325,IFERROR(VLOOKUP('AUP Library'!A325,'Updated Quanities'!F:I,5,0),R325))","v":10365.030000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A325,'Updated Quanities'!F:I,6,0),R325)=\"\",R325,IFERROR(VLOOKUP('AUP Library'!A325,'Updated Quanities'!F:I,6,0),R325))","v":10365.030000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A325,'Updated Quanities'!F:I,7,0),R325)=\"\",R325,IFERROR(VLOOKUP('AUP Library'!A325,'Updated Quanities'!F:I,7,0),R325))","v":10365.030000000001},10365.030000000001,{"$f":"IFERROR(VLOOKUP('AUP Library'!A325,'Updated Quanities'!F:G,4,0),R325)","v":10365.030000000001}]
["611-31.04","Catch Basins, Type 31, > 12' - 16' Depth","EA",12762.04,12762.04,12762.04,12762.04,12762.04,12762.04,12762.04,12762.04,12762.04,12762.04,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A326,'Updated Quanities'!F:I,4,0),R326)=\"\",R326,IFERROR(VLOOKUP('AUP Library'!A326,'Updated Quanities'!F:I,4,0),R326))","v":12762.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A326,'Updated Quanities'!F:I,5,0),R326)=\"\",R326,IFERROR(VLOOKUP('AUP Library'!A326,'Updated Quanities'!F:I,5,0),R326))","v":12762.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A326,'Updated Quanities'!F:I,6,0),R326)=\"\",R326,IFERROR(VLOOKUP('AUP Library'!A326,'Updated Quanities'!F:I,6,0),R326))","v":12762.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A326,'Updated Quanities'!F:I,7,0),R326)=\"\",R326,IFERROR(VLOOKUP('AUP Library'!A326,'Updated Quanities'!F:I,7,0),R326))","v":12762.04},12762.04,{"$f":"IFERROR(VLOOKUP('AUP Library'!A326,'Updated Quanities'!F:G,4,0),R326)","v":12762.04}]
["611-32.01","Catch Basins, Type 32, > 0' - 4' Depth","EA",4678.1899999999996,4678.1899999999996,4678.1899999999996,4678.1899999999996,4678.1899999999996,4678.1899999999996,4678.1899999999996,4678.1899999999996,4678.1899999999996,4678.1899999999996,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A327,'Updated Quanities'!F:I,4,0),R327)=\"\",R327,IFERROR(VLOOKUP('AUP Library'!A327,'Updated Quanities'!F:I,4,0),R327))","v":4678.1899999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A327,'Updated Quanities'!F:I,5,0),R327)=\"\",R327,IFERROR(VLOOKUP('AUP Library'!A327,'Updated Quanities'!F:I,5,0),R327))","v":4678.1899999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A327,'Updated Quanities'!F:I,6,0),R327)=\"\",R327,IFERROR(VLOOKUP('AUP Library'!A327,'Updated Quanities'!F:I,6,0),R327))","v":4678.1899999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A327,'Updated Quanities'!F:I,7,0),R327)=\"\",R327,IFERROR(VLOOKUP('AUP Library'!A327,'Updated Quanities'!F:I,7,0),R327))","v":4678.1899999999996},4678.1899999999996,{"$f":"IFERROR(VLOOKUP('AUP Library'!A327,'Updated Quanities'!F:G,4,0),R327)","v":4678.1899999999996}]
["611-32.02","Catch Basins, Type 32, > 4' - 6' Depth","EA",3304.07,3304.07,3304.07,3304.07,3304.07,3304.07,3304.07,3304.07,3304.07,3304.07,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A328,'Updated Quanities'!F:I,4,0),R328)=\"\",R328,IFERROR(VLOOKUP('AUP Library'!A328,'Updated Quanities'!F:I,4,0),R328))","v":3304.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A328,'Updated Quanities'!F:I,5,0),R328)=\"\",R328,IFERROR(VLOOKUP('AUP Library'!A328,'Updated Quanities'!F:I,5,0),R328))","v":3304.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A328,'Updated Quanities'!F:I,6,0),R328)=\"\",R328,IFERROR(VLOOKUP('AUP Library'!A328,'Updated Quanities'!F:I,6,0),R328))","v":3304.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A328,'Updated Quanities'!F:I,7,0),R328)=\"\",R328,IFERROR(VLOOKUP('AUP Library'!A328,'Updated Quanities'!F:I,7,0),R328))","v":3304.07},3304.07,{"$f":"IFERROR(VLOOKUP('AUP Library'!A328,'Updated Quanities'!F:G,4,0),R328)","v":3304.07}]
["611-38.02","Catch Basins, Type 38, > 4' - 8' Depth","EA",4691.21,4691.21,4691.21,4691.21,4691.21,4691.21,4691.21,4691.21,4691.21,4691.21,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A329,'Updated Quanities'!F:I,4,0),R329)=\"\",R329,IFERROR(VLOOKUP('AUP Library'!A329,'Updated Quanities'!F:I,4,0),R329))","v":4691.21},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A329,'Updated Quanities'!F:I,5,0),R329)=\"\",R329,IFERROR(VLOOKUP('AUP Library'!A329,'Updated Quanities'!F:I,5,0),R329))","v":4691.21},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A329,'Updated Quanities'!F:I,6,0),R329)=\"\",R329,IFERROR(VLOOKUP('AUP Library'!A329,'Updated Quanities'!F:I,6,0),R329))","v":4691.21},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A329,'Updated Quanities'!F:I,7,0),R329)=\"\",R329,IFERROR(VLOOKUP('AUP Library'!A329,'Updated Quanities'!F:I,7,0),R329))","v":4691.21},4691.21,{"$f":"IFERROR(VLOOKUP('AUP Library'!A329,'Updated Quanities'!F:G,4,0),R329)","v":4691.21}]
["611-39.01","Catch Basins, Type 39, > 0' - 4' Depth","EA",2883.1,2883.1,2883.1,2883.1,2883.1,2883.1,2883.1,2883.1,2883.1,2883.1,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A330,'Updated Quanities'!F:I,4,0),R330)=\"\",R330,IFERROR(VLOOKUP('AUP Library'!A330,'Updated Quanities'!F:I,4,0),R330))","v":2883.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A330,'Updated Quanities'!F:I,5,0),R330)=\"\",R330,IFERROR(VLOOKUP('AUP Library'!A330,'Updated Quanities'!F:I,5,0),R330))","v":2883.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A330,'Updated Quanities'!F:I,6,0),R330)=\"\",R330,IFERROR(VLOOKUP('AUP Library'!A330,'Updated Quanities'!F:I,6,0),R330))","v":2883.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A330,'Updated Quanities'!F:I,7,0),R330)=\"\",R330,IFERROR(VLOOKUP('AUP Library'!A330,'Updated Quanities'!F:I,7,0),R330))","v":2883.1},2883.1,{"$f":"IFERROR(VLOOKUP('AUP Library'!A330,'Updated Quanities'!F:G,4,0),R330)","v":2883.1}]
["611-39.02","Catch Basins, Type 39, > 4' - 8' Depth","EA",4395.67,4395.67,4395.67,4395.67,4395.67,4395.67,4395.67,4395.67,4395.67,4395.67,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A331,'Updated Quanities'!F:I,4,0),R331)=\"\",R331,IFERROR(VLOOKUP('AUP Library'!A331,'Updated Quanities'!F:I,4,0),R331))","v":4395.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A331,'Updated Quanities'!F:I,5,0),R331)=\"\",R331,IFERROR(VLOOKUP('AUP Library'!A331,'Updated Quanities'!F:I,5,0),R331))","v":4395.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A331,'Updated Quanities'!F:I,6,0),R331)=\"\",R331,IFERROR(VLOOKUP('AUP Library'!A331,'Updated Quanities'!F:I,6,0),R331))","v":4395.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A331,'Updated Quanities'!F:I,7,0),R331)=\"\",R331,IFERROR(VLOOKUP('AUP Library'!A331,'Updated Quanities'!F:I,7,0),R331))","v":4395.67},4395.67,{"$f":"IFERROR(VLOOKUP('AUP Library'!A331,'Updated Quanities'!F:G,4,0),R331)","v":4395.67}]
["611-39.03","Catch Basins, Type 39, > 8' - 12' Depth","EA",7232.38,7232.38,7232.38,7232.38,7232.38,7232.38,7232.38,7232.38,7232.38,7232.38,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A332,'Updated Quanities'!F:I,4,0),R332)=\"\",R332,IFERROR(VLOOKUP('AUP Library'!A332,'Updated Quanities'!F:I,4,0),R332))","v":7232.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A332,'Updated Quanities'!F:I,5,0),R332)=\"\",R332,IFERROR(VLOOKUP('AUP Library'!A332,'Updated Quanities'!F:I,5,0),R332))","v":7232.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A332,'Updated Quanities'!F:I,6,0),R332)=\"\",R332,IFERROR(VLOOKUP('AUP Library'!A332,'Updated Quanities'!F:I,6,0),R332))","v":7232.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A332,'Updated Quanities'!F:I,7,0),R332)=\"\",R332,IFERROR(VLOOKUP('AUP Library'!A332,'Updated Quanities'!F:I,7,0),R332))","v":7232.38},7232.38,{"$f":"IFERROR(VLOOKUP('AUP Library'!A332,'Updated Quanities'!F:G,4,0),R332)","v":7232.38}]
["611-39.04","Catch Basins, Type 39, > 12' - 16' Depth","EA",8000,8000,8000,8000,8000,8000,8000,8000,8000,8000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A333,'Updated Quanities'!F:I,4,0),R333)=\"\",R333,IFERROR(VLOOKUP('AUP Library'!A333,'Updated Quanities'!F:I,4,0),R333))","v":8000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A333,'Updated Quanities'!F:I,5,0),R333)=\"\",R333,IFERROR(VLOOKUP('AUP Library'!A333,'Updated Quanities'!F:I,5,0),R333))","v":8000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A333,'Updated Quanities'!F:I,6,0),R333)=\"\",R333,IFERROR(VLOOKUP('AUP Library'!A333,'Updated Quanities'!F:I,6,0),R333))","v":8000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A333,'Updated Quanities'!F:I,7,0),R333)=\"\",R333,IFERROR(VLOOKUP('AUP Library'!A333,'Updated Quanities'!F:I,7,0),R333))","v":8000},8000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A333,'Updated Quanities'!F:G,4,0),R333)","v":8000}]
["611-39.05","Catch Basins, Type 39, > 16' - 20' Depth","EA",14000,14000,14000,14000,14000,14000,14000,14000,14000,14000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A334,'Updated Quanities'!F:I,4,0),R334)=\"\",R334,IFERROR(VLOOKUP('AUP Library'!A334,'Updated Quanities'!F:I,4,0),R334))","v":14000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A334,'Updated Quanities'!F:I,5,0),R334)=\"\",R334,IFERROR(VLOOKUP('AUP Library'!A334,'Updated Quanities'!F:I,5,0),R334))","v":14000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A334,'Updated Quanities'!F:I,6,0),R334)=\"\",R334,IFERROR(VLOOKUP('AUP Library'!A334,'Updated Quanities'!F:I,6,0),R334))","v":14000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A334,'Updated Quanities'!F:I,7,0),R334)=\"\",R334,IFERROR(VLOOKUP('AUP Library'!A334,'Updated Quanities'!F:I,7,0),R334))","v":14000},14000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A334,'Updated Quanities'!F:G,4,0),R334)","v":14000}]
["611-40.01","Catch Basins, Type 40, > 0' - 4' Depth","EA",6500,6500,6500,6500,6500,6500,6500,6500,6500,6500,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A335,'Updated Quanities'!F:I,4,0),R335)=\"\",R335,IFERROR(VLOOKUP('AUP Library'!A335,'Updated Quanities'!F:I,4,0),R335))","v":6500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A335,'Updated Quanities'!F:I,5,0),R335)=\"\",R335,IFERROR(VLOOKUP('AUP Library'!A335,'Updated Quanities'!F:I,5,0),R335))","v":6500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A335,'Updated Quanities'!F:I,6,0),R335)=\"\",R335,IFERROR(VLOOKUP('AUP Library'!A335,'Updated Quanities'!F:I,6,0),R335))","v":6500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A335,'Updated Quanities'!F:I,7,0),R335)=\"\",R335,IFERROR(VLOOKUP('AUP Library'!A335,'Updated Quanities'!F:I,7,0),R335))","v":6500},6500,{"$f":"IFERROR(VLOOKUP('AUP Library'!A335,'Updated Quanities'!F:G,4,0),R335)","v":6500}]
["611-40.02","Catch Basins, Type 40, > 4' - 8' Depth","EA",6077.01,6077.01,6077.01,6077.01,6077.01,6077.01,6077.01,6077.01,6077.01,6077.01,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A336,'Updated Quanities'!F:I,4,0),R336)=\"\",R336,IFERROR(VLOOKUP('AUP Library'!A336,'Updated Quanities'!F:I,4,0),R336))","v":6077.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A336,'Updated Quanities'!F:I,5,0),R336)=\"\",R336,IFERROR(VLOOKUP('AUP Library'!A336,'Updated Quanities'!F:I,5,0),R336))","v":6077.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A336,'Updated Quanities'!F:I,6,0),R336)=\"\",R336,IFERROR(VLOOKUP('AUP Library'!A336,'Updated Quanities'!F:I,6,0),R336))","v":6077.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A336,'Updated Quanities'!F:I,7,0),R336)=\"\",R336,IFERROR(VLOOKUP('AUP Library'!A336,'Updated Quanities'!F:I,7,0),R336))","v":6077.01},6077.01,{"$f":"IFERROR(VLOOKUP('AUP Library'!A336,'Updated Quanities'!F:G,4,0),R336)","v":6077.01}]
["611-40.03","Catch Basins, Type 40, > 8' - 12' Depth","EA",6077.01,6077.01,6077.01,6077.01,6077.01,6077.01,6077.01,6077.01,6077.01,6077.01,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A337,'Updated Quanities'!F:I,4,0),R337)=\"\",R337,IFERROR(VLOOKUP('AUP Library'!A337,'Updated Quanities'!F:I,4,0),R337))","v":6077.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A337,'Updated Quanities'!F:I,5,0),R337)=\"\",R337,IFERROR(VLOOKUP('AUP Library'!A337,'Updated Quanities'!F:I,5,0),R337))","v":6077.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A337,'Updated Quanities'!F:I,6,0),R337)=\"\",R337,IFERROR(VLOOKUP('AUP Library'!A337,'Updated Quanities'!F:I,6,0),R337))","v":6077.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A337,'Updated Quanities'!F:I,7,0),R337)=\"\",R337,IFERROR(VLOOKUP('AUP Library'!A337,'Updated Quanities'!F:I,7,0),R337))","v":6077.01},6077.01,{"$f":"IFERROR(VLOOKUP('AUP Library'!A337,'Updated Quanities'!F:G,4,0),R337)","v":6077.01}]
["611-40.04","Catch Basins, Type 40, > 12' - 16' Depth","EA",6077.01,6077.01,6077.01,6077.01,6077.01,6077.01,6077.01,6077.01,6077.01,6077.01,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A338,'Updated Quanities'!F:I,4,0),R338)=\"\",R338,IFERROR(VLOOKUP('AUP Library'!A338,'Updated Quanities'!F:I,4,0),R338))","v":6077.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A338,'Updated Quanities'!F:I,5,0),R338)=\"\",R338,IFERROR(VLOOKUP('AUP Library'!A338,'Updated Quanities'!F:I,5,0),R338))","v":6077.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A338,'Updated Quanities'!F:I,6,0),R338)=\"\",R338,IFERROR(VLOOKUP('AUP Library'!A338,'Updated Quanities'!F:I,6,0),R338))","v":6077.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A338,'Updated Quanities'!F:I,7,0),R338)=\"\",R338,IFERROR(VLOOKUP('AUP Library'!A338,'Updated Quanities'!F:I,7,0),R338))","v":6077.01},6077.01,{"$f":"IFERROR(VLOOKUP('AUP Library'!A338,'Updated Quanities'!F:G,4,0),R338)","v":6077.01}]
["611-41.01","Catch Basins, Type 41, > 0' - 4' Depth","EA",2959.43,2959.43,2959.43,2959.43,2959.43,2959.43,2959.43,2959.43,2959.43,2959.43,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A339,'Updated Quanities'!F:I,4,0),R339)=\"\",R339,IFERROR(VLOOKUP('AUP Library'!A339,'Updated Quanities'!F:I,4,0),R339))","v":2959.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A339,'Updated Quanities'!F:I,5,0),R339)=\"\",R339,IFERROR(VLOOKUP('AUP Library'!A339,'Updated Quanities'!F:I,5,0),R339))","v":2959.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A339,'Updated Quanities'!F:I,6,0),R339)=\"\",R339,IFERROR(VLOOKUP('AUP Library'!A339,'Updated Quanities'!F:I,6,0),R339))","v":2959.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A339,'Updated Quanities'!F:I,7,0),R339)=\"\",R339,IFERROR(VLOOKUP('AUP Library'!A339,'Updated Quanities'!F:I,7,0),R339))","v":2959.43},2959.43,{"$f":"IFERROR(VLOOKUP('AUP Library'!A339,'Updated Quanities'!F:G,4,0),R339)","v":2959.43}]
["611-41.02","Catch Basins, Type 41, > 4' - 8' Depth","EA",4621.67,4621.67,4621.67,4621.67,4621.67,4621.67,4621.67,4621.67,4621.67,4621.67,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A340,'Updated Quanities'!F:I,4,0),R340)=\"\",R340,IFERROR(VLOOKUP('AUP Library'!A340,'Updated Quanities'!F:I,4,0),R340))","v":4621.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A340,'Updated Quanities'!F:I,5,0),R340)=\"\",R340,IFERROR(VLOOKUP('AUP Library'!A340,'Updated Quanities'!F:I,5,0),R340))","v":4621.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A340,'Updated Quanities'!F:I,6,0),R340)=\"\",R340,IFERROR(VLOOKUP('AUP Library'!A340,'Updated Quanities'!F:I,6,0),R340))","v":4621.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A340,'Updated Quanities'!F:I,7,0),R340)=\"\",R340,IFERROR(VLOOKUP('AUP Library'!A340,'Updated Quanities'!F:I,7,0),R340))","v":4621.67},4621.67,{"$f":"IFERROR(VLOOKUP('AUP Library'!A340,'Updated Quanities'!F:G,4,0),R340)","v":4621.67}]
["611-41.03","Catch Basins, Type 41, > 8' - 12' Depth","EA",3620,3620,3620,3620,3620,3620,3620,3620,3620,3620,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A341,'Updated Quanities'!F:I,4,0),R341)=\"\",R341,IFERROR(VLOOKUP('AUP Library'!A341,'Updated Quanities'!F:I,4,0),R341))","v":3620},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A341,'Updated Quanities'!F:I,5,0),R341)=\"\",R341,IFERROR(VLOOKUP('AUP Library'!A341,'Updated Quanities'!F:I,5,0),R341))","v":3620},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A341,'Updated Quanities'!F:I,6,0),R341)=\"\",R341,IFERROR(VLOOKUP('AUP Library'!A341,'Updated Quanities'!F:I,6,0),R341))","v":3620},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A341,'Updated Quanities'!F:I,7,0),R341)=\"\",R341,IFERROR(VLOOKUP('AUP Library'!A341,'Updated Quanities'!F:I,7,0),R341))","v":3620},3620,{"$f":"IFERROR(VLOOKUP('AUP Library'!A341,'Updated Quanities'!F:G,4,0),R341)","v":3620}]
["611-41.04","Catch Basins, Type 41, > 12' - 16' Depth","EA",9880,9880,9880,9880,9880,9880,9880,9880,9880,9880,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A342,'Updated Quanities'!F:I,4,0),R342)=\"\",R342,IFERROR(VLOOKUP('AUP Library'!A342,'Updated Quanities'!F:I,4,0),R342))","v":9880},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A342,'Updated Quanities'!F:I,5,0),R342)=\"\",R342,IFERROR(VLOOKUP('AUP Library'!A342,'Updated Quanities'!F:I,5,0),R342))","v":9880},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A342,'Updated Quanities'!F:I,6,0),R342)=\"\",R342,IFERROR(VLOOKUP('AUP Library'!A342,'Updated Quanities'!F:I,6,0),R342))","v":9880},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A342,'Updated Quanities'!F:I,7,0),R342)=\"\",R342,IFERROR(VLOOKUP('AUP Library'!A342,'Updated Quanities'!F:I,7,0),R342))","v":9880},9880,{"$f":"IFERROR(VLOOKUP('AUP Library'!A342,'Updated Quanities'!F:G,4,0),R342)","v":9880}]
["611-42.01","Catch Basins, Type 42, > 0' - 4' Depth","EA",2959.43,2959.43,2959.43,2959.43,2959.43,2959.43,2959.43,2959.43,2959.43,2959.43,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A343,'Updated Quanities'!F:I,4,0),R343)=\"\",R343,IFERROR(VLOOKUP('AUP Library'!A343,'Updated Quanities'!F:I,4,0),R343))","v":2959.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A343,'Updated Quanities'!F:I,5,0),R343)=\"\",R343,IFERROR(VLOOKUP('AUP Library'!A343,'Updated Quanities'!F:I,5,0),R343))","v":2959.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A343,'Updated Quanities'!F:I,6,0),R343)=\"\",R343,IFERROR(VLOOKUP('AUP Library'!A343,'Updated Quanities'!F:I,6,0),R343))","v":2959.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A343,'Updated Quanities'!F:I,7,0),R343)=\"\",R343,IFERROR(VLOOKUP('AUP Library'!A343,'Updated Quanities'!F:I,7,0),R343))","v":2959.43},2959.43,{"$f":"IFERROR(VLOOKUP('AUP Library'!A343,'Updated Quanities'!F:G,4,0),R343)","v":2959.43}]
["611-42.02","Catch Basins, Type 42, > 4' - 8' Depth","EA",3018.26,2422.85,2434.48,3064.67,3064.67,2583.25,3503.22,4522.91,3972.26,4126.17,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A344,'Updated Quanities'!F:I,4,0),R344)=\"\",R344,IFERROR(VLOOKUP('AUP Library'!A344,'Updated Quanities'!F:I,4,0),R344))","v":4315.97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A344,'Updated Quanities'!F:I,5,0),R344)=\"\",R344,IFERROR(VLOOKUP('AUP Library'!A344,'Updated Quanities'!F:I,5,0),R344))","v":4315.97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A344,'Updated Quanities'!F:I,6,0),R344)=\"\",R344,IFERROR(VLOOKUP('AUP Library'!A344,'Updated Quanities'!F:I,6,0),R344))","v":4315.97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A344,'Updated Quanities'!F:I,7,0),R344)=\"\",R344,IFERROR(VLOOKUP('AUP Library'!A344,'Updated Quanities'!F:I,7,0),R344))","v":4315.97},4315.97,{"$f":"IFERROR(VLOOKUP('AUP Library'!A344,'Updated Quanities'!F:G,4,0),R344)","v":4315.97}]
["611-42.03","Catch Basins, Type 42, > 8' - 12' Depth","EA",6051.93,6051.93,6051.93,6051.93,6051.93,6051.93,6051.93,6051.93,6051.93,6051.93,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A345,'Updated Quanities'!F:I,4,0),R345)=\"\",R345,IFERROR(VLOOKUP('AUP Library'!A345,'Updated Quanities'!F:I,4,0),R345))","v":6051.93},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A345,'Updated Quanities'!F:I,5,0),R345)=\"\",R345,IFERROR(VLOOKUP('AUP Library'!A345,'Updated Quanities'!F:I,5,0),R345))","v":6051.93},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A345,'Updated Quanities'!F:I,6,0),R345)=\"\",R345,IFERROR(VLOOKUP('AUP Library'!A345,'Updated Quanities'!F:I,6,0),R345))","v":6051.93},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A345,'Updated Quanities'!F:I,7,0),R345)=\"\",R345,IFERROR(VLOOKUP('AUP Library'!A345,'Updated Quanities'!F:I,7,0),R345))","v":6051.93},6051.93,{"$f":"IFERROR(VLOOKUP('AUP Library'!A345,'Updated Quanities'!F:G,4,0),R345)","v":6051.93}]
["611-42.04","Catch Basins, Type 42, > 12' - 16' Depth","EA",6051.93,6051.93,6051.93,6051.93,6051.93,6051.93,6051.93,6051.93,6051.93,6051.93,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A346,'Updated Quanities'!F:I,4,0),R346)=\"\",R346,IFERROR(VLOOKUP('AUP Library'!A346,'Updated Quanities'!F:I,4,0),R346))","v":6051.93},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A346,'Updated Quanities'!F:I,5,0),R346)=\"\",R346,IFERROR(VLOOKUP('AUP Library'!A346,'Updated Quanities'!F:I,5,0),R346))","v":6051.93},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A346,'Updated Quanities'!F:I,6,0),R346)=\"\",R346,IFERROR(VLOOKUP('AUP Library'!A346,'Updated Quanities'!F:I,6,0),R346))","v":6051.93},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A346,'Updated Quanities'!F:I,7,0),R346)=\"\",R346,IFERROR(VLOOKUP('AUP Library'!A346,'Updated Quanities'!F:I,7,0),R346))","v":6051.93},6051.93,{"$f":"IFERROR(VLOOKUP('AUP Library'!A346,'Updated Quanities'!F:G,4,0),R346)","v":6051.93}]
["611-43.01","Catch Basins, Type 43, > 0' - 4' Depth","EA",4623.43,4623.43,4623.43,4623.43,4623.43,4623.43,4623.43,4623.43,4623.43,4623.43,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A347,'Updated Quanities'!F:I,4,0),R347)=\"\",R347,IFERROR(VLOOKUP('AUP Library'!A347,'Updated Quanities'!F:I,4,0),R347))","v":4623.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A347,'Updated Quanities'!F:I,5,0),R347)=\"\",R347,IFERROR(VLOOKUP('AUP Library'!A347,'Updated Quanities'!F:I,5,0),R347))","v":4623.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A347,'Updated Quanities'!F:I,6,0),R347)=\"\",R347,IFERROR(VLOOKUP('AUP Library'!A347,'Updated Quanities'!F:I,6,0),R347))","v":4623.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A347,'Updated Quanities'!F:I,7,0),R347)=\"\",R347,IFERROR(VLOOKUP('AUP Library'!A347,'Updated Quanities'!F:I,7,0),R347))","v":4623.43},4623.43,{"$f":"IFERROR(VLOOKUP('AUP Library'!A347,'Updated Quanities'!F:G,4,0),R347)","v":4623.43}]
["611-43.02","Catch Basins, Type 43, > 4' - 8' Depth","EA",4879.16,4879.16,4879.16,4879.16,4879.16,4879.16,4879.16,4879.16,4879.16,4879.16,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A348,'Updated Quanities'!F:I,4,0),R348)=\"\",R348,IFERROR(VLOOKUP('AUP Library'!A348,'Updated Quanities'!F:I,4,0),R348))","v":4879.16},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A348,'Updated Quanities'!F:I,5,0),R348)=\"\",R348,IFERROR(VLOOKUP('AUP Library'!A348,'Updated Quanities'!F:I,5,0),R348))","v":4879.16},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A348,'Updated Quanities'!F:I,6,0),R348)=\"\",R348,IFERROR(VLOOKUP('AUP Library'!A348,'Updated Quanities'!F:I,6,0),R348))","v":4879.16},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A348,'Updated Quanities'!F:I,7,0),R348)=\"\",R348,IFERROR(VLOOKUP('AUP Library'!A348,'Updated Quanities'!F:I,7,0),R348))","v":4879.16},4879.16,{"$f":"IFERROR(VLOOKUP('AUP Library'!A348,'Updated Quanities'!F:G,4,0),R348)","v":4879.16}]
["611-43.03","Catch Basins, Type 43, > 8' - 12' Depth","EA",12762.04,12762.04,12762.04,12762.04,12762.04,12762.04,12762.04,12762.04,12762.04,12762.04,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A349,'Updated Quanities'!F:I,4,0),R349)=\"\",R349,IFERROR(VLOOKUP('AUP Library'!A349,'Updated Quanities'!F:I,4,0),R349))","v":12762.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A349,'Updated Quanities'!F:I,5,0),R349)=\"\",R349,IFERROR(VLOOKUP('AUP Library'!A349,'Updated Quanities'!F:I,5,0),R349))","v":12762.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A349,'Updated Quanities'!F:I,6,0),R349)=\"\",R349,IFERROR(VLOOKUP('AUP Library'!A349,'Updated Quanities'!F:I,6,0),R349))","v":12762.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A349,'Updated Quanities'!F:I,7,0),R349)=\"\",R349,IFERROR(VLOOKUP('AUP Library'!A349,'Updated Quanities'!F:I,7,0),R349))","v":12762.04},12762.04,{"$f":"IFERROR(VLOOKUP('AUP Library'!A349,'Updated Quanities'!F:G,4,0),R349)","v":12762.04}]
["611-43.04","Catch Basins, Type 43, > 12' - 16' Depth","EA",12762.04,12762.04,12762.04,12762.04,12762.04,12762.04,12762.04,12762.04,12762.04,12762.04,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A350,'Updated Quanities'!F:I,4,0),R350)=\"\",R350,IFERROR(VLOOKUP('AUP Library'!A350,'Updated Quanities'!F:I,4,0),R350))","v":12762.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A350,'Updated Quanities'!F:I,5,0),R350)=\"\",R350,IFERROR(VLOOKUP('AUP Library'!A350,'Updated Quanities'!F:I,5,0),R350))","v":12762.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A350,'Updated Quanities'!F:I,6,0),R350)=\"\",R350,IFERROR(VLOOKUP('AUP Library'!A350,'Updated Quanities'!F:I,6,0),R350))","v":12762.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A350,'Updated Quanities'!F:I,7,0),R350)=\"\",R350,IFERROR(VLOOKUP('AUP Library'!A350,'Updated Quanities'!F:I,7,0),R350))","v":12762.04},12762.04,{"$f":"IFERROR(VLOOKUP('AUP Library'!A350,'Updated Quanities'!F:G,4,0),R350)","v":12762.04}]
["611-44.01","Catch Basins, Type 44, > 0' - 4' Depth","EA",13700,13700,13700,13700,13700,13700,13700,13700,13700,13700,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A351,'Updated Quanities'!F:I,4,0),R351)=\"\",R351,IFERROR(VLOOKUP('AUP Library'!A351,'Updated Quanities'!F:I,4,0),R351))","v":13700},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A351,'Updated Quanities'!F:I,5,0),R351)=\"\",R351,IFERROR(VLOOKUP('AUP Library'!A351,'Updated Quanities'!F:I,5,0),R351))","v":13700},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A351,'Updated Quanities'!F:I,6,0),R351)=\"\",R351,IFERROR(VLOOKUP('AUP Library'!A351,'Updated Quanities'!F:I,6,0),R351))","v":13700},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A351,'Updated Quanities'!F:I,7,0),R351)=\"\",R351,IFERROR(VLOOKUP('AUP Library'!A351,'Updated Quanities'!F:I,7,0),R351))","v":13700},13700,{"$f":"IFERROR(VLOOKUP('AUP Library'!A351,'Updated Quanities'!F:G,4,0),R351)","v":13700}]
["611-44.02","Catch Basins, Type 44, > 4' - 8' Depth","EA",6100,6100,6100,6100,6100,6100,6100,6100,6100,6100,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A352,'Updated Quanities'!F:I,4,0),R352)=\"\",R352,IFERROR(VLOOKUP('AUP Library'!A352,'Updated Quanities'!F:I,4,0),R352))","v":6100},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A352,'Updated Quanities'!F:I,5,0),R352)=\"\",R352,IFERROR(VLOOKUP('AUP Library'!A352,'Updated Quanities'!F:I,5,0),R352))","v":6100},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A352,'Updated Quanities'!F:I,6,0),R352)=\"\",R352,IFERROR(VLOOKUP('AUP Library'!A352,'Updated Quanities'!F:I,6,0),R352))","v":6100},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A352,'Updated Quanities'!F:I,7,0),R352)=\"\",R352,IFERROR(VLOOKUP('AUP Library'!A352,'Updated Quanities'!F:I,7,0),R352))","v":6100},6100,{"$f":"IFERROR(VLOOKUP('AUP Library'!A352,'Updated Quanities'!F:G,4,0),R352)","v":6100}]
["611-44.03","Catch Basins, Type 44, > 8' - 12' Depth","EA",12760.04,12760.04,12760.04,12760.04,12760.04,12760.04,12760.04,12760.04,12760.04,12760.04,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A353,'Updated Quanities'!F:I,4,0),R353)=\"\",R353,IFERROR(VLOOKUP('AUP Library'!A353,'Updated Quanities'!F:I,4,0),R353))","v":12760.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A353,'Updated Quanities'!F:I,5,0),R353)=\"\",R353,IFERROR(VLOOKUP('AUP Library'!A353,'Updated Quanities'!F:I,5,0),R353))","v":12760.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A353,'Updated Quanities'!F:I,6,0),R353)=\"\",R353,IFERROR(VLOOKUP('AUP Library'!A353,'Updated Quanities'!F:I,6,0),R353))","v":12760.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A353,'Updated Quanities'!F:I,7,0),R353)=\"\",R353,IFERROR(VLOOKUP('AUP Library'!A353,'Updated Quanities'!F:I,7,0),R353))","v":12760.04},12760.04,{"$f":"IFERROR(VLOOKUP('AUP Library'!A353,'Updated Quanities'!F:G,4,0),R353)","v":12760.04}]
["611-44.04","Catch Basins, Type 44, > 12' - 16' Depth","EA",12760.04,12760.04,12760.04,12760.04,12760.04,12760.04,12760.04,12760.04,12760.04,12760.04,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A354,'Updated Quanities'!F:I,4,0),R354)=\"\",R354,IFERROR(VLOOKUP('AUP Library'!A354,'Updated Quanities'!F:I,4,0),R354))","v":12760.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A354,'Updated Quanities'!F:I,5,0),R354)=\"\",R354,IFERROR(VLOOKUP('AUP Library'!A354,'Updated Quanities'!F:I,5,0),R354))","v":12760.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A354,'Updated Quanities'!F:I,6,0),R354)=\"\",R354,IFERROR(VLOOKUP('AUP Library'!A354,'Updated Quanities'!F:I,6,0),R354))","v":12760.04},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A354,'Updated Quanities'!F:I,7,0),R354)=\"\",R354,IFERROR(VLOOKUP('AUP Library'!A354,'Updated Quanities'!F:I,7,0),R354))","v":12760.04},12760.04,{"$f":"IFERROR(VLOOKUP('AUP Library'!A354,'Updated Quanities'!F:G,4,0),R354)","v":12760.04}]
["611-46.01","Catch Basins, Type 46, > 0' - 4' Depth","EA",18816.810000000001,18816.810000000001,18816.810000000001,18816.810000000001,18816.810000000001,18816.810000000001,18816.810000000001,18816.810000000001,18816.810000000001,18816.810000000001,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A355,'Updated Quanities'!F:I,4,0),R355)=\"\",R355,IFERROR(VLOOKUP('AUP Library'!A355,'Updated Quanities'!F:I,4,0),R355))","v":18816.810000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A355,'Updated Quanities'!F:I,5,0),R355)=\"\",R355,IFERROR(VLOOKUP('AUP Library'!A355,'Updated Quanities'!F:I,5,0),R355))","v":18816.810000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A355,'Updated Quanities'!F:I,6,0),R355)=\"\",R355,IFERROR(VLOOKUP('AUP Library'!A355,'Updated Quanities'!F:I,6,0),R355))","v":18816.810000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A355,'Updated Quanities'!F:I,7,0),R355)=\"\",R355,IFERROR(VLOOKUP('AUP Library'!A355,'Updated Quanities'!F:I,7,0),R355))","v":18816.810000000001},18816.810000000001,{"$f":"IFERROR(VLOOKUP('AUP Library'!A355,'Updated Quanities'!F:G,4,0),R355)","v":18816.810000000001}]
["611-46.02","Catch Basins, Type 46, > 4' - 8' Depth","EA",18816.810000000001,18816.810000000001,18816.810000000001,18816.810000000001,18816.810000000001,18816.810000000001,18816.810000000001,18816.810000000001,18816.810000000001,18816.810000000001,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A356,'Updated Quanities'!F:I,4,0),R356)=\"\",R356,IFERROR(VLOOKUP('AUP Library'!A356,'Updated Quanities'!F:I,4,0),R356))","v":18816.810000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A356,'Updated Quanities'!F:I,5,0),R356)=\"\",R356,IFERROR(VLOOKUP('AUP Library'!A356,'Updated Quanities'!F:I,5,0),R356))","v":18816.810000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A356,'Updated Quanities'!F:I,6,0),R356)=\"\",R356,IFERROR(VLOOKUP('AUP Library'!A356,'Updated Quanities'!F:I,6,0),R356))","v":18816.810000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A356,'Updated Quanities'!F:I,7,0),R356)=\"\",R356,IFERROR(VLOOKUP('AUP Library'!A356,'Updated Quanities'!F:I,7,0),R356))","v":18816.810000000001},18816.810000000001,{"$f":"IFERROR(VLOOKUP('AUP Library'!A356,'Updated Quanities'!F:G,4,0),R356)","v":18816.810000000001}]
["611-46.03","Catch Basins, Type 46, > 8' - 12' Depth","EA",12500,12500,12500,12500,12500,12500,12500,12500,12500,12500,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A357,'Updated Quanities'!F:I,4,0),R357)=\"\",R357,IFERROR(VLOOKUP('AUP Library'!A357,'Updated Quanities'!F:I,4,0),R357))","v":12500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A357,'Updated Quanities'!F:I,5,0),R357)=\"\",R357,IFERROR(VLOOKUP('AUP Library'!A357,'Updated Quanities'!F:I,5,0),R357))","v":12500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A357,'Updated Quanities'!F:I,6,0),R357)=\"\",R357,IFERROR(VLOOKUP('AUP Library'!A357,'Updated Quanities'!F:I,6,0),R357))","v":12500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A357,'Updated Quanities'!F:I,7,0),R357)=\"\",R357,IFERROR(VLOOKUP('AUP Library'!A357,'Updated Quanities'!F:I,7,0),R357))","v":12500},12500,{"$f":"IFERROR(VLOOKUP('AUP Library'!A357,'Updated Quanities'!F:G,4,0),R357)","v":12500}]
["611-46.04","Catch Basins, Type 46, > 12' - 16' Depth","EA",12500,12500,12500,12500,12500,12500,12500,12500,12500,12500,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A358,'Updated Quanities'!F:I,4,0),R358)=\"\",R358,IFERROR(VLOOKUP('AUP Library'!A358,'Updated Quanities'!F:I,4,0),R358))","v":12500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A358,'Updated Quanities'!F:I,5,0),R358)=\"\",R358,IFERROR(VLOOKUP('AUP Library'!A358,'Updated Quanities'!F:I,5,0),R358))","v":12500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A358,'Updated Quanities'!F:I,6,0),R358)=\"\",R358,IFERROR(VLOOKUP('AUP Library'!A358,'Updated Quanities'!F:I,6,0),R358))","v":12500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A358,'Updated Quanities'!F:I,7,0),R358)=\"\",R358,IFERROR(VLOOKUP('AUP Library'!A358,'Updated Quanities'!F:I,7,0),R358))","v":12500},12500,{"$f":"IFERROR(VLOOKUP('AUP Library'!A358,'Updated Quanities'!F:G,4,0),R358)","v":12500}]
["611-51.01","Catch Basins, Type 51, > 0' - 4' Depth","EA",7235.77,7235.77,7235.77,7235.77,7235.77,7235.77,7235.77,7235.77,7235.77,7235.77,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A359,'Updated Quanities'!F:I,4,0),R359)=\"\",R359,IFERROR(VLOOKUP('AUP Library'!A359,'Updated Quanities'!F:I,4,0),R359))","v":7235.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A359,'Updated Quanities'!F:I,5,0),R359)=\"\",R359,IFERROR(VLOOKUP('AUP Library'!A359,'Updated Quanities'!F:I,5,0),R359))","v":7235.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A359,'Updated Quanities'!F:I,6,0),R359)=\"\",R359,IFERROR(VLOOKUP('AUP Library'!A359,'Updated Quanities'!F:I,6,0),R359))","v":7235.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A359,'Updated Quanities'!F:I,7,0),R359)=\"\",R359,IFERROR(VLOOKUP('AUP Library'!A359,'Updated Quanities'!F:I,7,0),R359))","v":7235.77},7235.77,{"$f":"IFERROR(VLOOKUP('AUP Library'!A359,'Updated Quanities'!F:G,4,0),R359)","v":7235.77}]
["611-51.02","Catch Basins, Type 51, > 4' - 8' Depth","EA",7235.77,7235.77,7235.77,7235.77,7235.77,7235.77,7235.77,7235.77,7235.77,7235.77,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A360,'Updated Quanities'!F:I,4,0),R360)=\"\",R360,IFERROR(VLOOKUP('AUP Library'!A360,'Updated Quanities'!F:I,4,0),R360))","v":7235.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A360,'Updated Quanities'!F:I,5,0),R360)=\"\",R360,IFERROR(VLOOKUP('AUP Library'!A360,'Updated Quanities'!F:I,5,0),R360))","v":7235.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A360,'Updated Quanities'!F:I,6,0),R360)=\"\",R360,IFERROR(VLOOKUP('AUP Library'!A360,'Updated Quanities'!F:I,6,0),R360))","v":7235.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A360,'Updated Quanities'!F:I,7,0),R360)=\"\",R360,IFERROR(VLOOKUP('AUP Library'!A360,'Updated Quanities'!F:I,7,0),R360))","v":7235.77},7235.77,{"$f":"IFERROR(VLOOKUP('AUP Library'!A360,'Updated Quanities'!F:G,4,0),R360)","v":7235.77}]
["611-51.03","Catch Basins, Type 51, > 8' - 12' Depth","EA",10500,10500,10500,10500,10500,10500,10500,10500,10500,10500,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A361,'Updated Quanities'!F:I,4,0),R361)=\"\",R361,IFERROR(VLOOKUP('AUP Library'!A361,'Updated Quanities'!F:I,4,0),R361))","v":10500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A361,'Updated Quanities'!F:I,5,0),R361)=\"\",R361,IFERROR(VLOOKUP('AUP Library'!A361,'Updated Quanities'!F:I,5,0),R361))","v":10500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A361,'Updated Quanities'!F:I,6,0),R361)=\"\",R361,IFERROR(VLOOKUP('AUP Library'!A361,'Updated Quanities'!F:I,6,0),R361))","v":10500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A361,'Updated Quanities'!F:I,7,0),R361)=\"\",R361,IFERROR(VLOOKUP('AUP Library'!A361,'Updated Quanities'!F:I,7,0),R361))","v":10500},10500,{"$f":"IFERROR(VLOOKUP('AUP Library'!A361,'Updated Quanities'!F:G,4,0),R361)","v":10500}]
["611-51.04","Catch Basins, Type 51, > 12' - 16' Depth","EA",6196.26,6196.26,6196.26,6196.26,6196.26,6196.26,6196.26,6196.26,6196.26,6196.26,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A362,'Updated Quanities'!F:I,4,0),R362)=\"\",R362,IFERROR(VLOOKUP('AUP Library'!A362,'Updated Quanities'!F:I,4,0),R362))","v":6196.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A362,'Updated Quanities'!F:I,5,0),R362)=\"\",R362,IFERROR(VLOOKUP('AUP Library'!A362,'Updated Quanities'!F:I,5,0),R362))","v":6196.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A362,'Updated Quanities'!F:I,6,0),R362)=\"\",R362,IFERROR(VLOOKUP('AUP Library'!A362,'Updated Quanities'!F:I,6,0),R362))","v":6196.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A362,'Updated Quanities'!F:I,7,0),R362)=\"\",R362,IFERROR(VLOOKUP('AUP Library'!A362,'Updated Quanities'!F:I,7,0),R362))","v":6196.26},6196.26,{"$f":"IFERROR(VLOOKUP('AUP Library'!A362,'Updated Quanities'!F:G,4,0),R362)","v":6196.26}]
["621-03.02","18\" Temporary Drainage Pipe","LF",34.119999999999997,34.119999999999997,34.119999999999997,34.119999999999997,34.119999999999997,34.119999999999997,34.119999999999997,34.119999999999997,34.119999999999997,34.119999999999997,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A363,'Updated Quanities'!F:I,4,0),R363)=\"\",R363,IFERROR(VLOOKUP('AUP Library'!A363,'Updated Quanities'!F:I,4,0),R363))","v":34.119999999999997},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A363,'Updated Quanities'!F:I,5,0),R363)=\"\",R363,IFERROR(VLOOKUP('AUP Library'!A363,'Updated Quanities'!F:I,5,0),R363))","v":34.119999999999997},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A363,'Updated Quanities'!F:I,6,0),R363)=\"\",R363,IFERROR(VLOOKUP('AUP Library'!A363,'Updated Quanities'!F:I,6,0),R363))","v":34.119999999999997},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A363,'Updated Quanities'!F:I,7,0),R363)=\"\",R363,IFERROR(VLOOKUP('AUP Library'!A363,'Updated Quanities'!F:I,7,0),R363))","v":34.119999999999997},34.119999999999997,{"$f":"IFERROR(VLOOKUP('AUP Library'!A363,'Updated Quanities'!F:G,4,0),R363)","v":34.119999999999997}]
["621-03.03","24\" Temporary Drainage Pipe","LF",36.49,36.49,36.49,36.49,36.49,36.49,36.49,36.49,36.49,36.49,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A364,'Updated Quanities'!F:I,4,0),R364)=\"\",R364,IFERROR(VLOOKUP('AUP Library'!A364,'Updated Quanities'!F:I,4,0),R364))","v":36.49},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A364,'Updated Quanities'!F:I,5,0),R364)=\"\",R364,IFERROR(VLOOKUP('AUP Library'!A364,'Updated Quanities'!F:I,5,0),R364))","v":36.49},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A364,'Updated Quanities'!F:I,6,0),R364)=\"\",R364,IFERROR(VLOOKUP('AUP Library'!A364,'Updated Quanities'!F:I,6,0),R364))","v":36.49},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A364,'Updated Quanities'!F:I,7,0),R364)=\"\",R364,IFERROR(VLOOKUP('AUP Library'!A364,'Updated Quanities'!F:I,7,0),R364))","v":36.49},36.49,{"$f":"IFERROR(VLOOKUP('AUP Library'!A364,'Updated Quanities'!F:G,4,0),R364)","v":36.49}]
["621-03.04","30\" Temporary Drainage Pipe","LF",57.03,57.03,57.03,57.03,57.03,57.03,57.03,57.03,57.03,57.03,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A365,'Updated Quanities'!F:I,4,0),R365)=\"\",R365,IFERROR(VLOOKUP('AUP Library'!A365,'Updated Quanities'!F:I,4,0),R365))","v":57.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A365,'Updated Quanities'!F:I,5,0),R365)=\"\",R365,IFERROR(VLOOKUP('AUP Library'!A365,'Updated Quanities'!F:I,5,0),R365))","v":57.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A365,'Updated Quanities'!F:I,6,0),R365)=\"\",R365,IFERROR(VLOOKUP('AUP Library'!A365,'Updated Quanities'!F:I,6,0),R365))","v":57.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A365,'Updated Quanities'!F:I,7,0),R365)=\"\",R365,IFERROR(VLOOKUP('AUP Library'!A365,'Updated Quanities'!F:I,7,0),R365))","v":57.03},57.03,{"$f":"IFERROR(VLOOKUP('AUP Library'!A365,'Updated Quanities'!F:G,4,0),R365)","v":57.03}]
["621-03.05","36\" Temporary Drainage Pipe","LF",56.06,56.06,56.06,56.06,56.06,56.06,56.06,56.06,56.06,56.06,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A366,'Updated Quanities'!F:I,4,0),R366)=\"\",R366,IFERROR(VLOOKUP('AUP Library'!A366,'Updated Quanities'!F:I,4,0),R366))","v":56.06},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A366,'Updated Quanities'!F:I,5,0),R366)=\"\",R366,IFERROR(VLOOKUP('AUP Library'!A366,'Updated Quanities'!F:I,5,0),R366))","v":56.06},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A366,'Updated Quanities'!F:I,6,0),R366)=\"\",R366,IFERROR(VLOOKUP('AUP Library'!A366,'Updated Quanities'!F:I,6,0),R366))","v":56.06},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A366,'Updated Quanities'!F:I,7,0),R366)=\"\",R366,IFERROR(VLOOKUP('AUP Library'!A366,'Updated Quanities'!F:I,7,0),R366))","v":56.06},56.06,{"$f":"IFERROR(VLOOKUP('AUP Library'!A366,'Updated Quanities'!F:G,4,0),R366)","v":56.06}]
["621-03.06","42\" Temporary Drainage Pipe","LF",53.77,53.77,53.77,53.77,53.77,53.77,53.77,53.77,53.77,53.77,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A367,'Updated Quanities'!F:I,4,0),R367)=\"\",R367,IFERROR(VLOOKUP('AUP Library'!A367,'Updated Quanities'!F:I,4,0),R367))","v":53.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A367,'Updated Quanities'!F:I,5,0),R367)=\"\",R367,IFERROR(VLOOKUP('AUP Library'!A367,'Updated Quanities'!F:I,5,0),R367))","v":53.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A367,'Updated Quanities'!F:I,6,0),R367)=\"\",R367,IFERROR(VLOOKUP('AUP Library'!A367,'Updated Quanities'!F:I,6,0),R367))","v":53.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A367,'Updated Quanities'!F:I,7,0),R367)=\"\",R367,IFERROR(VLOOKUP('AUP Library'!A367,'Updated Quanities'!F:I,7,0),R367))","v":53.77},53.77,{"$f":"IFERROR(VLOOKUP('AUP Library'!A367,'Updated Quanities'!F:G,4,0),R367)","v":53.77}]
["621-03.07","48\" Temporary Drainage Pipe","LF",61.94,61.94,61.94,61.94,61.94,61.94,61.94,61.94,61.94,61.94,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A368,'Updated Quanities'!F:I,4,0),R368)=\"\",R368,IFERROR(VLOOKUP('AUP Library'!A368,'Updated Quanities'!F:I,4,0),R368))","v":61.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A368,'Updated Quanities'!F:I,5,0),R368)=\"\",R368,IFERROR(VLOOKUP('AUP Library'!A368,'Updated Quanities'!F:I,5,0),R368))","v":61.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A368,'Updated Quanities'!F:I,6,0),R368)=\"\",R368,IFERROR(VLOOKUP('AUP Library'!A368,'Updated Quanities'!F:I,6,0),R368))","v":61.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A368,'Updated Quanities'!F:I,7,0),R368)=\"\",R368,IFERROR(VLOOKUP('AUP Library'!A368,'Updated Quanities'!F:I,7,0),R368))","v":61.94},61.94,{"$f":"IFERROR(VLOOKUP('AUP Library'!A368,'Updated Quanities'!F:G,4,0),R368)","v":61.94}]
["621-03.08","54\" Temporary Drainage Pipe","LF",85.63,85.63,85.63,85.63,85.63,85.63,85.63,85.63,85.63,85.63,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A369,'Updated Quanities'!F:I,4,0),R369)=\"\",R369,IFERROR(VLOOKUP('AUP Library'!A369,'Updated Quanities'!F:I,4,0),R369))","v":85.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A369,'Updated Quanities'!F:I,5,0),R369)=\"\",R369,IFERROR(VLOOKUP('AUP Library'!A369,'Updated Quanities'!F:I,5,0),R369))","v":85.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A369,'Updated Quanities'!F:I,6,0),R369)=\"\",R369,IFERROR(VLOOKUP('AUP Library'!A369,'Updated Quanities'!F:I,6,0),R369))","v":85.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A369,'Updated Quanities'!F:I,7,0),R369)=\"\",R369,IFERROR(VLOOKUP('AUP Library'!A369,'Updated Quanities'!F:I,7,0),R369))","v":85.63},85.63,{"$f":"IFERROR(VLOOKUP('AUP Library'!A369,'Updated Quanities'!F:G,4,0),R369)","v":85.63}]
["621-03.09","60\" Temporary Drainage Pipe","LF",95.17,95.17,95.17,95.17,95.17,95.17,95.17,95.17,95.17,95.17,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A370,'Updated Quanities'!F:I,4,0),R370)=\"\",R370,IFERROR(VLOOKUP('AUP Library'!A370,'Updated Quanities'!F:I,4,0),R370))","v":95.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A370,'Updated Quanities'!F:I,5,0),R370)=\"\",R370,IFERROR(VLOOKUP('AUP Library'!A370,'Updated Quanities'!F:I,5,0),R370))","v":95.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A370,'Updated Quanities'!F:I,6,0),R370)=\"\",R370,IFERROR(VLOOKUP('AUP Library'!A370,'Updated Quanities'!F:I,6,0),R370))","v":95.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A370,'Updated Quanities'!F:I,7,0),R370)=\"\",R370,IFERROR(VLOOKUP('AUP Library'!A370,'Updated Quanities'!F:I,7,0),R370))","v":95.17},95.17,{"$f":"IFERROR(VLOOKUP('AUP Library'!A370,'Updated Quanities'!F:G,4,0),R370)","v":95.17}]
["621-03.10","66\" Temporary Drainage Pipe","LF",110,110,110,110,110,110,110,110,110,110,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A371,'Updated Quanities'!F:I,4,0),R371)=\"\",R371,IFERROR(VLOOKUP('AUP Library'!A371,'Updated Quanities'!F:I,4,0),R371))","v":110},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A371,'Updated Quanities'!F:I,5,0),R371)=\"\",R371,IFERROR(VLOOKUP('AUP Library'!A371,'Updated Quanities'!F:I,5,0),R371))","v":110},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A371,'Updated Quanities'!F:I,6,0),R371)=\"\",R371,IFERROR(VLOOKUP('AUP Library'!A371,'Updated Quanities'!F:I,6,0),R371))","v":110},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A371,'Updated Quanities'!F:I,7,0),R371)=\"\",R371,IFERROR(VLOOKUP('AUP Library'!A371,'Updated Quanities'!F:I,7,0),R371))","v":110},110,{"$f":"IFERROR(VLOOKUP('AUP Library'!A371,'Updated Quanities'!F:G,4,0),R371)","v":110}]
["621-03.11","72\" Temporary Drainage Pipe","LF",120,120,120,120,120,120,120,120,120,120,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A372,'Updated Quanities'!F:I,4,0),R372)=\"\",R372,IFERROR(VLOOKUP('AUP Library'!A372,'Updated Quanities'!F:I,4,0),R372))","v":120},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A372,'Updated Quanities'!F:I,5,0),R372)=\"\",R372,IFERROR(VLOOKUP('AUP Library'!A372,'Updated Quanities'!F:I,5,0),R372))","v":120},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A372,'Updated Quanities'!F:I,6,0),R372)=\"\",R372,IFERROR(VLOOKUP('AUP Library'!A372,'Updated Quanities'!F:I,6,0),R372))","v":120},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A372,'Updated Quanities'!F:I,7,0),R372)=\"\",R372,IFERROR(VLOOKUP('AUP Library'!A372,'Updated Quanities'!F:I,7,0),R372))","v":120},120,{"$f":"IFERROR(VLOOKUP('AUP Library'!A372,'Updated Quanities'!F:G,4,0),R372)","v":120}]
["621-05.01","Temporary Shoring","SF",15.69,15.69,15.69,15.69,15.69,15.69,15.69,15.69,15.69,15.69,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A373,'Updated Quanities'!F:I,4,0),R373)=\"\",R373,IFERROR(VLOOKUP('AUP Library'!A373,'Updated Quanities'!F:I,4,0),R373))","v":15.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A373,'Updated Quanities'!F:I,5,0),R373)=\"\",R373,IFERROR(VLOOKUP('AUP Library'!A373,'Updated Quanities'!F:I,5,0),R373))","v":15.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A373,'Updated Quanities'!F:I,6,0),R373)=\"\",R373,IFERROR(VLOOKUP('AUP Library'!A373,'Updated Quanities'!F:I,6,0),R373))","v":15.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A373,'Updated Quanities'!F:I,7,0),R373)=\"\",R373,IFERROR(VLOOKUP('AUP Library'!A373,'Updated Quanities'!F:I,7,0),R373))","v":15.69},15.69,{"$f":"IFERROR(VLOOKUP('AUP Library'!A373,'Updated Quanities'!F:G,4,0),R373)","v":15.69}]
["703-01","Cement Concrete Ditch Paving","CY",238.63,238.63,238.63,238.63,238.63,238.63,238.63,238.63,238.63,238.63,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A374,'Updated Quanities'!F:I,4,0),R374)=\"\",R374,IFERROR(VLOOKUP('AUP Library'!A374,'Updated Quanities'!F:I,4,0),R374))","v":238.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A374,'Updated Quanities'!F:I,5,0),R374)=\"\",R374,IFERROR(VLOOKUP('AUP Library'!A374,'Updated Quanities'!F:I,5,0),R374))","v":238.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A374,'Updated Quanities'!F:I,6,0),R374)=\"\",R374,IFERROR(VLOOKUP('AUP Library'!A374,'Updated Quanities'!F:I,6,0),R374))","v":238.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A374,'Updated Quanities'!F:I,7,0),R374)=\"\",R374,IFERROR(VLOOKUP('AUP Library'!A374,'Updated Quanities'!F:I,7,0),R374))","v":238.63},238.63,{"$f":"IFERROR(VLOOKUP('AUP Library'!A374,'Updated Quanities'!F:G,4,0),R374)","v":238.63}]
["703-02","Cement Concrete Ditch Paving (Reinforced)","CY",286.35000000000002,286.35000000000002,286.35000000000002,286.35000000000002,286.35000000000002,286.35000000000002,286.35000000000002,286.35000000000002,286.35000000000002,286.35000000000002,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A375,'Updated Quanities'!F:I,4,0),R375)=\"\",R375,IFERROR(VLOOKUP('AUP Library'!A375,'Updated Quanities'!F:I,4,0),R375))","v":286.35000000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A375,'Updated Quanities'!F:I,5,0),R375)=\"\",R375,IFERROR(VLOOKUP('AUP Library'!A375,'Updated Quanities'!F:I,5,0),R375))","v":286.35000000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A375,'Updated Quanities'!F:I,6,0),R375)=\"\",R375,IFERROR(VLOOKUP('AUP Library'!A375,'Updated Quanities'!F:I,6,0),R375))","v":286.35000000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A375,'Updated Quanities'!F:I,7,0),R375)=\"\",R375,IFERROR(VLOOKUP('AUP Library'!A375,'Updated Quanities'!F:I,7,0),R375))","v":286.35000000000002},286.35000000000002,{"$f":"IFERROR(VLOOKUP('AUP Library'!A375,'Updated Quanities'!F:G,4,0),R375)","v":286.35000000000002}]
["703-02.05","Cement Concrete Ditch Paving (Slotted Drains)","CY",700,700,700,700,700,700,700,700,700,700,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A376,'Updated Quanities'!F:I,4,0),R376)=\"\",R376,IFERROR(VLOOKUP('AUP Library'!A376,'Updated Quanities'!F:I,4,0),R376))","v":700},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A376,'Updated Quanities'!F:I,5,0),R376)=\"\",R376,IFERROR(VLOOKUP('AUP Library'!A376,'Updated Quanities'!F:I,5,0),R376))","v":700},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A376,'Updated Quanities'!F:I,6,0),R376)=\"\",R376,IFERROR(VLOOKUP('AUP Library'!A376,'Updated Quanities'!F:I,6,0),R376))","v":700},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A376,'Updated Quanities'!F:I,7,0),R376)=\"\",R376,IFERROR(VLOOKUP('AUP Library'!A376,'Updated Quanities'!F:I,7,0),R376))","v":700},700,{"$f":"IFERROR(VLOOKUP('AUP Library'!A376,'Updated Quanities'!F:G,4,0),R376)","v":700}]
[710.02,"Aggregate Underdrains (with pipe)","LF",2.59,2.69,2.52,2.88,2.88,2.36,3.43,3.75,3.66,4.22,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A377,'Updated Quanities'!F:I,4,0),R377)=\"\",R377,IFERROR(VLOOKUP('AUP Library'!A377,'Updated Quanities'!F:I,4,0),R377))","v":5.46},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A377,'Updated Quanities'!F:I,5,0),R377)=\"\",R377,IFERROR(VLOOKUP('AUP Library'!A377,'Updated Quanities'!F:I,5,0),R377))","v":5.46},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A377,'Updated Quanities'!F:I,6,0),R377)=\"\",R377,IFERROR(VLOOKUP('AUP Library'!A377,'Updated Quanities'!F:I,6,0),R377))","v":5.46},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A377,'Updated Quanities'!F:I,7,0),R377)=\"\",R377,IFERROR(VLOOKUP('AUP Library'!A377,'Updated Quanities'!F:I,7,0),R377))","v":5.46},5.46,{"$f":"IFERROR(VLOOKUP('AUP Library'!A377,'Updated Quanities'!F:G,4,0),R377)","v":5.46}]
["710-04","Filter Cloth Underdrain (with pipe)","LF",6.9,6.9,6.9,6.9,6.9,6.9,6.9,6.9,6.9,6.9,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A378,'Updated Quanities'!F:I,4,0),R378)=\"\",R378,IFERROR(VLOOKUP('AUP Library'!A378,'Updated Quanities'!F:I,4,0),R378))","v":6.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A378,'Updated Quanities'!F:I,5,0),R378)=\"\",R378,IFERROR(VLOOKUP('AUP Library'!A378,'Updated Quanities'!F:I,5,0),R378))","v":6.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A378,'Updated Quanities'!F:I,6,0),R378)=\"\",R378,IFERROR(VLOOKUP('AUP Library'!A378,'Updated Quanities'!F:I,6,0),R378))","v":6.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A378,'Updated Quanities'!F:I,7,0),R378)=\"\",R378,IFERROR(VLOOKUP('AUP Library'!A378,'Updated Quanities'!F:I,7,0),R378))","v":6.9},6.9,{"$f":"IFERROR(VLOOKUP('AUP Library'!A378,'Updated Quanities'!F:G,4,0),R378)","v":6.9}]
["710-05","Lateral Underdrain","LF",2.6,2.6,2.6,2.6,2.6,2.6,2.6,2.6,2.6,2.6,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A379,'Updated Quanities'!F:I,4,0),R379)=\"\",R379,IFERROR(VLOOKUP('AUP Library'!A379,'Updated Quanities'!F:I,4,0),R379))","v":2.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A379,'Updated Quanities'!F:I,5,0),R379)=\"\",R379,IFERROR(VLOOKUP('AUP Library'!A379,'Updated Quanities'!F:I,5,0),R379))","v":2.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A379,'Updated Quanities'!F:I,6,0),R379)=\"\",R379,IFERROR(VLOOKUP('AUP Library'!A379,'Updated Quanities'!F:I,6,0),R379))","v":2.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A379,'Updated Quanities'!F:I,7,0),R379)=\"\",R379,IFERROR(VLOOKUP('AUP Library'!A379,'Updated Quanities'!F:I,7,0),R379))","v":2.6},2.6,{"$f":"IFERROR(VLOOKUP('AUP Library'!A379,'Updated Quanities'!F:G,4,0),R379)","v":2.6}]
["710-06.11","Lateral Underdrain Endwall (2:1)","EA",410.17,410.17,410.17,410.17,410.17,410.17,410.17,410.17,410.17,410.17,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A380,'Updated Quanities'!F:I,4,0),R380)=\"\",R380,IFERROR(VLOOKUP('AUP Library'!A380,'Updated Quanities'!F:I,4,0),R380))","v":410.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A380,'Updated Quanities'!F:I,5,0),R380)=\"\",R380,IFERROR(VLOOKUP('AUP Library'!A380,'Updated Quanities'!F:I,5,0),R380))","v":410.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A380,'Updated Quanities'!F:I,6,0),R380)=\"\",R380,IFERROR(VLOOKUP('AUP Library'!A380,'Updated Quanities'!F:I,6,0),R380))","v":410.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A380,'Updated Quanities'!F:I,7,0),R380)=\"\",R380,IFERROR(VLOOKUP('AUP Library'!A380,'Updated Quanities'!F:I,7,0),R380))","v":410.17},410.17,{"$f":"IFERROR(VLOOKUP('AUP Library'!A380,'Updated Quanities'!F:G,4,0),R380)","v":410.17}]
["710-06.12","Lateral Underdrain Endwall (3:1)","EA",346.43,346.43,346.43,346.43,346.43,346.43,346.43,346.43,346.43,346.43,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A381,'Updated Quanities'!F:I,4,0),R381)=\"\",R381,IFERROR(VLOOKUP('AUP Library'!A381,'Updated Quanities'!F:I,4,0),R381))","v":346.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A381,'Updated Quanities'!F:I,5,0),R381)=\"\",R381,IFERROR(VLOOKUP('AUP Library'!A381,'Updated Quanities'!F:I,5,0),R381))","v":346.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A381,'Updated Quanities'!F:I,6,0),R381)=\"\",R381,IFERROR(VLOOKUP('AUP Library'!A381,'Updated Quanities'!F:I,6,0),R381))","v":346.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A381,'Updated Quanities'!F:I,7,0),R381)=\"\",R381,IFERROR(VLOOKUP('AUP Library'!A381,'Updated Quanities'!F:I,7,0),R381))","v":346.43},346.43,{"$f":"IFERROR(VLOOKUP('AUP Library'!A381,'Updated Quanities'!F:G,4,0),R381)","v":346.43}]
["710-06.13","Lateral Underdrain Endwall (4:1)","EA",360.93,360.93,360.93,360.93,360.93,360.93,360.93,360.93,360.93,360.93,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A382,'Updated Quanities'!F:I,4,0),R382)=\"\",R382,IFERROR(VLOOKUP('AUP Library'!A382,'Updated Quanities'!F:I,4,0),R382))","v":360.93},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A382,'Updated Quanities'!F:I,5,0),R382)=\"\",R382,IFERROR(VLOOKUP('AUP Library'!A382,'Updated Quanities'!F:I,5,0),R382))","v":360.93},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A382,'Updated Quanities'!F:I,6,0),R382)=\"\",R382,IFERROR(VLOOKUP('AUP Library'!A382,'Updated Quanities'!F:I,6,0),R382))","v":360.93},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A382,'Updated Quanities'!F:I,7,0),R382)=\"\",R382,IFERROR(VLOOKUP('AUP Library'!A382,'Updated Quanities'!F:I,7,0),R382))","v":360.93},360.93,{"$f":"IFERROR(VLOOKUP('AUP Library'!A382,'Updated Quanities'!F:G,4,0),R382)","v":360.93}]
["710-06.15","Lateral Underdrain Endwall (6:1)","EA",364.76,364.76,364.76,364.76,364.76,364.76,364.76,364.76,364.76,364.76,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A383,'Updated Quanities'!F:I,4,0),R383)=\"\",R383,IFERROR(VLOOKUP('AUP Library'!A383,'Updated Quanities'!F:I,4,0),R383))","v":364.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A383,'Updated Quanities'!F:I,5,0),R383)=\"\",R383,IFERROR(VLOOKUP('AUP Library'!A383,'Updated Quanities'!F:I,5,0),R383))","v":364.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A383,'Updated Quanities'!F:I,6,0),R383)=\"\",R383,IFERROR(VLOOKUP('AUP Library'!A383,'Updated Quanities'!F:I,6,0),R383))","v":364.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A383,'Updated Quanities'!F:I,7,0),R383)=\"\",R383,IFERROR(VLOOKUP('AUP Library'!A383,'Updated Quanities'!F:I,7,0),R383))","v":364.76},364.76,{"$f":"IFERROR(VLOOKUP('AUP Library'!A383,'Updated Quanities'!F:G,4,0),R383)","v":364.76}]
["710-09.01","6\" Perforated Pipe With Vertical Drain System","LF",27.3,27.3,27.3,27.3,27.3,27.3,27.3,27.3,27.3,27.3,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A384,'Updated Quanities'!F:I,4,0),R384)=\"\",R384,IFERROR(VLOOKUP('AUP Library'!A384,'Updated Quanities'!F:I,4,0),R384))","v":27.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A384,'Updated Quanities'!F:I,5,0),R384)=\"\",R384,IFERROR(VLOOKUP('AUP Library'!A384,'Updated Quanities'!F:I,5,0),R384))","v":27.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A384,'Updated Quanities'!F:I,6,0),R384)=\"\",R384,IFERROR(VLOOKUP('AUP Library'!A384,'Updated Quanities'!F:I,6,0),R384))","v":27.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A384,'Updated Quanities'!F:I,7,0),R384)=\"\",R384,IFERROR(VLOOKUP('AUP Library'!A384,'Updated Quanities'!F:I,7,0),R384))","v":27.3},27.3,{"$f":"IFERROR(VLOOKUP('AUP Library'!A384,'Updated Quanities'!F:G,4,0),R384)","v":27.3}]
["710-13.03","Filter Cloth","SY",3,3,3,3,3,3,3,3,3,3,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A385,'Updated Quanities'!F:I,4,0),R385)=\"\",R385,IFERROR(VLOOKUP('AUP Library'!A385,'Updated Quanities'!F:I,4,0),R385))","v":3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A385,'Updated Quanities'!F:I,5,0),R385)=\"\",R385,IFERROR(VLOOKUP('AUP Library'!A385,'Updated Quanities'!F:I,5,0),R385))","v":3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A385,'Updated Quanities'!F:I,6,0),R385)=\"\",R385,IFERROR(VLOOKUP('AUP Library'!A385,'Updated Quanities'!F:I,6,0),R385))","v":3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A385,'Updated Quanities'!F:I,7,0),R385)=\"\",R385,IFERROR(VLOOKUP('AUP Library'!A385,'Updated Quanities'!F:I,7,0),R385))","v":3},3,{"$f":"IFERROR(VLOOKUP('AUP Library'!A385,'Updated Quanities'!F:G,4,0),R385)","v":3}]
["740-06.01","Geomembrane","SY",7.89,7.89,7.89,7.89,7.89,7.89,7.89,7.89,7.89,7.89,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A386,'Updated Quanities'!F:I,4,0),R386)=\"\",R386,IFERROR(VLOOKUP('AUP Library'!A386,'Updated Quanities'!F:I,4,0),R386))","v":7.89},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A386,'Updated Quanities'!F:I,5,0),R386)=\"\",R386,IFERROR(VLOOKUP('AUP Library'!A386,'Updated Quanities'!F:I,5,0),R386))","v":7.89},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A386,'Updated Quanities'!F:I,6,0),R386)=\"\",R386,IFERROR(VLOOKUP('AUP Library'!A386,'Updated Quanities'!F:I,6,0),R386))","v":7.89},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A386,'Updated Quanities'!F:I,7,0),R386)=\"\",R386,IFERROR(VLOOKUP('AUP Library'!A386,'Updated Quanities'!F:I,7,0),R386))","v":7.89},7.89,{"$f":"IFERROR(VLOOKUP('AUP Library'!A386,'Updated Quanities'!F:G,4,0),R386)","v":7.89}]
["740-07.01","GEO GRID REINFORCEMENT","SY",5,5,5,5,5,5,5,5,5,5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A387,'Updated Quanities'!F:I,4,0),R387)=\"\",R387,IFERROR(VLOOKUP('AUP Library'!A387,'Updated Quanities'!F:I,4,0),R387))","v":5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A387,'Updated Quanities'!F:I,5,0),R387)=\"\",R387,IFERROR(VLOOKUP('AUP Library'!A387,'Updated Quanities'!F:I,5,0),R387))","v":5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A387,'Updated Quanities'!F:I,6,0),R387)=\"\",R387,IFERROR(VLOOKUP('AUP Library'!A387,'Updated Quanities'!F:I,6,0),R387))","v":5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A387,'Updated Quanities'!F:I,7,0),R387)=\"\",R387,IFERROR(VLOOKUP('AUP Library'!A387,'Updated Quanities'!F:I,7,0),R387))","v":5},5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A387,'Updated Quanities'!F:G,4,0),R387)","v":5}]
["740-07.02","Geogrid Reinforcement (Soil Slopes)","SY",2.86,2.86,2.86,2.86,2.86,2.86,2.86,2.86,2.86,2.86,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A388,'Updated Quanities'!F:I,4,0),R388)=\"\",R388,IFERROR(VLOOKUP('AUP Library'!A388,'Updated Quanities'!F:I,4,0),R388))","v":2.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A388,'Updated Quanities'!F:I,5,0),R388)=\"\",R388,IFERROR(VLOOKUP('AUP Library'!A388,'Updated Quanities'!F:I,5,0),R388))","v":2.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A388,'Updated Quanities'!F:I,6,0),R388)=\"\",R388,IFERROR(VLOOKUP('AUP Library'!A388,'Updated Quanities'!F:I,6,0),R388))","v":2.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A388,'Updated Quanities'!F:I,7,0),R388)=\"\",R388,IFERROR(VLOOKUP('AUP Library'!A388,'Updated Quanities'!F:I,7,0),R388))","v":2.86},2.86,{"$f":"IFERROR(VLOOKUP('AUP Library'!A388,'Updated Quanities'!F:G,4,0),R388)","v":2.86}]
["740-10.01","GEOTEXTILE (TYPE I)(SUBSURFACE DRAINAGE)","SY",2.29,2.29,2.29,2.29,2.29,2.29,2.29,2.29,2.29,2.29,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A389,'Updated Quanities'!F:I,4,0),R389)=\"\",R389,IFERROR(VLOOKUP('AUP Library'!A389,'Updated Quanities'!F:I,4,0),R389))","v":2.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A389,'Updated Quanities'!F:I,5,0),R389)=\"\",R389,IFERROR(VLOOKUP('AUP Library'!A389,'Updated Quanities'!F:I,5,0),R389))","v":2.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A389,'Updated Quanities'!F:I,6,0),R389)=\"\",R389,IFERROR(VLOOKUP('AUP Library'!A389,'Updated Quanities'!F:I,6,0),R389))","v":2.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A389,'Updated Quanities'!F:I,7,0),R389)=\"\",R389,IFERROR(VLOOKUP('AUP Library'!A389,'Updated Quanities'!F:I,7,0),R389))","v":2.29},2.29,{"$f":"IFERROR(VLOOKUP('AUP Library'!A389,'Updated Quanities'!F:G,4,0),R389)","v":2.29}]
["740-10.02","GEOTEXTILE (TYPE II)(SEDIMENT CONTROL)","SY",2.31,2.31,2.31,2.31,2.31,2.31,2.31,2.31,2.31,2.31,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A390,'Updated Quanities'!F:I,4,0),R390)=\"\",R390,IFERROR(VLOOKUP('AUP Library'!A390,'Updated Quanities'!F:I,4,0),R390))","v":2.31},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A390,'Updated Quanities'!F:I,5,0),R390)=\"\",R390,IFERROR(VLOOKUP('AUP Library'!A390,'Updated Quanities'!F:I,5,0),R390))","v":2.31},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A390,'Updated Quanities'!F:I,6,0),R390)=\"\",R390,IFERROR(VLOOKUP('AUP Library'!A390,'Updated Quanities'!F:I,6,0),R390))","v":2.31},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A390,'Updated Quanities'!F:I,7,0),R390)=\"\",R390,IFERROR(VLOOKUP('AUP Library'!A390,'Updated Quanities'!F:I,7,0),R390))","v":2.31},2.31,{"$f":"IFERROR(VLOOKUP('AUP Library'!A390,'Updated Quanities'!F:G,4,0),R390)","v":2.31}]
["740-10.03","Geotextile (Type III)(Erosion Control)","SY",2.91,2.91,2.91,2.91,2.91,2.91,2.91,2.91,2.91,2.91,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A391,'Updated Quanities'!F:I,4,0),R391)=\"\",R391,IFERROR(VLOOKUP('AUP Library'!A391,'Updated Quanities'!F:I,4,0),R391))","v":2.91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A391,'Updated Quanities'!F:I,5,0),R391)=\"\",R391,IFERROR(VLOOKUP('AUP Library'!A391,'Updated Quanities'!F:I,5,0),R391))","v":2.91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A391,'Updated Quanities'!F:I,6,0),R391)=\"\",R391,IFERROR(VLOOKUP('AUP Library'!A391,'Updated Quanities'!F:I,6,0),R391))","v":2.91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A391,'Updated Quanities'!F:I,7,0),R391)=\"\",R391,IFERROR(VLOOKUP('AUP Library'!A391,'Updated Quanities'!F:I,7,0),R391))","v":2.91},2.91,{"$f":"IFERROR(VLOOKUP('AUP Library'!A391,'Updated Quanities'!F:G,4,0),R391)","v":2.91}]
["740-10.04","Geotextile (Type IV)(Stabilization)","SY",1.58,1.58,1.58,1.58,1.58,1.58,1.58,1.58,1.58,1.58,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A392,'Updated Quanities'!F:I,4,0),R392)=\"\",R392,IFERROR(VLOOKUP('AUP Library'!A392,'Updated Quanities'!F:I,4,0),R392))","v":1.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A392,'Updated Quanities'!F:I,5,0),R392)=\"\",R392,IFERROR(VLOOKUP('AUP Library'!A392,'Updated Quanities'!F:I,5,0),R392))","v":1.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A392,'Updated Quanities'!F:I,6,0),R392)=\"\",R392,IFERROR(VLOOKUP('AUP Library'!A392,'Updated Quanities'!F:I,6,0),R392))","v":1.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A392,'Updated Quanities'!F:I,7,0),R392)=\"\",R392,IFERROR(VLOOKUP('AUP Library'!A392,'Updated Quanities'!F:I,7,0),R392))","v":1.58},1.58,{"$f":"IFERROR(VLOOKUP('AUP Library'!A392,'Updated Quanities'!F:G,4,0),R392)","v":1.58}]
["740-11.01","TEMPORARY SEDIMENT TUBE 8IN (DESCRIPT)","LF",3.53,3.53,3.53,3.53,3.53,3.53,3.53,3.53,3.53,3.53,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A393,'Updated Quanities'!F:I,4,0),R393)=\"\",R393,IFERROR(VLOOKUP('AUP Library'!A393,'Updated Quanities'!F:I,4,0),R393))","v":3.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A393,'Updated Quanities'!F:I,5,0),R393)=\"\",R393,IFERROR(VLOOKUP('AUP Library'!A393,'Updated Quanities'!F:I,5,0),R393))","v":3.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A393,'Updated Quanities'!F:I,6,0),R393)=\"\",R393,IFERROR(VLOOKUP('AUP Library'!A393,'Updated Quanities'!F:I,6,0),R393))","v":3.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A393,'Updated Quanities'!F:I,7,0),R393)=\"\",R393,IFERROR(VLOOKUP('AUP Library'!A393,'Updated Quanities'!F:I,7,0),R393))","v":3.53},3.53,{"$f":"IFERROR(VLOOKUP('AUP Library'!A393,'Updated Quanities'!F:G,4,0),R393)","v":3.53}]
["740-11.02","TEMPORARY SEDIMENT TUBE 12IN (DESCRIPT)","LF",3.26,3.26,3.26,3.26,3.26,3.26,3.26,3.26,3.26,3.26,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A394,'Updated Quanities'!F:I,4,0),R394)=\"\",R394,IFERROR(VLOOKUP('AUP Library'!A394,'Updated Quanities'!F:I,4,0),R394))","v":3.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A394,'Updated Quanities'!F:I,5,0),R394)=\"\",R394,IFERROR(VLOOKUP('AUP Library'!A394,'Updated Quanities'!F:I,5,0),R394))","v":3.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A394,'Updated Quanities'!F:I,6,0),R394)=\"\",R394,IFERROR(VLOOKUP('AUP Library'!A394,'Updated Quanities'!F:I,6,0),R394))","v":3.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A394,'Updated Quanities'!F:I,7,0),R394)=\"\",R394,IFERROR(VLOOKUP('AUP Library'!A394,'Updated Quanities'!F:I,7,0),R394))","v":3.26},3.26,{"$f":"IFERROR(VLOOKUP('AUP Library'!A394,'Updated Quanities'!F:G,4,0),R394)","v":3.26}]
["740-11.03","TEMPORARY SEDIMENT TUBE 18IN (DESCRIPT)","LF",3.43,3.43,3.43,3.43,3.43,3.43,3.43,3.43,3.43,3.43,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A395,'Updated Quanities'!F:I,4,0),R395)=\"\",R395,IFERROR(VLOOKUP('AUP Library'!A395,'Updated Quanities'!F:I,4,0),R395))","v":3.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A395,'Updated Quanities'!F:I,5,0),R395)=\"\",R395,IFERROR(VLOOKUP('AUP Library'!A395,'Updated Quanities'!F:I,5,0),R395))","v":3.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A395,'Updated Quanities'!F:I,6,0),R395)=\"\",R395,IFERROR(VLOOKUP('AUP Library'!A395,'Updated Quanities'!F:I,6,0),R395))","v":3.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A395,'Updated Quanities'!F:I,7,0),R395)=\"\",R395,IFERROR(VLOOKUP('AUP Library'!A395,'Updated Quanities'!F:I,7,0),R395))","v":3.43},3.43,{"$f":"IFERROR(VLOOKUP('AUP Library'!A395,'Updated Quanities'!F:G,4,0),R395)","v":3.43}]
["740-11.04","TEMPORARY SEDIMENT TUBE 20IN (DESCRIPT)","LF",3.56,3.56,3.56,3.56,3.56,3.56,3.56,3.56,3.56,3.56,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A396,'Updated Quanities'!F:I,4,0),R396)=\"\",R396,IFERROR(VLOOKUP('AUP Library'!A396,'Updated Quanities'!F:I,4,0),R396))","v":3.56},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A396,'Updated Quanities'!F:I,5,0),R396)=\"\",R396,IFERROR(VLOOKUP('AUP Library'!A396,'Updated Quanities'!F:I,5,0),R396))","v":3.56},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A396,'Updated Quanities'!F:I,6,0),R396)=\"\",R396,IFERROR(VLOOKUP('AUP Library'!A396,'Updated Quanities'!F:I,6,0),R396))","v":3.56},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A396,'Updated Quanities'!F:I,7,0),R396)=\"\",R396,IFERROR(VLOOKUP('AUP Library'!A396,'Updated Quanities'!F:I,7,0),R396))","v":3.56},3.56,{"$f":"IFERROR(VLOOKUP('AUP Library'!A396,'Updated Quanities'!F:G,4,0),R396)","v":3.56}]
["740-11.05","TEMPORARY SEDIMENT TUBE 24IN (DESCRIPT)","LF",4.8,4.8,4.8,4.8,4.8,4.8,4.8,4.8,4.8,4.8,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A397,'Updated Quanities'!F:I,4,0),R397)=\"\",R397,IFERROR(VLOOKUP('AUP Library'!A397,'Updated Quanities'!F:I,4,0),R397))","v":4.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A397,'Updated Quanities'!F:I,5,0),R397)=\"\",R397,IFERROR(VLOOKUP('AUP Library'!A397,'Updated Quanities'!F:I,5,0),R397))","v":4.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A397,'Updated Quanities'!F:I,6,0),R397)=\"\",R397,IFERROR(VLOOKUP('AUP Library'!A397,'Updated Quanities'!F:I,6,0),R397))","v":4.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A397,'Updated Quanities'!F:I,7,0),R397)=\"\",R397,IFERROR(VLOOKUP('AUP Library'!A397,'Updated Quanities'!F:I,7,0),R397))","v":4.8},4.8,{"$f":"IFERROR(VLOOKUP('AUP Library'!A397,'Updated Quanities'!F:G,4,0),R397)","v":4.8}]
[]
[]
["Appurtenances"]
["202-03","Removal of Rigid Pvmt, Sidewalk, Etc","SY",10.35,10.35,10.35,10.35,10.35,10.35,10.35,10.35,10.35,10.35,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A401,'Updated Quanities'!F:I,4,0),R401)=\"\",R401,IFERROR(VLOOKUP('AUP Library'!A401,'Updated Quanities'!F:I,4,0),R401))","v":10.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A401,'Updated Quanities'!F:I,5,0),R401)=\"\",R401,IFERROR(VLOOKUP('AUP Library'!A401,'Updated Quanities'!F:I,5,0),R401))","v":10.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A401,'Updated Quanities'!F:I,6,0),R401)=\"\",R401,IFERROR(VLOOKUP('AUP Library'!A401,'Updated Quanities'!F:I,6,0),R401))","v":10.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A401,'Updated Quanities'!F:I,7,0),R401)=\"\",R401,IFERROR(VLOOKUP('AUP Library'!A401,'Updated Quanities'!F:I,7,0),R401))","v":10.35},10.35,{"$f":"IFERROR(VLOOKUP('AUP Library'!A401,'Updated Quanities'!F:G,4,0),R401)","v":10.35}]
["202-08.15","Removal of Curb and Gutter","LF",3.38,3.38,3.38,3.38,3.38,3.38,3.38,3.38,3.38,3.38,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A402,'Updated Quanities'!F:I,4,0),R402)=\"\",R402,IFERROR(VLOOKUP('AUP Library'!A402,'Updated Quanities'!F:I,4,0),R402))","v":3.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A402,'Updated Quanities'!F:I,5,0),R402)=\"\",R402,IFERROR(VLOOKUP('AUP Library'!A402,'Updated Quanities'!F:I,5,0),R402))","v":3.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A402,'Updated Quanities'!F:I,6,0),R402)=\"\",R402,IFERROR(VLOOKUP('AUP Library'!A402,'Updated Quanities'!F:I,6,0),R402))","v":3.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A402,'Updated Quanities'!F:I,7,0),R402)=\"\",R402,IFERROR(VLOOKUP('AUP Library'!A402,'Updated Quanities'!F:I,7,0),R402))","v":3.38},3.38,{"$f":"IFERROR(VLOOKUP('AUP Library'!A402,'Updated Quanities'!F:G,4,0),R402)","v":3.38}]
["202-08.28","Removal of Median Barrier","LF",85,85,85,85,85,85,85,85,85,85,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A403,'Updated Quanities'!F:I,4,0),R403)=\"\",R403,IFERROR(VLOOKUP('AUP Library'!A403,'Updated Quanities'!F:I,4,0),R403))","v":85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A403,'Updated Quanities'!F:I,5,0),R403)=\"\",R403,IFERROR(VLOOKUP('AUP Library'!A403,'Updated Quanities'!F:I,5,0),R403))","v":85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A403,'Updated Quanities'!F:I,6,0),R403)=\"\",R403,IFERROR(VLOOKUP('AUP Library'!A403,'Updated Quanities'!F:I,6,0),R403))","v":85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A403,'Updated Quanities'!F:I,7,0),R403)=\"\",R403,IFERROR(VLOOKUP('AUP Library'!A403,'Updated Quanities'!F:I,7,0),R403))","v":85},85,{"$f":"IFERROR(VLOOKUP('AUP Library'!A403,'Updated Quanities'!F:G,4,0),R403)","v":85}]
["604-04.62","Clean and Texture Finish Concrete Barrier","LF",7.38,7.38,7.38,7.38,7.38,7.38,7.38,7.38,7.38,7.38,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A404,'Updated Quanities'!F:I,4,0),R404)=\"\",R404,IFERROR(VLOOKUP('AUP Library'!A404,'Updated Quanities'!F:I,4,0),R404))","v":7.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A404,'Updated Quanities'!F:I,5,0),R404)=\"\",R404,IFERROR(VLOOKUP('AUP Library'!A404,'Updated Quanities'!F:I,5,0),R404))","v":7.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A404,'Updated Quanities'!F:I,6,0),R404)=\"\",R404,IFERROR(VLOOKUP('AUP Library'!A404,'Updated Quanities'!F:I,6,0),R404))","v":7.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A404,'Updated Quanities'!F:I,7,0),R404)=\"\",R404,IFERROR(VLOOKUP('AUP Library'!A404,'Updated Quanities'!F:I,7,0),R404))","v":7.38},7.38,{"$f":"IFERROR(VLOOKUP('AUP Library'!A404,'Updated Quanities'!F:G,4,0),R404)","v":7.38}]
["701-01.01","Concrete Sidewalk (4\")","SF",3.94,3.15,3.37,3.35,3.35,2.76,2.71,3.77,3.48,4.08,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A405,'Updated Quanities'!F:I,4,0),R405)=\"\",R405,IFERROR(VLOOKUP('AUP Library'!A405,'Updated Quanities'!F:I,4,0),R405))","v":4.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A405,'Updated Quanities'!F:I,5,0),R405)=\"\",R405,IFERROR(VLOOKUP('AUP Library'!A405,'Updated Quanities'!F:I,5,0),R405))","v":4.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A405,'Updated Quanities'!F:I,6,0),R405)=\"\",R405,IFERROR(VLOOKUP('AUP Library'!A405,'Updated Quanities'!F:I,6,0),R405))","v":4.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A405,'Updated Quanities'!F:I,7,0),R405)=\"\",R405,IFERROR(VLOOKUP('AUP Library'!A405,'Updated Quanities'!F:I,7,0),R405))","v":4.17},4.17,{"$f":"IFERROR(VLOOKUP('AUP Library'!A405,'Updated Quanities'!F:G,4,0),R405)","v":4.17}]
["701-01.02","Concrete Sidewalk (6\")","SF",5.82,5.82,5.82,5.82,5.82,5.82,5.82,5.82,5.82,5.82,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A406,'Updated Quanities'!F:I,4,0),R406)=\"\",R406,IFERROR(VLOOKUP('AUP Library'!A406,'Updated Quanities'!F:I,4,0),R406))","v":5.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A406,'Updated Quanities'!F:I,5,0),R406)=\"\",R406,IFERROR(VLOOKUP('AUP Library'!A406,'Updated Quanities'!F:I,5,0),R406))","v":5.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A406,'Updated Quanities'!F:I,6,0),R406)=\"\",R406,IFERROR(VLOOKUP('AUP Library'!A406,'Updated Quanities'!F:I,6,0),R406))","v":5.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A406,'Updated Quanities'!F:I,7,0),R406)=\"\",R406,IFERROR(VLOOKUP('AUP Library'!A406,'Updated Quanities'!F:I,7,0),R406))","v":5.82},5.82,{"$f":"IFERROR(VLOOKUP('AUP Library'!A406,'Updated Quanities'!F:G,4,0),R406)","v":5.82}]
["701-02","Concrete Driveway","SF",5.8,5.8,5.8,5.8,5.8,5.8,5.8,5.8,5.8,5.8,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A407,'Updated Quanities'!F:I,4,0),R407)=\"\",R407,IFERROR(VLOOKUP('AUP Library'!A407,'Updated Quanities'!F:I,4,0),R407))","v":5.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A407,'Updated Quanities'!F:I,5,0),R407)=\"\",R407,IFERROR(VLOOKUP('AUP Library'!A407,'Updated Quanities'!F:I,5,0),R407))","v":5.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A407,'Updated Quanities'!F:I,6,0),R407)=\"\",R407,IFERROR(VLOOKUP('AUP Library'!A407,'Updated Quanities'!F:I,6,0),R407))","v":5.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A407,'Updated Quanities'!F:I,7,0),R407)=\"\",R407,IFERROR(VLOOKUP('AUP Library'!A407,'Updated Quanities'!F:I,7,0),R407))","v":5.8},5.8,{"$f":"IFERROR(VLOOKUP('AUP Library'!A407,'Updated Quanities'!F:G,4,0),R407)","v":5.8}]
["701-02.02","Concrete Driveway (8\")","SF",6,6,6,6,6,6,6,6,6,6,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A408,'Updated Quanities'!F:I,4,0),R408)=\"\",R408,IFERROR(VLOOKUP('AUP Library'!A408,'Updated Quanities'!F:I,4,0),R408))","v":6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A408,'Updated Quanities'!F:I,5,0),R408)=\"\",R408,IFERROR(VLOOKUP('AUP Library'!A408,'Updated Quanities'!F:I,5,0),R408))","v":6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A408,'Updated Quanities'!F:I,6,0),R408)=\"\",R408,IFERROR(VLOOKUP('AUP Library'!A408,'Updated Quanities'!F:I,6,0),R408))","v":6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A408,'Updated Quanities'!F:I,7,0),R408)=\"\",R408,IFERROR(VLOOKUP('AUP Library'!A408,'Updated Quanities'!F:I,7,0),R408))","v":6},6,{"$f":"IFERROR(VLOOKUP('AUP Library'!A408,'Updated Quanities'!F:G,4,0),R408)","v":6}]
["701-02.01","Concrete Handicap Ramp (Retrofit)","SF",18.88,18.88,18.88,18.88,18.88,18.88,18.88,18.88,18.88,18.88,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A409,'Updated Quanities'!F:I,4,0),R409)=\"\",R409,IFERROR(VLOOKUP('AUP Library'!A409,'Updated Quanities'!F:I,4,0),R409))","v":18.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A409,'Updated Quanities'!F:I,5,0),R409)=\"\",R409,IFERROR(VLOOKUP('AUP Library'!A409,'Updated Quanities'!F:I,5,0),R409))","v":18.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A409,'Updated Quanities'!F:I,6,0),R409)=\"\",R409,IFERROR(VLOOKUP('AUP Library'!A409,'Updated Quanities'!F:I,6,0),R409))","v":18.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A409,'Updated Quanities'!F:I,7,0),R409)=\"\",R409,IFERROR(VLOOKUP('AUP Library'!A409,'Updated Quanities'!F:I,7,0),R409))","v":18.88},18.88,{"$f":"IFERROR(VLOOKUP('AUP Library'!A409,'Updated Quanities'!F:G,4,0),R409)","v":18.88}]
["701-02.03","Concrete Curb Ramp","SF",13.01,13.01,13.01,13.01,13.01,13.01,13.01,13.01,13.01,13.01,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A410,'Updated Quanities'!F:I,4,0),R410)=\"\",R410,IFERROR(VLOOKUP('AUP Library'!A410,'Updated Quanities'!F:I,4,0),R410))","v":13.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A410,'Updated Quanities'!F:I,5,0),R410)=\"\",R410,IFERROR(VLOOKUP('AUP Library'!A410,'Updated Quanities'!F:I,5,0),R410))","v":13.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A410,'Updated Quanities'!F:I,6,0),R410)=\"\",R410,IFERROR(VLOOKUP('AUP Library'!A410,'Updated Quanities'!F:I,6,0),R410))","v":13.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A410,'Updated Quanities'!F:I,7,0),R410)=\"\",R410,IFERROR(VLOOKUP('AUP Library'!A410,'Updated Quanities'!F:I,7,0),R410))","v":13.01},13.01,{"$f":"IFERROR(VLOOKUP('AUP Library'!A410,'Updated Quanities'!F:G,4,0),R410)","v":13.01}]
["702-01","Concrete Curb","CY",294.14999999999998,294.14999999999998,294.14999999999998,294.14999999999998,294.14999999999998,294.14999999999998,294.14999999999998,294.14999999999998,294.14999999999998,294.14999999999998,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A411,'Updated Quanities'!F:I,4,0),R411)=\"\",R411,IFERROR(VLOOKUP('AUP Library'!A411,'Updated Quanities'!F:I,4,0),R411))","v":294.14999999999998},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A411,'Updated Quanities'!F:I,5,0),R411)=\"\",R411,IFERROR(VLOOKUP('AUP Library'!A411,'Updated Quanities'!F:I,5,0),R411))","v":294.14999999999998},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A411,'Updated Quanities'!F:I,6,0),R411)=\"\",R411,IFERROR(VLOOKUP('AUP Library'!A411,'Updated Quanities'!F:I,6,0),R411))","v":294.14999999999998},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A411,'Updated Quanities'!F:I,7,0),R411)=\"\",R411,IFERROR(VLOOKUP('AUP Library'!A411,'Updated Quanities'!F:I,7,0),R411))","v":294.14999999999998},294.14999999999998,{"$f":"IFERROR(VLOOKUP('AUP Library'!A411,'Updated Quanities'!F:G,4,0),R411)","v":294.14999999999998}]
["702-01.01","Extruded Mountable Curb","LF",16.05,16.05,16.05,16.05,16.05,16.05,16.05,16.05,16.05,16.05,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A412,'Updated Quanities'!F:I,4,0),R412)=\"\",R412,IFERROR(VLOOKUP('AUP Library'!A412,'Updated Quanities'!F:I,4,0),R412))","v":16.05},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A412,'Updated Quanities'!F:I,5,0),R412)=\"\",R412,IFERROR(VLOOKUP('AUP Library'!A412,'Updated Quanities'!F:I,5,0),R412))","v":16.05},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A412,'Updated Quanities'!F:I,6,0),R412)=\"\",R412,IFERROR(VLOOKUP('AUP Library'!A412,'Updated Quanities'!F:I,6,0),R412))","v":16.05},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A412,'Updated Quanities'!F:I,7,0),R412)=\"\",R412,IFERROR(VLOOKUP('AUP Library'!A412,'Updated Quanities'!F:I,7,0),R412))","v":16.05},16.05,{"$f":"IFERROR(VLOOKUP('AUP Library'!A412,'Updated Quanities'!F:G,4,0),R412)","v":16.05}]
["702-01.02","Concrete Curb","LF",20.77,20.77,20.77,20.77,20.77,20.77,20.77,20.77,20.77,20.77,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A413,'Updated Quanities'!F:I,4,0),R413)=\"\",R413,IFERROR(VLOOKUP('AUP Library'!A413,'Updated Quanities'!F:I,4,0),R413))","v":20.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A413,'Updated Quanities'!F:I,5,0),R413)=\"\",R413,IFERROR(VLOOKUP('AUP Library'!A413,'Updated Quanities'!F:I,5,0),R413))","v":20.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A413,'Updated Quanities'!F:I,6,0),R413)=\"\",R413,IFERROR(VLOOKUP('AUP Library'!A413,'Updated Quanities'!F:I,6,0),R413))","v":20.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A413,'Updated Quanities'!F:I,7,0),R413)=\"\",R413,IFERROR(VLOOKUP('AUP Library'!A413,'Updated Quanities'!F:I,7,0),R413))","v":20.77},20.77,{"$f":"IFERROR(VLOOKUP('AUP Library'!A413,'Updated Quanities'!F:G,4,0),R413)","v":20.77}]
["702-01.03","Modular Curb w/ Delineator","LF",50.14,50.14,50.14,50.14,50.14,50.14,50.14,50.14,50.14,50.14,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A414,'Updated Quanities'!F:I,4,0),R414)=\"\",R414,IFERROR(VLOOKUP('AUP Library'!A414,'Updated Quanities'!F:I,4,0),R414))","v":50.14},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A414,'Updated Quanities'!F:I,5,0),R414)=\"\",R414,IFERROR(VLOOKUP('AUP Library'!A414,'Updated Quanities'!F:I,5,0),R414))","v":50.14},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A414,'Updated Quanities'!F:I,6,0),R414)=\"\",R414,IFERROR(VLOOKUP('AUP Library'!A414,'Updated Quanities'!F:I,6,0),R414))","v":50.14},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A414,'Updated Quanities'!F:I,7,0),R414)=\"\",R414,IFERROR(VLOOKUP('AUP Library'!A414,'Updated Quanities'!F:I,7,0),R414))","v":50.14},50.14,{"$f":"IFERROR(VLOOKUP('AUP Library'!A414,'Updated Quanities'!F:G,4,0),R414)","v":50.14}]
["702-03","Concrete Combined Curb & Gutter","CY",246.58,207.91,202.57,215.3,215.3,203.58,189.72,233.38,197.18,238.63,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A415,'Updated Quanities'!F:I,4,0),R415)=\"\",R415,IFERROR(VLOOKUP('AUP Library'!A415,'Updated Quanities'!F:I,4,0),R415))","v":262.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A415,'Updated Quanities'!F:I,5,0),R415)=\"\",R415,IFERROR(VLOOKUP('AUP Library'!A415,'Updated Quanities'!F:I,5,0),R415))","v":262.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A415,'Updated Quanities'!F:I,6,0),R415)=\"\",R415,IFERROR(VLOOKUP('AUP Library'!A415,'Updated Quanities'!F:I,6,0),R415))","v":262.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A415,'Updated Quanities'!F:I,7,0),R415)=\"\",R415,IFERROR(VLOOKUP('AUP Library'!A415,'Updated Quanities'!F:I,7,0),R415))","v":262.94},262.94,{"$f":"IFERROR(VLOOKUP('AUP Library'!A415,'Updated Quanities'!F:G,4,0),R415)","v":262.94}]
["711-04.01","Concrete Glare Screen Median Barrier @ Bridge Piers","LF",376.74,376.74,376.74,376.74,376.74,376.74,376.74,376.74,376.74,376.74,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A416,'Updated Quanities'!F:I,4,0),R416)=\"\",R416,IFERROR(VLOOKUP('AUP Library'!A416,'Updated Quanities'!F:I,4,0),R416))","v":376.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A416,'Updated Quanities'!F:I,5,0),R416)=\"\",R416,IFERROR(VLOOKUP('AUP Library'!A416,'Updated Quanities'!F:I,5,0),R416))","v":376.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A416,'Updated Quanities'!F:I,6,0),R416)=\"\",R416,IFERROR(VLOOKUP('AUP Library'!A416,'Updated Quanities'!F:I,6,0),R416))","v":376.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A416,'Updated Quanities'!F:I,7,0),R416)=\"\",R416,IFERROR(VLOOKUP('AUP Library'!A416,'Updated Quanities'!F:I,7,0),R416))","v":376.74},376.74,{"$f":"IFERROR(VLOOKUP('AUP Library'!A416,'Updated Quanities'!F:G,4,0),R416)","v":376.74}]
["711-04.05","Concrete Glare Screen (Median Barrier Cap)","LF",19,19,19,19,19,19,19,19,19,19,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A417,'Updated Quanities'!F:I,4,0),R417)=\"\",R417,IFERROR(VLOOKUP('AUP Library'!A417,'Updated Quanities'!F:I,4,0),R417))","v":19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A417,'Updated Quanities'!F:I,5,0),R417)=\"\",R417,IFERROR(VLOOKUP('AUP Library'!A417,'Updated Quanities'!F:I,5,0),R417))","v":19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A417,'Updated Quanities'!F:I,6,0),R417)=\"\",R417,IFERROR(VLOOKUP('AUP Library'!A417,'Updated Quanities'!F:I,6,0),R417))","v":19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A417,'Updated Quanities'!F:I,7,0),R417)=\"\",R417,IFERROR(VLOOKUP('AUP Library'!A417,'Updated Quanities'!F:I,7,0),R417))","v":19},19,{"$f":"IFERROR(VLOOKUP('AUP Library'!A417,'Updated Quanities'!F:G,4,0),R417)","v":19}]
["711-05.01","Removal & Disposal of Concrete Median Barrier","LF",152.55000000000001,152.55000000000001,152.55000000000001,152.55000000000001,152.55000000000001,152.55000000000001,152.55000000000001,152.55000000000001,152.55000000000001,152.55000000000001,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A418,'Updated Quanities'!F:I,4,0),R418)=\"\",R418,IFERROR(VLOOKUP('AUP Library'!A418,'Updated Quanities'!F:I,4,0),R418))","v":152.55000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A418,'Updated Quanities'!F:I,5,0),R418)=\"\",R418,IFERROR(VLOOKUP('AUP Library'!A418,'Updated Quanities'!F:I,5,0),R418))","v":152.55000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A418,'Updated Quanities'!F:I,6,0),R418)=\"\",R418,IFERROR(VLOOKUP('AUP Library'!A418,'Updated Quanities'!F:I,6,0),R418))","v":152.55000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A418,'Updated Quanities'!F:I,7,0),R418)=\"\",R418,IFERROR(VLOOKUP('AUP Library'!A418,'Updated Quanities'!F:I,7,0),R418))","v":152.55000000000001},152.55000000000001,{"$f":"IFERROR(VLOOKUP('AUP Library'!A418,'Updated Quanities'!F:G,4,0),R418)","v":152.55000000000001}]
["711-05.70","Single Slope Median Barrier Wall","LF",55.52,55.52,55.52,55.52,55.52,55.52,55.52,55.52,55.52,55.52,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A419,'Updated Quanities'!F:I,4,0),R419)=\"\",R419,IFERROR(VLOOKUP('AUP Library'!A419,'Updated Quanities'!F:I,4,0),R419))","v":55.52},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A419,'Updated Quanities'!F:I,5,0),R419)=\"\",R419,IFERROR(VLOOKUP('AUP Library'!A419,'Updated Quanities'!F:I,5,0),R419))","v":55.52},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A419,'Updated Quanities'!F:I,6,0),R419)=\"\",R419,IFERROR(VLOOKUP('AUP Library'!A419,'Updated Quanities'!F:I,6,0),R419))","v":55.52},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A419,'Updated Quanities'!F:I,7,0),R419)=\"\",R419,IFERROR(VLOOKUP('AUP Library'!A419,'Updated Quanities'!F:I,7,0),R419))","v":55.52},55.52,{"$f":"IFERROR(VLOOKUP('AUP Library'!A419,'Updated Quanities'!F:G,4,0),R419)","v":55.52}]
["711-05.71","51\" Single Slope Concrete Barrier Wall","LF",66.61,66.61,66.61,66.61,66.61,66.61,66.61,66.61,66.61,66.61,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A420,'Updated Quanities'!F:I,4,0),R420)=\"\",R420,IFERROR(VLOOKUP('AUP Library'!A420,'Updated Quanities'!F:I,4,0),R420))","v":107.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A420,'Updated Quanities'!F:I,5,0),R420)=\"\",R420,IFERROR(VLOOKUP('AUP Library'!A420,'Updated Quanities'!F:I,5,0),R420))","v":107.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A420,'Updated Quanities'!F:I,6,0),R420)=\"\",R420,IFERROR(VLOOKUP('AUP Library'!A420,'Updated Quanities'!F:I,6,0),R420))","v":107.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A420,'Updated Quanities'!F:I,7,0),R420)=\"\",R420,IFERROR(VLOOKUP('AUP Library'!A420,'Updated Quanities'!F:I,7,0),R420))","v":107.6},107.6,{"$f":"IFERROR(VLOOKUP('AUP Library'!A420,'Updated Quanities'!F:G,4,0),R420)","v":107.6}]
[]
[]
["Earthwork"]
["105-01","Constrction Stakes, Lines, and Grades","LS",50000,50000,50000,50000,50000,50000,50000,50000,50000,50000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A424,'Updated Quanities'!F:I,4,0),R424)=\"\",R424,IFERROR(VLOOKUP('AUP Library'!A424,'Updated Quanities'!F:I,4,0),R424))","v":38502.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A424,'Updated Quanities'!F:I,5,0),R424)=\"\",R424,IFERROR(VLOOKUP('AUP Library'!A424,'Updated Quanities'!F:I,5,0),R424))","v":38502.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A424,'Updated Quanities'!F:I,6,0),R424)=\"\",R424,IFERROR(VLOOKUP('AUP Library'!A424,'Updated Quanities'!F:I,6,0),R424))","v":38502.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A424,'Updated Quanities'!F:I,7,0),R424)=\"\",R424,IFERROR(VLOOKUP('AUP Library'!A424,'Updated Quanities'!F:I,7,0),R424))","v":38502.76},38502.76,{"$f":"IFERROR(VLOOKUP('AUP Library'!A424,'Updated Quanities'!F:G,4,0),R424)","v":38502.76}]
["203-01","Road & Drainage Excavation (Unclassified)","CY",3.95,3.87,4.05,3.53,3.53,3.35,3.56,4.82,4.3899999999999997,5.0999999999999996,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A425,'Updated Quanities'!F:I,4,0),R425)=\"\",R425,IFERROR(VLOOKUP('AUP Library'!A425,'Updated Quanities'!F:I,4,0),R425))","v":8.4600000000000009},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A425,'Updated Quanities'!F:I,5,0),R425)=\"\",R425,IFERROR(VLOOKUP('AUP Library'!A425,'Updated Quanities'!F:I,5,0),R425))","v":8.4600000000000009},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A425,'Updated Quanities'!F:I,6,0),R425)=\"\",R425,IFERROR(VLOOKUP('AUP Library'!A425,'Updated Quanities'!F:I,6,0),R425))","v":8.4600000000000009},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A425,'Updated Quanities'!F:I,7,0),R425)=\"\",R425,IFERROR(VLOOKUP('AUP Library'!A425,'Updated Quanities'!F:I,7,0),R425))","v":8.4600000000000009},8.4600000000000009,{"$f":"IFERROR(VLOOKUP('AUP Library'!A425,'Updated Quanities'!F:G,4,0),R425)","v":8.4600000000000009}]
["203-01.05","Excavation","CY",51.5,51.5,51.5,51.5,51.5,51.5,51.5,51.5,51.5,51.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A426,'Updated Quanities'!F:I,4,0),R426)=\"\",R426,IFERROR(VLOOKUP('AUP Library'!A426,'Updated Quanities'!F:I,4,0),R426))","v":51.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A426,'Updated Quanities'!F:I,5,0),R426)=\"\",R426,IFERROR(VLOOKUP('AUP Library'!A426,'Updated Quanities'!F:I,5,0),R426))","v":51.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A426,'Updated Quanities'!F:I,6,0),R426)=\"\",R426,IFERROR(VLOOKUP('AUP Library'!A426,'Updated Quanities'!F:I,6,0),R426))","v":51.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A426,'Updated Quanities'!F:I,7,0),R426)=\"\",R426,IFERROR(VLOOKUP('AUP Library'!A426,'Updated Quanities'!F:I,7,0),R426))","v":51.5},51.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A426,'Updated Quanities'!F:G,4,0),R426)","v":51.5}]
["203-01.06","Road & Drainage Excavation (Unclass)","LS",8500,8500,8500,8500,8500,8500,8500,8500,8500,8500,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A427,'Updated Quanities'!F:I,4,0),R427)=\"\",R427,IFERROR(VLOOKUP('AUP Library'!A427,'Updated Quanities'!F:I,4,0),R427))","v":8500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A427,'Updated Quanities'!F:I,5,0),R427)=\"\",R427,IFERROR(VLOOKUP('AUP Library'!A427,'Updated Quanities'!F:I,5,0),R427))","v":8500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A427,'Updated Quanities'!F:I,6,0),R427)=\"\",R427,IFERROR(VLOOKUP('AUP Library'!A427,'Updated Quanities'!F:I,6,0),R427))","v":8500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A427,'Updated Quanities'!F:I,7,0),R427)=\"\",R427,IFERROR(VLOOKUP('AUP Library'!A427,'Updated Quanities'!F:I,7,0),R427))","v":8500},8500,{"$f":"IFERROR(VLOOKUP('AUP Library'!A427,'Updated Quanities'!F:G,4,0),R427)","v":8500}]
["203-01.07","Rd & Drng (Acid Producing off Site)","CY",12.5,12.5,12.5,12.5,12.5,12.5,12.5,12.5,12.5,12.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A428,'Updated Quanities'!F:I,4,0),R428)=\"\",R428,IFERROR(VLOOKUP('AUP Library'!A428,'Updated Quanities'!F:I,4,0),R428))","v":12.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A428,'Updated Quanities'!F:I,5,0),R428)=\"\",R428,IFERROR(VLOOKUP('AUP Library'!A428,'Updated Quanities'!F:I,5,0),R428))","v":12.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A428,'Updated Quanities'!F:I,6,0),R428)=\"\",R428,IFERROR(VLOOKUP('AUP Library'!A428,'Updated Quanities'!F:I,6,0),R428))","v":12.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A428,'Updated Quanities'!F:I,7,0),R428)=\"\",R428,IFERROR(VLOOKUP('AUP Library'!A428,'Updated Quanities'!F:I,7,0),R428))","v":12.5},12.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A428,'Updated Quanities'!F:G,4,0),R428)","v":12.5}]
["203-01.08","Rd & Drng (Acid Producing off Site)","CY",8.6,8.6,8.6,8.6,8.6,8.6,8.6,8.6,8.6,8.6,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A429,'Updated Quanities'!F:I,4,0),R429)=\"\",R429,IFERROR(VLOOKUP('AUP Library'!A429,'Updated Quanities'!F:I,4,0),R429))","v":8.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A429,'Updated Quanities'!F:I,5,0),R429)=\"\",R429,IFERROR(VLOOKUP('AUP Library'!A429,'Updated Quanities'!F:I,5,0),R429))","v":8.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A429,'Updated Quanities'!F:I,6,0),R429)=\"\",R429,IFERROR(VLOOKUP('AUP Library'!A429,'Updated Quanities'!F:I,6,0),R429))","v":8.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A429,'Updated Quanities'!F:I,7,0),R429)=\"\",R429,IFERROR(VLOOKUP('AUP Library'!A429,'Updated Quanities'!F:I,7,0),R429))","v":8.6},8.6,{"$f":"IFERROR(VLOOKUP('AUP Library'!A429,'Updated Quanities'!F:G,4,0),R429)","v":8.6}]
["203-01.11","Presplitting of Rock Excavation","SY",17.2,17.2,17.2,17.2,17.2,17.2,17.2,17.2,17.2,17.2,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A430,'Updated Quanities'!F:I,4,0),R430)=\"\",R430,IFERROR(VLOOKUP('AUP Library'!A430,'Updated Quanities'!F:I,4,0),R430))","v":17.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A430,'Updated Quanities'!F:I,5,0),R430)=\"\",R430,IFERROR(VLOOKUP('AUP Library'!A430,'Updated Quanities'!F:I,5,0),R430))","v":17.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A430,'Updated Quanities'!F:I,6,0),R430)=\"\",R430,IFERROR(VLOOKUP('AUP Library'!A430,'Updated Quanities'!F:I,6,0),R430))","v":17.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A430,'Updated Quanities'!F:I,7,0),R430)=\"\",R430,IFERROR(VLOOKUP('AUP Library'!A430,'Updated Quanities'!F:I,7,0),R430))","v":17.2},17.2,{"$f":"IFERROR(VLOOKUP('AUP Library'!A430,'Updated Quanities'!F:G,4,0),R430)","v":17.2}]
["203-01.15","Drainage Rock","CY",50,50,50,50,50,50,50,50,50,50,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A431,'Updated Quanities'!F:I,4,0),R431)=\"\",R431,IFERROR(VLOOKUP('AUP Library'!A431,'Updated Quanities'!F:I,4,0),R431))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A431,'Updated Quanities'!F:I,5,0),R431)=\"\",R431,IFERROR(VLOOKUP('AUP Library'!A431,'Updated Quanities'!F:I,5,0),R431))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A431,'Updated Quanities'!F:I,6,0),R431)=\"\",R431,IFERROR(VLOOKUP('AUP Library'!A431,'Updated Quanities'!F:I,6,0),R431))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A431,'Updated Quanities'!F:I,7,0),R431)=\"\",R431,IFERROR(VLOOKUP('AUP Library'!A431,'Updated Quanities'!F:I,7,0),R431))","v":50},50,{"$f":"IFERROR(VLOOKUP('AUP Library'!A431,'Updated Quanities'!F:G,4,0),R431)","v":50}]
["203-01.29","Rock Excavation","CY",9.85,9.85,9.85,9.85,9.85,9.85,9.85,9.85,9.85,9.85,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A432,'Updated Quanities'!F:I,4,0),R432)=\"\",R432,IFERROR(VLOOKUP('AUP Library'!A432,'Updated Quanities'!F:I,4,0),R432))","v":9.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A432,'Updated Quanities'!F:I,5,0),R432)=\"\",R432,IFERROR(VLOOKUP('AUP Library'!A432,'Updated Quanities'!F:I,5,0),R432))","v":9.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A432,'Updated Quanities'!F:I,6,0),R432)=\"\",R432,IFERROR(VLOOKUP('AUP Library'!A432,'Updated Quanities'!F:I,6,0),R432))","v":9.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A432,'Updated Quanities'!F:I,7,0),R432)=\"\",R432,IFERROR(VLOOKUP('AUP Library'!A432,'Updated Quanities'!F:I,7,0),R432))","v":9.85},9.85,{"$f":"IFERROR(VLOOKUP('AUP Library'!A432,'Updated Quanities'!F:G,4,0),R432)","v":9.85}]
["203-01.51","Trenching","LF",8,8,8,8,8,8,8,8,8,8,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A433,'Updated Quanities'!F:I,4,0),R433)=\"\",R433,IFERROR(VLOOKUP('AUP Library'!A433,'Updated Quanities'!F:I,4,0),R433))","v":8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A433,'Updated Quanities'!F:I,5,0),R433)=\"\",R433,IFERROR(VLOOKUP('AUP Library'!A433,'Updated Quanities'!F:I,5,0),R433))","v":8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A433,'Updated Quanities'!F:I,6,0),R433)=\"\",R433,IFERROR(VLOOKUP('AUP Library'!A433,'Updated Quanities'!F:I,6,0),R433))","v":8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A433,'Updated Quanities'!F:I,7,0),R433)=\"\",R433,IFERROR(VLOOKUP('AUP Library'!A433,'Updated Quanities'!F:I,7,0),R433))","v":8},8,{"$f":"IFERROR(VLOOKUP('AUP Library'!A433,'Updated Quanities'!F:G,4,0),R433)","v":8}]
["203-01.60","Road & Drainage Excavation","CY",7.85,7.85,7.85,7.85,7.85,7.85,7.85,7.85,7.85,7.85,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A434,'Updated Quanities'!F:I,4,0),R434)=\"\",R434,IFERROR(VLOOKUP('AUP Library'!A434,'Updated Quanities'!F:I,4,0),R434))","v":7.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A434,'Updated Quanities'!F:I,5,0),R434)=\"\",R434,IFERROR(VLOOKUP('AUP Library'!A434,'Updated Quanities'!F:I,5,0),R434))","v":7.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A434,'Updated Quanities'!F:I,6,0),R434)=\"\",R434,IFERROR(VLOOKUP('AUP Library'!A434,'Updated Quanities'!F:I,6,0),R434))","v":7.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A434,'Updated Quanities'!F:I,7,0),R434)=\"\",R434,IFERROR(VLOOKUP('AUP Library'!A434,'Updated Quanities'!F:I,7,0),R434))","v":7.85},7.85,{"$f":"IFERROR(VLOOKUP('AUP Library'!A434,'Updated Quanities'!F:G,4,0),R434)","v":7.85}]
["203-01.77","Road and Drainage Excavation (Unclass)","CY",30,30,30,30,30,30,30,30,30,30,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A435,'Updated Quanities'!F:I,4,0),R435)=\"\",R435,IFERROR(VLOOKUP('AUP Library'!A435,'Updated Quanities'!F:I,4,0),R435))","v":30},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A435,'Updated Quanities'!F:I,5,0),R435)=\"\",R435,IFERROR(VLOOKUP('AUP Library'!A435,'Updated Quanities'!F:I,5,0),R435))","v":30},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A435,'Updated Quanities'!F:I,6,0),R435)=\"\",R435,IFERROR(VLOOKUP('AUP Library'!A435,'Updated Quanities'!F:I,6,0),R435))","v":30},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A435,'Updated Quanities'!F:I,7,0),R435)=\"\",R435,IFERROR(VLOOKUP('AUP Library'!A435,'Updated Quanities'!F:I,7,0),R435))","v":30},30,{"$f":"IFERROR(VLOOKUP('AUP Library'!A435,'Updated Quanities'!F:G,4,0),R435)","v":30}]
["203-01.79","Excavation/Backfill","CY",30.13,30.13,30.13,30.13,30.13,30.13,30.13,30.13,30.13,30.13,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A436,'Updated Quanities'!F:I,4,0),R436)=\"\",R436,IFERROR(VLOOKUP('AUP Library'!A436,'Updated Quanities'!F:I,4,0),R436))","v":30.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A436,'Updated Quanities'!F:I,5,0),R436)=\"\",R436,IFERROR(VLOOKUP('AUP Library'!A436,'Updated Quanities'!F:I,5,0),R436))","v":30.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A436,'Updated Quanities'!F:I,6,0),R436)=\"\",R436,IFERROR(VLOOKUP('AUP Library'!A436,'Updated Quanities'!F:I,6,0),R436))","v":30.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A436,'Updated Quanities'!F:I,7,0),R436)=\"\",R436,IFERROR(VLOOKUP('AUP Library'!A436,'Updated Quanities'!F:I,7,0),R436))","v":30.13},30.13,{"$f":"IFERROR(VLOOKUP('AUP Library'!A436,'Updated Quanities'!F:G,4,0),R436)","v":30.13}]
["203-01.85","Rock Blasting","CY",5.85,5.85,5.85,5.85,5.85,5.85,5.85,5.85,5.85,5.85,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A437,'Updated Quanities'!F:I,4,0),R437)=\"\",R437,IFERROR(VLOOKUP('AUP Library'!A437,'Updated Quanities'!F:I,4,0),R437))","v":5.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A437,'Updated Quanities'!F:I,5,0),R437)=\"\",R437,IFERROR(VLOOKUP('AUP Library'!A437,'Updated Quanities'!F:I,5,0),R437))","v":5.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A437,'Updated Quanities'!F:I,6,0),R437)=\"\",R437,IFERROR(VLOOKUP('AUP Library'!A437,'Updated Quanities'!F:I,6,0),R437))","v":5.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A437,'Updated Quanities'!F:I,7,0),R437)=\"\",R437,IFERROR(VLOOKUP('AUP Library'!A437,'Updated Quanities'!F:I,7,0),R437))","v":5.85},5.85,{"$f":"IFERROR(VLOOKUP('AUP Library'!A437,'Updated Quanities'!F:G,4,0),R437)","v":5.85}]
["203-01.95","Design-Build Grading and Roadways","LS",1088729.7,1088729.7,1088729.7,1088729.7,1088729.7,1088729.7,1088729.7,1088729.7,1088729.7,1088729.7,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A438,'Updated Quanities'!F:I,4,0),R438)=\"\",R438,IFERROR(VLOOKUP('AUP Library'!A438,'Updated Quanities'!F:I,4,0),R438))","v":1088729.7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A438,'Updated Quanities'!F:I,5,0),R438)=\"\",R438,IFERROR(VLOOKUP('AUP Library'!A438,'Updated Quanities'!F:I,5,0),R438))","v":1088729.7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A438,'Updated Quanities'!F:I,6,0),R438)=\"\",R438,IFERROR(VLOOKUP('AUP Library'!A438,'Updated Quanities'!F:I,6,0),R438))","v":1088729.7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A438,'Updated Quanities'!F:I,7,0),R438)=\"\",R438,IFERROR(VLOOKUP('AUP Library'!A438,'Updated Quanities'!F:I,7,0),R438))","v":1088729.7},1088729.7,{"$f":"IFERROR(VLOOKUP('AUP Library'!A438,'Updated Quanities'!F:G,4,0),R438)","v":1088729.7}]
["203-02.01","Borrow Excavation (Graded Solid Rock)","TON",18.89,18.89,18.89,18.89,18.89,18.89,18.89,18.89,18.89,18.89,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A439,'Updated Quanities'!F:I,4,0),R439)=\"\",R439,IFERROR(VLOOKUP('AUP Library'!A439,'Updated Quanities'!F:I,4,0),R439))","v":18.89},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A439,'Updated Quanities'!F:I,5,0),R439)=\"\",R439,IFERROR(VLOOKUP('AUP Library'!A439,'Updated Quanities'!F:I,5,0),R439))","v":18.89},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A439,'Updated Quanities'!F:I,6,0),R439)=\"\",R439,IFERROR(VLOOKUP('AUP Library'!A439,'Updated Quanities'!F:I,6,0),R439))","v":18.89},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A439,'Updated Quanities'!F:I,7,0),R439)=\"\",R439,IFERROR(VLOOKUP('AUP Library'!A439,'Updated Quanities'!F:I,7,0),R439))","v":18.89},18.89,{"$f":"IFERROR(VLOOKUP('AUP Library'!A439,'Updated Quanities'!F:G,4,0),R439)","v":18.89}]
["203-02.02","Borrow Excavation (Graded Solid Rock)","CY",44.5,44.5,44.5,44.5,44.5,44.5,44.5,44.5,44.5,44.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A440,'Updated Quanities'!F:I,4,0),R440)=\"\",R440,IFERROR(VLOOKUP('AUP Library'!A440,'Updated Quanities'!F:I,4,0),R440))","v":44.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A440,'Updated Quanities'!F:I,5,0),R440)=\"\",R440,IFERROR(VLOOKUP('AUP Library'!A440,'Updated Quanities'!F:I,5,0),R440))","v":44.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A440,'Updated Quanities'!F:I,6,0),R440)=\"\",R440,IFERROR(VLOOKUP('AUP Library'!A440,'Updated Quanities'!F:I,6,0),R440))","v":44.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A440,'Updated Quanities'!F:I,7,0),R440)=\"\",R440,IFERROR(VLOOKUP('AUP Library'!A440,'Updated Quanities'!F:I,7,0),R440))","v":44.5},44.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A440,'Updated Quanities'!F:G,4,0),R440)","v":44.5}]
["203-03","Borrow Excavation (Unclassified)","CY",5.32,4.91,5.89,4.7699999999999996,4.7699999999999996,3.66,2.5099999999999998,10.050000000000001,3.58,5.2,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A441,'Updated Quanities'!F:I,4,0),R441)=\"\",R441,IFERROR(VLOOKUP('AUP Library'!A441,'Updated Quanities'!F:I,4,0),R441))","v":2.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A441,'Updated Quanities'!F:I,5,0),R441)=\"\",R441,IFERROR(VLOOKUP('AUP Library'!A441,'Updated Quanities'!F:I,5,0),R441))","v":2.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A441,'Updated Quanities'!F:I,6,0),R441)=\"\",R441,IFERROR(VLOOKUP('AUP Library'!A441,'Updated Quanities'!F:I,6,0),R441))","v":2.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A441,'Updated Quanities'!F:I,7,0),R441)=\"\",R441,IFERROR(VLOOKUP('AUP Library'!A441,'Updated Quanities'!F:I,7,0),R441))","v":2.9},2.9,{"$f":"IFERROR(VLOOKUP('AUP Library'!A441,'Updated Quanities'!F:G,4,0),R441)","v":2.9}]
["203-03.01","Borrow Excavation (Select Material)","CY",2.39,2.39,2.39,2.39,2.39,2.39,2.39,2.39,2.39,2.39,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A442,'Updated Quanities'!F:I,4,0),R442)=\"\",R442,IFERROR(VLOOKUP('AUP Library'!A442,'Updated Quanities'!F:I,4,0),R442))","v":2.39},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A442,'Updated Quanities'!F:I,5,0),R442)=\"\",R442,IFERROR(VLOOKUP('AUP Library'!A442,'Updated Quanities'!F:I,5,0),R442))","v":2.39},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A442,'Updated Quanities'!F:I,6,0),R442)=\"\",R442,IFERROR(VLOOKUP('AUP Library'!A442,'Updated Quanities'!F:I,6,0),R442))","v":2.39},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A442,'Updated Quanities'!F:I,7,0),R442)=\"\",R442,IFERROR(VLOOKUP('AUP Library'!A442,'Updated Quanities'!F:I,7,0),R442))","v":2.39},2.39,{"$f":"IFERROR(VLOOKUP('AUP Library'!A442,'Updated Quanities'!F:G,4,0),R442)","v":2.39}]
["203-03.05","Borrow Excavation (Select Material)","TON",9.41,9.41,9.41,9.41,9.41,9.41,9.41,9.41,9.41,9.41,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A443,'Updated Quanities'!F:I,4,0),R443)=\"\",R443,IFERROR(VLOOKUP('AUP Library'!A443,'Updated Quanities'!F:I,4,0),R443))","v":9.41},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A443,'Updated Quanities'!F:I,5,0),R443)=\"\",R443,IFERROR(VLOOKUP('AUP Library'!A443,'Updated Quanities'!F:I,5,0),R443))","v":9.41},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A443,'Updated Quanities'!F:I,6,0),R443)=\"\",R443,IFERROR(VLOOKUP('AUP Library'!A443,'Updated Quanities'!F:I,6,0),R443))","v":9.41},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A443,'Updated Quanities'!F:I,7,0),R443)=\"\",R443,IFERROR(VLOOKUP('AUP Library'!A443,'Updated Quanities'!F:I,7,0),R443))","v":9.41},9.41,{"$f":"IFERROR(VLOOKUP('AUP Library'!A443,'Updated Quanities'!F:G,4,0),R443)","v":9.41}]
["203-03.10","Select Granular Material","TON",19.78,19.78,19.78,19.78,19.78,19.78,19.78,19.78,19.78,19.78,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A444,'Updated Quanities'!F:I,4,0),R444)=\"\",R444,IFERROR(VLOOKUP('AUP Library'!A444,'Updated Quanities'!F:I,4,0),R444))","v":19.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A444,'Updated Quanities'!F:I,5,0),R444)=\"\",R444,IFERROR(VLOOKUP('AUP Library'!A444,'Updated Quanities'!F:I,5,0),R444))","v":19.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A444,'Updated Quanities'!F:I,6,0),R444)=\"\",R444,IFERROR(VLOOKUP('AUP Library'!A444,'Updated Quanities'!F:I,6,0),R444))","v":19.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A444,'Updated Quanities'!F:I,7,0),R444)=\"\",R444,IFERROR(VLOOKUP('AUP Library'!A444,'Updated Quanities'!F:I,7,0),R444))","v":19.78},19.78,{"$f":"IFERROR(VLOOKUP('AUP Library'!A444,'Updated Quanities'!F:G,4,0),R444)","v":19.78}]
["203-03.11","Select Granular Material","CY",10,10,10,10,10,10,10,10,10,10,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A445,'Updated Quanities'!F:I,4,0),R445)=\"\",R445,IFERROR(VLOOKUP('AUP Library'!A445,'Updated Quanities'!F:I,4,0),R445))","v":10},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A445,'Updated Quanities'!F:I,5,0),R445)=\"\",R445,IFERROR(VLOOKUP('AUP Library'!A445,'Updated Quanities'!F:I,5,0),R445))","v":10},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A445,'Updated Quanities'!F:I,6,0),R445)=\"\",R445,IFERROR(VLOOKUP('AUP Library'!A445,'Updated Quanities'!F:I,6,0),R445))","v":10},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A445,'Updated Quanities'!F:I,7,0),R445)=\"\",R445,IFERROR(VLOOKUP('AUP Library'!A445,'Updated Quanities'!F:I,7,0),R445))","v":10},10,{"$f":"IFERROR(VLOOKUP('AUP Library'!A445,'Updated Quanities'!F:G,4,0),R445)","v":10}]
["203-04","Placing and Spreading of Topsoil","CY",4.12,4.12,4.12,4.12,4.12,4.12,4.12,4.12,4.12,4.12,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A446,'Updated Quanities'!F:I,4,0),R446)=\"\",R446,IFERROR(VLOOKUP('AUP Library'!A446,'Updated Quanities'!F:I,4,0),R446))","v":4.12},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A446,'Updated Quanities'!F:I,5,0),R446)=\"\",R446,IFERROR(VLOOKUP('AUP Library'!A446,'Updated Quanities'!F:I,5,0),R446))","v":4.12},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A446,'Updated Quanities'!F:I,6,0),R446)=\"\",R446,IFERROR(VLOOKUP('AUP Library'!A446,'Updated Quanities'!F:I,6,0),R446))","v":4.12},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A446,'Updated Quanities'!F:I,7,0),R446)=\"\",R446,IFERROR(VLOOKUP('AUP Library'!A446,'Updated Quanities'!F:I,7,0),R446))","v":4.12},4.12,{"$f":"IFERROR(VLOOKUP('AUP Library'!A446,'Updated Quanities'!F:G,4,0),R446)","v":4.12}]
["203-04.01","Placing and Spreading Soil for Landscaping","CY",30,30,30,30,30,30,30,30,30,30,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A447,'Updated Quanities'!F:I,4,0),R447)=\"\",R447,IFERROR(VLOOKUP('AUP Library'!A447,'Updated Quanities'!F:I,4,0),R447))","v":30},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A447,'Updated Quanities'!F:I,5,0),R447)=\"\",R447,IFERROR(VLOOKUP('AUP Library'!A447,'Updated Quanities'!F:I,5,0),R447))","v":30},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A447,'Updated Quanities'!F:I,6,0),R447)=\"\",R447,IFERROR(VLOOKUP('AUP Library'!A447,'Updated Quanities'!F:I,6,0),R447))","v":30},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A447,'Updated Quanities'!F:I,7,0),R447)=\"\",R447,IFERROR(VLOOKUP('AUP Library'!A447,'Updated Quanities'!F:I,7,0),R447))","v":30},30,{"$f":"IFERROR(VLOOKUP('AUP Library'!A447,'Updated Quanities'!F:G,4,0),R447)","v":30}]
["203-04.02","Stripping and Stockpile Topsoil","CY",1.5,1.5,1.5,1.5,1.5,1.5,1.5,1.5,1.5,1.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A448,'Updated Quanities'!F:I,4,0),R448)=\"\",R448,IFERROR(VLOOKUP('AUP Library'!A448,'Updated Quanities'!F:I,4,0),R448))","v":1.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A448,'Updated Quanities'!F:I,5,0),R448)=\"\",R448,IFERROR(VLOOKUP('AUP Library'!A448,'Updated Quanities'!F:I,5,0),R448))","v":1.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A448,'Updated Quanities'!F:I,6,0),R448)=\"\",R448,IFERROR(VLOOKUP('AUP Library'!A448,'Updated Quanities'!F:I,6,0),R448))","v":1.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A448,'Updated Quanities'!F:I,7,0),R448)=\"\",R448,IFERROR(VLOOKUP('AUP Library'!A448,'Updated Quanities'!F:I,7,0),R448))","v":1.5},1.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A448,'Updated Quanities'!F:G,4,0),R448)","v":1.5}]
["203-05","Undercutting","CY",6.51,6.51,6.51,6.51,6.51,6.51,6.51,6.51,6.51,6.51,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A449,'Updated Quanities'!F:I,4,0),R449)=\"\",R449,IFERROR(VLOOKUP('AUP Library'!A449,'Updated Quanities'!F:I,4,0),R449))","v":6.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A449,'Updated Quanities'!F:I,5,0),R449)=\"\",R449,IFERROR(VLOOKUP('AUP Library'!A449,'Updated Quanities'!F:I,5,0),R449))","v":6.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A449,'Updated Quanities'!F:I,6,0),R449)=\"\",R449,IFERROR(VLOOKUP('AUP Library'!A449,'Updated Quanities'!F:I,6,0),R449))","v":6.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A449,'Updated Quanities'!F:I,7,0),R449)=\"\",R449,IFERROR(VLOOKUP('AUP Library'!A449,'Updated Quanities'!F:I,7,0),R449))","v":6.51},6.51,{"$f":"IFERROR(VLOOKUP('AUP Library'!A449,'Updated Quanities'!F:G,4,0),R449)","v":6.51}]
["203-06","Water","MG",10.27,10.27,10.27,10.27,10.27,10.27,10.27,10.27,10.27,10.27,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A450,'Updated Quanities'!F:I,4,0),R450)=\"\",R450,IFERROR(VLOOKUP('AUP Library'!A450,'Updated Quanities'!F:I,4,0),R450))","v":10.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A450,'Updated Quanities'!F:I,5,0),R450)=\"\",R450,IFERROR(VLOOKUP('AUP Library'!A450,'Updated Quanities'!F:I,5,0),R450))","v":10.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A450,'Updated Quanities'!F:I,6,0),R450)=\"\",R450,IFERROR(VLOOKUP('AUP Library'!A450,'Updated Quanities'!F:I,6,0),R450))","v":10.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A450,'Updated Quanities'!F:I,7,0),R450)=\"\",R450,IFERROR(VLOOKUP('AUP Library'!A450,'Updated Quanities'!F:I,7,0),R450))","v":10.27},10.27,{"$f":"IFERROR(VLOOKUP('AUP Library'!A450,'Updated Quanities'!F:G,4,0),R450)","v":10.27}]
["203-07","Furnishing and Spreading Topsoil","CY",9.57,9.57,9.57,9.57,9.57,9.57,9.57,9.57,9.57,9.57,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A451,'Updated Quanities'!F:I,4,0),R451)=\"\",R451,IFERROR(VLOOKUP('AUP Library'!A451,'Updated Quanities'!F:I,4,0),R451))","v":9.57},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A451,'Updated Quanities'!F:I,5,0),R451)=\"\",R451,IFERROR(VLOOKUP('AUP Library'!A451,'Updated Quanities'!F:I,5,0),R451))","v":9.57},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A451,'Updated Quanities'!F:I,6,0),R451)=\"\",R451,IFERROR(VLOOKUP('AUP Library'!A451,'Updated Quanities'!F:I,6,0),R451))","v":9.57},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A451,'Updated Quanities'!F:I,7,0),R451)=\"\",R451,IFERROR(VLOOKUP('AUP Library'!A451,'Updated Quanities'!F:I,7,0),R451))","v":9.57},9.57,{"$f":"IFERROR(VLOOKUP('AUP Library'!A451,'Updated Quanities'!F:G,4,0),R451)","v":9.57}]
["203-08","Channel Excavation (Unclassified)","CY",8.58,8.58,8.58,8.58,8.58,8.58,8.58,8.58,8.58,8.58,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A452,'Updated Quanities'!F:I,4,0),R452)=\"\",R452,IFERROR(VLOOKUP('AUP Library'!A452,'Updated Quanities'!F:I,4,0),R452))","v":8.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A452,'Updated Quanities'!F:I,5,0),R452)=\"\",R452,IFERROR(VLOOKUP('AUP Library'!A452,'Updated Quanities'!F:I,5,0),R452))","v":8.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A452,'Updated Quanities'!F:I,6,0),R452)=\"\",R452,IFERROR(VLOOKUP('AUP Library'!A452,'Updated Quanities'!F:I,6,0),R452))","v":8.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A452,'Updated Quanities'!F:I,7,0),R452)=\"\",R452,IFERROR(VLOOKUP('AUP Library'!A452,'Updated Quanities'!F:I,7,0),R452))","v":8.58},8.58,{"$f":"IFERROR(VLOOKUP('AUP Library'!A452,'Updated Quanities'!F:G,4,0),R452)","v":8.58}]
["203-10","Embankment (Compacted in Place)","CY",13.51,13.51,13.51,13.51,13.51,13.51,13.51,13.51,13.51,13.51,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A453,'Updated Quanities'!F:I,4,0),R453)=\"\",R453,IFERROR(VLOOKUP('AUP Library'!A453,'Updated Quanities'!F:I,4,0),R453))","v":13.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A453,'Updated Quanities'!F:I,5,0),R453)=\"\",R453,IFERROR(VLOOKUP('AUP Library'!A453,'Updated Quanities'!F:I,5,0),R453))","v":13.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A453,'Updated Quanities'!F:I,6,0),R453)=\"\",R453,IFERROR(VLOOKUP('AUP Library'!A453,'Updated Quanities'!F:I,6,0),R453))","v":13.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A453,'Updated Quanities'!F:I,7,0),R453)=\"\",R453,IFERROR(VLOOKUP('AUP Library'!A453,'Updated Quanities'!F:I,7,0),R453))","v":13.51},13.51,{"$f":"IFERROR(VLOOKUP('AUP Library'!A453,'Updated Quanities'!F:G,4,0),R453)","v":13.51}]
["203-10.15","Waste Material","CY",2.71,2.71,2.71,2.71,2.71,2.71,2.71,2.71,2.71,2.71,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A454,'Updated Quanities'!F:I,4,0),R454)=\"\",R454,IFERROR(VLOOKUP('AUP Library'!A454,'Updated Quanities'!F:I,4,0),R454))","v":2.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A454,'Updated Quanities'!F:I,5,0),R454)=\"\",R454,IFERROR(VLOOKUP('AUP Library'!A454,'Updated Quanities'!F:I,5,0),R454))","v":2.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A454,'Updated Quanities'!F:I,6,0),R454)=\"\",R454,IFERROR(VLOOKUP('AUP Library'!A454,'Updated Quanities'!F:I,6,0),R454))","v":2.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A454,'Updated Quanities'!F:I,7,0),R454)=\"\",R454,IFERROR(VLOOKUP('AUP Library'!A454,'Updated Quanities'!F:I,7,0),R454))","v":2.71},2.71,{"$f":"IFERROR(VLOOKUP('AUP Library'!A454,'Updated Quanities'!F:G,4,0),R454)","v":2.71}]
["203-10.16","Graded Solid Rock (In-Place)","CY",80,80,80,80,80,80,80,80,80,80,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A455,'Updated Quanities'!F:I,4,0),R455)=\"\",R455,IFERROR(VLOOKUP('AUP Library'!A455,'Updated Quanities'!F:I,4,0),R455))","v":80},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A455,'Updated Quanities'!F:I,5,0),R455)=\"\",R455,IFERROR(VLOOKUP('AUP Library'!A455,'Updated Quanities'!F:I,5,0),R455))","v":80},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A455,'Updated Quanities'!F:I,6,0),R455)=\"\",R455,IFERROR(VLOOKUP('AUP Library'!A455,'Updated Quanities'!F:I,6,0),R455))","v":80},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A455,'Updated Quanities'!F:I,7,0),R455)=\"\",R455,IFERROR(VLOOKUP('AUP Library'!A455,'Updated Quanities'!F:I,7,0),R455))","v":80},80,{"$f":"IFERROR(VLOOKUP('AUP Library'!A455,'Updated Quanities'!F:G,4,0),R455)","v":80}]
["203-11","Scaling and Trimming","SY",33.25,33.25,33.25,33.25,33.25,33.25,33.25,33.25,33.25,33.25,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A456,'Updated Quanities'!F:I,4,0),R456)=\"\",R456,IFERROR(VLOOKUP('AUP Library'!A456,'Updated Quanities'!F:I,4,0),R456))","v":33.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A456,'Updated Quanities'!F:I,5,0),R456)=\"\",R456,IFERROR(VLOOKUP('AUP Library'!A456,'Updated Quanities'!F:I,5,0),R456))","v":33.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A456,'Updated Quanities'!F:I,6,0),R456)=\"\",R456,IFERROR(VLOOKUP('AUP Library'!A456,'Updated Quanities'!F:I,6,0),R456))","v":33.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A456,'Updated Quanities'!F:I,7,0),R456)=\"\",R456,IFERROR(VLOOKUP('AUP Library'!A456,'Updated Quanities'!F:I,7,0),R456))","v":33.25},33.25,{"$f":"IFERROR(VLOOKUP('AUP Library'!A456,'Updated Quanities'!F:G,4,0),R456)","v":33.25}]
["203-12.30","Wetland Materials Exc and Relocation","CY",25.25,25.25,25.25,25.25,25.25,25.25,25.25,25.25,25.25,25.25,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A457,'Updated Quanities'!F:I,4,0),R457)=\"\",R457,IFERROR(VLOOKUP('AUP Library'!A457,'Updated Quanities'!F:I,4,0),R457))","v":25.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A457,'Updated Quanities'!F:I,5,0),R457)=\"\",R457,IFERROR(VLOOKUP('AUP Library'!A457,'Updated Quanities'!F:I,5,0),R457))","v":25.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A457,'Updated Quanities'!F:I,6,0),R457)=\"\",R457,IFERROR(VLOOKUP('AUP Library'!A457,'Updated Quanities'!F:I,6,0),R457))","v":25.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A457,'Updated Quanities'!F:I,7,0),R457)=\"\",R457,IFERROR(VLOOKUP('AUP Library'!A457,'Updated Quanities'!F:I,7,0),R457))","v":25.25},25.25,{"$f":"IFERROR(VLOOKUP('AUP Library'!A457,'Updated Quanities'!F:G,4,0),R457)","v":25.25}]
["203-15.03","Compacted Clay","CY",23.23,23.23,23.23,23.23,23.23,23.23,23.23,23.23,23.23,23.23,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A458,'Updated Quanities'!F:I,4,0),R458)=\"\",R458,IFERROR(VLOOKUP('AUP Library'!A458,'Updated Quanities'!F:I,4,0),R458))","v":23.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A458,'Updated Quanities'!F:I,5,0),R458)=\"\",R458,IFERROR(VLOOKUP('AUP Library'!A458,'Updated Quanities'!F:I,5,0),R458))","v":23.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A458,'Updated Quanities'!F:I,6,0),R458)=\"\",R458,IFERROR(VLOOKUP('AUP Library'!A458,'Updated Quanities'!F:I,6,0),R458))","v":23.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A458,'Updated Quanities'!F:I,7,0),R458)=\"\",R458,IFERROR(VLOOKUP('AUP Library'!A458,'Updated Quanities'!F:I,7,0),R458))","v":23.23},23.23,{"$f":"IFERROR(VLOOKUP('AUP Library'!A458,'Updated Quanities'!F:G,4,0),R458)","v":23.23}]
["203-30.01","Roadway Approaches","LS",39898.85,39898.85,39898.85,39898.85,39898.85,39898.85,39898.85,39898.85,39898.85,39898.85,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A459,'Updated Quanities'!F:I,4,0),R459)=\"\",R459,IFERROR(VLOOKUP('AUP Library'!A459,'Updated Quanities'!F:I,4,0),R459))","v":39898.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A459,'Updated Quanities'!F:I,5,0),R459)=\"\",R459,IFERROR(VLOOKUP('AUP Library'!A459,'Updated Quanities'!F:I,5,0),R459))","v":39898.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A459,'Updated Quanities'!F:I,6,0),R459)=\"\",R459,IFERROR(VLOOKUP('AUP Library'!A459,'Updated Quanities'!F:I,6,0),R459))","v":39898.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A459,'Updated Quanities'!F:I,7,0),R459)=\"\",R459,IFERROR(VLOOKUP('AUP Library'!A459,'Updated Quanities'!F:I,7,0),R459))","v":39898.85},39898.85,{"$f":"IFERROR(VLOOKUP('AUP Library'!A459,'Updated Quanities'!F:G,4,0),R459)","v":39898.85}]
["203-40.02","Rock Anchors","LF",65.510000000000005,65.510000000000005,65.510000000000005,65.510000000000005,65.510000000000005,65.510000000000005,65.510000000000005,65.510000000000005,65.510000000000005,65.510000000000005,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A460,'Updated Quanities'!F:I,4,0),R460)=\"\",R460,IFERROR(VLOOKUP('AUP Library'!A460,'Updated Quanities'!F:I,4,0),R460))","v":65.510000000000005},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A460,'Updated Quanities'!F:I,5,0),R460)=\"\",R460,IFERROR(VLOOKUP('AUP Library'!A460,'Updated Quanities'!F:I,5,0),R460))","v":65.510000000000005},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A460,'Updated Quanities'!F:I,6,0),R460)=\"\",R460,IFERROR(VLOOKUP('AUP Library'!A460,'Updated Quanities'!F:I,6,0),R460))","v":65.510000000000005},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A460,'Updated Quanities'!F:I,7,0),R460)=\"\",R460,IFERROR(VLOOKUP('AUP Library'!A460,'Updated Quanities'!F:I,7,0),R460))","v":65.510000000000005},65.510000000000005,{"$f":"IFERROR(VLOOKUP('AUP Library'!A460,'Updated Quanities'!F:G,4,0),R460)","v":65.510000000000005}]
["203-40.05","Drilling","LF",50,50,50,50,50,50,50,50,50,50,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A461,'Updated Quanities'!F:I,4,0),R461)=\"\",R461,IFERROR(VLOOKUP('AUP Library'!A461,'Updated Quanities'!F:I,4,0),R461))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A461,'Updated Quanities'!F:I,5,0),R461)=\"\",R461,IFERROR(VLOOKUP('AUP Library'!A461,'Updated Quanities'!F:I,5,0),R461))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A461,'Updated Quanities'!F:I,6,0),R461)=\"\",R461,IFERROR(VLOOKUP('AUP Library'!A461,'Updated Quanities'!F:I,6,0),R461))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A461,'Updated Quanities'!F:I,7,0),R461)=\"\",R461,IFERROR(VLOOKUP('AUP Library'!A461,'Updated Quanities'!F:I,7,0),R461))","v":50},50,{"$f":"IFERROR(VLOOKUP('AUP Library'!A461,'Updated Quanities'!F:G,4,0),R461)","v":50}]
["203-40.16","Rock Bolt Pull Test","EA",650,650,650,650,650,650,650,650,650,650,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A462,'Updated Quanities'!F:I,4,0),R462)=\"\",R462,IFERROR(VLOOKUP('AUP Library'!A462,'Updated Quanities'!F:I,4,0),R462))","v":650},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A462,'Updated Quanities'!F:I,5,0),R462)=\"\",R462,IFERROR(VLOOKUP('AUP Library'!A462,'Updated Quanities'!F:I,5,0),R462))","v":650},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A462,'Updated Quanities'!F:I,6,0),R462)=\"\",R462,IFERROR(VLOOKUP('AUP Library'!A462,'Updated Quanities'!F:I,6,0),R462))","v":650},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A462,'Updated Quanities'!F:I,7,0),R462)=\"\",R462,IFERROR(VLOOKUP('AUP Library'!A462,'Updated Quanities'!F:I,7,0),R462))","v":650},650,{"$f":"IFERROR(VLOOKUP('AUP Library'!A462,'Updated Quanities'!F:G,4,0),R462)","v":650}]
["203-50","Construction of Haul Road","LS",75814.63,75814.63,75814.63,75814.63,75814.63,75814.63,75814.63,75814.63,75814.63,75814.63,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A463,'Updated Quanities'!F:I,4,0),R463)=\"\",R463,IFERROR(VLOOKUP('AUP Library'!A463,'Updated Quanities'!F:I,4,0),R463))","v":75814.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A463,'Updated Quanities'!F:I,5,0),R463)=\"\",R463,IFERROR(VLOOKUP('AUP Library'!A463,'Updated Quanities'!F:I,5,0),R463))","v":75814.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A463,'Updated Quanities'!F:I,6,0),R463)=\"\",R463,IFERROR(VLOOKUP('AUP Library'!A463,'Updated Quanities'!F:I,6,0),R463))","v":75814.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A463,'Updated Quanities'!F:I,7,0),R463)=\"\",R463,IFERROR(VLOOKUP('AUP Library'!A463,'Updated Quanities'!F:I,7,0),R463))","v":75814.63},75814.63,{"$f":"IFERROR(VLOOKUP('AUP Library'!A463,'Updated Quanities'!F:G,4,0),R463)","v":75814.63}]
["203-50.01","Construction of Haul Road","LS",35000,35000,35000,35000,35000,35000,35000,35000,35000,35000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A464,'Updated Quanities'!F:I,4,0),R464)=\"\",R464,IFERROR(VLOOKUP('AUP Library'!A464,'Updated Quanities'!F:I,4,0),R464))","v":35000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A464,'Updated Quanities'!F:I,5,0),R464)=\"\",R464,IFERROR(VLOOKUP('AUP Library'!A464,'Updated Quanities'!F:I,5,0),R464))","v":35000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A464,'Updated Quanities'!F:I,6,0),R464)=\"\",R464,IFERROR(VLOOKUP('AUP Library'!A464,'Updated Quanities'!F:I,6,0),R464))","v":35000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A464,'Updated Quanities'!F:I,7,0),R464)=\"\",R464,IFERROR(VLOOKUP('AUP Library'!A464,'Updated Quanities'!F:I,7,0),R464))","v":35000},35000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A464,'Updated Quanities'!F:G,4,0),R464)","v":35000}]
["204-01","Culvert Excavation (Unclassified)","CY",17.7,17.7,17.7,17.7,17.7,17.7,17.7,17.7,17.7,17.7,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A465,'Updated Quanities'!F:I,4,0),R465)=\"\",R465,IFERROR(VLOOKUP('AUP Library'!A465,'Updated Quanities'!F:I,4,0),R465))","v":17.7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A465,'Updated Quanities'!F:I,5,0),R465)=\"\",R465,IFERROR(VLOOKUP('AUP Library'!A465,'Updated Quanities'!F:I,5,0),R465))","v":17.7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A465,'Updated Quanities'!F:I,6,0),R465)=\"\",R465,IFERROR(VLOOKUP('AUP Library'!A465,'Updated Quanities'!F:I,6,0),R465))","v":17.7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A465,'Updated Quanities'!F:I,7,0),R465)=\"\",R465,IFERROR(VLOOKUP('AUP Library'!A465,'Updated Quanities'!F:I,7,0),R465))","v":17.7},17.7,{"$f":"IFERROR(VLOOKUP('AUP Library'!A465,'Updated Quanities'!F:G,4,0),R465)","v":17.7}]
["204-02.01","Dry Excavation (Bridges)","CY",16.84,16.84,16.84,16.84,16.84,16.84,16.84,16.84,16.84,16.84,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A466,'Updated Quanities'!F:I,4,0),R466)=\"\",R466,IFERROR(VLOOKUP('AUP Library'!A466,'Updated Quanities'!F:I,4,0),R466))","v":16.84},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A466,'Updated Quanities'!F:I,5,0),R466)=\"\",R466,IFERROR(VLOOKUP('AUP Library'!A466,'Updated Quanities'!F:I,5,0),R466))","v":16.84},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A466,'Updated Quanities'!F:I,6,0),R466)=\"\",R466,IFERROR(VLOOKUP('AUP Library'!A466,'Updated Quanities'!F:I,6,0),R466))","v":16.84},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A466,'Updated Quanities'!F:I,7,0),R466)=\"\",R466,IFERROR(VLOOKUP('AUP Library'!A466,'Updated Quanities'!F:I,7,0),R466))","v":16.84},16.84,{"$f":"IFERROR(VLOOKUP('AUP Library'!A466,'Updated Quanities'!F:G,4,0),R466)","v":16.84}]
["204-02.10","Drilled Caisson - Earth","LF",39,39,39,39,39,39,39,39,39,39,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A467,'Updated Quanities'!F:I,4,0),R467)=\"\",R467,IFERROR(VLOOKUP('AUP Library'!A467,'Updated Quanities'!F:I,4,0),R467))","v":39},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A467,'Updated Quanities'!F:I,5,0),R467)=\"\",R467,IFERROR(VLOOKUP('AUP Library'!A467,'Updated Quanities'!F:I,5,0),R467))","v":39},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A467,'Updated Quanities'!F:I,6,0),R467)=\"\",R467,IFERROR(VLOOKUP('AUP Library'!A467,'Updated Quanities'!F:I,6,0),R467))","v":39},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A467,'Updated Quanities'!F:I,7,0),R467)=\"\",R467,IFERROR(VLOOKUP('AUP Library'!A467,'Updated Quanities'!F:I,7,0),R467))","v":39},39,{"$f":"IFERROR(VLOOKUP('AUP Library'!A467,'Updated Quanities'!F:G,4,0),R467)","v":39}]
["204-02.11","Drilled Caisson - Earth","LF",115,115,115,115,115,115,115,115,115,115,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A468,'Updated Quanities'!F:I,4,0),R468)=\"\",R468,IFERROR(VLOOKUP('AUP Library'!A468,'Updated Quanities'!F:I,4,0),R468))","v":115},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A468,'Updated Quanities'!F:I,5,0),R468)=\"\",R468,IFERROR(VLOOKUP('AUP Library'!A468,'Updated Quanities'!F:I,5,0),R468))","v":115},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A468,'Updated Quanities'!F:I,6,0),R468)=\"\",R468,IFERROR(VLOOKUP('AUP Library'!A468,'Updated Quanities'!F:I,6,0),R468))","v":115},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A468,'Updated Quanities'!F:I,7,0),R468)=\"\",R468,IFERROR(VLOOKUP('AUP Library'!A468,'Updated Quanities'!F:I,7,0),R468))","v":115},115,{"$f":"IFERROR(VLOOKUP('AUP Library'!A468,'Updated Quanities'!F:G,4,0),R468)","v":115}]
["204-02.20","Drilled Caisson - Rock","LF",425,425,425,425,425,425,425,425,425,425,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A469,'Updated Quanities'!F:I,4,0),R469)=\"\",R469,IFERROR(VLOOKUP('AUP Library'!A469,'Updated Quanities'!F:I,4,0),R469))","v":425},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A469,'Updated Quanities'!F:I,5,0),R469)=\"\",R469,IFERROR(VLOOKUP('AUP Library'!A469,'Updated Quanities'!F:I,5,0),R469))","v":425},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A469,'Updated Quanities'!F:I,6,0),R469)=\"\",R469,IFERROR(VLOOKUP('AUP Library'!A469,'Updated Quanities'!F:I,6,0),R469))","v":425},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A469,'Updated Quanities'!F:I,7,0),R469)=\"\",R469,IFERROR(VLOOKUP('AUP Library'!A469,'Updated Quanities'!F:I,7,0),R469))","v":425},425,{"$f":"IFERROR(VLOOKUP('AUP Library'!A469,'Updated Quanities'!F:G,4,0),R469)","v":425}]
["204-02.21","Drilled Caisson - Rock","LF",170,170,170,170,170,170,170,170,170,170,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A470,'Updated Quanities'!F:I,4,0),R470)=\"\",R470,IFERROR(VLOOKUP('AUP Library'!A470,'Updated Quanities'!F:I,4,0),R470))","v":170},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A470,'Updated Quanities'!F:I,5,0),R470)=\"\",R470,IFERROR(VLOOKUP('AUP Library'!A470,'Updated Quanities'!F:I,5,0),R470))","v":170},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A470,'Updated Quanities'!F:I,6,0),R470)=\"\",R470,IFERROR(VLOOKUP('AUP Library'!A470,'Updated Quanities'!F:I,6,0),R470))","v":170},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A470,'Updated Quanities'!F:I,7,0),R470)=\"\",R470,IFERROR(VLOOKUP('AUP Library'!A470,'Updated Quanities'!F:I,7,0),R470))","v":170},170,{"$f":"IFERROR(VLOOKUP('AUP Library'!A470,'Updated Quanities'!F:G,4,0),R470)","v":170}]
["204-02.30","Drilled Caisson-Unclassified","LF",50,50,50,50,50,50,50,50,50,50,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A471,'Updated Quanities'!F:I,4,0),R471)=\"\",R471,IFERROR(VLOOKUP('AUP Library'!A471,'Updated Quanities'!F:I,4,0),R471))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A471,'Updated Quanities'!F:I,5,0),R471)=\"\",R471,IFERROR(VLOOKUP('AUP Library'!A471,'Updated Quanities'!F:I,5,0),R471))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A471,'Updated Quanities'!F:I,6,0),R471)=\"\",R471,IFERROR(VLOOKUP('AUP Library'!A471,'Updated Quanities'!F:I,6,0),R471))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A471,'Updated Quanities'!F:I,7,0),R471)=\"\",R471,IFERROR(VLOOKUP('AUP Library'!A471,'Updated Quanities'!F:I,7,0),R471))","v":50},50,{"$f":"IFERROR(VLOOKUP('AUP Library'!A471,'Updated Quanities'!F:G,4,0),R471)","v":50}]
["204-03.01","Wet Excavation","CY",34.28,34.28,34.28,34.28,34.28,34.28,34.28,34.28,34.28,34.28,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A472,'Updated Quanities'!F:I,4,0),R472)=\"\",R472,IFERROR(VLOOKUP('AUP Library'!A472,'Updated Quanities'!F:I,4,0),R472))","v":34.28},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A472,'Updated Quanities'!F:I,5,0),R472)=\"\",R472,IFERROR(VLOOKUP('AUP Library'!A472,'Updated Quanities'!F:I,5,0),R472))","v":34.28},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A472,'Updated Quanities'!F:I,6,0),R472)=\"\",R472,IFERROR(VLOOKUP('AUP Library'!A472,'Updated Quanities'!F:I,6,0),R472))","v":34.28},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A472,'Updated Quanities'!F:I,7,0),R472)=\"\",R472,IFERROR(VLOOKUP('AUP Library'!A472,'Updated Quanities'!F:I,7,0),R472))","v":34.28},34.28,{"$f":"IFERROR(VLOOKUP('AUP Library'!A472,'Updated Quanities'!F:G,4,0),R472)","v":34.28}]
["204-04.01","Rock Excavation (Bridges)","CY",71.17,71.17,71.17,71.17,71.17,71.17,71.17,71.17,71.17,71.17,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A473,'Updated Quanities'!F:I,4,0),R473)=\"\",R473,IFERROR(VLOOKUP('AUP Library'!A473,'Updated Quanities'!F:I,4,0),R473))","v":71.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A473,'Updated Quanities'!F:I,5,0),R473)=\"\",R473,IFERROR(VLOOKUP('AUP Library'!A473,'Updated Quanities'!F:I,5,0),R473))","v":71.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A473,'Updated Quanities'!F:I,6,0),R473)=\"\",R473,IFERROR(VLOOKUP('AUP Library'!A473,'Updated Quanities'!F:I,6,0),R473))","v":71.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A473,'Updated Quanities'!F:I,7,0),R473)=\"\",R473,IFERROR(VLOOKUP('AUP Library'!A473,'Updated Quanities'!F:I,7,0),R473))","v":71.17},71.17,{"$f":"IFERROR(VLOOKUP('AUP Library'!A473,'Updated Quanities'!F:G,4,0),R473)","v":71.17}]
["204-04.10","Structure Excavation Unclassifed","CY",14.6,14.6,14.6,14.6,14.6,14.6,14.6,14.6,14.6,14.6,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A474,'Updated Quanities'!F:I,4,0),R474)=\"\",R474,IFERROR(VLOOKUP('AUP Library'!A474,'Updated Quanities'!F:I,4,0),R474))","v":14.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A474,'Updated Quanities'!F:I,5,0),R474)=\"\",R474,IFERROR(VLOOKUP('AUP Library'!A474,'Updated Quanities'!F:I,5,0),R474))","v":14.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A474,'Updated Quanities'!F:I,6,0),R474)=\"\",R474,IFERROR(VLOOKUP('AUP Library'!A474,'Updated Quanities'!F:I,6,0),R474))","v":14.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A474,'Updated Quanities'!F:I,7,0),R474)=\"\",R474,IFERROR(VLOOKUP('AUP Library'!A474,'Updated Quanities'!F:I,7,0),R474))","v":14.6},14.6,{"$f":"IFERROR(VLOOKUP('AUP Library'!A474,'Updated Quanities'!F:G,4,0),R474)","v":14.6}]
["204-05","Rock Drilling (Bridges)","LF",24.58,24.58,24.58,24.58,24.58,24.58,24.58,24.58,24.58,24.58,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A475,'Updated Quanities'!F:I,4,0),R475)=\"\",R475,IFERROR(VLOOKUP('AUP Library'!A475,'Updated Quanities'!F:I,4,0),R475))","v":24.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A475,'Updated Quanities'!F:I,5,0),R475)=\"\",R475,IFERROR(VLOOKUP('AUP Library'!A475,'Updated Quanities'!F:I,5,0),R475))","v":24.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A475,'Updated Quanities'!F:I,6,0),R475)=\"\",R475,IFERROR(VLOOKUP('AUP Library'!A475,'Updated Quanities'!F:I,6,0),R475))","v":24.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A475,'Updated Quanities'!F:I,7,0),R475)=\"\",R475,IFERROR(VLOOKUP('AUP Library'!A475,'Updated Quanities'!F:I,7,0),R475))","v":24.58},24.58,{"$f":"IFERROR(VLOOKUP('AUP Library'!A475,'Updated Quanities'!F:G,4,0),R475)","v":24.58}]
["204-05.01","Core Drilling and Sampling","LF",43.25,43.25,43.25,43.25,43.25,43.25,43.25,43.25,43.25,43.25,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A476,'Updated Quanities'!F:I,4,0),R476)=\"\",R476,IFERROR(VLOOKUP('AUP Library'!A476,'Updated Quanities'!F:I,4,0),R476))","v":43.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A476,'Updated Quanities'!F:I,5,0),R476)=\"\",R476,IFERROR(VLOOKUP('AUP Library'!A476,'Updated Quanities'!F:I,5,0),R476))","v":43.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A476,'Updated Quanities'!F:I,6,0),R476)=\"\",R476,IFERROR(VLOOKUP('AUP Library'!A476,'Updated Quanities'!F:I,6,0),R476))","v":43.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A476,'Updated Quanities'!F:I,7,0),R476)=\"\",R476,IFERROR(VLOOKUP('AUP Library'!A476,'Updated Quanities'!F:I,7,0),R476))","v":43.25},43.25,{"$f":"IFERROR(VLOOKUP('AUP Library'!A476,'Updated Quanities'!F:G,4,0),R476)","v":43.25}]
["204-05.20","Grout Casing Installation","LF",35,35,35,35,35,35,35,35,35,35,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A477,'Updated Quanities'!F:I,4,0),R477)=\"\",R477,IFERROR(VLOOKUP('AUP Library'!A477,'Updated Quanities'!F:I,4,0),R477))","v":35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A477,'Updated Quanities'!F:I,5,0),R477)=\"\",R477,IFERROR(VLOOKUP('AUP Library'!A477,'Updated Quanities'!F:I,5,0),R477))","v":35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A477,'Updated Quanities'!F:I,6,0),R477)=\"\",R477,IFERROR(VLOOKUP('AUP Library'!A477,'Updated Quanities'!F:I,6,0),R477))","v":35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A477,'Updated Quanities'!F:I,7,0),R477)=\"\",R477,IFERROR(VLOOKUP('AUP Library'!A477,'Updated Quanities'!F:I,7,0),R477))","v":35},35,{"$f":"IFERROR(VLOOKUP('AUP Library'!A477,'Updated Quanities'!F:G,4,0),R477)","v":35}]
["204-05.50","Design-Build Geotechnical","LS",100000,100000,100000,100000,100000,100000,100000,100000,100000,100000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A478,'Updated Quanities'!F:I,4,0),R478)=\"\",R478,IFERROR(VLOOKUP('AUP Library'!A478,'Updated Quanities'!F:I,4,0),R478))","v":100000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A478,'Updated Quanities'!F:I,5,0),R478)=\"\",R478,IFERROR(VLOOKUP('AUP Library'!A478,'Updated Quanities'!F:I,5,0),R478))","v":100000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A478,'Updated Quanities'!F:I,6,0),R478)=\"\",R478,IFERROR(VLOOKUP('AUP Library'!A478,'Updated Quanities'!F:I,6,0),R478))","v":100000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A478,'Updated Quanities'!F:I,7,0),R478)=\"\",R478,IFERROR(VLOOKUP('AUP Library'!A478,'Updated Quanities'!F:I,7,0),R478))","v":100000},100000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A478,'Updated Quanities'!F:G,4,0),R478)","v":100000}]
["204-06.01","Flowable Fill (General)","CY",250,250,250,250,250,250,250,250,250,250,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A479,'Updated Quanities'!F:I,4,0),R479)=\"\",R479,IFERROR(VLOOKUP('AUP Library'!A479,'Updated Quanities'!F:I,4,0),R479))","v":250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A479,'Updated Quanities'!F:I,5,0),R479)=\"\",R479,IFERROR(VLOOKUP('AUP Library'!A479,'Updated Quanities'!F:I,5,0),R479))","v":250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A479,'Updated Quanities'!F:I,6,0),R479)=\"\",R479,IFERROR(VLOOKUP('AUP Library'!A479,'Updated Quanities'!F:I,6,0),R479))","v":250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A479,'Updated Quanities'!F:I,7,0),R479)=\"\",R479,IFERROR(VLOOKUP('AUP Library'!A479,'Updated Quanities'!F:I,7,0),R479))","v":250},250,{"$f":"IFERROR(VLOOKUP('AUP Library'!A479,'Updated Quanities'!F:G,4,0),R479)","v":250}]
["204-08","Foundation Fill Material","CY",46.69,46.69,46.69,46.69,46.69,46.69,46.69,46.69,46.69,46.69,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A480,'Updated Quanities'!F:I,4,0),R480)=\"\",R480,IFERROR(VLOOKUP('AUP Library'!A480,'Updated Quanities'!F:I,4,0),R480))","v":46.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A480,'Updated Quanities'!F:I,5,0),R480)=\"\",R480,IFERROR(VLOOKUP('AUP Library'!A480,'Updated Quanities'!F:I,5,0),R480))","v":46.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A480,'Updated Quanities'!F:I,6,0),R480)=\"\",R480,IFERROR(VLOOKUP('AUP Library'!A480,'Updated Quanities'!F:I,6,0),R480))","v":46.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A480,'Updated Quanities'!F:I,7,0),R480)=\"\",R480,IFERROR(VLOOKUP('AUP Library'!A480,'Updated Quanities'!F:I,7,0),R480))","v":46.69},46.69,{"$f":"IFERROR(VLOOKUP('AUP Library'!A480,'Updated Quanities'!F:G,4,0),R480)","v":46.69}]
["204-08.01","Backfill Material (Flowable Fill)","CY",195.51,195.51,195.51,195.51,195.51,195.51,195.51,195.51,195.51,195.51,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A481,'Updated Quanities'!F:I,4,0),R481)=\"\",R481,IFERROR(VLOOKUP('AUP Library'!A481,'Updated Quanities'!F:I,4,0),R481))","v":195.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A481,'Updated Quanities'!F:I,5,0),R481)=\"\",R481,IFERROR(VLOOKUP('AUP Library'!A481,'Updated Quanities'!F:I,5,0),R481))","v":195.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A481,'Updated Quanities'!F:I,6,0),R481)=\"\",R481,IFERROR(VLOOKUP('AUP Library'!A481,'Updated Quanities'!F:I,6,0),R481))","v":195.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A481,'Updated Quanities'!F:I,7,0),R481)=\"\",R481,IFERROR(VLOOKUP('AUP Library'!A481,'Updated Quanities'!F:I,7,0),R481))","v":195.51},195.51,{"$f":"IFERROR(VLOOKUP('AUP Library'!A481,'Updated Quanities'!F:G,4,0),R481)","v":195.51}]
["204-09.01","Cofferdam","LS",83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A482,'Updated Quanities'!F:I,4,0),R482)=\"\",R482,IFERROR(VLOOKUP('AUP Library'!A482,'Updated Quanities'!F:I,4,0),R482))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A482,'Updated Quanities'!F:I,5,0),R482)=\"\",R482,IFERROR(VLOOKUP('AUP Library'!A482,'Updated Quanities'!F:I,5,0),R482))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A482,'Updated Quanities'!F:I,6,0),R482)=\"\",R482,IFERROR(VLOOKUP('AUP Library'!A482,'Updated Quanities'!F:I,6,0),R482))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A482,'Updated Quanities'!F:I,7,0),R482)=\"\",R482,IFERROR(VLOOKUP('AUP Library'!A482,'Updated Quanities'!F:I,7,0),R482))","v":83375.600000000006},83375.600000000006,{"$f":"IFERROR(VLOOKUP('AUP Library'!A482,'Updated Quanities'!F:G,4,0),R482)","v":83375.600000000006}]
["204-09.02","Cofferdam","LS",83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A483,'Updated Quanities'!F:I,4,0),R483)=\"\",R483,IFERROR(VLOOKUP('AUP Library'!A483,'Updated Quanities'!F:I,4,0),R483))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A483,'Updated Quanities'!F:I,5,0),R483)=\"\",R483,IFERROR(VLOOKUP('AUP Library'!A483,'Updated Quanities'!F:I,5,0),R483))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A483,'Updated Quanities'!F:I,6,0),R483)=\"\",R483,IFERROR(VLOOKUP('AUP Library'!A483,'Updated Quanities'!F:I,6,0),R483))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A483,'Updated Quanities'!F:I,7,0),R483)=\"\",R483,IFERROR(VLOOKUP('AUP Library'!A483,'Updated Quanities'!F:I,7,0),R483))","v":83375.600000000006},83375.600000000006,{"$f":"IFERROR(VLOOKUP('AUP Library'!A483,'Updated Quanities'!F:G,4,0),R483)","v":83375.600000000006}]
["204-09.03","Cofferdam","LS",83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A484,'Updated Quanities'!F:I,4,0),R484)=\"\",R484,IFERROR(VLOOKUP('AUP Library'!A484,'Updated Quanities'!F:I,4,0),R484))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A484,'Updated Quanities'!F:I,5,0),R484)=\"\",R484,IFERROR(VLOOKUP('AUP Library'!A484,'Updated Quanities'!F:I,5,0),R484))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A484,'Updated Quanities'!F:I,6,0),R484)=\"\",R484,IFERROR(VLOOKUP('AUP Library'!A484,'Updated Quanities'!F:I,6,0),R484))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A484,'Updated Quanities'!F:I,7,0),R484)=\"\",R484,IFERROR(VLOOKUP('AUP Library'!A484,'Updated Quanities'!F:I,7,0),R484))","v":83375.600000000006},83375.600000000006,{"$f":"IFERROR(VLOOKUP('AUP Library'!A484,'Updated Quanities'!F:G,4,0),R484)","v":83375.600000000006}]
["204-09.04","Cofferdam","LS",83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A485,'Updated Quanities'!F:I,4,0),R485)=\"\",R485,IFERROR(VLOOKUP('AUP Library'!A485,'Updated Quanities'!F:I,4,0),R485))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A485,'Updated Quanities'!F:I,5,0),R485)=\"\",R485,IFERROR(VLOOKUP('AUP Library'!A485,'Updated Quanities'!F:I,5,0),R485))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A485,'Updated Quanities'!F:I,6,0),R485)=\"\",R485,IFERROR(VLOOKUP('AUP Library'!A485,'Updated Quanities'!F:I,6,0),R485))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A485,'Updated Quanities'!F:I,7,0),R485)=\"\",R485,IFERROR(VLOOKUP('AUP Library'!A485,'Updated Quanities'!F:I,7,0),R485))","v":83375.600000000006},83375.600000000006,{"$f":"IFERROR(VLOOKUP('AUP Library'!A485,'Updated Quanities'!F:G,4,0),R485)","v":83375.600000000006}]
["204-09.05","Cofferdam","LS",83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A486,'Updated Quanities'!F:I,4,0),R486)=\"\",R486,IFERROR(VLOOKUP('AUP Library'!A486,'Updated Quanities'!F:I,4,0),R486))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A486,'Updated Quanities'!F:I,5,0),R486)=\"\",R486,IFERROR(VLOOKUP('AUP Library'!A486,'Updated Quanities'!F:I,5,0),R486))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A486,'Updated Quanities'!F:I,6,0),R486)=\"\",R486,IFERROR(VLOOKUP('AUP Library'!A486,'Updated Quanities'!F:I,6,0),R486))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A486,'Updated Quanities'!F:I,7,0),R486)=\"\",R486,IFERROR(VLOOKUP('AUP Library'!A486,'Updated Quanities'!F:I,7,0),R486))","v":83375.600000000006},83375.600000000006,{"$f":"IFERROR(VLOOKUP('AUP Library'!A486,'Updated Quanities'!F:G,4,0),R486)","v":83375.600000000006}]
["204-09.06","Cofferdam","LS",83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,83375.600000000006,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A487,'Updated Quanities'!F:I,4,0),R487)=\"\",R487,IFERROR(VLOOKUP('AUP Library'!A487,'Updated Quanities'!F:I,4,0),R487))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A487,'Updated Quanities'!F:I,5,0),R487)=\"\",R487,IFERROR(VLOOKUP('AUP Library'!A487,'Updated Quanities'!F:I,5,0),R487))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A487,'Updated Quanities'!F:I,6,0),R487)=\"\",R487,IFERROR(VLOOKUP('AUP Library'!A487,'Updated Quanities'!F:I,6,0),R487))","v":83375.600000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A487,'Updated Quanities'!F:I,7,0),R487)=\"\",R487,IFERROR(VLOOKUP('AUP Library'!A487,'Updated Quanities'!F:I,7,0),R487))","v":83375.600000000006},83375.600000000006,{"$f":"IFERROR(VLOOKUP('AUP Library'!A487,'Updated Quanities'!F:G,4,0),R487)","v":83375.600000000006}]
["204-10.01","Foundation Prepartation","LS",30333.33,30333.33,30333.33,30333.33,30333.33,30333.33,30333.33,30333.33,30333.33,30333.33,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A488,'Updated Quanities'!F:I,4,0),R488)=\"\",R488,IFERROR(VLOOKUP('AUP Library'!A488,'Updated Quanities'!F:I,4,0),R488))","v":30333.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A488,'Updated Quanities'!F:I,5,0),R488)=\"\",R488,IFERROR(VLOOKUP('AUP Library'!A488,'Updated Quanities'!F:I,5,0),R488))","v":30333.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A488,'Updated Quanities'!F:I,6,0),R488)=\"\",R488,IFERROR(VLOOKUP('AUP Library'!A488,'Updated Quanities'!F:I,6,0),R488))","v":30333.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A488,'Updated Quanities'!F:I,7,0),R488)=\"\",R488,IFERROR(VLOOKUP('AUP Library'!A488,'Updated Quanities'!F:I,7,0),R488))","v":30333.33},30333.33,{"$f":"IFERROR(VLOOKUP('AUP Library'!A488,'Updated Quanities'!F:G,4,0),R488)","v":30333.33}]
["204-10.02","Foundation Prepartation","LS",30333,30333,30333,30333,30333,30333,30333,30333,30333,30333,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A489,'Updated Quanities'!F:I,4,0),R489)=\"\",R489,IFERROR(VLOOKUP('AUP Library'!A489,'Updated Quanities'!F:I,4,0),R489))","v":30333},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A489,'Updated Quanities'!F:I,5,0),R489)=\"\",R489,IFERROR(VLOOKUP('AUP Library'!A489,'Updated Quanities'!F:I,5,0),R489))","v":30333},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A489,'Updated Quanities'!F:I,6,0),R489)=\"\",R489,IFERROR(VLOOKUP('AUP Library'!A489,'Updated Quanities'!F:I,6,0),R489))","v":30333},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A489,'Updated Quanities'!F:I,7,0),R489)=\"\",R489,IFERROR(VLOOKUP('AUP Library'!A489,'Updated Quanities'!F:I,7,0),R489))","v":30333},30333,{"$f":"IFERROR(VLOOKUP('AUP Library'!A489,'Updated Quanities'!F:G,4,0),R489)","v":30333}]
["204-10.03","Foundation Prepartation","LS",27000,27000,27000,27000,27000,27000,27000,27000,27000,27000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A490,'Updated Quanities'!F:I,4,0),R490)=\"\",R490,IFERROR(VLOOKUP('AUP Library'!A490,'Updated Quanities'!F:I,4,0),R490))","v":27000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A490,'Updated Quanities'!F:I,5,0),R490)=\"\",R490,IFERROR(VLOOKUP('AUP Library'!A490,'Updated Quanities'!F:I,5,0),R490))","v":27000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A490,'Updated Quanities'!F:I,6,0),R490)=\"\",R490,IFERROR(VLOOKUP('AUP Library'!A490,'Updated Quanities'!F:I,6,0),R490))","v":27000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A490,'Updated Quanities'!F:I,7,0),R490)=\"\",R490,IFERROR(VLOOKUP('AUP Library'!A490,'Updated Quanities'!F:I,7,0),R490))","v":27000},27000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A490,'Updated Quanities'!F:G,4,0),R490)","v":27000}]
["204-10.04","Foundation Prepartation","LS",33000,33000,33000,33000,33000,33000,33000,33000,33000,33000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A491,'Updated Quanities'!F:I,4,0),R491)=\"\",R491,IFERROR(VLOOKUP('AUP Library'!A491,'Updated Quanities'!F:I,4,0),R491))","v":33000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A491,'Updated Quanities'!F:I,5,0),R491)=\"\",R491,IFERROR(VLOOKUP('AUP Library'!A491,'Updated Quanities'!F:I,5,0),R491))","v":33000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A491,'Updated Quanities'!F:I,6,0),R491)=\"\",R491,IFERROR(VLOOKUP('AUP Library'!A491,'Updated Quanities'!F:I,6,0),R491))","v":33000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A491,'Updated Quanities'!F:I,7,0),R491)=\"\",R491,IFERROR(VLOOKUP('AUP Library'!A491,'Updated Quanities'!F:I,7,0),R491))","v":33000},33000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A491,'Updated Quanities'!F:G,4,0),R491)","v":33000}]
["204-10.05","Foundation Prepartation","LS",40000,40000,40000,40000,40000,40000,40000,40000,40000,40000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A492,'Updated Quanities'!F:I,4,0),R492)=\"\",R492,IFERROR(VLOOKUP('AUP Library'!A492,'Updated Quanities'!F:I,4,0),R492))","v":40000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A492,'Updated Quanities'!F:I,5,0),R492)=\"\",R492,IFERROR(VLOOKUP('AUP Library'!A492,'Updated Quanities'!F:I,5,0),R492))","v":40000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A492,'Updated Quanities'!F:I,6,0),R492)=\"\",R492,IFERROR(VLOOKUP('AUP Library'!A492,'Updated Quanities'!F:I,6,0),R492))","v":40000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A492,'Updated Quanities'!F:I,7,0),R492)=\"\",R492,IFERROR(VLOOKUP('AUP Library'!A492,'Updated Quanities'!F:I,7,0),R492))","v":40000},40000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A492,'Updated Quanities'!F:G,4,0),R492)","v":40000}]
["204-10.06","Foundation Prepartation","LS",40000,40000,40000,40000,40000,40000,40000,40000,40000,40000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A493,'Updated Quanities'!F:I,4,0),R493)=\"\",R493,IFERROR(VLOOKUP('AUP Library'!A493,'Updated Quanities'!F:I,4,0),R493))","v":40000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A493,'Updated Quanities'!F:I,5,0),R493)=\"\",R493,IFERROR(VLOOKUP('AUP Library'!A493,'Updated Quanities'!F:I,5,0),R493))","v":40000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A493,'Updated Quanities'!F:I,6,0),R493)=\"\",R493,IFERROR(VLOOKUP('AUP Library'!A493,'Updated Quanities'!F:I,6,0),R493))","v":40000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A493,'Updated Quanities'!F:I,7,0),R493)=\"\",R493,IFERROR(VLOOKUP('AUP Library'!A493,'Updated Quanities'!F:I,7,0),R493))","v":40000},40000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A493,'Updated Quanities'!F:G,4,0),R493)","v":40000}]
["204-10.07","Foundation Prepartation","LS",40000,40000,40000,40000,40000,40000,40000,40000,40000,40000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A494,'Updated Quanities'!F:I,4,0),R494)=\"\",R494,IFERROR(VLOOKUP('AUP Library'!A494,'Updated Quanities'!F:I,4,0),R494))","v":40000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A494,'Updated Quanities'!F:I,5,0),R494)=\"\",R494,IFERROR(VLOOKUP('AUP Library'!A494,'Updated Quanities'!F:I,5,0),R494))","v":40000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A494,'Updated Quanities'!F:I,6,0),R494)=\"\",R494,IFERROR(VLOOKUP('AUP Library'!A494,'Updated Quanities'!F:I,6,0),R494))","v":40000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A494,'Updated Quanities'!F:I,7,0),R494)=\"\",R494,IFERROR(VLOOKUP('AUP Library'!A494,'Updated Quanities'!F:I,7,0),R494))","v":40000},40000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A494,'Updated Quanities'!F:G,4,0),R494)","v":40000}]
["204-10.08","Foundation Prepartation","LS",40000,40000,40000,40000,40000,40000,40000,40000,40000,40000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A495,'Updated Quanities'!F:I,4,0),R495)=\"\",R495,IFERROR(VLOOKUP('AUP Library'!A495,'Updated Quanities'!F:I,4,0),R495))","v":40000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A495,'Updated Quanities'!F:I,5,0),R495)=\"\",R495,IFERROR(VLOOKUP('AUP Library'!A495,'Updated Quanities'!F:I,5,0),R495))","v":40000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A495,'Updated Quanities'!F:I,6,0),R495)=\"\",R495,IFERROR(VLOOKUP('AUP Library'!A495,'Updated Quanities'!F:I,6,0),R495))","v":40000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A495,'Updated Quanities'!F:I,7,0),R495)=\"\",R495,IFERROR(VLOOKUP('AUP Library'!A495,'Updated Quanities'!F:I,7,0),R495))","v":40000},40000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A495,'Updated Quanities'!F:G,4,0),R495)","v":40000}]
["204-11","Bridge Excavation (Unclassified)","CY",50.02,50.02,50.02,50.02,50.02,50.02,50.02,50.02,50.02,50.02,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A496,'Updated Quanities'!F:I,4,0),R496)=\"\",R496,IFERROR(VLOOKUP('AUP Library'!A496,'Updated Quanities'!F:I,4,0),R496))","v":50.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A496,'Updated Quanities'!F:I,5,0),R496)=\"\",R496,IFERROR(VLOOKUP('AUP Library'!A496,'Updated Quanities'!F:I,5,0),R496))","v":50.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A496,'Updated Quanities'!F:I,6,0),R496)=\"\",R496,IFERROR(VLOOKUP('AUP Library'!A496,'Updated Quanities'!F:I,6,0),R496))","v":50.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A496,'Updated Quanities'!F:I,7,0),R496)=\"\",R496,IFERROR(VLOOKUP('AUP Library'!A496,'Updated Quanities'!F:I,7,0),R496))","v":50.02},50.02,{"$f":"IFERROR(VLOOKUP('AUP Library'!A496,'Updated Quanities'!F:G,4,0),R496)","v":50.02}]
["204-12","Core Drilling (Concrete Seal)","LF",151.12,151.12,151.12,151.12,151.12,151.12,151.12,151.12,151.12,151.12,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A497,'Updated Quanities'!F:I,4,0),R497)=\"\",R497,IFERROR(VLOOKUP('AUP Library'!A497,'Updated Quanities'!F:I,4,0),R497))","v":151.12},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A497,'Updated Quanities'!F:I,5,0),R497)=\"\",R497,IFERROR(VLOOKUP('AUP Library'!A497,'Updated Quanities'!F:I,5,0),R497))","v":151.12},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A497,'Updated Quanities'!F:I,6,0),R497)=\"\",R497,IFERROR(VLOOKUP('AUP Library'!A497,'Updated Quanities'!F:I,6,0),R497))","v":151.12},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A497,'Updated Quanities'!F:I,7,0),R497)=\"\",R497,IFERROR(VLOOKUP('AUP Library'!A497,'Updated Quanities'!F:I,7,0),R497))","v":151.12},151.12,{"$f":"IFERROR(VLOOKUP('AUP Library'!A497,'Updated Quanities'!F:G,4,0),R497)","v":151.12}]
["204-14","Core Drilling afor Piles (Rock)","LF",101.29,101.29,101.29,101.29,101.29,101.29,101.29,101.29,101.29,101.29,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A498,'Updated Quanities'!F:I,4,0),R498)=\"\",R498,IFERROR(VLOOKUP('AUP Library'!A498,'Updated Quanities'!F:I,4,0),R498))","v":101.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A498,'Updated Quanities'!F:I,5,0),R498)=\"\",R498,IFERROR(VLOOKUP('AUP Library'!A498,'Updated Quanities'!F:I,5,0),R498))","v":101.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A498,'Updated Quanities'!F:I,6,0),R498)=\"\",R498,IFERROR(VLOOKUP('AUP Library'!A498,'Updated Quanities'!F:I,6,0),R498))","v":101.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A498,'Updated Quanities'!F:I,7,0),R498)=\"\",R498,IFERROR(VLOOKUP('AUP Library'!A498,'Updated Quanities'!F:I,7,0),R498))","v":101.29},101.29,{"$f":"IFERROR(VLOOKUP('AUP Library'!A498,'Updated Quanities'!F:G,4,0),R498)","v":101.29}]
["204-15","Core Drilling for Piles (Soil)","LF",57.28,57.28,57.28,57.28,57.28,57.28,57.28,57.28,57.28,57.28,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A499,'Updated Quanities'!F:I,4,0),R499)=\"\",R499,IFERROR(VLOOKUP('AUP Library'!A499,'Updated Quanities'!F:I,4,0),R499))","v":57.28},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A499,'Updated Quanities'!F:I,5,0),R499)=\"\",R499,IFERROR(VLOOKUP('AUP Library'!A499,'Updated Quanities'!F:I,5,0),R499))","v":57.28},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A499,'Updated Quanities'!F:I,6,0),R499)=\"\",R499,IFERROR(VLOOKUP('AUP Library'!A499,'Updated Quanities'!F:I,6,0),R499))","v":57.28},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A499,'Updated Quanities'!F:I,7,0),R499)=\"\",R499,IFERROR(VLOOKUP('AUP Library'!A499,'Updated Quanities'!F:I,7,0),R499))","v":57.28},57.28,{"$f":"IFERROR(VLOOKUP('AUP Library'!A499,'Updated Quanities'!F:G,4,0),R499)","v":57.28}]
["207-01.01","Subgrade Construction and Preparation","STA",145.87,145.87,145.87,145.87,145.87,145.87,145.87,145.87,145.87,145.87,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A500,'Updated Quanities'!F:I,4,0),R500)=\"\",R500,IFERROR(VLOOKUP('AUP Library'!A500,'Updated Quanities'!F:I,4,0),R500))","v":145.87},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A500,'Updated Quanities'!F:I,5,0),R500)=\"\",R500,IFERROR(VLOOKUP('AUP Library'!A500,'Updated Quanities'!F:I,5,0),R500))","v":145.87},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A500,'Updated Quanities'!F:I,6,0),R500)=\"\",R500,IFERROR(VLOOKUP('AUP Library'!A500,'Updated Quanities'!F:I,6,0),R500))","v":145.87},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A500,'Updated Quanities'!F:I,7,0),R500)=\"\",R500,IFERROR(VLOOKUP('AUP Library'!A500,'Updated Quanities'!F:I,7,0),R500))","v":145.87},145.87,{"$f":"IFERROR(VLOOKUP('AUP Library'!A500,'Updated Quanities'!F:G,4,0),R500)","v":145.87}]
["208-01","Shoulders and Ditches","LM",592.66,592.66,592.66,592.66,592.66,592.66,592.66,592.66,592.66,592.66,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A501,'Updated Quanities'!F:I,4,0),R501)=\"\",R501,IFERROR(VLOOKUP('AUP Library'!A501,'Updated Quanities'!F:I,4,0),R501))","v":592.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A501,'Updated Quanities'!F:I,5,0),R501)=\"\",R501,IFERROR(VLOOKUP('AUP Library'!A501,'Updated Quanities'!F:I,5,0),R501))","v":592.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A501,'Updated Quanities'!F:I,6,0),R501)=\"\",R501,IFERROR(VLOOKUP('AUP Library'!A501,'Updated Quanities'!F:I,6,0),R501))","v":592.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A501,'Updated Quanities'!F:I,7,0),R501)=\"\",R501,IFERROR(VLOOKUP('AUP Library'!A501,'Updated Quanities'!F:I,7,0),R501))","v":592.66},592.66,{"$f":"IFERROR(VLOOKUP('AUP Library'!A501,'Updated Quanities'!F:G,4,0),R501)","v":592.66}]
["208-01.01","Ditches","LF",25,25,25,25,25,25,25,25,25,25,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A502,'Updated Quanities'!F:I,4,0),R502)=\"\",R502,IFERROR(VLOOKUP('AUP Library'!A502,'Updated Quanities'!F:I,4,0),R502))","v":25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A502,'Updated Quanities'!F:I,5,0),R502)=\"\",R502,IFERROR(VLOOKUP('AUP Library'!A502,'Updated Quanities'!F:I,5,0),R502))","v":25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A502,'Updated Quanities'!F:I,6,0),R502)=\"\",R502,IFERROR(VLOOKUP('AUP Library'!A502,'Updated Quanities'!F:I,6,0),R502))","v":25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A502,'Updated Quanities'!F:I,7,0),R502)=\"\",R502,IFERROR(VLOOKUP('AUP Library'!A502,'Updated Quanities'!F:I,7,0),R502))","v":25},25,{"$f":"IFERROR(VLOOKUP('AUP Library'!A502,'Updated Quanities'!F:G,4,0),R502)","v":25}]
["208-01.02","Shoulder Preparation","LM",984,984,984,984,984,984,984,984,984,984,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A503,'Updated Quanities'!F:I,4,0),R503)=\"\",R503,IFERROR(VLOOKUP('AUP Library'!A503,'Updated Quanities'!F:I,4,0),R503))","v":984},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A503,'Updated Quanities'!F:I,5,0),R503)=\"\",R503,IFERROR(VLOOKUP('AUP Library'!A503,'Updated Quanities'!F:I,5,0),R503))","v":984},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A503,'Updated Quanities'!F:I,6,0),R503)=\"\",R503,IFERROR(VLOOKUP('AUP Library'!A503,'Updated Quanities'!F:I,6,0),R503))","v":984},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A503,'Updated Quanities'!F:I,7,0),R503)=\"\",R503,IFERROR(VLOOKUP('AUP Library'!A503,'Updated Quanities'!F:I,7,0),R503))","v":984},984,{"$f":"IFERROR(VLOOKUP('AUP Library'!A503,'Updated Quanities'!F:G,4,0),R503)","v":984}]
["209-65.20","Sequencing for Const in the Dry (Desc)","LS",10009.93,10009.93,10009.93,10009.93,10009.93,10009.93,10009.93,10009.93,10009.93,10009.93,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A504,'Updated Quanities'!F:I,4,0),R504)=\"\",R504,IFERROR(VLOOKUP('AUP Library'!A504,'Updated Quanities'!F:I,4,0),R504))","v":10009.93},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A504,'Updated Quanities'!F:I,5,0),R504)=\"\",R504,IFERROR(VLOOKUP('AUP Library'!A504,'Updated Quanities'!F:I,5,0),R504))","v":10009.93},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A504,'Updated Quanities'!F:I,6,0),R504)=\"\",R504,IFERROR(VLOOKUP('AUP Library'!A504,'Updated Quanities'!F:I,6,0),R504))","v":10009.93},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A504,'Updated Quanities'!F:I,7,0),R504)=\"\",R504,IFERROR(VLOOKUP('AUP Library'!A504,'Updated Quanities'!F:I,7,0),R504))","v":10009.93},10009.93,{"$f":"IFERROR(VLOOKUP('AUP Library'!A504,'Updated Quanities'!F:G,4,0),R504)","v":10009.93}]
["209-65.21","Sequencing for Const in the Dry (Desc)","LS",7773.12,7773.12,7773.12,7773.12,7773.12,7773.12,7773.12,7773.12,7773.12,7773.12,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A505,'Updated Quanities'!F:I,4,0),R505)=\"\",R505,IFERROR(VLOOKUP('AUP Library'!A505,'Updated Quanities'!F:I,4,0),R505))","v":7773.12},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A505,'Updated Quanities'!F:I,5,0),R505)=\"\",R505,IFERROR(VLOOKUP('AUP Library'!A505,'Updated Quanities'!F:I,5,0),R505))","v":7773.12},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A505,'Updated Quanities'!F:I,6,0),R505)=\"\",R505,IFERROR(VLOOKUP('AUP Library'!A505,'Updated Quanities'!F:I,6,0),R505))","v":7773.12},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A505,'Updated Quanities'!F:I,7,0),R505)=\"\",R505,IFERROR(VLOOKUP('AUP Library'!A505,'Updated Quanities'!F:I,7,0),R505))","v":7773.12},7773.12,{"$f":"IFERROR(VLOOKUP('AUP Library'!A505,'Updated Quanities'!F:G,4,0),R505)","v":7773.12}]
["209-65.22","Sequencing for Const in the Dry (Desc)","LS",6687.99,6687.99,6687.99,6687.99,6687.99,6687.99,6687.99,6687.99,6687.99,6687.99,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A506,'Updated Quanities'!F:I,4,0),R506)=\"\",R506,IFERROR(VLOOKUP('AUP Library'!A506,'Updated Quanities'!F:I,4,0),R506))","v":6687.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A506,'Updated Quanities'!F:I,5,0),R506)=\"\",R506,IFERROR(VLOOKUP('AUP Library'!A506,'Updated Quanities'!F:I,5,0),R506))","v":6687.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A506,'Updated Quanities'!F:I,6,0),R506)=\"\",R506,IFERROR(VLOOKUP('AUP Library'!A506,'Updated Quanities'!F:I,6,0),R506))","v":6687.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A506,'Updated Quanities'!F:I,7,0),R506)=\"\",R506,IFERROR(VLOOKUP('AUP Library'!A506,'Updated Quanities'!F:I,7,0),R506))","v":6687.99},6687.99,{"$f":"IFERROR(VLOOKUP('AUP Library'!A506,'Updated Quanities'!F:G,4,0),R506)","v":6687.99}]
["209-65.23","Sequencing for Const in the Dry (Desc)","LS",4240.1099999999997,4240.1099999999997,4240.1099999999997,4240.1099999999997,4240.1099999999997,4240.1099999999997,4240.1099999999997,4240.1099999999997,4240.1099999999997,4240.1099999999997,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A507,'Updated Quanities'!F:I,4,0),R507)=\"\",R507,IFERROR(VLOOKUP('AUP Library'!A507,'Updated Quanities'!F:I,4,0),R507))","v":4240.1099999999997},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A507,'Updated Quanities'!F:I,5,0),R507)=\"\",R507,IFERROR(VLOOKUP('AUP Library'!A507,'Updated Quanities'!F:I,5,0),R507))","v":4240.1099999999997},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A507,'Updated Quanities'!F:I,6,0),R507)=\"\",R507,IFERROR(VLOOKUP('AUP Library'!A507,'Updated Quanities'!F:I,6,0),R507))","v":4240.1099999999997},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A507,'Updated Quanities'!F:I,7,0),R507)=\"\",R507,IFERROR(VLOOKUP('AUP Library'!A507,'Updated Quanities'!F:I,7,0),R507))","v":4240.1099999999997},4240.1099999999997,{"$f":"IFERROR(VLOOKUP('AUP Library'!A507,'Updated Quanities'!F:G,4,0),R507)","v":4240.1099999999997}]
["303-01.01","Granular Backfill (Roadway)","TON",16.86,16.86,16.86,16.86,16.86,16.86,16.86,16.86,16.86,16.86,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A508,'Updated Quanities'!F:I,4,0),R508)=\"\",R508,IFERROR(VLOOKUP('AUP Library'!A508,'Updated Quanities'!F:I,4,0),R508))","v":16.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A508,'Updated Quanities'!F:I,5,0),R508)=\"\",R508,IFERROR(VLOOKUP('AUP Library'!A508,'Updated Quanities'!F:I,5,0),R508))","v":16.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A508,'Updated Quanities'!F:I,6,0),R508)=\"\",R508,IFERROR(VLOOKUP('AUP Library'!A508,'Updated Quanities'!F:I,6,0),R508))","v":16.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A508,'Updated Quanities'!F:I,7,0),R508)=\"\",R508,IFERROR(VLOOKUP('AUP Library'!A508,'Updated Quanities'!F:I,7,0),R508))","v":16.86},16.86,{"$f":"IFERROR(VLOOKUP('AUP Library'!A508,'Updated Quanities'!F:G,4,0),R508)","v":16.86}]
["303-01.02","Granular Backfill (Bridges)","TON",35.68,35.68,35.68,35.68,35.68,35.68,35.68,35.68,35.68,35.68,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A509,'Updated Quanities'!F:I,4,0),R509)=\"\",R509,IFERROR(VLOOKUP('AUP Library'!A509,'Updated Quanities'!F:I,4,0),R509))","v":35.68},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A509,'Updated Quanities'!F:I,5,0),R509)=\"\",R509,IFERROR(VLOOKUP('AUP Library'!A509,'Updated Quanities'!F:I,5,0),R509))","v":35.68},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A509,'Updated Quanities'!F:I,6,0),R509)=\"\",R509,IFERROR(VLOOKUP('AUP Library'!A509,'Updated Quanities'!F:I,6,0),R509))","v":35.68},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A509,'Updated Quanities'!F:I,7,0),R509)=\"\",R509,IFERROR(VLOOKUP('AUP Library'!A509,'Updated Quanities'!F:I,7,0),R509))","v":35.68},35.68,{"$f":"IFERROR(VLOOKUP('AUP Library'!A509,'Updated Quanities'!F:G,4,0),R509)","v":35.68}]
["303-01.03","Granular Backfill (Retaining Walls)","TON",44.98,44.98,44.98,44.98,44.98,44.98,44.98,44.98,44.98,44.98,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A510,'Updated Quanities'!F:I,4,0),R510)=\"\",R510,IFERROR(VLOOKUP('AUP Library'!A510,'Updated Quanities'!F:I,4,0),R510))","v":44.98},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A510,'Updated Quanities'!F:I,5,0),R510)=\"\",R510,IFERROR(VLOOKUP('AUP Library'!A510,'Updated Quanities'!F:I,5,0),R510))","v":44.98},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A510,'Updated Quanities'!F:I,6,0),R510)=\"\",R510,IFERROR(VLOOKUP('AUP Library'!A510,'Updated Quanities'!F:I,6,0),R510))","v":44.98},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A510,'Updated Quanities'!F:I,7,0),R510)=\"\",R510,IFERROR(VLOOKUP('AUP Library'!A510,'Updated Quanities'!F:I,7,0),R510))","v":44.98},44.98,{"$f":"IFERROR(VLOOKUP('AUP Library'!A510,'Updated Quanities'!F:G,4,0),R510)","v":44.98}]
["303-01.08","Mineral Aggr, Ty A Base, Grading D Gravel","TON",35,35,35,35,35,35,35,35,35,35,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A511,'Updated Quanities'!F:I,4,0),R511)=\"\",R511,IFERROR(VLOOKUP('AUP Library'!A511,'Updated Quanities'!F:I,4,0),R511))","v":35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A511,'Updated Quanities'!F:I,5,0),R511)=\"\",R511,IFERROR(VLOOKUP('AUP Library'!A511,'Updated Quanities'!F:I,5,0),R511))","v":35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A511,'Updated Quanities'!F:I,6,0),R511)=\"\",R511,IFERROR(VLOOKUP('AUP Library'!A511,'Updated Quanities'!F:I,6,0),R511))","v":35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A511,'Updated Quanities'!F:I,7,0),R511)=\"\",R511,IFERROR(VLOOKUP('AUP Library'!A511,'Updated Quanities'!F:I,7,0),R511))","v":35},35,{"$f":"IFERROR(VLOOKUP('AUP Library'!A511,'Updated Quanities'!F:G,4,0),R511)","v":35}]
["303-01.09","Mineral Aggregate, Type A Base, Grading D Limestone","TON",21.85,21.85,21.85,21.85,21.85,21.85,21.85,21.85,21.85,21.85,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A512,'Updated Quanities'!F:I,4,0),R512)=\"\",R512,IFERROR(VLOOKUP('AUP Library'!A512,'Updated Quanities'!F:I,4,0),R512))","v":21.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A512,'Updated Quanities'!F:I,5,0),R512)=\"\",R512,IFERROR(VLOOKUP('AUP Library'!A512,'Updated Quanities'!F:I,5,0),R512))","v":21.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A512,'Updated Quanities'!F:I,6,0),R512)=\"\",R512,IFERROR(VLOOKUP('AUP Library'!A512,'Updated Quanities'!F:I,6,0),R512))","v":21.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A512,'Updated Quanities'!F:I,7,0),R512)=\"\",R512,IFERROR(VLOOKUP('AUP Library'!A512,'Updated Quanities'!F:I,7,0),R512))","v":21.85},21.85,{"$f":"IFERROR(VLOOKUP('AUP Library'!A512,'Updated Quanities'!F:G,4,0),R512)","v":21.85}]
["303-02","Mineral Aggr, TY B Base, GR","TON",22.22,22.22,22.22,22.22,22.22,22.22,22.22,22.22,22.22,22.22,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A513,'Updated Quanities'!F:I,4,0),R513)=\"\",R513,IFERROR(VLOOKUP('AUP Library'!A513,'Updated Quanities'!F:I,4,0),R513))","v":22.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A513,'Updated Quanities'!F:I,5,0),R513)=\"\",R513,IFERROR(VLOOKUP('AUP Library'!A513,'Updated Quanities'!F:I,5,0),R513))","v":22.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A513,'Updated Quanities'!F:I,6,0),R513)=\"\",R513,IFERROR(VLOOKUP('AUP Library'!A513,'Updated Quanities'!F:I,6,0),R513))","v":22.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A513,'Updated Quanities'!F:I,7,0),R513)=\"\",R513,IFERROR(VLOOKUP('AUP Library'!A513,'Updated Quanities'!F:I,7,0),R513))","v":22.22},22.22,{"$f":"IFERROR(VLOOKUP('AUP Library'!A513,'Updated Quanities'!F:G,4,0),R513)","v":22.22}]
["303-10.01","Mineral Aggregate (Size 57)","TON",30.59,30.59,30.59,30.59,30.59,30.59,30.59,30.59,30.59,30.59,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A514,'Updated Quanities'!F:I,4,0),R514)=\"\",R514,IFERROR(VLOOKUP('AUP Library'!A514,'Updated Quanities'!F:I,4,0),R514))","v":30.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A514,'Updated Quanities'!F:I,5,0),R514)=\"\",R514,IFERROR(VLOOKUP('AUP Library'!A514,'Updated Quanities'!F:I,5,0),R514))","v":30.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A514,'Updated Quanities'!F:I,6,0),R514)=\"\",R514,IFERROR(VLOOKUP('AUP Library'!A514,'Updated Quanities'!F:I,6,0),R514))","v":30.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A514,'Updated Quanities'!F:I,7,0),R514)=\"\",R514,IFERROR(VLOOKUP('AUP Library'!A514,'Updated Quanities'!F:I,7,0),R514))","v":30.59},30.59,{"$f":"IFERROR(VLOOKUP('AUP Library'!A514,'Updated Quanities'!F:G,4,0),R514)","v":30.59}]
["303-10.02","Mineral Aggregate (Size 2)","TON",20,20,20,20,20,20,20,20,20,20,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A515,'Updated Quanities'!F:I,4,0),R515)=\"\",R515,IFERROR(VLOOKUP('AUP Library'!A515,'Updated Quanities'!F:I,4,0),R515))","v":20},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A515,'Updated Quanities'!F:I,5,0),R515)=\"\",R515,IFERROR(VLOOKUP('AUP Library'!A515,'Updated Quanities'!F:I,5,0),R515))","v":20},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A515,'Updated Quanities'!F:I,6,0),R515)=\"\",R515,IFERROR(VLOOKUP('AUP Library'!A515,'Updated Quanities'!F:I,6,0),R515))","v":20},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A515,'Updated Quanities'!F:I,7,0),R515)=\"\",R515,IFERROR(VLOOKUP('AUP Library'!A515,'Updated Quanities'!F:I,7,0),R515))","v":20},20,{"$f":"IFERROR(VLOOKUP('AUP Library'!A515,'Updated Quanities'!F:G,4,0),R515)","v":20}]
["303-10.03","Mineral Aggregate (Size 68)","TON",47.61,47.61,47.61,47.61,47.61,47.61,47.61,47.61,47.61,47.61,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A516,'Updated Quanities'!F:I,4,0),R516)=\"\",R516,IFERROR(VLOOKUP('AUP Library'!A516,'Updated Quanities'!F:I,4,0),R516))","v":47.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A516,'Updated Quanities'!F:I,5,0),R516)=\"\",R516,IFERROR(VLOOKUP('AUP Library'!A516,'Updated Quanities'!F:I,5,0),R516))","v":47.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A516,'Updated Quanities'!F:I,6,0),R516)=\"\",R516,IFERROR(VLOOKUP('AUP Library'!A516,'Updated Quanities'!F:I,6,0),R516))","v":47.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A516,'Updated Quanities'!F:I,7,0),R516)=\"\",R516,IFERROR(VLOOKUP('AUP Library'!A516,'Updated Quanities'!F:I,7,0),R516))","v":47.61},47.61,{"$f":"IFERROR(VLOOKUP('AUP Library'!A516,'Updated Quanities'!F:G,4,0),R516)","v":47.61}]
["303-10.04","Mineral Aggregate","TON",28.2,28.2,28.2,28.2,28.2,28.2,28.2,28.2,28.2,28.2,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A517,'Updated Quanities'!F:I,4,0),R517)=\"\",R517,IFERROR(VLOOKUP('AUP Library'!A517,'Updated Quanities'!F:I,4,0),R517))","v":28.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A517,'Updated Quanities'!F:I,5,0),R517)=\"\",R517,IFERROR(VLOOKUP('AUP Library'!A517,'Updated Quanities'!F:I,5,0),R517))","v":28.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A517,'Updated Quanities'!F:I,6,0),R517)=\"\",R517,IFERROR(VLOOKUP('AUP Library'!A517,'Updated Quanities'!F:I,6,0),R517))","v":28.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A517,'Updated Quanities'!F:I,7,0),R517)=\"\",R517,IFERROR(VLOOKUP('AUP Library'!A517,'Updated Quanities'!F:I,7,0),R517))","v":28.2},28.2,{"$f":"IFERROR(VLOOKUP('AUP Library'!A517,'Updated Quanities'!F:G,4,0),R517)","v":28.2}]
["303-20.02","River Gravel","TON",30,30,30,30,30,30,30,30,30,30,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A518,'Updated Quanities'!F:I,4,0),R518)=\"\",R518,IFERROR(VLOOKUP('AUP Library'!A518,'Updated Quanities'!F:I,4,0),R518))","v":30},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A518,'Updated Quanities'!F:I,5,0),R518)=\"\",R518,IFERROR(VLOOKUP('AUP Library'!A518,'Updated Quanities'!F:I,5,0),R518))","v":30},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A518,'Updated Quanities'!F:I,6,0),R518)=\"\",R518,IFERROR(VLOOKUP('AUP Library'!A518,'Updated Quanities'!F:I,6,0),R518))","v":30},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A518,'Updated Quanities'!F:I,7,0),R518)=\"\",R518,IFERROR(VLOOKUP('AUP Library'!A518,'Updated Quanities'!F:I,7,0),R518))","v":30},30,{"$f":"IFERROR(VLOOKUP('AUP Library'!A518,'Updated Quanities'!F:G,4,0),R518)","v":30}]
[]
[]
["Structures"]
["202-01","Removal of Structures and Obstructions","LS",13623.35,13623.35,13623.35,13623.35,13623.35,13623.35,13623.35,13623.35,13623.35,13623.35,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A522,'Updated Quanities'!F:I,4,0),R522)=\"\",R522,IFERROR(VLOOKUP('AUP Library'!A522,'Updated Quanities'!F:I,4,0),R522))","v":13623.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A522,'Updated Quanities'!F:I,5,0),R522)=\"\",R522,IFERROR(VLOOKUP('AUP Library'!A522,'Updated Quanities'!F:I,5,0),R522))","v":13623.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A522,'Updated Quanities'!F:I,6,0),R522)=\"\",R522,IFERROR(VLOOKUP('AUP Library'!A522,'Updated Quanities'!F:I,6,0),R522))","v":13623.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A522,'Updated Quanities'!F:I,7,0),R522)=\"\",R522,IFERROR(VLOOKUP('AUP Library'!A522,'Updated Quanities'!F:I,7,0),R522))","v":13623.35},13623.35,{"$f":"IFERROR(VLOOKUP('AUP Library'!A522,'Updated Quanities'!F:G,4,0),R522)","v":13623.35}]
["202-04.01","Removal of Structures","LS",71677.679999999993,71677.679999999993,71677.679999999993,71677.679999999993,71677.679999999993,71677.679999999993,71677.679999999993,71677.679999999993,71677.679999999993,71677.679999999993,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A523,'Updated Quanities'!F:I,4,0),R523)=\"\",R523,IFERROR(VLOOKUP('AUP Library'!A523,'Updated Quanities'!F:I,4,0),R523))","v":71677.679999999993},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A523,'Updated Quanities'!F:I,5,0),R523)=\"\",R523,IFERROR(VLOOKUP('AUP Library'!A523,'Updated Quanities'!F:I,5,0),R523))","v":71677.679999999993},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A523,'Updated Quanities'!F:I,6,0),R523)=\"\",R523,IFERROR(VLOOKUP('AUP Library'!A523,'Updated Quanities'!F:I,6,0),R523))","v":71677.679999999993},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A523,'Updated Quanities'!F:I,7,0),R523)=\"\",R523,IFERROR(VLOOKUP('AUP Library'!A523,'Updated Quanities'!F:I,7,0),R523))","v":71677.679999999993},71677.679999999993,{"$f":"IFERROR(VLOOKUP('AUP Library'!A523,'Updated Quanities'!F:G,4,0),R523)","v":71677.679999999993}]
["202-04.02","Removal of Structures","LS",27942.52,27942.52,27942.52,27942.52,27942.52,27942.52,27942.52,27942.52,27942.52,27942.52,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A524,'Updated Quanities'!F:I,4,0),R524)=\"\",R524,IFERROR(VLOOKUP('AUP Library'!A524,'Updated Quanities'!F:I,4,0),R524))","v":27942.52},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A524,'Updated Quanities'!F:I,5,0),R524)=\"\",R524,IFERROR(VLOOKUP('AUP Library'!A524,'Updated Quanities'!F:I,5,0),R524))","v":27942.52},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A524,'Updated Quanities'!F:I,6,0),R524)=\"\",R524,IFERROR(VLOOKUP('AUP Library'!A524,'Updated Quanities'!F:I,6,0),R524))","v":27942.52},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A524,'Updated Quanities'!F:I,7,0),R524)=\"\",R524,IFERROR(VLOOKUP('AUP Library'!A524,'Updated Quanities'!F:I,7,0),R524))","v":27942.52},27942.52,{"$f":"IFERROR(VLOOKUP('AUP Library'!A524,'Updated Quanities'!F:G,4,0),R524)","v":27942.52}]
["202-04.03","Removal of Structures","LS",7512.5,7512.5,7512.5,7512.5,7512.5,7512.5,7512.5,7512.5,7512.5,7512.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A525,'Updated Quanities'!F:I,4,0),R525)=\"\",R525,IFERROR(VLOOKUP('AUP Library'!A525,'Updated Quanities'!F:I,4,0),R525))","v":7512.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A525,'Updated Quanities'!F:I,5,0),R525)=\"\",R525,IFERROR(VLOOKUP('AUP Library'!A525,'Updated Quanities'!F:I,5,0),R525))","v":7512.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A525,'Updated Quanities'!F:I,6,0),R525)=\"\",R525,IFERROR(VLOOKUP('AUP Library'!A525,'Updated Quanities'!F:I,6,0),R525))","v":7512.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A525,'Updated Quanities'!F:I,7,0),R525)=\"\",R525,IFERROR(VLOOKUP('AUP Library'!A525,'Updated Quanities'!F:I,7,0),R525))","v":7512.5},7512.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A525,'Updated Quanities'!F:G,4,0),R525)","v":7512.5}]
["202-04.04","Removal of Structures","LS",8493.75,8493.75,8493.75,8493.75,8493.75,8493.75,8493.75,8493.75,8493.75,8493.75,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A526,'Updated Quanities'!F:I,4,0),R526)=\"\",R526,IFERROR(VLOOKUP('AUP Library'!A526,'Updated Quanities'!F:I,4,0),R526))","v":8493.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A526,'Updated Quanities'!F:I,5,0),R526)=\"\",R526,IFERROR(VLOOKUP('AUP Library'!A526,'Updated Quanities'!F:I,5,0),R526))","v":8493.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A526,'Updated Quanities'!F:I,6,0),R526)=\"\",R526,IFERROR(VLOOKUP('AUP Library'!A526,'Updated Quanities'!F:I,6,0),R526))","v":8493.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A526,'Updated Quanities'!F:I,7,0),R526)=\"\",R526,IFERROR(VLOOKUP('AUP Library'!A526,'Updated Quanities'!F:I,7,0),R526))","v":8493.75},8493.75,{"$f":"IFERROR(VLOOKUP('AUP Library'!A526,'Updated Quanities'!F:G,4,0),R526)","v":8493.75}]
["202-04.05","Removal of Structures","LS",6500,6500,6500,6500,6500,6500,6500,6500,6500,6500,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A527,'Updated Quanities'!F:I,4,0),R527)=\"\",R527,IFERROR(VLOOKUP('AUP Library'!A527,'Updated Quanities'!F:I,4,0),R527))","v":6500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A527,'Updated Quanities'!F:I,5,0),R527)=\"\",R527,IFERROR(VLOOKUP('AUP Library'!A527,'Updated Quanities'!F:I,5,0),R527))","v":6500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A527,'Updated Quanities'!F:I,6,0),R527)=\"\",R527,IFERROR(VLOOKUP('AUP Library'!A527,'Updated Quanities'!F:I,6,0),R527))","v":6500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A527,'Updated Quanities'!F:I,7,0),R527)=\"\",R527,IFERROR(VLOOKUP('AUP Library'!A527,'Updated Quanities'!F:I,7,0),R527))","v":6500},6500,{"$f":"IFERROR(VLOOKUP('AUP Library'!A527,'Updated Quanities'!F:G,4,0),R527)","v":6500}]
["202-04.06","Removal of Structures","LS",550,550,550,550,550,550,550,550,550,550,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A528,'Updated Quanities'!F:I,4,0),R528)=\"\",R528,IFERROR(VLOOKUP('AUP Library'!A528,'Updated Quanities'!F:I,4,0),R528))","v":550},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A528,'Updated Quanities'!F:I,5,0),R528)=\"\",R528,IFERROR(VLOOKUP('AUP Library'!A528,'Updated Quanities'!F:I,5,0),R528))","v":550},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A528,'Updated Quanities'!F:I,6,0),R528)=\"\",R528,IFERROR(VLOOKUP('AUP Library'!A528,'Updated Quanities'!F:I,6,0),R528))","v":550},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A528,'Updated Quanities'!F:I,7,0),R528)=\"\",R528,IFERROR(VLOOKUP('AUP Library'!A528,'Updated Quanities'!F:I,7,0),R528))","v":550},550,{"$f":"IFERROR(VLOOKUP('AUP Library'!A528,'Updated Quanities'!F:G,4,0),R528)","v":550}]
["202-04.07","Removal of Structures","LS",550,550,550,550,550,550,550,550,550,550,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A529,'Updated Quanities'!F:I,4,0),R529)=\"\",R529,IFERROR(VLOOKUP('AUP Library'!A529,'Updated Quanities'!F:I,4,0),R529))","v":550},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A529,'Updated Quanities'!F:I,5,0),R529)=\"\",R529,IFERROR(VLOOKUP('AUP Library'!A529,'Updated Quanities'!F:I,5,0),R529))","v":550},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A529,'Updated Quanities'!F:I,6,0),R529)=\"\",R529,IFERROR(VLOOKUP('AUP Library'!A529,'Updated Quanities'!F:I,6,0),R529))","v":550},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A529,'Updated Quanities'!F:I,7,0),R529)=\"\",R529,IFERROR(VLOOKUP('AUP Library'!A529,'Updated Quanities'!F:I,7,0),R529))","v":550},550,{"$f":"IFERROR(VLOOKUP('AUP Library'!A529,'Updated Quanities'!F:G,4,0),R529)","v":550}]
["202-04.08","Removal of Structures","LS",1000,1000,1000,1000,1000,1000,1000,1000,1000,1000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A530,'Updated Quanities'!F:I,4,0),R530)=\"\",R530,IFERROR(VLOOKUP('AUP Library'!A530,'Updated Quanities'!F:I,4,0),R530))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A530,'Updated Quanities'!F:I,5,0),R530)=\"\",R530,IFERROR(VLOOKUP('AUP Library'!A530,'Updated Quanities'!F:I,5,0),R530))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A530,'Updated Quanities'!F:I,6,0),R530)=\"\",R530,IFERROR(VLOOKUP('AUP Library'!A530,'Updated Quanities'!F:I,6,0),R530))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A530,'Updated Quanities'!F:I,7,0),R530)=\"\",R530,IFERROR(VLOOKUP('AUP Library'!A530,'Updated Quanities'!F:I,7,0),R530))","v":1000},1000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A530,'Updated Quanities'!F:G,4,0),R530)","v":1000}]
["202-04.09","Removal of Structures","LS",1000,1000,1000,1000,1000,1000,1000,1000,1000,1000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A531,'Updated Quanities'!F:I,4,0),R531)=\"\",R531,IFERROR(VLOOKUP('AUP Library'!A531,'Updated Quanities'!F:I,4,0),R531))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A531,'Updated Quanities'!F:I,5,0),R531)=\"\",R531,IFERROR(VLOOKUP('AUP Library'!A531,'Updated Quanities'!F:I,5,0),R531))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A531,'Updated Quanities'!F:I,6,0),R531)=\"\",R531,IFERROR(VLOOKUP('AUP Library'!A531,'Updated Quanities'!F:I,6,0),R531))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A531,'Updated Quanities'!F:I,7,0),R531)=\"\",R531,IFERROR(VLOOKUP('AUP Library'!A531,'Updated Quanities'!F:I,7,0),R531))","v":1000},1000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A531,'Updated Quanities'!F:G,4,0),R531)","v":1000}]
["202-04.10","Removal of Structures","LS",1000,1000,1000,1000,1000,1000,1000,1000,1000,1000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A532,'Updated Quanities'!F:I,4,0),R532)=\"\",R532,IFERROR(VLOOKUP('AUP Library'!A532,'Updated Quanities'!F:I,4,0),R532))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A532,'Updated Quanities'!F:I,5,0),R532)=\"\",R532,IFERROR(VLOOKUP('AUP Library'!A532,'Updated Quanities'!F:I,5,0),R532))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A532,'Updated Quanities'!F:I,6,0),R532)=\"\",R532,IFERROR(VLOOKUP('AUP Library'!A532,'Updated Quanities'!F:I,6,0),R532))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A532,'Updated Quanities'!F:I,7,0),R532)=\"\",R532,IFERROR(VLOOKUP('AUP Library'!A532,'Updated Quanities'!F:I,7,0),R532))","v":1000},1000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A532,'Updated Quanities'!F:G,4,0),R532)","v":1000}]
["202-04.11","Removal of Structures","LS",1000,1000,1000,1000,1000,1000,1000,1000,1000,1000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A533,'Updated Quanities'!F:I,4,0),R533)=\"\",R533,IFERROR(VLOOKUP('AUP Library'!A533,'Updated Quanities'!F:I,4,0),R533))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A533,'Updated Quanities'!F:I,5,0),R533)=\"\",R533,IFERROR(VLOOKUP('AUP Library'!A533,'Updated Quanities'!F:I,5,0),R533))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A533,'Updated Quanities'!F:I,6,0),R533)=\"\",R533,IFERROR(VLOOKUP('AUP Library'!A533,'Updated Quanities'!F:I,6,0),R533))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A533,'Updated Quanities'!F:I,7,0),R533)=\"\",R533,IFERROR(VLOOKUP('AUP Library'!A533,'Updated Quanities'!F:I,7,0),R533))","v":1000},1000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A533,'Updated Quanities'!F:G,4,0),R533)","v":1000}]
["202-04.12","Removal of Structures","LS",1000,1000,1000,1000,1000,1000,1000,1000,1000,1000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A534,'Updated Quanities'!F:I,4,0),R534)=\"\",R534,IFERROR(VLOOKUP('AUP Library'!A534,'Updated Quanities'!F:I,4,0),R534))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A534,'Updated Quanities'!F:I,5,0),R534)=\"\",R534,IFERROR(VLOOKUP('AUP Library'!A534,'Updated Quanities'!F:I,5,0),R534))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A534,'Updated Quanities'!F:I,6,0),R534)=\"\",R534,IFERROR(VLOOKUP('AUP Library'!A534,'Updated Quanities'!F:I,6,0),R534))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A534,'Updated Quanities'!F:I,7,0),R534)=\"\",R534,IFERROR(VLOOKUP('AUP Library'!A534,'Updated Quanities'!F:I,7,0),R534))","v":1000},1000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A534,'Updated Quanities'!F:G,4,0),R534)","v":1000}]
["202-04.13","Removal of Structures","LS",1000,1000,1000,1000,1000,1000,1000,1000,1000,1000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A535,'Updated Quanities'!F:I,4,0),R535)=\"\",R535,IFERROR(VLOOKUP('AUP Library'!A535,'Updated Quanities'!F:I,4,0),R535))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A535,'Updated Quanities'!F:I,5,0),R535)=\"\",R535,IFERROR(VLOOKUP('AUP Library'!A535,'Updated Quanities'!F:I,5,0),R535))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A535,'Updated Quanities'!F:I,6,0),R535)=\"\",R535,IFERROR(VLOOKUP('AUP Library'!A535,'Updated Quanities'!F:I,6,0),R535))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A535,'Updated Quanities'!F:I,7,0),R535)=\"\",R535,IFERROR(VLOOKUP('AUP Library'!A535,'Updated Quanities'!F:I,7,0),R535))","v":1000},1000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A535,'Updated Quanities'!F:G,4,0),R535)","v":1000}]
["202-04.14","Removal of Structures","LS",1000,1000,1000,1000,1000,1000,1000,1000,1000,1000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A536,'Updated Quanities'!F:I,4,0),R536)=\"\",R536,IFERROR(VLOOKUP('AUP Library'!A536,'Updated Quanities'!F:I,4,0),R536))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A536,'Updated Quanities'!F:I,5,0),R536)=\"\",R536,IFERROR(VLOOKUP('AUP Library'!A536,'Updated Quanities'!F:I,5,0),R536))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A536,'Updated Quanities'!F:I,6,0),R536)=\"\",R536,IFERROR(VLOOKUP('AUP Library'!A536,'Updated Quanities'!F:I,6,0),R536))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A536,'Updated Quanities'!F:I,7,0),R536)=\"\",R536,IFERROR(VLOOKUP('AUP Library'!A536,'Updated Quanities'!F:I,7,0),R536))","v":1000},1000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A536,'Updated Quanities'!F:G,4,0),R536)","v":1000}]
["202-04.15","Removal of Structures","LS",62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A537,'Updated Quanities'!F:I,4,0),R537)=\"\",R537,IFERROR(VLOOKUP('AUP Library'!A537,'Updated Quanities'!F:I,4,0),R537))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A537,'Updated Quanities'!F:I,5,0),R537)=\"\",R537,IFERROR(VLOOKUP('AUP Library'!A537,'Updated Quanities'!F:I,5,0),R537))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A537,'Updated Quanities'!F:I,6,0),R537)=\"\",R537,IFERROR(VLOOKUP('AUP Library'!A537,'Updated Quanities'!F:I,6,0),R537))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A537,'Updated Quanities'!F:I,7,0),R537)=\"\",R537,IFERROR(VLOOKUP('AUP Library'!A537,'Updated Quanities'!F:I,7,0),R537))","v":62.72},62.72,{"$f":"IFERROR(VLOOKUP('AUP Library'!A537,'Updated Quanities'!F:G,4,0),R537)","v":62.72}]
["202-04.16","Removal of Structures","LS",62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A538,'Updated Quanities'!F:I,4,0),R538)=\"\",R538,IFERROR(VLOOKUP('AUP Library'!A538,'Updated Quanities'!F:I,4,0),R538))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A538,'Updated Quanities'!F:I,5,0),R538)=\"\",R538,IFERROR(VLOOKUP('AUP Library'!A538,'Updated Quanities'!F:I,5,0),R538))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A538,'Updated Quanities'!F:I,6,0),R538)=\"\",R538,IFERROR(VLOOKUP('AUP Library'!A538,'Updated Quanities'!F:I,6,0),R538))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A538,'Updated Quanities'!F:I,7,0),R538)=\"\",R538,IFERROR(VLOOKUP('AUP Library'!A538,'Updated Quanities'!F:I,7,0),R538))","v":62.72},62.72,{"$f":"IFERROR(VLOOKUP('AUP Library'!A538,'Updated Quanities'!F:G,4,0),R538)","v":62.72}]
["202-04.17","Removal of Structures","LS",62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A539,'Updated Quanities'!F:I,4,0),R539)=\"\",R539,IFERROR(VLOOKUP('AUP Library'!A539,'Updated Quanities'!F:I,4,0),R539))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A539,'Updated Quanities'!F:I,5,0),R539)=\"\",R539,IFERROR(VLOOKUP('AUP Library'!A539,'Updated Quanities'!F:I,5,0),R539))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A539,'Updated Quanities'!F:I,6,0),R539)=\"\",R539,IFERROR(VLOOKUP('AUP Library'!A539,'Updated Quanities'!F:I,6,0),R539))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A539,'Updated Quanities'!F:I,7,0),R539)=\"\",R539,IFERROR(VLOOKUP('AUP Library'!A539,'Updated Quanities'!F:I,7,0),R539))","v":62.72},62.72,{"$f":"IFERROR(VLOOKUP('AUP Library'!A539,'Updated Quanities'!F:G,4,0),R539)","v":62.72}]
["202-04.18","Removal of Structures","LS",62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A540,'Updated Quanities'!F:I,4,0),R540)=\"\",R540,IFERROR(VLOOKUP('AUP Library'!A540,'Updated Quanities'!F:I,4,0),R540))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A540,'Updated Quanities'!F:I,5,0),R540)=\"\",R540,IFERROR(VLOOKUP('AUP Library'!A540,'Updated Quanities'!F:I,5,0),R540))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A540,'Updated Quanities'!F:I,6,0),R540)=\"\",R540,IFERROR(VLOOKUP('AUP Library'!A540,'Updated Quanities'!F:I,6,0),R540))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A540,'Updated Quanities'!F:I,7,0),R540)=\"\",R540,IFERROR(VLOOKUP('AUP Library'!A540,'Updated Quanities'!F:I,7,0),R540))","v":62.72},62.72,{"$f":"IFERROR(VLOOKUP('AUP Library'!A540,'Updated Quanities'!F:G,4,0),R540)","v":62.72}]
["202-04.19","Removal of Structures","LS",62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A541,'Updated Quanities'!F:I,4,0),R541)=\"\",R541,IFERROR(VLOOKUP('AUP Library'!A541,'Updated Quanities'!F:I,4,0),R541))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A541,'Updated Quanities'!F:I,5,0),R541)=\"\",R541,IFERROR(VLOOKUP('AUP Library'!A541,'Updated Quanities'!F:I,5,0),R541))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A541,'Updated Quanities'!F:I,6,0),R541)=\"\",R541,IFERROR(VLOOKUP('AUP Library'!A541,'Updated Quanities'!F:I,6,0),R541))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A541,'Updated Quanities'!F:I,7,0),R541)=\"\",R541,IFERROR(VLOOKUP('AUP Library'!A541,'Updated Quanities'!F:I,7,0),R541))","v":62.72},62.72,{"$f":"IFERROR(VLOOKUP('AUP Library'!A541,'Updated Quanities'!F:G,4,0),R541)","v":62.72}]
["202-04.21","Removal of Structures","LS",62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A542,'Updated Quanities'!F:I,4,0),R542)=\"\",R542,IFERROR(VLOOKUP('AUP Library'!A542,'Updated Quanities'!F:I,4,0),R542))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A542,'Updated Quanities'!F:I,5,0),R542)=\"\",R542,IFERROR(VLOOKUP('AUP Library'!A542,'Updated Quanities'!F:I,5,0),R542))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A542,'Updated Quanities'!F:I,6,0),R542)=\"\",R542,IFERROR(VLOOKUP('AUP Library'!A542,'Updated Quanities'!F:I,6,0),R542))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A542,'Updated Quanities'!F:I,7,0),R542)=\"\",R542,IFERROR(VLOOKUP('AUP Library'!A542,'Updated Quanities'!F:I,7,0),R542))","v":62.72},62.72,{"$f":"IFERROR(VLOOKUP('AUP Library'!A542,'Updated Quanities'!F:G,4,0),R542)","v":62.72}]
["202-04.22","Removal of Structures","LS",62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,62.72,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A543,'Updated Quanities'!F:I,4,0),R543)=\"\",R543,IFERROR(VLOOKUP('AUP Library'!A543,'Updated Quanities'!F:I,4,0),R543))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A543,'Updated Quanities'!F:I,5,0),R543)=\"\",R543,IFERROR(VLOOKUP('AUP Library'!A543,'Updated Quanities'!F:I,5,0),R543))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A543,'Updated Quanities'!F:I,6,0),R543)=\"\",R543,IFERROR(VLOOKUP('AUP Library'!A543,'Updated Quanities'!F:I,6,0),R543))","v":62.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A543,'Updated Quanities'!F:I,7,0),R543)=\"\",R543,IFERROR(VLOOKUP('AUP Library'!A543,'Updated Quanities'!F:I,7,0),R543))","v":62.72},62.72,{"$f":"IFERROR(VLOOKUP('AUP Library'!A543,'Updated Quanities'!F:G,4,0),R543)","v":62.72}]
["202-04.50","Removal of Structures","LS",12300,12300,12300,12300,12300,12300,12300,12300,12300,12300,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A544,'Updated Quanities'!F:I,4,0),R544)=\"\",R544,IFERROR(VLOOKUP('AUP Library'!A544,'Updated Quanities'!F:I,4,0),R544))","v":12300},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A544,'Updated Quanities'!F:I,5,0),R544)=\"\",R544,IFERROR(VLOOKUP('AUP Library'!A544,'Updated Quanities'!F:I,5,0),R544))","v":12300},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A544,'Updated Quanities'!F:I,6,0),R544)=\"\",R544,IFERROR(VLOOKUP('AUP Library'!A544,'Updated Quanities'!F:I,6,0),R544))","v":12300},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A544,'Updated Quanities'!F:I,7,0),R544)=\"\",R544,IFERROR(VLOOKUP('AUP Library'!A544,'Updated Quanities'!F:I,7,0),R544))","v":12300},12300,{"$f":"IFERROR(VLOOKUP('AUP Library'!A544,'Updated Quanities'!F:G,4,0),R544)","v":12300}]
["202-04.51","Removal of Structures","LS",4251.8500000000004,4251.8500000000004,4251.8500000000004,4251.8500000000004,4251.8500000000004,4251.8500000000004,4251.8500000000004,4251.8500000000004,4251.8500000000004,4251.8500000000004,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A545,'Updated Quanities'!F:I,4,0),R545)=\"\",R545,IFERROR(VLOOKUP('AUP Library'!A545,'Updated Quanities'!F:I,4,0),R545))","v":4251.8500000000004},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A545,'Updated Quanities'!F:I,5,0),R545)=\"\",R545,IFERROR(VLOOKUP('AUP Library'!A545,'Updated Quanities'!F:I,5,0),R545))","v":4251.8500000000004},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A545,'Updated Quanities'!F:I,6,0),R545)=\"\",R545,IFERROR(VLOOKUP('AUP Library'!A545,'Updated Quanities'!F:I,6,0),R545))","v":4251.8500000000004},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A545,'Updated Quanities'!F:I,7,0),R545)=\"\",R545,IFERROR(VLOOKUP('AUP Library'!A545,'Updated Quanities'!F:I,7,0),R545))","v":4251.8500000000004},4251.8500000000004,{"$f":"IFERROR(VLOOKUP('AUP Library'!A545,'Updated Quanities'!F:G,4,0),R545)","v":4251.8500000000004}]
["202-04.52","Removal of Structures","LS",2450,2450,2450,2450,2450,2450,2450,2450,2450,2450,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A546,'Updated Quanities'!F:I,4,0),R546)=\"\",R546,IFERROR(VLOOKUP('AUP Library'!A546,'Updated Quanities'!F:I,4,0),R546))","v":2450},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A546,'Updated Quanities'!F:I,5,0),R546)=\"\",R546,IFERROR(VLOOKUP('AUP Library'!A546,'Updated Quanities'!F:I,5,0),R546))","v":2450},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A546,'Updated Quanities'!F:I,6,0),R546)=\"\",R546,IFERROR(VLOOKUP('AUP Library'!A546,'Updated Quanities'!F:I,6,0),R546))","v":2450},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A546,'Updated Quanities'!F:I,7,0),R546)=\"\",R546,IFERROR(VLOOKUP('AUP Library'!A546,'Updated Quanities'!F:I,7,0),R546))","v":2450},2450,{"$f":"IFERROR(VLOOKUP('AUP Library'!A546,'Updated Quanities'!F:G,4,0),R546)","v":2450}]
["202-04.53","Removal of Structures","LS",1850,1850,1850,1850,1850,1850,1850,1850,1850,1850,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A547,'Updated Quanities'!F:I,4,0),R547)=\"\",R547,IFERROR(VLOOKUP('AUP Library'!A547,'Updated Quanities'!F:I,4,0),R547))","v":1850},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A547,'Updated Quanities'!F:I,5,0),R547)=\"\",R547,IFERROR(VLOOKUP('AUP Library'!A547,'Updated Quanities'!F:I,5,0),R547))","v":1850},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A547,'Updated Quanities'!F:I,6,0),R547)=\"\",R547,IFERROR(VLOOKUP('AUP Library'!A547,'Updated Quanities'!F:I,6,0),R547))","v":1850},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A547,'Updated Quanities'!F:I,7,0),R547)=\"\",R547,IFERROR(VLOOKUP('AUP Library'!A547,'Updated Quanities'!F:I,7,0),R547))","v":1850},1850,{"$f":"IFERROR(VLOOKUP('AUP Library'!A547,'Updated Quanities'!F:G,4,0),R547)","v":1850}]
["202-04.54","Removal of Structures","LS",1200,1200,1200,1200,1200,1200,1200,1200,1200,1200,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A548,'Updated Quanities'!F:I,4,0),R548)=\"\",R548,IFERROR(VLOOKUP('AUP Library'!A548,'Updated Quanities'!F:I,4,0),R548))","v":1200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A548,'Updated Quanities'!F:I,5,0),R548)=\"\",R548,IFERROR(VLOOKUP('AUP Library'!A548,'Updated Quanities'!F:I,5,0),R548))","v":1200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A548,'Updated Quanities'!F:I,6,0),R548)=\"\",R548,IFERROR(VLOOKUP('AUP Library'!A548,'Updated Quanities'!F:I,6,0),R548))","v":1200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A548,'Updated Quanities'!F:I,7,0),R548)=\"\",R548,IFERROR(VLOOKUP('AUP Library'!A548,'Updated Quanities'!F:I,7,0),R548))","v":1200},1200,{"$f":"IFERROR(VLOOKUP('AUP Library'!A548,'Updated Quanities'!F:G,4,0),R548)","v":1200}]
["202-04.55","Removal of Structures","LS",1600,1600,1600,1600,1600,1600,1600,1600,1600,1600,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A549,'Updated Quanities'!F:I,4,0),R549)=\"\",R549,IFERROR(VLOOKUP('AUP Library'!A549,'Updated Quanities'!F:I,4,0),R549))","v":1600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A549,'Updated Quanities'!F:I,5,0),R549)=\"\",R549,IFERROR(VLOOKUP('AUP Library'!A549,'Updated Quanities'!F:I,5,0),R549))","v":1600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A549,'Updated Quanities'!F:I,6,0),R549)=\"\",R549,IFERROR(VLOOKUP('AUP Library'!A549,'Updated Quanities'!F:I,6,0),R549))","v":1600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A549,'Updated Quanities'!F:I,7,0),R549)=\"\",R549,IFERROR(VLOOKUP('AUP Library'!A549,'Updated Quanities'!F:I,7,0),R549))","v":1600},1600,{"$f":"IFERROR(VLOOKUP('AUP Library'!A549,'Updated Quanities'!F:G,4,0),R549)","v":1600}]
["202-04.56","Removal of Structures","LS",2000,2000,2000,2000,2000,2000,2000,2000,2000,2000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A550,'Updated Quanities'!F:I,4,0),R550)=\"\",R550,IFERROR(VLOOKUP('AUP Library'!A550,'Updated Quanities'!F:I,4,0),R550))","v":2000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A550,'Updated Quanities'!F:I,5,0),R550)=\"\",R550,IFERROR(VLOOKUP('AUP Library'!A550,'Updated Quanities'!F:I,5,0),R550))","v":2000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A550,'Updated Quanities'!F:I,6,0),R550)=\"\",R550,IFERROR(VLOOKUP('AUP Library'!A550,'Updated Quanities'!F:I,6,0),R550))","v":2000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A550,'Updated Quanities'!F:I,7,0),R550)=\"\",R550,IFERROR(VLOOKUP('AUP Library'!A550,'Updated Quanities'!F:I,7,0),R550))","v":2000},2000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A550,'Updated Quanities'!F:G,4,0),R550)","v":2000}]
["202-04.57","Removal of Structures","LS",1500,1500,1500,1500,1500,1500,1500,1500,1500,1500,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A551,'Updated Quanities'!F:I,4,0),R551)=\"\",R551,IFERROR(VLOOKUP('AUP Library'!A551,'Updated Quanities'!F:I,4,0),R551))","v":1500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A551,'Updated Quanities'!F:I,5,0),R551)=\"\",R551,IFERROR(VLOOKUP('AUP Library'!A551,'Updated Quanities'!F:I,5,0),R551))","v":1500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A551,'Updated Quanities'!F:I,6,0),R551)=\"\",R551,IFERROR(VLOOKUP('AUP Library'!A551,'Updated Quanities'!F:I,6,0),R551))","v":1500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A551,'Updated Quanities'!F:I,7,0),R551)=\"\",R551,IFERROR(VLOOKUP('AUP Library'!A551,'Updated Quanities'!F:I,7,0),R551))","v":1500},1500,{"$f":"IFERROR(VLOOKUP('AUP Library'!A551,'Updated Quanities'!F:G,4,0),R551)","v":1500}]
["202-04.58","Removal of Structures","LS",1200,1200,1200,1200,1200,1200,1200,1200,1200,1200,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A552,'Updated Quanities'!F:I,4,0),R552)=\"\",R552,IFERROR(VLOOKUP('AUP Library'!A552,'Updated Quanities'!F:I,4,0),R552))","v":1200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A552,'Updated Quanities'!F:I,5,0),R552)=\"\",R552,IFERROR(VLOOKUP('AUP Library'!A552,'Updated Quanities'!F:I,5,0),R552))","v":1200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A552,'Updated Quanities'!F:I,6,0),R552)=\"\",R552,IFERROR(VLOOKUP('AUP Library'!A552,'Updated Quanities'!F:I,6,0),R552))","v":1200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A552,'Updated Quanities'!F:I,7,0),R552)=\"\",R552,IFERROR(VLOOKUP('AUP Library'!A552,'Updated Quanities'!F:I,7,0),R552))","v":1200},1200,{"$f":"IFERROR(VLOOKUP('AUP Library'!A552,'Updated Quanities'!F:G,4,0),R552)","v":1200}]
["202-04.59","Removal of Structures","LS",6000,6000,6000,6000,6000,6000,6000,6000,6000,6000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A553,'Updated Quanities'!F:I,4,0),R553)=\"\",R553,IFERROR(VLOOKUP('AUP Library'!A553,'Updated Quanities'!F:I,4,0),R553))","v":6000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A553,'Updated Quanities'!F:I,5,0),R553)=\"\",R553,IFERROR(VLOOKUP('AUP Library'!A553,'Updated Quanities'!F:I,5,0),R553))","v":6000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A553,'Updated Quanities'!F:I,6,0),R553)=\"\",R553,IFERROR(VLOOKUP('AUP Library'!A553,'Updated Quanities'!F:I,6,0),R553))","v":6000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A553,'Updated Quanities'!F:I,7,0),R553)=\"\",R553,IFERROR(VLOOKUP('AUP Library'!A553,'Updated Quanities'!F:I,7,0),R553))","v":6000},6000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A553,'Updated Quanities'!F:G,4,0),R553)","v":6000}]
["202-04.60","Removal of Structures","LS",1600,1600,1600,1600,1600,1600,1600,1600,1600,1600,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A554,'Updated Quanities'!F:I,4,0),R554)=\"\",R554,IFERROR(VLOOKUP('AUP Library'!A554,'Updated Quanities'!F:I,4,0),R554))","v":1600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A554,'Updated Quanities'!F:I,5,0),R554)=\"\",R554,IFERROR(VLOOKUP('AUP Library'!A554,'Updated Quanities'!F:I,5,0),R554))","v":1600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A554,'Updated Quanities'!F:I,6,0),R554)=\"\",R554,IFERROR(VLOOKUP('AUP Library'!A554,'Updated Quanities'!F:I,6,0),R554))","v":1600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A554,'Updated Quanities'!F:I,7,0),R554)=\"\",R554,IFERROR(VLOOKUP('AUP Library'!A554,'Updated Quanities'!F:I,7,0),R554))","v":1600},1600,{"$f":"IFERROR(VLOOKUP('AUP Library'!A554,'Updated Quanities'!F:G,4,0),R554)","v":1600}]
["202-04.61","Removal of Structures","LS",2000,2000,2000,2000,2000,2000,2000,2000,2000,2000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A555,'Updated Quanities'!F:I,4,0),R555)=\"\",R555,IFERROR(VLOOKUP('AUP Library'!A555,'Updated Quanities'!F:I,4,0),R555))","v":2000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A555,'Updated Quanities'!F:I,5,0),R555)=\"\",R555,IFERROR(VLOOKUP('AUP Library'!A555,'Updated Quanities'!F:I,5,0),R555))","v":2000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A555,'Updated Quanities'!F:I,6,0),R555)=\"\",R555,IFERROR(VLOOKUP('AUP Library'!A555,'Updated Quanities'!F:I,6,0),R555))","v":2000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A555,'Updated Quanities'!F:I,7,0),R555)=\"\",R555,IFERROR(VLOOKUP('AUP Library'!A555,'Updated Quanities'!F:I,7,0),R555))","v":2000},2000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A555,'Updated Quanities'!F:G,4,0),R555)","v":2000}]
["202-04.62","Removal of Structures","LS",1200,1200,1200,1200,1200,1200,1200,1200,1200,1200,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A556,'Updated Quanities'!F:I,4,0),R556)=\"\",R556,IFERROR(VLOOKUP('AUP Library'!A556,'Updated Quanities'!F:I,4,0),R556))","v":1200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A556,'Updated Quanities'!F:I,5,0),R556)=\"\",R556,IFERROR(VLOOKUP('AUP Library'!A556,'Updated Quanities'!F:I,5,0),R556))","v":1200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A556,'Updated Quanities'!F:I,6,0),R556)=\"\",R556,IFERROR(VLOOKUP('AUP Library'!A556,'Updated Quanities'!F:I,6,0),R556))","v":1200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A556,'Updated Quanities'!F:I,7,0),R556)=\"\",R556,IFERROR(VLOOKUP('AUP Library'!A556,'Updated Quanities'!F:I,7,0),R556))","v":1200},1200,{"$f":"IFERROR(VLOOKUP('AUP Library'!A556,'Updated Quanities'!F:G,4,0),R556)","v":1200}]
["202-04.63","Removal of Structures","LS",10000,10000,10000,10000,10000,10000,10000,10000,10000,10000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A557,'Updated Quanities'!F:I,4,0),R557)=\"\",R557,IFERROR(VLOOKUP('AUP Library'!A557,'Updated Quanities'!F:I,4,0),R557))","v":10000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A557,'Updated Quanities'!F:I,5,0),R557)=\"\",R557,IFERROR(VLOOKUP('AUP Library'!A557,'Updated Quanities'!F:I,5,0),R557))","v":10000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A557,'Updated Quanities'!F:I,6,0),R557)=\"\",R557,IFERROR(VLOOKUP('AUP Library'!A557,'Updated Quanities'!F:I,6,0),R557))","v":10000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A557,'Updated Quanities'!F:I,7,0),R557)=\"\",R557,IFERROR(VLOOKUP('AUP Library'!A557,'Updated Quanities'!F:I,7,0),R557))","v":10000},10000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A557,'Updated Quanities'!F:G,4,0),R557)","v":10000}]
["604-02.01","Class A Concrete (Box Bridges)","CY",519.78,519.78,519.78,519.78,519.78,519.78,519.78,519.78,519.78,519.78,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A558,'Updated Quanities'!F:I,4,0),R558)=\"\",R558,IFERROR(VLOOKUP('AUP Library'!A558,'Updated Quanities'!F:I,4,0),R558))","v":519.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A558,'Updated Quanities'!F:I,5,0),R558)=\"\",R558,IFERROR(VLOOKUP('AUP Library'!A558,'Updated Quanities'!F:I,5,0),R558))","v":519.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A558,'Updated Quanities'!F:I,6,0),R558)=\"\",R558,IFERROR(VLOOKUP('AUP Library'!A558,'Updated Quanities'!F:I,6,0),R558))","v":519.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A558,'Updated Quanities'!F:I,7,0),R558)=\"\",R558,IFERROR(VLOOKUP('AUP Library'!A558,'Updated Quanities'!F:I,7,0),R558))","v":519.78},519.78,{"$f":"IFERROR(VLOOKUP('AUP Library'!A558,'Updated Quanities'!F:G,4,0),R558)","v":519.78}]
["604-02.02","Steel Bar Reinforcement (Box Bridges)","LB",0.86,0.86,0.86,0.86,0.86,0.86,0.86,0.86,0.86,0.86,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A559,'Updated Quanities'!F:I,4,0),R559)=\"\",R559,IFERROR(VLOOKUP('AUP Library'!A559,'Updated Quanities'!F:I,4,0),R559))","v":0.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A559,'Updated Quanities'!F:I,5,0),R559)=\"\",R559,IFERROR(VLOOKUP('AUP Library'!A559,'Updated Quanities'!F:I,5,0),R559))","v":0.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A559,'Updated Quanities'!F:I,6,0),R559)=\"\",R559,IFERROR(VLOOKUP('AUP Library'!A559,'Updated Quanities'!F:I,6,0),R559))","v":0.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A559,'Updated Quanities'!F:I,7,0),R559)=\"\",R559,IFERROR(VLOOKUP('AUP Library'!A559,'Updated Quanities'!F:I,7,0),R559))","v":0.86},0.86,{"$f":"IFERROR(VLOOKUP('AUP Library'!A559,'Updated Quanities'!F:G,4,0),R559)","v":0.86}]
["604-04.01","APPLIED TEXTURE FINISH (NEW STRUCTURES)","SY",7.72,7.72,7.72,7.72,7.72,7.72,7.72,7.72,7.72,7.72,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A560,'Updated Quanities'!F:I,4,0),R560)=\"\",R560,IFERROR(VLOOKUP('AUP Library'!A560,'Updated Quanities'!F:I,4,0),R560))","v":7.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A560,'Updated Quanities'!F:I,5,0),R560)=\"\",R560,IFERROR(VLOOKUP('AUP Library'!A560,'Updated Quanities'!F:I,5,0),R560))","v":7.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A560,'Updated Quanities'!F:I,6,0),R560)=\"\",R560,IFERROR(VLOOKUP('AUP Library'!A560,'Updated Quanities'!F:I,6,0),R560))","v":7.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A560,'Updated Quanities'!F:I,7,0),R560)=\"\",R560,IFERROR(VLOOKUP('AUP Library'!A560,'Updated Quanities'!F:I,7,0),R560))","v":7.72},7.72,{"$f":"IFERROR(VLOOKUP('AUP Library'!A560,'Updated Quanities'!F:G,4,0),R560)","v":7.72}]
["604-04.02","APPLIED TEXTURE FINISH (EX STRUCTURES)","SY",8.1999999999999993,8.1999999999999993,8.1999999999999993,8.1999999999999993,8.1999999999999993,8.1999999999999993,8.1999999999999993,8.1999999999999993,8.1999999999999993,8.1999999999999993,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A561,'Updated Quanities'!F:I,4,0),R561)=\"\",R561,IFERROR(VLOOKUP('AUP Library'!A561,'Updated Quanities'!F:I,4,0),R561))","v":8.1999999999999993},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A561,'Updated Quanities'!F:I,5,0),R561)=\"\",R561,IFERROR(VLOOKUP('AUP Library'!A561,'Updated Quanities'!F:I,5,0),R561))","v":8.1999999999999993},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A561,'Updated Quanities'!F:I,6,0),R561)=\"\",R561,IFERROR(VLOOKUP('AUP Library'!A561,'Updated Quanities'!F:I,6,0),R561))","v":8.1999999999999993},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A561,'Updated Quanities'!F:I,7,0),R561)=\"\",R561,IFERROR(VLOOKUP('AUP Library'!A561,'Updated Quanities'!F:I,7,0),R561))","v":8.1999999999999993},8.1999999999999993,{"$f":"IFERROR(VLOOKUP('AUP Library'!A561,'Updated Quanities'!F:G,4,0),R561)","v":8.1999999999999993}]
["604-04.03","BRIDGE END DRAINS(2'X8')","EA",4227.1400000000003,4227.1400000000003,4227.1400000000003,4227.1400000000003,4227.1400000000003,4227.1400000000003,4227.1400000000003,4227.1400000000003,4227.1400000000003,4227.1400000000003,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A562,'Updated Quanities'!F:I,4,0),R562)=\"\",R562,IFERROR(VLOOKUP('AUP Library'!A562,'Updated Quanities'!F:I,4,0),R562))","v":4227.1400000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A562,'Updated Quanities'!F:I,5,0),R562)=\"\",R562,IFERROR(VLOOKUP('AUP Library'!A562,'Updated Quanities'!F:I,5,0),R562))","v":4227.1400000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A562,'Updated Quanities'!F:I,6,0),R562)=\"\",R562,IFERROR(VLOOKUP('AUP Library'!A562,'Updated Quanities'!F:I,6,0),R562))","v":4227.1400000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A562,'Updated Quanities'!F:I,7,0),R562)=\"\",R562,IFERROR(VLOOKUP('AUP Library'!A562,'Updated Quanities'!F:I,7,0),R562))","v":4227.1400000000003},4227.1400000000003,{"$f":"IFERROR(VLOOKUP('AUP Library'!A562,'Updated Quanities'!F:G,4,0),R562)","v":4227.1400000000003}]
["604-04.04","BRIDGE END DRAINS(4'X8')","EA",2000,2000,2000,2000,2000,2000,2000,2000,2000,2000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A563,'Updated Quanities'!F:I,4,0),R563)=\"\",R563,IFERROR(VLOOKUP('AUP Library'!A563,'Updated Quanities'!F:I,4,0),R563))","v":2000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A563,'Updated Quanities'!F:I,5,0),R563)=\"\",R563,IFERROR(VLOOKUP('AUP Library'!A563,'Updated Quanities'!F:I,5,0),R563))","v":2000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A563,'Updated Quanities'!F:I,6,0),R563)=\"\",R563,IFERROR(VLOOKUP('AUP Library'!A563,'Updated Quanities'!F:I,6,0),R563))","v":2000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A563,'Updated Quanities'!F:I,7,0),R563)=\"\",R563,IFERROR(VLOOKUP('AUP Library'!A563,'Updated Quanities'!F:I,7,0),R563))","v":2000},2000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A563,'Updated Quanities'!F:G,4,0),R563)","v":2000}]
["604-04.20","PAINTING CONCRETE SURFACES","SF",10.74,10.74,10.74,10.74,10.74,10.74,10.74,10.74,10.74,10.74,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A564,'Updated Quanities'!F:I,4,0),R564)=\"\",R564,IFERROR(VLOOKUP('AUP Library'!A564,'Updated Quanities'!F:I,4,0),R564))","v":10.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A564,'Updated Quanities'!F:I,5,0),R564)=\"\",R564,IFERROR(VLOOKUP('AUP Library'!A564,'Updated Quanities'!F:I,5,0),R564))","v":10.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A564,'Updated Quanities'!F:I,6,0),R564)=\"\",R564,IFERROR(VLOOKUP('AUP Library'!A564,'Updated Quanities'!F:I,6,0),R564))","v":10.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A564,'Updated Quanities'!F:I,7,0),R564)=\"\",R564,IFERROR(VLOOKUP('AUP Library'!A564,'Updated Quanities'!F:I,7,0),R564))","v":10.74},10.74,{"$f":"IFERROR(VLOOKUP('AUP Library'!A564,'Updated Quanities'!F:G,4,0),R564)","v":10.74}]
["604-04.62","CLN & TEXTURE FINISH CONCRETE MEDIAN B.R","LF",7.38,7.38,7.38,7.38,7.38,7.38,7.38,7.38,7.38,7.38,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A565,'Updated Quanities'!F:I,4,0),R565)=\"\",R565,IFERROR(VLOOKUP('AUP Library'!A565,'Updated Quanities'!F:I,4,0),R565))","v":7.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A565,'Updated Quanities'!F:I,5,0),R565)=\"\",R565,IFERROR(VLOOKUP('AUP Library'!A565,'Updated Quanities'!F:I,5,0),R565))","v":7.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A565,'Updated Quanities'!F:I,6,0),R565)=\"\",R565,IFERROR(VLOOKUP('AUP Library'!A565,'Updated Quanities'!F:I,6,0),R565))","v":7.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A565,'Updated Quanities'!F:I,7,0),R565)=\"\",R565,IFERROR(VLOOKUP('AUP Library'!A565,'Updated Quanities'!F:I,7,0),R565))","v":7.38},7.38,{"$f":"IFERROR(VLOOKUP('AUP Library'!A565,'Updated Quanities'!F:G,4,0),R565)","v":7.38}]
["604-07.01","Retaining Wall","SF",65.400000000000006,65.400000000000006,65.400000000000006,65.400000000000006,65.400000000000006,65.400000000000006,65.400000000000006,65.400000000000006,65.400000000000006,65.400000000000006,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A566,'Updated Quanities'!F:I,4,0),R566)=\"\",R566,IFERROR(VLOOKUP('AUP Library'!A566,'Updated Quanities'!F:I,4,0),R566))","v":65.400000000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A566,'Updated Quanities'!F:I,5,0),R566)=\"\",R566,IFERROR(VLOOKUP('AUP Library'!A566,'Updated Quanities'!F:I,5,0),R566))","v":65.400000000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A566,'Updated Quanities'!F:I,6,0),R566)=\"\",R566,IFERROR(VLOOKUP('AUP Library'!A566,'Updated Quanities'!F:I,6,0),R566))","v":65.400000000000006},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A566,'Updated Quanities'!F:I,7,0),R566)=\"\",R566,IFERROR(VLOOKUP('AUP Library'!A566,'Updated Quanities'!F:I,7,0),R566))","v":65.400000000000006},65.400000000000006,{"$f":"IFERROR(VLOOKUP('AUP Library'!A566,'Updated Quanities'!F:G,4,0),R566)","v":65.400000000000006}]
["604-07.02","Retaining Wall","SF",57.27,57.27,57.27,57.27,57.27,57.27,57.27,57.27,57.27,57.27,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A567,'Updated Quanities'!F:I,4,0),R567)=\"\",R567,IFERROR(VLOOKUP('AUP Library'!A567,'Updated Quanities'!F:I,4,0),R567))","v":57.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A567,'Updated Quanities'!F:I,5,0),R567)=\"\",R567,IFERROR(VLOOKUP('AUP Library'!A567,'Updated Quanities'!F:I,5,0),R567))","v":57.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A567,'Updated Quanities'!F:I,6,0),R567)=\"\",R567,IFERROR(VLOOKUP('AUP Library'!A567,'Updated Quanities'!F:I,6,0),R567))","v":57.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A567,'Updated Quanities'!F:I,7,0),R567)=\"\",R567,IFERROR(VLOOKUP('AUP Library'!A567,'Updated Quanities'!F:I,7,0),R567))","v":57.27},57.27,{"$f":"IFERROR(VLOOKUP('AUP Library'!A567,'Updated Quanities'!F:G,4,0),R567)","v":57.27}]
["604-07.03","Retaining Wall","SF",65.349999999999994,65.349999999999994,65.349999999999994,65.349999999999994,65.349999999999994,65.349999999999994,65.349999999999994,65.349999999999994,65.349999999999994,65.349999999999994,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A568,'Updated Quanities'!F:I,4,0),R568)=\"\",R568,IFERROR(VLOOKUP('AUP Library'!A568,'Updated Quanities'!F:I,4,0),R568))","v":65.349999999999994},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A568,'Updated Quanities'!F:I,5,0),R568)=\"\",R568,IFERROR(VLOOKUP('AUP Library'!A568,'Updated Quanities'!F:I,5,0),R568))","v":65.349999999999994},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A568,'Updated Quanities'!F:I,6,0),R568)=\"\",R568,IFERROR(VLOOKUP('AUP Library'!A568,'Updated Quanities'!F:I,6,0),R568))","v":65.349999999999994},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A568,'Updated Quanities'!F:I,7,0),R568)=\"\",R568,IFERROR(VLOOKUP('AUP Library'!A568,'Updated Quanities'!F:I,7,0),R568))","v":65.349999999999994},65.349999999999994,{"$f":"IFERROR(VLOOKUP('AUP Library'!A568,'Updated Quanities'!F:G,4,0),R568)","v":65.349999999999994}]
["604-07.04","Retaining Wall","SF",75.099999999999994,75.099999999999994,75.099999999999994,75.099999999999994,75.099999999999994,75.099999999999994,75.099999999999994,75.099999999999994,75.099999999999994,75.099999999999994,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A569,'Updated Quanities'!F:I,4,0),R569)=\"\",R569,IFERROR(VLOOKUP('AUP Library'!A569,'Updated Quanities'!F:I,4,0),R569))","v":75.099999999999994},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A569,'Updated Quanities'!F:I,5,0),R569)=\"\",R569,IFERROR(VLOOKUP('AUP Library'!A569,'Updated Quanities'!F:I,5,0),R569))","v":75.099999999999994},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A569,'Updated Quanities'!F:I,6,0),R569)=\"\",R569,IFERROR(VLOOKUP('AUP Library'!A569,'Updated Quanities'!F:I,6,0),R569))","v":75.099999999999994},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A569,'Updated Quanities'!F:I,7,0),R569)=\"\",R569,IFERROR(VLOOKUP('AUP Library'!A569,'Updated Quanities'!F:I,7,0),R569))","v":75.099999999999994},75.099999999999994,{"$f":"IFERROR(VLOOKUP('AUP Library'!A569,'Updated Quanities'!F:G,4,0),R569)","v":75.099999999999994}]
["604-07.05","Retaining Wall","SF",80.41,80.41,80.41,80.41,80.41,80.41,80.41,80.41,80.41,80.41,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A570,'Updated Quanities'!F:I,4,0),R570)=\"\",R570,IFERROR(VLOOKUP('AUP Library'!A570,'Updated Quanities'!F:I,4,0),R570))","v":80.41},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A570,'Updated Quanities'!F:I,5,0),R570)=\"\",R570,IFERROR(VLOOKUP('AUP Library'!A570,'Updated Quanities'!F:I,5,0),R570))","v":80.41},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A570,'Updated Quanities'!F:I,6,0),R570)=\"\",R570,IFERROR(VLOOKUP('AUP Library'!A570,'Updated Quanities'!F:I,6,0),R570))","v":80.41},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A570,'Updated Quanities'!F:I,7,0),R570)=\"\",R570,IFERROR(VLOOKUP('AUP Library'!A570,'Updated Quanities'!F:I,7,0),R570))","v":80.41},80.41,{"$f":"IFERROR(VLOOKUP('AUP Library'!A570,'Updated Quanities'!F:G,4,0),R570)","v":80.41}]
["604-07.06","Retaining Wall","SF",127.97,127.97,127.97,127.97,127.97,127.97,127.97,127.97,127.97,127.97,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A571,'Updated Quanities'!F:I,4,0),R571)=\"\",R571,IFERROR(VLOOKUP('AUP Library'!A571,'Updated Quanities'!F:I,4,0),R571))","v":127.97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A571,'Updated Quanities'!F:I,5,0),R571)=\"\",R571,IFERROR(VLOOKUP('AUP Library'!A571,'Updated Quanities'!F:I,5,0),R571))","v":127.97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A571,'Updated Quanities'!F:I,6,0),R571)=\"\",R571,IFERROR(VLOOKUP('AUP Library'!A571,'Updated Quanities'!F:I,6,0),R571))","v":127.97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A571,'Updated Quanities'!F:I,7,0),R571)=\"\",R571,IFERROR(VLOOKUP('AUP Library'!A571,'Updated Quanities'!F:I,7,0),R571))","v":127.97},127.97,{"$f":"IFERROR(VLOOKUP('AUP Library'!A571,'Updated Quanities'!F:G,4,0),R571)","v":127.97}]
["604-07.07","Retaining Wall","SF",65,65,65,65,65,65,65,65,65,65,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A572,'Updated Quanities'!F:I,4,0),R572)=\"\",R572,IFERROR(VLOOKUP('AUP Library'!A572,'Updated Quanities'!F:I,4,0),R572))","v":65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A572,'Updated Quanities'!F:I,5,0),R572)=\"\",R572,IFERROR(VLOOKUP('AUP Library'!A572,'Updated Quanities'!F:I,5,0),R572))","v":65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A572,'Updated Quanities'!F:I,6,0),R572)=\"\",R572,IFERROR(VLOOKUP('AUP Library'!A572,'Updated Quanities'!F:I,6,0),R572))","v":65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A572,'Updated Quanities'!F:I,7,0),R572)=\"\",R572,IFERROR(VLOOKUP('AUP Library'!A572,'Updated Quanities'!F:I,7,0),R572))","v":65},65,{"$f":"IFERROR(VLOOKUP('AUP Library'!A572,'Updated Quanities'!F:G,4,0),R572)","v":65}]
["607-50.03","PRECAST CONCRETE BOX CULVERT (12' X 4')","LF",1185,1185,1185,1185,1185,1185,1185,1185,1185,1185,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A573,'Updated Quanities'!F:I,4,0),R573)=\"\",R573,IFERROR(VLOOKUP('AUP Library'!A573,'Updated Quanities'!F:I,4,0),R573))","v":1185},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A573,'Updated Quanities'!F:I,5,0),R573)=\"\",R573,IFERROR(VLOOKUP('AUP Library'!A573,'Updated Quanities'!F:I,5,0),R573))","v":1185},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A573,'Updated Quanities'!F:I,6,0),R573)=\"\",R573,IFERROR(VLOOKUP('AUP Library'!A573,'Updated Quanities'!F:I,6,0),R573))","v":1185},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A573,'Updated Quanities'!F:I,7,0),R573)=\"\",R573,IFERROR(VLOOKUP('AUP Library'!A573,'Updated Quanities'!F:I,7,0),R573))","v":1185},1185,{"$f":"IFERROR(VLOOKUP('AUP Library'!A573,'Updated Quanities'!F:G,4,0),R573)","v":1185}]
["607-50.04","PRECAST CONCRETE BOX CULVERT (10' X 4')","LF",1250,1250,1250,1250,1250,1250,1250,1250,1250,1250,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A574,'Updated Quanities'!F:I,4,0),R574)=\"\",R574,IFERROR(VLOOKUP('AUP Library'!A574,'Updated Quanities'!F:I,4,0),R574))","v":1250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A574,'Updated Quanities'!F:I,5,0),R574)=\"\",R574,IFERROR(VLOOKUP('AUP Library'!A574,'Updated Quanities'!F:I,5,0),R574))","v":1250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A574,'Updated Quanities'!F:I,6,0),R574)=\"\",R574,IFERROR(VLOOKUP('AUP Library'!A574,'Updated Quanities'!F:I,6,0),R574))","v":1250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A574,'Updated Quanities'!F:I,7,0),R574)=\"\",R574,IFERROR(VLOOKUP('AUP Library'!A574,'Updated Quanities'!F:I,7,0),R574))","v":1250},1250,{"$f":"IFERROR(VLOOKUP('AUP Library'!A574,'Updated Quanities'!F:G,4,0),R574)","v":1250}]
["607-50.05","PRECAST CONCRETE BOX CULVERT (8' X 4')","LF",740,740,740,740,740,740,740,740,740,740,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A575,'Updated Quanities'!F:I,4,0),R575)=\"\",R575,IFERROR(VLOOKUP('AUP Library'!A575,'Updated Quanities'!F:I,4,0),R575))","v":740},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A575,'Updated Quanities'!F:I,5,0),R575)=\"\",R575,IFERROR(VLOOKUP('AUP Library'!A575,'Updated Quanities'!F:I,5,0),R575))","v":740},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A575,'Updated Quanities'!F:I,6,0),R575)=\"\",R575,IFERROR(VLOOKUP('AUP Library'!A575,'Updated Quanities'!F:I,6,0),R575))","v":740},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A575,'Updated Quanities'!F:I,7,0),R575)=\"\",R575,IFERROR(VLOOKUP('AUP Library'!A575,'Updated Quanities'!F:I,7,0),R575))","v":740},740,{"$f":"IFERROR(VLOOKUP('AUP Library'!A575,'Updated Quanities'!F:G,4,0),R575)","v":740}]
["607-50.07","PRECAST CONCRETE BOX CULVERT (12' X 6')","LF",2084,2084,2084,2084,2084,2084,2084,2084,2084,2084,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A576,'Updated Quanities'!F:I,4,0),R576)=\"\",R576,IFERROR(VLOOKUP('AUP Library'!A576,'Updated Quanities'!F:I,4,0),R576))","v":2084},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A576,'Updated Quanities'!F:I,5,0),R576)=\"\",R576,IFERROR(VLOOKUP('AUP Library'!A576,'Updated Quanities'!F:I,5,0),R576))","v":2084},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A576,'Updated Quanities'!F:I,6,0),R576)=\"\",R576,IFERROR(VLOOKUP('AUP Library'!A576,'Updated Quanities'!F:I,6,0),R576))","v":2084},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A576,'Updated Quanities'!F:I,7,0),R576)=\"\",R576,IFERROR(VLOOKUP('AUP Library'!A576,'Updated Quanities'!F:I,7,0),R576))","v":2084},2084,{"$f":"IFERROR(VLOOKUP('AUP Library'!A576,'Updated Quanities'!F:G,4,0),R576)","v":2084}]
["607-50.09","PRECAST CONCRETE BOX CULVERT (6' X 4')","LF",542.80999999999995,542.80999999999995,542.80999999999995,542.80999999999995,542.80999999999995,542.80999999999995,542.80999999999995,542.80999999999995,542.80999999999995,542.80999999999995,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A577,'Updated Quanities'!F:I,4,0),R577)=\"\",R577,IFERROR(VLOOKUP('AUP Library'!A577,'Updated Quanities'!F:I,4,0),R577))","v":542.80999999999995},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A577,'Updated Quanities'!F:I,5,0),R577)=\"\",R577,IFERROR(VLOOKUP('AUP Library'!A577,'Updated Quanities'!F:I,5,0),R577))","v":542.80999999999995},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A577,'Updated Quanities'!F:I,6,0),R577)=\"\",R577,IFERROR(VLOOKUP('AUP Library'!A577,'Updated Quanities'!F:I,6,0),R577))","v":542.80999999999995},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A577,'Updated Quanities'!F:I,7,0),R577)=\"\",R577,IFERROR(VLOOKUP('AUP Library'!A577,'Updated Quanities'!F:I,7,0),R577))","v":542.80999999999995},542.80999999999995,{"$f":"IFERROR(VLOOKUP('AUP Library'!A577,'Updated Quanities'!F:G,4,0),R577)","v":542.80999999999995}]
["607-50.12","PRECAST CONCRETE BOX CULVERT","LF",574.22,574.22,574.22,574.22,574.22,574.22,574.22,574.22,574.22,574.22,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A578,'Updated Quanities'!F:I,4,0),R578)=\"\",R578,IFERROR(VLOOKUP('AUP Library'!A578,'Updated Quanities'!F:I,4,0),R578))","v":574.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A578,'Updated Quanities'!F:I,5,0),R578)=\"\",R578,IFERROR(VLOOKUP('AUP Library'!A578,'Updated Quanities'!F:I,5,0),R578))","v":574.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A578,'Updated Quanities'!F:I,6,0),R578)=\"\",R578,IFERROR(VLOOKUP('AUP Library'!A578,'Updated Quanities'!F:I,6,0),R578))","v":574.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A578,'Updated Quanities'!F:I,7,0),R578)=\"\",R578,IFERROR(VLOOKUP('AUP Library'!A578,'Updated Quanities'!F:I,7,0),R578))","v":574.22},574.22,{"$f":"IFERROR(VLOOKUP('AUP Library'!A578,'Updated Quanities'!F:G,4,0),R578)","v":574.22}]
["607-50.13","PRECAST CONCRETE BOX CULVERT","LF",623.83000000000004,623.83000000000004,623.83000000000004,623.83000000000004,623.83000000000004,623.83000000000004,623.83000000000004,623.83000000000004,623.83000000000004,623.83000000000004,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A579,'Updated Quanities'!F:I,4,0),R579)=\"\",R579,IFERROR(VLOOKUP('AUP Library'!A579,'Updated Quanities'!F:I,4,0),R579))","v":623.83000000000004},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A579,'Updated Quanities'!F:I,5,0),R579)=\"\",R579,IFERROR(VLOOKUP('AUP Library'!A579,'Updated Quanities'!F:I,5,0),R579))","v":623.83000000000004},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A579,'Updated Quanities'!F:I,6,0),R579)=\"\",R579,IFERROR(VLOOKUP('AUP Library'!A579,'Updated Quanities'!F:I,6,0),R579))","v":623.83000000000004},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A579,'Updated Quanities'!F:I,7,0),R579)=\"\",R579,IFERROR(VLOOKUP('AUP Library'!A579,'Updated Quanities'!F:I,7,0),R579))","v":623.83000000000004},623.83000000000004,{"$f":"IFERROR(VLOOKUP('AUP Library'!A579,'Updated Quanities'!F:G,4,0),R579)","v":623.83000000000004}]
["607-50.30","PRECAST CONCRETE BOX BRIDGE","LF",1985,1985,1985,1985,1985,1985,1985,1985,1985,1985,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A580,'Updated Quanities'!F:I,4,0),R580)=\"\",R580,IFERROR(VLOOKUP('AUP Library'!A580,'Updated Quanities'!F:I,4,0),R580))","v":1985},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A580,'Updated Quanities'!F:I,5,0),R580)=\"\",R580,IFERROR(VLOOKUP('AUP Library'!A580,'Updated Quanities'!F:I,5,0),R580))","v":1985},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A580,'Updated Quanities'!F:I,6,0),R580)=\"\",R580,IFERROR(VLOOKUP('AUP Library'!A580,'Updated Quanities'!F:I,6,0),R580))","v":1985},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A580,'Updated Quanities'!F:I,7,0),R580)=\"\",R580,IFERROR(VLOOKUP('AUP Library'!A580,'Updated Quanities'!F:I,7,0),R580))","v":1985},1985,{"$f":"IFERROR(VLOOKUP('AUP Library'!A580,'Updated Quanities'!F:G,4,0),R580)","v":1985}]
["607-50.50","PRECAST CONCRETE BOX CULVERT","LF",70000,70000,70000,70000,70000,70000,70000,70000,70000,70000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A581,'Updated Quanities'!F:I,4,0),R581)=\"\",R581,IFERROR(VLOOKUP('AUP Library'!A581,'Updated Quanities'!F:I,4,0),R581))","v":70000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A581,'Updated Quanities'!F:I,5,0),R581)=\"\",R581,IFERROR(VLOOKUP('AUP Library'!A581,'Updated Quanities'!F:I,5,0),R581))","v":70000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A581,'Updated Quanities'!F:I,6,0),R581)=\"\",R581,IFERROR(VLOOKUP('AUP Library'!A581,'Updated Quanities'!F:I,6,0),R581))","v":70000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A581,'Updated Quanities'!F:I,7,0),R581)=\"\",R581,IFERROR(VLOOKUP('AUP Library'!A581,'Updated Quanities'!F:I,7,0),R581))","v":70000},70000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A581,'Updated Quanities'!F:G,4,0),R581)","v":70000}]
["607-50.51","PRECAST CONCRETE BOX CULVERT","LF",9000,9000,9000,9000,9000,9000,9000,9000,9000,9000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A582,'Updated Quanities'!F:I,4,0),R582)=\"\",R582,IFERROR(VLOOKUP('AUP Library'!A582,'Updated Quanities'!F:I,4,0),R582))","v":9000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A582,'Updated Quanities'!F:I,5,0),R582)=\"\",R582,IFERROR(VLOOKUP('AUP Library'!A582,'Updated Quanities'!F:I,5,0),R582))","v":9000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A582,'Updated Quanities'!F:I,6,0),R582)=\"\",R582,IFERROR(VLOOKUP('AUP Library'!A582,'Updated Quanities'!F:I,6,0),R582))","v":9000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A582,'Updated Quanities'!F:I,7,0),R582)=\"\",R582,IFERROR(VLOOKUP('AUP Library'!A582,'Updated Quanities'!F:I,7,0),R582))","v":9000},9000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A582,'Updated Quanities'!F:G,4,0),R582)","v":9000}]
["607-50.52","PRECAST CONCRETE BOX CULVERT","LF",5000,5000,5000,5000,5000,5000,5000,5000,5000,5000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A583,'Updated Quanities'!F:I,4,0),R583)=\"\",R583,IFERROR(VLOOKUP('AUP Library'!A583,'Updated Quanities'!F:I,4,0),R583))","v":5000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A583,'Updated Quanities'!F:I,5,0),R583)=\"\",R583,IFERROR(VLOOKUP('AUP Library'!A583,'Updated Quanities'!F:I,5,0),R583))","v":5000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A583,'Updated Quanities'!F:I,6,0),R583)=\"\",R583,IFERROR(VLOOKUP('AUP Library'!A583,'Updated Quanities'!F:I,6,0),R583))","v":5000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A583,'Updated Quanities'!F:I,7,0),R583)=\"\",R583,IFERROR(VLOOKUP('AUP Library'!A583,'Updated Quanities'!F:I,7,0),R583))","v":5000},5000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A583,'Updated Quanities'!F:G,4,0),R583)","v":5000}]
["607-50.60","THREE SIDED PRECAST CULV - BBL","LF",4049.4,4049.4,4049.4,4049.4,4049.4,4049.4,4049.4,4049.4,4049.4,4049.4,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A584,'Updated Quanities'!F:I,4,0),R584)=\"\",R584,IFERROR(VLOOKUP('AUP Library'!A584,'Updated Quanities'!F:I,4,0),R584))","v":4049.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A584,'Updated Quanities'!F:I,5,0),R584)=\"\",R584,IFERROR(VLOOKUP('AUP Library'!A584,'Updated Quanities'!F:I,5,0),R584))","v":4049.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A584,'Updated Quanities'!F:I,6,0),R584)=\"\",R584,IFERROR(VLOOKUP('AUP Library'!A584,'Updated Quanities'!F:I,6,0),R584))","v":4049.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A584,'Updated Quanities'!F:I,7,0),R584)=\"\",R584,IFERROR(VLOOKUP('AUP Library'!A584,'Updated Quanities'!F:I,7,0),R584))","v":4049.4},4049.4,{"$f":"IFERROR(VLOOKUP('AUP Library'!A584,'Updated Quanities'!F:G,4,0),R584)","v":4049.4}]
["607-50.61","THREE SIDED PRECAST CULV - BBL","LF",2016.34,2016.34,2016.34,2016.34,2016.34,2016.34,2016.34,2016.34,2016.34,2016.34,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A585,'Updated Quanities'!F:I,4,0),R585)=\"\",R585,IFERROR(VLOOKUP('AUP Library'!A585,'Updated Quanities'!F:I,4,0),R585))","v":2016.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A585,'Updated Quanities'!F:I,5,0),R585)=\"\",R585,IFERROR(VLOOKUP('AUP Library'!A585,'Updated Quanities'!F:I,5,0),R585))","v":2016.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A585,'Updated Quanities'!F:I,6,0),R585)=\"\",R585,IFERROR(VLOOKUP('AUP Library'!A585,'Updated Quanities'!F:I,6,0),R585))","v":2016.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A585,'Updated Quanities'!F:I,7,0),R585)=\"\",R585,IFERROR(VLOOKUP('AUP Library'!A585,'Updated Quanities'!F:I,7,0),R585))","v":2016.34},2016.34,{"$f":"IFERROR(VLOOKUP('AUP Library'!A585,'Updated Quanities'!F:G,4,0),R585)","v":2016.34}]
["607-50.65","THREE SIDED PRECAST CULV - BBL(SIZE)","LS",307500,307500,307500,307500,307500,307500,307500,307500,307500,307500,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A586,'Updated Quanities'!F:I,4,0),R586)=\"\",R586,IFERROR(VLOOKUP('AUP Library'!A586,'Updated Quanities'!F:I,4,0),R586))","v":307500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A586,'Updated Quanities'!F:I,5,0),R586)=\"\",R586,IFERROR(VLOOKUP('AUP Library'!A586,'Updated Quanities'!F:I,5,0),R586))","v":307500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A586,'Updated Quanities'!F:I,6,0),R586)=\"\",R586,IFERROR(VLOOKUP('AUP Library'!A586,'Updated Quanities'!F:I,6,0),R586))","v":307500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A586,'Updated Quanities'!F:I,7,0),R586)=\"\",R586,IFERROR(VLOOKUP('AUP Library'!A586,'Updated Quanities'!F:I,7,0),R586))","v":307500},307500,{"$f":"IFERROR(VLOOKUP('AUP Library'!A586,'Updated Quanities'!F:G,4,0),R586)","v":307500}]
["621-01.01","Temporary Structure","LS",11500,11500,11500,11500,11500,11500,11500,11500,11500,11500,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A587,'Updated Quanities'!F:I,4,0),R587)=\"\",R587,IFERROR(VLOOKUP('AUP Library'!A587,'Updated Quanities'!F:I,4,0),R587))","v":11500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A587,'Updated Quanities'!F:I,5,0),R587)=\"\",R587,IFERROR(VLOOKUP('AUP Library'!A587,'Updated Quanities'!F:I,5,0),R587))","v":11500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A587,'Updated Quanities'!F:I,6,0),R587)=\"\",R587,IFERROR(VLOOKUP('AUP Library'!A587,'Updated Quanities'!F:I,6,0),R587))","v":11500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A587,'Updated Quanities'!F:I,7,0),R587)=\"\",R587,IFERROR(VLOOKUP('AUP Library'!A587,'Updated Quanities'!F:I,7,0),R587))","v":11500},11500,{"$f":"IFERROR(VLOOKUP('AUP Library'!A587,'Updated Quanities'!F:G,4,0),R587)","v":11500}]
["621-01.02","Temporary Structure","LS",7980,7980,7980,7980,7980,7980,7980,7980,7980,7980,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A588,'Updated Quanities'!F:I,4,0),R588)=\"\",R588,IFERROR(VLOOKUP('AUP Library'!A588,'Updated Quanities'!F:I,4,0),R588))","v":7980},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A588,'Updated Quanities'!F:I,5,0),R588)=\"\",R588,IFERROR(VLOOKUP('AUP Library'!A588,'Updated Quanities'!F:I,5,0),R588))","v":7980},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A588,'Updated Quanities'!F:I,6,0),R588)=\"\",R588,IFERROR(VLOOKUP('AUP Library'!A588,'Updated Quanities'!F:I,6,0),R588))","v":7980},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A588,'Updated Quanities'!F:I,7,0),R588)=\"\",R588,IFERROR(VLOOKUP('AUP Library'!A588,'Updated Quanities'!F:I,7,0),R588))","v":7980},7980,{"$f":"IFERROR(VLOOKUP('AUP Library'!A588,'Updated Quanities'!F:G,4,0),R588)","v":7980}]
["621-01.03","Temporary Structure","LS",9975,9975,9975,9975,9975,9975,9975,9975,9975,9975,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A589,'Updated Quanities'!F:I,4,0),R589)=\"\",R589,IFERROR(VLOOKUP('AUP Library'!A589,'Updated Quanities'!F:I,4,0),R589))","v":9975},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A589,'Updated Quanities'!F:I,5,0),R589)=\"\",R589,IFERROR(VLOOKUP('AUP Library'!A589,'Updated Quanities'!F:I,5,0),R589))","v":9975},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A589,'Updated Quanities'!F:I,6,0),R589)=\"\",R589,IFERROR(VLOOKUP('AUP Library'!A589,'Updated Quanities'!F:I,6,0),R589))","v":9975},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A589,'Updated Quanities'!F:I,7,0),R589)=\"\",R589,IFERROR(VLOOKUP('AUP Library'!A589,'Updated Quanities'!F:I,7,0),R589))","v":9975},9975,{"$f":"IFERROR(VLOOKUP('AUP Library'!A589,'Updated Quanities'!F:G,4,0),R589)","v":9975}]
["621-01.04","Temporary Structure","LS",20000,20000,20000,20000,20000,20000,20000,20000,20000,20000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A590,'Updated Quanities'!F:I,4,0),R590)=\"\",R590,IFERROR(VLOOKUP('AUP Library'!A590,'Updated Quanities'!F:I,4,0),R590))","v":20000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A590,'Updated Quanities'!F:I,5,0),R590)=\"\",R590,IFERROR(VLOOKUP('AUP Library'!A590,'Updated Quanities'!F:I,5,0),R590))","v":20000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A590,'Updated Quanities'!F:I,6,0),R590)=\"\",R590,IFERROR(VLOOKUP('AUP Library'!A590,'Updated Quanities'!F:I,6,0),R590))","v":20000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A590,'Updated Quanities'!F:I,7,0),R590)=\"\",R590,IFERROR(VLOOKUP('AUP Library'!A590,'Updated Quanities'!F:I,7,0),R590))","v":20000},20000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A590,'Updated Quanities'!F:G,4,0),R590)","v":20000}]
["621-01.05","Temporary Structure","LS",1599.01,1599.01,1599.01,1599.01,1599.01,1599.01,1599.01,1599.01,1599.01,1599.01,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A591,'Updated Quanities'!F:I,4,0),R591)=\"\",R591,IFERROR(VLOOKUP('AUP Library'!A591,'Updated Quanities'!F:I,4,0),R591))","v":1599.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A591,'Updated Quanities'!F:I,5,0),R591)=\"\",R591,IFERROR(VLOOKUP('AUP Library'!A591,'Updated Quanities'!F:I,5,0),R591))","v":1599.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A591,'Updated Quanities'!F:I,6,0),R591)=\"\",R591,IFERROR(VLOOKUP('AUP Library'!A591,'Updated Quanities'!F:I,6,0),R591))","v":1599.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A591,'Updated Quanities'!F:I,7,0),R591)=\"\",R591,IFERROR(VLOOKUP('AUP Library'!A591,'Updated Quanities'!F:I,7,0),R591))","v":1599.01},1599.01,{"$f":"IFERROR(VLOOKUP('AUP Library'!A591,'Updated Quanities'!F:G,4,0),R591)","v":1599.01}]
["621-01.06","Temporary Structure","LS",872.5,872.5,872.5,872.5,872.5,872.5,872.5,872.5,872.5,872.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A592,'Updated Quanities'!F:I,4,0),R592)=\"\",R592,IFERROR(VLOOKUP('AUP Library'!A592,'Updated Quanities'!F:I,4,0),R592))","v":872.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A592,'Updated Quanities'!F:I,5,0),R592)=\"\",R592,IFERROR(VLOOKUP('AUP Library'!A592,'Updated Quanities'!F:I,5,0),R592))","v":872.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A592,'Updated Quanities'!F:I,6,0),R592)=\"\",R592,IFERROR(VLOOKUP('AUP Library'!A592,'Updated Quanities'!F:I,6,0),R592))","v":872.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A592,'Updated Quanities'!F:I,7,0),R592)=\"\",R592,IFERROR(VLOOKUP('AUP Library'!A592,'Updated Quanities'!F:I,7,0),R592))","v":872.5},872.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A592,'Updated Quanities'!F:G,4,0),R592)","v":872.5}]
["621-01.07","Temporary Structure","LS",840,840,840,840,840,840,840,840,840,840,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A593,'Updated Quanities'!F:I,4,0),R593)=\"\",R593,IFERROR(VLOOKUP('AUP Library'!A593,'Updated Quanities'!F:I,4,0),R593))","v":840},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A593,'Updated Quanities'!F:I,5,0),R593)=\"\",R593,IFERROR(VLOOKUP('AUP Library'!A593,'Updated Quanities'!F:I,5,0),R593))","v":840},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A593,'Updated Quanities'!F:I,6,0),R593)=\"\",R593,IFERROR(VLOOKUP('AUP Library'!A593,'Updated Quanities'!F:I,6,0),R593))","v":840},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A593,'Updated Quanities'!F:I,7,0),R593)=\"\",R593,IFERROR(VLOOKUP('AUP Library'!A593,'Updated Quanities'!F:I,7,0),R593))","v":840},840,{"$f":"IFERROR(VLOOKUP('AUP Library'!A593,'Updated Quanities'!F:G,4,0),R593)","v":840}]
["621-01.08","Temporary Structure","LS",810,810,810,810,810,810,810,810,810,810,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A594,'Updated Quanities'!F:I,4,0),R594)=\"\",R594,IFERROR(VLOOKUP('AUP Library'!A594,'Updated Quanities'!F:I,4,0),R594))","v":810},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A594,'Updated Quanities'!F:I,5,0),R594)=\"\",R594,IFERROR(VLOOKUP('AUP Library'!A594,'Updated Quanities'!F:I,5,0),R594))","v":810},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A594,'Updated Quanities'!F:I,6,0),R594)=\"\",R594,IFERROR(VLOOKUP('AUP Library'!A594,'Updated Quanities'!F:I,6,0),R594))","v":810},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A594,'Updated Quanities'!F:I,7,0),R594)=\"\",R594,IFERROR(VLOOKUP('AUP Library'!A594,'Updated Quanities'!F:I,7,0),R594))","v":810},810,{"$f":"IFERROR(VLOOKUP('AUP Library'!A594,'Updated Quanities'!F:G,4,0),R594)","v":810}]
["621-01.09","Temporary Structure","LS",1370,1370,1370,1370,1370,1370,1370,1370,1370,1370,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A595,'Updated Quanities'!F:I,4,0),R595)=\"\",R595,IFERROR(VLOOKUP('AUP Library'!A595,'Updated Quanities'!F:I,4,0),R595))","v":1370},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A595,'Updated Quanities'!F:I,5,0),R595)=\"\",R595,IFERROR(VLOOKUP('AUP Library'!A595,'Updated Quanities'!F:I,5,0),R595))","v":1370},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A595,'Updated Quanities'!F:I,6,0),R595)=\"\",R595,IFERROR(VLOOKUP('AUP Library'!A595,'Updated Quanities'!F:I,6,0),R595))","v":1370},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A595,'Updated Quanities'!F:I,7,0),R595)=\"\",R595,IFERROR(VLOOKUP('AUP Library'!A595,'Updated Quanities'!F:I,7,0),R595))","v":1370},1370,{"$f":"IFERROR(VLOOKUP('AUP Library'!A595,'Updated Quanities'!F:G,4,0),R595)","v":1370}]
["621-01.10","Temporary Structure","LS",1210,1210,1210,1210,1210,1210,1210,1210,1210,1210,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A596,'Updated Quanities'!F:I,4,0),R596)=\"\",R596,IFERROR(VLOOKUP('AUP Library'!A596,'Updated Quanities'!F:I,4,0),R596))","v":1210},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A596,'Updated Quanities'!F:I,5,0),R596)=\"\",R596,IFERROR(VLOOKUP('AUP Library'!A596,'Updated Quanities'!F:I,5,0),R596))","v":1210},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A596,'Updated Quanities'!F:I,6,0),R596)=\"\",R596,IFERROR(VLOOKUP('AUP Library'!A596,'Updated Quanities'!F:I,6,0),R596))","v":1210},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A596,'Updated Quanities'!F:I,7,0),R596)=\"\",R596,IFERROR(VLOOKUP('AUP Library'!A596,'Updated Quanities'!F:I,7,0),R596))","v":1210},1210,{"$f":"IFERROR(VLOOKUP('AUP Library'!A596,'Updated Quanities'!F:G,4,0),R596)","v":1210}]
["N/A","Removal of Bridge","SF"]
["N/A","Widen Existing Bridge (Box):","SF"]
["N/A","Widen Existing Bridge (Concrete Girder):","SF"]
["N/A","Widen Existing Bridge (Steel Girder):","SF"]
["N/A","New Bridge (Box):","SF"]
["N/A","New Bridge (Concrete Girder):","SF"]
["N/A","New Bridge (Steel Girder):","SF"]
["604-07.01","Retaining Wall","SF",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IFERROR(VLOOKUP('AUP Library'!A604,'Updated Quanities'!F:G,4,0),R604)","v":0}]
[]
[]
["Interchanges and Unique Intersections"]
["N/A","Roundabout","EA"]
["N/A","Urban Standard Diamond","EA"]
["N/A","Urban Tight Diamond","EA"]
["N/A","Urban - Single Point Urban Interchange","EA"]
["N/A","Rural - Diamond","EA"]
["N/A","Rural - Partial Cloverleaf","EA"]
["N/A","Rural - Cloverleaf","EA"]
[]
[]
["Traffic Signal & Lighting"]
["714-01.32","Structural Lighting","LS",9743.2900000000009,9743.2900000000009,9743.2900000000009,9743.2900000000009,9743.2900000000009,9743.2900000000009,9743.2900000000009,9743.2900000000009,9743.2900000000009,9743.2900000000009,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A618,'Updated Quanities'!F:I,4,0),R618)=\"\",R618,IFERROR(VLOOKUP('AUP Library'!A618,'Updated Quanities'!F:I,4,0),R618))","v":9743.2900000000009},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A618,'Updated Quanities'!F:I,5,0),R618)=\"\",R618,IFERROR(VLOOKUP('AUP Library'!A618,'Updated Quanities'!F:I,5,0),R618))","v":9743.2900000000009},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A618,'Updated Quanities'!F:I,6,0),R618)=\"\",R618,IFERROR(VLOOKUP('AUP Library'!A618,'Updated Quanities'!F:I,6,0),R618))","v":9743.2900000000009},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A618,'Updated Quanities'!F:I,7,0),R618)=\"\",R618,IFERROR(VLOOKUP('AUP Library'!A618,'Updated Quanities'!F:I,7,0),R618))","v":9743.2900000000009},9743.2900000000009,{"$f":"IFERROR(VLOOKUP('AUP Library'!A618,'Updated Quanities'!F:G,4,0),R618)","v":9743.2900000000009}]
["714-01.38","Light Pole Relocation","EA",1561.78,1561.78,1561.78,1561.78,1561.78,1561.78,1561.78,1561.78,1561.78,1561.78,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A619,'Updated Quanities'!F:I,4,0),R619)=\"\",R619,IFERROR(VLOOKUP('AUP Library'!A619,'Updated Quanities'!F:I,4,0),R619))","v":1561.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A619,'Updated Quanities'!F:I,5,0),R619)=\"\",R619,IFERROR(VLOOKUP('AUP Library'!A619,'Updated Quanities'!F:I,5,0),R619))","v":1561.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A619,'Updated Quanities'!F:I,6,0),R619)=\"\",R619,IFERROR(VLOOKUP('AUP Library'!A619,'Updated Quanities'!F:I,6,0),R619))","v":1561.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A619,'Updated Quanities'!F:I,7,0),R619)=\"\",R619,IFERROR(VLOOKUP('AUP Library'!A619,'Updated Quanities'!F:I,7,0),R619))","v":1561.78},1561.78,{"$f":"IFERROR(VLOOKUP('AUP Library'!A619,'Updated Quanities'!F:G,4,0),R619)","v":1561.78}]
["714-03","Jacked or Bored Conduit","LF",16.239999999999998,16.239999999999998,16.239999999999998,16.239999999999998,16.239999999999998,16.239999999999998,16.239999999999998,16.239999999999998,16.239999999999998,16.239999999999998,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A620,'Updated Quanities'!F:I,4,0),R620)=\"\",R620,IFERROR(VLOOKUP('AUP Library'!A620,'Updated Quanities'!F:I,4,0),R620))","v":16.239999999999998},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A620,'Updated Quanities'!F:I,5,0),R620)=\"\",R620,IFERROR(VLOOKUP('AUP Library'!A620,'Updated Quanities'!F:I,5,0),R620))","v":16.239999999999998},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A620,'Updated Quanities'!F:I,6,0),R620)=\"\",R620,IFERROR(VLOOKUP('AUP Library'!A620,'Updated Quanities'!F:I,6,0),R620))","v":16.239999999999998},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A620,'Updated Quanities'!F:I,7,0),R620)=\"\",R620,IFERROR(VLOOKUP('AUP Library'!A620,'Updated Quanities'!F:I,7,0),R620))","v":16.239999999999998},16.239999999999998,{"$f":"IFERROR(VLOOKUP('AUP Library'!A620,'Updated Quanities'!F:G,4,0),R620)","v":16.239999999999998}]
["714-03.01","Direct Brl Conduit (2\" PVC, Schedule 40)","LF",5.96,5.96,5.96,5.96,5.96,5.96,5.96,5.96,5.96,5.96,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A621,'Updated Quanities'!F:I,4,0),R621)=\"\",R621,IFERROR(VLOOKUP('AUP Library'!A621,'Updated Quanities'!F:I,4,0),R621))","v":5.96},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A621,'Updated Quanities'!F:I,5,0),R621)=\"\",R621,IFERROR(VLOOKUP('AUP Library'!A621,'Updated Quanities'!F:I,5,0),R621))","v":5.96},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A621,'Updated Quanities'!F:I,6,0),R621)=\"\",R621,IFERROR(VLOOKUP('AUP Library'!A621,'Updated Quanities'!F:I,6,0),R621))","v":5.96},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A621,'Updated Quanities'!F:I,7,0),R621)=\"\",R621,IFERROR(VLOOKUP('AUP Library'!A621,'Updated Quanities'!F:I,7,0),R621))","v":5.96},5.96,{"$f":"IFERROR(VLOOKUP('AUP Library'!A621,'Updated Quanities'!F:G,4,0),R621)","v":5.96}]
["714-03.03","Direct Burial Conduit","LF",8.16,8.16,8.16,8.16,8.16,8.16,8.16,8.16,8.16,8.16,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A622,'Updated Quanities'!F:I,4,0),R622)=\"\",R622,IFERROR(VLOOKUP('AUP Library'!A622,'Updated Quanities'!F:I,4,0),R622))","v":8.16},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A622,'Updated Quanities'!F:I,5,0),R622)=\"\",R622,IFERROR(VLOOKUP('AUP Library'!A622,'Updated Quanities'!F:I,5,0),R622))","v":8.16},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A622,'Updated Quanities'!F:I,6,0),R622)=\"\",R622,IFERROR(VLOOKUP('AUP Library'!A622,'Updated Quanities'!F:I,6,0),R622))","v":8.16},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A622,'Updated Quanities'!F:I,7,0),R622)=\"\",R622,IFERROR(VLOOKUP('AUP Library'!A622,'Updated Quanities'!F:I,7,0),R622))","v":8.16},8.16,{"$f":"IFERROR(VLOOKUP('AUP Library'!A622,'Updated Quanities'!F:G,4,0),R622)","v":8.16}]
["714-04.02","Conduit (Structures - 2\" RGS)","LF",11.72,11.72,11.72,11.72,11.72,11.72,11.72,11.72,11.72,11.72,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A623,'Updated Quanities'!F:I,4,0),R623)=\"\",R623,IFERROR(VLOOKUP('AUP Library'!A623,'Updated Quanities'!F:I,4,0),R623))","v":11.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A623,'Updated Quanities'!F:I,5,0),R623)=\"\",R623,IFERROR(VLOOKUP('AUP Library'!A623,'Updated Quanities'!F:I,5,0),R623))","v":11.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A623,'Updated Quanities'!F:I,6,0),R623)=\"\",R623,IFERROR(VLOOKUP('AUP Library'!A623,'Updated Quanities'!F:I,6,0),R623))","v":11.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A623,'Updated Quanities'!F:I,7,0),R623)=\"\",R623,IFERROR(VLOOKUP('AUP Library'!A623,'Updated Quanities'!F:I,7,0),R623))","v":11.72},11.72,{"$f":"IFERROR(VLOOKUP('AUP Library'!A623,'Updated Quanities'!F:G,4,0),R623)","v":11.72}]
["714-04.03","Conduit","LF",9,9,9,9,9,9,9,9,9,9,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A624,'Updated Quanities'!F:I,4,0),R624)=\"\",R624,IFERROR(VLOOKUP('AUP Library'!A624,'Updated Quanities'!F:I,4,0),R624))","v":9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A624,'Updated Quanities'!F:I,5,0),R624)=\"\",R624,IFERROR(VLOOKUP('AUP Library'!A624,'Updated Quanities'!F:I,5,0),R624))","v":9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A624,'Updated Quanities'!F:I,6,0),R624)=\"\",R624,IFERROR(VLOOKUP('AUP Library'!A624,'Updated Quanities'!F:I,6,0),R624))","v":9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A624,'Updated Quanities'!F:I,7,0),R624)=\"\",R624,IFERROR(VLOOKUP('AUP Library'!A624,'Updated Quanities'!F:I,7,0),R624))","v":9},9,{"$f":"IFERROR(VLOOKUP('AUP Library'!A624,'Updated Quanities'!F:G,4,0),R624)","v":9}]
["714-04.04","Conduit","LF",78,78,78,78,78,78,78,78,78,78,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A625,'Updated Quanities'!F:I,4,0),R625)=\"\",R625,IFERROR(VLOOKUP('AUP Library'!A625,'Updated Quanities'!F:I,4,0),R625))","v":78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A625,'Updated Quanities'!F:I,5,0),R625)=\"\",R625,IFERROR(VLOOKUP('AUP Library'!A625,'Updated Quanities'!F:I,5,0),R625))","v":78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A625,'Updated Quanities'!F:I,6,0),R625)=\"\",R625,IFERROR(VLOOKUP('AUP Library'!A625,'Updated Quanities'!F:I,6,0),R625))","v":78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A625,'Updated Quanities'!F:I,7,0),R625)=\"\",R625,IFERROR(VLOOKUP('AUP Library'!A625,'Updated Quanities'!F:I,7,0),R625))","v":78},78,{"$f":"IFERROR(VLOOKUP('AUP Library'!A625,'Updated Quanities'!F:G,4,0),R625)","v":78}]
["714-05.02","Pull Boxes (Type A)","EA",431.67,431.67,431.67,431.67,431.67,431.67,431.67,431.67,431.67,431.67,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A626,'Updated Quanities'!F:I,4,0),R626)=\"\",R626,IFERROR(VLOOKUP('AUP Library'!A626,'Updated Quanities'!F:I,4,0),R626))","v":431.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A626,'Updated Quanities'!F:I,5,0),R626)=\"\",R626,IFERROR(VLOOKUP('AUP Library'!A626,'Updated Quanities'!F:I,5,0),R626))","v":431.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A626,'Updated Quanities'!F:I,6,0),R626)=\"\",R626,IFERROR(VLOOKUP('AUP Library'!A626,'Updated Quanities'!F:I,6,0),R626))","v":431.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A626,'Updated Quanities'!F:I,7,0),R626)=\"\",R626,IFERROR(VLOOKUP('AUP Library'!A626,'Updated Quanities'!F:I,7,0),R626))","v":431.67},431.67,{"$f":"IFERROR(VLOOKUP('AUP Library'!A626,'Updated Quanities'!F:G,4,0),R626)","v":431.67}]
["714-05.03","Pull Boxes (Type B)","EA",375.69,375.69,375.69,375.69,375.69,375.69,375.69,375.69,375.69,375.69,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A627,'Updated Quanities'!F:I,4,0),R627)=\"\",R627,IFERROR(VLOOKUP('AUP Library'!A627,'Updated Quanities'!F:I,4,0),R627))","v":375.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A627,'Updated Quanities'!F:I,5,0),R627)=\"\",R627,IFERROR(VLOOKUP('AUP Library'!A627,'Updated Quanities'!F:I,5,0),R627))","v":375.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A627,'Updated Quanities'!F:I,6,0),R627)=\"\",R627,IFERROR(VLOOKUP('AUP Library'!A627,'Updated Quanities'!F:I,6,0),R627))","v":375.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A627,'Updated Quanities'!F:I,7,0),R627)=\"\",R627,IFERROR(VLOOKUP('AUP Library'!A627,'Updated Quanities'!F:I,7,0),R627))","v":375.69},375.69,{"$f":"IFERROR(VLOOKUP('AUP Library'!A627,'Updated Quanities'!F:G,4,0),R627)","v":375.69}]
["714-05.04","Pull Boxes (Type C)","EA",640.91,640.91,640.91,640.91,640.91,640.91,640.91,640.91,640.91,640.91,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A628,'Updated Quanities'!F:I,4,0),R628)=\"\",R628,IFERROR(VLOOKUP('AUP Library'!A628,'Updated Quanities'!F:I,4,0),R628))","v":640.91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A628,'Updated Quanities'!F:I,5,0),R628)=\"\",R628,IFERROR(VLOOKUP('AUP Library'!A628,'Updated Quanities'!F:I,5,0),R628))","v":640.91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A628,'Updated Quanities'!F:I,6,0),R628)=\"\",R628,IFERROR(VLOOKUP('AUP Library'!A628,'Updated Quanities'!F:I,6,0),R628))","v":640.91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A628,'Updated Quanities'!F:I,7,0),R628)=\"\",R628,IFERROR(VLOOKUP('AUP Library'!A628,'Updated Quanities'!F:I,7,0),R628))","v":640.91},640.91,{"$f":"IFERROR(VLOOKUP('AUP Library'!A628,'Updated Quanities'!F:G,4,0),R628)","v":640.91}]
["714-05.05","Pull Boxes","EA",468.5,468.5,468.5,468.5,468.5,468.5,468.5,468.5,468.5,468.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A629,'Updated Quanities'!F:I,4,0),R629)=\"\",R629,IFERROR(VLOOKUP('AUP Library'!A629,'Updated Quanities'!F:I,4,0),R629))","v":468.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A629,'Updated Quanities'!F:I,5,0),R629)=\"\",R629,IFERROR(VLOOKUP('AUP Library'!A629,'Updated Quanities'!F:I,5,0),R629))","v":468.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A629,'Updated Quanities'!F:I,6,0),R629)=\"\",R629,IFERROR(VLOOKUP('AUP Library'!A629,'Updated Quanities'!F:I,6,0),R629))","v":468.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A629,'Updated Quanities'!F:I,7,0),R629)=\"\",R629,IFERROR(VLOOKUP('AUP Library'!A629,'Updated Quanities'!F:I,7,0),R629))","v":468.5},468.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A629,'Updated Quanities'!F:G,4,0),R629)","v":468.5}]
["714-05.06","Pull Boxes (Memphis Standard)","EA",468.5,468.5,468.5,468.5,468.5,468.5,468.5,468.5,468.5,468.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A630,'Updated Quanities'!F:I,4,0),R630)=\"\",R630,IFERROR(VLOOKUP('AUP Library'!A630,'Updated Quanities'!F:I,4,0),R630))","v":468.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A630,'Updated Quanities'!F:I,5,0),R630)=\"\",R630,IFERROR(VLOOKUP('AUP Library'!A630,'Updated Quanities'!F:I,5,0),R630))","v":468.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A630,'Updated Quanities'!F:I,6,0),R630)=\"\",R630,IFERROR(VLOOKUP('AUP Library'!A630,'Updated Quanities'!F:I,6,0),R630))","v":468.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A630,'Updated Quanities'!F:I,7,0),R630)=\"\",R630,IFERROR(VLOOKUP('AUP Library'!A630,'Updated Quanities'!F:I,7,0),R630))","v":468.5},468.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A630,'Updated Quanities'!F:G,4,0),R630)","v":468.5}]
["714-05.15","Electric Manhole","EA",5970,5970,5970,5970,5970,5970,5970,5970,5970,5970,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A631,'Updated Quanities'!F:I,4,0),R631)=\"\",R631,IFERROR(VLOOKUP('AUP Library'!A631,'Updated Quanities'!F:I,4,0),R631))","v":5970},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A631,'Updated Quanities'!F:I,5,0),R631)=\"\",R631,IFERROR(VLOOKUP('AUP Library'!A631,'Updated Quanities'!F:I,5,0),R631))","v":5970},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A631,'Updated Quanities'!F:I,6,0),R631)=\"\",R631,IFERROR(VLOOKUP('AUP Library'!A631,'Updated Quanities'!F:I,6,0),R631))","v":5970},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A631,'Updated Quanities'!F:I,7,0),R631)=\"\",R631,IFERROR(VLOOKUP('AUP Library'!A631,'Updated Quanities'!F:I,7,0),R631))","v":5970},5970,{"$f":"IFERROR(VLOOKUP('AUP Library'!A631,'Updated Quanities'!F:G,4,0),R631)","v":5970}]
["714-06.02","Cable (1/C # 12 AWG)","LF",0.35,0.35,0.35,0.35,0.35,0.35,0.35,0.35,0.35,0.35,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A632,'Updated Quanities'!F:I,4,0),R632)=\"\",R632,IFERROR(VLOOKUP('AUP Library'!A632,'Updated Quanities'!F:I,4,0),R632))","v":0.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A632,'Updated Quanities'!F:I,5,0),R632)=\"\",R632,IFERROR(VLOOKUP('AUP Library'!A632,'Updated Quanities'!F:I,5,0),R632))","v":0.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A632,'Updated Quanities'!F:I,6,0),R632)=\"\",R632,IFERROR(VLOOKUP('AUP Library'!A632,'Updated Quanities'!F:I,6,0),R632))","v":0.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A632,'Updated Quanities'!F:I,7,0),R632)=\"\",R632,IFERROR(VLOOKUP('AUP Library'!A632,'Updated Quanities'!F:I,7,0),R632))","v":0.35},0.35,{"$f":"IFERROR(VLOOKUP('AUP Library'!A632,'Updated Quanities'!F:G,4,0),R632)","v":0.35}]
["714-06.03","Cable (1/C # 10 AWG)","LF",1.78,1.78,1.78,1.78,1.78,1.78,1.78,1.78,1.78,1.78,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A633,'Updated Quanities'!F:I,4,0),R633)=\"\",R633,IFERROR(VLOOKUP('AUP Library'!A633,'Updated Quanities'!F:I,4,0),R633))","v":1.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A633,'Updated Quanities'!F:I,5,0),R633)=\"\",R633,IFERROR(VLOOKUP('AUP Library'!A633,'Updated Quanities'!F:I,5,0),R633))","v":1.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A633,'Updated Quanities'!F:I,6,0),R633)=\"\",R633,IFERROR(VLOOKUP('AUP Library'!A633,'Updated Quanities'!F:I,6,0),R633))","v":1.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A633,'Updated Quanities'!F:I,7,0),R633)=\"\",R633,IFERROR(VLOOKUP('AUP Library'!A633,'Updated Quanities'!F:I,7,0),R633))","v":1.78},1.78,{"$f":"IFERROR(VLOOKUP('AUP Library'!A633,'Updated Quanities'!F:G,4,0),R633)","v":1.78}]
["714-06.04","Cable (1/C # 8 AWG)","LF",0.69,0.69,0.69,0.69,0.69,0.69,0.69,0.69,0.69,0.69,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A634,'Updated Quanities'!F:I,4,0),R634)=\"\",R634,IFERROR(VLOOKUP('AUP Library'!A634,'Updated Quanities'!F:I,4,0),R634))","v":0.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A634,'Updated Quanities'!F:I,5,0),R634)=\"\",R634,IFERROR(VLOOKUP('AUP Library'!A634,'Updated Quanities'!F:I,5,0),R634))","v":0.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A634,'Updated Quanities'!F:I,6,0),R634)=\"\",R634,IFERROR(VLOOKUP('AUP Library'!A634,'Updated Quanities'!F:I,6,0),R634))","v":0.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A634,'Updated Quanities'!F:I,7,0),R634)=\"\",R634,IFERROR(VLOOKUP('AUP Library'!A634,'Updated Quanities'!F:I,7,0),R634))","v":0.69},0.69,{"$f":"IFERROR(VLOOKUP('AUP Library'!A634,'Updated Quanities'!F:G,4,0),R634)","v":0.69}]
["714-06.05","Cable (1/C # 6 AWG)","LF",1.05,1.05,1.05,1.05,1.05,1.05,1.05,1.05,1.05,1.05,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A635,'Updated Quanities'!F:I,4,0),R635)=\"\",R635,IFERROR(VLOOKUP('AUP Library'!A635,'Updated Quanities'!F:I,4,0),R635))","v":1.05},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A635,'Updated Quanities'!F:I,5,0),R635)=\"\",R635,IFERROR(VLOOKUP('AUP Library'!A635,'Updated Quanities'!F:I,5,0),R635))","v":1.05},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A635,'Updated Quanities'!F:I,6,0),R635)=\"\",R635,IFERROR(VLOOKUP('AUP Library'!A635,'Updated Quanities'!F:I,6,0),R635))","v":1.05},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A635,'Updated Quanities'!F:I,7,0),R635)=\"\",R635,IFERROR(VLOOKUP('AUP Library'!A635,'Updated Quanities'!F:I,7,0),R635))","v":1.05},1.05,{"$f":"IFERROR(VLOOKUP('AUP Library'!A635,'Updated Quanities'!F:G,4,0),R635)","v":1.05}]
["714-06.06","Cable (1/C # 4 AWG)","LF",1.65,1.65,1.65,1.65,1.65,1.65,1.65,1.65,1.65,1.65,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A636,'Updated Quanities'!F:I,4,0),R636)=\"\",R636,IFERROR(VLOOKUP('AUP Library'!A636,'Updated Quanities'!F:I,4,0),R636))","v":1.65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A636,'Updated Quanities'!F:I,5,0),R636)=\"\",R636,IFERROR(VLOOKUP('AUP Library'!A636,'Updated Quanities'!F:I,5,0),R636))","v":1.65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A636,'Updated Quanities'!F:I,6,0),R636)=\"\",R636,IFERROR(VLOOKUP('AUP Library'!A636,'Updated Quanities'!F:I,6,0),R636))","v":1.65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A636,'Updated Quanities'!F:I,7,0),R636)=\"\",R636,IFERROR(VLOOKUP('AUP Library'!A636,'Updated Quanities'!F:I,7,0),R636))","v":1.65},1.65,{"$f":"IFERROR(VLOOKUP('AUP Library'!A636,'Updated Quanities'!F:G,4,0),R636)","v":1.65}]
["714-06.07","Cable (1/C # 2 AWG)","LF",1.65,1.65,1.65,1.65,1.65,1.65,1.65,1.65,1.65,1.65,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A637,'Updated Quanities'!F:I,4,0),R637)=\"\",R637,IFERROR(VLOOKUP('AUP Library'!A637,'Updated Quanities'!F:I,4,0),R637))","v":1.65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A637,'Updated Quanities'!F:I,5,0),R637)=\"\",R637,IFERROR(VLOOKUP('AUP Library'!A637,'Updated Quanities'!F:I,5,0),R637))","v":1.65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A637,'Updated Quanities'!F:I,6,0),R637)=\"\",R637,IFERROR(VLOOKUP('AUP Library'!A637,'Updated Quanities'!F:I,6,0),R637))","v":1.65},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A637,'Updated Quanities'!F:I,7,0),R637)=\"\",R637,IFERROR(VLOOKUP('AUP Library'!A637,'Updated Quanities'!F:I,7,0),R637))","v":1.65},1.65,{"$f":"IFERROR(VLOOKUP('AUP Library'!A637,'Updated Quanities'!F:G,4,0),R637)","v":1.65}]
["714-06.08","Cable","LF",3.94,3.94,3.94,3.94,3.94,3.94,3.94,3.94,3.94,3.94,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A638,'Updated Quanities'!F:I,4,0),R638)=\"\",R638,IFERROR(VLOOKUP('AUP Library'!A638,'Updated Quanities'!F:I,4,0),R638))","v":3.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A638,'Updated Quanities'!F:I,5,0),R638)=\"\",R638,IFERROR(VLOOKUP('AUP Library'!A638,'Updated Quanities'!F:I,5,0),R638))","v":3.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A638,'Updated Quanities'!F:I,6,0),R638)=\"\",R638,IFERROR(VLOOKUP('AUP Library'!A638,'Updated Quanities'!F:I,6,0),R638))","v":3.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A638,'Updated Quanities'!F:I,7,0),R638)=\"\",R638,IFERROR(VLOOKUP('AUP Library'!A638,'Updated Quanities'!F:I,7,0),R638))","v":3.94},3.94,{"$f":"IFERROR(VLOOKUP('AUP Library'!A638,'Updated Quanities'!F:G,4,0),R638)","v":3.94}]
["714-06.09","Cable","LF",2.08,2.08,2.08,2.08,2.08,2.08,2.08,2.08,2.08,2.08,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A639,'Updated Quanities'!F:I,4,0),R639)=\"\",R639,IFERROR(VLOOKUP('AUP Library'!A639,'Updated Quanities'!F:I,4,0),R639))","v":2.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A639,'Updated Quanities'!F:I,5,0),R639)=\"\",R639,IFERROR(VLOOKUP('AUP Library'!A639,'Updated Quanities'!F:I,5,0),R639))","v":2.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A639,'Updated Quanities'!F:I,6,0),R639)=\"\",R639,IFERROR(VLOOKUP('AUP Library'!A639,'Updated Quanities'!F:I,6,0),R639))","v":2.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A639,'Updated Quanities'!F:I,7,0),R639)=\"\",R639,IFERROR(VLOOKUP('AUP Library'!A639,'Updated Quanities'!F:I,7,0),R639))","v":2.08},2.08,{"$f":"IFERROR(VLOOKUP('AUP Library'!A639,'Updated Quanities'!F:G,4,0),R639)","v":2.08}]
["714-06.10","Cable","LF",2.66,2.66,2.66,2.66,2.66,2.66,2.66,2.66,2.66,2.66,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A640,'Updated Quanities'!F:I,4,0),R640)=\"\",R640,IFERROR(VLOOKUP('AUP Library'!A640,'Updated Quanities'!F:I,4,0),R640))","v":2.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A640,'Updated Quanities'!F:I,5,0),R640)=\"\",R640,IFERROR(VLOOKUP('AUP Library'!A640,'Updated Quanities'!F:I,5,0),R640))","v":2.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A640,'Updated Quanities'!F:I,6,0),R640)=\"\",R640,IFERROR(VLOOKUP('AUP Library'!A640,'Updated Quanities'!F:I,6,0),R640))","v":2.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A640,'Updated Quanities'!F:I,7,0),R640)=\"\",R640,IFERROR(VLOOKUP('AUP Library'!A640,'Updated Quanities'!F:I,7,0),R640))","v":2.66},2.66,{"$f":"IFERROR(VLOOKUP('AUP Library'!A640,'Updated Quanities'!F:G,4,0),R640)","v":2.66}]
["714-06.11","Cable","LF",1.82,1.82,1.82,1.82,1.82,1.82,1.82,1.82,1.82,1.82,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A641,'Updated Quanities'!F:I,4,0),R641)=\"\",R641,IFERROR(VLOOKUP('AUP Library'!A641,'Updated Quanities'!F:I,4,0),R641))","v":1.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A641,'Updated Quanities'!F:I,5,0),R641)=\"\",R641,IFERROR(VLOOKUP('AUP Library'!A641,'Updated Quanities'!F:I,5,0),R641))","v":1.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A641,'Updated Quanities'!F:I,6,0),R641)=\"\",R641,IFERROR(VLOOKUP('AUP Library'!A641,'Updated Quanities'!F:I,6,0),R641))","v":1.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A641,'Updated Quanities'!F:I,7,0),R641)=\"\",R641,IFERROR(VLOOKUP('AUP Library'!A641,'Updated Quanities'!F:I,7,0),R641))","v":1.82},1.82,{"$f":"IFERROR(VLOOKUP('AUP Library'!A641,'Updated Quanities'!F:G,4,0),R641)","v":1.82}]
["714-06.12","Cale","LF",1.6,1.6,1.6,1.6,1.6,1.6,1.6,1.6,1.6,1.6,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A642,'Updated Quanities'!F:I,4,0),R642)=\"\",R642,IFERROR(VLOOKUP('AUP Library'!A642,'Updated Quanities'!F:I,4,0),R642))","v":1.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A642,'Updated Quanities'!F:I,5,0),R642)=\"\",R642,IFERROR(VLOOKUP('AUP Library'!A642,'Updated Quanities'!F:I,5,0),R642))","v":1.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A642,'Updated Quanities'!F:I,6,0),R642)=\"\",R642,IFERROR(VLOOKUP('AUP Library'!A642,'Updated Quanities'!F:I,6,0),R642))","v":1.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A642,'Updated Quanities'!F:I,7,0),R642)=\"\",R642,IFERROR(VLOOKUP('AUP Library'!A642,'Updated Quanities'!F:I,7,0),R642))","v":1.6},1.6,{"$f":"IFERROR(VLOOKUP('AUP Library'!A642,'Updated Quanities'!F:G,4,0),R642)","v":1.6}]
["714-06.23","Cable (1/C #1 AWG)","LF",3,3,3,3,3,3,3,3,3,3,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A643,'Updated Quanities'!F:I,4,0),R643)=\"\",R643,IFERROR(VLOOKUP('AUP Library'!A643,'Updated Quanities'!F:I,4,0),R643))","v":3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A643,'Updated Quanities'!F:I,5,0),R643)=\"\",R643,IFERROR(VLOOKUP('AUP Library'!A643,'Updated Quanities'!F:I,5,0),R643))","v":3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A643,'Updated Quanities'!F:I,6,0),R643)=\"\",R643,IFERROR(VLOOKUP('AUP Library'!A643,'Updated Quanities'!F:I,6,0),R643))","v":3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A643,'Updated Quanities'!F:I,7,0),R643)=\"\",R643,IFERROR(VLOOKUP('AUP Library'!A643,'Updated Quanities'!F:I,7,0),R643))","v":3},3,{"$f":"IFERROR(VLOOKUP('AUP Library'!A643,'Updated Quanities'!F:G,4,0),R643)","v":3}]
["714-06.24","Cable (1/C #3 AWG)","LF",2,2,2,2,2,2,2,2,2,2,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A644,'Updated Quanities'!F:I,4,0),R644)=\"\",R644,IFERROR(VLOOKUP('AUP Library'!A644,'Updated Quanities'!F:I,4,0),R644))","v":2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A644,'Updated Quanities'!F:I,5,0),R644)=\"\",R644,IFERROR(VLOOKUP('AUP Library'!A644,'Updated Quanities'!F:I,5,0),R644))","v":2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A644,'Updated Quanities'!F:I,6,0),R644)=\"\",R644,IFERROR(VLOOKUP('AUP Library'!A644,'Updated Quanities'!F:I,6,0),R644))","v":2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A644,'Updated Quanities'!F:I,7,0),R644)=\"\",R644,IFERROR(VLOOKUP('AUP Library'!A644,'Updated Quanities'!F:I,7,0),R644))","v":2},2,{"$f":"IFERROR(VLOOKUP('AUP Library'!A644,'Updated Quanities'!F:G,4,0),R644)","v":2}]
["714-08.01","Light Standards (45' MH, 15' ARM)","EA",3722.26,3722.26,3722.26,3722.26,3722.26,3722.26,3722.26,3722.26,3722.26,3722.26,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A645,'Updated Quanities'!F:I,4,0),R645)=\"\",R645,IFERROR(VLOOKUP('AUP Library'!A645,'Updated Quanities'!F:I,4,0),R645))","v":3722.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A645,'Updated Quanities'!F:I,5,0),R645)=\"\",R645,IFERROR(VLOOKUP('AUP Library'!A645,'Updated Quanities'!F:I,5,0),R645))","v":3722.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A645,'Updated Quanities'!F:I,6,0),R645)=\"\",R645,IFERROR(VLOOKUP('AUP Library'!A645,'Updated Quanities'!F:I,6,0),R645))","v":3722.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A645,'Updated Quanities'!F:I,7,0),R645)=\"\",R645,IFERROR(VLOOKUP('AUP Library'!A645,'Updated Quanities'!F:I,7,0),R645))","v":3722.26},3722.26,{"$f":"IFERROR(VLOOKUP('AUP Library'!A645,'Updated Quanities'!F:G,4,0),R645)","v":3722.26}]
["714-08.04","Light Standards (45' MH, 2 - 15' ARM)","EA",4785.76,4785.76,4785.76,4785.76,4785.76,4785.76,4785.76,4785.76,4785.76,4785.76,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A646,'Updated Quanities'!F:I,4,0),R646)=\"\",R646,IFERROR(VLOOKUP('AUP Library'!A646,'Updated Quanities'!F:I,4,0),R646))","v":4785.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A646,'Updated Quanities'!F:I,5,0),R646)=\"\",R646,IFERROR(VLOOKUP('AUP Library'!A646,'Updated Quanities'!F:I,5,0),R646))","v":4785.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A646,'Updated Quanities'!F:I,6,0),R646)=\"\",R646,IFERROR(VLOOKUP('AUP Library'!A646,'Updated Quanities'!F:I,6,0),R646))","v":4785.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A646,'Updated Quanities'!F:I,7,0),R646)=\"\",R646,IFERROR(VLOOKUP('AUP Library'!A646,'Updated Quanities'!F:I,7,0),R646))","v":4785.76},4785.76,{"$f":"IFERROR(VLOOKUP('AUP Library'!A646,'Updated Quanities'!F:G,4,0),R646)","v":4785.76}]
["714-08.06","Light Standards (Steel)","EA",3900,3900,3900,3900,3900,3900,3900,3900,3900,3900,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A647,'Updated Quanities'!F:I,4,0),R647)=\"\",R647,IFERROR(VLOOKUP('AUP Library'!A647,'Updated Quanities'!F:I,4,0),R647))","v":3900},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A647,'Updated Quanities'!F:I,5,0),R647)=\"\",R647,IFERROR(VLOOKUP('AUP Library'!A647,'Updated Quanities'!F:I,5,0),R647))","v":3900},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A647,'Updated Quanities'!F:I,6,0),R647)=\"\",R647,IFERROR(VLOOKUP('AUP Library'!A647,'Updated Quanities'!F:I,6,0),R647))","v":3900},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A647,'Updated Quanities'!F:I,7,0),R647)=\"\",R647,IFERROR(VLOOKUP('AUP Library'!A647,'Updated Quanities'!F:I,7,0),R647))","v":3900},3900,{"$f":"IFERROR(VLOOKUP('AUP Library'!A647,'Updated Quanities'!F:G,4,0),R647)","v":3900}]
["714-08.09","Light Standards","EA",2982.76,2982.76,2982.76,2982.76,2982.76,2982.76,2982.76,2982.76,2982.76,2982.76,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A648,'Updated Quanities'!F:I,4,0),R648)=\"\",R648,IFERROR(VLOOKUP('AUP Library'!A648,'Updated Quanities'!F:I,4,0),R648))","v":2982.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A648,'Updated Quanities'!F:I,5,0),R648)=\"\",R648,IFERROR(VLOOKUP('AUP Library'!A648,'Updated Quanities'!F:I,5,0),R648))","v":2982.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A648,'Updated Quanities'!F:I,6,0),R648)=\"\",R648,IFERROR(VLOOKUP('AUP Library'!A648,'Updated Quanities'!F:I,6,0),R648))","v":2982.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A648,'Updated Quanities'!F:I,7,0),R648)=\"\",R648,IFERROR(VLOOKUP('AUP Library'!A648,'Updated Quanities'!F:I,7,0),R648))","v":2982.76},2982.76,{"$f":"IFERROR(VLOOKUP('AUP Library'!A648,'Updated Quanities'!F:G,4,0),R648)","v":2982.76}]
["714-08.10","Light Standards","EA",3072.37,3072.37,3072.37,3072.37,3072.37,3072.37,3072.37,3072.37,3072.37,3072.37,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A649,'Updated Quanities'!F:I,4,0),R649)=\"\",R649,IFERROR(VLOOKUP('AUP Library'!A649,'Updated Quanities'!F:I,4,0),R649))","v":3072.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A649,'Updated Quanities'!F:I,5,0),R649)=\"\",R649,IFERROR(VLOOKUP('AUP Library'!A649,'Updated Quanities'!F:I,5,0),R649))","v":3072.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A649,'Updated Quanities'!F:I,6,0),R649)=\"\",R649,IFERROR(VLOOKUP('AUP Library'!A649,'Updated Quanities'!F:I,6,0),R649))","v":3072.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A649,'Updated Quanities'!F:I,7,0),R649)=\"\",R649,IFERROR(VLOOKUP('AUP Library'!A649,'Updated Quanities'!F:I,7,0),R649))","v":3072.37},3072.37,{"$f":"IFERROR(VLOOKUP('AUP Library'!A649,'Updated Quanities'!F:G,4,0),R649)","v":3072.37}]
["714-08.11","Light Standards","EA",16963.64,16963.64,16963.64,16963.64,16963.64,16963.64,16963.64,16963.64,16963.64,16963.64,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A650,'Updated Quanities'!F:I,4,0),R650)=\"\",R650,IFERROR(VLOOKUP('AUP Library'!A650,'Updated Quanities'!F:I,4,0),R650))","v":16963.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A650,'Updated Quanities'!F:I,5,0),R650)=\"\",R650,IFERROR(VLOOKUP('AUP Library'!A650,'Updated Quanities'!F:I,5,0),R650))","v":16963.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A650,'Updated Quanities'!F:I,6,0),R650)=\"\",R650,IFERROR(VLOOKUP('AUP Library'!A650,'Updated Quanities'!F:I,6,0),R650))","v":16963.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A650,'Updated Quanities'!F:I,7,0),R650)=\"\",R650,IFERROR(VLOOKUP('AUP Library'!A650,'Updated Quanities'!F:I,7,0),R650))","v":16963.64},16963.64,{"$f":"IFERROR(VLOOKUP('AUP Library'!A650,'Updated Quanities'!F:G,4,0),R650)","v":16963.64}]
["714-08.12","Light Standards","EA",2950,2950,2950,2950,2950,2950,2950,2950,2950,2950,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A651,'Updated Quanities'!F:I,4,0),R651)=\"\",R651,IFERROR(VLOOKUP('AUP Library'!A651,'Updated Quanities'!F:I,4,0),R651))","v":2950},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A651,'Updated Quanities'!F:I,5,0),R651)=\"\",R651,IFERROR(VLOOKUP('AUP Library'!A651,'Updated Quanities'!F:I,5,0),R651))","v":2950},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A651,'Updated Quanities'!F:I,6,0),R651)=\"\",R651,IFERROR(VLOOKUP('AUP Library'!A651,'Updated Quanities'!F:I,6,0),R651))","v":2950},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A651,'Updated Quanities'!F:I,7,0),R651)=\"\",R651,IFERROR(VLOOKUP('AUP Library'!A651,'Updated Quanities'!F:I,7,0),R651))","v":2950},2950,{"$f":"IFERROR(VLOOKUP('AUP Library'!A651,'Updated Quanities'!F:G,4,0),R651)","v":2950}]
["714-08.13","Light Standards","EA",2055,2055,2055,2055,2055,2055,2055,2055,2055,2055,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A652,'Updated Quanities'!F:I,4,0),R652)=\"\",R652,IFERROR(VLOOKUP('AUP Library'!A652,'Updated Quanities'!F:I,4,0),R652))","v":2055},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A652,'Updated Quanities'!F:I,5,0),R652)=\"\",R652,IFERROR(VLOOKUP('AUP Library'!A652,'Updated Quanities'!F:I,5,0),R652))","v":2055},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A652,'Updated Quanities'!F:I,6,0),R652)=\"\",R652,IFERROR(VLOOKUP('AUP Library'!A652,'Updated Quanities'!F:I,6,0),R652))","v":2055},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A652,'Updated Quanities'!F:I,7,0),R652)=\"\",R652,IFERROR(VLOOKUP('AUP Library'!A652,'Updated Quanities'!F:I,7,0),R652))","v":2055},2055,{"$f":"IFERROR(VLOOKUP('AUP Library'!A652,'Updated Quanities'!F:G,4,0),R652)","v":2055}]
["714-08.14","Light Standards","EA",3000,3000,3000,3000,3000,3000,3000,3000,3000,3000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A653,'Updated Quanities'!F:I,4,0),R653)=\"\",R653,IFERROR(VLOOKUP('AUP Library'!A653,'Updated Quanities'!F:I,4,0),R653))","v":3000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A653,'Updated Quanities'!F:I,5,0),R653)=\"\",R653,IFERROR(VLOOKUP('AUP Library'!A653,'Updated Quanities'!F:I,5,0),R653))","v":3000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A653,'Updated Quanities'!F:I,6,0),R653)=\"\",R653,IFERROR(VLOOKUP('AUP Library'!A653,'Updated Quanities'!F:I,6,0),R653))","v":3000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A653,'Updated Quanities'!F:I,7,0),R653)=\"\",R653,IFERROR(VLOOKUP('AUP Library'!A653,'Updated Quanities'!F:I,7,0),R653))","v":3000},3000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A653,'Updated Quanities'!F:G,4,0),R653)","v":3000}]
["714-08.20","Foundation (Only) for Light Standard","EA",894.35,894.35,894.35,894.35,894.35,894.35,894.35,894.35,894.35,894.35,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A654,'Updated Quanities'!F:I,4,0),R654)=\"\",R654,IFERROR(VLOOKUP('AUP Library'!A654,'Updated Quanities'!F:I,4,0),R654))","v":894.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A654,'Updated Quanities'!F:I,5,0),R654)=\"\",R654,IFERROR(VLOOKUP('AUP Library'!A654,'Updated Quanities'!F:I,5,0),R654))","v":894.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A654,'Updated Quanities'!F:I,6,0),R654)=\"\",R654,IFERROR(VLOOKUP('AUP Library'!A654,'Updated Quanities'!F:I,6,0),R654))","v":894.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A654,'Updated Quanities'!F:I,7,0),R654)=\"\",R654,IFERROR(VLOOKUP('AUP Library'!A654,'Updated Quanities'!F:I,7,0),R654))","v":894.35},894.35,{"$f":"IFERROR(VLOOKUP('AUP Library'!A654,'Updated Quanities'!F:G,4,0),R654)","v":894.35}]
["714-08.26","Foundation for Light Stadards (Med Barr)","EA",6912.77,6912.77,6912.77,6912.77,6912.77,6912.77,6912.77,6912.77,6912.77,6912.77,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A655,'Updated Quanities'!F:I,4,0),R655)=\"\",R655,IFERROR(VLOOKUP('AUP Library'!A655,'Updated Quanities'!F:I,4,0),R655))","v":6912.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A655,'Updated Quanities'!F:I,5,0),R655)=\"\",R655,IFERROR(VLOOKUP('AUP Library'!A655,'Updated Quanities'!F:I,5,0),R655))","v":6912.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A655,'Updated Quanities'!F:I,6,0),R655)=\"\",R655,IFERROR(VLOOKUP('AUP Library'!A655,'Updated Quanities'!F:I,6,0),R655))","v":6912.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A655,'Updated Quanities'!F:I,7,0),R655)=\"\",R655,IFERROR(VLOOKUP('AUP Library'!A655,'Updated Quanities'!F:I,7,0),R655))","v":6912.77},6912.77,{"$f":"IFERROR(VLOOKUP('AUP Library'!A655,'Updated Quanities'!F:G,4,0),R655)","v":6912.77}]
["714-08.27","Found for Light Standards - High Mast","EA",11496,11496,11496,11496,11496,11496,11496,11496,11496,11496,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A656,'Updated Quanities'!F:I,4,0),R656)=\"\",R656,IFERROR(VLOOKUP('AUP Library'!A656,'Updated Quanities'!F:I,4,0),R656))","v":11496},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A656,'Updated Quanities'!F:I,5,0),R656)=\"\",R656,IFERROR(VLOOKUP('AUP Library'!A656,'Updated Quanities'!F:I,5,0),R656))","v":11496},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A656,'Updated Quanities'!F:I,6,0),R656)=\"\",R656,IFERROR(VLOOKUP('AUP Library'!A656,'Updated Quanities'!F:I,6,0),R656))","v":11496},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A656,'Updated Quanities'!F:I,7,0),R656)=\"\",R656,IFERROR(VLOOKUP('AUP Library'!A656,'Updated Quanities'!F:I,7,0),R656))","v":11496},11496,{"$f":"IFERROR(VLOOKUP('AUP Library'!A656,'Updated Quanities'!F:G,4,0),R656)","v":11496}]
["714-08.28","Found for Light Standards - Roadway","EA",1384.42,1384.42,1384.42,1384.42,1384.42,1384.42,1384.42,1384.42,1384.42,1384.42,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A657,'Updated Quanities'!F:I,4,0),R657)=\"\",R657,IFERROR(VLOOKUP('AUP Library'!A657,'Updated Quanities'!F:I,4,0),R657))","v":1384.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A657,'Updated Quanities'!F:I,5,0),R657)=\"\",R657,IFERROR(VLOOKUP('AUP Library'!A657,'Updated Quanities'!F:I,5,0),R657))","v":1384.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A657,'Updated Quanities'!F:I,6,0),R657)=\"\",R657,IFERROR(VLOOKUP('AUP Library'!A657,'Updated Quanities'!F:I,6,0),R657))","v":1384.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A657,'Updated Quanities'!F:I,7,0),R657)=\"\",R657,IFERROR(VLOOKUP('AUP Library'!A657,'Updated Quanities'!F:I,7,0),R657))","v":1384.42},1384.42,{"$f":"IFERROR(VLOOKUP('AUP Library'!A657,'Updated Quanities'!F:G,4,0),R657)","v":1384.42}]
["714-08.30","Remove and Relocate Light Standard","EA",2046.75,2046.75,2046.75,2046.75,2046.75,2046.75,2046.75,2046.75,2046.75,2046.75,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A658,'Updated Quanities'!F:I,4,0),R658)=\"\",R658,IFERROR(VLOOKUP('AUP Library'!A658,'Updated Quanities'!F:I,4,0),R658))","v":2046.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A658,'Updated Quanities'!F:I,5,0),R658)=\"\",R658,IFERROR(VLOOKUP('AUP Library'!A658,'Updated Quanities'!F:I,5,0),R658))","v":2046.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A658,'Updated Quanities'!F:I,6,0),R658)=\"\",R658,IFERROR(VLOOKUP('AUP Library'!A658,'Updated Quanities'!F:I,6,0),R658))","v":2046.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A658,'Updated Quanities'!F:I,7,0),R658)=\"\",R658,IFERROR(VLOOKUP('AUP Library'!A658,'Updated Quanities'!F:I,7,0),R658))","v":2046.75},2046.75,{"$f":"IFERROR(VLOOKUP('AUP Library'!A658,'Updated Quanities'!F:G,4,0),R658)","v":2046.75}]
["714-08.32","Removal of Light Standard & Foundation","EA",262.37,262.37,262.37,262.37,262.37,262.37,262.37,262.37,262.37,262.37,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A659,'Updated Quanities'!F:I,4,0),R659)=\"\",R659,IFERROR(VLOOKUP('AUP Library'!A659,'Updated Quanities'!F:I,4,0),R659))","v":262.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A659,'Updated Quanities'!F:I,5,0),R659)=\"\",R659,IFERROR(VLOOKUP('AUP Library'!A659,'Updated Quanities'!F:I,5,0),R659))","v":262.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A659,'Updated Quanities'!F:I,6,0),R659)=\"\",R659,IFERROR(VLOOKUP('AUP Library'!A659,'Updated Quanities'!F:I,6,0),R659))","v":262.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A659,'Updated Quanities'!F:I,7,0),R659)=\"\",R659,IFERROR(VLOOKUP('AUP Library'!A659,'Updated Quanities'!F:I,7,0),R659))","v":262.37},262.37,{"$f":"IFERROR(VLOOKUP('AUP Library'!A659,'Updated Quanities'!F:G,4,0),R659)","v":262.37}]
["714-08.46","Foundation (Only) for High Mast Light Standard","EA",2606.73,2606.73,2606.73,2606.73,2606.73,2606.73,2606.73,2606.73,2606.73,2606.73,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A660,'Updated Quanities'!F:I,4,0),R660)=\"\",R660,IFERROR(VLOOKUP('AUP Library'!A660,'Updated Quanities'!F:I,4,0),R660))","v":2606.73},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A660,'Updated Quanities'!F:I,5,0),R660)=\"\",R660,IFERROR(VLOOKUP('AUP Library'!A660,'Updated Quanities'!F:I,5,0),R660))","v":2606.73},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A660,'Updated Quanities'!F:I,6,0),R660)=\"\",R660,IFERROR(VLOOKUP('AUP Library'!A660,'Updated Quanities'!F:I,6,0),R660))","v":2606.73},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A660,'Updated Quanities'!F:I,7,0),R660)=\"\",R660,IFERROR(VLOOKUP('AUP Library'!A660,'Updated Quanities'!F:I,7,0),R660))","v":2606.73},2606.73,{"$f":"IFERROR(VLOOKUP('AUP Library'!A660,'Updated Quanities'!F:G,4,0),R660)","v":2606.73}]
["714-09.01","Luminaires (150 WATT)","EA",563.66,563.66,563.66,563.66,563.66,563.66,563.66,563.66,563.66,563.66,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A661,'Updated Quanities'!F:I,4,0),R661)=\"\",R661,IFERROR(VLOOKUP('AUP Library'!A661,'Updated Quanities'!F:I,4,0),R661))","v":563.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A661,'Updated Quanities'!F:I,5,0),R661)=\"\",R661,IFERROR(VLOOKUP('AUP Library'!A661,'Updated Quanities'!F:I,5,0),R661))","v":563.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A661,'Updated Quanities'!F:I,6,0),R661)=\"\",R661,IFERROR(VLOOKUP('AUP Library'!A661,'Updated Quanities'!F:I,6,0),R661))","v":563.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A661,'Updated Quanities'!F:I,7,0),R661)=\"\",R661,IFERROR(VLOOKUP('AUP Library'!A661,'Updated Quanities'!F:I,7,0),R661))","v":563.66},563.66,{"$f":"IFERROR(VLOOKUP('AUP Library'!A661,'Updated Quanities'!F:G,4,0),R661)","v":563.66}]
["714-09.03","Luminaires (250 WATT)","EA",472.73,472.73,472.73,472.73,472.73,472.73,472.73,472.73,472.73,472.73,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A662,'Updated Quanities'!F:I,4,0),R662)=\"\",R662,IFERROR(VLOOKUP('AUP Library'!A662,'Updated Quanities'!F:I,4,0),R662))","v":472.73},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A662,'Updated Quanities'!F:I,5,0),R662)=\"\",R662,IFERROR(VLOOKUP('AUP Library'!A662,'Updated Quanities'!F:I,5,0),R662))","v":472.73},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A662,'Updated Quanities'!F:I,6,0),R662)=\"\",R662,IFERROR(VLOOKUP('AUP Library'!A662,'Updated Quanities'!F:I,6,0),R662))","v":472.73},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A662,'Updated Quanities'!F:I,7,0),R662)=\"\",R662,IFERROR(VLOOKUP('AUP Library'!A662,'Updated Quanities'!F:I,7,0),R662))","v":472.73},472.73,{"$f":"IFERROR(VLOOKUP('AUP Library'!A662,'Updated Quanities'!F:G,4,0),R662)","v":472.73}]
["714-09.04","Luminaires (400 WATT)","EA",735,735,735,735,735,735,735,735,735,735,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A663,'Updated Quanities'!F:I,4,0),R663)=\"\",R663,IFERROR(VLOOKUP('AUP Library'!A663,'Updated Quanities'!F:I,4,0),R663))","v":735},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A663,'Updated Quanities'!F:I,5,0),R663)=\"\",R663,IFERROR(VLOOKUP('AUP Library'!A663,'Updated Quanities'!F:I,5,0),R663))","v":735},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A663,'Updated Quanities'!F:I,6,0),R663)=\"\",R663,IFERROR(VLOOKUP('AUP Library'!A663,'Updated Quanities'!F:I,6,0),R663))","v":735},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A663,'Updated Quanities'!F:I,7,0),R663)=\"\",R663,IFERROR(VLOOKUP('AUP Library'!A663,'Updated Quanities'!F:I,7,0),R663))","v":735},735,{"$f":"IFERROR(VLOOKUP('AUP Library'!A663,'Updated Quanities'!F:G,4,0),R663)","v":735}]
["714-09.06","Luminaires (1000 WATT - High Mast)","EA",1250,1250,1250,1250,1250,1250,1250,1250,1250,1250,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A664,'Updated Quanities'!F:I,4,0),R664)=\"\",R664,IFERROR(VLOOKUP('AUP Library'!A664,'Updated Quanities'!F:I,4,0),R664))","v":1250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A664,'Updated Quanities'!F:I,5,0),R664)=\"\",R664,IFERROR(VLOOKUP('AUP Library'!A664,'Updated Quanities'!F:I,5,0),R664))","v":1250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A664,'Updated Quanities'!F:I,6,0),R664)=\"\",R664,IFERROR(VLOOKUP('AUP Library'!A664,'Updated Quanities'!F:I,6,0),R664))","v":1250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A664,'Updated Quanities'!F:I,7,0),R664)=\"\",R664,IFERROR(VLOOKUP('AUP Library'!A664,'Updated Quanities'!F:I,7,0),R664))","v":1250},1250,{"$f":"IFERROR(VLOOKUP('AUP Library'!A664,'Updated Quanities'!F:G,4,0),R664)","v":1250}]
["714-09.09","Luminaires","EA",743.32,743.32,743.32,743.32,743.32,743.32,743.32,743.32,743.32,743.32,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A665,'Updated Quanities'!F:I,4,0),R665)=\"\",R665,IFERROR(VLOOKUP('AUP Library'!A665,'Updated Quanities'!F:I,4,0),R665))","v":743.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A665,'Updated Quanities'!F:I,5,0),R665)=\"\",R665,IFERROR(VLOOKUP('AUP Library'!A665,'Updated Quanities'!F:I,5,0),R665))","v":743.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A665,'Updated Quanities'!F:I,6,0),R665)=\"\",R665,IFERROR(VLOOKUP('AUP Library'!A665,'Updated Quanities'!F:I,6,0),R665))","v":743.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A665,'Updated Quanities'!F:I,7,0),R665)=\"\",R665,IFERROR(VLOOKUP('AUP Library'!A665,'Updated Quanities'!F:I,7,0),R665))","v":743.32},743.32,{"$f":"IFERROR(VLOOKUP('AUP Library'!A665,'Updated Quanities'!F:G,4,0),R665)","v":743.32}]
["714-09.10","Luminaires","EA",1177.27,1177.27,1177.27,1177.27,1177.27,1177.27,1177.27,1177.27,1177.27,1177.27,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A666,'Updated Quanities'!F:I,4,0),R666)=\"\",R666,IFERROR(VLOOKUP('AUP Library'!A666,'Updated Quanities'!F:I,4,0),R666))","v":1177.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A666,'Updated Quanities'!F:I,5,0),R666)=\"\",R666,IFERROR(VLOOKUP('AUP Library'!A666,'Updated Quanities'!F:I,5,0),R666))","v":1177.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A666,'Updated Quanities'!F:I,6,0),R666)=\"\",R666,IFERROR(VLOOKUP('AUP Library'!A666,'Updated Quanities'!F:I,6,0),R666))","v":1177.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A666,'Updated Quanities'!F:I,7,0),R666)=\"\",R666,IFERROR(VLOOKUP('AUP Library'!A666,'Updated Quanities'!F:I,7,0),R666))","v":1177.27},1177.27,{"$f":"IFERROR(VLOOKUP('AUP Library'!A666,'Updated Quanities'!F:G,4,0),R666)","v":1177.27}]
["714-12.01","Control Center (No. 1)","LS",7735.45,7735.45,7735.45,7735.45,7735.45,7735.45,7735.45,7735.45,7735.45,7735.45,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A667,'Updated Quanities'!F:I,4,0),R667)=\"\",R667,IFERROR(VLOOKUP('AUP Library'!A667,'Updated Quanities'!F:I,4,0),R667))","v":7735.45},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A667,'Updated Quanities'!F:I,5,0),R667)=\"\",R667,IFERROR(VLOOKUP('AUP Library'!A667,'Updated Quanities'!F:I,5,0),R667))","v":7735.45},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A667,'Updated Quanities'!F:I,6,0),R667)=\"\",R667,IFERROR(VLOOKUP('AUP Library'!A667,'Updated Quanities'!F:I,6,0),R667))","v":7735.45},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A667,'Updated Quanities'!F:I,7,0),R667)=\"\",R667,IFERROR(VLOOKUP('AUP Library'!A667,'Updated Quanities'!F:I,7,0),R667))","v":7735.45},7735.45,{"$f":"IFERROR(VLOOKUP('AUP Library'!A667,'Updated Quanities'!F:G,4,0),R667)","v":7735.45}]
["714-12.02","Control Center (No. 2)","LS",8437.5,8437.5,8437.5,8437.5,8437.5,8437.5,8437.5,8437.5,8437.5,8437.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A668,'Updated Quanities'!F:I,4,0),R668)=\"\",R668,IFERROR(VLOOKUP('AUP Library'!A668,'Updated Quanities'!F:I,4,0),R668))","v":8437.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A668,'Updated Quanities'!F:I,5,0),R668)=\"\",R668,IFERROR(VLOOKUP('AUP Library'!A668,'Updated Quanities'!F:I,5,0),R668))","v":8437.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A668,'Updated Quanities'!F:I,6,0),R668)=\"\",R668,IFERROR(VLOOKUP('AUP Library'!A668,'Updated Quanities'!F:I,6,0),R668))","v":8437.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A668,'Updated Quanities'!F:I,7,0),R668)=\"\",R668,IFERROR(VLOOKUP('AUP Library'!A668,'Updated Quanities'!F:I,7,0),R668))","v":8437.5},8437.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A668,'Updated Quanities'!F:G,4,0),R668)","v":8437.5}]
["714-12.03","Control Center (No. 3)","LS",9696,9696,9696,9696,9696,9696,9696,9696,9696,9696,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A669,'Updated Quanities'!F:I,4,0),R669)=\"\",R669,IFERROR(VLOOKUP('AUP Library'!A669,'Updated Quanities'!F:I,4,0),R669))","v":9696},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A669,'Updated Quanities'!F:I,5,0),R669)=\"\",R669,IFERROR(VLOOKUP('AUP Library'!A669,'Updated Quanities'!F:I,5,0),R669))","v":9696},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A669,'Updated Quanities'!F:I,6,0),R669)=\"\",R669,IFERROR(VLOOKUP('AUP Library'!A669,'Updated Quanities'!F:I,6,0),R669))","v":9696},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A669,'Updated Quanities'!F:I,7,0),R669)=\"\",R669,IFERROR(VLOOKUP('AUP Library'!A669,'Updated Quanities'!F:I,7,0),R669))","v":9696},9696,{"$f":"IFERROR(VLOOKUP('AUP Library'!A669,'Updated Quanities'!F:G,4,0),R669)","v":9696}]
["714-12.04","Control Center (No. 4)","LS",8601,8601,8601,8601,8601,8601,8601,8601,8601,8601,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A670,'Updated Quanities'!F:I,4,0),R670)=\"\",R670,IFERROR(VLOOKUP('AUP Library'!A670,'Updated Quanities'!F:I,4,0),R670))","v":8601},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A670,'Updated Quanities'!F:I,5,0),R670)=\"\",R670,IFERROR(VLOOKUP('AUP Library'!A670,'Updated Quanities'!F:I,5,0),R670))","v":8601},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A670,'Updated Quanities'!F:I,6,0),R670)=\"\",R670,IFERROR(VLOOKUP('AUP Library'!A670,'Updated Quanities'!F:I,6,0),R670))","v":8601},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A670,'Updated Quanities'!F:I,7,0),R670)=\"\",R670,IFERROR(VLOOKUP('AUP Library'!A670,'Updated Quanities'!F:I,7,0),R670))","v":8601},8601,{"$f":"IFERROR(VLOOKUP('AUP Library'!A670,'Updated Quanities'!F:G,4,0),R670)","v":8601}]
["714-12.05","Control Center (No. 5)","LS",9565,9565,9565,9565,9565,9565,9565,9565,9565,9565,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A671,'Updated Quanities'!F:I,4,0),R671)=\"\",R671,IFERROR(VLOOKUP('AUP Library'!A671,'Updated Quanities'!F:I,4,0),R671))","v":9565},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A671,'Updated Quanities'!F:I,5,0),R671)=\"\",R671,IFERROR(VLOOKUP('AUP Library'!A671,'Updated Quanities'!F:I,5,0),R671))","v":9565},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A671,'Updated Quanities'!F:I,6,0),R671)=\"\",R671,IFERROR(VLOOKUP('AUP Library'!A671,'Updated Quanities'!F:I,6,0),R671))","v":9565},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A671,'Updated Quanities'!F:I,7,0),R671)=\"\",R671,IFERROR(VLOOKUP('AUP Library'!A671,'Updated Quanities'!F:I,7,0),R671))","v":9565},9565,{"$f":"IFERROR(VLOOKUP('AUP Library'!A671,'Updated Quanities'!F:G,4,0),R671)","v":9565}]
["714-12.06","Control Center (No. 6)","LS",9565,9565,9565,9565,9565,9565,9565,9565,9565,9565,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A672,'Updated Quanities'!F:I,4,0),R672)=\"\",R672,IFERROR(VLOOKUP('AUP Library'!A672,'Updated Quanities'!F:I,4,0),R672))","v":9565},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A672,'Updated Quanities'!F:I,5,0),R672)=\"\",R672,IFERROR(VLOOKUP('AUP Library'!A672,'Updated Quanities'!F:I,5,0),R672))","v":9565},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A672,'Updated Quanities'!F:I,6,0),R672)=\"\",R672,IFERROR(VLOOKUP('AUP Library'!A672,'Updated Quanities'!F:I,6,0),R672))","v":9565},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A672,'Updated Quanities'!F:I,7,0),R672)=\"\",R672,IFERROR(VLOOKUP('AUP Library'!A672,'Updated Quanities'!F:I,7,0),R672))","v":9565},9565,{"$f":"IFERROR(VLOOKUP('AUP Library'!A672,'Updated Quanities'!F:G,4,0),R672)","v":9565}]
["714-25","Electrical Connection","EA",3654.45,3654.45,3654.45,3654.45,3654.45,3654.45,3654.45,3654.45,3654.45,3654.45,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A673,'Updated Quanities'!F:I,4,0),R673)=\"\",R673,IFERROR(VLOOKUP('AUP Library'!A673,'Updated Quanities'!F:I,4,0),R673))","v":3654.45},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A673,'Updated Quanities'!F:I,5,0),R673)=\"\",R673,IFERROR(VLOOKUP('AUP Library'!A673,'Updated Quanities'!F:I,5,0),R673))","v":3654.45},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A673,'Updated Quanities'!F:I,6,0),R673)=\"\",R673,IFERROR(VLOOKUP('AUP Library'!A673,'Updated Quanities'!F:I,6,0),R673))","v":3654.45},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A673,'Updated Quanities'!F:I,7,0),R673)=\"\",R673,IFERROR(VLOOKUP('AUP Library'!A673,'Updated Quanities'!F:I,7,0),R673))","v":3654.45},3654.45,{"$f":"IFERROR(VLOOKUP('AUP Library'!A673,'Updated Quanities'!F:G,4,0),R673)","v":3654.45}]
["714-26.05","Temporary Roadway Lighting","LS",6825,6825,6825,6825,6825,6825,6825,6825,6825,6825,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A674,'Updated Quanities'!F:I,4,0),R674)=\"\",R674,IFERROR(VLOOKUP('AUP Library'!A674,'Updated Quanities'!F:I,4,0),R674))","v":6825},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A674,'Updated Quanities'!F:I,5,0),R674)=\"\",R674,IFERROR(VLOOKUP('AUP Library'!A674,'Updated Quanities'!F:I,5,0),R674))","v":6825},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A674,'Updated Quanities'!F:I,6,0),R674)=\"\",R674,IFERROR(VLOOKUP('AUP Library'!A674,'Updated Quanities'!F:I,6,0),R674))","v":6825},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A674,'Updated Quanities'!F:I,7,0),R674)=\"\",R674,IFERROR(VLOOKUP('AUP Library'!A674,'Updated Quanities'!F:I,7,0),R674))","v":6825},6825,{"$f":"IFERROR(VLOOKUP('AUP Library'!A674,'Updated Quanities'!F:G,4,0),R674)","v":6825}]
["714-60.01","Light Pole Base Demolition","EA",265,265,265,265,265,265,265,265,265,265,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A675,'Updated Quanities'!F:I,4,0),R675)=\"\",R675,IFERROR(VLOOKUP('AUP Library'!A675,'Updated Quanities'!F:I,4,0),R675))","v":265},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A675,'Updated Quanities'!F:I,5,0),R675)=\"\",R675,IFERROR(VLOOKUP('AUP Library'!A675,'Updated Quanities'!F:I,5,0),R675))","v":265},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A675,'Updated Quanities'!F:I,6,0),R675)=\"\",R675,IFERROR(VLOOKUP('AUP Library'!A675,'Updated Quanities'!F:I,6,0),R675))","v":265},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A675,'Updated Quanities'!F:I,7,0),R675)=\"\",R675,IFERROR(VLOOKUP('AUP Library'!A675,'Updated Quanities'!F:I,7,0),R675))","v":265},265,{"$f":"IFERROR(VLOOKUP('AUP Library'!A675,'Updated Quanities'!F:G,4,0),R675)","v":265}]
["714-60.02","Light Pole Base Type A (Pole by MTEMC)","EA",1250,1250,1250,1250,1250,1250,1250,1250,1250,1250,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A676,'Updated Quanities'!F:I,4,0),R676)=\"\",R676,IFERROR(VLOOKUP('AUP Library'!A676,'Updated Quanities'!F:I,4,0),R676))","v":1250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A676,'Updated Quanities'!F:I,5,0),R676)=\"\",R676,IFERROR(VLOOKUP('AUP Library'!A676,'Updated Quanities'!F:I,5,0),R676))","v":1250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A676,'Updated Quanities'!F:I,6,0),R676)=\"\",R676,IFERROR(VLOOKUP('AUP Library'!A676,'Updated Quanities'!F:I,6,0),R676))","v":1250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A676,'Updated Quanities'!F:I,7,0),R676)=\"\",R676,IFERROR(VLOOKUP('AUP Library'!A676,'Updated Quanities'!F:I,7,0),R676))","v":1250},1250,{"$f":"IFERROR(VLOOKUP('AUP Library'!A676,'Updated Quanities'!F:G,4,0),R676)","v":1250}]
["714-60.03","Light Pole Base Type B (Pole By MTEMC)","EA",1080,1080,1080,1080,1080,1080,1080,1080,1080,1080,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A677,'Updated Quanities'!F:I,4,0),R677)=\"\",R677,IFERROR(VLOOKUP('AUP Library'!A677,'Updated Quanities'!F:I,4,0),R677))","v":1080},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A677,'Updated Quanities'!F:I,5,0),R677)=\"\",R677,IFERROR(VLOOKUP('AUP Library'!A677,'Updated Quanities'!F:I,5,0),R677))","v":1080},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A677,'Updated Quanities'!F:I,6,0),R677)=\"\",R677,IFERROR(VLOOKUP('AUP Library'!A677,'Updated Quanities'!F:I,6,0),R677))","v":1080},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A677,'Updated Quanities'!F:I,7,0),R677)=\"\",R677,IFERROR(VLOOKUP('AUP Library'!A677,'Updated Quanities'!F:I,7,0),R677))","v":1080},1080,{"$f":"IFERROR(VLOOKUP('AUP Library'!A677,'Updated Quanities'!F:G,4,0),R677)","v":1080}]
["714-60.04","Light Pole Base Type B","EA",1080,1080,1080,1080,1080,1080,1080,1080,1080,1080,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A678,'Updated Quanities'!F:I,4,0),R678)=\"\",R678,IFERROR(VLOOKUP('AUP Library'!A678,'Updated Quanities'!F:I,4,0),R678))","v":1080},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A678,'Updated Quanities'!F:I,5,0),R678)=\"\",R678,IFERROR(VLOOKUP('AUP Library'!A678,'Updated Quanities'!F:I,5,0),R678))","v":1080},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A678,'Updated Quanities'!F:I,6,0),R678)=\"\",R678,IFERROR(VLOOKUP('AUP Library'!A678,'Updated Quanities'!F:I,6,0),R678))","v":1080},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A678,'Updated Quanities'!F:I,7,0),R678)=\"\",R678,IFERROR(VLOOKUP('AUP Library'!A678,'Updated Quanities'!F:I,7,0),R678))","v":1080},1080,{"$f":"IFERROR(VLOOKUP('AUP Library'!A678,'Updated Quanities'!F:G,4,0),R678)","v":1080}]
["714-60.05","Light Pole Rewiring","EA",135,135,135,135,135,135,135,135,135,135,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A679,'Updated Quanities'!F:I,4,0),R679)=\"\",R679,IFERROR(VLOOKUP('AUP Library'!A679,'Updated Quanities'!F:I,4,0),R679))","v":135},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A679,'Updated Quanities'!F:I,5,0),R679)=\"\",R679,IFERROR(VLOOKUP('AUP Library'!A679,'Updated Quanities'!F:I,5,0),R679))","v":135},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A679,'Updated Quanities'!F:I,6,0),R679)=\"\",R679,IFERROR(VLOOKUP('AUP Library'!A679,'Updated Quanities'!F:I,6,0),R679))","v":135},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A679,'Updated Quanities'!F:I,7,0),R679)=\"\",R679,IFERROR(VLOOKUP('AUP Library'!A679,'Updated Quanities'!F:I,7,0),R679))","v":135},135,{"$f":"IFERROR(VLOOKUP('AUP Library'!A679,'Updated Quanities'!F:G,4,0),R679)","v":135}]
["714-60.06","Light Pole Convenience Electric Assembly","EA",136,136,136,136,136,136,136,136,136,136,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A680,'Updated Quanities'!F:I,4,0),R680)=\"\",R680,IFERROR(VLOOKUP('AUP Library'!A680,'Updated Quanities'!F:I,4,0),R680))","v":136},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A680,'Updated Quanities'!F:I,5,0),R680)=\"\",R680,IFERROR(VLOOKUP('AUP Library'!A680,'Updated Quanities'!F:I,5,0),R680))","v":136},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A680,'Updated Quanities'!F:I,6,0),R680)=\"\",R680,IFERROR(VLOOKUP('AUP Library'!A680,'Updated Quanities'!F:I,6,0),R680))","v":136},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A680,'Updated Quanities'!F:I,7,0),R680)=\"\",R680,IFERROR(VLOOKUP('AUP Library'!A680,'Updated Quanities'!F:I,7,0),R680))","v":136},136,{"$f":"IFERROR(VLOOKUP('AUP Library'!A680,'Updated Quanities'!F:G,4,0),R680)","v":136}]
["714-60.07","Panel (sq)","EA",2700,2700,2700,2700,2700,2700,2700,2700,2700,2700,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A681,'Updated Quanities'!F:I,4,0),R681)=\"\",R681,IFERROR(VLOOKUP('AUP Library'!A681,'Updated Quanities'!F:I,4,0),R681))","v":2700},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A681,'Updated Quanities'!F:I,5,0),R681)=\"\",R681,IFERROR(VLOOKUP('AUP Library'!A681,'Updated Quanities'!F:I,5,0),R681))","v":2700},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A681,'Updated Quanities'!F:I,6,0),R681)=\"\",R681,IFERROR(VLOOKUP('AUP Library'!A681,'Updated Quanities'!F:I,6,0),R681))","v":2700},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A681,'Updated Quanities'!F:I,7,0),R681)=\"\",R681,IFERROR(VLOOKUP('AUP Library'!A681,'Updated Quanities'!F:I,7,0),R681))","v":2700},2700,{"$f":"IFERROR(VLOOKUP('AUP Library'!A681,'Updated Quanities'!F:G,4,0),R681)","v":2700}]
["714-60.08","Time Clock","EA",500,500,500,500,500,500,500,500,500,500,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A682,'Updated Quanities'!F:I,4,0),R682)=\"\",R682,IFERROR(VLOOKUP('AUP Library'!A682,'Updated Quanities'!F:I,4,0),R682))","v":500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A682,'Updated Quanities'!F:I,5,0),R682)=\"\",R682,IFERROR(VLOOKUP('AUP Library'!A682,'Updated Quanities'!F:I,5,0),R682))","v":500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A682,'Updated Quanities'!F:I,6,0),R682)=\"\",R682,IFERROR(VLOOKUP('AUP Library'!A682,'Updated Quanities'!F:I,6,0),R682))","v":500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A682,'Updated Quanities'!F:I,7,0),R682)=\"\",R682,IFERROR(VLOOKUP('AUP Library'!A682,'Updated Quanities'!F:I,7,0),R682))","v":500},500,{"$f":"IFERROR(VLOOKUP('AUP Library'!A682,'Updated Quanities'!F:G,4,0),R682)","v":500}]
["714-60.09","Spider Box 50A","EA",450,450,450,450,450,450,450,450,450,450,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A683,'Updated Quanities'!F:I,4,0),R683)=\"\",R683,IFERROR(VLOOKUP('AUP Library'!A683,'Updated Quanities'!F:I,4,0),R683))","v":450},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A683,'Updated Quanities'!F:I,5,0),R683)=\"\",R683,IFERROR(VLOOKUP('AUP Library'!A683,'Updated Quanities'!F:I,5,0),R683))","v":450},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A683,'Updated Quanities'!F:I,6,0),R683)=\"\",R683,IFERROR(VLOOKUP('AUP Library'!A683,'Updated Quanities'!F:I,6,0),R683))","v":450},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A683,'Updated Quanities'!F:I,7,0),R683)=\"\",R683,IFERROR(VLOOKUP('AUP Library'!A683,'Updated Quanities'!F:I,7,0),R683))","v":450},450,{"$f":"IFERROR(VLOOKUP('AUP Library'!A683,'Updated Quanities'!F:G,4,0),R683)","v":450}]
["714-60.10","Elec Pull Box Traf Bearing 13x24x18IN","EA",325,325,325,325,325,325,325,325,325,325,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A684,'Updated Quanities'!F:I,4,0),R684)=\"\",R684,IFERROR(VLOOKUP('AUP Library'!A684,'Updated Quanities'!F:I,4,0),R684))","v":325},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A684,'Updated Quanities'!F:I,5,0),R684)=\"\",R684,IFERROR(VLOOKUP('AUP Library'!A684,'Updated Quanities'!F:I,5,0),R684))","v":325},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A684,'Updated Quanities'!F:I,6,0),R684)=\"\",R684,IFERROR(VLOOKUP('AUP Library'!A684,'Updated Quanities'!F:I,6,0),R684))","v":325},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A684,'Updated Quanities'!F:I,7,0),R684)=\"\",R684,IFERROR(VLOOKUP('AUP Library'!A684,'Updated Quanities'!F:I,7,0),R684))","v":325},325,{"$f":"IFERROR(VLOOKUP('AUP Library'!A684,'Updated Quanities'!F:G,4,0),R684)","v":325}]
["714-60.11","Elec Pull Box Ped Bearing 13x24x18IN","EA",375,375,375,375,375,375,375,375,375,375,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A685,'Updated Quanities'!F:I,4,0),R685)=\"\",R685,IFERROR(VLOOKUP('AUP Library'!A685,'Updated Quanities'!F:I,4,0),R685))","v":375},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A685,'Updated Quanities'!F:I,5,0),R685)=\"\",R685,IFERROR(VLOOKUP('AUP Library'!A685,'Updated Quanities'!F:I,5,0),R685))","v":375},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A685,'Updated Quanities'!F:I,6,0),R685)=\"\",R685,IFERROR(VLOOKUP('AUP Library'!A685,'Updated Quanities'!F:I,6,0),R685))","v":375},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A685,'Updated Quanities'!F:I,7,0),R685)=\"\",R685,IFERROR(VLOOKUP('AUP Library'!A685,'Updated Quanities'!F:I,7,0),R685))","v":375},375,{"$f":"IFERROR(VLOOKUP('AUP Library'!A685,'Updated Quanities'!F:G,4,0),R685)","v":375}]
["713-15.07","Suspended Flat Sheet Aluminum Sign (0.080\" Thick)","EA",121.44,121.44,121.44,121.44,121.44,121.44,121.44,121.44,121.44,121.44,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A686,'Updated Quanities'!F:I,4,0),R686)=\"\",R686,IFERROR(VLOOKUP('AUP Library'!A686,'Updated Quanities'!F:I,4,0),R686))","v":121.44},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A686,'Updated Quanities'!F:I,5,0),R686)=\"\",R686,IFERROR(VLOOKUP('AUP Library'!A686,'Updated Quanities'!F:I,5,0),R686))","v":121.44},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A686,'Updated Quanities'!F:I,6,0),R686)=\"\",R686,IFERROR(VLOOKUP('AUP Library'!A686,'Updated Quanities'!F:I,6,0),R686))","v":121.44},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A686,'Updated Quanities'!F:I,7,0),R686)=\"\",R686,IFERROR(VLOOKUP('AUP Library'!A686,'Updated Quanities'!F:I,7,0),R686))","v":121.44},121.44,{"$f":"IFERROR(VLOOKUP('AUP Library'!A686,'Updated Quanities'!F:G,4,0),R686)","v":121.44}]
["730-01.01","REMOVE & RELOCATE EX TRAFFIC SIGNAL EQP","EA",678.68,678.68,678.68,678.68,678.68,678.68,678.68,678.68,678.68,678.68,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A687,'Updated Quanities'!F:I,4,0),R687)=\"\",R687,IFERROR(VLOOKUP('AUP Library'!A687,'Updated Quanities'!F:I,4,0),R687))","v":678.68},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A687,'Updated Quanities'!F:I,5,0),R687)=\"\",R687,IFERROR(VLOOKUP('AUP Library'!A687,'Updated Quanities'!F:I,5,0),R687))","v":678.68},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A687,'Updated Quanities'!F:I,6,0),R687)=\"\",R687,IFERROR(VLOOKUP('AUP Library'!A687,'Updated Quanities'!F:I,6,0),R687))","v":678.68},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A687,'Updated Quanities'!F:I,7,0),R687)=\"\",R687,IFERROR(VLOOKUP('AUP Library'!A687,'Updated Quanities'!F:I,7,0),R687))","v":678.68},678.68,{"$f":"IFERROR(VLOOKUP('AUP Library'!A687,'Updated Quanities'!F:G,4,0),R687)","v":678.68}]
["730-01.02","Removal of Signal Equipment","EA",1689.88,1689.88,1689.88,1689.88,1689.88,1689.88,1689.88,1689.88,1689.88,1689.88,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A688,'Updated Quanities'!F:I,4,0),R688)=\"\",R688,IFERROR(VLOOKUP('AUP Library'!A688,'Updated Quanities'!F:I,4,0),R688))","v":1689.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A688,'Updated Quanities'!F:I,5,0),R688)=\"\",R688,IFERROR(VLOOKUP('AUP Library'!A688,'Updated Quanities'!F:I,5,0),R688))","v":1689.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A688,'Updated Quanities'!F:I,6,0),R688)=\"\",R688,IFERROR(VLOOKUP('AUP Library'!A688,'Updated Quanities'!F:I,6,0),R688))","v":1689.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A688,'Updated Quanities'!F:I,7,0),R688)=\"\",R688,IFERROR(VLOOKUP('AUP Library'!A688,'Updated Quanities'!F:I,7,0),R688))","v":1689.88},1689.88,{"$f":"IFERROR(VLOOKUP('AUP Library'!A688,'Updated Quanities'!F:G,4,0),R688)","v":1689.88}]
["730-01.03","MODIFICATION EXISTING TRAFFIC SIGNAL EQP","EA",1392.5,1392.5,1392.5,1392.5,1392.5,1392.5,1392.5,1392.5,1392.5,1392.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A689,'Updated Quanities'!F:I,4,0),R689)=\"\",R689,IFERROR(VLOOKUP('AUP Library'!A689,'Updated Quanities'!F:I,4,0),R689))","v":1392.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A689,'Updated Quanities'!F:I,5,0),R689)=\"\",R689,IFERROR(VLOOKUP('AUP Library'!A689,'Updated Quanities'!F:I,5,0),R689))","v":1392.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A689,'Updated Quanities'!F:I,6,0),R689)=\"\",R689,IFERROR(VLOOKUP('AUP Library'!A689,'Updated Quanities'!F:I,6,0),R689))","v":1392.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A689,'Updated Quanities'!F:I,7,0),R689)=\"\",R689,IFERROR(VLOOKUP('AUP Library'!A689,'Updated Quanities'!F:I,7,0),R689))","v":1392.5},1392.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A689,'Updated Quanities'!F:G,4,0),R689)","v":1392.5}]
["730-01.04","MODIFICATION EXISTING TRAFFIC SIGNAL EQP","LS",1712.34,1712.34,1712.34,1712.34,1712.34,1712.34,1712.34,1712.34,1712.34,1712.34,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A690,'Updated Quanities'!F:I,4,0),R690)=\"\",R690,IFERROR(VLOOKUP('AUP Library'!A690,'Updated Quanities'!F:I,4,0),R690))","v":1712.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A690,'Updated Quanities'!F:I,5,0),R690)=\"\",R690,IFERROR(VLOOKUP('AUP Library'!A690,'Updated Quanities'!F:I,5,0),R690))","v":1712.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A690,'Updated Quanities'!F:I,6,0),R690)=\"\",R690,IFERROR(VLOOKUP('AUP Library'!A690,'Updated Quanities'!F:I,6,0),R690))","v":1712.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A690,'Updated Quanities'!F:I,7,0),R690)=\"\",R690,IFERROR(VLOOKUP('AUP Library'!A690,'Updated Quanities'!F:I,7,0),R690))","v":1712.34},1712.34,{"$f":"IFERROR(VLOOKUP('AUP Library'!A690,'Updated Quanities'!F:G,4,0),R690)","v":1712.34}]
["730-01.05","REMOVE & RELOCATE SCHOOL SIGNAL EQP","LS",2500,2500,2500,2500,2500,2500,2500,2500,2500,2500,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A691,'Updated Quanities'!F:I,4,0),R691)=\"\",R691,IFERROR(VLOOKUP('AUP Library'!A691,'Updated Quanities'!F:I,4,0),R691))","v":2500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A691,'Updated Quanities'!F:I,5,0),R691)=\"\",R691,IFERROR(VLOOKUP('AUP Library'!A691,'Updated Quanities'!F:I,5,0),R691))","v":2500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A691,'Updated Quanities'!F:I,6,0),R691)=\"\",R691,IFERROR(VLOOKUP('AUP Library'!A691,'Updated Quanities'!F:I,6,0),R691))","v":2500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A691,'Updated Quanities'!F:I,7,0),R691)=\"\",R691,IFERROR(VLOOKUP('AUP Library'!A691,'Updated Quanities'!F:I,7,0),R691))","v":2500},2500,{"$f":"IFERROR(VLOOKUP('AUP Library'!A691,'Updated Quanities'!F:G,4,0),R691)","v":2500}]
["730-01.07","REMOVAL OF CONCRETE BASE","EA",1000,1000,1000,1000,1000,1000,1000,1000,1000,1000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A692,'Updated Quanities'!F:I,4,0),R692)=\"\",R692,IFERROR(VLOOKUP('AUP Library'!A692,'Updated Quanities'!F:I,4,0),R692))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A692,'Updated Quanities'!F:I,5,0),R692)=\"\",R692,IFERROR(VLOOKUP('AUP Library'!A692,'Updated Quanities'!F:I,5,0),R692))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A692,'Updated Quanities'!F:I,6,0),R692)=\"\",R692,IFERROR(VLOOKUP('AUP Library'!A692,'Updated Quanities'!F:I,6,0),R692))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A692,'Updated Quanities'!F:I,7,0),R692)=\"\",R692,IFERROR(VLOOKUP('AUP Library'!A692,'Updated Quanities'!F:I,7,0),R692))","v":1000},1000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A692,'Updated Quanities'!F:G,4,0),R692)","v":1000}]
["730-01.08","SCHOOL SPEED LIMIT FLASHG SIGNAL INSTED","EA",3747.86,3747.86,3747.86,3747.86,3747.86,3747.86,3747.86,3747.86,3747.86,3747.86,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A693,'Updated Quanities'!F:I,4,0),R693)=\"\",R693,IFERROR(VLOOKUP('AUP Library'!A693,'Updated Quanities'!F:I,4,0),R693))","v":3747.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A693,'Updated Quanities'!F:I,5,0),R693)=\"\",R693,IFERROR(VLOOKUP('AUP Library'!A693,'Updated Quanities'!F:I,5,0),R693))","v":3747.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A693,'Updated Quanities'!F:I,6,0),R693)=\"\",R693,IFERROR(VLOOKUP('AUP Library'!A693,'Updated Quanities'!F:I,6,0),R693))","v":3747.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A693,'Updated Quanities'!F:I,7,0),R693)=\"\",R693,IFERROR(VLOOKUP('AUP Library'!A693,'Updated Quanities'!F:I,7,0),R693))","v":3747.86},3747.86,{"$f":"IFERROR(VLOOKUP('AUP Library'!A693,'Updated Quanities'!F:G,4,0),R693)","v":3747.86}]
["730-01.09","UTILITY DUCT BANK","LF",42,42,42,42,42,42,42,42,42,42,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A694,'Updated Quanities'!F:I,4,0),R694)=\"\",R694,IFERROR(VLOOKUP('AUP Library'!A694,'Updated Quanities'!F:I,4,0),R694))","v":42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A694,'Updated Quanities'!F:I,5,0),R694)=\"\",R694,IFERROR(VLOOKUP('AUP Library'!A694,'Updated Quanities'!F:I,5,0),R694))","v":42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A694,'Updated Quanities'!F:I,6,0),R694)=\"\",R694,IFERROR(VLOOKUP('AUP Library'!A694,'Updated Quanities'!F:I,6,0),R694))","v":42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A694,'Updated Quanities'!F:I,7,0),R694)=\"\",R694,IFERROR(VLOOKUP('AUP Library'!A694,'Updated Quanities'!F:I,7,0),R694))","v":42},42,{"$f":"IFERROR(VLOOKUP('AUP Library'!A694,'Updated Quanities'!F:G,4,0),R694)","v":42}]
["730-01.11","REMOVE AND REPLACE BEACON","LS",3600,3600,3600,3600,3600,3600,3600,3600,3600,3600,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A695,'Updated Quanities'!F:I,4,0),R695)=\"\",R695,IFERROR(VLOOKUP('AUP Library'!A695,'Updated Quanities'!F:I,4,0),R695))","v":3600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A695,'Updated Quanities'!F:I,5,0),R695)=\"\",R695,IFERROR(VLOOKUP('AUP Library'!A695,'Updated Quanities'!F:I,5,0),R695))","v":3600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A695,'Updated Quanities'!F:I,6,0),R695)=\"\",R695,IFERROR(VLOOKUP('AUP Library'!A695,'Updated Quanities'!F:I,6,0),R695))","v":3600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A695,'Updated Quanities'!F:I,7,0),R695)=\"\",R695,IFERROR(VLOOKUP('AUP Library'!A695,'Updated Quanities'!F:I,7,0),R695))","v":3600},3600,{"$f":"IFERROR(VLOOKUP('AUP Library'!A695,'Updated Quanities'!F:G,4,0),R695)","v":3600}]
["730-01.12","SOLAR PANEL & POWER SYSTEM UNIT","EA",2989.17,2989.17,2989.17,2989.17,2989.17,2989.17,2989.17,2989.17,2989.17,2989.17,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A696,'Updated Quanities'!F:I,4,0),R696)=\"\",R696,IFERROR(VLOOKUP('AUP Library'!A696,'Updated Quanities'!F:I,4,0),R696))","v":2989.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A696,'Updated Quanities'!F:I,5,0),R696)=\"\",R696,IFERROR(VLOOKUP('AUP Library'!A696,'Updated Quanities'!F:I,5,0),R696))","v":2989.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A696,'Updated Quanities'!F:I,6,0),R696)=\"\",R696,IFERROR(VLOOKUP('AUP Library'!A696,'Updated Quanities'!F:I,6,0),R696))","v":2989.17},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A696,'Updated Quanities'!F:I,7,0),R696)=\"\",R696,IFERROR(VLOOKUP('AUP Library'!A696,'Updated Quanities'!F:I,7,0),R696))","v":2989.17},2989.17,{"$f":"IFERROR(VLOOKUP('AUP Library'!A696,'Updated Quanities'!F:G,4,0),R696)","v":2989.17}]
["730-01.50","DESIGN-BUILD SIGNALS","LS",98244.83,98244.83,98244.83,98244.83,98244.83,98244.83,98244.83,98244.83,98244.83,98244.83,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A697,'Updated Quanities'!F:I,4,0),R697)=\"\",R697,IFERROR(VLOOKUP('AUP Library'!A697,'Updated Quanities'!F:I,4,0),R697))","v":98244.83},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A697,'Updated Quanities'!F:I,5,0),R697)=\"\",R697,IFERROR(VLOOKUP('AUP Library'!A697,'Updated Quanities'!F:I,5,0),R697))","v":98244.83},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A697,'Updated Quanities'!F:I,6,0),R697)=\"\",R697,IFERROR(VLOOKUP('AUP Library'!A697,'Updated Quanities'!F:I,6,0),R697))","v":98244.83},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A697,'Updated Quanities'!F:I,7,0),R697)=\"\",R697,IFERROR(VLOOKUP('AUP Library'!A697,'Updated Quanities'!F:I,7,0),R697))","v":98244.83},98244.83,{"$f":"IFERROR(VLOOKUP('AUP Library'!A697,'Updated Quanities'!F:G,4,0),R697)","v":98244.83}]
["730-02.09","Signal Head Assembly (130 With Backplate)","EA",792.63,792.63,792.63,792.63,792.63,792.63,792.63,792.63,792.63,792.63,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A698,'Updated Quanities'!F:I,4,0),R698)=\"\",R698,IFERROR(VLOOKUP('AUP Library'!A698,'Updated Quanities'!F:I,4,0),R698))","v":792.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A698,'Updated Quanities'!F:I,5,0),R698)=\"\",R698,IFERROR(VLOOKUP('AUP Library'!A698,'Updated Quanities'!F:I,5,0),R698))","v":792.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A698,'Updated Quanities'!F:I,6,0),R698)=\"\",R698,IFERROR(VLOOKUP('AUP Library'!A698,'Updated Quanities'!F:I,6,0),R698))","v":792.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A698,'Updated Quanities'!F:I,7,0),R698)=\"\",R698,IFERROR(VLOOKUP('AUP Library'!A698,'Updated Quanities'!F:I,7,0),R698))","v":792.63},792.63,{"$f":"IFERROR(VLOOKUP('AUP Library'!A698,'Updated Quanities'!F:G,4,0),R698)","v":792.63}]
["730-02.17","Signal Head Assembly (150 A2H With Backplate)","EA",1337.01,1337.01,1337.01,1337.01,1337.01,1337.01,1337.01,1337.01,1337.01,1337.01,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A699,'Updated Quanities'!F:I,4,0),R699)=\"\",R699,IFERROR(VLOOKUP('AUP Library'!A699,'Updated Quanities'!F:I,4,0),R699))","v":1337.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A699,'Updated Quanities'!F:I,5,0),R699)=\"\",R699,IFERROR(VLOOKUP('AUP Library'!A699,'Updated Quanities'!F:I,5,0),R699))","v":1337.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A699,'Updated Quanities'!F:I,6,0),R699)=\"\",R699,IFERROR(VLOOKUP('AUP Library'!A699,'Updated Quanities'!F:I,6,0),R699))","v":1337.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A699,'Updated Quanities'!F:I,7,0),R699)=\"\",R699,IFERROR(VLOOKUP('AUP Library'!A699,'Updated Quanities'!F:I,7,0),R699))","v":1337.01},1337.01,{"$f":"IFERROR(VLOOKUP('AUP Library'!A699,'Updated Quanities'!F:G,4,0),R699)","v":1337.01}]
["730-02.30","Signal Head Assembly (130 A3 With Backplate)","EA",836.19,836.19,836.19,836.19,836.19,836.19,836.19,836.19,836.19,836.19,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A700,'Updated Quanities'!F:I,4,0),R700)=\"\",R700,IFERROR(VLOOKUP('AUP Library'!A700,'Updated Quanities'!F:I,4,0),R700))","v":836.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A700,'Updated Quanities'!F:I,5,0),R700)=\"\",R700,IFERROR(VLOOKUP('AUP Library'!A700,'Updated Quanities'!F:I,5,0),R700))","v":836.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A700,'Updated Quanities'!F:I,6,0),R700)=\"\",R700,IFERROR(VLOOKUP('AUP Library'!A700,'Updated Quanities'!F:I,6,0),R700))","v":836.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A700,'Updated Quanities'!F:I,7,0),R700)=\"\",R700,IFERROR(VLOOKUP('AUP Library'!A700,'Updated Quanities'!F:I,7,0),R700))","v":836.19},836.19,{"$f":"IFERROR(VLOOKUP('AUP Library'!A700,'Updated Quanities'!F:G,4,0),R700)","v":836.19}]
["730-02.31","Signal Head Assembly (140 A1 With Backplate)","EA",852.01,852.01,852.01,852.01,852.01,852.01,852.01,852.01,852.01,852.01,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A701,'Updated Quanities'!F:I,4,0),R701)=\"\",R701,IFERROR(VLOOKUP('AUP Library'!A701,'Updated Quanities'!F:I,4,0),R701))","v":852.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A701,'Updated Quanities'!F:I,5,0),R701)=\"\",R701,IFERROR(VLOOKUP('AUP Library'!A701,'Updated Quanities'!F:I,5,0),R701))","v":852.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A701,'Updated Quanities'!F:I,6,0),R701)=\"\",R701,IFERROR(VLOOKUP('AUP Library'!A701,'Updated Quanities'!F:I,6,0),R701))","v":852.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A701,'Updated Quanities'!F:I,7,0),R701)=\"\",R701,IFERROR(VLOOKUP('AUP Library'!A701,'Updated Quanities'!F:I,7,0),R701))","v":852.01},852.01,{"$f":"IFERROR(VLOOKUP('AUP Library'!A701,'Updated Quanities'!F:G,4,0),R701)","v":852.01}]
["730-03.20","Install Pull Box (Type A)","EA",354.33,354.33,354.33,354.33,354.33,354.33,354.33,354.33,354.33,354.33,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A702,'Updated Quanities'!F:I,4,0),R702)=\"\",R702,IFERROR(VLOOKUP('AUP Library'!A702,'Updated Quanities'!F:I,4,0),R702))","v":354.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A702,'Updated Quanities'!F:I,5,0),R702)=\"\",R702,IFERROR(VLOOKUP('AUP Library'!A702,'Updated Quanities'!F:I,5,0),R702))","v":354.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A702,'Updated Quanities'!F:I,6,0),R702)=\"\",R702,IFERROR(VLOOKUP('AUP Library'!A702,'Updated Quanities'!F:I,6,0),R702))","v":354.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A702,'Updated Quanities'!F:I,7,0),R702)=\"\",R702,IFERROR(VLOOKUP('AUP Library'!A702,'Updated Quanities'!F:I,7,0),R702))","v":354.33},354.33,{"$f":"IFERROR(VLOOKUP('AUP Library'!A702,'Updated Quanities'!F:G,4,0),R702)","v":354.33}]
["730-03.21","Install Pull Box (Type B)","EA",442.63,442.63,442.63,442.63,442.63,442.63,442.63,442.63,442.63,442.63,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A703,'Updated Quanities'!F:I,4,0),R703)=\"\",R703,IFERROR(VLOOKUP('AUP Library'!A703,'Updated Quanities'!F:I,4,0),R703))","v":442.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A703,'Updated Quanities'!F:I,5,0),R703)=\"\",R703,IFERROR(VLOOKUP('AUP Library'!A703,'Updated Quanities'!F:I,5,0),R703))","v":442.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A703,'Updated Quanities'!F:I,6,0),R703)=\"\",R703,IFERROR(VLOOKUP('AUP Library'!A703,'Updated Quanities'!F:I,6,0),R703))","v":442.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A703,'Updated Quanities'!F:I,7,0),R703)=\"\",R703,IFERROR(VLOOKUP('AUP Library'!A703,'Updated Quanities'!F:I,7,0),R703))","v":442.63},442.63,{"$f":"IFERROR(VLOOKUP('AUP Library'!A703,'Updated Quanities'!F:G,4,0),R703)","v":442.63}]
["730-03.25","Install Pull Box","EA",1320,1320,1320,1320,1320,1320,1320,1320,1320,1320,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A704,'Updated Quanities'!F:I,4,0),R704)=\"\",R704,IFERROR(VLOOKUP('AUP Library'!A704,'Updated Quanities'!F:I,4,0),R704))","v":1320},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A704,'Updated Quanities'!F:I,5,0),R704)=\"\",R704,IFERROR(VLOOKUP('AUP Library'!A704,'Updated Quanities'!F:I,5,0),R704))","v":1320},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A704,'Updated Quanities'!F:I,6,0),R704)=\"\",R704,IFERROR(VLOOKUP('AUP Library'!A704,'Updated Quanities'!F:I,6,0),R704))","v":1320},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A704,'Updated Quanities'!F:I,7,0),R704)=\"\",R704,IFERROR(VLOOKUP('AUP Library'!A704,'Updated Quanities'!F:I,7,0),R704))","v":1320},1320,{"$f":"IFERROR(VLOOKUP('AUP Library'!A704,'Updated Quanities'!F:G,4,0),R704)","v":1320}]
["730-05.01","Electrical Service Connection","EA",1886.85,1886.85,1886.85,1886.85,1886.85,1886.85,1886.85,1886.85,1886.85,1886.85,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A705,'Updated Quanities'!F:I,4,0),R705)=\"\",R705,IFERROR(VLOOKUP('AUP Library'!A705,'Updated Quanities'!F:I,4,0),R705))","v":1886.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A705,'Updated Quanities'!F:I,5,0),R705)=\"\",R705,IFERROR(VLOOKUP('AUP Library'!A705,'Updated Quanities'!F:I,5,0),R705))","v":1886.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A705,'Updated Quanities'!F:I,6,0),R705)=\"\",R705,IFERROR(VLOOKUP('AUP Library'!A705,'Updated Quanities'!F:I,6,0),R705))","v":1886.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A705,'Updated Quanities'!F:I,7,0),R705)=\"\",R705,IFERROR(VLOOKUP('AUP Library'!A705,'Updated Quanities'!F:I,7,0),R705))","v":1886.85},1886.85,{"$f":"IFERROR(VLOOKUP('AUP Library'!A705,'Updated Quanities'!F:G,4,0),R705)","v":1886.85}]
["730-08.01","Signal Cable - 3 Conductor","LF",1.19,1.19,1.19,1.19,1.19,1.19,1.19,1.19,1.19,1.19,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A706,'Updated Quanities'!F:I,4,0),R706)=\"\",R706,IFERROR(VLOOKUP('AUP Library'!A706,'Updated Quanities'!F:I,4,0),R706))","v":1.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A706,'Updated Quanities'!F:I,5,0),R706)=\"\",R706,IFERROR(VLOOKUP('AUP Library'!A706,'Updated Quanities'!F:I,5,0),R706))","v":1.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A706,'Updated Quanities'!F:I,6,0),R706)=\"\",R706,IFERROR(VLOOKUP('AUP Library'!A706,'Updated Quanities'!F:I,6,0),R706))","v":1.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A706,'Updated Quanities'!F:I,7,0),R706)=\"\",R706,IFERROR(VLOOKUP('AUP Library'!A706,'Updated Quanities'!F:I,7,0),R706))","v":1.19},1.19,{"$f":"IFERROR(VLOOKUP('AUP Library'!A706,'Updated Quanities'!F:G,4,0),R706)","v":1.19}]
["730-08.02","Signal Cable - 5 Conductor","LF",1.37,1.37,1.37,1.37,1.37,1.37,1.37,1.37,1.37,1.37,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A707,'Updated Quanities'!F:I,4,0),R707)=\"\",R707,IFERROR(VLOOKUP('AUP Library'!A707,'Updated Quanities'!F:I,4,0),R707))","v":1.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A707,'Updated Quanities'!F:I,5,0),R707)=\"\",R707,IFERROR(VLOOKUP('AUP Library'!A707,'Updated Quanities'!F:I,5,0),R707))","v":1.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A707,'Updated Quanities'!F:I,6,0),R707)=\"\",R707,IFERROR(VLOOKUP('AUP Library'!A707,'Updated Quanities'!F:I,6,0),R707))","v":1.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A707,'Updated Quanities'!F:I,7,0),R707)=\"\",R707,IFERROR(VLOOKUP('AUP Library'!A707,'Updated Quanities'!F:I,7,0),R707))","v":1.37},1.37,{"$f":"IFERROR(VLOOKUP('AUP Library'!A707,'Updated Quanities'!F:G,4,0),R707)","v":1.37}]
["730-08.03","Signal Cable - 7 Conductor","LF",1.53,1.53,1.53,1.53,1.53,1.53,1.53,1.53,1.53,1.53,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A708,'Updated Quanities'!F:I,4,0),R708)=\"\",R708,IFERROR(VLOOKUP('AUP Library'!A708,'Updated Quanities'!F:I,4,0),R708))","v":1.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A708,'Updated Quanities'!F:I,5,0),R708)=\"\",R708,IFERROR(VLOOKUP('AUP Library'!A708,'Updated Quanities'!F:I,5,0),R708))","v":1.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A708,'Updated Quanities'!F:I,6,0),R708)=\"\",R708,IFERROR(VLOOKUP('AUP Library'!A708,'Updated Quanities'!F:I,6,0),R708))","v":1.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A708,'Updated Quanities'!F:I,7,0),R708)=\"\",R708,IFERROR(VLOOKUP('AUP Library'!A708,'Updated Quanities'!F:I,7,0),R708))","v":1.53},1.53,{"$f":"IFERROR(VLOOKUP('AUP Library'!A708,'Updated Quanities'!F:G,4,0),R708)","v":1.53}]
["730-08.30","Interconnect Cable (Copper-Twisted Pair)","LF",2.67,2.67,2.67,2.67,2.67,2.67,2.67,2.67,2.67,2.67,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A709,'Updated Quanities'!F:I,4,0),R709)=\"\",R709,IFERROR(VLOOKUP('AUP Library'!A709,'Updated Quanities'!F:I,4,0),R709))","v":2.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A709,'Updated Quanities'!F:I,5,0),R709)=\"\",R709,IFERROR(VLOOKUP('AUP Library'!A709,'Updated Quanities'!F:I,5,0),R709))","v":2.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A709,'Updated Quanities'!F:I,6,0),R709)=\"\",R709,IFERROR(VLOOKUP('AUP Library'!A709,'Updated Quanities'!F:I,6,0),R709))","v":2.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A709,'Updated Quanities'!F:I,7,0),R709)=\"\",R709,IFERROR(VLOOKUP('AUP Library'!A709,'Updated Quanities'!F:I,7,0),R709))","v":2.67},2.67,{"$f":"IFERROR(VLOOKUP('AUP Library'!A709,'Updated Quanities'!F:G,4,0),R709)","v":2.67}]
["730-09.01","SPAN WIRE ASSEMBLY","LF",3.19,3.19,3.19,3.19,3.19,3.19,3.19,3.19,3.19,3.19,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A710,'Updated Quanities'!F:I,4,0),R710)=\"\",R710,IFERROR(VLOOKUP('AUP Library'!A710,'Updated Quanities'!F:I,4,0),R710))","v":3.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A710,'Updated Quanities'!F:I,5,0),R710)=\"\",R710,IFERROR(VLOOKUP('AUP Library'!A710,'Updated Quanities'!F:I,5,0),R710))","v":3.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A710,'Updated Quanities'!F:I,6,0),R710)=\"\",R710,IFERROR(VLOOKUP('AUP Library'!A710,'Updated Quanities'!F:I,6,0),R710))","v":3.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A710,'Updated Quanities'!F:I,7,0),R710)=\"\",R710,IFERROR(VLOOKUP('AUP Library'!A710,'Updated Quanities'!F:I,7,0),R710))","v":3.19},3.19,{"$f":"IFERROR(VLOOKUP('AUP Library'!A710,'Updated Quanities'!F:G,4,0),R710)","v":3.19}]
["730-09.02","SPAN WIRE ASSEMBLY","LF",4.42,4.42,4.42,4.42,4.42,4.42,4.42,4.42,4.42,4.42,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A711,'Updated Quanities'!F:I,4,0),R711)=\"\",R711,IFERROR(VLOOKUP('AUP Library'!A711,'Updated Quanities'!F:I,4,0),R711))","v":4.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A711,'Updated Quanities'!F:I,5,0),R711)=\"\",R711,IFERROR(VLOOKUP('AUP Library'!A711,'Updated Quanities'!F:I,5,0),R711))","v":4.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A711,'Updated Quanities'!F:I,6,0),R711)=\"\",R711,IFERROR(VLOOKUP('AUP Library'!A711,'Updated Quanities'!F:I,6,0),R711))","v":4.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A711,'Updated Quanities'!F:I,7,0),R711)=\"\",R711,IFERROR(VLOOKUP('AUP Library'!A711,'Updated Quanities'!F:I,7,0),R711))","v":4.42},4.42,{"$f":"IFERROR(VLOOKUP('AUP Library'!A711,'Updated Quanities'!F:G,4,0),R711)","v":4.42}]
["730-10.01","TETHER WIRE ASSEMBLY - 1/4\" DIAMETER","LF",2.19,2.19,2.19,2.19,2.19,2.19,2.19,2.19,2.19,2.19,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A712,'Updated Quanities'!F:I,4,0),R712)=\"\",R712,IFERROR(VLOOKUP('AUP Library'!A712,'Updated Quanities'!F:I,4,0),R712))","v":2.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A712,'Updated Quanities'!F:I,5,0),R712)=\"\",R712,IFERROR(VLOOKUP('AUP Library'!A712,'Updated Quanities'!F:I,5,0),R712))","v":2.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A712,'Updated Quanities'!F:I,6,0),R712)=\"\",R712,IFERROR(VLOOKUP('AUP Library'!A712,'Updated Quanities'!F:I,6,0),R712))","v":2.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A712,'Updated Quanities'!F:I,7,0),R712)=\"\",R712,IFERROR(VLOOKUP('AUP Library'!A712,'Updated Quanities'!F:I,7,0),R712))","v":2.19},2.19,{"$f":"IFERROR(VLOOKUP('AUP Library'!A712,'Updated Quanities'!F:G,4,0),R712)","v":2.19}]
["730-10.02","MESSENGER CABLE - 1/4\" DIAMETER","LF",2.11,2.11,2.11,2.11,2.11,2.11,2.11,2.11,2.11,2.11,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A713,'Updated Quanities'!F:I,4,0),R713)=\"\",R713,IFERROR(VLOOKUP('AUP Library'!A713,'Updated Quanities'!F:I,4,0),R713))","v":2.11},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A713,'Updated Quanities'!F:I,5,0),R713)=\"\",R713,IFERROR(VLOOKUP('AUP Library'!A713,'Updated Quanities'!F:I,5,0),R713))","v":2.11},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A713,'Updated Quanities'!F:I,6,0),R713)=\"\",R713,IFERROR(VLOOKUP('AUP Library'!A713,'Updated Quanities'!F:I,6,0),R713))","v":2.11},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A713,'Updated Quanities'!F:I,7,0),R713)=\"\",R713,IFERROR(VLOOKUP('AUP Library'!A713,'Updated Quanities'!F:I,7,0),R713))","v":2.11},2.11,{"$f":"IFERROR(VLOOKUP('AUP Library'!A713,'Updated Quanities'!F:G,4,0),R713)","v":2.11}]
["730-11.01","STEEL CONDUIT RISER ASSEMBLY","EA",315.82,315.82,315.82,315.82,315.82,315.82,315.82,315.82,315.82,315.82,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A714,'Updated Quanities'!F:I,4,0),R714)=\"\",R714,IFERROR(VLOOKUP('AUP Library'!A714,'Updated Quanities'!F:I,4,0),R714))","v":315.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A714,'Updated Quanities'!F:I,5,0),R714)=\"\",R714,IFERROR(VLOOKUP('AUP Library'!A714,'Updated Quanities'!F:I,5,0),R714))","v":315.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A714,'Updated Quanities'!F:I,6,0),R714)=\"\",R714,IFERROR(VLOOKUP('AUP Library'!A714,'Updated Quanities'!F:I,6,0),R714))","v":315.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A714,'Updated Quanities'!F:I,7,0),R714)=\"\",R714,IFERROR(VLOOKUP('AUP Library'!A714,'Updated Quanities'!F:I,7,0),R714))","v":315.82},315.82,{"$f":"IFERROR(VLOOKUP('AUP Library'!A714,'Updated Quanities'!F:G,4,0),R714)","v":315.82}]
["730-11.10","RISER ASSEMBLY","EA",399.69,399.69,399.69,399.69,399.69,399.69,399.69,399.69,399.69,399.69,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A715,'Updated Quanities'!F:I,4,0),R715)=\"\",R715,IFERROR(VLOOKUP('AUP Library'!A715,'Updated Quanities'!F:I,4,0),R715))","v":399.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A715,'Updated Quanities'!F:I,5,0),R715)=\"\",R715,IFERROR(VLOOKUP('AUP Library'!A715,'Updated Quanities'!F:I,5,0),R715))","v":399.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A715,'Updated Quanities'!F:I,6,0),R715)=\"\",R715,IFERROR(VLOOKUP('AUP Library'!A715,'Updated Quanities'!F:I,6,0),R715))","v":399.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A715,'Updated Quanities'!F:I,7,0),R715)=\"\",R715,IFERROR(VLOOKUP('AUP Library'!A715,'Updated Quanities'!F:I,7,0),R715))","v":399.69},399.69,{"$f":"IFERROR(VLOOKUP('AUP Library'!A715,'Updated Quanities'!F:G,4,0),R715)","v":399.69}]
["730-11.11","RISER ASSEMBLY","EA",2218.29,2218.29,2218.29,2218.29,2218.29,2218.29,2218.29,2218.29,2218.29,2218.29,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A716,'Updated Quanities'!F:I,4,0),R716)=\"\",R716,IFERROR(VLOOKUP('AUP Library'!A716,'Updated Quanities'!F:I,4,0),R716))","v":2218.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A716,'Updated Quanities'!F:I,5,0),R716)=\"\",R716,IFERROR(VLOOKUP('AUP Library'!A716,'Updated Quanities'!F:I,5,0),R716))","v":2218.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A716,'Updated Quanities'!F:I,6,0),R716)=\"\",R716,IFERROR(VLOOKUP('AUP Library'!A716,'Updated Quanities'!F:I,6,0),R716))","v":2218.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A716,'Updated Quanities'!F:I,7,0),R716)=\"\",R716,IFERROR(VLOOKUP('AUP Library'!A716,'Updated Quanities'!F:I,7,0),R716))","v":2218.29},2218.29,{"$f":"IFERROR(VLOOKUP('AUP Library'!A716,'Updated Quanities'!F:G,4,0),R716)","v":2218.29}]
["730-12.01","Conduit 1\" Diameter (PVC)","LF",6.22,6.22,6.22,6.22,6.22,6.22,6.22,6.22,6.22,6.22,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A717,'Updated Quanities'!F:I,4,0),R717)=\"\",R717,IFERROR(VLOOKUP('AUP Library'!A717,'Updated Quanities'!F:I,4,0),R717))","v":6.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A717,'Updated Quanities'!F:I,5,0),R717)=\"\",R717,IFERROR(VLOOKUP('AUP Library'!A717,'Updated Quanities'!F:I,5,0),R717))","v":6.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A717,'Updated Quanities'!F:I,6,0),R717)=\"\",R717,IFERROR(VLOOKUP('AUP Library'!A717,'Updated Quanities'!F:I,6,0),R717))","v":6.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A717,'Updated Quanities'!F:I,7,0),R717)=\"\",R717,IFERROR(VLOOKUP('AUP Library'!A717,'Updated Quanities'!F:I,7,0),R717))","v":6.22},6.22,{"$f":"IFERROR(VLOOKUP('AUP Library'!A717,'Updated Quanities'!F:G,4,0),R717)","v":6.22}]
["730-12.02","Conduit 2\" Diameter (PVC)","LF",6.03,6.03,6.03,6.03,6.03,6.03,6.03,6.03,6.03,6.03,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A718,'Updated Quanities'!F:I,4,0),R718)=\"\",R718,IFERROR(VLOOKUP('AUP Library'!A718,'Updated Quanities'!F:I,4,0),R718))","v":6.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A718,'Updated Quanities'!F:I,5,0),R718)=\"\",R718,IFERROR(VLOOKUP('AUP Library'!A718,'Updated Quanities'!F:I,5,0),R718))","v":6.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A718,'Updated Quanities'!F:I,6,0),R718)=\"\",R718,IFERROR(VLOOKUP('AUP Library'!A718,'Updated Quanities'!F:I,6,0),R718))","v":6.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A718,'Updated Quanities'!F:I,7,0),R718)=\"\",R718,IFERROR(VLOOKUP('AUP Library'!A718,'Updated Quanities'!F:I,7,0),R718))","v":6.03},6.03,{"$f":"IFERROR(VLOOKUP('AUP Library'!A718,'Updated Quanities'!F:G,4,0),R718)","v":6.03}]
["730-12.14","Conduit 3\" Diameter (Jack and Bore)","LF",22.49,22.49,22.49,22.49,22.49,22.49,22.49,22.49,22.49,22.49,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A719,'Updated Quanities'!F:I,4,0),R719)=\"\",R719,IFERROR(VLOOKUP('AUP Library'!A719,'Updated Quanities'!F:I,4,0),R719))","v":22.49},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A719,'Updated Quanities'!F:I,5,0),R719)=\"\",R719,IFERROR(VLOOKUP('AUP Library'!A719,'Updated Quanities'!F:I,5,0),R719))","v":22.49},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A719,'Updated Quanities'!F:I,6,0),R719)=\"\",R719,IFERROR(VLOOKUP('AUP Library'!A719,'Updated Quanities'!F:I,6,0),R719))","v":22.49},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A719,'Updated Quanities'!F:I,7,0),R719)=\"\",R719,IFERROR(VLOOKUP('AUP Library'!A719,'Updated Quanities'!F:I,7,0),R719))","v":22.49},22.49,{"$f":"IFERROR(VLOOKUP('AUP Library'!A719,'Updated Quanities'!F:G,4,0),R719)","v":22.49}]
["730-12.16","Conduit (2\" Conduit Schedule 80)","LF",17.71,17.71,17.71,17.71,17.71,17.71,17.71,17.71,17.71,17.71,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A720,'Updated Quanities'!F:I,4,0),R720)=\"\",R720,IFERROR(VLOOKUP('AUP Library'!A720,'Updated Quanities'!F:I,4,0),R720))","v":17.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A720,'Updated Quanities'!F:I,5,0),R720)=\"\",R720,IFERROR(VLOOKUP('AUP Library'!A720,'Updated Quanities'!F:I,5,0),R720))","v":17.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A720,'Updated Quanities'!F:I,6,0),R720)=\"\",R720,IFERROR(VLOOKUP('AUP Library'!A720,'Updated Quanities'!F:I,6,0),R720))","v":17.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A720,'Updated Quanities'!F:I,7,0),R720)=\"\",R720,IFERROR(VLOOKUP('AUP Library'!A720,'Updated Quanities'!F:I,7,0),R720))","v":17.71},17.71,{"$f":"IFERROR(VLOOKUP('AUP Library'!A720,'Updated Quanities'!F:G,4,0),R720)","v":17.71}]
["730-12.17","Conduit (3\" Conduit Schedule 80)","LF",26.33,26.33,26.33,26.33,26.33,26.33,26.33,26.33,26.33,26.33,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A721,'Updated Quanities'!F:I,4,0),R721)=\"\",R721,IFERROR(VLOOKUP('AUP Library'!A721,'Updated Quanities'!F:I,4,0),R721))","v":26.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A721,'Updated Quanities'!F:I,5,0),R721)=\"\",R721,IFERROR(VLOOKUP('AUP Library'!A721,'Updated Quanities'!F:I,5,0),R721))","v":26.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A721,'Updated Quanities'!F:I,6,0),R721)=\"\",R721,IFERROR(VLOOKUP('AUP Library'!A721,'Updated Quanities'!F:I,6,0),R721))","v":26.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A721,'Updated Quanities'!F:I,7,0),R721)=\"\",R721,IFERROR(VLOOKUP('AUP Library'!A721,'Updated Quanities'!F:I,7,0),R721))","v":26.33},26.33,{"$f":"IFERROR(VLOOKUP('AUP Library'!A721,'Updated Quanities'!F:G,4,0),R721)","v":26.33}]
["730-13.01","VEHICLE LOOP DETECTOR (SHELF MOUNT)","EA",175.12,175.12,175.12,175.12,175.12,175.12,175.12,175.12,175.12,175.12,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A722,'Updated Quanities'!F:I,4,0),R722)=\"\",R722,IFERROR(VLOOKUP('AUP Library'!A722,'Updated Quanities'!F:I,4,0),R722))","v":175.12},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A722,'Updated Quanities'!F:I,5,0),R722)=\"\",R722,IFERROR(VLOOKUP('AUP Library'!A722,'Updated Quanities'!F:I,5,0),R722))","v":175.12},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A722,'Updated Quanities'!F:I,6,0),R722)=\"\",R722,IFERROR(VLOOKUP('AUP Library'!A722,'Updated Quanities'!F:I,6,0),R722))","v":175.12},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A722,'Updated Quanities'!F:I,7,0),R722)=\"\",R722,IFERROR(VLOOKUP('AUP Library'!A722,'Updated Quanities'!F:I,7,0),R722))","v":175.12},175.12,{"$f":"IFERROR(VLOOKUP('AUP Library'!A722,'Updated Quanities'!F:G,4,0),R722)","v":175.12}]
["730-13.02","Vehicle Detector (Video)","EA",6581.42,6581.42,6581.42,6581.42,6581.42,6581.42,6581.42,6581.42,6581.42,6581.42,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A723,'Updated Quanities'!F:I,4,0),R723)=\"\",R723,IFERROR(VLOOKUP('AUP Library'!A723,'Updated Quanities'!F:I,4,0),R723))","v":6581.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A723,'Updated Quanities'!F:I,5,0),R723)=\"\",R723,IFERROR(VLOOKUP('AUP Library'!A723,'Updated Quanities'!F:I,5,0),R723))","v":6581.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A723,'Updated Quanities'!F:I,6,0),R723)=\"\",R723,IFERROR(VLOOKUP('AUP Library'!A723,'Updated Quanities'!F:I,6,0),R723))","v":6581.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A723,'Updated Quanities'!F:I,7,0),R723)=\"\",R723,IFERROR(VLOOKUP('AUP Library'!A723,'Updated Quanities'!F:I,7,0),R723))","v":6581.42},6581.42,{"$f":"IFERROR(VLOOKUP('AUP Library'!A723,'Updated Quanities'!F:G,4,0),R723)","v":6581.42}]
["730-13.03","Vehicle Detector (4-Channel, Rack Mount)","EA",341.07,341.07,341.07,341.07,341.07,341.07,341.07,341.07,341.07,341.07,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A724,'Updated Quanities'!F:I,4,0),R724)=\"\",R724,IFERROR(VLOOKUP('AUP Library'!A724,'Updated Quanities'!F:I,4,0),R724))","v":341.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A724,'Updated Quanities'!F:I,5,0),R724)=\"\",R724,IFERROR(VLOOKUP('AUP Library'!A724,'Updated Quanities'!F:I,5,0),R724))","v":341.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A724,'Updated Quanities'!F:I,6,0),R724)=\"\",R724,IFERROR(VLOOKUP('AUP Library'!A724,'Updated Quanities'!F:I,6,0),R724))","v":341.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A724,'Updated Quanities'!F:I,7,0),R724)=\"\",R724,IFERROR(VLOOKUP('AUP Library'!A724,'Updated Quanities'!F:I,7,0),R724))","v":341.07},341.07,{"$f":"IFERROR(VLOOKUP('AUP Library'!A724,'Updated Quanities'!F:G,4,0),R724)","v":341.07}]
["730-14.01","Shielded Detector Cable","LF",1.07,1.07,1.07,1.07,1.07,1.07,1.07,1.07,1.07,1.07,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A725,'Updated Quanities'!F:I,4,0),R725)=\"\",R725,IFERROR(VLOOKUP('AUP Library'!A725,'Updated Quanities'!F:I,4,0),R725))","v":1.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A725,'Updated Quanities'!F:I,5,0),R725)=\"\",R725,IFERROR(VLOOKUP('AUP Library'!A725,'Updated Quanities'!F:I,5,0),R725))","v":1.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A725,'Updated Quanities'!F:I,6,0),R725)=\"\",R725,IFERROR(VLOOKUP('AUP Library'!A725,'Updated Quanities'!F:I,6,0),R725))","v":1.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A725,'Updated Quanities'!F:I,7,0),R725)=\"\",R725,IFERROR(VLOOKUP('AUP Library'!A725,'Updated Quanities'!F:I,7,0),R725))","v":1.07},1.07,{"$f":"IFERROR(VLOOKUP('AUP Library'!A725,'Updated Quanities'!F:G,4,0),R725)","v":1.07}]
["730-14.02","Saw Slot","LF",2.81,2.81,2.81,2.81,2.81,2.81,2.81,2.81,2.81,2.81,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A726,'Updated Quanities'!F:I,4,0),R726)=\"\",R726,IFERROR(VLOOKUP('AUP Library'!A726,'Updated Quanities'!F:I,4,0),R726))","v":2.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A726,'Updated Quanities'!F:I,5,0),R726)=\"\",R726,IFERROR(VLOOKUP('AUP Library'!A726,'Updated Quanities'!F:I,5,0),R726))","v":2.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A726,'Updated Quanities'!F:I,6,0),R726)=\"\",R726,IFERROR(VLOOKUP('AUP Library'!A726,'Updated Quanities'!F:I,6,0),R726))","v":2.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A726,'Updated Quanities'!F:I,7,0),R726)=\"\",R726,IFERROR(VLOOKUP('AUP Library'!A726,'Updated Quanities'!F:I,7,0),R726))","v":2.81},2.81,{"$f":"IFERROR(VLOOKUP('AUP Library'!A726,'Updated Quanities'!F:G,4,0),R726)","v":2.81}]
["730-14.03","Loop Wire","LF",0.53,0.53,0.53,0.53,0.53,0.53,0.53,0.53,0.53,0.53,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A727,'Updated Quanities'!F:I,4,0),R727)=\"\",R727,IFERROR(VLOOKUP('AUP Library'!A727,'Updated Quanities'!F:I,4,0),R727))","v":0.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A727,'Updated Quanities'!F:I,5,0),R727)=\"\",R727,IFERROR(VLOOKUP('AUP Library'!A727,'Updated Quanities'!F:I,5,0),R727))","v":0.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A727,'Updated Quanities'!F:I,6,0),R727)=\"\",R727,IFERROR(VLOOKUP('AUP Library'!A727,'Updated Quanities'!F:I,6,0),R727))","v":0.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A727,'Updated Quanities'!F:I,7,0),R727)=\"\",R727,IFERROR(VLOOKUP('AUP Library'!A727,'Updated Quanities'!F:I,7,0),R727))","v":0.53},0.53,{"$f":"IFERROR(VLOOKUP('AUP Library'!A727,'Updated Quanities'!F:G,4,0),R727)","v":0.53}]
["730-15.07","Cabinet","EA",3869.67,3869.67,3869.67,3869.67,3869.67,3869.67,3869.67,3869.67,3869.67,3869.67,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A728,'Updated Quanities'!F:I,4,0),R728)=\"\",R728,IFERROR(VLOOKUP('AUP Library'!A728,'Updated Quanities'!F:I,4,0),R728))","v":3869.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A728,'Updated Quanities'!F:I,5,0),R728)=\"\",R728,IFERROR(VLOOKUP('AUP Library'!A728,'Updated Quanities'!F:I,5,0),R728))","v":3869.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A728,'Updated Quanities'!F:I,6,0),R728)=\"\",R728,IFERROR(VLOOKUP('AUP Library'!A728,'Updated Quanities'!F:I,6,0),R728))","v":3869.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A728,'Updated Quanities'!F:I,7,0),R728)=\"\",R728,IFERROR(VLOOKUP('AUP Library'!A728,'Updated Quanities'!F:I,7,0),R728))","v":3869.67},3869.67,{"$f":"IFERROR(VLOOKUP('AUP Library'!A728,'Updated Quanities'!F:G,4,0),R728)","v":3869.67}]
["730-15.32","Cabinet (Eight Phase Base Mounted)","EA",11759.07,11759.07,11759.07,11759.07,11759.07,11759.07,11759.07,11759.07,11759.07,11759.07,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A729,'Updated Quanities'!F:I,4,0),R729)=\"\",R729,IFERROR(VLOOKUP('AUP Library'!A729,'Updated Quanities'!F:I,4,0),R729))","v":11759.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A729,'Updated Quanities'!F:I,5,0),R729)=\"\",R729,IFERROR(VLOOKUP('AUP Library'!A729,'Updated Quanities'!F:I,5,0),R729))","v":11759.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A729,'Updated Quanities'!F:I,6,0),R729)=\"\",R729,IFERROR(VLOOKUP('AUP Library'!A729,'Updated Quanities'!F:I,6,0),R729))","v":11759.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A729,'Updated Quanities'!F:I,7,0),R729)=\"\",R729,IFERROR(VLOOKUP('AUP Library'!A729,'Updated Quanities'!F:I,7,0),R729))","v":11759.07},11759.07,{"$f":"IFERROR(VLOOKUP('AUP Library'!A729,'Updated Quanities'!F:G,4,0),R729)","v":11759.07}]
["730-16.02","Eight Phase Actuated Controller","EA",4418.8900000000003,4418.8900000000003,4418.8900000000003,4418.8900000000003,4418.8900000000003,4418.8900000000003,4418.8900000000003,4418.8900000000003,4418.8900000000003,4418.8900000000003,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A730,'Updated Quanities'!F:I,4,0),R730)=\"\",R730,IFERROR(VLOOKUP('AUP Library'!A730,'Updated Quanities'!F:I,4,0),R730))","v":4418.8900000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A730,'Updated Quanities'!F:I,5,0),R730)=\"\",R730,IFERROR(VLOOKUP('AUP Library'!A730,'Updated Quanities'!F:I,5,0),R730))","v":4418.8900000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A730,'Updated Quanities'!F:I,6,0),R730)=\"\",R730,IFERROR(VLOOKUP('AUP Library'!A730,'Updated Quanities'!F:I,6,0),R730))","v":4418.8900000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A730,'Updated Quanities'!F:I,7,0),R730)=\"\",R730,IFERROR(VLOOKUP('AUP Library'!A730,'Updated Quanities'!F:I,7,0),R730))","v":4418.8900000000003},4418.8900000000003,{"$f":"IFERROR(VLOOKUP('AUP Library'!A730,'Updated Quanities'!F:G,4,0),R730)","v":4418.8900000000003}]
["730-18.01","Master Controller","EA",5444.38,5444.38,5444.38,5444.38,5444.38,5444.38,5444.38,5444.38,5444.38,5444.38,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A731,'Updated Quanities'!F:I,4,0),R731)=\"\",R731,IFERROR(VLOOKUP('AUP Library'!A731,'Updated Quanities'!F:I,4,0),R731))","v":5444.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A731,'Updated Quanities'!F:I,5,0),R731)=\"\",R731,IFERROR(VLOOKUP('AUP Library'!A731,'Updated Quanities'!F:I,5,0),R731))","v":5444.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A731,'Updated Quanities'!F:I,6,0),R731)=\"\",R731,IFERROR(VLOOKUP('AUP Library'!A731,'Updated Quanities'!F:I,6,0),R731))","v":5444.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A731,'Updated Quanities'!F:I,7,0),R731)=\"\",R731,IFERROR(VLOOKUP('AUP Library'!A731,'Updated Quanities'!F:I,7,0),R731))","v":5444.38},5444.38,{"$f":"IFERROR(VLOOKUP('AUP Library'!A731,'Updated Quanities'!F:G,4,0),R731)","v":5444.38}]
["730-23.01","STEEL STRAIN POLE (SIGNAL SUPPORT)","EA",11019.99,11019.99,11019.99,11019.99,11019.99,11019.99,11019.99,11019.99,11019.99,11019.99,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A732,'Updated Quanities'!F:I,4,0),R732)=\"\",R732,IFERROR(VLOOKUP('AUP Library'!A732,'Updated Quanities'!F:I,4,0),R732))","v":11019.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A732,'Updated Quanities'!F:I,5,0),R732)=\"\",R732,IFERROR(VLOOKUP('AUP Library'!A732,'Updated Quanities'!F:I,5,0),R732))","v":11019.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A732,'Updated Quanities'!F:I,6,0),R732)=\"\",R732,IFERROR(VLOOKUP('AUP Library'!A732,'Updated Quanities'!F:I,6,0),R732))","v":11019.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A732,'Updated Quanities'!F:I,7,0),R732)=\"\",R732,IFERROR(VLOOKUP('AUP Library'!A732,'Updated Quanities'!F:I,7,0),R732))","v":11019.99},11019.99,{"$f":"IFERROR(VLOOKUP('AUP Library'!A732,'Updated Quanities'!F:G,4,0),R732)","v":11019.99}]
["730-23.30","Pedestal Pole (10' Pedestrian)","EA",1457.9,1457.9,1457.9,1457.9,1457.9,1457.9,1457.9,1457.9,1457.9,1457.9,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A733,'Updated Quanities'!F:I,4,0),R733)=\"\",R733,IFERROR(VLOOKUP('AUP Library'!A733,'Updated Quanities'!F:I,4,0),R733))","v":1457.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A733,'Updated Quanities'!F:I,5,0),R733)=\"\",R733,IFERROR(VLOOKUP('AUP Library'!A733,'Updated Quanities'!F:I,5,0),R733))","v":1457.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A733,'Updated Quanities'!F:I,6,0),R733)=\"\",R733,IFERROR(VLOOKUP('AUP Library'!A733,'Updated Quanities'!F:I,6,0),R733))","v":1457.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A733,'Updated Quanities'!F:I,7,0),R733)=\"\",R733,IFERROR(VLOOKUP('AUP Library'!A733,'Updated Quanities'!F:I,7,0),R733))","v":1457.9},1457.9,{"$f":"IFERROR(VLOOKUP('AUP Library'!A733,'Updated Quanities'!F:G,4,0),R733)","v":1457.9}]
["730-23.72","Cantilever Signal Support (1 ARM @ 35')","EA",10861,10861,10861,10861,10861,10861,10861,10861,10861,10861,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A734,'Updated Quanities'!F:I,4,0),R734)=\"\",R734,IFERROR(VLOOKUP('AUP Library'!A734,'Updated Quanities'!F:I,4,0),R734))","v":10861},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A734,'Updated Quanities'!F:I,5,0),R734)=\"\",R734,IFERROR(VLOOKUP('AUP Library'!A734,'Updated Quanities'!F:I,5,0),R734))","v":10861},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A734,'Updated Quanities'!F:I,6,0),R734)=\"\",R734,IFERROR(VLOOKUP('AUP Library'!A734,'Updated Quanities'!F:I,6,0),R734))","v":10861},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A734,'Updated Quanities'!F:I,7,0),R734)=\"\",R734,IFERROR(VLOOKUP('AUP Library'!A734,'Updated Quanities'!F:I,7,0),R734))","v":10861},10861,{"$f":"IFERROR(VLOOKUP('AUP Library'!A734,'Updated Quanities'!F:G,4,0),R734)","v":10861}]
["730-23.88","Cantilever Signal Support (1 ARM @ 45')","EA",14116.19,14116.19,14116.19,14116.19,14116.19,14116.19,14116.19,14116.19,14116.19,14116.19,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A735,'Updated Quanities'!F:I,4,0),R735)=\"\",R735,IFERROR(VLOOKUP('AUP Library'!A735,'Updated Quanities'!F:I,4,0),R735))","v":14116.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A735,'Updated Quanities'!F:I,5,0),R735)=\"\",R735,IFERROR(VLOOKUP('AUP Library'!A735,'Updated Quanities'!F:I,5,0),R735))","v":14116.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A735,'Updated Quanities'!F:I,6,0),R735)=\"\",R735,IFERROR(VLOOKUP('AUP Library'!A735,'Updated Quanities'!F:I,6,0),R735))","v":14116.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A735,'Updated Quanities'!F:I,7,0),R735)=\"\",R735,IFERROR(VLOOKUP('AUP Library'!A735,'Updated Quanities'!F:I,7,0),R735))","v":14116.19},14116.19,{"$f":"IFERROR(VLOOKUP('AUP Library'!A735,'Updated Quanities'!F:G,4,0),R735)","v":14116.19}]
["730-23.96","Cantilever Signal Support (1 ARM @ 50')","EA",18934.23,18934.23,18934.23,18934.23,18934.23,18934.23,18934.23,18934.23,18934.23,18934.23,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A736,'Updated Quanities'!F:I,4,0),R736)=\"\",R736,IFERROR(VLOOKUP('AUP Library'!A736,'Updated Quanities'!F:I,4,0),R736))","v":18934.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A736,'Updated Quanities'!F:I,5,0),R736)=\"\",R736,IFERROR(VLOOKUP('AUP Library'!A736,'Updated Quanities'!F:I,5,0),R736))","v":18934.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A736,'Updated Quanities'!F:I,6,0),R736)=\"\",R736,IFERROR(VLOOKUP('AUP Library'!A736,'Updated Quanities'!F:I,6,0),R736))","v":18934.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A736,'Updated Quanities'!F:I,7,0),R736)=\"\",R736,IFERROR(VLOOKUP('AUP Library'!A736,'Updated Quanities'!F:I,7,0),R736))","v":18934.23},18934.23,{"$f":"IFERROR(VLOOKUP('AUP Library'!A736,'Updated Quanities'!F:G,4,0),R736)","v":18934.23}]
["730-23.97","Cantilever Signal Support (1 ARM @ 55')","EA",19008.8,19008.8,19008.8,19008.8,19008.8,19008.8,19008.8,19008.8,19008.8,19008.8,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A737,'Updated Quanities'!F:I,4,0),R737)=\"\",R737,IFERROR(VLOOKUP('AUP Library'!A737,'Updated Quanities'!F:I,4,0),R737))","v":19008.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A737,'Updated Quanities'!F:I,5,0),R737)=\"\",R737,IFERROR(VLOOKUP('AUP Library'!A737,'Updated Quanities'!F:I,5,0),R737))","v":19008.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A737,'Updated Quanities'!F:I,6,0),R737)=\"\",R737,IFERROR(VLOOKUP('AUP Library'!A737,'Updated Quanities'!F:I,6,0),R737))","v":19008.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A737,'Updated Quanities'!F:I,7,0),R737)=\"\",R737,IFERROR(VLOOKUP('AUP Library'!A737,'Updated Quanities'!F:I,7,0),R737))","v":19008.8},19008.8,{"$f":"IFERROR(VLOOKUP('AUP Library'!A737,'Updated Quanities'!F:G,4,0),R737)","v":19008.8}]
["730-23.98","Cantilever Signal Support (1 ARM @ 60\")","EA",19836.84,19836.84,19836.84,19836.84,19836.84,19836.84,19836.84,19836.84,19836.84,19836.84,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A738,'Updated Quanities'!F:I,4,0),R738)=\"\",R738,IFERROR(VLOOKUP('AUP Library'!A738,'Updated Quanities'!F:I,4,0),R738))","v":19836.84},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A738,'Updated Quanities'!F:I,5,0),R738)=\"\",R738,IFERROR(VLOOKUP('AUP Library'!A738,'Updated Quanities'!F:I,5,0),R738))","v":19836.84},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A738,'Updated Quanities'!F:I,6,0),R738)=\"\",R738,IFERROR(VLOOKUP('AUP Library'!A738,'Updated Quanities'!F:I,6,0),R738))","v":19836.84},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A738,'Updated Quanities'!F:I,7,0),R738)=\"\",R738,IFERROR(VLOOKUP('AUP Library'!A738,'Updated Quanities'!F:I,7,0),R738))","v":19836.84},19836.84,{"$f":"IFERROR(VLOOKUP('AUP Library'!A738,'Updated Quanities'!F:G,4,0),R738)","v":19836.84}]
["730-26.02","PEDESTRIAN PUSHBUTTON WITH 12\" SIGN","EA",600,600,600,600,600,600,600,600,600,600,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A739,'Updated Quanities'!F:I,4,0),R739)=\"\",R739,IFERROR(VLOOKUP('AUP Library'!A739,'Updated Quanities'!F:I,4,0),R739))","v":600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A739,'Updated Quanities'!F:I,5,0),R739)=\"\",R739,IFERROR(VLOOKUP('AUP Library'!A739,'Updated Quanities'!F:I,5,0),R739))","v":600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A739,'Updated Quanities'!F:I,6,0),R739)=\"\",R739,IFERROR(VLOOKUP('AUP Library'!A739,'Updated Quanities'!F:I,6,0),R739))","v":600},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A739,'Updated Quanities'!F:I,7,0),R739)=\"\",R739,IFERROR(VLOOKUP('AUP Library'!A739,'Updated Quanities'!F:I,7,0),R739))","v":600},600,{"$f":"IFERROR(VLOOKUP('AUP Library'!A739,'Updated Quanities'!F:G,4,0),R739)","v":600}]
["730-26.05","Countdown Pedestrian Signal","EA",647.99,647.99,647.99,647.99,647.99,647.99,647.99,647.99,647.99,647.99,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A740,'Updated Quanities'!F:I,4,0),R740)=\"\",R740,IFERROR(VLOOKUP('AUP Library'!A740,'Updated Quanities'!F:I,4,0),R740))","v":647.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A740,'Updated Quanities'!F:I,5,0),R740)=\"\",R740,IFERROR(VLOOKUP('AUP Library'!A740,'Updated Quanities'!F:I,5,0),R740))","v":647.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A740,'Updated Quanities'!F:I,6,0),R740)=\"\",R740,IFERROR(VLOOKUP('AUP Library'!A740,'Updated Quanities'!F:I,6,0),R740))","v":647.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A740,'Updated Quanities'!F:I,7,0),R740)=\"\",R740,IFERROR(VLOOKUP('AUP Library'!A740,'Updated Quanities'!F:I,7,0),R740))","v":647.99},647.99,{"$f":"IFERROR(VLOOKUP('AUP Library'!A740,'Updated Quanities'!F:G,4,0),R740)","v":647.99}]
["N/A","Traffic Signal","EA"]
["730-40","Temporary Traffic Signal System","EA"]
[]
[]
["Guardrail"]
["705-01.01","Guardrail at Bridge Ends","LF",47.7,55.03,53.71,61.04,61.04,56.85,61.19,57.91,57.33,64.44,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A746,'Updated Quanities'!F:I,4,0),R746)=\"\",R746,IFERROR(VLOOKUP('AUP Library'!A746,'Updated Quanities'!F:I,4,0),R746))","v":62.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A746,'Updated Quanities'!F:I,5,0),R746)=\"\",R746,IFERROR(VLOOKUP('AUP Library'!A746,'Updated Quanities'!F:I,5,0),R746))","v":62.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A746,'Updated Quanities'!F:I,6,0),R746)=\"\",R746,IFERROR(VLOOKUP('AUP Library'!A746,'Updated Quanities'!F:I,6,0),R746))","v":62.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A746,'Updated Quanities'!F:I,7,0),R746)=\"\",R746,IFERROR(VLOOKUP('AUP Library'!A746,'Updated Quanities'!F:I,7,0),R746))","v":62.78},62.78,{"$f":"IFERROR(VLOOKUP('AUP Library'!A746,'Updated Quanities'!F:G,4,0),R746)","v":62.78}]
["705-01.04","Metal Beam Guard Fence (Guardrail)","LF",71.959999999999994,71.959999999999994,71.959999999999994,71.959999999999994,71.959999999999994,71.959999999999994,71.959999999999994,71.959999999999994,71.959999999999994,71.959999999999994,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A747,'Updated Quanities'!F:I,4,0),R747)=\"\",R747,IFERROR(VLOOKUP('AUP Library'!A747,'Updated Quanities'!F:I,4,0),R747))","v":71.959999999999994},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A747,'Updated Quanities'!F:I,5,0),R747)=\"\",R747,IFERROR(VLOOKUP('AUP Library'!A747,'Updated Quanities'!F:I,5,0),R747))","v":71.959999999999994},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A747,'Updated Quanities'!F:I,6,0),R747)=\"\",R747,IFERROR(VLOOKUP('AUP Library'!A747,'Updated Quanities'!F:I,6,0),R747))","v":71.959999999999994},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A747,'Updated Quanities'!F:I,7,0),R747)=\"\",R747,IFERROR(VLOOKUP('AUP Library'!A747,'Updated Quanities'!F:I,7,0),R747))","v":71.959999999999994},71.959999999999994,{"$f":"IFERROR(VLOOKUP('AUP Library'!A747,'Updated Quanities'!F:G,4,0),R747)","v":71.959999999999994}]
["705-02.02","Single Guardrail (Type 2)","LF",15.08,16.47,17.420000000000002,18.489999999999998,18.489999999999998,15.55,16.11,15.66,15.34,15.65,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A748,'Updated Quanities'!F:I,4,0),R748)=\"\",R748,IFERROR(VLOOKUP('AUP Library'!A748,'Updated Quanities'!F:I,4,0),R748))","v":15.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A748,'Updated Quanities'!F:I,5,0),R748)=\"\",R748,IFERROR(VLOOKUP('AUP Library'!A748,'Updated Quanities'!F:I,5,0),R748))","v":15.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A748,'Updated Quanities'!F:I,6,0),R748)=\"\",R748,IFERROR(VLOOKUP('AUP Library'!A748,'Updated Quanities'!F:I,6,0),R748))","v":15.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A748,'Updated Quanities'!F:I,7,0),R748)=\"\",R748,IFERROR(VLOOKUP('AUP Library'!A748,'Updated Quanities'!F:I,7,0),R748))","v":15.81},15.81,{"$f":"IFERROR(VLOOKUP('AUP Library'!A748,'Updated Quanities'!F:G,4,0),R748)","v":15.81}]
["705-02.03","Single Guardrail (Type 2) Long Post","LF",20.6,20.6,20.6,20.6,20.6,20.6,20.6,20.6,20.6,20.6,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A749,'Updated Quanities'!F:I,4,0),R749)=\"\",R749,IFERROR(VLOOKUP('AUP Library'!A749,'Updated Quanities'!F:I,4,0),R749))","v":20.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A749,'Updated Quanities'!F:I,5,0),R749)=\"\",R749,IFERROR(VLOOKUP('AUP Library'!A749,'Updated Quanities'!F:I,5,0),R749))","v":20.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A749,'Updated Quanities'!F:I,6,0),R749)=\"\",R749,IFERROR(VLOOKUP('AUP Library'!A749,'Updated Quanities'!F:I,6,0),R749))","v":20.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A749,'Updated Quanities'!F:I,7,0),R749)=\"\",R749,IFERROR(VLOOKUP('AUP Library'!A749,'Updated Quanities'!F:I,7,0),R749))","v":20.6},20.6,{"$f":"IFERROR(VLOOKUP('AUP Library'!A749,'Updated Quanities'!F:G,4,0),R749)","v":20.6}]
["705-02.50","Shop Curved Guardrail","LF",21.9,21.9,21.9,21.9,21.9,21.9,21.9,21.9,21.9,21.9,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A750,'Updated Quanities'!F:I,4,0),R750)=\"\",R750,IFERROR(VLOOKUP('AUP Library'!A750,'Updated Quanities'!F:I,4,0),R750))","v":21.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A750,'Updated Quanities'!F:I,5,0),R750)=\"\",R750,IFERROR(VLOOKUP('AUP Library'!A750,'Updated Quanities'!F:I,5,0),R750))","v":21.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A750,'Updated Quanities'!F:I,6,0),R750)=\"\",R750,IFERROR(VLOOKUP('AUP Library'!A750,'Updated Quanities'!F:I,6,0),R750))","v":21.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A750,'Updated Quanities'!F:I,7,0),R750)=\"\",R750,IFERROR(VLOOKUP('AUP Library'!A750,'Updated Quanities'!F:I,7,0),R750))","v":21.9},21.9,{"$f":"IFERROR(VLOOKUP('AUP Library'!A750,'Updated Quanities'!F:G,4,0),R750)","v":21.9}]
["705-04.02","Guardrail Terminal (Type 12)","EA",862.9,862.9,862.9,862.9,862.9,862.9,862.9,862.9,862.9,862.9,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A751,'Updated Quanities'!F:I,4,0),R751)=\"\",R751,IFERROR(VLOOKUP('AUP Library'!A751,'Updated Quanities'!F:I,4,0),R751))","v":862.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A751,'Updated Quanities'!F:I,5,0),R751)=\"\",R751,IFERROR(VLOOKUP('AUP Library'!A751,'Updated Quanities'!F:I,5,0),R751))","v":862.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A751,'Updated Quanities'!F:I,6,0),R751)=\"\",R751,IFERROR(VLOOKUP('AUP Library'!A751,'Updated Quanities'!F:I,6,0),R751))","v":862.9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A751,'Updated Quanities'!F:I,7,0),R751)=\"\",R751,IFERROR(VLOOKUP('AUP Library'!A751,'Updated Quanities'!F:I,7,0),R751))","v":862.9},862.9,{"$f":"IFERROR(VLOOKUP('AUP Library'!A751,'Updated Quanities'!F:G,4,0),R751)","v":862.9}]
["705-04.03","Guardrail Terminal (Type 13)","EA",564.27,564.27,564.27,564.27,564.27,564.27,564.27,564.27,564.27,564.27,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A752,'Updated Quanities'!F:I,4,0),R752)=\"\",R752,IFERROR(VLOOKUP('AUP Library'!A752,'Updated Quanities'!F:I,4,0),R752))","v":564.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A752,'Updated Quanities'!F:I,5,0),R752)=\"\",R752,IFERROR(VLOOKUP('AUP Library'!A752,'Updated Quanities'!F:I,5,0),R752))","v":564.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A752,'Updated Quanities'!F:I,6,0),R752)=\"\",R752,IFERROR(VLOOKUP('AUP Library'!A752,'Updated Quanities'!F:I,6,0),R752))","v":564.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A752,'Updated Quanities'!F:I,7,0),R752)=\"\",R752,IFERROR(VLOOKUP('AUP Library'!A752,'Updated Quanities'!F:I,7,0),R752))","v":564.27},564.27,{"$f":"IFERROR(VLOOKUP('AUP Library'!A752,'Updated Quanities'!F:G,4,0),R752)","v":564.27}]
["705-04.04","Guardrail Terminal (Type 21)","EA",1813.42,1813.42,1813.42,1813.42,1813.42,1813.42,1813.42,1813.42,1813.42,1813.42,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A753,'Updated Quanities'!F:I,4,0),R753)=\"\",R753,IFERROR(VLOOKUP('AUP Library'!A753,'Updated Quanities'!F:I,4,0),R753))","v":1813.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A753,'Updated Quanities'!F:I,5,0),R753)=\"\",R753,IFERROR(VLOOKUP('AUP Library'!A753,'Updated Quanities'!F:I,5,0),R753))","v":1813.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A753,'Updated Quanities'!F:I,6,0),R753)=\"\",R753,IFERROR(VLOOKUP('AUP Library'!A753,'Updated Quanities'!F:I,6,0),R753))","v":1813.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A753,'Updated Quanities'!F:I,7,0),R753)=\"\",R753,IFERROR(VLOOKUP('AUP Library'!A753,'Updated Quanities'!F:I,7,0),R753))","v":1813.42},1813.42,{"$f":"IFERROR(VLOOKUP('AUP Library'!A753,'Updated Quanities'!F:G,4,0),R753)","v":1813.42}]
["705-04.05","Guardrail Terminal (Type-In-Line)","EA",590.37,590.37,590.37,590.37,590.37,590.37,590.37,590.37,590.37,590.37,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A754,'Updated Quanities'!F:I,4,0),R754)=\"\",R754,IFERROR(VLOOKUP('AUP Library'!A754,'Updated Quanities'!F:I,4,0),R754))","v":590.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A754,'Updated Quanities'!F:I,5,0),R754)=\"\",R754,IFERROR(VLOOKUP('AUP Library'!A754,'Updated Quanities'!F:I,5,0),R754))","v":590.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A754,'Updated Quanities'!F:I,6,0),R754)=\"\",R754,IFERROR(VLOOKUP('AUP Library'!A754,'Updated Quanities'!F:I,6,0),R754))","v":590.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A754,'Updated Quanities'!F:I,7,0),R754)=\"\",R754,IFERROR(VLOOKUP('AUP Library'!A754,'Updated Quanities'!F:I,7,0),R754))","v":590.37},590.37,{"$f":"IFERROR(VLOOKUP('AUP Library'!A754,'Updated Quanities'!F:G,4,0),R754)","v":590.37}]
["705-04.07","Tan Energy Absg Term (NCHRP, 350, TL3)","EA",2317.8200000000002,2396.41,2431.9,2508.0700000000002,2508.0700000000002,2133.41,2119.59,2087.29,2030.23,2191.75,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A755,'Updated Quanities'!F:I,4,0),R755)=\"\",R755,IFERROR(VLOOKUP('AUP Library'!A755,'Updated Quanities'!F:I,4,0),R755))","v":2058.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A755,'Updated Quanities'!F:I,5,0),R755)=\"\",R755,IFERROR(VLOOKUP('AUP Library'!A755,'Updated Quanities'!F:I,5,0),R755))","v":2058.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A755,'Updated Quanities'!F:I,6,0),R755)=\"\",R755,IFERROR(VLOOKUP('AUP Library'!A755,'Updated Quanities'!F:I,6,0),R755))","v":2058.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A755,'Updated Quanities'!F:I,7,0),R755)=\"\",R755,IFERROR(VLOOKUP('AUP Library'!A755,'Updated Quanities'!F:I,7,0),R755))","v":2058.13},2058.13,{"$f":"IFERROR(VLOOKUP('AUP Library'!A755,'Updated Quanities'!F:G,4,0),R755)","v":2058.13}]
["705-04.09","Earth Pad for Type 38 GR End Treatment","EA",4201,3275,2390,1042.8599999999999,1042.8599999999999,1217.1500000000001,1055.94,1141.95,1026.93,991.02,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A756,'Updated Quanities'!F:I,4,0),R756)=\"\",R756,IFERROR(VLOOKUP('AUP Library'!A756,'Updated Quanities'!F:I,4,0),R756))","v":1091.55},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A756,'Updated Quanities'!F:I,5,0),R756)=\"\",R756,IFERROR(VLOOKUP('AUP Library'!A756,'Updated Quanities'!F:I,5,0),R756))","v":1091.55},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A756,'Updated Quanities'!F:I,6,0),R756)=\"\",R756,IFERROR(VLOOKUP('AUP Library'!A756,'Updated Quanities'!F:I,6,0),R756))","v":1091.55},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A756,'Updated Quanities'!F:I,7,0),R756)=\"\",R756,IFERROR(VLOOKUP('AUP Library'!A756,'Updated Quanities'!F:I,7,0),R756))","v":1091.55},1091.55,{"$f":"IFERROR(VLOOKUP('AUP Library'!A756,'Updated Quanities'!F:G,4,0),R756)","v":1091.55}]
["705-04.21","Guardrail Delineation Enhancement","LF",4.08,4.08,4.08,4.08,4.08,4.08,4.08,4.08,4.08,4.08,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A757,'Updated Quanities'!F:I,4,0),R757)=\"\",R757,IFERROR(VLOOKUP('AUP Library'!A757,'Updated Quanities'!F:I,4,0),R757))","v":4.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A757,'Updated Quanities'!F:I,5,0),R757)=\"\",R757,IFERROR(VLOOKUP('AUP Library'!A757,'Updated Quanities'!F:I,5,0),R757))","v":4.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A757,'Updated Quanities'!F:I,6,0),R757)=\"\",R757,IFERROR(VLOOKUP('AUP Library'!A757,'Updated Quanities'!F:I,6,0),R757))","v":4.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A757,'Updated Quanities'!F:I,7,0),R757)=\"\",R757,IFERROR(VLOOKUP('AUP Library'!A757,'Updated Quanities'!F:I,7,0),R757))","v":4.08},4.08,{"$f":"IFERROR(VLOOKUP('AUP Library'!A757,'Updated Quanities'!F:G,4,0),R757)","v":4.08}]
["705-08.13","Permanent Impact Attenuator NCHRP350 TL-3","EA",16750.169999999998,16750.169999999998,16750.169999999998,16750.169999999998,16750.169999999998,16750.169999999998,16750.169999999998,16750.169999999998,16750.169999999998,16750.169999999998,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A758,'Updated Quanities'!F:I,4,0),R758)=\"\",R758,IFERROR(VLOOKUP('AUP Library'!A758,'Updated Quanities'!F:I,4,0),R758))","v":16750.169999999998},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A758,'Updated Quanities'!F:I,5,0),R758)=\"\",R758,IFERROR(VLOOKUP('AUP Library'!A758,'Updated Quanities'!F:I,5,0),R758))","v":16750.169999999998},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A758,'Updated Quanities'!F:I,6,0),R758)=\"\",R758,IFERROR(VLOOKUP('AUP Library'!A758,'Updated Quanities'!F:I,6,0),R758))","v":16750.169999999998},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A758,'Updated Quanities'!F:I,7,0),R758)=\"\",R758,IFERROR(VLOOKUP('AUP Library'!A758,'Updated Quanities'!F:I,7,0),R758))","v":16750.169999999998},16750.169999999998,{"$f":"IFERROR(VLOOKUP('AUP Library'!A758,'Updated Quanities'!F:G,4,0),R758)","v":16750.169999999998}]
["705-08.21","Impact Attenuator (TAU-II Parallel)","EA",18793.34,18793.34,18793.34,18793.34,18793.34,18793.34,18793.34,18793.34,18793.34,18793.34,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A759,'Updated Quanities'!F:I,4,0),R759)=\"\",R759,IFERROR(VLOOKUP('AUP Library'!A759,'Updated Quanities'!F:I,4,0),R759))","v":18793.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A759,'Updated Quanities'!F:I,5,0),R759)=\"\",R759,IFERROR(VLOOKUP('AUP Library'!A759,'Updated Quanities'!F:I,5,0),R759))","v":18793.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A759,'Updated Quanities'!F:I,6,0),R759)=\"\",R759,IFERROR(VLOOKUP('AUP Library'!A759,'Updated Quanities'!F:I,6,0),R759))","v":18793.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A759,'Updated Quanities'!F:I,7,0),R759)=\"\",R759,IFERROR(VLOOKUP('AUP Library'!A759,'Updated Quanities'!F:I,7,0),R759))","v":18793.34},18793.34,{"$f":"IFERROR(VLOOKUP('AUP Library'!A759,'Updated Quanities'!F:G,4,0),R759)","v":18793.34}]
["705-08.51","Portable Impact Attenuator NCHRP 350, TL3","EA",4871.5600000000004,4871.5600000000004,4871.5600000000004,4871.5600000000004,4871.5600000000004,4871.5600000000004,4871.5600000000004,4871.5600000000004,4871.5600000000004,4871.5600000000004,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A760,'Updated Quanities'!F:I,4,0),R760)=\"\",R760,IFERROR(VLOOKUP('AUP Library'!A760,'Updated Quanities'!F:I,4,0),R760))","v":4871.5600000000004},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A760,'Updated Quanities'!F:I,5,0),R760)=\"\",R760,IFERROR(VLOOKUP('AUP Library'!A760,'Updated Quanities'!F:I,5,0),R760))","v":4871.5600000000004},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A760,'Updated Quanities'!F:I,6,0),R760)=\"\",R760,IFERROR(VLOOKUP('AUP Library'!A760,'Updated Quanities'!F:I,6,0),R760))","v":4871.5600000000004},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A760,'Updated Quanities'!F:I,7,0),R760)=\"\",R760,IFERROR(VLOOKUP('AUP Library'!A760,'Updated Quanities'!F:I,7,0),R760))","v":4871.5600000000004},4871.5600000000004,{"$f":"IFERROR(VLOOKUP('AUP Library'!A760,'Updated Quanities'!F:G,4,0),R760)","v":4871.5600000000004}]
["705-80.18","Cable Barrier Terminal","EA",2566.15,2566.15,2566.15,2566.15,2566.15,2566.15,2566.15,2566.15,2566.15,2566.15,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A761,'Updated Quanities'!F:I,4,0),R761)=\"\",R761,IFERROR(VLOOKUP('AUP Library'!A761,'Updated Quanities'!F:I,4,0),R761))","v":2566.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A761,'Updated Quanities'!F:I,5,0),R761)=\"\",R761,IFERROR(VLOOKUP('AUP Library'!A761,'Updated Quanities'!F:I,5,0),R761))","v":2566.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A761,'Updated Quanities'!F:I,6,0),R761)=\"\",R761,IFERROR(VLOOKUP('AUP Library'!A761,'Updated Quanities'!F:I,6,0),R761))","v":2566.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A761,'Updated Quanities'!F:I,7,0),R761)=\"\",R761,IFERROR(VLOOKUP('AUP Library'!A761,'Updated Quanities'!F:I,7,0),R761))","v":2566.15},2566.15,{"$f":"IFERROR(VLOOKUP('AUP Library'!A761,'Updated Quanities'!F:G,4,0),R761)","v":2566.15}]
["705-80.21","Longitudinal Cable Barrier Cable","LF",82.84,82.84,82.84,82.84,82.84,82.84,82.84,82.84,82.84,82.84,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A762,'Updated Quanities'!F:I,4,0),R762)=\"\",R762,IFERROR(VLOOKUP('AUP Library'!A762,'Updated Quanities'!F:I,4,0),R762))","v":82.84},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A762,'Updated Quanities'!F:I,5,0),R762)=\"\",R762,IFERROR(VLOOKUP('AUP Library'!A762,'Updated Quanities'!F:I,5,0),R762))","v":82.84},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A762,'Updated Quanities'!F:I,6,0),R762)=\"\",R762,IFERROR(VLOOKUP('AUP Library'!A762,'Updated Quanities'!F:I,6,0),R762))","v":82.84},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A762,'Updated Quanities'!F:I,7,0),R762)=\"\",R762,IFERROR(VLOOKUP('AUP Library'!A762,'Updated Quanities'!F:I,7,0),R762))","v":82.84},82.84,{"$f":"IFERROR(VLOOKUP('AUP Library'!A762,'Updated Quanities'!F:G,4,0),R762)","v":82.84}]
["706-01","Guardrail Removed","LF",0.89,0.89,0.89,0.89,0.89,0.89,0.89,0.89,0.89,0.89,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A763,'Updated Quanities'!F:I,4,0),R763)=\"\",R763,IFERROR(VLOOKUP('AUP Library'!A763,'Updated Quanities'!F:I,4,0),R763))","v":0.89},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A763,'Updated Quanities'!F:I,5,0),R763)=\"\",R763,IFERROR(VLOOKUP('AUP Library'!A763,'Updated Quanities'!F:I,5,0),R763))","v":0.89},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A763,'Updated Quanities'!F:I,6,0),R763)=\"\",R763,IFERROR(VLOOKUP('AUP Library'!A763,'Updated Quanities'!F:I,6,0),R763))","v":0.89},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A763,'Updated Quanities'!F:I,7,0),R763)=\"\",R763,IFERROR(VLOOKUP('AUP Library'!A763,'Updated Quanities'!F:I,7,0),R763))","v":0.89},0.89,{"$f":"IFERROR(VLOOKUP('AUP Library'!A763,'Updated Quanities'!F:G,4,0),R763)","v":0.89}]
["706-06.03","Radius Rail","LF",21.47,21.47,21.47,21.47,21.47,21.47,21.47,21.47,21.47,21.47,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A764,'Updated Quanities'!F:I,4,0),R764)=\"\",R764,IFERROR(VLOOKUP('AUP Library'!A764,'Updated Quanities'!F:I,4,0),R764))","v":21.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A764,'Updated Quanities'!F:I,5,0),R764)=\"\",R764,IFERROR(VLOOKUP('AUP Library'!A764,'Updated Quanities'!F:I,5,0),R764))","v":21.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A764,'Updated Quanities'!F:I,6,0),R764)=\"\",R764,IFERROR(VLOOKUP('AUP Library'!A764,'Updated Quanities'!F:I,6,0),R764))","v":21.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A764,'Updated Quanities'!F:I,7,0),R764)=\"\",R764,IFERROR(VLOOKUP('AUP Library'!A764,'Updated Quanities'!F:I,7,0),R764))","v":21.47},21.47,{"$f":"IFERROR(VLOOKUP('AUP Library'!A764,'Updated Quanities'!F:G,4,0),R764)","v":21.47}]
["706.06.03","Radius Rail Long Post (6-9 ft)","LF",28.07,28.07,28.07,28.07,28.07,28.07,28.07,28.07,28.07,28.07,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A765,'Updated Quanities'!F:I,4,0),R765)=\"\",R765,IFERROR(VLOOKUP('AUP Library'!A765,'Updated Quanities'!F:I,4,0),R765))","v":28.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A765,'Updated Quanities'!F:I,5,0),R765)=\"\",R765,IFERROR(VLOOKUP('AUP Library'!A765,'Updated Quanities'!F:I,5,0),R765))","v":28.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A765,'Updated Quanities'!F:I,6,0),R765)=\"\",R765,IFERROR(VLOOKUP('AUP Library'!A765,'Updated Quanities'!F:I,6,0),R765))","v":28.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A765,'Updated Quanities'!F:I,7,0),R765)=\"\",R765,IFERROR(VLOOKUP('AUP Library'!A765,'Updated Quanities'!F:I,7,0),R765))","v":28.07},28.07,{"$f":"IFERROR(VLOOKUP('AUP Library'!A765,'Updated Quanities'!F:G,4,0),R765)","v":28.07}]
["706-06.06","Radius Rail Long Post (9-12 ft)","LF",28.36,28.36,28.36,28.36,28.36,28.36,28.36,28.36,28.36,28.36,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A766,'Updated Quanities'!F:I,4,0),R766)=\"\",R766,IFERROR(VLOOKUP('AUP Library'!A766,'Updated Quanities'!F:I,4,0),R766))","v":28.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A766,'Updated Quanities'!F:I,5,0),R766)=\"\",R766,IFERROR(VLOOKUP('AUP Library'!A766,'Updated Quanities'!F:I,5,0),R766))","v":28.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A766,'Updated Quanities'!F:I,6,0),R766)=\"\",R766,IFERROR(VLOOKUP('AUP Library'!A766,'Updated Quanities'!F:I,6,0),R766))","v":28.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A766,'Updated Quanities'!F:I,7,0),R766)=\"\",R766,IFERROR(VLOOKUP('AUP Library'!A766,'Updated Quanities'!F:I,7,0),R766))","v":28.36},28.36,{"$f":"IFERROR(VLOOKUP('AUP Library'!A766,'Updated Quanities'!F:G,4,0),R766)","v":28.36}]
["706-10.24","FLARED END ELEMENT","EA",44.3,44.3,44.3,44.3,44.3,44.3,44.3,44.3,44.3,44.3,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A767,'Updated Quanities'!F:I,4,0),R767)=\"\",R767,IFERROR(VLOOKUP('AUP Library'!A767,'Updated Quanities'!F:I,4,0),R767))","v":44.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A767,'Updated Quanities'!F:I,5,0),R767)=\"\",R767,IFERROR(VLOOKUP('AUP Library'!A767,'Updated Quanities'!F:I,5,0),R767))","v":44.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A767,'Updated Quanities'!F:I,6,0),R767)=\"\",R767,IFERROR(VLOOKUP('AUP Library'!A767,'Updated Quanities'!F:I,6,0),R767))","v":44.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A767,'Updated Quanities'!F:I,7,0),R767)=\"\",R767,IFERROR(VLOOKUP('AUP Library'!A767,'Updated Quanities'!F:I,7,0),R767))","v":44.3},44.3,{"$f":"IFERROR(VLOOKUP('AUP Library'!A767,'Updated Quanities'!F:G,4,0),R767)","v":44.3}]
["706-10.26","ROUNDED END ELEMENT","EA",42.68,42.68,42.68,42.68,42.68,42.68,42.68,42.68,42.68,42.68,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A768,'Updated Quanities'!F:I,4,0),R768)=\"\",R768,IFERROR(VLOOKUP('AUP Library'!A768,'Updated Quanities'!F:I,4,0),R768))","v":42.68},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A768,'Updated Quanities'!F:I,5,0),R768)=\"\",R768,IFERROR(VLOOKUP('AUP Library'!A768,'Updated Quanities'!F:I,5,0),R768))","v":42.68},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A768,'Updated Quanities'!F:I,6,0),R768)=\"\",R768,IFERROR(VLOOKUP('AUP Library'!A768,'Updated Quanities'!F:I,6,0),R768))","v":42.68},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A768,'Updated Quanities'!F:I,7,0),R768)=\"\",R768,IFERROR(VLOOKUP('AUP Library'!A768,'Updated Quanities'!F:I,7,0),R768))","v":42.68},42.68,{"$f":"IFERROR(VLOOKUP('AUP Library'!A768,'Updated Quanities'!F:G,4,0),R768)","v":42.68}]
["706-10.54","RE-ALIGN GUARDRAIL","LF",0.8,0.8,0.8,0.8,0.8,0.8,0.8,0.8,0.8,0.8,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A769,'Updated Quanities'!F:I,4,0),R769)=\"\",R769,IFERROR(VLOOKUP('AUP Library'!A769,'Updated Quanities'!F:I,4,0),R769))","v":0.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A769,'Updated Quanities'!F:I,5,0),R769)=\"\",R769,IFERROR(VLOOKUP('AUP Library'!A769,'Updated Quanities'!F:I,5,0),R769))","v":0.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A769,'Updated Quanities'!F:I,6,0),R769)=\"\",R769,IFERROR(VLOOKUP('AUP Library'!A769,'Updated Quanities'!F:I,6,0),R769))","v":0.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A769,'Updated Quanities'!F:I,7,0),R769)=\"\",R769,IFERROR(VLOOKUP('AUP Library'!A769,'Updated Quanities'!F:I,7,0),R769))","v":0.8},0.8,{"$f":"IFERROR(VLOOKUP('AUP Library'!A769,'Updated Quanities'!F:G,4,0),R769)","v":0.8}]
["706-10.56","BUFFER ENDS 88\"","EA",29.89,29.89,29.89,29.89,29.89,29.89,29.89,29.89,29.89,29.89,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A770,'Updated Quanities'!F:I,4,0),R770)=\"\",R770,IFERROR(VLOOKUP('AUP Library'!A770,'Updated Quanities'!F:I,4,0),R770))","v":29.89},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A770,'Updated Quanities'!F:I,5,0),R770)=\"\",R770,IFERROR(VLOOKUP('AUP Library'!A770,'Updated Quanities'!F:I,5,0),R770))","v":29.89},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A770,'Updated Quanities'!F:I,6,0),R770)=\"\",R770,IFERROR(VLOOKUP('AUP Library'!A770,'Updated Quanities'!F:I,6,0),R770))","v":29.89},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A770,'Updated Quanities'!F:I,7,0),R770)=\"\",R770,IFERROR(VLOOKUP('AUP Library'!A770,'Updated Quanities'!F:I,7,0),R770))","v":29.89},29.89,{"$f":"IFERROR(VLOOKUP('AUP Library'!A770,'Updated Quanities'!F:G,4,0),R770)","v":29.89}]
["706-10.71","HAZARD MARKERS","EA",9.31,9.31,9.31,9.31,9.31,9.31,9.31,9.31,9.31,9.31,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A771,'Updated Quanities'!F:I,4,0),R771)=\"\",R771,IFERROR(VLOOKUP('AUP Library'!A771,'Updated Quanities'!F:I,4,0),R771))","v":9.31},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A771,'Updated Quanities'!F:I,5,0),R771)=\"\",R771,IFERROR(VLOOKUP('AUP Library'!A771,'Updated Quanities'!F:I,5,0),R771))","v":9.31},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A771,'Updated Quanities'!F:I,6,0),R771)=\"\",R771,IFERROR(VLOOKUP('AUP Library'!A771,'Updated Quanities'!F:I,6,0),R771))","v":9.31},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A771,'Updated Quanities'!F:I,7,0),R771)=\"\",R771,IFERROR(VLOOKUP('AUP Library'!A771,'Updated Quanities'!F:I,7,0),R771))","v":9.31},9.31,{"$f":"IFERROR(VLOOKUP('AUP Library'!A771,'Updated Quanities'!F:G,4,0),R771)","v":9.31}]
["706-10.72","PULL AND RENSTALL GURDRAIL POST FOR VERI","EA",49.2,49.2,49.2,49.2,49.2,49.2,49.2,49.2,49.2,49.2,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A772,'Updated Quanities'!F:I,4,0),R772)=\"\",R772,IFERROR(VLOOKUP('AUP Library'!A772,'Updated Quanities'!F:I,4,0),R772))","v":49.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A772,'Updated Quanities'!F:I,5,0),R772)=\"\",R772,IFERROR(VLOOKUP('AUP Library'!A772,'Updated Quanities'!F:I,5,0),R772))","v":49.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A772,'Updated Quanities'!F:I,6,0),R772)=\"\",R772,IFERROR(VLOOKUP('AUP Library'!A772,'Updated Quanities'!F:I,6,0),R772))","v":49.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A772,'Updated Quanities'!F:I,7,0),R772)=\"\",R772,IFERROR(VLOOKUP('AUP Library'!A772,'Updated Quanities'!F:I,7,0),R772))","v":49.2},49.2,{"$f":"IFERROR(VLOOKUP('AUP Library'!A772,'Updated Quanities'!F:G,4,0),R772)","v":49.2}]
["706-10.73","REMOVAL OF GUARDRAIL & POST FOR REUSE","CY",3.5,3.5,3.5,3.5,3.5,3.5,3.5,3.5,3.5,3.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A773,'Updated Quanities'!F:I,4,0),R773)=\"\",R773,IFERROR(VLOOKUP('AUP Library'!A773,'Updated Quanities'!F:I,4,0),R773))","v":3.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A773,'Updated Quanities'!F:I,5,0),R773)=\"\",R773,IFERROR(VLOOKUP('AUP Library'!A773,'Updated Quanities'!F:I,5,0),R773))","v":3.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A773,'Updated Quanities'!F:I,6,0),R773)=\"\",R773,IFERROR(VLOOKUP('AUP Library'!A773,'Updated Quanities'!F:I,6,0),R773))","v":3.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A773,'Updated Quanities'!F:I,7,0),R773)=\"\",R773,IFERROR(VLOOKUP('AUP Library'!A773,'Updated Quanities'!F:I,7,0),R773))","v":3.5},3.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A773,'Updated Quanities'!F:G,4,0),R773)","v":3.5}]
["706-10.74","CONCRETE BARRIER WALL REPAIR","EA",3676.47,3676.47,3676.47,3676.47,3676.47,3676.47,3676.47,3676.47,3676.47,3676.47,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A774,'Updated Quanities'!F:I,4,0),R774)=\"\",R774,IFERROR(VLOOKUP('AUP Library'!A774,'Updated Quanities'!F:I,4,0),R774))","v":3676.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A774,'Updated Quanities'!F:I,5,0),R774)=\"\",R774,IFERROR(VLOOKUP('AUP Library'!A774,'Updated Quanities'!F:I,5,0),R774))","v":3676.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A774,'Updated Quanities'!F:I,6,0),R774)=\"\",R774,IFERROR(VLOOKUP('AUP Library'!A774,'Updated Quanities'!F:I,6,0),R774))","v":3676.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A774,'Updated Quanities'!F:I,7,0),R774)=\"\",R774,IFERROR(VLOOKUP('AUP Library'!A774,'Updated Quanities'!F:I,7,0),R774))","v":3676.47},3676.47,{"$f":"IFERROR(VLOOKUP('AUP Library'!A774,'Updated Quanities'!F:G,4,0),R774)","v":3676.47}]
["706-10.80","MICHIGAN AND MODIFIED MICHIGAN END SHOE","EA",35.42,35.42,35.42,35.42,35.42,35.42,35.42,35.42,35.42,35.42,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A775,'Updated Quanities'!F:I,4,0),R775)=\"\",R775,IFERROR(VLOOKUP('AUP Library'!A775,'Updated Quanities'!F:I,4,0),R775))","v":35.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A775,'Updated Quanities'!F:I,5,0),R775)=\"\",R775,IFERROR(VLOOKUP('AUP Library'!A775,'Updated Quanities'!F:I,5,0),R775))","v":35.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A775,'Updated Quanities'!F:I,6,0),R775)=\"\",R775,IFERROR(VLOOKUP('AUP Library'!A775,'Updated Quanities'!F:I,6,0),R775))","v":35.42},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A775,'Updated Quanities'!F:I,7,0),R775)=\"\",R775,IFERROR(VLOOKUP('AUP Library'!A775,'Updated Quanities'!F:I,7,0),R775))","v":35.42},35.42,{"$f":"IFERROR(VLOOKUP('AUP Library'!A775,'Updated Quanities'!F:G,4,0),R775)","v":35.42}]
["706-10.81","GUARDRAIL REFLECTORS","EA",5.6,5.6,5.6,5.6,5.6,5.6,5.6,5.6,5.6,5.6,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A776,'Updated Quanities'!F:I,4,0),R776)=\"\",R776,IFERROR(VLOOKUP('AUP Library'!A776,'Updated Quanities'!F:I,4,0),R776))","v":5.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A776,'Updated Quanities'!F:I,5,0),R776)=\"\",R776,IFERROR(VLOOKUP('AUP Library'!A776,'Updated Quanities'!F:I,5,0),R776))","v":5.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A776,'Updated Quanities'!F:I,6,0),R776)=\"\",R776,IFERROR(VLOOKUP('AUP Library'!A776,'Updated Quanities'!F:I,6,0),R776))","v":5.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A776,'Updated Quanities'!F:I,7,0),R776)=\"\",R776,IFERROR(VLOOKUP('AUP Library'!A776,'Updated Quanities'!F:I,7,0),R776))","v":5.6},5.6,{"$f":"IFERROR(VLOOKUP('AUP Library'!A776,'Updated Quanities'!F:G,4,0),R776)","v":5.6}]
["706-10.82","CONC BR END OR PIER PROTECTION REPAIR","CY",3042.86,3042.86,3042.86,3042.86,3042.86,3042.86,3042.86,3042.86,3042.86,3042.86,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A777,'Updated Quanities'!F:I,4,0),R777)=\"\",R777,IFERROR(VLOOKUP('AUP Library'!A777,'Updated Quanities'!F:I,4,0),R777))","v":3042.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A777,'Updated Quanities'!F:I,5,0),R777)=\"\",R777,IFERROR(VLOOKUP('AUP Library'!A777,'Updated Quanities'!F:I,5,0),R777))","v":3042.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A777,'Updated Quanities'!F:I,6,0),R777)=\"\",R777,IFERROR(VLOOKUP('AUP Library'!A777,'Updated Quanities'!F:I,6,0),R777))","v":3042.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A777,'Updated Quanities'!F:I,7,0),R777)=\"\",R777,IFERROR(VLOOKUP('AUP Library'!A777,'Updated Quanities'!F:I,7,0),R777))","v":3042.86},3042.86,{"$f":"IFERROR(VLOOKUP('AUP Library'!A777,'Updated Quanities'!F:G,4,0),R777)","v":3042.86}]
["706-10.83","DRILL BR. PAR. WALL, MICHIGAN END SHOE","EA",235.51,235.51,235.51,235.51,235.51,235.51,235.51,235.51,235.51,235.51,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A778,'Updated Quanities'!F:I,4,0),R778)=\"\",R778,IFERROR(VLOOKUP('AUP Library'!A778,'Updated Quanities'!F:I,4,0),R778))","v":235.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A778,'Updated Quanities'!F:I,5,0),R778)=\"\",R778,IFERROR(VLOOKUP('AUP Library'!A778,'Updated Quanities'!F:I,5,0),R778))","v":235.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A778,'Updated Quanities'!F:I,6,0),R778)=\"\",R778,IFERROR(VLOOKUP('AUP Library'!A778,'Updated Quanities'!F:I,6,0),R778))","v":235.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A778,'Updated Quanities'!F:I,7,0),R778)=\"\",R778,IFERROR(VLOOKUP('AUP Library'!A778,'Updated Quanities'!F:I,7,0),R778))","v":235.51},235.51,{"$f":"IFERROR(VLOOKUP('AUP Library'!A778,'Updated Quanities'!F:G,4,0),R778)","v":235.51}]
[]
[]
["Seeding and Sodding"]
["801-01","Seeding (With Mulch)","UNIT",21.08,21.33,26.92,29.46,29.46,24.06,22.68,25.01,24.47,25.9,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A782,'Updated Quanities'!F:I,4,0),R782)=\"\",R782,IFERROR(VLOOKUP('AUP Library'!A782,'Updated Quanities'!F:I,4,0),R782))","v":26.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A782,'Updated Quanities'!F:I,5,0),R782)=\"\",R782,IFERROR(VLOOKUP('AUP Library'!A782,'Updated Quanities'!F:I,5,0),R782))","v":26.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A782,'Updated Quanities'!F:I,6,0),R782)=\"\",R782,IFERROR(VLOOKUP('AUP Library'!A782,'Updated Quanities'!F:I,6,0),R782))","v":26.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A782,'Updated Quanities'!F:I,7,0),R782)=\"\",R782,IFERROR(VLOOKUP('AUP Library'!A782,'Updated Quanities'!F:I,7,0),R782))","v":26.32},26.32,{"$f":"IFERROR(VLOOKUP('AUP Library'!A782,'Updated Quanities'!F:G,4,0),R782)","v":26.32}]
["801.01.02","Crown Vetch Mixture (with mulch)","UNIT",21.37,21.37,21.37,21.37,21.37,21.37,21.37,21.37,21.37,21.37,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A783,'Updated Quanities'!F:I,4,0),R783)=\"\",R783,IFERROR(VLOOKUP('AUP Library'!A783,'Updated Quanities'!F:I,4,0),R783))","v":21.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A783,'Updated Quanities'!F:I,5,0),R783)=\"\",R783,IFERROR(VLOOKUP('AUP Library'!A783,'Updated Quanities'!F:I,5,0),R783))","v":21.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A783,'Updated Quanities'!F:I,6,0),R783)=\"\",R783,IFERROR(VLOOKUP('AUP Library'!A783,'Updated Quanities'!F:I,6,0),R783))","v":21.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A783,'Updated Quanities'!F:I,7,0),R783)=\"\",R783,IFERROR(VLOOKUP('AUP Library'!A783,'Updated Quanities'!F:I,7,0),R783))","v":21.37},21.37,{"$f":"IFERROR(VLOOKUP('AUP Library'!A783,'Updated Quanities'!F:G,4,0),R783)","v":21.37}]
["801-01.07","Temporary Seeding (With Mulch)","UNIT",17.260000000000002,20.63,9,15.15,25.15,17.77,15.11,15.07,16.07,18.399999999999999,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A784,'Updated Quanities'!F:I,4,0),R784)=\"\",R784,IFERROR(VLOOKUP('AUP Library'!A784,'Updated Quanities'!F:I,4,0),R784))","v":20.91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A784,'Updated Quanities'!F:I,5,0),R784)=\"\",R784,IFERROR(VLOOKUP('AUP Library'!A784,'Updated Quanities'!F:I,5,0),R784))","v":20.91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A784,'Updated Quanities'!F:I,6,0),R784)=\"\",R784,IFERROR(VLOOKUP('AUP Library'!A784,'Updated Quanities'!F:I,6,0),R784))","v":20.91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A784,'Updated Quanities'!F:I,7,0),R784)=\"\",R784,IFERROR(VLOOKUP('AUP Library'!A784,'Updated Quanities'!F:I,7,0),R784))","v":20.91},20.91,{"$f":"IFERROR(VLOOKUP('AUP Library'!A784,'Updated Quanities'!F:G,4,0),R784)","v":20.91}]
["801-02","Seeding (Without Mulch)","UNIT",17.190000000000001,18.760000000000002,21.74,21.91,21.91,14.36,11.83,12.35,14.91,19.47,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A785,'Updated Quanities'!F:I,4,0),R785)=\"\",R785,IFERROR(VLOOKUP('AUP Library'!A785,'Updated Quanities'!F:I,4,0),R785))","v":11.79},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A785,'Updated Quanities'!F:I,5,0),R785)=\"\",R785,IFERROR(VLOOKUP('AUP Library'!A785,'Updated Quanities'!F:I,5,0),R785))","v":11.79},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A785,'Updated Quanities'!F:I,6,0),R785)=\"\",R785,IFERROR(VLOOKUP('AUP Library'!A785,'Updated Quanities'!F:I,6,0),R785))","v":11.79},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A785,'Updated Quanities'!F:I,7,0),R785)=\"\",R785,IFERROR(VLOOKUP('AUP Library'!A785,'Updated Quanities'!F:I,7,0),R785))","v":11.79},11.79,{"$f":"IFERROR(VLOOKUP('AUP Library'!A785,'Updated Quanities'!F:G,4,0),R785)","v":11.79}]
["801-02.15","Fertilizer","TON",290.85000000000002,290.85000000000002,290.85000000000002,290.85000000000002,290.85000000000002,290.85000000000002,290.85000000000002,290.85000000000002,290.85000000000002,290.85000000000002,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A786,'Updated Quanities'!F:I,4,0),R786)=\"\",R786,IFERROR(VLOOKUP('AUP Library'!A786,'Updated Quanities'!F:I,4,0),R786))","v":290.85000000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A786,'Updated Quanities'!F:I,5,0),R786)=\"\",R786,IFERROR(VLOOKUP('AUP Library'!A786,'Updated Quanities'!F:I,5,0),R786))","v":290.85000000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A786,'Updated Quanities'!F:I,6,0),R786)=\"\",R786,IFERROR(VLOOKUP('AUP Library'!A786,'Updated Quanities'!F:I,6,0),R786))","v":290.85000000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A786,'Updated Quanities'!F:I,7,0),R786)=\"\",R786,IFERROR(VLOOKUP('AUP Library'!A786,'Updated Quanities'!F:I,7,0),R786))","v":290.85000000000002},290.85000000000002,{"$f":"IFERROR(VLOOKUP('AUP Library'!A786,'Updated Quanities'!F:G,4,0),R786)","v":290.85000000000002}]
["801-03","Water (Seeding & Sodding)","MG",9.23,9.23,9.23,9.23,9.23,9.23,9.23,9.23,9.23,9.23,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A787,'Updated Quanities'!F:I,4,0),R787)=\"\",R787,IFERROR(VLOOKUP('AUP Library'!A787,'Updated Quanities'!F:I,4,0),R787))","v":9.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A787,'Updated Quanities'!F:I,5,0),R787)=\"\",R787,IFERROR(VLOOKUP('AUP Library'!A787,'Updated Quanities'!F:I,5,0),R787))","v":9.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A787,'Updated Quanities'!F:I,6,0),R787)=\"\",R787,IFERROR(VLOOKUP('AUP Library'!A787,'Updated Quanities'!F:I,6,0),R787))","v":9.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A787,'Updated Quanities'!F:I,7,0),R787)=\"\",R787,IFERROR(VLOOKUP('AUP Library'!A787,'Updated Quanities'!F:I,7,0),R787))","v":9.23},9.23,{"$f":"IFERROR(VLOOKUP('AUP Library'!A787,'Updated Quanities'!F:G,4,0),R787)","v":9.23}]
["801-07","Seed (Supplemental Application)","TON",0.34,0.34,0.34,0.34,0.34,0.34,0.34,0.34,0.34,0.34,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A788,'Updated Quanities'!F:I,4,0),R788)=\"\",R788,IFERROR(VLOOKUP('AUP Library'!A788,'Updated Quanities'!F:I,4,0),R788))","v":0.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A788,'Updated Quanities'!F:I,5,0),R788)=\"\",R788,IFERROR(VLOOKUP('AUP Library'!A788,'Updated Quanities'!F:I,5,0),R788))","v":0.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A788,'Updated Quanities'!F:I,6,0),R788)=\"\",R788,IFERROR(VLOOKUP('AUP Library'!A788,'Updated Quanities'!F:I,6,0),R788))","v":0.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A788,'Updated Quanities'!F:I,7,0),R788)=\"\",R788,IFERROR(VLOOKUP('AUP Library'!A788,'Updated Quanities'!F:I,7,0),R788))","v":0.34},0.34,{"$f":"IFERROR(VLOOKUP('AUP Library'!A788,'Updated Quanities'!F:G,4,0),R788)","v":0.34}]
["801-08","Fertilizer (Supplemental Application)","TON",670.2,670.2,670.2,670.2,670.2,670.2,670.2,670.2,670.2,670.2,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A789,'Updated Quanities'!F:I,4,0),R789)=\"\",R789,IFERROR(VLOOKUP('AUP Library'!A789,'Updated Quanities'!F:I,4,0),R789))","v":670.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A789,'Updated Quanities'!F:I,5,0),R789)=\"\",R789,IFERROR(VLOOKUP('AUP Library'!A789,'Updated Quanities'!F:I,5,0),R789))","v":670.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A789,'Updated Quanities'!F:I,6,0),R789)=\"\",R789,IFERROR(VLOOKUP('AUP Library'!A789,'Updated Quanities'!F:I,6,0),R789))","v":670.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A789,'Updated Quanities'!F:I,7,0),R789)=\"\",R789,IFERROR(VLOOKUP('AUP Library'!A789,'Updated Quanities'!F:I,7,0),R789))","v":670.2},670.2,{"$f":"IFERROR(VLOOKUP('AUP Library'!A789,'Updated Quanities'!F:G,4,0),R789)","v":670.2}]
["802-01.10","Tree","EA",150,150,150,150,150,150,150,150,150,150,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A790,'Updated Quanities'!F:I,4,0),R790)=\"\",R790,IFERROR(VLOOKUP('AUP Library'!A790,'Updated Quanities'!F:I,4,0),R790))","v":150},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A790,'Updated Quanities'!F:I,5,0),R790)=\"\",R790,IFERROR(VLOOKUP('AUP Library'!A790,'Updated Quanities'!F:I,5,0),R790))","v":150},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A790,'Updated Quanities'!F:I,6,0),R790)=\"\",R790,IFERROR(VLOOKUP('AUP Library'!A790,'Updated Quanities'!F:I,6,0),R790))","v":150},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A790,'Updated Quanities'!F:I,7,0),R790)=\"\",R790,IFERROR(VLOOKUP('AUP Library'!A790,'Updated Quanities'!F:I,7,0),R790))","v":150},150,{"$f":"IFERROR(VLOOKUP('AUP Library'!A790,'Updated Quanities'!F:G,4,0),R790)","v":150}]
["802-01.11","Tree","EA",150,150,150,150,150,150,150,150,150,150,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A791,'Updated Quanities'!F:I,4,0),R791)=\"\",R791,IFERROR(VLOOKUP('AUP Library'!A791,'Updated Quanities'!F:I,4,0),R791))","v":150},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A791,'Updated Quanities'!F:I,5,0),R791)=\"\",R791,IFERROR(VLOOKUP('AUP Library'!A791,'Updated Quanities'!F:I,5,0),R791))","v":150},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A791,'Updated Quanities'!F:I,6,0),R791)=\"\",R791,IFERROR(VLOOKUP('AUP Library'!A791,'Updated Quanities'!F:I,6,0),R791))","v":150},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A791,'Updated Quanities'!F:I,7,0),R791)=\"\",R791,IFERROR(VLOOKUP('AUP Library'!A791,'Updated Quanities'!F:I,7,0),R791))","v":150},150,{"$f":"IFERROR(VLOOKUP('AUP Library'!A791,'Updated Quanities'!F:G,4,0),R791)","v":150}]
["802-01.12","Tree","EA",150,150,150,150,150,150,150,150,150,150,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A792,'Updated Quanities'!F:I,4,0),R792)=\"\",R792,IFERROR(VLOOKUP('AUP Library'!A792,'Updated Quanities'!F:I,4,0),R792))","v":150},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A792,'Updated Quanities'!F:I,5,0),R792)=\"\",R792,IFERROR(VLOOKUP('AUP Library'!A792,'Updated Quanities'!F:I,5,0),R792))","v":150},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A792,'Updated Quanities'!F:I,6,0),R792)=\"\",R792,IFERROR(VLOOKUP('AUP Library'!A792,'Updated Quanities'!F:I,6,0),R792))","v":150},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A792,'Updated Quanities'!F:I,7,0),R792)=\"\",R792,IFERROR(VLOOKUP('AUP Library'!A792,'Updated Quanities'!F:I,7,0),R792))","v":150},150,{"$f":"IFERROR(VLOOKUP('AUP Library'!A792,'Updated Quanities'!F:G,4,0),R792)","v":150}]
["802-01.13","Tree","EA",150,150,150,150,150,150,150,150,150,150,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A793,'Updated Quanities'!F:I,4,0),R793)=\"\",R793,IFERROR(VLOOKUP('AUP Library'!A793,'Updated Quanities'!F:I,4,0),R793))","v":150},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A793,'Updated Quanities'!F:I,5,0),R793)=\"\",R793,IFERROR(VLOOKUP('AUP Library'!A793,'Updated Quanities'!F:I,5,0),R793))","v":150},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A793,'Updated Quanities'!F:I,6,0),R793)=\"\",R793,IFERROR(VLOOKUP('AUP Library'!A793,'Updated Quanities'!F:I,6,0),R793))","v":150},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A793,'Updated Quanities'!F:I,7,0),R793)=\"\",R793,IFERROR(VLOOKUP('AUP Library'!A793,'Updated Quanities'!F:I,7,0),R793))","v":150},150,{"$f":"IFERROR(VLOOKUP('AUP Library'!A793,'Updated Quanities'!F:G,4,0),R793)","v":150}]
["802-01.14","Tree","EA",7.5,7.5,7.5,7.5,7.5,7.5,7.5,7.5,7.5,7.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A794,'Updated Quanities'!F:I,4,0),R794)=\"\",R794,IFERROR(VLOOKUP('AUP Library'!A794,'Updated Quanities'!F:I,4,0),R794))","v":7.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A794,'Updated Quanities'!F:I,5,0),R794)=\"\",R794,IFERROR(VLOOKUP('AUP Library'!A794,'Updated Quanities'!F:I,5,0),R794))","v":7.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A794,'Updated Quanities'!F:I,6,0),R794)=\"\",R794,IFERROR(VLOOKUP('AUP Library'!A794,'Updated Quanities'!F:I,6,0),R794))","v":7.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A794,'Updated Quanities'!F:I,7,0),R794)=\"\",R794,IFERROR(VLOOKUP('AUP Library'!A794,'Updated Quanities'!F:I,7,0),R794))","v":7.5},7.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A794,'Updated Quanities'!F:G,4,0),R794)","v":7.5}]
["802-12.07","Tree","EA",7.5,7.5,7.5,7.5,7.5,7.5,7.5,7.5,7.5,7.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A795,'Updated Quanities'!F:I,4,0),R795)=\"\",R795,IFERROR(VLOOKUP('AUP Library'!A795,'Updated Quanities'!F:I,4,0),R795))","v":7.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A795,'Updated Quanities'!F:I,5,0),R795)=\"\",R795,IFERROR(VLOOKUP('AUP Library'!A795,'Updated Quanities'!F:I,5,0),R795))","v":7.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A795,'Updated Quanities'!F:I,6,0),R795)=\"\",R795,IFERROR(VLOOKUP('AUP Library'!A795,'Updated Quanities'!F:I,6,0),R795))","v":7.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A795,'Updated Quanities'!F:I,7,0),R795)=\"\",R795,IFERROR(VLOOKUP('AUP Library'!A795,'Updated Quanities'!F:I,7,0),R795))","v":7.5},7.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A795,'Updated Quanities'!F:G,4,0),R795)","v":7.5}]
["802-12.18","Tree","EA",5.5,5.5,5.5,5.5,5.5,5.5,5.5,5.5,5.5,5.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A796,'Updated Quanities'!F:I,4,0),R796)=\"\",R796,IFERROR(VLOOKUP('AUP Library'!A796,'Updated Quanities'!F:I,4,0),R796))","v":5.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A796,'Updated Quanities'!F:I,5,0),R796)=\"\",R796,IFERROR(VLOOKUP('AUP Library'!A796,'Updated Quanities'!F:I,5,0),R796))","v":5.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A796,'Updated Quanities'!F:I,6,0),R796)=\"\",R796,IFERROR(VLOOKUP('AUP Library'!A796,'Updated Quanities'!F:I,6,0),R796))","v":5.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A796,'Updated Quanities'!F:I,7,0),R796)=\"\",R796,IFERROR(VLOOKUP('AUP Library'!A796,'Updated Quanities'!F:I,7,0),R796))","v":5.5},5.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A796,'Updated Quanities'!F:G,4,0),R796)","v":5.5}]
["802-12.26","Tree","EA",3,3,3,3,3,3,3,3,3,3,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A797,'Updated Quanities'!F:I,4,0),R797)=\"\",R797,IFERROR(VLOOKUP('AUP Library'!A797,'Updated Quanities'!F:I,4,0),R797))","v":3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A797,'Updated Quanities'!F:I,5,0),R797)=\"\",R797,IFERROR(VLOOKUP('AUP Library'!A797,'Updated Quanities'!F:I,5,0),R797))","v":3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A797,'Updated Quanities'!F:I,6,0),R797)=\"\",R797,IFERROR(VLOOKUP('AUP Library'!A797,'Updated Quanities'!F:I,6,0),R797))","v":3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A797,'Updated Quanities'!F:I,7,0),R797)=\"\",R797,IFERROR(VLOOKUP('AUP Library'!A797,'Updated Quanities'!F:I,7,0),R797))","v":3},3,{"$f":"IFERROR(VLOOKUP('AUP Library'!A797,'Updated Quanities'!F:G,4,0),R797)","v":3}]
["802-12.38","Tree","EA",10,10,10,10,10,10,10,10,10,10,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A798,'Updated Quanities'!F:I,4,0),R798)=\"\",R798,IFERROR(VLOOKUP('AUP Library'!A798,'Updated Quanities'!F:I,4,0),R798))","v":10},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A798,'Updated Quanities'!F:I,5,0),R798)=\"\",R798,IFERROR(VLOOKUP('AUP Library'!A798,'Updated Quanities'!F:I,5,0),R798))","v":10},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A798,'Updated Quanities'!F:I,6,0),R798)=\"\",R798,IFERROR(VLOOKUP('AUP Library'!A798,'Updated Quanities'!F:I,6,0),R798))","v":10},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A798,'Updated Quanities'!F:I,7,0),R798)=\"\",R798,IFERROR(VLOOKUP('AUP Library'!A798,'Updated Quanities'!F:I,7,0),R798))","v":10},10,{"$f":"IFERROR(VLOOKUP('AUP Library'!A798,'Updated Quanities'!F:G,4,0),R798)","v":10}]
["802-12.42","Tree","EA",5.58,5.58,5.58,5.58,5.58,5.58,5.58,5.58,5.58,5.58,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A799,'Updated Quanities'!F:I,4,0),R799)=\"\",R799,IFERROR(VLOOKUP('AUP Library'!A799,'Updated Quanities'!F:I,4,0),R799))","v":5.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A799,'Updated Quanities'!F:I,5,0),R799)=\"\",R799,IFERROR(VLOOKUP('AUP Library'!A799,'Updated Quanities'!F:I,5,0),R799))","v":5.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A799,'Updated Quanities'!F:I,6,0),R799)=\"\",R799,IFERROR(VLOOKUP('AUP Library'!A799,'Updated Quanities'!F:I,6,0),R799))","v":5.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A799,'Updated Quanities'!F:I,7,0),R799)=\"\",R799,IFERROR(VLOOKUP('AUP Library'!A799,'Updated Quanities'!F:I,7,0),R799))","v":5.58},5.58,{"$f":"IFERROR(VLOOKUP('AUP Library'!A799,'Updated Quanities'!F:G,4,0),R799)","v":5.58}]
["803-01","Sodding (New Sod)","SY",2.4500000000000002,2.4500000000000002,2.4500000000000002,2.4500000000000002,2.4500000000000002,2.4500000000000002,2.4500000000000002,2.4500000000000002,2.4500000000000002,2.4500000000000002,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A800,'Updated Quanities'!F:I,4,0),R800)=\"\",R800,IFERROR(VLOOKUP('AUP Library'!A800,'Updated Quanities'!F:I,4,0),R800))","v":2.4500000000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A800,'Updated Quanities'!F:I,5,0),R800)=\"\",R800,IFERROR(VLOOKUP('AUP Library'!A800,'Updated Quanities'!F:I,5,0),R800))","v":2.4500000000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A800,'Updated Quanities'!F:I,6,0),R800)=\"\",R800,IFERROR(VLOOKUP('AUP Library'!A800,'Updated Quanities'!F:I,6,0),R800))","v":2.4500000000000002},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A800,'Updated Quanities'!F:I,7,0),R800)=\"\",R800,IFERROR(VLOOKUP('AUP Library'!A800,'Updated Quanities'!F:I,7,0),R800))","v":2.4500000000000002},2.4500000000000002,{"$f":"IFERROR(VLOOKUP('AUP Library'!A800,'Updated Quanities'!F:G,4,0),R800)","v":2.4500000000000002}]
["805-01.03","Turf Reinforcement Mat (Class III)","SY",3.5,3.5,3.5,3.5,3.5,3.5,3.5,3.5,3.5,3.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A801,'Updated Quanities'!F:I,4,0),R801)=\"\",R801,IFERROR(VLOOKUP('AUP Library'!A801,'Updated Quanities'!F:I,4,0),R801))","v":3.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A801,'Updated Quanities'!F:I,5,0),R801)=\"\",R801,IFERROR(VLOOKUP('AUP Library'!A801,'Updated Quanities'!F:I,5,0),R801))","v":3.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A801,'Updated Quanities'!F:I,6,0),R801)=\"\",R801,IFERROR(VLOOKUP('AUP Library'!A801,'Updated Quanities'!F:I,6,0),R801))","v":3.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A801,'Updated Quanities'!F:I,7,0),R801)=\"\",R801,IFERROR(VLOOKUP('AUP Library'!A801,'Updated Quanities'!F:I,7,0),R801))","v":3.5},3.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A801,'Updated Quanities'!F:G,4,0),R801)","v":3.5}]
["805-12.01","Erosion Control Blanket (Type I)","SY",0.94,0.94,0.94,0.94,0.94,0.94,0.94,0.94,0.94,0.94,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A802,'Updated Quanities'!F:I,4,0),R802)=\"\",R802,IFERROR(VLOOKUP('AUP Library'!A802,'Updated Quanities'!F:I,4,0),R802))","v":0.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A802,'Updated Quanities'!F:I,5,0),R802)=\"\",R802,IFERROR(VLOOKUP('AUP Library'!A802,'Updated Quanities'!F:I,5,0),R802))","v":0.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A802,'Updated Quanities'!F:I,6,0),R802)=\"\",R802,IFERROR(VLOOKUP('AUP Library'!A802,'Updated Quanities'!F:I,6,0),R802))","v":0.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A802,'Updated Quanities'!F:I,7,0),R802)=\"\",R802,IFERROR(VLOOKUP('AUP Library'!A802,'Updated Quanities'!F:I,7,0),R802))","v":0.94},0.94,{"$f":"IFERROR(VLOOKUP('AUP Library'!A802,'Updated Quanities'!F:G,4,0),R802)","v":0.94}]
["805-12.02","Erosion Control Blanket (Type II)","SY",1.08,1.08,1.08,1.08,1.08,1.08,1.08,1.08,1.08,1.08,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A803,'Updated Quanities'!F:I,4,0),R803)=\"\",R803,IFERROR(VLOOKUP('AUP Library'!A803,'Updated Quanities'!F:I,4,0),R803))","v":1.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A803,'Updated Quanities'!F:I,5,0),R803)=\"\",R803,IFERROR(VLOOKUP('AUP Library'!A803,'Updated Quanities'!F:I,5,0),R803))","v":1.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A803,'Updated Quanities'!F:I,6,0),R803)=\"\",R803,IFERROR(VLOOKUP('AUP Library'!A803,'Updated Quanities'!F:I,6,0),R803))","v":1.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A803,'Updated Quanities'!F:I,7,0),R803)=\"\",R803,IFERROR(VLOOKUP('AUP Library'!A803,'Updated Quanities'!F:I,7,0),R803))","v":1.08},1.08,{"$f":"IFERROR(VLOOKUP('AUP Library'!A803,'Updated Quanities'!F:G,4,0),R803)","v":1.08}]
["805-12.03","Erosion Control Blanket (Type III)","SY",1.37,1.37,1.37,1.37,1.37,1.37,1.37,1.37,1.37,1.37,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A804,'Updated Quanities'!F:I,4,0),R804)=\"\",R804,IFERROR(VLOOKUP('AUP Library'!A804,'Updated Quanities'!F:I,4,0),R804))","v":1.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A804,'Updated Quanities'!F:I,5,0),R804)=\"\",R804,IFERROR(VLOOKUP('AUP Library'!A804,'Updated Quanities'!F:I,5,0),R804))","v":1.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A804,'Updated Quanities'!F:I,6,0),R804)=\"\",R804,IFERROR(VLOOKUP('AUP Library'!A804,'Updated Quanities'!F:I,6,0),R804))","v":1.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A804,'Updated Quanities'!F:I,7,0),R804)=\"\",R804,IFERROR(VLOOKUP('AUP Library'!A804,'Updated Quanities'!F:I,7,0),R804))","v":1.37},1.37,{"$f":"IFERROR(VLOOKUP('AUP Library'!A804,'Updated Quanities'!F:G,4,0),R804)","v":1.37}]
["806-01","Mowing","Acre",36.28,36.28,36.28,36.28,36.28,36.28,36.28,36.28,36.28,36.28,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A805,'Updated Quanities'!F:I,4,0),R805)=\"\",R805,IFERROR(VLOOKUP('AUP Library'!A805,'Updated Quanities'!F:I,4,0),R805))","v":36.28},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A805,'Updated Quanities'!F:I,5,0),R805)=\"\",R805,IFERROR(VLOOKUP('AUP Library'!A805,'Updated Quanities'!F:I,5,0),R805))","v":36.28},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A805,'Updated Quanities'!F:I,6,0),R805)=\"\",R805,IFERROR(VLOOKUP('AUP Library'!A805,'Updated Quanities'!F:I,6,0),R805))","v":36.28},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A805,'Updated Quanities'!F:I,7,0),R805)=\"\",R805,IFERROR(VLOOKUP('AUP Library'!A805,'Updated Quanities'!F:I,7,0),R805))","v":36.28},36.28,{"$f":"IFERROR(VLOOKUP('AUP Library'!A805,'Updated Quanities'!F:G,4,0),R805)","v":36.28}]
["806-02.03","Project Mowing","CYCL",2143.71,2143.71,2143.71,2143.71,2143.71,2143.71,2143.71,2143.71,2143.71,2143.71,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A806,'Updated Quanities'!F:I,4,0),R806)=\"\",R806,IFERROR(VLOOKUP('AUP Library'!A806,'Updated Quanities'!F:I,4,0),R806))","v":2143.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A806,'Updated Quanities'!F:I,5,0),R806)=\"\",R806,IFERROR(VLOOKUP('AUP Library'!A806,'Updated Quanities'!F:I,5,0),R806))","v":2143.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A806,'Updated Quanities'!F:I,6,0),R806)=\"\",R806,IFERROR(VLOOKUP('AUP Library'!A806,'Updated Quanities'!F:I,6,0),R806))","v":2143.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A806,'Updated Quanities'!F:I,7,0),R806)=\"\",R806,IFERROR(VLOOKUP('AUP Library'!A806,'Updated Quanities'!F:I,7,0),R806))","v":2143.71},2143.71,{"$f":"IFERROR(VLOOKUP('AUP Library'!A806,'Updated Quanities'!F:G,4,0),R806)","v":2143.71}]
["806-02.05","Herbicide Application","Acre",1000,1000,1000,1000,1000,1000,1000,1000,1000,1000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A807,'Updated Quanities'!F:I,4,0),R807)=\"\",R807,IFERROR(VLOOKUP('AUP Library'!A807,'Updated Quanities'!F:I,4,0),R807))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A807,'Updated Quanities'!F:I,5,0),R807)=\"\",R807,IFERROR(VLOOKUP('AUP Library'!A807,'Updated Quanities'!F:I,5,0),R807))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A807,'Updated Quanities'!F:I,6,0),R807)=\"\",R807,IFERROR(VLOOKUP('AUP Library'!A807,'Updated Quanities'!F:I,6,0),R807))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A807,'Updated Quanities'!F:I,7,0),R807)=\"\",R807,IFERROR(VLOOKUP('AUP Library'!A807,'Updated Quanities'!F:I,7,0),R807))","v":1000},1000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A807,'Updated Quanities'!F:G,4,0),R807)","v":1000}]
["806-02.10","Herbicide Application","LS",2000,2000,2000,2000,2000,2000,2000,2000,2000,2000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A808,'Updated Quanities'!F:I,4,0),R808)=\"\",R808,IFERROR(VLOOKUP('AUP Library'!A808,'Updated Quanities'!F:I,4,0),R808))","v":2000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A808,'Updated Quanities'!F:I,5,0),R808)=\"\",R808,IFERROR(VLOOKUP('AUP Library'!A808,'Updated Quanities'!F:I,5,0),R808))","v":2000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A808,'Updated Quanities'!F:I,6,0),R808)=\"\",R808,IFERROR(VLOOKUP('AUP Library'!A808,'Updated Quanities'!F:I,6,0),R808))","v":2000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A808,'Updated Quanities'!F:I,7,0),R808)=\"\",R808,IFERROR(VLOOKUP('AUP Library'!A808,'Updated Quanities'!F:I,7,0),R808))","v":2000},2000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A808,'Updated Quanities'!F:G,4,0),R808)","v":2000}]
["806-02.12","Mowing, Weedeating & Litter Pickup (Urban)","Cycl",4000,4000,4000,4000,4000,4000,4000,4000,4000,4000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A809,'Updated Quanities'!F:I,4,0),R809)=\"\",R809,IFERROR(VLOOKUP('AUP Library'!A809,'Updated Quanities'!F:I,4,0),R809))","v":4000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A809,'Updated Quanities'!F:I,5,0),R809)=\"\",R809,IFERROR(VLOOKUP('AUP Library'!A809,'Updated Quanities'!F:I,5,0),R809))","v":4000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A809,'Updated Quanities'!F:I,6,0),R809)=\"\",R809,IFERROR(VLOOKUP('AUP Library'!A809,'Updated Quanities'!F:I,6,0),R809))","v":4000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A809,'Updated Quanities'!F:I,7,0),R809)=\"\",R809,IFERROR(VLOOKUP('AUP Library'!A809,'Updated Quanities'!F:I,7,0),R809))","v":4000},4000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A809,'Updated Quanities'!F:G,4,0),R809)","v":4000}]
["806-02.13","Swath Mowing","Acre",38.369999999999997,38.369999999999997,38.369999999999997,38.369999999999997,38.369999999999997,38.369999999999997,38.369999999999997,38.369999999999997,38.369999999999997,38.369999999999997,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A810,'Updated Quanities'!F:I,4,0),R810)=\"\",R810,IFERROR(VLOOKUP('AUP Library'!A810,'Updated Quanities'!F:I,4,0),R810))","v":38.369999999999997},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A810,'Updated Quanities'!F:I,5,0),R810)=\"\",R810,IFERROR(VLOOKUP('AUP Library'!A810,'Updated Quanities'!F:I,5,0),R810))","v":38.369999999999997},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A810,'Updated Quanities'!F:I,6,0),R810)=\"\",R810,IFERROR(VLOOKUP('AUP Library'!A810,'Updated Quanities'!F:I,6,0),R810))","v":38.369999999999997},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A810,'Updated Quanities'!F:I,7,0),R810)=\"\",R810,IFERROR(VLOOKUP('AUP Library'!A810,'Updated Quanities'!F:I,7,0),R810))","v":38.369999999999997},38.369999999999997,{"$f":"IFERROR(VLOOKUP('AUP Library'!A810,'Updated Quanities'!F:G,4,0),R810)","v":38.369999999999997}]
["806-03.01","Tree Cutting","LS",10500,10500,10500,10500,10500,10500,10500,10500,10500,10500,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A811,'Updated Quanities'!F:I,4,0),R811)=\"\",R811,IFERROR(VLOOKUP('AUP Library'!A811,'Updated Quanities'!F:I,4,0),R811))","v":10500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A811,'Updated Quanities'!F:I,5,0),R811)=\"\",R811,IFERROR(VLOOKUP('AUP Library'!A811,'Updated Quanities'!F:I,5,0),R811))","v":10500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A811,'Updated Quanities'!F:I,6,0),R811)=\"\",R811,IFERROR(VLOOKUP('AUP Library'!A811,'Updated Quanities'!F:I,6,0),R811))","v":10500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A811,'Updated Quanities'!F:I,7,0),R811)=\"\",R811,IFERROR(VLOOKUP('AUP Library'!A811,'Updated Quanities'!F:I,7,0),R811))","v":10500},10500,{"$f":"IFERROR(VLOOKUP('AUP Library'!A811,'Updated Quanities'!F:G,4,0),R811)","v":10500}]
[]
[]
["Maintenace of Traffic"]
[null,"Traffic Control","LS"]
["712-01","Traffic Control","LS",21717.03,21717.03,21717.03,21717.03,21717.03,21717.03,21717.03,21717.03,21717.03,21717.03,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A816,'Updated Quanities'!F:I,4,0),R816)=\"\",R816,IFERROR(VLOOKUP('AUP Library'!A816,'Updated Quanities'!F:I,4,0),R816))","v":21717.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A816,'Updated Quanities'!F:I,5,0),R816)=\"\",R816,IFERROR(VLOOKUP('AUP Library'!A816,'Updated Quanities'!F:I,5,0),R816))","v":21717.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A816,'Updated Quanities'!F:I,6,0),R816)=\"\",R816,IFERROR(VLOOKUP('AUP Library'!A816,'Updated Quanities'!F:I,6,0),R816))","v":21717.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A816,'Updated Quanities'!F:I,7,0),R816)=\"\",R816,IFERROR(VLOOKUP('AUP Library'!A816,'Updated Quanities'!F:I,7,0),R816))","v":21717.03},21717.03,{"$f":"IFERROR(VLOOKUP('AUP Library'!A816,'Updated Quanities'!F:G,4,0),R816)","v":21717.03}]
["712-02.02","Interconnected Portable Barrier Rail","LF","14.0","17.97","19.36","21.13","21.13",22.5,22.52,25.49,24.96,26.47,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A817,'Updated Quanities'!F:I,4,0),R817)=\"\",R817,IFERROR(VLOOKUP('AUP Library'!A817,'Updated Quanities'!F:I,4,0),R817))","v":25.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A817,'Updated Quanities'!F:I,5,0),R817)=\"\",R817,IFERROR(VLOOKUP('AUP Library'!A817,'Updated Quanities'!F:I,5,0),R817))","v":25.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A817,'Updated Quanities'!F:I,6,0),R817)=\"\",R817,IFERROR(VLOOKUP('AUP Library'!A817,'Updated Quanities'!F:I,6,0),R817))","v":25.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A817,'Updated Quanities'!F:I,7,0),R817)=\"\",R817,IFERROR(VLOOKUP('AUP Library'!A817,'Updated Quanities'!F:I,7,0),R817))","v":25.26},25.26,{"$f":"IFERROR(VLOOKUP('AUP Library'!A817,'Updated Quanities'!F:G,4,0),R817)","v":25.26}]
["712-01.02","Lane Closure","EA",117.36,117.36,117.36,117.36,117.36,117.36,117.36,117.36,117.36,117.36,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A818,'Updated Quanities'!F:I,4,0),R818)=\"\",R818,IFERROR(VLOOKUP('AUP Library'!A818,'Updated Quanities'!F:I,4,0),R818))","v":117.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A818,'Updated Quanities'!F:I,5,0),R818)=\"\",R818,IFERROR(VLOOKUP('AUP Library'!A818,'Updated Quanities'!F:I,5,0),R818))","v":117.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A818,'Updated Quanities'!F:I,6,0),R818)=\"\",R818,IFERROR(VLOOKUP('AUP Library'!A818,'Updated Quanities'!F:I,6,0),R818))","v":117.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A818,'Updated Quanities'!F:I,7,0),R818)=\"\",R818,IFERROR(VLOOKUP('AUP Library'!A818,'Updated Quanities'!F:I,7,0),R818))","v":117.36},117.36,{"$f":"IFERROR(VLOOKUP('AUP Library'!A818,'Updated Quanities'!F:G,4,0),R818)","v":117.36}]
["712-04.01","Flexible Drums (Channelizing)","EA",26.26,26.26,26.26,26.26,26.26,26.26,26.26,26.26,26.26,26.26,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A819,'Updated Quanities'!F:I,4,0),R819)=\"\",R819,IFERROR(VLOOKUP('AUP Library'!A819,'Updated Quanities'!F:I,4,0),R819))","v":26.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A819,'Updated Quanities'!F:I,5,0),R819)=\"\",R819,IFERROR(VLOOKUP('AUP Library'!A819,'Updated Quanities'!F:I,5,0),R819))","v":26.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A819,'Updated Quanities'!F:I,6,0),R819)=\"\",R819,IFERROR(VLOOKUP('AUP Library'!A819,'Updated Quanities'!F:I,6,0),R819))","v":26.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A819,'Updated Quanities'!F:I,7,0),R819)=\"\",R819,IFERROR(VLOOKUP('AUP Library'!A819,'Updated Quanities'!F:I,7,0),R819))","v":26.26},26.26,{"$f":"IFERROR(VLOOKUP('AUP Library'!A819,'Updated Quanities'!F:G,4,0),R819)","v":26.26}]
["712-04.50","Portable Barrier Rail Delineator","EA",11.28,11.28,11.28,11.28,11.28,11.28,11.28,11.28,11.28,11.28,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A820,'Updated Quanities'!F:I,4,0),R820)=\"\",R820,IFERROR(VLOOKUP('AUP Library'!A820,'Updated Quanities'!F:I,4,0),R820))","v":11.28},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A820,'Updated Quanities'!F:I,5,0),R820)=\"\",R820,IFERROR(VLOOKUP('AUP Library'!A820,'Updated Quanities'!F:I,5,0),R820))","v":11.28},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A820,'Updated Quanities'!F:I,6,0),R820)=\"\",R820,IFERROR(VLOOKUP('AUP Library'!A820,'Updated Quanities'!F:I,6,0),R820))","v":11.28},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A820,'Updated Quanities'!F:I,7,0),R820)=\"\",R820,IFERROR(VLOOKUP('AUP Library'!A820,'Updated Quanities'!F:I,7,0),R820))","v":11.28},11.28,{"$f":"IFERROR(VLOOKUP('AUP Library'!A820,'Updated Quanities'!F:G,4,0),R820)","v":11.28}]
["712-05.01","Warning Lights (Type A)","EA",22.35,22.35,22.35,22.35,22.35,22.35,22.35,22.35,22.35,22.35,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A821,'Updated Quanities'!F:I,4,0),R821)=\"\",R821,IFERROR(VLOOKUP('AUP Library'!A821,'Updated Quanities'!F:I,4,0),R821))","v":22.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A821,'Updated Quanities'!F:I,5,0),R821)=\"\",R821,IFERROR(VLOOKUP('AUP Library'!A821,'Updated Quanities'!F:I,5,0),R821))","v":22.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A821,'Updated Quanities'!F:I,6,0),R821)=\"\",R821,IFERROR(VLOOKUP('AUP Library'!A821,'Updated Quanities'!F:I,6,0),R821))","v":22.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A821,'Updated Quanities'!F:I,7,0),R821)=\"\",R821,IFERROR(VLOOKUP('AUP Library'!A821,'Updated Quanities'!F:I,7,0),R821))","v":22.35},22.35,{"$f":"IFERROR(VLOOKUP('AUP Library'!A821,'Updated Quanities'!F:G,4,0),R821)","v":22.35}]
["712-05.03","Warning Lights (Type C)","EA",19.77,19.77,19.77,19.77,19.77,19.77,19.77,19.77,19.77,19.77,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A822,'Updated Quanities'!F:I,4,0),R822)=\"\",R822,IFERROR(VLOOKUP('AUP Library'!A822,'Updated Quanities'!F:I,4,0),R822))","v":19.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A822,'Updated Quanities'!F:I,5,0),R822)=\"\",R822,IFERROR(VLOOKUP('AUP Library'!A822,'Updated Quanities'!F:I,5,0),R822))","v":19.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A822,'Updated Quanities'!F:I,6,0),R822)=\"\",R822,IFERROR(VLOOKUP('AUP Library'!A822,'Updated Quanities'!F:I,6,0),R822))","v":19.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A822,'Updated Quanities'!F:I,7,0),R822)=\"\",R822,IFERROR(VLOOKUP('AUP Library'!A822,'Updated Quanities'!F:I,7,0),R822))","v":19.77},19.77,{"$f":"IFERROR(VLOOKUP('AUP Library'!A822,'Updated Quanities'!F:G,4,0),R822)","v":19.77}]
["712-06","Signs (Construction)","SF",7,7,7,7,7,7,7,7,7,7,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A823,'Updated Quanities'!F:I,4,0),R823)=\"\",R823,IFERROR(VLOOKUP('AUP Library'!A823,'Updated Quanities'!F:I,4,0),R823))","v":7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A823,'Updated Quanities'!F:I,5,0),R823)=\"\",R823,IFERROR(VLOOKUP('AUP Library'!A823,'Updated Quanities'!F:I,5,0),R823))","v":7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A823,'Updated Quanities'!F:I,6,0),R823)=\"\",R823,IFERROR(VLOOKUP('AUP Library'!A823,'Updated Quanities'!F:I,6,0),R823))","v":7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A823,'Updated Quanities'!F:I,7,0),R823)=\"\",R823,IFERROR(VLOOKUP('AUP Library'!A823,'Updated Quanities'!F:I,7,0),R823))","v":7},7,{"$f":"IFERROR(VLOOKUP('AUP Library'!A823,'Updated Quanities'!F:G,4,0),R823)","v":7}]
["712-06.01","Vertical Panels","SF",13.66,13.66,13.66,13.66,13.66,13.66,13.66,13.66,13.66,13.66,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A824,'Updated Quanities'!F:I,4,0),R824)=\"\",R824,IFERROR(VLOOKUP('AUP Library'!A824,'Updated Quanities'!F:I,4,0),R824))","v":13.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A824,'Updated Quanities'!F:I,5,0),R824)=\"\",R824,IFERROR(VLOOKUP('AUP Library'!A824,'Updated Quanities'!F:I,5,0),R824))","v":13.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A824,'Updated Quanities'!F:I,6,0),R824)=\"\",R824,IFERROR(VLOOKUP('AUP Library'!A824,'Updated Quanities'!F:I,6,0),R824))","v":13.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A824,'Updated Quanities'!F:I,7,0),R824)=\"\",R824,IFERROR(VLOOKUP('AUP Library'!A824,'Updated Quanities'!F:I,7,0),R824))","v":13.66},13.66,{"$f":"IFERROR(VLOOKUP('AUP Library'!A824,'Updated Quanities'!F:G,4,0),R824)","v":13.66}]
["712-06.10","New Signs (Construction)","SF",15,15,15,15,15,15,15,15,15,15,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A825,'Updated Quanities'!F:I,4,0),R825)=\"\",R825,IFERROR(VLOOKUP('AUP Library'!A825,'Updated Quanities'!F:I,4,0),R825))","v":15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A825,'Updated Quanities'!F:I,5,0),R825)=\"\",R825,IFERROR(VLOOKUP('AUP Library'!A825,'Updated Quanities'!F:I,5,0),R825))","v":15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A825,'Updated Quanities'!F:I,6,0),R825)=\"\",R825,IFERROR(VLOOKUP('AUP Library'!A825,'Updated Quanities'!F:I,6,0),R825))","v":15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A825,'Updated Quanities'!F:I,7,0),R825)=\"\",R825,IFERROR(VLOOKUP('AUP Library'!A825,'Updated Quanities'!F:I,7,0),R825))","v":15},15,{"$f":"IFERROR(VLOOKUP('AUP Library'!A825,'Updated Quanities'!F:G,4,0),R825)","v":15}]
["712-06.16","Signs (Constr)(Reduced Speed Warning)","EA",522.25,522.25,522.25,522.25,522.25,522.25,522.25,522.25,522.25,522.25,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A826,'Updated Quanities'!F:I,4,0),R826)=\"\",R826,IFERROR(VLOOKUP('AUP Library'!A826,'Updated Quanities'!F:I,4,0),R826))","v":522.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A826,'Updated Quanities'!F:I,5,0),R826)=\"\",R826,IFERROR(VLOOKUP('AUP Library'!A826,'Updated Quanities'!F:I,5,0),R826))","v":522.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A826,'Updated Quanities'!F:I,6,0),R826)=\"\",R826,IFERROR(VLOOKUP('AUP Library'!A826,'Updated Quanities'!F:I,6,0),R826))","v":522.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A826,'Updated Quanities'!F:I,7,0),R826)=\"\",R826,IFERROR(VLOOKUP('AUP Library'!A826,'Updated Quanities'!F:I,7,0),R826))","v":522.25},522.25,{"$f":"IFERROR(VLOOKUP('AUP Library'!A826,'Updated Quanities'!F:G,4,0),R826)","v":522.25}]
["712-07.03","Temporary Barricades (Type III)","LF",14.13,14.13,14.13,14.13,14.13,14.13,14.13,14.13,14.13,14.13,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A827,'Updated Quanities'!F:I,4,0),R827)=\"\",R827,IFERROR(VLOOKUP('AUP Library'!A827,'Updated Quanities'!F:I,4,0),R827))","v":14.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A827,'Updated Quanities'!F:I,5,0),R827)=\"\",R827,IFERROR(VLOOKUP('AUP Library'!A827,'Updated Quanities'!F:I,5,0),R827))","v":14.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A827,'Updated Quanities'!F:I,6,0),R827)=\"\",R827,IFERROR(VLOOKUP('AUP Library'!A827,'Updated Quanities'!F:I,6,0),R827))","v":14.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A827,'Updated Quanities'!F:I,7,0),R827)=\"\",R827,IFERROR(VLOOKUP('AUP Library'!A827,'Updated Quanities'!F:I,7,0),R827))","v":14.13},14.13,{"$f":"IFERROR(VLOOKUP('AUP Library'!A827,'Updated Quanities'!F:G,4,0),R827)","v":14.13}]
["712-08.03","Arrow Board (Type C)","EA",993.78,993.78,993.78,993.78,993.78,993.78,993.78,993.78,993.78,993.78,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A828,'Updated Quanities'!F:I,4,0),R828)=\"\",R828,IFERROR(VLOOKUP('AUP Library'!A828,'Updated Quanities'!F:I,4,0),R828))","v":993.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A828,'Updated Quanities'!F:I,5,0),R828)=\"\",R828,IFERROR(VLOOKUP('AUP Library'!A828,'Updated Quanities'!F:I,5,0),R828))","v":993.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A828,'Updated Quanities'!F:I,6,0),R828)=\"\",R828,IFERROR(VLOOKUP('AUP Library'!A828,'Updated Quanities'!F:I,6,0),R828))","v":993.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A828,'Updated Quanities'!F:I,7,0),R828)=\"\",R828,IFERROR(VLOOKUP('AUP Library'!A828,'Updated Quanities'!F:I,7,0),R828))","v":993.78},993.78,{"$f":"IFERROR(VLOOKUP('AUP Library'!A828,'Updated Quanities'!F:G,4,0),R828)","v":993.78}]
["712-08.06","Uniformed Police Officer","HR",50.67,50.67,50.67,50.67,50.67,50.67,50.67,50.67,50.67,50.67,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A829,'Updated Quanities'!F:I,4,0),R829)=\"\",R829,IFERROR(VLOOKUP('AUP Library'!A829,'Updated Quanities'!F:I,4,0),R829))","v":50.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A829,'Updated Quanities'!F:I,5,0),R829)=\"\",R829,IFERROR(VLOOKUP('AUP Library'!A829,'Updated Quanities'!F:I,5,0),R829))","v":50.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A829,'Updated Quanities'!F:I,6,0),R829)=\"\",R829,IFERROR(VLOOKUP('AUP Library'!A829,'Updated Quanities'!F:I,6,0),R829))","v":50.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A829,'Updated Quanities'!F:I,7,0),R829)=\"\",R829,IFERROR(VLOOKUP('AUP Library'!A829,'Updated Quanities'!F:I,7,0),R829))","v":50.67},50.67,{"$f":"IFERROR(VLOOKUP('AUP Library'!A829,'Updated Quanities'!F:G,4,0),R829)","v":50.67}]
["712-09.01","Removable Pavement Marking Line","LF",1.99,1.99,1.99,1.99,1.99,1.99,1.99,1.99,1.99,1.99,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A830,'Updated Quanities'!F:I,4,0),R830)=\"\",R830,IFERROR(VLOOKUP('AUP Library'!A830,'Updated Quanities'!F:I,4,0),R830))","v":1.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A830,'Updated Quanities'!F:I,5,0),R830)=\"\",R830,IFERROR(VLOOKUP('AUP Library'!A830,'Updated Quanities'!F:I,5,0),R830))","v":1.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A830,'Updated Quanities'!F:I,6,0),R830)=\"\",R830,IFERROR(VLOOKUP('AUP Library'!A830,'Updated Quanities'!F:I,6,0),R830))","v":1.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A830,'Updated Quanities'!F:I,7,0),R830)=\"\",R830,IFERROR(VLOOKUP('AUP Library'!A830,'Updated Quanities'!F:I,7,0),R830))","v":1.99},1.99,{"$f":"IFERROR(VLOOKUP('AUP Library'!A830,'Updated Quanities'!F:G,4,0),R830)","v":1.99}]
["712-09.02","Removable Pavement Marking (8\" Barrier Line)","LF",3.19,3.19,3.19,3.19,3.19,3.19,3.19,3.19,3.19,3.19,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A831,'Updated Quanities'!F:I,4,0),R831)=\"\",R831,IFERROR(VLOOKUP('AUP Library'!A831,'Updated Quanities'!F:I,4,0),R831))","v":3.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A831,'Updated Quanities'!F:I,5,0),R831)=\"\",R831,IFERROR(VLOOKUP('AUP Library'!A831,'Updated Quanities'!F:I,5,0),R831))","v":3.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A831,'Updated Quanities'!F:I,6,0),R831)=\"\",R831,IFERROR(VLOOKUP('AUP Library'!A831,'Updated Quanities'!F:I,6,0),R831))","v":3.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A831,'Updated Quanities'!F:I,7,0),R831)=\"\",R831,IFERROR(VLOOKUP('AUP Library'!A831,'Updated Quanities'!F:I,7,0),R831))","v":3.19},3.19,{"$f":"IFERROR(VLOOKUP('AUP Library'!A831,'Updated Quanities'!F:G,4,0),R831)","v":3.19}]
["712-09.03","Removable Pavement Marking (Channelizing Striping)","SY",32.4,32.4,32.4,32.4,32.4,32.4,32.4,32.4,32.4,32.4,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A832,'Updated Quanities'!F:I,4,0),R832)=\"\",R832,IFERROR(VLOOKUP('AUP Library'!A832,'Updated Quanities'!F:I,4,0),R832))","v":32.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A832,'Updated Quanities'!F:I,5,0),R832)=\"\",R832,IFERROR(VLOOKUP('AUP Library'!A832,'Updated Quanities'!F:I,5,0),R832))","v":32.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A832,'Updated Quanities'!F:I,6,0),R832)=\"\",R832,IFERROR(VLOOKUP('AUP Library'!A832,'Updated Quanities'!F:I,6,0),R832))","v":32.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A832,'Updated Quanities'!F:I,7,0),R832)=\"\",R832,IFERROR(VLOOKUP('AUP Library'!A832,'Updated Quanities'!F:I,7,0),R832))","v":32.4},32.4,{"$f":"IFERROR(VLOOKUP('AUP Library'!A832,'Updated Quanities'!F:G,4,0),R832)","v":32.4}]
["712-09.04","Removable Pavement Marking (Stop Line)","LF",15.01,15.01,15.01,15.01,15.01,15.01,15.01,15.01,15.01,15.01,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A833,'Updated Quanities'!F:I,4,0),R833)=\"\",R833,IFERROR(VLOOKUP('AUP Library'!A833,'Updated Quanities'!F:I,4,0),R833))","v":15.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A833,'Updated Quanities'!F:I,5,0),R833)=\"\",R833,IFERROR(VLOOKUP('AUP Library'!A833,'Updated Quanities'!F:I,5,0),R833))","v":15.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A833,'Updated Quanities'!F:I,6,0),R833)=\"\",R833,IFERROR(VLOOKUP('AUP Library'!A833,'Updated Quanities'!F:I,6,0),R833))","v":15.01},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A833,'Updated Quanities'!F:I,7,0),R833)=\"\",R833,IFERROR(VLOOKUP('AUP Library'!A833,'Updated Quanities'!F:I,7,0),R833))","v":15.01},15.01,{"$f":"IFERROR(VLOOKUP('AUP Library'!A833,'Updated Quanities'!F:G,4,0),R833)","v":15.01}]
["712-09.05","Removable Pavement Marking (Arrow)","EA",227.86,227.86,227.86,227.86,227.86,227.86,227.86,227.86,227.86,227.86,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A834,'Updated Quanities'!F:I,4,0),R834)=\"\",R834,IFERROR(VLOOKUP('AUP Library'!A834,'Updated Quanities'!F:I,4,0),R834))","v":227.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A834,'Updated Quanities'!F:I,5,0),R834)=\"\",R834,IFERROR(VLOOKUP('AUP Library'!A834,'Updated Quanities'!F:I,5,0),R834))","v":227.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A834,'Updated Quanities'!F:I,6,0),R834)=\"\",R834,IFERROR(VLOOKUP('AUP Library'!A834,'Updated Quanities'!F:I,6,0),R834))","v":227.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A834,'Updated Quanities'!F:I,7,0),R834)=\"\",R834,IFERROR(VLOOKUP('AUP Library'!A834,'Updated Quanities'!F:I,7,0),R834))","v":227.86},227.86,{"$f":"IFERROR(VLOOKUP('AUP Library'!A834,'Updated Quanities'!F:G,4,0),R834)","v":227.86}]
["712-09.06","REMOVABLE PAVEMENT MARKING LINE (6IN)","LF",3.94,3.94,3.94,3.94,3.94,3.94,3.94,3.94,3.94,3.94,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A835,'Updated Quanities'!F:I,4,0),R835)=\"\",R835,IFERROR(VLOOKUP('AUP Library'!A835,'Updated Quanities'!F:I,4,0),R835))","v":3.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A835,'Updated Quanities'!F:I,5,0),R835)=\"\",R835,IFERROR(VLOOKUP('AUP Library'!A835,'Updated Quanities'!F:I,5,0),R835))","v":3.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A835,'Updated Quanities'!F:I,6,0),R835)=\"\",R835,IFERROR(VLOOKUP('AUP Library'!A835,'Updated Quanities'!F:I,6,0),R835))","v":3.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A835,'Updated Quanities'!F:I,7,0),R835)=\"\",R835,IFERROR(VLOOKUP('AUP Library'!A835,'Updated Quanities'!F:I,7,0),R835))","v":3.94},3.94,{"$f":"IFERROR(VLOOKUP('AUP Library'!A835,'Updated Quanities'!F:G,4,0),R835)","v":3.94}]
["712-09.20","TEMPORARY PLASTIC PVMT MKG(NOISE STRIP)","LF",31.25,31.25,31.25,31.25,31.25,31.25,31.25,31.25,31.25,31.25,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A836,'Updated Quanities'!F:I,4,0),R836)=\"\",R836,IFERROR(VLOOKUP('AUP Library'!A836,'Updated Quanities'!F:I,4,0),R836))","v":31.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A836,'Updated Quanities'!F:I,5,0),R836)=\"\",R836,IFERROR(VLOOKUP('AUP Library'!A836,'Updated Quanities'!F:I,5,0),R836))","v":31.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A836,'Updated Quanities'!F:I,6,0),R836)=\"\",R836,IFERROR(VLOOKUP('AUP Library'!A836,'Updated Quanities'!F:I,6,0),R836))","v":31.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A836,'Updated Quanities'!F:I,7,0),R836)=\"\",R836,IFERROR(VLOOKUP('AUP Library'!A836,'Updated Quanities'!F:I,7,0),R836))","v":31.25},31.25,{"$f":"IFERROR(VLOOKUP('AUP Library'!A836,'Updated Quanities'!F:G,4,0),R836)","v":31.25}]
["712-09.21","REMOVABLE WET REFLECTIVE PVMT MARK. TAPE","LF",1.75,1.75,1.75,1.75,1.75,1.75,1.75,1.75,1.75,1.75,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A837,'Updated Quanities'!F:I,4,0),R837)=\"\",R837,IFERROR(VLOOKUP('AUP Library'!A837,'Updated Quanities'!F:I,4,0),R837))","v":1.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A837,'Updated Quanities'!F:I,5,0),R837)=\"\",R837,IFERROR(VLOOKUP('AUP Library'!A837,'Updated Quanities'!F:I,5,0),R837))","v":1.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A837,'Updated Quanities'!F:I,6,0),R837)=\"\",R837,IFERROR(VLOOKUP('AUP Library'!A837,'Updated Quanities'!F:I,6,0),R837))","v":1.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A837,'Updated Quanities'!F:I,7,0),R837)=\"\",R837,IFERROR(VLOOKUP('AUP Library'!A837,'Updated Quanities'!F:I,7,0),R837))","v":1.75},1.75,{"$f":"IFERROR(VLOOKUP('AUP Library'!A837,'Updated Quanities'!F:G,4,0),R837)","v":1.75}]
["712-09.30","REMOVABLE BLACK-OUT TAPE (6\")","LF",4.3600000000000003,4.3600000000000003,4.3600000000000003,4.3600000000000003,4.3600000000000003,4.3600000000000003,4.3600000000000003,4.3600000000000003,4.3600000000000003,4.3600000000000003,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A838,'Updated Quanities'!F:I,4,0),R838)=\"\",R838,IFERROR(VLOOKUP('AUP Library'!A838,'Updated Quanities'!F:I,4,0),R838))","v":4.3600000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A838,'Updated Quanities'!F:I,5,0),R838)=\"\",R838,IFERROR(VLOOKUP('AUP Library'!A838,'Updated Quanities'!F:I,5,0),R838))","v":4.3600000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A838,'Updated Quanities'!F:I,6,0),R838)=\"\",R838,IFERROR(VLOOKUP('AUP Library'!A838,'Updated Quanities'!F:I,6,0),R838))","v":4.3600000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A838,'Updated Quanities'!F:I,7,0),R838)=\"\",R838,IFERROR(VLOOKUP('AUP Library'!A838,'Updated Quanities'!F:I,7,0),R838))","v":4.3600000000000003},4.3600000000000003,{"$f":"IFERROR(VLOOKUP('AUP Library'!A838,'Updated Quanities'!F:G,4,0),R838)","v":4.3600000000000003}]
["712-09.31","REMOVABLE BLACK-OUT TAPE (8IN)","LF",3,3,3,3,3,3,3,3,3,3,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A839,'Updated Quanities'!F:I,4,0),R839)=\"\",R839,IFERROR(VLOOKUP('AUP Library'!A839,'Updated Quanities'!F:I,4,0),R839))","v":3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A839,'Updated Quanities'!F:I,5,0),R839)=\"\",R839,IFERROR(VLOOKUP('AUP Library'!A839,'Updated Quanities'!F:I,5,0),R839))","v":3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A839,'Updated Quanities'!F:I,6,0),R839)=\"\",R839,IFERROR(VLOOKUP('AUP Library'!A839,'Updated Quanities'!F:I,6,0),R839))","v":3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A839,'Updated Quanities'!F:I,7,0),R839)=\"\",R839,IFERROR(VLOOKUP('AUP Library'!A839,'Updated Quanities'!F:I,7,0),R839))","v":3},3,{"$f":"IFERROR(VLOOKUP('AUP Library'!A839,'Updated Quanities'!F:G,4,0),R839)","v":3}]
["712-09.33","Modify Existing Overhead Signs","EA",1200,1200,1200,1200,1200,1200,1200,1200,1200,1200,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A840,'Updated Quanities'!F:I,4,0),R840)=\"\",R840,IFERROR(VLOOKUP('AUP Library'!A840,'Updated Quanities'!F:I,4,0),R840))","v":1200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A840,'Updated Quanities'!F:I,5,0),R840)=\"\",R840,IFERROR(VLOOKUP('AUP Library'!A840,'Updated Quanities'!F:I,5,0),R840))","v":1200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A840,'Updated Quanities'!F:I,6,0),R840)=\"\",R840,IFERROR(VLOOKUP('AUP Library'!A840,'Updated Quanities'!F:I,6,0),R840))","v":1200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A840,'Updated Quanities'!F:I,7,0),R840)=\"\",R840,IFERROR(VLOOKUP('AUP Library'!A840,'Updated Quanities'!F:I,7,0),R840))","v":1200},1200,{"$f":"IFERROR(VLOOKUP('AUP Library'!A840,'Updated Quanities'!F:G,4,0),R840)","v":1200}]
["712-12.10","TEMPORARY CURB W/FLEXIBLE DELINEATOR","LF",45,45,45,45,45,45,45,45,45,45,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A841,'Updated Quanities'!F:I,4,0),R841)=\"\",R841,IFERROR(VLOOKUP('AUP Library'!A841,'Updated Quanities'!F:I,4,0),R841))","v":45},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A841,'Updated Quanities'!F:I,5,0),R841)=\"\",R841,IFERROR(VLOOKUP('AUP Library'!A841,'Updated Quanities'!F:I,5,0),R841))","v":45},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A841,'Updated Quanities'!F:I,6,0),R841)=\"\",R841,IFERROR(VLOOKUP('AUP Library'!A841,'Updated Quanities'!F:I,6,0),R841))","v":45},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A841,'Updated Quanities'!F:I,7,0),R841)=\"\",R841,IFERROR(VLOOKUP('AUP Library'!A841,'Updated Quanities'!F:I,7,0),R841))","v":45},45,{"$f":"IFERROR(VLOOKUP('AUP Library'!A841,'Updated Quanities'!F:G,4,0),R841)","v":45}]
["712-12.47","BRIDGE MNTED INTERCON PORT BARRIER RAIL","LF",35.08,35.08,35.08,35.08,35.08,35.08,35.08,35.08,35.08,35.08,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A842,'Updated Quanities'!F:I,4,0),R842)=\"\",R842,IFERROR(VLOOKUP('AUP Library'!A842,'Updated Quanities'!F:I,4,0),R842))","v":35.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A842,'Updated Quanities'!F:I,5,0),R842)=\"\",R842,IFERROR(VLOOKUP('AUP Library'!A842,'Updated Quanities'!F:I,5,0),R842))","v":35.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A842,'Updated Quanities'!F:I,6,0),R842)=\"\",R842,IFERROR(VLOOKUP('AUP Library'!A842,'Updated Quanities'!F:I,6,0),R842))","v":35.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A842,'Updated Quanities'!F:I,7,0),R842)=\"\",R842,IFERROR(VLOOKUP('AUP Library'!A842,'Updated Quanities'!F:I,7,0),R842))","v":35.08},35.08,{"$f":"IFERROR(VLOOKUP('AUP Library'!A842,'Updated Quanities'!F:G,4,0),R842)","v":35.08}]
["717-01","Mobilization","LS",47118.78,47118.78,47118.78,47118.78,47118.78,47118.78,47118.78,47118.78,47118.78,47118.78,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A843,'Updated Quanities'!F:I,4,0),R843)=\"\",R843,IFERROR(VLOOKUP('AUP Library'!A843,'Updated Quanities'!F:I,4,0),R843))","v":47118.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A843,'Updated Quanities'!F:I,5,0),R843)=\"\",R843,IFERROR(VLOOKUP('AUP Library'!A843,'Updated Quanities'!F:I,5,0),R843))","v":47118.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A843,'Updated Quanities'!F:I,6,0),R843)=\"\",R843,IFERROR(VLOOKUP('AUP Library'!A843,'Updated Quanities'!F:I,6,0),R843))","v":47118.78},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A843,'Updated Quanities'!F:I,7,0),R843)=\"\",R843,IFERROR(VLOOKUP('AUP Library'!A843,'Updated Quanities'!F:I,7,0),R843))","v":47118.78},47118.78,{"$f":"IFERROR(VLOOKUP('AUP Library'!A843,'Updated Quanities'!F:G,4,0),R843)","v":47118.78}]
["717-01.03","Mobilization","EA",207.06,207.06,207.06,207.06,207.06,207.06,207.06,207.06,207.06,207.06,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A844,'Updated Quanities'!F:I,4,0),R844)=\"\",R844,IFERROR(VLOOKUP('AUP Library'!A844,'Updated Quanities'!F:I,4,0),R844))","v":207.06},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A844,'Updated Quanities'!F:I,5,0),R844)=\"\",R844,IFERROR(VLOOKUP('AUP Library'!A844,'Updated Quanities'!F:I,5,0),R844))","v":207.06},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A844,'Updated Quanities'!F:I,6,0),R844)=\"\",R844,IFERROR(VLOOKUP('AUP Library'!A844,'Updated Quanities'!F:I,6,0),R844))","v":207.06},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A844,'Updated Quanities'!F:I,7,0),R844)=\"\",R844,IFERROR(VLOOKUP('AUP Library'!A844,'Updated Quanities'!F:I,7,0),R844))","v":207.06},207.06,{"$f":"IFERROR(VLOOKUP('AUP Library'!A844,'Updated Quanities'!F:G,4,0),R844)","v":207.06}]
["717-01.04","Mobilization","EA",389.18,389.18,389.18,389.18,389.18,389.18,389.18,389.18,389.18,389.18,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A845,'Updated Quanities'!F:I,4,0),R845)=\"\",R845,IFERROR(VLOOKUP('AUP Library'!A845,'Updated Quanities'!F:I,4,0),R845))","v":389.18},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A845,'Updated Quanities'!F:I,5,0),R845)=\"\",R845,IFERROR(VLOOKUP('AUP Library'!A845,'Updated Quanities'!F:I,5,0),R845))","v":389.18},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A845,'Updated Quanities'!F:I,6,0),R845)=\"\",R845,IFERROR(VLOOKUP('AUP Library'!A845,'Updated Quanities'!F:I,6,0),R845))","v":389.18},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A845,'Updated Quanities'!F:I,7,0),R845)=\"\",R845,IFERROR(VLOOKUP('AUP Library'!A845,'Updated Quanities'!F:I,7,0),R845))","v":389.18},389.18,{"$f":"IFERROR(VLOOKUP('AUP Library'!A845,'Updated Quanities'!F:G,4,0),R845)","v":389.18}]
["717-01.05","Mobilization","EA",349.79,349.79,349.79,349.79,349.79,349.79,349.79,349.79,349.79,349.79,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A846,'Updated Quanities'!F:I,4,0),R846)=\"\",R846,IFERROR(VLOOKUP('AUP Library'!A846,'Updated Quanities'!F:I,4,0),R846))","v":349.79},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A846,'Updated Quanities'!F:I,5,0),R846)=\"\",R846,IFERROR(VLOOKUP('AUP Library'!A846,'Updated Quanities'!F:I,5,0),R846))","v":349.79},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A846,'Updated Quanities'!F:I,6,0),R846)=\"\",R846,IFERROR(VLOOKUP('AUP Library'!A846,'Updated Quanities'!F:I,6,0),R846))","v":349.79},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A846,'Updated Quanities'!F:I,7,0),R846)=\"\",R846,IFERROR(VLOOKUP('AUP Library'!A846,'Updated Quanities'!F:I,7,0),R846))","v":349.79},349.79,{"$f":"IFERROR(VLOOKUP('AUP Library'!A846,'Updated Quanities'!F:G,4,0),R846)","v":349.79}]
["717-01.07","Mobilization","EA",50,50,50,50,50,50,50,50,50,50,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A847,'Updated Quanities'!F:I,4,0),R847)=\"\",R847,IFERROR(VLOOKUP('AUP Library'!A847,'Updated Quanities'!F:I,4,0),R847))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A847,'Updated Quanities'!F:I,5,0),R847)=\"\",R847,IFERROR(VLOOKUP('AUP Library'!A847,'Updated Quanities'!F:I,5,0),R847))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A847,'Updated Quanities'!F:I,6,0),R847)=\"\",R847,IFERROR(VLOOKUP('AUP Library'!A847,'Updated Quanities'!F:I,6,0),R847))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A847,'Updated Quanities'!F:I,7,0),R847)=\"\",R847,IFERROR(VLOOKUP('AUP Library'!A847,'Updated Quanities'!F:I,7,0),R847))","v":50},50,{"$f":"IFERROR(VLOOKUP('AUP Library'!A847,'Updated Quanities'!F:G,4,0),R847)","v":50}]
["717-01.08","Mobilization","EA",50,50,50,50,50,50,50,50,50,50,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A848,'Updated Quanities'!F:I,4,0),R848)=\"\",R848,IFERROR(VLOOKUP('AUP Library'!A848,'Updated Quanities'!F:I,4,0),R848))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A848,'Updated Quanities'!F:I,5,0),R848)=\"\",R848,IFERROR(VLOOKUP('AUP Library'!A848,'Updated Quanities'!F:I,5,0),R848))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A848,'Updated Quanities'!F:I,6,0),R848)=\"\",R848,IFERROR(VLOOKUP('AUP Library'!A848,'Updated Quanities'!F:I,6,0),R848))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A848,'Updated Quanities'!F:I,7,0),R848)=\"\",R848,IFERROR(VLOOKUP('AUP Library'!A848,'Updated Quanities'!F:I,7,0),R848))","v":50},50,{"$f":"IFERROR(VLOOKUP('AUP Library'!A848,'Updated Quanities'!F:G,4,0),R848)","v":50}]
["717-01.09","Mobilization","EA",50,50,50,50,50,50,50,50,50,50,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A849,'Updated Quanities'!F:I,4,0),R849)=\"\",R849,IFERROR(VLOOKUP('AUP Library'!A849,'Updated Quanities'!F:I,4,0),R849))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A849,'Updated Quanities'!F:I,5,0),R849)=\"\",R849,IFERROR(VLOOKUP('AUP Library'!A849,'Updated Quanities'!F:I,5,0),R849))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A849,'Updated Quanities'!F:I,6,0),R849)=\"\",R849,IFERROR(VLOOKUP('AUP Library'!A849,'Updated Quanities'!F:I,6,0),R849))","v":50},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A849,'Updated Quanities'!F:I,7,0),R849)=\"\",R849,IFERROR(VLOOKUP('AUP Library'!A849,'Updated Quanities'!F:I,7,0),R849))","v":50},50,{"$f":"IFERROR(VLOOKUP('AUP Library'!A849,'Updated Quanities'!F:G,4,0),R849)","v":50}]
["717-01.11","Mobilization","EA",1800000,1800000,1800000,1800000,1800000,1800000,1800000,1800000,1800000,1800000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A850,'Updated Quanities'!F:I,4,0),R850)=\"\",R850,IFERROR(VLOOKUP('AUP Library'!A850,'Updated Quanities'!F:I,4,0),R850))","v":1800000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A850,'Updated Quanities'!F:I,5,0),R850)=\"\",R850,IFERROR(VLOOKUP('AUP Library'!A850,'Updated Quanities'!F:I,5,0),R850))","v":1800000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A850,'Updated Quanities'!F:I,6,0),R850)=\"\",R850,IFERROR(VLOOKUP('AUP Library'!A850,'Updated Quanities'!F:I,6,0),R850))","v":1800000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A850,'Updated Quanities'!F:I,7,0),R850)=\"\",R850,IFERROR(VLOOKUP('AUP Library'!A850,'Updated Quanities'!F:I,7,0),R850))","v":1800000},1800000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A850,'Updated Quanities'!F:G,4,0),R850)","v":1800000}]
[]
[]
["Signs"]
["713-01.01","Class A Concrete (Foundation for Sign Supports)","CY",657.02,657.02,657.02,657.02,657.02,657.02,657.02,657.02,657.02,657.02,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A854,'Updated Quanities'!F:I,4,0),R854)=\"\",R854,IFERROR(VLOOKUP('AUP Library'!A854,'Updated Quanities'!F:I,4,0),R854))","v":657.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A854,'Updated Quanities'!F:I,5,0),R854)=\"\",R854,IFERROR(VLOOKUP('AUP Library'!A854,'Updated Quanities'!F:I,5,0),R854))","v":657.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A854,'Updated Quanities'!F:I,6,0),R854)=\"\",R854,IFERROR(VLOOKUP('AUP Library'!A854,'Updated Quanities'!F:I,6,0),R854))","v":657.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A854,'Updated Quanities'!F:I,7,0),R854)=\"\",R854,IFERROR(VLOOKUP('AUP Library'!A854,'Updated Quanities'!F:I,7,0),R854))","v":657.02},657.02,{"$f":"IFERROR(VLOOKUP('AUP Library'!A854,'Updated Quanities'!F:G,4,0),R854)","v":657.02}]
["713-01.02","Steel Bar Reinforcement (Foundation for Sign Supports)","LB",2.81,2.81,2.81,2.81,2.81,2.81,2.81,2.81,2.81,2.81,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A855,'Updated Quanities'!F:I,4,0),R855)=\"\",R855,IFERROR(VLOOKUP('AUP Library'!A855,'Updated Quanities'!F:I,4,0),R855))","v":2.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A855,'Updated Quanities'!F:I,5,0),R855)=\"\",R855,IFERROR(VLOOKUP('AUP Library'!A855,'Updated Quanities'!F:I,5,0),R855))","v":2.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A855,'Updated Quanities'!F:I,6,0),R855)=\"\",R855,IFERROR(VLOOKUP('AUP Library'!A855,'Updated Quanities'!F:I,6,0),R855))","v":2.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A855,'Updated Quanities'!F:I,7,0),R855)=\"\",R855,IFERROR(VLOOKUP('AUP Library'!A855,'Updated Quanities'!F:I,7,0),R855))","v":2.81},2.81,{"$f":"IFERROR(VLOOKUP('AUP Library'!A855,'Updated Quanities'!F:G,4,0),R855)","v":2.81}]
["713-02.04","Delineator (Mile Marker) & Steel Post","EA",149.13999999999999,149.13999999999999,149.13999999999999,149.13999999999999,149.13999999999999,149.13999999999999,149.13999999999999,149.13999999999999,149.13999999999999,149.13999999999999,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A856,'Updated Quanities'!F:I,4,0),R856)=\"\",R856,IFERROR(VLOOKUP('AUP Library'!A856,'Updated Quanities'!F:I,4,0),R856))","v":149.13999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A856,'Updated Quanities'!F:I,5,0),R856)=\"\",R856,IFERROR(VLOOKUP('AUP Library'!A856,'Updated Quanities'!F:I,5,0),R856))","v":149.13999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A856,'Updated Quanities'!F:I,6,0),R856)=\"\",R856,IFERROR(VLOOKUP('AUP Library'!A856,'Updated Quanities'!F:I,6,0),R856))","v":149.13999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A856,'Updated Quanities'!F:I,7,0),R856)=\"\",R856,IFERROR(VLOOKUP('AUP Library'!A856,'Updated Quanities'!F:I,7,0),R856))","v":149.13999999999999},149.13999999999999,{"$f":"IFERROR(VLOOKUP('AUP Library'!A856,'Updated Quanities'!F:G,4,0),R856)","v":149.13999999999999}]
["713-02.11","Removal of Existing Delineators","EA",8.85,8.85,8.85,8.85,8.85,8.85,8.85,8.85,8.85,8.85,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A857,'Updated Quanities'!F:I,4,0),R857)=\"\",R857,IFERROR(VLOOKUP('AUP Library'!A857,'Updated Quanities'!F:I,4,0),R857))","v":8.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A857,'Updated Quanities'!F:I,5,0),R857)=\"\",R857,IFERROR(VLOOKUP('AUP Library'!A857,'Updated Quanities'!F:I,5,0),R857))","v":8.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A857,'Updated Quanities'!F:I,6,0),R857)=\"\",R857,IFERROR(VLOOKUP('AUP Library'!A857,'Updated Quanities'!F:I,6,0),R857))","v":8.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A857,'Updated Quanities'!F:I,7,0),R857)=\"\",R857,IFERROR(VLOOKUP('AUP Library'!A857,'Updated Quanities'!F:I,7,0),R857))","v":8.85},8.85,{"$f":"IFERROR(VLOOKUP('AUP Library'!A857,'Updated Quanities'!F:G,4,0),R857)","v":8.85}]
["713-02.14","Flexible Delineator (White)","EA",33.369999999999997,33.369999999999997,33.369999999999997,33.369999999999997,33.369999999999997,33.369999999999997,33.369999999999997,33.369999999999997,33.369999999999997,33.369999999999997,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A858,'Updated Quanities'!F:I,4,0),R858)=\"\",R858,IFERROR(VLOOKUP('AUP Library'!A858,'Updated Quanities'!F:I,4,0),R858))","v":33.369999999999997},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A858,'Updated Quanities'!F:I,5,0),R858)=\"\",R858,IFERROR(VLOOKUP('AUP Library'!A858,'Updated Quanities'!F:I,5,0),R858))","v":33.369999999999997},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A858,'Updated Quanities'!F:I,6,0),R858)=\"\",R858,IFERROR(VLOOKUP('AUP Library'!A858,'Updated Quanities'!F:I,6,0),R858))","v":33.369999999999997},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A858,'Updated Quanities'!F:I,7,0),R858)=\"\",R858,IFERROR(VLOOKUP('AUP Library'!A858,'Updated Quanities'!F:I,7,0),R858))","v":33.369999999999997},33.369999999999997,{"$f":"IFERROR(VLOOKUP('AUP Library'!A858,'Updated Quanities'!F:G,4,0),R858)","v":33.369999999999997}]
["713-02.15","Flexible Delineator (Yellow)","EA",31.91,31.91,31.91,31.91,31.91,31.91,31.91,31.91,31.91,31.91,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A859,'Updated Quanities'!F:I,4,0),R859)=\"\",R859,IFERROR(VLOOKUP('AUP Library'!A859,'Updated Quanities'!F:I,4,0),R859))","v":31.91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A859,'Updated Quanities'!F:I,5,0),R859)=\"\",R859,IFERROR(VLOOKUP('AUP Library'!A859,'Updated Quanities'!F:I,5,0),R859))","v":31.91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A859,'Updated Quanities'!F:I,6,0),R859)=\"\",R859,IFERROR(VLOOKUP('AUP Library'!A859,'Updated Quanities'!F:I,6,0),R859))","v":31.91},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A859,'Updated Quanities'!F:I,7,0),R859)=\"\",R859,IFERROR(VLOOKUP('AUP Library'!A859,'Updated Quanities'!F:I,7,0),R859))","v":31.91},31.91,{"$f":"IFERROR(VLOOKUP('AUP Library'!A859,'Updated Quanities'!F:G,4,0),R859)","v":31.91}]
["713-02.16","Flexible Type II Object Marker","EA",33,33,33,33,33,33,33,33,33,33,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A860,'Updated Quanities'!F:I,4,0),R860)=\"\",R860,IFERROR(VLOOKUP('AUP Library'!A860,'Updated Quanities'!F:I,4,0),R860))","v":33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A860,'Updated Quanities'!F:I,5,0),R860)=\"\",R860,IFERROR(VLOOKUP('AUP Library'!A860,'Updated Quanities'!F:I,5,0),R860))","v":33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A860,'Updated Quanities'!F:I,6,0),R860)=\"\",R860,IFERROR(VLOOKUP('AUP Library'!A860,'Updated Quanities'!F:I,6,0),R860))","v":33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A860,'Updated Quanities'!F:I,7,0),R860)=\"\",R860,IFERROR(VLOOKUP('AUP Library'!A860,'Updated Quanities'!F:I,7,0),R860))","v":33},33,{"$f":"IFERROR(VLOOKUP('AUP Library'!A860,'Updated Quanities'!F:G,4,0),R860)","v":33}]
["713-02.20","Roadside Obstacle Delineation","SF",17.899999999999999,17.899999999999999,17.899999999999999,17.899999999999999,17.899999999999999,17.899999999999999,17.899999999999999,17.899999999999999,17.899999999999999,17.899999999999999,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A861,'Updated Quanities'!F:I,4,0),R861)=\"\",R861,IFERROR(VLOOKUP('AUP Library'!A861,'Updated Quanities'!F:I,4,0),R861))","v":17.899999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A861,'Updated Quanities'!F:I,5,0),R861)=\"\",R861,IFERROR(VLOOKUP('AUP Library'!A861,'Updated Quanities'!F:I,5,0),R861))","v":17.899999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A861,'Updated Quanities'!F:I,6,0),R861)=\"\",R861,IFERROR(VLOOKUP('AUP Library'!A861,'Updated Quanities'!F:I,6,0),R861))","v":17.899999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A861,'Updated Quanities'!F:I,7,0),R861)=\"\",R861,IFERROR(VLOOKUP('AUP Library'!A861,'Updated Quanities'!F:I,7,0),R861))","v":17.899999999999999},17.899999999999999,{"$f":"IFERROR(VLOOKUP('AUP Library'!A861,'Updated Quanities'!F:G,4,0),R861)","v":17.899999999999999}]
["713-02.21","Sign Post Delineation Enhancement","LF",6.2,6.2,6.2,6.2,6.2,6.2,6.2,6.2,6.2,6.2,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A862,'Updated Quanities'!F:I,4,0),R862)=\"\",R862,IFERROR(VLOOKUP('AUP Library'!A862,'Updated Quanities'!F:I,4,0),R862))","v":6.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A862,'Updated Quanities'!F:I,5,0),R862)=\"\",R862,IFERROR(VLOOKUP('AUP Library'!A862,'Updated Quanities'!F:I,5,0),R862))","v":6.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A862,'Updated Quanities'!F:I,6,0),R862)=\"\",R862,IFERROR(VLOOKUP('AUP Library'!A862,'Updated Quanities'!F:I,6,0),R862))","v":6.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A862,'Updated Quanities'!F:I,7,0),R862)=\"\",R862,IFERROR(VLOOKUP('AUP Library'!A862,'Updated Quanities'!F:I,7,0),R862))","v":6.2},6.2,{"$f":"IFERROR(VLOOKUP('AUP Library'!A862,'Updated Quanities'!F:G,4,0),R862)","v":6.2}]
["713-02.22","Barrier Wall Delineation Enhancement","LF",8.69,8.69,8.69,8.69,8.69,8.69,8.69,8.69,8.69,8.69,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A863,'Updated Quanities'!F:I,4,0),R863)=\"\",R863,IFERROR(VLOOKUP('AUP Library'!A863,'Updated Quanities'!F:I,4,0),R863))","v":8.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A863,'Updated Quanities'!F:I,5,0),R863)=\"\",R863,IFERROR(VLOOKUP('AUP Library'!A863,'Updated Quanities'!F:I,5,0),R863))","v":8.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A863,'Updated Quanities'!F:I,6,0),R863)=\"\",R863,IFERROR(VLOOKUP('AUP Library'!A863,'Updated Quanities'!F:I,6,0),R863))","v":8.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A863,'Updated Quanities'!F:I,7,0),R863)=\"\",R863,IFERROR(VLOOKUP('AUP Library'!A863,'Updated Quanities'!F:I,7,0),R863))","v":8.69},8.69,{"$f":"IFERROR(VLOOKUP('AUP Library'!A863,'Updated Quanities'!F:G,4,0),R863)","v":8.69}]
["713-02.26","Concrete Barrier/Parapet Delineator","EA",10.48,10.48,10.48,10.48,10.48,10.48,10.48,10.48,10.48,10.48,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A864,'Updated Quanities'!F:I,4,0),R864)=\"\",R864,IFERROR(VLOOKUP('AUP Library'!A864,'Updated Quanities'!F:I,4,0),R864))","v":10.48},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A864,'Updated Quanities'!F:I,5,0),R864)=\"\",R864,IFERROR(VLOOKUP('AUP Library'!A864,'Updated Quanities'!F:I,5,0),R864))","v":10.48},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A864,'Updated Quanities'!F:I,6,0),R864)=\"\",R864,IFERROR(VLOOKUP('AUP Library'!A864,'Updated Quanities'!F:I,6,0),R864))","v":10.48},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A864,'Updated Quanities'!F:I,7,0),R864)=\"\",R864,IFERROR(VLOOKUP('AUP Library'!A864,'Updated Quanities'!F:I,7,0),R864))","v":10.48},10.48,{"$f":"IFERROR(VLOOKUP('AUP Library'!A864,'Updated Quanities'!F:G,4,0),R864)","v":10.48}]
["713-02.33","Flexible Delineator (Red)","EA",34.5,34.5,34.5,34.5,34.5,34.5,34.5,34.5,34.5,34.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A865,'Updated Quanities'!F:I,4,0),R865)=\"\",R865,IFERROR(VLOOKUP('AUP Library'!A865,'Updated Quanities'!F:I,4,0),R865))","v":34.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A865,'Updated Quanities'!F:I,5,0),R865)=\"\",R865,IFERROR(VLOOKUP('AUP Library'!A865,'Updated Quanities'!F:I,5,0),R865))","v":34.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A865,'Updated Quanities'!F:I,6,0),R865)=\"\",R865,IFERROR(VLOOKUP('AUP Library'!A865,'Updated Quanities'!F:I,6,0),R865))","v":34.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A865,'Updated Quanities'!F:I,7,0),R865)=\"\",R865,IFERROR(VLOOKUP('AUP Library'!A865,'Updated Quanities'!F:I,7,0),R865))","v":34.5},34.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A865,'Updated Quanities'!F:G,4,0),R865)","v":34.5}]
["713-02.34","Delineators (All)","EA",12.75,12.75,12.75,12.75,12.75,12.75,12.75,12.75,12.75,12.75,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A866,'Updated Quanities'!F:I,4,0),R866)=\"\",R866,IFERROR(VLOOKUP('AUP Library'!A866,'Updated Quanities'!F:I,4,0),R866))","v":12.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A866,'Updated Quanities'!F:I,5,0),R866)=\"\",R866,IFERROR(VLOOKUP('AUP Library'!A866,'Updated Quanities'!F:I,5,0),R866))","v":12.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A866,'Updated Quanities'!F:I,6,0),R866)=\"\",R866,IFERROR(VLOOKUP('AUP Library'!A866,'Updated Quanities'!F:I,6,0),R866))","v":12.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A866,'Updated Quanities'!F:I,7,0),R866)=\"\",R866,IFERROR(VLOOKUP('AUP Library'!A866,'Updated Quanities'!F:I,7,0),R866))","v":12.75},12.75,{"$f":"IFERROR(VLOOKUP('AUP Library'!A866,'Updated Quanities'!F:G,4,0),R866)","v":12.75}]
["713-02.35","Barrier Delineation Sheeting","LF",8.89,8.89,8.89,8.89,8.89,8.89,8.89,8.89,8.89,8.89,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A867,'Updated Quanities'!F:I,4,0),R867)=\"\",R867,IFERROR(VLOOKUP('AUP Library'!A867,'Updated Quanities'!F:I,4,0),R867))","v":8.89},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A867,'Updated Quanities'!F:I,5,0),R867)=\"\",R867,IFERROR(VLOOKUP('AUP Library'!A867,'Updated Quanities'!F:I,5,0),R867))","v":8.89},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A867,'Updated Quanities'!F:I,6,0),R867)=\"\",R867,IFERROR(VLOOKUP('AUP Library'!A867,'Updated Quanities'!F:I,6,0),R867))","v":8.89},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A867,'Updated Quanities'!F:I,7,0),R867)=\"\",R867,IFERROR(VLOOKUP('AUP Library'!A867,'Updated Quanities'!F:I,7,0),R867))","v":8.89},8.89,{"$f":"IFERROR(VLOOKUP('AUP Library'!A867,'Updated Quanities'!F:G,4,0),R867)","v":8.89}]
["713-04.02","Steel I-Beams & W-F Beams-Sign Supports","LB",4.59,4.59,4.59,4.59,4.59,4.59,4.59,4.59,4.59,4.59,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A868,'Updated Quanities'!F:I,4,0),R868)=\"\",R868,IFERROR(VLOOKUP('AUP Library'!A868,'Updated Quanities'!F:I,4,0),R868))","v":4.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A868,'Updated Quanities'!F:I,5,0),R868)=\"\",R868,IFERROR(VLOOKUP('AUP Library'!A868,'Updated Quanities'!F:I,5,0),R868))","v":4.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A868,'Updated Quanities'!F:I,6,0),R868)=\"\",R868,IFERROR(VLOOKUP('AUP Library'!A868,'Updated Quanities'!F:I,6,0),R868))","v":4.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A868,'Updated Quanities'!F:I,7,0),R868)=\"\",R868,IFERROR(VLOOKUP('AUP Library'!A868,'Updated Quanities'!F:I,7,0),R868))","v":4.59},4.59,{"$f":"IFERROR(VLOOKUP('AUP Library'!A868,'Updated Quanities'!F:G,4,0),R868)","v":4.59}]
["713-05","Steel Hollow Sq Pst (BKWY) Sign Supports","LB",4.68,4.68,4.68,4.68,4.68,4.68,4.68,4.68,4.68,4.68,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A869,'Updated Quanities'!F:I,4,0),R869)=\"\",R869,IFERROR(VLOOKUP('AUP Library'!A869,'Updated Quanities'!F:I,4,0),R869))","v":4.68},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A869,'Updated Quanities'!F:I,5,0),R869)=\"\",R869,IFERROR(VLOOKUP('AUP Library'!A869,'Updated Quanities'!F:I,5,0),R869))","v":4.68},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A869,'Updated Quanities'!F:I,6,0),R869)=\"\",R869,IFERROR(VLOOKUP('AUP Library'!A869,'Updated Quanities'!F:I,6,0),R869))","v":4.68},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A869,'Updated Quanities'!F:I,7,0),R869)=\"\",R869,IFERROR(VLOOKUP('AUP Library'!A869,'Updated Quanities'!F:I,7,0),R869))","v":4.68},4.68,{"$f":"IFERROR(VLOOKUP('AUP Library'!A869,'Updated Quanities'!F:G,4,0),R869)","v":4.68}]
["713-06","Steel I-Beams & W-F-BMs(BKWY) Sign Support","LB",4.2699999999999996,4.2699999999999996,4.2699999999999996,4.2699999999999996,4.2699999999999996,4.2699999999999996,4.2699999999999996,4.2699999999999996,4.2699999999999996,4.2699999999999996,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A870,'Updated Quanities'!F:I,4,0),R870)=\"\",R870,IFERROR(VLOOKUP('AUP Library'!A870,'Updated Quanities'!F:I,4,0),R870))","v":4.2699999999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A870,'Updated Quanities'!F:I,5,0),R870)=\"\",R870,IFERROR(VLOOKUP('AUP Library'!A870,'Updated Quanities'!F:I,5,0),R870))","v":4.2699999999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A870,'Updated Quanities'!F:I,6,0),R870)=\"\",R870,IFERROR(VLOOKUP('AUP Library'!A870,'Updated Quanities'!F:I,6,0),R870))","v":4.2699999999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A870,'Updated Quanities'!F:I,7,0),R870)=\"\",R870,IFERROR(VLOOKUP('AUP Library'!A870,'Updated Quanities'!F:I,7,0),R870))","v":4.2699999999999996},4.2699999999999996,{"$f":"IFERROR(VLOOKUP('AUP Library'!A870,'Updated Quanities'!F:G,4,0),R870)","v":4.2699999999999996}]
["713-06.01","Steel I-BMs & WF-BMs (Brksafe) Sign Support","LB",5.5,5.5,5.5,5.5,5.5,5.5,5.5,5.5,5.5,5.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A871,'Updated Quanities'!F:I,4,0),R871)=\"\",R871,IFERROR(VLOOKUP('AUP Library'!A871,'Updated Quanities'!F:I,4,0),R871))","v":5.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A871,'Updated Quanities'!F:I,5,0),R871)=\"\",R871,IFERROR(VLOOKUP('AUP Library'!A871,'Updated Quanities'!F:I,5,0),R871))","v":5.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A871,'Updated Quanities'!F:I,6,0),R871)=\"\",R871,IFERROR(VLOOKUP('AUP Library'!A871,'Updated Quanities'!F:I,6,0),R871))","v":5.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A871,'Updated Quanities'!F:I,7,0),R871)=\"\",R871,IFERROR(VLOOKUP('AUP Library'!A871,'Updated Quanities'!F:I,7,0),R871))","v":5.5},5.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A871,'Updated Quanities'!F:G,4,0),R871)","v":5.5}]
["713-09.01","Steel Overhead Sign Structure","EA",80975.759999999995,80975.759999999995,80975.759999999995,80975.759999999995,80975.759999999995,80975.759999999995,80975.759999999995,80975.759999999995,80975.759999999995,80975.759999999995,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A872,'Updated Quanities'!F:I,4,0),R872)=\"\",R872,IFERROR(VLOOKUP('AUP Library'!A872,'Updated Quanities'!F:I,4,0),R872))","v":80975.759999999995},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A872,'Updated Quanities'!F:I,5,0),R872)=\"\",R872,IFERROR(VLOOKUP('AUP Library'!A872,'Updated Quanities'!F:I,5,0),R872))","v":80975.759999999995},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A872,'Updated Quanities'!F:I,6,0),R872)=\"\",R872,IFERROR(VLOOKUP('AUP Library'!A872,'Updated Quanities'!F:I,6,0),R872))","v":80975.759999999995},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A872,'Updated Quanities'!F:I,7,0),R872)=\"\",R872,IFERROR(VLOOKUP('AUP Library'!A872,'Updated Quanities'!F:I,7,0),R872))","v":80975.759999999995},80975.759999999995,{"$f":"IFERROR(VLOOKUP('AUP Library'!A872,'Updated Quanities'!F:G,4,0),R872)","v":80975.759999999995}]
["713-09.02","Steel Overhead Sign Structure","EA",78933.69,78933.69,78933.69,78933.69,78933.69,78933.69,78933.69,78933.69,78933.69,78933.69,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A873,'Updated Quanities'!F:I,4,0),R873)=\"\",R873,IFERROR(VLOOKUP('AUP Library'!A873,'Updated Quanities'!F:I,4,0),R873))","v":78933.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A873,'Updated Quanities'!F:I,5,0),R873)=\"\",R873,IFERROR(VLOOKUP('AUP Library'!A873,'Updated Quanities'!F:I,5,0),R873))","v":78933.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A873,'Updated Quanities'!F:I,6,0),R873)=\"\",R873,IFERROR(VLOOKUP('AUP Library'!A873,'Updated Quanities'!F:I,6,0),R873))","v":78933.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A873,'Updated Quanities'!F:I,7,0),R873)=\"\",R873,IFERROR(VLOOKUP('AUP Library'!A873,'Updated Quanities'!F:I,7,0),R873))","v":78933.69},78933.69,{"$f":"IFERROR(VLOOKUP('AUP Library'!A873,'Updated Quanities'!F:G,4,0),R873)","v":78933.69}]
["713-09.03","Steel Overhead Sign Structure","EA",74881.67,74881.67,74881.67,74881.67,74881.67,74881.67,74881.67,74881.67,74881.67,74881.67,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A874,'Updated Quanities'!F:I,4,0),R874)=\"\",R874,IFERROR(VLOOKUP('AUP Library'!A874,'Updated Quanities'!F:I,4,0),R874))","v":74881.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A874,'Updated Quanities'!F:I,5,0),R874)=\"\",R874,IFERROR(VLOOKUP('AUP Library'!A874,'Updated Quanities'!F:I,5,0),R874))","v":74881.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A874,'Updated Quanities'!F:I,6,0),R874)=\"\",R874,IFERROR(VLOOKUP('AUP Library'!A874,'Updated Quanities'!F:I,6,0),R874))","v":74881.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A874,'Updated Quanities'!F:I,7,0),R874)=\"\",R874,IFERROR(VLOOKUP('AUP Library'!A874,'Updated Quanities'!F:I,7,0),R874))","v":74881.67},74881.67,{"$f":"IFERROR(VLOOKUP('AUP Library'!A874,'Updated Quanities'!F:G,4,0),R874)","v":74881.67}]
["713-09.04","Steel Overhead Sign Structure","EA",87372.5,87372.5,87372.5,87372.5,87372.5,87372.5,87372.5,87372.5,87372.5,87372.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A875,'Updated Quanities'!F:I,4,0),R875)=\"\",R875,IFERROR(VLOOKUP('AUP Library'!A875,'Updated Quanities'!F:I,4,0),R875))","v":87372.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A875,'Updated Quanities'!F:I,5,0),R875)=\"\",R875,IFERROR(VLOOKUP('AUP Library'!A875,'Updated Quanities'!F:I,5,0),R875))","v":87372.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A875,'Updated Quanities'!F:I,6,0),R875)=\"\",R875,IFERROR(VLOOKUP('AUP Library'!A875,'Updated Quanities'!F:I,6,0),R875))","v":87372.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A875,'Updated Quanities'!F:I,7,0),R875)=\"\",R875,IFERROR(VLOOKUP('AUP Library'!A875,'Updated Quanities'!F:I,7,0),R875))","v":87372.5},87372.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A875,'Updated Quanities'!F:G,4,0),R875)","v":87372.5}]
["713-09.05","Steel Overhead Sign Structure","EA",92012.5,92012.5,92012.5,92012.5,92012.5,92012.5,92012.5,92012.5,92012.5,92012.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A876,'Updated Quanities'!F:I,4,0),R876)=\"\",R876,IFERROR(VLOOKUP('AUP Library'!A876,'Updated Quanities'!F:I,4,0),R876))","v":92012.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A876,'Updated Quanities'!F:I,5,0),R876)=\"\",R876,IFERROR(VLOOKUP('AUP Library'!A876,'Updated Quanities'!F:I,5,0),R876))","v":92012.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A876,'Updated Quanities'!F:I,6,0),R876)=\"\",R876,IFERROR(VLOOKUP('AUP Library'!A876,'Updated Quanities'!F:I,6,0),R876))","v":92012.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A876,'Updated Quanities'!F:I,7,0),R876)=\"\",R876,IFERROR(VLOOKUP('AUP Library'!A876,'Updated Quanities'!F:I,7,0),R876))","v":92012.5},92012.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A876,'Updated Quanities'!F:G,4,0),R876)","v":92012.5}]
["713-09.06","Steel Overhead Sign Structure","EA",133120,133120,133120,133120,133120,133120,133120,133120,133120,133120,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A877,'Updated Quanities'!F:I,4,0),R877)=\"\",R877,IFERROR(VLOOKUP('AUP Library'!A877,'Updated Quanities'!F:I,4,0),R877))","v":133120},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A877,'Updated Quanities'!F:I,5,0),R877)=\"\",R877,IFERROR(VLOOKUP('AUP Library'!A877,'Updated Quanities'!F:I,5,0),R877))","v":133120},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A877,'Updated Quanities'!F:I,6,0),R877)=\"\",R877,IFERROR(VLOOKUP('AUP Library'!A877,'Updated Quanities'!F:I,6,0),R877))","v":133120},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A877,'Updated Quanities'!F:I,7,0),R877)=\"\",R877,IFERROR(VLOOKUP('AUP Library'!A877,'Updated Quanities'!F:I,7,0),R877))","v":133120},133120,{"$f":"IFERROR(VLOOKUP('AUP Library'!A877,'Updated Quanities'!F:G,4,0),R877)","v":133120}]
["713-09.07","Steel Overhead Sign Structure","EA",128675,128675,128675,128675,128675,128675,128675,128675,128675,128675,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A878,'Updated Quanities'!F:I,4,0),R878)=\"\",R878,IFERROR(VLOOKUP('AUP Library'!A878,'Updated Quanities'!F:I,4,0),R878))","v":128675},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A878,'Updated Quanities'!F:I,5,0),R878)=\"\",R878,IFERROR(VLOOKUP('AUP Library'!A878,'Updated Quanities'!F:I,5,0),R878))","v":128675},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A878,'Updated Quanities'!F:I,6,0),R878)=\"\",R878,IFERROR(VLOOKUP('AUP Library'!A878,'Updated Quanities'!F:I,6,0),R878))","v":128675},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A878,'Updated Quanities'!F:I,7,0),R878)=\"\",R878,IFERROR(VLOOKUP('AUP Library'!A878,'Updated Quanities'!F:I,7,0),R878))","v":128675},128675,{"$f":"IFERROR(VLOOKUP('AUP Library'!A878,'Updated Quanities'!F:G,4,0),R878)","v":128675}]
["713-09.08","Steel Overhead Sign Structure","EA",158415,158415,158415,158415,158415,158415,158415,158415,158415,158415,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A879,'Updated Quanities'!F:I,4,0),R879)=\"\",R879,IFERROR(VLOOKUP('AUP Library'!A879,'Updated Quanities'!F:I,4,0),R879))","v":158415},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A879,'Updated Quanities'!F:I,5,0),R879)=\"\",R879,IFERROR(VLOOKUP('AUP Library'!A879,'Updated Quanities'!F:I,5,0),R879))","v":158415},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A879,'Updated Quanities'!F:I,6,0),R879)=\"\",R879,IFERROR(VLOOKUP('AUP Library'!A879,'Updated Quanities'!F:I,6,0),R879))","v":158415},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A879,'Updated Quanities'!F:I,7,0),R879)=\"\",R879,IFERROR(VLOOKUP('AUP Library'!A879,'Updated Quanities'!F:I,7,0),R879))","v":158415},158415,{"$f":"IFERROR(VLOOKUP('AUP Library'!A879,'Updated Quanities'!F:G,4,0),R879)","v":158415}]
["713-09.09","Steel Overhead Sign Structure","EA",165750,165750,165750,165750,165750,165750,165750,165750,165750,165750,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A880,'Updated Quanities'!F:I,4,0),R880)=\"\",R880,IFERROR(VLOOKUP('AUP Library'!A880,'Updated Quanities'!F:I,4,0),R880))","v":165750},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A880,'Updated Quanities'!F:I,5,0),R880)=\"\",R880,IFERROR(VLOOKUP('AUP Library'!A880,'Updated Quanities'!F:I,5,0),R880))","v":165750},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A880,'Updated Quanities'!F:I,6,0),R880)=\"\",R880,IFERROR(VLOOKUP('AUP Library'!A880,'Updated Quanities'!F:I,6,0),R880))","v":165750},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A880,'Updated Quanities'!F:I,7,0),R880)=\"\",R880,IFERROR(VLOOKUP('AUP Library'!A880,'Updated Quanities'!F:I,7,0),R880))","v":165750},165750,{"$f":"IFERROR(VLOOKUP('AUP Library'!A880,'Updated Quanities'!F:G,4,0),R880)","v":165750}]
["713-09.10","Steel Overhead Sign Structure","EA",195515,195515,195515,195515,195515,195515,195515,195515,195515,195515,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A881,'Updated Quanities'!F:I,4,0),R881)=\"\",R881,IFERROR(VLOOKUP('AUP Library'!A881,'Updated Quanities'!F:I,4,0),R881))","v":195515},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A881,'Updated Quanities'!F:I,5,0),R881)=\"\",R881,IFERROR(VLOOKUP('AUP Library'!A881,'Updated Quanities'!F:I,5,0),R881))","v":195515},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A881,'Updated Quanities'!F:I,6,0),R881)=\"\",R881,IFERROR(VLOOKUP('AUP Library'!A881,'Updated Quanities'!F:I,6,0),R881))","v":195515},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A881,'Updated Quanities'!F:I,7,0),R881)=\"\",R881,IFERROR(VLOOKUP('AUP Library'!A881,'Updated Quanities'!F:I,7,0),R881))","v":195515},195515,{"$f":"IFERROR(VLOOKUP('AUP Library'!A881,'Updated Quanities'!F:G,4,0),R881)","v":195515}]
["713-09.11","Steel Overhead Sign Structure","EA",92625,92625,92625,92625,92625,92625,92625,92625,92625,92625,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A882,'Updated Quanities'!F:I,4,0),R882)=\"\",R882,IFERROR(VLOOKUP('AUP Library'!A882,'Updated Quanities'!F:I,4,0),R882))","v":92625},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A882,'Updated Quanities'!F:I,5,0),R882)=\"\",R882,IFERROR(VLOOKUP('AUP Library'!A882,'Updated Quanities'!F:I,5,0),R882))","v":92625},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A882,'Updated Quanities'!F:I,6,0),R882)=\"\",R882,IFERROR(VLOOKUP('AUP Library'!A882,'Updated Quanities'!F:I,6,0),R882))","v":92625},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A882,'Updated Quanities'!F:I,7,0),R882)=\"\",R882,IFERROR(VLOOKUP('AUP Library'!A882,'Updated Quanities'!F:I,7,0),R882))","v":92625},92625,{"$f":"IFERROR(VLOOKUP('AUP Library'!A882,'Updated Quanities'!F:G,4,0),R882)","v":92625}]
["713-09.12","Steel Overhead Sign Structure","EA",93250,93250,93250,93250,93250,93250,93250,93250,93250,93250,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A883,'Updated Quanities'!F:I,4,0),R883)=\"\",R883,IFERROR(VLOOKUP('AUP Library'!A883,'Updated Quanities'!F:I,4,0),R883))","v":93250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A883,'Updated Quanities'!F:I,5,0),R883)=\"\",R883,IFERROR(VLOOKUP('AUP Library'!A883,'Updated Quanities'!F:I,5,0),R883))","v":93250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A883,'Updated Quanities'!F:I,6,0),R883)=\"\",R883,IFERROR(VLOOKUP('AUP Library'!A883,'Updated Quanities'!F:I,6,0),R883))","v":93250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A883,'Updated Quanities'!F:I,7,0),R883)=\"\",R883,IFERROR(VLOOKUP('AUP Library'!A883,'Updated Quanities'!F:I,7,0),R883))","v":93250},93250,{"$f":"IFERROR(VLOOKUP('AUP Library'!A883,'Updated Quanities'!F:G,4,0),R883)","v":93250}]
["713-09.13","Steel Overhead Sign Structure","EA",91250,91250,91250,91250,91250,91250,91250,91250,91250,91250,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A884,'Updated Quanities'!F:I,4,0),R884)=\"\",R884,IFERROR(VLOOKUP('AUP Library'!A884,'Updated Quanities'!F:I,4,0),R884))","v":91250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A884,'Updated Quanities'!F:I,5,0),R884)=\"\",R884,IFERROR(VLOOKUP('AUP Library'!A884,'Updated Quanities'!F:I,5,0),R884))","v":91250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A884,'Updated Quanities'!F:I,6,0),R884)=\"\",R884,IFERROR(VLOOKUP('AUP Library'!A884,'Updated Quanities'!F:I,6,0),R884))","v":91250},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A884,'Updated Quanities'!F:I,7,0),R884)=\"\",R884,IFERROR(VLOOKUP('AUP Library'!A884,'Updated Quanities'!F:I,7,0),R884))","v":91250},91250,{"$f":"IFERROR(VLOOKUP('AUP Library'!A884,'Updated Quanities'!F:G,4,0),R884)","v":91250}]
["713-09.14","Steel Overhead Sign Structure","EA",77000,77000,77000,77000,77000,77000,77000,77000,77000,77000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A885,'Updated Quanities'!F:I,4,0),R885)=\"\",R885,IFERROR(VLOOKUP('AUP Library'!A885,'Updated Quanities'!F:I,4,0),R885))","v":77000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A885,'Updated Quanities'!F:I,5,0),R885)=\"\",R885,IFERROR(VLOOKUP('AUP Library'!A885,'Updated Quanities'!F:I,5,0),R885))","v":77000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A885,'Updated Quanities'!F:I,6,0),R885)=\"\",R885,IFERROR(VLOOKUP('AUP Library'!A885,'Updated Quanities'!F:I,6,0),R885))","v":77000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A885,'Updated Quanities'!F:I,7,0),R885)=\"\",R885,IFERROR(VLOOKUP('AUP Library'!A885,'Updated Quanities'!F:I,7,0),R885))","v":77000},77000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A885,'Updated Quanities'!F:G,4,0),R885)","v":77000}]
["713-09.15","Steel Overhead Sign Structure","EA",78775,78775,78775,78775,78775,78775,78775,78775,78775,78775,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A886,'Updated Quanities'!F:I,4,0),R886)=\"\",R886,IFERROR(VLOOKUP('AUP Library'!A886,'Updated Quanities'!F:I,4,0),R886))","v":78775},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A886,'Updated Quanities'!F:I,5,0),R886)=\"\",R886,IFERROR(VLOOKUP('AUP Library'!A886,'Updated Quanities'!F:I,5,0),R886))","v":78775},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A886,'Updated Quanities'!F:I,6,0),R886)=\"\",R886,IFERROR(VLOOKUP('AUP Library'!A886,'Updated Quanities'!F:I,6,0),R886))","v":78775},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A886,'Updated Quanities'!F:I,7,0),R886)=\"\",R886,IFERROR(VLOOKUP('AUP Library'!A886,'Updated Quanities'!F:I,7,0),R886))","v":78775},78775,{"$f":"IFERROR(VLOOKUP('AUP Library'!A886,'Updated Quanities'!F:G,4,0),R886)","v":78775}]
["713-09.16","Steel Overhead Sign Structure","EA",96000,96000,96000,96000,96000,96000,96000,96000,96000,96000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A887,'Updated Quanities'!F:I,4,0),R887)=\"\",R887,IFERROR(VLOOKUP('AUP Library'!A887,'Updated Quanities'!F:I,4,0),R887))","v":96000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A887,'Updated Quanities'!F:I,5,0),R887)=\"\",R887,IFERROR(VLOOKUP('AUP Library'!A887,'Updated Quanities'!F:I,5,0),R887))","v":96000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A887,'Updated Quanities'!F:I,6,0),R887)=\"\",R887,IFERROR(VLOOKUP('AUP Library'!A887,'Updated Quanities'!F:I,6,0),R887))","v":96000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A887,'Updated Quanities'!F:I,7,0),R887)=\"\",R887,IFERROR(VLOOKUP('AUP Library'!A887,'Updated Quanities'!F:I,7,0),R887))","v":96000},96000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A887,'Updated Quanities'!F:G,4,0),R887)","v":96000}]
["713-09.17","Steel Overhead Sign Structure","EA",96000,96000,96000,96000,96000,96000,96000,96000,96000,96000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A888,'Updated Quanities'!F:I,4,0),R888)=\"\",R888,IFERROR(VLOOKUP('AUP Library'!A888,'Updated Quanities'!F:I,4,0),R888))","v":96000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A888,'Updated Quanities'!F:I,5,0),R888)=\"\",R888,IFERROR(VLOOKUP('AUP Library'!A888,'Updated Quanities'!F:I,5,0),R888))","v":96000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A888,'Updated Quanities'!F:I,6,0),R888)=\"\",R888,IFERROR(VLOOKUP('AUP Library'!A888,'Updated Quanities'!F:I,6,0),R888))","v":96000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A888,'Updated Quanities'!F:I,7,0),R888)=\"\",R888,IFERROR(VLOOKUP('AUP Library'!A888,'Updated Quanities'!F:I,7,0),R888))","v":96000},96000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A888,'Updated Quanities'!F:G,4,0),R888)","v":96000}]
["713-09.18","Steel Overhead Sign Structure","EA",98775,98775,98775,98775,98775,98775,98775,98775,98775,98775,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A889,'Updated Quanities'!F:I,4,0),R889)=\"\",R889,IFERROR(VLOOKUP('AUP Library'!A889,'Updated Quanities'!F:I,4,0),R889))","v":98775},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A889,'Updated Quanities'!F:I,5,0),R889)=\"\",R889,IFERROR(VLOOKUP('AUP Library'!A889,'Updated Quanities'!F:I,5,0),R889))","v":98775},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A889,'Updated Quanities'!F:I,6,0),R889)=\"\",R889,IFERROR(VLOOKUP('AUP Library'!A889,'Updated Quanities'!F:I,6,0),R889))","v":98775},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A889,'Updated Quanities'!F:I,7,0),R889)=\"\",R889,IFERROR(VLOOKUP('AUP Library'!A889,'Updated Quanities'!F:I,7,0),R889))","v":98775},98775,{"$f":"IFERROR(VLOOKUP('AUP Library'!A889,'Updated Quanities'!F:G,4,0),R889)","v":98775}]
["713-09.19","Steel Overhead Sign Structure","EA",98500,98500,98500,98500,98500,98500,98500,98500,98500,98500,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A890,'Updated Quanities'!F:I,4,0),R890)=\"\",R890,IFERROR(VLOOKUP('AUP Library'!A890,'Updated Quanities'!F:I,4,0),R890))","v":98500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A890,'Updated Quanities'!F:I,5,0),R890)=\"\",R890,IFERROR(VLOOKUP('AUP Library'!A890,'Updated Quanities'!F:I,5,0),R890))","v":98500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A890,'Updated Quanities'!F:I,6,0),R890)=\"\",R890,IFERROR(VLOOKUP('AUP Library'!A890,'Updated Quanities'!F:I,6,0),R890))","v":98500},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A890,'Updated Quanities'!F:I,7,0),R890)=\"\",R890,IFERROR(VLOOKUP('AUP Library'!A890,'Updated Quanities'!F:I,7,0),R890))","v":98500},98500,{"$f":"IFERROR(VLOOKUP('AUP Library'!A890,'Updated Quanities'!F:G,4,0),R890)","v":98500}]
["713-09.20","Steel Overhead Sign Structure","EA",67835,67835,67835,67835,67835,67835,67835,67835,67835,67835,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A891,'Updated Quanities'!F:I,4,0),R891)=\"\",R891,IFERROR(VLOOKUP('AUP Library'!A891,'Updated Quanities'!F:I,4,0),R891))","v":67835},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A891,'Updated Quanities'!F:I,5,0),R891)=\"\",R891,IFERROR(VLOOKUP('AUP Library'!A891,'Updated Quanities'!F:I,5,0),R891))","v":67835},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A891,'Updated Quanities'!F:I,6,0),R891)=\"\",R891,IFERROR(VLOOKUP('AUP Library'!A891,'Updated Quanities'!F:I,6,0),R891))","v":67835},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A891,'Updated Quanities'!F:I,7,0),R891)=\"\",R891,IFERROR(VLOOKUP('AUP Library'!A891,'Updated Quanities'!F:I,7,0),R891))","v":67835},67835,{"$f":"IFERROR(VLOOKUP('AUP Library'!A891,'Updated Quanities'!F:G,4,0),R891)","v":67835}]
["713-09.21","Steel Overhead Sign Structure","EA",101750,101750,101750,101750,101750,101750,101750,101750,101750,101750,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A892,'Updated Quanities'!F:I,4,0),R892)=\"\",R892,IFERROR(VLOOKUP('AUP Library'!A892,'Updated Quanities'!F:I,4,0),R892))","v":101750},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A892,'Updated Quanities'!F:I,5,0),R892)=\"\",R892,IFERROR(VLOOKUP('AUP Library'!A892,'Updated Quanities'!F:I,5,0),R892))","v":101750},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A892,'Updated Quanities'!F:I,6,0),R892)=\"\",R892,IFERROR(VLOOKUP('AUP Library'!A892,'Updated Quanities'!F:I,6,0),R892))","v":101750},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A892,'Updated Quanities'!F:I,7,0),R892)=\"\",R892,IFERROR(VLOOKUP('AUP Library'!A892,'Updated Quanities'!F:I,7,0),R892))","v":101750},101750,{"$f":"IFERROR(VLOOKUP('AUP Library'!A892,'Updated Quanities'!F:G,4,0),R892)","v":101750}]
["713-09.22","Steel Overhead Sign Structure","EA",74775,74775,74775,74775,74775,74775,74775,74775,74775,74775,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A893,'Updated Quanities'!F:I,4,0),R893)=\"\",R893,IFERROR(VLOOKUP('AUP Library'!A893,'Updated Quanities'!F:I,4,0),R893))","v":74775},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A893,'Updated Quanities'!F:I,5,0),R893)=\"\",R893,IFERROR(VLOOKUP('AUP Library'!A893,'Updated Quanities'!F:I,5,0),R893))","v":74775},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A893,'Updated Quanities'!F:I,6,0),R893)=\"\",R893,IFERROR(VLOOKUP('AUP Library'!A893,'Updated Quanities'!F:I,6,0),R893))","v":74775},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A893,'Updated Quanities'!F:I,7,0),R893)=\"\",R893,IFERROR(VLOOKUP('AUP Library'!A893,'Updated Quanities'!F:I,7,0),R893))","v":74775},74775,{"$f":"IFERROR(VLOOKUP('AUP Library'!A893,'Updated Quanities'!F:G,4,0),R893)","v":74775}]
["713-10.01","Steel Cntlv Sign Structure","EA",63140,63140,63140,63140,63140,63140,63140,63140,63140,63140,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A894,'Updated Quanities'!F:I,4,0),R894)=\"\",R894,IFERROR(VLOOKUP('AUP Library'!A894,'Updated Quanities'!F:I,4,0),R894))","v":63140},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A894,'Updated Quanities'!F:I,5,0),R894)=\"\",R894,IFERROR(VLOOKUP('AUP Library'!A894,'Updated Quanities'!F:I,5,0),R894))","v":63140},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A894,'Updated Quanities'!F:I,6,0),R894)=\"\",R894,IFERROR(VLOOKUP('AUP Library'!A894,'Updated Quanities'!F:I,6,0),R894))","v":63140},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A894,'Updated Quanities'!F:I,7,0),R894)=\"\",R894,IFERROR(VLOOKUP('AUP Library'!A894,'Updated Quanities'!F:I,7,0),R894))","v":63140},63140,{"$f":"IFERROR(VLOOKUP('AUP Library'!A894,'Updated Quanities'!F:G,4,0),R894)","v":63140}]
["713-11.01","\"U\" Section Steel Posts","LB",3.21,3.21,3.21,3.21,3.21,3.21,3.21,3.21,3.21,3.21,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A895,'Updated Quanities'!F:I,4,0),R895)=\"\",R895,IFERROR(VLOOKUP('AUP Library'!A895,'Updated Quanities'!F:I,4,0),R895))","v":3.21},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A895,'Updated Quanities'!F:I,5,0),R895)=\"\",R895,IFERROR(VLOOKUP('AUP Library'!A895,'Updated Quanities'!F:I,5,0),R895))","v":3.21},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A895,'Updated Quanities'!F:I,6,0),R895)=\"\",R895,IFERROR(VLOOKUP('AUP Library'!A895,'Updated Quanities'!F:I,6,0),R895))","v":3.21},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A895,'Updated Quanities'!F:I,7,0),R895)=\"\",R895,IFERROR(VLOOKUP('AUP Library'!A895,'Updated Quanities'!F:I,7,0),R895))","v":3.21},3.21,{"$f":"IFERROR(VLOOKUP('AUP Library'!A895,'Updated Quanities'!F:G,4,0),R895)","v":3.21}]
["713-11.02","Perforated/Knockout Square Tube Post","LB",4.2300000000000004,4.2300000000000004,4.2300000000000004,4.2300000000000004,4.2300000000000004,4.2300000000000004,4.2300000000000004,4.2300000000000004,4.2300000000000004,4.2300000000000004,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A896,'Updated Quanities'!F:I,4,0),R896)=\"\",R896,IFERROR(VLOOKUP('AUP Library'!A896,'Updated Quanities'!F:I,4,0),R896))","v":4.2300000000000004},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A896,'Updated Quanities'!F:I,5,0),R896)=\"\",R896,IFERROR(VLOOKUP('AUP Library'!A896,'Updated Quanities'!F:I,5,0),R896))","v":4.2300000000000004},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A896,'Updated Quanities'!F:I,6,0),R896)=\"\",R896,IFERROR(VLOOKUP('AUP Library'!A896,'Updated Quanities'!F:I,6,0),R896))","v":4.2300000000000004},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A896,'Updated Quanities'!F:I,7,0),R896)=\"\",R896,IFERROR(VLOOKUP('AUP Library'!A896,'Updated Quanities'!F:I,7,0),R896))","v":4.2300000000000004},4.2300000000000004,{"$f":"IFERROR(VLOOKUP('AUP Library'!A896,'Updated Quanities'!F:G,4,0),R896)","v":4.2300000000000004}]
["713-11.03","2 1/2\" Dia Round Steel Tube Post","LB",6.94,6.94,6.94,6.94,6.94,6.94,6.94,6.94,6.94,6.94,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A897,'Updated Quanities'!F:I,4,0),R897)=\"\",R897,IFERROR(VLOOKUP('AUP Library'!A897,'Updated Quanities'!F:I,4,0),R897))","v":6.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A897,'Updated Quanities'!F:I,5,0),R897)=\"\",R897,IFERROR(VLOOKUP('AUP Library'!A897,'Updated Quanities'!F:I,5,0),R897))","v":6.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A897,'Updated Quanities'!F:I,6,0),R897)=\"\",R897,IFERROR(VLOOKUP('AUP Library'!A897,'Updated Quanities'!F:I,6,0),R897))","v":6.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A897,'Updated Quanities'!F:I,7,0),R897)=\"\",R897,IFERROR(VLOOKUP('AUP Library'!A897,'Updated Quanities'!F:I,7,0),R897))","v":6.94},6.94,{"$f":"IFERROR(VLOOKUP('AUP Library'!A897,'Updated Quanities'!F:G,4,0),R897)","v":6.94}]
["713-11.05","Square Tube Sign Support","LB",4.75,4.75,4.75,4.75,4.75,4.75,4.75,4.75,4.75,4.75,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A898,'Updated Quanities'!F:I,4,0),R898)=\"\",R898,IFERROR(VLOOKUP('AUP Library'!A898,'Updated Quanities'!F:I,4,0),R898))","v":4.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A898,'Updated Quanities'!F:I,5,0),R898)=\"\",R898,IFERROR(VLOOKUP('AUP Library'!A898,'Updated Quanities'!F:I,5,0),R898))","v":4.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A898,'Updated Quanities'!F:I,6,0),R898)=\"\",R898,IFERROR(VLOOKUP('AUP Library'!A898,'Updated Quanities'!F:I,6,0),R898))","v":4.75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A898,'Updated Quanities'!F:I,7,0),R898)=\"\",R898,IFERROR(VLOOKUP('AUP Library'!A898,'Updated Quanities'!F:I,7,0),R898))","v":4.75},4.75,{"$f":"IFERROR(VLOOKUP('AUP Library'!A898,'Updated Quanities'!F:G,4,0),R898)","v":4.75}]
["713-11.21","P Post Slip Base","EA",340.56,340.56,340.56,340.56,340.56,340.56,340.56,340.56,340.56,340.56,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A899,'Updated Quanities'!F:I,4,0),R899)=\"\",R899,IFERROR(VLOOKUP('AUP Library'!A899,'Updated Quanities'!F:I,4,0),R899))","v":340.56},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A899,'Updated Quanities'!F:I,5,0),R899)=\"\",R899,IFERROR(VLOOKUP('AUP Library'!A899,'Updated Quanities'!F:I,5,0),R899))","v":340.56},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A899,'Updated Quanities'!F:I,6,0),R899)=\"\",R899,IFERROR(VLOOKUP('AUP Library'!A899,'Updated Quanities'!F:I,6,0),R899))","v":340.56},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A899,'Updated Quanities'!F:I,7,0),R899)=\"\",R899,IFERROR(VLOOKUP('AUP Library'!A899,'Updated Quanities'!F:I,7,0),R899))","v":340.56},340.56,{"$f":"IFERROR(VLOOKUP('AUP Library'!A899,'Updated Quanities'!F:G,4,0),R899)","v":340.56}]
["713-11.22","U Post Slip Base","EA",420.47,420.47,420.47,420.47,420.47,420.47,420.47,420.47,420.47,420.47,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A900,'Updated Quanities'!F:I,4,0),R900)=\"\",R900,IFERROR(VLOOKUP('AUP Library'!A900,'Updated Quanities'!F:I,4,0),R900))","v":420.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A900,'Updated Quanities'!F:I,5,0),R900)=\"\",R900,IFERROR(VLOOKUP('AUP Library'!A900,'Updated Quanities'!F:I,5,0),R900))","v":420.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A900,'Updated Quanities'!F:I,6,0),R900)=\"\",R900,IFERROR(VLOOKUP('AUP Library'!A900,'Updated Quanities'!F:I,6,0),R900))","v":420.47},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A900,'Updated Quanities'!F:I,7,0),R900)=\"\",R900,IFERROR(VLOOKUP('AUP Library'!A900,'Updated Quanities'!F:I,7,0),R900))","v":420.47},420.47,{"$f":"IFERROR(VLOOKUP('AUP Library'!A900,'Updated Quanities'!F:G,4,0),R900)","v":420.47}]
["713-11.23","Round Post Slip Base","EA",290.95,290.95,290.95,290.95,290.95,290.95,290.95,290.95,290.95,290.95,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A901,'Updated Quanities'!F:I,4,0),R901)=\"\",R901,IFERROR(VLOOKUP('AUP Library'!A901,'Updated Quanities'!F:I,4,0),R901))","v":290.95},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A901,'Updated Quanities'!F:I,5,0),R901)=\"\",R901,IFERROR(VLOOKUP('AUP Library'!A901,'Updated Quanities'!F:I,5,0),R901))","v":290.95},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A901,'Updated Quanities'!F:I,6,0),R901)=\"\",R901,IFERROR(VLOOKUP('AUP Library'!A901,'Updated Quanities'!F:I,6,0),R901))","v":290.95},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A901,'Updated Quanities'!F:I,7,0),R901)=\"\",R901,IFERROR(VLOOKUP('AUP Library'!A901,'Updated Quanities'!F:I,7,0),R901))","v":290.95},290.95,{"$f":"IFERROR(VLOOKUP('AUP Library'!A901,'Updated Quanities'!F:G,4,0),R901)","v":290.95}]
["713-13.02","Flat Sheet Aluminum Signs (0.080\" Thick)","SF",12.94,12.94,12.94,12.94,12.94,12.94,12.94,12.94,12.94,12.94,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A902,'Updated Quanities'!F:I,4,0),R902)=\"\",R902,IFERROR(VLOOKUP('AUP Library'!A902,'Updated Quanities'!F:I,4,0),R902))","v":12.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A902,'Updated Quanities'!F:I,5,0),R902)=\"\",R902,IFERROR(VLOOKUP('AUP Library'!A902,'Updated Quanities'!F:I,5,0),R902))","v":12.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A902,'Updated Quanities'!F:I,6,0),R902)=\"\",R902,IFERROR(VLOOKUP('AUP Library'!A902,'Updated Quanities'!F:I,6,0),R902))","v":12.94},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A902,'Updated Quanities'!F:I,7,0),R902)=\"\",R902,IFERROR(VLOOKUP('AUP Library'!A902,'Updated Quanities'!F:I,7,0),R902))","v":12.94},12.94,{"$f":"IFERROR(VLOOKUP('AUP Library'!A902,'Updated Quanities'!F:G,4,0),R902)","v":12.94}]
["713-13.03","Flat Sheet Aluminum Signs (0.100\" Thick)","SF",14.26,14.26,14.26,14.26,14.26,14.26,14.26,14.26,14.26,14.26,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A903,'Updated Quanities'!F:I,4,0),R903)=\"\",R903,IFERROR(VLOOKUP('AUP Library'!A903,'Updated Quanities'!F:I,4,0),R903))","v":14.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A903,'Updated Quanities'!F:I,5,0),R903)=\"\",R903,IFERROR(VLOOKUP('AUP Library'!A903,'Updated Quanities'!F:I,5,0),R903))","v":14.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A903,'Updated Quanities'!F:I,6,0),R903)=\"\",R903,IFERROR(VLOOKUP('AUP Library'!A903,'Updated Quanities'!F:I,6,0),R903))","v":14.26},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A903,'Updated Quanities'!F:I,7,0),R903)=\"\",R903,IFERROR(VLOOKUP('AUP Library'!A903,'Updated Quanities'!F:I,7,0),R903))","v":14.26},14.26,{"$f":"IFERROR(VLOOKUP('AUP Library'!A903,'Updated Quanities'!F:G,4,0),R903)","v":14.26}]
["713-13.04","Flat Sheet Aluminum Signs (0.125\" Thick)","SF",40,40,40,40,40,40,40,40,40,40,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A904,'Updated Quanities'!F:I,4,0),R904)=\"\",R904,IFERROR(VLOOKUP('AUP Library'!A904,'Updated Quanities'!F:I,4,0),R904))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A904,'Updated Quanities'!F:I,5,0),R904)=\"\",R904,IFERROR(VLOOKUP('AUP Library'!A904,'Updated Quanities'!F:I,5,0),R904))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A904,'Updated Quanities'!F:I,6,0),R904)=\"\",R904,IFERROR(VLOOKUP('AUP Library'!A904,'Updated Quanities'!F:I,6,0),R904))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A904,'Updated Quanities'!F:I,7,0),R904)=\"\",R904,IFERROR(VLOOKUP('AUP Library'!A904,'Updated Quanities'!F:I,7,0),R904))","v":40},40,{"$f":"IFERROR(VLOOKUP('AUP Library'!A904,'Updated Quanities'!F:G,4,0),R904)","v":40}]
["713-13.12","Flat Sheet Alum Signs Overlay (0.080\" Thick)","SF",21.19,21.19,21.19,21.19,21.19,21.19,21.19,21.19,21.19,21.19,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A905,'Updated Quanities'!F:I,4,0),R905)=\"\",R905,IFERROR(VLOOKUP('AUP Library'!A905,'Updated Quanities'!F:I,4,0),R905))","v":21.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A905,'Updated Quanities'!F:I,5,0),R905)=\"\",R905,IFERROR(VLOOKUP('AUP Library'!A905,'Updated Quanities'!F:I,5,0),R905))","v":21.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A905,'Updated Quanities'!F:I,6,0),R905)=\"\",R905,IFERROR(VLOOKUP('AUP Library'!A905,'Updated Quanities'!F:I,6,0),R905))","v":21.19},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A905,'Updated Quanities'!F:I,7,0),R905)=\"\",R905,IFERROR(VLOOKUP('AUP Library'!A905,'Updated Quanities'!F:I,7,0),R905))","v":21.19},21.19,{"$f":"IFERROR(VLOOKUP('AUP Library'!A905,'Updated Quanities'!F:G,4,0),R905)","v":21.19}]
["713-13.14","Florescent Yellow Sign Sheeting","SF",2,2,2,2,2,2,2,2,2,2,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A906,'Updated Quanities'!F:I,4,0),R906)=\"\",R906,IFERROR(VLOOKUP('AUP Library'!A906,'Updated Quanities'!F:I,4,0),R906))","v":2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A906,'Updated Quanities'!F:I,5,0),R906)=\"\",R906,IFERROR(VLOOKUP('AUP Library'!A906,'Updated Quanities'!F:I,5,0),R906))","v":2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A906,'Updated Quanities'!F:I,6,0),R906)=\"\",R906,IFERROR(VLOOKUP('AUP Library'!A906,'Updated Quanities'!F:I,6,0),R906))","v":2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A906,'Updated Quanities'!F:I,7,0),R906)=\"\",R906,IFERROR(VLOOKUP('AUP Library'!A906,'Updated Quanities'!F:I,7,0),R906))","v":2},2,{"$f":"IFERROR(VLOOKUP('AUP Library'!A906,'Updated Quanities'!F:G,4,0),R906)","v":2}]
["713-14","Extruded Aluminum Panel Signs","SF",24.03,24.03,24.03,24.03,24.03,24.03,24.03,24.03,24.03,24.03,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A907,'Updated Quanities'!F:I,4,0),R907)=\"\",R907,IFERROR(VLOOKUP('AUP Library'!A907,'Updated Quanities'!F:I,4,0),R907))","v":24.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A907,'Updated Quanities'!F:I,5,0),R907)=\"\",R907,IFERROR(VLOOKUP('AUP Library'!A907,'Updated Quanities'!F:I,5,0),R907))","v":24.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A907,'Updated Quanities'!F:I,6,0),R907)=\"\",R907,IFERROR(VLOOKUP('AUP Library'!A907,'Updated Quanities'!F:I,6,0),R907))","v":24.03},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A907,'Updated Quanities'!F:I,7,0),R907)=\"\",R907,IFERROR(VLOOKUP('AUP Library'!A907,'Updated Quanities'!F:I,7,0),R907))","v":24.03},24.03,{"$f":"IFERROR(VLOOKUP('AUP Library'!A907,'Updated Quanities'!F:G,4,0),R907)","v":24.03}]
["713-15","Removal Signs, Posts, and Footings","LS",966.62,966.62,966.62,966.62,966.62,966.62,966.62,966.62,966.62,966.62,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A908,'Updated Quanities'!F:I,4,0),R908)=\"\",R908,IFERROR(VLOOKUP('AUP Library'!A908,'Updated Quanities'!F:I,4,0),R908))","v":966.62},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A908,'Updated Quanities'!F:I,5,0),R908)=\"\",R908,IFERROR(VLOOKUP('AUP Library'!A908,'Updated Quanities'!F:I,5,0),R908))","v":966.62},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A908,'Updated Quanities'!F:I,6,0),R908)=\"\",R908,IFERROR(VLOOKUP('AUP Library'!A908,'Updated Quanities'!F:I,6,0),R908))","v":966.62},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A908,'Updated Quanities'!F:I,7,0),R908)=\"\",R908,IFERROR(VLOOKUP('AUP Library'!A908,'Updated Quanities'!F:I,7,0),R908))","v":966.62},966.62,{"$f":"IFERROR(VLOOKUP('AUP Library'!A908,'Updated Quanities'!F:G,4,0),R908)","v":966.62}]
["713-15.01","Removal of Existing Sign Post","EA",25.85,25.85,25.85,25.85,25.85,25.85,25.85,25.85,25.85,25.85,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A909,'Updated Quanities'!F:I,4,0),R909)=\"\",R909,IFERROR(VLOOKUP('AUP Library'!A909,'Updated Quanities'!F:I,4,0),R909))","v":25.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A909,'Updated Quanities'!F:I,5,0),R909)=\"\",R909,IFERROR(VLOOKUP('AUP Library'!A909,'Updated Quanities'!F:I,5,0),R909))","v":25.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A909,'Updated Quanities'!F:I,6,0),R909)=\"\",R909,IFERROR(VLOOKUP('AUP Library'!A909,'Updated Quanities'!F:I,6,0),R909))","v":25.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A909,'Updated Quanities'!F:I,7,0),R909)=\"\",R909,IFERROR(VLOOKUP('AUP Library'!A909,'Updated Quanities'!F:I,7,0),R909))","v":25.85},25.85,{"$f":"IFERROR(VLOOKUP('AUP Library'!A909,'Updated Quanities'!F:G,4,0),R909)","v":25.85}]
["713-15.02","Removal & Relocation of Sign & Support","EA",198.32,198.32,198.32,198.32,198.32,198.32,198.32,198.32,198.32,198.32,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A910,'Updated Quanities'!F:I,4,0),R910)=\"\",R910,IFERROR(VLOOKUP('AUP Library'!A910,'Updated Quanities'!F:I,4,0),R910))","v":198.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A910,'Updated Quanities'!F:I,5,0),R910)=\"\",R910,IFERROR(VLOOKUP('AUP Library'!A910,'Updated Quanities'!F:I,5,0),R910))","v":198.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A910,'Updated Quanities'!F:I,6,0),R910)=\"\",R910,IFERROR(VLOOKUP('AUP Library'!A910,'Updated Quanities'!F:I,6,0),R910))","v":198.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A910,'Updated Quanities'!F:I,7,0),R910)=\"\",R910,IFERROR(VLOOKUP('AUP Library'!A910,'Updated Quanities'!F:I,7,0),R910))","v":198.32},198.32,{"$f":"IFERROR(VLOOKUP('AUP Library'!A910,'Updated Quanities'!F:G,4,0),R910)","v":198.32}]
["713-15.04","Installation of Letters & Arrows","LS",2005.62,2005.62,2005.62,2005.62,2005.62,2005.62,2005.62,2005.62,2005.62,2005.62,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A911,'Updated Quanities'!F:I,4,0),R911)=\"\",R911,IFERROR(VLOOKUP('AUP Library'!A911,'Updated Quanities'!F:I,4,0),R911))","v":2005.62},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A911,'Updated Quanities'!F:I,5,0),R911)=\"\",R911,IFERROR(VLOOKUP('AUP Library'!A911,'Updated Quanities'!F:I,5,0),R911))","v":2005.62},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A911,'Updated Quanities'!F:I,6,0),R911)=\"\",R911,IFERROR(VLOOKUP('AUP Library'!A911,'Updated Quanities'!F:I,6,0),R911))","v":2005.62},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A911,'Updated Quanities'!F:I,7,0),R911)=\"\",R911,IFERROR(VLOOKUP('AUP Library'!A911,'Updated Quanities'!F:I,7,0),R911))","v":2005.62},2005.62,{"$f":"IFERROR(VLOOKUP('AUP Library'!A911,'Updated Quanities'!F:G,4,0),R911)","v":2005.62}]
["713-15.06","Mile Post Sign","EA",166.67,166.67,166.67,166.67,166.67,166.67,166.67,166.67,166.67,166.67,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A912,'Updated Quanities'!F:I,4,0),R912)=\"\",R912,IFERROR(VLOOKUP('AUP Library'!A912,'Updated Quanities'!F:I,4,0),R912))","v":166.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A912,'Updated Quanities'!F:I,5,0),R912)=\"\",R912,IFERROR(VLOOKUP('AUP Library'!A912,'Updated Quanities'!F:I,5,0),R912))","v":166.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A912,'Updated Quanities'!F:I,6,0),R912)=\"\",R912,IFERROR(VLOOKUP('AUP Library'!A912,'Updated Quanities'!F:I,6,0),R912))","v":166.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A912,'Updated Quanities'!F:I,7,0),R912)=\"\",R912,IFERROR(VLOOKUP('AUP Library'!A912,'Updated Quanities'!F:I,7,0),R912))","v":166.67},166.67,{"$f":"IFERROR(VLOOKUP('AUP Library'!A912,'Updated Quanities'!F:G,4,0),R912)","v":166.67}]
["713-15.07","Suspended Flat Sht Alm Sgn (0.080\" Thick)","EA",121.44,121.44,121.44,121.44,121.44,121.44,121.44,121.44,121.44,121.44,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A913,'Updated Quanities'!F:I,4,0),R913)=\"\",R913,IFERROR(VLOOKUP('AUP Library'!A913,'Updated Quanities'!F:I,4,0),R913))","v":121.44},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A913,'Updated Quanities'!F:I,5,0),R913)=\"\",R913,IFERROR(VLOOKUP('AUP Library'!A913,'Updated Quanities'!F:I,5,0),R913))","v":121.44},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A913,'Updated Quanities'!F:I,6,0),R913)=\"\",R913,IFERROR(VLOOKUP('AUP Library'!A913,'Updated Quanities'!F:I,6,0),R913))","v":121.44},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A913,'Updated Quanities'!F:I,7,0),R913)=\"\",R913,IFERROR(VLOOKUP('AUP Library'!A913,'Updated Quanities'!F:I,7,0),R913))","v":121.44},121.44,{"$f":"IFERROR(VLOOKUP('AUP Library'!A913,'Updated Quanities'!F:G,4,0),R913)","v":121.44}]
["713-15.35","Metal Barricade (Type III)","EA",652.70000000000005,652.70000000000005,652.70000000000005,652.70000000000005,652.70000000000005,652.70000000000005,652.70000000000005,652.70000000000005,652.70000000000005,652.70000000000005,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A914,'Updated Quanities'!F:I,4,0),R914)=\"\",R914,IFERROR(VLOOKUP('AUP Library'!A914,'Updated Quanities'!F:I,4,0),R914))","v":652.70000000000005},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A914,'Updated Quanities'!F:I,5,0),R914)=\"\",R914,IFERROR(VLOOKUP('AUP Library'!A914,'Updated Quanities'!F:I,5,0),R914))","v":652.70000000000005},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A914,'Updated Quanities'!F:I,6,0),R914)=\"\",R914,IFERROR(VLOOKUP('AUP Library'!A914,'Updated Quanities'!F:I,6,0),R914))","v":652.70000000000005},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A914,'Updated Quanities'!F:I,7,0),R914)=\"\",R914,IFERROR(VLOOKUP('AUP Library'!A914,'Updated Quanities'!F:I,7,0),R914))","v":652.70000000000005},652.70000000000005,{"$f":"IFERROR(VLOOKUP('AUP Library'!A914,'Updated Quanities'!F:G,4,0),R914)","v":652.70000000000005}]
["713-15.36","Remove, Sign, Support & Footing","EA",31.54,31.54,31.54,31.54,31.54,31.54,31.54,31.54,31.54,31.54,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A915,'Updated Quanities'!F:I,4,0),R915)=\"\",R915,IFERROR(VLOOKUP('AUP Library'!A915,'Updated Quanities'!F:I,4,0),R915))","v":31.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A915,'Updated Quanities'!F:I,5,0),R915)=\"\",R915,IFERROR(VLOOKUP('AUP Library'!A915,'Updated Quanities'!F:I,5,0),R915))","v":31.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A915,'Updated Quanities'!F:I,6,0),R915)=\"\",R915,IFERROR(VLOOKUP('AUP Library'!A915,'Updated Quanities'!F:I,6,0),R915))","v":31.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A915,'Updated Quanities'!F:I,7,0),R915)=\"\",R915,IFERROR(VLOOKUP('AUP Library'!A915,'Updated Quanities'!F:I,7,0),R915))","v":31.54},31.54,{"$f":"IFERROR(VLOOKUP('AUP Library'!A915,'Updated Quanities'!F:G,4,0),R915)","v":31.54}]
["713-15.37","Installation of Sign Message (Letter, #, AR)","SF",42.4,42.4,42.4,42.4,42.4,42.4,42.4,42.4,42.4,42.4,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A916,'Updated Quanities'!F:I,4,0),R916)=\"\",R916,IFERROR(VLOOKUP('AUP Library'!A916,'Updated Quanities'!F:I,4,0),R916))","v":42.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A916,'Updated Quanities'!F:I,5,0),R916)=\"\",R916,IFERROR(VLOOKUP('AUP Library'!A916,'Updated Quanities'!F:I,5,0),R916))","v":42.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A916,'Updated Quanities'!F:I,6,0),R916)=\"\",R916,IFERROR(VLOOKUP('AUP Library'!A916,'Updated Quanities'!F:I,6,0),R916))","v":42.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A916,'Updated Quanities'!F:I,7,0),R916)=\"\",R916,IFERROR(VLOOKUP('AUP Library'!A916,'Updated Quanities'!F:I,7,0),R916))","v":42.4},42.4,{"$f":"IFERROR(VLOOKUP('AUP Library'!A916,'Updated Quanities'!F:G,4,0),R916)","v":42.4}]
["713-15.38","Extrd Alm Panels for Overlaying Bkground","SF",4.8,4.8,4.8,4.8,4.8,4.8,4.8,4.8,4.8,4.8,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A917,'Updated Quanities'!F:I,4,0),R917)=\"\",R917,IFERROR(VLOOKUP('AUP Library'!A917,'Updated Quanities'!F:I,4,0),R917))","v":4.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A917,'Updated Quanities'!F:I,5,0),R917)=\"\",R917,IFERROR(VLOOKUP('AUP Library'!A917,'Updated Quanities'!F:I,5,0),R917))","v":4.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A917,'Updated Quanities'!F:I,6,0),R917)=\"\",R917,IFERROR(VLOOKUP('AUP Library'!A917,'Updated Quanities'!F:I,6,0),R917))","v":4.8},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A917,'Updated Quanities'!F:I,7,0),R917)=\"\",R917,IFERROR(VLOOKUP('AUP Library'!A917,'Updated Quanities'!F:I,7,0),R917))","v":4.8},4.8,{"$f":"IFERROR(VLOOKUP('AUP Library'!A917,'Updated Quanities'!F:G,4,0),R917)","v":4.8}]
["713-15.40","Sign Installation (Description)","LS",2000.59,2000.59,2000.59,2000.59,2000.59,2000.59,2000.59,2000.59,2000.59,2000.59,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A918,'Updated Quanities'!F:I,4,0),R918)=\"\",R918,IFERROR(VLOOKUP('AUP Library'!A918,'Updated Quanities'!F:I,4,0),R918))","v":2000.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A918,'Updated Quanities'!F:I,5,0),R918)=\"\",R918,IFERROR(VLOOKUP('AUP Library'!A918,'Updated Quanities'!F:I,5,0),R918))","v":2000.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A918,'Updated Quanities'!F:I,6,0),R918)=\"\",R918,IFERROR(VLOOKUP('AUP Library'!A918,'Updated Quanities'!F:I,6,0),R918))","v":2000.59},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A918,'Updated Quanities'!F:I,7,0),R918)=\"\",R918,IFERROR(VLOOKUP('AUP Library'!A918,'Updated Quanities'!F:I,7,0),R918))","v":2000.59},2000.59,{"$f":"IFERROR(VLOOKUP('AUP Library'!A918,'Updated Quanities'!F:G,4,0),R918)","v":2000.59}]
["713-15.41","Sign Removal (Description)","LS",403.33,403.33,403.33,403.33,403.33,403.33,403.33,403.33,403.33,403.33,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A919,'Updated Quanities'!F:I,4,0),R919)=\"\",R919,IFERROR(VLOOKUP('AUP Library'!A919,'Updated Quanities'!F:I,4,0),R919))","v":403.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A919,'Updated Quanities'!F:I,5,0),R919)=\"\",R919,IFERROR(VLOOKUP('AUP Library'!A919,'Updated Quanities'!F:I,5,0),R919))","v":403.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A919,'Updated Quanities'!F:I,6,0),R919)=\"\",R919,IFERROR(VLOOKUP('AUP Library'!A919,'Updated Quanities'!F:I,6,0),R919))","v":403.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A919,'Updated Quanities'!F:I,7,0),R919)=\"\",R919,IFERROR(VLOOKUP('AUP Library'!A919,'Updated Quanities'!F:I,7,0),R919))","v":403.33},403.33,{"$f":"IFERROR(VLOOKUP('AUP Library'!A919,'Updated Quanities'!F:G,4,0),R919)","v":403.33}]
["713-16.01","Changeable Message Sign Unit","EA",5916.82,5916.82,5916.82,5916.82,5916.82,5916.82,5916.82,5916.82,5916.82,5916.82,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A920,'Updated Quanities'!F:I,4,0),R920)=\"\",R920,IFERROR(VLOOKUP('AUP Library'!A920,'Updated Quanities'!F:I,4,0),R920))","v":5916.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A920,'Updated Quanities'!F:I,5,0),R920)=\"\",R920,IFERROR(VLOOKUP('AUP Library'!A920,'Updated Quanities'!F:I,5,0),R920))","v":5916.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A920,'Updated Quanities'!F:I,6,0),R920)=\"\",R920,IFERROR(VLOOKUP('AUP Library'!A920,'Updated Quanities'!F:I,6,0),R920))","v":5916.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A920,'Updated Quanities'!F:I,7,0),R920)=\"\",R920,IFERROR(VLOOKUP('AUP Library'!A920,'Updated Quanities'!F:I,7,0),R920))","v":5916.82},5916.82,{"$f":"IFERROR(VLOOKUP('AUP Library'!A920,'Updated Quanities'!F:G,4,0),R920)","v":5916.82}]
["713-16.02","Truck Mtd Imp Attn (w/ Flashing Arrow Board)","EA",9872.67,9872.67,9872.67,9872.67,9872.67,9872.67,9872.67,9872.67,9872.67,9872.67,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A921,'Updated Quanities'!F:I,4,0),R921)=\"\",R921,IFERROR(VLOOKUP('AUP Library'!A921,'Updated Quanities'!F:I,4,0),R921))","v":9872.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A921,'Updated Quanities'!F:I,5,0),R921)=\"\",R921,IFERROR(VLOOKUP('AUP Library'!A921,'Updated Quanities'!F:I,5,0),R921))","v":9872.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A921,'Updated Quanities'!F:I,6,0),R921)=\"\",R921,IFERROR(VLOOKUP('AUP Library'!A921,'Updated Quanities'!F:I,6,0),R921))","v":9872.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A921,'Updated Quanities'!F:I,7,0),R921)=\"\",R921,IFERROR(VLOOKUP('AUP Library'!A921,'Updated Quanities'!F:I,7,0),R921))","v":9872.67},9872.67,{"$f":"IFERROR(VLOOKUP('AUP Library'!A921,'Updated Quanities'!F:G,4,0),R921)","v":9872.67}]
["713-16.05","Railroad Cross-Buck Sign & Support","EA",333.51,333.51,333.51,333.51,333.51,333.51,333.51,333.51,333.51,333.51,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A922,'Updated Quanities'!F:I,4,0),R922)=\"\",R922,IFERROR(VLOOKUP('AUP Library'!A922,'Updated Quanities'!F:I,4,0),R922))","v":333.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A922,'Updated Quanities'!F:I,5,0),R922)=\"\",R922,IFERROR(VLOOKUP('AUP Library'!A922,'Updated Quanities'!F:I,5,0),R922))","v":333.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A922,'Updated Quanities'!F:I,6,0),R922)=\"\",R922,IFERROR(VLOOKUP('AUP Library'!A922,'Updated Quanities'!F:I,6,0),R922))","v":333.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A922,'Updated Quanities'!F:I,7,0),R922)=\"\",R922,IFERROR(VLOOKUP('AUP Library'!A922,'Updated Quanities'!F:I,7,0),R922))","v":333.51},333.51,{"$f":"IFERROR(VLOOKUP('AUP Library'!A922,'Updated Quanities'!F:G,4,0),R922)","v":333.51}]
["713-16.06","Dead End Sign and Support","EA",200,200,200,200,200,200,200,200,200,200,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A923,'Updated Quanities'!F:I,4,0),R923)=\"\",R923,IFERROR(VLOOKUP('AUP Library'!A923,'Updated Quanities'!F:I,4,0),R923))","v":200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A923,'Updated Quanities'!F:I,5,0),R923)=\"\",R923,IFERROR(VLOOKUP('AUP Library'!A923,'Updated Quanities'!F:I,5,0),R923))","v":200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A923,'Updated Quanities'!F:I,6,0),R923)=\"\",R923,IFERROR(VLOOKUP('AUP Library'!A923,'Updated Quanities'!F:I,6,0),R923))","v":200},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A923,'Updated Quanities'!F:I,7,0),R923)=\"\",R923,IFERROR(VLOOKUP('AUP Library'!A923,'Updated Quanities'!F:I,7,0),R923))","v":200},200,{"$f":"IFERROR(VLOOKUP('AUP Library'!A923,'Updated Quanities'!F:G,4,0),R923)","v":200}]
["713-16.07","End of Roadway Sign and Support","EA",199.7,199.7,199.7,199.7,199.7,199.7,199.7,199.7,199.7,199.7,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A924,'Updated Quanities'!F:I,4,0),R924)=\"\",R924,IFERROR(VLOOKUP('AUP Library'!A924,'Updated Quanities'!F:I,4,0),R924))","v":199.7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A924,'Updated Quanities'!F:I,5,0),R924)=\"\",R924,IFERROR(VLOOKUP('AUP Library'!A924,'Updated Quanities'!F:I,5,0),R924))","v":199.7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A924,'Updated Quanities'!F:I,6,0),R924)=\"\",R924,IFERROR(VLOOKUP('AUP Library'!A924,'Updated Quanities'!F:I,6,0),R924))","v":199.7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A924,'Updated Quanities'!F:I,7,0),R924)=\"\",R924,IFERROR(VLOOKUP('AUP Library'!A924,'Updated Quanities'!F:I,7,0),R924))","v":199.7},199.7,{"$f":"IFERROR(VLOOKUP('AUP Library'!A924,'Updated Quanities'!F:G,4,0),R924)","v":199.7}]
["713-16.09","Railroad Advance Warning Sign and Support","EA",277.22000000000003,277.22000000000003,277.22000000000003,277.22000000000003,277.22000000000003,277.22000000000003,277.22000000000003,277.22000000000003,277.22000000000003,277.22000000000003,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A925,'Updated Quanities'!F:I,4,0),R925)=\"\",R925,IFERROR(VLOOKUP('AUP Library'!A925,'Updated Quanities'!F:I,4,0),R925))","v":277.22000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A925,'Updated Quanities'!F:I,5,0),R925)=\"\",R925,IFERROR(VLOOKUP('AUP Library'!A925,'Updated Quanities'!F:I,5,0),R925))","v":277.22000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A925,'Updated Quanities'!F:I,6,0),R925)=\"\",R925,IFERROR(VLOOKUP('AUP Library'!A925,'Updated Quanities'!F:I,6,0),R925))","v":277.22000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A925,'Updated Quanities'!F:I,7,0),R925)=\"\",R925,IFERROR(VLOOKUP('AUP Library'!A925,'Updated Quanities'!F:I,7,0),R925))","v":277.22000000000003},277.22000000000003,{"$f":"IFERROR(VLOOKUP('AUP Library'!A925,'Updated Quanities'!F:G,4,0),R925)","v":277.22000000000003}]
["713-16.20","Signs","EA",184.23,184.23,184.23,184.23,184.23,184.23,184.23,184.23,184.23,184.23,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A926,'Updated Quanities'!F:I,4,0),R926)=\"\",R926,IFERROR(VLOOKUP('AUP Library'!A926,'Updated Quanities'!F:I,4,0),R926))","v":184.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A926,'Updated Quanities'!F:I,5,0),R926)=\"\",R926,IFERROR(VLOOKUP('AUP Library'!A926,'Updated Quanities'!F:I,5,0),R926))","v":184.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A926,'Updated Quanities'!F:I,6,0),R926)=\"\",R926,IFERROR(VLOOKUP('AUP Library'!A926,'Updated Quanities'!F:I,6,0),R926))","v":184.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A926,'Updated Quanities'!F:I,7,0),R926)=\"\",R926,IFERROR(VLOOKUP('AUP Library'!A926,'Updated Quanities'!F:I,7,0),R926))","v":184.23},184.23,{"$f":"IFERROR(VLOOKUP('AUP Library'!A926,'Updated Quanities'!F:G,4,0),R926)","v":184.23}]
["713-16.21","Signs","EA",205.86,205.86,205.86,205.86,205.86,205.86,205.86,205.86,205.86,205.86,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A927,'Updated Quanities'!F:I,4,0),R927)=\"\",R927,IFERROR(VLOOKUP('AUP Library'!A927,'Updated Quanities'!F:I,4,0),R927))","v":205.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A927,'Updated Quanities'!F:I,5,0),R927)=\"\",R927,IFERROR(VLOOKUP('AUP Library'!A927,'Updated Quanities'!F:I,5,0),R927))","v":205.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A927,'Updated Quanities'!F:I,6,0),R927)=\"\",R927,IFERROR(VLOOKUP('AUP Library'!A927,'Updated Quanities'!F:I,6,0),R927))","v":205.86},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A927,'Updated Quanities'!F:I,7,0),R927)=\"\",R927,IFERROR(VLOOKUP('AUP Library'!A927,'Updated Quanities'!F:I,7,0),R927))","v":205.86},205.86,{"$f":"IFERROR(VLOOKUP('AUP Library'!A927,'Updated Quanities'!F:G,4,0),R927)","v":205.86}]
["713-16.22","Signs","EA",197.29,197.29,197.29,197.29,197.29,197.29,197.29,197.29,197.29,197.29,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A928,'Updated Quanities'!F:I,4,0),R928)=\"\",R928,IFERROR(VLOOKUP('AUP Library'!A928,'Updated Quanities'!F:I,4,0),R928))","v":197.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A928,'Updated Quanities'!F:I,5,0),R928)=\"\",R928,IFERROR(VLOOKUP('AUP Library'!A928,'Updated Quanities'!F:I,5,0),R928))","v":197.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A928,'Updated Quanities'!F:I,6,0),R928)=\"\",R928,IFERROR(VLOOKUP('AUP Library'!A928,'Updated Quanities'!F:I,6,0),R928))","v":197.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A928,'Updated Quanities'!F:I,7,0),R928)=\"\",R928,IFERROR(VLOOKUP('AUP Library'!A928,'Updated Quanities'!F:I,7,0),R928))","v":197.29},197.29,{"$f":"IFERROR(VLOOKUP('AUP Library'!A928,'Updated Quanities'!F:G,4,0),R928)","v":197.29}]
["713-16.23","Signs","EA",199.25,199.25,199.25,199.25,199.25,199.25,199.25,199.25,199.25,199.25,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A929,'Updated Quanities'!F:I,4,0),R929)=\"\",R929,IFERROR(VLOOKUP('AUP Library'!A929,'Updated Quanities'!F:I,4,0),R929))","v":199.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A929,'Updated Quanities'!F:I,5,0),R929)=\"\",R929,IFERROR(VLOOKUP('AUP Library'!A929,'Updated Quanities'!F:I,5,0),R929))","v":199.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A929,'Updated Quanities'!F:I,6,0),R929)=\"\",R929,IFERROR(VLOOKUP('AUP Library'!A929,'Updated Quanities'!F:I,6,0),R929))","v":199.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A929,'Updated Quanities'!F:I,7,0),R929)=\"\",R929,IFERROR(VLOOKUP('AUP Library'!A929,'Updated Quanities'!F:I,7,0),R929))","v":199.25},199.25,{"$f":"IFERROR(VLOOKUP('AUP Library'!A929,'Updated Quanities'!F:G,4,0),R929)","v":199.25}]
["713-16.24","Signs","EA",179.61,179.61,179.61,179.61,179.61,179.61,179.61,179.61,179.61,179.61,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A930,'Updated Quanities'!F:I,4,0),R930)=\"\",R930,IFERROR(VLOOKUP('AUP Library'!A930,'Updated Quanities'!F:I,4,0),R930))","v":179.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A930,'Updated Quanities'!F:I,5,0),R930)=\"\",R930,IFERROR(VLOOKUP('AUP Library'!A930,'Updated Quanities'!F:I,5,0),R930))","v":179.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A930,'Updated Quanities'!F:I,6,0),R930)=\"\",R930,IFERROR(VLOOKUP('AUP Library'!A930,'Updated Quanities'!F:I,6,0),R930))","v":179.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A930,'Updated Quanities'!F:I,7,0),R930)=\"\",R930,IFERROR(VLOOKUP('AUP Library'!A930,'Updated Quanities'!F:I,7,0),R930))","v":179.61},179.61,{"$f":"IFERROR(VLOOKUP('AUP Library'!A930,'Updated Quanities'!F:G,4,0),R930)","v":179.61}]
["713-16.25","Signs","EA",132.66,132.66,132.66,132.66,132.66,132.66,132.66,132.66,132.66,132.66,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A931,'Updated Quanities'!F:I,4,0),R931)=\"\",R931,IFERROR(VLOOKUP('AUP Library'!A931,'Updated Quanities'!F:I,4,0),R931))","v":132.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A931,'Updated Quanities'!F:I,5,0),R931)=\"\",R931,IFERROR(VLOOKUP('AUP Library'!A931,'Updated Quanities'!F:I,5,0),R931))","v":132.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A931,'Updated Quanities'!F:I,6,0),R931)=\"\",R931,IFERROR(VLOOKUP('AUP Library'!A931,'Updated Quanities'!F:I,6,0),R931))","v":132.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A931,'Updated Quanities'!F:I,7,0),R931)=\"\",R931,IFERROR(VLOOKUP('AUP Library'!A931,'Updated Quanities'!F:I,7,0),R931))","v":132.66},132.66,{"$f":"IFERROR(VLOOKUP('AUP Library'!A931,'Updated Quanities'!F:G,4,0),R931)","v":132.66}]
["713-16.26","Signs","EA",104.15,104.15,104.15,104.15,104.15,104.15,104.15,104.15,104.15,104.15,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A932,'Updated Quanities'!F:I,4,0),R932)=\"\",R932,IFERROR(VLOOKUP('AUP Library'!A932,'Updated Quanities'!F:I,4,0),R932))","v":104.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A932,'Updated Quanities'!F:I,5,0),R932)=\"\",R932,IFERROR(VLOOKUP('AUP Library'!A932,'Updated Quanities'!F:I,5,0),R932))","v":104.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A932,'Updated Quanities'!F:I,6,0),R932)=\"\",R932,IFERROR(VLOOKUP('AUP Library'!A932,'Updated Quanities'!F:I,6,0),R932))","v":104.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A932,'Updated Quanities'!F:I,7,0),R932)=\"\",R932,IFERROR(VLOOKUP('AUP Library'!A932,'Updated Quanities'!F:I,7,0),R932))","v":104.15},104.15,{"$f":"IFERROR(VLOOKUP('AUP Library'!A932,'Updated Quanities'!F:G,4,0),R932)","v":104.15}]
["713-16.27","Signs","EA",74.13,74.13,74.13,74.13,74.13,74.13,74.13,74.13,74.13,74.13,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A933,'Updated Quanities'!F:I,4,0),R933)=\"\",R933,IFERROR(VLOOKUP('AUP Library'!A933,'Updated Quanities'!F:I,4,0),R933))","v":74.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A933,'Updated Quanities'!F:I,5,0),R933)=\"\",R933,IFERROR(VLOOKUP('AUP Library'!A933,'Updated Quanities'!F:I,5,0),R933))","v":74.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A933,'Updated Quanities'!F:I,6,0),R933)=\"\",R933,IFERROR(VLOOKUP('AUP Library'!A933,'Updated Quanities'!F:I,6,0),R933))","v":74.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A933,'Updated Quanities'!F:I,7,0),R933)=\"\",R933,IFERROR(VLOOKUP('AUP Library'!A933,'Updated Quanities'!F:I,7,0),R933))","v":74.13},74.13,{"$f":"IFERROR(VLOOKUP('AUP Library'!A933,'Updated Quanities'!F:G,4,0),R933)","v":74.13}]
["713-16.28","Signs","EA",117,117,117,117,117,117,117,117,117,117,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A934,'Updated Quanities'!F:I,4,0),R934)=\"\",R934,IFERROR(VLOOKUP('AUP Library'!A934,'Updated Quanities'!F:I,4,0),R934))","v":117},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A934,'Updated Quanities'!F:I,5,0),R934)=\"\",R934,IFERROR(VLOOKUP('AUP Library'!A934,'Updated Quanities'!F:I,5,0),R934))","v":117},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A934,'Updated Quanities'!F:I,6,0),R934)=\"\",R934,IFERROR(VLOOKUP('AUP Library'!A934,'Updated Quanities'!F:I,6,0),R934))","v":117},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A934,'Updated Quanities'!F:I,7,0),R934)=\"\",R934,IFERROR(VLOOKUP('AUP Library'!A934,'Updated Quanities'!F:I,7,0),R934))","v":117},117,{"$f":"IFERROR(VLOOKUP('AUP Library'!A934,'Updated Quanities'!F:G,4,0),R934)","v":117}]
["713-16.29","Signs","EA",141.62,141.62,141.62,141.62,141.62,141.62,141.62,141.62,141.62,141.62,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A935,'Updated Quanities'!F:I,4,0),R935)=\"\",R935,IFERROR(VLOOKUP('AUP Library'!A935,'Updated Quanities'!F:I,4,0),R935))","v":141.62},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A935,'Updated Quanities'!F:I,5,0),R935)=\"\",R935,IFERROR(VLOOKUP('AUP Library'!A935,'Updated Quanities'!F:I,5,0),R935))","v":141.62},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A935,'Updated Quanities'!F:I,6,0),R935)=\"\",R935,IFERROR(VLOOKUP('AUP Library'!A935,'Updated Quanities'!F:I,6,0),R935))","v":141.62},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A935,'Updated Quanities'!F:I,7,0),R935)=\"\",R935,IFERROR(VLOOKUP('AUP Library'!A935,'Updated Quanities'!F:I,7,0),R935))","v":141.62},141.62,{"$f":"IFERROR(VLOOKUP('AUP Library'!A935,'Updated Quanities'!F:G,4,0),R935)","v":141.62}]
["713-16.30","Signs (Description)","EA",121.16,121.16,121.16,121.16,121.16,121.16,121.16,121.16,121.16,121.16,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A936,'Updated Quanities'!F:I,4,0),R936)=\"\",R936,IFERROR(VLOOKUP('AUP Library'!A936,'Updated Quanities'!F:I,4,0),R936))","v":121.16},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A936,'Updated Quanities'!F:I,5,0),R936)=\"\",R936,IFERROR(VLOOKUP('AUP Library'!A936,'Updated Quanities'!F:I,5,0),R936))","v":121.16},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A936,'Updated Quanities'!F:I,6,0),R936)=\"\",R936,IFERROR(VLOOKUP('AUP Library'!A936,'Updated Quanities'!F:I,6,0),R936))","v":121.16},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A936,'Updated Quanities'!F:I,7,0),R936)=\"\",R936,IFERROR(VLOOKUP('AUP Library'!A936,'Updated Quanities'!F:I,7,0),R936))","v":121.16},121.16,{"$f":"IFERROR(VLOOKUP('AUP Library'!A936,'Updated Quanities'!F:G,4,0),R936)","v":121.16}]
["713-16.31","Signs (Description)","EA",100.64,100.64,100.64,100.64,100.64,100.64,100.64,100.64,100.64,100.64,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A937,'Updated Quanities'!F:I,4,0),R937)=\"\",R937,IFERROR(VLOOKUP('AUP Library'!A937,'Updated Quanities'!F:I,4,0),R937))","v":100.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A937,'Updated Quanities'!F:I,5,0),R937)=\"\",R937,IFERROR(VLOOKUP('AUP Library'!A937,'Updated Quanities'!F:I,5,0),R937))","v":100.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A937,'Updated Quanities'!F:I,6,0),R937)=\"\",R937,IFERROR(VLOOKUP('AUP Library'!A937,'Updated Quanities'!F:I,6,0),R937))","v":100.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A937,'Updated Quanities'!F:I,7,0),R937)=\"\",R937,IFERROR(VLOOKUP('AUP Library'!A937,'Updated Quanities'!F:I,7,0),R937))","v":100.64},100.64,{"$f":"IFERROR(VLOOKUP('AUP Library'!A937,'Updated Quanities'!F:G,4,0),R937)","v":100.64}]
["713-16.32","Signs (Description)","EA",143.94999999999999,143.94999999999999,143.94999999999999,143.94999999999999,143.94999999999999,143.94999999999999,143.94999999999999,143.94999999999999,143.94999999999999,143.94999999999999,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A938,'Updated Quanities'!F:I,4,0),R938)=\"\",R938,IFERROR(VLOOKUP('AUP Library'!A938,'Updated Quanities'!F:I,4,0),R938))","v":143.94999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A938,'Updated Quanities'!F:I,5,0),R938)=\"\",R938,IFERROR(VLOOKUP('AUP Library'!A938,'Updated Quanities'!F:I,5,0),R938))","v":143.94999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A938,'Updated Quanities'!F:I,6,0),R938)=\"\",R938,IFERROR(VLOOKUP('AUP Library'!A938,'Updated Quanities'!F:I,6,0),R938))","v":143.94999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A938,'Updated Quanities'!F:I,7,0),R938)=\"\",R938,IFERROR(VLOOKUP('AUP Library'!A938,'Updated Quanities'!F:I,7,0),R938))","v":143.94999999999999},143.94999999999999,{"$f":"IFERROR(VLOOKUP('AUP Library'!A938,'Updated Quanities'!F:G,4,0),R938)","v":143.94999999999999}]
["713-16.33","Signs (Description)","EA",158.07,158.07,158.07,158.07,158.07,158.07,158.07,158.07,158.07,158.07,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A939,'Updated Quanities'!F:I,4,0),R939)=\"\",R939,IFERROR(VLOOKUP('AUP Library'!A939,'Updated Quanities'!F:I,4,0),R939))","v":158.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A939,'Updated Quanities'!F:I,5,0),R939)=\"\",R939,IFERROR(VLOOKUP('AUP Library'!A939,'Updated Quanities'!F:I,5,0),R939))","v":158.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A939,'Updated Quanities'!F:I,6,0),R939)=\"\",R939,IFERROR(VLOOKUP('AUP Library'!A939,'Updated Quanities'!F:I,6,0),R939))","v":158.07},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A939,'Updated Quanities'!F:I,7,0),R939)=\"\",R939,IFERROR(VLOOKUP('AUP Library'!A939,'Updated Quanities'!F:I,7,0),R939))","v":158.07},158.07,{"$f":"IFERROR(VLOOKUP('AUP Library'!A939,'Updated Quanities'!F:G,4,0),R939)","v":158.07}]
["713-16.34","Signs (Description)","EA",102.83,102.83,102.83,102.83,102.83,102.83,102.83,102.83,102.83,102.83,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A940,'Updated Quanities'!F:I,4,0),R940)=\"\",R940,IFERROR(VLOOKUP('AUP Library'!A940,'Updated Quanities'!F:I,4,0),R940))","v":102.83},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A940,'Updated Quanities'!F:I,5,0),R940)=\"\",R940,IFERROR(VLOOKUP('AUP Library'!A940,'Updated Quanities'!F:I,5,0),R940))","v":102.83},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A940,'Updated Quanities'!F:I,6,0),R940)=\"\",R940,IFERROR(VLOOKUP('AUP Library'!A940,'Updated Quanities'!F:I,6,0),R940))","v":102.83},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A940,'Updated Quanities'!F:I,7,0),R940)=\"\",R940,IFERROR(VLOOKUP('AUP Library'!A940,'Updated Quanities'!F:I,7,0),R940))","v":102.83},102.83,{"$f":"IFERROR(VLOOKUP('AUP Library'!A940,'Updated Quanities'!F:G,4,0),R940)","v":102.83}]
["713-16.35","Signs (Description)","EA",102.82,102.82,102.82,102.82,102.82,102.82,102.82,102.82,102.82,102.82,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A941,'Updated Quanities'!F:I,4,0),R941)=\"\",R941,IFERROR(VLOOKUP('AUP Library'!A941,'Updated Quanities'!F:I,4,0),R941))","v":102.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A941,'Updated Quanities'!F:I,5,0),R941)=\"\",R941,IFERROR(VLOOKUP('AUP Library'!A941,'Updated Quanities'!F:I,5,0),R941))","v":102.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A941,'Updated Quanities'!F:I,6,0),R941)=\"\",R941,IFERROR(VLOOKUP('AUP Library'!A941,'Updated Quanities'!F:I,6,0),R941))","v":102.82},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A941,'Updated Quanities'!F:I,7,0),R941)=\"\",R941,IFERROR(VLOOKUP('AUP Library'!A941,'Updated Quanities'!F:I,7,0),R941))","v":102.82},102.82,{"$f":"IFERROR(VLOOKUP('AUP Library'!A941,'Updated Quanities'!F:G,4,0),R941)","v":102.82}]
["713-16.36","Signs (Description)","EA",118.51,118.51,118.51,118.51,118.51,118.51,118.51,118.51,118.51,118.51,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A942,'Updated Quanities'!F:I,4,0),R942)=\"\",R942,IFERROR(VLOOKUP('AUP Library'!A942,'Updated Quanities'!F:I,4,0),R942))","v":118.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A942,'Updated Quanities'!F:I,5,0),R942)=\"\",R942,IFERROR(VLOOKUP('AUP Library'!A942,'Updated Quanities'!F:I,5,0),R942))","v":118.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A942,'Updated Quanities'!F:I,6,0),R942)=\"\",R942,IFERROR(VLOOKUP('AUP Library'!A942,'Updated Quanities'!F:I,6,0),R942))","v":118.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A942,'Updated Quanities'!F:I,7,0),R942)=\"\",R942,IFERROR(VLOOKUP('AUP Library'!A942,'Updated Quanities'!F:I,7,0),R942))","v":118.51},118.51,{"$f":"IFERROR(VLOOKUP('AUP Library'!A942,'Updated Quanities'!F:G,4,0),R942)","v":118.51}]
["713-16.37","Signs (Description)","EA",166.48,166.48,166.48,166.48,166.48,166.48,166.48,166.48,166.48,166.48,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A943,'Updated Quanities'!F:I,4,0),R943)=\"\",R943,IFERROR(VLOOKUP('AUP Library'!A943,'Updated Quanities'!F:I,4,0),R943))","v":166.48},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A943,'Updated Quanities'!F:I,5,0),R943)=\"\",R943,IFERROR(VLOOKUP('AUP Library'!A943,'Updated Quanities'!F:I,5,0),R943))","v":166.48},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A943,'Updated Quanities'!F:I,6,0),R943)=\"\",R943,IFERROR(VLOOKUP('AUP Library'!A943,'Updated Quanities'!F:I,6,0),R943))","v":166.48},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A943,'Updated Quanities'!F:I,7,0),R943)=\"\",R943,IFERROR(VLOOKUP('AUP Library'!A943,'Updated Quanities'!F:I,7,0),R943))","v":166.48},166.48,{"$f":"IFERROR(VLOOKUP('AUP Library'!A943,'Updated Quanities'!F:G,4,0),R943)","v":166.48}]
["713-16.38","Signs (Description)","EA",155,155,155,155,155,155,155,155,155,155,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A944,'Updated Quanities'!F:I,4,0),R944)=\"\",R944,IFERROR(VLOOKUP('AUP Library'!A944,'Updated Quanities'!F:I,4,0),R944))","v":155},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A944,'Updated Quanities'!F:I,5,0),R944)=\"\",R944,IFERROR(VLOOKUP('AUP Library'!A944,'Updated Quanities'!F:I,5,0),R944))","v":155},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A944,'Updated Quanities'!F:I,6,0),R944)=\"\",R944,IFERROR(VLOOKUP('AUP Library'!A944,'Updated Quanities'!F:I,6,0),R944))","v":155},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A944,'Updated Quanities'!F:I,7,0),R944)=\"\",R944,IFERROR(VLOOKUP('AUP Library'!A944,'Updated Quanities'!F:I,7,0),R944))","v":155},155,{"$f":"IFERROR(VLOOKUP('AUP Library'!A944,'Updated Quanities'!F:G,4,0),R944)","v":155}]
["713-16.41","Relocate Sign","LS",2847.13,2847.13,2847.13,2847.13,2847.13,2847.13,2847.13,2847.13,2847.13,2847.13,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A945,'Updated Quanities'!F:I,4,0),R945)=\"\",R945,IFERROR(VLOOKUP('AUP Library'!A945,'Updated Quanities'!F:I,4,0),R945))","v":2847.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A945,'Updated Quanities'!F:I,5,0),R945)=\"\",R945,IFERROR(VLOOKUP('AUP Library'!A945,'Updated Quanities'!F:I,5,0),R945))","v":2847.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A945,'Updated Quanities'!F:I,6,0),R945)=\"\",R945,IFERROR(VLOOKUP('AUP Library'!A945,'Updated Quanities'!F:I,6,0),R945))","v":2847.13},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A945,'Updated Quanities'!F:I,7,0),R945)=\"\",R945,IFERROR(VLOOKUP('AUP Library'!A945,'Updated Quanities'!F:I,7,0),R945))","v":2847.13},2847.13,{"$f":"IFERROR(VLOOKUP('AUP Library'!A945,'Updated Quanities'!F:G,4,0),R945)","v":2847.13}]
["713-16.42","Relocate Sign and Rewire","LS",4000,4000,4000,4000,4000,4000,4000,4000,4000,4000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A946,'Updated Quanities'!F:I,4,0),R946)=\"\",R946,IFERROR(VLOOKUP('AUP Library'!A946,'Updated Quanities'!F:I,4,0),R946))","v":4000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A946,'Updated Quanities'!F:I,5,0),R946)=\"\",R946,IFERROR(VLOOKUP('AUP Library'!A946,'Updated Quanities'!F:I,5,0),R946))","v":4000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A946,'Updated Quanities'!F:I,6,0),R946)=\"\",R946,IFERROR(VLOOKUP('AUP Library'!A946,'Updated Quanities'!F:I,6,0),R946))","v":4000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A946,'Updated Quanities'!F:I,7,0),R946)=\"\",R946,IFERROR(VLOOKUP('AUP Library'!A946,'Updated Quanities'!F:I,7,0),R946))","v":4000},4000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A946,'Updated Quanities'!F:G,4,0),R946)","v":4000}]
["713-16.50","Remove and Replace Sign","EA",72.430000000000007,72.430000000000007,72.430000000000007,72.430000000000007,72.430000000000007,72.430000000000007,72.430000000000007,72.430000000000007,72.430000000000007,72.430000000000007,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A947,'Updated Quanities'!F:I,4,0),R947)=\"\",R947,IFERROR(VLOOKUP('AUP Library'!A947,'Updated Quanities'!F:I,4,0),R947))","v":72.430000000000007},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A947,'Updated Quanities'!F:I,5,0),R947)=\"\",R947,IFERROR(VLOOKUP('AUP Library'!A947,'Updated Quanities'!F:I,5,0),R947))","v":72.430000000000007},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A947,'Updated Quanities'!F:I,6,0),R947)=\"\",R947,IFERROR(VLOOKUP('AUP Library'!A947,'Updated Quanities'!F:I,6,0),R947))","v":72.430000000000007},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A947,'Updated Quanities'!F:I,7,0),R947)=\"\",R947,IFERROR(VLOOKUP('AUP Library'!A947,'Updated Quanities'!F:I,7,0),R947))","v":72.430000000000007},72.430000000000007,{"$f":"IFERROR(VLOOKUP('AUP Library'!A947,'Updated Quanities'!F:G,4,0),R947)","v":72.430000000000007}]
["713-16.51","Remove and Replace Sign","EA",173,173,173,173,173,173,173,173,173,173,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A948,'Updated Quanities'!F:I,4,0),R948)=\"\",R948,IFERROR(VLOOKUP('AUP Library'!A948,'Updated Quanities'!F:I,4,0),R948))","v":173},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A948,'Updated Quanities'!F:I,5,0),R948)=\"\",R948,IFERROR(VLOOKUP('AUP Library'!A948,'Updated Quanities'!F:I,5,0),R948))","v":173},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A948,'Updated Quanities'!F:I,6,0),R948)=\"\",R948,IFERROR(VLOOKUP('AUP Library'!A948,'Updated Quanities'!F:I,6,0),R948))","v":173},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A948,'Updated Quanities'!F:I,7,0),R948)=\"\",R948,IFERROR(VLOOKUP('AUP Library'!A948,'Updated Quanities'!F:I,7,0),R948))","v":173},173,{"$f":"IFERROR(VLOOKUP('AUP Library'!A948,'Updated Quanities'!F:G,4,0),R948)","v":173}]
["713-16.52","Remove and Replace Sign","EA",156.44999999999999,156.44999999999999,156.44999999999999,156.44999999999999,156.44999999999999,156.44999999999999,156.44999999999999,156.44999999999999,156.44999999999999,156.44999999999999,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A949,'Updated Quanities'!F:I,4,0),R949)=\"\",R949,IFERROR(VLOOKUP('AUP Library'!A949,'Updated Quanities'!F:I,4,0),R949))","v":156.44999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A949,'Updated Quanities'!F:I,5,0),R949)=\"\",R949,IFERROR(VLOOKUP('AUP Library'!A949,'Updated Quanities'!F:I,5,0),R949))","v":156.44999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A949,'Updated Quanities'!F:I,6,0),R949)=\"\",R949,IFERROR(VLOOKUP('AUP Library'!A949,'Updated Quanities'!F:I,6,0),R949))","v":156.44999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A949,'Updated Quanities'!F:I,7,0),R949)=\"\",R949,IFERROR(VLOOKUP('AUP Library'!A949,'Updated Quanities'!F:I,7,0),R949))","v":156.44999999999999},156.44999999999999,{"$f":"IFERROR(VLOOKUP('AUP Library'!A949,'Updated Quanities'!F:G,4,0),R949)","v":156.44999999999999}]
["713-16.53","Remove and Replace Sign","EA",369.29,369.29,369.29,369.29,369.29,369.29,369.29,369.29,369.29,369.29,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A950,'Updated Quanities'!F:I,4,0),R950)=\"\",R950,IFERROR(VLOOKUP('AUP Library'!A950,'Updated Quanities'!F:I,4,0),R950))","v":369.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A950,'Updated Quanities'!F:I,5,0),R950)=\"\",R950,IFERROR(VLOOKUP('AUP Library'!A950,'Updated Quanities'!F:I,5,0),R950))","v":369.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A950,'Updated Quanities'!F:I,6,0),R950)=\"\",R950,IFERROR(VLOOKUP('AUP Library'!A950,'Updated Quanities'!F:I,6,0),R950))","v":369.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A950,'Updated Quanities'!F:I,7,0),R950)=\"\",R950,IFERROR(VLOOKUP('AUP Library'!A950,'Updated Quanities'!F:I,7,0),R950))","v":369.29},369.29,{"$f":"IFERROR(VLOOKUP('AUP Library'!A950,'Updated Quanities'!F:G,4,0),R950)","v":369.29}]
["713-16.54","Remove and Replace Sign","EA",178.33,178.33,178.33,178.33,178.33,178.33,178.33,178.33,178.33,178.33,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A951,'Updated Quanities'!F:I,4,0),R951)=\"\",R951,IFERROR(VLOOKUP('AUP Library'!A951,'Updated Quanities'!F:I,4,0),R951))","v":178.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A951,'Updated Quanities'!F:I,5,0),R951)=\"\",R951,IFERROR(VLOOKUP('AUP Library'!A951,'Updated Quanities'!F:I,5,0),R951))","v":178.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A951,'Updated Quanities'!F:I,6,0),R951)=\"\",R951,IFERROR(VLOOKUP('AUP Library'!A951,'Updated Quanities'!F:I,6,0),R951))","v":178.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A951,'Updated Quanities'!F:I,7,0),R951)=\"\",R951,IFERROR(VLOOKUP('AUP Library'!A951,'Updated Quanities'!F:I,7,0),R951))","v":178.33},178.33,{"$f":"IFERROR(VLOOKUP('AUP Library'!A951,'Updated Quanities'!F:G,4,0),R951)","v":178.33}]
["713-16.55","Remove and Replace Sign","EA",95,95,95,95,95,95,95,95,95,95,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A952,'Updated Quanities'!F:I,4,0),R952)=\"\",R952,IFERROR(VLOOKUP('AUP Library'!A952,'Updated Quanities'!F:I,4,0),R952))","v":95},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A952,'Updated Quanities'!F:I,5,0),R952)=\"\",R952,IFERROR(VLOOKUP('AUP Library'!A952,'Updated Quanities'!F:I,5,0),R952))","v":95},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A952,'Updated Quanities'!F:I,6,0),R952)=\"\",R952,IFERROR(VLOOKUP('AUP Library'!A952,'Updated Quanities'!F:I,6,0),R952))","v":95},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A952,'Updated Quanities'!F:I,7,0),R952)=\"\",R952,IFERROR(VLOOKUP('AUP Library'!A952,'Updated Quanities'!F:I,7,0),R952))","v":95},95,{"$f":"IFERROR(VLOOKUP('AUP Library'!A952,'Updated Quanities'!F:G,4,0),R952)","v":95}]
["713-16.56","Remove and Replace Sign","EA",175,175,175,175,175,175,175,175,175,175,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A953,'Updated Quanities'!F:I,4,0),R953)=\"\",R953,IFERROR(VLOOKUP('AUP Library'!A953,'Updated Quanities'!F:I,4,0),R953))","v":175},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A953,'Updated Quanities'!F:I,5,0),R953)=\"\",R953,IFERROR(VLOOKUP('AUP Library'!A953,'Updated Quanities'!F:I,5,0),R953))","v":175},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A953,'Updated Quanities'!F:I,6,0),R953)=\"\",R953,IFERROR(VLOOKUP('AUP Library'!A953,'Updated Quanities'!F:I,6,0),R953))","v":175},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A953,'Updated Quanities'!F:I,7,0),R953)=\"\",R953,IFERROR(VLOOKUP('AUP Library'!A953,'Updated Quanities'!F:I,7,0),R953))","v":175},175,{"$f":"IFERROR(VLOOKUP('AUP Library'!A953,'Updated Quanities'!F:G,4,0),R953)","v":175}]
["713-16.57","Remove and Replace Sign","EA",145,145,145,145,145,145,145,145,145,145,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A954,'Updated Quanities'!F:I,4,0),R954)=\"\",R954,IFERROR(VLOOKUP('AUP Library'!A954,'Updated Quanities'!F:I,4,0),R954))","v":145},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A954,'Updated Quanities'!F:I,5,0),R954)=\"\",R954,IFERROR(VLOOKUP('AUP Library'!A954,'Updated Quanities'!F:I,5,0),R954))","v":145},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A954,'Updated Quanities'!F:I,6,0),R954)=\"\",R954,IFERROR(VLOOKUP('AUP Library'!A954,'Updated Quanities'!F:I,6,0),R954))","v":145},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A954,'Updated Quanities'!F:I,7,0),R954)=\"\",R954,IFERROR(VLOOKUP('AUP Library'!A954,'Updated Quanities'!F:I,7,0),R954))","v":145},145,{"$f":"IFERROR(VLOOKUP('AUP Library'!A954,'Updated Quanities'!F:G,4,0),R954)","v":145}]
["713-16.58","Remove and Replace Sign (Description)","EA",111.67,111.67,111.67,111.67,111.67,111.67,111.67,111.67,111.67,111.67,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A955,'Updated Quanities'!F:I,4,0),R955)=\"\",R955,IFERROR(VLOOKUP('AUP Library'!A955,'Updated Quanities'!F:I,4,0),R955))","v":111.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A955,'Updated Quanities'!F:I,5,0),R955)=\"\",R955,IFERROR(VLOOKUP('AUP Library'!A955,'Updated Quanities'!F:I,5,0),R955))","v":111.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A955,'Updated Quanities'!F:I,6,0),R955)=\"\",R955,IFERROR(VLOOKUP('AUP Library'!A955,'Updated Quanities'!F:I,6,0),R955))","v":111.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A955,'Updated Quanities'!F:I,7,0),R955)=\"\",R955,IFERROR(VLOOKUP('AUP Library'!A955,'Updated Quanities'!F:I,7,0),R955))","v":111.67},111.67,{"$f":"IFERROR(VLOOKUP('AUP Library'!A955,'Updated Quanities'!F:G,4,0),R955)","v":111.67}]
["713-16.59","Remove and Replace Sign (Description)","EA",217.5,217.5,217.5,217.5,217.5,217.5,217.5,217.5,217.5,217.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A956,'Updated Quanities'!F:I,4,0),R956)=\"\",R956,IFERROR(VLOOKUP('AUP Library'!A956,'Updated Quanities'!F:I,4,0),R956))","v":217.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A956,'Updated Quanities'!F:I,5,0),R956)=\"\",R956,IFERROR(VLOOKUP('AUP Library'!A956,'Updated Quanities'!F:I,5,0),R956))","v":217.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A956,'Updated Quanities'!F:I,6,0),R956)=\"\",R956,IFERROR(VLOOKUP('AUP Library'!A956,'Updated Quanities'!F:I,6,0),R956))","v":217.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A956,'Updated Quanities'!F:I,7,0),R956)=\"\",R956,IFERROR(VLOOKUP('AUP Library'!A956,'Updated Quanities'!F:I,7,0),R956))","v":217.5},217.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A956,'Updated Quanities'!F:G,4,0),R956)","v":217.5}]
["713-16.60","Remove and Replace Sign (Description)","EA",225,225,225,225,225,225,225,225,225,225,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A957,'Updated Quanities'!F:I,4,0),R957)=\"\",R957,IFERROR(VLOOKUP('AUP Library'!A957,'Updated Quanities'!F:I,4,0),R957))","v":225},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A957,'Updated Quanities'!F:I,5,0),R957)=\"\",R957,IFERROR(VLOOKUP('AUP Library'!A957,'Updated Quanities'!F:I,5,0),R957))","v":225},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A957,'Updated Quanities'!F:I,6,0),R957)=\"\",R957,IFERROR(VLOOKUP('AUP Library'!A957,'Updated Quanities'!F:I,6,0),R957))","v":225},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A957,'Updated Quanities'!F:I,7,0),R957)=\"\",R957,IFERROR(VLOOKUP('AUP Library'!A957,'Updated Quanities'!F:I,7,0),R957))","v":225},225,{"$f":"IFERROR(VLOOKUP('AUP Library'!A957,'Updated Quanities'!F:G,4,0),R957)","v":225}]
["713-17.02","Inst Aux Support for Exit Number Panel","EA",91.43,91.43,91.43,91.43,91.43,91.43,91.43,91.43,91.43,91.43,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A958,'Updated Quanities'!F:I,4,0),R958)=\"\",R958,IFERROR(VLOOKUP('AUP Library'!A958,'Updated Quanities'!F:I,4,0),R958))","v":91.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A958,'Updated Quanities'!F:I,5,0),R958)=\"\",R958,IFERROR(VLOOKUP('AUP Library'!A958,'Updated Quanities'!F:I,5,0),R958))","v":91.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A958,'Updated Quanities'!F:I,6,0),R958)=\"\",R958,IFERROR(VLOOKUP('AUP Library'!A958,'Updated Quanities'!F:I,6,0),R958))","v":91.43},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A958,'Updated Quanities'!F:I,7,0),R958)=\"\",R958,IFERROR(VLOOKUP('AUP Library'!A958,'Updated Quanities'!F:I,7,0),R958))","v":91.43},91.43,{"$f":"IFERROR(VLOOKUP('AUP Library'!A958,'Updated Quanities'!F:G,4,0),R958)","v":91.43}]
["713-17.04","Install Aux Support On Existing Sign","LF",7.18,7.18,7.18,7.18,7.18,7.18,7.18,7.18,7.18,7.18,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A959,'Updated Quanities'!F:I,4,0),R959)=\"\",R959,IFERROR(VLOOKUP('AUP Library'!A959,'Updated Quanities'!F:I,4,0),R959))","v":7.18},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A959,'Updated Quanities'!F:I,5,0),R959)=\"\",R959,IFERROR(VLOOKUP('AUP Library'!A959,'Updated Quanities'!F:I,5,0),R959))","v":7.18},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A959,'Updated Quanities'!F:I,6,0),R959)=\"\",R959,IFERROR(VLOOKUP('AUP Library'!A959,'Updated Quanities'!F:I,6,0),R959))","v":7.18},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A959,'Updated Quanities'!F:I,7,0),R959)=\"\",R959,IFERROR(VLOOKUP('AUP Library'!A959,'Updated Quanities'!F:I,7,0),R959))","v":7.18},7.18,{"$f":"IFERROR(VLOOKUP('AUP Library'!A959,'Updated Quanities'!F:G,4,0),R959)","v":7.18}]
["713-17.20","Overhead Sign Supp. Footing","LS",33305.5,33305.5,33305.5,33305.5,33305.5,33305.5,33305.5,33305.5,33305.5,33305.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A960,'Updated Quanities'!F:I,4,0),R960)=\"\",R960,IFERROR(VLOOKUP('AUP Library'!A960,'Updated Quanities'!F:I,4,0),R960))","v":33305.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A960,'Updated Quanities'!F:I,5,0),R960)=\"\",R960,IFERROR(VLOOKUP('AUP Library'!A960,'Updated Quanities'!F:I,5,0),R960))","v":33305.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A960,'Updated Quanities'!F:I,6,0),R960)=\"\",R960,IFERROR(VLOOKUP('AUP Library'!A960,'Updated Quanities'!F:I,6,0),R960))","v":33305.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A960,'Updated Quanities'!F:I,7,0),R960)=\"\",R960,IFERROR(VLOOKUP('AUP Library'!A960,'Updated Quanities'!F:I,7,0),R960))","v":33305.5},33305.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A960,'Updated Quanities'!F:G,4,0),R960)","v":33305.5}]
["713-17.50","Sign Mounted on Bridge Parapet","EA",664.69,664.69,664.69,664.69,664.69,664.69,664.69,664.69,664.69,664.69,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A961,'Updated Quanities'!F:I,4,0),R961)=\"\",R961,IFERROR(VLOOKUP('AUP Library'!A961,'Updated Quanities'!F:I,4,0),R961))","v":664.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A961,'Updated Quanities'!F:I,5,0),R961)=\"\",R961,IFERROR(VLOOKUP('AUP Library'!A961,'Updated Quanities'!F:I,5,0),R961))","v":664.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A961,'Updated Quanities'!F:I,6,0),R961)=\"\",R961,IFERROR(VLOOKUP('AUP Library'!A961,'Updated Quanities'!F:I,6,0),R961))","v":664.69},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A961,'Updated Quanities'!F:I,7,0),R961)=\"\",R961,IFERROR(VLOOKUP('AUP Library'!A961,'Updated Quanities'!F:I,7,0),R961))","v":664.69},664.69,{"$f":"IFERROR(VLOOKUP('AUP Library'!A961,'Updated Quanities'!F:G,4,0),R961)","v":664.69}]
["713-20.01","Traf Sign Base","EA",350,350,350,350,350,350,350,350,350,350,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A962,'Updated Quanities'!F:I,4,0),R962)=\"\",R962,IFERROR(VLOOKUP('AUP Library'!A962,'Updated Quanities'!F:I,4,0),R962))","v":350},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A962,'Updated Quanities'!F:I,5,0),R962)=\"\",R962,IFERROR(VLOOKUP('AUP Library'!A962,'Updated Quanities'!F:I,5,0),R962))","v":350},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A962,'Updated Quanities'!F:I,6,0),R962)=\"\",R962,IFERROR(VLOOKUP('AUP Library'!A962,'Updated Quanities'!F:I,6,0),R962))","v":350},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A962,'Updated Quanities'!F:I,7,0),R962)=\"\",R962,IFERROR(VLOOKUP('AUP Library'!A962,'Updated Quanities'!F:I,7,0),R962))","v":350},350,{"$f":"IFERROR(VLOOKUP('AUP Library'!A962,'Updated Quanities'!F:G,4,0),R962)","v":350}]
["713-20.02","Architectural Traf Sign Pole & Frame","EA",940,940,940,940,940,940,940,940,940,940,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A963,'Updated Quanities'!F:I,4,0),R963)=\"\",R963,IFERROR(VLOOKUP('AUP Library'!A963,'Updated Quanities'!F:I,4,0),R963))","v":940},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A963,'Updated Quanities'!F:I,5,0),R963)=\"\",R963,IFERROR(VLOOKUP('AUP Library'!A963,'Updated Quanities'!F:I,5,0),R963))","v":940},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A963,'Updated Quanities'!F:I,6,0),R963)=\"\",R963,IFERROR(VLOOKUP('AUP Library'!A963,'Updated Quanities'!F:I,6,0),R963))","v":940},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A963,'Updated Quanities'!F:I,7,0),R963)=\"\",R963,IFERROR(VLOOKUP('AUP Library'!A963,'Updated Quanities'!F:I,7,0),R963))","v":940},940,{"$f":"IFERROR(VLOOKUP('AUP Library'!A963,'Updated Quanities'!F:G,4,0),R963)","v":940}]
["713-20.30","Sign Adjustments","EA",257.41000000000003,257.41000000000003,257.41000000000003,257.41000000000003,257.41000000000003,257.41000000000003,257.41000000000003,257.41000000000003,257.41000000000003,257.41000000000003,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A964,'Updated Quanities'!F:I,4,0),R964)=\"\",R964,IFERROR(VLOOKUP('AUP Library'!A964,'Updated Quanities'!F:I,4,0),R964))","v":257.41000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A964,'Updated Quanities'!F:I,5,0),R964)=\"\",R964,IFERROR(VLOOKUP('AUP Library'!A964,'Updated Quanities'!F:I,5,0),R964))","v":257.41000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A964,'Updated Quanities'!F:I,6,0),R964)=\"\",R964,IFERROR(VLOOKUP('AUP Library'!A964,'Updated Quanities'!F:I,6,0),R964))","v":257.41000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A964,'Updated Quanities'!F:I,7,0),R964)=\"\",R964,IFERROR(VLOOKUP('AUP Library'!A964,'Updated Quanities'!F:I,7,0),R964))","v":257.41000000000003},257.41000000000003,{"$f":"IFERROR(VLOOKUP('AUP Library'!A964,'Updated Quanities'!F:G,4,0),R964)","v":257.41000000000003}]
["713-30.02","Bridge Mounted Sign Support","LB",8.64,8.64,8.64,8.64,8.64,8.64,8.64,8.64,8.64,8.64,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A965,'Updated Quanities'!F:I,4,0),R965)=\"\",R965,IFERROR(VLOOKUP('AUP Library'!A965,'Updated Quanities'!F:I,4,0),R965))","v":8.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A965,'Updated Quanities'!F:I,5,0),R965)=\"\",R965,IFERROR(VLOOKUP('AUP Library'!A965,'Updated Quanities'!F:I,5,0),R965))","v":8.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A965,'Updated Quanities'!F:I,6,0),R965)=\"\",R965,IFERROR(VLOOKUP('AUP Library'!A965,'Updated Quanities'!F:I,6,0),R965))","v":8.64},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A965,'Updated Quanities'!F:I,7,0),R965)=\"\",R965,IFERROR(VLOOKUP('AUP Library'!A965,'Updated Quanities'!F:I,7,0),R965))","v":8.64},8.64,{"$f":"IFERROR(VLOOKUP('AUP Library'!A965,'Updated Quanities'!F:G,4,0),R965)","v":8.64}]
["713-30.05","Barrier Mounted Square Tube Sign Support","LB",6,6,6,6,6,6,6,6,6,6,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A966,'Updated Quanities'!F:I,4,0),R966)=\"\",R966,IFERROR(VLOOKUP('AUP Library'!A966,'Updated Quanities'!F:I,4,0),R966))","v":6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A966,'Updated Quanities'!F:I,5,0),R966)=\"\",R966,IFERROR(VLOOKUP('AUP Library'!A966,'Updated Quanities'!F:I,5,0),R966))","v":6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A966,'Updated Quanities'!F:I,6,0),R966)=\"\",R966,IFERROR(VLOOKUP('AUP Library'!A966,'Updated Quanities'!F:I,6,0),R966))","v":6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A966,'Updated Quanities'!F:I,7,0),R966)=\"\",R966,IFERROR(VLOOKUP('AUP Library'!A966,'Updated Quanities'!F:I,7,0),R966))","v":6},6,{"$f":"IFERROR(VLOOKUP('AUP Library'!A966,'Updated Quanities'!F:G,4,0),R966)","v":6}]
["713-30.08","Barrier Mounted Perf/Knockout Sign Supp","LB",10.15,10.15,10.15,10.15,10.15,10.15,10.15,10.15,10.15,10.15,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A967,'Updated Quanities'!F:I,4,0),R967)=\"\",R967,IFERROR(VLOOKUP('AUP Library'!A967,'Updated Quanities'!F:I,4,0),R967))","v":10.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A967,'Updated Quanities'!F:I,5,0),R967)=\"\",R967,IFERROR(VLOOKUP('AUP Library'!A967,'Updated Quanities'!F:I,5,0),R967))","v":10.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A967,'Updated Quanities'!F:I,6,0),R967)=\"\",R967,IFERROR(VLOOKUP('AUP Library'!A967,'Updated Quanities'!F:I,6,0),R967))","v":10.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A967,'Updated Quanities'!F:I,7,0),R967)=\"\",R967,IFERROR(VLOOKUP('AUP Library'!A967,'Updated Quanities'!F:I,7,0),R967))","v":10.15},10.15,{"$f":"IFERROR(VLOOKUP('AUP Library'!A967,'Updated Quanities'!F:G,4,0),R967)","v":10.15}]
["713-30.09","Barrier Mounted Sign Support (Descr)","EA",291.87,291.87,291.87,291.87,291.87,291.87,291.87,291.87,291.87,291.87,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A968,'Updated Quanities'!F:I,4,0),R968)=\"\",R968,IFERROR(VLOOKUP('AUP Library'!A968,'Updated Quanities'!F:I,4,0),R968))","v":291.87},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A968,'Updated Quanities'!F:I,5,0),R968)=\"\",R968,IFERROR(VLOOKUP('AUP Library'!A968,'Updated Quanities'!F:I,5,0),R968))","v":291.87},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A968,'Updated Quanities'!F:I,6,0),R968)=\"\",R968,IFERROR(VLOOKUP('AUP Library'!A968,'Updated Quanities'!F:I,6,0),R968))","v":291.87},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A968,'Updated Quanities'!F:I,7,0),R968)=\"\",R968,IFERROR(VLOOKUP('AUP Library'!A968,'Updated Quanities'!F:I,7,0),R968))","v":291.87},291.87,{"$f":"IFERROR(VLOOKUP('AUP Library'!A968,'Updated Quanities'!F:G,4,0),R968)","v":291.87}]
["713-30.10","Barrier Mounted Sign Support (Descr)","EA",214.51,214.51,214.51,214.51,214.51,214.51,214.51,214.51,214.51,214.51,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A969,'Updated Quanities'!F:I,4,0),R969)=\"\",R969,IFERROR(VLOOKUP('AUP Library'!A969,'Updated Quanities'!F:I,4,0),R969))","v":214.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A969,'Updated Quanities'!F:I,5,0),R969)=\"\",R969,IFERROR(VLOOKUP('AUP Library'!A969,'Updated Quanities'!F:I,5,0),R969))","v":214.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A969,'Updated Quanities'!F:I,6,0),R969)=\"\",R969,IFERROR(VLOOKUP('AUP Library'!A969,'Updated Quanities'!F:I,6,0),R969))","v":214.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A969,'Updated Quanities'!F:I,7,0),R969)=\"\",R969,IFERROR(VLOOKUP('AUP Library'!A969,'Updated Quanities'!F:I,7,0),R969))","v":214.51},214.51,{"$f":"IFERROR(VLOOKUP('AUP Library'!A969,'Updated Quanities'!F:G,4,0),R969)","v":214.51}]
["713-99.91","Signs","LS",7100,7100,7100,7100,7100,7100,7100,7100,7100,7100,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A970,'Updated Quanities'!F:I,4,0),R970)=\"\",R970,IFERROR(VLOOKUP('AUP Library'!A970,'Updated Quanities'!F:I,4,0),R970))","v":7100},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A970,'Updated Quanities'!F:I,5,0),R970)=\"\",R970,IFERROR(VLOOKUP('AUP Library'!A970,'Updated Quanities'!F:I,5,0),R970))","v":7100},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A970,'Updated Quanities'!F:I,6,0),R970)=\"\",R970,IFERROR(VLOOKUP('AUP Library'!A970,'Updated Quanities'!F:I,6,0),R970))","v":7100},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A970,'Updated Quanities'!F:I,7,0),R970)=\"\",R970,IFERROR(VLOOKUP('AUP Library'!A970,'Updated Quanities'!F:I,7,0),R970))","v":7100},7100,{"$f":"IFERROR(VLOOKUP('AUP Library'!A970,'Updated Quanities'!F:G,4,0),R970)","v":7100}]
["Not Listed","Signs","LS",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IFERROR(VLOOKUP('AUP Library'!A971,'Updated Quanities'!F:G,4,0),R971)","v":0}]
[]
[]
["Pavement Markings"]
["N/A","Pavement Markings (Widening Projects)","LS"]
["716-01.05","Temporary Raised Pavement Marker","EA",8.25,8.25,8.25,8.25,8.25,8.25,8.25,8.25,8.25,8.25,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A976,'Updated Quanities'!F:I,4,0),R976)=\"\",R976,IFERROR(VLOOKUP('AUP Library'!A976,'Updated Quanities'!F:I,4,0),R976))","v":8.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A976,'Updated Quanities'!F:I,5,0),R976)=\"\",R976,IFERROR(VLOOKUP('AUP Library'!A976,'Updated Quanities'!F:I,5,0),R976))","v":8.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A976,'Updated Quanities'!F:I,6,0),R976)=\"\",R976,IFERROR(VLOOKUP('AUP Library'!A976,'Updated Quanities'!F:I,6,0),R976))","v":8.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A976,'Updated Quanities'!F:I,7,0),R976)=\"\",R976,IFERROR(VLOOKUP('AUP Library'!A976,'Updated Quanities'!F:I,7,0),R976))","v":8.25},8.25,{"$f":"IFERROR(VLOOKUP('AUP Library'!A976,'Updated Quanities'!F:G,4,0),R976)","v":8.25}]
["716-01.06","Temporary Raised Pavement Marker, White","EA",10.62,10.62,10.62,10.62,10.62,10.62,10.62,10.62,10.62,10.62,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A977,'Updated Quanities'!F:I,4,0),R977)=\"\",R977,IFERROR(VLOOKUP('AUP Library'!A977,'Updated Quanities'!F:I,4,0),R977))","v":10.62},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A977,'Updated Quanities'!F:I,5,0),R977)=\"\",R977,IFERROR(VLOOKUP('AUP Library'!A977,'Updated Quanities'!F:I,5,0),R977))","v":10.62},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A977,'Updated Quanities'!F:I,6,0),R977)=\"\",R977,IFERROR(VLOOKUP('AUP Library'!A977,'Updated Quanities'!F:I,6,0),R977))","v":10.62},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A977,'Updated Quanities'!F:I,7,0),R977)=\"\",R977,IFERROR(VLOOKUP('AUP Library'!A977,'Updated Quanities'!F:I,7,0),R977))","v":10.62},10.62,{"$f":"IFERROR(VLOOKUP('AUP Library'!A977,'Updated Quanities'!F:G,4,0),R977)","v":10.62}]
["716-01.07","Temporary Raised Pavement Marker, Yellow","EA",11,11,11,11,11,11,11,11,11,11,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A978,'Updated Quanities'!F:I,4,0),R978)=\"\",R978,IFERROR(VLOOKUP('AUP Library'!A978,'Updated Quanities'!F:I,4,0),R978))","v":11},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A978,'Updated Quanities'!F:I,5,0),R978)=\"\",R978,IFERROR(VLOOKUP('AUP Library'!A978,'Updated Quanities'!F:I,5,0),R978))","v":11},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A978,'Updated Quanities'!F:I,6,0),R978)=\"\",R978,IFERROR(VLOOKUP('AUP Library'!A978,'Updated Quanities'!F:I,6,0),R978))","v":11},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A978,'Updated Quanities'!F:I,7,0),R978)=\"\",R978,IFERROR(VLOOKUP('AUP Library'!A978,'Updated Quanities'!F:I,7,0),R978))","v":11},11,{"$f":"IFERROR(VLOOKUP('AUP Library'!A978,'Updated Quanities'!F:G,4,0),R978)","v":11}]
["716-01.10","Snowplowable Reflective Marker","EA",34.53,34.53,34.53,34.53,34.53,34.53,34.53,34.53,34.53,34.53,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A979,'Updated Quanities'!F:I,4,0),R979)=\"\",R979,IFERROR(VLOOKUP('AUP Library'!A979,'Updated Quanities'!F:I,4,0),R979))","v":34.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A979,'Updated Quanities'!F:I,5,0),R979)=\"\",R979,IFERROR(VLOOKUP('AUP Library'!A979,'Updated Quanities'!F:I,5,0),R979))","v":34.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A979,'Updated Quanities'!F:I,6,0),R979)=\"\",R979,IFERROR(VLOOKUP('AUP Library'!A979,'Updated Quanities'!F:I,6,0),R979))","v":34.53},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A979,'Updated Quanities'!F:I,7,0),R979)=\"\",R979,IFERROR(VLOOKUP('AUP Library'!A979,'Updated Quanities'!F:I,7,0),R979))","v":34.53},34.53,{"$f":"IFERROR(VLOOKUP('AUP Library'!A979,'Updated Quanities'!F:G,4,0),R979)","v":34.53}]
["716-01.11","Raised Pvmt Markers (Bi-Dir, 1 Color)","EA",5.76,5.76,5.76,5.76,5.76,5.76,5.76,5.76,5.76,5.76,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A980,'Updated Quanities'!F:I,4,0),R980)=\"\",R980,IFERROR(VLOOKUP('AUP Library'!A980,'Updated Quanities'!F:I,4,0),R980))","v":5.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A980,'Updated Quanities'!F:I,5,0),R980)=\"\",R980,IFERROR(VLOOKUP('AUP Library'!A980,'Updated Quanities'!F:I,5,0),R980))","v":5.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A980,'Updated Quanities'!F:I,6,0),R980)=\"\",R980,IFERROR(VLOOKUP('AUP Library'!A980,'Updated Quanities'!F:I,6,0),R980))","v":5.76},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A980,'Updated Quanities'!F:I,7,0),R980)=\"\",R980,IFERROR(VLOOKUP('AUP Library'!A980,'Updated Quanities'!F:I,7,0),R980))","v":5.76},5.76,{"$f":"IFERROR(VLOOKUP('AUP Library'!A980,'Updated Quanities'!F:G,4,0),R980)","v":5.76}]
["716-01.12","Raised Pvmt Markers (Mono-Dir, 1 Color)","EA",9.5299999999999994,9.5299999999999994,9.5299999999999994,9.5299999999999994,9.5299999999999994,9.5299999999999994,9.5299999999999994,9.5299999999999994,9.5299999999999994,9.5299999999999994,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A981,'Updated Quanities'!F:I,4,0),R981)=\"\",R981,IFERROR(VLOOKUP('AUP Library'!A981,'Updated Quanities'!F:I,4,0),R981))","v":9.5299999999999994},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A981,'Updated Quanities'!F:I,5,0),R981)=\"\",R981,IFERROR(VLOOKUP('AUP Library'!A981,'Updated Quanities'!F:I,5,0),R981))","v":9.5299999999999994},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A981,'Updated Quanities'!F:I,6,0),R981)=\"\",R981,IFERROR(VLOOKUP('AUP Library'!A981,'Updated Quanities'!F:I,6,0),R981))","v":9.5299999999999994},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A981,'Updated Quanities'!F:I,7,0),R981)=\"\",R981,IFERROR(VLOOKUP('AUP Library'!A981,'Updated Quanities'!F:I,7,0),R981))","v":9.5299999999999994},9.5299999999999994,{"$f":"IFERROR(VLOOKUP('AUP Library'!A981,'Updated Quanities'!F:G,4,0),R981)","v":9.5299999999999994}]
["716-01.13","Raised Pvmt Markers (Bi-Dir, 2 Color)","EA",4,4,4,4,4,4,4,4,4,4,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A982,'Updated Quanities'!F:I,4,0),R982)=\"\",R982,IFERROR(VLOOKUP('AUP Library'!A982,'Updated Quanities'!F:I,4,0),R982))","v":4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A982,'Updated Quanities'!F:I,5,0),R982)=\"\",R982,IFERROR(VLOOKUP('AUP Library'!A982,'Updated Quanities'!F:I,5,0),R982))","v":4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A982,'Updated Quanities'!F:I,6,0),R982)=\"\",R982,IFERROR(VLOOKUP('AUP Library'!A982,'Updated Quanities'!F:I,6,0),R982))","v":4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A982,'Updated Quanities'!F:I,7,0),R982)=\"\",R982,IFERROR(VLOOKUP('AUP Library'!A982,'Updated Quanities'!F:I,7,0),R982))","v":4},4,{"$f":"IFERROR(VLOOKUP('AUP Library'!A982,'Updated Quanities'!F:G,4,0),R982)","v":4}]
["716-01.21","Snwplwble Pvmt Mrkrs (Bi-Dir)(1 Color)","EA",28.1,28.1,28.1,28.1,28.1,28.1,28.1,28.1,28.1,28.1,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A983,'Updated Quanities'!F:I,4,0),R983)=\"\",R983,IFERROR(VLOOKUP('AUP Library'!A983,'Updated Quanities'!F:I,4,0),R983))","v":28.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A983,'Updated Quanities'!F:I,5,0),R983)=\"\",R983,IFERROR(VLOOKUP('AUP Library'!A983,'Updated Quanities'!F:I,5,0),R983))","v":28.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A983,'Updated Quanities'!F:I,6,0),R983)=\"\",R983,IFERROR(VLOOKUP('AUP Library'!A983,'Updated Quanities'!F:I,6,0),R983))","v":28.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A983,'Updated Quanities'!F:I,7,0),R983)=\"\",R983,IFERROR(VLOOKUP('AUP Library'!A983,'Updated Quanities'!F:I,7,0),R983))","v":28.1},28.1,{"$f":"IFERROR(VLOOKUP('AUP Library'!A983,'Updated Quanities'!F:G,4,0),R983)","v":28.1}]
["716-01.22","Snwplwble Pvmt Mrkrs (Mono-Dir)(1 Color)","EA",27.39,27.39,27.39,27.39,27.39,27.39,27.39,27.39,27.39,27.39,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A984,'Updated Quanities'!F:I,4,0),R984)=\"\",R984,IFERROR(VLOOKUP('AUP Library'!A984,'Updated Quanities'!F:I,4,0),R984))","v":27.39},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A984,'Updated Quanities'!F:I,5,0),R984)=\"\",R984,IFERROR(VLOOKUP('AUP Library'!A984,'Updated Quanities'!F:I,5,0),R984))","v":27.39},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A984,'Updated Quanities'!F:I,6,0),R984)=\"\",R984,IFERROR(VLOOKUP('AUP Library'!A984,'Updated Quanities'!F:I,6,0),R984))","v":27.39},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A984,'Updated Quanities'!F:I,7,0),R984)=\"\",R984,IFERROR(VLOOKUP('AUP Library'!A984,'Updated Quanities'!F:I,7,0),R984))","v":27.39},27.39,{"$f":"IFERROR(VLOOKUP('AUP Library'!A984,'Updated Quanities'!F:G,4,0),R984)","v":27.39}]
["716-01.23","Snwplwble Pvmt Mrkrs (Bi-Dir)(2 Color)","EA",29.6,29.6,29.6,29.6,29.6,29.6,29.6,29.6,29.6,29.6,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A985,'Updated Quanities'!F:I,4,0),R985)=\"\",R985,IFERROR(VLOOKUP('AUP Library'!A985,'Updated Quanities'!F:I,4,0),R985))","v":29.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A985,'Updated Quanities'!F:I,5,0),R985)=\"\",R985,IFERROR(VLOOKUP('AUP Library'!A985,'Updated Quanities'!F:I,5,0),R985))","v":29.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A985,'Updated Quanities'!F:I,6,0),R985)=\"\",R985,IFERROR(VLOOKUP('AUP Library'!A985,'Updated Quanities'!F:I,6,0),R985))","v":29.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A985,'Updated Quanities'!F:I,7,0),R985)=\"\",R985,IFERROR(VLOOKUP('AUP Library'!A985,'Updated Quanities'!F:I,7,0),R985))","v":29.6},29.6,{"$f":"IFERROR(VLOOKUP('AUP Library'!A985,'Updated Quanities'!F:G,4,0),R985)","v":29.6}]
["716-02.01","PLASTIC PAVEMENT MARKING (4\" LINE)","LM",3172.32,3172.32,3172.32,3172.32,3172.32,3172.32,3172.32,3172.32,3172.32,3172.32,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A986,'Updated Quanities'!F:I,4,0),R986)=\"\",R986,IFERROR(VLOOKUP('AUP Library'!A986,'Updated Quanities'!F:I,4,0),R986))","v":3172.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A986,'Updated Quanities'!F:I,5,0),R986)=\"\",R986,IFERROR(VLOOKUP('AUP Library'!A986,'Updated Quanities'!F:I,5,0),R986))","v":3172.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A986,'Updated Quanities'!F:I,6,0),R986)=\"\",R986,IFERROR(VLOOKUP('AUP Library'!A986,'Updated Quanities'!F:I,6,0),R986))","v":3172.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A986,'Updated Quanities'!F:I,7,0),R986)=\"\",R986,IFERROR(VLOOKUP('AUP Library'!A986,'Updated Quanities'!F:I,7,0),R986))","v":3172.32},3172.32,{"$f":"IFERROR(VLOOKUP('AUP Library'!A986,'Updated Quanities'!F:G,4,0),R986)","v":3172.32}]
["716-02.02","PLASTIC PAVEMENT MKG (8\" BARRIER LINE)","LF",2.95,2.95,2.95,2.95,2.95,2.95,2.95,2.95,2.95,2.95,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A987,'Updated Quanities'!F:I,4,0),R987)=\"\",R987,IFERROR(VLOOKUP('AUP Library'!A987,'Updated Quanities'!F:I,4,0),R987))","v":2.95},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A987,'Updated Quanities'!F:I,5,0),R987)=\"\",R987,IFERROR(VLOOKUP('AUP Library'!A987,'Updated Quanities'!F:I,5,0),R987))","v":2.95},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A987,'Updated Quanities'!F:I,6,0),R987)=\"\",R987,IFERROR(VLOOKUP('AUP Library'!A987,'Updated Quanities'!F:I,6,0),R987))","v":2.95},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A987,'Updated Quanities'!F:I,7,0),R987)=\"\",R987,IFERROR(VLOOKUP('AUP Library'!A987,'Updated Quanities'!F:I,7,0),R987))","v":2.95},2.95,{"$f":"IFERROR(VLOOKUP('AUP Library'!A987,'Updated Quanities'!F:G,4,0),R987)","v":2.95}]
["716-02.03","Plastic Pavement Marking (Cross-Walk)","LF",9.81,9.81,9.81,9.81,9.81,9.81,9.81,9.81,9.81,9.81,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A988,'Updated Quanities'!F:I,4,0),R988)=\"\",R988,IFERROR(VLOOKUP('AUP Library'!A988,'Updated Quanities'!F:I,4,0),R988))","v":9.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A988,'Updated Quanities'!F:I,5,0),R988)=\"\",R988,IFERROR(VLOOKUP('AUP Library'!A988,'Updated Quanities'!F:I,5,0),R988))","v":9.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A988,'Updated Quanities'!F:I,6,0),R988)=\"\",R988,IFERROR(VLOOKUP('AUP Library'!A988,'Updated Quanities'!F:I,6,0),R988))","v":9.81},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A988,'Updated Quanities'!F:I,7,0),R988)=\"\",R988,IFERROR(VLOOKUP('AUP Library'!A988,'Updated Quanities'!F:I,7,0),R988))","v":9.81},9.81,{"$f":"IFERROR(VLOOKUP('AUP Library'!A988,'Updated Quanities'!F:G,4,0),R988)","v":9.81}]
["716-02.04","Plastic Pavement Marking (Chnz Striping)","SY",18.55,18.55,18.55,18.55,18.55,18.55,18.55,18.55,18.55,18.55,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A989,'Updated Quanities'!F:I,4,0),R989)=\"\",R989,IFERROR(VLOOKUP('AUP Library'!A989,'Updated Quanities'!F:I,4,0),R989))","v":18.55},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A989,'Updated Quanities'!F:I,5,0),R989)=\"\",R989,IFERROR(VLOOKUP('AUP Library'!A989,'Updated Quanities'!F:I,5,0),R989))","v":18.55},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A989,'Updated Quanities'!F:I,6,0),R989)=\"\",R989,IFERROR(VLOOKUP('AUP Library'!A989,'Updated Quanities'!F:I,6,0),R989))","v":18.55},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A989,'Updated Quanities'!F:I,7,0),R989)=\"\",R989,IFERROR(VLOOKUP('AUP Library'!A989,'Updated Quanities'!F:I,7,0),R989))","v":18.55},18.55,{"$f":"IFERROR(VLOOKUP('AUP Library'!A989,'Updated Quanities'!F:G,4,0),R989)","v":18.55}]
["716-02.05","Plastic Pavement Marking (Stop Line)","LF",11.37,11.37,11.37,11.37,11.37,11.37,11.37,11.37,11.37,11.37,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A990,'Updated Quanities'!F:I,4,0),R990)=\"\",R990,IFERROR(VLOOKUP('AUP Library'!A990,'Updated Quanities'!F:I,4,0),R990))","v":11.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A990,'Updated Quanities'!F:I,5,0),R990)=\"\",R990,IFERROR(VLOOKUP('AUP Library'!A990,'Updated Quanities'!F:I,5,0),R990))","v":11.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A990,'Updated Quanities'!F:I,6,0),R990)=\"\",R990,IFERROR(VLOOKUP('AUP Library'!A990,'Updated Quanities'!F:I,6,0),R990))","v":11.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A990,'Updated Quanities'!F:I,7,0),R990)=\"\",R990,IFERROR(VLOOKUP('AUP Library'!A990,'Updated Quanities'!F:I,7,0),R990))","v":11.37},11.37,{"$f":"IFERROR(VLOOKUP('AUP Library'!A990,'Updated Quanities'!F:G,4,0),R990)","v":11.37}]
["716-02.06","Plastic Pavement Marking (Turn Lane Arrow)","EA",138.38,138.38,138.38,138.38,138.38,138.38,138.38,138.38,138.38,138.38,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A991,'Updated Quanities'!F:I,4,0),R991)=\"\",R991,IFERROR(VLOOKUP('AUP Library'!A991,'Updated Quanities'!F:I,4,0),R991))","v":138.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A991,'Updated Quanities'!F:I,5,0),R991)=\"\",R991,IFERROR(VLOOKUP('AUP Library'!A991,'Updated Quanities'!F:I,5,0),R991))","v":138.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A991,'Updated Quanities'!F:I,6,0),R991)=\"\",R991,IFERROR(VLOOKUP('AUP Library'!A991,'Updated Quanities'!F:I,6,0),R991))","v":138.38},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A991,'Updated Quanities'!F:I,7,0),R991)=\"\",R991,IFERROR(VLOOKUP('AUP Library'!A991,'Updated Quanities'!F:I,7,0),R991))","v":138.38},138.38,{"$f":"IFERROR(VLOOKUP('AUP Library'!A991,'Updated Quanities'!F:G,4,0),R991)","v":138.38}]
["716-02.07","Plastic Pavement Marking (24\" Barrier Line)","LF",11.52,11.52,11.52,11.52,11.52,11.52,11.52,11.52,11.52,11.52,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A992,'Updated Quanities'!F:I,4,0),R992)=\"\",R992,IFERROR(VLOOKUP('AUP Library'!A992,'Updated Quanities'!F:I,4,0),R992))","v":11.52},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A992,'Updated Quanities'!F:I,5,0),R992)=\"\",R992,IFERROR(VLOOKUP('AUP Library'!A992,'Updated Quanities'!F:I,5,0),R992))","v":11.52},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A992,'Updated Quanities'!F:I,6,0),R992)=\"\",R992,IFERROR(VLOOKUP('AUP Library'!A992,'Updated Quanities'!F:I,6,0),R992))","v":11.52},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A992,'Updated Quanities'!F:I,7,0),R992)=\"\",R992,IFERROR(VLOOKUP('AUP Library'!A992,'Updated Quanities'!F:I,7,0),R992))","v":11.52},11.52,{"$f":"IFERROR(VLOOKUP('AUP Library'!A992,'Updated Quanities'!F:G,4,0),R992)","v":11.52}]
["716-02.08","Plastic Pavement Marking (8\" Dotted Line)","LF",6.56,6.56,6.56,6.56,6.56,6.56,6.56,6.56,6.56,6.56,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A993,'Updated Quanities'!F:I,4,0),R993)=\"\",R993,IFERROR(VLOOKUP('AUP Library'!A993,'Updated Quanities'!F:I,4,0),R993))","v":6.56},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A993,'Updated Quanities'!F:I,5,0),R993)=\"\",R993,IFERROR(VLOOKUP('AUP Library'!A993,'Updated Quanities'!F:I,5,0),R993))","v":6.56},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A993,'Updated Quanities'!F:I,6,0),R993)=\"\",R993,IFERROR(VLOOKUP('AUP Library'!A993,'Updated Quanities'!F:I,6,0),R993))","v":6.56},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A993,'Updated Quanities'!F:I,7,0),R993)=\"\",R993,IFERROR(VLOOKUP('AUP Library'!A993,'Updated Quanities'!F:I,7,0),R993))","v":6.56},6.56,{"$f":"IFERROR(VLOOKUP('AUP Library'!A993,'Updated Quanities'!F:G,4,0),R993)","v":6.56}]
["716-02.09","Plastic Pavement Marking (Longitudinal X-Walk)","LF",22.27,22.27,22.27,22.27,22.27,22.27,22.27,22.27,22.27,22.27,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A994,'Updated Quanities'!F:I,4,0),R994)=\"\",R994,IFERROR(VLOOKUP('AUP Library'!A994,'Updated Quanities'!F:I,4,0),R994))","v":22.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A994,'Updated Quanities'!F:I,5,0),R994)=\"\",R994,IFERROR(VLOOKUP('AUP Library'!A994,'Updated Quanities'!F:I,5,0),R994))","v":22.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A994,'Updated Quanities'!F:I,6,0),R994)=\"\",R994,IFERROR(VLOOKUP('AUP Library'!A994,'Updated Quanities'!F:I,6,0),R994))","v":22.27},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A994,'Updated Quanities'!F:I,7,0),R994)=\"\",R994,IFERROR(VLOOKUP('AUP Library'!A994,'Updated Quanities'!F:I,7,0),R994))","v":22.27},22.27,{"$f":"IFERROR(VLOOKUP('AUP Library'!A994,'Updated Quanities'!F:G,4,0),R994)","v":22.27}]
["716-02.13","Plastic Pavement Marking (Cross-Walk)","SF",10.97,10.97,10.97,10.97,10.97,10.97,10.97,10.97,10.97,10.97,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A995,'Updated Quanities'!F:I,4,0),R995)=\"\",R995,IFERROR(VLOOKUP('AUP Library'!A995,'Updated Quanities'!F:I,4,0),R995))","v":10.97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A995,'Updated Quanities'!F:I,5,0),R995)=\"\",R995,IFERROR(VLOOKUP('AUP Library'!A995,'Updated Quanities'!F:I,5,0),R995))","v":10.97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A995,'Updated Quanities'!F:I,6,0),R995)=\"\",R995,IFERROR(VLOOKUP('AUP Library'!A995,'Updated Quanities'!F:I,6,0),R995))","v":10.97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A995,'Updated Quanities'!F:I,7,0),R995)=\"\",R995,IFERROR(VLOOKUP('AUP Library'!A995,'Updated Quanities'!F:I,7,0),R995))","v":10.97},10.97,{"$f":"IFERROR(VLOOKUP('AUP Library'!A995,'Updated Quanities'!F:G,4,0),R995)","v":10.97}]
["716-03.01","Plastic Word Pavement Marking (Only)","EA",207.32,207.32,207.32,207.32,207.32,207.32,207.32,207.32,207.32,207.32,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A996,'Updated Quanities'!F:I,4,0),R996)=\"\",R996,IFERROR(VLOOKUP('AUP Library'!A996,'Updated Quanities'!F:I,4,0),R996))","v":207.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A996,'Updated Quanities'!F:I,5,0),R996)=\"\",R996,IFERROR(VLOOKUP('AUP Library'!A996,'Updated Quanities'!F:I,5,0),R996))","v":207.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A996,'Updated Quanities'!F:I,6,0),R996)=\"\",R996,IFERROR(VLOOKUP('AUP Library'!A996,'Updated Quanities'!F:I,6,0),R996))","v":207.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A996,'Updated Quanities'!F:I,7,0),R996)=\"\",R996,IFERROR(VLOOKUP('AUP Library'!A996,'Updated Quanities'!F:I,7,0),R996))","v":207.32},207.32,{"$f":"IFERROR(VLOOKUP('AUP Library'!A996,'Updated Quanities'!F:G,4,0),R996)","v":207.32}]
["716-03.02","Plastic Word Pavement Marking (RXR)","EA",360.08,360.08,360.08,360.08,360.08,360.08,360.08,360.08,360.08,360.08,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A997,'Updated Quanities'!F:I,4,0),R997)=\"\",R997,IFERROR(VLOOKUP('AUP Library'!A997,'Updated Quanities'!F:I,4,0),R997))","v":360.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A997,'Updated Quanities'!F:I,5,0),R997)=\"\",R997,IFERROR(VLOOKUP('AUP Library'!A997,'Updated Quanities'!F:I,5,0),R997))","v":360.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A997,'Updated Quanities'!F:I,6,0),R997)=\"\",R997,IFERROR(VLOOKUP('AUP Library'!A997,'Updated Quanities'!F:I,6,0),R997))","v":360.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A997,'Updated Quanities'!F:I,7,0),R997)=\"\",R997,IFERROR(VLOOKUP('AUP Library'!A997,'Updated Quanities'!F:I,7,0),R997))","v":360.08},360.08,{"$f":"IFERROR(VLOOKUP('AUP Library'!A997,'Updated Quanities'!F:G,4,0),R997)","v":360.08}]
["716-03.03","Plastic Word Pavement Marking (Stop Ahead)","EA",372.7,372.7,372.7,372.7,372.7,372.7,372.7,372.7,372.7,372.7,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A998,'Updated Quanities'!F:I,4,0),R998)=\"\",R998,IFERROR(VLOOKUP('AUP Library'!A998,'Updated Quanities'!F:I,4,0),R998))","v":372.7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A998,'Updated Quanities'!F:I,5,0),R998)=\"\",R998,IFERROR(VLOOKUP('AUP Library'!A998,'Updated Quanities'!F:I,5,0),R998))","v":372.7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A998,'Updated Quanities'!F:I,6,0),R998)=\"\",R998,IFERROR(VLOOKUP('AUP Library'!A998,'Updated Quanities'!F:I,6,0),R998))","v":372.7},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A998,'Updated Quanities'!F:I,7,0),R998)=\"\",R998,IFERROR(VLOOKUP('AUP Library'!A998,'Updated Quanities'!F:I,7,0),R998))","v":372.7},372.7,{"$f":"IFERROR(VLOOKUP('AUP Library'!A998,'Updated Quanities'!F:G,4,0),R998)","v":372.7}]
["716-03.04","Plastic Word Pavement Marking (School)","EA",205.11,205.11,205.11,205.11,205.11,205.11,205.11,205.11,205.11,205.11,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A999,'Updated Quanities'!F:I,4,0),R999)=\"\",R999,IFERROR(VLOOKUP('AUP Library'!A999,'Updated Quanities'!F:I,4,0),R999))","v":205.11},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A999,'Updated Quanities'!F:I,5,0),R999)=\"\",R999,IFERROR(VLOOKUP('AUP Library'!A999,'Updated Quanities'!F:I,5,0),R999))","v":205.11},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A999,'Updated Quanities'!F:I,6,0),R999)=\"\",R999,IFERROR(VLOOKUP('AUP Library'!A999,'Updated Quanities'!F:I,6,0),R999))","v":205.11},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A999,'Updated Quanities'!F:I,7,0),R999)=\"\",R999,IFERROR(VLOOKUP('AUP Library'!A999,'Updated Quanities'!F:I,7,0),R999))","v":205.11},205.11,{"$f":"IFERROR(VLOOKUP('AUP Library'!A999,'Updated Quanities'!F:G,4,0),R999)","v":205.11}]
["716-03.05","Plastic Word Pavement Marking (Bike Lane)","EA",177.88,177.88,177.88,177.88,177.88,177.88,177.88,177.88,177.88,177.88,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1000,'Updated Quanities'!F:I,4,0),R1000)=\"\",R1000,IFERROR(VLOOKUP('AUP Library'!A1000,'Updated Quanities'!F:I,4,0),R1000))","v":177.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1000,'Updated Quanities'!F:I,5,0),R1000)=\"\",R1000,IFERROR(VLOOKUP('AUP Library'!A1000,'Updated Quanities'!F:I,5,0),R1000))","v":177.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1000,'Updated Quanities'!F:I,6,0),R1000)=\"\",R1000,IFERROR(VLOOKUP('AUP Library'!A1000,'Updated Quanities'!F:I,6,0),R1000))","v":177.88},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1000,'Updated Quanities'!F:I,7,0),R1000)=\"\",R1000,IFERROR(VLOOKUP('AUP Library'!A1000,'Updated Quanities'!F:I,7,0),R1000))","v":177.88},177.88,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1000,'Updated Quanities'!F:G,4,0),R1000)","v":177.88}]
["716-03.06","Plastic Word Pavement Marking (Signal Ahead)","EA",310.33,310.33,310.33,310.33,310.33,310.33,310.33,310.33,310.33,310.33,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1001,'Updated Quanities'!F:I,4,0),R1001)=\"\",R1001,IFERROR(VLOOKUP('AUP Library'!A1001,'Updated Quanities'!F:I,4,0),R1001))","v":310.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1001,'Updated Quanities'!F:I,5,0),R1001)=\"\",R1001,IFERROR(VLOOKUP('AUP Library'!A1001,'Updated Quanities'!F:I,5,0),R1001))","v":310.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1001,'Updated Quanities'!F:I,6,0),R1001)=\"\",R1001,IFERROR(VLOOKUP('AUP Library'!A1001,'Updated Quanities'!F:I,6,0),R1001))","v":310.33},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1001,'Updated Quanities'!F:I,7,0),R1001)=\"\",R1001,IFERROR(VLOOKUP('AUP Library'!A1001,'Updated Quanities'!F:I,7,0),R1001))","v":310.33},310.33,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1001,'Updated Quanities'!F:G,4,0),R1001)","v":310.33}]
["716-03.07","Plastic Word Pavement Marking (Stop)","EA",166.61,166.61,166.61,166.61,166.61,166.61,166.61,166.61,166.61,166.61,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1002,'Updated Quanities'!F:I,4,0),R1002)=\"\",R1002,IFERROR(VLOOKUP('AUP Library'!A1002,'Updated Quanities'!F:I,4,0),R1002))","v":166.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1002,'Updated Quanities'!F:I,5,0),R1002)=\"\",R1002,IFERROR(VLOOKUP('AUP Library'!A1002,'Updated Quanities'!F:I,5,0),R1002))","v":166.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1002,'Updated Quanities'!F:I,6,0),R1002)=\"\",R1002,IFERROR(VLOOKUP('AUP Library'!A1002,'Updated Quanities'!F:I,6,0),R1002))","v":166.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1002,'Updated Quanities'!F:I,7,0),R1002)=\"\",R1002,IFERROR(VLOOKUP('AUP Library'!A1002,'Updated Quanities'!F:I,7,0),R1002))","v":166.61},166.61,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1002,'Updated Quanities'!F:G,4,0),R1002)","v":166.61}]
["716-03.08","Plastic Word Pavement Marking (Ped-Xing)","EA",139,139,139,139,139,139,139,139,139,139,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1003,'Updated Quanities'!F:I,4,0),R1003)=\"\",R1003,IFERROR(VLOOKUP('AUP Library'!A1003,'Updated Quanities'!F:I,4,0),R1003))","v":139},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1003,'Updated Quanities'!F:I,5,0),R1003)=\"\",R1003,IFERROR(VLOOKUP('AUP Library'!A1003,'Updated Quanities'!F:I,5,0),R1003))","v":139},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1003,'Updated Quanities'!F:I,6,0),R1003)=\"\",R1003,IFERROR(VLOOKUP('AUP Library'!A1003,'Updated Quanities'!F:I,6,0),R1003))","v":139},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1003,'Updated Quanities'!F:I,7,0),R1003)=\"\",R1003,IFERROR(VLOOKUP('AUP Library'!A1003,'Updated Quanities'!F:I,7,0),R1003))","v":139},139,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1003,'Updated Quanities'!F:G,4,0),R1003)","v":139}]
["716-04.01","Plastic Word Pavement Marking (Straight-Turn Arrow)","EA",184.72,184.72,184.72,184.72,184.72,184.72,184.72,184.72,184.72,184.72,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1004,'Updated Quanities'!F:I,4,0),R1004)=\"\",R1004,IFERROR(VLOOKUP('AUP Library'!A1004,'Updated Quanities'!F:I,4,0),R1004))","v":184.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1004,'Updated Quanities'!F:I,5,0),R1004)=\"\",R1004,IFERROR(VLOOKUP('AUP Library'!A1004,'Updated Quanities'!F:I,5,0),R1004))","v":184.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1004,'Updated Quanities'!F:I,6,0),R1004)=\"\",R1004,IFERROR(VLOOKUP('AUP Library'!A1004,'Updated Quanities'!F:I,6,0),R1004))","v":184.72},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1004,'Updated Quanities'!F:I,7,0),R1004)=\"\",R1004,IFERROR(VLOOKUP('AUP Library'!A1004,'Updated Quanities'!F:I,7,0),R1004))","v":184.72},184.72,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1004,'Updated Quanities'!F:G,4,0),R1004)","v":184.72}]
["716-04.02","Plastic Pavment Marking (Double Turning Arrow)","EA",226.98,226.98,226.98,226.98,226.98,226.98,226.98,226.98,226.98,226.98,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1005,'Updated Quanities'!F:I,4,0),R1005)=\"\",R1005,IFERROR(VLOOKUP('AUP Library'!A1005,'Updated Quanities'!F:I,4,0),R1005))","v":226.98},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1005,'Updated Quanities'!F:I,5,0),R1005)=\"\",R1005,IFERROR(VLOOKUP('AUP Library'!A1005,'Updated Quanities'!F:I,5,0),R1005))","v":226.98},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1005,'Updated Quanities'!F:I,6,0),R1005)=\"\",R1005,IFERROR(VLOOKUP('AUP Library'!A1005,'Updated Quanities'!F:I,6,0),R1005))","v":226.98},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1005,'Updated Quanities'!F:I,7,0),R1005)=\"\",R1005,IFERROR(VLOOKUP('AUP Library'!A1005,'Updated Quanities'!F:I,7,0),R1005))","v":226.98},226.98,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1005,'Updated Quanities'!F:G,4,0),R1005)","v":226.98}]
["716-04.03","Plastic Pavment Marking (4\" Dotted Line)","LF",1.61,1.61,1.61,1.61,1.61,1.61,1.61,1.61,1.61,1.61,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1006,'Updated Quanities'!F:I,4,0),R1006)=\"\",R1006,IFERROR(VLOOKUP('AUP Library'!A1006,'Updated Quanities'!F:I,4,0),R1006))","v":1.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1006,'Updated Quanities'!F:I,5,0),R1006)=\"\",R1006,IFERROR(VLOOKUP('AUP Library'!A1006,'Updated Quanities'!F:I,5,0),R1006))","v":1.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1006,'Updated Quanities'!F:I,6,0),R1006)=\"\",R1006,IFERROR(VLOOKUP('AUP Library'!A1006,'Updated Quanities'!F:I,6,0),R1006))","v":1.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1006,'Updated Quanities'!F:I,7,0),R1006)=\"\",R1006,IFERROR(VLOOKUP('AUP Library'!A1006,'Updated Quanities'!F:I,7,0),R1006))","v":1.61},1.61,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1006,'Updated Quanities'!F:G,4,0),R1006)","v":1.61}]
["716-04.04","Plastic Pavment Marking (Transverse Shoulder)","LF",17.79,17.79,17.79,17.79,17.79,17.79,17.79,17.79,17.79,17.79,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1007,'Updated Quanities'!F:I,4,0),R1007)=\"\",R1007,IFERROR(VLOOKUP('AUP Library'!A1007,'Updated Quanities'!F:I,4,0),R1007))","v":17.79},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1007,'Updated Quanities'!F:I,5,0),R1007)=\"\",R1007,IFERROR(VLOOKUP('AUP Library'!A1007,'Updated Quanities'!F:I,5,0),R1007))","v":17.79},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1007,'Updated Quanities'!F:I,6,0),R1007)=\"\",R1007,IFERROR(VLOOKUP('AUP Library'!A1007,'Updated Quanities'!F:I,6,0),R1007))","v":17.79},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1007,'Updated Quanities'!F:I,7,0),R1007)=\"\",R1007,IFERROR(VLOOKUP('AUP Library'!A1007,'Updated Quanities'!F:I,7,0),R1007))","v":17.79},17.79,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1007,'Updated Quanities'!F:G,4,0),R1007)","v":17.79}]
["716-04.05","Plastic Pavement Marking (Straight Arrow)","EA",62.1,62.1,62.1,62.1,62.1,62.1,62.1,62.1,62.1,62.1,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1008,'Updated Quanities'!F:I,4,0),R1008)=\"\",R1008,IFERROR(VLOOKUP('AUP Library'!A1008,'Updated Quanities'!F:I,4,0),R1008))","v":62.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1008,'Updated Quanities'!F:I,5,0),R1008)=\"\",R1008,IFERROR(VLOOKUP('AUP Library'!A1008,'Updated Quanities'!F:I,5,0),R1008))","v":62.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1008,'Updated Quanities'!F:I,6,0),R1008)=\"\",R1008,IFERROR(VLOOKUP('AUP Library'!A1008,'Updated Quanities'!F:I,6,0),R1008))","v":62.1},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1008,'Updated Quanities'!F:I,7,0),R1008)=\"\",R1008,IFERROR(VLOOKUP('AUP Library'!A1008,'Updated Quanities'!F:I,7,0),R1008))","v":62.1},62.1,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1008,'Updated Quanities'!F:G,4,0),R1008)","v":62.1}]
["716-04.06","Plastic Pavement Marking (Wrong Way Arrow)","EA",168.29,168.29,168.29,168.29,168.29,168.29,168.29,168.29,168.29,168.29,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1009,'Updated Quanities'!F:I,4,0),R1009)=\"\",R1009,IFERROR(VLOOKUP('AUP Library'!A1009,'Updated Quanities'!F:I,4,0),R1009))","v":168.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1009,'Updated Quanities'!F:I,5,0),R1009)=\"\",R1009,IFERROR(VLOOKUP('AUP Library'!A1009,'Updated Quanities'!F:I,5,0),R1009))","v":168.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1009,'Updated Quanities'!F:I,6,0),R1009)=\"\",R1009,IFERROR(VLOOKUP('AUP Library'!A1009,'Updated Quanities'!F:I,6,0),R1009))","v":168.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1009,'Updated Quanities'!F:I,7,0),R1009)=\"\",R1009,IFERROR(VLOOKUP('AUP Library'!A1009,'Updated Quanities'!F:I,7,0),R1009))","v":168.29},168.29,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1009,'Updated Quanities'!F:G,4,0),R1009)","v":168.29}]
["716-04.07","Plastic Pavement Marking (Exit Only Arrow)","EA",143.05000000000001,143.05000000000001,143.05000000000001,143.05000000000001,143.05000000000001,143.05000000000001,143.05000000000001,143.05000000000001,143.05000000000001,143.05000000000001,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1010,'Updated Quanities'!F:I,4,0),R1010)=\"\",R1010,IFERROR(VLOOKUP('AUP Library'!A1010,'Updated Quanities'!F:I,4,0),R1010))","v":143.05000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1010,'Updated Quanities'!F:I,5,0),R1010)=\"\",R1010,IFERROR(VLOOKUP('AUP Library'!A1010,'Updated Quanities'!F:I,5,0),R1010))","v":143.05000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1010,'Updated Quanities'!F:I,6,0),R1010)=\"\",R1010,IFERROR(VLOOKUP('AUP Library'!A1010,'Updated Quanities'!F:I,6,0),R1010))","v":143.05000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1010,'Updated Quanities'!F:I,7,0),R1010)=\"\",R1010,IFERROR(VLOOKUP('AUP Library'!A1010,'Updated Quanities'!F:I,7,0),R1010))","v":143.05000000000001},143.05000000000001,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1010,'Updated Quanities'!F:G,4,0),R1010)","v":143.05000000000001}]
["716-04.08","Plastic Pavement Marking (Option Lane Arrow)","EA",197.58,197.58,197.58,197.58,197.58,197.58,197.58,197.58,197.58,197.58,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1011,'Updated Quanities'!F:I,4,0),R1011)=\"\",R1011,IFERROR(VLOOKUP('AUP Library'!A1011,'Updated Quanities'!F:I,4,0),R1011))","v":197.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1011,'Updated Quanities'!F:I,5,0),R1011)=\"\",R1011,IFERROR(VLOOKUP('AUP Library'!A1011,'Updated Quanities'!F:I,5,0),R1011))","v":197.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1011,'Updated Quanities'!F:I,6,0),R1011)=\"\",R1011,IFERROR(VLOOKUP('AUP Library'!A1011,'Updated Quanities'!F:I,6,0),R1011))","v":197.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1011,'Updated Quanities'!F:I,7,0),R1011)=\"\",R1011,IFERROR(VLOOKUP('AUP Library'!A1011,'Updated Quanities'!F:I,7,0),R1011))","v":197.58},197.58,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1011,'Updated Quanities'!F:G,4,0),R1011)","v":197.58}]
["716-04.09","Plastic Pavement Marking (H.O.V. Diamond)","EA",188.22,188.22,188.22,188.22,188.22,188.22,188.22,188.22,188.22,188.22,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1012,'Updated Quanities'!F:I,4,0),R1012)=\"\",R1012,IFERROR(VLOOKUP('AUP Library'!A1012,'Updated Quanities'!F:I,4,0),R1012))","v":188.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1012,'Updated Quanities'!F:I,5,0),R1012)=\"\",R1012,IFERROR(VLOOKUP('AUP Library'!A1012,'Updated Quanities'!F:I,5,0),R1012))","v":188.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1012,'Updated Quanities'!F:I,6,0),R1012)=\"\",R1012,IFERROR(VLOOKUP('AUP Library'!A1012,'Updated Quanities'!F:I,6,0),R1012))","v":188.22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1012,'Updated Quanities'!F:I,7,0),R1012)=\"\",R1012,IFERROR(VLOOKUP('AUP Library'!A1012,'Updated Quanities'!F:I,7,0),R1012))","v":188.22},188.22,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1012,'Updated Quanities'!F:G,4,0),R1012)","v":188.22}]
["716-04.10","Plastic Pavement Marking (Handicap Symbol)","EA",182.85,182.85,182.85,182.85,182.85,182.85,182.85,182.85,182.85,182.85,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1013,'Updated Quanities'!F:I,4,0),R1013)=\"\",R1013,IFERROR(VLOOKUP('AUP Library'!A1013,'Updated Quanities'!F:I,4,0),R1013))","v":182.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1013,'Updated Quanities'!F:I,5,0),R1013)=\"\",R1013,IFERROR(VLOOKUP('AUP Library'!A1013,'Updated Quanities'!F:I,5,0),R1013))","v":182.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1013,'Updated Quanities'!F:I,6,0),R1013)=\"\",R1013,IFERROR(VLOOKUP('AUP Library'!A1013,'Updated Quanities'!F:I,6,0),R1013))","v":182.85},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1013,'Updated Quanities'!F:I,7,0),R1013)=\"\",R1013,IFERROR(VLOOKUP('AUP Library'!A1013,'Updated Quanities'!F:I,7,0),R1013))","v":182.85},182.85,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1013,'Updated Quanities'!F:G,4,0),R1013)","v":182.85}]
["716-04.12","Plastic Pavement Marking (Yield Line)","SF",82.84,82.84,82.84,82.84,82.84,82.84,82.84,82.84,82.84,82.84,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1014,'Updated Quanities'!F:I,4,0),R1014)=\"\",R1014,IFERROR(VLOOKUP('AUP Library'!A1014,'Updated Quanities'!F:I,4,0),R1014))","v":82.84},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1014,'Updated Quanities'!F:I,5,0),R1014)=\"\",R1014,IFERROR(VLOOKUP('AUP Library'!A1014,'Updated Quanities'!F:I,5,0),R1014))","v":82.84},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1014,'Updated Quanities'!F:I,6,0),R1014)=\"\",R1014,IFERROR(VLOOKUP('AUP Library'!A1014,'Updated Quanities'!F:I,6,0),R1014))","v":82.84},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1014,'Updated Quanities'!F:I,7,0),R1014)=\"\",R1014,IFERROR(VLOOKUP('AUP Library'!A1014,'Updated Quanities'!F:I,7,0),R1014))","v":82.84},82.84,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1014,'Updated Quanities'!F:G,4,0),R1014)","v":82.84}]
["716-04.13","PLASTIC PAVEMENT MARKING(BLANE SY ARROW)","EA",null,null,null,null,null,null,null,null,null,null,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1015,'Updated Quanities'!F:I,4,0),R1015)=\"\",R1015,IFERROR(VLOOKUP('AUP Library'!A1015,'Updated Quanities'!F:I,4,0),R1015))","v":0},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1015,'Updated Quanities'!F:I,5,0),R1015)=\"\",R1015,IFERROR(VLOOKUP('AUP Library'!A1015,'Updated Quanities'!F:I,5,0),R1015))","v":0},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1015,'Updated Quanities'!F:I,6,0),R1015)=\"\",R1015,IFERROR(VLOOKUP('AUP Library'!A1015,'Updated Quanities'!F:I,6,0),R1015))","v":0},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1015,'Updated Quanities'!F:I,7,0),R1015)=\"\",R1015,IFERROR(VLOOKUP('AUP Library'!A1015,'Updated Quanities'!F:I,7,0),R1015))","v":0},null,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1015,'Updated Quanities'!F:G,4,0),R1015)","v":0}]
["716-04.14","PLASTIC PAVEMENT MARKING(LANE RED ARROW)","EA",null,null,null,null,null,null,null,null,null,null,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1016,'Updated Quanities'!F:I,4,0),R1016)=\"\",R1016,IFERROR(VLOOKUP('AUP Library'!A1016,'Updated Quanities'!F:I,4,0),R1016))","v":0},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1016,'Updated Quanities'!F:I,5,0),R1016)=\"\",R1016,IFERROR(VLOOKUP('AUP Library'!A1016,'Updated Quanities'!F:I,5,0),R1016))","v":0},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1016,'Updated Quanities'!F:I,6,0),R1016)=\"\",R1016,IFERROR(VLOOKUP('AUP Library'!A1016,'Updated Quanities'!F:I,6,0),R1016))","v":0},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1016,'Updated Quanities'!F:I,7,0),R1016)=\"\",R1016,IFERROR(VLOOKUP('AUP Library'!A1016,'Updated Quanities'!F:I,7,0),R1016))","v":0},null,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1016,'Updated Quanities'!F:G,4,0),R1016)","v":0}]
["716-04.15","PLASTIC PAVEMT MARKING-BIKE SYMBOL/AR SH","EA",null,null,null,null,null,null,null,null,null,null,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1017,'Updated Quanities'!F:I,4,0),R1017)=\"\",R1017,IFERROR(VLOOKUP('AUP Library'!A1017,'Updated Quanities'!F:I,4,0),R1017))","v":0},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1017,'Updated Quanities'!F:I,5,0),R1017)=\"\",R1017,IFERROR(VLOOKUP('AUP Library'!A1017,'Updated Quanities'!F:I,5,0),R1017))","v":0},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1017,'Updated Quanities'!F:I,6,0),R1017)=\"\",R1017,IFERROR(VLOOKUP('AUP Library'!A1017,'Updated Quanities'!F:I,6,0),R1017))","v":0},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1017,'Updated Quanities'!F:I,7,0),R1017)=\"\",R1017,IFERROR(VLOOKUP('AUP Library'!A1017,'Updated Quanities'!F:I,7,0),R1017))","v":0},null,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1017,'Updated Quanities'!F:G,4,0),R1017)","v":0}]
["716-04.16","Painted Pavement Marking (Noise Strip)","LF",9.5399999999999991,9.5399999999999991,9.5399999999999991,9.5399999999999991,9.5399999999999991,9.5399999999999991,9.5399999999999991,9.5399999999999991,9.5399999999999991,9.5399999999999991,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1018,'Updated Quanities'!F:I,4,0),R1018)=\"\",R1018,IFERROR(VLOOKUP('AUP Library'!A1018,'Updated Quanities'!F:I,4,0),R1018))","v":9.5399999999999991},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1018,'Updated Quanities'!F:I,5,0),R1018)=\"\",R1018,IFERROR(VLOOKUP('AUP Library'!A1018,'Updated Quanities'!F:I,5,0),R1018))","v":9.5399999999999991},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1018,'Updated Quanities'!F:I,6,0),R1018)=\"\",R1018,IFERROR(VLOOKUP('AUP Library'!A1018,'Updated Quanities'!F:I,6,0),R1018))","v":9.5399999999999991},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1018,'Updated Quanities'!F:I,7,0),R1018)=\"\",R1018,IFERROR(VLOOKUP('AUP Library'!A1018,'Updated Quanities'!F:I,7,0),R1018))","v":9.5399999999999991},9.5399999999999991,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1018,'Updated Quanities'!F:G,4,0),R1018)","v":9.5399999999999991}]
["716-04.17","Plastic Pavement Marking (Yield Symbol)","EA",22,22,22,22,22,22,22,22,22,22,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1019,'Updated Quanities'!F:I,4,0),R1019)=\"\",R1019,IFERROR(VLOOKUP('AUP Library'!A1019,'Updated Quanities'!F:I,4,0),R1019))","v":22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1019,'Updated Quanities'!F:I,5,0),R1019)=\"\",R1019,IFERROR(VLOOKUP('AUP Library'!A1019,'Updated Quanities'!F:I,5,0),R1019))","v":22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1019,'Updated Quanities'!F:I,6,0),R1019)=\"\",R1019,IFERROR(VLOOKUP('AUP Library'!A1019,'Updated Quanities'!F:I,6,0),R1019))","v":22},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1019,'Updated Quanities'!F:I,7,0),R1019)=\"\",R1019,IFERROR(VLOOKUP('AUP Library'!A1019,'Updated Quanities'!F:I,7,0),R1019))","v":22},22,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1019,'Updated Quanities'!F:G,4,0),R1019)","v":22}]
["716-05.01","Painted Pavement Marking (4\" Line)","LM",558.66999999999996,558.66999999999996,558.66999999999996,558.66999999999996,558.66999999999996,558.66999999999996,558.66999999999996,558.66999999999996,558.66999999999996,558.66999999999996,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1020,'Updated Quanities'!F:I,4,0),R1020)=\"\",R1020,IFERROR(VLOOKUP('AUP Library'!A1020,'Updated Quanities'!F:I,4,0),R1020))","v":558.66999999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1020,'Updated Quanities'!F:I,5,0),R1020)=\"\",R1020,IFERROR(VLOOKUP('AUP Library'!A1020,'Updated Quanities'!F:I,5,0),R1020))","v":558.66999999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1020,'Updated Quanities'!F:I,6,0),R1020)=\"\",R1020,IFERROR(VLOOKUP('AUP Library'!A1020,'Updated Quanities'!F:I,6,0),R1020))","v":558.66999999999996},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1020,'Updated Quanities'!F:I,7,0),R1020)=\"\",R1020,IFERROR(VLOOKUP('AUP Library'!A1020,'Updated Quanities'!F:I,7,0),R1020))","v":558.66999999999996},558.66999999999996,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1020,'Updated Quanities'!F:G,4,0),R1020)","v":558.66999999999996}]
["716-05.02","Painted Pavement Marking (8\" Barrier Line)","LF",0.46,0.46,0.46,0.46,0.46,0.46,0.46,0.46,0.46,0.46,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1021,'Updated Quanities'!F:I,4,0),R1021)=\"\",R1021,IFERROR(VLOOKUP('AUP Library'!A1021,'Updated Quanities'!F:I,4,0),R1021))","v":0.46},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1021,'Updated Quanities'!F:I,5,0),R1021)=\"\",R1021,IFERROR(VLOOKUP('AUP Library'!A1021,'Updated Quanities'!F:I,5,0),R1021))","v":0.46},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1021,'Updated Quanities'!F:I,6,0),R1021)=\"\",R1021,IFERROR(VLOOKUP('AUP Library'!A1021,'Updated Quanities'!F:I,6,0),R1021))","v":0.46},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1021,'Updated Quanities'!F:I,7,0),R1021)=\"\",R1021,IFERROR(VLOOKUP('AUP Library'!A1021,'Updated Quanities'!F:I,7,0),R1021))","v":0.46},0.46,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1021,'Updated Quanities'!F:G,4,0),R1021)","v":0.46}]
["716-05.03","Painted Pavement Mkg (Cross-Walk)","LF",2.5,2.5,2.5,2.5,2.5,2.5,2.5,2.5,2.5,2.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1022,'Updated Quanities'!F:I,4,0),R1022)=\"\",R1022,IFERROR(VLOOKUP('AUP Library'!A1022,'Updated Quanities'!F:I,4,0),R1022))","v":2.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1022,'Updated Quanities'!F:I,5,0),R1022)=\"\",R1022,IFERROR(VLOOKUP('AUP Library'!A1022,'Updated Quanities'!F:I,5,0),R1022))","v":2.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1022,'Updated Quanities'!F:I,6,0),R1022)=\"\",R1022,IFERROR(VLOOKUP('AUP Library'!A1022,'Updated Quanities'!F:I,6,0),R1022))","v":2.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1022,'Updated Quanities'!F:I,7,0),R1022)=\"\",R1022,IFERROR(VLOOKUP('AUP Library'!A1022,'Updated Quanities'!F:I,7,0),R1022))","v":2.5},2.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1022,'Updated Quanities'!F:G,4,0),R1022)","v":2.5}]
["716-05.04","Painted Pavement Mkg (Chnz Striping)","SY",8.1199999999999992,8.1199999999999992,8.1199999999999992,8.1199999999999992,8.1199999999999992,8.1199999999999992,8.1199999999999992,8.1199999999999992,8.1199999999999992,8.1199999999999992,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1023,'Updated Quanities'!F:I,4,0),R1023)=\"\",R1023,IFERROR(VLOOKUP('AUP Library'!A1023,'Updated Quanities'!F:I,4,0),R1023))","v":8.1199999999999992},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1023,'Updated Quanities'!F:I,5,0),R1023)=\"\",R1023,IFERROR(VLOOKUP('AUP Library'!A1023,'Updated Quanities'!F:I,5,0),R1023))","v":8.1199999999999992},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1023,'Updated Quanities'!F:I,6,0),R1023)=\"\",R1023,IFERROR(VLOOKUP('AUP Library'!A1023,'Updated Quanities'!F:I,6,0),R1023))","v":8.1199999999999992},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1023,'Updated Quanities'!F:I,7,0),R1023)=\"\",R1023,IFERROR(VLOOKUP('AUP Library'!A1023,'Updated Quanities'!F:I,7,0),R1023))","v":8.1199999999999992},8.1199999999999992,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1023,'Updated Quanities'!F:G,4,0),R1023)","v":8.1199999999999992}]
["716-05.05","Painted Pavement Marking (Stop Line)","LF",6.6,6.6,6.6,6.6,6.6,6.6,6.6,6.6,6.6,6.6,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1024,'Updated Quanities'!F:I,4,0),R1024)=\"\",R1024,IFERROR(VLOOKUP('AUP Library'!A1024,'Updated Quanities'!F:I,4,0),R1024))","v":6.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1024,'Updated Quanities'!F:I,5,0),R1024)=\"\",R1024,IFERROR(VLOOKUP('AUP Library'!A1024,'Updated Quanities'!F:I,5,0),R1024))","v":6.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1024,'Updated Quanities'!F:I,6,0),R1024)=\"\",R1024,IFERROR(VLOOKUP('AUP Library'!A1024,'Updated Quanities'!F:I,6,0),R1024))","v":6.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1024,'Updated Quanities'!F:I,7,0),R1024)=\"\",R1024,IFERROR(VLOOKUP('AUP Library'!A1024,'Updated Quanities'!F:I,7,0),R1024))","v":6.6},6.6,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1024,'Updated Quanities'!F:G,4,0),R1024)","v":6.6}]
["716-05.06","Painted Pavement Mkg (Turn Lane Arrow)","EA",47.62,47.62,47.62,47.62,47.62,47.62,47.62,47.62,47.62,47.62,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1025,'Updated Quanities'!F:I,4,0),R1025)=\"\",R1025,IFERROR(VLOOKUP('AUP Library'!A1025,'Updated Quanities'!F:I,4,0),R1025))","v":47.62},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1025,'Updated Quanities'!F:I,5,0),R1025)=\"\",R1025,IFERROR(VLOOKUP('AUP Library'!A1025,'Updated Quanities'!F:I,5,0),R1025))","v":47.62},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1025,'Updated Quanities'!F:I,6,0),R1025)=\"\",R1025,IFERROR(VLOOKUP('AUP Library'!A1025,'Updated Quanities'!F:I,6,0),R1025))","v":47.62},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1025,'Updated Quanities'!F:I,7,0),R1025)=\"\",R1025,IFERROR(VLOOKUP('AUP Library'!A1025,'Updated Quanities'!F:I,7,0),R1025))","v":47.62},47.62,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1025,'Updated Quanities'!F:G,4,0),R1025)","v":47.62}]
["716-05.07","Painted Pavement Mkg (24\" Barrier Line)","LF",0.35,0.35,0.35,0.35,0.35,0.35,0.35,0.35,0.35,0.35,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1026,'Updated Quanities'!F:I,4,0),R1026)=\"\",R1026,IFERROR(VLOOKUP('AUP Library'!A1026,'Updated Quanities'!F:I,4,0),R1026))","v":0.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1026,'Updated Quanities'!F:I,5,0),R1026)=\"\",R1026,IFERROR(VLOOKUP('AUP Library'!A1026,'Updated Quanities'!F:I,5,0),R1026))","v":0.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1026,'Updated Quanities'!F:I,6,0),R1026)=\"\",R1026,IFERROR(VLOOKUP('AUP Library'!A1026,'Updated Quanities'!F:I,6,0),R1026))","v":0.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1026,'Updated Quanities'!F:I,7,0),R1026)=\"\",R1026,IFERROR(VLOOKUP('AUP Library'!A1026,'Updated Quanities'!F:I,7,0),R1026))","v":0.35},0.35,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1026,'Updated Quanities'!F:G,4,0),R1026)","v":0.35}]
["716-05.08","Painted Pavement Marking (Parking Line)","LF",2.46,2.46,2.46,2.46,2.46,2.46,2.46,2.46,2.46,2.46,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1027,'Updated Quanities'!F:I,4,0),R1027)=\"\",R1027,IFERROR(VLOOKUP('AUP Library'!A1027,'Updated Quanities'!F:I,4,0),R1027))","v":2.46},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1027,'Updated Quanities'!F:I,5,0),R1027)=\"\",R1027,IFERROR(VLOOKUP('AUP Library'!A1027,'Updated Quanities'!F:I,5,0),R1027))","v":2.46},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1027,'Updated Quanities'!F:I,6,0),R1027)=\"\",R1027,IFERROR(VLOOKUP('AUP Library'!A1027,'Updated Quanities'!F:I,6,0),R1027))","v":2.46},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1027,'Updated Quanities'!F:I,7,0),R1027)=\"\",R1027,IFERROR(VLOOKUP('AUP Library'!A1027,'Updated Quanities'!F:I,7,0),R1027))","v":2.46},2.46,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1027,'Updated Quanities'!F:G,4,0),R1027)","v":2.46}]
["716-05.09","Painted Pavement Marking (Str-Turn Arrow)","EA",75,75,75,75,75,75,75,75,75,75,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1028,'Updated Quanities'!F:I,4,0),R1028)=\"\",R1028,IFERROR(VLOOKUP('AUP Library'!A1028,'Updated Quanities'!F:I,4,0),R1028))","v":75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1028,'Updated Quanities'!F:I,5,0),R1028)=\"\",R1028,IFERROR(VLOOKUP('AUP Library'!A1028,'Updated Quanities'!F:I,5,0),R1028))","v":75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1028,'Updated Quanities'!F:I,6,0),R1028)=\"\",R1028,IFERROR(VLOOKUP('AUP Library'!A1028,'Updated Quanities'!F:I,6,0),R1028))","v":75},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1028,'Updated Quanities'!F:I,7,0),R1028)=\"\",R1028,IFERROR(VLOOKUP('AUP Library'!A1028,'Updated Quanities'!F:I,7,0),R1028))","v":75},75,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1028,'Updated Quanities'!F:G,4,0),R1028)","v":75}]
["716-05.10","Painted Pavement Marking (RXR)","EA",428,428,428,428,428,428,428,428,428,428,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1029,'Updated Quanities'!F:I,4,0),R1029)=\"\",R1029,IFERROR(VLOOKUP('AUP Library'!A1029,'Updated Quanities'!F:I,4,0),R1029))","v":428},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1029,'Updated Quanities'!F:I,5,0),R1029)=\"\",R1029,IFERROR(VLOOKUP('AUP Library'!A1029,'Updated Quanities'!F:I,5,0),R1029))","v":428},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1029,'Updated Quanities'!F:I,6,0),R1029)=\"\",R1029,IFERROR(VLOOKUP('AUP Library'!A1029,'Updated Quanities'!F:I,6,0),R1029))","v":428},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1029,'Updated Quanities'!F:I,7,0),R1029)=\"\",R1029,IFERROR(VLOOKUP('AUP Library'!A1029,'Updated Quanities'!F:I,7,0),R1029))","v":428},428,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1029,'Updated Quanities'!F:G,4,0),R1029)","v":428}]
["716-05.11","Painted Pavement Marking (Str-Arrow)","EA",48.61,48.61,48.61,48.61,48.61,48.61,48.61,48.61,48.61,48.61,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1030,'Updated Quanities'!F:I,4,0),R1030)=\"\",R1030,IFERROR(VLOOKUP('AUP Library'!A1030,'Updated Quanities'!F:I,4,0),R1030))","v":48.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1030,'Updated Quanities'!F:I,5,0),R1030)=\"\",R1030,IFERROR(VLOOKUP('AUP Library'!A1030,'Updated Quanities'!F:I,5,0),R1030))","v":48.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1030,'Updated Quanities'!F:I,6,0),R1030)=\"\",R1030,IFERROR(VLOOKUP('AUP Library'!A1030,'Updated Quanities'!F:I,6,0),R1030))","v":48.61},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1030,'Updated Quanities'!F:I,7,0),R1030)=\"\",R1030,IFERROR(VLOOKUP('AUP Library'!A1030,'Updated Quanities'!F:I,7,0),R1030))","v":48.61},48.61,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1030,'Updated Quanities'!F:G,4,0),R1030)","v":48.61}]
["716-05.20","Painted Pavement Marking (6\" Line)","LM",1176.29,1176.29,1176.29,1176.29,1176.29,1176.29,1176.29,1176.29,1176.29,1176.29,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1031,'Updated Quanities'!F:I,4,0),R1031)=\"\",R1031,IFERROR(VLOOKUP('AUP Library'!A1031,'Updated Quanities'!F:I,4,0),R1031))","v":1176.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1031,'Updated Quanities'!F:I,5,0),R1031)=\"\",R1031,IFERROR(VLOOKUP('AUP Library'!A1031,'Updated Quanities'!F:I,5,0),R1031))","v":1176.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1031,'Updated Quanities'!F:I,6,0),R1031)=\"\",R1031,IFERROR(VLOOKUP('AUP Library'!A1031,'Updated Quanities'!F:I,6,0),R1031))","v":1176.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1031,'Updated Quanities'!F:I,7,0),R1031)=\"\",R1031,IFERROR(VLOOKUP('AUP Library'!A1031,'Updated Quanities'!F:I,7,0),R1031))","v":1176.29},1176.29,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1031,'Updated Quanities'!F:G,4,0),R1031)","v":1176.29}]
["716-08.01","Removal of Pavement Marking (Line)","LF",0.54,0.54,0.54,0.54,0.54,0.54,0.54,0.54,0.54,0.54,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1032,'Updated Quanities'!F:I,4,0),R1032)=\"\",R1032,IFERROR(VLOOKUP('AUP Library'!A1032,'Updated Quanities'!F:I,4,0),R1032))","v":0.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1032,'Updated Quanities'!F:I,5,0),R1032)=\"\",R1032,IFERROR(VLOOKUP('AUP Library'!A1032,'Updated Quanities'!F:I,5,0),R1032))","v":0.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1032,'Updated Quanities'!F:I,6,0),R1032)=\"\",R1032,IFERROR(VLOOKUP('AUP Library'!A1032,'Updated Quanities'!F:I,6,0),R1032))","v":0.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1032,'Updated Quanities'!F:I,7,0),R1032)=\"\",R1032,IFERROR(VLOOKUP('AUP Library'!A1032,'Updated Quanities'!F:I,7,0),R1032))","v":0.54},0.54,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1032,'Updated Quanities'!F:G,4,0),R1032)","v":0.54}]
["716-08.03","Removal of Pavement Marking (Cross Walk)","LF",9,9,9,9,9,9,9,9,9,9,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1033,'Updated Quanities'!F:I,4,0),R1033)=\"\",R1033,IFERROR(VLOOKUP('AUP Library'!A1033,'Updated Quanities'!F:I,4,0),R1033))","v":9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1033,'Updated Quanities'!F:I,5,0),R1033)=\"\",R1033,IFERROR(VLOOKUP('AUP Library'!A1033,'Updated Quanities'!F:I,5,0),R1033))","v":9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1033,'Updated Quanities'!F:I,6,0),R1033)=\"\",R1033,IFERROR(VLOOKUP('AUP Library'!A1033,'Updated Quanities'!F:I,6,0),R1033))","v":9},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1033,'Updated Quanities'!F:I,7,0),R1033)=\"\",R1033,IFERROR(VLOOKUP('AUP Library'!A1033,'Updated Quanities'!F:I,7,0),R1033))","v":9},9,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1033,'Updated Quanities'!F:G,4,0),R1033)","v":9}]
["716-08.04","Removal Pavement Marking (Chnz Striping)","SY",11.54,11.54,11.54,11.54,11.54,11.54,11.54,11.54,11.54,11.54,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1034,'Updated Quanities'!F:I,4,0),R1034)=\"\",R1034,IFERROR(VLOOKUP('AUP Library'!A1034,'Updated Quanities'!F:I,4,0),R1034))","v":11.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1034,'Updated Quanities'!F:I,5,0),R1034)=\"\",R1034,IFERROR(VLOOKUP('AUP Library'!A1034,'Updated Quanities'!F:I,5,0),R1034))","v":11.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1034,'Updated Quanities'!F:I,6,0),R1034)=\"\",R1034,IFERROR(VLOOKUP('AUP Library'!A1034,'Updated Quanities'!F:I,6,0),R1034))","v":11.54},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1034,'Updated Quanities'!F:I,7,0),R1034)=\"\",R1034,IFERROR(VLOOKUP('AUP Library'!A1034,'Updated Quanities'!F:I,7,0),R1034))","v":11.54},11.54,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1034,'Updated Quanities'!F:G,4,0),R1034)","v":11.54}]
["716-08.05","Removal of Pavement Marking (Stop Line)","LF",3.49,3.49,3.49,3.49,3.49,3.49,3.49,3.49,3.49,3.49,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1035,'Updated Quanities'!F:I,4,0),R1035)=\"\",R1035,IFERROR(VLOOKUP('AUP Library'!A1035,'Updated Quanities'!F:I,4,0),R1035))","v":3.49},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1035,'Updated Quanities'!F:I,5,0),R1035)=\"\",R1035,IFERROR(VLOOKUP('AUP Library'!A1035,'Updated Quanities'!F:I,5,0),R1035))","v":3.49},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1035,'Updated Quanities'!F:I,6,0),R1035)=\"\",R1035,IFERROR(VLOOKUP('AUP Library'!A1035,'Updated Quanities'!F:I,6,0),R1035))","v":3.49},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1035,'Updated Quanities'!F:I,7,0),R1035)=\"\",R1035,IFERROR(VLOOKUP('AUP Library'!A1035,'Updated Quanities'!F:I,7,0),R1035))","v":3.49},3.49,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1035,'Updated Quanities'!F:G,4,0),R1035)","v":3.49}]
["716-08.06","Removal of Pavement Marking (Turn Lane Arrow)","EA",35.97,35.97,35.97,35.97,35.97,35.97,35.97,35.97,35.97,35.97,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1036,'Updated Quanities'!F:I,4,0),R1036)=\"\",R1036,IFERROR(VLOOKUP('AUP Library'!A1036,'Updated Quanities'!F:I,4,0),R1036))","v":35.97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1036,'Updated Quanities'!F:I,5,0),R1036)=\"\",R1036,IFERROR(VLOOKUP('AUP Library'!A1036,'Updated Quanities'!F:I,5,0),R1036))","v":35.97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1036,'Updated Quanities'!F:I,6,0),R1036)=\"\",R1036,IFERROR(VLOOKUP('AUP Library'!A1036,'Updated Quanities'!F:I,6,0),R1036))","v":35.97},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1036,'Updated Quanities'!F:I,7,0),R1036)=\"\",R1036,IFERROR(VLOOKUP('AUP Library'!A1036,'Updated Quanities'!F:I,7,0),R1036))","v":35.97},35.97,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1036,'Updated Quanities'!F:G,4,0),R1036)","v":35.97}]
["716-08.07","Removal Pavement Marking (Straight-Turn Arrow)","EA",51.74,51.74,51.74,51.74,51.74,51.74,51.74,51.74,51.74,51.74,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1037,'Updated Quanities'!F:I,4,0),R1037)=\"\",R1037,IFERROR(VLOOKUP('AUP Library'!A1037,'Updated Quanities'!F:I,4,0),R1037))","v":51.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1037,'Updated Quanities'!F:I,5,0),R1037)=\"\",R1037,IFERROR(VLOOKUP('AUP Library'!A1037,'Updated Quanities'!F:I,5,0),R1037))","v":51.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1037,'Updated Quanities'!F:I,6,0),R1037)=\"\",R1037,IFERROR(VLOOKUP('AUP Library'!A1037,'Updated Quanities'!F:I,6,0),R1037))","v":51.74},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1037,'Updated Quanities'!F:I,7,0),R1037)=\"\",R1037,IFERROR(VLOOKUP('AUP Library'!A1037,'Updated Quanities'!F:I,7,0),R1037))","v":51.74},51.74,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1037,'Updated Quanities'!F:G,4,0),R1037)","v":51.74}]
["716-08.08","Removal Pavement Marking (Double Turning Arrow)","EA",57.5,57.5,57.5,57.5,57.5,57.5,57.5,57.5,57.5,57.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1038,'Updated Quanities'!F:I,4,0),R1038)=\"\",R1038,IFERROR(VLOOKUP('AUP Library'!A1038,'Updated Quanities'!F:I,4,0),R1038))","v":57.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1038,'Updated Quanities'!F:I,5,0),R1038)=\"\",R1038,IFERROR(VLOOKUP('AUP Library'!A1038,'Updated Quanities'!F:I,5,0),R1038))","v":57.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1038,'Updated Quanities'!F:I,6,0),R1038)=\"\",R1038,IFERROR(VLOOKUP('AUP Library'!A1038,'Updated Quanities'!F:I,6,0),R1038))","v":57.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1038,'Updated Quanities'!F:I,7,0),R1038)=\"\",R1038,IFERROR(VLOOKUP('AUP Library'!A1038,'Updated Quanities'!F:I,7,0),R1038))","v":57.5},57.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1038,'Updated Quanities'!F:G,4,0),R1038)","v":57.5}]
["716-08.09","Removal of Pavement Marking (Dotted Line)","LF",11.58,11.58,11.58,11.58,11.58,11.58,11.58,11.58,11.58,11.58,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1039,'Updated Quanities'!F:I,4,0),R1039)=\"\",R1039,IFERROR(VLOOKUP('AUP Library'!A1039,'Updated Quanities'!F:I,4,0),R1039))","v":11.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1039,'Updated Quanities'!F:I,5,0),R1039)=\"\",R1039,IFERROR(VLOOKUP('AUP Library'!A1039,'Updated Quanities'!F:I,5,0),R1039))","v":11.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1039,'Updated Quanities'!F:I,6,0),R1039)=\"\",R1039,IFERROR(VLOOKUP('AUP Library'!A1039,'Updated Quanities'!F:I,6,0),R1039))","v":11.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1039,'Updated Quanities'!F:I,7,0),R1039)=\"\",R1039,IFERROR(VLOOKUP('AUP Library'!A1039,'Updated Quanities'!F:I,7,0),R1039))","v":11.58},11.58,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1039,'Updated Quanities'!F:G,4,0),R1039)","v":11.58}]
["716-08.10","Removal Pavement Marking (Transverse Shoulder)","LF",251.06,251.06,251.06,251.06,251.06,251.06,251.06,251.06,251.06,251.06,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1040,'Updated Quanities'!F:I,4,0),R1040)=\"\",R1040,IFERROR(VLOOKUP('AUP Library'!A1040,'Updated Quanities'!F:I,4,0),R1040))","v":251.06},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1040,'Updated Quanities'!F:I,5,0),R1040)=\"\",R1040,IFERROR(VLOOKUP('AUP Library'!A1040,'Updated Quanities'!F:I,5,0),R1040))","v":251.06},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1040,'Updated Quanities'!F:I,6,0),R1040)=\"\",R1040,IFERROR(VLOOKUP('AUP Library'!A1040,'Updated Quanities'!F:I,6,0),R1040))","v":251.06},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1040,'Updated Quanities'!F:I,7,0),R1040)=\"\",R1040,IFERROR(VLOOKUP('AUP Library'!A1040,'Updated Quanities'!F:I,7,0),R1040))","v":251.06},251.06,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1040,'Updated Quanities'!F:G,4,0),R1040)","v":251.06}]
["716-08.11","Removal of Word Pavement Marking","EA",519.04999999999995,519.04999999999995,519.04999999999995,519.04999999999995,519.04999999999995,519.04999999999995,519.04999999999995,519.04999999999995,519.04999999999995,519.04999999999995,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1041,'Updated Quanities'!F:I,4,0),R1041)=\"\",R1041,IFERROR(VLOOKUP('AUP Library'!A1041,'Updated Quanities'!F:I,4,0),R1041))","v":519.04999999999995},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1041,'Updated Quanities'!F:I,5,0),R1041)=\"\",R1041,IFERROR(VLOOKUP('AUP Library'!A1041,'Updated Quanities'!F:I,5,0),R1041))","v":519.04999999999995},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1041,'Updated Quanities'!F:I,6,0),R1041)=\"\",R1041,IFERROR(VLOOKUP('AUP Library'!A1041,'Updated Quanities'!F:I,6,0),R1041))","v":519.04999999999995},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1041,'Updated Quanities'!F:I,7,0),R1041)=\"\",R1041,IFERROR(VLOOKUP('AUP Library'!A1041,'Updated Quanities'!F:I,7,0),R1041))","v":519.04999999999995},519.04999999999995,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1041,'Updated Quanities'!F:G,4,0),R1041)","v":519.04999999999995}]
["716-08.30","Hyrdoblast Removal of Pavement Marking (Line)","LF",3950,3950,3950,3950,3950,3950,3950,3950,3950,3950,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1042,'Updated Quanities'!F:I,4,0),R1042)=\"\",R1042,IFERROR(VLOOKUP('AUP Library'!A1042,'Updated Quanities'!F:I,4,0),R1042))","v":3950},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1042,'Updated Quanities'!F:I,5,0),R1042)=\"\",R1042,IFERROR(VLOOKUP('AUP Library'!A1042,'Updated Quanities'!F:I,5,0),R1042))","v":3950},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1042,'Updated Quanities'!F:I,6,0),R1042)=\"\",R1042,IFERROR(VLOOKUP('AUP Library'!A1042,'Updated Quanities'!F:I,6,0),R1042))","v":3950},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1042,'Updated Quanities'!F:I,7,0),R1042)=\"\",R1042,IFERROR(VLOOKUP('AUP Library'!A1042,'Updated Quanities'!F:I,7,0),R1042))","v":3950},3950,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1042,'Updated Quanities'!F:G,4,0),R1042)","v":3950}]
["716-09.03","WET REFLECTIVE PAVEMENT MARKING(6\" LINE)","LM",16275,16275,16275,16275,16275,16275,16275,16275,16275,16275,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1043,'Updated Quanities'!F:I,4,0),R1043)=\"\",R1043,IFERROR(VLOOKUP('AUP Library'!A1043,'Updated Quanities'!F:I,4,0),R1043))","v":16275},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1043,'Updated Quanities'!F:I,5,0),R1043)=\"\",R1043,IFERROR(VLOOKUP('AUP Library'!A1043,'Updated Quanities'!F:I,5,0),R1043))","v":16275},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1043,'Updated Quanities'!F:I,6,0),R1043)=\"\",R1043,IFERROR(VLOOKUP('AUP Library'!A1043,'Updated Quanities'!F:I,6,0),R1043))","v":16275},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1043,'Updated Quanities'!F:I,7,0),R1043)=\"\",R1043,IFERROR(VLOOKUP('AUP Library'!A1043,'Updated Quanities'!F:I,7,0),R1043))","v":16275},16275,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1043,'Updated Quanities'!F:G,4,0),R1043)","v":16275}]
["716-09.31","STOP LINE","LF",16.649999999999999,16.649999999999999,16.649999999999999,16.649999999999999,16.649999999999999,16.649999999999999,16.649999999999999,16.649999999999999,16.649999999999999,16.649999999999999,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1044,'Updated Quanities'!F:I,4,0),R1044)=\"\",R1044,IFERROR(VLOOKUP('AUP Library'!A1044,'Updated Quanities'!F:I,4,0),R1044))","v":16.649999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1044,'Updated Quanities'!F:I,5,0),R1044)=\"\",R1044,IFERROR(VLOOKUP('AUP Library'!A1044,'Updated Quanities'!F:I,5,0),R1044))","v":16.649999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1044,'Updated Quanities'!F:I,6,0),R1044)=\"\",R1044,IFERROR(VLOOKUP('AUP Library'!A1044,'Updated Quanities'!F:I,6,0),R1044))","v":16.649999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1044,'Updated Quanities'!F:I,7,0),R1044)=\"\",R1044,IFERROR(VLOOKUP('AUP Library'!A1044,'Updated Quanities'!F:I,7,0),R1044))","v":16.649999999999999},16.649999999999999,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1044,'Updated Quanities'!F:G,4,0),R1044)","v":16.649999999999999}]
["716-09.33","6 INCH DOTTED LINE","LF",1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,1.1000000000000001,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1045,'Updated Quanities'!F:I,4,0),R1045)=\"\",R1045,IFERROR(VLOOKUP('AUP Library'!A1045,'Updated Quanities'!F:I,4,0),R1045))","v":1.1000000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1045,'Updated Quanities'!F:I,5,0),R1045)=\"\",R1045,IFERROR(VLOOKUP('AUP Library'!A1045,'Updated Quanities'!F:I,5,0),R1045))","v":1.1000000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1045,'Updated Quanities'!F:I,6,0),R1045)=\"\",R1045,IFERROR(VLOOKUP('AUP Library'!A1045,'Updated Quanities'!F:I,6,0),R1045))","v":1.1000000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1045,'Updated Quanities'!F:I,7,0),R1045)=\"\",R1045,IFERROR(VLOOKUP('AUP Library'!A1045,'Updated Quanities'!F:I,7,0),R1045))","v":1.1000000000000001},1.1000000000000001,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1045,'Updated Quanities'!F:G,4,0),R1045)","v":1.1000000000000001}]
["716-09.72","WET REFLEC PAVEMEMT MARKING (4\"LINE)","LM",15900.21,15900.21,15900.21,15900.21,15900.21,15900.21,15900.21,15900.21,15900.21,15900.21,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1046,'Updated Quanities'!F:I,4,0),R1046)=\"\",R1046,IFERROR(VLOOKUP('AUP Library'!A1046,'Updated Quanities'!F:I,4,0),R1046))","v":15900.21},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1046,'Updated Quanities'!F:I,5,0),R1046)=\"\",R1046,IFERROR(VLOOKUP('AUP Library'!A1046,'Updated Quanities'!F:I,5,0),R1046))","v":15900.21},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1046,'Updated Quanities'!F:I,6,0),R1046)=\"\",R1046,IFERROR(VLOOKUP('AUP Library'!A1046,'Updated Quanities'!F:I,6,0),R1046))","v":15900.21},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1046,'Updated Quanities'!F:I,7,0),R1046)=\"\",R1046,IFERROR(VLOOKUP('AUP Library'!A1046,'Updated Quanities'!F:I,7,0),R1046))","v":15900.21},15900.21,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1046,'Updated Quanities'!F:G,4,0),R1046)","v":15900.21}]
["716-10.50","Preformed Plastic Pavement Marking (Interstate Shield)","EA",796.71,796.71,796.71,796.71,796.71,796.71,796.71,796.71,796.71,796.71,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1047,'Updated Quanities'!F:I,4,0),R1047)=\"\",R1047,IFERROR(VLOOKUP('AUP Library'!A1047,'Updated Quanities'!F:I,4,0),R1047))","v":796.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1047,'Updated Quanities'!F:I,5,0),R1047)=\"\",R1047,IFERROR(VLOOKUP('AUP Library'!A1047,'Updated Quanities'!F:I,5,0),R1047))","v":796.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1047,'Updated Quanities'!F:I,6,0),R1047)=\"\",R1047,IFERROR(VLOOKUP('AUP Library'!A1047,'Updated Quanities'!F:I,6,0),R1047))","v":796.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1047,'Updated Quanities'!F:I,7,0),R1047)=\"\",R1047,IFERROR(VLOOKUP('AUP Library'!A1047,'Updated Quanities'!F:I,7,0),R1047))","v":796.71},796.71,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1047,'Updated Quanities'!F:G,4,0),R1047)","v":796.71}]
["716-12.01","Enhanced Flat Thermo P.M. (4\")","LM",2990.29,2990.29,2990.29,2990.29,2990.29,2990.29,2990.29,2990.29,2990.29,2990.29,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1048,'Updated Quanities'!F:I,4,0),R1048)=\"\",R1048,IFERROR(VLOOKUP('AUP Library'!A1048,'Updated Quanities'!F:I,4,0),R1048))","v":2990.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1048,'Updated Quanities'!F:I,5,0),R1048)=\"\",R1048,IFERROR(VLOOKUP('AUP Library'!A1048,'Updated Quanities'!F:I,5,0),R1048))","v":2990.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1048,'Updated Quanities'!F:I,6,0),R1048)=\"\",R1048,IFERROR(VLOOKUP('AUP Library'!A1048,'Updated Quanities'!F:I,6,0),R1048))","v":2990.29},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1048,'Updated Quanities'!F:I,7,0),R1048)=\"\",R1048,IFERROR(VLOOKUP('AUP Library'!A1048,'Updated Quanities'!F:I,7,0),R1048))","v":2990.29},2990.29,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1048,'Updated Quanities'!F:G,4,0),R1048)","v":2990.29}]
["716-12.02","Enhanced Flat Thermo P.M. (6\")","LM",4833.41,4833.41,4833.41,4833.41,4833.41,4833.41,4833.41,4833.41,4833.41,4833.41,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1049,'Updated Quanities'!F:I,4,0),R1049)=\"\",R1049,IFERROR(VLOOKUP('AUP Library'!A1049,'Updated Quanities'!F:I,4,0),R1049))","v":4833.41},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1049,'Updated Quanities'!F:I,5,0),R1049)=\"\",R1049,IFERROR(VLOOKUP('AUP Library'!A1049,'Updated Quanities'!F:I,5,0),R1049))","v":4833.41},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1049,'Updated Quanities'!F:I,6,0),R1049)=\"\",R1049,IFERROR(VLOOKUP('AUP Library'!A1049,'Updated Quanities'!F:I,6,0),R1049))","v":4833.41},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1049,'Updated Quanities'!F:I,7,0),R1049)=\"\",R1049,IFERROR(VLOOKUP('AUP Library'!A1049,'Updated Quanities'!F:I,7,0),R1049))","v":4833.41},4833.41,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1049,'Updated Quanities'!F:G,4,0),R1049)","v":4833.41}]
["716-12.03","Enhanced Flat Thermo P.M. (8\" Barrier)","LF",2.35,2.35,2.35,2.35,2.35,2.35,2.35,2.35,2.35,2.35,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1050,'Updated Quanities'!F:I,4,0),R1050)=\"\",R1050,IFERROR(VLOOKUP('AUP Library'!A1050,'Updated Quanities'!F:I,4,0),R1050))","v":2.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1050,'Updated Quanities'!F:I,5,0),R1050)=\"\",R1050,IFERROR(VLOOKUP('AUP Library'!A1050,'Updated Quanities'!F:I,5,0),R1050))","v":2.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1050,'Updated Quanities'!F:I,6,0),R1050)=\"\",R1050,IFERROR(VLOOKUP('AUP Library'!A1050,'Updated Quanities'!F:I,6,0),R1050))","v":2.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1050,'Updated Quanities'!F:I,7,0),R1050)=\"\",R1050,IFERROR(VLOOKUP('AUP Library'!A1050,'Updated Quanities'!F:I,7,0),R1050))","v":2.35},2.35,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1050,'Updated Quanities'!F:G,4,0),R1050)","v":2.35}]
["716-12.04","Enhanced Flat Thermo (4\" Dotted)","LF",1.52,1.52,1.52,1.52,1.52,1.52,1.52,1.52,1.52,1.52,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1051,'Updated Quanities'!F:I,4,0),R1051)=\"\",R1051,IFERROR(VLOOKUP('AUP Library'!A1051,'Updated Quanities'!F:I,4,0),R1051))","v":1.52},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1051,'Updated Quanities'!F:I,5,0),R1051)=\"\",R1051,IFERROR(VLOOKUP('AUP Library'!A1051,'Updated Quanities'!F:I,5,0),R1051))","v":1.52},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1051,'Updated Quanities'!F:I,6,0),R1051)=\"\",R1051,IFERROR(VLOOKUP('AUP Library'!A1051,'Updated Quanities'!F:I,6,0),R1051))","v":1.52},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1051,'Updated Quanities'!F:I,7,0),R1051)=\"\",R1051,IFERROR(VLOOKUP('AUP Library'!A1051,'Updated Quanities'!F:I,7,0),R1051))","v":1.52},1.52,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1051,'Updated Quanities'!F:G,4,0),R1051)","v":1.52}]
["716-12.05","Enhanced Flat Thermo (6\" Dotted)","LF",2.09,2.09,2.09,2.09,2.09,2.09,2.09,2.09,2.09,2.09,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1052,'Updated Quanities'!F:I,4,0),R1052)=\"\",R1052,IFERROR(VLOOKUP('AUP Library'!A1052,'Updated Quanities'!F:I,4,0),R1052))","v":2.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1052,'Updated Quanities'!F:I,5,0),R1052)=\"\",R1052,IFERROR(VLOOKUP('AUP Library'!A1052,'Updated Quanities'!F:I,5,0),R1052))","v":2.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1052,'Updated Quanities'!F:I,6,0),R1052)=\"\",R1052,IFERROR(VLOOKUP('AUP Library'!A1052,'Updated Quanities'!F:I,6,0),R1052))","v":2.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1052,'Updated Quanities'!F:I,7,0),R1052)=\"\",R1052,IFERROR(VLOOKUP('AUP Library'!A1052,'Updated Quanities'!F:I,7,0),R1052))","v":2.09},2.09,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1052,'Updated Quanities'!F:G,4,0),R1052)","v":2.09}]
["716-12.06","Enhanced Flat Thermo (8\" Line)","LF",12.77,12.77,12.77,12.77,12.77,12.77,12.77,12.77,12.77,12.77,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1053,'Updated Quanities'!F:I,4,0),R1053)=\"\",R1053,IFERROR(VLOOKUP('AUP Library'!A1053,'Updated Quanities'!F:I,4,0),R1053))","v":12.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1053,'Updated Quanities'!F:I,5,0),R1053)=\"\",R1053,IFERROR(VLOOKUP('AUP Library'!A1053,'Updated Quanities'!F:I,5,0),R1053))","v":12.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1053,'Updated Quanities'!F:I,6,0),R1053)=\"\",R1053,IFERROR(VLOOKUP('AUP Library'!A1053,'Updated Quanities'!F:I,6,0),R1053))","v":12.77},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1053,'Updated Quanities'!F:I,7,0),R1053)=\"\",R1053,IFERROR(VLOOKUP('AUP Library'!A1053,'Updated Quanities'!F:I,7,0),R1053))","v":12.77},12.77,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1053,'Updated Quanities'!F:G,4,0),R1053)","v":12.77}]
["716-12.07","Enhanced Flat Thermo (8\" Broken Line)","LF",20.51,20.51,20.51,20.51,20.51,20.51,20.51,20.51,20.51,20.51,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1054,'Updated Quanities'!F:I,4,0),R1054)=\"\",R1054,IFERROR(VLOOKUP('AUP Library'!A1054,'Updated Quanities'!F:I,4,0),R1054))","v":20.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1054,'Updated Quanities'!F:I,5,0),R1054)=\"\",R1054,IFERROR(VLOOKUP('AUP Library'!A1054,'Updated Quanities'!F:I,5,0),R1054))","v":20.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1054,'Updated Quanities'!F:I,6,0),R1054)=\"\",R1054,IFERROR(VLOOKUP('AUP Library'!A1054,'Updated Quanities'!F:I,6,0),R1054))","v":20.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1054,'Updated Quanities'!F:I,7,0),R1054)=\"\",R1054,IFERROR(VLOOKUP('AUP Library'!A1054,'Updated Quanities'!F:I,7,0),R1054))","v":20.51},20.51,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1054,'Updated Quanities'!F:G,4,0),R1054)","v":20.51}]
["716-12.08","Enhanced Flat Thermo (12\" Barrier)","LF",3.4,3.4,3.4,3.4,3.4,3.4,3.4,3.4,3.4,3.4,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1055,'Updated Quanities'!F:I,4,0),R1055)=\"\",R1055,IFERROR(VLOOKUP('AUP Library'!A1055,'Updated Quanities'!F:I,4,0),R1055))","v":3.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1055,'Updated Quanities'!F:I,5,0),R1055)=\"\",R1055,IFERROR(VLOOKUP('AUP Library'!A1055,'Updated Quanities'!F:I,5,0),R1055))","v":3.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1055,'Updated Quanities'!F:I,6,0),R1055)=\"\",R1055,IFERROR(VLOOKUP('AUP Library'!A1055,'Updated Quanities'!F:I,6,0),R1055))","v":3.4},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1055,'Updated Quanities'!F:I,7,0),R1055)=\"\",R1055,IFERROR(VLOOKUP('AUP Library'!A1055,'Updated Quanities'!F:I,7,0),R1055))","v":3.4},3.4,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1055,'Updated Quanities'!F:G,4,0),R1055)","v":3.4}]
["716-12.09","Enhanced Flat Thermo (12\" Line)","LF",3.09,3.09,3.09,3.09,3.09,3.09,3.09,3.09,3.09,3.09,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1056,'Updated Quanities'!F:I,4,0),R1056)=\"\",R1056,IFERROR(VLOOKUP('AUP Library'!A1056,'Updated Quanities'!F:I,4,0),R1056))","v":3.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1056,'Updated Quanities'!F:I,5,0),R1056)=\"\",R1056,IFERROR(VLOOKUP('AUP Library'!A1056,'Updated Quanities'!F:I,5,0),R1056))","v":3.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1056,'Updated Quanities'!F:I,6,0),R1056)=\"\",R1056,IFERROR(VLOOKUP('AUP Library'!A1056,'Updated Quanities'!F:I,6,0),R1056))","v":3.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1056,'Updated Quanities'!F:I,7,0),R1056)=\"\",R1056,IFERROR(VLOOKUP('AUP Library'!A1056,'Updated Quanities'!F:I,7,0),R1056))","v":3.09},3.09,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1056,'Updated Quanities'!F:G,4,0),R1056)","v":3.09}]
["716-12.10","Enhanced Flat Thermo (12\" Dotted)","LF",3.3,3.3,3.3,3.3,3.3,3.3,3.3,3.3,3.3,3.3,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1057,'Updated Quanities'!F:I,4,0),R1057)=\"\",R1057,IFERROR(VLOOKUP('AUP Library'!A1057,'Updated Quanities'!F:I,4,0),R1057))","v":3.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1057,'Updated Quanities'!F:I,5,0),R1057)=\"\",R1057,IFERROR(VLOOKUP('AUP Library'!A1057,'Updated Quanities'!F:I,5,0),R1057))","v":3.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1057,'Updated Quanities'!F:I,6,0),R1057)=\"\",R1057,IFERROR(VLOOKUP('AUP Library'!A1057,'Updated Quanities'!F:I,6,0),R1057))","v":3.3},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1057,'Updated Quanities'!F:I,7,0),R1057)=\"\",R1057,IFERROR(VLOOKUP('AUP Library'!A1057,'Updated Quanities'!F:I,7,0),R1057))","v":3.3},3.3,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1057,'Updated Quanities'!F:G,4,0),R1057)","v":3.3}]
["716-13.01","Spray Thermo P.M. (60 Mil 4\")","LM",1948.24,1948.24,1948.24,1948.24,1948.24,1948.24,1948.24,1948.24,1948.24,1948.24,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1058,'Updated Quanities'!F:I,4,0),R1058)=\"\",R1058,IFERROR(VLOOKUP('AUP Library'!A1058,'Updated Quanities'!F:I,4,0),R1058))","v":1948.24},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1058,'Updated Quanities'!F:I,5,0),R1058)=\"\",R1058,IFERROR(VLOOKUP('AUP Library'!A1058,'Updated Quanities'!F:I,5,0),R1058))","v":1948.24},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1058,'Updated Quanities'!F:I,6,0),R1058)=\"\",R1058,IFERROR(VLOOKUP('AUP Library'!A1058,'Updated Quanities'!F:I,6,0),R1058))","v":1948.24},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1058,'Updated Quanities'!F:I,7,0),R1058)=\"\",R1058,IFERROR(VLOOKUP('AUP Library'!A1058,'Updated Quanities'!F:I,7,0),R1058))","v":1948.24},1948.24,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1058,'Updated Quanities'!F:G,4,0),R1058)","v":1948.24}]
["716-13.02","Spray Thermo P.M. (60 mil 6\")","LM",2749.24,2749.24,2749.24,2749.24,2749.24,2749.24,2749.24,2749.24,2749.24,2749.24,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1059,'Updated Quanities'!F:I,4,0),R1059)=\"\",R1059,IFERROR(VLOOKUP('AUP Library'!A1059,'Updated Quanities'!F:I,4,0),R1059))","v":2749.24},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1059,'Updated Quanities'!F:I,5,0),R1059)=\"\",R1059,IFERROR(VLOOKUP('AUP Library'!A1059,'Updated Quanities'!F:I,5,0),R1059))","v":2749.24},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1059,'Updated Quanities'!F:I,6,0),R1059)=\"\",R1059,IFERROR(VLOOKUP('AUP Library'!A1059,'Updated Quanities'!F:I,6,0),R1059))","v":2749.24},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1059,'Updated Quanities'!F:I,7,0),R1059)=\"\",R1059,IFERROR(VLOOKUP('AUP Library'!A1059,'Updated Quanities'!F:I,7,0),R1059))","v":2749.24},2749.24,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1059,'Updated Quanities'!F:G,4,0),R1059)","v":2749.24}]
["716-13.03","Spray Thermo P.M. (60 mil 8\" Barrier)","LF",2.35,2.35,2.35,2.35,2.35,2.35,2.35,2.35,2.35,2.35,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1060,'Updated Quanities'!F:I,4,0),R1060)=\"\",R1060,IFERROR(VLOOKUP('AUP Library'!A1060,'Updated Quanities'!F:I,4,0),R1060))","v":2.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1060,'Updated Quanities'!F:I,5,0),R1060)=\"\",R1060,IFERROR(VLOOKUP('AUP Library'!A1060,'Updated Quanities'!F:I,5,0),R1060))","v":2.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1060,'Updated Quanities'!F:I,6,0),R1060)=\"\",R1060,IFERROR(VLOOKUP('AUP Library'!A1060,'Updated Quanities'!F:I,6,0),R1060))","v":2.35},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1060,'Updated Quanities'!F:I,7,0),R1060)=\"\",R1060,IFERROR(VLOOKUP('AUP Library'!A1060,'Updated Quanities'!F:I,7,0),R1060))","v":2.35},2.35,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1060,'Updated Quanities'!F:G,4,0),R1060)","v":2.35}]
["716-13.04","Spray Thermo (60 Mil 4\" Dotted)","LF",1.55,1.55,1.55,1.55,1.55,1.55,1.55,1.55,1.55,1.55,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1061,'Updated Quanities'!F:I,4,0),R1061)=\"\",R1061,IFERROR(VLOOKUP('AUP Library'!A1061,'Updated Quanities'!F:I,4,0),R1061))","v":1.55},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1061,'Updated Quanities'!F:I,5,0),R1061)=\"\",R1061,IFERROR(VLOOKUP('AUP Library'!A1061,'Updated Quanities'!F:I,5,0),R1061))","v":1.55},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1061,'Updated Quanities'!F:I,6,0),R1061)=\"\",R1061,IFERROR(VLOOKUP('AUP Library'!A1061,'Updated Quanities'!F:I,6,0),R1061))","v":1.55},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1061,'Updated Quanities'!F:I,7,0),R1061)=\"\",R1061,IFERROR(VLOOKUP('AUP Library'!A1061,'Updated Quanities'!F:I,7,0),R1061))","v":1.55},1.55,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1061,'Updated Quanities'!F:G,4,0),R1061)","v":1.55}]
["716-13.05","Spray Thermo P.M. (60 mil 6\" Dotted)","LF",2.15,2.15,2.15,2.15,2.15,2.15,2.15,2.15,2.15,2.15,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1062,'Updated Quanities'!F:I,4,0),R1062)=\"\",R1062,IFERROR(VLOOKUP('AUP Library'!A1062,'Updated Quanities'!F:I,4,0),R1062))","v":2.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1062,'Updated Quanities'!F:I,5,0),R1062)=\"\",R1062,IFERROR(VLOOKUP('AUP Library'!A1062,'Updated Quanities'!F:I,5,0),R1062))","v":2.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1062,'Updated Quanities'!F:I,6,0),R1062)=\"\",R1062,IFERROR(VLOOKUP('AUP Library'!A1062,'Updated Quanities'!F:I,6,0),R1062))","v":2.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1062,'Updated Quanities'!F:I,7,0),R1062)=\"\",R1062,IFERROR(VLOOKUP('AUP Library'!A1062,'Updated Quanities'!F:I,7,0),R1062))","v":2.15},2.15,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1062,'Updated Quanities'!F:G,4,0),R1062)","v":2.15}]
["716-13.06","Spray Thermo P.M. (40 mil 4\")","LM",1677.41,1457.6,1734.12,1658.42,1658.42,2100.9299999999998,1687.17,1246.6500000000001,1208.3499999999999,1376.74,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1063,'Updated Quanities'!F:I,4,0),R1063)=\"\",R1063,IFERROR(VLOOKUP('AUP Library'!A1063,'Updated Quanities'!F:I,4,0),R1063))","v":1188.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1063,'Updated Quanities'!F:I,5,0),R1063)=\"\",R1063,IFERROR(VLOOKUP('AUP Library'!A1063,'Updated Quanities'!F:I,5,0),R1063))","v":1188.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1063,'Updated Quanities'!F:I,6,0),R1063)=\"\",R1063,IFERROR(VLOOKUP('AUP Library'!A1063,'Updated Quanities'!F:I,6,0),R1063))","v":1188.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1063,'Updated Quanities'!F:I,7,0),R1063)=\"\",R1063,IFERROR(VLOOKUP('AUP Library'!A1063,'Updated Quanities'!F:I,7,0),R1063))","v":1188.71},1188.71,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1063,'Updated Quanities'!F:G,4,0),R1063)","v":1188.71}]
["716-13.07","Spray Thermo P.M. (40 mil 6\")","LM",1237.5,1237.5,1237.5,1237.5,1237.5,1237.5,1237.5,1237.5,1237.5,1237.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1064,'Updated Quanities'!F:I,4,0),R1064)=\"\",R1064,IFERROR(VLOOKUP('AUP Library'!A1064,'Updated Quanities'!F:I,4,0),R1064))","v":1237.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1064,'Updated Quanities'!F:I,5,0),R1064)=\"\",R1064,IFERROR(VLOOKUP('AUP Library'!A1064,'Updated Quanities'!F:I,5,0),R1064))","v":1237.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1064,'Updated Quanities'!F:I,6,0),R1064)=\"\",R1064,IFERROR(VLOOKUP('AUP Library'!A1064,'Updated Quanities'!F:I,6,0),R1064))","v":1237.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1064,'Updated Quanities'!F:I,7,0),R1064)=\"\",R1064,IFERROR(VLOOKUP('AUP Library'!A1064,'Updated Quanities'!F:I,7,0),R1064))","v":1237.5},1237.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1064,'Updated Quanities'!F:G,4,0),R1064)","v":1237.5}]
["716-13.08","Spray Thermo P.M. (40 mil 8\" Barrier)","LF",0.23,0.23,0.23,0.23,0.23,0.23,0.23,0.23,0.23,0.23,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1065,'Updated Quanities'!F:I,4,0),R1065)=\"\",R1065,IFERROR(VLOOKUP('AUP Library'!A1065,'Updated Quanities'!F:I,4,0),R1065))","v":0.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1065,'Updated Quanities'!F:I,5,0),R1065)=\"\",R1065,IFERROR(VLOOKUP('AUP Library'!A1065,'Updated Quanities'!F:I,5,0),R1065))","v":0.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1065,'Updated Quanities'!F:I,6,0),R1065)=\"\",R1065,IFERROR(VLOOKUP('AUP Library'!A1065,'Updated Quanities'!F:I,6,0),R1065))","v":0.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1065,'Updated Quanities'!F:I,7,0),R1065)=\"\",R1065,IFERROR(VLOOKUP('AUP Library'!A1065,'Updated Quanities'!F:I,7,0),R1065))","v":0.23},0.23,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1065,'Updated Quanities'!F:G,4,0),R1065)","v":0.23}]
["716-13.09","Spray Thermo P.M. (40 mil 4\" Dotted)","LF",246.02,246.02,246.02,246.02,246.02,246.02,246.02,246.02,246.02,246.02,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1066,'Updated Quanities'!F:I,4,0),R1066)=\"\",R1066,IFERROR(VLOOKUP('AUP Library'!A1066,'Updated Quanities'!F:I,4,0),R1066))","v":246.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1066,'Updated Quanities'!F:I,5,0),R1066)=\"\",R1066,IFERROR(VLOOKUP('AUP Library'!A1066,'Updated Quanities'!F:I,5,0),R1066))","v":246.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1066,'Updated Quanities'!F:I,6,0),R1066)=\"\",R1066,IFERROR(VLOOKUP('AUP Library'!A1066,'Updated Quanities'!F:I,6,0),R1066))","v":246.02},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1066,'Updated Quanities'!F:I,7,0),R1066)=\"\",R1066,IFERROR(VLOOKUP('AUP Library'!A1066,'Updated Quanities'!F:I,7,0),R1066))","v":246.02},246.02,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1066,'Updated Quanities'!F:G,4,0),R1066)","v":246.02}]
["716-13.10","Spray Thermo P.M. (40 mil 6\" Dotted)","LF",568.71,568.71,568.71,568.71,568.71,568.71,568.71,568.71,568.71,568.71,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1067,'Updated Quanities'!F:I,4,0),R1067)=\"\",R1067,IFERROR(VLOOKUP('AUP Library'!A1067,'Updated Quanities'!F:I,4,0),R1067))","v":568.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1067,'Updated Quanities'!F:I,5,0),R1067)=\"\",R1067,IFERROR(VLOOKUP('AUP Library'!A1067,'Updated Quanities'!F:I,5,0),R1067))","v":568.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1067,'Updated Quanities'!F:I,6,0),R1067)=\"\",R1067,IFERROR(VLOOKUP('AUP Library'!A1067,'Updated Quanities'!F:I,6,0),R1067))","v":568.71},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1067,'Updated Quanities'!F:I,7,0),R1067)=\"\",R1067,IFERROR(VLOOKUP('AUP Library'!A1067,'Updated Quanities'!F:I,7,0),R1067))","v":568.71},568.71,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1067,'Updated Quanities'!F:G,4,0),R1067)","v":568.71}]
[]
[]
["Fencing"]
["707-01.01","Chain Link Fence (4 Foot)","LF",10.15,10.15,10.15,10.15,10.15,10.15,10.15,10.15,10.15,10.15,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1071,'Updated Quanities'!F:I,4,0),R1071)=\"\",R1071,IFERROR(VLOOKUP('AUP Library'!A1071,'Updated Quanities'!F:I,4,0),R1071))","v":10.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1071,'Updated Quanities'!F:I,5,0),R1071)=\"\",R1071,IFERROR(VLOOKUP('AUP Library'!A1071,'Updated Quanities'!F:I,5,0),R1071))","v":10.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1071,'Updated Quanities'!F:I,6,0),R1071)=\"\",R1071,IFERROR(VLOOKUP('AUP Library'!A1071,'Updated Quanities'!F:I,6,0),R1071))","v":10.15},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1071,'Updated Quanities'!F:I,7,0),R1071)=\"\",R1071,IFERROR(VLOOKUP('AUP Library'!A1071,'Updated Quanities'!F:I,7,0),R1071))","v":10.15},10.15,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1071,'Updated Quanities'!F:G,4,0),R1071)","v":10.15}]
["707-01.02","End & Corner Post Assembly (CL Fence 4')","EA",132.38999999999999,132.38999999999999,132.38999999999999,132.38999999999999,132.38999999999999,132.38999999999999,132.38999999999999,132.38999999999999,132.38999999999999,132.38999999999999,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1072,'Updated Quanities'!F:I,4,0),R1072)=\"\",R1072,IFERROR(VLOOKUP('AUP Library'!A1072,'Updated Quanities'!F:I,4,0),R1072))","v":132.38999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1072,'Updated Quanities'!F:I,5,0),R1072)=\"\",R1072,IFERROR(VLOOKUP('AUP Library'!A1072,'Updated Quanities'!F:I,5,0),R1072))","v":132.38999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1072,'Updated Quanities'!F:I,6,0),R1072)=\"\",R1072,IFERROR(VLOOKUP('AUP Library'!A1072,'Updated Quanities'!F:I,6,0),R1072))","v":132.38999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1072,'Updated Quanities'!F:I,7,0),R1072)=\"\",R1072,IFERROR(VLOOKUP('AUP Library'!A1072,'Updated Quanities'!F:I,7,0),R1072))","v":132.38999999999999},132.38999999999999,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1072,'Updated Quanities'!F:G,4,0),R1072)","v":132.38999999999999}]
["707-01.11","Chain Link Fence (6 Foot)","LF",10.029999999999999,10.029999999999999,10.029999999999999,10.029999999999999,10.029999999999999,10.029999999999999,10.029999999999999,10.029999999999999,10.029999999999999,10.029999999999999,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1073,'Updated Quanities'!F:I,4,0),R1073)=\"\",R1073,IFERROR(VLOOKUP('AUP Library'!A1073,'Updated Quanities'!F:I,4,0),R1073))","v":10.029999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1073,'Updated Quanities'!F:I,5,0),R1073)=\"\",R1073,IFERROR(VLOOKUP('AUP Library'!A1073,'Updated Quanities'!F:I,5,0),R1073))","v":10.029999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1073,'Updated Quanities'!F:I,6,0),R1073)=\"\",R1073,IFERROR(VLOOKUP('AUP Library'!A1073,'Updated Quanities'!F:I,6,0),R1073))","v":10.029999999999999},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1073,'Updated Quanities'!F:I,7,0),R1073)=\"\",R1073,IFERROR(VLOOKUP('AUP Library'!A1073,'Updated Quanities'!F:I,7,0),R1073))","v":10.029999999999999},10.029999999999999,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1073,'Updated Quanities'!F:G,4,0),R1073)","v":10.029999999999999}]
["707-01.12","End & Corner Post ASM(CL Fence 6')","EA",165.92,165.92,165.92,165.92,165.92,165.92,165.92,165.92,165.92,165.92,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1074,'Updated Quanities'!F:I,4,0),R1074)=\"\",R1074,IFERROR(VLOOKUP('AUP Library'!A1074,'Updated Quanities'!F:I,4,0),R1074))","v":165.92},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1074,'Updated Quanities'!F:I,5,0),R1074)=\"\",R1074,IFERROR(VLOOKUP('AUP Library'!A1074,'Updated Quanities'!F:I,5,0),R1074))","v":165.92},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1074,'Updated Quanities'!F:I,6,0),R1074)=\"\",R1074,IFERROR(VLOOKUP('AUP Library'!A1074,'Updated Quanities'!F:I,6,0),R1074))","v":165.92},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1074,'Updated Quanities'!F:I,7,0),R1074)=\"\",R1074,IFERROR(VLOOKUP('AUP Library'!A1074,'Updated Quanities'!F:I,7,0),R1074))","v":165.92},165.92,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1074,'Updated Quanities'!F:G,4,0),R1074)","v":165.92}]
["707-01.13","Gate -CL Fence-6 Foot","EA",1411.2,1411.2,1411.2,1411.2,1411.2,1411.2,1411.2,1411.2,1411.2,1411.2,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1075,'Updated Quanities'!F:I,4,0),R1075)=\"\",R1075,IFERROR(VLOOKUP('AUP Library'!A1075,'Updated Quanities'!F:I,4,0),R1075))","v":1411.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1075,'Updated Quanities'!F:I,5,0),R1075)=\"\",R1075,IFERROR(VLOOKUP('AUP Library'!A1075,'Updated Quanities'!F:I,5,0),R1075))","v":1411.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1075,'Updated Quanities'!F:I,6,0),R1075)=\"\",R1075,IFERROR(VLOOKUP('AUP Library'!A1075,'Updated Quanities'!F:I,6,0),R1075))","v":1411.2},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1075,'Updated Quanities'!F:I,7,0),R1075)=\"\",R1075,IFERROR(VLOOKUP('AUP Library'!A1075,'Updated Quanities'!F:I,7,0),R1075))","v":1411.2},1411.2,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1075,'Updated Quanities'!F:G,4,0),R1075)","v":1411.2}]
["707-01.14","Gate-CL Fence - 6 Foot","EA",3000,3000,3000,3000,3000,3000,3000,3000,3000,3000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1076,'Updated Quanities'!F:I,4,0),R1076)=\"\",R1076,IFERROR(VLOOKUP('AUP Library'!A1076,'Updated Quanities'!F:I,4,0),R1076))","v":3000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1076,'Updated Quanities'!F:I,5,0),R1076)=\"\",R1076,IFERROR(VLOOKUP('AUP Library'!A1076,'Updated Quanities'!F:I,5,0),R1076))","v":3000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1076,'Updated Quanities'!F:I,6,0),R1076)=\"\",R1076,IFERROR(VLOOKUP('AUP Library'!A1076,'Updated Quanities'!F:I,6,0),R1076))","v":3000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1076,'Updated Quanities'!F:I,7,0),R1076)=\"\",R1076,IFERROR(VLOOKUP('AUP Library'!A1076,'Updated Quanities'!F:I,7,0),R1076))","v":3000},3000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1076,'Updated Quanities'!F:G,4,0),R1076)","v":3000}]
["707-01.20","Temp 6ft Chainlink W/3 Strand B. Wire","LF",10,10,10,10,10,10,10,10,10,10,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1077,'Updated Quanities'!F:I,4,0),R1077)=\"\",R1077,IFERROR(VLOOKUP('AUP Library'!A1077,'Updated Quanities'!F:I,4,0),R1077))","v":10},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1077,'Updated Quanities'!F:I,5,0),R1077)=\"\",R1077,IFERROR(VLOOKUP('AUP Library'!A1077,'Updated Quanities'!F:I,5,0),R1077))","v":10},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1077,'Updated Quanities'!F:I,6,0),R1077)=\"\",R1077,IFERROR(VLOOKUP('AUP Library'!A1077,'Updated Quanities'!F:I,6,0),R1077))","v":10},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1077,'Updated Quanities'!F:I,7,0),R1077)=\"\",R1077,IFERROR(VLOOKUP('AUP Library'!A1077,'Updated Quanities'!F:I,7,0),R1077))","v":10},10,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1077,'Updated Quanities'!F:G,4,0),R1077)","v":10}]
["707-01.23","Chain-Link (6FT)(Vinyl CTD) W/3 STR B.W.","LF",19.350000000000001,19.350000000000001,19.350000000000001,19.350000000000001,19.350000000000001,19.350000000000001,19.350000000000001,19.350000000000001,19.350000000000001,19.350000000000001,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1078,'Updated Quanities'!F:I,4,0),R1078)=\"\",R1078,IFERROR(VLOOKUP('AUP Library'!A1078,'Updated Quanities'!F:I,4,0),R1078))","v":19.350000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1078,'Updated Quanities'!F:I,5,0),R1078)=\"\",R1078,IFERROR(VLOOKUP('AUP Library'!A1078,'Updated Quanities'!F:I,5,0),R1078))","v":19.350000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1078,'Updated Quanities'!F:I,6,0),R1078)=\"\",R1078,IFERROR(VLOOKUP('AUP Library'!A1078,'Updated Quanities'!F:I,6,0),R1078))","v":19.350000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1078,'Updated Quanities'!F:I,7,0),R1078)=\"\",R1078,IFERROR(VLOOKUP('AUP Library'!A1078,'Updated Quanities'!F:I,7,0),R1078))","v":19.350000000000001},19.350000000000001,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1078,'Updated Quanities'!F:G,4,0),R1078)","v":19.350000000000001}]
["707-01.28","End & Corner Post Assembly (Description)","EA",112,112,112,112,112,112,112,112,112,112,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1079,'Updated Quanities'!F:I,4,0),R1079)=\"\",R1079,IFERROR(VLOOKUP('AUP Library'!A1079,'Updated Quanities'!F:I,4,0),R1079))","v":112},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1079,'Updated Quanities'!F:I,5,0),R1079)=\"\",R1079,IFERROR(VLOOKUP('AUP Library'!A1079,'Updated Quanities'!F:I,5,0),R1079))","v":112},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1079,'Updated Quanities'!F:I,6,0),R1079)=\"\",R1079,IFERROR(VLOOKUP('AUP Library'!A1079,'Updated Quanities'!F:I,6,0),R1079))","v":112},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1079,'Updated Quanities'!F:I,7,0),R1079)=\"\",R1079,IFERROR(VLOOKUP('AUP Library'!A1079,'Updated Quanities'!F:I,7,0),R1079))","v":112},112,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1079,'Updated Quanities'!F:G,4,0),R1079)","v":112}]
["707-01.50","Chain-Link Fence","LF",10.58,10.58,10.58,10.58,10.58,10.58,10.58,10.58,10.58,10.58,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1080,'Updated Quanities'!F:I,4,0),R1080)=\"\",R1080,IFERROR(VLOOKUP('AUP Library'!A1080,'Updated Quanities'!F:I,4,0),R1080))","v":10.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1080,'Updated Quanities'!F:I,5,0),R1080)=\"\",R1080,IFERROR(VLOOKUP('AUP Library'!A1080,'Updated Quanities'!F:I,5,0),R1080))","v":10.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1080,'Updated Quanities'!F:I,6,0),R1080)=\"\",R1080,IFERROR(VLOOKUP('AUP Library'!A1080,'Updated Quanities'!F:I,6,0),R1080))","v":10.58},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1080,'Updated Quanities'!F:I,7,0),R1080)=\"\",R1080,IFERROR(VLOOKUP('AUP Library'!A1080,'Updated Quanities'!F:I,7,0),R1080))","v":10.58},10.58,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1080,'Updated Quanities'!F:G,4,0),R1080)","v":10.58}]
["707-01.51","End and Corner Post Assembly (Chain-Link Fence 6\")","EA",172.5,172.5,172.5,172.5,172.5,172.5,172.5,172.5,172.5,172.5,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1081,'Updated Quanities'!F:I,4,0),R1081)=\"\",R1081,IFERROR(VLOOKUP('AUP Library'!A1081,'Updated Quanities'!F:I,4,0),R1081))","v":172.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1081,'Updated Quanities'!F:I,5,0),R1081)=\"\",R1081,IFERROR(VLOOKUP('AUP Library'!A1081,'Updated Quanities'!F:I,5,0),R1081))","v":172.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1081,'Updated Quanities'!F:I,6,0),R1081)=\"\",R1081,IFERROR(VLOOKUP('AUP Library'!A1081,'Updated Quanities'!F:I,6,0),R1081))","v":172.5},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1081,'Updated Quanities'!F:I,7,0),R1081)=\"\",R1081,IFERROR(VLOOKUP('AUP Library'!A1081,'Updated Quanities'!F:I,7,0),R1081))","v":172.5},172.5,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1081,'Updated Quanities'!F:G,4,0),R1081)","v":172.5}]
["707-01.52","Gate - CL Fence","EA",700,700,700,700,700,700,700,700,700,700,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1082,'Updated Quanities'!F:I,4,0),R1082)=\"\",R1082,IFERROR(VLOOKUP('AUP Library'!A1082,'Updated Quanities'!F:I,4,0),R1082))","v":700},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1082,'Updated Quanities'!F:I,5,0),R1082)=\"\",R1082,IFERROR(VLOOKUP('AUP Library'!A1082,'Updated Quanities'!F:I,5,0),R1082))","v":700},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1082,'Updated Quanities'!F:I,6,0),R1082)=\"\",R1082,IFERROR(VLOOKUP('AUP Library'!A1082,'Updated Quanities'!F:I,6,0),R1082))","v":700},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1082,'Updated Quanities'!F:I,7,0),R1082)=\"\",R1082,IFERROR(VLOOKUP('AUP Library'!A1082,'Updated Quanities'!F:I,7,0),R1082))","v":700},700,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1082,'Updated Quanities'!F:G,4,0),R1082)","v":700}]
["707-06.01","Removal of Fence","LF",2.0299999999999998,2.0299999999999998,2.0299999999999998,2.0299999999999998,2.0299999999999998,2.0299999999999998,2.0299999999999998,2.0299999999999998,2.0299999999999998,2.0299999999999998,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1083,'Updated Quanities'!F:I,4,0),R1083)=\"\",R1083,IFERROR(VLOOKUP('AUP Library'!A1083,'Updated Quanities'!F:I,4,0),R1083))","v":2.0299999999999998},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1083,'Updated Quanities'!F:I,5,0),R1083)=\"\",R1083,IFERROR(VLOOKUP('AUP Library'!A1083,'Updated Quanities'!F:I,5,0),R1083))","v":2.0299999999999998},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1083,'Updated Quanities'!F:I,6,0),R1083)=\"\",R1083,IFERROR(VLOOKUP('AUP Library'!A1083,'Updated Quanities'!F:I,6,0),R1083))","v":2.0299999999999998},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1083,'Updated Quanities'!F:I,7,0),R1083)=\"\",R1083,IFERROR(VLOOKUP('AUP Library'!A1083,'Updated Quanities'!F:I,7,0),R1083))","v":2.0299999999999998},2.0299999999999998,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1083,'Updated Quanities'!F:G,4,0),R1083)","v":2.0299999999999998}]
["707-06.03","Removal and Reset Fence","LF",16.23,16.23,16.23,16.23,16.23,16.23,16.23,16.23,16.23,16.23,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1084,'Updated Quanities'!F:I,4,0),R1084)=\"\",R1084,IFERROR(VLOOKUP('AUP Library'!A1084,'Updated Quanities'!F:I,4,0),R1084))","v":16.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1084,'Updated Quanities'!F:I,5,0),R1084)=\"\",R1084,IFERROR(VLOOKUP('AUP Library'!A1084,'Updated Quanities'!F:I,5,0),R1084))","v":16.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1084,'Updated Quanities'!F:I,6,0),R1084)=\"\",R1084,IFERROR(VLOOKUP('AUP Library'!A1084,'Updated Quanities'!F:I,6,0),R1084))","v":16.23},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1084,'Updated Quanities'!F:I,7,0),R1084)=\"\",R1084,IFERROR(VLOOKUP('AUP Library'!A1084,'Updated Quanities'!F:I,7,0),R1084))","v":16.23},16.23,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1084,'Updated Quanities'!F:G,4,0),R1084)","v":16.23}]
["707-07.01","Chain-Link Fence (Bridges)","LF",17.489999999999998,17.489999999999998,17.489999999999998,17.489999999999998,17.489999999999998,17.489999999999998,17.489999999999998,17.489999999999998,17.489999999999998,17.489999999999998,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1085,'Updated Quanities'!F:I,4,0),R1085)=\"\",R1085,IFERROR(VLOOKUP('AUP Library'!A1085,'Updated Quanities'!F:I,4,0),R1085))","v":17.489999999999998},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1085,'Updated Quanities'!F:I,5,0),R1085)=\"\",R1085,IFERROR(VLOOKUP('AUP Library'!A1085,'Updated Quanities'!F:I,5,0),R1085))","v":17.489999999999998},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1085,'Updated Quanities'!F:I,6,0),R1085)=\"\",R1085,IFERROR(VLOOKUP('AUP Library'!A1085,'Updated Quanities'!F:I,6,0),R1085))","v":17.489999999999998},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1085,'Updated Quanities'!F:I,7,0),R1085)=\"\",R1085,IFERROR(VLOOKUP('AUP Library'!A1085,'Updated Quanities'!F:I,7,0),R1085))","v":17.489999999999998},17.489999999999998,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1085,'Updated Quanities'!F:G,4,0),R1085)","v":17.489999999999998}]
["707-08.01 ","High Visibility Construction Fence","LF",1.67,1.67,1.67,1.67,1.67,1.67,1.67,1.67,1.67,1.67,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1086,'Updated Quanities'!F:I,4,0),R1086)=\"\",R1086,IFERROR(VLOOKUP('AUP Library'!A1086,'Updated Quanities'!F:I,4,0),R1086))","v":1.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1086,'Updated Quanities'!F:I,5,0),R1086)=\"\",R1086,IFERROR(VLOOKUP('AUP Library'!A1086,'Updated Quanities'!F:I,5,0),R1086))","v":1.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1086,'Updated Quanities'!F:I,6,0),R1086)=\"\",R1086,IFERROR(VLOOKUP('AUP Library'!A1086,'Updated Quanities'!F:I,6,0),R1086))","v":1.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1086,'Updated Quanities'!F:I,7,0),R1086)=\"\",R1086,IFERROR(VLOOKUP('AUP Library'!A1086,'Updated Quanities'!F:I,7,0),R1086))","v":1.67},1.67,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1086,'Updated Quanities'!F:G,4,0),R1086)","v":1.67}]
["707-08.02 ","Gate","EA",1000,1000,1000,1000,1000,1000,1000,1000,1000,1000,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1087,'Updated Quanities'!F:I,4,0),R1087)=\"\",R1087,IFERROR(VLOOKUP('AUP Library'!A1087,'Updated Quanities'!F:I,4,0),R1087))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1087,'Updated Quanities'!F:I,5,0),R1087)=\"\",R1087,IFERROR(VLOOKUP('AUP Library'!A1087,'Updated Quanities'!F:I,5,0),R1087))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1087,'Updated Quanities'!F:I,6,0),R1087)=\"\",R1087,IFERROR(VLOOKUP('AUP Library'!A1087,'Updated Quanities'!F:I,6,0),R1087))","v":1000},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1087,'Updated Quanities'!F:I,7,0),R1087)=\"\",R1087,IFERROR(VLOOKUP('AUP Library'!A1087,'Updated Quanities'!F:I,7,0),R1087))","v":1000},1000,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1087,'Updated Quanities'!F:G,4,0),R1087)","v":1000}]
["707-08.11","High Visibility Construction Fence","LF",1.67,1.67,1.67,1.67,1.67,1.67,1.67,1.67,1.67,1.67,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1088,'Updated Quanities'!F:I,4,0),R1088)=\"\",R1088,IFERROR(VLOOKUP('AUP Library'!A1088,'Updated Quanities'!F:I,4,0),R1088))","v":1.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1088,'Updated Quanities'!F:I,5,0),R1088)=\"\",R1088,IFERROR(VLOOKUP('AUP Library'!A1088,'Updated Quanities'!F:I,5,0),R1088))","v":1.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1088,'Updated Quanities'!F:I,6,0),R1088)=\"\",R1088,IFERROR(VLOOKUP('AUP Library'!A1088,'Updated Quanities'!F:I,6,0),R1088))","v":1.67},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1088,'Updated Quanities'!F:I,7,0),R1088)=\"\",R1088,IFERROR(VLOOKUP('AUP Library'!A1088,'Updated Quanities'!F:I,7,0),R1088))","v":1.67},1.67,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1088,'Updated Quanities'!F:G,4,0),R1088)","v":1.67}]
["708-02.01","Markers (Concrete ROW Posts)","EA",184.36,184.36,184.36,184.36,184.36,184.36,184.36,184.36,184.36,184.36,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1089,'Updated Quanities'!F:I,4,0),R1089)=\"\",R1089,IFERROR(VLOOKUP('AUP Library'!A1089,'Updated Quanities'!F:I,4,0),R1089))","v":184.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1089,'Updated Quanities'!F:I,5,0),R1089)=\"\",R1089,IFERROR(VLOOKUP('AUP Library'!A1089,'Updated Quanities'!F:I,5,0),R1089))","v":184.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1089,'Updated Quanities'!F:I,6,0),R1089)=\"\",R1089,IFERROR(VLOOKUP('AUP Library'!A1089,'Updated Quanities'!F:I,6,0),R1089))","v":184.36},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1089,'Updated Quanities'!F:I,7,0),R1089)=\"\",R1089,IFERROR(VLOOKUP('AUP Library'!A1089,'Updated Quanities'!F:I,7,0),R1089))","v":184.36},184.36,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1089,'Updated Quanities'!F:G,4,0),R1089)","v":184.36}]
[]
[]
["Rip-Rap"]
["709-01.01","Rubble Stone Rip-Rap","CY",108.6,108.6,108.6,108.6,108.6,108.6,108.6,108.6,108.6,108.6,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1093,'Updated Quanities'!F:I,4,0),R1093)=\"\",R1093,IFERROR(VLOOKUP('AUP Library'!A1093,'Updated Quanities'!F:I,4,0),R1093))","v":108.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1093,'Updated Quanities'!F:I,5,0),R1093)=\"\",R1093,IFERROR(VLOOKUP('AUP Library'!A1093,'Updated Quanities'!F:I,5,0),R1093))","v":108.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1093,'Updated Quanities'!F:I,6,0),R1093)=\"\",R1093,IFERROR(VLOOKUP('AUP Library'!A1093,'Updated Quanities'!F:I,6,0),R1093))","v":108.6},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1093,'Updated Quanities'!F:I,7,0),R1093)=\"\",R1093,IFERROR(VLOOKUP('AUP Library'!A1093,'Updated Quanities'!F:I,7,0),R1093))","v":108.6},108.6,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1093,'Updated Quanities'!F:G,4,0),R1093)","v":108.6}]
["709-01.02","Rubble Stone Rip-Rap","TON",83.63,83.63,83.63,83.63,83.63,83.63,83.63,83.63,83.63,83.63,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1094,'Updated Quanities'!F:I,4,0),R1094)=\"\",R1094,IFERROR(VLOOKUP('AUP Library'!A1094,'Updated Quanities'!F:I,4,0),R1094))","v":83.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1094,'Updated Quanities'!F:I,5,0),R1094)=\"\",R1094,IFERROR(VLOOKUP('AUP Library'!A1094,'Updated Quanities'!F:I,5,0),R1094))","v":83.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1094,'Updated Quanities'!F:I,6,0),R1094)=\"\",R1094,IFERROR(VLOOKUP('AUP Library'!A1094,'Updated Quanities'!F:I,6,0),R1094))","v":83.63},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1094,'Updated Quanities'!F:I,7,0),R1094)=\"\",R1094,IFERROR(VLOOKUP('AUP Library'!A1094,'Updated Quanities'!F:I,7,0),R1094))","v":83.63},83.63,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1094,'Updated Quanities'!F:G,4,0),R1094)","v":83.63}]
["709-02.01","Rubble Stone Rip-Rap (Grouted)","CY",331.08,331.08,331.08,331.08,331.08,331.08,331.08,331.08,331.08,331.08,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1095,'Updated Quanities'!F:I,4,0),R1095)=\"\",R1095,IFERROR(VLOOKUP('AUP Library'!A1095,'Updated Quanities'!F:I,4,0),R1095))","v":331.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1095,'Updated Quanities'!F:I,5,0),R1095)=\"\",R1095,IFERROR(VLOOKUP('AUP Library'!A1095,'Updated Quanities'!F:I,5,0),R1095))","v":331.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1095,'Updated Quanities'!F:I,6,0),R1095)=\"\",R1095,IFERROR(VLOOKUP('AUP Library'!A1095,'Updated Quanities'!F:I,6,0),R1095))","v":331.08},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1095,'Updated Quanities'!F:I,7,0),R1095)=\"\",R1095,IFERROR(VLOOKUP('AUP Library'!A1095,'Updated Quanities'!F:I,7,0),R1095))","v":331.08},331.08,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1095,'Updated Quanities'!F:G,4,0),R1095)","v":331.08}]
["709-04","Reinforced Concrete Slope Pavement","CY",490.25,490.25,490.25,490.25,490.25,490.25,490.25,490.25,490.25,490.25,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1096,'Updated Quanities'!F:I,4,0),R1096)=\"\",R1096,IFERROR(VLOOKUP('AUP Library'!A1096,'Updated Quanities'!F:I,4,0),R1096))","v":490.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1096,'Updated Quanities'!F:I,5,0),R1096)=\"\",R1096,IFERROR(VLOOKUP('AUP Library'!A1096,'Updated Quanities'!F:I,5,0),R1096))","v":490.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1096,'Updated Quanities'!F:I,6,0),R1096)=\"\",R1096,IFERROR(VLOOKUP('AUP Library'!A1096,'Updated Quanities'!F:I,6,0),R1096))","v":490.25},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1096,'Updated Quanities'!F:I,7,0),R1096)=\"\",R1096,IFERROR(VLOOKUP('AUP Library'!A1096,'Updated Quanities'!F:I,7,0),R1096))","v":490.25},490.25,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1096,'Updated Quanities'!F:G,4,0),R1096)","v":490.25}]
["709-05.02","Machined Rip-Rap (Rubble Stone)","CY",475,475,475,475,475,475,475,475,475,475,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1097,'Updated Quanities'!F:I,4,0),R1097)=\"\",R1097,IFERROR(VLOOKUP('AUP Library'!A1097,'Updated Quanities'!F:I,4,0),R1097))","v":475},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1097,'Updated Quanities'!F:I,5,0),R1097)=\"\",R1097,IFERROR(VLOOKUP('AUP Library'!A1097,'Updated Quanities'!F:I,5,0),R1097))","v":475},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1097,'Updated Quanities'!F:I,6,0),R1097)=\"\",R1097,IFERROR(VLOOKUP('AUP Library'!A1097,'Updated Quanities'!F:I,6,0),R1097))","v":475},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1097,'Updated Quanities'!F:I,7,0),R1097)=\"\",R1097,IFERROR(VLOOKUP('AUP Library'!A1097,'Updated Quanities'!F:I,7,0),R1097))","v":475},475,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1097,'Updated Quanities'!F:G,4,0),R1097)","v":475}]
["709-05.05","Machined Rip-Rap (Class A-3)","TON",30.37,30.37,30.37,30.37,30.37,30.37,30.37,30.37,30.37,30.37,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1098,'Updated Quanities'!F:I,4,0),R1098)=\"\",R1098,IFERROR(VLOOKUP('AUP Library'!A1098,'Updated Quanities'!F:I,4,0),R1098))","v":30.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1098,'Updated Quanities'!F:I,5,0),R1098)=\"\",R1098,IFERROR(VLOOKUP('AUP Library'!A1098,'Updated Quanities'!F:I,5,0),R1098))","v":30.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1098,'Updated Quanities'!F:I,6,0),R1098)=\"\",R1098,IFERROR(VLOOKUP('AUP Library'!A1098,'Updated Quanities'!F:I,6,0),R1098))","v":30.37},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1098,'Updated Quanities'!F:I,7,0),R1098)=\"\",R1098,IFERROR(VLOOKUP('AUP Library'!A1098,'Updated Quanities'!F:I,7,0),R1098))","v":30.37},30.37,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1098,'Updated Quanities'!F:G,4,0),R1098)","v":30.37}]
["709-05.06","Machined Rip-Rap (Class A-1)","TON",32.99,32.99,32.99,32.99,32.99,32.99,32.99,32.99,32.99,32.99,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1099,'Updated Quanities'!F:I,4,0),R1099)=\"\",R1099,IFERROR(VLOOKUP('AUP Library'!A1099,'Updated Quanities'!F:I,4,0),R1099))","v":32.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1099,'Updated Quanities'!F:I,5,0),R1099)=\"\",R1099,IFERROR(VLOOKUP('AUP Library'!A1099,'Updated Quanities'!F:I,5,0),R1099))","v":32.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1099,'Updated Quanities'!F:I,6,0),R1099)=\"\",R1099,IFERROR(VLOOKUP('AUP Library'!A1099,'Updated Quanities'!F:I,6,0),R1099))","v":32.99},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1099,'Updated Quanities'!F:I,7,0),R1099)=\"\",R1099,IFERROR(VLOOKUP('AUP Library'!A1099,'Updated Quanities'!F:I,7,0),R1099))","v":32.99},32.99,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1099,'Updated Quanities'!F:G,4,0),R1099)","v":32.99}]
["709-05.07","Machined Rip-Rap (Class A-2)","TON",63.34,63.34,63.34,63.34,63.34,63.34,63.34,63.34,63.34,63.34,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1100,'Updated Quanities'!F:I,4,0),R1100)=\"\",R1100,IFERROR(VLOOKUP('AUP Library'!A1100,'Updated Quanities'!F:I,4,0),R1100))","v":63.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1100,'Updated Quanities'!F:I,5,0),R1100)=\"\",R1100,IFERROR(VLOOKUP('AUP Library'!A1100,'Updated Quanities'!F:I,5,0),R1100))","v":63.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1100,'Updated Quanities'!F:I,6,0),R1100)=\"\",R1100,IFERROR(VLOOKUP('AUP Library'!A1100,'Updated Quanities'!F:I,6,0),R1100))","v":63.34},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1100,'Updated Quanities'!F:I,7,0),R1100)=\"\",R1100,IFERROR(VLOOKUP('AUP Library'!A1100,'Updated Quanities'!F:I,7,0),R1100))","v":63.34},63.34,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1100,'Updated Quanities'!F:G,4,0),R1100)","v":63.34}]
["709-05.08","Machined Rip-Rap (Class B)","TON",31.09,31.09,31.09,31.09,31.09,31.09,31.09,31.09,31.09,31.09,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1101,'Updated Quanities'!F:I,4,0),R1101)=\"\",R1101,IFERROR(VLOOKUP('AUP Library'!A1101,'Updated Quanities'!F:I,4,0),R1101))","v":31.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1101,'Updated Quanities'!F:I,5,0),R1101)=\"\",R1101,IFERROR(VLOOKUP('AUP Library'!A1101,'Updated Quanities'!F:I,5,0),R1101))","v":31.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1101,'Updated Quanities'!F:I,6,0),R1101)=\"\",R1101,IFERROR(VLOOKUP('AUP Library'!A1101,'Updated Quanities'!F:I,6,0),R1101))","v":31.09},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1101,'Updated Quanities'!F:I,7,0),R1101)=\"\",R1101,IFERROR(VLOOKUP('AUP Library'!A1101,'Updated Quanities'!F:I,7,0),R1101))","v":31.09},31.09,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1101,'Updated Quanities'!F:G,4,0),R1101)","v":31.09}]
["709-05.09","Machined Rip-Rap (Class C)","TON",33.590000000000003,33.590000000000003,33.590000000000003,33.590000000000003,33.590000000000003,33.590000000000003,33.590000000000003,33.590000000000003,33.590000000000003,33.590000000000003,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1102,'Updated Quanities'!F:I,4,0),R1102)=\"\",R1102,IFERROR(VLOOKUP('AUP Library'!A1102,'Updated Quanities'!F:I,4,0),R1102))","v":33.590000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1102,'Updated Quanities'!F:I,5,0),R1102)=\"\",R1102,IFERROR(VLOOKUP('AUP Library'!A1102,'Updated Quanities'!F:I,5,0),R1102))","v":33.590000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1102,'Updated Quanities'!F:I,6,0),R1102)=\"\",R1102,IFERROR(VLOOKUP('AUP Library'!A1102,'Updated Quanities'!F:I,6,0),R1102))","v":33.590000000000003},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1102,'Updated Quanities'!F:I,7,0),R1102)=\"\",R1102,IFERROR(VLOOKUP('AUP Library'!A1102,'Updated Quanities'!F:I,7,0),R1102))","v":33.590000000000003},33.590000000000003,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1102,'Updated Quanities'!F:G,4,0),R1102)","v":33.590000000000003}]
["709-05.10","Machined Rip-Rap","CY",129.58000000000001,129.58000000000001,129.58000000000001,129.58000000000001,129.58000000000001,129.58000000000001,129.58000000000001,129.58000000000001,129.58000000000001,129.58000000000001,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1103,'Updated Quanities'!F:I,4,0),R1103)=\"\",R1103,IFERROR(VLOOKUP('AUP Library'!A1103,'Updated Quanities'!F:I,4,0),R1103))","v":129.58000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1103,'Updated Quanities'!F:I,5,0),R1103)=\"\",R1103,IFERROR(VLOOKUP('AUP Library'!A1103,'Updated Quanities'!F:I,5,0),R1103))","v":129.58000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1103,'Updated Quanities'!F:I,6,0),R1103)=\"\",R1103,IFERROR(VLOOKUP('AUP Library'!A1103,'Updated Quanities'!F:I,6,0),R1103))","v":129.58000000000001},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1103,'Updated Quanities'!F:I,7,0),R1103)=\"\",R1103,IFERROR(VLOOKUP('AUP Library'!A1103,'Updated Quanities'!F:I,7,0),R1103))","v":129.58000000000001},129.58000000000001,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1103,'Updated Quanities'!F:G,4,0),R1103)","v":129.58000000000001}]
["709-05.12","Machined Rip-Rap","TON",40,40,40,40,40,40,40,40,40,40,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1104,'Updated Quanities'!F:I,4,0),R1104)=\"\",R1104,IFERROR(VLOOKUP('AUP Library'!A1104,'Updated Quanities'!F:I,4,0),R1104))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1104,'Updated Quanities'!F:I,5,0),R1104)=\"\",R1104,IFERROR(VLOOKUP('AUP Library'!A1104,'Updated Quanities'!F:I,5,0),R1104))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1104,'Updated Quanities'!F:I,6,0),R1104)=\"\",R1104,IFERROR(VLOOKUP('AUP Library'!A1104,'Updated Quanities'!F:I,6,0),R1104))","v":40},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1104,'Updated Quanities'!F:I,7,0),R1104)=\"\",R1104,IFERROR(VLOOKUP('AUP Library'!A1104,'Updated Quanities'!F:I,7,0),R1104))","v":40},40,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1104,'Updated Quanities'!F:G,4,0),R1104)","v":40}]
["709-05.81","Rock Riffles","LS",4449.66,4449.66,4449.66,4449.66,4449.66,4449.66,4449.66,4449.66,4449.66,4449.66,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1105,'Updated Quanities'!F:I,4,0),R1105)=\"\",R1105,IFERROR(VLOOKUP('AUP Library'!A1105,'Updated Quanities'!F:I,4,0),R1105))","v":4449.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1105,'Updated Quanities'!F:I,5,0),R1105)=\"\",R1105,IFERROR(VLOOKUP('AUP Library'!A1105,'Updated Quanities'!F:I,5,0),R1105))","v":4449.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1105,'Updated Quanities'!F:I,6,0),R1105)=\"\",R1105,IFERROR(VLOOKUP('AUP Library'!A1105,'Updated Quanities'!F:I,6,0),R1105))","v":4449.66},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1105,'Updated Quanities'!F:I,7,0),R1105)=\"\",R1105,IFERROR(VLOOKUP('AUP Library'!A1105,'Updated Quanities'!F:I,7,0),R1105))","v":4449.66},4449.66,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1105,'Updated Quanities'!F:G,4,0),R1105)","v":4449.66}]
["709-05.83","Embedded Riprap","TON",32.32,32.32,32.32,32.32,32.32,32.32,32.32,32.32,32.32,32.32,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1106,'Updated Quanities'!F:I,4,0),R1106)=\"\",R1106,IFERROR(VLOOKUP('AUP Library'!A1106,'Updated Quanities'!F:I,4,0),R1106))","v":32.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1106,'Updated Quanities'!F:I,5,0),R1106)=\"\",R1106,IFERROR(VLOOKUP('AUP Library'!A1106,'Updated Quanities'!F:I,5,0),R1106))","v":32.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1106,'Updated Quanities'!F:I,6,0),R1106)=\"\",R1106,IFERROR(VLOOKUP('AUP Library'!A1106,'Updated Quanities'!F:I,6,0),R1106))","v":32.32},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1106,'Updated Quanities'!F:I,7,0),R1106)=\"\",R1106,IFERROR(VLOOKUP('AUP Library'!A1106,'Updated Quanities'!F:I,7,0),R1106))","v":32.32},32.32,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1106,'Updated Quanities'!F:G,4,0),R1106)","v":32.32}]
["709-10.01","Gabions","CY",136,136,136,136,136,136,136,136,136,136,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1107,'Updated Quanities'!F:I,4,0),R1107)=\"\",R1107,IFERROR(VLOOKUP('AUP Library'!A1107,'Updated Quanities'!F:I,4,0),R1107))","v":136},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1107,'Updated Quanities'!F:I,5,0),R1107)=\"\",R1107,IFERROR(VLOOKUP('AUP Library'!A1107,'Updated Quanities'!F:I,5,0),R1107))","v":136},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1107,'Updated Quanities'!F:I,6,0),R1107)=\"\",R1107,IFERROR(VLOOKUP('AUP Library'!A1107,'Updated Quanities'!F:I,6,0),R1107))","v":136},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1107,'Updated Quanities'!F:I,7,0),R1107)=\"\",R1107,IFERROR(VLOOKUP('AUP Library'!A1107,'Updated Quanities'!F:I,7,0),R1107))","v":136},136,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1107,'Updated Quanities'!F:G,4,0),R1107)","v":136}]
["709-10.02","Gabions","CY",170,170,170,170,170,170,170,170,170,170,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1108,'Updated Quanities'!F:I,4,0),R1108)=\"\",R1108,IFERROR(VLOOKUP('AUP Library'!A1108,'Updated Quanities'!F:I,4,0),R1108))","v":170},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1108,'Updated Quanities'!F:I,5,0),R1108)=\"\",R1108,IFERROR(VLOOKUP('AUP Library'!A1108,'Updated Quanities'!F:I,5,0),R1108))","v":170},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1108,'Updated Quanities'!F:I,6,0),R1108)=\"\",R1108,IFERROR(VLOOKUP('AUP Library'!A1108,'Updated Quanities'!F:I,6,0),R1108))","v":170},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1108,'Updated Quanities'!F:I,7,0),R1108)=\"\",R1108,IFERROR(VLOOKUP('AUP Library'!A1108,'Updated Quanities'!F:I,7,0),R1108))","v":170},170,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1108,'Updated Quanities'!F:G,4,0),R1108)","v":170}]
[]
[]
["Clearing and Grubing"]
["201-01","Clearing and Grubbing","LS",60931.51,60931.51,60931.51,60931.51,60931.51,60931.51,60931.51,60931.51,60931.51,60931.51,{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1112,'Updated Quanities'!F:I,4,0),R1112)=\"\",R1112,IFERROR(VLOOKUP('AUP Library'!A1112,'Updated Quanities'!F:I,4,0),R1112))","v":60931.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1112,'Updated Quanities'!F:I,5,0),R1112)=\"\",R1112,IFERROR(VLOOKUP('AUP Library'!A1112,'Updated Quanities'!F:I,5,0),R1112))","v":60931.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1112,'Updated Quanities'!F:I,6,0),R1112)=\"\",R1112,IFERROR(VLOOKUP('AUP Library'!A1112,'Updated Quanities'!F:I,6,0),R1112))","v":60931.51},{"$f":"IF(IFERROR(VLOOKUP('AUP Library'!A1112,'Updated Quanities'!F:I,7,0),R1112)=\"\",R1112,IFERROR(VLOOKUP('AUP Library'!A1112,'Updated Quanities'!F:I,7,0),R1112))","v":60931.51},60931.51,{"$f":"IFERROR(VLOOKUP('AUP Library'!A1112,'Updated Quanities'!F:G,4,0),R1112)","v":60931.51}]
[]
[]
["Railroad At-Grade Crossing"]
["720-03-01","Railroad Crossing Signal System","LS"]
[]
[]
["Utilties"]
["N/A","Power","LF"]
["N/A","Communication","LF"]
["N/A","Gas","LF"]
["N/A","Water","LF"]
["N/A","Sewer","LF"]
["N/A","Miscellaneous","LS"]
[]
[]
["Right-of-Way"]
["N/A","Right-of-Way","LS"]

{"sheet":"Sheet1","index":10,"n_rows":14,"n_cols":7,"rows_kept":14,"cut":false,"hidden":true,"merged":[[2,1,2,6]]}
[]
[]
[null,"Full Depth Table"]
[null,"Item","Local (sqft)","SIA (sqft)","Collector (sqft)","Arterial (sqft)","Freeway (sqft)"]
[null,"D mix"]
[null,"Tack"]
[null,"BM2"]
[null,"Tack"]
[null,"A mix"]
[null,"Tack"]
[null,"A-S mix"]
[null,"Prime Coat (TON)"]
[null,"Agg. Cover (TON)"]
[null,"Stone (Road)"]

{"sheet":"Sign Quantities","index":11,"n_rows":146,"n_cols":63,"rows_kept":146,"cut":false,"hidden":true,"merged":[[127,2,127,9],[128,2,128,9],[124,2,124,9],[125,2,125,9],[126,2,126,9]]}
["Sign Image","Sign Code","Description","No.","Length (in)","Width (in)","Size (Sqft)","QTY 0.080\"","QTY 0.100\"","Post Type","Post Type Manual",1,{"$f":"L1+1","v":2},{"$f":"M1+1","v":3},4,5,6,7,8,9,{"$f":"T1+1","v":10},11,12,13,{"$f":"X1+1","v":14},15,16,17,{"$f":"AB1+1","v":18},19,{"$f":"AD1+1","v":20},21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,null,"Plaque"]
["WARNING SIGNS"]
[null,"W1-1","Sharp Curve Horizontal Alignment",null,30,30,{"$f":"E3*F3/144","v":6.25}]
[null,"W1-1aL","Combination Horizontal Alignment/Advisory Speed",null,36,36,{"$f":"E4*F4/144","v":9}]
[null,"W1-2L","Normal Curve Horizontal Alignment",null,30,30,6.25]
[null,"W1-2aL","Combination Horizontal Alignment/Advisory Speed",null,30,30,6.25]
[null,"W1-3L","Sharp Reverse Curve",null,30,30,6.25]
[null,"W1-4L","Normal Reverse Curve",null,30,30,6.25]
[null,"W1-5L","Winding Road",null,30,30,{"$f":"E9*F9/144","v":6.25}]
[null,"W1-6L","One-Direction Large Arrow",null,48,24,8]
[null,"W1-7","Two Direction Large Arrow",null,48,24,8]
[null,"W1-8","Chevron Alignment",null,18,24,3]
[null,"W1-10","Combination Horizontal Alignment/Intersection",null,36,36,9]
[null,"W1-10a","a: Combination Horizontal Alignment/Intersection",null,36,36,9]
[null,"W1-10b","b: Combination Horizontal Alignment/Intersection",null,36,36,9]
[null,"W1-10c","c: Combination Horizontal Alignment/Intersection",null,36,36,9]
[null,"W1-10d","d: Combination Horizontal Alignment/Intersection",null,36,36,9]
[null,"W1-10e","e: Combination Horizontal Alignment/Intersection",null,36,36,9]
[null,"W1-11","Harpin Curve",null,30,30,6.25]
[null,"W1-13","Truck Rollover",null,36,36,9]
[null,"W1-15","270-degree Loop",null,30,30,6.25]
[null,"W13-1P","Advisory Speed Plaque",null,18,18,2.25]
[null,"OM-3","Object Marker",null,6,24,1]
[null,"W2-1","Cross Road",null,30,30,6.25]
[null,"W2-2","Side Road",null,30,30,6.25]
[null,"W2-3","Skewed Side Road",null,30,30,6.25]
[null,"W2-4","T-Intersection ",null,30,30,6.25]
[null,"W2-5","Y-Intersection",null,30,30,6.25]
[null,"W2-6","Circular Intersection",null,30,30,6.25]
[null,"W2-7","Offset Side Road",null,30,30,6.25]
[null,"W2-8","Double Side Road",null,30,30,6.25]
[null,"W3-1","Stop Ahead",null,30,30,6.25]
[null,"W3-2","Yield Ahead",null,30,30,6.25]
[null,"W3-3","Traffic Signal Ahead",null,30,30,6.25]
[null,"W3-4","Be Prepared to Stop",null,36,36,9]
[null,"W3-5","Reduced Speed Limit Ahead",null,36,36,9]
[null,"W3-5a","XX MPH Speed Zone Ahead",null,36,36,9]
[null,"W4-4P","Cross Traffic Does Not Stop",null,24,12,2]
[null,"W5-1","Road Narrows",null,36,36,9]
[null,"W5-2","Narrow Bridge",null,36,36,9]
[null,"W5-3","One Lane Bridge",null,36,36,9]
[null,"W6-1","Divided Highway",null,36,36,9]
[null,"W6-2","Divided Highway Ends",null,36,36,9]
[null,"W6-3","Two-Way Traffic",null,36,36,9]
[null,"W7-1","Hill",null,30,30,6.25]
[null,"W7-1a","Hill with Grade",null,30,30,6.25]
[null,"W7-3P","XX% Grade"]
[null,"W7-3aP","Next XX Miles"]
[null,"W7-6","Hill Blocks View",null,30,30,6.25]
[null,"W8-1","Bump",null,30,30,6.25]
[null,"W8-2","Dip",null,30,30,6.25]
[null,"W8-5","Slipper When Wet",null,30,30,6.25]
[null,"W8-6","Truck Crossing",null,36,36,9]
[null,"W8-14","Fallen Rocks",null,30,30,6.25]
[null,"W8-22","Fog Area",null,36,36,9]
[null,"W9-1","Right (Left) Lane Ends"]
[null,"W9-2","Lane Ends Merge Left (Right)"]
[null,"W11-1","Bicycle",null,30,30,6.25]
[null,"W11-2","Pedestrian",null,30,30,6.25]
[null,"W11-3","Deer",null,30,30,6.25]
[null,"W11-4","Cow",null,30,30,6.25]
[null,"W11-5","Farm Vehicle",null,30,30,6.25]
[null,"W11-7","Equestrian",null,30,30,6.25]
[null,"W11-8","Emergency Vehicle",null,30,30,6.25]
[null,"W11-9","Handicapped",null,30,30,6.25]
[null,"W11-10","Truck",null,30,30,6.25]
[null,"W11-11","Golf Cart",null,30,30,6.25]
[null,"W11-14","Horse-Drawn Vehicle",null,30,30,6.25]
[null,"W12-2","Low Clearance (with arrows)",null,36,36,9]
[null,"W12-2a","Low Clearance",null,78,24,13]
[null,"W14-1, 2","Dead End, No Outlet ",null,30,30,6.25]
["REGULATORY SIGNS"]
[null,"R1-1","Stop",{"$f":"SUM(L73:BI73)","v":0},30,30,{"$f":"E73*F73/144","v":6.25}]
[null,"R1-2","Yield"]
[null,"R1-2aP","To Oncoming Traffic"]
[null,"R1-3P","All Way"]
[null,"R1-5","Yield Here to Peds"]
[null,"R1-5a","Yield Here to Peds"]
[null,"R1-5b","Stop Here for Peds"]
[null,"R1-5c","Stop Here for Peds"]
[null,"R2-1","Speed Limit"]
[null,"R2-2P","Truck Speed Limit"]
[null,"R3-1","No Right Turn"]
[null,"R3-3","No Left Turn"]
[null,"R3-4","No U-Turn"]
[null,"R3-5","Turn Only"]
[null,"R3-5a","Straight Through Only"]
[null,"R3-6","Intersection Lane Control"]
[null,"R3-7","Left (Right) Lane Must Turn Left (Right)"]
[null,"R3-8","Advance Intersection Lane Control"]
[null,"R3-8a","Advance Intersection Lane Control"]
[null,"R3-8b","Advance Intersection Lane Control"]
[null,"R3-9a","Two-Way Left Turn Only (Overhead)"]
[null,"R3-9b","Two-Way Left Turn Only (Post Mounted)"]
[null,"R3-9cP","Begin"]
[null,"R3-9dP","End"]
[null,"R3-20L","Begin Left Turn Lane"]
[null,"R3-20R","Begin Right Turn Lane"]
[null,"R3-27","No Straight Through"]
[null,"R4-1","Do Not Pass"]
[null,"R4-7","Keep Right"]
[null,"R4-7a","Keep Right"]
[null,"R4-7b","Keep Right"]
[null,"R4-8","Keep Left"]
[null,"R4-8a","Keep Left"]
[null,"R4-8b","Keep Left"]
[null,"R5-1","Do Not Enter"]
[null,"R5-1a","Wrong Way"]
[null,"R5-2","No Trucks"]
[null,"R5-6","No Bicycles"]
[null,"R6-1","One Way"]
[null,"R6-2","One Way"]
[null,"R6-3","Divided Highway Crossing"]
[null,"R6-3a","Divided Highway Crossing"]
[null,"R6-4","Roundabout Directional Arrow"]
[null,"R6-4a","Roundabout Directional Arrow"]
[null,"R6-4b","Roundabout Directional Arrow"]
[null,"R6-5P","Roundabout Circulation"]
[null,"R6-6","Begin One Way"]
[null,"R6-7","End One Way"]
[null,"R8-3","No Parking"]
[]
[]
[]
[null,null,"FOOTNOTES:"]
[null,1,"All P5 mounted signs require a multidirectional slip base breakaway sign support."]
[null,2,"Mount on two (2) sign supports."]
[null,3,"An adjustable mounting bracket allowing for dual panel/single post mount shall be used."]
[null,4,"Mount on support with other signs."]
[]
[null,null,null,null,"Unit Post Weight (LBS/FT)"]
[null,null,null,"P1"]
[null,null,null,"P2"]
[null,null,null,"P3"]
[null,null,null,"P4"]
[null,null,null,"P5"]
[null,null,null,"P6"]
[null,null,null,"P7"]
[null,null,null,"P8"]
[null,null,null,"U1"]
[null,null,null,"U2"]
[null,null,null,"U3"]
[null,null,null,"U4"]
[null,null,null,"U5"]
[null,null,null,"U6"]
[null,null,null,"U7"]

{"sheet":"Sign Schedule","index":12,"n_rows":68,"n_cols":9,"rows_kept":68,"cut":false,"hidden":true,"merged":[[1,1,1,8]]}
[]
[null,"SIGN SCHEDULE"]
[null,"DESCRIPTION","NO.","SIGN ID","SQFT/SIGN","QTY 0.080\" (S.F.)","QTY 0.100\" (S.F.)","POST TYPE","FOOTNOTE"]
[null,"Sharp Curve Horizontal Alignment",{"$f":"'Sign Quantities'!D3","v":0},"W1-1",{"$f":"'Sign Quantities'!G3","v":6.25},{"$f":"IF(E4<=5,E4*C4,\"\")","v":""},{"$f":"IF(E4>=5,E4*C4,\"\")","v":0}]
[null,"Combination Horizontal Alignment/Advisory Speed",{"$f":"'Sign Quantities'!D4","v":0},"W1-1aL",{"$f":"'Sign Quantities'!G4","v":9},{"$f":"IF(E5<=5,E5*C5,\"\")","v":""},{"$f":"IF(E5>=5,E5*C5,\"\")","v":0}]
[null,"Normal Curve Horizontal Alignment",{"$f":"'Sign Quantities'!D5","v":0},"W1-2L",{"$f":"'Sign Quantities'!G5","v":6.25},"",0]
[null,"Combination Horizontal Alignment/Advisory Speed",{"$f":"'Sign Quantities'!D6","v":0},"W1-2aL",{"$f":"'Sign Quantities'!G6","v":6.25},"",0]
[null,"Sharp Reverse Curve",{"$f":"'Sign Quantities'!D7","v":0},"W1-3L",{"$f":"'Sign Quantities'!G7","v":6.25},"",0]
[null,"Normal Reverse Curve",{"$f":"'Sign Quantities'!D8","v":0},"W1-4L",{"$f":"'Sign Quantities'!G8","v":6.25},"",0]
[null,"Winding Road",{"$f":"'Sign Quantities'!D9","v":0},"W1-5L",{"$f":"'Sign Quantities'!G9","v":6.25},"",0]
[null,"One-Direction Large Arrow",{"$f":"'Sign Quantities'!D10","v":0},"W1-6L",{"$f":"'Sign Quantities'!G10","v":8},"",0]
[null,"Two Direction Large Arrow",{"$f":"'Sign Quantities'!D11","v":0},"W1-7",{"$f":"'Sign Quantities'!G11","v":8},"",0]
[null,"Chevron Alignment",{"$f":"'Sign Quantities'!D12","v":0},"W1-8",{"$f":"'Sign Quantities'!G12","v":3},0,""]
[null,"Combination Horizontal Alignment/Intersection",{"$f":"'Sign Quantities'!D13","v":0},"W1-10L",{"$f":"'Sign Quantities'!G13","v":9},"",0]
[null,"a: Combination Horizontal Alignment/Intersection",{"$f":"'Sign Quantities'!D14","v":0},"W1-10aL",{"$f":"'Sign Quantities'!G14","v":9},"",0]
[null,"b: Combination Horizontal Alignment/Intersection",{"$f":"'Sign Quantities'!D15","v":0},"W1-10bL",{"$f":"'Sign Quantities'!G15","v":9},"",0]
[null,"c: Combination Horizontal Alignment/Intersection",{"$f":"'Sign Quantities'!D16","v":0},"W1-10cL",{"$f":"'Sign Quantities'!G16","v":9},"",0]
[null,"d: Combination Horizontal Alignment/Intersection",{"$f":"'Sign Quantities'!D17","v":0},"W1-10dL",{"$f":"'Sign Quantities'!G17","v":9},"",0]
[null,"e: Combination Horizontal Alignment/Intersection",{"$f":"'Sign Quantities'!D18","v":0},"W1-10eL",{"$f":"'Sign Quantities'!G18","v":9},"",0]
[null,"Harpin Curve",{"$f":"'Sign Quantities'!D19","v":0},"W1-11",{"$f":"'Sign Quantities'!G19","v":6.25},"",0]
[null,"Truck Rollover",{"$f":"'Sign Quantities'!D20","v":0},"W1-13",{"$f":"'Sign Quantities'!G20","v":9},"",0]
[null,"270-degree Loop",{"$f":"'Sign Quantities'!D21","v":0},"W1-15",{"$f":"'Sign Quantities'!G21","v":6.25},"",0]
[null,"Advisory Speed Plaque",{"$f":"'Sign Quantities'!D22","v":0},"W13-1P",{"$f":"'Sign Quantities'!G22","v":2.25},0,""]
[null,"Object Marker",{"$f":"'Sign Quantities'!D23","v":0},"OM-3",{"$f":"'Sign Quantities'!G23","v":1},0,""]
[null,"Cross Road",{"$f":"'Sign Quantities'!D24","v":0},"W2-1",{"$f":"'Sign Quantities'!G24","v":6.25},"",0]
[null,"Side Road",{"$f":"'Sign Quantities'!D25","v":0},"W2-2",{"$f":"'Sign Quantities'!G25","v":6.25},"",0]
[null,"Skewed Side Road",{"$f":"'Sign Quantities'!D26","v":0},"W2-3",{"$f":"'Sign Quantities'!G26","v":6.25},"",0]
[null,"T-Intersection ",{"$f":"'Sign Quantities'!D27","v":0},"W2-4",{"$f":"'Sign Quantities'!G27","v":6.25},"",0]
[null,"Y-Intersection",{"$f":"'Sign Quantities'!D28","v":0},"W2-5",{"$f":"'Sign Quantities'!G28","v":6.25},"",0]
[null,"Circular Intersection",{"$f":"'Sign Quantities'!D29","v":0},"W2-6",{"$f":"'Sign Quantities'!G29","v":6.25},"",0]
[null,"Offset Side Road",{"$f":"'Sign Quantities'!D30","v":0},"W2-7",{"$f":"'Sign Quantities'!G30","v":6.25},"",0]
[null,"Double Side Road",{"$f":"'Sign Quantities'!D31","v":0},"W2-8",{"$f":"'Sign Quantities'!G31","v":6.25},"",0]
[null,"Stop Ahead",{"$f":"'Sign Quantities'!D32","v":0},"W3-1",{"$f":"'Sign Quantities'!G32","v":6.25},"",0]
[null,"Yield Ahead",{"$f":"'Sign Quantities'!D33","v":0},"W3-2",{"$f":"'Sign Quantities'!G33","v":6.25},"",0]
[null,"Traffic Signal Ahead",{"$f":"'Sign Quantities'!D34","v":0},"W3-3",{"$f":"'Sign Quantities'!G34","v":6.25},"",0]
[null,"Be Prepared to Stop",{"$f":"'Sign Quantities'!D35","v":0},"W3-4",{"$f":"'Sign Quantities'!G35","v":9},"",0]
[null,"Reduced Speed Limit Ahead",{"$f":"'Sign Quantities'!D36","v":0},"W3-5",{"$f":"'Sign Quantities'!G36","v":9},"",0]
[null,"XX MPH Speed Zone Ahead",{"$f":"'Sign Quantities'!D37","v":0},"W3-5a",{"$f":"'Sign Quantities'!G37","v":9},"",0]
[null,"Cross Traffic Does Not Stop",{"$f":"'Sign Quantities'!D38","v":0},"W4-4P",{"$f":"'Sign Quantities'!G38","v":2},0,""]
[null,"Road Narrows",{"$f":"'Sign Quantities'!D39","v":0},"W5-1",{"$f":"'Sign Quantities'!G39","v":9},"",0]
[null,"Narrow Bridge",{"$f":"'Sign Quantities'!D40","v":0},"W5-2",{"$f":"'Sign Quantities'!G40","v":9},"",0]
[null,"One Lane Bridge",{"$f":"'Sign Quantities'!D41","v":0},"W5-3",{"$f":"'Sign Quantities'!G41","v":9},"",0]
[null,"Divided Highway",{"$f":"'Sign Quantities'!D42","v":0},"W6-1",{"$f":"'Sign Quantities'!G42","v":9},"",0]
[null,"Divided Highway Ends",{"$f":"'Sign Quantities'!D43","v":0},"W6-2",{"$f":"'Sign Quantities'!G43","v":9},"",0]
[null,"Two-Way Traffic",{"$f":"'Sign Quantities'!D44","v":0},"W6-3",{"$f":"'Sign Quantities'!G44","v":9},"",0]
[null,"Hill",{"$f":"'Sign Quantities'!D45","v":0},"W7-1",{"$f":"'Sign Quantities'!G45","v":6.25},"",0]
[null,"Hill with Grade",{"$f":"'Sign Quantities'!D46","v":0},"W7-1a",{"$f":"'Sign Quantities'!G46","v":6.25},"",0]
[null,"Hill Blocks View",{"$f":"'Sign Quantities'!D49","v":0},"W7-6",{"$f":"'Sign Quantities'!G49","v":6.25},"",0]
[null,"Bump",{"$f":"'Sign Quantities'!D50","v":0},"W8-1",{"$f":"'Sign Quantities'!G50","v":6.25},"",0]
[null,"Dip",{"$f":"'Sign Quantities'!D51","v":0},"W8-2",{"$f":"'Sign Quantities'!G51","v":6.25},"",0]
[null,"Slipper When Wet",{"$f":"'Sign Quantities'!D52","v":0},"W8-5",{"$f":"'Sign Quantities'!G52","v":6.25},"",0]
[null,"Truck Crossing",{"$f":"'Sign Quantities'!D53","v":0},"W8-6",{"$f":"'Sign Quantities'!G53","v":9},"",0]
[null,"Fallen Rocks",{"$f":"'Sign Quantities'!D54","v":0},"W8-14",{"$f":"'Sign Quantities'!G54","v":6.25},"",0]
[null,"Fog Area",{"$f":"'Sign Quantities'!D55","v":0},"W8-22",{"$f":"'Sign Quantities'!G55","v":9},"",0]
[null,"Bicycle",{"$f":"'Sign Quantities'!D58","v":0},"W11-1",{"$f":"'Sign Quantities'!G58","v":6.25},"",0]
[null,"Pedestrian",{"$f":"'Sign Quantities'!D59","v":0},"W11-2",{"$f":"'Sign Quantities'!G59","v":6.25},"",0]
[null,"Deer",{"$f":"'Sign Quantities'!D60","v":0},"W11-3",{"$f":"'Sign Quantities'!G60","v":6.25},"",0]
[null,"Cow",{"$f":"'Sign Quantities'!D61","v":0},"W11-4",{"$f":"'Sign Quantities'!G61","v":6.25},"",0]
[null,"Farm Vehicle",{"$f":"'Sign Quantities'!D62","v":0},"W11-5",{"$f":"'Sign Quantities'!G62","v":6.25},"",0]
[null,"Equestrian",{"$f":"'Sign Quantities'!D63","v":0},"W11-7",{"$f":"'Sign Quantities'!G63","v":6.25},"",0]
[null,"Emergency Vehicle",{"$f":"'Sign Quantities'!D64","v":0},"W11-8",{"$f":"'Sign Quantities'!G64","v":6.25},"",0]
[null,"Handicapped",{"$f":"'Sign Quantities'!D65","v":0},"W11-9",{"$f":"'Sign Quantities'!G65","v":6.25},"",0]
[null,"Truck",{"$f":"'Sign Quantities'!D66","v":0},"W11-10",{"$f":"'Sign Quantities'!G66","v":6.25},"",0]
[null,"Golf Cart",{"$f":"'Sign Quantities'!D67","v":0},"W11-11",{"$f":"'Sign Quantities'!G67","v":6.25},"",0]
[null,"Horse-Drawn Vehicle",{"$f":"'Sign Quantities'!D68","v":0},"W11-14",{"$f":"'Sign Quantities'!G68","v":6.25},"",0]
[null,"Low Clearance (with arrows)",{"$f":"'Sign Quantities'!D69","v":0},"W12-2",{"$f":"'Sign Quantities'!G69","v":9},"",0]
[null,"Low Clearance",{"$f":"'Sign Quantities'!D70","v":0},"W12-2a",{"$f":"'Sign Quantities'!G70","v":13},"",0]
[null,"Dead End, No Outlet ",{"$f":"'Sign Quantities'!D71","v":0},"W14-1, 2",{"$f":"'Sign Quantities'!G71","v":6.25},"",0]

{"sheet":"Updated Quanities","index":13,"n_rows":3625,"n_cols":20,"rows_kept":3625,"cut":false,"hidden":true,"merged":[]}
[]
[null,null,null,null,"Equation Applies","Item No","Total Data Set Count","AUP_2018",null,"Tool Quantities","Description","Count","Average",null,"Item #","Description","Total Cost","Overall Contribution","Count","Weighted Average"]
[null,null,null,null,null,"105-01",108,null,null,"203-01","Road & Drainage Excavation (Unclassified)",105,6.3250695162361339,null,"000-01.12","TRAFFIC CONTROL SYSTEMS",1046.76,6.2291315973017404E-7,2,523.38]
[null,null,null,null,null,"109-10.01",56,null,null,"203-03","Borrow Excavation (Unclassified)",47,5.0301933835939945,null,"105-01","CONSTRUCTION STAKES, LINES AND GRADES",15147065.940000001,9.0138204605895323E-3,106,142896.84849056604]
[null,null,null,null,null,"201-01",110,null,null,"303-01","Mineral Aggregate, Type A Base, Grading D",107,18.880689461305796,null,"105M01","CONSTRUCTION STAKES, LINES AND GRADES",300000,1.7852606893562249E-4,1,300000]
[null,null,null,null,null,"202-01",35,null,null,"307-02.01","Asphalt Concrete Mix (PG70-22) (BPMB-HM) Grading A",58,65.573574233564429,null,"106-04.01","SMPLNG & TSTNG OF POTENTIALLY ACIDIC MAT.",473800,2.8195217153899316E-4,1,118.45]
[null,null,null,null,null,"202-01.56",9,null,null,"307-02.02","Asphalt Cement (PG70-22)(BPMB-HM) Grading A-S",39,664.95169658662985,null,"109-10.01","TRAINEE",180136,1.0719657317929099E-4,72,0.8]
[null,null,null,null,null,"202-02.01",25,null,null,"307-02.03","Aggregate (BPMB-HM) Grading A-S Mix",39,49.95209773913129,null,"109M10.01","TRAINEE",5312,3.1611015939534223E-6,1,0.8]
[null,null,null,null,null,"202-02.02",13,null,null,"307-02.08","Asphalt Concrete Mix (PG70-22) (BPMB-HM) Grading B-M2",59,72.932729904781397,null,"201-01","CLEARING AND GRUBBING",33200215.27,1.9757013066565091E-2,100,332002.15269999998]
[null,null,null,null,null,"202-02.03",11,null,null,"402-01","Bituminous Material For Prime Coat (PC)",107,570.81430731675027,null,"201-07.01","REMOVAL AND DISPOSAL OF BRUSH & TREES",24910,1.4823614590621188E-5,2,12455]
[null,null,null,null,null,"202-02.04",10,null,null,"402-02","Aggregate For Cover Material (PC)",95,31.411894758440059,null,"201M01","CLEARING AND GRUBBING",1435000,8.5394969640872767E-4,1,1435000]
[null,null,null,null,null,"202-02.05",8,null,null,"403-01","Bituminous Material For Tack Coat (TC)",108,657.79942929082995,null,"202-01","REMOVAL OF STRUCTURES AND OBSTRUCTIONS",1154164.46,6.8682814649668501E-4,44,26231.010454545452]
[null,null,null,null,null,"202-02.07",8,null,null,"411-01.07","ACS (PG64-22) GR \"E\"",74,88.647251228833838,null,"202-01.01","REMOVAL OF STRUCTURES AND OBSTRUCTIONS",3712.4,2.2092005943886833E-6,1,3712.4]
[null,null,null,null,null,"202-03",22,null,null,"411-02.10","ACS Mix(PG70-22) Grading D",59,90.7573192312543,null,"202-01.02","REMOVAL OF ASBESTOS",249163.6,1.4827399343282624E-4,7,35594.800000000003]
[null,null,null,null,null,"202-03.01",80,null,null,"313-03","Treated Permeable Base",25,17.317026716415324,null,"202-01.03","REMOVAL OF TRASH AND DEBRIS",3500,2.0828041375822626E-6,1,3500]
[null,null,null,null,null,"202-04.01",19,null,null,"501-01.03","Portland Cement Concrete 10\"",23,68.957283131915815,null,"202-01.05","REMOVAL OF ASBESTOS (#)",27775.5,1.6528836092404608E-5,3,9258.5]
[null,null,null,null,null,"202-04.50",9,null,null,"415-01.02","Cold Planning Bituminous Pavement",50,2.4192375238742168,null,"202-01.06","REMOVAL OF ASBESTOS (BRIDGE NO. 2)",16488,9.8117927487018119E-6,2,8244]
[null,null,null,null,null,"202-06.01",23,null,null,"202-03.01","Asphalt Removal (SY)",17,4.6569298895731031,null,"202-01.07","REMOVAL OF ASBESTOS (BRIDGE NO. 3)",16488,9.8117927487018119E-6,2,8244]
[null,null,null,null,null,"202-06.02",14,null,null,"202-03.02","Concrete Removal (CY)",1,14.81,null,"202-01.08","REMOVAL OF ASBESTOS (SEE PLANS)",48708,2.8985492552387668E-5,2,24354]
[null,null,null,null,null,"202-06.03",11,null,null,"502-04.01","Sawing Concrete Pvmt",5,4.9125933609958503,null,"202-01.09","REMOVAL OF ASBESTOS (BRIDGE NO. 5)",4488,2.6707499912769127E-6,1,4488]
[null,null,null,null,null,"202-06.04",8,null,null,"607-05.02","24\" Concrete Pipe Culvert (Class III)",65,70.507620098291753,null,"202-01.13","REMOVAL OF PIPE (15\", STA. 300+99.95 AT S.B. OFF-RAMP)",11150,6.6352188954406359E-6,3,57.47422680412371]
[null,null,null,null,null,"202-06.05",8,null,null,"611-07.01","Class A Concrete (Pipe Endwalls)",79,704.22780070613715,null,"202-01.50","REMOVAL OF STRUCTURES AND OBSTRUCTIONS",78175,4.6520918130140961E-5,6,1240.8730158730159]
[null,null,null,null,null,"202-08.15",8,null,null,"611-07.02","Steel Bar Reinforcement (Pipe Endwalls)",78,1.4414270453993687,null,"202-01.51","REMOVAL OF STRUCTURES AND OBSTRUCTIONS",20000,1.1901737929041499E-5,1,2000]
[null,null,null,null,null,"203-01",101,null,null,"611-12.02","Catch Basins, Type 12, > 4' - 8' Depth",43,4082.3930414438505,null,"202-01.52","REMOVAL OF STRUCTURES AND OBSTRUCTIONS",4000,2.3803475858082999E-6,1,2000]
[null,null,null,null,null,"203-01.11",13,null,null,"611-14.02","Catch Basins, Type 14, > 4' - 8' Depth",37,6847.8780522565321,null,"202-01.53","REMOVAL OF STRUCTURES AND OBSTRUCTIONS",53000,3.1539605511959974E-5,1,1000]
[null,null,null,null,null,"203-02.01",51,null,null,"611-42.02","Catch Basins, Type 42, > 4' - 8' Depth",34,3988.8950595238102,null,"202-01.56","REMOVAL OF STRUCTURES & OBSTRUCTIONS (PED. BRIDGE)",379907,2.2607767757041846E-4,8,47488.375]
[null,null,null,null,null,"203-02.02",8,null,null,"701-01.01","Concrete Sidewalk (4\")",41,4.6114421551356619,null,"202-01.57","REMOVAL OF STRUCTURES & OBSTRUCTIONS (SEE PLANS)",13250,7.8849013779899934E-6,2,6625]
[null,null,null,null,null,"203-03",40,null,null,"702-03","Concrete Combined Curb & Gutter",52,322.50872870104058,null,"202-02.01","REMOVAL OF PIPE (30\" CMP,STA. 11+47 TO STA. 13+60 LT.)",84833.18,5.0483113802360233E-5,25,22.760443440419404]
[null,null,null,null,null,"203-04",48,null,null,"705-02.02","Single Guardrail (Type 2)",76,16.523559908883264,null,"202-02.02","REMOVAL OF PIPE (24\" RCP,STA. 13+62)",42602,2.53518919626513E-5,17,19.650369003690038]
[null,null,null,null,null,"203-05",27,null,null,"705-04.07","Tan Energy Absg Term (NCHRP, 350, TL3)",58,2178.0697972972976,null,"202-02.03","REMOVAL OF PIPE (24\" RCP, STA. 34+91)",14080.039999999999,8.3788473055210728E-6,16,13.473722488038279]
[null,null,null,null,null,"203-06",158,null,null,"705-04.09","Earth Pad for Type 38 GR End Treatment",12,1135.379012345679,null,"202-02.04","REMOVAL OF PIPE (30\" RCP, STA. 35+71)",11522.98,6.8571744060793313E-6,14,12.383643202579258]
[null,null,null,null,null,"203-07",26,null,null,"705-01.01","Guardrail @ Bridge Ends (LF)",50,66.518388929779505,null,"202-02.05","REMOVAL OF PIPE (24\" RCP 610+90 LT SLR)",11698.2,6.9614455320756641E-6,12,11.804439959636731]
[null,null,null,null,null,"203-15.03",9,null,null,"710-02","Aggregate Underdrains (with pipe)",77,4.9394443611497767,null,"202-02.06","REMOVAL OF PIPE (36\" CMP 137+00 LT RAMP ES)",10117.200000000001,6.0206131487849338E-6,11,11.105598243688256]
[null,null,null,null,null,"204-02.01",20,null,null,"711-05.71","Barrier Wall",12,87.301524283787003,null,"202-02.07","REMOVAL OF PIPE (36\" CMP 137+36 LT RAMP ES)",26283.775000000001,1.5641130091794638E-5,11,13.851791831357049]
[null,null,null,null,null,"204-03.01",8,null,null,"712-01","Traffic Control",105,119825.42580952382,null,"202-02.08","REMOVAL OF PIPE (15\" CMP 136+80 RAMP ES)",9707.9500000000007,5.777073836411922E-6,8,13.596568627450981]
[null,null,null,null,null,"204-04.01",8,null,null,"712-02.02","Interconnected Portable Barrier Rail",97,29.526058859563886,null,"202-02.09","REMOVAL OF PIPE (12\" CMP 130+00 RT RAMP ES)",8753.94,5.2093549863276777E-6,8,16.241076066790352]
[null,null,null,null,null,"204-05",8,null,null,"713-16.20","Signs",33,297.6653439153439,null,"202-02.10","REMOVAL OF PIPE (12\" CMP 132+00 LT RAMP ES)",15918.6,9.4729502698620005E-6,7,17.865993265993268]
[null,null,null,null,null,"204-08",43,null,null,"716-13.06","Spray Thermo P.M. (40 mil 4\")",9,1654.2273950855883,null,"202-02.11","REMOVAL OF PIPE (12\" CMP 133+20 LT RAMP ES)",15315.785,9.1142229623772439E-6,7,17.736867400115809]
[null,null,null,null,null,"204-08.01",33,null,null,"801-01","Seeding (With Mulch)",63,24.462667643496928,null,"202-02.12","REMOVAL OF PIPE (8\" PVC/12\" CMP 36+61 RT S.R. 311)",5545,3.2997568408267557E-6,5,13.26555023923445]
[null,null,null,null,null,"208-01",17,null,null,"801-01.07","Temporary Seeding (With Mulch)",89,18.727230289871308,null,"202-02.13","REMOVAL OF PIPE (30\" RCP 41+00 RT S.R. 311)",5065,3.0141151305297599E-6,5,13.399470899470899]
[null,null,null,null,null,"209-02.03",20,null,null,"801-02","Seeding (Without Mulch)",59,15.049922902876958,null,"202-02.14","REMOVAL OF PIPE (18\" CMP 340+00 RT RAMP WN)",5090,3.0289923029410616E-6,4,24.950980392156861]
[null,null,null,null,null,"209-02.05",32,null,null,null,null,null,null,null,"202-02.15","REMOVAL OF PIPE (48\" RCP 548+82 ESLR)",2426.46,1.4439545507651019E-6,5,9.5907509881422932]
[null,null,null,null,null,"209-02.06",12,null,null,null,null,null,null,null,"202-02.17","REMOVAL OF PIPE (3.75\" X 6' ELLIP. CMP 540+00 RT ESLR)",3611.8199999999997,2.1493467543435332E-6,4,13.838390804597701]
[null,null,null,null,null,"209-02.07",30,null,null,null,null,null,null,null,"202-02.18","REMOVAL OF PIPE (48\" RCP 548+82 ESLR)",3446.4,2.0509074799324315E-6,4,16.029767441860464]
[null,null,null,null,null,"209-05",99,null,null,null,null,null,null,null,"202-02.19","REMOVAL OF PIPE (15\", ELMER LANGFORD RD. - 110+46.06)",2340,1.3925033376978556E-6,3,13.764705882352942]
[null,null,null,null,null,"209-08.02",91,null,null,null,null,null,null,null,"202-02.20","REMOVAL OF PIPE (SIZE ,STA.)",3470,2.0649515306887003E-6,3,15.917431192660551]
[null,null,null,null,null,"209-08.03",100,null,null,null,null,null,null,null,"202-02.21","REMOVAL OF PIPE (12\")",79311.139999999985,4.7197020156676013E-5,7,15.017465529059351]
[null,null,null,null,null,"209-08.07",82,null,null,null,null,null,null,null,"202-02.22","REMOVAL OF PIPE (15\")",20037.100000000002,1.1923815652899874E-5,6,13.600887851101668]
[null,null,null,null,null,"209-08.08",90,null,null,null,null,null,null,null,"202-02.23","REMOVAL OF PIPE (18\")",28419.590000000004,1.6912125611540429E-5,4,15.350904484883843]
[null,null,null,null,null,"209-08.09",8,null,null,null,null,null,null,null,"202-02.24","REMOVAL OF PIPE (24\")",19468.45,1.15854194892324E-5,4,18.252128178204458]
[null,null,null,null,null,"209-09.01",51,null,null,null,null,null,null,null,"202-02.25","REMOVAL OF PIPE (30\")",6454,3.8406908297016923E-6,3,21.877966101694916]
[null,null,null,null,null,"209-09.03",46,null,null,null,null,null,null,null,"202-02.26","REMOVAL OF PIPE (36\")",23039.8,1.3710683076876516E-5,4,30.59734395750332]
[null,null,null,null,null,"209-09.04",17,null,null,null,null,null,null,null,"202-02.27","REMOVAL OF PIPE (40\")",11414.099999999999,6.792381344793628E-6,3,35.012576687116557]
[null,null,null,null,null,"209-09.22",13,null,null,null,null,null,null,null,"202-02.28","REMOVAL OF PIPE (64\")",5222,3.1075437732727355E-6,2,62.915662650602407]
[null,null,null,null,null,"209-09.41",16,null,null,null,null,null,null,null,"202-02.29","REMOVAL OF PIPE (15\", TOWER HILL RD. 2 - 170+45.04)",2459.4,1.4635567131342334E-6,2,25.354639175257734]
[null,null,null,null,null,"209-09.43",24,null,null,null,null,null,null,null,"202-02.30","REMOVAL OF PIPE (24\", SR-52 - 680+38.19)",1800,1.0711564136137351E-6,1,20]
[null,null,null,null,null,"209-10.20",16,null,null,null,null,null,null,null,"202-02.31","REMOVAL OF PIPE (18\", SR-52 - 699+87.49 )",2060,1.2258790066912745E-6,1,20]
[null,null,null,null,null,"209-20.03",44,null,null,null,null,null,null,null,"202-03","REMOVAL OF RIGID PAVEMENT, SIDEWALK, ETC.",256758.46,1.5279359509921424E-4,16,8.6412836132332647]
[null,null,null,null,null,"209-40.30",18,null,null,null,null,null,null,null,"202-03.01","REMOVAL OF ASPHALT PAVEMENT",1041293.1464,6.1965990678799219E-4,17,4.6569298895731031]
[null,null,null,null,null,"209-40.33",34,null,null,null,null,null,null,null,"202-03.02","REMOVAL OF RIGID PAVEMENT",86001.67,5.1178466889995521E-5,1,14.81]
[null,null,null,null,null,"209-40.41",28,null,null,null,null,null,null,null,"202-03.03","REMOVAL OF ASPHALT PAVEMENT",433537.19999999995,2.5799230684452252E-4,4,10.94293502953203]
[null,null,null,null,null,"209-40.42",30,null,null,null,null,null,null,null,"202-04.01","REMOVAL OF STRUCTURES (BR. NO. 78-SR66-8.56 LT. & RT.)",4584361.2799999993,2.7280933263302614E-3,34,134834.15529411766]
[null,null,null,null,null,"209-40.43",11,null,null,null,null,null,null,null,"202-04.02","REMOVAL OF STRUCTURES (EXIST. BR. NO. 63I00240026)",1571527.8099999998,9.3519560714102614E-4,15,104768.52066666666]
[null,null,null,null,null,"209-40.44",16,null,null,null,null,null,null,null,"202-04.03","REMOVAL OF STRUCTURES (BRIDGE NO. 65-SR029-0.33)",302297.59999999998,1.7989334058891076E-4,8,37787.199999999997]
[null,null,null,null,null,"209-40.45",8,null,null,null,null,null,null,null,"202-04.04","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",816700,4.8600746833240963E-4,4,204175]
[null,null,null,null,null,"209-40.46",18,null,null,null,null,null,null,null,"202-04.05","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",463200,2.7564425043660116E-4,3,154400]
[null,null,null,null,null,"209-40.47",18,null,null,null,null,null,null,null,"202-04.06","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",21500,1.2794368273719613E-5,3,7166.666666666667]
[null,null,null,null,null,"209-40.48",11,null,null,null,null,null,null,null,"202-04.07","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",2000,1.1901737929041499E-6,1,2000]
[null,null,null,null,null,"209-65.03",34,null,null,null,null,null,null,null,"202-04.08","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",1500,8.9263034467811245E-7,1,1500]
[null,null,null,null,null,"209-65.04",14,null,null,null,null,null,null,null,"202-04.09","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",12200,7.2600601367153146E-6,1,12200]
[null,null,null,null,null,"303-01",321,null,null,null,null,null,null,null,"202-04.10","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",4300,2.5588736547439225E-6,1,4300]
[null,null,null,null,null,"303-01.01",45,null,null,null,null,null,null,null,"202-04.11","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",2000,1.1901737929041499E-6,1,2000]
[null,null,null,null,null,"303-01.02",26,null,null,null,null,null,null,null,"202-04.50","REMOVAL OF STRUCTURES (SLAB BRIDGE, STA. 130+27.05)",285562.99,1.6993479346067493E-4,12,23796.915833333333]
[null,null,null,null,null,"303-01.03",16,null,null,null,null,null,null,null,"202-04.51","REMOVAL OF STRUCTURES (BOX CULVERT STA. 112+03.00)",86513.7,5.148316923358588E-5,8,10814.2125]
[null,null,null,null,null,"303-02",66,null,null,null,null,null,null,null,"202-04.52","REMOVAL OF STRUCTURES (BOX CULVERT SAT. 127+45.21)",39408.14,2.3451267727548874E-5,5,7881.6279999999997]
[null,null,null,null,null,"303-10.01",93,null,null,null,null,null,null,null,"202-04.53","REMOVAL OF STRUCTURES (BOX CULVERT, STA. 161+78.87)",18962.2,1.1284156747903537E-5,4,4740.55]
[null,null,null,null,null,"303-10.03",14,null,null,null,null,null,null,null,"202-04.54","REMOVAL OF STRUCTURES (3'X4' RCBC STA. 501+60 LT.)",326708.14,1.9441973307823002E-4,3,108902.71333333333]
[null,null,null,null,null,"307-01.01",122,null,null,null,null,null,null,null,"202-04.55","REMOVAL OF STRUCTURES (4'X3' RCBC STA. 507+36 LT.)",1600,9.5213903432331998E-7,1,1600]
[null,null,null,null,null,"307-01.02",14,null,null,null,null,null,null,null,"202-04.56","REMOVAL OF STRUCTURES (4'X6' RCBC STA. 521+50)",2000,1.1901737929041499E-6,1,2000]
[null,null,null,null,null,"307-01.03",13,null,null,null,null,null,null,null,"202-04.57","REMOVAL OF STRUCTURES (5'X4' RCBC STA. 538+46 LT.)",1500,8.9263034467811245E-7,1,1500]
[null,null,null,null,null,"307-01.07",10,null,null,null,null,null,null,null,"202-04.58","REMOVAL OF STRUCTURES (2'X2' RCBC STA. 613+46)",1200,7.1410427574249004E-7,1,1200]
[null,null,null,null,null,"307-01.08",181,null,null,null,null,null,null,null,"202-04.59","REMOVAL OF STRUCTURES (5'X8' RCBC STA. 617+74)",6000,3.5705213787124498E-6,1,6000]
[null,null,null,null,null,"307-01.15",58,null,null,null,null,null,null,null,"202-04.60","REMOVAL OF STRUCTURES (5'X4' RCBC STA. 627+43 RT.)",1600,9.5213903432331998E-7,1,1600]
[null,null,null,null,null,"307-02.01",53,null,null,null,null,null,null,null,"202-04.61","REMOVAL OF STRUCTURES (5'X4' RCBC STA. 644+21 RT.)",2000,1.1901737929041499E-6,1,2000]
[null,null,null,null,null,"307-02.02",39,null,null,null,null,null,null,null,"202-04.62","REMOVAL OF STRUCTURES (4'X3' RCBC STA. 693+66)",1200,7.1410427574249004E-7,1,1200]
[null,null,null,null,null,"307-02.03",39,null,null,null,null,null,null,null,"202-04.63","REMOVAL OF STRUCTURES (8'X7' RCBC STA. 719+46)",10000,5.9508689645207496E-6,1,10000]
[null,null,null,null,null,"307-02.08",67,null,null,null,null,null,null,null,"202-06.01","REMOVAL OF BUILDINGS (Tract No. 5)",247389.00999999998,1.4721795817725132E-4,31,7980.2906451612907]
[null,null,null,null,null,"307-03.01",20,null,null,null,null,null,null,null,"202-06.02","REMOVAL OF BUILDINGS (Tract No. 6)",142841.71,8.5003229887807317E-5,21,6801.986190476191]
[null,null,null,null,null,"307-03.02",16,null,null,null,null,null,null,null,"202-06.03","REMOVAL OF BUILDINGS (Tract No. 13)",211591.64,1.2591541236280473E-4,19,11136.402105263158]
[null,null,null,null,null,"307-03.03",16,null,null,null,null,null,null,null,"202-06.04","REMOVAL OF BUILDINGS (Tract No. 14)",45490.119999999995,2.7070574330032463E-5,14,3249.2942857142853]
[null,null,null,null,null,"307-03.08",46,null,null,null,null,null,null,null,"202-06.05","REMOVAL OF BUILDINGS (Tract No. 16)",71622.720000000001,4.2621742160255964E-5,14,5115.9085714285711]
[null,null,null,null,null,"307-03.09",11,null,null,null,null,null,null,null,"202-06.06","REMOVAL OF BUILDINGS (Tract No. 24)",74051.94,4.4067339150855271E-5,10,7405.1940000000004]
[null,null,null,null,null,"307-03.10",19,null,null,null,null,null,null,null,"202-06.07","REMOVAL OF BUILDINGS (TRACT 54B)",25212.71,1.5003753345046195E-5,8,3151.5887499999999]
[null,null,null,null,null,"309-01.01",8,null,null,null,null,null,null,null,"202-06.08","REMOVAL OF BUILDINGS (TRACT 54C)",30046.55,1.7880308188592093E-5,7,4292.3642857142859]
[null,null,null,null,null,"309-01.02",8,null,null,null,null,null,null,null,"202-06.09","REMOVAL OF BUILDINGS (TRACT NO.66)",23900.260000000002,1.4222731547797671E-5,5,4780.0520000000006]
[null,null,null,null,null,"313-03",23,null,null,null,null,null,null,null,"202-06.10","REMOVAL OF BUILDINGS (TRACT NO.74)",31025.26,1.8462725685018703E-5,4,7756.3149999999996]
[null,null,null,null,null,"402-01",112,null,null,null,null,null,null,null,"202-06.11","REMOVAL OF BUILDINGS (TRACT NO.75)",8114.92,4.8290825577568724E-6,1,8114.92]
[null,null,null,null,null,"402-02",94,null,null,null,null,null,null,null,"202-06.12","REMOVAL OF BUILDINGS (TRACT NO.76)",1174.26,6.9878673902781355E-7,1,1174.26]
[null,null,null,null,null,"403-01",453,null,null,null,null,null,null,null,"202-06.13","REMOVAL OF BUILDINGS (TRACT NO.79)",16282.52,9.6895142932188397E-6,3,5427.5066666666671]
[null,null,null,null,null,"403-05.01",33,null,null,null,null,null,null,null,"202-06.14","REMOVAL OF BUILDINGS (TRACT NO.80)",1174.26,6.9878673902781355E-7,1,1174.26]
[null,null,null,null,null,"405-01.01",20,null,null,null,null,null,null,null,"202-08.10","REMOVAL OF CURB (RAMPS I, J, AND K)",83843.02,4.9893882560969258E-5,6,5.121122648424139]
[null,null,null,null,null,"405-01.02",20,null,null,null,null,null,null,null,"202-08.15","REMOVAL OF CURB AND GUTTER (S.B. OFF-RAMP AND LIPSCOMB DR. )",77766.83,4.6278021511616124E-5,10,5.3166630204416494]
[null,null,null,null,null,"407-20.05",24,null,null,null,null,null,null,null,"202-08.28","REMOVAL OF MEDIAN BARRIER (EXISTING I-65 MEDIAN BARRIER)",48324,2.8756979184150074E-5,2,34.71551724137931]
[null,null,null,null,null,"411-01.07",145,null,null,null,null,null,null,null,"202-11","CONSTRUCTION & REMOVAL OF TEMPORARY STRUCTURES",1540000,9.1643382053619555E-4,1,1540000]
[null,null,null,null,null,"411-01.10",187,null,null,null,null,null,null,null,"202-12","CONSTRUCTION & REMOVAL OF TEMPORARY RUNAROUND",20000,1.1901737929041499E-5,1,20000]
[null,null,null,null,null,"411-02.10",171,null,null,null,null,null,null,null,"202-13","WATER WELL ABANDONMENT",31184.52,1.8557499224147663E-5,7,2598.71]
[null,null,null,null,null,"411-03.07",16,null,null,null,null,null,null,null,"202-13.01","WELL ABANDONMENT (STA. 142+57)",2900,1.7257519997110176E-6,1,2900]
[null,null,null,null,null,"411-03.10",43,null,null,null,null,null,null,null,"202M01","REMOVAL OF STRUCTURES AND OBSTRUCTIONS",69634.62,4.1438649901419585E-5,1,69634.62]
[null,null,null,null,null,"411-03.12",91,null,null,null,null,null,null,null,"203-01","ROAD & DRAINAGE EXCAVATION (UNCLASSIFIED)",107152847.41940002,6.3765255416813493E-2,105,6.3250695162361339]
[null,null,null,null,null,"411-03.13",34,null,null,null,null,null,null,null,"203-01.07","RD & DRNG EXCV (ACID PRODUCING- OFF SITE DISPOSAL)",429062.5,2.5532947150896842E-4,1,12.5]
[null,null,null,null,null,"411-03.15",15,null,null,null,null,null,null,null,"203-01.09","ACID PRODUCING MATERIAL HAUL & TIP FEE",14556395.040000001,8.6623199478839778E-3,2,25.814108421278508]
[null,null,null,null,null,"411-03.16",15,null,null,null,null,null,null,null,"203-01.11","PRESPLITTING OF ROCK EXCAVATION",1856375.2379999999,1.104704579031902E-3,17,17.525741611497384]
[null,null,null,null,null,"411-03.23",29,null,null,null,null,null,null,null,"203-01.29","ROCK EXCAVATION",50616.649999999994,3.0121305157300919E-5,1,16.45]
[null,null,null,null,null,"411-12.01",116,null,null,null,null,null,null,null,"203-01.60","ROAD & DRAINAGE EXCAVATION (ROCK)",259556.85,1.5445888031937678E-4,1,31.45]
[null,null,null,null,null,"411-12.02",91,null,null,null,null,null,null,null,"203-01.79","EXCAVATION/BACKFILL",148889.5,8.8602190469301223E-5,4,23.402939327255581]
[null,null,null,null,null,"411-12.03",137,null,null,null,null,null,null,null,"203-02","BORROW EXCAVATION (SOLID ROCK)",3766.1400000000003,2.2411805642040181E-6,1,30.87]
[null,null,null,null,null,"411-12.04",45,null,null,null,null,null,null,null,"203-02.01","BORROW EXCAVATION (GRADED SOLID ROCK)",33854325.691979997,2.0146265607518123E-2,58,15.822052514621925]
[null,null,null,null,null,"415-01.01",190,null,null,null,null,null,null,null,"203-02.02","BORROW EXCAVATION (GRADED SOLID ROCK)",1244292.8399999999,7.4046236443313829E-4,10,29.071583374220225]
[null,null,null,null,null,"415-01.02",172,null,null,null,null,null,null,null,"203-02.04","BORROW EXCAVATION (SOLID ROCK)",3085,1.8358430755546513E-6,1,30.85]
[null,null,null,null,null,"501-01",8,null,null,null,null,null,null,null,"203-03","BORROW EXCAVATION (UNCLASSIFIED)",32867953.021750003,1.9559288156445809E-2,47,5.0301933835939945]
[null,null,null,null,null,"501-01.03",20,null,null,null,null,null,null,null,"203-03.01","BORROW EXCAVATION (SELECT MATERIAL)",1804011,1.0735433071554043E-3,2,11.56706484313386]
[null,null,null,null,null,"502-04.01",12,null,null,null,null,null,null,null,"203-03.10","SELECT GRANULAR MATERIAL",1984961.7349999999,1.1812247184572761E-3,7,14.888234531491792]
[null,null,null,null,null,"502-04.02",9,null,null,null,null,null,null,null,"203-04","PLACING AND SPREADING TOPSOIL",3436254.6018500002,2.0448700864340772E-3,62,4.4537589683777465]
[null,null,null,null,null,"502-04.03",10,null,null,null,null,null,null,null,"203-04.01","PLACING SPREADING SOIL FOR LANDSCAPING",27360,1.6281577486928772E-5,1,40]
[null,null,null,null,null,"502-08.01",15,null,null,null,null,null,null,null,"203-04.02","STRIPPING & STOCKPILE TOPSOIL",89632.93,5.3339382133606082E-5,3,1.5371793860401302]
[null,null,null,null,null,"502-08.07",8,null,null,null,null,null,null,null,"203-05","UNDERCUTTING",3039316.16,1.8086572209910384E-3,33,6.0613090985962117]
[null,null,null,null,null,"604-01.01",47,null,null,null,null,null,null,null,"203-06","WATER",1550700.8373099999,9.2280174860044184E-4,101,7.3065906166134837]
[null,null,null,null,null,"604-01.02",31,null,null,null,null,null,null,null,"203-07","FURNISHING & SPREADING TOPSOIL",822768.64000000001,4.8961883647569463E-4,23,7.0196711856598046]
[null,null,null,null,null,"604-02.01",21,null,null,null,null,null,null,null,"203-08","CHANNEL EXCAVATION (UNCLASSIFIED)",136366.66999999998,8.1150018429804267E-5,8,10.765506434041209]
[null,null,null,null,null,"604-02.02",20,null,null,null,null,null,null,null,"203-10","EMBANKMENT (COMPACTED IN PLACE)",6980079.2599999998,4.1537537038228963E-3,2,8.0043475957414607]
[null,null,null,null,null,"604-02.03",23,null,null,null,null,null,null,null,"203-10.15","WASTE MATERIAL",205168.95,1.2209335370383097E-4,4,9.9877786973030869]
[null,null,null,null,null,"604-03.01",23,null,null,null,null,null,null,null,"203-11","SCALING AND TRIMMING",682416,4.0609681952923923E-4,1,48]
[null,null,null,null,null,"604-03.02",23,null,null,null,null,null,null,null,"203-12.30","WETLAND MATERIALS EXCAVATION AND RELOCATION",4292.5,2.5544105030205318E-6,1,25.25]
[null,null,null,null,null,"604-03.04",19,null,null,null,null,null,null,null,"203-15.03","COMPACTED CLAY",1047652.2,6.2344409625918857E-4,9,12.354680534918275]
[null,null,null,null,null,"604-03.09",19,null,null,null,null,null,null,null,"203-40.02","ROCK ANCHORS (SEE PLANS)",533522.88,3.1749247484537282E-4,2,1010.46]
[null,null,null,null,null,"604-04.01",20,null,null,null,null,null,null,null,"203-40.05","DRILLING",155000,9.2238468950071626E-5,1,50]
[null,null,null,null,null,"604-04.02",10,null,null,null,null,null,null,null,"203-50","CONSTRUCTION OF HAUL ROAD",1315000,7.8253926883447861E-4,5,263000]
[null,null,null,null,null,"604-05.31",19,null,null,null,null,null,null,null,"203-50.01","CONSTRUCTION OF HAUL ROAD",35000,2.0828041375822623E-5,1,35000]
[null,null,null,null,null,"604-07.01",20,null,null,null,null,null,null,null,"203-70.07","STANDPIPE",102000,6.0698863438111652E-5,1,3400]
[null,null,null,null,null,"604-07.02",13,null,null,null,null,null,null,null,"203M01","ROAD & DRAINAGE EXCAVATION (UNCLASSIFIED)",2936118.85,1.7472458540609356E-3,1,8.35]
[null,null,null,null,null,"604-07.03",8,null,null,null,null,null,null,null,"203M02.01","BORROW EXCAVATION (GRADED SOLID ROCK)",2910416.3200000003,1.7319506152522694E-3,1,27.370000000000005]
[null,null,null,null,null,"604-07.04",8,null,null,null,null,null,null,null,"203M03","BORROW EXCAVATION (UNCLASSIFIED)",588330,3.5010747378964928E-4,1,6.75]
[null,null,null,null,null,"604-07.05",9,null,null,null,null,null,null,null,"203M06","WATER",20670,1.230044614966439E-5,1,0.53]
[null,null,null,null,null,"604-10.30",12,null,null,null,null,null,null,null,"203M07","FURNISHING & SPREADING TOPSOIL",265585.04000000004,1.5804617719770021E-4,1,10.640000000000002]
[null,null,null,null,null,"604-10.34",9,null,null,null,null,null,null,null,"203M40.10","TIE-BACK ANCHORS (SOIL)",4211856.43,2.5064205712304159E-3,1,167.89]
[null,null,null,null,null,"604-10.44",14,null,null,null,null,null,null,null,"203M40.11","TIE-BACK ANCHORS (ROCK)",2524897.71,1.5025335421028512E-3,1,167.89]
[null,null,null,null,null,"604-10.50",36,null,null,null,null,null,null,null,"203M40.13","SUPPLEMENTAL WALERS",8262.68,4.9170125975766316E-6,1,2065.67]
[null,null,null,null,null,"604-10.56",9,null,null,null,null,null,null,null,"203M40.20","SOIL ANCHOR PULLOUT TEST",51500,3.0646975167281863E-5,1,12875]
[null,null,null,null,null,"606-02.03",13,null,null,null,null,null,null,null,"203M40.21","ROCK ANCHOR PULLOUT TEST",25750,1.5323487583640931E-5,1,12875]
[null,null,null,null,null,"606-02.06",12,null,null,null,null,null,null,null,"204-01","CULVERT EXCAVATION (UNCLASSIFIED)",9191.25,5.4695924370151345E-6,1,4.75]
[null,null,null,null,null,"607-03.02",62,null,null,null,null,null,null,null,"204-02.01","DRY EXCAVATION (BRIDGES)",1042350.3500000001,6.2028903479723421E-4,32,23.261037468478722]
[null,null,null,null,null,"607-03.30",24,null,null,null,null,null,null,null,"204-03.01","WET EXCAVATION (BRIDGES)",191298.97,1.138395103517786E-4,13,28.93646498260475]
[null,null,null,null,null,"607-05.02",57,null,null,null,null,null,null,null,"204-04.01","ROCK EXCAVATION (BRIDGES)",103115.26,6.1362540050248783E-5,14,78.593948170731721]
[null,null,null,null,null,"607-05.30",20,null,null,null,null,null,null,null,"204-05","ROCK DRILLING (BRIDGES)",35317.68,2.1017088581087519E-5,14,28.029904761904763]
[null,null,null,null,null,"607-06.02",39,null,null,null,null,null,null,null,"204-05.01","CORE DRILLING AND SAMPLING",171928.75,1.0231254624838469E-4,2,65.372148288973378]
[null,null,null,null,null,"607-06.30",16,null,null,null,null,null,null,null,"204-05.20","GROUT CASING INSTALLATION",98992,5.8908842053583808E-5,1,61.87]
[null,null,null,null,null,"607-07.02",33,null,null,null,null,null,null,null,"204-06.01","FLOWABLE FILL (GENERAL)",340914.32,2.0287364464486956E-4,9,151.92260249554369]
[null,null,null,null,null,"607-07.30",12,null,null,null,null,null,null,null,"204-08","FOUNDATION FILL MATERIAL",897791.82300000032,5.3426414960912089E-4,55,55.918772105260039]
[null,null,null,null,null,"607-08.02",18,null,null,null,null,null,null,null,"204-08.01","BACKFILL MATERIAL (FLOWABLE FILL)",1088491.1100000001,6.477467964655742E-4,44,212.58205226455928]
[null,null,null,null,null,"607-09.02",20,null,null,null,null,null,null,null,"204-09.01","COFFERDAM (STA. 142+99.73)",299329.53000000003,1.7812708102415829E-4,2,149664.76500000001]
[null,null,null,null,null,"607-37.02",12,null,null,null,null,null,null,null,"204-09.02","COFFERDAM (STA. 143+66.10)",285965.27,1.7017418501737969E-4,2,142982.63500000001]
[null,null,null,null,null,"607-39.02",77,null,null,null,null,null,null,null,"204-09.03","COFFERDAM (STA. 143+10.06)",285965.27,1.7017418501737969E-4,2,142982.63500000001]
[null,null,null,null,null,"607-39.03",31,null,null,null,null,null,null,null,"204-09.04","COFFERDAM (STA. 143+75.75)",285965.27,1.7017418501737969E-4,2,142982.63500000001]
[null,null,null,null,null,"607-39.04",21,null,null,null,null,null,null,null,"204-10.01","FOUNDATION PREPARATION (BENT NO. 1 LT. LN., STA. 591+00.25)",402339.53,2.3942698222768655E-4,12,33528.294166666667]
[null,null,null,null,null,"607-39.05",13,null,null,null,null,null,null,null,"204-10.02","FOUNDATION PREPARATION (BENT NO. 2 LT. LN., STA. 591+99.75)",335857.61,1.9986446278471139E-4,9,37317.51222222222]
[null,null,null,null,null,"610-07.03",11,null,null,null,null,null,null,null,"204-10.03","FOUNDATION PREPARATION (BENT NO. 1 RT. LN., STA. 591+00.25)",274255.84999999998,1.632060626103258E-4,5,54851.17]
[null,null,null,null,null,"611-01.02",17,null,null,null,null,null,null,null,"204-10.04","FOUNDATION PREPARATION (BENT NO. 2 RT. LN., STA. 591+99.75)",274255.84999999998,1.632060626103258E-4,5,54851.17]
[null,null,null,null,null,"611-01.03",11,null,null,null,null,null,null,null,"204-10.05","FOUNDATION PREPARATION (BENT NO. 1 LT. LN., STA. 748+14.08)",78966.209999999992,4.6991756833482805E-5,2,39483.104999999996]
[null,null,null,null,null,"611-01.20",24,null,null,null,null,null,null,null,"204-10.06","FOUNDATION PREPARATION (BENT NO. 2 LT. LN., STA. 748+97.42)",78966.209999999992,4.6991756833482805E-5,2,39483.104999999996]
[null,null,null,null,null,"611-02.10",15,null,null,null,null,null,null,null,"204-10.07","FOUNDATION PREPARATION (BENT NO. 1 RT. LN., STA. 748+14.08)",78966.209999999992,4.6991756833482805E-5,2,39483.104999999996]
[null,null,null,null,null,"611-02.11",21,null,null,null,null,null,null,null,"204-10.08","FOUNDATION PREPARATION (BENT NO. 2 RT. LN., STA. 748+97.42)",78966.209999999992,4.6991756833482805E-5,2,39483.104999999996]
[null,null,null,null,null,"611-07.01",70,null,null,null,null,null,null,null,"204-10.09","FOUNDATION PREPARATION (STA. 174+34.11)",38966.21,2.3188280975399809E-5,1,38966.21]
[null,null,null,null,null,"611-07.02",69,null,null,null,null,null,null,null,"204-11","BRIDGE EXCAVATION (UNCLASSIFIED)",3500,2.0828041375822626E-6,1,70]
[null,null,null,null,null,"611-07.03",17,null,null,null,null,null,null,null,"204-14","CORE DRILLING FOR PILES(ROCK)",445438.9,2.6507485256002623E-4,6,172.51700232378002]
[null,null,null,null,null,"611-07.31",20,null,null,null,null,null,null,null,"204-15","CORE DRILLING FOR PILES(SOIL)",360615.3,2.1459743969013396E-4,7,86.895253012048187]
[null,null,null,null,null,"611-07.32",14,null,null,null,null,null,null,null,"204M02.01","DRY EXCAVATION (BRIDGES)",14844.36,8.8336841222173245E-6,1,24.02]
[null,null,null,null,null,"611-07.54",36,null,null,null,null,null,null,null,"204M06.02","FLOWABLE FILL (EXCAVATABLE)",854078.55,5.0825095364578834E-4,1,271.05]
[null,null,null,null,null,"611-07.55",18,null,null,null,null,null,null,null,"204M08","FOUNDATION FILL MATERIAL",3134.04,1.8650261369566611E-6,1,76.44]
[null,null,null,null,null,"611-07.56",19,null,null,null,null,null,null,null,"204M08.01","BACKFILL MATERIAL (FLOWABLE FILL)",33645,2.0021698631130063E-5,1,224.3]
[null,null,null,null,null,"611-07.57",31,null,null,null,null,null,null,null,"204M14","CORE DRILLING FOR PILES(ROCK)",3500583.75,2.0831515195580664E-3,1,1364.75]
[null,null,null,null,null,"611-07.58",21,null,null,null,null,null,null,null,"204M15","CORE DRILLING FOR PILES(SOIL)",735157.35000000009,4.3748250581543191E-4,1,139.05000000000001]
[null,null,null,null,null,"611-07.59",15,null,null,null,null,null,null,null,"205-02.01","RSS BACKFILL MATERIAL",84720,5.0415761867419796E-5,1,10]
[null,null,null,null,null,"611-07.60",21,null,null,null,null,null,null,null,"209-01.31","TEMPORARY MULCH FILTER BERM",118902.22,7.0757153081061838E-5,7,11.074063518673745]
[null,null,null,null,null,"611-07.61",14,null,null,null,null,null,null,null,"209-02.03","8\" TEMPORARY SLOPE DRAIN",113688.87,6.7654756809443415E-5,19,8.8356936348799255]
[null,null,null,null,null,"611-07.62",10,null,null,null,null,null,null,null,"209-02.04","10\" TEMPORARY SLOPE DRAIN",35497.08,2.1123847170311022E-5,10,10.818982017677538]
[null,null,null,null,null,"611-07.63",17,null,null,null,null,null,null,null,"209-02.05","12\" TEMPORARY SLOPE DRAIN",316151.94,1.8813787678190262E-4,36,13.391332008962797]
[null,null,null,null,null,"611-07.64",8,null,null,null,null,null,null,null,"209-02.06","15\" TEMPORARY SLOPE DRAIN",84020.11,4.999926649946195E-5,17,16.442291585127201]
[null,null,null,null,null,"611-07.69",8,null,null,null,null,null,null,null,"209-02.07","18\" TEMPORARY SLOPE DRAIN",698295.53,4.1554651975405683E-4,41,17.523979371612128]
[null,null,null,null,null,"611-09.01",41,null,null,null,null,null,null,null,"209-03.20","FILTER SOCK (8 INCH)",22135.15,1.3172337716001149E-5,5,3.1136798424532284]
[null,null,null,null,null,"611-09.02",12,null,null,null,null,null,null,null,"209-03.21","FILTER SOCK (12 INCH)",293173.06,1.7446344639875796E-4,8,3.7613776734280178]
[null,null,null,null,null,"611-09.03",8,null,null,null,null,null,null,null,"209-03.22","FILTER SOCK (18 INCH)",391962.2,2.3325156912452753E-4,10,1.9354246494173415]
[null,null,null,null,null,"611-12.01",28,null,null,null,null,null,null,null,"209-03.23","FILTER SOCK (24 INCH)",362264.83,2.1557905337843855E-4,9,8.2140632156542637]
[null,null,null,null,null,"611-12.02",29,null,null,null,null,null,null,null,"209-03.31","STREAM MITIGATION-COCONUT FIBER ROLLS",30782,1.8317964846587772E-5,2,15.908010335917313]
[null,null,null,null,null,"611-12.03",17,null,null,null,null,null,null,null,"209-03.34","STREAM MITIGATION-LOG VANES",61526.69,3.661372700106892E-5,4,214.37871080139374]
[null,null,null,null,null,"611-12.04",10,null,null,null,null,null,null,null,"209-03.35","STREAM MITIGATION-LOG DROP STRUCTURE",7146.25,4.2526397337706414E-6,2,109.94230769230769]
[null,null,null,null,null,"611-14.02",25,null,null,null,null,null,null,null,"209-03.36","STREAM MITIGATION-STEP POOL",380564.92,2.2646919714133221E-4,3,4374.3094252873561]
[null,null,null,null,null,"611-25.02",9,null,null,null,null,null,null,null,"209-03.37","STREAM MITIGATION CROSS VANE STRUCTURE",5852.08,3.4824961249892591E-6,1,2926.04]
[null,null,null,null,null,"611-38.01",16,null,null,null,null,null,null,null,"209-03.38","STREAM MITIGATION -J -HOOK",7120,4.2370187027387742E-6,1,3560]
[null,null,null,null,null,"611-38.02",15,null,null,null,null,null,null,null,"209-03.40","STREAM MITIGATION - LOG RIFFLE",212584,1.2650595279536792E-4,2,219.83867631851086]
[null,null,null,null,null,"611-39.01",13,null,null,null,null,null,null,null,"209-03.41","STREAM MITIGATION - BOULDER RIFFLE",21500,1.2794368273719613E-5,1,500]
[null,null,null,null,null,"611-39.02",11,null,null,null,null,null,null,null,"209-03.42","STREAM MITIGATION - LIVE BRUSH LAYERING",175780,1.0460437465834575E-4,1,170]
[null,null,null,null,null,"611-41.02",8,null,null,null,null,null,null,null,"209-03.43","STREAM MITIGATION - VEGETATED RIP-RAP (DESCRIP)",10500,6.2484124127467873E-6,1,75]
[null,null,null,null,null,"611-42.01",26,null,null,null,null,null,null,null,"209-03.44","STREAM MITIGATION - WILLOW POLES (SPECIES)",36760,2.1875394313578276E-5,3,17.266322217003289]
[null,null,null,null,null,"611-42.02",27,null,null,null,null,null,null,null,"209-03.45","STREAM MITIGATION - LIVE FASCINES (SPECIES)",9540,5.6771289921527958E-6,1,3]
[null,null,null,null,null,"617-01",13,null,null,null,null,null,null,null,"209-03.47","STREAM MITIGATION - LONGITUDINAL STONE TOE (DESCRIP)",589.5,3.508037254584982E-7,1,98.25]
[null,null,null,null,null,"617-04.01",12,null,null,null,null,null,null,null,"209-03.55","STREAM MITIGATION (LOG RIFFLE)",38556.75,2.2944616694778542E-5,3,3855.6750000000002]
[null,null,null,null,null,"617-04.02",17,null,null,null,null,null,null,null,"209-03.56","STREAM MITIGATION (ROCK RIFFLES)",15367.96,9.1452716211996294E-6,1,3841.99]
[null,null,null,null,null,"620-05.01",13,null,null,null,null,null,null,null,"209-03.57","STREAM MITIGATION (LOG VANE AND ROOT WAD)",92900,5.5283572680397765E-5,3,60.324675324675326]
[null,null,null,null,null,"621-03.02",44,null,null,null,null,null,null,null,"209-03.58","STREAM MITIGATION (DESCRIPTION)",11960,7.1172392815668174E-6,1,260]
[null,null,null,null,null,"621-03.03",22,null,null,null,null,null,null,null,"209-03.59","STREAM MITIGATION - BRUSH MATTRESS",75620,4.5000471109705909E-5,1,95]
[null,null,null,null,null,"621-03.04",9,null,null,null,null,null,null,null,"209-03.60","STREAM MITIGATION - ROCK VANE",15000,8.9263034467811257E-6,1,7500]
[null,null,null,null,null,"621-03.05",13,null,null,null,null,null,null,null,"209-03.62","STREAM MITIGATION - ROOT WAD",3000,1.7852606893562249E-6,1,500]
[null,null,null,null,null,"621-03.06",12,null,null,null,null,null,null,null,"209-03.66","PLACING NATIVE STONE IN NEW CHANNEL",14000,8.3312165503290503E-6,1,100]
[null,null,null,null,null,"621-03.07",15,null,null,null,null,null,null,null,"209-03.67","Stream Mitigation – Wood Toe W/Reinforced Earth",76516,4.5533668968926972E-5,1,74]
[null,null,null,null,null,"701-01.01",41,null,null,null,null,null,null,null,"209-04","BRUSH BARRIERS",44986.05,2.677060887813787E-5,2,6.0101603206412832]
[null,null,null,null,null,"701-02",28,null,null,null,null,null,null,null,"209-05","SEDIMENT REMOVAL",1281210.8240000003,7.6243177295496581E-4,102,8.6384060395729509]
[null,null,null,null,null,"701-02.01",75,null,null,null,null,null,null,null,"209-06","BALED HAY OR STRAW EROSION CHECKS",45000,2.6778910340343374E-5,1,5]
[null,null,null,null,null,"701-02.03",31,null,null,null,null,null,null,null,"209-06.02","12\" DIA COIR LOG (LOW FLOW CHANNEL)",33524.959999999999,1.9950264400079956E-5,6,10.440660230457802]
[null,null,null,null,null,"701-03",15,null,null,null,null,null,null,null,"209-06.05","BALED HAY OR STRAW",87798.6,5.2247796386837156E-5,4,6.3310210556677244]
[null,null,null,null,null,"702-01",31,null,null,null,null,null,null,null,"209-06.13","20IN DIA COIR LOG (IN STREAM)",2850,1.6959976548884138E-6,1,28.5]
[null,null,null,null,null,"702-03",48,null,null,null,null,null,null,null,"209-08.02","TEMPORARY SILT FENCE (WITH BACKING)",6261105.2439999999,3.7259016880117719E-3,98,3.6576123913081284]
[null,null,null,null,null,"703-01",29,null,null,null,null,null,null,null,"209-08.03","TEMPORARY SILT FENCE (WITHOUT BACKING)",1646640.7649999997,9.7989434241532031E-4,86,1.3443043615538961]
[null,null,null,null,null,"705-01.01",60,null,null,null,null,null,null,null,"209-08.04","TEMPORARY ENHANCED SILT FENCE",4761,2.8332087140083292E-6,1,9]
[null,null,null,null,null,"705-01.04",23,null,null,null,null,null,null,null,"209-08.05","ENHANCED SILT FENCE CHECK (V-DITCH)",121654.56,7.2395034549642743E-5,7,439.18613718411552]
[null,null,null,null,null,"705-02.02",177,null,null,null,null,null,null,null,"209-08.06","ENHANCED SILT FENCE CHECK (TRAPEZOIDAL)",4950,2.9456801374377711E-6,1,450]
[null,null,null,null,null,"705-02.03",9,null,null,null,null,null,null,null,"209-08.07","ROCK CHECK DAM PER",2748512.33,1.6356036723199614E-3,91,218.44796773168019]
[null,null,null,null,null,"705-02.10",10,null,null,null,null,null,null,null,"209-08.08","ENHANCED ROCK CHECK DAM",1941562.99,1.155398693985311E-3,97,394.94771969080546]
[null,null,null,null,null,"705-04.02",9,null,null,null,null,null,null,null,"209-08.09","FILTER SOCK CHECK DAM",316942.65000000002,1.8860841794179626E-4,14,209.75688285903377]
[null,null,null,null,null,"705-04.03",67,null,null,null,null,null,null,null,"209-09.01","SANDBAGS",635180.86199999996,3.7798780785333369E-4,65,3.0886619641603277]
[null,null,null,null,null,"705-04.04",49,null,null,null,null,null,null,null,"209-09.02","TEMPORARY SEDIMENT FILTER BAG (14'6\" X 2'0\" X 13'3\")",10168.34,6.0510458926694925E-6,4,598.13764705882352]
[null,null,null,null,null,"705-04.05",68,null,null,null,null,null,null,null,"209-09.03","SEDIMENT FILTER BAG (15' X 15')",282614.59999999998,1.6818024520604458E-4,59,541.40727969348654]
[null,null,null,null,null,"705-04.07",238,null,null,null,null,null,null,null,"209-09.04","SEDIMENT FILTER BAG(15' X 10')",59218.69,3.5240266444057533E-5,21,501.85330508474578]
[null,null,null,null,null,"705-04.09",55,null,null,null,null,null,null,null,"209-09.20","POLYMER FLOCCULENT",24480,1.4567727225146795E-5,1,12]
[null,null,null,null,null,"705-04.21",31,null,null,null,null,null,null,null,"209-09.21","POLYACRYLAMIDE GEL LOGS",202975.16,1.2078785802126335E-4,5,102.4609591115598]
[null,null,null,null,null,"705-04.50",14,null,null,null,null,null,null,null,"209-09.22","POLYACRYLAMIDE POWDER",226226.26588999998,1.34624286464422E-4,15,9.1556509786222158]
[null,null,null,null,null,"705-06.20",34,null,null,null,null,null,null,null,"209-09.23","POLYACRYLAMIDE LIQUID",18935,1.126797038432004E-5,3,51.453804347826086]
[null,null,null,null,null,"705-08.51",86,null,null,null,null,null,null,null,"209-09.24","JUTE MESH FABRIC",20260.68,1.2056865181208627E-5,5,1.4121893078692409]
[null,null,null,null,null,"705-17.97",8,null,null,null,null,null,null,null,"209-09.40","CURB INLET PROTECTION (TYPE 1)",23594.879999999997,1.4041003911359135E-5,5,262.16533333333331]
[null,null,null,null,null,"706-01",168,null,null,null,null,null,null,null,"209-09.41","CURB INLET PROTECTION (TYPE 2)",143948.5,8.5661866113931516E-5,20,203.89305949008499]
[null,null,null,null,null,"706-05",13,null,null,null,null,null,null,null,"209-09.42","CURB INLET PROTECTION (TYPE 3)",5107.5,3.039406323628973E-6,2,510.75]
[null,null,null,null,null,"706-06.03",22,null,null,null,null,null,null,null,"209-09.43","CURB INLET PROTECTION (TYPE 4)",450067.5,2.6782927176894429E-4,36,169.900906002265]
[null,null,null,null,null,"707-01.11",8,null,null,null,null,null,null,null,"209-10.01","TEMPORARY DEWATERING STRUCTURE",29150,1.7346783031577986E-5,3,14.219512195121951]
[null,null,null,null,null,"707-01.12",8,null,null,null,null,null,null,null,"209-10.02","8IN SKIMMER W/6IN HEAD",5500,3.2729779304864125E-6,1,5500]
[null,null,null,null,null,"707-03.01",10,null,null,null,null,null,null,null,"209-10.20","TEMPORARY SEDIMENT TRAP",400824.48499999999,2.3852539880065129E-4,22,6.9573089807678956]
[null,null,null,null,null,"707-03.02",10,null,null,null,null,null,null,null,"209-11.01","SEDIMENT BASIN RISER (24\")",14550,8.6585143433776905E-6,2,3637.5]
[null,null,null,null,null,"707-06.01",13,null,null,null,null,null,null,null,"209-11.20","SEDIMENT BASIN BAFFLES",1875,1.1157879308476407E-6,1,25]
[null,null,null,null,null,"707-08.11",80,null,null,null,null,null,null,null,"209-13.04","TURBIDITY CURTAIN (LIGHTED MARKERS)",167330,9.9575890383325711E-5,2,34.190845933796489]
[null,null,null,null,null,"708-02.01",45,null,null,null,null,null,null,null,"209-20.03","POLYETHYLENE SHEETING (6 MIL. MINIMUM)",289601.26560000004,1.723379183544971E-4,55,1.4993857805418269]
[null,null,null,null,null,"709-05.05",99,null,null,null,null,null,null,null,"209-20.04","POLYETHYLENE SHEETING (10 MIL.)",3599.7,2.1421343011585341E-6,3,14.573684210526315]
[null,null,null,null,null,"709-05.06",97,null,null,null,null,null,null,null,"209-40.30","CATCH BASIN PROTECTION (TYPE A)",139986.26,8.330398900933325E-5,24,616.67955947136568]
[null,null,null,null,null,"709-05.08",60,null,null,null,null,null,null,null,"209-40.31","CATCH BASIN PROTECTION (TYPE B)",6346,3.776421444884868E-6,4,317.3]
[null,null,null,null,null,"709-05.09",39,null,null,null,null,null,null,null,"209-40.32","CATCH BASIN PROTECTION (TYPE C)",250,1.4877172411301874E-7,1,250]
[null,null,null,null,null,"710-02",65,null,null,null,null,null,null,null,"209-40.33","CATCH BASIN PROTECTION (TYPE D)",345943.36000000004,2.0586636045060293E-4,43,227.29524310118268]
[null,null,null,null,null,"710-05",49,null,null,null,null,null,null,null,"209-40.34","CATCH BASIN PROTECTION (TYPE E)",27091.5,1.6121796655231391E-5,7,190.78521126760563]
[null,null,null,null,null,"710-06.11",14,null,null,null,null,null,null,null,"209-40.41","CATCH BASIN FILTER ASSEMBLY(TYPE 1)",251867.08999999997,1.4988280490651543E-4,37,477.92616698292221]
[null,null,null,null,null,"710-06.12",27,null,null,null,null,null,null,null,"209-40.42","CATCH BASIN FILTER ASSEMBLY(TYPE 2)",390455.34,2.3235485648373974E-4,40,541.54693481276013]
[null,null,null,null,null,"710-06.13",32,null,null,null,null,null,null,null,"209-40.43","CATCH BASIN FILTER ASSEMBLY(TYPE 3)",108588.23999999999,6.4619438732793069E-5,16,638.75435294117642]
[null,null,null,null,null,"710-06.15",49,null,null,null,null,null,null,null,"209-40.44","CATCH BASIN FILTER ASSEMBLY(TYPE 4)",213129.72,1.2683070361649973E-4,22,717.60848484848498]
[null,null,null,null,null,"710-09.01",25,null,null,null,null,null,null,null,"209-40.45","CATCH BASIN FILTER ASSEMBLY(TYPE 5)",65238.080000000002,3.8822326557692185E-5,13,893.6723287671233]
[null,null,null,null,null,"710-09.02",20,null,null,null,null,null,null,null,"209-40.46","CATCH BASIN FILTER ASSEMBLY(TYPE 6)",677746.57000000007,4.0331810292233906E-4,25,502.03449629629637]
[null,null,null,null,null,"711-05.70",9,null,null,null,null,null,null,null,"209-40.47","CATCH BASIN FILTER ASSEMBLY(TYPE 7)",260778.18999999997,1.5518568374948952E-4,25,771.53310650887579]
[null,null,null,null,null,"711-05.71",9,null,null,null,null,null,null,null,"209-40.48","CATCH BASIN FILTER ASSEMBLY(TYPE 8)",70865.42,4.2171082853572805E-5,14,998.10450704225354]
[null,null,null,null,null,"711-05.72",9,null,null,null,null,null,null,null,"209-40.50","CATCH BASIN FILTER ASSEMBLY(TYPE 10)",3970,2.3624949789147376E-6,2,794]
[null,null,null,null,null,"712-01",449,null,null,null,null,null,null,null,"209-65.01","TEMPORARY STREAM DIVERSION (DESCRIPTION)",231640.9,1.3784646427236546E-4,8,28955.112499999999]
[null,null,null,null,null,"712-02.02",103,null,null,null,null,null,null,null,"209-65.02","TEMPORARY STREAM DIVERSION (GRAVITY FLOW)",74061.42,4.4072980574633638E-5,3,24687.14]
[null,null,null,null,null,"712-04.01",309,null,null,null,null,null,null,null,"209-65.03","TEMPORARY DIVERSION CHANNEL",1098978.48,6.5398769293081882E-4,41,25.374119276858071]
[null,null,null,null,null,"712-04.02",48,null,null,null,null,null,null,null,"209-65.04","TEMPORARY IN STREAM DIVERSION",626317.28,3.7271320634950529E-4,22,54.462372173913046]
[null,null,null,null,null,"712-04.50",62,null,null,null,null,null,null,null,"209-65.14","TEMPORARY STREAM DIVERSION",55850.77,3.3236061383758656E-5,2,27925.384999999998]
[null,null,null,null,null,"712-05.01",282,null,null,null,null,null,null,null,"209M02.05","300mm TEMPORARY SLOPE DRAIN",35223.599999999999,2.0961102805869308E-5,1,35.76]
[null,null,null,null,null,"712-05.03",73,null,null,null,null,null,null,null,"209M02.07","450mm TEMPORARY SLOPE DRAIN",982.08,5.8442293926765379E-7,1,89.28]
[null,null,null,null,null,"712-06",451,null,null,null,null,null,null,null,"209M03.22","FILTER SOCK (450mm)",9223.1999999999989,5.4886054633567773E-6,1,32.94]
[null,null,null,null,null,"712-06.01",23,null,null,null,null,null,null,null,"209M03.23","Filter Sock (24 inch)",1534.56,9.1319654781949619E-7,1,33.36]
[null,null,null,null,null,"712-06.16",46,null,null,null,null,null,null,null,"209M05","SEDIMENT REMOVAL",21963.759999999998,1.3070345772818225E-5,1,3.92]
[null,null,null,null,null,"712-07.03",80,null,null,null,null,null,null,null,"209M05.01","SEDIMENT REMOVAL (CULVERTS)",37062,2.2055110556306804E-5,1,61.77]
[null,null,null,null,null,"712-08.03",269,null,null,null,null,null,null,null,"209M08.02","TEMPORARY SILT FENCE (WITH BACKING)",165013.52000000002,9.8197383489432425E-5,1,11.48]
[null,null,null,null,null,"712-08.10",60,null,null,null,null,null,null,null,"209M08.03","TEMPORARY SILT FENCE (WITHOUT BACKING)",63410.85,3.7734965927888057E-5,1,4.59]
[null,null,null,null,null,"712-09.01",30,null,null,null,null,null,null,null,"209M08.07","Rock Check Dam",67818.78,4.0358067311366058E-5,1,203.66]
[null,null,null,null,null,"712-09.02",18,null,null,null,null,null,null,null,"209M08.08","Enhanced Rock Check Dam",30132.339999999997,1.7931360693438714E-5,1,298.33999999999997]
[null,null,null,null,null,"712-09.04",18,null,null,null,null,null,null,null,"209M08.09","FILTER SOCK CHECK DAM",6607.92,3.9322866048035951E-6,1,300.36]
[null,null,null,null,null,"713-01.01",35,null,null,null,null,null,null,null,"209M09.01","SANDBAGS",46063.89,2.7412017338609773E-5,1,2.61]
[null,null,null,null,null,"713-01.02",35,null,null,null,null,null,null,null,"209M09.04","SEDIMENT FILTER BAG (450mm X 300mm)",17089.02,1.0169451875207439E-5,1,657.27]
[null,null,null,null,null,"713-02.04",20,null,null,null,null,null,null,null,"209M09.43","CURB INLET PROTECTION (TYPE 4)",21225.440000000002,1.2630981215429733E-5,1,100.12]
[null,null,null,null,null,"713-02.14",91,null,null,null,null,null,null,null,"209M10.20","TEMPORARY SEDIMENT TRAP",822.92000000000007,4.8970890882834165E-7,1,117.56000000000002]
[null,null,null,null,null,"713-02.15",51,null,null,null,null,null,null,null,"209M20.03","POLYETHYLENE SHEETING (6 MIL. MINIMUM)",1487.02,8.8490611676216453E-7,1,2.98]
[null,null,null,null,null,"713-02.21",26,null,null,null,null,null,null,null,"209M40.33","Catch Basin Filter Assembly (Type D)",12922.470000000001,7.6899925667950467E-6,1,226.71]
[null,null,null,null,null,"713-05",9,null,null,null,null,null,null,null,"209M40.41","CATCH BASIN FILTER ASSEMBLY(TYPE 1)",4846.82,2.884279071461846E-6,1,440.61999999999995]
[null,null,null,null,null,"713-06",34,null,null,null,null,null,null,null,"209M40.42","CATCH BASIN FILTER ASSEMBLY(TYPE 2)",17511.45,1.042083443287569E-5,1,530.65]
[null,null,null,null,null,"713-09.01",8,null,null,null,null,null,null,null,"209M40.43","CATCH BASIN FILTER ASSEMBLY(TYPE 3)",8650.92,5.148049134255185E-6,1,720.91]
[null,null,null,null,null,"713-09.02",8,null,null,null,null,null,null,null,"209M40.44","CATCH BASIN FILTER ASSEMBLY(TYPE 4)",4245.16,2.5262390893424904E-6,1,1061.29]
[null,null,null,null,null,"713-11.01",73,null,null,null,null,null,null,null,"209M40.45","CATCH BASIN FILTER ASSEMBLY(TYPE 5)",7208.64,4.2897672052402858E-6,1,1201.44]
[null,null,null,null,null,"713-11.02",82,null,null,null,null,null,null,null,"209M40.46","CATCH BASIN FILTER ASSEMBLY(TYPE 6)",60527.5,3.601912212500297E-5,1,390.5]
[null,null,null,null,null,"713-11.03",8,null,null,null,null,null,null,null,"209M40.47","CATCH BASIN FILTER ASSEMBLY(TYPE 7)",8510.8000000000011,5.0646655583243202E-6,1,851.08000000000015]
[null,null,null,null,null,"713-11.21",43,null,null,null,null,null,null,null,"209M40.48","CATCH BASIN FILTER ASSEMBLY(TYPE 8)",1131.3699999999999,6.7326346203898405E-7,1,1131.3699999999999]
[null,null,null,null,null,"713-13.02",83,null,null,null,null,null,null,null,"209M65.01","TEMPORARY STREAM DIVERSION (STR-2)",73349.119999999995,4.3649100178290822E-5,1,73349.119999999995]
[null,null,null,null,null,"713-13.03",87,null,null,null,null,null,null,null,"209M65.02","TEMPORARY STREAM DIVERSION (DESCRIPTION)",54694.22,3.2547813633667011E-5,1,54694.22]
[null,null,null,null,null,"713-14",26,null,null,null,null,null,null,null,"209M65.03","TEMPORARY DIVERSION CHANNEL",32135.000000000004,1.9123117417487432E-5,1,642.70000000000005]
[null,null,null,null,null,"713-15",79,null,null,null,null,null,null,null,"303-01","MINERAL AGGREGATE, TYPE A BASE, GRADING D",105950120.79057001,6.3049528559982776E-2,107,18.880689461305796]
[null,null,null,null,null,"713-15.02",8,null,null,null,null,null,null,null,"303-01.01","GRANULAR BACKFILL (ROADWAY)",5764171.934799999,3.4301831872962838E-3,53,23.395204652925511]
[null,null,null,null,null,"713-15.07",23,null,null,null,null,null,null,null,"303-01.02","GRANULAR BACKFILL (BRIDGES)",2050977.5300000003,1.2205098530206427E-3,41,33.828883189285477]
[null,null,null,null,null,"713-15.36",17,null,null,null,null,null,null,null,"303-01.03","GRANULAR BACKFILL (RETAINING WALLS)",219998.12,1.3091799845609117E-4,15,28.184782034968901]
[null,null,null,null,null,"713-15.40",15,null,null,null,null,null,null,null,"303-01.09","MINERAL AGGREGATE, TYPE A BASE,GRADING D LIMESTONE",10117102.803779999,6.0205553085880261E-3,3,29.99161919229142]
[null,null,null,null,null,"713-16.01",139,null,null,null,null,null,null,null,"303-02","MINERAL AGGREGATE, TYPE B BASE, GRADING (MAINT ROCK)",463960,2.760965164779047E-4,8,22.146062052505968]
[null,null,null,null,null,"713-16.05",14,null,null,null,null,null,null,null,"303-10.01","MINERAL AGGREGATE (SIZE 57)",3877615.267,2.3075180348742143E-3,98,31.257597159871235]
[null,null,null,null,null,"713-16.07",20,null,null,null,null,null,null,null,"303-10.03","MINERAL AGGREGATE (SIZE 68)",136364.13,8.11485069090873E-5,15,36.847362612894997]
[null,null,null,null,null,"713-16.09",30,null,null,null,null,null,null,null,"303-10.04","MINERAL AGGREGATE (SIZE   )",21281.84,1.2664544116389628E-5,3,44.06178053830228]
[null,null,null,null,null,"713-16.20",143,null,null,null,null,null,null,null,"303-20","PEA GRAVEL",2400,1.4282085514849801E-6,1,100]
[null,null,null,null,null,"713-16.21",105,null,null,null,null,null,null,null,"303-20.02","RIVER GRAVEL",37400,2.2256249927307604E-5,1,25]
[null,null,null,null,null,"713-16.22",66,null,null,null,null,null,null,null,"303M01","MINERAL AGGREGATE, TYPE A BASE, GRADING D",2855143.86,1.6990586985715977E-3,1,26.58]
[null,null,null,null,null,"713-16.23",54,null,null,null,null,null,null,null,"303M01.01","GRANULAR BACKFILL (ROADWAY)",226805.85,1.3496918937367486E-4,1,38.950000000000003]
[null,null,null,null,null,"713-16.24",40,null,null,null,null,null,null,null,"303M01.02","GRANULAR BACKFILL (BRIDGES)",6930.84,4.1244520654058992E-6,1,62.440000000000005]
[null,null,null,null,null,"713-16.25",31,null,null,null,null,null,null,null,"303M01.03","GRANULAR BACKFILL (RETAINING WALLS)",106689.39000000001,6.3489457979465049E-5,2,42.286718192627831]
[null,null,null,null,null,"713-16.26",23,null,null,null,null,null,null,null,"303M10.01","MINERAL AGGREGATE (SIZE 57)",1068483.24,6.3584037520265761E-4,1,37.619999999999997]
[null,null,null,null,null,"713-16.27",17,null,null,null,null,null,null,null,"303M10.02","MINERAL AGGREGATE (SIZE 2)",24804.000000000004,1.4760535379597271E-5,1,41.34]
[null,null,null,null,null,"713-16.28",13,null,null,null,null,null,null,null,"307-01.01","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING A",24121532.320200004,1.435440780609624E-2,68,73.594482039181131]
[null,null,null,null,null,"713-16.29",11,null,null,null,null,null,null,null,"307-01.02","ASPHALT CEMENT (PG64-22) (BPMB-HM) GRADING A-S",1570582.7749999999,9.3463322919583758E-4,15,594.5220453660196]
[null,null,null,null,null,"713-16.30",11,null,null,null,null,null,null,null,"307-01.03","AGGREGATE (BPMB-HM) GRADING A-S MIX",3937379.4530000007,2.3430829188399393E-3,14,53.926929286914337]
[null,null,null,null,null,"713-16.31",10,null,null,null,null,null,null,null,"307-01.06","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING B",84170,5.0088464074371154E-5,1,110.75]
[null,null,null,null,null,"713-16.32",8,null,null,null,null,null,null,null,"307-01.07","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING B-M",40000,2.3803475858082999E-5,1,250]
[null,null,null,null,null,"713-16.50",15,null,null,null,null,null,null,null,"307-01.08","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING B-M2",26302489.509799998,1.5652266851350141E-2,94,78.122602460258392]
[null,null,null,null,null,"713-16.51",8,null,null,null,null,null,null,null,"307-01.15","ASC MIX (PG64-22) (BPMLC-HM) GRADING CS",152241.51,9.0596927697077548E-5,3,95.032153558052443]
[null,null,null,null,null,"713-30.09",11,null,null,null,null,null,null,null,"307-01.20","ASP. CONC. MIX(PG64-22) (BPMB-HM) GR. A-S",2796787.8,1.6643317719370265E-3,4,75.631785608047807]
[null,null,null,null,null,"714-03.01",17,null,null,null,null,null,null,null,"307-01.21","ASP. CONC. MIX(PG70-22) (BPMB-HM) GR. A-S",9567531.7916599996,5.6935128006055094E-3,13,65.944487667829009]
[null,null,null,null,null,"714-05.04",12,null,null,null,null,null,null,null,"307-01.22","ASP. CONC. MIX(PG76-22) (BPMB-HM) GR. A-S",1036413.7531200001,6.1675624378442796E-4,2,70.970215373667543]
[null,null,null,null,null,"714-05.05",8,null,null,null,null,null,null,null,"307-02.01","ASPHALT CONCRETE MIX (PG70-22) (BPMB-HM) GRADING A",43608355.77758,2.5950761099057997E-2,58,65.573574233564429]
[null,null,null,null,null,"714-06.06",9,null,null,null,null,null,null,null,"307-02.02","ASPHALT CEMENT (PG70-22)(BPMB-HM) GRADING A-S",6915254.2721800003,4.1151772030085495E-3,39,664.95169658662985]
[null,null,null,null,null,"714-06.08",10,null,null,null,null,null,null,null,"307-02.03","AGGREGATE (BPMB-HM) GRADING A-S MIX",14802797.400959998,8.8089507641461277E-3,39,49.95209773913129]
[null,null,null,null,null,"714-08.09",12,null,null,null,null,null,null,null,"307-02.08","ASPHALT CONCRETE MIX (PG70-22) (BPMB-HM) GRADING B-M2",31781410.635019999,1.8912701019663022E-2,59,72.932729904781397]
[null,null,null,null,null,"714-25",8,null,null,null,null,null,null,null,"307-03.01","ASPHALT CONCRETE MIX (PG76-22) (BPMB-HM) GRADING A",13844585.246159999,8.2387312668035402E-3,17,75.403285660907784]
[null,null,null,null,null,"716-01.05",15,null,null,null,null,null,null,null,"307-03.02","PERF. GRADE ASPH. CEMENT(PG76-22)GRADING AS",1594104.41,9.4863064596746604E-4,16,719.93428433102895]
[null,null,null,null,null,"716-01.06",8,null,null,null,null,null,null,null,"307-03.03","AGGREGATE(BPMB-HM) GRADING AS",3774099.3679000004,2.2459170797453493E-3,16,57.339217795157282]
[null,null,null,null,null,"716-01.07",16,null,null,null,null,null,null,null,"307-03.08","ASPHALT CONCRETE MIX (PG76-22) (BPMB-HM) GRADING B-M2",5806169.7223699996,3.4551755203591689E-3,18,78.376641268301626]
[null,null,null,null,null,"716-01.10",13,null,null,null,null,null,null,null,"307-03.10","ASPHALT CONC MIX (PG76-22)(BPMB-HM) GR CS",1384630.2220000001,8.2397530154372761E-4,5,84.45183968455737]
[null,null,null,null,null,"716-01.21",283,null,null,null,null,null,null,null,"307M01.01","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING A",561525.4,3.3415640756501001E-4,1,74.92]
[null,null,null,null,null,"716-01.22",172,null,null,null,null,null,null,null,"307M01.08","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING B-M2",1149177.9100000001,6.838607159331821E-4,1,82.090000000000018]
[null,null,null,null,null,"716-01.23",136,null,null,null,null,null,null,null,"307M01.15","ASC MIX (PG64-22) (BPMLC-HM) GRADING CS",17683.2,1.0523040607341333E-5,1,147.36000000000001]
[null,null,null,null,null,"716-01.30",116,null,null,null,null,null,null,null,"307M02.01","ASPHALT CONCRETE MIX (PG70-22) (BPMB-HM) GRADING A",1198116.54,7.1298345337649839E-4,1,67.02]
[null,null,null,null,null,"716-02.03",79,null,null,null,null,null,null,null,"307M02.02","ASPHALT CEMENT (PG70-22) (BPMB-HM) GRADING A-S",394662.24,2.3485832754842396E-4,1,707.28]
[null,null,null,null,null,"716-02.04",273,null,null,null,null,null,null,null,"307M02.03","AGGREGATE (BPMB-HM) GRADING A-S",817313.25,4.8637240537165887E-4,1,49.31]
[null,null,null,null,null,"716-02.05",369,null,null,null,null,null,null,null,"307M02.08","ASPHALT CONCRETE MIX (PG70-22) (BPMB-HM) GRADING B-M2",890030.34,5.2964539277878511E-4,1,76.11]
[null,null,null,null,null,"716-02.06",276,null,null,null,null,null,null,null,"309-01.01","MINERAL AGGREGATE (A-CBC)",3745516.9309999999,2.2289080460774907E-3,9,18.328301148221893]
[null,null,null,null,null,"716-02.07",58,null,null,null,null,null,null,null,"309-01.02","PORTLAND CEMENT (A-CBC)",2115676.3759200005,1.2590112884432066E-3,9,210.11999487530713]
[null,null,null,null,null,"716-02.08",43,null,null,null,null,null,null,null,"309-02","BITUMINOUS MATERIAL (A-CBC)",235165.93406,1.3994416585101871E-4,7,663.07430795691653]
[null,null,null,null,null,"716-02.09",54,null,null,null,null,null,null,null,"313-03","TREATED PERMEABLE BASE",6758768.181499999,4.022054380967869E-3,25,17.317026716415324]
[null,null,null,null,null,"716-02.11",12,null,null,null,null,null,null,null,"402-01","BITUMINOUS MATERIAL FOR PRIME COAT (PC)",6801956.285720001,4.0477550558717986E-3,107,570.81430731675027]
[null,null,null,null,null,"716-03.01",71,null,null,null,null,null,null,null,"402-02","AGGREGATE FOR COVER MATERIAL (PC)",1279099.42224,7.611753054344438E-4,95,31.411894758440059]
[null,null,null,null,null,"716-03.02",47,null,null,null,null,null,null,null,"402M01","BITUMINOUS MATERIAL FOR PRIME COAT (PC)",99458.849999999991,5.9186658371192455E-5,1,454.15]
[null,null,null,null,null,"716-03.03",47,null,null,null,null,null,null,null,"402M02","AGGREGATE FOR COVER MATERIAL (PC)",13079.04,7.783165322172547E-6,1,17.03]
[null,null,null,null,null,"716-03.06",18,null,null,null,null,null,null,null,"403-01","BITUMINOUS MATERIAL FOR TACK COAT (TC)",3878499.2344000009,2.3080440722908456E-3,108,657.79942929082995]
[null,null,null,null,null,"716-03.09",23,null,null,null,null,null,null,null,"403-02","ASPHALT CEMENT FOR TACK COAT (TC)",106440,6.3341049258358869E-5,2,704.9006622516556]
[null,null,null,null,null,"716-04.01",58,null,null,null,null,null,null,null,"403-02.02","HOT APPLIED TACK COAT",14420,8.5811530468389212E-6,1,2060]
[null,null,null,null,null,"716-04.02",33,null,null,null,null,null,null,null,"403M01","BITUMINOUS MATERIAL FOR TACK COAT (TC)",9805.6,5.8351840718504668E-6,1,700.4]
[null,null,null,null,null,"716-04.03",32,null,null,null,null,null,null,null,"404-01.01","BITUMINOUS MATERIAL (DBST)",22730.940000000002,1.352688453803833E-5,2,783.82551724137943]
[null,null,null,null,null,"716-04.04",27,null,null,null,null,null,null,null,"404-01.02","MINERAL AGGREGATE (DBST)",8584.93,5.1087793499583124E-6,2,37.986415929203538]
[null,null,null,null,null,"716-04.05",94,null,null,null,null,null,null,null,"405-01.01","BITUMINOUS MATERIAL (BSC)",16493.059999999998,9.8148038883978583E-6,1,970.17999999999984]
[null,null,null,null,null,"716-04.06",19,null,null,null,null,null,null,null,"405-01.02","MINERAL AGGREGATE (BSC)",15129.4,9.0033076911820239E-6,1,105.8]
[null,null,null,null,null,"716-04.07",20,null,null,null,null,null,null,null,"406-04.02","HIGH FRICTION SURFACE TREATMENT",95300.800000000003,5.6712257301399908E-5,2,44.45]
[null,null,null,null,null,"716-04.08",11,null,null,null,null,null,null,null,"407-02.12","REMOVAL & DISPOSAL OF EXISTING ASPHALT PAVEMENT",64712.480000000003,3.8509548884916976E-5,1,10.64]
[null,null,null,null,null,"716-04.12",52,null,null,null,null,null,null,null,"407-02.13","REMOVAL & DISPOSAL OF EXISTING ASPHALT PAVEMENT",218824.5,1.3021959257267709E-4,2,4.2611824041438666]
[null,null,null,null,null,"716-04.13",19,null,null,null,null,null,null,null,"407-20.05","SAW CUTTING ASPHALT PAVEMENT",489986.92000000004,2.915847955249112E-4,23,2.7534161253343528]
[null,null,null,null,null,"716-04.14",77,null,null,null,null,null,null,null,"411-01.07","ACS MIX (PG64-22) GRADING E SHOULDER",8240602.1117199995,4.9038743355598697E-3,74,88.647251228833838]
[null,null,null,null,null,"716-04.15",17,null,null,null,null,null,null,null,"411-01.10","ACS MIX(PG64-22) GRADING D",18569858.83774,1.1050679663303833E-2,85,97.206311955538112]
[null,null,null,null,null,"716-04.16",8,null,null,null,null,null,null,null,"411-02.10","ACS MIX(PG70-22) GRADING D",24691880.617890004,1.4693814604465307E-2,59,90.7573192312543]
[null,null,null,null,null,"716-05.01",338,null,null,null,null,null,null,null,"411-02.11","ACS MIX(PG70-22) GRADING E RWDY",17820,1.0604448494775976E-5,1,165]
[null,null,null,null,null,"716-05.02",58,null,null,null,null,null,null,null,"411-03.07","ACS MIX(PG64-22) THIN LIFT CS ASPHALT",141075.9,8.3952419495183286E-5,1,95.97]
[null,null,null,null,null,"716-05.04",11,null,null,null,null,null,null,null,"411-03.10","ACS MIX(PG76-22) GRADING D",5879957.04,3.4990853862051294E-3,15,103.93391027680559]
[null,null,null,null,null,"716-05.05",41,null,null,null,null,null,null,null,"411-03.15","ASP CEM(PG76-22)FOR OGFC MIX",437384.75,2.6028193343296673E-4,2,869.55218687872764]
[null,null,null,null,null,"716-05.06",16,null,null,null,null,null,null,null,"411-03.16","AGGREGATE FOR OGFC MIX",386305.75,2.2988548984909118E-4,2,49.148314249363871]
[null,null,null,null,null,"716-05.08",9,null,null,null,null,null,null,null,"411-03.22","ACS MIX (PG70-22) OGFC",131986.65000000002,7.8543525921606283E-5,1,131.33000000000001]
[null,null,null,null,null,"716-05.20",65,null,null,null,null,null,null,null,"411-03.23","ACS MIX (PG76-22) OGFC",2289191.1743899998,1.3622676713532257E-3,5,103.48340041065329]
[null,null,null,null,null,"716-05.49",23,null,null,null,null,null,null,null,"411-12.01","SCORING SHOULDERS (CONTINUOUS) (16IN WIDTH)",188675.66949999999,1.1227841859877242E-4,31,1318.5251125118803]
[null,null,null,null,null,"716-08.01",29,null,null,null,null,null,null,null,"411-12.02","SCORING SHOULDERS (NON-CONTINUOUS) (16IN WIDTH)",102267.28640000001,6.0857922072351507E-5,26,1243.7795555987987]
[null,null,null,null,null,"716-08.04",10,null,null,null,null,null,null,null,"411-12.03","SCORING FOR RUMBLE STRIPE (NON-CONTINUOUS) (8IN WIDTH)",96304.695000000007,5.7309662061313666E-5,21,1901.3760118460018]
[null,null,null,null,null,"716-08.05",8,null,null,null,null,null,null,null,"411-12.04","SCORING FOR RUMBLE STRIPE (NON-CONTINUOUS) (4IN WIDTH)",7996.74,4.7587551883341661E-6,2,4979.2901618929018]
[null,null,null,null,null,"716-08.20",9,null,null,null,null,null,null,null,"411-33.34","STAMPED ASPHALT PATTERN",74920,4.4583910282189459E-5,1,20]
[null,null,null,null,null,"716-08.30",11,null,null,null,null,null,null,null,"411M01.07","ASPHALT CONCRETE MIX (PG64-22) (ACS) GRADING E (SHOULDER)",176482.07,1.0502216731573786E-4,1,111.91000000000001]
[null,null,null,null,null,"716-10.30",23,null,null,null,null,null,null,null,"411M01.10","ACS MIX(PG64-22) GRADING D",568686.56000000006,3.3841792004440674E-4,1,108.28000000000002]
[null,null,null,null,null,"716-12.01",69,null,null,null,null,null,null,null,"411M02.10","ACS MIX(PG70-22) GRADING D",733674.15,4.3659987293061416E-4,1,101.97]
[null,null,null,null,null,"716-12.02",272,null,null,null,null,null,null,null,"411M12.01","SCORING SHOULDERS (CONT 16IN WIDTH)",5500,3.2729779304864125E-6,1,5000]
[null,null,null,null,null,"716-12.03",107,null,null,null,null,null,null,null,"415-01.01","COLD PLANING BITUMINOUS PAVEMENT",1819045.095,1.08248990008992E-3,31,19.919245013407981]
[null,null,null,null,null,"716-12.04",23,null,null,null,null,null,null,null,"415-01.02","COLD PLANING BITUMINOUS PAVEMENT",1759388.0700000003,1.0469887862311063E-3,50,2.4192375238742168]
[null,null,null,null,null,"716-12.05",122,null,null,null,null,null,null,null,"415-01.03","COLD PLANING BITUMINOUS PAVEMENT",38648.050000000003,2.299894812842462E-5,2,35.752127659574469]
[null,null,null,null,null,"716-12.10",10,null,null,null,null,null,null,null,"415M01.02","COLD PLANING BITUMINOUS PAVEMENT",9100,5.4152907577138826E-6,1,1.82]
[null,null,null,null,null,"716-13.01",146,null,null,null,null,null,null,null,"501-01","PORTLAND CEMENT CONCRETE PAVEMENT(REPLACEMENT)",61100,3.635980937322178E-5,1,65]
[null,null,null,null,null,"716-13.02",87,null,null,null,null,null,null,null,"501-01.01","PORTLAND CEMENT CONCRETE PAVEMENT (PLAIN) 8\"",55327,3.2924372720003954E-5,1,61]
[null,null,null,null,null,"716-13.03",25,null,null,null,null,null,null,null,"501-01.02","PORTLAND CEMENT CONCRETE PAVEMENT (PLAIN) 9\"",40715,2.4228962989046234E-5,1,85]
[null,null,null,null,null,"716-13.04",22,null,null,null,null,null,null,null,"501-01.03","PORTLAND CEMENT CONCRETE PAVEMENT (PLAIN) 10\"",24828100.408679999,1.4774877217001875E-2,23,68.957283131915815]
[null,null,null,null,null,"716-13.05",22,null,null,null,null,null,null,null,"501-01.04","PORTLAND CEMENT CONCRETE PAVEMENT (PLAIN) 11\"",1049172,6.2434850932441646E-4,2,56.816419365320044]
[null,null,null,null,null,"716-13.06",24,null,null,null,null,null,null,null,"501-03.10","CONCRETE SHOULDER RUMBLE STRIPS",210.41,1.2521223388248109E-7,1,0.53]
[null,null,null,null,null,"717-01",439,null,null,null,null,null,null,null,"501-04.03","ROLLER COMPACTED CONCRETE PAVEMENT(DEPTH)",45646.54,2.7163657822375501E-5,1,36.17]
[null,null,null,null,null,"730-01.02",30,null,null,null,null,null,null,null,"502-03.01","CEMENT GROUTING",11780,7.0101236402054438E-6,2,10.051194539249147]
[null,null,null,null,null,"730-02.09",44,null,null,null,null,null,null,null,"502-03.13","CONCRETE PAVEMENT REMOVAL",73785,4.3908486654716356E-5,2,25.575389948006933]
[null,null,null,null,null,"730-02.17",41,null,null,null,null,null,null,null,"502-04.01","SAWING CONCRETE PAVEMENT (FULL DEPTH)",4735.74,2.8181768190039496E-6,5,4.9125933609958503]
[null,null,null,null,null,"730-02.30",28,null,null,null,null,null,null,null,"502-04.03","TRANSVERSE TIE-BARS",4736,2.8183315415970271E-6,2,13.119113573407203]
[null,null,null,null,null,"730-02.31",16,null,null,null,null,null,null,null,"502-08.01","RESEALING JOINTS (HOT POURED ELASTIC)",7250.25,4.314528771001657E-6,2,1.6058139534883722]
[null,null,null,null,null,"730-03.20",50,null,null,null,null,null,null,null,"502-08.02","RESEALING JOINTS (SILICONE SEALANT)",8667.6,5.1579751836880058E-6,1,9.32]
[null,null,null,null,null,"730-03.21",46,null,null,null,null,null,null,null,"502-25","SAWING CONCRETE JOINTS",665,3.9573278614062987E-7,1,1.33]
[null,null,null,null,null,"730-03.23",18,null,null,null,null,null,null,null,"503-01.01","MILLING CONCRETE PAVEMENT",115659.84,6.882765522974356E-5,1,7.46]
[null,null,null,null,null,"730-03.24",18,null,null,null,null,null,null,null,"504-01","CRACKING & SEATING CONCRETE PAVEMENT",45012,2.6786051383100798E-5,1,3.72]
[null,null,null,null,null,"730-05.01",44,null,null,null,null,null,null,null,"602-01","STRUCTURAL STEEL",13421.34,7.9868635668280923E-6,4,1.5917148956356737]
[null,null,null,null,null,"730-05.02",11,null,null,null,null,null,null,null,"602-02.01","STRUCTURAL STEEL (WALL 13 SOLDIER PILES)",80487.900000000009,4.7897294612944974E-5,1,0.90000000000000013]
[null,null,null,null,null,"730-08.01",22,null,null,null,null,null,null,null,"602-02.10","STRUCTURAL STEEL (INSTALLATION OF SOLDIER PILES)",26000,1.547225930775395E-5,1,26000]
[null,null,null,null,null,"730-08.02",33,null,null,null,null,null,null,null,"602-03","STEEL STRUCTURES",71000,4.2251169648097327E-5,1,71000]
[null,null,null,null,null,"730-08.03",39,null,null,null,null,null,null,null,"602-04.01","STEEL STRUCTURES (BRIDGE NO. 1)",21693558.48,1.2909552388864794E-2,6,3615593.08]
[null,null,null,null,null,"730-08.40",18,null,null,null,null,null,null,null,"602-04.02","STEEL STRUCTURES (BRIDGE NO. 2)",5860008.8499999996,3.4872144797281927E-3,5,1172001.77]
[null,null,null,null,null,"730-09.01",25,null,null,null,null,null,null,null,"602-04.03","STEEL STRUCTURES (BRIDGE NO. 4)",252834.43,1.5045845626492939E-4,1,252834.43]
[null,null,null,null,null,"730-10.01",22,null,null,null,null,null,null,null,"602-04.98","STEEL STRUCTURES (WB POPLAR, MATERIAL ONLY, 1,228,215 LBS .)",1271916,7.5690054498773747E-4,1,1271916]
[null,null,null,null,null,"730-12.01",55,null,null,null,null,null,null,null,"602-04.99","STEEL STRUCTURES (EB POPLAR, MATERIAL ONLY, 573,770 LBS.)",600000,3.5705213787124497E-4,1,600000]
[null,null,null,null,null,"730-12.02",60,null,null,null,null,null,null,null,"602-10.05","BRACING REPAIRS",0.01,5.9508689645207504E-12,1,0.01]
[null,null,null,null,null,"730-12.03",20,null,null,null,null,null,null,null,"602-10.17","STEEL PILING",127125,7.5650421711470034E-5,1,125]
[null,null,null,null,null,"730-12.07",12,null,null,null,null,null,null,null,"602-10.60","BEARING DEVICE (DESCRIPTION)",439700,2.6165970836997739E-4,3,5941.8918918918916]
[null,null,null,null,null,"730-12.08",14,null,null,null,null,null,null,null,"602-10.61","BEARING DEVICE (LR SEISMIC ISOLATION BEARING, BENT NO. 1 & 2)",365800,2.1768278672216904E-4,2,4943.2432432432433]
[null,null,null,null,null,"730-12.09",9,null,null,null,null,null,null,null,"602M04.01","STEEL STRUCTURES (BRIDGE NO. 1)",1331154.6000000001,7.9215265961190336E-4,1,1331154.6000000001]
[null,null,null,null,null,"730-12.13",14,null,null,null,null,null,null,null,"603-01","PAINT STEEL STRUCTURE",72000,4.2846256544549401E-5,1,72000]
[null,null,null,null,null,"730-12.14",10,null,null,null,null,null,null,null,"603-02.20","SPOT PAINTING EXISTING STEEL STRUCTURES",37800,2.2494284685888434E-5,1,9]
[null,null,null,null,null,"730-12.16",10,null,null,null,null,null,null,null,"604-01.01","CLASS A CONCRETE (ROADWAY)",13151870.8586,7.826506011782761E-3,55,577.8116503823843]
[null,null,null,null,null,"730-13.01",9,null,null,null,null,null,null,null,"604-01.02","STEEL BAR REINFORCEMENT (ROADWAY)",3911708.8816000009,2.3278066981753617E-3,42,0.86884344729392948]
[null,null,null,null,null,"730-13.02",10,null,null,null,null,null,null,null,"604-01.04","1-1/2\" STEEL PIPE HANDRAIL",237936,1.4159259579422091E-4,5,121.08702290076336]
[null,null,null,null,null,"730-13.03",21,null,null,null,null,null,null,null,"604-01.20","BOX TUBE SAFETY RAIL",630122.75,3.7497779168134675E-4,7,140.52692908117751]
[null,null,null,null,null,"730-13.07",11,null,null,null,null,null,null,null,"604-02.01","CLASS A CONCRETE (BOX BRIDGES)",12831411.059399998,7.6358045844391762E-3,27,491.00338343338547]
[null,null,null,null,null,"730-13.08",19,null,null,null,null,null,null,null,"604-02.02","STEEL BAR REINFORCEMENT (BOX BRIDGES)",3496616.25,2.0807905122963927E-3,26,0.84362048449445026]
[null,null,null,null,null,"730-14.01",54,null,null,null,null,null,null,null,"604-02.03","EPOXY COATED REINFORCING STEEL",10221970.450000003,6.0829606707153219E-3,38,0.92916276484442262]
[null,null,null,null,null,"730-14.02",149,null,null,null,null,null,null,null,"604-02.10","REINFORCEMENT STEEL (ASTM A706)",52364.4,3.1161368280575038E-5,1,1.1000000000000001]
[null,null,null,null,null,"730-14.03",149,null,null,null,null,null,null,null,"604-02.41","ENERGY DISSIPATER (USBR TYPE VI IMPACT BASIN)",118394.93,7.0455271449360659E-5,6,16913.561428571429]
[null,null,null,null,null,"730-15.32",39,null,null,null,null,null,null,null,"604-02.42","ENERGY DISSIPATER (STA. 164+14.50 LT.)",146994.93,8.747475668789001E-5,5,29398.985999999997]
[null,null,null,null,null,"730-16.02",44,null,null,null,null,null,null,null,"604-02.43","ENERGY DISSIPATER (STA. 191+50.00 LT.)",29394.93,1.7492537665125991E-5,2,7348.7325000000001]
[null,null,null,null,null,"730-18.01",17,null,null,null,null,null,null,null,"604-02.44","ENERGY DISSIPATER (STA. 216+35.00 LT.)",33294.93,1.9813376561289086E-5,2,8323.7325000000001]
[null,null,null,null,null,"730-23.01",21,null,null,null,null,null,null,null,"604-02.45","ENERGY DISSIPATER (TYPE USBR VI, 42\" PIPE)",9900,5.8913602748755421E-6,1,9900]
[null,null,null,null,null,"730-23.02",14,null,null,null,null,null,null,null,"604-02.46","ENERGY DISSIPATER (TYPE USBR VI, 48\" PIPE)",10800,6.4269384816824099E-6,1,10800]
[null,null,null,null,null,"730-23.30",19,null,null,null,null,null,null,null,"604-02.48","ENERGY DISSIPATER (TYPE USBR VI, 60\" PIPE)",15300,9.1048295157167475E-6,1,15300]
[null,null,null,null,null,"730-23.36",18,null,null,null,null,null,null,null,"604-03.01","CLASS A CONCRETE (BRIDGES)",22436971.809999999,1.3351947920195594E-2,35,630.28742654081702]
[null,null,null,null,null,"730-23.37",15,null,null,null,null,null,null,null,"604-03.02","STEEL BAR REINFORCEMENT (BRIDGES)",7036137.9399999995,4.1871134897232959E-3,37,0.98296963610998644]
[null,null,null,null,null,"730-23.38",12,null,null,null,null,null,null,null,"604-03.04","PAVEMENT @ BRIDGE ENDS",5165700.3600000003,3.0740405952337669E-3,30,231.69770621215517]
[null,null,null,null,null,"730-23.39",8,null,null,null,null,null,null,null,"604-03.07","CLASS A CONCRETE (DESCRIPTION)",1074250,6.3927209851364155E-4,3,597.13729849916615]
[null,null,null,null,null,"730-23.96",14,null,null,null,null,null,null,null,"604-03.08","CLASS A CONCRETE (SOLDIER PILE FOOTING)",182000,1.0830581515427766E-4,1,520]
[null,null,null,null,null,"730-23.97",13,null,null,null,null,null,null,null,"604-03.09","CLASS D CONCRETE (BRIDGE DECK)",12966635.970000001,7.7162751568111412E-3,26,562.32429723752114]
[null,null,null,null,null,"730-26.05",15,null,null,null,null,null,null,null,"604-03.25","CLASS S CONCRETE (FOUNDATION SEAL)",168063.75,1.0001253539359742E-4,2,293.81774475524475]
[null,null,null,null,null,"730-26.11",9,null,null,null,null,null,null,null,"604-03.30","CLASS D CONCRETE",109632.31999999999,6.5240757059640745E-5,1,921.28]
[null,null,null,null,null,"730-35.06",10,null,null,null,null,null,null,null,"604-03.32","CLASS DS CONCRETE",6865860,4.0857833188744433E-3,7,740.57383238054149]
[null,null,null,null,null,"730-40",22,null,null,null,null,null,null,null,"604-03.35","CLASS L CONCRETE",215180,1.2805079837855749E-4,1,530]
[null,null,null,null,null,"740-06.01",15,null,null,null,null,null,null,null,"604-03.40","SEISMIC MODIFICATION (STEEL RESTRAINER ASSEMBLY)",84000,4.9987299301974299E-5,1,420]
[null,null,null,null,null,"740-10.03",100,null,null,null,null,null,null,null,"604-03.74","CLASS X CONCRETE",106250,6.3227982748032972E-5,1,1250]
[null,null,null,null,null,"740-10.04",57,null,null,null,null,null,null,null,"604-04.01","APPLIED TEXTURE FINISH (NEW STRUCTURES)",1019297.83,6.0657078221503468E-4,35,7.7371931835433436]
[null,null,null,null,null,"740-11.01",17,null,null,null,null,null,null,null,"604-04.02","APPLIED TEXTURE FINISH (EXISTING STRUCTURES)",88064.540000000008,5.2406053796079624E-5,7,9.3825420839548279]
[null,null,null,null,null,"740-11.02",25,null,null,null,null,null,null,null,"604-04.03","BRIDGE END DRAINS(2'X8')",24000,1.4282085514849799E-5,1,12000]
[null,null,null,null,null,"740-11.03",40,null,null,null,null,null,null,null,"604-04.04","BRIDGE END DRAINS(4'X8')",1500,8.9263034467811245E-7,1,750]
[null,null,null,null,null,"740-11.04",24,null,null,null,null,null,null,null,"604-04.41","THREE STAR STATE EMBLEM",69030,4.1078848462086737E-5,8,1278.3333333333333]
[null,null,null,null,null,"790-02.04",8,null,null,null,null,null,null,null,"604-04.62","CLEAN & TEXTURE FINISH CONCRETE MEDIAN BARRIER",93015.45,5.535227546259316E-5,2,7.3774944479695428]
[null,null,null,null,null,"790-03.03",15,null,null,null,null,null,null,null,"604-05.31","BRIDGE DECK GROOVING (MECHANICAL)",467570.8,2.7824525624361388E-4,30,3.6239337172442121]
[null,null,null,null,null,"790-04.02",8,null,null,null,null,null,null,null,"604-07.01","RETAINING WALL (WALL #1)",8883492.209999999,5.2864498089050839E-3,28,81.624986998428781]
[null,null,null,null,null,"790-04.03",13,null,null,null,null,null,null,null,"604-07.02","RETAINING WALL (WALL NO. 2)",6148464.8099999996,3.6588708417276969E-3,18,95.617075564126097]
[null,null,null,null,null,"790-04.07",9,null,null,null,null,null,null,null,"604-07.03","RETAINING WALL (WALL NO. 3)",3274040.54,1.9483386238068757E-3,11,90.333311444652907]
[null,null,null,null,null,"790-05.02",17,null,null,null,null,null,null,null,"604-07.04","RETAINING WALL (WALL NO. 4)",3231462.76,1.9230011448488564E-3,11,94.858884518288022]
[null,null,null,null,null,"790-05.06",8,null,null,null,null,null,null,null,"604-07.05","RETAINING WALL (WALL NO. 5)",6677892.3400000008,3.9739262274516851E-3,10,91.536911984428329]
[null,null,null,null,null,"790-06.02",8,null,null,null,null,null,null,null,"604-07.06","RETAINING WALL (WALL NO. 6)",6739079.2000000002,4.0103377260727324E-3,7,106.53323216035916]
[null,null,null,null,null,"790-20.01",15,null,null,null,null,null,null,null,"604-07.07","RETAINING WALL (HAMLET DRIVE)",11007402.699999999,6.5503611107411907E-3,6,126.85431590835752]
[null,null,null,null,null,"790-21.07",9,null,null,null,null,null,null,null,"604-07.08","RETAINING WALL (WALL NO. 6)",1210857.75,7.2056558049244247E-4,5,86.675572655690772]
[null,null,null,null,null,"790-21.08",14,null,null,null,null,null,null,null,"604-07.09","RETAINING WALL (WALL NO. 7)",3864375.6399999997,2.2996393063326008E-3,5,91.63368206392866]
[null,null,null,null,null,"790-21.09",14,null,null,null,null,null,null,null,"604-07.10","RETAINING WALL (WALL NO. 8)",2021390.64,1.2029030824748735E-3,5,79.369822522381028]
[null,null,null,null,null,"790-21.10",10,null,null,null,null,null,null,null,"604-07.11","RETAINING WALL (WALL NO. 1)",3319280,1.9752600336554434E-3,4,86.246427272254849]
[null,null,null,null,null,"790-25.01",10,null,null,null,null,null,null,null,"604-07.12","RETAINING WALL (WALL NO. 2)",2157250,1.2837512073712387E-3,2,81.026517427884613]
[null,null,null,null,null,"790-25.10",9,null,null,null,null,null,null,null,"604-07.13","RETAINING WALL (WALL NO. 3)",9301199,5.5350216461931435E-3,2,100.51546982222942]
[null,null,null,null,null,"790-25.21",15,null,null,null,null,null,null,null,"604-07.14","RETAINING WALL (WALL NO. 4)",985920,5.8670807295002983E-4,2,79.400821454457599]
[null,null,null,null,null,"790-25.23",13,null,null,null,null,null,null,null,"604-07.15","RETAINING WALL (NO. 15)",581100,3.4580499552830076E-4,1,130]
[null,null,null,null,null,"790-30.03",12,null,null,null,null,null,null,null,"604-07.16","RETAINING WALL (NO. 16)",243960,1.4517739925844821E-4,1,95]
[null,null,null,null,null,"790-30.04",9,null,null,null,null,null,null,null,"604-07.17","RETAINING WALL (NO. 17)",489000,2.9099749236506466E-4,1,100]
[null,null,null,null,null,"790-30.06",11,null,null,null,null,null,null,null,"604-07.18","RETAINING WALL (NO. 18)",761880,4.533848046689069E-4,1,105]
[null,null,null,null,null,"790-31.02",15,null,null,null,null,null,null,null,"604-07.19","RETAINING WALL (NO. 19)",1035975,6.1649514755193844E-4,1,95]
[null,null,null,null,null,"790-31.11",8,null,null,null,null,null,null,null,"604-07.20","RETAINING WALL (NO. 20)",265250,1.5784679928391291E-4,1,125]
[null,null,null,null,null,"790-32.01",18,null,null,null,null,null,null,null,"604-07.21","RETAINING WALL (NO. 21)",287840,1.7128981227476528E-4,1,80]
[null,null,null,null,null,"790-32.02",10,null,null,null,null,null,null,null,"604-09.10","CLASS A CONCRETE (RETAINING WALLS)",552240,3.286307876966939E-4,1,720]
[null,null,null,null,null,"790-32.07",19,null,null,null,null,null,null,null,"604-10.05","CONCRETE",1024,6.0936898196692482E-7,1,256]
[null,null,null,null,null,"790-32.23",17,null,null,null,null,null,null,null,"604-10.07","CONCRETE REMOVAL",10000,5.9508689645207496E-6,1,10000]
[null,null,null,null,null,"790-33.04",11,null,null,null,null,null,null,null,"604-10.14","REMOVE EXISTING WEARING SURFACE",62000,3.689538758002865E-5,1,62000]
[null,null,null,null,null,"790-33.20",9,null,null,null,null,null,null,null,"604-10.20","HYDRODEMOLITION",95017.5,5.6543669183635036E-5,1,22.5]
[null,null,null,null,null,"790-40.02",12,null,null,null,null,null,null,null,"604-10.29","CONCRETE SLOPE PAVING REPAIRS",57480,3.4205594808065271E-5,1,120]
[null,null,null,null,null,"790-40.03",17,null,null,null,null,null,null,null,"604-10.30","BRIDGE DECK REPAIRS (FULL DEPTH OF SLAB)",18790,1.1181682784334488E-5,3,313.16666666666669]
[null,null,null,null,null,"790-40.05",12,null,null,null,null,null,null,null,"604-10.34","CONCRETE OVERLAYED BRIDGE DECK REPAIR (FULL DEPTH)",21000,1.2496824825493575E-5,1,700]
[null,null,null,null,null,"790-40.09",9,null,null,null,null,null,null,null,"604-10.39","PRECAST REINFORCED CONCRETE UNITS",45415,2.7025871402370986E-5,1,31]
[null,null,null,null,null,"790-40.49",12,null,null,null,null,null,null,null,"604-10.43","PENETRATING WATER REPELLENT CONCRETE SEAL",18000,1.071156413613735E-5,1,25]
[null,null,null,null,null,"790-46.01",19,null,null,null,null,null,null,null,"604-10.44","EXPANSION JOINT REPAIRS",28800,1.7138502617819761E-5,1,200]
[null,null,null,null,null,"790-46.03",9,null,null,null,null,null,null,null,"604-10.50","BRIDGE DECK REPAIRS (PARTIAL DEPTH OF SLAB)",51125,3.0423817581112335E-5,2,329.83870967741933]
[null,null,null,null,null,"790-58.06",8,null,null,null,null,null,null,null,"604-10.51","SCARIFYING",89169.65,5.3063690276217767E-5,7,6.0954029667099592]
[null,null,null,null,null,"790-60.02",8,null,null,null,null,null,null,null,"604-10.54","CONCRETE REPAIRS",19435,1.1565513832546077E-5,3,150.65891472868216]
[null,null,null,null,null,"790-68.01",19,null,null,null,null,null,null,null,"604-10.56","CONCRETE OVERLAYED BRIDGE DECK REPAIR (PARTIAL DEPTH)",12200,7.2600601367153146E-6,1,244]
[null,null,null,null,null,"790-68.10",16,null,null,null,null,null,null,null,"604-10.67","CONCRETE REPAIRS (SR 11 EXISTING SIDEWALK)",3150,1.8745237238240362E-6,2,7.875]
[null,null,null,null,null,"790-69.28",8,null,null,null,null,null,null,null,"604-10.90","MISCELLANEOUS BRIDGE ITEMS",50000,2.9754344822603749E-5,1,50000]
[null,null,null,null,null,"790-70.20",13,null,null,null,null,null,null,null,"604-11.01","EXPANSION DEVICE (@ ABUTMENT NOS. 1, 2, & 4)",53862.57,3.2052909616232641E-5,2,398.98199999999997]
[null,null,null,null,null,"790-98.01",26,null,null,null,null,null,null,null,"604-11.02","EXPANSION DEVICE (PIER NO. 3, 10\" MOVEMENT)",192000,1.1425668411879839E-4,1,2000]
[null,null,null,null,null,"790-98.02",27,null,null,null,null,null,null,null,"604-12.01","CONCRETE IMPRINTING",30522.41,1.8163486239137779E-5,2,6.2971755725190839]
[null,null,null,null,null,"790-98.03",26,null,null,null,null,null,null,null,"604-12.03","CONCRETE PIGMENT",625.95000000000005,3.7249464283417639E-7,1,3.2100000000000004]
[null,null,null,null,null,"791-01.02",14,null,null,null,null,null,null,null,"604-12.04","STONE VENEER FINISH",139642.07,8.3099166050443413E-5,2,29.232168725141303]
[null,null,null,null,null,"791-01.05",8,null,null,null,null,null,null,null,"604-12.15","DRILL & GROUT STEEL BARS",113316,6.7432866758363326E-5,1,38]
[null,null,null,null,null,"791-02.02",8,null,null,null,null,null,null,null,"604-15.01","PORTLAND CEMENT GROUT",74231.850000000006,4.4174401234395969E-5,6,208.51643258426967]
[null,null,null,null,null,"791-02.04",8,null,null,null,null,null,null,null,"604-15.20","COMPACTION GROUT",92052,5.4778938992206407E-5,1,51.14]
[null,null,null,null,null,"791-06.02",13,null,null,null,null,null,null,null,"604-20.11","PAINTED METAL HANDRAIL",68090.880000000005,4.0519990455890667E-5,1,218.24]
[null,null,null,null,null,"791-06.03",10,null,null,null,null,null,null,null,"604-36","SCARIFYING",5437.2,3.2356064733892219E-6,1,9.1999999999999993]
[null,null,null,null,null,"791-06.31",11,null,null,null,null,null,null,null,"604-36.10","BRIDGE DECK REPAIRS",3000,1.7852606893562249E-6,1,1000]
[null,null,null,null,null,"791-07.01",10,null,null,null,null,null,null,null,"604-50.10","MECHANICAL COUPLER",69564,4.1396624864792147E-5,1,93]
[null,null,null,null,null,"791-07.02",8,null,null,null,null,null,null,null,"604M01.01","CLASS A CONCRETE (ROADWAY)",226303.6,1.346703069799318E-4,1,689.95]
[null,null,null,null,null,"791-07.03",9,null,null,null,null,null,null,null,"604M01.02","STEEL BAR REINFORCEMENT (ROADWAY)",56184.479999999996,3.3434647831973679E-5,1,1.44]
[null,null,null,null,null,"791-07.09",11,null,null,null,null,null,null,null,"604M02.01","CLASS A CONCRETE (BOX BRIDGES)",238862.24,1.4214378908119067E-4,1,878.17]
[null,null,null,null,null,"791-08.02",10,null,null,null,null,null,null,null,"604M02.02","STEEL BAR REINFORCEMENT (BOX BRIDGES)",56184.479999999996,3.3434647831973679E-5,1,1.44]
[null,null,null,null,null,"791-10.04",8,null,null,null,null,null,null,null,"604M02.03","EPOXY COATED REINFORCING STEEL",358417.5,2.1328955770911158E-4,1,1.75]
[null,null,null,null,null,"793-01.40",8,null,null,null,null,null,null,null,"604M03.01","CLASS A CONCRETE (BRIDGES)",548638.36,3.2648749892695626E-4,1,792.82999999999993]
[null,null,null,null,null,"793-01.41",15,null,null,null,null,null,null,null,"604M03.02","STEEL BAR REINFORCEMENT (BRIDGES)",95816.16,5.7018941284355455E-5,1,1.44]
[null,null,null,null,null,"793-07.16",8,null,null,null,null,null,null,null,"604M03.04","PAVEMENT @ BRIDGE ENDS",195117.86000000002,1.1611208174977048E-4,1,275.98]
[null,null,null,null,null,"793-13.07",11,null,null,null,null,null,null,null,"604M03.09","CLASS D CONCRETE (BRIDGE DECK)",725049.4,4.314673972204391E-4,1,777.95]
[null,null,null,null,null,"793-98.01",9,null,null,null,null,null,null,null,"604M04.01","APPLIED TEXTURE FINISH (NEW STRUCTURES)",57455.619999999995,3.4191086589529768E-5,1,8.93]
[null,null,null,null,null,"793-98.04",19,null,null,null,null,null,null,null,"604M05.31","BRIDGE DECK GROOVING (MECHANICAL)",12213.5,7.2680938098174179E-6,1,3.25]
[null,null,null,null,null,"793-98.06",11,null,null,null,null,null,null,null,"604M07.01","RETAINING WALL (WALL NO. 1)",95718.33,5.6960723933275546E-5,1,625.61]
[null,null,null,null,null,"793-98.08",13,null,null,null,null,null,null,null,"604M07.02","RETAINING WALL (WALL NO. 2)",126402.1,7.5220233394024838E-5,1,837.1]
[null,null,null,null,null,"795-01.03",10,null,null,null,null,null,null,null,"604M07.03","RETAINING WALL (WALL NO. 3)",29045.1,1.7284358416140164E-5,1,968.17]
[null,null,null,null,null,"795-01.04",14,null,null,null,null,null,null,null,"604M07.04","RETAINING WALL (WALL NO. 4)",28089,1.6715395834442333E-5,1,1123.56]
[null,null,null,null,null,"795-01.05",15,null,null,null,null,null,null,null,"604M07.05","RETAINING WALL (WALL NO. 5)",449969.14,2.6777073902180926E-4,1,1335.22]
[null,null,null,null,null,"795-01.06",14,null,null,null,null,null,null,null,"604M07.06","RETAINING WALL (WALL NO. 6)",52466.920000000006,3.1222376589199305E-5,1,1192.43]
[null,null,null,null,null,"795-01.09",11,null,null,null,null,null,null,null,"604M07.07","RETAINING WALL (WALL NO. 7)",1013563.6499999999,6.0315844683513716E-4,1,617.65]
[null,null,null,null,null,"795-01.10",14,null,null,null,null,null,null,null,"604M07.08","RETAINING WALL (WALL NO. 8)",3022500.1500000004,1.7986502337894313E-3,1,419.85000000000008]
[null,null,null,null,null,"795-03.02",15,null,null,null,null,null,null,null,"604M07.09","RETAINING WALL (WALL NO. 9)",767707.20000000007,4.5685249503191248E-4,1,1845.4500000000003]
[null,null,null,null,null,"795-03.05",12,null,null,null,null,null,null,null,"604M07.10","RETAINING WALL (WALL NO. 10)",127022.39999999999,7.5589365795894047E-5,1,1411.36]
[null,null,null,null,null,"795-03.06",12,null,null,null,null,null,null,null,"604M36","SCARIFYING",14895,8.8638193226536572E-6,1,29.79]
[null,null,null,null,null,"795-03.08",10,null,null,null,null,null,null,null,"605-03","WATERPROOFING RAILROAD BRIDGE DECK",113500,6.7542362747310513E-5,1,10]
[null,null,null,null,null,"795-05.63",8,null,null,null,null,null,null,null,"605-05","DAMPPROOFING (RAILROAD STRUCTURES)",58300,3.4693566063155972E-5,1,10]
[null,null,null,null,null,"795-05.65",13,null,null,null,null,null,null,null,"606-02.01","TEST PILES (STEEL PILES, 10 INCH)",45250,2.6927682064456392E-5,1,250]
[null,null,null,null,null,"795-06.01",14,null,null,null,null,null,null,null,"606-02.02","LOADING TEST (STEEL PILES, 10 INCH)",17400,1.0354511998266105E-5,1,5800]
[null,null,null,null,null,"795-06.03",9,null,null,null,null,null,null,null,"606-02.03","STEEL PILES (10 INCH)",1930865.0600000003,1.1490324960231498E-3,24,44.980200340112283]
[null,null,null,null,null,"795-06.04",20,null,null,null,null,null,null,null,"606-02.06","PILE TIPS (STEEL PILES, 10 INCH)",198355.69,1.1803887195570989E-4,22,128.05402840542286]
[null,null,null,null,null,"795-06.05",15,null,null,null,null,null,null,null,"606-03.01","TEST PILES (STEEL PILES, 12 INCH)",76000,4.5226604130357702E-5,1,200]
[null,null,null,null,null,"795-06.06",9,null,null,null,null,null,null,null,"606-03.02","LOADING TEST (STEEL PILES, 12 INCH)",17400,1.0354511998266105E-5,1,5800]
[null,null,null,null,null,"795-06.07",14,null,null,null,null,null,null,null,"606-03.03","STEEL PILES (12 INCH)",1949288.6400000001,1.1599961270668863E-3,7,56.520779401530973]
[null,null,null,null,null,"795-07.03",19,null,null,null,null,null,null,null,"606-03.06","PILE TIPS (STEEL PILES, 12 INCH)",75870.399999999994,4.5149480868577505E-5,7,109.32334293948126]
[null,null,null,null,null,"795-07.06",12,null,null,null,null,null,null,null,"606-04.01","TEST PILES (STEEL PILES, 14 INCH)",49680,2.9563917015739085E-5,1,270]
[null,null,null,null,null,"795-07.15",13,null,null,null,null,null,null,null,"606-04.02","LOADING TEST (STEEL PILES, 14 INCH)",17400,1.0354511998266105E-5,1,5800]
[null,null,null,null,null,"795-08.01",15,null,null,null,null,null,null,null,"606-04.03","STEEL PILES (14 INCH)",279600,1.6638629624800017E-4,2,93.386773547094194]
[null,null,null,null,null,"795-08.03",11,null,null,null,null,null,null,null,"606-04.06","PILE TIPS (STEEL PILES, 14 INCH)",3960,2.3565441099502168E-6,1,120]
[null,null,null,null,null,"795-08.04",29,null,null,null,null,null,null,null,"606-09.01","TEST PILES (PRECAST CONCRETE, SIZE 1)",169764.6,1.0102468894142794E-4,7,59.987491166077739]
[null,null,null,null,null,"795-08.05",25,null,null,null,null,null,null,null,"606-09.02","LOADING TEST (PRECAST CONCRETE, SIZE 1)",106217.25,6.320849365217416E-5,7,5590.3815789473683]
[null,null,null,null,null,"795-08.09",17,null,null,null,null,null,null,null,"606-09.03","PRECAST CONCRETE PILES (SIZE 1)",2317047.2999999998,1.3788444866896599E-3,7,38.720710227272725]
[null,null,null,null,null,"795-09.01",22,null,null,null,null,null,null,null,"606-10.01","TEST PILES (PRECAST CONCRETE, SIZE 2)",45315,2.6966362712725779E-5,1,57]
[null,null,null,null,null,"795-09.09",24,null,null,null,null,null,null,null,"606-10.02","LOADING TEST (PRECAST CONCRETE, SIZE 2)",22000,1.309191172194565E-5,1,5500]
[null,null,null,null,null,"795-09.10",9,null,null,null,null,null,null,null,"606-10.03","PRECAST CONCRETE PILES (SIZE 2)",546960,3.2548872888342695E-4,1,53]
[null,null,null,null,null,"795-09.14",8,null,null,null,null,null,null,null,"606-12.01","PILE ANCHORAGE SYSTEM (SEISMIC)",203744.43,1.2124564051809704E-4,7,120.13232900943396]
[null,null,null,null,null,"795-09.28",20,null,null,null,null,null,null,null,"606-18.01","TEST PILES (STEEL PIPE PILES, 14-INCH)",24300,1.4460611583785423E-5,1,45]
[null,null,null,null,null,"795-09.29",9,null,null,null,null,null,null,null,"606-18.02","LOADING TEST (STEEL PIPE PILES, 14-INCH)",10800,6.4269384816824099E-6,1,5400]
[null,null,null,null,null,"795-10.03",11,null,null,null,null,null,null,null,"606-18.03","STEEL PIPE PILES (14-INCH)",352800,2.0994665706829205E-4,1,42]
[null,null,null,null,null,"795-11.01",11,null,null,null,null,null,null,null,"606-22.01","STEEL PIPE PILES (20 IN)",1670900,9.9433069528177213E-4,2,102.13325183374083]
[null,null,null,null,null,"795-11.02",26,null,null,null,null,null,null,null,"606-22.03","TEST PILES (STEEL PIPE PILES 20 IN)",89900,5.3498311991041544E-5,2,109.63414634146342]
[null,null,null,null,null,"795-11.04",8,null,null,null,null,null,null,null,"606-22.04","LOAD TESTING (STEEL PIPE PILES 20 IN)",14200,8.4502339296194654E-6,2,4733.333333333333]
[null,null,null,null,null,"795-12.01",10,null,null,null,null,null,null,null,"606-24.12","TEMPORARY SHEET PILES",591124.4,3.5177038461309495E-4,7,6.5195147237233924]
[null,null,null,null,null,"795-13.01",28,null,null,null,null,null,null,null,"606-24.13","TEMPORARY SHEET PILES",91696.95,5.4567653389621096E-5,3,30565.649999999998]
[null,null,null,null,null,"795-14.05",9,null,null,null,null,null,null,null,"606-27.11","TEST PILES (7.625 INCH MICROPILE)",12000,7.1410427574248996E-6,1,200]
[null,null,null,null,null,"795-14.08",9,null,null,null,null,null,null,null,"606-27.12","VERIFICATION LOADING TEST (7.625 INCH MICROPILE)",14000,8.3312165503290503E-6,1,14000]
[null,null,null,null,null,"795-14.10",10,null,null,null,null,null,null,null,"606-27.13","MICROPILE TYPE B (7.625 INCH)",779250,4.6372146406027946E-4,1,125]
[null,null,null,null,null,"795-15.02",10,null,null,null,null,null,null,null,"606-27.14","PROOF LOADING TEST MICROPILE (7.625 IN)",17500,1.0414020687911312E-5,1,2500]
[null,null,null,null,null,"797-03.06",8,null,null,null,null,null,null,null,"606-28.01","TEST PILES (7 5/8\" S .500\" MICROPILE)",43200,2.570775392672964E-5,1,200]
[null,null,null,null,null,"797-05.01",9,null,null,null,null,null,null,null,"606-28.02","VERIFICATION LOADING TEST (7 5/8\" s .500\" MICROPILE)",56000,3.3324866201316201E-5,1,14000]
[null,null,null,null,null,"797-05.02",13,null,null,null,null,null,null,null,"606-28.03","MICROPILE(7 5/8\" s .500\" MICROPILE)",2473250,1.4717986666500946E-3,1,125]
[null,null,null,null,null,"797-05.03",8,null,null,null,null,null,null,null,"606-28.04","PROOF LOADING TEST (7 5/8\" s .500\" MICROPILE)",42500,2.5291193099213186E-5,1,2500]
[null,null,null,null,null,"797-05.51",15,null,null,null,null,null,null,null,"606M02.03","STEEL PILES (250mm)",584856.2699999999,3.4804030258483678E-4,1,259.58999999999997]
[null,null,null,null,null,"797-05.52",18,null,null,null,null,null,null,null,"606M02.06","PILE TIPS (STEEL PILES, 250mm)",37542.400000000001,2.2340990301362381E-5,1,146.65]
[null,null,null,null,null,"797-05.53",13,null,null,null,null,null,null,null,"606M02.31","WOOD LAGGING (SEE PLANS)",663884,3.9506866916418938E-4,1,75.099999999999994]
[null,null,null,null,null,"797-06.64",11,null,null,null,null,null,null,null,"606M04.03","STEEL PILES (350mm)",2341510.08,1.39340196651845E-3,1,306.32]
[null,null,null,null,null,"797-07.02",12,null,null,null,null,null,null,null,"607-01.02","12\" CONCRETE PIPE CULVERT (CLASS III)",1380,8.2121991710386351E-7,1,60]
[null,null,null,null,null,"797-07.03",19,null,null,null,null,null,null,null,"607-02.02","15\" CONCRETE PIPE CULVERT(CLASS III)",8850.7999999999993,5.266995103118025E-6,4,119.60540540540539]
[null,null,null,null,null,"797-07.04",19,null,null,null,null,null,null,null,"607-03.02","18\" CONCRETE PIPE CULVERT (CLASS III)",17370309.938699998,1.0336843831831614E-2,69,58.836649608633174]
[null,null,null,null,null,"797-07.05",14,null,null,null,null,null,null,null,"607-03.03","18\" CONCRETE PIPE CULVERT (CLASS IV)",172359.91999999998,1.0256912986552792E-4,6,47.626394031500411]
[null,null,null,null,null,"797-07.06",14,null,null,null,null,null,null,null,"607-03.04","18\" CONCRETE PIPE CULVERT (CLASS V)",5416.04,3.2230144346602964E-6,1,58.87]
[null,null,null,null,null,"797-07.07",12,null,null,null,null,null,null,null,"607-03.05","18\" CONCRETE PIPE CULVERT(CLASS IV)JACKED-IN-PLACE",1215948.98,7.2359530475226623E-4,10,558.28695133149677]
[null,null,null,null,null,"797-07.56",12,null,null,null,null,null,null,null,"607-03.30","18\" PIPE CULVERT",2700504.2199999997,1.6070346751355315E-3,26,47.047931497064404]
[null,null,null,null,null,"797-08.01",11,null,null,null,null,null,null,null,"607-05.02","24\" CONCRETE PIPE CULVERT (CLASS III)",4618887.2104000002,2.7486392550991187E-3,65,70.507620098291753]
[null,null,null,null,null,"797-08.05",18,null,null,null,null,null,null,null,"607-05.03","24\" CONCRETE PIPE CULVERT (CLASS IV)",51720,3.0777894284501317E-5,5,54.730158730158728]
[null,null,null,null,null,"797-08.08",12,null,null,null,null,null,null,null,"607-05.04","24\" CONCRETE PIPE CULVERT (CLASS V)",35793.520000000004,2.1300254729895278E-5,1,91.310000000000016]
[null,null,null,null,null,"797-10.02",14,null,null,null,null,null,null,null,"607-05.05","24\" CONCRETE PIPE CULVERT(CLASS IV)JACKED-IN-PLACE",429067,2.5533214940000245E-4,5,609.4701704545455]
[null,null,null,null,null,"797-10.06",13,null,null,null,null,null,null,null,"607-05.06","24\" PIPE CULVERT (JACKED-IN-PLACE)",155530,9.255386500519122E-5,2,563.51449275362324]
[null,null,null,null,null,"797-10.09",14,null,null,null,null,null,null,null,"607-05.30","24\" PIPE CULVERT",1247138.78,7.4215594603522714E-4,25,61.782363023877934]
[null,null,null,null,null,"797-11.15",8,null,null,null,null,null,null,null,"607-06.02","30\" CONCRETE PIPE CULVERT (CLASS III)",2011638.6196999997,1.1970997829804089E-3,54,91.47836955987907]
[null,null,null,null,null,"797-11.25",18,null,null,null,null,null,null,null,"607-06.03","30\" CONCRETE PIPE CULVERT (CLASS IV)",117320,6.9815594691757435E-5,4,88.276899924755455]
[null,null,null,null,null,"797-11.31",10,null,null,null,null,null,null,null,"607-06.04","30\" CONCRETE PIPE CULVERT (CLASS V)",182030.26,1.083238224837643E-4,4,95.204110878661098]
[null,null,null,null,null,"797-11.38",10,null,null,null,null,null,null,null,"607-06.05","30\" CONCRETE PIPE CULVERT(CLASS IV)JACKED-IN-PLACE",738915,4.3971863409188498E-4,5,808.44091903719914]
[null,null,null,null,null,"797-11.40",11,null,null,null,null,null,null,null,"607-06.06","30\" PIPE CULVERT (JACKED-IN-PLACE)",216700,1.2895533046116466E-4,1,985]
[null,null,null,null,null,"801-01",56,null,null,null,null,null,null,null,"607-06.08","36\" CONCRETE PIPE CULVERT CLASS V (JACKED-IN-PLACE) (SEE PLANS)",195125,1.1611633067021114E-4,1,875]
[null,null,null,null,null,"801-01.07",79,null,null,null,null,null,null,null,"607-06.30","30\" PIPE CULVERT",784024.72000000009,4.6656283736650714E-4,21,88.043202695115099]
[null,null,null,null,null,"801-02",49,null,null,null,null,null,null,null,"607-07.02","36\" CONCRETE PIPE CULVERT (CLASS III)",1708217.5391999998,1.0165378738675286E-3,44,106.67492267053012]
[null,null,null,null,null,"801-02.01",14,null,null,null,null,null,null,null,"607-07.03","36\" CONCRETE PIPE CULVERT (CLASS IV)",154883,9.2168843783186729E-5,5,92.357185450208704]
[null,null,null,null,null,"801-02.15",11,null,null,null,null,null,null,null,"607-07.04","36\" CONCRETE PIPE CULVERT (CLASS V)",31690,1.8858303748566255E-5,2,119.13533834586467]
[null,null,null,null,null,"801-03",95,null,null,null,null,null,null,null,"607-07.05","36\" CONCRETE PIPE CULVERT(CLASS IV)JACKED-IN-PLACE",499513.85,2.9725414673132733E-4,4,1156.2820601851852]
[null,null,null,null,null,"801-07",17,null,null,null,null,null,null,null,"607-07.30","36\" PIPE CULVERT",1528122.3599999999,9.0936559261142042E-4,18,105.48231932077033]
[null,null,null,null,null,"801-08",23,null,null,null,null,null,null,null,"607-08.02","42\" CONCRETE PIPE CULVERT (CLASS III)",823651.72,4.9014434581221347E-4,26,113.20117097306212]
[null,null,null,null,null,"802-11.02",9,null,null,null,null,null,null,null,"607-08.03","42\" CONCRETE PIPE CULVERT (CLASS IV)",27810.16,1.6549461804235637E-5,1,131.18]
[null,null,null,null,null,"802-11.26",9,null,null,null,null,null,null,null,"607-08.04","42\" CONCRETE PIPE CULVERT (CLASS V)",85845.8,5.1085710695445544E-5,2,158.97370370370371]
[null,null,null,null,null,"802-12.02",8,null,null,null,null,null,null,null,"607-08.05","42\" CONCRETE PIPE CULVERT(CLASS IV)JACKED-IN-PLACE",777154.95,4.6247472725786747E-4,6,1269.8610294117645]
[null,null,null,null,null,"802-12.18",8,null,null,null,null,null,null,null,"607-08.06","42\" CONCRETE PIPE CULVERT (CLASS V) JACKED-IN-PLACE",368030,2.1900983050125716E-4,1,1235]
[null,null,null,null,null,"803-01",86,null,null,null,null,null,null,null,"607-08.30","42\" PIPE CULVERT",809278.13,4.8159081074823889E-4,13,138.74132178981657]
[null,null,null,null,null,"805-01.01",8,null,null,null,null,null,null,null,"607-09.02","48\" CONCRETE PIPE CULVERT (CLASS III)",859651.94640000002,5.1156760881216159E-4,24,162.76631993501857]
[null,null,null,null,null,"805-01.02",12,null,null,null,null,null,null,null,"607-09.03","48\" CONCRETE PIPE CULVERT (CLASS IV)",109423,6.5116193470475403E-5,4,173.96343402225756]
[null,null,null,null,null,"805-01.03",9,null,null,null,null,null,null,null,"607-09.05","48\" CONCRETE PIPE CULVERT(CLASS IV)JACKED-IN-PLACE",1140980,6.7898224711388855E-4,4,2109.0203327171903]
[null,null,null,null,null,"805-12.01",19,null,null,null,null,null,null,null,"607-09.30","48\" PIPE CULVERT",229519.3,1.3658392791285272E-4,12,165.5386224305806]
[null,null,null,null,null,"805-12.02",40,null,null,null,null,null,null,null,"607-10.02","54\" CONCRETE PIPE CULVERT (CLASS III)",165846.04999999999,9.8692811183335641E-5,3,148.87437163375225]
[null,null,null,null,null,"805-12.03",10,null,null,null,null,null,null,null,"607-10.04","54\" CONCRETE PIPE CULVERT (CLASS V)",41736,2.4836546710323802E-5,1,188]
[null,null,null,null,null,"806-02.03",48,null,null,null,null,null,null,null,"607-10.30","54\" PIPE CULVERT",61040,3.6324104159434658E-5,2,179.52941176470588]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-11.02","60\" CONCRETE PIPE CULVERT (CLASS II)",115990,6.9024129119476174E-5,2,310.13368983957218]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-11.03","60\" CONCRETE PIPE CULVERT (CLASS III)",279594.46000000002,1.6638299946659385E-4,7,223.49677058353319]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-11.05","60\" CONCRETE PIPE CULVERT (CLASS V)",72912,4.3388975794113696E-5,1,196]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-11.06","60\" CONCRETE PIPE CULVERT(CLASS IV)JACKED-IN-PLACE",454808,2.7065028120157531E-4,2,1612.7943262411347]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-11.30","60\" PIPE CULVERT",182249.87,1.0845450951709413E-4,6,274.01874906029167]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-12.30","66\" PIPE CULVERT",4200,2.4993649650987149E-6,1,200]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-13.03","72\" CONCRETE PIPE CULVERT (CLASS III)",50097,2.9812068251559601E-5,3,267.89839572192511]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-13.30","72\" PIPE CULVERT",78966.98,4.6992215050393075E-5,1,242.23]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-14.03","78\" CONCRETE PIPE CULVERT (CLASS III)",36520,2.1732573458429778E-5,1,415]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-16.01","23\"X 14\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",70048.959999999992,4.1685218206095538E-5,10,78.530224215246633]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-16.02","30\"X 19\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",140563.31,8.3647383902930923E-5,7,77.147810098792533]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-16.03","34\"X 22\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",19488,1.1597053438058038E-5,1,87]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-16.04","38\"X 24\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",89269.459999999992,5.3123085899352646E-5,8,88.385603960396026]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-16.05","45\"X 29\" HORIZONTAL OVAL CONCRETE PIPE CULVERT (CLASS__)",8223.2799999999988,4.893566173856419E-6,2,128.48874999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-16.06","45\"X 29\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",86690,5.1588083053430379E-5,7,132.25019069412664]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-16.07","49\"X 32\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",55670,3.3128487525487014E-5,1,190]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-16.08","53\"X 34\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",79571.97,4.7352236671877622E-5,4,168.58468220338983]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-16.09","60\"X 38\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",29064.9,1.7296141136689916E-5,2,189.96666666666667]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-16.10","68\"X 43\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",11750,6.9922710333118811E-6,1,250]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-16.11","76\"X 48\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",187185.95,1.113919060449333E-4,4,272.07260174418604]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-17.34","34IN X 22IN HORIZONTAL OVAL CONCRETE PIPE CULVERT",3306.96,1.9679285630911541E-6,1,91.86]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-20.01","18\" CROSSDRAIN PIPE CULVERT(COLLECTORS & LOCAL ROADS)",10241,6.0942849065656998E-6,2,51.462311557788944]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-20.02","24\" CROSSDRAIN PIPE CULVERT(COLLECTORS & LOCAL ROADS)",22833.239999999998,1.3587761927545376E-5,2,71.131588785046716]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-20.04","36\" CROSSDRAIN PIPE CULVERT(COLLECTORS & LOCAL ROADS)",6502,3.8692550007313915E-6,2,70.673913043478265]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-37.02","18\" CORRUGATED METAL PIPE CULVERT",63641.71,3.7872347688802986E-5,8,50.389319081551861]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-37.03","24\" CORRUGATED METAL PIPE CULVERT",11416,6.7935120098968886E-6,4,67.952380952380949]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-37.04","30\" CORRUGATED METAL PIPE CULVERT",20691.32,1.2313133402296748E-5,3,92.786188340807172]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-37.05","36\" CORRUGATED METAL PIPE CULVERT",4101.76,2.4409036283912634E-6,1,141.44]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-37.06","42\" CORRUGATED METAL PIPE CULVERT",6962.95,4.1435603056509752E-6,2,154.73222222222222]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-37.11","72\" CORRUGATED METAL PIPE CULVERT",30960,1.842389031415624E-5,1,258]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-37.30","12IN CORRUGATED METAL PIPE CULVERT",3218.4900000000002,1.9152812253620389E-6,4,45.978428571428573]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-38.10","66\" CORRUGATED METAL PIPE CULVERT (PRECOATED)",27160,1.6162560107638356E-5,1,97]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-38.11","72\" CORRUGATED METAL PIPE CULVERT (PRECOATED)",14700,8.7477773778455023E-6,1,105]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-39.01","15\" PIPE CULVERT (SIDE DRAIN)",17757.84,1.0567457893292516E-5,9,32.228384754990927]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-39.02","18\" PIPE CULVERT (SIDE DRAIN)",1033512.9600000001,6.1503001980939753E-4,59,37.9062152943334]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-39.03","24\" PIPE CULVERT (SIDE DRAIN)",285703.39,1.7001834366093681E-4,34,47.728598396257937]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-39.04","30\" PIPE CULVERT (SIDE DRAIN)",129424.35,7.7018734766827121E-5,22,59.423484848484854]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-39.05","36\" PIPE CULVERT (SIDE DRAIN)",107725.29,6.4105908495499747E-5,17,80.935604808414737]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-39.06","42\" PIPE CULVERT (SIDE DRAIN)",48214.7,2.8691936186367859E-5,7,124.26469072164947]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-39.07","48\" PIPE CULVERT (SIDE DRAIN)",23799,1.4162473048662934E-5,5,97.938271604938265]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-39.09","60\" PIPE CULVERT (SIDE DRAIN)",3693.12,2.1977273190250873E-6,1,153.88]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-39.10","66\" PIPE CULVERT (SIDE DRAIN)",9700,5.7723428955851279E-6,1,97]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-40.02","CORRUGATED METAL PIPE ARCH (SIZE EQUIV. 18\" ROUND)",6686.55,3.9790782874716223E-6,1,49.53]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-40.05","CORRUGATED METAL PIPE ARCH (SIZE EQUIV. 30\" ROUND)",12920,7.6885227021608089E-6,1,170]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-41.02","15\" SLOPE DRAIN PIPE",11097.900000000001,6.6042148681354841E-6,1,32.450000000000003]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-41.03","18\" SLOPE DRAIN PIPE",28600,1.7019485238529344E-5,2,30.425531914893618]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-41.04","24\" SLOPE DRAIN PIPE",48452.91,2.883369183597171E-5,1,53.07]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-45.02","18\" SLOTTED DRAIN PIPE",15200,9.0453208260715408E-6,2,152]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-50.04","PRECAST CONCRETE BOX CULVERT (10' X 4')",91006.2,5.4156597115896829E-5,1,1596.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-50.05","PRECAST CONCRETE BOX CULVERT (8' X 4')",802032,4.772787337352506E-4,1,616]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-50.07","PRECAST CONCRETE BOX CULVERT (12' X 6')",239400,1.4246380301062675E-4,1,1400]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-50.09","PRECAST CONCRETE BOX CULVERT (6' X 4')",621600,3.6990601483460981E-4,1,600]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-50.10","PRECAST CONCRETE BOX CULVERT (10' X 8')",562120,3.3451024623364041E-4,1,940]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-50.12","PRECAST CONCRETE BOX CULVERT (12'x7')",106476.98,6.3363055571789652E-5,2,686.94825806451615]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-50.13","PRECAST CONCRETE BOX CULVERT (8'-0\" x 8'-0\")",269356.5,1.6029052362419335E-4,1,598.57000000000005]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-50.60","THREE SIDED PRECAST CULVERT STRUCTURE - BARREL (28'x3'-9\")",575820,3.4266293671503381E-4,2,3739.090909090909]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-50.69","DEEP CORRUGATED STRUCTURE PLATE BRIDGE",101485.8,6.0392869755955991E-5,1,1561.32]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-57.02","REINFORCED CONCRETE PIPE ARCH (29\" X 18\")",12300,7.3195688263605222E-6,1,75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-57.06","REINFORCED CONCRETE PIPE ARCH (58\" X 36\")",13490,8.0277222331384915E-6,1,190]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-60.18","36\" STEEL PIPE CULVERT (JACK-IN-PLACE)",151680,9.0262780453850741E-5,1,790]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-65.63","15\" MINIMUM ID PIPE TO SLIP LINE 18\" PIPE",93074,5.5387117800380429E-5,2,53.094124358243015]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-65.64","18\" MINIMUM ID PIPE TO SLIP LINE 24\" PIPE",33773.300000000003,2.0098048279944868E-5,2,72.787284482758622]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-65.65","24\" MINIMUM ID PIPE TO SLIP LINE 30\" PIPE",23751,1.4133908877633233E-5,1,117]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607-65.78","54IN MIN I.D. to SLIP LINE 60IN CMP",7350,4.3738886889227511E-6,1,50]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M03.02","450mm CONCRETE PIPE CULVERT (CLASS III)",269612.88,1.6044309200270571E-4,1,183.66]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M03.03","450mm CONCRETE PIPE CULVERT (CLASS IV)",6701.4,3.9879153278839354E-6,1,197.1]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M03.04","450mm CONCRETE PIPE CULVERT (CLASS V)",18652,1.1099560792624103E-5,1,233.15]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M05.02","600mm CONCRETE PIPE CULVERT (CLASS III)",528539.42499999993,3.1452688607581421E-4,1,227.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M05.03","600mm CONCRETE PIPE CULVERT (CLASS IV)",8069.56,4.8020894161338065E-6,1,237.34]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M06.02","750mm CONCRETE PIPE CULVERT (CLASS III)",254165.65,1.5125064784322434E-4,1,304.39]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M07.02","900mm CONCRETE PIPE CULVERT (CLASS III)",305156.07,1.8159437862981216E-4,1,359.43]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M07.04","900mm CONCRETE PIPE CULVERT (CLASS V)",21734.239999999998,1.2933761428344546E-5,1,410.08]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M09.02","1200mm CONCRETE PIPE CULVERT (CLASS III)",215965.34999999998,1.2851814987268611E-4,1,558.04999999999995]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M09.03","1200mm CONCRETE PIPE CULVERT (CLASS IV)",100198.28,5.9626683475036016E-5,1,550.54]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M09.04","1200mm CONCRETE PIPE CULVERT (CLASS V)",43864.56,2.610322487463583E-5,1,609.23]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M11.03","1500mm CONCRETE PIPE CULVERT (CLASS III)",59890.9,3.564028980672158E-5,1,1015.1]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M11.04","1500mm CONCRETE PIPE CULVERT (CLASS IV)",98751.78,5.8765890279318091E-5,1,802.86]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M13.03","1800mm CONCRETE PIPE CULVERT (CLASS III)",306698.36,1.8251217519934122E-4,1,1061.24]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M13.04","1800mm CONCRETE PIPE CULVERT (CLASS IV)",130273.18,7.7523862377142525E-5,1,1104.01]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M13.05","1800mm CONCRETE PIPE CULVERT (CLASS V)",382452.47999999998,2.2759245936359928E-4,1,1327.96]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M38.02","450mm CORRUGATED METAL PIPE CULVERT (PRECOATED)",5063.0999999999995,3.0129844654265006E-6,1,241.09999999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M39.02","450mm PIPE CULVERT (SIDE DRAIN)",14397.44,8.5677278864549633E-6,1,112.48]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"607M39.03","600mm PIPE CULVERT (SIDE DRAIN)",9736.48,5.7940516655676989E-6,1,157.04]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"610-07.03","18\" PIPE DRAIN (BRIDGE DRAIN)",145536.46,8.6606840302021546E-5,17,36.511906673356755]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"610-10.04","DRAINAGE SYSTEM - BRIDGE DECK (CLOSED SYSTEM)",90000,5.3557820680686748E-5,1,90000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"610-10.14","DRAINAGE SYSTEM - BRIDGE DECK (CLOSED SYSTEM RAILROAD)",474398,2.8230803350307146E-4,1,474398]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"610-10.45","DECK DRAINS (GRATE TYPE 2)",46000,2.7373997236795451E-5,2,3833.3333333333335]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"610-10.46","DECK DRAINS (GRATE TYPE 2)",19660.16,1.1699503598151227E-5,2,1228.76]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"610-12.02","HORIZONTAL DRAINS",2090,1.2437316135848367E-6,1,19]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"610M07.03","450mm PIPE DRAIN (BRIDGE DRAIN)",6409.2000000000007,3.8140309367406395E-6,1,65.400000000000006]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-01.01","MANHOLES, 0' - 4' DEPTH",8620,5.1296490474168865E-6,2,2873.3333333333335]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-01.02","MANHOLES, > 4' - 8' DEPTH",414766.60000000003,2.4682216874597922E-4,25,4822.8674418604651]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-01.03","MANHOLES, > 8' - 12' DEPTH",405628.08,2.4138395524101399E-4,18,8278.1240816326535]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-01.04","MANHOLES, > 12' - 16' DEPTH",225993.15,1.3448556225292824E-4,9,12555.175000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-01.05","MANHOLES, > 16' - 20' DEPTH",194231,1.1558432298478299E-4,5,17657.363636363636]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-01.06","MANHOLES, > 20' - 24' DEPTH",77969.72,4.639875869203728E-5,3,19492.43]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-01.07","MANHOLES, > 24' - 28' DEPTH",95837.02,5.703135479701544E-5,5,19167.404000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-01.08","MANHOLES, > 28' - 32' DEPTH",12500,7.4385862056509373E-6,1,12500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-01.10","MANHOLES,( __' - __' DEPTH) ( 40' - 44' DEPTH)",25505.49,1.5177982886589435E-5,1,25505.49]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-01.20","ADJUSTMENT OF EXISTING MANHOLE",31886,1.8974940780270864E-5,5,1226.3846153846155]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-01.21","REWORK MANHOLE",1955.7,1.1638114433913232E-6,1,1955.7]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-02.01","SPRING DRAIN BOX, TYPE 1",33584.6,1.9985755382584356E-5,8,3053.1454545454544]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-02.02","SPRING DRAIN BOX, TYPE 2A",6606.38,3.931370170983059E-6,2,3303.19]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-02.10","JUNCTION BOX, TYPE 1",234422.44,1.3950172227832275E-4,19,3907.0406666666668]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-02.11","JUNCTION BOX, TYPE 2",359241.95,2.1378017710089152E-4,31,3742.1036458333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-02.12","JUNCTION BOX, TYPE 3",69879.66,4.1584469994526208E-5,9,5375.3584615384616]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-02.13","JUNCTION BOX, TYPE 4",102818.22,6.1185775438526668E-5,6,8568.1849999999995]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-02.14","JUNCTION BOX, TYPE 5",123420,7.3445624760115101E-5,5,12342]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-05.01","TRENCH DRAINS",231608.4,1.3782712394823076E-4,2,328.52255319148935]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-06.10","BRIDGE END DRAIN (2' X 3')",12532.36,7.4578432176201267E-6,1,3133.09]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.01","CLASS A CONCRETE (PIPE ENDWALLS)",2503212.929,1.4896292130773183E-3,79,704.22780070613715]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.02","STEEL BAR REINFORCEMENT (PIPE ENDWALLS)",415606.65999999986,2.4732207744421268E-4,78,1.4414270453993687]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.03","STRUCTURAL STEEL (PIPE ENDWALLS)",209426.61,1.2462703137937909E-4,18,4.2799519741682328]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.30","15IN ENDWALL (SIDE DRAIN)",23600,1.4044050756268971E-5,2,1475]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.31","18IN ENDWALL (SIDE DRAIN)",1169093.71,6.9571234754554217E-4,26,3117.5832266666666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.32","24IN ENDWALL (SIDE DRAIN)",215850.03000000003,1.284495244517873E-4,17,2698.1253750000005]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.33","30IN ENDWALL (SIDE DRAIN)",15058.1,8.9608779954649914E-6,3,1075.5785714285714]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.34","36IN ENDWALL (SIDE DRAIN)",64693.36,3.849817082345681E-5,4,4043.335]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.35","42IN ENDWALL (SIDE DRAIN)",104664.72,6.2284603392825426E-5,4,6541.5450000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.36","48IN ENDWALL (SIDE DRAIN)",18632.080000000002,1.1087706661646778E-5,1,2329.0100000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.51","15IN ENDWALL (CROSS DRAIN) 3:1",8574.5400000000009,5.1025963971041753E-6,3,2143.6350000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.52","15IN ENDWALL (CROSS DRAIN) 4:1",3550,2.1125584824048664E-6,2,1775]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.53","15IN ENDWALL (CROSS DRAIN) 6:1",1890,1.1247142342944218E-6,1,1890]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.54","18IN ENDWALL (CROSS DRAIN) 3:1",377202.28,2.2446813413984663E-4,41,1858.1393103448277]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.55","18IN ENDWALL (CROSS DRAIN) 4:1",119242,7.0959351706738328E-5,28,1548.5974025974026]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.56","18IN ENDWALL (CROSS DRAIN) 6:1",153830.14000000001,9.1542300593388205E-5,25,2136.5297222222225]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.57","24IN ENDWALL (CROSS DRAIN) 3:1",186498.18,1.1098262313016044E-4,36,2331.2272499999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.58","24IN ENDWALL (CROSS DRAIN) 4:1",131765.15,7.8411714174042121E-5,29,2395.7300000000005]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.59","24IN ENDWALL (CROSS DRAIN) 6:1",124578.23999999999,7.4134878207061738E-5,19,2595.3799999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.60","30IN ENDWALL (CROSS DRAIN) 3:1",249911.66,1.4871915413658618E-4,34,3377.1845945945952]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.61","30IN ENDWALL (CROSS DRAIN) 4:1",131683.97000000003,7.836340501978817E-5,16,3559.0262162162162]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.62","30IN ENDWALL (CROSS DRAIN) 6:1",145962.45000000001,8.6860341369041181E-5,16,4170.3557142857144]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.63","36IN ENDWALL (CROSS DRAIN) 3:1",180662.72,1.0751001734939021E-4,22,3763.8066666666668]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.64","36IN ENDWALL (CROSS DRAIN) 4:1",83129.709999999992,4.9469401126861019E-5,11,4375.2478947368418]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.65","36IN ENDWALL (CROSS DRAIN) 6:1",63269.070000000007,3.7650594507709087E-5,10,4866.8515384615384]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.66","42IN ENDWALL (CROSS DRAIN) 3:1",87672.290000000008,5.2172630960946293E-5,11,4614.331052631579]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.67","42IN ENDWALL (CROSS DRAIN) 4:1",34035.040000000001,2.0253806324222232E-5,3,4254.38]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.68","42IN ENDWALL (CROSS DRAIN) 6:1",88935.34,5.2924255465510085E-5,7,7411.2783333333327]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.69","48IN ENDWALL (CROSS DRAIN) 3:1",157957.68,9.3998545561969993E-5,12,5850.2844444444445]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.70","48IN ENDWALL (CROSS DRAIN) 4:1",77204.47,4.5943368444527333E-5,9,6433.7058333333334]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.71","48IN ENDWALL (CROSS DRAIN) 6:1",83024.36,4.9406708722319798E-5,8,7547.6690909090912]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-07.73","18IN ENDWALL (MEDIAN DRAIN)",110852.7,6.5966989206332934E-5,7,3079.2416666666668]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-09.01","ADJUSTMENT OF EXISTING CATCHBASIN",65606.42,3.9041520865131341E-5,16,1025.1003125]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-09.02","REWORK CATCHBASIN",33094.21,1.9693930719433224E-5,5,1575.9147619047619]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-09.03","CAPPING EXISTING CATCHBASIN",65231.26,3.8818268065058385E-5,16,1207.9862962962961]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-10.01","CATCH BASINS, TYPE 10, 0' - 4' DEPTH",25320.93,1.5068153648980239E-5,5,3165.11625]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-10.02","CATCH BASINS, TYPE 10, > 4' - 8' DEPTH",59410.979999999996,3.5354695703376297E-5,5,3494.7635294117645]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-12.01","CATCH BASINS, TYPE 12, 0' - 4' DEPTH",1698996.22,1.0110503876436068E-3,34,3254.7820306513413]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-12.02","CATCH BASINS, TYPE 12, > 4' - 8' DEPTH",6107259.9900000002,3.6343503932750308E-3,43,4082.3930414438505]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-12.03","CATCH BASINS, TYPE 12, > 8' - 12' DEPTH",1513036.5899999999,9.0038824856153053E-4,30,6278.1601244813282]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-12.04","CATCH BASINS, TYPE 12, > 12' - 16' DEPTH",649295.06000000006,3.8638698213706385E-4,19,8774.2575675675689]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-12.05","CATCH BASINS, TYPE 12, > 16' - 20' DEPTH",177052.47999999998,1.0536161083234306E-4,5,12646.605714285713]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-12.06","CATCH BASINS, TYPE 12, > 20' - 24' DEPTH",24000,1.4282085514849799E-5,1,12000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-13.01","CATCH BASINS, TYPE 13, 0' - 4' DEPTH",15117.48,8.996214255376314E-6,1,3779.37]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-13.02","CATCH BASINS, TYPE 13, > 4' - 8' DEPTH",34793.460000000006,2.0705132128229418E-5,2,3865.9400000000005]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-14.01","CATCH BASINS, TYPE 14, 0' - 4' DEPTH",292574.58999999997,1.7410730474383827E-4,10,4876.2431666666662]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-14.02","CATCH BASINS, TYPE 14, > 4' - 8' DEPTH",2882956.66,1.7156097314052401E-3,37,6847.8780522565321]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-14.03","CATCH BASINS, TYPE 14, > 8' - 12' DEPTH",510201.07,3.0361397131282785E-4,15,9811.5590384615389]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-14.04","CATCH BASINS, TYPE 14, > 12' - 16' DEPTH",218725.07,1.3016042308256287E-4,10,14581.671333333334]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-14.05","CATCH BASINS, TYPE 14, > 16' - 20' DEPTH",100932.38,6.0063536765721488E-5,3,20186.476000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-16.02","CATCH BASINS, TYPE 16, > 4' - 8' DEPTH",86719.16,5.1605435787330929E-5,5,6670.7046153846159]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-16.03","CATCH BASINS, TYPE 16, > 8' - 12' DEPTH",24000,1.4282085514849799E-5,1,12000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-25.01","CATCH BASINS, TYPE 25, 0' - 4' DEPTH",121139.62,7.208860050318371E-5,9,2472.2371428571428]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-25.02","CATCH BASINS, TYPE 25, > 4' - 8' DEPTH",714322.99,4.250842511834666E-4,12,3065.7639055793993]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-25.03","CATCH BASINS, TYPE 25, > 8' - 12' DEPTH",143545.43,8.542200443857857E-5,7,4349.8615151515151]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-25.04","CATCH BASINS, TYPE 25, > 12' - 16' DEPTH",70472.22,4.1937094685887849E-5,2,5033.7300000000005]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-25.05","CATCH BASINS, TYPE 25, > 16' - 20' DEPTH",11907.96,7.0862709594754502E-6,2,5953.98]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-26.01","CATCH BASINS, TYPE 26, 0' - 4' DEPTH",7790.66,4.6361196807133226E-6,1,3895.33]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-26.02","CATCH BASINS, TYPE 26, > 4' - 8' DEPTH",85160.19,5.0677713168369035E-5,9,5677.3460000000005]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-26.03","CATCH BASINS, TYPE 26, > 8' - 12' DEPTH",20069.260000000002,1.1942953647489771E-5,3,5017.3150000000005]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-27.02","CATCH BASINS, TYPE 27, > 4' - 8' DEPTH",21498.400000000001,1.279341613468529E-5,2,5374.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-28.01","CATCH BASINS, TYPE 28, 0' - 4' DEPTH",12000,7.1410427574248996E-6,1,4000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-28.02","CATCH BASINS, TYPE 28, > 4' - 8' DEPTH",10000,5.9508689645207496E-6,1,5000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-28.03","CATCH BASINS, TYPE 28, > 8' - 12' DEPTH",10600,6.3079211023919949E-6,1,10600]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-28.05","CATCH BASINS, TYPE 28, > 16' - 20' DEPTH",18500,1.1009107584363387E-5,1,18500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-29.02","CATCH BASINS, TYPE 29, > 4' - 8' DEPTH",8500,5.0582386198426374E-6,1,8500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-31.02","CATCH BASINS, TYPE 31, > 4' - 8' DEPTH",826354.91,4.9175297875983374E-4,7,6829.3794214876025]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-31.03","CATCH BASINS, TYPE 31, > 8' - 12' DEPTH",174235.03,1.0368498325593418E-4,4,10249.119411764706]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-31.04","CATCH BASINS, TYPE 31, > 12' - 16' DEPTH",42192.04,2.5107930138581806E-5,3,10548.01]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-31.06","CATCH BASINS, TYPE 31, > 20' - 24' DEPTH",84000,4.9987299301974299E-5,1,42000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-31.07","CATCH BASINS, TYPE 31, > 24' - 28' DEPTH",42000,2.4993649650987149E-5,1,42000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-32.01","CATCH BASINS, TYPE 32, > 0' - 4' DEPTH",9356.3799999999992,5.567859136226265E-6,1,4678.1899999999996]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-32.02","CATCH BASINS, TYPE 32, > 4' - 6' DEPTH",3304.07,1.9662087619604077E-6,1,3304.07]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-38.01","CATCH BASINS, TYPE 38, 0' - 4' DEPTH",227052.59000000003,1.3511602111450545E-4,24,3339.0086764705884]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-38.02","CATCH BASINS, TYPE 38, > 4' - 8' DEPTH",224112.44,1.3336637637590188E-4,21,3673.974426229508]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-38.03","CATCH BASINS, TYPE 38, > 8' - 12' DEPTH",133282,7.9314371732925454E-5,7,4595.9310344827591]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-38.04","CATCH BASINS, TYPE 38, > 12' - 16' DEPTH",39624.47,2.3580002875858353E-5,5,7924.8940000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-38.05","CATCH BASINS, TYPE 38, > 16' - 20' DEPTH",38705,2.3032838327177563E-5,3,6450.833333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-38.06","CATCH BASINS, TYPE 38, > 20' - 24' DEPTH",26045,1.5499038218094293E-5,2,13022.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-38.08","CATCH BASINS, TYPE 38, >(  ' -   ' DEPTH) (28' - 32' DEPTH)",11600,6.9030079988440703E-6,1,11600]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-39.01","CATCH BASINS, TYPE 39, 0' - 4' DEPTH",165438.11000000002,9.8450051434797008E-5,16,3519.9597872340423]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-39.02","CATCH BASINS, TYPE 39, > 4' - 8' DEPTH",196312.15000000002,1.1682278807933423E-4,12,4788.1012195121948]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-39.03","CATCH BASINS, TYPE 39, > 8' - 12' DEPTH",129336.22,7.6966289758642788E-5,7,7185.3455555555556]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-39.04","CATCH BASINS, TYPE 39, > 12' - 16' DEPTH",79999,4.760635662926955E-5,5,7999.9]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-39.05","CATCH BASINS, TYPE 39, > 16' - 20' DEPTH",53030.92,3.1558005598798272E-5,5,8838.4866666666658]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-39.06","CATCH BASINS, TYPE 39, > 20' - 24' DEPTH",28000,1.6662433100658101E-5,1,14000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-39.07","CATCH BASINS, TYPE 39, > 24' - 28' DEPTH",19035,1.1327479073965248E-5,2,9517.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-40.01","CATCH BASINS, TYPE 40, 0' - 4' DEPTH",63125.43,3.7565116225902712E-5,5,5738.6754545454542]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-40.02","CATCH BASINS, TYPE 40, > 4' - 8' DEPTH",59339.75,3.5312307663742021E-5,5,6593.3055555555557]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-40.05","CATCH BASINS, TYPE 40, > 16' - 20' DEPTH",6695,3.9841067717466424E-6,1,6695]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-41.01","CATCH BASINS, TYPE 41, 0' - 4' DEPTH",63056,3.7523799342682038E-5,4,3503.1111111111113]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-41.02","CATCH BASINS, TYPE 41, > 4' - 8' DEPTH",195447,1.163079486508687E-4,9,4158.4468085106382]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-41.03","CATCH BASINS, TYPE 41, > 8' - 12' DEPTH",48000.56,2.8564504278361611E-5,6,4363.6872727272721]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-41.08","CATCH BASINS, TYPE 41, >(  ' -   ' DEPTH) (SEE PLANS)",18761.82,1.1164913235592469E-5,1,9380.91]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-42.01","CATCH BASINS, TYPE 42, 0' - 4' DEPTH",801911.74,4.7720716858508328E-4,35,3273.1091428571426]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-42.02","CATCH BASINS, TYPE 42, > 4' - 8' DEPTH",670134.37,3.9878818244916652E-4,34,3988.8950595238102]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-42.03","CATCH BASINS, TYPE 42, > 8' - 12' DEPTH",105570.92,6.2823871138390297E-5,7,7038.0613333333331]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-42.04","CATCH BASINS, TYPE 42, > 12' - 16' DEPTH",35700,2.1244602203339077E-5,2,7140]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-42.05","CATCH BASINS, TYPE 42, > 16' - 20' DEPTH",11027,6.5620232071770308E-6,2,5513.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-43.01","CATCH BASINS, TYPE 43, 0' - 4' DEPTH",77123,4.5894886715073381E-5,7,5932.5384615384619]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-43.02","CATCH BASINS, TYPE 43, > 4' - 8' DEPTH",187075.02000000002,1.1132589305550987E-4,8,6235.8340000000007]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-43.03","CATCH BASINS, TYPE 43, > 8' - 12' DEPTH",25524.080000000002,1.518904555199448E-5,1,12762.04]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-44.02","CATCH BASINS, TYPE 44, > 4' - 8' DEPTH",79800,4.7487934336875584E-5,2,15960]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-44.03","CATCH BASINS, TYPE 44, > 8' - 12' DEPTH",34760.35,2.0685428801087885E-5,2,17380.174999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-44.04","CATCH BASINS, TYPE 44, > 12' - 16' DEPTH",14915,8.8757210605826978E-6,1,14915]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-46.02","CATCH BASINS, TYPE 46, > 4' - 8' DEPTH",67050.42,3.9900826343608138E-5,4,16762.605]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-51.02","CATCH BASINS, TYPE 51, > 4' - 8' DEPTH",273653.07,1.6284735613088244E-4,5,5822.4057446808511]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-51.03","CATCH BASINS, TYPE 51, > 8' - 12' DEPTH",50124.25,2.9828284369487921E-5,2,10024.85]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-51.04","CATCH BASINS, TYPE 51, > 12' - 16' DEPTH",11354.87,6.7571343479167737E-6,1,11354.87]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-52.02","CATCH BASINS, TYPE 52, > 4FT - 8FT DEPTH",122745.82,7.3044429076265038E-5,3,24549.164000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611-52.03","CATCH BASINS, TYPE 52, > 8FT - 12FT DEPTH",22485.759999999998,1.3380981132766208E-5,1,22485.759999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M01.04","MANHOLES, > 3m - 5m DEPTH",52607.62,3.1306105315530109E-5,1,26303.81]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M01.06","MANHOLES, > 6m - 7m DEPTH",35589.72,2.1178976020398342E-5,1,35589.72]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M01.07","MANHOLES, > 7m - 8m DEPTH",82135.3,4.8877640766160116E-5,1,41067.65]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M01.10","MANHOLES, ( > 8m - 9m DEPTH)",135984.78,8.0922760694918198E-5,1,45328.26]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M01.11","MANHOLES, ( > 11m - 12m DEPTH)",58266.12,3.4673404519104179E-5,1,58266.12]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M02.01","SPRING DRAIN BOX, TYPE 1",24147.420000000002,1.4369813225124765E-5,1,4024.57]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M02.10","JUNCTION BOX, TYPE 1",4024.6,2.3949867234610211E-6,1,4024.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M02.11","JUNCTION BOX, TYPE 2",18040.5,1.0735665155443658E-5,1,6013.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M02.12","JUNCTION BOX, TYPE 3",16469.82,9.8009740689243131E-6,1,8234.91]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M07.03","STRUCTURAL STEEL (PIPE ENDWALLS)",8120,4.8321055991908488E-6,1,10]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M07.57","24IN ENDWALL (CROSS DRAIN) 3:1",2393.61,1.4244059462166514E-6,1,2393.61]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M07.58","600mm ENDWALL (CROSS DRAIN) 4:1",8429.52,5.0162968953806956E-6,1,2809.84]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M12.02","CATCH BASINS, TYPE 12, > 1m - 2m DEPTH",84045.6,5.0014435264452518E-5,1,2801.52]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M12.03","CATCH BASINS, TYPE 12, > 2m - 3m DEPTH",14579.12,8.6758432738023754E-6,1,3644.78]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M14.02","CATCH BASINS, TYPE 14, > 1m - 2m DEPTH",34842.78,2.073448181396243E-5,1,5807.13]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M14.03","CATCH BASINS, TYPE 14, > 2m - 3m DEPTH",7908.87,4.7064649027429221E-6,1,7908.87]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M16.03","CATCH BASINS, TYPE 16, > 2m - 3m DEPTH",9895.09,5.888438398213963E-6,1,9895.09]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M25.02","CATCH BASINS, TYPE 25, > 1m - 2m DEPTH",160977.5,9.57956008736139E-5,1,3219.55]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M25.03","CATCH BASINS, TYPE 25, > 2m - 3m DEPTH",56879.34,3.3848149912842365E-5,1,4062.81]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M25.04","CATCH BASINS, TYPE 25, > 3m - 4m DEPTH",20238.84,1.2043868483390113E-5,1,5059.71]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M26.02","CATCH BASINS, TYPE 26, > 1m - 2m DEPTH",38344.86,2.2818523732289312E-5,1,6390.81]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M26.03","CATCH BASINS, TYPE 26, > 2m - 3m DEPTH",8138.03,4.8428350159338793E-6,1,8138.03]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M41.02","CATCH BASINS, TYPE 41, > 1m - 2m DEPTH",171156.96000000002,1.0185326413257195E-4,1,4388.6400000000003]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M41.03","CATCH BASINS, TYPE 41, > 2m - 3m DEPTH",87371.839999999997,5.1993837102907264E-5,1,5460.74]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M42.02","CATCH BASINS, TYPE 42, > 1m - 2m DEPTH",79708.800000000003,4.7433662411919158E-5,1,4195.2]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M42.03","CATCH BASINS, TYPE 42, > 2m - 3m DEPTH",42138.400000000001,2.5076009677456117E-5,1,5267.3]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M42.05","CATCH BASINS, TYPE 42, > 4m - 5m DEPTH",7029.13,4.1829431564581742E-6,1,7029.13]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M42.06","CATCH BASINS, TYPE 42, > 5m - 6m DEPTH",8713.51,5.1852956231041199E-6,1,8713.51]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M42.08","CATCH BASINS, TYPE 42, > 7m - 8m DEPTH",11087.63,6.5981033257089196E-6,1,11087.63]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M43.02","CATCH BASINS, TYPE 43, > 1m - 2m DEPTH",8842.2099999999991,5.2618833066775016E-6,1,8842.2099999999991]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M43.03","CATCH BASINS, TYPE 43, > 2m - 3m DEPTH",11587.65,6.8956586756728864E-6,1,11587.65]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M44.02","CATCH BASINS, TYPE 44, > 1m - 2m DEPTH",17751.919999999998,1.0563934978865518E-5,1,17751.919999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M44.03","CATCH BASINS, TYPE 44, > 2m - 3m DEPTH",43572.5,2.5929423795658037E-5,1,21786.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M44.07","CATCH BASINS, TYPE 44, > 6m - 7m DEPTH",122753.67,7.304910050840219E-5,1,40917.89]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M44.09","CATCH BASINS, TYPE 44, > 8m - 9m DEPTH",152630.37,9.0828333187631895E-5,1,50876.79]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M45.02","CATCH BASINS, TYPE 45, > 1m - 2m DEPTH",19987.599999999999,1.1894358851525494E-5,1,9993.7999999999993]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"611M45.03","CATCH BASINS, TYPE 45, > 2m - 3m DEPTH",46368.639999999999,2.7593370070303542E-5,1,11592.16]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"612-01","UNIFORM-COURSE STONE MASONRY",4336,2.5802967830161974E-6,1,542]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"615-01.02","PRESTRESSED CONCRETE I-BEAM (TYPE II)",1090846.96,6.4914873193058081E-4,4,130.15713637990692]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"615-01.03","PRESTRESSED CONCRETE I-BEAM (TYPE III)",2096634.92,1.2476799675358444E-3,6,170.29198505523067]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"615-01.10","PRESTRESSED CONCRETE BULB TEE BEAM (6\" WEB)(BT-54)",2945824.07,1.7530213033101201E-3,5,207.61322644301922]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"615-01.11","PRESTRESSED CONCRETE BULB TEE BEAM (6\" WEB)(BT-63)",2398738.4900000002,1.4274578434142369E-3,4,231.44910169818604]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"615-01.12","PRESTRESSED CONCRETE BULB TEE BEAM (6\" WEB)(BT-72)",5925128.1899999995,3.5259661456678E-3,8,209.5165555162659]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"615-02.04","PRESTRESSED CONCRETE BOX BEAM (27\" X 36\")",102700,6.1115424265628096E-5,1,260]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"615-02.12","PRESTRESSED CONCRETE BOX BEAM (42\" X 48\")",345851,2.058113982248466E-4,1,253]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"615-02.17","PRESTRESSED CONCRETE BOX BEAM (36\" X 36\")",449470,2.6747370734831415E-4,2,279.17391304347825]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"615-02.19","PRESTRESSED CONCRETE BOX BEAM (24\" X 36\")",56070,3.3366522284067847E-5,1,210]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"615-02.28","PRESTRESSED CONCRETE BOX BEAM (24\" X 48\")",214320,1.2753902364760872E-4,1,235]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"615-02.37","PRESTRESSED CONCRETE BOX BEAM (30\" X 36\")",642200,3.8216480490152254E-4,1,325]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"615-02.52","PRESTRESSED CONCRETE BOX BEAM (--\" X --\") (14\" x 36\")",271800,1.6174461845567398E-4,1,200]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"615M01.11","PRESTRESSED CONCRETE BULB TEE BEAM (150mm WEB)(BT-63)",627604.44000000006,3.7347917839914254E-4,1,755.24000000000012]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"617-01","BRIDGE DECK SEALANT",89084,5.3012721083536651E-5,2,21.491917973462002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"617-02","BRIDGE DECK CRACK SEALING",24394.649999999998,1.451693655853461E-5,15,3.0360485376477908]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"617-05","SEALANT (HIGH MOLECULAR WEIGHT METHACRYLATE)",11345.4,6.7514988750073716E-6,13,276.71707317073168]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"619-01","BRIDGE DECK OVERLAY (PMC)",241133.30000000002,1.4349526712824714E-4,1,57.1]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"620-03.11","CONCRETE PARAPET (STD-11-1, MODIFIED)",42687.96,2.5403045632270319E-5,1,79.94]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"620-05","CONCRETE PARAPET WITH STRUCTURAL TUBING",2167955.0300000003,1.2901216304503653E-3,16,163.15134181216138]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"620-05.01","CONC PARAPET SINGLE SLOPE (STD-1-1SS)",2118589.61,1.2607449158705119E-3,23,62.386690126328801]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"620-06","CONCRETE RAILING",26560,1.5805507969767112E-5,1,80]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"620-08","CONCRETE PARAPET WITH STRUCTURAL TUBING",11600,6.9030079988440703E-6,1,100]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"620M05","CONCRETE PARAPET WITH STRUCTURAL TUBING",266395.76999999996,1.5852863199726077E-4,1,519.29]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621-01.01","TEMPORARY STRUCTURE (56' OF 18\" PIPE - STA 14+29.50)",154500,9.1940925501845589E-5,3,51500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621-01.02","TEMPORARY STRUCTURE (90' OF 18\" PIPE - STA 15+12.00)",53200,3.1658622891250387E-5,2,26600]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621-01.03","TEMPORARY STRUCTURE (80' OF 18\" PIPE - STA 19+85.00)",37700,2.2434775996243228E-5,2,18850]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621-03.02","18\" TEMPORARY DRAINAGE PIPE",582594.69999999984,3.4669447191242758E-4,52,36.2355205871377]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621-03.03","24\" TEMPORARY DRAINAGE PIPE",784226.89999999991,4.666831520352317E-4,27,87.907958749019173]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621-03.04","30\" TEMPORARY DRAINAGE PIPE",166681.89000000001,9.9190208614866163E-5,18,49.31416863905325]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621-03.05","36\" TEMPORARY DRAINAGE PIPE",268905.87,1.6002235961604515E-4,20,56.815100359180221]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621-03.06","42\" TEMPORARY DRAINAGE PIPE",193749.95,1.1529805643324472E-4,13,70.557155863073561]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621-03.07","48\" TEMPORARY DRAINAGE PIPE",479892.20999999996,2.8557756588042739E-4,21,77.564604816550826]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621-03.08","54\" TEMPORARY DRAINAGE PIPE",108560.01000000001,6.4602639429706235E-5,6,100.61168674698796]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621-03.09","60\" TEMPORARY DRAINAGE PIPE",123360,7.3409919546327972E-5,3,98.530351437699679]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621-03.10","66\" TEMPORARY DRAINAGE PIPE",55000,3.2729779304864128E-5,1,110]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621-03.11","72\" TEMPORARY DRAINAGE PIPE",93825,5.5834028059615938E-5,4,126.61943319838056]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621-05.01","TEMPORARY SHORING",378385,2.2517195531401841E-4,5,18.129701499688561]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621-05.02","TEMPORARY SHORING",1146775,6.8243077567882828E-4,5,229355]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621M03.02","450mm TEMPORARY DRAINAGE PIPE",29694.720000000001,1.7670938765813361E-5,1,112.48]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621M03.03","600mm TEMPORARY DRAINAGE PIPE",67056.08,3.9904194535442059E-5,1,157.04]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621M03.04","750mm TEMPORARY DRAINAGE PIPE",57456.52,3.4191622167736572E-5,1,214.39]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"621M05.01","TEMPORARY SHORING",375000,2.2315758616952812E-4,1,50]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"622-01.01","SHOTCRETE BUTTRESS",32400,1.9280815445047229E-5,1,900]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"622-01.02","STEEL REINFORCEMENT- SHOTCRETE BUTTRESS",32440,1.9304618920905314E-5,1,8]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"624-03.01","RETAINING WALL REINFORCING STEEL",138780.35,8.2586367770032728E-5,1,0.85000000000000009]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"624M01.01","LOAD CELLS",13184,7.8456256428241575E-6,1,1648]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"624M03.01","RETAINING WALL REINFORCING STEEL",308070.71999999997,1.8332884865255618E-4,1,1.44]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"625-02.01","DRILLED SHAFT-SOIL (DIA.)",5469377.4500000002,3.2547548522454642E-3,4,1055.0496624228394]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"625-02.13","DRILLED SHAFT-ROCK (DIA.)",2314494.2000000002,1.3773251703343282E-3,4,730.81597726555106]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"625-02.14","DRILLED SHAFT-ROCK (DIA.)",498800,2.9682934395029503E-4,1,2900]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"625-02.25","DRILLED SHAFT CASING-PERMANENT (DIA.)",1863198.3,1.1087648938217821E-3,2,1039.7311941964285]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"625-02.40","DRILLED SHAFT CONCRETE",2369160,1.4098560715983979E-3,2,360]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"625-02.43","CONCRETE CORING",444150,2.643078450591891E-4,2,72.787610619469021]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"625-02.44","DRILLED SHAFT REINFORCING STEEL",18741.05,1.115255328075316E-5,1,1.07]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"625-02.46","SONIC LOGGING TESTING",40260,2.3958198451160541E-5,1,3355]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"625M01.07","PIEZOMETER",37250,2.2166986892839793E-5,1,250]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"625M01.08","INCLINOMETER",37250,2.2166986892839793E-5,1,250]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"625M02.40","DRILLED SHAFT CONCRETE",550417.91999999993,3.2754649176440644E-4,1,307.83999999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"626-01.01","AGGREGATE FOUNDATION SYSTEMS",1068021,6.3556530223564162E-4,1,1068021]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"630M01.06","CONCRETE BOLLARD/GUARD POST",6000,3.5705213787124498E-6,1,500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"680-02.01","BUILDING (DESCRIPTION)",110200,6.5578575989018662E-5,1,110200]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"701-01.01","CONCRETE SIDEWALK (4 \")",8535993.1695000008,5.0796576833738666E-3,41,4.6114421551356619]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"701-01.02","CONCRETE SIDEWALK (6 \")",1925423.56,1.1457943306761057E-3,7,8.5104979203592634]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"701-01.03","CONCRETE SIDEWALK - 4 \" (5.0 FT WIDE)",436860.3,2.599698401101224E-4,1,4.7]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"701-01.05","CONCRETE SIDEWALK -6IN (DESCRIPTION)",13078.999999999998,7.7831415186966873E-6,1,8.1999999999999993]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"701-01.07","EXPOSED AGGREGATE CONCRETE DRIVEWAY",25714.799999999999,1.5302540524885817E-5,2,9.9554006968641104]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"701-01.09","ORNAMENTAL CONCRETE (DESCRIPTION)",10080,5.9984759162369157E-6,1,15]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"701-02","CONCRETE DRIVEWAY",2921870.9300000006,1.7387671035672386E-3,46,6.7024150634371935]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"701-02.01","CONCRETE CURB RAMP (RETROFIT)",23990.95,1.427669997843691E-5,4,27.169818799546999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"701-02.02","CONCRETE DRIVEWAY (8\")",173075.4,1.0299490263820146E-4,2,10.877719816479164]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"701-02.03","CONCRETE CURB RAMP",2477524.7700000005,1.4743425262624412E-3,40,16.922174281284367]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"701-03","CONCRETE MEDIAN PAVEMENT",615643.03,3.6636110004505172E-4,16,392.88004467134652]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"701M01.01","CONCRETE SIDEWALK (100mm)",36302.14,2.160292782716873E-5,1,43.58]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"701M02","CONCRETE DRIVEWAY",101471.36,6.0384276701171222E-5,1,76.64]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"701M02.03","CONCRETE HANDICAP RAMP",2507.4,1.4921208841639329E-6,1,278.60000000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"701M03","CONCRETE MEDIAN PAVEMENT",343483.2,2.0440235147142739E-4,1,318.04000000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"702-01","CONCRETE CURB",1588749.8570000001,9.4544422164080796E-4,31,353.56229640262154]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"702-01.01","EXTRUDED MOUNTABLE CURB",63503.51,3.779010667971331E-5,10,10.273986409966025]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"702-01.02","CONCRETE CURB",13077,7.7819513449037849E-6,2,19.202643171806166]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"702-01.03","MODULAR CURB W/DELINEATOR",120291.24,7.1583740681971711E-5,2,52.460200610553862]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"702-03","CONCRETE COMBINED CURB & GUTTER",13348784.957459999,7.9436870117410158E-3,52,322.50872870104058]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"702M01","CONCRETE CURB",22388.730000000003,1.3323239851203466E-5,1,379.47]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"702M03","CONCRETE COMBINED CURB & GUTTER",546274.07999999996,3.2508054687941252E-4,1,344.86999999999995]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"703-01","CEMENT CONCRETE DITCH PAVING",1750663.1999999997,1.0417967304208581E-3,34,362.85258241768486]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"703-02","CEMENT CONCRETE DITCH PAVING (REINFORCED)",24575,1.4624260480309744E-5,4,614.375]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"703M01","CEMENT CONCRETE DITCH PAVING",75540.5,4.4953161701437974E-5,1,431.66]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-01.01","GUARDRAIL AT BRIDGE ENDS",544596.29399999999,3.2408211841576179E-4,50,66.518388929779505]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-01.04","METAL BEAM GUARD FENCE",144307.36499999999,8.5875421973026793E-5,18,71.386279990106345]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-02.02","SINGLE GUARDRAIL (TYPE 2)",3755871.5920000002,2.2350699691557944E-3,76,16.523559908883264]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-02.03","SINGLE GUARDRAIL (TYPE 2) LONG POST",131607.52000000002,7.8317910626554403E-5,5,19.569891449814129]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-02.10","GUARDRAIL TRANSITION 27IN TO 31IN",2125,1.2645596549606594E-6,3,236.11111111111111]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-03.03","MEDIAN DIVIDER GUARDRAIL (TYPE 2) (27\" MT HT)",8725,5.1921331715443542E-6,2,34.9]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-03.04","MEDIAN DIVIDER GUARDRAIL AT CONCRETE BARRIER",975,5.8020972404077308E-7,1,39]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-04.02","GUARDRAIL TERMINAL (TYPE 12)",8531,5.0766863136326521E-6,6,1066.375]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-04.03","GUARDRAIL TERMINAL (TYPE 13)",137392.50000000003,8.1760476420791737E-5,45,594.77272727272714]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-04.04","GUARDRAIL TERMINAL (TYPE 21)",369838.9,2.2008628318824933E-4,38,1916.2637305699479]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-04.05","GUARDRAIL TERMINAL (TYPE-IN-LINE)",133178.82,7.9252970666949534E-5,33,561.9359493670886]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-04.07","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",967062.99,5.7548651339276401E-4,58,2178.0697972972976]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-04.09","EARTH PAD FOR TYPE 38 GR END TREATMENT",91965.7,5.4727582993042594E-5,12,1135.379012345679]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-04.10","EARTH PAD FOR GUARD RAIL END TREATMENT",1790,1.0652055446492143E-6,1,895]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-04.21","GUARDRAIL DELINEATION ENHANCEMENT",13968.75,8.3126200848149222E-6,3,4.3313953488372094]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-04.23","GUARDRAIL DELINEATION ENHANCEMENT (BI-DIRECTIONAL)",66411,3.9520315880278756E-5,2,23.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-04.25","GUARDRAIL & BARRIER DELINEATOR",480,2.8564171029699597E-7,1,12]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-04.30","TAN ENG ABSG TRM NCHRP 350,TL3(RMV & RPL)",2200,1.309191172194565E-6,1,2200]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-04.50","PORTABLE BARRIER RAIL DELINEATOR",42556.2,2.5324636982793792E-5,14,10.157944360238217]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-05.09","BOLT SIDE GUIDE",17050,1.0146231584507878E-5,1,50]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-06.01","W BEAM GR (TYPE 2) MASH TL3",1431636.14,8.519479074012283E-4,17,18.55700912531757]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-06.10","GR TERMINALTRAILING END (TYPE 13) MASH TL3",99971.86,5.9491943899941339E-5,14,970.60058252427189]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-06.11","GR TERMINAL (IN-INLINE) MASH TL3",45058.18,2.6813532495978957E-5,10,608.89432432432432]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-06.20","TANGENT ENERGY ABSORBING TERM MASH TL-3",567199,3.3753269258072051E-4,21,2578.1772727272728]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-06.30","GR TERMINAL (TYPE 21) MASH TL2",94375.8,5.6161801922181742E-5,9,2247.0428571428574]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-08.10","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-2",239560,1.4255901691405908E-4,4,5207.826086956522]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-08.11","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",111108,6.6118914890997155E-5,4,6172.666666666667]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-08.13","PERMANENT IMPACT ATTENUATOR NCHRP350 TL-3",67000.679999999993,3.9871226721378608E-5,1,16750.169999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-08.50","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-2",126700,7.5397509780477905E-5,3,4368.9655172413795]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-08.51","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",3557028.4940000004,2.1167410470860587E-3,75,4771.9727582506039]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-09.07","REPOSITIONING IMPACT ATTENUATOR (NCHRP350 TL-3)",106539.87,6.3400480586707524E-5,1,977.43]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-11.01","GUARDRAIL AT BRIDGE ENDS (POWDER COATED)",6480,3.856163089009446E-6,1,120]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-11.03","SINGLE GUARDRAIL (TYPE 2) (POWDER COATED)",28295.45,1.6838251524214864E-5,2,27.740637254901962]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-11.08","GUARDRAIL TERMINAL (TYPE 13) (POWDER COATED)",2400,1.4282085514849801E-6,1,2400]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-11.11","TAN ENERGY ABSORB  TERMINAL (NCHRP 350, TL 3)(POWDER COATED)",3700,2.2018215168726777E-6,1,3700]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-11.13","GUARDRAIL TERMINAL (TYPE 21)(POWDER COATED)",3025,1.8001378617675268E-6,1,3025]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-17.97","ATTENUATOR (NARROW- LOW MAINTENANCE)",133982.71,7.9731355072138385E-5,5,26796.541999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-20.20","LOW MAINT CRASH CUSHN NARROW (MASH TL-3)",120000,7.1410427574249006E-5,1,30000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-20.22","REUSABLE CRSH CUSHION NARW (MASH TL-3)",24800,1.4758155032011459E-5,1,24800]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-20.25","TEMPORARY CRASH CUSHION (MASH TL-3)",561800,3.3431981842677575E-4,4,5732.6530612244896]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-80.01","LONGITUDINAL CABLE BARRIER",434253.82,2.58418758016258E-4,3,15.051082074032996]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-80.03","LONGITUDINAL CABLE BARRIER (END TERMINAL) TL-3",47700,2.8385644960763978E-5,1,5300]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705-80.18","CABLE BARRIER TERMINAL",23950,1.4252331170027196E-5,2,3991.6666666666665]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705M01.01","GUARDRAIL AT BRIDGE ENDS",35310.6,2.101287536586064E-5,1,226.35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705M02.02","SINGLE GUARDRAIL (TYPE 2)",124990.5,7.4380208730993077E-5,1,51.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705M02.03","SINGLE GUARDRAIL (TYPE 2) LONG POST",1412.08,8.40310304742046E-7,1,74.319999999999993]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705M03.04","MEDIAN DIVIDER GUARDRAIL AT CONCRETE BARRIER",668.87999999999988,3.9804172329886386E-7,1,74.319999999999993]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705M04.03","GUARDRAIL TERMINAL (TYPE 13)",1699.5,1.0113501805203015E-6,1,566.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705M04.04","GUARDRAIL TERMINAL (TYPE 21)",23175,1.3791138825276838E-5,1,1931.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705M04.05","GUARDRAIL TERMINAL (TYPE-IN-LINE)",5098.5,3.0340505415609043E-6,1,566.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705M04.07","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",22376.75,1.331611071018397E-5,1,2034.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705M07.11","TRUCK MOUNTED ENERGY ATTENUATOR",40000,2.3803475858082999E-5,1,20000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705M08.13","PERMANENT IMPACT ATTENUATOR NCHRP 350 TL-3",34608,2.0594767312413413E-5,1,17304]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"705M08.51","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",115102.5,6.8495989498874968E-5,1,7673.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"706-01","GUARDRAIL REMOVED",205697.03,1.2240760719210936E-4,45,1.5546427009907307]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"706-02.01","GUARDRAIL REMOVED AND RESET",525,3.1242062063733937E-7,1,7]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"706-02.21","RESET SINGLE GUARDRAIL (TYPE 2)",1407.5,8.3758480675629558E-7,2,14.074999999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"706-03.01","POSTS FURNISHED",800,4.7606951716165999E-7,1,100]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"706-03.10","POST BLOCKOUTS & BACKUP PLATES",1000,5.9508689645207496E-7,1,125]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"706-06.03","RADIUS RAIL",7096.2325000000001,4.2228749749273494E-6,3,27.692614634146342]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"706-06.05","RADIUS RAIL LONG POST (6-9 FT)",1030.18,6.130466189869987E-7,1,27.110000000000003]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"706-06.06","RADIUS RAIL LONG POST (9-12 FT)",15997.800000000001,9.5200811520610066E-6,2,32.782377049180333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"706-10.26","ROUNDED END ELEMENT",1396,8.3074130744709667E-7,3,73.473684210526315]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"706-10.73","REMOVAL OF GUARDRAIL & POST FOR REUSE",2825,1.6811204824771119E-6,1,5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"706-80.18","CABLE BARRIER TERMINAL (REMOVAL)",10755,6.4001595713420668E-6,4,827.30769230769226]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"706-80.19","CABLE BARRIER (REMOVAL)",114380.15,6.8066128479222807E-5,4,2.8191198580336674]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"706M01","GUARDRAIL REMOVED",1055.75,6.2826299092927813E-7,1,1.03]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-01.01","CHAIN-LINK FENCE (4-FOOT)",89887.709999999992,5.349099837308414E-5,4,10.565081100141043]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-01.02","END & CORNER POST ASSEMBLY(CHAIN-LINK FENCE 4')",9785.83,5.8234192039076088E-6,4,155.33063492063491]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-01.11","CHAIN LINK FENCE (6 FOOT)",518592.25,3.0860745257659862E-4,11,10.498031336666735]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-01.12","END & CORNER POST ASSEMBLY(CHAIN-LINK FENCE 6')",43582.75,2.593552343634667E-5,9,178.61782786885246]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-01.13","GATE - CHAIN-LINK FENCE-6 FOOT (12')",5907,3.5151782973424069E-6,4,984.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-01.22","TEMP GATE - CHAIN LINK FENCE-6FT (DESCRIPTION)",500,2.9754344822603748E-7,1,500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-01.50","CHAIN-LINK FENCE (8 FOOT)",36288.5,2.1594810841901123E-5,2,16.917715617715618]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-01.51","END & CORNER POST ASSEMBLY (CHAIN-LINK FENCE __') (CHAIN-LINK FENCE 8')",4145.75,2.46708150096619E-6,2,259.109375]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-01.52","GATE - CHAIN-LINK FENCE (8 FOOT - 4' WIDE)",1751,1.0419971556875833E-6,2,875.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-02.01","CHAIN-LINK FENCE (4') (VINYL COATED)",453235.3,2.6971438803952515E-4,1,8.33]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-02.02","END & CORNER POST ASSEMBLIES (4' VINYL COATED)",21879.200000000001,1.3020025224854239E-5,1,156.28]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-02.11","CHAIN-LINK FENCE (6 FOOT) (VINYL COATED)",7488,4.4560106806331376E-6,1,16.64]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-03.01","STOCK FENCE",311103.43,1.8513357463429537E-4,12,4.739901424544831]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-03.02","END, BRACED LINE, CORNER POST ASSEMBLY(STOCK FENCE)",56193.82,3.3440205943586544E-5,12,155.66155124653739]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-03.03","STOCK FENCE GATE (DESCRIPTION)",800,4.7606951716165999E-7,1,800]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-03.20","DRIVE GATE (STOCK FENCE) (DESCRIPTION)",4350,2.5886279995665262E-6,2,870]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-04","WATER CROSSING",1921.5,1.1434594715326622E-6,4,7.3903846153846153]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-05","WATER GATE",1400,8.3312165503290501E-7,1,25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-06.01","REMOVAL OF FENCE (CHAIN LINK)",187088.63999999998,1.1133399813903953E-4,18,2.7642303714429239]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-06.04","REMOVAL AND RESET GATE (METAL STOCK, DRIVE ENT. GATE)",3000,1.7852606893562249E-6,1,750]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-06.05","REMOVAL OF FENCE (CHAIN LINK)",2500,1.4877172411301874E-6,1,2500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-07.01","CHAIN-LINK FENCE (BRIDGES)",168564.36,1.0031044184483029E-4,3,25.166372051358611]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-08.01","FENCE (WOOD PLANK)",13143.599999999999,7.821584132207492E-6,2,10.406650831353918]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-08.02","GATE (POWER)",10000,5.9508689645207496E-6,1,10000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-08.11","HIGH-VISIBILITY CONSTRUCTION FENCE",928790.16900000011,5.5271085912540828E-4,90,1.758898098898501]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-10.01","ROCKFALL FENCE (TYPE I)",91000,5.4152907577138828E-5,1,260]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707-11.01","PEDESTRIAN CONSTRUCTION BARRIER FENCE",4950,2.9456801374377711E-6,1,9.9]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707M01.11","CHAIN LINK FENCE (1.8m)",158169.84,9.412479919792127E-5,1,35.479999999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707M01.12","END & CORNER POST ASSEMBLY(CHAIN-LINK FENCE 1.8m)",19106.5,1.1370027787061571E-5,1,180.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"707M06.01","REMOVAL OF FENCE (WOVEN WIRE)",2060,1.2258790066912745E-6,1,20.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"708-01.01","MONUMENTS (R.O.W.)",34307.550000000003,2.0415973454374387E-5,2,179.62068062827225]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"708-02.01","MARKERS (CONCRETE R.O.W. POSTS)",918726.3600000001,5.4672201826111183E-4,59,202.94375082836316]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"708-02.04","(CONCRETE R.O.W. POSTS) MOVE AND RESET",1200,7.1410427574249004E-7,1,200]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"708-03.10","SIGN WALLS",120000,7.1410427574249006E-5,1,30000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"708-03.11","CONCRETE PAD",2490000,1.4817663721656668E-3,1,15000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"708M02.01","MARKERS (CONCRETE R.O.W. POSTS)",32484.870000000003,1.9331320469949119E-5,1,268.47000000000003]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"709-01.01","RUBBLE STONE RIP-RAP",18013.370000000003,1.0719520447942916E-5,10,137.08805175038052]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"709-01.02","RUBBLE STONE RIP-RAP",3814,2.2696614230682141E-6,2,200.73684210526315]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"709-04","REINFORCED CONCRETE SLOPE PAVEMENT",249310.59,1.4836146525573572E-4,7,566.61497727272729]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"709-05.05","MACHINED RIP-RAP (CLASS A-3)",3105361.3616000004,1.8479598550367341E-3,108,35.421264516323312]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"709-05.06","MACHINED RIP-RAP (CLASS A-1)",13002951.799999999,7.7378862313779214E-3,100,33.164375563401784]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"709-05.07","MACHINED RIP-RAP (CLASS A-2)",59920,3.5657606835408333E-5,2,39.866932801064536]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"709-05.08","MACHINED RIP-RAP (CLASS B)",5214099.0086100008,3.1028419968275665E-3,73,34.254304254157958]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"709-05.09","MACHINED RIP-RAP (CLASS C)",1876752.625,1.1168308950195349E-3,50,33.730043227953168]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"709-05.10","MACHINED RIP-RAP (GROUTED)",33696.720000000001,2.0052476525414567E-5,2,180.19636363636366]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"709-05.21","DUMPED RIP-RAP",7500,4.4631517233905629E-6,1,25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"709-05.81","ROCK RIFFLES",464450,2.7638810905716621E-4,5,92890]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"709-05.83","EMBEDDED RIPRAP",905.44999999999993,5.3882143039253122E-7,1,27.86]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"709M04","REINFORCED CONCRETE SLOPE PAVEMENT",92554.8,5.5078148683742513E-5,1,474.64000000000004]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"709M05.05","MACHINED RIP-RAP (CLASS A-3)",30865.599999999999,1.8367714111131165E-5,1,40.4]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"709M05.06","MACHINED RIP-RAP (CLASS A-1)",30744.399999999998,1.8295589579281172E-5,1,40.4]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"709M05.08","MACHINED RIP-RAP (CLASS B)",344028.96,2.0472712609603507E-4,1,48.84]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"709M05.09","MACHINED RIP-RAP (CLASS C)",8498.16,5.0571436599531657E-6,1,48.839999999999996]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710-02","AGGREGATE UNDERDRAINS (WITH PIPE)",6625881.3095999993,3.9429751447896738E-3,77,4.9394443611497767]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710-04","FILTER CLOTH UNDERDRAIN (WITH PIPE)",109113.69,6.4932127142533814E-5,3,5.5624841965742249]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710-04.01","GEOCOMPOSITE EDGE DRAIN",1620,9.6404077225236149E-7,1,5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710-05","LATERAL UNDERDRAIN",413475.66000000003,2.4605394726787339E-4,55,3.4008067336482717]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710-06.10","LATERAL UNDERDRAIN ENDWALL (1:1)",7462.5,4.4408359647736099E-6,2,438.97058823529414]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710-06.11","LATERAL UNDERDRAIN ENDWALL (2:1)",91412.08,5.4398130985428799E-5,14,540.89988165680461]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710-06.12","LATERAL UNDERDRAIN ENDWALL (3:1)",260628.87,1.5509682537411131E-4,30,467.07682795698923]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710-06.13","LATERAL UNDERDRAIN ENDWALL (4:1)",288244.30000000005,1.7153040590700086E-4,33,501.29443478260879]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710-06.14","LATERAL UNDERDRAIN ENDWALL (5:1)",5594.3,3.3290946248218435E-6,4,399.59285714285716]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710-06.15","LATERAL UNDERDRAIN ENDWALL (6:1)",1294815.1000000001,7.705274993382832E-4,52,498.7731510015409]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710-09.01","6\" PERFORATED PIPE WITH VERTICAL DRAIN SYSTEM",650437.88,3.870670593440672E-4,40,36.21591759465479]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710-09.02","6\" PIPE UNDERDRAIN",48366.770000000004,2.8782431050711329E-5,34,15.507140109009299]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710-10.01","4\" PERFORATED PLASTIC PIPE",8100,4.8202038612618072E-6,1,6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710-10.08","18\" PERFORATED PLASTIC PIPE",14445.11,8.596095678808833E-6,2,33.829297423887589]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710-13.03","FILTER CLOTH",33343.699999999997,1.9842398949229051E-5,4,3.0186221256563459]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710M02","AGGREGATE UNDERDRAINS (WITH PIPE)",101056.62,6.0137470361736692E-5,1,18.579999999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710M05","LATERAL UNDERDRAIN",5698.68,3.3912097950735109E-6,1,10.14]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710M06.15","LATERAL UNDERDRAIN ENDWALL (6:1)",14935,8.8876227985117402E-6,1,515]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710M09.01","150mm PERFORATED PIPE WITH VERTICAL DRAIN SYSTEM",10723.77,6.3815750075658685E-6,1,70.09]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"710M09.02","150mm PIPE UNDERDRAIN",2618.7000000000003,1.558354055739049E-6,1,87.29]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711-01","CONCRETE MEDIAN BARRIER",6600,3.927573516583695E-6,1,110]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711-01.01","CONCRETE MEDIAN BARRIER (MODIFIED)",38400,2.2851336823759681E-5,1,320]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711-01.08","MEDIAM BARRIER EMERGENCY ACCESS GATE",610722,3.6343265957500416E-4,2,152680.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711-02","CONCRETE MEDIAN B.R (BR PIER PROTECTION)",41174.85,2.4502613698379719E-5,1,204.85]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711-04.01","CONCRETE GLARE SCREEN MEDIAN BARRIER @ BRIDGE PIERS",82130,4.8874486805608919E-5,2,376.74311926605503]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711-05.01","REMOVAL & DISPOSAL OF CONCRETE MEDIAN BARRIER",170480,1.0145041410714975E-4,4,36.988500759383811]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711-05.70","32IN SINGLE SLOPE CONCRETE BARRIER WALL",686560.46,4.0856313336810895E-4,10,52.804219350869097]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711-05.71","51IN SINGLE SLOPE CONCRETE BARRIER WALL",4400346.0299999993,2.6185882623079087E-3,12,87.301524283787003]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711-05.72","SINGLE SLOPE HALF CONCRETE BARRIER WALL",1446304.98,8.6067714187138043E-4,11,73.115867751883115]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711-05.74","CONC MEDIAN BARR SING SLOPE (STD-1-3SS)",75680,4.5036176323493038E-5,1,110]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711-05.77","FLARED S/S CONCRETE MEDIAN BARRIER WALL",414985.61,2.4695249872717115E-4,7,233.26903316469927]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711-05.78","GRADE SEPARATED SINGE SLOPE MEDIAN WALL",1291386.8,7.6848736293117653E-4,4,173.01538049303323]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711M01.05","CONCRETE BARRIER WALL (MODIFIED)",54194.87,3.2250656991923665E-5,1,558.71]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711M02.04","REINFORCED CONCRETE MEDIAN BARRIER (1300 mm)",72287.399999999994,4.3017284518589724E-5,1,380.46]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711M05.70","SINGLE SLOPE MEDIAN BARRIER WALL",356598.36,2.1220701133229975E-4,1,192.34]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711M05.72","SINGLE SLOPE HALF CONCRETE BARRIER WALL (0.85 m)",340261.83,2.0248535639580355E-4,2,184.82445953286259]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711M05.75","SINGLE SLOPE CONCRETE BARRIER WALL",807488.1,4.8052558735098278E-4,1,272.33999999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"711M05.77","FLARED S/S CONCRETE MEDIAN BARRIER WALL",109419.36,6.5114027354172313E-5,1,369.66]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-01","TRAFFIC CONTROL",12581669.709999999,7.4871867799089775E-3,105,119825.42580952382]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-01.05","FLAGMAN",23040,1.3710802094255808E-5,1,32]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-01.51","PORTABLE BARRIER RAIL DELINEATOR (DOUBLE)",8106,4.8237743826405203E-6,1,7]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-02.02","INTERCONNECTED PORTABLE BARRIER RAIL",23564702.460000005,1.402304565273798E-2,97,29.526058859563886]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-02.36","REMOVE AND RELOCATE PORTABLE BARRIER RAIL",209664,1.2476829905772786E-4,1,14.4]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-02.47","BRIDGE MOUNTED INTERCONNECTED PORTABLE BARRIER RAIL",179984,1.0710611997103026E-4,5,53.407715133531156]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-04.01","FLEXIBLE DRUMS (CHANNELIZING)",1294961.1099999999,7.7061438797603398E-4,98,34.657525458657275]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-04.02","FLEXIBLE DRUMS (CHANNELIZATION)",55016,3.273930069520736E-5,3,31.223609534619751]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-04.10","TEMPORARY FLEXIBLE TUBULAR DELINEATOR",42187.08,2.5104978507575404E-5,3,48.997770034843207]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-04.50","PORTABLE BARRIER RAIL DELINEATOR",218428.52000000002,1.2998395006342002E-4,48,11.478536782750812]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-05.01","WARNING LIGHTS (TYPE A)",179649.55,1.0690709315851187E-4,80,33.219221523668637]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-05.03","WARNING LIGHTS (TYPE C)",82348.61,4.900457875204231E-5,43,34.155375362919948]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-06","SIGNS (CONSTRUCTION)",708561.14579999982,4.2165545320064813E-4,105,7.4833875560156091]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-06.01","VERTICAL PANELS",165217.76999999999,9.8318929988032739E-5,29,11.942877692641318]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-06.16","SIGNS (CONSTRUCTION)(REDUCED SPEED WARNING)",15105.119999999999,8.9888589813361668E-6,7,656.74434782608694]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-07.03","TEMPORARY BARRICADES (TYPE III)",385700.01,2.2952502191243431E-4,82,14.92358328496808]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-08.01","UNIFORMED POLICE OFFICER",294000,1.7495554755691005E-4,2,1]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-08.03","ARROW BOARD (TYPE C)",351511.43999999994,2.0917985189699973E-4,85,1167.8120930232558]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-08.10","MOBILE MESSAGE SIGN UNIT W/ATTENUATOR",752541.2,4.4782740716032025E-4,16,30.376249293614272]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-09.01","REMOVABLE PAVEMENT MARKING LINE",712541.00999999989,4.2402381823572688E-4,32,2.2568334885311949]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-09.02","REMOVABLE PAVEMENT MARKING (8\" BARRIER LINE)",771236.17,4.5895253883688493E-4,15,3.4007521253703965]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-09.03","REMOVABLE PAVEMENT MARKING(CHANNELIZING STRIPING)",612,3.6419318062866989E-7,1,68]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-09.04","REMOVABLE PAVEMENT MARKING (STOP LINE)",37981.089999999997,2.2602048971966939E-5,17,17.154963866305327]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-09.05","REMOVABLE PAVEMENT MARKING (ARROW)",8544.02,5.0844343450244584E-6,7,189.86711111111111]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-09.07","REMOVABLE PAVEMENT MARKING (STOP AHEAD)",300,1.7852606893562251E-7,1,300]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-09.21","REMOVABLE WET REFLECTIVE PAVEMENT MARKING TAPE",6572,3.9109110834830372E-6,1,4]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-09.30","REMOVABLE BLACK-OUT TAPE (6\")",38608.6,2.297547195035958E-5,3,2.4160575719649562]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712-12.47","BRIDGE MOUNTED INTERCONNECTED PORTABLE BARRIER RAIL",18082.260000000002,1.0760515984239499E-5,1,80.010000000000005]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712M01","TRAFFIC CONTROL",366924.57,2.1835200359331214E-4,1,366924.57]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712M02.02","INTERCONNECTED PORTABLE BARRIER RAIL",660806.40000000002,3.9323722973166848E-4,1,54.2]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712M04.01","FLEXIBLE DRUMS (CHANNELIZING)",42642,2.5375695438509382E-5,1,47.38]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712M04.50","PORTABLE BARRIER RAIL DELINEATOR",6120.7,3.6423483671142153E-6,1,12.62]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712M05.01","WARNING LIGHTS (TYPE A)",10176.4,6.0558422930548959E-6,1,53.559999999999995]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712M05.03","WARNING LIGHTS (TYPE C)",13925.6,8.2869420852330157E-6,1,53.56]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712M06","SIGNS (CONSTRUCTION)",14832,8.8263288481771757E-6,1,92.7]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712M06.16","SIGNS (CONSTRUCTION)(REDUCED SPEED WARNING)",2420.5,1.4404078328622476E-6,1,1210.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712M07.03","TEMPORARY BARRICADES (TYPE III)",10602.57,6.309450475715877E-6,1,50.73]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712M08.03","ARROW BOARD (TYPE C)",11124,6.6197466361328822E-6,1,1390.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712M08.06","UNIFORMED POLICE OFFICER",346080,2.0594767312413412E-4,1,41.2]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712M08.10","MOBILE MESSAGE SIGN UNIT W/ATTENUATOR",735420,4.3763880538878497E-4,1,87.55]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712M09.01","REMOVABLE PAVEMENT MARKING LINE",2131.1999999999998,1.2682491937186622E-6,1,5.92]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712M09.02","REMOVABLE PAVEMENT MARKING (200mm BARRIER LINE)",3811.9999999999995,2.2684712492753096E-6,1,9.5299999999999994]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"712M12.10","TEMP CURB W/FLEXIBLE DELINEATORS",127925.99999999999,7.6127086315528142E-5,1,142.13999999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-01.01","CLASS A CONCRETE (FOUNDATION FOR SIGN SUPPORTS)",108577.91,6.4613291485152719E-5,38,615.03291038858049]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-01.02","STEEL BAR REINFORCEMENT(FOUNDATION FOR SIGN SUPPORTS)",109535.12600000003,6.5182918183827012E-5,38,2.5438298581903869]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-01.10","SIGNING",2000,1.1901737929041499E-6,1,2000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-02.04","DELINEATOR (MILE MARKER) & STEEL POST",10340.710000000001,6.1536210210109366E-6,12,169.51983606557377]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-02.11","REMOVAL OF EXISTING DELINEATORS",180,1.071156413613735E-7,1,4]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-02.14","FLEXIBLE DELINEATOR (WHITE)",167022.85999999999,9.9393115393949416E-5,33,33.172365441906656]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-02.15","FLEXIBLE DELINEATOR (YELLOW)",39617.08,2.3575605183693571E-5,25,33.72699720765511]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-02.21","SIGN POST DELINEATION ENHANCEMENT",18824.87,1.1202433464413772E-5,9,7.0930180859080645]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-02.26","CONCRETE BARRIER/PARAPET DELINEATOR",3844.47,2.2877937208031088E-6,3,10.679083333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-02.27","CONCRETE BARRIER/PARAPET DELINEATOR (BI-DIRECTIONAL)",1190,7.0815340677796929E-7,1,8.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-02.30","FLEXIBLE TUBULAR DELINEATOR",1886,1.1223338867086135E-6,1,46]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-02.34","DELINEATORS (ALL)",6120,3.6419318062866988E-6,1,34]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-02.36","FLEXIBLE BARRIER DELINEATOR",1109.4000000000001,6.6018940292393204E-7,2,12.9]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-05","STEEL HOLLOW SQUARE POST (BREAKAWAY) SIGN SUPPORTS",34302.42,2.0412920658595584E-5,9,5.3040358855336827]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-06","STEEL I-BEAMS & WF-BEAMS(BREAKAWAY) SIGN SUPPORT",561336.77049999998,3.3404415662127566E-4,33,4.1596138585431186]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-06.01","STEEL I-BEAMS & WF-BEAMS(BREAKSAFE) SIGN SUPPORT",44,2.61838234438913E-8,1,5.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-09.01","STEEL OVERHEAD SIGN STRUCTURE (SPAN 81')",824675.33000000007,4.9075348271029082E-4,12,63436.56384615384]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-09.02","STEEL OVERHEAD SIGN STRUCTURE (SPAN 91')",703612.14,4.1871036469860289E-4,10,70361.214000000007]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-09.03","STEEL OVERHEAD SIGN STRUCTURE (SPAN 92')",425805,2.5339097594377581E-4,7,60829.285714285717]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-09.04","STEEL OVERHEAD SIGN STRUCTURE (SPAN 112')",322405,1.9185899085063124E-4,5,64481]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-09.05","STEEL OVERHEAD SIGN STRUCTURE (SPAN 112')",337150,2.0063354713881708E-4,5,67430]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-09.06","STEEL OVERHEAD SIGN STRUCTURE (SPAN 128')",224230,1.3343633479144878E-4,3,74743.333333333328]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-09.07","STEEL OVERHEAD SIGN STRUCTURE (SPAN 128')",241600,1.4377299418282132E-4,3,80533.333333333328]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-09.08","STEEL OVERHEAD SIGN STRUCTURE (SPAN 141')",272335,1.6206298994527585E-4,3,90778.333333333328]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-09.09","STEEL OVERHEAD SIGN STRUCTURE (SPAN 161')",276030,1.6426183602766625E-4,3,92010]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-09.10","STEEL OVERHEAD SIGN STRUCTURE (SPAN 172')",311895,1.8560462756891992E-4,3,103965]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-09.11","STEEL OVERHEAD SIGN STRUCTURE (SPAN 165.50')",46000,2.7373997236795451E-5,1,46000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-09.12","STEEL OVERHEAD SIGN STRUCTURE (SPAN 80.50')",41100,2.4458071444180282E-5,1,41100]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-09.13","STEEL OVERHEAD SIGN STRUCTURE (SPAN 187')",100000,5.9508689645207498E-5,1,100000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-09.14","STEEL OVERHEAD SIGN STRUCTURE (SPAN 175')",100000,5.9508689645207498E-5,1,100000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-11.01","\"U\" SECTION STEEL POSTS",232487.49199999997,1.3835026007820659E-4,62,3.3843589948509845]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-11.02","PERFORATED/KNOCKOUT SQUARE TUBE POST",540742.72952000005,3.2178891268908066E-4,77,4.0022169769140135]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-11.03","2 1/2\" DIA ROUND STEEL TUBE SIGN POST",21397.8,1.273355039290221E-5,8,8.1670992366412207]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-11.04","SURFACE MNT BREAKAWAY BASE FOR SIGN POST",3600,2.1423128272274701E-6,1,240]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-11.05","SQUARE TUBE SIGN SUPPORT",23602.340749999999,1.4045443705921839E-5,6,6.8163341145348246]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-11.21","P POST SLIP BASE",154140.17000000001,9.1726795383895244E-5,33,383.43325870646771]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-11.22","U POST SLIP BASE",9137.5,5.4376065163308356E-6,2,397.28260869565219]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-11.23","ROUND POST SLIP BASE",17879.2,1.063967763904594E-5,8,357.584]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-13.02","FLAT SHEET ALUMINUM SIGNS (0.080\" THICK)",307229.79700000002,1.8282842639433104E-4,77,12.906859448102113]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-13.03","FLAT SHEET ALUMINUM SIGNS (0.100\" THICK)",371464.11499999993,2.2105342733866665E-4,82,14.197663370120871]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-13.04","FLAT SHEET ALUMINUM SIGNS (0.125\" THICK)",3040,1.8090641652143079E-6,2,49.83606557377049]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-14","EXTRUDED ALUMINUM PANEL SIGNS",775726.89,4.6162490746452019E-4,26,22.250721108338354]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-14.01","EXTRUDED ALUMINUM PANEL SIGNS (ANODIZED)",2547,1.5156863252634351E-6,1,18]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-14.21","STREET NAME SIGN (RIGID 0.100IN THICK",42057.880000000005,2.5028093280553798E-5,11,18.238456201214227]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-14.22","STREET NAME SIGN (SUSPENDED 0.100IN THICK)",90538.739999999991,5.3878417795281337E-5,9,55.579337016574577]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-15","REMOVAL OF SIGNS, POSTS AND FOOTINGS",112741.23999999999,6.7090834613758526E-5,87,1295.8763218390804]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-15.01","REMOVAL OF EXISTING SIGN POST",150,8.9263034467811255E-8,1,50]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-15.02","REMOVAL & RELOCATION OF SIGN & SUPPORT",9446.25,5.6213395956104131E-6,10,100.49202127659575]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-15.04","INSTALLATION OF LETTERS & ARROWS",5912.67,3.5185524400452904E-6,3,1970.89]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-15.06","MILE POST SIGN",1252.52,7.4535823954415293E-7,2,156.565]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-15.07","SUSPENDED FLAT SHEET ALUMINUM SIGN (0.080\" THICK)",42248.58,2.5141576351707207E-5,25,299.63531914893616]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-15.08","SUSPENDED FLAT SHEET ALUMINUM SIGN (0.100\" THICK)",4060,2.4160527995954244E-6,1,290]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-15.11","SIGN SUPPORT ASSEMBLY ON BRIDGES (SIGN 16)",25140,1.4960484576805166E-5,2,12570]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-15.12","SIGN SUPPORT ASSEMBLY ON BRIDGES (SIGN 17)",7140,4.2489204406678157E-6,1,7140]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-15.35","METAL BARRICADE (TYPE III)",13813.5,8.2202328441407386E-6,6,575.5625]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-15.36","REMOVE SIGN, SUPPORT & FOOTING",100,5.9508689645207499E-8,1,50]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-15.40","SIGN INSTALLATION (DESCRIPTION)",41116.409999999996,2.4467836820151057E-5,15,2741.0940000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-15.41","SIGN REMOVAL (DESCRIPTION)",765,4.5524147578583735E-7,1,765]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.01","CHANGEABLE MESSAGE SIGN UNIT",2390551.4900000002,1.4225858669929838E-3,80,7114.7365773809533]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.03","CHANGEABLE MESSAGE SIGN",9000,5.3557820680686751E-6,1,4500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.04","CHANGEABLE MESSAGE SIGN UNIT  (DESCRIPT)",85863.44,5.1096208028298953E-5,2,7155.2866666666669]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.05","RAILROAD CROSS-BUCK SIGN & SUPPORT",840,4.9987299301974301E-7,1,210]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.06","DEAD END SIGN AND SUPPORT",1060,6.3079211023919949E-7,4,212]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.07","END OF ROADWAY SIGN AND SUPPORT",14660.960000000001,8.7245451854080132E-6,22,187.96102564102563]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.09","RAILROAD ADVANCE WARNING SIGN AND SUPPORT",350,2.0828041375822625E-7,1,175]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.20","SIGNS (R3-1)",56258.75,3.3478844935773176E-5,33,297.6653439153439]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.21","SIGNS (R3-2)",36048.35,2.1451900723718157E-5,23,439.61402439024391]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.22","SIGNS (R3-5a)",6205.66,3.6929069498367838E-6,12,193.92687499999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.23","SIGNS (STREET NAME SIGNS)",7889.8,4.6951165956275814E-6,14,179.31363636363636]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.24","SIGNS (R10-12)",3925.4,2.3359541033329752E-6,10,206.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.25","SIGNS (R10-10)",2669.15,1.588376189665056E-6,9,166.82187500000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.26","SIGNS (R10-11A)",3405,2.0262708824193152E-6,6,227]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.27","SIGNS (R6-1R w/ 1-P8 SUPPORT)",1135,6.7542362747310514E-7,3,227]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.28","SIGNS (R6-3 w/ 1-P8 SUPPORT)",1125,6.6947275850858439E-7,2,160.71428571428572]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.29","SIGNS (Bus Stop)",1340,7.9741644124578049E-7,3,191.42857142857142]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.35","SIGNS (DO NOT MOW)",2080,1.237780744620316E-6,1,160]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.41","RELOCATE SIGN",9082.2200000000012,5.4047101126949655E-6,7,1297.4600000000003]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.42","RELOCATE SIGN & REWIRE",4244,2.5255487885426065E-6,1,4244]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.50","REMOVE AND REPLACE SIGN (NO TRUCKS)",45962,2.735138393473027E-5,6,2298.1]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.51","REMOVE AND REPLACE SIGN (BONNY VALE LANE)",265,1.5769802755979987E-7,1,265]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-16.52","REMOVE AND REPLACE SIGN (SR 153, HWY 58, I-75 DIRECT.)",371,2.2077723858371982E-7,1,371]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-17.02","INSTALL AUXILIARY SUPPORT FOR EXIT NUMBER PANEL",4933,2.9355636601980861E-6,8,140.94285714285715]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-17.30","MODIFY EXISTING OVERHEAD SIGN STRUCTURE",2257.5,1.3434086687405592E-6,1,2257.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-17.31","MODIFY EXISTING OVERHEAD SIGN STRUCTURE",2310,1.3746507308042933E-6,1,2310]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-17.32","MODIFY EXISTING OVERHEAD SIGN STRUCTURE",2310,1.3746507308042933E-6,1,2310]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-17.33","MODIFY EXISTING OVERHEAD SIGN STRUCTURE",2677.5,1.5933451652504309E-6,1,2677.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-17.50","SIGN MOUNTED ON BRIDGE PARAPET",25479.38,1.5162445167723071E-5,2,3184.9225000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-17.62","SIGN MOUNTED ON CONCRETE MEDIAN BARRIER (STD.T-S-21)",2673,1.5906672742163965E-6,1,121.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-17.63","SIGN MOUNTED ON CONCRETE MEDIAN BARRIER (SIDE WALL MOUNT)",3213,1.9120141983005168E-6,1,803.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-20.30","SIGN ADJUSTMENTS",4750,2.8266627581473564E-6,1,125]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-30.09","BARRIER MOUNTED SIGN SUPPORT (M.M. 12)",15206.15,9.0489806104847204E-6,10,345.59431818181815]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-30.10","BARRIER MOUNTED SIGN SUPPORT (E5-1A)",4873.8999999999996,2.9003940246177679E-6,4,609.23749999999995]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713-99.91","SIGNS",2021.25,1.2028193894537567E-6,1,2021.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M01.01","CLASS A CONCRETE (FOUNDATION FOR SIGN SUPPORTS)",5768,3.4324612187355688E-6,1,721]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M01.02","STEEL BAR REINFORCEMENT(FOUNDATION FOR SIGN SUPPORTS)",6296.5,3.7469646435104903E-6,1,5.14]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M09.01","STEEL OVERHEAD SIGN STRUCTURE (SPAN 22m)",44345.62,2.6389497377043066E-5,1,44345.62]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M09.02","STEEL OVERHEAD SIGN STRUCTURE (SPAN 17.7m)",40658.22,2.4195173955065685E-5,1,40658.22]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M09.03","STEEL OVERHEAD SIGN STRUCTURE (SPAN 19.8m)",44541.32,2.6505955882678737E-5,1,44541.32]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M09.04","STEEL OVERHEAD SIGN STRUCTURE (SPAN 13.9m)",42089.919999999998,2.504715986471612E-5,1,42089.919999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M09.05","STEEL OVERHEAD SIGN STRUCTURE (SPAN 17.5m)",46181.08,2.7481755572004993E-5,1,46181.08]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M09.06","STEEL OVERHEAD SIGN STRUCTURE (SPAN 14.7m)",42945.85,2.5556512591996346E-5,1,42945.85]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M09.07","STEEL OVERHEAD SIGN STRUCTURE (SPAN 15.9m)",40526.379999999997,2.4116717698637443E-5,1,40526.379999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M11.01","\"U\" SECTION STEEL POSTS",3351.72,1.9945646525763488E-6,1,9.01]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M11.02","PERFORATED/KNOCKOUT SQUARE TUBE POST",9672.5999999999985,5.7560375146223396E-6,1,10.29]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M11.05","SQUARE TUBE SIGN SUPPORT",5922.58,3.5244497511891304E-6,1,5922.58]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M13.02","FLAT SHEET ALUMINUM SIGNS (2.032mm THICK)",5622.75,3.3460248470259047E-6,1,114.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M13.03","FLAT SHEET ALUMINUM SIGNS (2.540mm THICK)",10111.200000000001,6.0170426274062208E-6,1,126.39000000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M14","EXTRUDED ALUMINUM PANEL SIGNS",15386.76,9.1564592548529293E-6,1,284.94]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M15","REMOVAL OF SIGNS, POSTS AND FOOTINGS",1339,7.9682135434932846E-7,1,1339]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M16.04","CHANGEABLE MESSAGE SIGN UNIT  (DESCRIPT)",87550,5.2099857784379168E-5,1,8755]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M17.02","INSTALL AUXILIARY SUPPORT FOR EXIT NUMBER PANEL",1128.8800000000001,6.7178169566681849E-7,1,141.11000000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"713M30.09","BARRIER MOUNTED SIGN SUPPORT",5687.66,3.3846519374746087E-6,1,517.05999999999995]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-01","STRUCTURAL LIGHTING",9250,5.5045537921816935E-6,1,9250]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-01.01","STRUCTURAL LIGHTING (BRIDGE OVERPASS AND UNDERPASS)",53459.8,3.1813226466948644E-5,7,7637.1142857142859]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-01.02","STRUCTURAL LIGHTING (BR. NO. 2)",16175,9.6255305501123137E-6,3,5391.666666666667]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-01.03","STRUCTURAL LIGHTING (BR. NO. 3)",3675,2.1869443444613756E-6,1,3675]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-01.04","STRUCTURAL LIGHTING (BR. NO. 4)",3675,2.1869443444613756E-6,1,3675]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-01.20","STRUCTURAL LIGHTING (RET. WALL NO. 3)",15482.56,9.2134685795330374E-6,3,5160.8533333333335]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-01.21","STRUCTURAL LIGHTING (RET. WALL NO. 4)",22142.989999999998,1.3177003197269331E-5,3,7380.996666666666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-01.22","STRUCTURAL LIGHTING (RET. WALL NO. 4)",16422.989999999998,9.7731061495634614E-6,2,8211.494999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-01.23","STRUCTURAL LIGHTING (RET. WALL NO. 5)",16272,9.6832539790681643E-6,2,8136]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-01.24","STRUCTURAL LIGHTING (RET. WALL NO. 5)",18109.5,1.0776726151298852E-5,2,9054.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-01.31","STRUCTURAL LIGHTING (DESC) (MEDIAN BARRIER)",9743.2900000000009,5.7981042073325385E-6,1,9743.2900000000009]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-01.32","STRUCTURAL LIGHTING (DESC) (MEDIAN BARRIER)",9743.2900000000009,5.7981042073325385E-6,1,9743.2900000000009]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-01.38","LIGHT POLE RELOCATION",24168,1.4382060113453749E-5,1,1272]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-02.01","ENCASED CONDUIT (2\" PVC, SCHEDULE 80)",42885,2.5520301554347238E-5,2,15.824723247232471]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-02.02","ENCASED CONDUIT (2\" PVC, SCHEDULE 40)",9300,5.5343081370042977E-6,1,15.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-02.04","ENCASED CONDUIT (CONDUIT IN MEDIAN BARRIER)",157200,9.3547660122266193E-5,1,6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-03","JACKED OR BORED CONDUIT",156247.54,9.298086365687145E-5,11,15.846606490872212]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-03.01","DIRECT BURIAL CONDUIT (2\" PVC, SCHEDULE 40)",780310.65999999992,4.6435264892787028E-4,19,6.7122342841413483]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-03.02","DIRECT BURIAL CONDUIT (3\" PVC, SCHEDULE 40)",103500,6.1591493782789763E-5,1,10]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-03.03","DIRECT BURIAL CONDUIT (2\" PVC, SCHEDULE 80)",7874.4000000000005,4.6859522574222193E-6,1,8.16]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-04.01","CONDUIT (STRUCTURES - 1\" RGS)",16800,9.9974598603948597E-6,1,10.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-04.02","CONDUIT (STRUCTURES - 2\" RGS)",73770,4.389956035126957E-5,2,51.515363128491622]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-04.03","CONDUIT (LIGHTING)",32385.200000000001,1.9272008158979739E-5,4,10.104586583463339]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-05.02","PULL BOXES (TYPE A)",4345,2.5856525650842661E-6,2,362.08333333333331]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-05.03","PULL BOXES (TYPE B)",90797.739999999991,5.4032545301462425E-5,7,496.16251366120224]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-05.04","PULL BOXES (TYPE C)",55309.38,3.2913887288888469E-5,11,570.19979381443295]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-05.05","PULL BOXES (MEMPHIS STANDARD)",49377.75,2.9384052001286447E-5,7,382.77325581395348]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-05.06","PULL BOXES (SEE PLANS)",1726,1.0271199832762814E-6,2,246.57142857142858]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-05.07","PULL BOXES (MEMPHIS STANDARD)",2000,1.1901737929041499E-6,1,500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-05.46","WOOD POLE (DESCRIPTION)",13210,7.8610979021319104E-6,4,1100.8333333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-06.03","CABLE (1/C # 10 AWG)",48642,2.8946216817221831E-5,5,1.4762367223065251]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-06.04","CABLE (1/C # 8 AWG)",6128.85,3.6471983253203002E-6,2,0.63478508544795442]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-06.05","CABLE (1/C # 6 AWG)",24234,1.4421335848619585E-5,2,1.5101888203402505]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-06.06","CABLE (1/C # 4 AWG)",291215.15000000002,1.7329831981332551E-4,12,1.7760486802302891]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-06.07","CABLE (1/C # 2 AWG)",277733.5,1.6527556655577237E-4,6,2.4034745359352687]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-06.08","CABLE (1/C #1/0 AWG)",279386,1.6625894765215943E-4,10,2.7816485628092673]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-06.09","CABLE (1/C #2/0 AWG)",222438,1.3236993907300666E-4,8,2.2000692349537609]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-06.10","CABLE (1/C # 2 AWG)",111439,6.6315888653722783E-5,3,2.2659414396095974]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-06.11","CABLE (# 4 SOLID COPPER SOFT DRAWN)",18684.2,1.111872259068986E-5,3,1.7651582427964101]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-06.12","CABLE (# 4 COPPER SOFT DRAWN BARE)",51135.5,3.0430065993525083E-5,2,1.657821364888961]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-08.01","LIGHT STANDARDS (45' M.H., 15' ARM)",587377.43999999994,3.4954061781556484E-4,4,3625.7866666666664]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-08.04","LIGHT STANDARDS (45' M.H., 2 - 15' ARMS)",95715.200000000012,5.6958861311289658E-5,1,4785.76]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-08.05","LIGHT STANDARDS (ALUMINUM)",91500,5.4450451025364865E-5,2,3155.1724137931033]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-08.08","LIGHT STANDARDS (NEW MEDIAN BARRIER MOUNTED)",103350,6.1502230748321948E-5,1,1950]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-08.09","LIGHT STANDARDS (40' M.H.)",878886.08,5.2301358968213007E-4,15,3837.9304803493451]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-08.10","LIGHT STANDARDS (50' M.H.)",164571,9.7934045636014432E-5,6,3827.2325581395348]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-08.11","LIGHT STANDARDS (35' POLE W/TENON)",180060,1.0715134657516062E-4,3,4187.4418604651164]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-08.20","FOUNDATION (ONLY) FOR LIGHT STANDARD",333192.86,1.982787049773907E-4,9,1061.1237579617834]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-08.26","FOUNDATION FOR LIGHT STANDARDS(MEDIAN BARRIER)",73852.160000000003,4.394845269068208E-5,2,1210.6911475409836]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-08.27","FOUNDATION  FOR LIGHT STANDARDS - HIGH MAST (HIGH MAST)",99496,5.9208765849395653E-5,2,5852.7058823529414]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-08.28","FOUNDATION  FOR LIGHT STANDARDS - ROADWAY (BARRIER WALL)",16613.04,9.8862024142341809E-6,1,1384.42]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-08.30","REMOVE & RELOCATE LIGHT STANDARD",37147.64,2.2106073798118957E-5,5,1768.935238095238]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-08.32","REMOVAL OF LIGHT STANDARD & FOUNDATION",65570,3.9019847800362561E-5,4,443.04054054054052]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-08.33","REMOVAL OF EXISTING COBRA HEAD LUMINAIRE",5879.4,3.4987538990003295E-6,2,133.62272727272727]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-08.34","REMOVAL OF LIGHT STANDARD",22287.88,1.3263225337696273E-5,3,353.77587301587306]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-08.46","FOUNDATION (ONLY) FOR HIGH MAST LIGHT STANDARD",5000,2.9754344822603748E-6,1,5000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-09.01","LUMINAIRES (150 WATT)",22581.96,1.3438228492204899E-5,2,1254.5533333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-09.03","LUMINAIRES (250 WATT)",92027.150000000009,5.4764151082829576E-5,6,479.30807291666662]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-09.04","LUMINAIRES (400 WATT)",25725,1.5308610411229629E-5,1,735]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-09.06","LUMINAIRES (1000 WATT - HIGH MAST)",6800,4.0465908958741101E-6,1,850]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-09.07","LUMINAIRES (150 WATT - UNDERPASS)",30400,1.8090641652143082E-5,1,1600]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-09.09","LUMINAIRES (REMOVE AND RELOCATE EXISTING FIXTURE)",198536.5,1.1814646961745739E-4,9,1096.8867403314916]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-09.10","LUMINAIRES (363 WATT LED OFFSET)",286309,1.7037873423629714E-4,9,1072.318352059925]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-09.11","LUMINAIRES (250 WATT, SIGNAL POLE MOUNTED)",51485.5,3.0638346407283304E-5,4,627.8719512195122]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-09.12","LUMINAIRES (SEE PLANS)",85522.15,5.0893110821408821E-5,3,724.7639830508474]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-09.13","LUMINAIRES (SEE PLANS)",35177,2.0933371756494642E-5,3,1065.969696969697]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-09.14","LUMINAIRES (165W LED, LCUB POLE MOUNTED)",3151.75,1.8755651258928275E-6,1,630.35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-09.15","LUMINAIRES (LED TEARDROP)",77610,4.618469403364554E-5,1,1990]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-10.01","OVERHEAD CONDUCTORS (GAUGE & TYPE) (#6 DPX)",948,5.6414237783656713E-7,1,1.58]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-12.01","CONTROL CENTER (NO. 1)",58681.78,3.4920758338483444E-5,7,8383.1114285714284]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-12.02","CONTROL CENTER (NO. 2)",36875,2.1943829306670265E-5,4,9218.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-12.03","CONTROL CENTER (NO. 3)",10500,6.2484124127467873E-6,1,10500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-12.10","RELOCATION OF CONTROL CENTER",2500,1.4877172411301874E-6,1,2500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-14.03","MASTARM (DESCRIPTION)",6500,3.8680648269384875E-6,1,500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-14.04","MASTARM (DESCRIPTION)",11250,6.6947275850858434E-6,1,750]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-14.05","MASTARM (DESCRIPTION)",3000,1.7852606893562249E-6,1,250]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-14.06","MASTARM (DESCRIPTION)",3900,2.3208388961630923E-6,1,300]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-16.01","NAVIGATIONAL LIGHTING",200000,1.19017379290415E-4,1,200000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-25","ELECTRICAL CONNECTION",86145.72,5.1264189157429448E-5,12,990.18068965517227]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-25.02","ELECTRICAL CONNECTION (COORDINATION WITH ELECTRICAL COMPANY )",2600,1.5472259307753949E-6,1,2600]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-25.03","ELECTRICAL CONNECTION (NEW ELECTRICAL SERVICE)",19800,1.1782720549751084E-5,1,19800]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-25.04","ELECTRICAL CONNECTION (ELECTRICAL SERVICE UPGRADES )",3840,2.2851336823759678E-6,1,3840]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-25.09","ELECTRICAL CONNECTION (DESCRIPTION)",5317.52,3.1643864736218379E-6,1,2658.76]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-25.22","INSTALL SVC RISER (SEE PLANS)",472.5,2.8117855857360546E-7,1,472.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-26.05","TEMPORARY ROADWAY LIGHTING",6825,4.0614680682854118E-6,1,6825]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714-30","AS-BUILT PLANS",3397,2.0215101872476989E-6,1,3397]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M01","STRUCTURAL LIGHTING",42352.57,2.5203459438069257E-5,1,42352.57]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M02.01","ENCASED CONDUIT (50mm PVC, SCHEDULE 80)",30282,1.8020421398361735E-5,1,43.26]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M03.01","DIRECT BURIAL CONDUIT (50mm PVC, SCHEDULE 40)",132097.5,7.8609491304077979E-5,1,19.57]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M05.03","PULL BOXES (TYPE B)",35003.520000000004,2.0830136081698138E-5,1,729.24000000000012]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M05.05","PULL BOXES (JUNCTION BOX IN WALL)",7774.4400000000005,4.6264673712528707E-6,1,647.87]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M06.05","CABLE (1/C # 6 AWG)",143685,8.5505060716716393E-5,1,3.09]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M08.01","LIGHT STANDARDS (13.5m M.H., 4.5m ARM)",277173,1.6494202035031099E-4,1,4017]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M08.04","LIGHT STANDARDS (13.5m M.H., 2 - 4.5m ARMS)",4429,2.6356398643862402E-6,1,4429]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M08.08","LIGHT STANDARDS (NEW MEDIAN BARRIER MOUNTED)",110467.5,6.57377617338196E-5,1,2832.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M08.09","LIGHT STANDARDS (13.5m M.H., 1.8m ARM)",73336,4.3641292638209371E-5,1,3666.8]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M08.10","LIGHT STANDARDS (13.5m M.H., 3.1m ARM)",16150.4,9.610891412459592E-6,1,4037.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M08.32","REMOVAL OF LIGHT STANDARD & FOUNDATION",26697.600000000002,1.5887391926718919E-5,1,333.72]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M09.09","LUMINAIRES (TYPE A - LED)",70946.400000000009,4.2219272990447498E-5,1,886.83000000000015]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M09.10","LUMINAIRES (TYPE B - LED)",80701.53,4.8024423026634026E-5,1,886.83]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M09.11","LUMINAIRES (TYPE C - LED)",3106.48,1.848625542090442E-6,1,776.62]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M10.01","OVERHEAD CONDUCTORS (GAUGE & TYPE) (#2 TRIPLEX)",389.40000000000003,2.3172683747843802E-7,1,12.98]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M12.01","CONTROL CENTER (NO. 1)",13390,7.9682135434932848E-6,1,13390]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M12.02","CONTROL CENTER (NO. 2)",13390,7.9682135434932848E-6,1,13390]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M12.03","CONTROL CENTER (NO. 3)",13390,7.9682135434932848E-6,1,13390]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M12.04","CONTROL CENTER (NO. 4)",13390,7.9682135434932848E-6,1,13390]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"714M25","ELECTRICAL CONNECTION",15829.04,9.4196542874157531E-6,1,3957.26]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-01.05","TEMPORARY RAISED PAVEMENT MARKER",89316.82,5.3151269214768628E-5,20,9.0091607827314917]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-01.06","TEMPORARY RAISED PAVEMENT MARKER,WHITE",50740.54,3.0195030472902371E-5,10,9.7484226705091253]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-01.07","TEMPORARY RAISED PAVEMENT MARKER,YELLOW",49498.492499999993,2.9455904280881307E-5,21,9.7282382999631487]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-01.10","SNOWPLOWABLE REFLECTIVE MARKER",8080,4.8083021233327657E-6,1,20]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-01.11","RAISED PVMT MARKERS (BI-DIRECTIONAL) (1 COLOR LENS)",17839.75,1.0616201460980905E-5,6,8.5032173498570067]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-01.12","RAISED PVMT MARKERS (MONO-DIRECTIONAL) (1 COLOR LENS)",13361.28,7.9511226478271807E-6,5,10.023465866466617]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-01.13","RAISED PVMT MARKERS (BI-DIRECTIONAL) (2 COLOR LENS)",15229.15,9.0626676091031171E-6,4,9.4649782473586068]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-01.14","RAISED PAVEMENT MARKER REMOVAL",3600,2.1423128272274701E-6,1,10]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-01.21","Snwplwble Pvmt Mrkrs (Bi-Dir)(1 Color)",486313.26500000001,2.8939865157232551E-4,54,31.872152114429898]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-01.22","Snwplwble Pvmt Mrkrs (Mono-Dir)(1 Color)",377395.10250000004,2.2458288028293774E-4,52,32.107121645968199]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-01.23","Snwplwble Pvmt Mrkrs (Bi-Dir)(2 Color)",502903.68999999994,2.9927139609639639E-4,37,34.44031576107129]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-01.30","REMOVAL OF SNOWPLOWABLE REFLECTIVE MARKER",31118.469999999998,1.8518193734637E-5,16,10.865387569832402]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-02.03","PLASTIC PAVEMENT MARKING (CROSS-WALK)",83500.399999999994,4.9689993888506839E-5,20,8.4309773828756054]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-02.04","PLASTIC PAVEMENT MARKING(CHANNELIZATION STRIPING)",568042.51798999996,3.3803465908349104E-4,66,18.917564622792348]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-02.05","PLASTIC PAVEMENT MARKING (STOP LINE)",399008.82,2.3744492035080464E-4,81,12.95182094032686]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-02.06","PLASTIC PAVEMENT MARKING (TURN LANE ARROW)",355743.95,2.1169856313710215E-4,81,156.09651162790695]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-02.07","PLASTIC PAVEMENT MARKING (24\" BARRIER LINE)",306758.55,1.8254799347963867E-4,26,12.729875219576446]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-02.08","PLASTIC PAVEMENT MARKING (8\" DOTTED LINE)",39566.660000000003,2.3545600902374458E-5,29,2.0770292771936898]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-02.09","PLASTIC PAVEMENT MARKING (LONGITUDINAL CROSS-WALK)",463498.67,2.7582198503996446E-4,23,26.697694257243249]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-02.11","PLASTIC PAVEMENT MARKING (6\" DOTTED LINE)",8109.12,4.8256310537574506E-6,7,2.0732411650783305]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-02.12","PLASTIC PAVEMENT MARKING (8IN LINE)",22666.608399999997,1.3488601645850531E-5,4,9304.8474548440063]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-02.13","PLASTIC PAVEMENT MARKING (CROSSWALK)",38608,2.2975114898221711E-5,1,16]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-03.01","PLASTIC WORD PAVEMENT MARKING (ONLY)",40887.449999999997,2.4331585724339393E-5,33,233.64257142857142]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-03.02","PLASTIC WORD PAVEMENT MARKING (RXR)",4145,2.466635185793851E-6,5,460.55555555555554]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-03.03","PLASTIC WORD PAVEMENT MARKING (STOP AHEAD)",750,4.4631517233905622E-7,2,375]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-03.06","PLASTIC WORD PAVEMENT MARKING (SIGNAL AHEAD)",3600,2.1423128272274701E-6,1,600]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-03.07","PLASTIC WORD PAVEMENT MARKING (STOP)",500,2.9754344822603748E-7,1,500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-03.09","PLASTIC WORD PAVEMENT MARKING (YIELD)",4395,2.6154069099068694E-6,4,399.54545454545456]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-04.01","PLASTIC PAVEMENT MARKING (STRAIGHT-TURN ARROW)",31380.65,1.8674213617148809E-5,32,212.03141891891892]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-04.02","PLASTIC PAVEMENT MARKING(DOUBLE TURNING ARROW)",18886.45,1.1239078915497293E-5,13,255.2222972972973]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-04.03","PLASTIC PAVEMENT MARKING (4\" DOTTED LINE)",5795.8099999999995,3.4490105853259007E-6,6,1.213274021352313]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-04.04","PLASTIC PAVEMENT MARKING (TRANSVERSE SHOULDER)",29544.73,1.7581681682214514E-5,9,7.0294384963121574]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-04.05","PLASTIC PAVEMENT MARKING (STRAIGHT ARROW)",29602.93,1.7616315739588024E-5,30,138.98089201877934]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-04.06","PLASTIC PAVEMENT MARKING (WRONG WAY ARROW)",3254.4,1.9366507958136331E-6,4,295.85454545454547]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-04.07","PLASTIC PAVEMENT MARKING (EXIT ONLY ARROW)",8593,5.1135817012126807E-6,7,232.24324324324326]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-04.08","PLASTIC PAVEMENT MARKING (OPTION LANE ARROW)",2850,1.6959976548884138E-6,3,316.66666666666669]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-04.11","PLASTIC PAVEMENT MARKING (BICYCLE SYMBOL W/RIDER)",26074.52,1.551660518327756E-5,5,299.70712643678161]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-04.12","PLASTIC PAVEMENT MARKING (YIELD LINE)",17300.36,1.0295217539903621E-5,20,18.575912160312157]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-04.13","PLASTIC PAVEMENT MARKING (BIKELANE SYMBOL & ARROW)",32067.08,1.9082699115480406E-5,7,314.38313725490195]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-04.14","PLASTIC PAVEMENT MARKING (LANE REDUCTION ARROW)",45344.350000000006,2.698382851313665E-5,39,317.09335664335663]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-04.15","PLASTIC PAVEMENT MARKING-BIKE SYMBOL/ARROW SHARED",48210.54,2.8689460624878622E-5,7,309.04192307692307]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-04.16","PLASTIC PAVEMENT MARKING (NOISE STRIP)",1080,6.4269384816824099E-7,1,15]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-05.01","PAINTED PAVEMENT MARKING (4\" LINE)",668280.29626999993,3.9768484746738743E-4,69,959.96043442973814]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-05.02","PAINTED PAVEMENT MARKING (8\" BARRIER LINE)",646235.71800000011,3.8456640780109842E-4,48,0.5989548698417696]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-05.03","PAINTED PAVEMENT MARKING (CROSS-WALK)",65,3.8680648269384874E-8,1,2.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-05.04","PAINTED PAVEMENT MARKING (CHANNELIZATION STRIPING)",26844.731400000001,1.5974947894915568E-5,12,11.552978283884627]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-05.05","PAINTED PAVEMENT MARKING (STOP LINE)",133177.04,7.9251911412273849E-5,41,6.4935901311619277]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-05.06","PAINTED PAVEMENT MARKING (TURN LANE ARROW)",66543.16,3.9598962564513864E-5,22,82.662310559006215]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-05.07","PAINTED PAVEMENT MARKING (24\" BARRIER LINE)",3355.22,1.9966474567139309E-6,2,0.56580438448566606]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-05.09","PAINTED PAVEMENT MARKING(STRAIGHT-TURN ARROW)",7824.05,4.6559896321858573E-6,10,137.26403508771929]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-05.11","PAINTED PAVEMENT MARKING(STRAIGHT ARROW)",7054.8099999999995,4.1982249879590632E-6,7,69.849603960396038]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-05.20","PAINTED PAVEMENT MARKING (6\" LINE)",444270.22500000003,2.6437938938131508E-4,31,1407.9903180312801]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-05.21","PAINTED PAVEMENT MARKING(4\"DOTTED LINE)",3648.2200000000003,2.1710079173743893E-6,12,0.47564797913950457]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-05.22","PAINTED PAVEMENT MARKING (LONGITUDINAL CROSS-WALK)",45876.85,2.7300712285497375E-5,5,13.24007215007215]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-05.49","PAINTED PAVEMENT MARKINGS(8\" LINE)",185403.03200000001,1.1033091490568475E-4,11,1375.0873841133277]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-05.50","PAINTED PAVEMENT MARKINGS(8\" LINE)",2919.84,1.7375585237366267E-6,3,0.26975609756097563]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-05.51","PAINTED PAVEMENT MARKINGS(12\" LINE)",3781.3500000000004,2.2502318358990539E-6,2,6.3127712854757938]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-06.01","PAINTED WORD PVMT MARK (           )",9064.7999999999993,5.3943436989587694E-6,5,188.85]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-08.01","REMOVAL OF PAVEMENT MARKING (LINE)",379590.09,2.2588908858206384E-4,25,0.71234225223128822]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-08.02","REMOVAL OF PAVEMENT MARKING (8\" BARRIER LINE)",69319,4.125082857516139E-5,2,0.86356218310473276]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-08.03","REMOVAL OF PAVEMENT MARKING (CROSS-WALK)",1316.2,7.8325337311022115E-7,3,5.0623076923076926]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-08.04","REMOVAL OF PAVEMENT MARKING (CHANNELIZATION STRIPING)",149082.76,8.8717196962909549E-5,11,12.316817580964971]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-08.05","REMOVAL OF PAVEMENT MARKING (STOP LINE)",18644.5,1.1095097640900712E-5,9,3.7199720670391061]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-08.06","REMOVAL OF PAVEMENT MARKING (TURN LANE ARROW)",11760.58,6.9985670526763445E-6,9,81.107448275862069]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-08.07","REMOVAL OF PAVEMENT MARKING (STRAIGHT-TURN ARROW)",79.5,4.7309408267939962E-8,1,79.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-08.08","REMOVAL OF PAVEMENT MARKING (DOUBLE TURNING ARROW)",78.75,4.6863093095600904E-8,1,78.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-08.09","REMOVAL OF PAVEMENT MARKING (DOTTED LINE)",839.8,4.997539756404526E-7,1,0.85]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-08.11","REMOVAL OF WORD PAVEMENT MARKING (ONLY)",375,2.2315758616952811E-7,1,75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-08.20","REMOVAL OF PAVEMENT MARKING (LINE)",335171.57140000002,1.9945621020339108E-4,16,3673.8378134864961]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-08.30","HYDROBLAST REMOVAL OF PAVEMENT MARKING (LINE)",133837.5,7.9644942503904591E-5,4,2530.0094517958414]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-08.32","HYDROBLAST REMOVAL OF PAVEMENT MARKING (SR 253 LIPSCOMB DRIVE AND GENERAL MACAR THUR DRIVE PAVEMENT MARKING REMOVAL)",7821.15,4.6542638801861464E-6,3,2.2782260413632391]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-08.33","HYDROBLAST REMOVAL OF PAVEMENT MARKING (LANE REDUCTION ARROW)",3000,1.7852606893562249E-6,1,1500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-09.33","6 INCH DOTTED LINE",1033.5,6.1502230748321955E-7,1,3.9]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-10.07","PREFORMED PLASTIC PAVEMENT MARKING (STOP LINE)",3000,1.7852606893562249E-6,1,20]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-10.26","WET NIGHT VISIBLE PAVEMENT MARKING (6\" DOTTED LINE)",4440,2.642185820247213E-6,2,9.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-12.01","ENHANCED FLATLINE THERMO  PVMT MRKNG (4IN LINE)",769901.11859999993,4.5815806724265487E-4,31,3558.2454145888314]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-12.02","ENHANCED FLATLINE THERMO  PVMT MRKNG (6IN LINE)",3422975.0261999993,2.0369675849743175E-3,71,5075.5631665339561]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-12.03","ENHANCED FLATLINE THERMO  PVMT MRKNG (8IN BARRIER LINE)",135322.23999999999,8.0528491822542841E-5,21,2.6857692114563663]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-12.04","ENHANCED FLATLINE THERMO  PVMT MRKNG (4IN DOTTED LINE)",16258.789999999999,9.6753928811660325E-6,11,1.6868869535625428]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-12.05","ENHANCED FLATLINE THERMO  PVMT MRKNG (6IN DOTTED LINE)",76128.403999999995,4.5303015668209727E-5,33,2.1740321056414982]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-12.06","ENHANCED FLAT LINE THERMO (8IN LINE)",166236.85999999999,9.8925377093338074E-5,6,3.2014802118440056]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-12.07","ENHANCED FLAT LINE THERMO (8IN BROKEN LN)",460,2.7373997236795452E-7,1,2]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-12.08","ENHANCED FLAT LINE THERMO (12IN BARRIER LINE)",55872.800000000003,3.3249171148087496E-5,4,7.652759895904671]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-12.09","ENHANCED FLAT LINE THERMO (12IN LINE)",43571.1,2.5928590674003005E-5,5,6.5733962947317606]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-12.10","ENHANCED FLAT LINE THERMO (12IN DOTTED)",37166.449999999997,2.211726738264122E-5,4,5.7610166522769575]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-13.01","SPRAY THERMO PVMT MRKNG (60 mil) (4IN LINE)",293836.34759999992,1.7485816015809706E-4,33,2441.6571599511399]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-13.02","SPRAY THERMO PVMT MRKNG (60 mil) (6IN LINE)",63754.144800000002,3.7939256164988199E-5,6,2928.5321451538821]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-13.03","SPRAY THERMO PVMT MRKNG (60 mil) (8IN BARRIER LINE)",1034.5,6.1561739437967159E-7,4,1.3701986754966888]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-13.04","SPRAY THERMO PVMT MRKNG (60 mil) (4IN DOTTED LINE)",1342.97,7.9918384932824313E-7,4,1.2142585895117541]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-13.05","SPRAY THERMO PVMT MRKNG (60 mil) (6IN DOTTED LINE)",2888.24,1.718753777808741E-6,2,1.0095211464522893]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-13.06","SPRAY THERMO PVMT MRKNG (40 mil) (4IN LINE)",47932.893000000004,2.8524236533339393E-5,9,1654.2273950855883]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-13.08","SPRAY THERMO PVMT MRKNG (40 mil) (8IN BARRIER LINE)",1101.1200000000001,6.5526208342130889E-7,1,1.86]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-13.09","SPRAY THERMO PVMT MRKNG (40 mil) (4IN DOTTED LINE)",890.94,5.3018671952501169E-7,1,1.86]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-13.11","SPRAY THERMO PVMT KRKNG (60 MIL 12IN BARRIER LINE)",9630,5.7306868128334822E-6,1,5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716-16.10","PREFORMED  YIELD WORD (8FT W/ 1 Â½IN BLACK CONTRAST)",1200,7.1410427574249004E-7,1,1200]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M01.05","TEMPORARY RAISED PAVEMENT MARKER",41700,2.4815123582051526E-5,1,6.95]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M01.21","SNWPLWBLE PVMT MRKRS (BI-DIR)(1 COLOR)",7416,4.4131644240885879E-6,1,24.72]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M01.22","SNWPLWBLE PVMT MRKRS (MONO-DIR)(1 COLOR)",26227.919999999998,1.5607891513193307E-5,1,24.72]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M02.01","PLASTIC PAVEMENT MARKING (100mm LINE)",51912,3.0892150968620114E-5,1,1442]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M02.02","PLASTIC PAVEMENT MARKING (200mm BARRIER LINE)",5296.0999999999995,3.1516397122998341E-6,1,4.22]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M02.03","PLASTIC PAVEMENT MARKING (CROSS-WALK)",501.82,2.9862650637758029E-7,1,22.81]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M02.04","PLASTIC PAVEMENT MARKING(CHANNELIZATION STRIPING)",127443,7.5839659344541791E-5,1,17.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M02.05","PLASTIC PAVEMENT MARKING (STOP LINE)",6232,3.7085815386893312E-6,1,31.16]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M02.06","PLASTIC PAVEMENT MARKING (TURN LANE ARROW)",988.8,5.8842192321181177E-7,1,123.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M02.08","PLASTIC PAVEMENT MARKING (200mm DOTTED LINE)",106.56,6.3412459685933114E-8,1,5.92]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M02.10","PLASTIC PAVEMENT MARKING (150mm LINE)",186790.5,1.1115657893173132E-4,1,2394.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M02.11","PLASTIC PAVEMENT MARKING (150mm DOTTED LINE)",2583.35,1.537317733949468E-6,1,4.2699999999999996]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M04.01","PLASTIC PAVEMENT MARKING (STRAIGHT-TURN ARROW)",2090.9,1.2442671917916438E-6,1,149.35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M04.05","PLASTIC PAVEMENT MARKING (STRAIGHT ARROW)",1112.3999999999999,6.6197466361328814E-7,1,123.59999999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M04.06","PLASTIC PAVEMENT MARKING (WRONG WAY ARROW)",180.25,1.0726441308548653E-7,1,180.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M04.12","PLASTIC PAVEMENT MARKING (YIELD LINE)",3674.3,2.1865277836338591E-6,1,25.34]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M04.14","PLASTIC PAVEMENT MARKING (LANE REDUCTION ARROW)",1854,1.103291106022147E-6,1,231.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M12.02","ENHNCD FLTLNE THERMO PVMT MRKNG (6IN LINE)",69937,4.161859227716877E-5,1,2497.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M13.01","SPRAY THERMO PVMT MRKNG (60 mil)  (100 mm)",8482.0500000000011,5.047556810051323E-6,1,942.45000000000016]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"716M13.02","SPRAY THERMO PVMT MRKNG (60 mil) (200mm LINE)",13209.75,7.8609491304077969E-6,1,1467.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"717-01","MOBILIZATION",66730491.019999996,3.971044079981486E-2,106,629532.9341509433]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"717M01","MOBILIZATION",3100000,1.8447693790014325E-3,1,3100000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"719-01.01","SWEEPING",3000,1.7852606893562249E-6,1,500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"721-01.01","BENCH (6')",12500,7.4385862056509373E-6,1,2500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"721-01.02","TRASH RECEPTACLE",10000,5.9508689645207496E-6,1,2000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"721-01.03","IRRIGATION SYSTEM",10000,5.9508689645207496E-6,1,10000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"722M01.02","FIELD OFFICE (TYPE 2)",81125,4.8276424474674583E-5,1,81125]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-02.16","CONDUIT (STRUCTURES - DESCRIPTION)",9825,5.8467287576416371E-6,1,15]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-02.41","FIBER OPTIC TERMINATION SPLICE UNIT",5240,3.1182553374088729E-6,2,1048]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-02.79","FIBER SPLICE ENCLOSURE (WEATHER PROOF)",8317.52,4.9496471629780628E-6,2,2079.38]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-03.08","VIDEO ENCODER",3710,2.2077723858371984E-6,1,3710]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-03.09","ETHERNET SWITCH (TYPE A)",8000,4.7606951716165997E-6,1,4000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-03.28","RAILROAD FLAGMAN",2,1.19017379290415E-9,1,0.01]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-03.44","FIBER OPTIC MODEM TRANSCEIVER (TYPE I)",4260,2.5350701788858395E-6,1,4260]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-03.50","RADAR DETECTION SYSTEM",8049,4.7898544295427519E-6,1,8049]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-03.53","VIDEO DETECTION SYSTEM",128468,7.6449623413405167E-5,1,32117]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-03.60","CABLE MARKER",2660,1.5829311445625195E-6,3,221.66666666666666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-03.80","CCTV CAMERA SYSTEM",41040,2.4422366230393157E-5,1,10260]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-05.04","SPLICE ENCLOSURE (UNDER GRADE)",8950,5.3260277232460709E-6,4,1118.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-05.06","FUSION SPLICE",4240,2.5231684409567979E-6,4,86.530612244897952]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-12.42","FO DROP CABLE, 4F",159.5,9.4916359984105966E-8,1,15.95]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-20.23","STEEL OVERHEAD SIGN STRUCTURE (SPANS 71FT TO 90FT)",200000,1.19017379290415E-4,1,200000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-20.43","PULL BOX (TYPE C)",25890,1.5406799749144223E-5,3,417.58064516129031]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-20.44","PULL BOX (TYPE D)",47930,2.8522514946947956E-5,4,1369.4285714285713]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-20.45","PULL BOX (TYPE E)",22970,1.3669146011504163E-5,4,1766.9230769230769]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-20.56","CABLE (1/C #4 AWG.)",3725.9999999999995,2.2172937761804314E-6,1,2.2999999999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-20.75","COMMUNICATION CONNECTION (DESCRIPTION)",2500,1.4877172411301874E-6,1,2500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-20.91","CCTV CAMERA SYSTEM (PAN TILT & ZOOM)",28500,1.6959976548884138E-5,1,9500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-21.05","DYNAMIC MESSAGE SIGN REMOVE & REPLACE",17720,1.0544939805130769E-5,1,17720]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-21.07","PORTABLE SMART WORK ZONE SYSTEM",695660,4.1397815038585049E-4,2,302.98780487804879]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-21.11","NETWORK SWITCH (TYPE A)",18000,1.071156413613735E-5,1,3000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-21.15","NETWORK SWITCH (DESCRIPTION)",94428,5.619286545817654E-5,2,13489.714285714286]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-21.91","RADAR DETECTION SYSTEM",18000,1.071156413613735E-5,1,18000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-21.96","RDS COMM CABLE",6720,3.9989839441579441E-6,1,7]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-22.21","CONDUIT BANK (TYPE 1)",6000,3.5705213787124498E-6,1,8]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-22.24","CONDUIT BANK (TYPE 4)",181068.5,1.0775149171023254E-4,4,7.8242373174315096]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-22.32","CONDUIT BANK BORED (TYPE 2)",1800,1.0711564136137351E-6,1,12]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-22.34","CONDUIT BANK BORED (TYPE 4)",46750,2.7820312409134506E-5,2,12.158647594278284]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-22.50","DMS CONDUIT BANK",1023.75,6.0922021024281181E-7,1,13.65]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-22.74","2IN CONDUIT W/BANK",29480,1.7543161707407171E-5,1,2]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-22.75","2IN CONDUIT BORED W/BANK",4720,2.8088101512537941E-6,1,2]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-23.01","ITS CABLE MARKER",18600,1.1068616274008595E-5,4,197.87234042553192]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-23.10","FIBER OPTIC CABLE (72 F)",5966.4000000000005,3.5505264589916606E-6,1,2.2000000000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-23.11","FIBER OPTIC CABLE (60 F)",8962.5,5.3334663094517222E-6,1,2.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-23.21","FIBER OPTIC DROP CABLE (12 F)",1333.5,7.9354837641884206E-7,1,2.1]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-23.23","FIBER OPTIC DROP CABLE ( 4 F )",3457.5,2.0575129444830495E-6,1,1.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-23.24","FIBER OPTIC DROP CABLE (DESCRIPTION)",1350,8.0336731021030124E-7,1,450]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-23.25","FIBER OPTIC CLOSURE (72 F )",1200,7.1410427574249004E-7,1,1200]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-23.27","FIBER OPTIC CLOSURE (96F)",1000,5.9508689645207496E-7,1,1000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-23.28","FIBER OPTIC SPLICE FUSION",9515,5.6622518197414933E-6,3,68.453237410071949]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-23.31","FIBER OPTIC DROP PANEL ( 12 F )",2000,1.1901737929041499E-6,1,1000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-23.32","FIBER OPTIC SPLICE MODIFICATION",3125,1.8596465514127343E-6,1,625]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-24.01","CABINET (TYPE A)",4500,2.6778910340343375E-6,1,4500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-24.41","BURN-IN PERIOD",3050,1.8150150341788287E-6,1,3050]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-24.51","SYSTEM INTEGRATION",4250,2.5291193099213187E-6,1,4250]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725-24.55","AS-BUILT PLANS",2200,1.309191172194565E-6,2,1100]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725M20.44","PULL BOX (TYPE D)",31157.5,1.8541419976205526E-5,1,1246.3]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725M20.45","PULL BOX (TYPE E)",3300.12,1.9638581687194218E-6,1,1650.06]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725M21.07","PORTABLE SMART WORK ZONE SYSTEM",565037.4,3.362463527453497E-4,1,422.3]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725M22.24","CONDUIT BANK (TYPE 4)",62122.400000000001,3.6968226216154386E-5,1,23.18]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725M22.34","CONDUIT BANK BORED (TYPE 4)",1940.4,1.1547066138756064E-6,1,64.680000000000007]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725M22.44","CONDUIT BANK IN ROCK (TYPE 4)",18127.5,1.078743771543499E-5,1,72.510000000000005]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"725M24.55","AS-BUILT PLANS",4158.1099999999997,2.4744367750063376E-6,1,4158.1099999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-01.01","REMOVE & RELOCATE EXISTING TRAFFIC SIGNAL EQUIPMENT",2646.5499999999997,1.574927225805239E-6,2,330.81874999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-01.02","REMOVAL OF SIGNAL EQUIPMENT",200696.66999999998,1.1943195847856625E-4,41,979.00814634146332]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-01.03","MODIFICATION OF EXISTING TRAFFIC SIGNAL EQUIPMENT",6205.9,3.6930497706919319E-6,3,2068.6333333333332]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-01.04","MODIFICATION OF EXISTING TRAFFIC SIGNAL EQUIPMENT",2360,1.4044050756268971E-6,2,1180]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-01.08","SCHOOL SPEED LIMIT FLASHING SIGNAL INSTALLED",41791.56,2.4869609738290679E-5,6,4643.5066666666662]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-02.07","SIGNAL HEAD ASSEMBLY (130)",4706.1000000000004,2.8005384433931105E-6,1,784.35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-02.08","SIGNAL HEAD ASSEMBLY (130 POLE MOUNTED)",6825.64,4.0618489238991411E-6,4,682.56400000000008]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-02.09","SIGNAL HEAD ASSEMBLY (130 WITH BACKPLATE)",531145.83000000007,3.1607792353816148E-4,56,798.71553383458661]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-02.10","SIGNAL HEAD ASSEMBLY (130 A2)",8230.4,4.8978031925591574E-6,2,633.10769230769233]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-02.13","SIGNAL HEAD ASSEMBLY (140 A1)",4506,2.6814615554130497E-6,2,901.2]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-02.17","SIGNAL HEAD ASSEMBLY (150 A2H WITH BACKPLATE)",340877.77999999997,2.0285190016967319E-4,52,1321.2317054263567]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-02.18","SIGNAL HEAD ASSEMBLY (150 A2V)",12560.55,7.47461871723111E-6,3,1141.8681818181817]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-02.21","SIGNAL HEAD ASSEMBLY (220)",1460,8.6882686882002954E-7,1,730]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-02.27","SIGNAL HEAD ASSEMBLY (440)",1447,8.6109073916615247E-7,1,1447]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-02.30","SIGNAL HEAD ASSEMBLY (130 A2 WITH BACKPLATE)",132860.52000000002,7.906355450780885E-5,33,825.22062111801256]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-02.31","SIGNAL HEAD ASSEMBLY (140 A1L WITH BACKPLATE)",60499.5,3.6002459691902313E-5,18,889.69852941176475]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-02.32","SIGNAL HEAD ASSEMBLY (130 A3L WITH BACKPLATE)",14297,8.507957358575316E-6,4,1099.7692307692307]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-02.33","SIGNAL HEAD ASSEMBLY (140 A1L WITH BACKPLATE)",2070,1.2318298756557952E-6,1,1035]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-03.11","INSTALL SPLICE BOX (UNDER GRADE)",8727.7200000000012,5.1937518079027045E-6,2,969.74666666666678]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-03.12","AERIAL SPLICE ENCLOSURE",2200,1.309191172194565E-6,1,2200]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-03.20","INSTALL PULL BOX (TYPE A)",120344.04000000001,7.1615161270104379E-5,36,361.39351351351354]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-03.21","INSTALL PULL BOX (TYPE B)",279303.81,1.6621003746014002E-4,50,452.68040518638566]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-03.23","INSTALL PULL BOX (FIBER OPTIC-TYPE A)",199537.34999999998,1.1874206233777143E-4,21,1425.2667857142856]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-03.24","INSTALL PULL BOX (FIBER OPTIC-TYPE B)",111063.4,6.609237401541539E-5,20,1851.0566666666668]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-03.25","INSTALL PULL BOX (DESCRIPTION)",20000,1.1901737929041499E-5,1,500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-03.31","FIBER DISTRIBUTION BOX",2127,1.2657498287535634E-6,1,1063.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-03.32","FIBER OPTIC DROP CABLE",975,5.8020972404077308E-7,1,3.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-03.33","FIBER OFPTIC SPLICE FUSION",2160,1.285387696336482E-6,2,60]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-03.34","FIBER OPTIC TERMINATION CABINET",3640,2.1661163030855531E-6,1,3640]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-05.01","ELECTRICAL SERVICE CONNECTION",275634.79000000004,1.6402665173531947E-4,52,2240.9332520325202]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-05.02","SERVICE CABLE (2 CONDUCTOR, # 8 AWG)",8715.4500000000007,5.1864500916832377E-6,13,1.8168542839274548]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-05.03","SERVICE CABLE (1 CONDUCTOR, # 6 AWG)",2811,1.6727892659267828E-6,2,2.0669117647058823]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-05.04","MODIFY EXISTING ELECTRICAL SERVICE CONNECTION (SEE PLANS)",6733,4.0067200738118213E-6,2,1683.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-08.01","SIGNAL CABLE - 3 CONDUCTOR",45687.19,2.7187848104716276E-5,28,1.2083041971912936]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-08.02","SIGNAL CABLE - 5 CONDUCTOR",93771.299999999988,5.5802071893276453E-5,39,1.4013494732122844]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-08.03","SIGNAL CABLE - 7 CONDUCTOR",208465.16,1.2405488508278526E-4,52,1.584780222286418]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-08.04","SIGNAL CABLE - 9 CONDUCTOR",15184.710000000001,9.0362219474247888E-6,5,1.8472883211678832]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-08.05","SIGNAL CABLE - 12 CONDUCTOR",9781.5,5.820842477645972E-6,3,1.7592625899280576]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-08.10","SIGNAL CABLE - (EMERGENCY PREEMPT)",2565,1.5263978893995723E-6,3,0.56126914660831506]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-08.11","SIGNAL CABLE - (3 CONDUCTOR #10 AWG)",2644.75,1.5738560693916253E-6,2,2.0188931297709924]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-08.30","INTERCONNECT CABLE (COPPER-TWISTED PAIR)",54320.160000000003,3.232521542918015E-5,5,2.9647505730815413]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-08.31","INTERCONNECT CABLE (12 FIBER MULTI-MODE)",10225,6.0847635162224672E-6,2,2.1191709844559585]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-08.32","INTERCONNECT CABLE (Fiber Cable Hybrid 6sm/6mm)",28289,1.683441321373275E-5,2,2.9094929548493265]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-08.33","INTERCONNECT CABLE (6-Fiber Drop Cable)",1125,6.6947275850858439E-7,1,4.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-08.40","INTERCONNECT CABLE - FIBER OPTIC (6F,SINGLE MODE DROP CABLE)",110356.21,6.5671534513113446E-5,20,2.7729781139281857]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-08.41","INTERCONNECT CABLE - FIBER OPTIC (12 MMFO / 48 SMFO CABLE)",58869.25,3.5032319278961314E-5,10,2.9512834010126836]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-09.01","SPAN WIRE ASSEMBLY (16,000 LBS.MIN.BRK STRENGTH)",59088.08,3.5162542144511928E-5,25,3.2223417134754864]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-09.02","SPAN WIRE ASSEMBLY (19,172 LBS.MIN.BRK STRENGTH)",9484.33,5.6440005046273082E-6,8,3.4475936023264269]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-09.03","SPAN WIRE ASSEMBLY (13,250 LBS.MIN.BRK STRENGTH)",5280.44,3.1423206515013948E-6,4,2.4954820415879015]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-09.04","SPAN WIRE ASSEMBLY (18,900 LBS.MIN.BRK STRENGTH)",1334.16,7.9394113377050041E-7,1,2.04]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-10.01","TETHER WIRE ASSEMBLY - 1/4\" DIAMETER",39224.54,2.3342009773360274E-5,22,2.3249682887795626]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-10.02","MESSENGER CABLE - 1/4\" DIAMETER",6390.3,3.8027837943976948E-6,5,1.649109677419355]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-11.01","STEEL CONDUIT RISER ASSEMBLY",7457,4.4375629868431229E-6,4,355.09523809523807]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-11.10","RISER ASSEMBLY (2\" RGS CONDUIT W/WEATHER HEAD AND FUSE BOX)",7293.34,4.3401710653697764E-6,7,486.22266666666667]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-12.01","CONDUIT 1\" DIAMETER (PVC)",279596.83999999997,1.6638441577340737E-4,40,5.9488689361702125]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-12.02","CONDUIT 2\" DIAMETER (PVC)",670693.54000000015,3.9912093718905573E-4,52,6.6351431511050452]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-12.03","CONDUIT 3\" DIAMETER (PVC)",104015.33999999998,6.1898165864007366E-5,26,10.484360447535531]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-12.06","CONDUIT 2 1/2\" DIAMETER (PVC)",281.95999999999998,1.6779070132362707E-7,1,7.419999999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-12.07","CONDUIT 1\" DIAMETER (RGS)",22109.98,1.3157359378817449E-5,7,13.498156288156288]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-12.08","CONDUIT 2\" DIAMETER (RGS)",246632.68000000002,1.4676787610485775E-4,16,17.079825484764541]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-12.09","CONDUIT 3\" DIAMETER (RGS)",165065.22,9.8228149481978982E-5,11,26.852972181551976]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-12.13","CONDUIT 2\" DIAMETER (JACK AND BORE)",283306.81000000006,1.6859217030663773E-4,23,21.585280761904766]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-12.14","CONDUIT 3\" DIAMETER (JACK AND BORE)",117522.35999999999,6.9936016476123474E-5,14,21.309584768812329]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-12.16","CONDUIT (HDPE)",308576.5,1.8362983170304372E-4,12,7.2041766861998928]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-12.17","CONDUIT (BRIDGE ATTACHED)",59002,3.511131706446533E-5,3,25.508862948551666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-12.18","CONDUIT (BRIDGE ATTACHED)",39973.5,2.3787706055327019E-5,3,18.944786729857821]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-12.22","PAINT (DESCRIPTION)",3125,1.8596465514127343E-6,2,1562.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-12.30","TRENCHING",20519,1.2210588028300126E-5,1,5.78]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-13.01","VEHICLE LOOP DETECTOR (SHELF MOUNT)",49192.87,2.9274032335870389E-5,12,186.33662878787879]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-13.02","VEHICLE DETECTOR (VIDEO)",526240.58000000007,3.1315887353933994E-4,15,7411.8391549295784]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-13.03","VEHICLE DETECTOR (4 - CHANNEL, RACK MOUNT)",38986.32,2.3200248172887461E-5,24,364.35813084112146]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-13.05","VEHICLE DETECTOR (EXT. CALL - DELAY CALL)",2346,1.396073859076568E-6,2,234.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-13.06","VEHICLE DETECTOR (OPTICALLY ACTIVATED PRIORITY CONTROL)",30770.82,1.8311311775085439E-5,2,6154.1639999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-13.07","VEHICLE DETECTOR (SIREN ACTIVATED PRIORITY CONTROL)",388168.28,2.3099385704634007E-4,14,3404.9849122807018]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-13.08","VEHICLE DETECTOR (WIRELESS VIDEO)",931414.8899999999,5.5427279619935078E-4,21,6899.369555555556]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-13.09","VEHICLE DETECTOR (FISH EYE VIDEO)",246442.71000000002,1.4665482744713877E-4,7,7467.9609090909098]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-13.10","VEHICLE DETECTOR (REPEATERS)",68000,4.0465908958741099E-5,2,11333.333333333334]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-13.11","VEHICLE DETECTOR (CONTACT CLOSURE CARDS)",31000,1.8447693790014325E-5,2,10333.333333333334]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-13.12","VEHICLE DETECTOR (ACCESS BOX INSTALLED)",2000,1.1901737929041499E-6,1,1000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-13.13","VEHICLE DETECTOR (RADAR)",27664,1.6462483903450204E-5,1,6916]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-14.01","SHIELDED DETECTOR CABLE",177844.7,1.0583305057345035E-4,42,1.0659532129392657]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-14.02","SAW SLOT",364857.01,2.1712162572968369E-4,40,3.9559471972243307]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-14.03","LOOP WIRE",160231.35000000006,9.5351576785826229E-5,40,0.66711083447480535]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-14.10","PREFORMED DETECTION LOOP(6FT x 6FT)",9498.24,5.6522781633569564E-6,1,593.64]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-14.11","PREFORMED DETECTION LOOP (6FT x 50FT QUADRUPOLE)",17329.36,1.031247505990073E-5,2,1925.4844444444445]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-14.12","PREFORMED DETECTION LOOP (6FT x 20FT)",652.79999999999995,3.8847272600391454E-7,1,652.79999999999995]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-15.07","CABINET (EIGHT-PHASE POLE MOUNTED)",9415,5.6027431300962857E-6,1,9415]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-15.08","CABINET (FLASHER POLE MOUNTED)",1119,6.6590223712987187E-7,1,1119]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-15.11","MODIFY CABINET (Install F.O. Telemetry)",50264,2.9911447763267099E-5,5,8377.3333333333339]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-15.30","CABINET (FOUR PHASE POLE MOUNTED)",25815.45,1.5362436021013721E-5,2,12907.725]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-15.31","CABINET (FOUR PHASE BASE MOUNTED)",27863.919999999998,1.6581453675788901E-5,2,9287.9733333333334]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-15.32","CABINET (EIGHT PHASE BASE MOUNTED)",1501091.6099999999,8.9327994748514847E-4,50,12940.444913793104]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-15.42","MASTER CONTROLLER (FIBER)",6881,4.0947929344867282E-6,1,6881]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-16.01","FOUR PHASE ACTUATED CONTROLLER",7658.16,4.5572706669334223E-6,1,3829.08]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-16.02","EIGHT PHASE ACTUATED CONTROLLER",529463.09000000008,3.1507654701402573E-4,55,4412.1924166666677]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-16.03","CONTROLLER (FLASHING BEACON)",554,3.2967814063444954E-7,1,554]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-16.25","INSTALLATION OF CABINET AND CONTROLLER",10950,6.5162015161502208E-6,1,2190]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-17.01","INSTALL MODEM",1575,9.372618619120181E-7,1,1575]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-18.01","MASTER CONTROLLER",109403.39,6.5104523816435979E-5,17,3529.1416129032264]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-21.01","WOOD POLE (SIGNAL SUPPORT) CLASS 3, 35' LENGTH",840,4.9987299301974301E-7,1,840]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.01","STEEL STRAIN POLE (SIGNAL SUPPORT)",2023022.3,1.2038740619603387E-3,23,13856.31712328767]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.02","STEEL STRAIN POLE (SIGNAL SUPPORT)",438413.64,2.6089421238985729E-4,14,14142.375483870968]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.03","STEEL STRAIN POLE (SIGNAL SUPPORT)",171778.96,1.0222340818216512E-4,6,12269.925714285713]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.04","STEEL STRAIN POLE (SIGNAL SUPPORT)",75071,4.4673768403553721E-5,3,10724.428571428571]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.05","STEEL STRAIN POLE (SIGNAL SUPPORT)",12000,7.1410427574248996E-6,1,12000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.20","CANTILEVER SIGNAL SUPPORT (1 ARM @ 65')",38060,2.2649007278965973E-5,1,19030]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.30","PEDESTAL POLE (10')",337930.08,2.0109776252500144E-4,28,1579.1125233644862]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.31","PEDESTAL POLE (SEE PLANS)",17885.04,1.0643152946521219E-5,3,2555.0057142857145]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.36","CANTILEVER SIGNAL SUPPORT (1 ARM @ 50')",649439.11,3.8647270440449774E-4,29,17090.502894736841]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.37","CANTILEVER SIGNAL SUPPORT (1@55')",547882.23999999999,3.260375418228109E-4,21,18892.491034482759]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.38","CANTILEVER SIGNAL SUPPORT (1 ARM @ 66')",379406.63999999996,2.2577991989090968E-4,16,21078.146666666667]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.39","CANTILEVER SIGNAL SUPPORT (1 ARM @ 68')",288127.45,1.7146087000315043E-4,12,20580.532142857144]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.40","CANTILEVER SIGNAL SUPPORT (1 ARM @ 15')",18886.32,1.1239001554200753E-5,1,9443.16]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.48","CANTILEVER SIGNAL SUPPORT (1 ARM @ 20')",53738.66,3.1979172398893264E-5,3,10747.732]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.64","CANTILEVER SIGNAL SUPPORT (1 ARM @ 30')",11760,6.9982219022764023E-6,1,5880]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.72","CANTILEVER SIGNAL SUPPORT (1 ARM @ 35')",54119.75,3.2205954064262185E-5,5,10823.95]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.80","CANTILEVER SIGNAL SUPPORT (1 ARM @ 40')",116779.3,6.9493831206845805E-5,6,12975.477777777778]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.88","CANTILEVER SIGNAL SUPPORT (1 ARM @ 45')",91466.76999999999,5.4430676287795756E-5,8,11433.346249999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.94","CANTILEVER SIGNAL SUPPORT (2 @ 45' & 40')",17183.599999999999,1.0225735193873875E-5,1,17183.599999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.95","CANTILEVER SIGNAL SUPPORT (2 @ 45' & 45')",13000,7.736129653876975E-6,1,13000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.96","CANTILEVER SIGNAL SUPPORT (1 ARM @ 50')",466643.41000000003,2.7769337860671317E-4,18,19443.475416666668]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.97","CANTILEVER SIGNAL SUPPORT (1 ARM @ 55')",476780.2,2.8372564950779962E-4,18,18337.7]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.98","CANTILEVER SIGNAL SUPPORT (2 @ 70' & 60')",352841.91000000003,2.0997159716012239E-4,12,18570.626842105266]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-23.99","CANTILEVER SIGNAL SUPPORT (1 ARM @ 65')",273618.70999999996,1.6282690894512032E-4,9,15201.039444444443]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-24.02","FOUNDATION (TRAFFIC SIGNAL CONTROLLER)",8250,4.909466895729619E-6,1,1650]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-24.03","FOUNDATION - CANTILEVER SIGNAL SUPPORT, (_____)",92200,5.4867011852881315E-5,1,4610]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-24.07","FOUNDATION (PEDESTRIAN POLE,_____) (PEDESTRIAN POLE,_____)",800,4.7606951716165999E-7,1,800]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-24.08","FOUNDATION (Cabinet)",1135,6.7542362747310514E-7,1,1135]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-24.41","CANTILEVER SIGNAL SUPPORT (1 ARM @ 54')",57307.45,3.4102912564082467E-5,3,14326.862499999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-24.42","CANTILEVER SIGNAL SUPPORT (2 @ 65' & 75')",84655.26999999999,5.0377241892612442E-5,3,28218.423333333329]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-24.43","CANTILEVER SIGNAL SUPPORT (2 @ 52' & 68')",98732.97,5.8754696694795828E-5,3,24683.2425]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-24.44","CANTILEVER SIGNAL SUPPORT (DESCRIPTION)",21369,1.271641189028439E-5,1,21369]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-24.45","CANTILEVER SIGNAL SUPPORT (DESCRIPTION)",66036,3.9297158294109225E-5,1,22012]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-24.46","CANTILEVER SIGNAL SUPPORT (DESCRIPTION)",25278,1.5042606568515552E-5,1,25278]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-24.47","CANTILEVER SIGNAL SUPPORT (DESCRIPTION)",51734,3.0786225501051649E-5,1,25867]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-24.48","CANTILEVER SIGNAL SUPPORT (DESCRIPTION)",25906,1.5416321139487455E-5,1,25906]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-26.03","PEDESTRIAN SIGNAL HEAD, PUSHBUTTON & 12\" SIGN",45720,2.7207372905788868E-5,1,1270]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-26.05","COUNTDOWN PEDESTRIAN SIGNAL",184470.2,1.0977579880589357E-4,14,991.77526881720416]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-26.06","PEDESTRIAN PUSHBUTTON POST",70668,4.2053600798475239E-5,5,1158.4918032786886]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-26.08","FLASHING WARNING BEACON (DESCRIPTION)",34012.54,2.0240416869052061E-5,4,4858.9342857142856]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-26.09","PEDESTRIAN PUSHBUTTON WITH 15IN SIGN",12425.88,7.3944783648859092E-6,7,248.51759999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-26.11","COUNTDOWN PED SGNL HEAD W/AUDIBLE PUSH BUTTON & 15IN SIGN",273904.12,1.6299675269623671E-4,19,1078.3626771653544]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-35.01","RF DATA SYSTEM (ENCOM MODEL 5200 RADIO)",18052.099999999999,1.0742568163442502E-5,5,3008.6833333333329]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-35.05","DATA SYSTEM POWER SUPPLY",362.5,2.157189999638772E-7,2,120.83333333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-35.06","BATTERY BACK-UP AND POWER CONDITIONER",385498.97000000003,2.2940538564277159E-4,14,9402.4139024390242]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-35.10","ANTENNA (OMNI)",265,1.5769802755979987E-7,1,265]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-35.11","ANTENNA (YAGI)",1824.7,1.0858550599561013E-6,2,608.23333333333335]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-35.20","RF DATA SYSTEM CABLE",488.99999999999994,2.9099749236506464E-7,1,3.26]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-35.21","RF DATA SYSTEM CABLE (RGA COXIAL)",126,7.4980948952961456E-8,1,3.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-40","TEMPORARY TRAFFIC SIGNAL SYSTEM",632556.06999999995,3.7642582852822146E-4,25,14376.27431818182]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-40.02","TEMPORARY TRAFFIC SIGNAL SYSTEM",180647.31,1.0750084706031589E-4,5,36129.462]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730-41.50","BRIDGE SUSPENDED SIGNALS",38000,2.2613302065178851E-5,1,38000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"730M11.10","RISER ASSEMBLY (STREET LIGHTING)",589.16,3.5060139591370451E-7,1,589.16]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"740-06.01","GEOMEMBRANE",261630.61000000002,1.5569294772176324E-4,16,9.8320409620443456]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"740-07.01","GEO GRID REINFORCEMENT",480816,2.8612730120450091E-4,2,2.4719091881220696]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"740-07.02","GEOGRID REINFORCEMENT (SOIL SLOPES)",314172.48,1.8695992607385158E-4,2,2.8592065962268269]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"740-07.06","GEOGRID REINFORCEMENT TYPE 4",116670,6.9428788209063597E-5,1,6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"740-10.03","GEOTEXTILE (TYPE III)(EROSION CONTROL)",1513989.5119899998,9.0095531995112055E-4,108,2.634534840452456]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"740-10.04","GEOTEXTILE (TYPE IV)(STABILIZATION)",2673924.6148000001,1.5912175003681421E-3,71,1.4265982250762155]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"740-11.01","TEMPORARY SEDIMENT TUBE 8IN (SEE PLANS)",379191.26,2.2565175007515186E-4,10,3.2777627370641218]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"740-11.02","TEMPORARY SEDIMENT TUBE 12IN (SEE PLANS)",1175523.8500000001,6.9953883960189461E-4,32,2.8673061772059274]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"740-11.03","TEMPORARY SEDIMENT TUBE 18IN (18INCH)",2861234.6500000004,1.7026832478896393E-3,50,3.1032375251622533]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"740-11.04","TEMPORARY SEDIMENT TUBE 20IN (DESCRIPTION)",1073306.8505999998,6.3871084266430478E-4,28,3.2022090375470555]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"740-11.05","TEMPORARY SEDIMENT TUBE 24IN (EROSION CONTROL)",558523.60000000009,3.3237007571924019E-4,7,4.65432454729544]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"740M06.01","GEOMEMBRANE",4040,2.4041510616663829E-6,1,40.4]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"740M10.03","GEOTEXTILE (TYPE III)(EROSION CONTROL)",59605,3.5470154463025931E-5,1,3.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"740M10.04","GEOTEXTILE (TYPE IV) STABILIZATION",12862.43,7.6542635495320633E-6,1,3.61]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"740M11.03","TEMPORARY SEDIMENT TUBE 18IN (450mm)",315307.2,1.8763518307699371E-4,1,9.92]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.01","INSTALL OVERHEAD CONDUCTOR - 336 AAC",59035.62,3.5131323885924048E-5,1,3.83]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.02","INSTALL OVERHEAD CONDUCTOR - 4/0 AAC",15320.18,9.1168383692871504E-6,1,2.98]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.03","INSTALL OVERHEAD CONDUCOTR - 3/0 ACSR",4844.9699999999993,2.8831781607034094E-6,1,3.03]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.04","INSTALL OVER HEAD CONDUCTOR - 1/0 ACSR",1359.1499999999999,8.0881235531283766E-7,1,2.5499999999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.05","INSTALL OVERHEAD CONDUCTOR - #2ACSR",9830.1600000000017,5.8497994060273304E-6,1,2.2200000000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.07","INSTALL OVERHEAD CONDUCTOR - #2 TPX",528.65,3.1459268780938945E-7,1,5.45]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.08","INSTALL WOOD POLE CLASS 1 60FT LENGTH",3203.3,1.9062418554049319E-6,1,3203.3]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.09","INSTALL WOOD POLE CLASS 2 55 FT LENGTH",10176.4,6.0558422930548959E-6,1,2544.1]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.10","INSTALL WOOD POLE CLASS 2 50 FT LENGTH",15177.050000000001,9.0316635817979654E-6,1,2168.15]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.11","INSTALL WOOD POLE CLASS 3 45 FT LENGTH",36462,2.169805841843556E-5,1,1823.1]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.12","INSTALL WOOD POLE CLASS 4 40 FT LENGTH",10923.15,6.5002234329804825E-6,1,1560.45]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.13","INSTALL ELECTRIC UTILITY ASSY (C1C)",664.35,3.9534597965793605E-7,1,664.35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.14","INSTALL ELECTRIC UTILITY ASSY (C1-2CL)",12195.2,7.2572037196123457E-6,1,762.2]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.15","INSTALL ELECTRIC UTILITY ASSY (C1-3CL)",2327.8000000000002,1.3852432775611403E-6,1,1163.9000000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.16","INSTALL ELECTRIC UTILITY ASSY (C2C)",1086.6500000000001,6.4665117602964733E-7,1,1086.6500000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.17","INSTALL ELECTRIC UTILITY ASSY (C2-2CL)",3388.7,2.0165709660071466E-6,1,1694.35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.21","INSTALL ELECTRIC UTILITY ASSY (C7C)",1333.85,7.9375665683260017E-7,1,1333.85]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.22","INSTALL ELECTRIC UTILITY ASSY (C7-1C)",4851.2999999999993,2.8869450607579512E-6,1,1617.0999999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.23","INSTALL ELECTRIC UTILITY ASSY (C8C)",2909.75,1.7315540969514253E-6,1,2909.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.24","INSTALL ELECTRIC UTILITY ASSY (C8-3CL)",13719.6,8.1643541845638884E-6,1,3429.9]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.25","INSTALL ELECTRIC UTILITY ASSY (A1)",432.6,2.5743459140516765E-7,1,216.3]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.27","INSTALL ELECTRIC UTILITY ASSY (A2)",293.55,1.7468775845350663E-7,1,293.55]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.28","INSTALL ELECTRIC UTILITY ASSY (A3)",607.70000000000005,3.6163430697392599E-7,1,303.85000000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.30","INSTALL ELECTRIC UTILITY ASSY (A5)",1153.5999999999999,6.864922437471137E-7,1,288.39999999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.31","INSTALL ELECTRIC UTILITY ASSY (A5-1)",942.44999999999993,5.6083964556125803E-7,1,314.14999999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.32","INSTALL ELECTRIC UTILITY ASSY (A5-2)",751.9,4.4744583744231519E-7,1,375.95]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.33","INSTALL ELECTRIC UTILITY ASSY (A5-2A)",381.1,2.267876162378858E-7,1,381.1]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.34","INSTALL ELECTRIC UTILITY ASSY (A6)",896.1,5.3325736791070439E-7,1,448.05]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.36","INSTALL ELECTRIC UTILITY ASSY (A8)",1678.9,9.9909139045338878E-7,1,839.45]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.37","INSTALL ELECTRIC UTILITY ASSY (M2-11R)",7266.65,4.3242881961034704E-6,1,427.45]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.38","INSTALL ELECTRIC UTILITY ASSY (M2-12B)",6597.15,3.9258775189288063E-6,1,314.14999999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.40","INSTALL ELECTRIC UTILITY ASSY (E1-2F)",386.25,2.2985231375461396E-7,1,386.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.41","INSTALL ELECTRIC UTILITY ASSY (E1-2T)",11613.25,6.9108929002220601E-6,1,283.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.43","INSTALL ELECTRIC UTILITY ASSY (E3-10P)",1771.6000000000001,1.0542559457544961E-6,1,41.2]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.46","INSTALL ELECTRIC UTILITY ASSY (FP-2)",39907.35,2.3748341057126714E-5,1,973.34999999999991]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.48","INSTALL ELECTRIC UTILITY ASSY (G11-15)",4403.25,2.6203163768025991E-6,1,880.65]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.50","INSTALL ELECTRIC UTILITY ASSY (K6)",216.3,1.2871729570258382E-7,1,108.15]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.51","INSTALL ELECTRIC UTILITY ASSY (K7)",515,3.0646975167281861E-7,1,103]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.53","INSTALL ELECTRIC UTILITY ASSY (M5-2S)",319.3,1.9001124603714754E-7,1,159.65]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.54","INSTALL ELECTRIC UTILITY ASSY (M5-4A)",149.35,8.8876227985117394E-8,1,149.35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.55","INSTALL ELECTRIC UTILITY ASSY (M5-5S)",4727.7000000000007,2.8133923203564752E-6,1,139.05000000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.58","INSTALL ELECTRIC UTILITY ASSY (M5-10C)",2873.7,1.7101012143343278E-6,1,478.95]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.60","INSTALL ELECTRIC UTILITY ASSY (SL-2)",592.25,3.5244021442374139E-7,1,592.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.62","REMOVE OVERHEAD PRI. CONDUCTORS",43445.81,2.5854032236746523E-5,1,43445.81]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.64","REMOVE OVERHEAD SEC. CONDUCTORS",12666.12,7.5374420408895566E-6,1,12666.12]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.65","REMOVE WOOD POLES'",18277.349999999999,1.0876611486868331E-5,1,18277.349999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.66","REMOVE OH ELECTRIC UTILITY PRI ASSY",31518,1.8755948802376499E-5,1,31518]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.67","REMOVE OH ELECTRIC UTILITY GUY/ANCHOR ASSY",29200.5,1.7376834919848815E-5,1,29200.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.68","REMOVE OH ELECTRIC UTILITY MISC ASSY",1169.05,6.9568633629729824E-7,1,1169.05]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.69","REMOVE OH ELECTRIC UTILITY SEC ASSY",4738,2.8195217153899312E-6,1,4738]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.71","REMOVE ELECTRIC UTILITY ASSY (G11-10)",1405.9499999999998,8.3666242206679472E-7,1,468.64999999999992]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-13.72","REMOVE ELECTRIC UTILITY ASSY (G11-15)",3749.2,2.2310997921781194E-6,1,468.65]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.01","1-PH CROSSARM CNSTR DEADEND (VA7)",2882.64,1.7154212911886094E-6,1,960.88]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.02","1-PH DBLE SUPPORTS (VA2 VA1-1)",5040.2199999999993,2.9993688772356769E-6,1,219.13999999999996]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.03","1-PH TAP (VA5-1 VA5-2)",6485.94,3.859697905174371E-6,1,240.22]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.04","1-PH SUPPORT (VA1)",9103.0499999999993,5.4171057727480609E-6,1,202.29]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.05","1-PH DBLE DEADEND ANGLE (VA4)",2446.56,1.4559157973837886E-6,1,271.83999999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.06","1-PH VERTICAL DEADEND (VA6)",4513.84,2.6861270366812341E-6,1,265.52]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.07","1-PH ANGLE (VA3)",161.12,9.5880400756358326E-8,1,161.12]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.08","1-PH DEADEND SINGLE (VA5)",1264.3000000000002,7.5236836318435852E-7,1,126.43000000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.09","3 PH CROSSARM DEADEND (SINGLE VC7-1)",6757.0999999999995,4.0210616680163153E-6,1,965.3]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.10","3 PH CROSSARM DEADEND (DBLE VC8-3)",2233.66,1.3292217971291417E-6,1,1116.83]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.11","3 PH DBLE PRIMARY SUPPORTS (VC1-3)",5512.4400000000005,3.2803808114782767E-6,1,918.74000000000012]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.12","3 PH DBLE PRIMARY SUPPORTS (ANGLE VC2-2)",3002.73,1.7868852765835392E-6,1,1000.91]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.13","3 PH VERTICAL DBLE DEADEND (VC4-1)",1024.1099999999999,6.0943444152553443E-7,1,1024.1099999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.14","3 PH VERITCAL SINGLE DEADEND (VC5)",1011.15,6.0172211534751566E-7,1,1011.15]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.15","3 PH VERTICAL CNSTR ANGLE (VC3)",1990.24,1.1843657447947777E-6,1,995.12]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.16","DOWN GUY 7/16 IN (E1-3)",26972.800000000003,1.6051159840622532E-5,1,168.58]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.17","GUY MARKER (E3-10)",1840,1.0949598894718181E-6,1,11.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.18","OVERHEAD GUY 7/16 IN (E2-3)",379.32,2.2572836156220108E-7,1,189.66]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.19","ANCHOR ASMBLY PISA TWIN 10IN HELIX (F1-3S)",32656.320000000003,1.9433348118345828E-5,1,320.16000000000003]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.20","POLE GROUND (VM2-11 VM2-12)",17989.45,1.0705285969379782E-5,1,156.43]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.21","LIGTHING ARRESTER (VM5-6)",4799.34,2.8560243456183018E-6,1,228.54000000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.22","FUSE CUTOUT (VM5-9)",5781.72,3.4406258109548911E-6,1,275.32]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.23","SECONDARY ASSEMBLIES (K11 K11C J6 J8)",1340.8000000000002,7.9789251076294222E-7,1,67.040000000000006]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.24","TRANSFORMER VG25KVA(ALL 25 KVA'S)*",427.76,2.545543708263396E-7,1,427.76]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.25","TRANSFORMER VG15KVA (ALL 15 KVA'S)*",3849.84,2.2909893374370566E-6,1,427.76]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.26","TRANSFORMER VG37.5KVA (ALL 37.5 KVA'S)*",427.76,2.545543708263396E-7,1,427.76]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.27","TRANSFORMER VG10KVA (ALL 10 KVA'S)*",427.76,2.545543708263396E-7,1,427.76]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.28","TRANSFORMER VG50KVA (ALL 50 KVA'S)*",427.76,2.545543708263396E-7,1,427.76]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.29","WOOD POLE (45-3)",38493.449999999997,2.2906947694233124E-5,1,855.41]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.30","WOOD POLE (40-4)",25093.769999999997,1.4932973709582184E-5,1,643.42999999999995]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.31","WOOD POLE (50-2)",24478.52,1.4566846496540048E-5,1,1112.6600000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.32","WOOD POLE (55-2)",11680.38,6.9508410835808872E-6,1,1297.82]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.33","WOOD POLE (60-2)",1558.8,9.2762145418949453E-7,1,1558.8]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.34","PRIMARY CONDUCTOR (336.4 KCM ACSR)*",54836.25,3.2632333825570101E-5,1,1.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.35","NEUTRAL CONDUCTOR (3/0 ACSR)*",34357.4,2.0445638536162521E-5,1,1.4000000000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.36","TAP CONDUCTOR (4 ACSR)",17845.699999999997,1.0619742228014794E-5,1,1.1499999999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.37","TAP CONDUCTOR (2 ACSR)",1805.4999999999998,1.0744293915442212E-6,1,1.1499999999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.38","SECONDARY CABLE (4 TRIPLEX)",581.58000000000004,3.4609063723859778E-7,1,1.62]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.39","SECONDARY CABLE (2 TRIPLEX)",855,5.0879929646652414E-7,1,1.9]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.40","SECONDARY CABLE (1/0 TRIPLEX)",962.88,5.7299727085577402E-7,1,3.54]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.41","SECONDARY CABLE (4/0 TRIPLEX)",1472.32,8.7615833938431901E-7,1,6.88]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.42","RMVE 30 FOOT WOOD POLE (30)",1556.75,9.2640152605176776E-7,1,119.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.43","RMVE 35 FOOT WOOD POLE (35)",7903.5,4.7032692861089751E-6,1,119.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.44","RMVE 40 FOOT WOOD POLE (40)",2065.5,1.2291519846217608E-6,1,121.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.45","RMVE 45 FOOT WOOD POLE (45)",486,2.8921223167570844E-7,1,121.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.46","RMVE 50 FOOT WOOD POLE (50)",250,1.4877172411301874E-7,1,125]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.47","RMVE 55 FOOT WOOD POLE (55)",125,7.438586205650937E-8,1,125]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.48","RMVE 60 FOOT WOOD POLE (60)",131,7.795638343522182E-8,1,131]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.49","RMVE 1-PH SUPPORT (VA1)",1295,7.706375309054371E-7,1,35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.50","RMVE 1-PH DBLE SUPPORT (VA1-1 VA2)",840,4.9987299301974301E-7,1,35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.51","RMVE 1-PH ANGLE (VA3)",70,4.1656082751645251E-8,1,35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.52","RMVE 1-PH DBLE DEADEND ANGLE (VA4)",70,4.1656082751645251E-8,1,35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.53","RMVE 1-PH TAP (VA5-1 VA5-2 VA5-4)",700,4.1656082751645251E-7,1,35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.54","RMVE 1-PH DEADEND SINGLE (VA5)",280,1.66624331006581E-7,1,35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.55","RMVE 1-PH VERTICAL DEADEND (A6)",245,1.4579628963075836E-7,1,35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.56","RMVE 1-PH XARM CNSTR DEADEND (VA7)",112.5,6.6947275850858441E-8,1,37.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.57","RMVE 1-PH XARM DBLE DEADEND (VA8)",37.5,2.2315758616952814E-8,1,37.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.58","RMVE 1-PH DBLE XARM CNSTR (VA9)",75,4.4631517233905628E-8,1,37.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.59","RMVE 1-PH SINGLE XARM CNSTR (VA9-1)",37.5,2.2315758616952814E-8,1,37.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.60","RMVE 3-PH XARM SUPPORT (VC1)",60,3.5705213787124497E-8,1,60]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.61","RMVE 3-PH DBLE XARM SUPPORT (VC1-1)",60,3.5705213787124497E-8,1,60]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.62","RMVE 3-PH XARM SUPPORT (VC1-3)",120,7.1410427574248994E-8,1,60]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.63","RMVE 3-PH XARM SUPPORT (VC2-2)",195,1.1604194480815462E-7,1,65]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.64","RMVE 3-PH VERTICAL CNSTR (VC3-1 VC3)",65,3.8680648269384874E-8,1,65]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.65","RMVE 3-PH XARM DEADEND SINGLE (VC7)",140,8.3312165503290501E-8,1,70]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.66","RMVE 3-PH XARM DEADEND DBLE (VC8)",70,4.1656082751645251E-8,1,70]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.67","RMVE LIGHTING ARRESTER (VM5-6)",14.5,8.6287599985550878E-9,1,14.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.68","RMVE FUSE CUTOUT (VM5-9)",101.5,6.0401319989885615E-8,1,14.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.69","RMVE SRVCE DROPS ALL SIZES & TYPES(6 TO 4/0)",3880,2.3089371582340508E-6,1,2]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.70","RMVE SEC CABLE ALL SIZES & TYPES (6 TO 4/0 )",10084,6.0008562638227246E-6,1,2]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.71","RMVE CROSSARM PINS (VM5-5 VM5-2)",129,7.6766209642317675E-8,1,21.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.72","RMVE SECONDARY METERING (M8)",220,1.3091911721945651E-7,1,55]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.73","RMVE UG SRVCE & CONDUIT (2 TO 4/0 TRIPLEX)",337.5,2.0084182755257531E-7,1,4.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.74","RMVE CONDUCTOR (ALL SIZE COPPER)",4034.1,2.4006400489773159E-6,1,0.35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.75","RMVE CONDUCTOR (4 ACSR)",10165,6.0490583024353427E-6,1,0.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.76","RMVE CONDUCTOR (2 ACSR)",863.5,5.1385753508636674E-7,1,0.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.77","RMVE CONDUCTOR (1/0 ACSR)",2973.6,1.7695503952898902E-6,1,0.35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.78","RMVE SECONDARY ASSEMBLIES (ALL K & J)",1204,7.1648462332829828E-7,1,21.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.79","RMVE DOWN GUY & GUY GUARD(ALL E1-)",2100,1.2496824825493575E-6,1,30]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.80","RMVE ANCHOR (ALL F1-)",2600,1.5472259307753949E-6,1,40]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.81","RMVE OVERHEAD GUY (ALL E2-)",280,1.66624331006581E-7,1,35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.82","RMVE SECURITY LIGHT (M26-5)",450,2.6778910340343377E-7,1,45]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.83","RMVE TRANSFORMER (10KVA TO 50KVA)",2088,1.2425414397919326E-6,1,87]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"760-15.84","ROCK HOLE DRILL",500,2.9754344822603748E-7,1,500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771-04.52","REMOVE FARM TAP",8460,5.0344351439845544E-6,1,470]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.01","HDD 50mm PE PIPE - UNCONSOLIDATED",98548.319999999992,5.864481389936595E-5,1,74.319999999999993]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.02","HDD 100mm PE PIPE - UNCONSOLIDATED",697531.24,4.1509170078996748E-4,1,141.88999999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.03","50 MM PE Straight Tie-In to 50 MM PE Main",3296,1.9614064107060394E-6,1,824]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.04","100 MM PE Straight Tie-In to 150 MM PE Main",1030,6.1293950334563723E-7,1,1030]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.05","200 MM PE Straight Tie-In to 150 MM PE Main",2575,1.5323487583640931E-6,1,2575]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.06","50 MM PE Straight Tie-In to 50 MM STL Main",12360,7.3552740401476467E-6,1,3090]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.08","50mm PE GAS VALVE ASSEMBLY",721,4.290576523419461E-7,1,721]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.09","50 MM PE Main on New 100 MM PE Main",15450,9.1940925501845592E-6,1,1545]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.10","100mm PE GAS VALVE ASSEMBLY",4635,2.7582277650553675E-6,1,927]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.11","100 MM PE Main on New 100 MM PE Main",9888,5.8842192321181177E-6,1,2472]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.14","50mm STOPPLES",6180,3.6776370200738234E-6,1,6180]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.15","100mm STOPPLES",7210,4.2905765234194606E-6,1,7210]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.16","15mm SERVICE ASSEMBLY",19570,1.1645850563567108E-5,1,1030]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.17","25mm SERVICE ASSEMBLY",17304,1.0297383656206706E-5,1,1442]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.18","32mm SERVICE ASSEMBLY",2987,1.777524559702348E-6,1,1493.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.19","50mm SERVICE ASSEMBLY",5150,3.0646975167281861E-6,1,2575]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.20","15mm PE SERVICE PIPE",18526.78,1.1025044011450373E-5,1,20.27]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.21","25mm PE SERVICE PIPE",15891.68,9.4569305306095118E-6,1,20.27]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.22","32mm PE SERVICE PIPE",6012.84,3.5781622944628947E-6,1,33.78]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.23","50mm PE SERVICE PIPE",11310.66,6.7308255562246263E-6,1,40.54]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.24","RESTORE ASPHALT",10809.5,6.4325918071987051E-6,1,166.3]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.25","RESTORE CONCRETE",4434.8,2.6390913683856625E-6,1,221.74]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.26","RESTORE GRAVEL",1330.3999999999999,7.9170360703984055E-7,1,66.52]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.27","RETIRE IN PLACE 25mm SERV CUT & PLUG",12772,7.6004498414859021E-6,1,412]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.28","RET. IN PLACE 32mm SERV CUT & PLUG",824,4.9035160267650984E-7,1,412]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.29","RETIRE IN PLACE 50mm SERV CUT & PLUG",1030,6.1293950334563723E-7,1,515]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.30","RETIRE GAS MAIN",20600,1.2258790066912745E-5,1,20600]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.31","CREEK CROSSING #5",10300,6.1293950334563723E-6,1,10300]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.32","CREEK CROSSING #6",10300,6.1293950334563723E-6,1,10300]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.33","SEEDING (WITH MULCH)",360.5,2.1452882617097305E-7,1,36.049999999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.34","100 MM PE STRAIGHT TIE-IN TO 100 MM PE MAIN",8240,4.9035160267650978E-6,1,1030]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.35","100 MM PE STRAIGHT TIE-IN TO 100 MM STL MAIN",4120,2.4517580133825489E-6,1,4120]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.36","100 MM PE STRAIGHT TIE-IN TO 150 MM CI/DI MAIN",5150,3.0646975167281861E-6,1,5150]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.37","50 MM X 100 MM TEE ON PE MAIN & 3 VALVES",16480,9.8070320535301956E-6,1,2060]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.38","100 MM X 100 MM TEE ON PE MAIN & 1 VALVE",2781,1.6549366590332206E-6,1,927]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.39","100 MM X 50 MM REDUCER",2884,1.7162306093677844E-6,1,412]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.40","50MM CUT/PLUG (END CAP)",9064,5.3938676294416078E-6,1,824]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"771M10.41","100MM CUT/PLUG (END CAP)",2060,1.2258790066912745E-6,1,1030]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-12.83","PLACE 1 1/4 IN TRIPLE EYE ANCHOR",16830,1.0015312467288422E-5,1,765]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-12.84","PLACE 35FT POLE",1224,7.2838636125733979E-7,1,1224]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-12.85","PLACE 40 FT POLE",1428,8.497840881335631E-7,1,1428]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-12.86","PLACE 45 FT POLE",1632,9.7118181500978631E-7,1,1632]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-12.87","PLACE 55 FT POLE",2244,1.3353749956384564E-6,1,2244]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-12.88","REMOVE 30 FT POLE",255,1.5174715859527912E-7,1,255]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-12.89","REMOVE 35 FT POLE",2550,1.5174715859527912E-6,1,255]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-12.90","REMOVE 40 FT POLE",2295,1.3657244273575122E-6,1,255]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-12.91","REMOVE 45 FT POLE",510,3.0349431719055824E-7,1,255]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-12.92","REMOVE 55 FT POLE",255,1.5174715859527912E-7,1,255]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-12.93","REMOVE PUSH BRACE",255,1.5174715859527912E-7,1,127.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-24.44","PLACE ANCHOR 1-1/4 IN TRIPLE EYE",3225.96,1.919726524478536E-6,1,358.44]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-24.45","PLACE WOOD POLE - 45FT CLASS 3",2821.8,1.6792162044084654E-6,1,940.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-24.46","REMOVE 30FT POLE",154.5,9.1940925501845589E-8,1,154.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-24.47","REMOVE 40FT POLE",741.6,4.4131644240885883E-7,1,185.4]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-24.48","REMOVE 12IN PEDESTAL",111.24,6.6197466361328814E-8,1,37.08]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-24.49","PLACE SPLICE PEDESTAL",166.86,9.9296199541993247E-8,1,166.86]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-24.50","PLACE BURIED COPPER CABLE AT 24IN COVER",3031,1.8037083831462394E-6,1,4.33]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.26","INSTALL 35-2 SYP WOOD POLE",2933.44,1.7456517055283748E-6,3,977.81333333333339]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.27","INSTALL 35-4 SYP WOOD POLE",2653.41,1.5790095219149002E-6,3,884.46999999999991]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.28","INSTALL 3\" SLIC SPLICE CASE",10442.739999999998,6.2143377370559405E-6,3,158.2233333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.29","INSTALL 5\" SLIC SPLICE CASE",35037.9,2.0850595169198158E-5,3,204.9]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.30","INSTALL 7\" SLIC SPLICE CASE",3968.12,2.3613762155494078E-6,3,330.67666666666668]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.31","INSTALL 9\" SLIC SPLICE CASE",5477.5199999999995,3.2596003770541695E-6,3,456.46]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.32","INSTALL AKF25-24(.25M) COMM. CA.",1393.92,8.2950352670247644E-7,3,3.6300000000000003]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.33","INSTALL AKF25-24(10M) COMM. CA.",19068.39,1.1347349025437781E-5,3,3.63]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.34","INSTALL AKF50-24(10M) COMM. CA.",4828.4799999999996,2.8733651777809149E-6,3,5.0933333333333328]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.35","INSTALL AKF100-24(10M) COMM. CA.",19539.28,1.16275694941081E-5,3,6.9733333333333327]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.36","INSTALL AKF100-24(E) COMM. CA.",7685.0400000000009,4.5732666027100547E-6,3,6.0133333333333336]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.38","INSTALL AKF300-24(10M) COMM. CA.",24747.119999999999,1.4726686836927074E-5,3,15.389999999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.39","INSTALL AKF400-24(10M) COMM. CA.",645921.6399999999,3.8437950409883441E-4,3,17.59333333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.40","INSTALL AKF400-26(10M) COMM. CA.",5322.2800000000007,3.16721908724895E-6,3,18.873333333333335]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.41","INSTALL AKF600-24(10M) COMM. CA.",361784.9,2.1529345332422432E-4,3,25.823333333333334]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.43","INSTALL BM80 1 INCH RISER GUARD",323.76,1.9266533359532379E-7,3,53.96]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.44","INSTALL BM83 SERVICE GUARD",423.44,2.5198359543366666E-7,3,35.286666666666669]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.45","INSTALL FOSB(A)2 SNOW SHOE",7978.74,4.7480436241980286E-6,3,120.89]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.46","INSTALL HACO(12) FIBER SPLICE CASE",3189.5299999999997,1.8980475088407865E-6,3,1063.1766666666665]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.47","INSTALL HACO(24) FIBER SPLICE CASE",3329.54,1.9813656252130418E-6,3,1109.8466666666666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.48","INSTALL HACO(72) FIBER SPLICE CASE",13878.2,8.2587349663411876E-6,3,1156.5166666666667]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.50","INSTALL HO1 FIBER CA. SPLICING",11750.4,6.992509068070462E-6,3,40.799999999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.51","INSTALL PE1-3G DOWN GUY ASSEMBLY",26914.68,1.6016573390200734E-5,3,110.76]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.52","INSTALL PE2-3G OVHD GUY ASSEMBLY",6392.88,3.8043191185905415E-6,3,163.92000000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.53","INSTALL PF1-5A ANCHOR ASSEMBLY",710.64,4.2289255209470256E-7,3,236.88]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.54","INSTALL PF3-5A SCREW IN ANCHOR ASSMBLY",26066.78,1.5511999210699019E-5,3,255.55666666666664]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.55","INSTALL PF5-3A ROCK ANCHOR ASSMBLY",29087.279999999999,1.7309459181432511E-5,3,269.32666666666665]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.56","INSTALL PG31-100(88) LOAD COIL",8225.5399999999991,4.8949110702424006E-6,3,2741.8466666666664]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.57","INSTALL PG32-12(88) LOAD COIL",7143.78,4.2511698691364044E-6,3,793.75333333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.58","INTALL PM11 GUY GUARD ASSEMBLY",4254.25,2.5316484292312403E-6,3,18.416666666666668]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.59","INSTALL PM2A POLE GRND ASSMBLY",25287.51,1.504826584490081E-5,3,46.57]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.60","INSTALL PM52 POLE NUMBER",6143.84,3.6561186778981166E-6,3,43.573333333333338]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.61","INSTALL PM91-25-24-20 CABLE STUB",435.76,2.5931506599795618E-7,3,72.626666666666665]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.62","INSTALL PM91-50-24-20 CABLE STUB",547.76,3.2596479840058859E-7,3,91.293333333333337]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.63","INSTALL PM91-200-24-24 CABLE STUB",1509.42,8.9823606324269113E-7,3,251.57000000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.64","INSTALL SEA2-22 AERIAL DROP",40529.360000000001,2.411849105758887E-5,3,1.9266666666666667]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.65","INSTALL SEB2-22 BURIED DROP",3413.9799999999996,2.0316147627494549E-6,3,2.6966666666666663]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.66","INSTALL SEB5-22 BURIED DROP",2598,1.5460357569824909E-6,3,2.8866666666666667]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.67","INSTALL UO12 UNDGRD FIBER CABLE",583,3.4693566063155972E-7,3,1.9433333333333334]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.68","INSTALL YFD12-SMDE(10M) FIBER CA.",275.88,1.6417257299319844E-7,3,2.42]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.69","INSTALL YFD12-SMDE(E) FIBER CA.",4378.74,2.6057307969705589E-6,3,1.67]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.70","INSTALL YFD12-SMDE LOOP FIBER CA.",2254.5,1.3416234080512031E-6,3,1.67]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.71","INSTALL YFD24-SMDE(.25M) FIBER CA.",1190.28,7.0832003110897586E-7,3,2.5433333333333334]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.72","INSTALL YFD24-SMDE LOOP FIBER CA.",1078,6.4150367437533682E-7,3,1.7966666666666666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.73","INSTALL YFD72-SMDE(10M) FIBER CA.",146140.20000000001,8.6966118064885539E-5,3,3.1]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.74","INSTALL YFD72-SMDE LOOP FIBER CA.",12672,7.5409411518406946E-6,3,2.3466666666666667]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.75","REARRANGE EXISTING BURIED CA.",1424.01,8.4740969141671928E-7,3,158.22333333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.76","REARRANGE CABLE STRAIGHT LINE POLE",846.95999999999992,5.0401479781904937E-7,3,70.58]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.77","REARRANGE CABLE ANGLE POLE",5573.4,3.3166573086859947E-6,3,92.89]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.78","REARRANGE COMM. CABLE",1548,9.2119451570781215E-7,3,0.86]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.79","REARRANGE COMM. CA. SPLICING",86413.5,5.1423541526561385E-5,3,5.55]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.80","REARRANGE FIBER CA. SPLICING",21294.240000000002,1.2671923193905634E-5,3,53.773333333333341]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.81","REARRANGE COMM. SPLICE CASE",400.5,2.3833230202905604E-7,3,66.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.82","REARRANGE PM4 CABLE ARM",529.31999999999994,3.1499139603001231E-7,3,176.43999999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.83","REARRANGE AERIAL DROP WIRE",12464.760000000002,7.4176153434199676E-6,3,53.960000000000008]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.84","REARRANGE RISER GUARD",362.68,2.1582611560523856E-7,3,60.446666666666665]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.85","REARRANGE WIRE TERMINAL",11125.85,6.6208475468913189E-6,3,127.88333333333334]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.86","REMOVE COMM. CABLE",182277.81,1.0847113624498099E-4,3,1.17]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.87","REMOVE DISTRIBUTION WIRE",194.66000000000003,1.1583961526336093E-7,3,32.443333333333335]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.88","REMOVE COMM. SPLICE CASE",58.389999999999993,3.4747123883836657E-8,3,19.463333333333331]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.89","REMOVE GUY ASSEMBLY",5313.49,3.1619882734291358E-6,3,19.463333333333331]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.90","REMOVE ANCHOR ASSEMBLY",3270.12,1.9460055618258595E-6,3,25.953333333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.91","REMOVE PM4 CROSS ARM",1362.55,8.1083565076077479E-7,3,64.883333333333326]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.92","REMOVE SYP POLE",19270.350000000002,1.1467532775045244E-5,3,64.88333333333334]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.93","REMOVE AERIAL DROP",11834.72,7.0426867951793008E-6,3,25.953333333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.94","REMOVE RISER GUARD",778.6,4.6333465757758559E-7,3,25.953333333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.95","REMOVE WIRE TERMINAL",408.65999999999997,2.4318821110410497E-7,3,19.459999999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.96","INSTALL AKFS104-24(10M) COMM. CA.",6100.56,3.6303633170196709E-6,3,6.87]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.97","INSTALL AKF200-24(10M) COMM. CA.",7826.5599999999995,4.6574833002959515E-6,3,11.646666666666667]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-25.98","INSTALL HC3 COMM. CA. SPLICING",68918.039999999994,4.1012222533159956E-5,3,5.34]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.42","45-3    45 FOOT CLASS 3    WOOD POLE  (SPEC A45-3)",11287.2,6.7168648176338616E-6,1,940.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.43","55-2    55 FOOT CLASS 2    WOOD POLE (SPEC A55-2)",5028.3599999999997,2.9923111466437557E-6,1,1257.0899999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.44","CO(36)E    36 FIBER LASHED TO EXISTING STRAND",2388.7200000000003,1.4214959712930007E-6,1,1.1100000000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.45","CW12-24(10M)    AERIAL FILLED CABLE     10M STRAND",1779,1.0586595887882415E-6,1,5.93]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.46","CW25-24(10M)    AERIAL FILLED CABLE    10M STRAND",1929,1.1479226232560526E-6,1,6.43]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.47","CW100-24(10M)    AERIAL FILLED CABLE    10M STRAND",7586.16,4.5144244103888734E-6,1,4.33]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.48","HAC(12-24)    AERIAL NONFILLED CLOSURE",123.6,7.3552740401476471E-8,1,123.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.49","HAC(50-24)    AERIAL NONFILLED CLOSURE",247.2,1.4710548080295294E-7,1,123.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.50","HAC(100-24)    AERIAL NONFILLED CLOSURE",247.2,1.4710548080295294E-7,1,123.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.51","HACO(36)    AERIAL NONFILLED FIBER OPTIC CLOSURE",1545,9.1940925501845584E-7,1,772.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.52","HAFO  SB    FIBER OPTIC SNOW SHOE (SPEC PM92)",247.2,1.4710548080295294E-7,1,123.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.53","PE1-3G    10M STRAND DOWN GUY",2847.84,1.6947122671920774E-6,1,118.66000000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.54","PF1-5A    EXPANDING ANCHOR ANCHOR",6506.3600000000006,3.8718495795999233E-6,1,232.37000000000003]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.55","PM52-1   POLE NUMBER (SPEC PM52)",160.69999999999999,9.5630464259848445E-8,1,32.14]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.56","PM11   GUY GUARD",533.91999999999996,3.1772879575369187E-7,1,33.369999999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.57","PM2A   GROUND WIRE ELECTRIC NEUTRAL",426.45,2.5377480699198738E-7,1,28.43]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.58","SEA2-22    AERIAL TWO PAIR DROP",4940,2.9397292684732503E-6,1,4.9400000000000004]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.59","WPE TRANSFER OR TIGHTEN EXISTING DOWN GUY",24.72,1.4710548080295294E-8,1,24.72]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.60","WC    RELASHING EXISTING AERIAL CABLE STRAND",1736,1.0330708522408022E-6,1,1.24]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.61","WC1    REMOVE & REATTACH AERIAL CABLE",494.4,2.9421096160590589E-7,1,61.8]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.62","WC2    SAME AS WC1  ON ANGLE/DEAD-END POLE",444.96,2.6478986544531525E-7,1,74.16]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.63","WHC    RE-TERMINATE ONE EXISTING CABLE SPLICE",1595.3,9.4934212590999522E-7,1,3.71]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.64","WSEA    REARRANGE ONE EXISTING AERIAL DROP",12.36,7.355274040147647E-9,1,12.36]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.65","WHO    RE-TERMINATE ONE FIBER FUSION SPLICE",4438.0199999999995,2.6410075481922376E-6,1,38.929999999999993]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.66","XX   POLE    REMOVE ANY SIZE WOOD POLE",2595.6000000000004,1.544607548431006E-6,1,216.30000000000004]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.67","XXCA    REMOVE ANY SIZE AERIAL CABLE/STRAND",1822.8000000000002,1.0847243948528425E-6,1,0.93]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.68","XXDW    REMOVE ANY SIZE DISTRIBUTION WIRE",52.7,3.1361079443024351E-8,1,0.31]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.69","XXPE   REMOVE ANY SIZE DOWN OR OVERHEAD GUY",321.36,1.9123712504383884E-7,1,24.720000000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.70","XXPF    REMOVE ANY SIZE OR TYPE OF ANCHOR ROD",433.80999999999995,2.5815464654987461E-7,1,33.369999999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"773-26.71","XXSEA    REMOVE ANY SIZE AERIAL DROP",12.36,7.355274040147647E-9,1,12.36]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-60.01","18IN BALL AND SOCKET RESTRAINED DUCTILE IRON PIPE",83473.740000000005,4.9674128871847437E-5,1,662.49]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-60.02","12IN BALL AND SOCKET RESTRAINED DUCTILE IRON PIPE",23235.119999999999,1.3826915449491536E-5,1,215.14]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.01","6\" C900-07 PC 305 PVC WATERLINE",508972.5,3.0288286540445375E-4,1,22.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.02","4\" C900-07 PC 305 PVC WATERLINE",122626,7.2973125764332143E-5,1,19]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.03","4\" HDPE DR 7 WATERLINE",2222,1.3222830839165106E-6,1,22]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.04","2\" HDPE DR 7 WATERLINE",17374,1.033903973895835E-5,1,17]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.05","8\" HDPE DR 7 INSTALLED IN CASING",33002,1.963905775671138E-5,1,29]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.06","6\" HDPE DR 7 INSTALLED IN CASING",10511,6.2549583686077605E-6,1,23]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.07","4\" HDPE DR 7 INSTALLED IN CASING",7974,4.745222912308846E-6,1,18]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.08","2\" HDPE DR 7 INSTALLED IN CASING",3060,1.8209659031433494E-6,1,12]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.09","8\" HDPE DR 7 DIRECTIONAL BORE CREEK CROSSING",103200,6.1412967713854146E-5,1,172]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.10","6\" GATE VALVE & BOX",14300,8.5097426192646721E-6,1,1100]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.11","4\" GATE VALVE & BOX",6300,3.7490474476480724E-6,1,900]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.12","2\" GATE VALVE & BOX",1400,8.3312165503290501E-7,1,700]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.13","DIP FITTINGS",44000,2.61838234438913E-5,1,4]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.14","WITNESS POST",13900,8.271707860683842E-6,1,100]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.15","2\" TIE - CUT IN 90 TO EXISTING LINE",1020,6.0698863438111647E-7,1,510]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.16","2\" TAP & VALVE",2560,1.5234224549173119E-6,1,640]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.17","4\" WET TAP & VALVE",14800,8.8072860674907107E-6,1,1850]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.18","6\" WET TAP & VALVE",2300,1.3686998618397725E-6,1,2300]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.19","4\" HYDRA-STOP INSERTION VALVE",32800,1.9518850203628059E-5,1,4100]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.20","6\" HYDRA-STOP INSERTION VALVE",4400,2.61838234438913E-6,1,4400]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.21","FIRE HYDRANT ASSEMBLY",5600,3.3324866201316201E-6,1,2800]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.22","2-1/2\" BLOW OFF",12600,7.4980948952961448E-6,1,1800]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.23","3/4\" SERVICE METER INSTALLATION",35280,2.0994665706829206E-5,1,840]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.24","3/4\" COPPER SERVICE LINE (TRENCHED)",23430,1.3942885983872117E-5,1,22]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.25","14\" CASED ROAD BORE (INCLUDING SPACERS)",249750,1.4862295238890572E-4,1,225]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.26","12\" CASED ROAD BORE (INCLUDING SPACERS)",86070,5.1219129177630099E-5,1,190]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.27","8\" CASED ROAD BORE (INCLUDING SPACERS)",41040,2.4422366230393157E-5,1,190]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.28","6\" CASED ROAD BORE (INCLUDING SPACERS)",48450,2.8831960133103033E-5,1,190]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.29","12\" CASING TRENCHED (INCLUDING SPACERS)",8288,4.9320801977947979E-6,1,32]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.30","8\" CASING TRENCHED (INCLUDING SPACERS)",10624,6.3222031879068445E-6,1,32]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.31","MANUAL AIR RELEASE VALVE & BOX",4720,2.8088101512537941E-6,1,590]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775-71.32","ROCK EXCAVATION IN WATERLINE TRENCH",7280,4.3322326061711063E-6,1,26]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M01.18","600mm STEEL CASING PIPE OPEN CUT METHOD",171453.80000000002,1.0202990972691479E-4,1,1182.44]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M01.19","400mm DIP SLIP JOINT WATER LINE",50676.25,3.0156772336329467E-5,1,405.41]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.01","150mm DIP SLIP JOINT WATER LINE",21132.170000000002,1.2575477460597647E-5,1,152.03]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.02","200mm DIP SLIP JOINT WATER LINE",1270700.7,7.5617733588247919E-4,1,253.38]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.03","200mm Water Line Under Pavement",131758.25,7.8407608074456615E-5,1,405.41]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.04","300mm DIP SLIP JOINT WATER LINE",8108.2000000000007,4.8250835738127148E-6,1,405.41]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.05","50mm HDPE WATER LINE",10540.4,6.2724539233634512E-6,1,40.54]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.06","50mm Water Line Under Pavement",2702.72,1.608353256778952E-6,1,168.92]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.07","150mm HDPE WATER LINE",93954.54,5.5911115616182332E-5,1,152.03]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.08","BORE/JACK 400mm STEEL CASING PIPE-UNCON.",163176.72,9.7104327878029236E-5,1,1013.52]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.09","CONNECT TO 50mm WATER LINE",6489,3.8615188710775143E-6,1,927]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.10","CONNECT TO 150mm WATER LINE",25750,1.5323487583640931E-5,1,5150]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.11","CONNECT TO 200mm WATER LINE",72100,4.2905765234194604E-5,1,7210]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.12","CONNECT TO 400mm WATER LINE",51500,3.0646975167281863E-5,1,10300]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.13","50mm GATE VALVE ASSEMBLY",2060,1.2258790066912745E-6,1,515]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.14","150mm GATE VALVE ASSEMBLY",25956,1.5446075484310057E-5,1,1236]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.15","200mm GATE VALVE ASSEMBLY",89301,5.3141854940066751E-5,1,1751]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.16","300mm GATE VALVE ASSEMBLY",16686,9.9296199541993229E-6,1,2781]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.17","20mm WATER SERVICE METER ASSEMBLY",48204,2.8685568756575823E-5,1,927]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.18","25mm WATER SERVICE METER ASSEMBLY",3708,2.2065822120442939E-6,1,927]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.19","40mm WATER SERVICE METER ASSEMBLY",4120,2.4517580133825489E-6,1,2060]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.20","50mm WATER SERVICE METER ASSEMBLY",9270,5.516455530110735E-6,1,3090]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.21","100mm WATER SERVICE METER ASSEMBLY",10300,6.1293950334563723E-6,1,10300]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.26","25mm HDPE SERVICE PIPE",19297.04,1.1483415644311549E-5,1,40.54]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.30","25mm AUTO AIR RELEASE VALVE ASSEMBLY",30591,1.8204303249365425E-5,1,2781]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.31","50mm BLOW-OFF ASSEMBLY",10815,6.4358647851291913E-6,1,3605]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.32","FIRE HYDRANT ASSEMBLY",98880,5.8842192321181174E-5,1,4120]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.33","REMOVE FIRE HYDRANT",1339,7.9682135434932846E-7,1,103]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.34","REMOVE BLOW-OFF ASSEMBLY",3090,1.8388185100369117E-6,1,3090]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.35","DI FITTINGS",74002,4.4037620511246456E-5,1,9.08]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.36","CREEK CROSSING #7",15450,9.1940925501845592E-6,1,15450]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.37","CREEK CROSSING #8",15450,9.1940925501845592E-6,1,15450]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.38","CONCRETE ENCASEMENT",2533.7999999999997,1.5078311782302674E-6,1,168.92]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.39","RESTORE ASPHALT",31569.690000000002,1.8786708844054108E-5,1,8.31]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.40","RESTORE CONCRETE",1773.8,1.0555651369266905E-6,1,88.69]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.41","RESTORE GRAVEL",1352.98,8.0514066916172841E-7,1,22.18]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.42","REMOVE & REPLACE ASPHALT CONC DRIVEWAY",14700.919999999998,8.7483248577902381E-6,1,33.26]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.43","REMOVE & REPLACE PORTLAND CONC DW",1884.79,1.1216138315639063E-6,1,110.87]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.44","REMOVE & REPLACE BRICK PAVEMENT",3325.8,1.9791400002203112E-6,1,55.43]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.45","REMOVE & REPLACE CONCRETE CURB",9121.5,5.4280851259876022E-6,1,101.35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.46","REMOVE & REPLACE ASPHALT CONCRETE CURB",3378,2.0102035362151095E-6,1,33.78]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.47","300mm STEEL CASING PIPE OPEN CUT METHOD",7179.1,4.2721883383190919E-6,1,422.3]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.48","400mm STEEL CASING PIPE OPEN CUT METHOD",94595.199999999997,5.6292363987263326E-5,1,422.3]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.49","RECONNECT SERVICE ASSEMBLY",46144,2.745968974988455E-5,1,721]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.50","RETIRE WATER METER ASSEMBLIES",10300,6.1293950334563723E-6,1,10300]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.51","RETIRE EXISTING MAINS",10300,6.1293950334563723E-6,1,10300]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.52","RETIRE WATER, AIR, & BLOWOFF VALVE ASSY",4120,2.4517580133825489E-6,1,103]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.53","FLOWABLE FILL",4688.4299999999994,2.7900232579328018E-6,1,161.66999999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.54","SEEDING (WITH MULCH)",6025.5,3.5856960945719779E-6,1,30.9]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.55","300MM WATER LINE UNDER PAVEMENT",172299.25,1.0253302594352019E-4,1,405.41]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.56","CONNECT TO 100MM WATER LINE",7210,4.2905765234194606E-6,1,3605]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.57","CONNECT TO 300MM WATER LINE",7210,4.2905765234194606E-6,1,7210]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.58","150MM FIRE CONNECTION",5150,3.0646975167281861E-6,1,5150]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.59","200MM FIRE CONNECTION",5150,3.0646975167281861E-6,1,5150]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.60","50MM HDPE SERVICE PIPE",3642.1,2.1673659855681024E-6,1,47.3]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.61","100MM DUCTILE IRON SERVICE PIPE",3783.68,2.2516183883677872E-6,1,118.24]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.62","20MM COPPER SERVICE PIPE",6756.9999999999991,4.0210021593266701E-6,1,67.569999999999993]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.63","RESTRAINED JOINT GASKET FOR 200MM PIPE",6180,3.6776370200738234E-6,1,103]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.64","RESTRAINED JOINT GASKET FOR 300MM PIPE",3090,1.8388185100369117E-6,1,154.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"775M02.65","100MM STEEL CASING PIPE OPEN CUT METHOD",2575,1.5323487583640931E-6,1,257.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.01","250mm PVC FORCE MAIN",30526.16,1.8165717814999473E-5,1,229.52]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.02","200mm DIP GRVTY SWR 0M-1.829M DEPTH",36113.4,2.1490611126332366E-5,1,601.89]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.03","200mm DIP GRVTY SWR 1.829M-2.438M DEPTH",55585,3.3077905139288589E-5,1,444.68]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.04","200mm DIP GRVTY SWR 2.438M-3.048M DEPTH",51817.7,3.0836034274284685E-5,1,304.81]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.05","200mm DIP GRVTY SWR 3.048M-3.658M DEPTH",44352,2.6393294031442429E-5,1,369.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.06","200mm DIP GRVTY SWR 3.658M-4.267M DEPTH",46900.799999999996,2.7910051513119476E-5,1,390.84]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.07","200mm DIP GRVTY SWR 4.267M-4.877M DEPTH",76635,4.5604484309604769E-5,1,510.9]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.08","200mm DIP GRVTY SWR 4.877M-5.486M DEPTH",128777.9,7.6634040842615665E-5,1,815.05]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.09","200mm DIP GRVTY SWR 5.486M-6.096M DEPTH",57008,3.3924713792939891E-5,1,814.4]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.10","200mm DIP GRVTY SWR >6.096M DEPTH",48052.55,2.8595442846108159E-5,1,814.45]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.11","FLOWABLE FILL",17292,1.029024261344928E-5,1,216.15]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.12","BORE/JACK 400mm STEEL CASING PIPE-UNCON.",133519.65,7.9455794133867299E-5,1,1405.47]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.13","BORE/JACK 500mm STEEL CASING PIPE-UNCON.",141150,8.3996515434210382E-5,1,1411.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.16","OPEN CUT 400mm STEEL CASING PIPE",114179.18999999999,6.7946539816511793E-5,1,623.92999999999995]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.17","1200mm MANHOLE 0M-1.219M DEPTH",3203.97,1.9066405636255545E-6,1,3203.97]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.18","1200mm MANHOLE 1.219M-1.829M DEPTH",7581.48,4.5116394037134771E-6,1,3790.74]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.19","1200mm MANHOLE 1.829M-2.438M DEPTH",4474.88,2.6629424511954616E-6,1,4474.88]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.20","1200mm MANHOLE 2.438M-3.048M DEPTH",21399.040000000001,1.2734288300653811E-5,1,5349.76]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.21","1200mm MANHOLE 3.048M-3.658M DEPTH",33451.4,1.9906489807976942E-5,1,6690.2800000000007]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.22","1200mm MANHOLE 3.658M-4.267M DEPTH",22653.449999999997,1.3480771254432257E-5,1,7551.1499999999987]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.23","1200mm MANHOLE 4.267M-4.877M DEPTH",8407.65,5.0032823449552883E-6,1,8407.65]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.24","1200mm MANHOLE 4.877M-5.486M DEPTH",9334.24,5.5546839123388162E-6,1,9334.24]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.25","1200mm MANHOLE >5.486M DEPTH",12827.41,7.6334236064183105E-6,1,12827.41]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.26","INSERTION VALVE (250mm)",14258.7,8.4851655304412023E-6,1,14258.7]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.27","MANHOLE DROP CONNECTION ASSEMBLY",4351.97,2.5898003207525372E-6,1,4351.97]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.28","1.219M DROP MANHOLE 3.658M-4.267M DEPTH",9277.84,5.5211210113789198E-6,1,9277.84]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.29","150mm PVC PIPE FOR SERVICE LATERAL",1630.6999999999998,9.7040820204439867E-7,1,163.07]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.30","150mm CLEAN OUT ASSEMBLY",6979.95,4.1536767828906606E-6,1,1395.99]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.31","CONNECT SERVICE LINES (ALL SIZES)",6524.2,3.8824659298326275E-6,1,1304.8399999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.32","CONNECT EX. 200mm SEWER TO NEW MANHOLE",23707.439999999999,1.410798689242378E-5,1,2963.43]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.33","CONNECT TO 250mm FORCE MAIN",10664.02,6.3460185655028574E-6,1,5332.01]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.34","RETIREIN PLACE 1200mm MANHOLE",16439.5,9.7829310342238874E-6,1,1174.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.35","TV INSPECTION",7467.6500000000005,4.4439006622903383E-6,1,6.41]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.36","RESTORE ASPHALT",14949,8.8959540150620687E-6,1,4.95]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.37","RESTORE CONCRETE",13203,7.8569322938567461E-6,1,132.03]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.38","RESTORE GRAVEL",6640,3.951376992441778E-6,1,13.28]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.39","REMOVE & REPLACE ASP CONC DW",13232.939999999999,7.8747491955365208E-6,1,38.58]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.40","REMOVE & REPLACE BRICK PAVEMENT",5061,3.0117347829439514E-6,1,50.61]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.41","REMOVE AND REPLACE CONCRETE CURB",1825,1.0860335860250369E-6,1,36.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.42","REMOVE AND REPLACE ASPHALT CONCRETE CURB",3650,2.1720671720500739E-6,1,36.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.43","CREEK CROSSING #1",4979.49,2.9632292500141428E-6,1,4979.49]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.44","CREEK CROSSING #2",4979.49,2.9632292500141428E-6,1,4979.49]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.45","CREEK CROSSING #3",4979.49,2.9632292500141428E-6,1,4979.49]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.46","CREEK CROSSING #4",4979.49,2.9632292500141428E-6,1,4979.49]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.47","CONCRETE ENCASEMENT",15428.099999999999,9.1810601471522572E-6,1,514.27]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.48","SEEDING (WITH MULCH)",2205,1.3121666066768254E-6,1,35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"777M02.49","OPEN CUT 20IN STEEL CASING PIPE",11035.31,6.5669683792865476E-6,1,848.87]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-01.03","POLE 30FT CLASS 4 WOOD",517,3.0765992546572278E-7,1,517]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-01.04","POLE 30FT CLASS 5 WOOD",1259.1399999999999,7.492977147986656E-7,2,419.71333333333331]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-01.05","POLE 30FT CLASS 6 WOOD",12993.52,7.7322734907879658E-6,5,1443.7244444444448]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-02.01","POLE 35FT CLASS 2 WOOD",17522.229999999996,1.042724946961944E-5,4,973.45722222222219]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-02.02","POLE 35FT CLASS 3 WOOD",2237,1.3312093873632917E-6,2,1118.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-02.03","POLE 35FT CLASS 4 WOOD",11940.92,7.1058850235825118E-6,5,852.9228571428572]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-02.04","POLE 35FT CLASS 5 WOOD",50827.609999999993,3.0246844688976447E-5,11,1373.7191891891891]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-02.05","POLE 35FT CLASS 6 WOOD",675,4.0168365510515062E-7,1,675]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-02.07","POLE 35FT CLASS 2 METAL",7590,4.5167095440712492E-6,2,3795]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-02.09","POLE 35FT CLASS H2 METAL",5996.71,3.5685635428231226E-6,1,5996.71]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-03.01","POLE 40FT CLASS 2 WOOD",21348.07,1.2703956721541649E-5,7,1524.8621428571428]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-03.02","POLE 40FT CLASS 3 WOOD",120841.13,7.1910973015461735E-5,8,3356.6980555555556]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-03.03","POLE 40FT CLASS 4 WOOD",284665.83999999997,1.6940091125152294E-4,23,1860.5610457516339]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-03.06","POLE 40FT CLASS 2 METAL",100865,6.0023439810638542E-5,5,4034.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-04.01","POLE 45FT CLASS 1 WOOD",57302.99,3.4100258476524285E-5,6,1685.3820588235294]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-04.02","POLE 45FT CLASS 2 WOOD",376416.75,2.2400067553007659E-4,16,1601.7734042553191]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-04.03","POLE 45FT CLASS 3 WOOD",197047.46,1.1726036142516439E-4,15,1728.48649122807]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-04.04","POLE 45FT CLASS 4 WOOD",96768.790000000008,5.7585838914522599E-5,12,1444.3102985074627]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-04.06","POLE 45FT CLASS 1 METAL",14642.7,8.7136788986787982E-6,3,3660.6750000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-04.07","POLE 45FT CLASS 2 METAL",254273.93,1.5131508385237216E-4,10,4237.8988333333336]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-04.08","POLE 45FT CLASS H1 METAL",27370,1.6287528355893293E-5,3,5474]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-05.01","POLE 50FT CLASS 1 WOOD",53057.59,3.1573876566326649E-5,8,1894.9139285714284]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-05.02","POLE 50FT CLASS 2 WOOD",627916.39,3.7366481575649074E-4,25,2019.0237620578778]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-05.03","POLE 50FT CLASS 3 WOOD",98559.54,5.8651490774344142E-5,8,1564.437142857143]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-05.04","POLE 50FT CLASS 4 WOOD",1127.92,6.7121041224622443E-7,1,1127.92]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-05.05","POLE 50FT CLASS 1 METAL",86610.81,5.154095812210034E-5,4,4558.4636842105265]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-05.06","POLE 50FT CLASS 2 METAL",119232.27,7.0953561511235847E-5,9,4968.0112500000005]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-05.07","POLE 50FT CLASS H1 METAL",609652.19999999995,3.627960356131797E-4,7,4916.5499999999993]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-05.08","POLE 50FT CLASS H2 METAL",207916.42,1.2372833709922614E-4,3,5331.1902564102566]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-06.01","POLE 55FT CLASS 1 WOOD",79360.639999999999,4.7226476958050398E-5,9,2404.8678787878789]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-06.02","POLE 55FT CLASS 2 WOOD",1331179.17,7.9216728089694913E-4,15,3124.8337323943665]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-06.03","POLE 55FT CLASS 3 WOOD",19378.52,1.1531903324634464E-5,5,2153.1688888888889]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-06.05","POLE 55 FT CLASS 1 METAL",473436.76,2.817360121747259E-4,10,5379.9631818181815]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-06.06","POLE 55 FT CLASS 2 METAL",28212,1.6788591522705938E-5,2,4702]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-06.07","POLE 55FT CLASS H1 METAL",335497.88,1.996503921754507E-4,8,5083.3012121212123]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-06.08","POLE 55FT CLASS H2 METAL",275162.5,1.6374559814499409E-4,4,6711.2804878048782]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-07.01","POLE 60FT CLASS 1 WOOD",262923.92000000004,1.5646257955581367E-4,9,5477.581666666666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-07.02","POLE 60FT CLASS 2 WOOD",92019.28,5.4759467748954494E-5,7,2706.4494117647059]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-07.03","POLE 60FT CLASS 3 WOOD",12052,7.1719872760404078E-6,1,3013]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-07.05","POLE 60FT CLASS 1 METAL",285004.82999999996,1.6960263975855121E-4,6,6333.4406666666673]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-07.06","POLE 60FT CLASS 2 METAL",5092.16,3.030277690637398E-6,1,5092.16]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-07.07","POLE 60FT CLASS H1 METAL",129004.11,7.6768655449462088E-5,5,5608.8743478260867]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-07.08","POLE 60FT CLASS H2 METAL",199686.18,1.188306291205704E-4,4,7987.4471999999996]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-07.09","POLE 60FT CLASS H3 METAL",67287,4.0041612001570771E-5,2,8410.875]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-08.01","POLE 65FT CLASS 2 WOOD",53696.36,3.195400022317334E-5,4,3356.0225]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-08.02","POLE 65FT CLASS 3 WOOD",40150,2.389273889255081E-5,1,3650]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-08.04","POLE 65FT CLASS H2 METAL",183748.66,1.0934641980662754E-4,7,7989.072173913044]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-08.05","POLE 65FT CLASS H3 METAL",9305,5.5372835714865579E-6,1,9305]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-08.06","POLE 65FT CLASS H4 METAL",9445,5.6205957369898484E-6,1,9445]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-09.01","POLE 70FT CLASS 1 WOOD",12055,7.1737725367297639E-6,1,12055]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-09.02","POLE 70FT CLASS 2 WOOD",8054.62,4.7931988179008123E-6,1,4027.31]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-09.05","POLE 70FT CLASS H2 METAL",235760.36,1.4029790093882393E-4,6,8731.8651851851846]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-10.02","POLE 75FT CLASS 2 WOOD",5146,3.062317169142378E-6,1,5146]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-10.05","POLE 75FT CLASS H2 METAL",83190.59,4.9505630017117023E-5,6,10398.82375]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-10.07","POLE 75FT CLASS H4 METAL",51115.76,3.0418318978189117E-5,3,10223.152]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-11.05","POLE 80FT CLASS H2 METAL",220524.96,1.3123151403661798E-4,5,11026.248]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-11.06","POLE 80FT CLASS H3 METAL",104987.39,6.2476620081703611E-5,5,11665.265555555556]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-11.07","POLE 80FT CLASS H4 METAL",11530,6.8613519160924246E-6,1,11530]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-11.08","POLE 80FT CLASS H5 METAL",16080,9.5689972949493655E-6,1,16080]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-12.05","POLE 85FT CLASS H2 METAL",163438.38,9.7260038315354891E-5,3,10895.892]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-12.06","POLE 85FT CLASS H3 METAL",49476.53,2.9442834684917982E-5,3,16492.176666666666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-12.07","POLE 85FT CLASS H4 METAL",21529.73,1.2812060207151133E-5,2,10764.865]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-12.08","POLE 85FT CLASS H5 METAL",17100,1.0175985929330483E-5,1,17100]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-13.05","POLE 90FT CLASS H2 METAL",83710.16,4.9814819315906631E-5,3,11958.594285714285]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-13.06","POLE 90FT CLASS H3 METAL",305840.64000000001,1.8200175726651636E-4,3,11763.101538461538]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-13.07","POLE 90FT CLASS H4 METAL",18925.419999999998,1.1262269451852029E-5,1,18925.419999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-13.08","POLE 90FT CLASS H5 METAL",52890,3.1474145953350246E-5,1,17630]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-14.05","POLE 95FT CLASS H2 METAL",6075,3.6151528959463556E-6,1,6075]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-14.06","POLE 95FT CLASS H3 METAL",94826.13,5.6429787404261007E-5,4,11853.266250000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-14.07","POLE 95FT CLASS H4 METAL",54052.42,3.2165886863524067E-5,3,10810.484]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-14.10","POLE 95FT CLASS H7 METAL",40560,2.4136724520096161E-5,1,20280]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-15.01","POLE 100FT CLASS H4 METAL",41042.99,2.442414554021355E-5,3,10260.747499999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-15.03","POLE 100FT CLASS H6 METAL",14840,8.8310895433487937E-6,1,7420]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-16.01","POLE 105FT CLASS H4 METAL",36159.97,2.1518324323100138E-5,3,12053.323333333334]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-17.01","POLE 110FT CLASS H4 METAL",28716.97,1.7089092552807346E-5,2,14358.485000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-17.02","POLE 110FT CLASS H5 METAL",153509.85,9.1351700211323575E-5,3,13955.44090909091]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-18.01","POLE 115FT CLASS H4 METAL",31110.93,1.8513706779437755E-5,2,15555.465]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.01","POLE (52' Engineered)",762671.01,4.5385552435486944E-4,20,9079.4167857142857]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.02","POLE (60FT CLASS H6 METAL)",220857.25,1.3142925546144005E-4,10,10517.011904761905]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.03","POLE (90FT CLASS H1 METAL)",186923.97,1.1123600517980078E-4,5,10995.527647058823]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.04","POLE (90FT CLASS H7 METAL)",118163.94,7.0317812327149202E-5,6,13129.326666666668]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.05","POLE (H2-110)",89921.97,5.3511386050156594E-5,4,9991.33]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.06","POLE (H3-100)",104162.3,6.1985619834309974E-5,3,10416.23]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.07","POLE (H3-110)",55476.97,3.3013617901864871E-5,3,11095.394]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.08","POLE (H2-85)",287947,1.7135348657268564E-4,3,11997.791666666666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.09","POLE (SPECIFY POLE LENGTH, CLASS, AND MATERIAL) (80FT SELF SUPPORTING METAL)",59735,3.5547515759564699E-5,1,59735]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.10","POLE (SPECIFY POLE LENGTH, CLASS, AND MATERIAL) (80FT CLASS 1 METAL)",9775,5.8169744128190329E-6,1,9775]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.11","POLE (SPECIFY POLE LENGTH, CLASS, AND MATERIAL) (85FT CLASS H1 METAL)",10730,6.3852823989307651E-6,1,10730]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.12","POLE (SPECIFY POLE LENGTH, CLASS, AND MATERIAL) (90FT CLASS 1 METAL)",11100,6.6054645506180326E-6,1,11100]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.13","POLE (SPECIFY POLE LENGTH, CLASS, AND MATERIAL) (90FT CLASS H1 METAL)",22880,1.3615588190823476E-5,1,11440]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.14","POLE (SPECIFY POLE LENGTH, CLASS, AND MATERIAL) (92FT SELF SUPPORTING METAL)",64305,3.8267062876350683E-5,1,64305]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.30","TOP EXISTING POLE",1960,1.1663703170460669E-6,1,280]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.31","FIELD POLE MODIFICTION",1100,6.545955860972825E-7,1,55]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.51","4 FT. DIA DRILLED PIER FOUNDATION",28400,1.6900467859238931E-5,1,1775]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.52","5 FT. DIA DRILLED PIER FOUNDATION",46350,2.7582277650553676E-5,1,2575]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-20.53","6 FT. DIA DRILLED PIER FOUNDATION",68800,4.094197847590276E-5,1,3440]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-21.01","1PH SGL PRIMARY SUPPORT 15KV",13202.3,7.8565157330292289E-6,8,388.30294117647054]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-21.02","1PH SGL PRIMARY SUPPORT MISC 15KV",781.77,4.6522108303933864E-7,1,260.58999999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-21.04","1PH SGL SUPPORT 15KV",261.14,1.5540099213949487E-7,1,261.14]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-21.05","1PH DBL PRIMARY SUPPORT 15KV",5522.4400000000005,3.2863316804427974E-6,9,262.97333333333336]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-21.06","1PH PRIMARY MED ANGLE 15KV",2109.75,1.2554845797897652E-6,3,527.4375]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-21.07","1PH PRIMARY LG ANGLE 15KV",8685.3499999999985,5.1685379761000289E-6,13,394.78863636363639]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-21.08","1PH DEADEND 15KV",25035.45,1.4898268241781101E-5,18,272.12445652173915]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-21.09","1PH PRIMARY TAP 15KV",40599.719999999994,2.4160361371623234E-5,17,356.1378947368421]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-21.10","1PH VERTICAL DDE 15KV",15552.23,9.2549282836088535E-6,14,420.33054054054054]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-21.11","1PH CROSSARM DEADEND 15KV",2646,1.5745999280121904E-6,1,882]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-22.01","1PH SGL PRIMARY SUPPORT 25KV",11948.02,7.1101101405473212E-6,12,271.54590909090911]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-22.02","1PH DBL PRIMARY SUPPORT 25KV",1469.1399999999999,8.7426596305360144E-7,3,293.82799999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-22.07","1PH DBL PTS ANGLE 25KV",3354.09,1.9959750085209405E-6,7,304.91727272727275]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-22.10","1PH SUSPENSION ANGLE 25KV",3204.22,1.9067893353496675E-6,8,400.52750000000003]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-22.11","1PH DDE ANGLE 25KV",12064.21,7.1792532870460876E-6,11,402.14033333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-22.12","1PH DEAD END MISC 25KV",58643.43,3.4897936756004507E-5,4,424.95239130434783]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-22.13","1PH DEAD END 25KV",37430.46,2.2274376274173536E-5,14,290.15860465116276]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-22.14","1PH DEAD END TAP 25KV",15589.36,9.2770238600741196E-6,7,399.72717948717951]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-22.15","1PH DEAD END TAP W/ EXTENSION 25KV",127965.54000000001,7.6150616051413869E-5,10,882.52096551724139]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-22.16","1PH DDE TANGENT 25KV",18130.2,1.078904445005541E-5,12,464.87692307692311]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-22.18","1PH SGL DEAD END XARM 25KV",2610.1400000000003,1.5532601119054192E-6,3,652.53499999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-22.19","1PH CROSSARM DBL TANGENT 25KV",476.55,2.8358866050423635E-7,1,476.55]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-23.01","2PH CROSSARM SGL PRIM SUPPORT 15KV",3904.6,2.3235762958867721E-6,5,557.79999999999995]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-23.06","2PH VERTICAL CONST DEADEND (SGL) 15KV",4612.34,2.7447430959817636E-6,2,922.46800000000007]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-23.07","2PH CROSSARM CONST DEADEND (SGL) 15KV",12072.51,7.1841925082866403E-6,8,1097.5009090909091]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-23.08","2PH CROSSARM CONST DEADEND (DBL) 15KV",5745,3.4187742201171708E-6,3,1436.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-24.01","2PH CROSSARM SGL 25KV",353.17,2.1016683921997933E-7,1,353.17]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-24.02","2PH DBL CROSSARM, ANGLE 25KV",685,4.0763452406967138E-7,1,685]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-24.06","2PH DEAD END 25KV",507.21,3.0183402474945696E-7,2,253.60499999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-24.08","2PH DEAD END CROSSARM 25KV",13646.05,8.1205855433298384E-6,6,852.87812499999995]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-24.10","2PH DDE XARM 25KV",5523.34,3.2868672586496038E-6,5,1104.6680000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.01","3PH CROSSARM SGL 15KV",143051.10999999999,8.5127841083924377E-5,14,1044.1686861313867]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.02","3PH NARROW PROFILE SGL 15KV",19837.02,1.1804750666657741E-5,3,991.851]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.03","3PH NARROW PROFILE SGL LG COND 15KV",28637.9,1.7042039031904879E-5,2,1363.7095238095239]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.06","3PH CROSSARM DBL 15KV",83447,4.9658216248236302E-5,1,1703]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.07","3PH CROSSARM DBL LRG COND 15KV",107694.91,6.4087829755585542E-5,8,1958.0892727272728]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.08","3PH CROSSARM SGL LRG COND 15KV",161225.85999999999,9.5943396655216728E-5,8,977.12642424242415]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.10","3PH CROSSARM DBL DBL PRIM SUPPORT 15KV",95220.62,5.6664543234042376E-5,13,1763.3448148148148]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.11","3PH CROSSARM DBL PRIM SUP LRG COND 15KV",86742.83,5.1619521494169945E-5,5,1845.5921276595745]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.12","3PH CROSSARM DBL 10FT PRIM SUP 15KV",94269.9,5.6098782219847459E-5,6,2005.7425531914892]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.13","3PH NARROW PROFILE DBL SUPPORT 15KV",1479.72,8.8056198241806447E-7,1,739.86]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.14","3PH NARROW PROFILE LG COND SM ANGLE 15KV",4120,2.4517580133825489E-6,1,2060]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.15","3PH VERTICAL 15KV",14342.5,8.5350338123638861E-6,5,1792.8125]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.16","3PH VERTICAL LRG COND 15KV",8922.83,5.3098592122694679E-6,5,1274.69]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.17","3PH VERTICAL DEADEND LARGE ANGLE 15KV",22973.119999999999,1.3671002682621093E-5,5,2297.3119999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.18","3PH VERTICAL DEADEND LRG ANG LG COND 15KV",21305.58,1.2678671479311401E-5,4,1775.4650000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.19","3PH VERTICAL DEADEND 15KV",8685.9399999999987,5.1688890773689352E-6,4,1737.1880000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.20","3PH VERTICAL DEADEND LG COND 15KV",5242,3.119445511201777E-6,2,1747.3333333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.21","3PH CROSSARM DEADEND SGL 15KV",347129.79000000004,2.0657238939716057E-4,20,1542.7990666666669]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.22","3PH XARM DEADEND SGL NARROW PROFILE 15KV",21041.51,1.25215268825653E-5,3,1315.0943749999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.23","3PH CROSSARM DDE 15KV",202803.14,1.2068549117333567E-4,16,2778.1252054794522]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.24","3PH CROSSARM DDE LRG COND 15KV",163192.07999999999,9.7113468412758725E-5,9,2914.1442857142861]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.25","3PH CROSSARM DDE NARROW PROFILE 15KV",28457.42,1.6934637748833206E-5,3,2189.0323076923078]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.27","3PH CROSSARM DDE 10FT ARMS LRG COND 15KV",31270,1.8608367252056384E-5,3,3127]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.28","3PH CROSSARM SGL 10FT 15KV",26296,1.5648405029103765E-5,2,1460.8888888888889]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.29","3PH CROSSARM SGL 10FT LRG COND 15KV",55510,3.3033273622054681E-5,3,957.06896551724139]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.30","3PH CROSSARM DBL 10FT LRG COND 15KV",100591.5,5.9860683544458902E-5,5,2011.83]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.37","3PH 8FT FIBERGLASS CROSSARM DEADEND 15kV",7425,4.418520206156657E-6,1,1485]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.38","3PH 10FT FIBERGLASS CROSSARM DEADEND 15kV",8275,4.9243440681409207E-6,1,1655]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.39","3PH 8FT FIBERGLASS DOUBLE DEADEND 15kV",12040,7.1648462332829826E-6,1,3010]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.40","3PH 10FT FIBERGLASS DOUBLE DEADEND 15kV",39960,2.3779672382224917E-5,1,3330]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.41","3PH FIBERGLASS 8FT CROSSARM DOUBLE SUPPORT",1585,9.4321273087653885E-7,1,1585]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.43","3PH FIBERGLASS DOUBLE 10FT LARGE CONDUCTOR 15kV",50760,3.0206610863907328E-5,1,1880]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-25.46","3PH FIBERGLASS WITH NEUTRAL ON ARM",9675,5.7574657231738253E-6,1,1935]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.01","3PH CROSSARM 25KV",100861.25,6.0021208234776848E-5,5,1344.8166666666666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.02","3PH CROSSARM DBL LRG COND 25KV",330631.38,1.9675440179386667E-4,11,1419.0187982832617]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.03","3PH CROSSARM SGL LRG COND 25KV",246758.39,1.4684268447861075E-4,8,956.4278682170542]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.04","3PH CROSSARM SGL LRG COND ON ST POLE 25KV",24297.599999999999,1.4459183375233936E-5,1,759.3]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.07","3PH CROSSARM SGL LRG COND ON ST PL 25KV",164777.1,9.8056693045373217E-5,3,1168.631914893617]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.09","3PH CROSSARM SGL ON ST POLE 25KV",9150,5.445045102536486E-6,1,3050]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.11","3PH VERTICAL TANGENT SM ANGLE 25KV",5025,2.9903116546716769E-6,1,1675]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.12","3PH CROSSARM DBL SM ANGLE 25KV",35777.26,2.1290578616958967E-5,3,2385.1506666666669]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.13","3PH CROSSARM DBL SM ANGLE LRG COND 25KV",7798,4.6404876185332806E-6,1,1114]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.14","3PH CROSSARM DBL 10FT SM ANGLE 25KV",10350,6.1591493782789764E-6,1,2070]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.15","3PH XARM DBL 10FT LRG COND SM ANGLE 25KV",233911.5,1.3919766857944954E-4,11,1707.3832116788321]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.16","3PH XARM FBRGLS LRG COND MED ANGLE 25KV",29306.23,1.7439753457410694E-5,4,1831.639375]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.17","3PH VERTICAL MED ANGLE 25KV",1650,9.8189337914592375E-7,1,1650]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.18","3PH VERTICAL SM ANGLE SUSP BKT 25KV",23385.78,1.3916571241311005E-5,3,2598.42]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.20","3PH VERTICAL ANGLE LRG COND 25KV",52146.559999999998,3.1031734551051917E-5,9,1337.091282051282]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.21","3PH VERTICAL DDE ANGLE 25KV",21092.880000000001,1.2552096496436045E-5,6,2109.288]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.22","3PH VERTICAL DDE ANGLE LRG COND 25KV",21453.32,1.2766589617393229E-5,4,1340.8325]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.23","3PH VERTICAL DEAD END 25KV",13225,7.8700242055786926E-6,3,1889.2857142857142]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.24","3PH VERTICAL DEAD END LRG COND 25KV",46731.450000000004,2.7809273547205321E-5,9,1112.6535714285715]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.25","3PH CROSSARM DDE 25KV",63930,3.8043905290181152E-5,4,2905.909090909091]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.26","3PH CROSSARM DEAD END 25KV",134182.88,7.9850473616201206E-5,12,1242.434074074074]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.27","3PH CROSSARM DBL DDE 25KV",121724.25,7.2436506155456492E-5,11,2098.6939655172418]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.28","3PH DBL 10FT XARM DDE 25KV",34946.57,2.0796245882945192E-5,7,2496.1835714285712]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.29","3PH DDE UNBALANCED LOAD 25KV",16711,9.9444971266106254E-6,4,2785.1666666666665]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.30","3PH CROSSARM DBL-DDE-INV ARM 25KV",11572,6.8863455657434116E-6,2,2893]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.32","3PH CROSSARM 10FT FBRGLS X-ARM DDE 25KV",8935,5.3171014197992904E-6,2,2978.3333333333335]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.37","3PH XARM DBL 10FT LG COND NOX SM ANG 25KV",35832.899999999994,2.1323689251877556E-5,2,1023.7971428571427]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.38","3PH CROSSARM 10FT LRG COND 25KV",18000,1.071156413613735E-5,1,1000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-26.39","3PH XARM FBRGLS NEUT ON ARM BRCLESS 25KV",33008.25,1.9642777049814206E-5,1,1000.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-27.01","DBL CKT CROSSARM 15KV",111024.27,6.6069088265157221E-5,2,2846.7761538461541]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-27.06","DBL CKT DBL XARM SM ANG 15KV",18873.96,1.1231646280160605E-5,2,2696.2799999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-27.10","DBL CKT CROSSARM DDE 15KV",27259.5,1.6221771253835339E-5,2,4543.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-27.11","DBL CKT CROSSARM 3PH TAP 15KV",3204,1.9066584162324483E-6,1,3204]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-28.02","DBL CKT LRG COND CONST 25KV",37192.83,2.2132965774969631E-5,2,2860.9869230769232]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-30.01","SECONDARY ASSEMBLIES SMALL ANGLE",3052.37,1.8164253901234202E-6,6,82.496486486486489]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-30.02","SECONDARY ASSEMBLIES LRG ANGLE",5917.22,3.5212600854241475E-6,3,657.46888888888896]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-30.03","SECONDARY ASSEMBLIES DEADEND",120819.63,7.1898178647188021E-5,22,216.52263440860216]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-30.04","SECONDARY ASSEMBLIES MISC",51112.959999999999,3.0416652734879051E-5,13,157.27064615384617]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-30.06","SECONDARY CONDUCTOR 6 AL DUPLEX",29137.940000000002,1.7339606283606775E-5,15,2.9175868629217985]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-30.07","SECONDARY CONDUCTOR 4 AL DUPLEX",2531,1.5061649349202019E-6,2,2.8279329608938548]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-30.08","SECONDARY CONDUCTOR 2 AL DUPLEX",2615.15,1.5562414972566439E-6,1,2.71]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-30.12","SECONDARY CONDUCTOR 4 AL TRIPLEX",7107.1900000000005,4.2293956395952233E-6,5,2.331755249343832]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-30.13","SECONDARY CONDUCTOR 2 AL TRIPLEX",24906.39,1.4821466326924996E-5,7,5.1555350859035389]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-30.14","SECONDARY CONDUCTOR 1/0 AL TRIPLEX",21479.899999999998,1.2782407027100925E-5,10,4.9664508670520231]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-30.15","SECONDARY CONDUCTOR 2/0 AL TRIPLEX",376.65,2.2413947954867405E-7,1,8.3699999999999992]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-30.22","SECONDARY CONDUCTOR 1/0 AL QPLEX",4034.63,2.4009554450324355E-6,3,8.5479449152542379]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-30.24","SECONDARY CONDUCTOR 3/0 AL QPLEX",1621,9.6463585914881353E-7,2,7.0478260869565217]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-30.25","SECONDARY CONDUCTOR 4/0 AL QPLEX",2138.4,1.2725338193731172E-6,1,11.88]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-30.42","SECONDARY CONDUCTOR___ SGL COND (SEE PLANS)",31701.300000000003,1.8865028230496167E-5,1,12.55]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-31.02","SERVICE ASSEMBLY-POLE TYPE",114404.92,6.8080868781647926E-5,24,148.19290155440413]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-31.03","SERVICE ASSEMBLY-MAST TYPE",3581,2.1310061761948806E-6,2,298.41666666666669]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-31.04","SERVICE CONDUCTOR 6 AL DUPLEX",16014.720000000001,9.530150022348975E-6,8,2.5347768281101613]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-31.05","SERVICE CONDUCTOR 4 AL DUPLEX",10047.540000000001,5.9791593955780818E-6,1,3.0200000000000005]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-31.10","SERVICE CONDUCTOR 4 AL TRIPLEX",383.25,2.2806705306525775E-7,1,5.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-31.11","SERVICE CONDUCTOR 2 AL TRIPLEX",50886.839050000002,3.0282091120520759E-5,13,5.423680225998937]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-31.12","SERVICE CONDUCTOR 1/0 AL TRIPLEX",64241.558219999999,3.8229309504385089E-5,9,4.9301343252506626]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-31.13","SERVICE CONDUCTOR 2/0 AL TRIPLEX",2357.7600000000002,1.4030720809788445E-6,3,8.1866666666666674]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-31.16","SERVICE CONDUCTOR__ AL TRIPLEX (SEE PLANS)",4369.4800000000005,2.6002202923094131E-6,1,3.49]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-31.20","SERVICE CONDUCTOR 1/0 AL QPLEX",15013.91,8.9345811055107731E-6,6,11.04776306107432]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-31.21","SERVICE CONDUCTOR 2/0 AL QPLEX",753.12000000000012,4.4817184345598678E-7,1,10.46]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-31.33","SERVICE CONDUCTOR 336.4MCM AL SGL COND",505.5,3.0081642615652393E-7,1,10.11]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.01","DOWN GUY - THROUGH BOLT TYPE",485910.42,2.8915892379152426E-4,26,303.69401249999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.02","DOWN GUY - THROUGH BOLT TYPE HEAVY DUTY",282242.08999999997,1.6795856938624722E-4,14,384.002843537415]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.03","DOWN GUY - THROUGH BOLT ST PL",33286.199999999997,1.9808181452683056E-5,2,326.33529411764704]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.04","DOWN GUY - WRAP TYPE",6500.95,3.8686301594901165E-6,1,282.64999999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.06","DOWN GUY - INSULATED",116087.34,6.9082054877976824E-5,6,403.08104166666664]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.07","OH GUY - THROUGH BOLT TYPE",122662.83,7.2995042814728476E-5,28,506.87119834710745]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.08","OH GUY - THROUGH BOLT TYPE HEAVY DUTY",17555.54,1.0447071814140262E-5,5,585.18466666666666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.12","OH GUY - CROSSARM DEADEND HEAVY DUTY",954,5.6771289921527954E-7,1,954]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.17","DOWN GUY - FOUR GUYS LG COND",2201.8000000000002,1.3102623286081789E-6,1,550.45000000000005]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.19","DN GUY HVY CONST - 1 PREFORM",120382.64,7.1638131624307422E-5,10,317.6322955145119]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.20","DN GUY HVY CONST-3 BOLT CLAMPS",33145,1.9724155182904026E-5,3,419.55696202531647]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.21","OH GUY HVY CONST -THROUGH BOLT TYPE",29770.799999999999,1.7716212976895435E-5,9,465.16874999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.23","GUY GUARD",43077.24,2.5634701059321183E-5,21,33.034693251533746]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.24","GUY (INSULATOR-PORCELAIN-JOHNNY BALL TYPE)",40545.58,2.4128143367049325E-5,3,371.97779816513764]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.25","ANCHOR (POWER INSTALLED HELIX SCREW ANCHOR)",155945.54999999999,9.2801153365011874E-5,6,721.97013888888887]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.26","DOWN GUY LIGHT CONSTRUCTION - PREFORM",1575,9.372618619120181E-7,1,315]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.27","OVERHEAD GUY LIGHT CONSTRUCTION - PREFORM",1060,6.3079211023919949E-7,1,530]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.28","DOUBLE OVERHEAD GUY LIGHT CONSTRUCTION - PREFORM",10840.32,6.4509323853473576E-6,1,225.84]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.30","OVERHEAD GUY HEAVY CONSTRUCTION - PREFORM",9775,5.8169744128190329E-6,1,575]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-32.31","DOUBLE OVERHEAD GUY HEAVY CONSTRUCTION - PREFORM",1410,8.3907252399742577E-7,1,705]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-33.01","EXPANDING TYPE ANCHOR 6,000LB-8,000LB",40896.400000000001,2.4336911752062642E-5,2,397.05242718446601]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-33.03","SCREW TYPE ANCHOR 6,000LB-8,000LB",50736.45,3.0192596567495878E-5,4,349.9065517241379]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-33.04","SCREW TYPE ANCHOR 10,000LB-12,000LB",173804.08000000002,1.0342853055790817E-4,17,496.58308571428574]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-33.10","LOG TYPE ANCHOR 10IN-12IN DIA",23704.42,1.4106189729996495E-5,1,640.66]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-33.14","3/4IN TWIN EYE",44940,2.6743205126556252E-5,1,535]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-33.15","1IN TRIPLE EYE",20195.25,1.2017928645573768E-5,2,469.65697674418607]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-33.16","ROCK ANCHOR TRIPLE EYE",3285,1.9548604548450662E-6,3,657]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-33.18","ROCK ANCHOR GUY BOLT TYPE",254978.01,1.5173407263442614E-4,3,597.13819672131149]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-33.19","ROCK ANCHOR TRIPLE EYE 53IN EXPANDING",8304,4.9416015881380305E-6,3,922.66666666666663]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-33.20","ANCHOR TRIPLE EYE POWER INSTALLED",293324.02,1.7455328071664639E-4,11,757.94320413436697]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-33.21","ANCHOR TWIN EYE POWER INSTALLED",266322.83999999997,1.5848523230990253E-4,10,688.17271317829454]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-33.22","SWAMP ANCHOR 10IN",6135,3.6508581097334802E-6,1,2045]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-33.25","SCREW TYPE ANCHOR 15,000LB",1920,1.1425668411879839E-6,1,480]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-33.26","SCREW TYPE ANCHOR 28,000LB",7205,4.2876010889372004E-6,1,655]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-33.31","SCREW TYPE ANCHOR 23,000LB (F1-5D-P)",26335,1.5671613418065396E-5,2,849.51612903225805]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-33.32","SCREW TYPE ANCHOR 36,000LB (F1-6T-P)",54916.7,3.2680208566389662E-5,3,742.11756756756756]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-36.01","SWITCH-900A-UNDERSLUNG",80606.740000000005,4.7968014739719338E-5,3,2303.0497142857139]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-36.02","TRANSFER CAPACITOR BANK",23520.800000000003,1.3996919874069968E-5,4,3360.1142857142854]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-36.03","TRANSFER PCR SWITCH",49320,2.9349685733016339E-5,1,2740]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-36.04","TRANSFER SERVICE",17325.489999999998,1.0310172073611459E-5,8,188.32054347826084]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-36.05","TRANSFER SECONDARY",5331.5599999999995,3.1727414936480249E-6,4,161.56242424242421]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-36.06","TRANSFER LIGHT",28475.190000000002,1.6945212442983162E-5,9,355.93987500000003]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-36.08","TRANSFER SECONDARY/SERVICE ASSEMBLY",192.24,1.143995049739469E-7,1,96.12]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-36.10","TRANSFER - LIGHT ASSEMBLY",1470.69,8.7518834774310219E-7,1,163.41]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-36.11","TRANSFER EXISTING 1PH TRANSFORMER/RECLOSER",11446.76,6.8118168828317539E-6,1,880.52]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-36.12","TRANSFER EXISTING 3PH TRANSFORMER/RECLOSER",4427.92,2.634997170538072E-6,1,4427.92]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-36.13","TRANSFER STREET LIGHT",11687.8,6.9552566283525621E-6,2,365.24374999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-36.14","TRANSFER CONDUCTOR",42118.34,2.5064072234313287E-5,7,176.22736401673637]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.01","OH COND 4 7/1 ACSR SWANATE",93967.939999999988,5.5919089780594788E-5,9,1.823381003201707]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.02","OH COND 2 7/1 ACSR SPARATE",335297.06,1.9953088682490519E-4,16,2.7950039595541956]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.03","OH COND 1/0 6/1 ACSR RAVEN",300843,1.790277271893316E-4,26,3.0871523858388916]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.05","OH COND 3/0 6/1 ACSR PIGEON",768599.83000000007,4.5738368744829247E-4,19,3.3667106012422581]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.06","OH COND 4/0 6/1 ACSR PENGUIN",67168.52,3.9971106106079131E-5,5,3.9383476986221053]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.09","OH COND 336.4 18/1 ACSR MERLIN",1058443.6299999999,6.2986593484616832E-4,14,3.0981800113571829]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.10","OH COND 336.4 26/7 ACSR LINNET",14182.2,8.4396413828626192E-6,4,4.4236431690580167]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.13","OH COND 397.5 26/7 ACSR IBIS",124553.8,7.4120334283312459E-5,3,6.4097262247838618]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.15","OH COND 477 18/1 ACSR PELICAN",2308.08,1.3735081639631052E-6,1,3.26]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.18","OH COND 556.5 18/1 ACSR OSPREY",88926.459999999992,5.2918971093869587E-5,2,4.8973708558211255]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.24","OH COND 795 26/7 ACSR DRAKE",2372341.0099999998,1.4117490489668808E-3,4,6.2614409537559279]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.35","OH COND 2 7 AAC IRIS",3862.2,2.2983446114772038E-6,1,2.46]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.36","OH COND 1/0 7 AAC POPPY",3550.14,2.1126417945703696E-6,1,3.63]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.38","OH COND 3/0 7 AAC PHLOX",5560.68,3.3090878033631244E-6,2,3.2981494661921711]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.39","OH COND 4/0 7 AAC OXLIP",119865.80999999998,7.1330572863614086E-5,6,2.7869288537549406]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.42","OH COND 336.4 19 AAC TULIP",272978.48,1.6244591646140481E-4,9,3.6233836841965545]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.43","OH COND 397.5 19 AAC CANNA",12282.89,7.3093868895622275E-6,1,3.73]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.46","OH COND 556.5 19 AAC DAHLIA",137690.70000000001,8.1937931333313731E-5,2,3.4521925535915763]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.49","OH COND 795 37 AAC ARBUTUS",3048992.6999999997,1.8144156031480324E-3,18,5.343897356263013]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.73","OH PRI COND _____ _____ ____ ________ (1033 37 AAC BLUEBELL)",92680.38,5.5152879696198966E-5,10,3.5200873561472141]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.74","OH PRI COND _____ _____ ____ ________ (SEE PLANS)",3581.7,2.1314227370223971E-6,2,2.4054398925453322]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-40.76","OH STATIC COND _____ _____ ___________ (SEE PLANS)",210608.58000000002,1.2533040623837857E-4,6,2.9327769732078206]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-41.01","UG PRI COND 2 AL 15KV",1389.3,8.2675422524086773E-7,1,8.42]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-41.03","UG PRI COND 1/0 AL 15KV",49755.58,2.9608893683372936E-5,5,15.860879821485494]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-41.05","UG PRI COND 3/0 AL 15KV",7474.0499999999993,4.4477092184276305E-6,1,9.77]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-41.06","UG PRI COND 4/0 AL 15KV",288953.10000000003,1.719522034992061E-4,3,61.768512184694323]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-41.12","UG PRI COND 1 AL 25KV",6870.45,4.0885147677291588E-6,2,11.508291457286433]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-41.13","UG PRI COND 1/0 AL 25KV",4003.9199999999996,2.3826803264423918E-6,1,16.079999999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-41.30","UG PRI COND 500MCM CU 15KV",61272,3.6462164319411536E-5,1,102.12]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-41.43","UG PRI COND ____ __ __ ____ ________ (2 1/0 AL CD)",17420.32,1.036660416400201E-5,2,33.629961389961387]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-41.45","UG SEC COND 2 AL TPLX",1037.55,6.1743240941385039E-7,2,6.4846874999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-41.46","UG SEC COND 1/0 AL TPLX",4980.93,2.9640861751450341E-6,2,11.371986301369864]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-41.47","UG SEC COND 2/0 AL TPLX",4644.5,2.7638810905716623E-6,2,8.2642348754448403]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-41.49","UG SEC COND 4/0 AL TPLX",15829.98,9.4202136690984171E-6,4,12.553513084853291]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-41.55","UG SEC COND 1/0 AL QPLX",3199,1.9036829817501879E-6,2,8.5306666666666668]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-41.62","UG SEC COND TPLX ____ __ __ (500 CU)",6681.6,3.9761326073341843E-6,1,27.84]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-41.63","UG SEC COND QDLX ____ __ __ (1/0AL)",1594,9.4856851294460757E-7,1,7.97]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-41.64","UG SEC COND SGL COND ____ __ __ (SEE PLANS)",126342.9,7.5185004249754865E-5,3,1.6972447608812467]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-42.04","2IN DIA GALVINIZED METAL PIPE",58561.16,3.48489789570334E-5,3,18.842072072072071]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-42.08","2IN DIA PVC PIPE",198321.44,1.1801849022950641E-4,7,9.6044089302145377]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-42.09","3IN DIA PVC PIPE",12998.079999999998,7.7349870870357854E-6,2,7.3936746302616596]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-42.10","4IN DIA PVC PIPE",14085,8.3817989365274765E-6,2,22.0078125]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-42.11","6IN DIA PVC PIPE",3170.4,1.8866634965116587E-6,2,17.137297297297298]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-42.12","CONDUIT - POLE MTD - 2IN SCH 80 PVC",47035.54,2.7990233521547431E-5,8,25.772898630136986]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-42.13","CONDUIT - POLE MTD - 3IN SCH 80 PVC",43572.049999999996,2.5929156006554631E-5,4,49.345469988674964]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-42.14","CONDUIT - POLE MTD - 4IN SCH 80 PVC",41865.279999999999,2.4913479544297125E-5,3,50.258439375750299]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-42.15","CONDUIT - POLE MTD - 6IN SCH 80 PVC",6712,3.9942232489863278E-6,1,67.12]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-42.16","1 DUCT @ 36IN-48IN DEPTH",59755.960000000006,3.555998878091434E-5,4,51.469388458225673]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-42.17","2 DUCT BANK @ 36IN-48IN DEPTH",58288,3.4686425020398548E-5,2,191.10819672131149]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-42.18","3 DUCT BANK @ 36IN-48IN DEPTH",217113.75,1.2920154766457169E-4,1,236.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.01","LOADBREAK ELBOW 200A 15KV",12775.2,7.6023541195545486E-6,2,425.84000000000003]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.05","LOADBREAK JUNCTION 3 PT 200A 15KV",10962,6.5233425589076461E-6,1,913.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.08","ELBOW ARRESTER 200A 15KV",4515,2.6868173374811185E-6,1,451.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.10","SPLICE 200A 15KV",1370.54,8.1559039506342685E-7,1,685.27]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.14","SPLICE 600A 15KV",5925,3.5258898614785443E-6,1,1975]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.21","LOADBREAK JUNCTION 3 PT 200A 25KV",14325.95,8.5251851242276036E-6,1,2865.19]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.27","OUTDOOR TERMINATOR URD 25KV",16497.48,9.8174341724801788E-6,4,1031.0925]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.33","UG FAULT INDICATOR",4630.5,2.7555498740213334E-6,1,514.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.34","UG GROUND ROD ASSEMBLY",1811.25,1.0778511411988209E-6,1,362.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.45","FIBERGLASS VAULT-TRANS PAD-SMALL",1181.9100000000001,7.0333915378567202E-7,1,1181.9100000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.46","SECONDARY PULLBOX LARGE",139957.22999999998,8.3286713636729234E-5,10,760.63711956521729]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.47","PRIMARY PULLBOX",57027.28,3.393618706830349E-5,9,3564.2049999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.48","SEC PULLBOX SMALL (REPLACE ONLY)",5850,3.4812583442446389E-6,2,1170]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.50","SECONDARY RISER W/ 2IN CONDUIT",52034.43,3.0965007457352748E-5,7,1269.1324390243904]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.51","SECONDARY RISER W/ 3IN CONDUIT",20655,1.229151984621761E-5,2,1475.3571428571429]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.52","SECONDARY RISER W/ 4IN CONDUIT",12834.5,7.6376427725141559E-6,2,1604.3125]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.53","1PH PRIMARY RISER W/ 3IN CONDUIT",13084.5,7.786414496627176E-6,3,3271.125]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.58","3PH PRIMARY RISER W/ 6IN CONDUIT",48705,2.8983707291698314E-5,4,4058.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.59","SECONDARY RISER (SEE PLANS)",11603.44,6.9050550977678653E-6,4,773.5626666666667]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-43.60","PRIMARY RISER (THREE PHASE SINGLE CONDUCTOR)",83040.19,4.9416128947890637E-5,7,5190.0118750000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-46.01","1PH TRANSFORMER",366630.57999999996,2.1817705399662418E-4,29,914.29072319201987]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-46.02","1PH TRANSFORMER CONV W/POLE MTD FUSE & LA",90804.86,5.4036782320165167E-5,8,1179.283896103896]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-46.03","1PH TRANSFORMER CONV W/XARM MTD FUSE & LA",67878.02,4.0393320259111878E-5,12,905.04026666666675]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-47.02","2PH XFMR BNK POLE MTD W/ FUSE/ARRESTERS",32929.599999999999,1.9595973465408249E-5,6,2533.0461538461536]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-49.01","3PH XFMR BNK POLE MTD NO FUSE/ARRESTERS",41805.050000000003,2.4877637460523819E-5,5,8361.01]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-49.02","3PH XFMR BNK POLE MTD W/ FUSE/ARRESTERS",190368.4,1.1328574033854719E-4,14,5439.0971428571429]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-49.05","3PH XFMR BNK MISC",10620,6.3198228403210364E-6,1,3540]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-49.10","RECTIFIER AND POLE RECONNECT",1085.8,6.46145352167663E-7,1,1085.8]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-50.01","1PH PAD MTD TRANSFORMER RADIAL FEED",9298.19,5.53323102972172E-6,2,4649.0950000000003]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-52.02","5KVA 1PH OH XFORMER 7.2KV 120/240",5515.37,3.2821244160848807E-6,2,2757.6849999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-52.03","10KVA 1PH OH XFORMER 7.2KV 120/240",28595,1.7016509804047086E-5,2,2859.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-52.04","15KVA 1PH OH XFORMER 7.2KV 120/240",16342.210000000001,9.7250350300680653E-6,5,1634.221]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-52.06","25KVA 1PH OH XFORMER 7.2KV 120/240",11034,6.5661888154521958E-6,2,919.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-52.09","37.5KVA 1PH OH XFORMER 7.2KV 120/240",3647.76,2.1707341774020213E-6,1,911.94]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-52.11","50KVA 1PH OH XFORMER 7.2KV 120/240",4132.72,2.4593275187054196E-6,1,1033.18]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-52.16","75KKVA 1PH OH XFORMER 7.2KV 120/240",1096.44,6.5247707674591316E-7,1,1096.44]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-54.01","1.5KVA 1PH OH  XFORMER 14 .4KV 120/240",13865.35,8.2510880997217786E-6,2,1066.5653846153846]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-54.03","10KVA 1PH OH XFORMER 14.4KV 120/240",894.85,5.3251350929013935E-7,1,894.85]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-54.04","15KVA 1PH OH XFORMER 14.4KV 120/240",36266.100000000006,2.1581480895420601E-5,2,1066.6500000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-54.06","25KVA 1PH OH XFORMER 14.4KV 120/240",30699.599999999999,1.8268929686320121E-5,2,1096.4142857142856]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-54.09","37.5KVA 1PH OH XFORMER 14.4KV 120/240",2140,1.2734859584074405E-6,1,2140]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-54.17","100KVA 1PH OH XFORMER 14.4KV 120/240",894.85,5.3251350929013935E-7,1,894.85]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-58.02","HOOK STICK SWITCH VERTICAL, SINGLE 15KV",5645,3.3592655304719632E-6,1,5645]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-58.03","CUTOUT KNIFE SWITCH, SNGL LOADBREAK 15KV",29475.79,1.7540656391573109E-5,3,2267.3684615384618]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-58.04","HOOK STICK SWITH LINE TENSION, SNGL 15KV",4415,2.6273086478359109E-6,1,4415]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-58.05","GOLB SWITCH 15KV",98404.790000000008,5.8559401077118192E-5,3,10933.865555555556]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-58.06","GOAB SWITCH 15KV",197655.65000000002,1.1762228732471759E-4,9,11626.802941176471]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-58.09","3PH FUSE CUTOUT BRKT MT 15kV",9175,5.4599222749477885E-6,2,1529.1666666666667]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-59.02","HOOK STICK SWITCH VERTICAL - SINGLE 25KV",84534,5.0305075704679708E-5,3,4226.7]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-59.03","CUTOUT KNIFE SWITCH-SNGL LOADBREAK 25KV",52675,3.1346202270613048E-5,4,1120.7446808510638]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-59.04","HOOK STICK SWITH LINE TENSION-SNGL 25KV",9410.619999999999,5.6001366494898258E-6,2,2352.6549999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-59.05","GOLB SWITCH 25KV",12255,7.292789916020179E-6,2,6127.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-60.01","1PH FUSE CUTOUT XARM MOUNT 15KV",40282,2.3971290362882485E-5,6,479.54761904761904]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-60.02","1PH FUSE CUTOUT BRKT MOUNT 15KV",45200.15,2.6898016982668258E-5,9,393.04478260869564]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-60.03","1PH SECTIONALIZER OR RECLOSER 15KV",3618,2.1530243913636071E-6,1,723.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-60.04","2 - 1PH SECTIONALIZERS OR RECLOSERS 15KV",47519.86,2.82784460072371E-5,3,7919.9766666666665]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-60.09","3PH SECTIONALIZER OR RECL 15KV",30288.57,1.8024331119271425E-5,2,6057.7139999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-61.01","1PH FUSE CUTOUT XARM MOUNT 25KV",136800.08000000002,8.1407935041595585E-5,13,465.30639455782318]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-61.02","1PH FUSE CUTOUT BRKT MOUNT 25KV",3856.25,2.2948038444433142E-6,3,550.89285714285711]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-61.03","1PH SECTIONALIZERS OR RECLOSER 25KV",3385,2.0143691444902737E-6,2,1128.3333333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-61.05","2 - 1PH SECTIONALIZERS OR RECLOSERS 25KV",42142.27,2.5078312663745385E-5,4,8428.4539999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-61.09","3PH SECTIONALIZER OR RECL 25KV",11470,6.8256467023053E-6,1,11470]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-61.10","3PH SECTLR OR RECL W/ BYPASS SW 25KV",179137.49,1.0660237296231462E-4,8,10537.499411764706]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-61.11","3PH SECTLR OR RECL W/ BYP SW ELECTC 25KV",13036,7.7575527821492498E-6,1,13036]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-62.03","1PH HYDR RECL 50A CONT 1250A INT 15KV",34737.56,2.067186677071774E-5,3,2894.7966666666666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-62.08","1PH HYDR RECL 560A CONT 10000A INT 15KV",21665.86,1.2893069386365153E-5,3,7221.9533333333338]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-63.15","3PH ELECTR RECL 800A CONT 16000A INT 25KV",95882,5.7058121805617853E-5,2,31960.666666666668]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-63.16","3PH OVR-3SP ELECTRONIC RECLOSER 25KV",8330,4.957073847445785E-6,1,8330]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-63.17","3PH TYPE SDR ELECTRONIC RECLOSER 25KV",10100,6.0103776541659572E-6,1,10100]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-64.01","SEC MTG 1PH 120/240 VOLTS",17938.969999999998,1.0675245982846878E-5,7,1195.9313333333332]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-64.09","SEC MTG 3PH W/ TRANSFORMER CABINET",12251.49,7.2907011610136319E-6,1,4083.83]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-64.10","SEC MTG 3PH 120/240 VOLTS (4 WIRE ?)",47269.8,2.8129638577910295E-5,3,5252.2000000000007]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-64.11","SEC MTG 3PH 240 OR 480 VOLTS (3 W GRD ?)",1845,1.0979353239540785E-6,1,1845]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-64.14","PRI MTG 3PH CLUSTER MOUNT",259618.74999999997,1.5449571619826713E-4,4,19970.673076923078]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-65.03","LIGHTNING ARRESTER ARM MTD 9 KV",41201.78,2.4518639388501174E-5,8,292.21120567375885]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-65.05","LIGHTNING ARRESTER ARM MTD 18 KV",28265,1.6820131128217901E-5,4,448.65079365079367]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-65.06","LIGHTNING ARRESTER POLE MTD 18 KV",22075.39,1.3136775323069172E-5,10,272.53567901234567]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-65.07","LIGHTNING ARRESTOR 18KV INTERMEDIATE",14310,8.5156934882291924E-6,2,550.38461538461536]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-65.16","3PH CAPACITOR ASSEMBLY SWITCHED 15KV",4480,2.665989296105296E-6,1,4480]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-65.17","3PH CAPACITOR ASSEMBLY 25KV",107400.51000000001,6.3912636173270049E-5,4,13425.063750000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-68.01","POLE GROUND ROD TYPE",507922.99000000005,3.0225831575575836E-4,28,324.75894501278776]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-68.02","POLE GROUND PLATE TYPE",7563.45,4.5009099869704465E-6,5,222.45441176470587]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-68.03","POLE GROUND WRAP TYPE",4530.47,2.6960233317692323E-6,3,411.8609090909091]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-68.07","POLE GROUND FOR AIR BREAK SWITCH",701.18,4.1726303005426591E-7,1,701.18]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-68.08","POLE GROUND W/ PLTFM FOR AIR BREAK SWCH",7140,4.2489204406678157E-6,1,1785]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-68.10","MISCELLANEOUS ASSEMBLIES",500676.23000000004,2.9794586383802529E-4,26,625.84528749999993]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-68.11","DEAD END SHOE",45697.07,2.7193727563253224E-5,6,121.85885333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-68.12","LARGE BRACES",1211.42,7.2090016809997279E-7,5,242.28400000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-68.13","SGL PHASE MOUNTING BRACKET - FIBERGLASS",37594.259999999995,2.237185150781238E-5,12,278.47599999999994]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-68.14","3 MOUNTING BRACKET - FIBERGLASS",980,5.8318515852303346E-7,1,245]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-68.25","TWO OR THREE PHASE CAPACITOR ASSY",46670.91,2.7773246986494113E-5,2,23335.455000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.02","CROSSARM - 10FT",1350,8.0336731021030124E-7,1,675]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.03","10FT DBL CROSSARM",12769.27,7.5988252542585876E-6,5,1418.8077777777778]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.04","FIBERGLASS CROSSARM ASSEMBLY",10580.26,6.2961740870560309E-6,5,1058.0260000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.06","HARDWARE FOR SGL PH CONV TRANS",55800,3.3205848822025788E-5,4,664.28571428571433]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.07","HARDWARE FOR SGL PH CONV TRANS DE",13050,7.7658839986995783E-6,2,932.14285714285711]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.08","GROUND-GROUND ROD",41917.920000000006,2.4944804918526366E-5,2,322.44553846153849]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.09","GND-ASSY GND ROD WITH ALUMINUM",31869.300000000003,1.8965002829100116E-5,1,259.10000000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.11","GROUND-GROUND ROD FOR ST POLE",69369.25,4.1280731691708102E-5,4,370.9585561497326]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.12","GROUND ASSEMBLY GROUND PLATE TYPE",450,2.6778910340343377E-7,1,450]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.18","GND ASSY GOLB ON ST POLE",5190,3.0885009925862691E-6,1,1730]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.21","1-SGL PHASE RECLOSER",35183.78,2.0937406445652586E-5,5,3518.3779999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.22","POLE TOP PIN",2208.4700000000003,1.3142315582075141E-6,7,84.941153846153853]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.23","PAIR OF 10IN OR THREE 6IN BELLS",1219.7799999999997,7.2587509455431189E-7,2,135.53111111111107]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.24","EPOXY DEAD END",31299.45,1.86258925611569E-5,1,1490.45]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.26","EXTENSION LINK - EPOXY -1FT",80,4.7606951716165998E-8,1,80]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.27","EXTENSION LINK - EPOXY -4FT",31530,1.8763089845133926E-5,5,179.14772727272728]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.28","EXTENSION LINK - EPOXY -6FT",50246.96,2.9901307482551553E-5,11,172.66996563573883]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.29","SADDLE PIN",117,6.9625166884892775E-8,1,117]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.30","POLE TOP PIN FOR ST POLE",1850,1.1009107584363388E-6,2,205.55555555555554]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.31","STICK PIN",5078.82,3.0223392314387275E-6,6,195.33923076923077]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.32","ARM PIN",25520.09,1.5186671155277635E-5,12,144.18129943502825]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-69.33","DEADEND ASSEMBLY",35192.589999999997,2.0942649161210328E-5,3,926.12078947368411]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-70.01","STREET LIGHT ON WOOD POLE",7573.1299999999992,4.5066704281281022E-6,6,582.54846153846142]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-70.04","STREET LIGHT W/ FRNG ANC BASE & MTL POLE",309194.03000000003,1.839973157142098E-4,4,2020.8760130718956]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-70.06","STREET LIGHT BASE, POWER INSTALLED",187156.88,1.1137460686885342E-4,3,1264.5735135135135]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-70.10","FLOOD LIGHT",62125.11,3.6969838901643767E-5,7,1129.5474545454545]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-70.11","STREET LIGHT - HPS  (400W)",38099.17,2.2672316832700001E-5,7,828.24282608695648]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-70.12","STREET LIGHT - HPS  (250W 15FT ARM)",40896.85,2.4337179541166044E-5,7,973.73452380952381]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-70.13","STREET LIGHT - HPS  (250W)",9025.8300000000017,5.3711531626040332E-6,5,1002.87]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-70.14","STREET LIGHT - HPS  (SEE PLANS)",2608.81,1.5524686463331378E-6,3,869.60333333333335]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-70.20","STREET LIGHT (STREET LIGHT 400W HP S)",469022.7,2.7910926290857267E-4,17,1138.4046116504855]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-70.21","STREET LIGHT (SEE PLANS)",7826.43,4.6574059389994131E-6,3,869.60333333333335]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-70.22","STREET LIGHT (METAL POLE MOUNTED)",83655,4.9781994322698332E-5,2,1032.7777777777778]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-70.23","STREET LIGHT (RENTAL LIGHT)",7790,4.6357269233616643E-6,2,973.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-71.15","DBL CKT SGL ARM LN POSTS 46KV MAX",101200,6.0222793920949992E-5,1,10120]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-71.20","TANGENT HOR LN POSTS 69KV MAX",122943.84,7.3162268183500474E-5,4,3615.9952941176471]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-71.21","SML ANGLE HOR LINE POSTS 69KV MAX",16585,9.8695161776576642E-6,2,5528.333333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-71.22","TANGENT LN POST/SUSP INS 69KV MAX",33026.520000000004,1.9653649287412386E-5,2,5504.420000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-71.29","MED VERT ANG 69KV MAX",4465,2.6570629926585147E-6,1,4465]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-71.31","LRG VERT ANG 69KV MAX",6955,4.138829364824182E-6,1,6955]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-71.33","DDE LRG VERT ANG 69KV MAX",198533.08000000002,1.1814443442027154E-4,4,8272.211666666668]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-71.50","DDE 2 POLE 69KV MAX",10945,6.5132260816679607E-6,1,10945]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-71.66","TANGENT W/ UPSWEPT ARMS 161KV MAX",621898.29,3.7008352330495254E-4,2,5866.9650000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-71.67","HORIZ POST TANGENT 161KV MAX",58070.400000000001,3.4556934111730579E-5,3,6452.2666666666664]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-71.68","HORIZ POST SM ANG 161KV MAX",83874.320000000007,4.9912508780828211E-5,3,6989.5266666666676]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-71.69","VERTICAL DDE 161KV MAX",474786.30000000005,2.8253910574496384E-4,4,13964.302941176473]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-71.70","INTERMEDIATE ANGLE SINGLE POLE 161KV ASSEMBLY",20692.02,1.2313549963124265E-5,2,5173.0050000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-71.71","LARGE ANGLE SINGLE POLE 161KV ASSEMBLY",11888.58,7.0747381754222098E-6,2,5944.29]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-72.06","GUY 3 BOLT CLAMP W/ THIMBLE CLEVIS",9790,5.8259007162658142E-6,1,445]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-72.07","GUY FACTORY FORMED WITH THIMBLE CLEVIS",56480,3.3610507911613198E-5,2,400.56737588652481]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-72.10","LIGHT DUTY GUYING PLATE - GUY ATTACHMENT",440,2.6183823443891301E-7,1,220]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-72.15","MEDIUM DUTY GUYING TEE",407759.28,2.4265220443473267E-4,3,738.69434782608698]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-72.17","MEDIUM DUTY POLE EYE PLATES",4875,2.9010486202038656E-6,1,125]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-73.02","INS STRING W/ CUSHIONED SUSP",25415.77,1.5124591690239754E-5,4,1411.9872222222223]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-73.03","LINE POST",63599.1,3.784699103614516E-5,4,211.99699999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-73.04","OHGW CUSHIONED SUSP & SUSP CLAMP",7840,4.6654812681842676E-6,1,1120]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-73.15","SWITCH GOAB 1W 1200A 69KV MAX",55515,3.3036249056536943E-5,1,18505]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-74.20","108-144 FIBER(INSTALLATION ONLY)",2820,1.6781450479948515E-6,1,705]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-74.25","FIBER SPLICE-12 FIBER RIBBON",49019.78,2.9171028744963497E-5,2,1361.6605555555554]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-74.26","FIBER OPTIC MAINTENANCE LOOP",5180,3.0825501236217484E-6,1,740]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-98.01","REMOVE WIRE",3518368.0599999991,2.0937347294015074E-3,38,1.8169963100964948]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-98.02","REMOVE POLES",1672394.64,9.952201359606852E-4,41,672.18434083601278]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-98.03","REMOVE FRAMING/ASSOCIATED APPARATUS",5247608.49,3.12278305010966E-3,40,384.55287190385462]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-98.04","REMOVE FIBER OPTIC CABLE",24963.3,1.4855332722202084E-5,2,1.7469069279216234]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-98.20","TREE AND BRUSH REMOVAL OFF ROW",351760.45,2.093280344850853E-4,14,25125.74642857143]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-99.01","RESERVED FOR TDOT USE ONLY",100000,5.9508689645207498E-5,1,100000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"790-99.02","RESERVED FOR TDOT USE ONLY",65123.280000000006,3.8754010581979488E-5,1,4.53]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-01.01","<2IN STEEL GAS MAIN",58677.5,3.4918211366566631E-5,3,52.390625]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-01.02","2IN STEEL GAS MAIN",1548067,9.2123438652987435E-4,18,45.166068563092637]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-01.03","3IN STEEL GAS MAIN",81600,4.8559090750489318E-5,1,408]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-01.04","4IN STEEL GAS MAIN",1207845.5999999999,7.1877308949729437E-4,8,73.58182150472129]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-01.05","6IN STEEL GAS MAIN",2809438.5,1.671860037737973E-3,12,65.2614114148993]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-01.06","8IN STEEL GAS MAIN",3681147.55,2.1906026709116594E-3,10,114.83848229605366]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-01.08","12IN STEEL GAS MAIN",3271460.25,1.9468031270388293E-3,4,181.37496534900481]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-01.09","__IN STEEL GAS MAIN (SEE PLANS)",18340,1.0913893680931055E-5,2,34.93333333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-01.20","8IN HIGH PRESSURE STEEL GAS MAIN",234600,1.396073859076568E-4,1,115]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-01.21","8IN PWRCRETE COATED HP STL GAS MN- OPEN CUT",5480,3.261076192557371E-6,1,137]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-01.22","8IN POWERCRETE CTD HP STL GAS MN-DIR  DRILL",482040,2.8685568756575821E-4,2,259.16129032258067]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-01.23","2IN POWERCRETE COATED STL GAS MAIN-OPEN CUT",21600,1.285387696336482E-5,1,72]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-01.26","4IN PWRCRETE CTD STL GAS MN-OPN CUT",2420,1.4401102894140216E-6,1,121]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-01.40","RELOCATE SERVICE",31905.690000000002,1.8986658041262005E-5,3,1100.1962068965518]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-02.01","<2IN MDPE GAS MAIN",526821.5,3.1350457141922681E-4,4,72.019343814080656]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-02.02","2IN MDPE GAS MAIN",482159.25,2.8692665167816012E-4,10,36.627108021877852]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-02.03","3IN MDPE GAS MAIN",12198.9,7.2594055411292174E-6,2,22.801682242990655]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-02.04","4IN MDPE GAS MAIN",1050836.0499999998,6.2533876367445735E-4,12,42.604340158118795]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-02.05","6IN MDPE GAS MAIN",5145768,3.0621791089824012E-3,9,63.649798998082751]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-02.06","8IN MDPE GAS MAIN",308967,1.8386221313610826E-4,2,71.886226151698466]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-02.30","<=2 IN PE TEMP. BY-PASS FOR TIE-IN",6300,3.7490474476480724E-6,1,525]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-03.01","<2IN HDPE GAS MAIN",24591,1.4633781870652976E-5,2,11.228767123287671]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-03.02","2IN HDPE GAS MAIN",830303.34,4.9410263771439199E-4,12,30.391776720351391]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-03.04","4IN HDPE GAS MAIN",932582.40000000002,5.5496756610182759E-4,9,42.502160240634403]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-03.05","6IN HDPE GAS MAIN",2385617.06,1.4196494523585237E-3,7,66.657829500684571]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-03.06","8IN HDPE GAS MAIN",690780.45,4.1107439412026777E-4,2,70.631947852760732]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-03.09","__IN HDPE GAS MAIN (SEE PLANS)",1900,1.1306651032589426E-6,1,19]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-03.10","__IN HDPE GAS MAIN (0.75\" HDPE GAS MAIN)",24650,1.4668891997543649E-5,1,17]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.01","HDD <2IN PE PIPE - UNCONSOLIDATED",59262.1,3.5266099166232515E-5,4,41.154236111111111]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.02","HDD 2IN PE PIPE - UNCONSOLIDATED",211994.6,1.2615520857859905E-4,8,47.351932097386644]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.04","HDD 4IN PE PIPE - UNCONSOLIDATED",81306.349999999991,4.8384343483346166E-5,7,39.622977582845998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.05","HDD 6IN PE PIPE - UNCONSOLIDATED",77017.05,4.5831837258394284E-5,7,57.604375467464472]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.06","HDD 8IN PE PIPE - UNCONSOLIDATED",28235,1.6802278521324337E-5,2,276.81372549019608]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.09","HDD __IN PE PIPE - UNCONSOLIDATED (SEE PLANS)",1380,8.2121991710386351E-7,1,46]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.10","HDD <2IN PE PIPE - ROCK",17270,1.0277150701727336E-5,1,157]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.11","HDD 2IN PE PIPE - ROCK",44937,2.6741419865866894E-5,4,148.7980132450331]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.13","HDD 4IN PE PIPE - ROCK",71431.199999999997,4.2507771117847457E-5,4,228.94615384615383]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.14","HDD 6IN PE PIPE - ROCK",468035.1,2.7852155508963653E-4,4,256.03670678336977]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.19","HDD <2IN STEEL PIPE - UNCONSOLIDATED",370280,2.2034877601827434E-4,2,128.12456747404843]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.20","HDD 2IN STEEL PIPE - UNCONSOLIDATED",178511,1.0622955697255636E-4,8,84.322626358053853]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.22","HDD 4IN STEEL PIPE - UNCONSOLIDATED",27490,1.635893878346754E-5,2,134.09756097560975]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.23","HDD 6IN STEEL PIPE - UNCONSOLIDATED",103470,6.1573641175896205E-5,4,106.67010309278351]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.24","HDD 8IN STEEL PIPE - UNCONSOLIDATED",21848,1.3001458513684934E-5,2,174.78399999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.25","HDD 12IN STEEL PIPE - UNCONSOLIDATED",53750,3.1985920684299029E-5,2,316.1764705882353]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.27","HDD __IN STEEL PIPE - UNCONSOLIDATED (SEE PLANS)",40276,2.3967719841503773E-5,2,58.969253294289899]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.29","HDD 2IN STEEL PIPE - ROCK",17100,1.0175985929330483E-5,1,136.80000000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.34","HDD 12IN STEEL PIPE - ROCK",125842.5,7.4887222766770243E-5,1,359.55]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.51","HDD 2IN POWERCRETE COATED STEEL GAS MN",24997.5,1.4875684694060745E-5,1,166.65]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-04.53","HDD 4IN POWERCRETE COATED STEEL GAS MN",50698.75,3.0170161791499639E-5,2,198.81862745098039]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-05.01","BORE/JACK 4IN - STEEL CASING PIPE - UNCON.",69785,4.1528139068908054E-5,2,168.15662650602408]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-05.02","BORE/JACK 6IN - STEEL CASING PIPE - UNCON.",129713.8,7.7190982669005166E-5,2,275.9868085106383]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-05.03","BORE/JACK 8IN - STEEL CASING PIPE - UNCON.",36215,2.1551071955011896E-5,2,134.12962962962962]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-05.04","BORE/JACK 12IN - STEEL CASING PIPE - UNCON.",65652,3.9068644925871631E-5,3,207.75949367088609]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-05.05","BORE/JACK 16IN - STEEL CASING PIPE - UNCON.",209090.25,1.2442686795088848E-4,1,572.85]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-05.07","BORE/JACK___IN - STEEL CASING PIPE - UNCON. (BORE/JACK 2IN - STEEL CASING PIPE - UNC ON.)",13600,8.0931817917482202E-6,1,170]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-05.11","BORE/JACK 12IN - STEEL CASING PIPE - UNCON.",146771.96,8.7342070162588093E-5,1,234.45999999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-05.14","BORE/JACK ___IN - STEEL CASING PIPE - UNCON. (BORE/JACK 10IN - STEEL CASING PIPE - UN CON.)",30400,1.8090641652143082E-5,1,380]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-05.20","BORE/JACK 10IN - STEEL CASING PIPE - ROCK",70400,4.189411751022608E-5,1,440]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-05.31","4IN STEEL CASING PIPE OPEN CUT",21736.199999999997,1.293492779866159E-5,1,362.26999999999992]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-05.52","6IN STEEL CASING OPEN CUT",112298.76,6.6827520563816421E-5,2,128.78298165137613]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-05.55","12IN STEEL CASING OPEN CUT",42230.09,2.5130573194991805E-5,1,144.13]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-05.73","12IN STEEL CASING",39292.5,2.3382451878843156E-5,1,157.16999999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-05.76","6IN STEEL CASING",31101,1.8507797566555986E-5,1,88.86]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.01","CONNECT TO 1-1/4IN EX. PE MAIN",5400,3.213469240841205E-6,1,1350]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.02","CONNECT TO 2IN EX. PE MAIN",114049.08000000002,6.7869113060414421E-5,19,1267.2119999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.03","CONNECT TO 4IN EX. PE MAIN",120748.78,7.1856016740574379E-5,16,2118.3996491228072]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.04","CONNECT TO 6IN EX. PE MAIN",40335.32,2.400302039620131E-5,8,2372.665882352941]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.05","CONNECT TO 8IN EX. PE MAIN",44976,2.6764628254828525E-5,2,3748]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.09","CONNECT TO __IN EX. PE MAIN (SEE PLANS)",24416.98,1.4530224848932386E-5,5,1356.4988888888888]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.10","CONNECT TO 2IN EX. STL MAIN",142499.06,8.479932336273802E-5,7,4749.9686666666666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.11","CONNECT TO 4IN EX. STL MAIN",57103.33,3.3981443426778666E-5,6,5710.3330000000005]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.12","CONNECT TO 6IN EX. STL MAIN",45719.11,2.7206843278451025E-5,7,5079.9011111111113]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.13","CONNECT TO 8IN EX. STL MAIN",323039.16000000003,1.9223637115688532E-4,4,6095.0784905660385]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.14","CONNECT TO 12IN EX. STL MAIN",82500,4.9094668957296188E-5,1,27500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.17","CONNECT TO __IN EX. STL MAIN (SEE PLANS)",20850,1.2407561791025763E-5,2,521.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.21","CONNECT TO __IN EX. CI/DI MAIN (SEE PLANS)",7500,4.4631517233905629E-6,1,2500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.24","CONNECT TO 4IN EX. PE MAIN",3000,1.7852606893562249E-6,2,1500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.25","CONNECT TO 6IN EX. PE MAIN",7700,4.5821691026809771E-6,2,2566.6666666666665]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.31","CONNECT TO 2IN EX. STL MAIN W/ STOPPLE",310941.70999999996,1.8503733718140111E-4,17,5015.1888709677414]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.32","CONNECT TO 4IN EX. STL MAIN W/ STOPPLE",357166.9,2.1254534203640863E-4,9,15528.995652173913]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.33","CONNECT TO 6IN EX. STL MAIN W/ STOPPLE",385425.48,2.2936165270675128E-4,11,16757.62956521739]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.34","CONNECT TO 8IN EX. STL MAIN W/ STOPPLE",123931.84,7.375021403719513E-5,3,24786.367999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.35","CONNECT TO 12IN EX. STL MAIN W/ STOPPLE",383196,2.2803491837284934E-4,3,54742.285714285717]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.38","CONNECT TO __IN EX. STL MAIN W/ STOPPLE (SEE PLANS)",36582,2.1769468846009807E-5,1,36582]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.39","CONNECT TO 4IN EX. CI/DI MAIN W/ STOPPLE",33600,1.9994919720789719E-5,1,8400]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.47","CONNECT TO 3/4IN EX. PE MAIN",12325,7.3344459987718247E-6,1,725]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.48","CONNECT TO 3/4IN EX. STEEL MAIN",6090,3.6240791993931366E-6,1,1015]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-06.51","2IN PE HOT TAP CONNECTION",3000,1.7852606893562249E-6,1,1500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.01","2IN PE GAS VALVE ASSEMBLY",42911.729999999996,2.5536208227089397E-5,19,523.31378048780493]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.02","4IN PE GAS VALVE ASSEMBLY",58050.62,3.4545163292918753E-5,17,983.90881355932208]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.03","6IN PE GAS VALVE ASSEMBLY",120305.29000000001,7.1592101652866858E-5,14,1822.8074242424243]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.04","8IN PE GAS VALVE ASSEMBLY",102529.60000000001,6.1014021458472669E-5,4,3015.5764705882357]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.08","__IN PE GAS VALVE ASSEMBLY (SEE PLANS)",4245,2.5261438754390585E-6,2,1061.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.09","2IN STEEL GAS VALVE ASSEMBLY",333958.41000000003,1.9873427375096962E-4,15,4574.7727397260278]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.10","4IN STEEL GAS VALVE ASSEMBLY",122455.49,7.2871657497618105E-5,8,3601.6320588235294]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.11","6IN STEEL GAS VALVE ASSEMBLY",130018.92,7.7372555582850617E-5,9,4815.5155555555557]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.12","8IN STEEL GAS VALVE ASSEMBLY",284901.07999999996,1.6954089949304432E-4,7,13566.718095238093]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.13","12IN STEEL GAS VALVE ASSEMBLY",54126,3.2209673357365014E-5,1,27063]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.16","__IN STEEL GAS VALVE ASSEMBLY (SEE PLANS)",4038,2.4029608878734788E-6,2,2019]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.21","EXCESS FLOW VALVE (EFV)",29627,1.7630639481185625E-5,1,559]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.25","1IN PE GAS VALVE ASSEMBLY",1180,7.0220253781344853E-7,1,590]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.30","4WAY PE VALVE SYSTEM (4-6IN)",5565,3.3116585787557972E-6,1,5565]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.31","4WAY PE VALVE SYSTEM (2 - 6 IN, 2 - 4 IN)",5145,3.061722082245926E-6,1,5145]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.32","4WAY PE VALVE SYSTEM (2-6IN,1-4IN,1-2IN)",9240,5.4986029232171732E-6,1,4620]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.33","3WAY PE VALVE SYSTEM (3 - 6 IN)",15120,8.9977138743553748E-6,1,5040]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.34","3WAY PE VALVE SYSTEM (3 - 4 IN)",4305,2.5618490892261831E-6,1,4305]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-07.35","2WAY PE VALVE SYSTEM (2 - 6 IN)",2782.5,1.6558292893778986E-6,1,2782.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.01","1/2IN SERVICE ASSEMBLY",28911.8,1.72050333328431E-5,2,1927.4533333333334]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.02","3/4IN SERVICE ASSEMBLY",409996.13,2.4398332455906148E-4,19,1184.9599132947976]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.03","1IN SERVICE ASSEMBLY",67024.899999999994,3.9885639726010679E-5,9,1340.4979999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.04","1-1/4IN SERVICE ASSEMBLY",85960,5.1153669619020365E-5,2,999.53488372093022]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.05","2IN SERVICE ASSEMBLY",78873,4.693628878386451E-5,8,2629.1]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.06","1/2IN PE SERVICE PIPE",34780.089999999997,2.0697175816423847E-5,2,21.888036500943986]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.07","3/4IN PE SERVICE PIPE",181149.8,1.0779987227491409E-4,14,24.0634697130712]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.08","1IN PE SERVICE PIPE",96576.27,5.7471272785217638E-5,5,22.094776938915579]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.09","1-1/4IN PE SERVICE PIPE",13756.99,8.1866044836222312E-6,2,24.698366247755835]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.10","2IN PE SERVICE PIPE",56028.43,3.3341784521782334E-5,5,45.184217741935484]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.12","3/4IN STEEL SERVICE PIPE",421693.5,2.5094427616901307E-4,9,61.651096491228067]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.13","1IN STEEL SERVICE PIPE",38337.5,2.2814143892731425E-5,3,37.402439024390247]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.15","2IN STEEL SERVICE PIPE",1700,1.0116477239685275E-6,1,85]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.17","HDD 3/4IN PE SERVICE PIPE",44983.75,2.6769240178276028E-5,6,45.164407630522085]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.18","HDD 1IN PE SERVICE PIPE",6375,3.7936789648819783E-6,2,16.776315789473685]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.20","HDD 2IN PE SERVICE PIPE",2500,1.4877172411301874E-6,1,25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.22","HDD 3/4IN STEEL SERVICE PIPE",190017,1.1307662680313393E-4,5,52.709292649098472]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.23","HDD 1IN STEEL SERVICE PIPE",44770,2.6642040354159396E-5,2,106.5952380952381]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.40","RECONNECT SERVICE ASSEMBLY",2750,1.6364889652432063E-6,1,550]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.50","1-1/2IN STEEL SERVICE PIPE",600,3.5705213787124502E-7,1,60]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-08.51","1-1/2IN STEEL SERVICE ASSEMBLY",4580,2.7254979857505036E-6,1,4580]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-09.02","3-WIRE CATHODIC PROTECTION STATION",33462.14,1.9912881041244838E-5,11,367.7158241758242]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-09.03","17LB MAGNESIUM ANODES",17375,1.0339634825854802E-5,7,284.8360655737705]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-09.04","REGULATOR STATION",187130.12,1.1135868234350437E-4,5,31188.353333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-09.05","RESTORE ASPHALT",117510,6.9928661202083332E-5,10,60.015321756894792]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-09.06","RESTORE CONCRETE",80505,4.7907470598874296E-5,9,110.4320987654321]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-09.07","RESTORE GRAVEL",20780,1.2365905708274119E-5,9,32.36760124610592]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-09.08","REMOVE REGULATOR STATION",49510,2.9462752243342233E-5,5,7072.8571428571431]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-09.15","2IN PE TIE-IN (2X2IN TO EXIST)",6510,3.8740156959030087E-6,1,1627.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-09.16","4 IN PE TIE-IN (4X4IN OR 4X2IN NEW TO EXIST)",10395,6.1859282886193196E-6,1,1732.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-09.17","6 IN PE TIE-IN (6X4IN OR 6X2IN NEW TO EXIST)",35280,2.0994665706829206E-5,1,2940]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-09.18","2X2 IN PE BRANCH TIE-IN W/ 2 IN VALVE",3958.5,2.3556514796055388E-6,1,1979.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-09.19","4X2 IN PE BRANCH TIE-IN W/ 2 IN VALVE",4063.5,2.4181356037330069E-6,1,2031.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-09.20","6X2 IN PE BRANCH TIE-IN W/ 2 IN VALVE",6142.5,3.6553212614568708E-6,1,2047.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-09.21","Cathodic Protection Junction Box",500,2.9754344822603748E-7,1,500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-09.31","9LB MAGNESIUM ANODE",2672,1.5900721873199443E-6,1,167]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-10.01","RETIRE IN PLACE 3/4IN SERV CUT & PLUG",104600,6.2246089368887047E-5,11,337.41935483870969]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-10.02","RETIRE IN PLACE 1IN SERV CUT & PLUG",6615,3.9364998200304764E-6,4,472.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-10.03","RET. IN PLACE 1-1/4IN SERV CUT & PLUG",8570,5.0998947025942831E-6,3,329.61538461538464]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-10.04","RETIRE IN PLACE 2IN SERV CUT & PLUG",79367.459999999992,4.7230535450684198E-5,15,853.41354838709674]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-10.05","RETIRE IN PLACE 4IN SERV CUT & PLUG",43470.15,2.586851665180617E-5,12,1207.5041666666666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-10.06","RETIRE IN PLACE 6IN SERV CUT & PLUG",58943.16,3.5076302151478094E-5,9,1786.1563636363637]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-10.07","RETIRE IN PLACE 8IN SERV CUT & PLUG",28850.3,1.7168435488711297E-5,4,801.39722222222224]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-10.08","RETIRE IN PLACE 12IN SERV CUT & PLUG",9492,5.6485648211230957E-6,3,1898.4]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-10.10","RETIRE GAS MAIN",90520,5.3867265866841832E-5,10,9052]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-10.11","RETIRE IN PLACE 3IN SERV CUT & PLUG",1000,5.9508689645207496E-7,1,1000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-99.01","ADDER FOR FULL CLEAN STONE BACKFILL",11812.5,7.0294639643401357E-6,1,26.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"791-99.02","CLEAN UP RESTORATION & CLOSEOUT",1050,6.2484124127467873E-7,1,1050]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.01","POLE 30FT CLASS 4 WOOD",13492.2,8.0290314243106859E-6,3,1226.5636363636365]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.03","POLE 30FT CLASS 6 WOOD",2202,1.3103813459874691E-6,1,2202]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.04","POLE 30FT CLASS 7 WOOD",22368,1.3310903699840013E-5,1,932]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.05","POLE 35FT CLASS 2 WOOD",4556.51,2.7115193945528445E-6,2,911.30200000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.06","POLE 35FT CLASS 3 WOOD",2000,1.1901737929041499E-6,1,1000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.07","POLE 35FT CLASS 4 WOOD",92993.97,5.5339492996057368E-5,7,1223.6048684210527]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.08","POLE 35FT CLASS 5 WOOD",53031.99,3.1558642341777477E-5,12,1233.3020930232558]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.12","POLE 40FT CLASS 4 WOOD",44247.32,2.6331000335121825E-5,7,1843.6383333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.14","POLE 45FT CLASS 1 WOOD",22917.3,1.3637784932061138E-5,2,1145.865]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.16","POLE 45FT CLASS 2 WOOD",1800,1.0711564136137351E-6,1,1800]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.17","POLE 45FT CLASS 3 WOOD",18040.45,1.0735635401098837E-5,4,1804.0450000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.18","POLE 45FT CLASS 4 WOOD",5961,3.5473129897508192E-6,2,1490.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.19","POLE 50FT CLASS 1 WOOD",51853.08,3.0857088448681165E-5,2,1152.2906666666668]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.24","POLE 55FT CLASS 2 WOOD",2322,1.3817917735617181E-6,1,2322]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.33","POLE (4IN X 6IN SAWN WOOD)",43435.919999999991,2.5848146827340607E-5,4,1173.9437837837836]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.34","POLE (INSTALL POLE 55FT CLASS H1 WOOD)",18932.52,1.1266494568816839E-5,1,1577.71]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.35","POLE (INSTALL POLE 60FT CLASS H1 WOOD)",5311.5,3.1608040505051962E-6,1,1770.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.36","POLE (INSTALL POLE 65FT CLASS H1 WOOD)",2758.63,1.6416245651595877E-6,1,2758.63]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.39","ANCHOR 5/8IN",3166.7999999999997,1.884521183684431E-6,1,243.59999999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.40","ANCHOR 3/4IN",63800.56,3.7966877242304394E-5,8,335.79242105263154]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.41","ANCHOR 1IN",229695.43,1.3668874056792484E-4,22,468.76618367346936]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-01.42","ANCHOR 1 1/4IN",79942.7,4.7572853236999295E-5,7,444.12611111111107]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-02.07","GUY WIRE 6.6M OR 1/4IN",1769.4,1.0529467545823016E-6,1,176.94]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-02.08","GUY WIRE 10M OR 3/8IN",30209.16,1.7977075268824167E-5,7,121.81112903225807]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-02.90","GUY WIRE (SEE PLANS)",137531.66,8.1843288713301986E-5,4,250.51304189435336]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-02.92","OVERHEAD GUY WIRE (3/8IN)",4773.6499999999996,2.8407365632484474E-6,3,183.60192307692307]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-02.93","OVERHEAD GUY WIRE (SEE PLANS)",1621.8400000000001,9.6513573214183344E-7,2,202.73000000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-03.01","25 PAIR GROUP AERIAL SPLICE",94358.76,5.6151661641466196E-5,4,4.180715994683208]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-03.02","6M STRAND",2358.3000000000002,1.4033934279029286E-6,2,1.9409876543209879]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-03.03","10M STRAND",234435.50999999998,1.3950950006405937E-4,6,1.9950939526492264]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-03.04","16M STRAND",21694.420000000002,1.2910065068127827E-5,1,3.41]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-03.08","1200 PAIR OR GREATER CABLE",196782.95,1.1710295499018386E-4,1,49.63]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-03.11","25 PAIR CABLE",2599.35,1.5468391242927011E-6,2,3.1431076178960096]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-03.12","50 PAIR CABLE",18390.599999999999,1.094400507789153E-5,3,4.0597350993377477]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-03.13","75  PAIR CABLE",1813.5,1.0791900867158379E-6,1,7.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-03.14","100 PAIR CABLE",159990.47999999998,9.5208238205077761E-5,3,6.9548982785602496]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-03.16","200 PAIRCABLE",261633.39999999997,1.5569460801420431E-4,2,11.676934749620635]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-03.17","300 PAIR CABLE",3987.5,2.372908999602649E-6,1,13.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-03.18","400 PAIR CABLE",25641,1.5258623111927655E-5,1,25.9]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-03.19","600 PAIR CABLE",440368.46,2.6205750015677976E-4,2,19.417454914237844]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-03.20","900 PAIR CABLE",11679.4,6.9502578984223642E-6,1,25.39]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-03.21","1200 PAIR CABLE",106558.91,6.3411811041215978E-5,1,49.31]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-03.41","AERIAL CABLE (DESCRIPTION)",26335.15,1.5671702681099864E-5,5,3.1933005941554504]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-04.01","RELASH/DELASH CABLE",6544.18,3.89435576602374E-6,7,1.5704775617950562]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-04.02","2 PAIR AERIAL DROP",18004.850000000002,1.0714450307585145E-5,5,2.1609277484397502]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-04.03","6 PAIR AERIAL DROP",3436.5499999999997,2.0450458740023781E-6,1,2.21]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-04.06","READY ACCESS CLOSURE",46076.18,2.7419330956567168E-5,6,341.30503703703704]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-04.07","AERIAL SPLICE CLOSURE",33710.660000000003,2.0060772036751109E-5,7,766.15136363636373]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-04.08","TRANSFER AERIAL CABLE",13501.45,8.0345359781028677E-6,5,24.459148550724638]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-04.09","TRANSFER AERIAL DROP",2428.52,1.4451804297717931E-6,3,43.366428571428571]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-04.12","UNDERGROUND SPLICE CLOSURE",41440.200000000004,2.4660520006353283E-5,2,881.70638297872347]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-04.21","3 PAIR AERIAL DROP",1014.9999999999999,6.0401319989885609E-7,1,2.0299999999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-04.25","HOT SPLICE EXISTING CABLES",105520.65000000001,6.2793956120105648E-5,6,5.1644797376664062]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-07.01","12 FIBER (MATERIAL ONLY)",29970.22,1.7834885205785909E-5,3,1.5187868038311458]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-07.02","24 FIBER(MATERIAL ONLY)",6961.37,4.142620068354581E-6,4,0.88308638843080056]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-07.03","36 FIBER(MATERIAL ONLY)",3285.2,1.9549794722243566E-6,1,1.91]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-07.04","48 FIBER(MATERIAL ONLY)",58719.78,3.4943371640548624E-5,6,2.4383265509509178]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-07.05","96 FIBER(MATERIAL ONLY)",55153.86,3.2821339374752242E-5,8,1.8518570996877413]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-07.07","144 FIBER(MATERIAL ONLY)",95674.260000000009,5.6934498453748905E-5,5,3.5046800249093373]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-07.16","12-96 FIBER(INSTALLATION ONLY)",217024.27,1.2914829928907715E-4,8,2.36443363439267]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-07.17","108-144 FIBER(INSTALLATION ONLY)",121324.37,7.2198542807303231E-5,4,3.9261008996181475]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-07.22","FIBER SPLICE-12 FIBER RIBBON",97958.3,5.8293700728721303E-5,5,77.071833202202995]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-07.23","FIBER OPTIC MAINTENANCE LOOP",27339.42,1.6269330598599789E-5,7,220.47919354838709]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-07.25","SINGLE FIBER OPTIC CABLE SPLICE",32971.9,1.9621145641128173E-5,5,43.845611702127663]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-07.26","120 FIBER(MATERIAL ONLY)",22788.300000000003,1.3561018722418822E-5,1,3.7000000000000006]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-07.31","SINGLE FIBER AERIAL DROP",558,3.3205848822025783E-7,1,1.86]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-07.41","HOT SPLICE EXISTING FIBER CABLES",95708.64,5.6954957541248925E-5,5,51.79038961038961]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-07.42","HOT SPLICE EXISTING RIBBON FIBERS",7000,4.1656082751645252E-6,1,875]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-07.51","72 FIBER (MATERIAL ONLY)",34649.4,2.0619403909926529E-5,1,2.37]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-09.01","25 PAIR BURIED CABLE",1904.4999999999998,1.1333429942929767E-6,2,4.7612499999999995]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-09.02","50 PAIR BURIED CABLE",24920.899999999998,1.4830101037792514E-5,3,5.4651096491228062]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-09.04","100 PAIR BURIED CABLE",69899.599999999991,4.1596336027241459E-5,3,18.01536082474227]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-09.07","300 PAIR BURIED CABLE",147391.5,8.7710750298416006E-5,2,17.198541423570596]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-09.08","400 PAIR BURIED CABLE",85747.5,5.10272136535243E-5,2,25.07236842105263]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-10.02","BURIED CABLE @ 36IN DEPTH",553538.03,3.2940322834089559E-4,8,9.9485627246585189]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-10.20","EXPOSE EXISTING CABLE/CONDUIT (ALL DEPTHS)",107549.85,6.4001506450386199E-5,3,33.092261538461543]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-11.01","25 GROUP BURIED SPLICE",79577.679999999993,4.7355634618056358E-5,2,28.339629629629627]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-11.06","8IN PEDESTAL",3859.54,2.2967616803326414E-6,3,428.83777777777777]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-11.07","8IN PEDESTAL W/TERMINAL",10051.52,5.9815278414259609E-6,3,502.57600000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-11.08","10IN PEDESTAL",6714.55,3.9957407205722801E-6,3,516.50384615384621]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-11.10","12IN PEDESTAL",14152.400000000001,8.421907793348347E-6,6,643.29090909090905]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-11.11","12IN PEDESTAL W/TERMINAL",13806.12,8.2158411028449217E-6,2,373.13837837837838]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-11.13","BURIED RISER GUARD",9420.41,5.6059625502060917E-6,6,129.04671232876711]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-11.14","2 PAIR BURIED DROP",16846.22,1.0024964776748875E-5,3,3.9957827324478181]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-11.15","5 PAIR BURIED DROP",1405,8.3609708951516539E-7,1,2.81]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-11.17","COMPOSITE HANDHOLE 5FTX3FTX3FT",86484.78,5.1465959320540489E-5,1,2543.67]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-11.19","MARKER POST",16691.2,9.9327144060608751E-6,6,142.65982905982906]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-11.20","HANDHOLE 30INX48IN",94541.16,5.626020549137906E-5,9,2555.1664864864861]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-11.21","HANDHOLE (36IN X 24IN X 24IN)",20192.099999999999,1.2016054121849942E-5,3,2243.5666666666666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-11.25","CONCRETE HANDHOLE 4FT X 4FT X 4FT",22691.4,1.3503354802152616E-5,2,7563.8]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-11.31","REMOVE HANDHOLE (30IN x 42 IN)",1813.71,1.0793150549640931E-6,3,453.42750000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-11.32","ENTER EXISTING HANDHOLE",1300,7.7361296538769747E-7,1,1300]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-12.01","DIG SPLICE PIT 80 C.F.",27952.37,1.6634089111780086E-5,10,1118.0947999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-12.02","REARRANGEMENT EXISTING CABLE",22153.129999999997,1.3183037378399355E-5,6,217.18754901960781]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-12.03","100 PAIR UG CABLE",14959.199999999999,8.9020239014058794E-6,1,5.52]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-12.05","200 PAIR UG CABLE",26356.799999999999,1.5684586312408049E-5,1,9.1199999999999992]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-12.06","300 PAIR UG CABLE",11154,6.6375992430264449E-6,1,13.2]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-12.07","400 PAIR UG CABLE",28962.75,1.7235353010217334E-5,1,16.79]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-12.08","600 PAIR UG CABLE",105943.67999999999,6.3045695729911769E-5,2,24.799550561797751]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-12.09","900 PAIR UG CABLE",70971.600000000006,4.2234269180238093E-5,1,36.21]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-12.12","1800 PAIR UG CABLE",20295.199999999997,1.2077407580874151E-5,1,88.239999999999981]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-12.15","3000 PAIR UG CABLE",23462.300000000003,1.3962107290627521E-5,1,102.01000000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-12.17","UG CABLE (50 PAIR)",21022.52,1.2510226182401676E-5,2,3.2893944609607262]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.01","2IN CASING",24000,1.4282085514849799E-5,1,15]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.02","4IN CASING",79220.56,4.7143117185595394E-5,1,43.48]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.06","25 PAIR GROUP UG SPLICE",97940.44,5.8283072476750666E-5,1,113.62]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.07","4IN SCHEDULE 40 PVC",511815.76,3.0457485217366009E-4,16,5.9499623343408512]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.09","2IN SCHEDULE 40 PVC",715.19999999999993,4.2560614834252399E-7,1,17.88]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.10","3IN SCHEDULE 40 PVC",788.8,4.6940454392139675E-7,1,19.72]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.12","1 DUCT FORMATION @ 36IN DEPTH",185325.62,1.102848480388566E-4,11,23.128119306127541]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.16","2 DUCT FORMATION @ 24IN DEPTH",14416.92,8.5793201791978489E-6,1,19.07]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.17","2 DUCT FORMATION @ 36IN DEPTH",579304.19999999995,3.4473633847965213E-4,11,30.758426250398212]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.22","3 DUCT FORMATION @ 36IN DEPTH",76863.149999999994,4.5740253385030303E-5,7,43.181544943820221]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.27","4 DUCT FORMATION @ 36IN DEPTH",353262.38,2.1022181334747356E-4,7,57.422363459037712]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.32","6 DUCT FORMATION @ 36IN DEPTH",719342.07999999996,4.280710458745802E-4,5,51.410954831332184]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.37","9 DUCT FORMATION @ 36IN DEPTH",122301.2,7.2779841540364509E-5,3,76.967400881057273]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.42","12 DUCT FORMATION @ 36IN DEPTH",87500,5.2070103439556563E-5,1,175]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.51","___DUCT FORMATION @ ___IN DEPTH (SEE PLANS)",62884.049999999996,3.7421474150837103E-5,2,29.44009831460674]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.52","___DUCT FORMATION @ ___IN DEPTH (1.25\")",41674.5,2.4799948866192E-5,1,24.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.63","6IN SPLIT STEEL (BSP)",3150,1.8745237238240362E-6,1,105]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-13.67","14IN SPLIT STEEL (BSP)",213150,1.2684277197875978E-4,1,105]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-14.01","SAND ENCASEMENT PER DUCT",107796.15000000001,6.414807635298235E-5,1,5.49]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-14.02","CONCRETE ENCASEMENT PER DUCT",301271.83999999997,1.7928292425400608E-4,5,5.3116564114317946]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-14.03","MH PRECAST 6-FT W X 12-FT L X 7-FT H",730833.47,4.3490942148560063E-4,6,24361.115666666665]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-14.05","MH PRECAST 4-FT W X 8-FT L X 6-FT H",53984.24,3.2125313838923967E-5,3,13496.06]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-14.06","CAST IN PLACE MANHOLE",92198.400000000009,5.4866059713846999E-5,1,96.04]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-14.09","BRIDGE CONDUIT HANGER SYSTEM",420733.5,2.5037299274841912E-4,2,210366.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-14.10","4IN CORE DRILL INTO MANHOLE",16043.02,9.5469909815185684E-6,5,445.63944444444445]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-14.12","1 1/4IN INNERDUCT",137417.41,8.1775300035382331E-5,6,2.5710486828319112]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-14.13","1 1/2IN INNERDUCT",23650.199999999997,1.4073924118470863E-5,2,5.0729729729729724]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-14.14","MULTI DUCT",45689.2,2.7189044229378142E-5,3,4.724839710444674]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-14.18","LOWER CONDUIT PER 12ININCREMENTS",27920,1.6614826148941935E-5,1,40]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-14.19","4IN SCH 80 ORANGE FLEXPIPE",6459.1,3.8437257728735976E-6,4,5.3960735171261494]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-14.20","PLACE MANHOLE OVER EXISTING CABLE",94536.35,5.6257343123407122E-5,3,15756.058333333334]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-14.21","ROD DUCTS",53263.899999999994,3.1696648943933674E-5,7,1.592962885426324]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-14.22","UNDERGROUND CABLE",82419.100000000006,4.9046526427373221E-5,4,4.99509696969697]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-14.26","UNDERGROUND TO OVERHEAD RISER",8540.76,5.082494361742024E-6,3,854.07600000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-15.01","TRANSFER CABLE ATTACHMENT",4747.3899999999994,2.8251095813476162E-6,4,115.78999999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-15.02","TRANSFER DROP ATTACHMENT",2362.81,1.4060772698059273E-6,3,98.450416666666669]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-15.04","TRANSFER DOWN GUY ATTACHMENT",102.18,6.0805979079473024E-8,1,102.18]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-15.07","PAD MOUNTED CARRIER",8230.66,4.8979579151522358E-6,1,8230.66]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-16.01","MH(RETIRE/REMOVE/GRAVEL BACKFILL)",142242.17000000001,8.464645148990845E-5,6,7112.1084999999994]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-16.02","DIRECTIONAL BORE 2IN/FLEX SLEEVE",68745.149999999994,4.0909337959632363E-5,5,21.022981651376146]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-16.03","DIRECTIONAL BORE 3IN/FLEX SLEEVE",203992.8,1.2139344225056884E-4,3,94.441111111111113]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-16.04","DIRECTIONAL BORE 4IN/FLEX SLEEVE",184856.82,1.1000587130179988E-4,9,29.600771817453964]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-16.05","STRAIGHT BORE/SLEEVE 2IN",16458.75,9.7943864569805895E-6,1,15.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-16.06","STRAIGHT BORE/SLEEVE 4IN",44890,2.6713450781733647E-5,2,76.084745762711862]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-16.14","BORE/JACK 12IN CASING - ROCK",92400,5.4986029232171729E-5,1,420]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-16.21","ADJUST MANHOLE LID",31383.71,1.867603458305195E-5,3,2241.6935714285714]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-16.22","GROUND BED",13721.2,8.1653063235982117E-6,5,653.39047619047619]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-97.01","RESTORE ASPHALT",15148.95,9.0149416400076624E-6,3,72.831490384615392]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-97.03","RESTORE GRAVEL",126,7.4980948952961456E-8,1,21]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-98.01","REMOVE  AERIAL CABLE AND WIRE",234007.02000000002,1.3925451127979864E-4,9,1.2166257844141395]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-98.02","REMOVE CROSSCONNECT CABINET",548.71,3.2653013095221808E-7,1,548.71]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-98.03","REMOVE CARRIER CABINET",863.73,5.139944050725507E-7,2,431.86500000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-98.04","REMOVE POLES ALL SIZES",91156.15,5.4245830396019816E-5,27,136.05395522388059]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-98.05","RETIRE BURIED FACILITIES IN PLACE",17316.900000000001,1.0305060277170938E-5,4,1.6843594981032974]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-98.06","REMOVE PEDESTALS",9496.3499999999985,5.6511534491226616E-6,13,102.11129032258063]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-98.07","REMOVE UNDERGROUND TO OVERHEAD RISER",2200,1.309191172194565E-6,2,275]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-98.08","REMOVE ANCHOR (ANY SIZE)",22648.149999999998,1.347761729388106E-5,14,90.592600000000004]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"793-98.21","TRIM UTILITY RIGHT-OF-WAY",133237.4,7.9287830857343688E-5,4,4.1234649665758853]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.01","4IN DIP RESTRAINED JOINT WATER LINE",8049.28,4.7900210538737584E-6,3,85.630638297872338]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.02","4IN DIP SLIP JOINT WATER LINE",24905,1.4820639156138928E-5,4,63.858974358974358]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.03","6IN DIP RESTRAINED JOINT WATER LINE",656077.55000000005,3.904231530613811E-4,19,41.43211556678245]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.04","6IN DIP SLIP JOINT WATER LINE",1878503.6500000001,1.117872907052395E-3,24,34.158338182347165]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.05","8IN DIP RESTRAINED JOINT WATER LINE",1227800.3,7.3064786998992663E-4,22,63.984590129761848]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.06","8IN DIP SLIP JOINT WATER LINE",2155268.2300000004,1.2825718820124571E-3,22,56.571689590004738]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.07","10IN DIP RESTRAINED JOINT WATER LINE",52005.5,3.0947791593438389E-5,4,50.836265884652981]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.08","10IN DIP SLIP JOINT WATER LINE",472513,2.811862947032593E-4,8,42.264132379248657]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.09","12IN DIP RESTRAINED JOINT WATER LINE",1624918.3,9.6696758813518172E-4,14,64.404213238208499]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.10","12IN DIP SLIP JOINT WATER LINE",6816672.7000000002,4.0565126011725865E-3,24,64.949765132964288]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.13","16IN DIP RESTRAINED JOINT WATER LINE",964075.02,5.7370841159877213E-4,4,89.035373106760247]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.14","16IN DIP SLIP JOINT WATER LINE",671945,3.9986566463648952E-4,6,99.917472118959111]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.15","18IN DIP RESTRAINED JOINT WATER LINE",132615.5,7.8917746316440156E-5,3,213.89596774193549]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.16","18IN DIP SLIP JOINT WATER LINE",244025,1.452160799067176E-4,2,111.93807339449542]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.17","20IN DIP RESTRAINED JOINT WATER LINE",1013171.89,6.0292531559258313E-4,3,229.12073496155585]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.18","20IN DIP SLIP JOINT WATER LINE",773982.00000000012,4.6058654628976996E-4,1,78.180000000000007]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.19","24IN DIP RESTRAINED JOINT WATER LINE",1694143.97,1.0081628772502973E-3,4,196.149585504226]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.20","24IN DIP SLIP JOINT WATER LINE",1247708.8,7.4249515746794279E-4,3,113.92520087655224]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.21","30IN DIP RESTRAINED JOINT WATER LINE",135135,8.0417067752051161E-5,1,231]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.22","30IN DIP SLIP JOINT WATER LINE",633150,3.7677926848863128E-4,1,210]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.23","36IN DIP RESTRAINED JOINT WATER LINE",87975,5.2352769715371298E-5,1,293.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.24","36IN DIP SLIP JOINT WATER LINE",1766800,1.0513995286515262E-3,1,315.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.26","2IN DIP SLIP JOINT WATER LINE",3654.8999999999996,2.1749830978426889E-6,1,23.58]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.31","3IN DIP RESTRAINED JOINT WATER LINE",800,4.7606951716165999E-7,1,40]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.90","MASTER METER VAULT W/BYPASS",50000,2.9754344822603749E-5,1,50000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-01.99","12IN DIP SLIP JOINT W/GEOTECH FABRIC STONE",333135,1.9824427324956201E-4,1,99]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-02.01","2IN HDPE WATER LINE",45194.8,2.689483326777224E-5,3,12.457221609702316]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-02.04","6IN HDPE WATER LINE",39606,2.3569011620880884E-5,1,24.15]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-02.05","8IN HDPE WATER LINE",27657,1.6458318295175038E-5,1,31.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-02.07","12IN HDPE WATER LINE",67450,4.0138611165692457E-5,2,116.29310344827586]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-02.08","14IN HDPE WATER LINE",360982.65,2.1481604486154566E-4,1,61.95]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-03.01","1-1/2IN PVC WATER LINE",8221.5,4.8925069191807343E-6,1,9.4499999999999993]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-03.02","2IN PVC WATER LINE",217509.2,1.2943687477777368E-4,20,20.208975192790117]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-03.03","3IN PVC WATER LINE",62040,3.6919191055886732E-5,1,20.68]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-03.04","4IN PVC WATER LINE",278834,1.6593045968531789E-4,6,34.129008567931457]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-03.05","6IN PVC WATER LINE",3034547.75,1.8058196026831271E-3,17,32.845691540026841]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-03.06","8IN PVC WATER LINE",2220716.5699999998,1.3215193315409971E-3,16,40.089478463371492]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-03.07","10IN PVC WATER LINE",1006907.52,5.9919747109105569E-4,7,50.461437305803344]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-03.08","12IN PVC WATER LINE",1475720.6400000001,8.7818201568786998E-4,11,61.807699782208083]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-03.11","18IN PVC WATER LINE",4800,2.8564171029699602E-6,1,100]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-03.34","6IN C900 PVC WATER LINE",169735,1.0100707436929295E-4,1,20.45]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-03.35","8IN C900 PVC WATER LINE",1206,7.1767479712120245E-7,1,24.12]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-03.36","10IN C900 PVC WATER LINE",14157,8.4246451930720263E-6,1,25.74]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-03.37","12IN C900 PVC WATER LINE",22085,1.3142494108144076E-5,1,31.55]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.01","HDD 2IN HDPE CARRIER PIPE-UNCON",161774,9.6269587586637979E-5,7,30.808227004380118]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.02","HDD 4IN HDPE CASING PIPE-UNCON",73248.040000000008,4.3588948794797452E-5,4,27.310976882923196]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.03","HDD 6IN HDPE CASING PIPE-UNCON",30252.95,1.8003134124019803E-5,2,41.160476190476189]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.04","HDD 8IN HDPE CASING PIPE-UNCON",6240,3.7133422338609479E-6,1,39]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.06","HDD 12IN HDPE CASING PIPE-UNCON",62750,3.7341702752367706E-5,2,96.538461538461533]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.08","HDD 16IN HDPE CASING PIPE-UNCON",59062.5,3.5147319821700679E-5,1,131.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.14","HDD __IN HDPE CASING PIPE-UNCON (SEE PLANS)",103919.7,6.1841251753230695E-5,5,47.23622727272727]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.15","HDD 2IN HDPE CARRIER PIPE-ROCK",26715,1.5897746438717182E-5,2,97.145454545454541]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.16","HDD 4IN HDPE CASING PIPE-ROCK",37125,2.2092601030783283E-5,1,165]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.18","HDD 8IN HDPE CASING PIPE-ROCK",128287.5,7.6342210228595568E-5,1,233.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.22","HDD 16IN HDPE CASING PIPE-ROCK",590584.5,3.5144909719770051E-4,1,437.47]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.28","HDD __IN HDPE CASING PIPE-ROCK (3/4 IN)",218500,1.3002648687477839E-4,3,101.62790697674419]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.60","BORE/JACK 6IN STEEL CASING PIPE-UNCON.",59972.5,3.5688848897472066E-5,2,226.31132075471697]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.61","BORE/JACK 8IN STEEL CASING PIPE-UNCON.",20306.400000000001,1.2084072554114417E-5,1,169.22]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.63","BORE/JACK 12IN STEEL CASING PIPE-UNCON.",1187364.9000000001,7.0658529329712847E-4,14,215.02442955450925]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.64","BORE/JACK 14IN STEEL CASING PIPE-UNCON.",83545.039999999994,4.9716558567564458E-5,3,225.18878706199459]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.65","BORE/JACK 16IN STEEL CASING PIPE-UNCON.",1027594.0599999999,6.1150775997798729E-4,16,231.64879621280431]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.66","BORE/JACK 18IN STEEL CASING PIPE-UNCON.",343427.9,2.0436944316605359E-4,9,286.42860717264386]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.67","BORE/JACK 20IN STEEL CASING PIPE-UNCON.",620397,3.6919012529817796E-4,7,314.76255707762556]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.68","BORE/JACK 24IN STEEL CASING PIPE-UNCON.",277601.74,1.6519715790629585E-4,6,331.66277180406212]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.69","BORE/JACK 30IN STEEL CASING PIPE-UNCON.",452124.29000000004,2.6905324054669796E-4,6,488.78301621621625]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.70","BORE/JACK 36IN STEEL CASING PIPE-UNCON.",230044.79999999996,1.3689664607693827E-4,2,1045.6581818181817]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.71","BORE/JACK __IN STEEL CASING PIPE-UNCON (SEE PLANS)",176229,1.0487156867485272E-4,3,417.60426540284362]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.74","BORE/JACK 6IN STEEL CASING PIPE-ROCK.",181436.79999999999,1.0797066221419583E-4,4,237.17228758169932]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.75","BORE/JACK 8IN STEEL CASING PIPE-ROCK.",83778.5,4.9855487554410164E-5,3,214.81666666666666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.76","BORE/JACK 10IN STEEL CASING PIPE-ROCK.",389670.8,2.3188798700999721E-4,3,374.68346153846153]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.77","BORE/JACK 12IN STEEL CASING PIPE-ROCK.",1487569.95,8.8523338480086839E-4,7,384.88226390685639]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.78","BORE/JACK 14IN STEEL CASING PIPE-ROCK.",155204,9.2359866676947847E-5,2,363.47540983606558]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.79","BORE/JACK 16IN STEEL CASING PIPE-ROCK.",1254507.2,7.4654079622478247E-4,8,538.41510729613731]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.80","BORE/JACK 18IN STEEL CASING PIPE-ROCK.",216669,1.2893688276737465E-4,5,358.13057851239671]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.81","BORE/JACK 20IN STEEL CASING PIPE-ROCK.",241930,1.4396937285865051E-4,4,417.12068965517244]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.82","BORE/JACK 24IN STEEL CASING PIPE-ROCK.",762027.01,4.5347228839355433E-4,5,555.41327259475224]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.83","BORE/JACK 30IN STEEL CASING PIPE-ROCK.",209475,1.2465582763429841E-4,1,735]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.91","2IN PVC CASING PIPE OPEN CUT",12667,7.5379657173584344E-6,2,22.823423423423424]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-05.92","4IN PVC CASING PIPE OPEN CUT",2430,1.4460611583785423E-6,1,27]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.01","CONNECT TO 2IN WATER LINE",53700.509999999995,3.1956469833793612E-5,21,1013.2171698113208]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.02","CONNECT TO 3IN WATER LINE",7172.41,4.2682072069818274E-6,4,1793.1025]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.03","CONNECT TO 4IN WATER LINE",77657.180000000008,4.6212770233420153E-5,13,2505.0703225806456]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.04","CONNECT TO 6IN WATER LINE",418588.01,2.4909623976295014E-4,30,1468.7298596491228]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.05","CONNECT TO 8IN WATER LINE",367634.79,2.1877464620891033E-4,23,2625.9627857142855]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.06","CONNECT TO 10IN WATER LINE",271529.64,1.6158373076234921E-4,12,3526.3589610389613]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.07","CONNECT TO 12IN WATER LINE",194590.1,1.1579801868929892E-4,20,3355.001724137931]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.08","CONNECT TO 14IN WATER LINE",9450,5.6235711714721086E-6,1,3150]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.09","CONNECT TO 16IN WATER LINE",31440,1.8709532024453237E-5,4,2858.181818181818]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.10","CONNECT TO 18IN WATER LINE",16295,9.6969409776865627E-6,2,4073.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.11","CONNECT TO 20IN WATER LINE",116945.16,6.959253231949135E-5,3,6496.9533333333338]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.12","CONNECT TO 24IN WATER LINE",63570.18,3.7829781123099769E-5,5,7063.3533333333335]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.13","CONNECT TO 30IN WATER LINE",79101.7,4.7072385157083099E-5,1,15820.34]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.30","CUT/CAP EXISTING LINES (ALL SIZES)",80001.31,4.7607731280000354E-5,3,1126.779014084507]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.31","CUT AND CAP 2IN WATER LINE",630,3.7490474476480723E-7,1,315]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.32","CUT AND CAP 4IN WATERLINE",6870,4.0882469786257549E-6,3,981.42857142857144]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.33","CUT AND CAP 6IN WATERLINE",26700.94,1.5889379516953068E-5,6,1213.6790909090907]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.34","CUT AND CAP 8IN WATERLINE",18522.78,1.1022663663864565E-5,6,1029.0433333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.35","CUT AND CAP SERVICE LINE",3675,2.1869443444613756E-6,1,105]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.36","CUT & CAP 10IN WATERLINE",6324,3.7633295331629225E-6,2,903.42857142857144]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.38","CUT AND CAP 14IN WATERLINE",2940,1.7495554755691006E-6,1,1470]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.39","CUT AND CAP 16IN WATER LINE",12330,7.3374214332540849E-6,2,2055]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-06.41","CONNECT TO 2 1/2 IN WATER LINE",12488.06,7.4314808681072991E-6,1,6244.03]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.01","4IN X 4IN TAPPING SLEEVE AND VALVE",57152.06,3.4010442011242774E-5,10,3008.0031578947369]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.03","6IN X 6IN TAPPING SLEEVE AND VALVE",573719.06999999995,3.4141270080167074E-4,29,3205.1344692737434]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.04","8IN X 4IN TAPPING SLEEVE AND VALVE",23753.42,1.4135348987922646E-5,3,3958.9033333333332]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.05","8IN X 6IN TAPPING SLEEVE AND VALVE",20623.12,1.2272548475958716E-5,6,3437.186666666667]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.06","8IN X 8IN TAPPING SLEEVE AND VALVE",278430.09999999998,1.6569010408784088E-4,19,3569.6166666666663]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.07","10IN X 4IN TAPPING SLEEVE AND VALVE",6121.24,3.6426697140382994E-6,2,3060.62]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.08","10IN X 6IN TAPPING SLEEVE AND VALVE",13826.48,8.2279570720566851E-6,3,4608.8266666666668]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.09","10IN X 8IN TAPPING SLEEVE AND VALVE",15453.4,9.1961158456324961E-6,2,3863.35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.10","10IN X 10IN TAPPING SLEEVE AND VALVE",50424.07,3.0006703322782183E-5,7,5042.4070000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.11","12IN X 4IN TAPPING SLEEVE AND VALVE",4120,2.4517580133825489E-6,1,4120]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.13","12IN X 8IN TAPPING SLEEVE AND VALVE",14474.619999999999,8.6136566931231337E-6,3,4824.873333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.15","12IN X 12IN TAPPING SLEEVE AND VALVE",236947.59,1.4100440595489873E-4,15,7180.23]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.18","16IN X 8IN TAPPING SLEEVE AND VALVE",23750,1.4133313790736781E-5,3,5937.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.21","16IN X 16IN TAPPING SLEEVE AND VALVE",152940,9.101258994338035E-5,4,15294]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.22","14IN X 6IN TAPPING SLEEVE AND VALVE",4200,2.4993649650987149E-6,1,4200]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.23","18IN X 12IN TAPPING SLEEVE & VALVE",7900,4.7011864819713922E-6,1,7900]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.27","20IN X 20IN TPPNG SLVE & VLVE",464154.56,2.7621229658447846E-4,2,29009.66]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.29","24IN X 24IN TPPNG SLVE & VLVE",104131.78,6.1967457782230253E-5,3,34710.593333333331]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.30","INSERTION VALVE (4IN)",22400,1.332994648052648E-5,2,5600]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.31","INSERTION VALVE (6IN)",231267.05,1.3762399103612685E-4,6,5640.6597560975606]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.32","INSERTION VALVE (8IN)",126999.48,7.5575726404227372E-5,6,7055.5266666666666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.33","INSERTION VALVE (10IN)",12000,7.1410427574248996E-6,1,12000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.34","INSERTION VALVE (12IN)",192908.41999999998,1.1479727295727338E-4,5,14839.109230769229]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.35","2IN X 2IN TAPPING SADDLE AND VALVE",2152.5,1.2809245446130915E-6,1,2152.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-07.61","__IN X __IN TAPPING SLEEVE AND VALVE (24\" x 16\")",95750.14,5.6979653647451687E-5,3,23937.535]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.01","2IN GATE VALVE ASSEMBLY",59303.990000000013,3.5291027356324899E-5,24,644.60858695652178]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.02","3IN GATE VALVE ASSEMBLY",2963.83,1.7637363963115534E-6,3,987.94333333333327]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.03","4IN GATE VALVE ASSEMBLY",37441.61,2.2281011493068977E-5,15,985.30552631578951]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.04","6IN GATE VALVE ASSEMBLY",657129.17999999993,3.9104896429429693E-4,45,1117.5666326530613]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.05","8IN GATE VALVE ASSEMBLY",618554.34000000008,3.6809358247756163E-4,37,1610.8185937500002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.06","10IN GATE VALVE ASSEMBLY",199731.77000000002,1.1885775913217967E-4,12,2295.7674712643679]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.08","12IN BUTTERFLY VALVE ASSEMBLY",523653.20999999996,3.1161916355606665E-4,6,3098.5397041420115]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.09","12IN GATE VALVE ASSEMBLY",452452.0500000001,2.6924828622787911E-4,24,2693.1669642857146]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.12","14IN GATE VALVE ASSEMBLY",89250,5.3111505508347692E-5,1,8925]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.13","16IN BUTTERFLY VALVE ASSEMBLY",40163.19,2.3900588088715016E-5,3,8032.6380000000008]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.14","16IN GATE VALVE ASSEMBLY",146890,8.7412314219845302E-5,3,8640.5882352941171]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.15","18IN BUTTERFLY VALVE ASSEMBLY",6710,3.9930330751934229E-6,1,6710]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.16","18IN GATE VALVE ASSEMBLY",113672.03,6.7644735546107168E-5,2,16238.861428571428]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.17","20IN BUTTERFLY VALVE ASSEMBLY",86214.659999999989,5.1305214448070844E-5,1,6158.19]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.18","20IN GATE VALVE ASSEMBLY",17000,1.0116477239685275E-5,1,17000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.19","24IN BUTTERFLY VALVE ASSEMBLY",232697.07,1.3847497719979125E-4,3,8024.0368965517246]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.20","24IN GATE VALVE ASSEMBLY",140000,8.3312165503290493E-5,1,14000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.21","30IN BUTTERFLY VALVE ASSEMBLY",84000,4.9987299301974299E-5,1,16800]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.22","36IN BUTTERFLY VALVE ASSEMBLY",60015,3.5714140090571282E-5,1,20005]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.25","ELECTRONIC CONTROL VALVE VAULT W/BYPASS",160755.62,9.5663562993029118E-5,3,53585.206666666665]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-08.41","CURB BOX",454,2.7016945098924206E-7,1,227]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.01","3/4IN WATER SERVICE METER ASSEMBLY",882818.54999999993,5.2535375104982096E-4,33,940.16884984025569]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.02","1IN WATER SERVICE METER ASSEMBLY",55113.95,3.2797589456714835E-5,10,1252.5897727272727]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.03","1-1/2IN WATER SERVICE METER ASSEMBLY",5739.1,3.4152632074281038E-6,3,1913.0333333333335]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.04","2IN WATER SERVICE METER ASSEMBLY",94950.290000000008,5.6503673393324498E-5,11,3956.2620833333335]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.05","3IN WATER SERVICE METER ASSEMBLY",10953,6.5179867768395778E-6,1,10953]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.06","4IN WATER SERVICE METER ASSEMBLY",57972,3.4498377561119692E-5,2,19324]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.07","6IN WATER SERVICE METER ASSEMBLY",69050,4.1090750200015778E-5,1,34525]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.08","8IN WATER SERVICE METER ASSEMBLY",78630,4.6791682668026654E-5,2,39315]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.09","RELOCATE/RECONNECT SERVICE ASSEMBLY",708950.98,4.218874384248571E-4,38,870.94714987714974]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.10","SAMPLE TAP",122170.59,7.270211724081891E-5,13,744.94262195121962]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.11","1-1/2IN COPPER SERVICE PIPE",8914,5.3046045949737969E-6,4,32.414545454545454]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.12","2IN COPPER SERVICE PIPE",30668.75,1.8250571255564574E-5,10,46.257541478129717]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.13","3IN COPPER SERVICE PIPE",7192,4.2798649592833231E-6,1,116]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.14","3/4IN HDPE SERVICE PIPE",160499,9.5510851793661591E-5,12,13.5442194092827]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.15","1IN HDPE SERVICE PIPE",128977.65,7.6752909450181965E-5,4,17.74840374294757]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.16","1-1/2IN HDPE SERVICE PIPE",1450,8.6287599985550878E-7,1,10]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.17","2IN HDPE SERVICE PIPE",48995.25,2.9156431263393527E-5,4,13.40132658643326]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.18","3IN HDPE SERVICE PIPE",1812.5,1.0785949998193859E-6,2,24.166666666666668]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.19","3/4IN PVC SERVICE PIPE",2565,1.5263978893995723E-6,2,18.321428571428573]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.20","1IN PVC SERVICE PIPE",1200,7.1410427574249004E-7,1,30]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.21","1-1/2IN PVC SERVICE PIPE",20460,1.2175477901409455E-5,1,16.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.22","2IN PVC SERVICE PIPE",1540,9.1643382053619546E-7,2,30.8]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.24","TI OF 2IN HDPE CASING FOR SERVICE PIPE-UNCON",69000,4.1060995855193173E-5,2,31.944444444444443]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.25","TI OF 2IN HDPE CASING FOR SERVICE PIPE-ROCK",284910,1.6954620766816068E-4,2,53.756603773584906]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.27","TI OF 2IN PVC CASING FOR SERVICE PIPE-ROCK",614675,3.6578503807667922E-4,3,96.7992125984252]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.28","3/4IN COPPER SERVICE PIPE",430978.88,2.5646988413559124E-4,28,16.438909104779341]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.29","1IN COPPER SERVICE PIPE",122147.29999999999,7.2688257667000535E-5,15,21.220865184155663]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.31","2IN TYPE \"K\" COPPER WATER LINE",12413.75,7.3872599608319456E-6,3,26.13421052631579]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.35","(TI) OF 3IN PVC CASING FOR SERVICE PIPE-UNCON",612.5,3.6449072407689596E-7,1,12.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.36","TI OF 4IN HDPE CASING FOR SERVICE PIPE-ROCK",1440,8.5692513089098803E-7,1,72]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.37","3/4IN SERVICE PIPE",134400,7.9979678883158878E-5,1,14]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.38","1N SERVICE PIPE",520,3.0944518615507899E-7,1,26]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.39","2N SERVICE PIPE",1720,1.023549461897569E-6,1,43]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.41","HDD 3/4IN COPPER SERVICE PIPE",4000,2.3803475858082999E-6,1,40]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.42","HDD 1-1/2IN COPPER SERVICE PIPE",3000,1.7852606893562249E-6,1,50]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.43","HDD 2IN COPPER SERVICE PIPE",3600,2.1423128272274701E-6,1,60]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.44","HDD 2IN COPPER CARRIER PIPE-UNCON",1527.6000000000001,9.0905474302018983E-7,1,25.46]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.51","RECONNECT SERVICE ASSEMBLY",3880,2.3089371582340508E-6,2,388]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.60","3/4IN PEXa SERVICE PIPE",21662.400000000001,1.289101038570343E-5,3,16.857898832684825]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.62","1IN PEXa SERVICE PIPE",62490,3.7186980159290163E-5,5,18.709580838323355]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-09.63","1 1/4 IN PEXa SERVICE PIPE",22100,1.3151420411590857E-5,1,34]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-10.01","3/4IN AUTO AIR RELEASE VALVE ASSEMBLY",17477.919999999998,1.0400881169237649E-5,3,1747.7919999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-10.03","1IN AUTO AIR RELEASE VALVE ASSEMBLY",126192.68000000001,7.5095610296169841E-5,15,2253.4407142857144]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-10.04","1IN MANUAL AIR RELEASE VALVE ASSEMBLY",890,5.2962733784234678E-7,1,890]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-10.05","2IN AUTO AIR RELEASE VALVE ASSEMBLY",101553.8,6.0433335664914736E-5,8,2901.537142857143]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-10.06","2IN MANUAL AIR RELEASE VALVE ASSEMBLY",24090,1.4335643335530487E-5,1,4015]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-10.07","3IN AUTOMATIC AIR RELEASE VALVE ASSEMBLY",4690.91,2.7914990734360032E-6,1,4690.91]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-10.09","4IN AUTO AIR RELEASE VALVE ASSEMBLY",12420,7.3909792539347712E-6,1,6210]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-10.20","2IN PRV ASSEMBLY",7200,4.2846256544549402E-6,1,1800]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-10.23","8IN PRV ASSEMBLY",189878.83000000002,1.1299440364665116E-4,2,94939.415000000008]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-10.24","12IN PRV ASSEMBLY",44763.66,2.6638267503235893E-5,1,44763.66]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-10.31","2IN BLOW-OFF ASSEMBLY",7400,4.4036430337453553E-6,1,1850]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-11.01","BLOW-OFF ASSEMBLY",88076.27,5.2413034165375005E-5,20,2201.9067500000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-11.02","FIRE HYDRANT ASSEMBLY",1665638.47,9.9119962772348268E-4,44,4292.8826546391765]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-11.03","RECONNECT FIRE HYDRANT",15450.47,9.1943722410258913E-6,6,2207.21]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-11.04","RELOCATE FIRE HYDRANT",114055.09,6.7872689532662091E-5,10,2715.5973809523807]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-11.12","RETIRE IN PLACE EXISTING WATER MAIN",8480,5.0463368819135959E-6,1,0.53]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-11.40","RESTORE ASPHALT",34125,2.0307340341427059E-5,1,52.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-11.41","RESTORE CONCRETE",12600,7.4980948952961448E-6,1,63]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-11.42","RESTORE GRAVEL",2100,1.2496824825493575E-6,1,10.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-12.01","REMOVE FIRE HYDRANT",92294.43,5.4923205908513279E-5,21,732.4954761904761]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-12.02","REMOVAL OF EXISTING LINE",364745.24,2.1705511286726725E-4,8,45593.155000000006]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-12.03","PIPE GROUTING",399511.23,2.3774389795845112E-4,8,49938.903749999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-12.04","REMOVE EX BACKFLOW APPARATUS",3020,1.7971624272852664E-6,2,1510]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-12.05","REMOVE BLOW-OFF ASSEMBLY",3520,2.0947058755113041E-6,2,1760]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-12.06","REMOVE EXISTING PRV ASSEMBLY",9050.9399999999987,5.3860957945739425E-6,2,4525.4699999999993]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-12.20","ADJUST EXISTING VALVE BOXES",4814.53,2.8650637155754086E-6,3,601.81624999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-12.26","REMOVE 6IN METER ASSEMBLY",3828,2.277992639618543E-6,1,3828]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-13.01","DI FITTINGS",2726742.4499999997,1.6226487019946271E-3,45,5.0276898468686912]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-13.02","HDPE FITTINGS",39867,2.3724329300854873E-5,3,9.7236585365853667]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-13.03","PVC FITTINGS",3750,2.2315758616952814E-6,1,25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-13.04","BRIDGE HANGER SYSTEM",233510,1.3895874119052403E-4,3,77836.666666666672]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-13.05","CREEK CROSSING #__ (CREEK CROSSING #1)",177742.62,1.0577230410306051E-4,11,16158.42]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-13.06","CREEK CROSSING (#) (2)",6890,4.1001487165547965E-6,2,3445]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-13.07","CREEK CROSSING (#) (3)",5250,3.1242062063733937E-6,1,5250]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-13.08","CREEK CROSSING (#) (4)",5250,3.1242062063733937E-6,1,5250]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-14.01","CLASS A CONCRETE",9210.42,5.4810002528201204E-6,3,146.19714285714286]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-14.02","CLASS B CONCRETE",122864.66,7.3115149203039403E-5,10,202.08003289473686]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-14.03","CLASS C CONCRETE",36638.199999999997,2.1802912729590413E-5,5,239.46535947712417]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-14.05","CONCRETE ENCASEMENT",235138.6,1.399278997100859E-4,15,59.907923566878985]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-14.07","CONCRETE VAULT",24263.21,1.4438718336864949E-5,2,12131.605]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-14.08","RESTORE ASPHALT",207061.08,1.2321933547321481E-4,21,45.259252459016388]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-14.09","RESTORE CONCRETE",45254.5,2.6930359955490427E-5,7,53.874404761904763]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-14.10","RESTORE GRAVEL",78015.95,4.6426269559260261E-5,18,20.854303662122426]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-14.15","SUPPORT STRUCTURE FOR UNSTABLE SUBGRADE",15000,8.9263034467811257E-6,1,15000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-15.02","12IN STEEL CASING PIPE OPEN CUT METHOD",372525.3,2.2168492462687817E-4,14,125.51391509433962]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-15.03","14IN STEEL CASING PIPE OPEN CUT METHOD",96975.679999999993,5.7708956442529557E-5,3,130.34365591397849]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-15.04","18IN STEEL CASING PIPE OPEN CUT METHOD",279166.09999999998,1.661280880436296E-4,10,122.9265081461911]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-15.05","20IN STEEL CASING PIPE OPEN CUT METHOD",173963.5,1.0352339931094055E-4,9,164.27148253068933]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-15.06","22IN STEEL CASING PIPE OPEN CUT METHOD",39750,2.365470413396998E-5,1,150]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-15.07","24IN STEEL CASING PIPE OPEN CUT METHOD",215819.19999999998,1.2843117792276965E-4,6,192.69571428571427]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-15.09","28IN STEEL CASING PIPE OPEN CUT METHOD",47250,2.8117855857360543E-5,1,236.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-15.10","30IN STEEL CASING PIPE OPEN CUT METHOD",185243.96,1.1023625324289232E-4,5,240.88941482444733]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-15.11","36IN STEEL CASING PIPE OPEN CUT METHOD",198401.8,1.1806631141250528E-4,2,314.92349206349206]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-15.12","42IN STEEL CASING PIPE OPEN CUT METHOD",246655,1.4678115844438656E-4,2,326.6953642384106]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-15.13","48IN STEEL CASING PIPE OPEN CUT METHOD",95625,5.6905184473229672E-5,1,318.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-15.22","6IN STEEL CASING PIPE OPEN CUT METHOD",1575,9.372618619120181E-7,1,63]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-15.25","16IN STEEL CASING PIPE OPEN CUT METHOD",608684.44999999995,3.6222014026913817E-4,10,170.97877808988764]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-16.10","RELOCATE/RECONNECT CHECK VALVE PIT",5000,2.9754344822603748E-6,1,5000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-16.36","6IN BACKFLOW PREVENTER ASSEMBLY",21865,1.3011574990924621E-5,1,21865]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-21.02","RETIRE WATER VALVES AND HYDRANTS",10096.64,6.0083781621938783E-6,1,10096.64]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-21.03","TRENCHLESS INSTAL 3IN HDPE CASING -UNCON",4260,2.5350701788858395E-6,1,35.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-21.04","TRENCHLESS INSTAL 3IN HDPE CASING - ROCK",3018,1.7959722534923623E-6,1,50.3]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-21.11","RETIRE IN PLACE EXISTING WATER LINE",80177.5,4.7712579640286242E-5,1,6.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"795-30.24","OPEN CUT 12IN PVC CASING PIPE",102261.24999999999,6.0854329889809748E-5,1,314.64999999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-01.01","4IN DIP FORCE MAIN",11400,6.7839906195536552E-6,1,40]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-01.02","6IN DIP FORCE MAIN",28548,1.6988540719913839E-5,2,70.488888888888894]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-01.03","8IN DIP FORCE MAIN",9900,5.8913602748755421E-6,1,30]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-01.05","12IN DIP FORCE MAIN",4750,2.8266627581473564E-6,1,50]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-01.13","6IN EPOXY COATED DIP FORCE MAIN",37275,2.2181864065251095E-5,1,74.55]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-01.15","10IN EPOXY COATED DIP FORCE MAIN",225281.75000000003,1.3406221743479226E-4,2,71.631717011128785]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-01.18","16IN EPOXY COATED DIP FORCE MAIN",32318,1.9232018319538159E-5,1,161.59]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-01.20","24IN EPOXY COATED DIP FORCE MAIN",722325.20000000007,4.2984626149712441E-4,1,149.86000000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-02.03","1-1/2IN HDPE FORCE MAIN",2100,1.2496824825493575E-6,1,25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-02.04","2IN HDPE FORCE MAIN",4368,2.5993395637026637E-6,1,13.65]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-02.11","16IN HDPE FORCE MAIN",27040,1.6091149680064108E-5,1,80]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-03.02","1-1/4IN PVC FORCE MAIN",2100,1.2496824825493575E-6,1,21]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-03.03","1-1/2IN PVC FORCE MAIN",17061,1.0152777540368852E-5,2,11.035575679172057]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-03.04","2IN PVC FORCE MAIN",69534.100000000006,4.1378831766588232E-5,7,21.070939393939394]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-03.05","3IN PVC FORCE MAIN",3150,1.8745237238240362E-6,1,31.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-03.06","4IN PVC FORCE MAIN",162521.23000000001,9.6714254368273877E-5,10,22.175089370991948]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-03.07","8IN PVC FORCE MAIN",226811.96000000002,1.3497282535461218E-4,4,30.679285810902208]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-03.08","6IN PVC FORCE MAIN",1040279.3700000001,6.1905662173641993E-4,8,39.218826390197918]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-03.09","10IN PVC FORCE MAIN",230270.19,1.3703077271252963E-4,3,33.170583405358684]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-03.10","12IN PVC FORCE MAIN",470417.92999999993,2.7993954599910941E-4,4,49.758613285381855]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-03.38","4IN PVC FORCE MAIN (0-8FT)",60076.499999999993,3.5750737934703078E-5,1,36.409999999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.01","8IN DIP GRAVITY SEWER 0FT-6FT DEPTH",272978.85000000003,1.6244613664355653E-4,15,101.32845211581291]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.02","8IN DIP GRAVITY SEWER 6FT-12FT DEPTH",2136070.98,1.2711478500895424E-3,22,121.99845679364898]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.03","8IN DIP GRAVITY SEWER 12FT-18FT DEPTH",894935.20000000007,5.3256421069371705E-4,15,144.11194847020934]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.04","8IN DIP GRAVITY SEWER >18FT DEPTH",122118.75,7.2671267936106837E-5,5,157.57258064516128]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.05","10IN DIP GRAVITY SEWER 0FT-6FT DEPTH",20360,1.2115969211764246E-5,2,106.04166666666667]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.06","10IN DIP GRAVITY SEWER 6FT-12FT DEPTH",127243.56,7.5720975213913394E-5,6,100.90686756542426]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.07","10IN DIP GRAVITY SEWER 12FT-18FT DEPTH",255800,1.522232281124408E-4,3,180.14084507042253]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.08","10IN DIP GRAVITY SEWER >18FT DEPTH",41050,2.4428317099357677E-5,2,283.10344827586209]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.09","12IN DIP GRAVITY SEWER 0FT-6FT DEPTH",49001.75,2.9160299328220466E-5,5,119.80867970660147]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.10","12IN DIP GRAVITY SEWER 6FT-12FT DEPTH",165535,9.8507709404194239E-5,7,129.93328100470958]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.11","12IN DIP GRAVITY SEWER 12FT-18FT DEPTH",158969.99,9.4600957978117388E-5,6,156.92990128331687]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.12","12IN DIP GRAVITY SEWER >18FT DEPTH",129831.34,7.7260929182814135E-5,4,216.74681135225376]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.17","18IN DIP GRAVITY SEWER 0FT-6FT DEPTH",15470,9.2059942881135999E-6,3,198.33333333333334]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.18","18IN DIP GRAVITY SEWER 6FT-12FT DEPTH",117100,6.9684675574537981E-5,5,198.47457627118644]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.19","18IN DIP GRAVITY SEWER 12FT-18FT DEPTH",81750,4.8648353784957133E-5,2,308.49056603773585]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.20","18IN DIP GRAVITY SEWER >18FT DEPTH",2000,1.1901737929041499E-6,1,200]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.21","24IN DIP GRAVITY SEWER 0FT-6FT DEPTH",2449.44,1.4576296476455707E-6,1,306.18]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.22","24IN DIP GRAVITY SEWER 6FT-12FT DEPTH",10442.120000000001,6.213968783180142E-6,1,242.84000000000003]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.23","24IN DIP GRAVITY SEWER 12FT-18FT DEPTH",9882,5.8806487107394055E-6,1,131.76]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.24","24IN DIP GRAVITY SEWER >18FT DEPTH",14471.12,8.6115738889855525E-6,1,136.52000000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.27","36IN DIP GRAVITY SEWER 12FT-18FT DEPTH",29187.399999999998,1.7369039281505294E-5,1,265.33999999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.29","__IN DIP GRAVITY SEWER 0FT-6FT DEPTH (SEE PLANS)",11550,6.8732536540214661E-6,1,70]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.30","__IN DIP GRAVITY SEWER 6FT-12FT DEPTH (30 IN)",44013.4,2.6191797608303759E-5,3,154.43298245614037]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.31","__IN DIP GRAVITY SEWER 12FT-18FT DEPTH (30 IN)",64052.7,3.8116922452375822E-5,2,237.23222222222222]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.32","__IN DIP GRAVITY SEWER >18FT DEPTH (SEE PLANS)",15491,9.2184911129390943E-6,1,88.52]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.41","6IN DIP SERVICE LATERAL",184081.09999999998,1.0954425049448405E-4,3,64.00594575799721]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.51","8IN PVC GRAVITY SEWER 0FT-6FT DEPTH",429410.73000000004,2.5553669861891999E-4,20,66.740865713397568]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.52","8IN PVC GRAVITY SEWER 6FT-12FT DEPTH",2238904.61,1.3323427958171433E-3,25,74.94743112509623]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.53","8IN PVC GRAVITY SEWER 12FT-18FT DEPTH",632555.66,3.7642558454259396E-4,18,72.151894604767875]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.54","8IN PVC GRAVITY SEWER >18FT DEPTH",184520.41999999998,1.0980568406983338E-4,6,126.21095759233926]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.55","10IN PVC GRAVITY SEWER 0FT-6FT DEPTH",75284,4.4800521912498013E-5,4,67.458781362007173]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.56","10IN PVC GRAVITY SEWER 6FT-12FT DEPTH",209412.75,1.2461878347499428E-4,4,66.186077749683946]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.57","10IN PVC GRAVITY SEWER 12FT-18FT DEPTH",65959.95,3.9251901935634042E-5,4,52.725779376498799]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.58","10IN PVC GRAVITY SEWER >18FT DEPTH",5335,3.1747885925718203E-6,1,55]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.59","12IN PVC GRAVITY SEWER 0FT-6FT DEPTH",114674,6.8240994763745251E-5,4,53.287174721189594]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.60","12IN PVC GRAVITY SEWER 6FT-12FT DEPTH",307903.2,1.8322915969566254E-4,8,79.376952822892505]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.61","12IN PVC GRAVITY SEWER 12FT-18FT DEPTH",296408.03999999998,1.7638854060704248E-4,4,66.939485094850951]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.62","12IN PVC GRAVITY SEWER >18FT DEPTH",2975,1.7703835169449232E-6,1,85]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.64","15IN PVC GRAVITY SEWER 6FT-12FT DEPTH",59860.4,3.5622139656379789E-5,2,45.905214723926385]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.65","15IN PVC GRAVITY SEWER 12FT-18FT DEPTH",129395.76,7.7001721232457549E-5,2,59.247142857142855]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.66","15IN PVC GRAVITY SEWER >18FT DEPTH",5005,2.9784099167426354E-6,1,77]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.67","18IN PVC GRAVITY SEWER 0FT-6FT DEPTH",37080,2.206582212044294E-5,2,87.452830188679243]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.68","18IN PVC GRAVITY SEWER 6FT-12FT DEPTH",147208.9,8.7602087431123857E-5,4,122.87888146911519]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.69","18IN PVC GRAVITY SEWER 12FT-18FT DEPTH",72684.98,4.3253879166881142E-5,4,153.66803382663846]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-05.70","18IN PVC GRAVITY SEWER >18FT DEPTH",57476.2,3.4203333477858748E-5,3,170.04792899408284]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.02","HDD 4IN HDPE CARRIER PIPE-UNCON",38195.199999999997,2.2729463027366295E-5,4,70.211764705882345]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.04","HDD 8IN HDPE CASING PIPE-UNCON",127375,7.5799193435583059E-5,2,72.372159090909093]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.61","BORE/JACK 10IN STEEL CASING PIPE-UNCON.",29120,1.7328930424684425E-5,1,182]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.62","BORE/JACK 12IN STEEL CASING PIPE-UNCON.",361605,2.1518639719155259E-4,5,192.34308510638297]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.64","BORE/JACK 16IN STEEL CASING PIPE-UNCON.",1088211.78,6.4758057084278822E-4,13,383.57835037010926]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.65","BORE/JACK 18IN STEEL CASING PIPE-UNCON.",97721.62,5.8152855562069021E-5,3,305.38006250000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.66","BORE/JACK 20IN STEEL CASING PIPE-UNCON.",378035.6,2.2496403195239803E-4,4,387.7288205128205]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.67","BORE/JACK 24IN STEEL CASING PIPE-UNCON.",1134128.92,6.7490525917934363E-4,6,1020.818109810981]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.68","BORE/JACK 30IN STEEL CASING PIPE-UNCON.",320841.66000000003,1.9092866770193187E-4,7,420.50020969855836]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.69","BORE/JACK 36IN STEEL CASING PIPE-UNCON.",105625,6.2856053437750423E-5,1,845]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.71","BORE/JACK __IN STEEL CASING PIPE-UNCON. (6'')",86847.6,5.1681868748311233E-5,2,423.64682926829272]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.72","BORE/JACK 6IN STEEL CASING PIPE-ROCK.",124296.3,7.3967099407476057E-5,3,218.06368421052633]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.73","BORE/JACK 8IN STEEL CASING PIPE-ROCK.",42314.8,2.5180983005990266E-5,1,384.68]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.74","BORE/JACK 10IN STEEL CASING PIPE-ROCK.",145499.20000000001,8.6584667364259757E-5,3,330.68]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.75","BORE/JACK 12IN STEEL CASING PIPE-ROCK.",411527.80000000005,2.4489480130575027E-4,4,345.82168067226894]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.77","BORE/JACK 16IN STEEL CASING PIPE-ROCK.",488007.74,2.9040701144119111E-4,3,758.9544945567651]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.78","BORE/JACK 18IN STEEL CASING PIPE-ROCK.",55340,3.2932108849657832E-5,2,614.88888888888891]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.79","BORE/JACK 20IN STEEL CASING PIPE-ROCK.",293802.7,1.7483813691224006E-4,2,773.16500000000008]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.80","BORE/JACK 24IN STEEL CASING PIPE-ROCK.",56250,3.347363792542922E-5,1,750]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.81","BORE/JACK 30IN STEEL CASING PIPE-ROCK.",161600.59999999998,9.6166399518793171E-5,3,765.8796208530805]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.84","BORE/JACK __IN STEEL CASING PIPE-ROCK (28)",298863.45,1.7784972292345989E-4,2,1245.264375]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.87","OPEN CUT 8IN STEEL CASING PIPE",28996.000000000004,1.725513964952437E-5,1,131.80000000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.89","OPEN CUT 12IN STEEL CASING PIPE",156440,9.3095394080962608E-5,6,133.7094017094017]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.90","OPEN CUT 16IN STEEL CASING PIPE",344959.95,2.0528114604576297E-4,11,163.02455103969754]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.91","OPEN CUT 18IN STEEL CASING PIPE",114645,6.8223737243748133E-5,3,248.14935064935065]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.92","OPEN CUT 20IN STEEL CASING PIPE",101138.95,6.0186463865921588E-5,4,243.70831325301205]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.93","OPEN CUT 24IN STEEL CASING PIPE",177612,1.0569457385264594E-4,4,205.33179190751446]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.94","OPEN CUT 30IN STEEL CASING PIPE",195246.6,1.1618869323681971E-4,5,224.67963176064441]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.97","OPEN CUT __IN STEEL CASING PIPE (54 IN)",60737.04,3.614381663328554E-5,1,519.12]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-06.99","HDD 10IN HDPE CARRIER PIPE-ROCK",73500,4.3738886889227511E-5,1,294]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.01","48IN MANHOLE 0FT-4FT DEPTH",37534.979999999996,2.2336574756590704E-5,11,2681.0699999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.02","48IN MANHOLE 4FT-6FT DEPTH",222169.58,1.3221020584826097E-4,20,3366.2057575757576]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.03","48IN MANHOLE 6FT-8FT DEPTH",426909.63000000006,2.5404832678220366E-4,29,3952.8669444444445]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.04","48IN MANHOLE 8FT-10FT DEPTH",527056.4,3.1364435733120344E-4,29,3737.9886524822696]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.05","48IN MANHOLE 10FT-12FT DEPTH",497402.03,2.9599743032166192E-4,23,4605.5743518518511]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.06","48IN MANHOLE 12FT-14FT DEPTH",347675.41,2.0689708070960271E-4,23,4762.6768493150694]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.07","48IN MANHOLE 14FT-16FT DEPTH",168654.02,1.0036379733596617E-4,14,4818.686285714286]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.08","48IN MANHOLE 16FT-20FT DEPTH",173588.03,1.0329996203392969E-4,10,7890.3649999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.09","48IN MANHOLE 20FT-24FT DEPTH",51465.9,3.0626682704112848E-5,6,7352.2714285714292]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.10","48IN MANHOLE 24FT-28FT DEPTH",11000,6.545955860972825E-6,1,11000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.11","48IN MANHOLE >28FT DEPTH",12000,7.1410427574248996E-6,1,12000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.14","60IN MANHOLE 6FT-8FT DEPTH",10420,6.2008054610306213E-6,1,5210]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.15","60IN MANHOLE 8FT-10FT DEPTH",4248.21,2.5280541043766696E-6,1,4248.21]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.16","60IN MANHOLE 10FT-12FT DEPTH",39835.410000000003,2.3705530505795954E-5,2,6639.2350000000006]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.17","60IN MANHOLE 12FT-14FT DEPTH",78148.209999999992,4.6504975752185004E-5,5,7104.3827272727267]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.18","60IN MANHOLE 14FT-16FT DEPTH",96423.86,5.7380575591329376E-5,5,8765.8054545454543]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.19","60IN MANHOLE 16FT-20FT DEPTH",39452.400000000001,2.3477606273585845E-5,4,9863.1]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.21","60IN MANHOLE 24FT-28FT DEPTH",18230,1.0848434122321328E-5,1,18230]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.22","60IN MANHOLE >28FT DEPTH",17760,1.0568743280988852E-5,1,17760]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.26","72IN MANHOLE 8FT-10FT DEPTH",7290,4.3381834751356266E-6,1,7290]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.27","72IN MANHOLE 10FT-12FT DEPTH",13327.1,7.9307825777064494E-6,1,6663.55]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.28","72IN MANHOLE 12FT-14FT DEPTH",8216.4699999999993,4.8895136320915802E-6,1,8216.4699999999993]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.36","84IN MANHOLE 6FT-8FT DEPTH",11427.84,6.8005578387508806E-6,1,11427.84]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.56","MANHOLE DROP CONNECTION ASSEMBLY",118748.44,7.0665640618125443E-5,18,2698.8281818181817]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.62","MANHOLE MODIFICATION",4529,2.6951485540314478E-6,1,4529]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-07.80","REMOVE SEWER MANHOLE",41276.559999999998,2.456313998661786E-5,6,938.10363636363627]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-08.01","DI FITTINGS",378039.05,2.2496608500219081E-4,15,8.5635757163891721]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-08.02","PVC FITTINGS",9033.74,5.3758602999549675E-6,7,7.6817517006802722]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-08.04","4IN PVC PIPE FOR SERVICE LATERAL",103210,6.1418918582818656E-5,7,24.341981132075471]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-08.05","6IN PVC PIPE FOR SERVICE LATERAL",625900.30000000005,3.7246506701542272E-4,26,42.419539139274825]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-08.06","8IN PVC PIPE FOR SERVICE LATERAL",1600,9.5213903432331998E-7,1,40]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-08.07","4IN CLEAN OUT ASSEMBLY",16352,9.7308609307843303E-6,6,224]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-08.08","6IN CLEAN OUT ASSEMBLY",231042.54,1.3749038807700441E-4,18,828.10946236559141]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-08.09","8IN CLEAN OUT ASSEMBLY",600,3.5705213787124502E-7,1,300]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-08.10","2IN LOW PRESS SERVICE ASSEMBLY",6109.5599999999995,3.6357190990877392E-6,1,1018.2599999999999]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-08.12","2IN END OF LINE FLUSHING ASSEMBLY",1392.97,8.289381941508469E-7,1,1392.97]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-08.20","CONNECT SERVICE LINES (ALL SIZES)",13559.85,8.0692890528556698E-6,2,616.3568181818182]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-08.34","8IN INSERTION VALVE",10389.75,6.182804082412946E-6,1,10389.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-08.36","12IN INSERTION VALVE",27982.5,1.6652019079970188E-5,1,13991.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-09.02","1-1/4IN BALL VALVE",4200,2.4993649650987149E-6,1,420]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-09.04","2IN PVC BALL VALVE",3603.65,2.14448489439952E-6,2,600.60833333333335]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-09.05","3IN PVC BALL VALVE",1050,6.2484124127467873E-7,1,525]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-09.06","4IN PLUG VALVE ASSEMBLY",3912.81,2.3284619593066437E-6,1,1304.27]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-09.07","6IN PLUG VALVE ASSEMBLY",35525.160000000003,2.1140557210363398E-5,3,1869.7452631578949]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-09.08","8IN PLUG VALVE ASSEMBLY",14733.060000000001,8.767450950642209E-6,3,2946.6120000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-09.09","10IN PLUG VALVE ASSEMBLY",6877.06,4.0924482921147071E-6,1,3438.53]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-09.10","12IN PLUG VALVE ASSEMBLY",18243.04,1.0856194055451062E-5,2,6081.0133333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-09.11","16IN PLUG VALVE ASSEMBLY",12527.33,7.4548499305309726E-6,1,12527.33]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-09.15","24IN PLUG VALVE ASSEMBLY",103376.38,6.1517929140650365E-5,1,51688.19]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-09.19","1IN COMBO AIR RELEASE VALVE ASSEMBLY",9240,5.4986029232171732E-6,1,2310]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-09.20","2IN COMBO AIR RELEASE VALVE ASSEMBLY",79639.010000000009,4.7392131297415773E-5,6,4977.4381250000006]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-09.22","4IN COMBO AIR RELEASE VALVE ASSEMBLY",18058.440000000002,1.074634101436601E-5,2,6019.4800000000005]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-09.26","2IN AIR/VAC VALVE ASSEMBLY",66920.13,3.9823292471869404E-5,6,4780.0092857142863]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-09.28","4IN AIR/VAC VALVE ASSEMBLY",56902.670000000006,3.38620332901366E-5,4,8128.9528571428582]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-09.40","CUT AND CAP (ALL LINES)",21764.86,1.295198298911391E-5,3,1145.5189473684211]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.01","CONNECT 6IN SEWER TO EXIST. MANHOLE",4435.6499999999996,2.6395971922476463E-6,2,2217.8249999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.02","CONNECT 8IN SEWER TO EXIST. MANHOLE",87844.040000000008,5.2274837135411936E-5,21,2374.1632432432434]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.03","CONNECT 10-18IN SEWER TO EXIST. MANHOLE",63398,3.772731906126865E-5,7,4528.4285714285716]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.05","CONNECT 4IN LATERAL TO SEWER LINE",36340,2.1625457817068405E-5,4,526.66666666666663]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.06","CONNECT 6IN LATERAL TO SEWER LINE",201683.08000000002,1.2001895814409557E-4,20,829.97152263374494]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.07","CONNECT 8IN LATERAL TO SEWER LINE",800,4.7606951716165999E-7,1,400]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.08","CONNECT EX. 6IN SEWER TO NEW MANHOLE",3176,1.8899959831317901E-6,1,1588]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.09","CONNECT EX. 8IN SEWER TO NEW MANHOLE",152444.97,9.0718004077029683E-5,20,1291.9065254237289]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.10","CONNECT EX.10-18IN SEWER TO NEW MANHOLE",33072.400000000001,1.9680951874221607E-5,10,1837.3555555555556]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.11","CONNECT EX. >18IN SEWER TO NEW MANHOLE",7754.8,4.614779864606551E-6,2,1550.96]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.12","CONNECT TO EXISTING PUMP STATION",13250,7.8849013779899934E-6,2,6625]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.14","CONNECT TO 2IN FORCE MAIN",13394.8,7.9710699605962545E-6,4,1674.35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.16","CONNECT TO 4IN FORCE MAIN",23298.12,1.3864405923968017E-5,8,1941.51]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.17","CONNECT TO 6IN FORCE MAIN",30324.880000000001,1.8045938724481602E-5,7,2021.6586666666667]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.18","CONNECT TO 8IN FORCE MAIN",6142,3.6550237180086448E-6,2,2047.3333333333333]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.19","CONNECT TO 10IN FORCE MAIN",18261.16,1.0866977030014773E-5,3,2608.7371428571428]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.20","CONNECT TO 12IN FORCE MAIN",32211.02,1.9168355923355716E-5,4,2684.2516666666666]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.24","REMOVE & REPLACE SEWER PUMP STATION",425478.75,2.5319682884380833E-4,4,106369.6875]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.31","RESIDENTIAL GRINDER PUMP STATION",75429.119999999995,4.4886880922911139E-5,2,10775.588571428571]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.32","PUMP STATION",517500,3.0795746891394883E-4,1,517500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.36","PUMP STATION RETIRE IN PLACE",11066,6.5852315961386617E-6,1,11066]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-10.41","CONNECT 8IN PVC TO EXISTING SEWER LINE",1820.82,1.0835461227978672E-6,1,1820.82]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.10","48IN MANHOLE REHABILITATION",2664.5,1.5856090355965538E-6,1,2664.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.15","48IN MH ADJUSTMENT INCREASE HEIGHT",47726.5,2.8401414763519958E-5,13,492.0257731958763]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.16","60IN MH ADJUSTMENT INCREASE HEIGHT",10572.720000000001,6.2916871318567834E-6,2,704.84800000000007]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.20","48IN MH ADJUSTMENT DECREASE HEIGHT",25045,1.4903951321642218E-5,7,659.07894736842104]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.25","RETIREIN PLACE 48IN MANHOLE",240052.21,1.4285192463536176E-4,26,836.418850174216]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.26","RETIREIN PLACE 60IN MANHOLE",1475.22,8.7788409138403011E-7,2,368.80500000000001]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.30","RETIREIN PLACE EXISTING SEWER <8IN",50916.6,3.0299801471891721E-5,10,3.3982913969165054]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.31","RETIREIN PLACE EXISTING SEWER 8IN-14IN",474808.19999999995,2.8255213814799607E-4,17,10.698215492767337]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.32","RETIREIN PLACE EXISTING SEWER 15IN-24IN",19247.800000000003,1.1454113565530251E-5,5,14.100952380952384]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.35","REMOVE EXISTING SEWER 8IN-14IN",80044.200000000012,4.7633254556989185E-5,4,18.833929411764707]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.36","REMOVE EXISTING SEWER 15IN-24IN",15947.8,9.4903268072384016E-6,4,26.229934210526313]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.38","BY-PASS PUMPING",380392.44,2.2636655655343215E-4,16,23774.5275]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.39","TV INSPECTION",51094.12,3.0405441297749897E-5,6,2.4678380989180835]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.40","RESTORE ASPHALT",389765,2.3194404419564301E-4,18,38.774870672502985]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.41","RESTORE CONCRETE",94877,5.6460059474683518E-5,12,72.758435582822088]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.42","RESTORE GRAVEL",50335.7,2.9954115493742711E-5,9,14.485093525179856]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.44","STREAM CROSSING (#)",3281.25,1.952628878983371E-6,1,3281.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.45","PIPE CHECK DAM",2060,1.2258790066912745E-6,1,206]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-11.46","CONCRETE CAP",1050,6.2484124127467873E-7,1,210]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-13.05","CREEK CROSSING (#) (SEE PLANS)",30500,1.8150150341788288E-5,2,15250]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-30.23","OPEN CUT 8IN PVC CASING PIPE",31668,1.884521183684431E-5,1,243.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-30.24","OPEN CUT 12IN PVC CASING PIPE",81054.2,4.8234292322405776E-5,2,253.294375]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-30.25","OPEN CUT 16IN PVC CASING PIPE",45293.75,2.6953717116176172E-5,1,362.35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"797-40.01","Concrete Encasement",47150,2.8058347167715336E-5,1,82]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"798-05.02","FIBER OPTIC CABLE ENCLOSURE",3700,2.2018215168726777E-6,1,1850]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"798-05.03","FIBER OPTIC CABLE SPLICE",39960,2.3779672382224917E-5,3,1998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"798-05.29","COMMUNICATION ASSEMBLY (CSC)",12955,7.7093507435366318E-6,2,259.10000000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"798-05.32","COMMUNICATION ASSEMBLY (DDE)",6840,4.0703943717321931E-6,2,488.57142857142856]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"798-05.33","COMMUNICATION ASSEMBLY (DE)",3420,2.0351971858660966E-6,1,570]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"798-05.40","COMMUNICATION ASSEMBLY (FOSS)",180,1.071156413613735E-7,1,60]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"798-06.13","FIBER OPTIC CABLE (DESCRIPTION)",11260.8,6.7011545235675254E-6,1,2.4]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"798-09.02","REMOVE AERIAL CABLE/TERMINALS",8559,5.0933487467333099E-6,1,1.8]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"798-09.03","REMOVE POLES, GUYS, ANCHORS",1610,9.5808990328784074E-7,1,35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-01","SEEDING (WITH MULCH)",822609.35392000002,4.8952404741669934E-4,63,24.462667643496928]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-01.02","CROWN VETCH MIXTURE (WITH MULCH)",74612.775999999998,4.4401085305513864E-5,11,26.656378447185283]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-01.04","SEEDING (WILDFLOWER MIXTURE)",39082.630000000005,2.3257560991884763E-5,3,43.415496556320818]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-01.06","SEEDING (SPECIAL MIXTURE)",3969,2.3618998920182856E-6,1,63]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-01.07","TEMPORARY SEEDING (WITH MULCH)",2636158.2728000004,1.5687432451170146E-3,89,18.727230289871308]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-01.08","SEEDING (SPECIAL MIXTURE) WITH MULCH",9600,5.7128342059399203E-6,1,100]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-01.10","SEEDING (WITH BONDED FIBER MATRIX)",79913.820000000007,4.7555667127429763E-5,2,59.283249258160239]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-01.13","BONDED FIBER MATRIX HYDROMULCH (WITHOUT SEED)",26574,1.5813839186317441E-5,2,66.435000000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-01.16","BONDED FIBER MATRIX HYDROMULCH (W/PERMANENT SEED)",113245,6.7390615588715233E-5,3,86.446564885496187]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-01.30","COVER CROP SEED MIX (RIPZN/FLPL) W/MULCH",86203.91,5.1298817263933993E-5,6,32.508922577968853]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-01.34","GRASS SEED MIX (RIPZN/FLPL)",11712.900000000001,6.9701933094535099E-6,6,63.484552845528462]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-01.35","GRASS SEED MIX (RIPZN/FLPL) W/MULCH",52949.1,3.1509315588930564E-5,2,54.869533678756476]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-01.36","SPECIAL WETLAND SEED MIXTURE",21811.91,1.2979981827591978E-5,4,69.686613418530357]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-01.65","TEMPORARY MULCH",195110.54,1.1610772571368845E-4,9,12.284237234779324]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-02","SEEDING (WITHOUT MULCH)",410989.4952,2.4457446317297296E-4,59,15.049922902876958]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-02.01","CROWN VETCH MIXTURE (WITHOUT MULCH)",95486.86,5.6822979169353779E-5,18,19.339894274198446]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-02.08","TEMPORARY SEEDING (WITHOUT MULCH)",96532.225000000006,5.7445062182863408E-5,9,21.235872684495178]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-02.15","FERTILIZER",196360.516,1.1685157005216802E-4,14,490.35821827326237]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-03","WATER (SEEDING & SODDING)",624442.61115000013,3.7159761548168345E-4,103,8.9857567508373926]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-06.01","COMPOSTED MULCH (TYPE A)",2152.5,1.2809245446130915E-6,2,43.05]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-07","SEED (SUPPLEMENTAL APPLICATION)",31520.145199999999,1.8757225382786768E-5,22,2.2311836204694862]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-07.01","CROWN VETCH SEED (SUPPLEMENTAL APPLICATION)",4881.6316999999999,2.9049950579750669E-6,8,2.1840247696579298]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-08","FERTILIZER (SUPPLEMENTAL APPLICATION)",58721.422899999998,3.4944349308810802E-5,23,285.62253649235618]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801-09","AGRICULTURAL LIME",18510.25,1.1015207225052021E-5,3,31.426570458404075]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801M01","SEEDING (WITH MULCH)",5133.82,3.0550690107435914E-6,1,26.06]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801M01.02","CROWN VETCH MIXTURE (WITH MULCH)",3078,1.8316774672794869E-6,1,30.78]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801M01.07","TEMPORARY SEEDING (WITH MULCH)",29955,1.7825827983221908E-5,1,15]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801M01.16","BONDED FIBER MATRIX HYDROMULCH (W/PERMANENT SEED)",26277.809999999998,1.5637580398457298E-5,1,51.83]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801M01.65","TEMPORARY MULCH",45331.9,2.697641968127582E-5,1,11.35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801M02","SEEDING (WITHOUT MULCH)",675.4,4.0192168986373144E-7,1,15.35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801M02.01","CROWN VETCH MIXTURE (WITHOUT MULCH)",3917.65,2.3313421798854715E-6,1,20.95]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801M02.08","TEMPORARY SEEDING (WITHOUT MULCH)",20169.7,1.2002724175369417E-5,1,5.05]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801M03","WATER (SEEDING & SODDING)",14008,8.3359772455006666E-6,1,13.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801M07","SEED (SUPPLEMENTAL APPLICATION)",2572.79,1.5310336163229341E-6,1,12.31]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801M07.01","CROWN VETCH SEED (SUPPLEMENTAL APPLICATION)",5631.75,3.3513806290939734E-6,1,25.03]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"801M08","FERTILIZER (SUPPLEMENTAL APPLICATION)",3706.32,2.2055824660582545E-6,1,926.58]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-01.07","TREES(LIQUIDAMBER STYRACIFLUA) (1.5 - 2\" CAL. B&B)",7425,4.418520206156657E-6,1,225]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-01.08","TREES(PLATANUS OCCIDENTALIS) (1.5 - 2\"CAL. B&B)",7425,4.418520206156657E-6,1,225]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-01.10","TREES (QUERCUS FALCATA 1.25\"-1.50\" CAL, B&B)",36078.9,2.147008062840477E-5,6,12.221849593495936]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-01.11","TREES (FAGUS GRANDIFOLIA 1.25\"-1.50\" CAL, B&B)",35875.61464,2.1349108174428225E-5,6,15.987293556885717]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-01.12","TREES (ULMUS RUBRUM 1.25\"-1.50\" CAL, B&B)",21800,1.2972894342655235E-5,4,239.56043956043956]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-01.13","TREES (PLATANUS OCCIDENTALIS 1.25\"-1.5\" CAL, B &B)",4100,2.4398562754535074E-6,2,170.83333333333334]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-01.14","TREES (ACER NEGUNDO 1.25\"-1.50\" CAL, B&B)",3400,2.023295447937055E-6,2,170]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-02.01","SEEDLINGS (ACER RUBRUM; RED MAPLE 18'-24\" HT BR)",1314.32,7.8213460974489122E-7,3,5.4087242798353907]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-02.02","SEEDLINGS (SALIX NIGRA; BLACK WILLOW, 18\"-24\" HT, BR)",1314.32,7.8213460974489122E-7,3,5.4087242798353907]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-02.03","SEEDLINGS (PLANTUS OCCIDENTALIS; SYCAMORE, 18\"-24\" HT, BR)",128,7.6171122745865602E-8,1,8]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-02.30","CUTTINGS: SALIX NIGRA (18IN-24IN LENGTH)",44645.2,2.6567773509482176E-5,11,12.017550471063256]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-02.31","CUTTINGS: SALIX SERICEA (18IN-24IN)",20757.2,1.2352337727035011E-5,7,12.813086419753088]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-02.32","CUTTINGS: CORNUS AMOMUM (18IN-24IN)",58969.664640000003,3.5092074715437269E-5,12,10.305764102392029]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-02.33","CUTTINGS: SAMBUCUS CANADENSIS (18IN-24IN)",37018.65,2.2029313539345608E-5,11,13.211509635974304]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-02.34","CUTTINGS: SALIX INTERIOR (18IN-24IN)",1776.8,1.0573503976160468E-6,3,9.0653061224489786]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-02.35","CUTTINGS: CEPHALANTHUS OCCIDENTALIS (18IN-24IN)",5238.6499999999996,3.1174519700986627E-6,4,7.8540479760119952]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-02.36","CUTTINGS: CORNUS SERICEA (18IN-24IN)",441,2.624333213353651E-7,1,9]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-02.37","CUTTINGS: ALNUS SERRULATA (18IN-24IN)",13600,8.0931817917482202E-6,1,17]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-03.01","SHRUBS (YUCCA FILAMENTOS)",50826.9,3.0246422177279973E-5,4,62.440909090909095]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-03.02","SHRUBS (BUXUS MICROPHILLA)",3459.9,2.0589411530345344E-6,2,48.730985915492958]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-03.03","SHRUBS (BLADDERNUT SEEDLING B.R.)",75.25,4.4780288958018642E-8,1,10.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-04.70","GROUND COVER (JUNIPERUS HORIZONTALIS)",22241.5,1.3235625207438825E-5,2,6.3710971068461761]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-04.71","GROUND COVER (1 GAL., @ 18\" O.C.)",4860,2.8921223167570847E-6,1,7.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-04.72","GROUND COVER (1 GAL., @ 36\" O.C.)",7794.5,4.6384048143956985E-6,1,8.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-04.73","GROUND COVER (3 GAL., @ 36\" O.C.)",2518.5,1.4987263487145509E-6,1,11.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-06.03","MULCH (3IN SHREDDED PINE BARK MULCH)",21820,1.2984796080584276E-5,2,55.805626598465473]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-07.01","FLOWER (SEE PLANS)",24200,1.4401102894140214E-5,1,20]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.01","ACER NEGUNDO (BOX ELDER 2-5FT CNTNR GRWN)",4226,2.5148372244064691E-6,2,32.507692307692309]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.02","ACER RUBRUM (RED MAPLE 2-5FT CNTNR GRWN)",16239.25,9.6637648832093589E-6,13,26.66543513957307]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.03","ACER SACCHARINUM (SILVER MAPLE 2-5FT CNTNR GRWN)",2650,1.5769802755979987E-6,1,25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.04","ACER SACCHARUM (SUGAR MAPLE 2-5FT CNTNR GRWN)",6957,4.1400195386170861E-6,6,28.165991902834008]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.06","ASIMINA TRILOBA (PAWPAW 2-5FT CNTNR GRWN)",1189.6499999999999,7.0794512636421097E-7,1,36.049999999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.07","BETULA NIGRA (RIVER BIRCH 2-5FT CNTNR GRWN)",639,3.8026052683287595E-7,2,35.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.09","CARYA OVATA (SHAGBARK HICKORY 2-5FT CNTNR GRWN)",7025,4.1804854475758268E-6,6,30.150214592274679]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.11","CERCIS CANADENSIS (REDBUD 2-5FT CNTNR GRWN)",11049,6.5751151188989763E-6,5,30.606648199445985]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.12","CORNUS FLORIDA (FLOWERING DOGWOOD 2-5FT CNTNR GRWN)",1692.1599999999999,1.0069822427003432E-6,4,22.265263157894736]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.13","CRATAEGUS PHAENOPYRUM (WSHNGTN HAWTHORN 2-5FT CNTNR GRWN)",1430,8.5097426192646727E-7,1,65]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.14","DIOSPYROS VIRGINIANA (PERSIMMON 2-5FT CNTNR GRWN)",2670,1.5888820135270402E-6,2,29.666666666666668]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.15","FAGUS GRANDIFOLIA (BEECH 2-5FT CNTNR GRWN)",4200,2.4993649650987149E-6,2,21.875]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.16","FRAXINUS PENNSYLVANICA (GREEN ASH 2-5FT CNTNR GRWN)",7433.43,4.4235367886937481E-6,7,20.939239436619719]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.18","LIQUIDAMBER STYRACIFLUA (SWEETGUM 2-5FT CNTNR GRWN)",13324.04,7.9289616118033053E-6,12,29.412891832229583]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.19","LIRIODENDRON TULIPIFERA (TULIP POPLAR 2-5FT CNTNR GRWN)",9390.61,5.5882289606918202E-6,5,31.198039867109635]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.26","PLATANUS OCCIDENTALIS (SYCAMORE 2-5FT CNTNR GRWN)",19220.39,1.1437802233698497E-5,17,26.008646820027064]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.28","PRUNUS SEROTINA (BLACK CHERRY 2-5FT CNTNR GRWN)",875,5.2070103439556565E-7,1,35]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.29","QUERCUS ALBA (WHITE OAK 2-5FT CNTNR GRWN)",1550,9.2238468950071622E-7,2,29.807692307692307]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.30","QUERCUS BICOLOR (SWAMP WHITE OAK 2-5FT CNTNR GRWN)",1155,6.8732536540214665E-7,1,11]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.31","QUERCUS FALCATA (SOUTHERN RED OAK 2-5FT CNTNR GRWN)",5285,3.1450342477492165E-6,6,22.878787878787879]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.32","QUERCUS LYRATA (OVERCUP OAK 2-5FT CNTNR GRWN)",2520,1.4996189790592289E-6,1,30]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.33","QUERCUS MICHAUXII (SWMP CHSTNT OAK 2-5FT CNTNR GRWN)",4359,2.593983781634595E-6,3,20.95673076923077]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.35","QUERCUS NIGRA (WATER OAK 2-5FT CNTNR GRWN)",684,4.0703943717321929E-7,1,36]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.37","QUERCUS PALUSTRIS (PIN OAK 2-5FT CNTNR GRWN)",922.86,5.4918189325976196E-7,2,25.635000000000002]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.38","QUERCUS PHELLOS (WILLOW OAK 2-5FT CNTNR GRWN)",3204,1.9066584162324483E-6,2,31.106796116504853]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.39","QUERCUS RUBRA (NORTHERN RED OAK 2-5FT CNTNR GRWN)",784.88000000000011,4.6707180328730467E-7,3,32.70333333333334]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.40","SALIX NIGRA (BLACK WILLOW 2-5FT CNTNR GRWN)",8300.56,4.9395544892142355E-6,5,34.442157676348543]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.41","SASSAFRAS ALBIDUM (SASSAFRAS 2-5FT CNTNR GRWN)",1155,6.8732536540214665E-7,1,11]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.44","ULMUS AMERICANA (AMERICAN ELM 2-5FT CNTNR GRWN)",52,3.0944518615507902E-8,1,13]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.45","CARPINUS CAROLINIANA (AMERICAN HORNBEAM 2-5FT CONTAINER GR)",3709.6499999999996,2.2075641054234398E-6,2,31.706410256410255]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.46","QUERCUS SHUMARDII (SHUMARD OAK 2-5 FT CNTNR GRWN)",2520,1.4996189790592289E-6,1,30]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.57","VIBURNUM RUFIDULUM (RUSTY BLACKHAW 2-5FT C.G.)",1430,8.5097426192646727E-7,1,65]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.62","CORNUS ALTERNIFOLIA (ALTERNATE LEAF DGWOOD 2-5FT CNTNR GRWN)",325,1.9340324134692437E-7,1,13]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.63","HAMAMELIS VIRGINIANA (AMERICAN WITCHHAZEL 2-5FT CNTNR GRWN)",2520,1.4996189790592289E-6,1,30]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-11.66","PRUNUS ANGUSTIFOLIA (CHICKASAW PLUM 2-5FT CNTNR GRWN)",585,3.4812583442446389E-7,1,13]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.01","ACER NEGUNDO (BOX ELDER SEEDLNG B.R.)",3112.16,1.8520056356622896E-6,9,6.6641541755888651]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.02","ACER RUBRUM (RED MAPLE SEEDLNG B.R.)",11957.9,7.1159895990842673E-6,11,20.978771929824561]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.03","ACER SACCHARINUM (SILVER MAPLE SEEDLNG B.R.)",116,6.9030079988440703E-8,2,9.6666666666666661]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.06","ASIMINA TRILOBA (PAWPAW SEEDLNG B.R.)",260,1.5472259307753949E-7,1,13]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.07","BETULA NIGRA (RIVER BIRCH SEEDLNG B.R.)",2166.04,1.2889820211910525E-6,3,5.1819138755980862]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.09","CARYA OVATA (SHAGBARK HICKORY SEEDLNG B.R.)",930,5.5343081370042979E-7,2,9.3939393939393945]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.11","CERCIS CANADENSIS (REDBUD SEEDLNG B.R.)",432,2.5707753926729638E-7,1,8]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.12","CORNUS FLORIDA (FLOWERING DOGWOOD SEEDLNG B.R.)",994,5.9151637507336255E-7,3,6.9027777777777777]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.14","DIOSPYROS VIRGINIANA (PERSIMMON SEEDLNG B.R.)",10880,6.474545433398576E-6,2,23.755458515283841]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.16","FRAXINUS PENNSYLVANICA (GREEN ASH SEEDLNG B.R.)",1511.5,8.9947384398731136E-7,6,8.2595628415300553]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.17","JUGLANS NIGRA (BLACK WALNUT SEEDLNG B.R.)",132,7.8551470331673906E-8,1,16.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.18","LIQUIDAMBER STYRACIFLUA (SWEETGUM SEEDLNG B.R.)",6146.79,3.6578741842426501E-6,14,11.843526011560694]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.19","LIRIODENDRON TULIPIFERA (TULIP POPLAR SEEDLNG B.R.)",12845.84,7.6443910579199228E-6,6,21.267947019867549]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.20","NYSSA AQUATICA (SWAMP TUPELO SEEDLNG B.R.)",64,3.8085561372932801E-8,1,8]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.21","NYSSA SYLVATICA (BLCKGUM SEEDLNG B.R.)",70,4.1656082751645251E-8,1,10]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.22","OSTRYA VIRGINIANA (IRONWOOD SEEDLNG B.R.)",214.76,1.2780086188204761E-7,1,16.52]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.26","PLATANUS OCCIDENTALIS (SYCAMORE SEEDLNG B.R.)",15360.9,9.1410703077106789E-6,11,13.80134770889488]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.27","POPULUS DELTOIDES (COTTONWOOD SEEDLNG B.R.)",1545.04,9.1943305849431392E-7,1,4.34]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.29","QUERCUS ALBA (WHITE OAK SEEDLNG B.R.)",81,4.8202038612618077E-8,1,3]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.31","QUERCUS FALCATA (SOUTHERN RED OAK SEEDLNG B.R.)",360,2.1423128272274701E-7,1,4]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.32","QUERCUS LYRATA (OVERCUP OAK SEEDLNG B.R.)",10800,6.4269384816824099E-6,1,24]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.33","QUERCUS MICHAUXII (SWMP CHSTNT OAK SEEDLNG B.R.)",11300,6.7244819299084476E-6,2,22.6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.35","QUERCUS NIGRA (WATER OAK SEEDLNG B.R.)",803,4.778547778510162E-7,3,7.1696428571428568]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.37","QUERCUS PALUSTRIS (PIN OAK SEEDLNG B.R.)",906,5.3914872818557994E-7,4,6.4255319148936172]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.38","QUERCUS PHELLOS (WILLOW OAK SEEDLNG B.R.)",11364,6.7625674912813803E-6,3,22.370078740157481]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.40","SALIX NIGRA (BLACK WILLOW SEEDLNG B.R.)",3315.52,1.9730225069247835E-6,13,7.5870022883295194]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.44","ULMUS AMERICANA (AMERICAN ELM SEEDLNG B.R.)",446.25,2.6555752754173848E-7,2,14.875]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.45","CARPINUS CAROLINIANA (AMERICAN HORNBEAM SEEDLING B.R.)",10899.75,6.4862983996035041E-6,2,23.850656455142232]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.46","QUERCUS SHUMARDII (SHUMARD OAK SEEDLING B.R.)",9765,5.8110235438545126E-6,2,23.817073170731707]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.51","CORNUS AMOMUM (SILKY DOGWOOD SEEDLING B.R.)",12345.04,7.3463715401767243E-6,2,15.316426799007445]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.55","CARYA LACINIOSA (SHELLBARK HICKORY SEEDLING B.R.)",142.5,8.479988274442069E-8,1,14.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.57","VIBURNUM RUFIDULUM (RUSTY BLACKHAW SDLNG B.R.)",90,5.3557820680686752E-8,1,10]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.59","PRUNUS AMERICANA (AMERICAN PLUM SEEDLING B.R.)",416,2.4755614892406321E-7,1,8]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-12.65","MALUS ANGUSTIFOLIA (SOUTHERN CRABAPPLE SEEDLING B.R.)",585,3.4812583442446389E-7,1,13]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.01","ALNUS SERRULATA (HAZEL ALDER 2-5FT CNTNR GRWN)",3743.6,2.227767305557988E-6,3,29.711111111111112]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.02","CALYCANTHUS FLORIDUS (SWEETSHRUB 2-5FT CNTNR GRWN)",1555,9.2536012398297659E-7,2,23.923076923076923]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.03","CEPHALANTHUS OCCIDENTALIS (BUTTONBUSH 2-5FT CNTNR GRWN)",1900,1.1306651032589426E-6,1,50]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.04","CORNUS AMOMUM (SILKY DOGWOOD 2-5FT CNTNR GRWN)",5709,3.3973510918448963E-6,3,39.92307692307692]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.06","HYDRANGEA QUERCIFOLIA (OAKLF HYDRANGEA 2-5FT CNTNR GRWN)",8060,4.7964003854037242E-6,3,33.583333333333336]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.07","ILEX OPACA (AMERICAN HOLLY 2-5FT CNTNR GRWN)",1909.6499999999999,1.1364076918097049E-6,2,36.031132075471696]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.08","ITEA VIRGINICA (VIRGINIA SWEETSPIRE 2-5FT CNTNR GRWN)",6360,3.7847526614351969E-6,1,30]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.09","LINDERA BENZOIN (SPICEBUSH 2-5FT CNTNR GRWN)",4100,2.4398562754535074E-6,3,30.597014925373134]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.10","SAMBUCUS CANADENSIS ( ELDERBERRY 2-5FT CNTNR GRWN)",2457,1.4621285045827483E-6,1,63]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.11","ARONIA MELANOCARPA (BLCK CHOKEBERRY 2-5FT C.G.)",614.25,3.6553212614568707E-7,1,47.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.13","VACCINIUM STAMINEUM (DEERBERRY 2-5FT C.G.)",1725,1.0265248963798294E-6,1,25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.14","CALLICARPA AMERICANA (AMRCN BEAUTYBERRY) 2-5FT C.G.",500,2.9754344822603748E-7,1,25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.15","PHYSOCARPUS OPULIFOLIUS (NINEBARK) 2-5FT C.G.",1919.25,1.1421205260156449E-6,3,24.60576923076923]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.16","CORYLUS AMERICANA (HAZELNUT) 2-5FT C.G.",1980,1.1782720549751084E-6,1,18]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.21","VACCINIUM ARBOREUM (FARKLEBERRY 2-5FT C.G.)",1980,1.1782720549751084E-6,1,18]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.23","RHODODENDRON CANESCENS (WILD AZALEA SDLNG BR)",1272,7.5695053228703938E-7,1,12]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.37","VIBURNUM NUDUM (POSSUMHAW VIBURNUM 2-5 FT CNTNR GRWN)",1155,6.8732536540214665E-7,1,11]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.52","CALYCANTHUS FLORIDUS (SWEETSHRUB SDLNG BARE ROOT)",90,5.3557820680686752E-8,1,10]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.53","CEPHALANTHUS OCCIDENTALIS (BUTTONBUSH SDLNG BARE ROOT)",1207,7.1826988401765448E-7,2,11.073394495412844]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.54","CORNUS AMOMUM (SILKY DOGWOOD SDLNG BARE ROOT)",1455,8.6585143433776916E-7,2,12.435897435897436]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.55","HAMAMELIS VIRGINIANA (WITCH HAZEL SDLNG BARE ROOT)",128,7.6171122745865602E-8,1,8]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.56","HYDRANGEA QUERCIFOLIA (OAKLF HYDRANGEA SDLNG BARE ROOT)",350,2.0828041375822625E-7,2,12.068965517241379]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.57","ILEX OPACA (AMERICAN HOLLY SDLNG BARE ROOT)",1505,8.9560577916037282E-7,2,7.5250000000000004]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.59","LINDERA BENZOIN (SPICEBUSH SDLNG BARE ROOT)",10800,6.4269384816824099E-6,1,24]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.62","ILEX VERTICILLATA (CMMN WINTERBERRY SDLNG B.R.)",300,1.7852606893562251E-7,1,25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.63","VACCINIUM STAMINEUM (DEERBERRY SDLNG B.R.)",585,3.4812583442446389E-7,1,13]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.66","CORNUS DRUMMONDII (ROUGH LEAF DOGWOOD SDLING B.R.)",99.75,5.9359917921094484E-8,1,14.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.67","RHODODENDRON CALENDULACEUM (FLAMING AZALEA SDLING B.R.)",585,3.4812583442446389E-7,1,13]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-13.72","RHUS TYPHINA (STAGHORN SUMAC SDLING B.R.)",585,3.4812583442446389E-7,1,13]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-15.04","JUNCUS EFFUSUS (SOFT RUSH)",2165.11,1.2884285903773521E-6,1,6.83]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-15.06","CASTANEA DENTATA (AMERICAN CHESTNUT)",3125,1.8596465514127343E-6,1,125]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802-50.99","PLANTING SOIL",60345,3.5910518766400463E-5,1,45]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802M02.30","CUTTINGS: SALIX NIGRA (18IN-24IN LENGTH)",576.72,3.4319851492184069E-7,1,21.36]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802M02.33","SAMBUCUS CANADENSIS (ELDERBERRY)18-24\" IN LENGTH",576.72,3.4319851492184069E-7,1,21.36]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802M13.01","ALNUS SERRULATA (HAZEL ALDER 2-5FT CNTNR GRWN)",365.96000000000004,2.1777800062560139E-7,1,26.140000000000004]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802M13.02","CALYCANTHUS FLORIDUS (SWEETSHRUB 2-5FT CNTNR GRWN)",235.26,1.4000014325931517E-7,1,26.14]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802M13.04","CORNUS AMOMUM (SILKY DOGWOOD 2-5FT CNTNR GRWN)",235.26,1.4000014325931517E-7,1,26.14]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802M13.09","LINDERA BENZOIN (SPICEBUSH 2-5FT CNTNR GRWN)",392.1,2.3333357209885862E-7,1,26.14]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802M13.60","SAMBUCUS CANADENSIS ( ELDERBERRY SDLNG BARE ROOT)",235.26,1.4000014325931517E-7,1,26.14]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"802M32.02","COMUS AMOMUM (SILKY DOGWOOD) 18-24' IN LENGTH (SILKY DOGWOOD)",576.72,3.4319851492184069E-7,1,21.36]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"803-01","SODDING (NEW SOD)",12677295.402769996,7.5440923766405552E-3,96,2.6596938522209288]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"803M01","SODDING (NEW SOD)",37677.15,2.24211782606593E-5,1,4.05]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"805-01.01","TURF REINFORCEMENT MAT (CLASS I)",161528.61974999998,9.6123565015214833E-5,13,3.2680978051520091]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"805-01.02","TURF REINFORCEMENT MAT (CLASS II)",300760.71250999998,1.7897875898229066E-4,18,3.1550279846521825]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"805-01.03","TURF REINFORCEMENT MAT (CLASS III)",235551.9645,1.4017388750749434E-4,12,3.5564854103253842]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"805-01.04","TURF REINFORCEMENT MAT (CLASS IV)",10498.21,6.2473472072021378E-6,2,3.6200724137931033]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"805-01.65","TEMPORARY MULCH",225,1.3389455170171688E-7,1,15]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"805-05.02","SOIL NAIL STABILIZATION",96000,5.7128342059399197E-5,1,40]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"805-12.01","EROSION CONTROL BLANKET (TYPE I)",603538.51500000001,3.5915786178064411E-4,28,0.87395942980970609]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"805-12.02","EROSION CONTROL BLANKET (TYPE II)",2365785.327,1.4078478479162874E-3,52,0.89650446262931138]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"805-12.03","EROSION CONTROL BLANKET (TYPE III)",610445.73999999987,3.6326826086899023E-4,13,1.4063398968362026]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"805-12.04","EROSION CONTROL BLANKET (TYPE IV)",14886.270000000002,8.8586242140476322E-6,3,1.1797646219686164]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"805-12.08","700 GRAM COIR FIBER EROSION BLANKET",89450,5.3230522887638106E-5,5,6.0073875083948955]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"805-13.03","FLEXIBLE CHANNEL LINER (CLASS III)",26563.9,1.5807828808663278E-5,1,3.1]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"805M12.01","EROSION CONTROL BLANKET (TYPE I)",3383.6400000000003,2.0135598263110994E-6,1,0.78]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"805M12.02","EROSION CONTROL BLANKET (TYPE II)",14571.960000000001,8.6715824516237789E-6,1,0.78]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"806-02.03","PROJECT MOWING",1133505.6000000001,6.7453432961504724E-4,68,2898.9913043478264]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"806-02.11","PROJECT MOWING",4200,2.4993649650987149E-6,1,3500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"806-03.01","TREE CUTTING (And Mulching)",838065.92,4.9872204735505298E-4,2,419032.96]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"806M02.03","PROJECT MOWING",44097.299999999996,2.6241725398916084E-5,1,2449.85]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"908-21.01","BEARINGS (BENT NO. 1)",228320,1.3587024019793775E-4,3,6342.2222222222226]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"908-21.02","BEARINGS (NSR BRIDGE SPANS 1 & 5 EXPANSION BEARIN G)",272000,1.618636358349644E-4,2,8500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"908-21.03","BEARINGS (NSR BRIDGE SPANS 2 - 4 FIXED BEARING)",216000,1.2853876963364819E-4,2,6750]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"908-21.04","BEARINGS (NSR BRIDGE SPANS 2 - 4 EXPANSION BEARIN G)",120000,7.1410427574249006E-5,1,5000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"908-21.05","BEARINGS (NSR BRIDGE RE-SET SPANS 1 & 5 FIXED BEA RING)",32000,1.9042780686466399E-5,1,2000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"908-21.06","BEARINGS (NSR BRIDGE RE-SET SPANS 1 & 5 EXPANSION BEARING)",32000,1.9042780686466399E-5,1,2000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"908-21.07","BEARINGS (NSR BRIDGE RE-SET SPANS 2 - 4 FIXED BEA RING)",48000,2.8564171029699598E-5,1,2000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"908-21.08","BEARINGS (NSR BRIDGE RE-SET SPANS 2 - 4 EXPANSION BEARING)",48000,2.8564171029699598E-5,1,2000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"915-01.01","6 IN CORRUGATED PIPE DRAIN SYSTEM",2736,1.6281577486928772E-6,1,18]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"915-01.02","6 IN CORRUGATED PIPE UNDERDRAIN",4439,2.641590733350761E-6,1,23]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"920-08.22","TEMPORARY SHORING",116500,6.9327623436666734E-5,2,24.1701244813278]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"920-10.04","(CITY OF CHATTANOOGA CURB INLET LEFT)",11765.32,7.0013877645655271E-6,1,2941.33]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"920-10.05","(SEE PLANS)",25000,1.4877172411301875E-5,1,25000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"920-11.04","(CITY OF CHATTANOOGA CURB INLET RIGHT)",2589.96,1.5412512583350161E-6,1,2589.96]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"920-12.04","(CITY OF CHATTANOOGA CURB INLET CENTER)",6010.26,3.5766269702700485E-6,1,3005.13]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"920-13.04","(CITY OF CHATTANOOGA CATCH BASIN STANDAR D)",9192.52,5.470348197373629E-6,1,4596.26]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"924-01.01","DECK REMOVAL AND REPAIR (SEE PLANS)",14240,8.4740374054775484E-6,1,890]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"925-01.01","RAILROAD SELECT BACKFILL",30476,1.8135868256273436E-5,1,38]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"930-08.26","LOADING TEST (SOIL NAILS)",6000,3.5705213787124498E-6,1,1500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"945-01.01","4,000 PSI STRUCTURAL CONCRETE",887040,5.2786588062884857E-4,1,660]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"945-01.02","6,000 PSI STRUCTURAL CONCRETE",187060,1.1131695485032515E-4,1,470]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"955-01.01","STEEL STRUCTURES MATERIAL",3301496,1.9646770082889396E-3,1,3301496]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"955-01.02","STEEL STRUCTURES",950000,5.6533255162947126E-4,1,950000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"955-01.03","MASONRY PLATE ANCHORS",12096,7.198171099484299E-6,1,48]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"955-02.01","FENCE",95760,5.6985521204250702E-5,1,140]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"955-02.02","WINGWALL HANDRAIL",5040,2.9992379581184578E-6,1,140]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"955-03.01","BRIDGE LATERAL SLIDE 1",160000,9.5213903432331994E-5,1,160000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"955-03.02","BRIDGE LATERAL SLIDE 2",160000,9.5213903432331994E-5,1,160000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"965-01.01","TEMPORARY BALLAST RETAINER TIMBERS",34200,2.0351971858660966E-5,1,100]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"965-01.02","CENTER DECK JOINT PLACEMENT",102600,6.1055915575982899E-5,1,300]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"970-06.17","COLUMN RETROFIT",280000,1.6662433100658099E-4,1,17500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"985-01.01","REMOVAL AND DISPOSAL OF BALLAST",119500,7.1112884126022969E-5,1,119500]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"985-02.01","PLACING BALLAST",6580,3.9156717786546535E-6,1,28]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"999-99.92","PAYMENT & PERFORMANCE BOND(ESTIMATED REIMBURSABLE COST)",216390,1.2877085352326452E-4,1,216390]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"999-99.93","ON-SITE CONSTRUCTION MANAGEMENT AND SUPPORT STAFF",3239000,1.9274864576082709E-3,1,3239000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"999-99.94","GENERAL CONDITIONS DIRECT COST",2686000,1.5984034038702734E-3,1,2686000]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"999-99.95","CM/GC FEE(5% OF COST OF WORK)",2565790,1.5268680080477695E-3,1,2565790]

{"sheet":"Average Unit Price","index":14,"n_rows":3424,"n_cols":4,"rows_kept":3424,"cut":false,"hidden":true,"merged":[]}
["Item","Item Class","Item Description","Weighted Average"]
["105-01","ENGR","CONSTRUCTION STAKES, LINES AND GRADES",120947.00376237623]
["109-10.01","NBI","TRAINEE",0.8]
["201-01","ERTH","CLEARING AND GRUBBING",420686.89757894742]
["202-01.50","ERTH","REMOVAL OF STRUCTURES AND OBSTRUCTIONS",1801.2186538461538]
["203-01","ERTH","ROAD & DRAINAGE EXCAVATION (UNCLASSIFIED)",7.5428937514003644]
["203-03","ERTH","BORROW EXCAVATION (UNCLASSIFIED)",4.6997050828246936]
["203-04","ERTH","PLACING AND SPREADING TOPSOIL",5.0034300853571887]
["203-06","ERTH","WATER",8.1152332832906868]
["203-07","ERTH","FURNISHING & SPREADING TOPSOIL",9.4974591671947515]
["204-06.01","CONC","FLOWABLE FILL (GENERAL)",153.60031720856463]
["209-02.03","EROS","8\" TEMPORARY SLOPE DRAIN",9.1975071704701339]
["209-05","EROS","SEDIMENT REMOVAL",7.886163566947781]
["209-08.02","EROS","TEMPORARY SILT FENCE (WITH BACKING)",3.7271435754021836]
["209-08.03","EROS","TEMPORARY SILT FENCE (WITHOUT BACKING)",1.571152643694318]
["209-08.07","EROS","ROCK CHECK DAM PER",277.34419864847638]
["209-08.08","EROS","ENHANCED ROCK CHECK DAM",447.85663097199335]
["209-09.04","EROS","SEDIMENT FILTER BAG(15' X 10')",722.1215068493151]
["209-09.41","EROS","CURB INLET PROTECTION (TYPE 2)",217.80707253886007]
["209-40.30","EROS","CATCH BASIN PROTECTION (TYPE A)",641.0838144329897]
["209-40.41","EROS","CATCH BASIN FILTER ASSEMBLY(TYPE 1)",501.9134158415842]
["209-40.42","EROS","CATCH BASIN FILTER ASSEMBLY(TYPE 2)",605.00091062394608]
["209-40.44","EROS","CATCH BASIN FILTER ASSEMBLY(TYPE 4)",668.34845201238397]
["303-01","BASE","MINERAL AGGREGATE, TYPE A BASE, GRADING D",21.028263373201817]
["303-01.01","BASE","GRANULAR BACKFILL (ROADWAY)",27.976884551321149]
["303-10.01","BASE","MINERAL AGGREGATE (SIZE 57)",33.555522703490062]
["307-03.01","ASPH","ASPHALT CONCRETE MIX (PG76-22) (BPMB-HM) GRADING A",75.20342903939563]
["307-03.02","ASPH","PERF. GRADE ASPH. CEMENT(PG76-22)GRADING AS",627.25412369595711]
["307-03.03","ASPH","AGGREGATE(BPMB-HM) GRADING AS",63.585739255183483]
["307-03.08","ASPH","ASPHALT CONCRETE MIX (PG76-22) (BPMB-HM) GRADING B-M2",81.528690976707821]
["402-01","ASPH","BITUMINOUS MATERIAL FOR PRIME COAT (PC)",605.61729140221973]
["403-01","ASPH","BITUMINOUS MATERIAL FOR TACK COAT (TC)",679.33300300774431]
["411-01.07","ASPH","ACS MIX (PG64-22) GRADING E SHOULDER",90.219221682175771]
["411-03.10","ASPH","ACS MIX(PG76-22) GRADING D",104.45626837094686]
["411-12.01","ASPH","SCORING SHOULDERS (CONTINUOUS) (16IN WIDTH)",1320.3283001157442]
["415-01.01","ASPH","COLD PLANING BITUMINOUS PAVEMENT",21.33804458953567]
["607-03.02","DRNG","18\" CONCRETE PIPE CULVERT (CLASS III)",64.474033168986722]
["607-05.02","DRNG","24\" CONCRETE PIPE CULVERT (CLASS III)",77.159241074766399]
["607-37.02","DRNG","18\" CORRUGATED METAL PIPE CULVERT",82.840291262135921]
["607-37.03","DRNG","24\" CORRUGATED METAL PIPE CULVERT",54.748571428571431]
["607-37.06","DRNG","42\" CORRUGATED METAL PIPE CULVERT",103]
["607-65.63","SLIP","15\" MINIMUM ID PIPE TO SLIP LINE 18\" PIPE",50]
["607-65.64","SLIP","18\" MINIMUM ID PIPE TO SLIP LINE 24\" PIPE",72.3]
["611-07.01","STDR","CLASS A CONCRETE (PIPE ENDWALLS)",986.00214540281661]
["611-07.02","STDR","STEEL BAR REINFORCEMENT (PIPE ENDWALLS)",2.0584493918331881]
["611-07.53","STDR","15IN ENDWALL (CROSS DRAIN) 6:1",1258]
["611-07.54","STDR","18IN ENDWALL (CROSS DRAIN) 3:1",1871.3086263736263]
["611-31.02","STDR","CATCH BASINS, TYPE 31, > 4' - 8' DEPTH",6957.3889781021899]
["611-38.01","STDR","CATCH BASINS, TYPE 38, 0' - 4' DEPTH",3884.6618987341772]
["611-41.01","STDR","CATCH BASINS, TYPE 41, 0' - 4' DEPTH",3735.2440000000001]
["611-41.02","STDR","CATCH BASINS, TYPE 41, > 4' - 8' DEPTH",4504.25]
["611-41.03","STDR","CATCH BASINS, TYPE 41, > 8' - 12' DEPTH",4604.4266666666672]
["611-42.01","STDR","CATCH BASINS, TYPE 42, 0' - 4' DEPTH",3482.9052403846149]
["703-01","FLAT","CEMENT CONCRETE DITCH PAVING",446.03012014838606]
["705-01.01","GAT","GUARDRAIL AT BRIDGE ENDS",68.458129370197483]
["705-02.02","GAT","SINGLE GUARDRAIL (TYPE 2)",17.292203805451464]
["705-02.03","GAT","SINGLE GUARDRAIL (TYPE 2) LONG POST",19.36291606251007]
["705-04.03","GAT","GUARDRAIL TERMINAL (TYPE 13)",633.4329230769232]
["705-04.07","GAT","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",2284.2392957746479]
["705-08.51","GAT","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",5045.7799360699864]
["706-01","GAT","GUARDRAIL REMOVED",1.9230237879041057]
["706-80.18","GAT","CABLE BARRIER TERMINAL (REMOVAL)",1256.6666666666667]
["706-80.19","GAT","CABLE BARRIER (REMOVAL)",3.4100662992757758]
["707-08.11","FNCE","HIGH-VISIBILITY CONSTRUCTION FENCE",1.8099890975696407]
["709-05.05","RIPR","MACHINED RIP-RAP (CLASS A-3)",36.172763843887488]
["709-05.06","RIPR","MACHINED RIP-RAP (CLASS A-1)",34.186605241106214]
["709-05.10","RIPR","MACHINED RIP-RAP (GROUTED)",271.64942807625653]
["710-02","DRNG","AGGREGATE UNDERDRAINS (WITH PIPE)",5.5529702045496601]
["711-01.08","BARR","MEDIAM BARRIER EMERGENCY ACCESS GATE",150000]
["711-05.71","BARR","51IN SINGLE SLOPE CONCRETE BARRIER WALL",92.339831977210324]
["711-05.78","BARR","GRADE SEPARATED SINGE SLOPE MEDIAN WALL",201.69527476373818]
["712-01","TRFT","TRAFFIC CONTROL",125912.59495145634]
["712-02.02","TRFT","INTERCONNECTED PORTABLE BARRIER RAIL",29.677028862280025]
["712-04.01","TRFT","FLEXIBLE DRUMS (CHANNELIZING)",33.448025216573299]
["712-06","TRFT","SIGNS (CONSTRUCTION)",8.0274933241946549]
["712-06.01","TRFT","VERTICAL PANELS",13.156556137289119]
["712-06.16","TRFT","SIGNS (CONSTRUCTION)(REDUCED SPEED WARNING)",837.1875]
["712-08.03","TRFT","ARROW BOARD (TYPE C)",1263.495019607843]
["712-08.10","TRFT","MOBILE MESSAGE SIGN UNIT W/ATTENUATOR",100.79626183751454]
["713-01.01","TRFP","CLASS A CONCRETE (FOUNDATION FOR SIGN SUPPORTS)",628.47508693213683]
["713-01.02","TRFP","STEEL BAR REINFORCEMENT(FOUNDATION FOR SIGN SUPPORTS)",2.9199436525264462]
["713-02.14","TRFP","FLEXIBLE DELINEATOR (WHITE)",33.076403073872093]
["713-02.15","TRFP","FLEXIBLE DELINEATOR (YELLOW)",35.001599090295308]
["713-06","TRFP","STEEL I-BEAMS & WF-BEAMS(BREAKAWAY) SIGN SUPPORT",4.4136517357595046]
["713-13.02","TRFP","FLAT SHEET ALUMINUM SIGNS (0.080\" THICK)",13.110265180137429]
["713-13.03","TRFP","FLAT SHEET ALUMINUM SIGNS (0.100\" THICK)",14.339840943279354]
["713-15","TRFP","REMOVAL OF SIGNS, POSTS AND FOOTINGS",1617.5427142857141]
["713-16.01","TRFP","CHANGEABLE MESSAGE SIGN UNIT",7189.3293898305083]
["713-30.09","TRFP","BARRIER MOUNTED SIGN SUPPORT (SEE PLANS)",422.49324324324323]
["716-01.05","PVMK","TEMPORARY RAISED PAVEMENT MARKER",9.9906537356321827]
["716-01.23","PVMK","Snwplwble Pvmt Mrkrs (Bi-Dir)(2 Color)",32.006063990860476]
["716-03.09","PVMK","PLASTIC WORD PAVEMENT MARKING (NO TRUCKS LEFT LANE)",500.71428571428572]
["716-04.14","PVMK","PLASTIC PAVEMENT MARKING (LANE REDUCTION ARROW)",333.1371171171171]
["716-05.02","PVMK","PAINTED PAVEMENT MARKING (8\" BARRIER LINE)",0.52454455537028122]
["716-08.30","PVMK","HYDROBLAST REMOVAL OF PAVEMENT MARKING (LINE)",3275.5939524838009]
["716-12.02","PVMK","ENHANCED FLATLINE THERMO  PVMT MRKNG (6IN LINE)",5153.3127980331947]
["717-01","MOBL","MOBILIZATION",648173.33213592239]
["740-06.01","BASE","GEOMEMBRANE",10.862534140838379]
["740-10.03","EROS","GEOTEXTILE (TYPE III)(EROSION CONTROL)",2.5128304237017152]
["740-11.04","EROS","TEMPORARY SEDIMENT TUBE 20IN (DESCRIPTION)",2.9525244596019262]
["740-11.05","EROS","TEMPORARY SEDIMENT TUBE 24IN (DESCRIPTION)",4.1840032195152155]
["801-01.07","LAND","TEMPORARY SEEDING (WITH MULCH)",20.898564261637411]
["801-02","LAND","SEEDING (WITHOUT MULCH)",15.439803978700127]
["801-03","LAND","WATER (SEEDING & SODDING)",11.601906553541356]
["803-01","LAND","SODDING (NEW SOD)",3.0073220035530546]
["805-12.02","LAND","EROSION CONTROL BLANKET (TYPE II)",0.87098490568611131]
["806-02.03","MOWL","PROJECT MOWING",3133.1135078534035]
["202-01","ERTH","REMOVAL OF STRUCTURES AND OBSTRUCTIONS","Check Plans"]
["209-40.33","EROS","CATCH BASIN PROTECTION (TYPE D)",250.41530503978782]
["307-01.08","ASPH","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING B-M2",81.83581558042728]
["307-02.01","ASPH","ASPHALT CONCRETE MIX (PG70-22) (BPMB-HM) GRADING A",66.729084448774699]
["307-02.08","ASPH","ASPHALT CONCRETE MIX (PG70-22) (BPMB-HM) GRADING B-M2",73.786548073645463]
["402-02","ASPH","AGGREGATE FOR COVER MATERIAL (PC)",34.448606359390411]
["411-01.10","ASPH","ACS MIX(PG64-22) GRADING D",102.56597480861728]
["411-02.10","ASPH","ACS MIX(PG70-22) GRADING D",91.69028332229972]
["607-07.02","DRNG","36\" CONCRETE PIPE CULVERT (CLASS III)",117.48569927341509]
["607-39.04","DRNG","30\" PIPE CULVERT (SIDE DRAIN)",70.00521531100479]
["611-07.03","STDR","STRUCTURAL STEEL (PIPE ENDWALLS)",5.0367577722562276]
["611-07.56","STDR","18IN ENDWALL (CROSS DRAIN) 6:1",2421.8128301886791]
["611-12.01","STDR","CATCH BASINS, TYPE 12, 0' - 4' DEPTH",3784.6562030905084]
["611-12.02","STDR","CATCH BASINS, TYPE 12, > 4' - 8' DEPTH",4250.0198579970101]
["611-12.03","STDR","CATCH BASINS, TYPE 12, > 8' - 12' DEPTH",6538.29095477387]
["611-14.02","STDR","CATCH BASINS, TYPE 14, > 4' - 8' DEPTH",7303.4684079601993]
["611-14.05","STDR","CATCH BASINS, TYPE 14, > 16' - 20' DEPTH",19078.333333333332]
["701-01.01","FLAT","CONCRETE SIDEWALK (4 \")",5.0476573380597305]
["702-03","FLAT","CONCRETE COMBINED CURB & GUTTER",339.08297919136885]
["707-01.11","FNCE","CHAIN LINK FENCE (6 FOOT)",11.006527508275312]
["707-01.12","FNCE","END & CORNER POST ASSEMBLY(CHAIN-LINK FENCE 6')",240.01935483870966]
["707-01.13","FNCE","GATE - CHAIN-LINK FENCE-6 FOOT (30' WIDTH)",1600.3500000000001]
["707-01.14","FNCE","GATE - CHAIN-LINK FENCE-6 FOOT (20' WIDTH)",1498]
["707-06.01","FNCE","REMOVAL OF FENCE (4' STOCK FENCE)",3.1626143762097483]
["712-07.03","TRFT","TEMPORARY BARRICADES (TYPE III)",16.322527064912659]
["713-15.02","TRFP","REMOVAL & RELOCATION OF SIGN & SUPPORT",203.83264462809916]
["713-16.20","TRFP","SIGNS (PARK AND RIDE - LEFT (D4-2L)",506.5671304347826]
["713-16.21","TRFP","SIGNS (PARK AND RIDE - RIGHT (D4-2R)",411.62545454545455]
["713-16.22","TRFP","SIGNS (BUS STOP NO PARKING (R7-107A)",221.98333333333332]
["713-16.23","TRFP","SIGNS (NO TRUCKS (R5-2A)",235.02083333333334]
["713-16.24","TRFP","SIGNS (HANDICAP PARKING (SP-1)",229.93333333333334]
["713-16.25","TRFP","SIGNS (STOP (R1-1)",168.38181818181818]
["714-02.02","LITE","ENCASED CONDUIT (2\" PVC, SCHEDULE 40)",18.252583333333334]
["714-03.01","LITE","DIRECT BURIAL CONDUIT (2\" PVC, SCHEDULE 40)",7.1309168091649981]
["714-05.04","LITE","PULL BOXES (TYPE C)",491.91057803468209]
["714-06.08","LITE","CABLE (2/C #6 AWG)",2.3969173459311586]
["714-06.09","LITE","CABLE (2/C #8 AWG)",1.314593726219667]
["714-06.10","LITE","CABLE (#8 COPPER, SOFT DRAWN BARE (GROUND)",1.272036620623193]
["714-06.11","LITE","CABLE (#8 AWG, THHN (GREEN)",1.1124491946409754]
["714-08.09","LITE","LIGHT STANDARDS (FOR 30' MOUNTING HEIGHT)",4609.1694029850751]
["714-09.09","LITE","LUMINAIRES (400 WATT, TYPE A (FLOOD)",1302.1339055793992]
["714-12","LITE","CONTROL CENTER",13465]
["714-25.01","LITE","ELECTRICAL CONNECTION (SEE PLANS)",3745]
["716-01.21","PVMK","Snwplwble Pvmt Mrkrs (Bi-Dir)(1 Color)",31.808669083782458]
["716-01.22","PVMK","Snwplwble Pvmt Mrkrs (Mono-Dir)(1 Color)",31.572914582301252]
["716-02.04","PVMK","PLASTIC PAVEMENT MARKING(CHANNELIZATION STRIPING)",16.555206277413998]
["716-02.05","PVMK","PLASTIC PAVEMENT MARKING (STOP LINE)",13.539830975279669]
["716-02.06","PVMK","PLASTIC PAVEMENT MARKING (TURN LANE ARROW)",165.13677986658581]
["716-02.08","PVMK","PLASTIC PAVEMENT MARKING (8\" DOTTED LINE)",2.3178878640689118]
["716-04.10","PVMK","PLASTIC PAVEMENT MARKING (HANDICAP SYMBOL)",391.28571428571428]
["716-05.01","PVMK","PAINTED PAVEMENT MARKING (4\" LINE)",1171.975756858212]
["716-08.01","PVMK","REMOVAL OF PAVEMENT MARKING (LINE)",0.73822918303680385]
["716-10.30","PVMK","TRUNCATED DOME DETECTABLE WARNING MAT",47.101020408163265]
["716-13.02","PVMK","SPRAY THERMO PVMT MRKNG (60 mil) (6IN LINE)",4288.7835082108368]
["730-02.09","TRFP","SIGNAL HEAD ASSEMBLY (130 WITH BACKPLATE)",838.07169741697408]
["730-02.17","TRFP","SIGNAL HEAD ASSEMBLY (150 A2H WITH BACKPLATE)",1284.5194270833335]
["730-02.30","TRFP","SIGNAL HEAD ASSEMBLY (140 A1 WITH BACKPLATE)",910.06645454545458]
["730-03.20","TRFP","INSTALL PULL BOX (TYPE A)",378.41142045454546]
["730-03.21","TRFP","INSTALL PULL BOX (TYPE B)",511.85512552301248]
["730-05.01","TRFP","ELECTRICAL SERVICE CONNECTION",2361.6944210526317]
["730-05.02","TRFP","SERVICE CABLE (2 CONDUCTOR, # 8 AWG)",1.6307486631016044]
["730-08.03","TRFP","SIGNAL CABLE - 7 CONDUCTOR",1.6224412211000343]
["730-08.40","TRFP","INTERCONNECT CABLE - FIBER OPTIC (6 MMFO CABLE)",2.757583756801727]
["730-09.01","TRFP","SPAN WIRE ASSEMBLY (20,753 LBS.MIN.BRK STRENGTH)",3.1483438378745272]
["730-10.01","TRFP","TETHER WIRE ASSEMBLY - 1/4\" DIAMETER",2.2823568644434822]
["730-12.01","TRFP","CONDUIT 1\" DIAMETER (PVC)",6.3259023625134789]
["730-12.02","TRFP","CONDUIT 2\" DIAMETER (PVC)",7.207751344104409]
["730-13.03","TRFP","VEHICLE DETECTOR (4 - CHANNEL, RACK MOUNT)",319.09296875000001]
["730-14.01","TRFP","SHIELDED DETECTOR CABLE",1.0749192428560987]
["730-14.02","TRFP","SAW SLOT",4.0061769794235644]
["730-14.03","TRFP","LOOP WIRE",0.65974321323164131]
["730-15.11","TRFP","MODIFY CABINET (INSTALL FIBER OPTIC INTERCONNECT)",7743.4285714285716]
["730-15.32","TRFP","CABINET (EIGHT PHASE BASE MOUNTED)",13715.871011235955]
["730-16.02","TRFP","EIGHT PHASE ACTUATED CONTROLLER",4262.9716483516486]
["730-23.01","TRFP","STEEL STRAIN POLE (SIGNAL SUPPORT)",13999.480909090909]
["730-35.06","TRFP","BATTERY BACK-UP AND POWER CONDITIONER",8269.0081395348843]
["740-11.01","EROS","TEMPORARY SEDIMENT TUBE 8IN (DESCRIPTION)",3.2615240588326642]
["105M01","ENGR","CONSTRUCTION STAKES, LINES AND GRADES",300000]
["109M10.01","NBI","TRAINEE",0.8]
["201M01","ERTH","CLEARING AND GRUBBING",1435000]
["202M01","ERTH","REMOVAL OF STRUCTURES AND OBSTRUCTIONS",69634.62]
["203M01","ERTH","ROAD & DRAINAGE EXCAVATION (UNCLASSIFIED)",8.35]
["203M02.01","ERTH","BORROW EXCAVATION (GRADED SOLID ROCK)",27.370000000000005]
["203M03","ERTH","BORROW EXCAVATION (UNCLASSIFIED)",6.75]
["203M06","ERTH","WATER",0.53]
["203M07","ERTH","FURNISHING & SPREADING TOPSOIL",10.640000000000002]
["203M40.10","MISC","TIE-BACK ANCHORS (SOIL)",167.89]
["203M40.11","MISC","TIE-BACK ANCHORS (ROCK)",167.89]
["203M40.13","MISC","SUPPLEMENTAL WALERS",2065.67]
["203M40.20","ERTH","SOIL ANCHOR PULLOUT TEST",12875]
["203M40.21","ERTH","ROCK ANCHOR PULLOUT TEST",12875]
["204M02.01","STBR","DRY EXCAVATION (BRIDGES)",24.02]
["204M06.02","CONC","FLOWABLE FILL (EXCAVATABLE)",271.05]
["204M08","BASE","FOUNDATION FILL MATERIAL",76.44]
["204M08.01","BASE","BACKFILL MATERIAL (FLOWABLE FILL)",224.3]
["204M14","STBR","CORE DRILLING FOR PILES(ROCK)",1364.75]
["204M15","STBR","CORE DRILLING FOR PILES(SOIL)",139.05000000000001]
["209M02.05","EROS","300mm TEMPORARY SLOPE DRAIN",35.76]
["209M02.07","EROS","450mm TEMPORARY SLOPE DRAIN",89.28]
["209M03.22","EROS","FILTER SOCK (450mm)",32.94]
["209M03.23","EROS","Filter Sock (24 inch)",33.36]
["209M05","EROS","SEDIMENT REMOVAL",3.92]
["209M05.01","EROS","SEDIMENT REMOVAL (CULVERTS)",61.77]
["209M08.02","EROS","TEMPORARY SILT FENCE (WITH BACKING)",11.48]
["209M08.03","EROS","TEMPORARY SILT FENCE (WITHOUT BACKING)",4.59]
["209M08.07","EROS","Rock Check Dam",203.66]
["209M08.08","EROS","Enhanced Rock Check Dam",298.33999999999997]
["209M08.09","EROS","FILTER SOCK CHECK DAM",300.36]
["209M09.01","EROS","SANDBAGS",2.61]
["209M09.04","EROS","SEDIMENT FILTER BAG (450mm X 300mm)",657.27]
["209M09.43","EROS","CURB INLET PROTECTION (TYPE 4)",100.12]
["209M10.20","EROS","TEMPORARY SEDIMENT TRAP",117.56000000000002]
["209M20.03","EROS","POLYETHYLENE SHEETING (6 MIL. MINIMUM)",2.98]
["209M40.33","EROS","Catch Basin Filter Assembly (Type D)",226.71]
["209M40.41","EROS","CATCH BASIN FILTER ASSEMBLY(TYPE 1)",440.61999999999995]
["209M40.42","EROS","CATCH BASIN FILTER ASSEMBLY(TYPE 2)",530.65]
["209M40.43","EROS","CATCH BASIN FILTER ASSEMBLY(TYPE 3)",720.91]
["209M40.44","EROS","CATCH BASIN FILTER ASSEMBLY(TYPE 4)",1061.29]
["209M40.45","EROS","CATCH BASIN FILTER ASSEMBLY(TYPE 5)",1201.44]
["209M40.46","EROS","CATCH BASIN FILTER ASSEMBLY(TYPE 6)",390.5]
["209M40.47","EROS","CATCH BASIN FILTER ASSEMBLY(TYPE 7)",851.08000000000015]
["209M40.48","EROS","CATCH BASIN FILTER ASSEMBLY(TYPE 8)",1131.3699999999999]
["209M65.01","EROS","TEMPORARY STREAM DIVERSION (STR-2)",73349.119999999995]
["209M65.02","EROS","TEMPORARY STREAM DIVERSION (DESCRIPTION)",54694.22]
["209M65.03","EROS","TEMPORARY DIVERSION CHANNEL",642.70000000000005]
["303M01","BASE","MINERAL AGGREGATE, TYPE A BASE, GRADING D",26.58]
["303M01.01","BASE","GRANULAR BACKFILL (ROADWAY)",38.950000000000003]
["303M01.02","BASE","GRANULAR BACKFILL (BRIDGES)",62.440000000000005]
["303M01.03","BASE","GRANULAR BACKFILL (RETAINING WALLS)",42.286718192627831]
["303M10.01","BASE","MINERAL AGGREGATE (SIZE 57)",37.619999999999997]
["303M10.02","BASE","MINERAL AGGREGATE (SIZE 2)",41.34]
["307M01.01","ASPH","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING A",74.92]
["307M01.08","ASPH","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING B-M2",82.090000000000018]
["307M01.15","ASPH","ASC MIX (PG64-22) (BPMLC-HM) GRADING CS",147.36000000000001]
["307M02.01","ASPH","ASPHALT CONCRETE MIX (PG70-22) (BPMB-HM) GRADING A",67.02]
["307M02.02","ASPH","ASPHALT CEMENT (PG70-22) (BPMB-HM) GRADING A-S",707.28]
["307M02.03","ASPH","AGGREGATE (BPMB-HM) GRADING A-S",49.31]
["307M02.08","ASPH","ASPHALT CONCRETE MIX (PG70-22) (BPMB-HM) GRADING B-M2",76.11]
["402M01","ASPH","BITUMINOUS MATERIAL FOR PRIME COAT (PC)",454.15]
["402M02","ASPH","AGGREGATE FOR COVER MATERIAL (PC)",17.03]
["403M01","ASPH","BITUMINOUS MATERIAL FOR TACK COAT (TC)",700.4]
["411M01.07","ASPH","ASPHALT CONCRETE MIX (PG64-22) (ACS) GRADING E (SHOULDER)",111.91000000000001]
["411M01.10","ASPH","ACS MIX(PG64-22) GRADING D",108.28000000000002]
["411M02.10","ASPH","ACS MIX(PG70-22) GRADING D",101.97]
["411M12.01","ASPH","SCORING SHOULDERS (CONT 16IN WIDTH)",5000]
["415M01.02","ASPH","COLD PLANING BITUMINOUS PAVEMENT",1.82]
["602M04.01","STBR","STEEL STRUCTURES (BRIDGE NO. 1)",1331154.6000000001]
["604M01.01","STDR","CLASS A CONCRETE (ROADWAY)",689.95]
["604M01.02","STDR","STEEL BAR REINFORCEMENT (ROADWAY)",1.44]
["604M02.01","STBR","CLASS A CONCRETE (BOX BRIDGES)",878.17]
["604M02.02","STBR","STEEL BAR REINFORCEMENT (BOX BRIDGES)",1.44]
["604M02.03","STBR","EPOXY COATED REINFORCING STEEL",1.75]
["604M03.01","STBR","CLASS A CONCRETE (BRIDGES)",792.82999999999993]
["604M03.02","STBR","STEEL BAR REINFORCEMENT (BRIDGES)",1.44]
["604M03.04","STBR","PAVEMENT @ BRIDGE ENDS",275.98]
["604M03.09","STBR","CLASS D CONCRETE (BRIDGE DECK)",777.95]
["604M04.01","STBR","APPLIED TEXTURE FINISH (NEW STRUCTURES)",8.93]
["604M05.31","STBR","BRIDGE DECK GROOVING (MECHANICAL)",3.25]
["604M07.01","WALL","RETAINING WALL (WALL NO. 1)",625.61]
["604M07.02","WALL","RETAINING WALL (WALL NO. 2)",837.1]
["604M07.03","WALL","RETAINING WALL (WALL NO. 3)",968.17]
["604M07.04","WALL","RETAINING WALL (WALL NO. 4)",1123.56]
["604M07.05","WALL","RETAINING WALL (WALL NO. 5)",1335.22]
["604M07.06","WALL","RETAINING WALL (WALL NO. 6)",1192.43]
["604M07.07","WALL","RETAINING WALL (WALL NO. 7)",617.65]
["604M07.08","WALL","RETAINING WALL (WALL NO. 8)",419.85000000000008]
["604M07.09","WALL","RETAINING WALL (WALL NO. 9)",1845.4500000000003]
["604M07.10","WALL","RETAINING WALL (WALL NO. 10)",1411.36]
["604M36","STBR","SCARIFYING",29.79]
["606M02.03","STBR","STEEL PILES (250mm)",259.58999999999997]
["606M02.06","STBR","PILE TIPS (STEEL PILES, 250mm)",146.65]
["606M02.31","STBR","WOOD LAGGING (SEE PLANS)",75.099999999999994]
["606M04.03","STBR","STEEL PILES (350mm)",306.32]
["607M03.02","DRNG","450mm CONCRETE PIPE CULVERT (CLASS III)",183.66]
["607M03.03","DRNG","450mm CONCRETE PIPE CULVERT (CLASS IV)",197.1]
["607M03.04","DRNG","450mm CONCRETE PIPE CULVERT (CLASS V)",233.15]
["607M05.02","DRNG","600mm CONCRETE PIPE CULVERT (CLASS III)",227.75]
["607M05.03","DRNG","600mm CONCRETE PIPE CULVERT (CLASS IV)",237.34]
["607M06.02","DRNG","750mm CONCRETE PIPE CULVERT (CLASS III)",304.39]
["607M07.02","DRNG","900mm CONCRETE PIPE CULVERT (CLASS III)",359.43]
["607M07.04","DRNG","900mm CONCRETE PIPE CULVERT (CLASS V)",410.08]
["607M09.02","DRNG","1200mm CONCRETE PIPE CULVERT (CLASS III)",558.04999999999995]
["607M09.03","DRNG","1200mm CONCRETE PIPE CULVERT (CLASS IV)",550.54]
["607M09.04","DRNG","1200mm CONCRETE PIPE CULVERT (CLASS V)",609.23]
["607M11.03","DRNG","1500mm CONCRETE PIPE CULVERT (CLASS III)",1015.1]
["607M11.04","DRNG","1500mm CONCRETE PIPE CULVERT (CLASS IV)",802.86]
["607M13.03","DRNG","1800mm CONCRETE PIPE CULVERT (CLASS III)",1061.24]
["607M13.04","DRNG","1800mm CONCRETE PIPE CULVERT (CLASS IV)",1104.01]
["607M13.05","DRNG","1800mm CONCRETE PIPE CULVERT (CLASS V)",1327.96]
["607M38.02","DRNG","450mm CORRUGATED METAL PIPE CULVERT (PRECOATED)",241.09999999999997]
["607M39.02","DRNG","450mm PIPE CULVERT (SIDE DRAIN)",112.48]
["607M39.03","DRNG","600mm PIPE CULVERT (SIDE DRAIN)",157.04]
["610M07.03","DRNG","450mm PIPE DRAIN (BRIDGE DRAIN)",65.400000000000006]
["611M01.04","STDR","MANHOLES, > 3m - 5m DEPTH",26303.81]
["611M01.06","STDR","MANHOLES, > 6m - 7m DEPTH",35589.72]
["611M01.07","STDR","MANHOLES, > 7m - 8m DEPTH",41067.65]
["611M01.10","STDR","MANHOLES, ( > 8m - 9m DEPTH)",45328.26]
["611M01.11","STDR","MANHOLES, ( > 11m - 12m DEPTH)",58266.12]
["611M02.01","STDR","SPRING DRAIN BOX, TYPE 1",4024.57]
["611M02.10","STDR","JUNCTION BOX, TYPE 1",4024.6]
["611M02.11","STDR","JUNCTION BOX, TYPE 2",6013.5]
["611M02.12","STDR","JUNCTION BOX, TYPE 3",8234.91]
["611M07.03","STDR","STRUCTURAL STEEL (PIPE ENDWALLS)",10]
["611M07.57","STDR","24IN ENDWALL (CROSS DRAIN) 3:1",2393.61]
["611M07.58","STDR","600mm ENDWALL (CROSS DRAIN) 4:1",2809.84]
["611M12.02","STDR","CATCH BASINS, TYPE 12, > 1m - 2m DEPTH",2801.52]
["611M12.03","STDR","CATCH BASINS, TYPE 12, > 2m - 3m DEPTH",3644.78]
["611M14.02","STDR","CATCH BASINS, TYPE 14, > 1m - 2m DEPTH",5807.13]
["611M14.03","STDR","CATCH BASINS, TYPE 14, > 2m - 3m DEPTH",7908.87]
["611M16.03","STDR","CATCH BASINS, TYPE 16, > 2m - 3m DEPTH",9895.09]
["611M25.02","STDR","CATCH BASINS, TYPE 25, > 1m - 2m DEPTH",3219.55]
["611M25.03","STDR","CATCH BASINS, TYPE 25, > 2m - 3m DEPTH",4062.81]
["611M25.04","STDR","CATCH BASINS, TYPE 25, > 3m - 4m DEPTH",5059.71]
["611M26.02","STDR","CATCH BASINS, TYPE 26, > 1m - 2m DEPTH",6390.81]
["611M26.03","STDR","CATCH BASINS, TYPE 26, > 2m - 3m DEPTH",8138.03]
["611M41.02","STDR","CATCH BASINS, TYPE 41, > 1m - 2m DEPTH",4388.6400000000003]
["611M41.03","STDR","CATCH BASINS, TYPE 41, > 2m - 3m DEPTH",5460.74]
["611M42.02","STDR","CATCH BASINS, TYPE 42, > 1m - 2m DEPTH",4195.2]
["611M42.03","STDR","CATCH BASINS, TYPE 42, > 2m - 3m DEPTH",5267.3]
["611M42.05","STDR","CATCH BASINS, TYPE 42, > 4m - 5m DEPTH",7029.13]
["611M42.06","STDR","CATCH BASINS, TYPE 42, > 5m - 6m DEPTH",8713.51]
["611M42.08","STDR","CATCH BASINS, TYPE 42, > 7m - 8m DEPTH",11087.63]
["611M43.02","STDR","CATCH BASINS, TYPE 43, > 1m - 2m DEPTH",8842.2099999999991]
["611M43.03","STDR","CATCH BASINS, TYPE 43, > 2m - 3m DEPTH",11587.65]
["611M44.02","STDR","CATCH BASINS, TYPE 44, > 1m - 2m DEPTH",17751.919999999998]
["611M44.03","STDR","CATCH BASINS, TYPE 44, > 2m - 3m DEPTH",21786.25]
["611M44.07","STDR","CATCH BASINS, TYPE 44, > 6m - 7m DEPTH",40917.89]
["611M44.09","STDR","CATCH BASINS, TYPE 44, > 8m - 9m DEPTH",50876.79]
["611M45.02","STDR","CATCH BASINS, TYPE 45, > 1m - 2m DEPTH",9993.7999999999993]
["611M45.03","STDR","CATCH BASINS, TYPE 45, > 2m - 3m DEPTH",11592.16]
["615M01.11","STBR","PRESTRESSED CONCRETE BULB TEE BEAM (150mm WEB)(BT-63)",755.24000000000012]
["620M05","BARR","CONCRETE PARAPET WITH STRUCTURAL TUBING",519.29]
["621M03.02","DRNG","450mm TEMPORARY DRAINAGE PIPE",112.48]
["621M03.03","DRNG","600mm TEMPORARY DRAINAGE PIPE",157.04]
["621M03.04","DRNG","750mm TEMPORARY DRAINAGE PIPE",214.39]
["621M05.01","ERTH","TEMPORARY SHORING",50]
["624M01.01","ERTH","LOAD CELLS",1648]
["624M03.01","WALL","RETAINING WALL REINFORCING STEEL",1.44]
["625M01.07","MISC","PIEZOMETER",250]
["625M01.08","ERTH","INCLINOMETER",250]
["625M02.40","STBR","DRILLED SHAFT CONCRETE",307.83999999999997]
["630M01.06","NONR","CONCRETE BOLLARD/GUARD POST",500]
["701M01.01","FLAT","CONCRETE SIDEWALK (100mm)",43.58]
["701M02","FLAT","CONCRETE DRIVEWAY",76.64]
["701M02.03","FLAT","CONCRETE HANDICAP RAMP",278.60000000000002]
["701M03","FLAT","CONCRETE MEDIAN PAVEMENT",318.04000000000002]
["702M01","FLAT","CONCRETE CURB",379.47]
["702M03","FLAT","CONCRETE COMBINED CURB & GUTTER",344.86999999999995]
["703M01","FLAT","CEMENT CONCRETE DITCH PAVING",431.66]
["705M01.01","GAT","GUARDRAIL AT BRIDGE ENDS",226.35]
["705M02.02","GAT","SINGLE GUARDRAIL (TYPE 2)",51.5]
["705M02.03","GAT","SINGLE GUARDRAIL (TYPE 2) LONG POST",74.319999999999993]
["705M03.04","GAT","MEDIAN DIVIDER GUARDRAIL AT CONCRETE BARRIER",74.319999999999993]
["705M04.03","GAT","GUARDRAIL TERMINAL (TYPE 13)",566.5]
["705M04.04","GAT","GUARDRAIL TERMINAL (TYPE 21)",1931.25]
["705M04.05","GAT","GUARDRAIL TERMINAL (TYPE-IN-LINE)",566.5]
["705M04.07","GAT","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",2034.25]
["705M07.11","GAT","TRUCK MOUNTED ENERGY ATTENUATOR",20000]
["705M08.13","GAT","PERMANENT IMPACT ATTENUATOR NCHRP 350 TL-3",17304]
["705M08.51","GAT","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",7673.5]
["706M01","GAT","GUARDRAIL REMOVED",1.03]
["707M01.11","FNCE","CHAIN LINK FENCE (1.8m)",35.479999999999997]
["707M01.12","FNCE","END & CORNER POST ASSEMBLY(CHAIN-LINK FENCE 1.8m)",180.25]
["707M06.01","FNCE","REMOVAL OF FENCE (WOVEN WIRE)",20.6]
["708M02.01","MISC","MARKERS (CONCRETE R.O.W. POSTS)",268.47000000000003]
["709M04","STBR","REINFORCED CONCRETE SLOPE PAVEMENT",474.64000000000004]
["709M05.05","RIPR","MACHINED RIP-RAP (CLASS A-3)",40.4]
["709M05.06","RIPR","MACHINED RIP-RAP (CLASS A-1)",40.4]
["709M05.08","RIPR","MACHINED RIP-RAP (CLASS B)",48.84]
["709M05.09","RIPR","MACHINED RIP-RAP (CLASS C)",48.839999999999996]
["710M02","DRNG","AGGREGATE UNDERDRAINS (WITH PIPE)",18.579999999999998]
["710M05","DRNG","LATERAL UNDERDRAIN",10.14]
["710M06.15","DRNG","LATERAL UNDERDRAIN ENDWALL (6:1)",515]
["710M09.01","DRNG","150mm PERFORATED PIPE WITH VERTICAL DRAIN SYSTEM",70.09]
["710M09.02","DRNG","150mm PIPE UNDERDRAIN",87.29]
["711M01.05","BARR","CONCRETE BARRIER WALL (MODIFIED)",558.71]
["711M02.04","BARR","REINFORCED CONCRETE MEDIAN BARRIER (1300 mm)",380.46]
["711M05.70","BARR","SINGLE SLOPE MEDIAN BARRIER WALL",192.34]
["711M05.72","BARR","SINGLE SLOPE HALF CONCRETE BARRIER WALL (0.85 m)",184.82445953286259]
["711M05.75","BARR","SINGLE SLOPE CONCRETE BARRIER WALL",272.33999999999997]
["711M05.77","BARR","FLARED S/S CONCRETE MEDIAN BARRIER WALL",369.66]
["712M01","TRFT","TRAFFIC CONTROL",366924.57]
["712M02.02","TRFT","INTERCONNECTED PORTABLE BARRIER RAIL",54.2]
["712M04.01","TRFT","FLEXIBLE DRUMS (CHANNELIZING)",47.38]
["712M04.50","TRFT","PORTABLE BARRIER RAIL DELINEATOR",12.62]
["712M05.01","TRFT","WARNING LIGHTS (TYPE A)",53.559999999999995]
["712M05.03","TRFT","WARNING LIGHTS (TYPE C)",53.56]
["712M06","TRFT","SIGNS (CONSTRUCTION)",92.7]
["712M06.16","TRFT","SIGNS (CONSTRUCTION)(REDUCED SPEED WARNING)",1210.25]
["712M07.03","TRFT","TEMPORARY BARRICADES (TYPE III)",50.73]
["712M08.03","TRFT","ARROW BOARD (TYPE C)",1390.5]
["712M08.06","TRFT","UNIFORMED POLICE OFFICER",41.2]
["712M08.10","TRFT","MOBILE MESSAGE SIGN UNIT W/ATTENUATOR",87.55]
["712M09.01","TRFT","REMOVABLE PAVEMENT MARKING LINE",5.92]
["712M09.02","TRFT","REMOVABLE PAVEMENT MARKING (200mm BARRIER LINE)",9.5299999999999994]
["712M12.10","TRFT","TEMP CURB W/FLEXIBLE DELINEATORS",142.13999999999999]
["713M01.01","TRFP","CLASS A CONCRETE (FOUNDATION FOR SIGN SUPPORTS)",721]
["713M01.02","TRFP","STEEL BAR REINFORCEMENT(FOUNDATION FOR SIGN SUPPORTS)",5.14]
["713M09.01","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 22m)",44345.62]
["713M09.02","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 17.7m)",40658.22]
["713M09.03","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 19.8m)",44541.32]
["713M09.04","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 13.9m)",42089.919999999998]
["713M09.05","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 17.5m)",46181.08]
["713M09.06","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 14.7m)",42945.85]
["713M09.07","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 15.9m)",40526.379999999997]
["713M11.01","TRFP","\"U\" SECTION STEEL POSTS",9.01]
["713M11.02","TRFP","PERFORATED/KNOCKOUT SQUARE TUBE POST",10.29]
["713M11.05","TRFP","SQUARE TUBE SIGN SUPPORT",5922.58]
["713M13.02","TRFP","FLAT SHEET ALUMINUM SIGNS (2.032mm THICK)",114.75]
["713M13.03","TRFP","FLAT SHEET ALUMINUM SIGNS (2.540mm THICK)",126.39000000000001]
["713M14","TRFP","EXTRUDED ALUMINUM PANEL SIGNS",284.94]
["713M15","TRFP","REMOVAL OF SIGNS, POSTS AND FOOTINGS",1339]
["713M16.04","TRFT","CHANGEABLE MESSAGE SIGN UNIT  (DESCRIPT)",8755]
["713M17.02","TRFP","INSTALL AUXILIARY SUPPORT FOR EXIT NUMBER PANEL",141.11000000000001]
["713M30.09","TRFP","BARRIER MOUNTED SIGN SUPPORT",517.05999999999995]
["714M01","LITE","STRUCTURAL LIGHTING",42352.57]
["714M02.01","LITE","ENCASED CONDUIT (50mm PVC, SCHEDULE 80)",43.26]
["714M03.01","LITE","DIRECT BURIAL CONDUIT (50mm PVC, SCHEDULE 40)",19.57]
["714M05.03","LITE","PULL BOXES (TYPE B)",729.24000000000012]
["714M05.05","LITE","PULL BOXES (JUNCTION BOX IN WALL)",647.87]
["714M06.05","LITE","CABLE (1/C # 6 AWG)",3.09]
["714M08.01","LITE","LIGHT STANDARDS (13.5m M.H., 4.5m ARM)",4017]
["714M08.04","LITE","LIGHT STANDARDS (13.5m M.H., 2 - 4.5m ARMS)",4429]
["714M08.08","LITE","LIGHT STANDARDS (NEW MEDIAN BARRIER MOUNTED)",2832.5]
["714M08.09","LITE","LIGHT STANDARDS (13.5m M.H., 1.8m ARM)",3666.8]
["714M08.10","LITE","LIGHT STANDARDS (13.5m M.H., 3.1m ARM)",4037.6]
["714M08.32","LITE","REMOVAL OF LIGHT STANDARD & FOUNDATION",333.72]
["714M09.09","LITE","LUMINAIRES (TYPE A - LED)",886.83000000000015]
["714M09.10","LITE","LUMINAIRES (TYPE B - LED)",886.83]
["714M09.11","LITE","LUMINAIRES (TYPE C - LED)",776.62]
["714M10.01","LITE","OVERHEAD CONDUCTORS (GAUGE & TYPE) (#2 TRIPLEX)",12.98]
["714M12.01","LITE","CONTROL CENTER (NO. 1)",13390]
["714M12.02","LITE","CONTROL CENTER (NO. 2)",13390]
["714M12.03","LITE","CONTROL CENTER (NO. 3)",13390]
["714M12.04","LITE","CONTROL CENTER (NO. 4)",13390]
["714M25","LITE","ELECTRICAL CONNECTION",3957.26]
["716M01.05","PVMK","TEMPORARY RAISED PAVEMENT MARKER",6.95]
["716M01.21","PVMK","SNWPLWBLE PVMT MRKRS (BI-DIR)(1 COLOR)",24.72]
["716M01.22","PVMK","SNWPLWBLE PVMT MRKRS (MONO-DIR)(1 COLOR)",24.72]
["716M02.01","PVMK","PLASTIC PAVEMENT MARKING (100mm LINE)",1442]
["716M02.02","PVMK","PLASTIC PAVEMENT MARKING (200mm BARRIER LINE)",4.22]
["716M02.03","PVMK","PLASTIC PAVEMENT MARKING (CROSS-WALK)",22.81]
["716M02.04","PVMK","PLASTIC PAVEMENT MARKING(CHANNELIZATION STRIPING)",17.25]
["716M02.05","PVMK","PLASTIC PAVEMENT MARKING (STOP LINE)",31.16]
["716M02.06","PVMK","PLASTIC PAVEMENT MARKING (TURN LANE ARROW)",123.6]
["716M02.08","PVMK","PLASTIC PAVEMENT MARKING (200mm DOTTED LINE)",5.92]
["716M02.10","PVMK","PLASTIC PAVEMENT MARKING (150mm LINE)",2394.75]
["716M02.11","PVMK","PLASTIC PAVEMENT MARKING (150mm DOTTED LINE)",4.2699999999999996]
["716M04.01","PVMK","PLASTIC PAVEMENT MARKING (STRAIGHT-TURN ARROW)",149.35]
["716M04.05","PVMK","PLASTIC PAVEMENT MARKING (STRAIGHT ARROW)",123.59999999999998]
["716M04.06","PVMK","PLASTIC PAVEMENT MARKING (WRONG WAY ARROW)",180.25]
["716M04.12","PVMK","PLASTIC PAVEMENT MARKING (YIELD LINE)",25.34]
["716M04.14","PVMK","PLASTIC PAVEMENT MARKING (LANE REDUCTION ARROW)",231.75]
["716M12.02","PVMK","ENHNCD FLTLNE THERMO PVMT MRKNG (6IN LINE)",2497.75]
["716M13.01","PVMK","SPRAY THERMO PVMT MRKNG (60 mil)  (100 mm)",942.45000000000016]
["716M13.02","PVMK","SPRAY THERMO PVMT MRKNG (60 mil) (200mm LINE)",1467.75]
["717M01","MOBL","MOBILIZATION",3100000]
["722M01.02","MISC","FIELD OFFICE (TYPE 2)",81125]
["725M20.44","ITS","PULL BOX (TYPE D)",1246.3]
["725M20.45","ITS","PULL BOX (TYPE E)",1650.06]
["725M21.07","ITS","PORTABLE SMART WORK ZONE SYSTEM",422.3]
["725M22.24","ITS","CONDUIT BANK (TYPE 4)",23.18]
["725M22.34","ITS","CONDUIT BANK BORED (TYPE 4)",64.680000000000007]
["725M22.44","ITS","CONDUIT BANK IN ROCK (TYPE 4)",72.510000000000005]
["725M24.55","ITS","AS-BUILT PLANS",4158.1099999999997]
["730M11.10","TRFP","RISER ASSEMBLY (STREET LIGHTING)",589.16]
["740M06.01","BASE","GEOMEMBRANE",40.4]
["740M10.03","EROS","GEOTEXTILE (TYPE III)(EROSION CONTROL)",3.5]
["740M10.04","EROS","GEOTEXTILE (TYPE IV) STABILIZATION",3.61]
["740M11.03","EROS","TEMPORARY SEDIMENT TUBE 18IN (450mm)",9.92]
["771M10.01","UTIL","HDD 50mm PE PIPE - UNCONSOLIDATED",74.319999999999993]
["771M10.02","UTIL","HDD 100mm PE PIPE - UNCONSOLIDATED",141.88999999999999]
["771M10.03","UTIL","50 MM PE Straight Tie-In to 50 MM PE Main",824]
["771M10.04","UTIL","100 MM PE Straight Tie-In to 150 MM PE Main",1030]
["771M10.05","UTIL","200 MM PE Straight Tie-In to 150 MM PE Main",2575]
["771M10.06","UTIL","50 MM PE Straight Tie-In to 50 MM STL Main",3090]
["771M10.08","UTIL","50mm PE GAS VALVE ASSEMBLY",721]
["771M10.09","UTIL","50 MM PE Main on New 100 MM PE Main",1545]
["771M10.10","UTIL","100mm PE GAS VALVE ASSEMBLY",927]
["771M10.11","UTIL","100 MM PE Main on New 100 MM PE Main",2472]
["771M10.14","UTIL","50mm STOPPLES",6180]
["771M10.15","UTIL","100mm STOPPLES",7210]
["771M10.16","UTIL","15mm SERVICE ASSEMBLY",1030]
["771M10.17","UTIL","25mm SERVICE ASSEMBLY",1442]
["771M10.18","UTIL","32mm SERVICE ASSEMBLY",1493.5]
["771M10.19","UTIL","50mm SERVICE ASSEMBLY",2575]
["771M10.20","UTIL","15mm PE SERVICE PIPE",20.27]
["771M10.21","UTIL","25mm PE SERVICE PIPE",20.27]
["771M10.22","UTIL","32mm PE SERVICE PIPE",33.78]
["771M10.23","UTIL","50mm PE SERVICE PIPE",40.54]
["771M10.24","UTIL","RESTORE ASPHALT",166.3]
["771M10.25","UTIL","RESTORE CONCRETE",221.74]
["771M10.26","UTIL","RESTORE GRAVEL",66.52]
["771M10.27","UTIL","RETIRE IN PLACE 25mm SERV CUT & PLUG",412]
["771M10.28","UTIL","RET. IN PLACE 32mm SERV CUT & PLUG",412]
["771M10.29","UTIL","RETIRE IN PLACE 50mm SERV CUT & PLUG",515]
["771M10.30","UTIL","RETIRE GAS MAIN",20600]
["771M10.31","UTIL","CREEK CROSSING #5",10300]
["771M10.32","UTIL","CREEK CROSSING #6",10300]
["771M10.33","UTIL","SEEDING (WITH MULCH)",36.049999999999997]
["771M10.34","UTIL","100 MM PE STRAIGHT TIE-IN TO 100 MM PE MAIN",1030]
["771M10.35","UTIL","100 MM PE STRAIGHT TIE-IN TO 100 MM STL MAIN",4120]
["771M10.36","UTIL","100 MM PE STRAIGHT TIE-IN TO 150 MM CI/DI MAIN",5150]
["771M10.37","UTIL","50 MM X 100 MM TEE ON PE MAIN & 3 VALVES",2060]
["771M10.38","UTIL","100 MM X 100 MM TEE ON PE MAIN & 1 VALVE",927]
["771M10.39","UTIL","100 MM X 50 MM REDUCER",412]
["771M10.40","UTIL","50MM CUT/PLUG (END CAP)",824]
["771M10.41","UTIL","100MM CUT/PLUG (END CAP)",1030]
["775M01.18","UTIL","600mm STEEL CASING PIPE OPEN CUT METHOD",1182.44]
["775M01.19","UTIL","400mm DIP SLIP JOINT WATER LINE",405.41]
["775M02.01","UTIL","150mm DIP SLIP JOINT WATER LINE",152.03]
["775M02.02","UTIL","200mm DIP SLIP JOINT WATER LINE",253.38]
["775M02.03","UTIL","200mm Water Line Under Pavement",405.41]
["775M02.04","UTIL","300mm DIP SLIP JOINT WATER LINE",405.41]
["775M02.05","UTIL","50mm HDPE WATER LINE",40.54]
["775M02.06","UTIL","50mm Water Line Under Pavement",168.92]
["775M02.07","UTIL","150mm HDPE WATER LINE",152.03]
["775M02.08","UTIL","BORE/JACK 400mm STEEL CASING PIPE-UNCON.",1013.52]
["775M02.09","UTIL","CONNECT TO 50mm WATER LINE",927]
["775M02.10","UTIL","CONNECT TO 150mm WATER LINE",5150]
["775M02.11","UTIL","CONNECT TO 200mm WATER LINE",7210]
["775M02.12","UTIL","CONNECT TO 400mm WATER LINE",10300]
["775M02.13","UTIL","50mm GATE VALVE ASSEMBLY",515]
["775M02.14","UTIL","150mm GATE VALVE ASSEMBLY",1236]
["775M02.15","UTIL","200mm GATE VALVE ASSEMBLY",1751]
["775M02.16","UTIL","300mm GATE VALVE ASSEMBLY",2781]
["775M02.17","UTIL","20mm WATER SERVICE METER ASSEMBLY",927]
["775M02.18","UTIL","25mm WATER SERVICE METER ASSEMBLY",927]
["775M02.19","UTIL","40mm WATER SERVICE METER ASSEMBLY",2060]
["775M02.20","UTIL","50mm WATER SERVICE METER ASSEMBLY",3090]
["775M02.21","UTIL","100mm WATER SERVICE METER ASSEMBLY",10300]
["775M02.26","UTIL","25mm HDPE SERVICE PIPE",40.54]
["775M02.30","UTIL","25mm AUTO AIR RELEASE VALVE ASSEMBLY",2781]
["775M02.31","UTIL","50mm BLOW-OFF ASSEMBLY",3605]
["775M02.32","UTIL","FIRE HYDRANT ASSEMBLY",4120]
["775M02.33","UTIL","REMOVE FIRE HYDRANT",103]
["775M02.34","UTIL","REMOVE BLOW-OFF ASSEMBLY",3090]
["775M02.35","UTIL","DI FITTINGS",9.08]
["775M02.36","UTIL","CREEK CROSSING #7",15450]
["775M02.37","UTIL","CREEK CROSSING #8",15450]
["775M02.38","UTIL","CONCRETE ENCASEMENT",168.92]
["775M02.39","UTIL","RESTORE ASPHALT",8.31]
["775M02.40","UTIL","RESTORE CONCRETE",88.69]
["775M02.41","UTIL","RESTORE GRAVEL",22.18]
["775M02.42","UTIL","REMOVE & REPLACE ASPHALT CONC DRIVEWAY",33.26]
["775M02.43","UTIL","REMOVE & REPLACE PORTLAND CONC DW",110.87]
["775M02.44","UTIL","REMOVE & REPLACE BRICK PAVEMENT",55.43]
["775M02.45","UTIL","REMOVE & REPLACE CONCRETE CURB",101.35]
["775M02.46","UTIL","REMOVE & REPLACE ASPHALT CONCRETE CURB",33.78]
["775M02.47","UTIL","300mm STEEL CASING PIPE OPEN CUT METHOD",422.3]
["775M02.48","UTIL","400mm STEEL CASING PIPE OPEN CUT METHOD",422.3]
["775M02.49","UTIL","RECONNECT SERVICE ASSEMBLY",721]
["775M02.50","UTIL","RETIRE WATER METER ASSEMBLIES",10300]
["775M02.51","UTIL","RETIRE EXISTING MAINS",10300]
["775M02.52","UTIL","RETIRE WATER, AIR, & BLOWOFF VALVE ASSY",103]
["775M02.53","UTIL","FLOWABLE FILL",161.66999999999999]
["775M02.54","UTIL","SEEDING (WITH MULCH)",30.9]
["775M02.55","UTIL","300MM WATER LINE UNDER PAVEMENT",405.41]
["775M02.56","UTIL","CONNECT TO 100MM WATER LINE",3605]
["775M02.57","UTIL","CONNECT TO 300MM WATER LINE",7210]
["775M02.58","UTIL","150MM FIRE CONNECTION",5150]
["775M02.59","UTIL","200MM FIRE CONNECTION",5150]
["775M02.60","UTIL","50MM HDPE SERVICE PIPE",47.3]
["775M02.61","UTIL","100MM DUCTILE IRON SERVICE PIPE",118.24]
["775M02.62","UTIL","20MM COPPER SERVICE PIPE",67.569999999999993]
["775M02.63","UTIL","RESTRAINED JOINT GASKET FOR 200MM PIPE",103]
["775M02.64","UTIL","RESTRAINED JOINT GASKET FOR 300MM PIPE",154.5]
["775M02.65","UTIL","100MM STEEL CASING PIPE OPEN CUT METHOD",257.5]
["777M02.01","UTIL","250mm PVC FORCE MAIN",229.52]
["777M02.02","UTIL","200mm DIP GRVTY SWR 0M-1.829M DEPTH",601.89]
["777M02.03","UTIL","200mm DIP GRVTY SWR 1.829M-2.438M DEPTH",444.68]
["777M02.04","UTIL","200mm DIP GRVTY SWR 2.438M-3.048M DEPTH",304.81]
["777M02.05","UTIL","200mm DIP GRVTY SWR 3.048M-3.658M DEPTH",369.6]
["777M02.06","UTIL","200mm DIP GRVTY SWR 3.658M-4.267M DEPTH",390.84]
["777M02.07","UTIL","200mm DIP GRVTY SWR 4.267M-4.877M DEPTH",510.9]
["777M02.08","UTIL","200mm DIP GRVTY SWR 4.877M-5.486M DEPTH",815.05]
["777M02.09","UTIL","200mm DIP GRVTY SWR 5.486M-6.096M DEPTH",814.4]
["777M02.10","UTIL","200mm DIP GRVTY SWR >6.096M DEPTH",814.45]
["777M02.11","UTIL","FLOWABLE FILL",216.15]
["777M02.12","UTIL","BORE/JACK 400mm STEEL CASING PIPE-UNCON.",1405.47]
["777M02.13","UTIL","BORE/JACK 500mm STEEL CASING PIPE-UNCON.",1411.5]
["777M02.16","UTIL","OPEN CUT 400mm STEEL CASING PIPE",623.92999999999995]
["777M02.17","UTIL","1200mm MANHOLE 0M-1.219M DEPTH",3203.97]
["777M02.18","UTIL","1200mm MANHOLE 1.219M-1.829M DEPTH",3790.74]
["777M02.19","UTIL","1200mm MANHOLE 1.829M-2.438M DEPTH",4474.88]
["777M02.20","UTIL","1200mm MANHOLE 2.438M-3.048M DEPTH",5349.76]
["777M02.21","UTIL","1200mm MANHOLE 3.048M-3.658M DEPTH",6690.2800000000007]
["777M02.22","UTIL","1200mm MANHOLE 3.658M-4.267M DEPTH",7551.1499999999987]
["777M02.23","UTIL","1200mm MANHOLE 4.267M-4.877M DEPTH",8407.65]
["777M02.24","UTIL","1200mm MANHOLE 4.877M-5.486M DEPTH",9334.24]
["777M02.25","UTIL","1200mm MANHOLE >5.486M DEPTH",12827.41]
["777M02.26","UTIL","INSERTION VALVE (250mm)",14258.7]
["777M02.27","UTIL","MANHOLE DROP CONNECTION ASSEMBLY",4351.97]
["777M02.28","UTIL","1.219M DROP MANHOLE 3.658M-4.267M DEPTH",9277.84]
["777M02.29","UTIL","150mm PVC PIPE FOR SERVICE LATERAL",163.07]
["777M02.30","UTIL","150mm CLEAN OUT ASSEMBLY",1395.99]
["777M02.31","UTIL","CONNECT SERVICE LINES (ALL SIZES)",1304.8399999999999]
["777M02.32","UTIL","CONNECT EX. 200mm SEWER TO NEW MANHOLE",2963.43]
["777M02.33","UTIL","CONNECT TO 250mm FORCE MAIN",5332.01]
["777M02.34","UTIL","RETIREIN PLACE 1200mm MANHOLE",1174.25]
["777M02.35","UTIL","TV INSPECTION",6.41]
["777M02.36","UTIL","RESTORE ASPHALT",4.95]
["777M02.37","UTIL","RESTORE CONCRETE",132.03]
["777M02.38","UTIL","RESTORE GRAVEL",13.28]
["777M02.39","UTIL","REMOVE & REPLACE ASP CONC DW",38.58]
["777M02.40","UTIL","REMOVE & REPLACE BRICK PAVEMENT",50.61]
["777M02.41","UTIL","REMOVE AND REPLACE CONCRETE CURB",36.5]
["777M02.42","UTIL","REMOVE AND REPLACE ASPHALT CONCRETE CURB",36.5]
["777M02.43","UTIL","CREEK CROSSING #1",4979.49]
["777M02.44","UTIL","CREEK CROSSING #2",4979.49]
["777M02.45","UTIL","CREEK CROSSING #3",4979.49]
["777M02.46","UTIL","CREEK CROSSING #4",4979.49]
["777M02.47","UTIL","CONCRETE ENCASEMENT",514.27]
["777M02.48","UTIL","SEEDING (WITH MULCH)",35]
["777M02.49","UTIL","OPEN CUT 20IN STEEL CASING PIPE",848.87]
["801M01","LAND","SEEDING (WITH MULCH)",26.06]
["801M01.02","LAND","CROWN VETCH MIXTURE (WITH MULCH)",30.78]
["801M01.07","LAND","TEMPORARY SEEDING (WITH MULCH)",15]
["801M01.16","EROS","BONDED FIBER MATRIX HYDROMULCH (W/PERMANENT SEED)",51.83]
["801M01.65","LAND","TEMPORARY MULCH",11.35]
["801M02","LAND","SEEDING (WITHOUT MULCH)",15.35]
["801M02.01","LAND","CROWN VETCH MIXTURE (WITHOUT MULCH)",20.95]
["801M02.08","LAND","TEMPORARY SEEDING (WITHOUT MULCH)",5.05]
["801M03","LAND","WATER (SEEDING & SODDING)",13.6]
["801M07","LAND","SEED (SUPPLEMENTAL APPLICATION)",12.31]
["801M07.01","LAND","CROWN VETCH SEED (SUPPLEMENTAL APPLICATION)",25.03]
["801M08","LAND","FERTILIZER (SUPPLEMENTAL APPLICATION)",926.58]
["802M02.30","LAND","CUTTINGS: SALIX NIGRA (18IN-24IN LENGTH)",21.36]
["802M02.33","LAND","SAMBUCUS CANADENSIS (ELDERBERRY)18-24\" IN LENGTH",21.36]
["802M13.01","LAND","ALNUS SERRULATA (HAZEL ALDER 2-5FT CNTNR GRWN)",26.140000000000004]
["802M13.02","LAND","CALYCANTHUS FLORIDUS (SWEETSHRUB 2-5FT CNTNR GRWN)",26.14]
["802M13.04","LAND","CORNUS AMOMUM (SILKY DOGWOOD 2-5FT CNTNR GRWN)",26.14]
["802M13.09","LAND","LINDERA BENZOIN (SPICEBUSH 2-5FT CNTNR GRWN)",26.14]
["802M13.60","LAND","SAMBUCUS CANADENSIS ( ELDERBERRY SDLNG BARE ROOT)",26.14]
["802M32.02","LAND","COMUS AMOMUM (SILKY DOGWOOD) 18-24' IN LENGTH (SILKY DOGWOOD)",21.36]
["803M01","LAND","SODDING (NEW SOD)",4.05]
["805M12.01","LAND","EROSION CONTROL BLANKET (TYPE I)",0.78]
["805M12.02","LAND","EROSION CONTROL BLANKET (TYPE II)",0.78]
["806M02.03","MOWL","PROJECT MOWING",2449.85]
["202-03.02","ERTH","REMOVAL OF RIGID PAVEMENT",14.931440619621343]
["202-03.03","ERTH","REMOVAL OF ASPHALT PAVEMENT",8.2421425758172511]
["202-04.01","RMVL","REMOVAL OF STRUCTURES (BRIDGE NO. 47-I-640-2.29)",184441.01935483873]
["202-04.02","RMVL","REMOVAL OF STRUCTURES (BRIDGE NO. 47-I-640-2.41)",117546.27416666666]
["202-04.03","RMVL","REMOVAL OF STRUCTURES (BRIDGE NO. 47-SR033-10.73)",39508.41777777778]
["202-06.01","RMVL","REMOVAL OF BUILDINGS (TRACT NO. 3)",9158.3785185185188]
["202-06.02","RMVL","REMOVAL OF BUILDINGS (TRACT NO. 5)",12392.456470588237]
["202-06.03","RMVL","REMOVAL OF BUILDINGS (TRACT NO. 6)",12137.979333333331]
["202-06.04","RMVL","REMOVAL OF BUILDINGS (TRACT NO. 7)",4360.1499999999996]
["202-06.05","RMVL","REMOVAL OF BUILDINGS (TRACT NO. 8)",7193.3966666666674]
["202-06.06","RMVL","REMOVAL OF BUILDINGS (TRACT NO. 9)",3137.3571428571427]
["202-06.07","RMVL","REMOVAL OF BUILDINGS (TRACT NO. 14)",3690.5]
["202-06.08","RMVL","REMOVAL OF BUILDINGS (TRACT NO. 15)",5165.3999999999996]
["202-06.09","RMVL","REMOVAL OF BUILDINGS (TRACT NO. 18)",4545.3999999999996]
["202-06.10","RMVL","REMOVAL OF BUILDINGS (TRACT NO. 19)",7463]
["203-01.60","ERTH","ROAD & DRAINAGE EXCAVATION (ROCK)",31.45]
["203-02.01","ERTH","BORROW EXCAVATION (GRADED SOLID ROCK)",17.478507520214976]
["203-15.03","ERTH","COMPACTED CLAY",12.270689614144466]
["204-02.01","STBR","DRY EXCAVATION (BRIDGES)",24.059212652570054]
["204-04.01","STBR","ROCK EXCAVATION (BRIDGES)",17.097735241805712]
["204-05","STBR","ROCK DRILLING (BRIDGES)",35.273212121212126]
["204-08","BASE","FOUNDATION FILL MATERIAL",52.931462484411426]
["204-08.01","CONC","BACKFILL MATERIAL (FLOWABLE FILL)",217.53958468669438]
["209-09.01","EROS","SANDBAGS",3.3811025136886568]
["209-09.03","EROS","SEDIMENT FILTER BAG (15' X 15')",602.96015822784807]
["209-20.03","EROS","POLYETHYLENE SHEETING (6 MIL. MINIMUM)",2.3178266362269526]
["209-40.34","EROS","CATCH BASIN PROTECTION (TYPE E)",206.875]
["209-40.43","EROS","CATCH BASIN FILTER ASSEMBLY(TYPE 3)",612.07932584269668]
["209-40.45","EROS","CATCH BASIN FILTER ASSEMBLY(TYPE 5)",895.76893333333328]
["209-40.46","EROS","CATCH BASIN FILTER ASSEMBLY(TYPE 6)",514.16413832199544]
["209-40.47","EROS","CATCH BASIN FILTER ASSEMBLY(TYPE 7)",760.1656078431372]
["209-65.03","EROS","TEMPORARY DIVERSION CHANNEL",28.835708441222167]
["209-65.04","EROS","TEMPORARY IN STREAM DIVERSION",59.653527127355801]
["303-01.02","BASE","GRANULAR BACKFILL (BRIDGES)",32.976449346541251]
["313-03","ASPH","TREATED PERMEABLE BASE",17.938169135680756]
["403-02.02","ASPH","HOT APPLIED TACK COAT",2060]
["411-03.22","ASPH","ACS MIX (PG70-22) OGFC",131.33000000000001]
["415-01.02","ASPH","COLD PLANING BITUMINOUS PAVEMENT",3.1478692477973418]
["501-01.03","CONC","PORTLAND CEMENT CONCRETE PAVEMENT (PLAIN) 10\"",80.927766163895072]
["501-03.10","CONC","CONCRETE SHOULDER RUMBLE STRIPS",0.53]
["503-01.01","CONC","MILLING CONCRETE PAVEMENT",7.46]
["602-04.01","STBR","STEEL STRUCTURES (BRIDGE NO. 1)",3999937.9737499999]
["602-04.02","STBR","STEEL STRUCTURES (BRIDGE NO. 2)",1172001.77]
["602-04.03","STBR","STEEL STRUCTURES (BRIDGE NO. 4)",879317.21499999997]
["604-01.01","STDR","CLASS A CONCRETE (ROADWAY)",683.52854235145844]
["604-01.02","STDR","STEEL BAR REINFORCEMENT (ROADWAY)",0.87354269339963508]
["604-02.03","STBR","EPOXY COATED REINFORCING STEEL",0.98939203832616018]
["604-03.01","STBR","CLASS A CONCRETE (BRIDGES)",679.56050278116948]
["604-03.02","STBR","STEEL BAR REINFORCEMENT (BRIDGES)",1.0240456296579601]
["604-03.04","STBR","PAVEMENT @ BRIDGE ENDS",263.06136802903876]
["604-03.09","STBR","CLASS D CONCRETE (BRIDGE DECK)",589.06831298557154]
["604-04.01","STBR","APPLIED TEXTURE FINISH (NEW STRUCTURES)",7.8851278756861305]
["604-05.31","STBR","BRIDGE DECK GROOVING (MECHANICAL)",4.0239967837972923]
["604-07.01","WALL","RETAINING WALL (SEE PLANS)",96.238077192288387]
["604-07.02","WALL","RETAINING WALL (SEE PLANS)",99.334216481788189]
["604-07.03","WALL","RETAINING WALL (SEE PLANS)",93.505215013825278]
["604-07.04","WALL","RETAINING WALL (SEE PLANS)",138.5956593201345]
["604-07.05","WALL","RETAINING WALL (SEE PLANS)",102.97910635423702]
["604-07.06","WALL","RETAINING WALL (SEE PLANS)",104.63211785772424]
["604-07.07","WALL","RETAINING WALL (SEE PLANS)",84.080018544274466]
["604-07.08","WALL","RETAINING WALL (SEE PLANS)",100.05379061371841]
["604-07.09","WALL","RETAINING WALL (SEE PLANS)",85.978961523360823]
["604-07.10","WALL","RETAINING WALL (SEE PLANS)",91.253252279635262]
["604-11.01","STBR","EXPANSION DEVICE (@ ABUTMENT NOS. 1, 2, & 4)",521.22307189542482]
["606-02.03","STBR","STEEL PILES (10 INCH)",47.074855819485997]
["606-02.06","STBR","PILE TIPS (STEEL PILES, 10 INCH)",129.09802706923477]
["607-06.02","DRNG","30\" CONCRETE PIPE CULVERT (CLASS III)",104.26146494930569]
["611-01.02","STDR","MANHOLES, > 4' - 8' DEPTH",5129.3090000000002]
["611-01.03","STDR","MANHOLES, > 8' - 12' DEPTH",7284.2207692307693]
["611-07.55","STDR","18IN ENDWALL (CROSS DRAIN) 4:1",1760.6293055555554]
["611-07.58","STDR","24IN ENDWALL (CROSS DRAIN) 4:1",2622.4938181818184]
["611-07.63","STDR","36IN ENDWALL (CROSS DRAIN) 3:1",5270.5997826086959]
["611-09.02","STDR","REWORK CATCHBASIN",1483.2147619047621]
["611-25.01","STDR","CATCH BASINS, TYPE 25, 0' - 4' DEPTH",3284.4869999999996]
["611-25.02","STDR","CATCH BASINS, TYPE 25, > 4' - 8' DEPTH",4307.8277272727273]
["611-25.03","STDR","CATCH BASINS, TYPE 25, > 8' - 12' DEPTH",8142.9449999999997]
["611-41.08","STDR","CATCH BASINS, TYPE 41, >(  ' -   ' DEPTH) (SEE PLANS)",9380.91]
["611-42.02","STDR","CATCH BASINS, TYPE 42, > 4' - 8' DEPTH",4901.4130088495576]
["611-51.02","STDR","CATCH BASINS, TYPE 51, > 4' - 8' DEPTH",5301.5005714285708]
["611-51.03","STDR","CATCH BASINS, TYPE 51, > 8' - 12' DEPTH",8124.25]
["611-51.04","STDR","CATCH BASINS, TYPE 51, > 12' - 16' DEPTH",11354.87]
["611-52.02","STDR","CATCH BASINS, TYPE 52, > 4FT - 8FT DEPTH",19645.213333333333]
["611-52.03","STDR","CATCH BASINS, TYPE 52, > 8FT - 12FT DEPTH",22485.759999999998]
["615-01.11","STBR","PRESTRESSED CONCRETE BULB TEE BEAM (6\" WEB)(BT-63)",266.86310738766184]
["620-05.01","BARR","CONC PARAPET SINGLE SLOPE (STD-1-1SS)",73.958484153073258]
["621-03.02","DRNG","18\" TEMPORARY DRAINAGE PIPE",37.163725587319554]
["621-03.07","DRNG","48\" TEMPORARY DRAINAGE PIPE",88.348633712004926]
["701-02.03","FLAT","CONCRETE CURB RAMP",16.969458744467403]
["701-03","FLAT","CONCRETE MEDIAN PAVEMENT",395.35150619337725]
["702-01","FLAT","CONCRETE CURB",447.75576404619551]
["702-01.03","TRFP","MODULAR CURB W/DELINEATOR",52.460200610553862]
["705-04.04","GAT","GUARDRAIL TERMINAL (TYPE 21)",2123.1253164556961]
["705-08.10","GAT","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-2",5221.8275862068967]
["705-17.97","GAT","ATTENUATOR (NARROW- LOW MAINTENANCE)",29400]
["709-04","STBR","REINFORCED CONCRETE SLOPE PAVEMENT",484.07324571428569]
["709-05.08","RIPR","MACHINED RIP-RAP (CLASS B)",38.35878228894903]
["710-05","DRNG","LATERAL UNDERDRAIN",3.9254150612678029]
["710-06.13","DRNG","LATERAL UNDERDRAIN ENDWALL (4:1)",664.40058997050153]
["710-06.15","DRNG","LATERAL UNDERDRAIN ENDWALL (6:1)",630.07988235294113]
["710-09.01","DRNG","6\" PERFORATED PIPE WITH VERTICAL DRAIN SYSTEM",38.840228618735267]
["710-09.02","DRNG","6\" PIPE UNDERDRAIN",16.470789473684214]
["711-05.72","BARR","SINGLE SLOPE HALF CONCRETE BARRIER WALL",93.016578811034819]
["711-05.77","BARR","FLARED S/S CONCRETE MEDIAN BARRIER WALL",258.22860100376414]
["712-05.01","TRFT","WARNING LIGHTS (TYPE A)",30.841818335875271]
["712-05.03","TRFT","WARNING LIGHTS (TYPE C)",32.351314948041569]
["712-09.30","TRFT","REMOVABLE BLACK-OUT TAPE (6\")",2.6784950837207391]
["713-09.01","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 96' - 6\")",54175.275454545459]
["713-09.02","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 83' - 0\")",55351.514999999999]
["713-09.03","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 90' - 0\")",57619.445]
["713-09.04","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 60' - 0\")",52879.547500000001]
["713-09.05","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 62' - 6\")",49465.907500000001]
["713-11.01","TRFP","\"U\" SECTION STEEL POSTS",3.2681783390621968]
["713-11.02","TRFP","PERFORATED/KNOCKOUT SQUARE TUBE POST",3.7627527449390596]
["713-14","TRFP","EXTRUDED ALUMINUM PANEL SIGNS",21.95087945115975]
["713-15.11","TRFP","SIGN SUPPORT ASSEMBLY ON BRIDGES (SIGN 16)",12570]
["713-15.12","TRFP","SIGN SUPPORT ASSEMBLY ON BRIDGES (SIGN 17)",7140]
["713-17.30","TRFP","MODIFY EXISTING OVERHEAD SIGN STRUCTURE",2763.75]
["713-17.31","TRFP","MODIFY EXISTING OVERHEAD SIGN STRUCTURE",2310]
["713-17.32","TRFP","MODIFY EXISTING OVERHEAD SIGN STRUCTURE",2310]
["713-17.33","TRFP","MODIFY EXISTING OVERHEAD SIGN STRUCTURE",2677.5]
["713-17.63","TRFP","SIGN MOUNTED ON CONCRETE MEDIAN BARRIER (SIDE WALL MOUNT)",709.6]
["714-01.01","LITE","STRUCTURAL LIGHTING (BR. NO. 1)",24729.383333333335]
["714-01.02","LITE","STRUCTURAL LIGHTING (BR. NO. 2)",6768.4600000000009]
["714-01.03","LITE","STRUCTURAL LIGHTING (BR. NO. 3)",6206.5]
["714-01.04","LITE","STRUCTURAL LIGHTING (BR. NO. 4)",3675]
["714-01.20","LITE","STRUCTURAL LIGHTING (SEE PLANS)",6370]
["714-01.21","LITE","STRUCTURAL LIGHTING (SEE PLANS)",3962.5]
["714-01.22","LITE","STRUCTURAL LIGHTING (SEE PLANS)",2205]
["714-01.23","LITE","STRUCTURAL LIGHTING (SEE PLANS)",1837.5]
["714-01.24","LITE","STRUCTURAL LIGHTING (SEE PLANS)",3675]
["714-02.01","LITE","ENCASED CONDUIT (2\" PVC, SCHEDULE 80)",15.824723247232471]
["714-04.01","LITE","CONDUIT (STRUCTURES - 1\" RGS)",11.408602150537634]
["714-04.03","LITE","CONDUIT (SEE PLANS)",23.829963459196104]
["714-05.03","LITE","PULL BOXES (TYPE B)",723.11625000000004]
["714-05.05","LITE","PULL BOXES (SEE PLANS)",422.96044776119408]
["714-05.06","LITE","PULL BOXES (SEE PLANS)",573.14705882352939]
["714-05.46","LITE","WOOD POLE (DESCRIPTION)",1100.8333333333333]
["714-06.03","LITE","CABLE (1/C # 10 AWG)",0.80987008494445933]
["714-06.06","LITE","CABLE (1/C # 4 AWG)",1.7415583892810422]
["714-08.01","LITE","LIGHT STANDARDS (45' M.H., 15' ARM)",3713.6904761904761]
["714-08.10","LITE","LIGHT STANDARDS (45' M.H., BRIDGE MOUNTED)",4425.354166666667]
["714-08.32","LITE","REMOVAL OF LIGHT STANDARD & FOUNDATION",425.95153846153846]
["714-08.33","LITE","REMOVAL OF EXISTING COBRA HEAD LUMINAIRE",133.62272727272727]
["714-09.03","LITE","LUMINAIRES (250 WATT)",605.40674603174602]
["714-09.10","LITE","LUMINAIRES (157 WATT LED)",1206.6621621621621]
["714-09.11","LITE","LUMINAIRES (107 WATT LED)",629.26099999999997]
["714-09.12","LITE","LUMINAIRES (SEE PLANS)",929.53283582089557]
["714-09.13","LITE","LUMINAIRES (SEE PLANS)",1341.8671641791045]
["714-10.01","LITE","OVERHEAD CONDUCTORS (GAUGE & TYPE) (#6 DPX)",0.55424836601307192]
["714-12.01","LITE","CONTROL CENTER (NO. 1)",12920.016666666666]
["714-12.02","LITE","CONTROL CENTER (NO. 2)",14525.025]
["714-12.03","LITE","CONTROL CENTER (NO. 3)",19956.383333333335]
["714-25","LITE","ELECTRICAL CONNECTION",1365.6491228070176]
["714-25.22","LITE","INSTALL SVC RISER (SEE PLANS)",1157.8076923076924]
["716-02.03","PVMK","PLASTIC PAVEMENT MARKING (CROSS-WALK)",8.4844628274472367]
["716-02.07","PVMK","PLASTIC PAVEMENT MARKING (24\" BARRIER LINE)",13.747352692501476]
["716-02.09","PVMK","PLASTIC PAVEMENT MARKING (LONGITUDINAL CROSS-WALK)",28.794245048572936]
["716-02.11","PVMK","PLASTIC PAVEMENT MARKING (6\" DOTTED LINE)",2.2723110818908623]
["716-02.12","PVMK","PLASTIC PAVEMENT MARKING (8IN LINE)",10000.238654147104]
["716-03.01","PVMK","PLASTIC WORD PAVEMENT MARKING (ONLY)",224.51101694915252]
["716-04.01","PVMK","PLASTIC PAVEMENT MARKING (STRAIGHT-TURN ARROW)",227.7328048780488]
["716-04.03","PVMK","PLASTIC PAVEMENT MARKING (4\" DOTTED LINE)",1.7642532005689899]
["716-04.05","PVMK","PLASTIC PAVEMENT MARKING (STRAIGHT ARROW)",155.36859060402685]
["716-04.15","PVMK","PLASTIC PAVEMENT MARKING-BIKE SYMBOL/ARROW SHARED",317.99642857142857]
["716-05.04","PVMK","PAINTED PAVEMENT MARKING (CHANNELIZATION STRIPING)",9.7912152411118853]
["716-05.05","PVMK","PAINTED PAVEMENT MARKING (STOP LINE)",7.7350276980908088]
["716-05.06","PVMK","PAINTED PAVEMENT MARKING (TURN LANE ARROW)",92.016010638297871]
["716-05.07","PVMK","PAINTED PAVEMENT MARKING (24\" BARRIER LINE)",0.78666199158485273]
["716-05.09","PVMK","PAINTED PAVEMENT MARKING(STRAIGHT-TURN ARROW)",124.26558823529413]
["716-05.20","PVMK","PAINTED PAVEMENT MARKING (6\" LINE)",1237.318474598429]
["716-05.21","PVMK","PAINTED PAVEMENT MARKING(4\"DOTTED LINE)",0.59171204316899673]
["716-05.50","PVMK","PAINTED PAVEMENT MARKINGS(8\" LINE)",0.23913631633714882]
["716-12.01","PVMK","ENHANCED FLATLINE THERMO  PVMT MRKNG (4IN LINE)",4221.7167194086232]
["716-13.01","PVMK","SPRAY THERMO PVMT MRKNG (60 mil) (4IN LINE)",2582.5097063123244]
["730-01.02","TRFP","REMOVAL OF SIGNAL EQUIPMENT",1037.3602923976609]
["730-01.03","TRFP","MODIFICATION OF EXISTING TRAFFIC SIGNAL EQUIPMENT",2055.2249999999999]
["730-03.23","TRFP","INSTALL PULL BOX (FIBER OPTIC-TYPE A)",1373.0377142857144]
["730-03.24","TRFP","INSTALL PULL BOX (FIBER OPTIC-TYPE B)",1997.5526436781611]
["730-08.01","TRFP","SIGNAL CABLE - 3 CONDUCTOR",1.1131879872942534]
["730-08.02","TRFP","SIGNAL CABLE - 5 CONDUCTOR",1.4376003756750411]
["730-12.08","TRFP","CONDUIT 2\" DIAMETER (RGS)",12.454390176024491]
["730-12.30","TRFP","TRENCHING",6.7219081942336878]
["730-13.07","TRFP","VEHICLE DETECTOR (SIREN ACTIVATED PRIORITY CONTROL)",4731.8184210526315]
["730-13.08","TRFP","VEHICLE DETECTOR (RF)",8270.0519999999997]
["730-23.30","TRFP","PEDESTAL POLE (20-ft)",1797.2972432432432]
["730-23.72","TRFP","CANTILEVER SIGNAL SUPPORT (1 ARM @ 35')",12975.4375]
["730-23.80","TRFP","CANTILEVER SIGNAL SUPPORT (1 ARM @ 40')",13334.071428571429]
["730-23.96","TRFP","CANTILEVER SIGNAL SUPPORT (2 @ 50' & 45')",24009.960454545453]
["730-26.11","TRFP","COUNTDOWN PED SGNL HEAD W/AUDIBLE PUSH BUTTON & 15IN SIGN",1140.6504255319148]
["740-10.04","EROS","GEOTEXTILE (TYPE IV)(STABILIZATION)",1.4943012220519158]
["740-11.03","EROS","TEMPORARY SEDIMENT TUBE 18IN (18 IN)",3.2974636666766797]
["790-03.03","UTIL","POLE 40FT CLASS 4 WOOD",1581.1563970588238]
["790-04.03","UTIL","POLE 45FT CLASS 3 WOOD",1522.1982644628099]
["790-05.01","UTIL","POLE 50FT CLASS 1 WOOD",2742.4130555555553]
["790-05.02","UTIL","POLE 50FT CLASS 2 WOOD",2013.0770312499997]
["790-06.01","UTIL","POLE 55FT CLASS 1 WOOD",3431.7952380952379]
["790-07.05","UTIL","POLE 60FT CLASS 1 METAL",6085.4093478260857]
["790-20.01","UTIL","POLE (65FT CLASS1 DUCTILE IRON)",8775.8735064935063]
["790-21.08","UTIL","1PH DEADEND 15KV",283.94237288135588]
["790-25.07","UTIL","3PH CROSSARM DBL LRG COND 15KV",1775.1529032258065]
["790-25.12","UTIL","3PH CROSSARM DBL 10FT PRIM SUP 15KV",1893.9205128205126]
["790-25.16","UTIL","3PH VERTICAL LRG COND 15KV",1309.9659999999999]
["790-25.19","UTIL","3PH VERTICAL DEADEND 15KV",1801.8854545454544]
["790-25.21","UTIL","3PH CROSSARM DEADEND SGL 15KV",1604.9804166666665]
["790-25.24","UTIL","3PH CROSSARM DDE LRG COND 15KV",2987.0973170731709]
["790-30.04","UTIL","SECONDARY ASSEMBLIES MISC",144.95290322580644]
["790-30.06","UTIL","SECONDARY CONDUCTOR 6 AL DUPLEX",3.044870642293477]
["790-30.13","UTIL","SECONDARY CONDUCTOR 2 AL TRIPLEX",5.1549999999999994]
["790-32.01","UTIL","DOWN GUY - THROUGH BOLT TYPE",334.03211023622049]
["790-32.02","UTIL","DOWN GUY - THROUGH BOLT TYPE HEAVY DUTY",366.75604166666665]
["790-32.08","UTIL","OH GUY - THROUGH BOLT TYPE HEAVY DUTY",527.00162162162167]
["790-33.03","UTIL","SCREW TYPE ANCHOR 6,000LB-8,000LB",360.47887500000002]
["790-33.04","UTIL","SCREW TYPE ANCHOR 10,000LB-12,000LB",510.36206703910614]
["790-36.01","UTIL","SWITCH-900A-UNDERSLUNG",8068.55]
["790-36.06","UTIL","TRANSFER LIGHT",430.34602409638558]
["790-40.01","UTIL","OH COND 4 7/1 ACSR SWANATE",2.017186255782375]
["790-40.03","UTIL","OH COND 1/0 6/1 ACSR RAVEN",3.1692426754522018]
["790-40.39","UTIL","OH COND 4/0 7 AAC OXLIP",3.1125414475667341]
["790-40.49","UTIL","OH COND 795 37 AAC ARBUTUS",5.0564998627033022]
["790-46.02","UTIL","1PH TRANSFORMER CONV W/POLE MTD FUSE & LA",1352.0957352941175]
["790-52.04","UTIL","15KVA 1PH OH XFORMER 7.2KV 120/240",1305.9124999999999]
["790-60.02","UTIL","1PH FUSE CUTOUT BRKT MOUNT 15KV",550.90043478260873]
["790-68.01","UTIL","POLE GROUND ROD TYPE",309.87231057764438]
["790-68.03","UTIL","POLE GROUND WRAP TYPE",411.8609090909091]
["790-68.11","UTIL","DEAD END SHOE",346.06444444444446]
["790-69.24","UTIL","EPOXY DEAD END",1490.45]
["790-69.32","UTIL","ARM PIN",162.80934426229507]
["790-69.33","UTIL","DEADEND ASSEMBLY",915.53785714285709]
["790-98.01","UTIL","REMOVE WIRE",1.6688474934929542]
["790-98.02","UTIL","REMOVE POLES",679.88906295050458]
["790-98.03","UTIL","REMOVE FRAMING/ASSOCIATED APPARATUS",410.95686709380652]
["791-02.01","UTIL","<2IN MDPE GAS MAIN",28.607055214723925]
["791-02.02","UTIL","2IN MDPE GAS MAIN",34.464513556618819]
["791-02.04","UTIL","4IN MDPE GAS MAIN",37.969800811606504]
["791-06.02","UTIL","CONNECT TO 2IN EX. PE MAIN",1238.2528749999999]
["791-06.03","UTIL","CONNECT TO 4IN EX. PE MAIN",2191.2134408602151]
["791-06.04","UTIL","CONNECT TO 6IN EX. PE MAIN",2288.75]
["791-07.01","UTIL","2IN PE GAS VALVE ASSEMBLY",845.28703703703707]
["791-07.02","UTIL","4IN PE GAS VALVE ASSEMBLY",1198.5355223880597]
["791-07.03","UTIL","6IN PE GAS VALVE ASSEMBLY",2367.038043478261]
["791-10.10","UTIL","RETIRE GAS MAIN",8887.5]
["793-01.42","UTIL","ANCHOR 1 1/4IN",473.2972789115646]
["793-11.10","UTIL","12IN PEDESTAL",443.18333333333334]
["793-12.01","UTIL","DIG SPLICE PIT 80 C.F.",1297.9568181818181]
["793-13.07","UTIL","4IN SCHEDULE 40 PVC",7.0771041904681304]
["793-13.12","UTIL","1 DUCT FORMATION @ 36IN DEPTH",20.16940329218107]
["793-13.17","UTIL","2 DUCT FORMATION @ 36IN DEPTH",30.861720762493558]
["793-13.22","UTIL","3 DUCT FORMATION @ 36IN DEPTH",40.856398910823685]
["793-13.27","UTIL","4 DUCT FORMATION @ 36IN DEPTH",49.945033153430998]
["793-13.51","UTIL","___DUCT FORMATION @ ___IN DEPTH (SEE PLANS)",35.087077131258454]
["793-14.02","UTIL","CONCRETE ENCASEMENT PER DUCT",4.834123243479687]
["793-14.03","UTIL","MH PRECAST 6-FT W X 12-FT L X 7-FT H",20485.679166666665]
["793-14.06","UTIL","CAST IN PLACE MANHOLE",96.04]
["793-14.10","UTIL","4IN CORE DRILL INTO MANHOLE",521.81479999999999]
["793-14.12","UTIL","1 1/4IN INNERDUCT",3.8589976187776394]
["793-16.01","UTIL","MH(RETIRE/REMOVE/GRAVEL BACKFILL)",2790.2391304347825]
["793-16.14","UTIL","BORE/JACK 12IN CASING - ROCK",420]
["793-97.01","UTIL","RESTORE ASPHALT",78.75]
["793-98.04","UTIL","REMOVE POLES ALL SIZES",160.60106353591161]
["793-98.06","UTIL","REMOVE PEDESTALS",429.22169491525426]
["795-01.05","UTIL","8IN DIP RESTRAINED JOINT WATER LINE",95.053961456102783]
["795-05.65","UTIL","BORE/JACK 16IN STEEL CASING PIPE-UNCON.",284.46604850213981]
["795-06.04","UTIL","CONNECT TO 6IN WATER LINE",2168.883956834532]
["795-06.05","UTIL","CONNECT TO 8IN WATER LINE",2963.4450943396228]
["795-07.18","UTIL","16IN X 8IN TAPPING SLEEVE AND VALVE",6233.333333333333]
["795-08.04","UTIL","6IN GATE VALVE ASSEMBLY",1231.3922823984526]
["795-08.05","UTIL","8IN GATE VALVE ASSEMBLY",1771.3177777777778]
["795-09.09","UTIL","RELOCATE/RECONNECT SERVICE ASSEMBLY",845.99717008797666]
["795-10.03","UTIL","1IN AUTO AIR RELEASE VALVE ASSEMBLY",2994.553142857143]
["795-11.04","UTIL","RELOCATE FIRE HYDRANT",2521.6029629629629]
["795-12.02","UTIL","REMOVAL OF EXISTING LINE",42634.957500000004]
["795-15.10","UTIL","30IN STEEL CASING PIPE OPEN CUT METHOD",240.88941482444733]
["797-05.02","UTIL","8IN DIP GRAVITY SEWER 6FT-12FT DEPTH",128.7710615960649]
["797-05.03","UTIL","8IN DIP GRAVITY SEWER 12FT-18FT DEPTH",151.60441842900303]
["797-06.64","UTIL","BORE/JACK 16IN STEEL CASING PIPE-UNCON.",373.83771155261223]
["797-07.03","UTIL","48IN MANHOLE 6FT-8FT DEPTH",4339.1888999999992]
["797-07.04","UTIL","48IN MANHOLE 8FT-10FT DEPTH",4330.4648913043484]
["797-07.05","UTIL","48IN MANHOLE 10FT-12FT DEPTH",5258.9676315789475]
["797-08.05","UTIL","6IN PVC PIPE FOR SERVICE LATERAL",55.114015665796337]
["797-08.08","UTIL","6IN CLEAN OUT ASSEMBLY",720.51411504424777]
["797-10.02","UTIL","CONNECT 8IN SEWER TO EXIST. MANHOLE",3274.7613043478264]
["797-10.06","UTIL","CONNECT 6IN LATERAL TO SEWER LINE",829.6238461538461]
["797-10.09","UTIL","CONNECT EX. 8IN SEWER TO NEW MANHOLE",1700.934838709677]
["797-11.16","UTIL","60IN MH ADJUSTMENT INCREASE HEIGHT",704.84800000000007]
["797-11.25","UTIL","RETIREIN PLACE 48IN MANHOLE",1022.8446268656718]
["797-11.31","UTIL","RETIREIN PLACE EXISTING SEWER 8IN-14IN",11.226501981337082]
["797-11.38","UTIL","BY-PASS PUMPING",23350.096666666665]
["802-02.31","LAND","CUTTINGS: SALIX SERICEA (18IN-24IN)",11.893509350935094]
["802-02.32","LAND","CUTTINGS: CORNUS AMOMUM (18IN-24IN)",10.297970799195491]
["802-02.33","LAND","CUTTINGS: SAMBUCUS CANADENSIS (18IN-24IN)",13.69520701230884]
["802-02.35","LAND","CUTTINGS: CEPHALANTHUS OCCIDENTALIS (18IN-24IN)",9.6428438661710043]
["802-15.04","LAND","JUNCUS EFFUSUS (SOFT RUSH)",10.176527415143603]
["805-01.01","LAND","TURF REINFORCEMENT MAT (CLASS I)",3.7960508896524976]
["805-12.04","LAND","EROSION CONTROL BLANKET (TYPE IV)",1.1236598806061535]
["202-03.01","ERTH","REMOVAL OF ASPHALT PAVEMENT",7.8423998875136283]
["203-03.01","ERTH","BORROW EXCAVATION (SELECT MATERIAL)",12.439771585878502]
["203-05","NBI","UNDERCUTTING",5.7951733114059731]
["209-02.07","EROS","18\" TEMPORARY SLOPE DRAIN",21.31319742981718]
["209-06.05","EROS","BALED HAY OR STRAW",6.3584306915061575]
["209-08.05","EROS","ENHANCED SILT FENCE CHECK (V-DITCH)",426.90192307692303]
["209-10.01","EROS","TEMPORARY DEWATERING STRUCTURE",13.224710712952595]
["209-10.20","EROS","TEMPORARY SEDIMENT TRAP",7.3483573213290114]
["307-01.01","ASPH","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING A",75.387246149402159]
["307-02.02","ASPH","ASPHALT CEMENT (PG70-22)(BPMB-HM) GRADING A-S",553.80237168384974]
["307-02.03","ASPH","AGGREGATE (BPMB-HM) GRADING A-S MIX",54.077966097047408]
["411-12.03","ASPH","SCORING FOR RUMBLE STRIPE (NON-CONTINUOUS) (8IN WIDTH)",4009.8048232651613]
["604-02.01","STBR","CLASS A CONCRETE (BOX BRIDGES)",566.08413773652796]
["604-02.02","STBR","STEEL BAR REINFORCEMENT (BOX BRIDGES)",0.89441867416682153]
["606-09.01","STBR","TEST PILES (PRECAST CONCRETE, SIZE 1)",53.703278688524591]
["606-09.02","STBR","LOADING TEST (PRECAST CONCRETE, SIZE 1)",5365]
["606-09.03","STBR","PRECAST CONCRETE PILES (SIZE 1)",38.015907809857829]
["606-12.01","STBR","PILE ANCHORAGE SYSTEM (SEISMIC)",121.99627097576135]
["606-18.01","STBR","TEST PILES (STEEL PIPE PILES, 14-INCH)",45]
["606-18.02","STBR","LOADING TEST (STEEL PIPE PILES, 14-INCH)",5400]
["606-18.03","STBR","STEEL PIPE PILES (14-INCH)",42]
["607-03.03","DRNG","18\" CONCRETE PIPE CULVERT (CLASS IV)",47.251975972178315]
["607-05.30","DRNG","24\" PIPE CULVERT",63.832999153379426]
["607-06.30","DRNG","30\" PIPE CULVERT",95.022060525144639]
["607-07.30","DRNG","36\" PIPE CULVERT",140.23755979811281]
["607-09.30","DRNG","48\" PIPE CULVERT",167.09050772626932]
["607-10.30","DRNG","54\" PIPE CULVERT",180]
["607-11.30","DRNG","60\" PIPE CULVERT",270.37438967501168]
["607-16.02","DRNG","30\"X 19\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",85.017712355212367]
["607-16.03","DRNG","34\"X 22\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",87]
["607-16.04","DRNG","38\"X 24\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",116.64493827160491]
["607-16.11","DRNG","76\"X 48\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",261.25647810218976]
["607-39.02","DRNG","18\" PIPE CULVERT (SIDE DRAIN)",41.832750118335554]
["607-39.03","DRNG","24\" PIPE CULVERT (SIDE DRAIN)",56.172336983993262]
["607-39.05","DRNG","36\" PIPE CULVERT (SIDE DRAIN)",81.945474860335196]
["611-07.59","STDR","24IN ENDWALL (CROSS DRAIN) 6:1",2992.6691891891892]
["611-07.60","STDR","30IN ENDWALL (CROSS DRAIN) 3:1",3814.4326470588235]
["611-07.61","STDR","30IN ENDWALL (CROSS DRAIN) 4:1",3628.2153125]
["611-07.62","STDR","30IN ENDWALL (CROSS DRAIN) 6:1",5118.7380952380954]
["611-07.64","STDR","36IN ENDWALL (CROSS DRAIN) 4:1",4615.7419354838712]
["611-07.65","STDR","36IN ENDWALL (CROSS DRAIN) 6:1",6353.8012500000004]
["611-07.71","STDR","48IN ENDWALL (CROSS DRAIN) 6:1",9110]
["611-07.73","STDR","18IN ENDWALL (MEDIAN DRAIN)",3573.9230769230771]
["611-38.02","STDR","CATCH BASINS, TYPE 38, > 4' - 8' DEPTH",4678.1734782608692]
["611-39.01","STDR","CATCH BASINS, TYPE 39, 0' - 4' DEPTH",5076.5896969696978]
["611-39.04","STDR","CATCH BASINS, TYPE 39, > 12' - 16' DEPTH",8920]
["611-39.05","STDR","CATCH BASINS, TYPE 39, > 16' - 20' DEPTH",8779.23]
["611-40.01","STDR","CATCH BASINS, TYPE 40, 0' - 4' DEPTH",5569.4922222222222]
["615-01.12","STBR","PRESTRESSED CONCRETE BULB TEE BEAM (6\" WEB)(BT-72)",249.03000160913993]
["615-02.12","STBR","PRESTRESSED CONCRETE BOX BEAM (42\" X 48\")",253]
["621-03.03","DRNG","24\" TEMPORARY DRAINAGE PIPE",80.451458072590754]
["621-03.04","DRNG","30\" TEMPORARY DRAINAGE PIPE",52.417918747918748]
["621-03.05","DRNG","36\" TEMPORARY DRAINAGE PIPE",63.843455733273252]
["621-03.06","DRNG","42\" TEMPORARY DRAINAGE PIPE",82.367853745541012]
["621-03.08","DRNG","54\" TEMPORARY DRAINAGE PIPE",120.52333901192503]
["621-03.11","DRNG","72\" TEMPORARY DRAINAGE PIPE",129.13407821229049]
["701-02","FLAT","CONCRETE DRIVEWAY",7.338242378404785]
["705-03.03","GAT","MEDIAN DIVIDER GUARDRAIL (TYPE 2) (27\" MT HT)",33]
["705-04.05","GAT","GUARDRAIL TERMINAL (TYPE-IN-LINE)",618.39217391304339]
["707-02.01","FNCE","CHAIN-LINK FENCE (4') (VINYL COATED)",8.7037515974756587]
["707-02.02","FNCE","END & CORNER POST ASSEMBLIES (4' VINYL COATED)",178.56941747572816]
["708-02.01","MISC","MARKERS (CONCRETE R.O.W. POSTS)",219.33368884002198]
["710-06.12","DRNG","LATERAL UNDERDRAIN ENDWALL (3:1)",632.2704081632653]
["711-05.70","BARR","32IN SINGLE SLOPE CONCRETE BARRIER WALL",70.467207158351414]
["712-04.50","BARR","PORTABLE BARRIER RAIL DELINEATOR",11.584576132357206]
["713-02.34","TRFP","DELINEATORS (ALL)",34]
["716-04.02","PVMK","PLASTIC PAVEMENT MARKING(DOUBLE TURNING ARROW)",233.67681159420292]
["716-04.06","PVMK","PLASTIC PAVEMENT MARKING (WRONG WAY ARROW)",263.67857142857144]
["716-05.49","PVMK","PAINTED PAVEMENT MARKINGS(8\" LINE)",1496.2660143246244]
["716-12.03","PVMK","ENHANCED FLATLINE THERMO  PVMT MRKNG (8IN BARRIER LINE)",2.8552485118327442]
["716-12.04","PVMK","ENHANCED FLATLINE THERMO  PVMT MRKNG (4IN DOTTED LINE)",2.0126375954102556]
["716-12.05","PVMK","ENHANCED FLATLINE THERMO  PVMT MRKNG (6IN DOTTED LINE)",2.2276925918141859]
["791-01.02","UTIL","2IN STEEL GAS MAIN",45.90959014886969]
["791-01.04","UTIL","4IN STEEL GAS MAIN",70.405856509128128]
["791-01.06","UTIL","8IN STEEL GAS MAIN",115.0991651425862]
["791-03.02","UTIL","2IN HDPE GAS MAIN",28.65350858873283]
["791-03.04","UTIL","4IN HDPE GAS MAIN",53.514178231065038]
["791-04.01","UTIL","HDD <2IN PE PIPE - UNCONSOLIDATED",37.248636363636365]
["791-06.31","UTIL","CONNECT TO 2IN EX. STL MAIN W/ STOPPLE",5962.12]
["791-07.09","UTIL","2IN STEEL GAS VALVE ASSEMBLY",5196.1810344827591]
["791-07.10","UTIL","4IN STEEL GAS VALVE ASSEMBLY",4814.4399999999996]
["791-08.02","UTIL","3/4IN SERVICE ASSEMBLY",1228.5189272030652]
["791-08.07","UTIL","3/4IN PE SERVICE PIPE",32.234498118424085]
["791-09.02","UTIL","3-WIRE CATHODIC PROTECTION STATION",392.83852459016396]
["791-09.03","UTIL","17LB MAGNESIUM ANODES",445.59615384615387]
["791-09.05","UTIL","RESTORE ASPHALT",72.902504472271914]
["791-09.06","UTIL","RESTORE CONCRETE",121.33585858585859]
["791-09.07","UTIL","RESTORE GRAVEL",23.888675623800385]
["791-10.01","UTIL","RETIRE IN PLACE 3/4IN SERV CUT & PLUG",511.28814432989685]
["791-10.04","UTIL","RETIRE IN PLACE 2IN SERV CUT & PLUG",1174.7402597402597]
["795-01.03","UTIL","6IN DIP RESTRAINED JOINT WATER LINE",61.860003626802069]
["795-03.05","UTIL","6IN PVC WATER LINE",30.311589708072827]
["795-03.08","UTIL","12IN PVC WATER LINE",59.650813122437022]
["795-05.02","UTIL","HDD 4IN HDPE CASING PIPE-UNCON",38.081873990306953]
["795-05.03","UTIL","HDD 6IN HDPE CASING PIPE-UNCON",41.160476190476189]
["795-05.66","UTIL","BORE/JACK 18IN STEEL CASING PIPE-UNCON.",431.43592233009713]
["795-06.41","UTIL","CONNECT TO 2 1/2 IN WATER LINE",6244.03]
["795-07.03","UTIL","6IN X 6IN TAPPING SLEEVE AND VALVE",3397.2799212598425]
["795-07.15","UTIL","12IN X 12IN TAPPING SLEEVE AND VALVE",7915.9231578947374]
["795-07.31","UTIL","INSERTION VALVE (6IN)",6231.1680000000006]
["795-07.34","UTIL","INSERTION VALVE (12IN)",17903.473333333332]
["795-08.03","UTIL","4IN GATE VALVE ASSEMBLY",1190.375]
["795-09.02","UTIL","1IN WATER SERVICE METER ASSEMBLY",1426.8772727272726]
["795-09.15","UTIL","1IN HDPE SERVICE PIPE",18.428290723155587]
["795-11.02","UTIL","FIRE HYDRANT ASSEMBLY",4482.5485373134325]
["795-12.01","UTIL","REMOVE FIRE HYDRANT",849.62740157480312]
["795-13.01","UTIL","DI FITTINGS",5.1477492332876329]
["795-14.03","UTIL","CLASS C CONCRETE",221.2968085106383]
["795-15.04","UTIL","18IN STEEL CASING PIPE OPEN CUT METHOD",150.32958486600106]
["797-01.01","UTIL","4IN DIP FORCE MAIN",40]
["797-03.04","UTIL","2IN PVC FORCE MAIN",23.011468945119951]
["797-03.06","UTIL","4IN PVC FORCE MAIN",22.065579334559434]
["797-05.06","UTIL","10IN DIP GRAVITY SEWER 6FT-12FT DEPTH",105]
["797-05.10","UTIL","12IN DIP GRAVITY SEWER 6FT-12FT DEPTH",133.51743375174337]
["797-05.41","UTIL","6IN DIP SERVICE LATERAL",55]
["797-05.51","UTIL","8IN PVC GRAVITY SEWER 0FT-6FT DEPTH",78.008143507972676]
["797-05.52","UTIL","8IN PVC GRAVITY SEWER 6FT-12FT DEPTH",98.702605880766114]
["797-05.53","UTIL","8IN PVC GRAVITY SEWER 12FT-18FT DEPTH",70.981280474878105]
["797-05.55","UTIL","10IN PVC GRAVITY SEWER 0FT-6FT DEPTH",52]
["797-05.56","UTIL","10IN PVC GRAVITY SEWER 6FT-12FT DEPTH",62.958362248438583]
["797-05.57","UTIL","10IN PVC GRAVITY SEWER 12FT-18FT DEPTH",50]
["797-05.58","UTIL","10IN PVC GRAVITY SEWER >18FT DEPTH",128.54285714285714]
["797-05.60","UTIL","12IN PVC GRAVITY SEWER 6FT-12FT DEPTH",83.796864975211435]
["797-06.02","UTIL","HDD 4IN HDPE CARRIER PIPE-UNCON",38.18181818181818]
["797-06.04","UTIL","HDD 8IN HDPE CASING PIPE-UNCON",72.372159090909093]
["797-06.62","UTIL","BORE/JACK 12IN STEEL CASING PIPE-UNCON.",270.49541284403671]
["797-06.67","UTIL","BORE/JACK 24IN STEEL CASING PIPE-UNCON.",450]
["797-06.89","UTIL","OPEN CUT 12IN STEEL CASING PIPE",140.65128205128204]
["797-06.90","UTIL","OPEN CUT 16IN STEEL CASING PIPE",192.2349643551523]
["797-07.06","UTIL","48IN MANHOLE 12FT-14FT DEPTH",5344.5339999999997]
["797-07.07","UTIL","48IN MANHOLE 14FT-16FT DEPTH",5716.9642857142853]
["797-08.01","UTIL","DI FITTINGS",7.0544019737299326]
["797-10.03","UTIL","CONNECT 10-18IN SEWER TO EXIST. MANHOLE",6206.9290909090914]
["797-10.14","UTIL","CONNECT TO 2IN FORCE MAIN",1710.5333333333333]
["797-10.16","UTIL","CONNECT TO 4IN FORCE MAIN",2234.7377777777779]
["797-10.24","UTIL","REMOVE & REPLACE SEWER PUMP STATION",86826.25]
["797-11.35","UTIL","REMOVE EXISTING SEWER 8IN-14IN",18.660596026490065]
["801-01","LAND","SEEDING (WITH MULCH)",25.1833411175548]
["801-01.65","LAND","TEMPORARY MULCH",13.367151947268905]
["802-01.07","LAND","TREES(LIQUIDAMBER STYRACIFLUA) (1.5 - 2\" CAL. B&B)",225]
["802-01.08","LAND","TREES(PLATANUS OCCIDENTALIS) (1.5 - 2\"CAL. B&B)",225]
["802-01.10","LAND","TREES (Populus deltoides 1 1#4\"- 1 1#2\" Cal, B &B)",14.054594957983193]
["802-01.11","LAND","TREES (Quercus Falcata 1 1#4\"- 1 1#2\" Cal, B&B )",19.434404761062325]
["802-01.12","LAND","TREES (Fraxinus pennsylvanica 1 1#4\"- 1 1#2\" C al, B&B)",279.18273631840799]
["908-21.01","STBR","BEARINGS (BENT NO. 1)",6362.9863013698632]
["203-11","ERTH","SCALING AND TRIMMING",50.735738202034241]
["203-40.02","MISC","ROCK ANCHORS (NON-TENSIONED)",393.32361111111118]
["209-03.20","EROS","FILTER SOCK (8 INCH)",3.2274491682070239]
["209-09.43","EROS","CURB INLET PROTECTION (TYPE 4)",169.98721433905899]
["411-03.12","ASPH","ACS MIX(PG64-22) THIN LIFT D ASPHALT",415]
["705-04.50","BARR","PORTABLE BARRIER RAIL DELINEATOR",9.0574036217968583]
["707-02.43","MISC","ROCK ANCHOR, TYPE I",55]
["707-02.44","MISC","ROCK ANCHOR, TYPE II",75]
["707-08.01","FNCE","FENCE (CATCHMENT FENCE)",29.608624898291293]
["707-10.06","MISC","ROCKFALL DRAPE (TYPE II)",80]
["712-04.10","TRFT","TEMPORARY FLEXIBLE TUBULAR DELINEATOR",51.788636363636364]
["712-09.01","TRFT","REMOVABLE PAVEMENT MARKING LINE",2.3862100640097186]
["712-09.31","TRFT","REMOVABLE BLACK-OUT TAPE (8IN)",4.0902702702702705]
["712-12.10","TRFT","TEMPORARY CURB W/FLEXIBLE DELINEATOR (SEE PLANS)",48.250819672131151]
["801-01.02","LAND","CROWN VETCH MIXTURE (WITH MULCH)",24.566687997795725]
["801-02.15","LAND","FERTILIZER",542.43360660395399]
["806-03.01","LAND","TREE CUTTING",330711.5]
["000-01.12","ENGR","TRAFFIC CONTROL SYSTEMS",546.76]
["202-06.13","RMVL","REMOVAL OF BUILDINGS (TRACT NO.79)",5036.4199999999992]
["203-01.79","ERTH","EXCAVATION/BACKFILL",22.092993302421434]
["209-03.22","EROS","FILTER SOCK (18 INCH)",1.6252335467729628]
["209-09.21","EROS","POLYACRYLAMIDE GEL LOGS",104.61316221765914]
["209-09.22","EROS","POLYACRYLAMIDE POWDER",9.9163433122528026]
["303-01.03","BASE","GRANULAR BACKFILL (RETAINING WALLS)",26.744952658412238]
["303-10.03","BASE","MINERAL AGGREGATE (SIZE 68)",37.711077111383112]
["411-12.02","ASPH","SCORING SHOULDERS (NON-CONTINUOUS) (16IN WIDTH)",1244.5760966701635]
["607-09.02","DRNG","48\" CONCRETE PIPE CULVERT (CLASS III)",171.03658521398205]
["611-07.31","STDR","18IN ENDWALL (SIDE DRAIN)",2950.6597315436234]
["611-07.57","STDR","24IN ENDWALL (CROSS DRAIN) 3:1",2494.2767647058827]
["611-12.04","STDR","CATCH BASINS, TYPE 12, > 12' - 16' DEPTH",9018.3559322033907]
["611-14.01","STDR","CATCH BASINS, TYPE 14, 0' - 4' DEPTH",5447.5321999999996]
["611-14.03","STDR","CATCH BASINS, TYPE 14, > 8' - 12' DEPTH",10373.105454545455]
["611-14.04","STDR","CATCH BASINS, TYPE 14, > 12' - 16' DEPTH",14741.474705882354]
["611-42.03","STDR","CATCH BASINS, TYPE 42, > 8' - 12' DEPTH",6758.0673684210524]
["705-04.09","GAT","EARTH PAD FOR TYPE 38 GR END TREATMENT",1138.8573195876288]
["710-06.11","DRNG","LATERAL UNDERDRAIN ENDWALL (2:1)",647.59251497005982]
["712-09.04","TRFT","REMOVABLE PAVEMENT MARKING (STOP LINE)",16.118475073313782]
["713-02.36","TRFP","FLEXIBLE BARRIER DELINEATOR",13.12]
["713-15.40","TRFP","SIGN INSTALLATION (DESCRIPTION)",984.17]
["713-16.07","TRFP","END OF ROADWAY SIGN AND SUPPORT",171.53760000000003]
["716-01.11","PVMK","RAISED PVMT MARKERS (BI-DIRECTIONAL) (1 COLOR LENS)",9.241433724075744]
["716-01.13","PVMK","RAISED PVMT MARKERS (BI-DIRECTIONAL) (2 COLOR LENS)",11.105455568053992]
["716-05.11","PVMK","PAINTED PAVEMENT MARKING(STRAIGHT ARROW)",59.210584415584421]
["716-05.22","PVMK","PAINTED PAVEMENT MARKING (LONGITUDINAL CROSS-WALK)",13.126703841387856]
["716-08.04","PVMK","REMOVAL OF PAVEMENT MARKING (CHANNELIZATION STRIPING)",12.423678707224333]
["716-08.05","PVMK","REMOVAL OF PAVEMENT MARKING (STOP LINE)",4.8033557046979869]
["730-15.30","TRFP","CABINET (FOUR PHASE POLE MOUNTED)",13805.67]
["730-23.02","TRFP","STEEL STRAIN POLE (SIGNAL SUPPORT)",11640.181034482759]
["730-40","TRFT","TEMPORARY TRAFFIC SIGNAL SYSTEM",17571.521818181816]
["773-25.26","UTIL","INSTALL 35-2 SYP WOOD POLE",978.005]
["773-25.27","UTIL","INSTALL 35-4 SYP WOOD POLE",884.22]
["773-25.28","UTIL","INSTALL 3\" SLIC SPLICE CASE",158.08500000000001]
["773-25.29","UTIL","INSTALL 5\" SLIC SPLICE CASE",204.98000000000002]
["773-25.30","UTIL","INSTALL 7\" SLIC SPLICE CASE",330.90999999999997]
["773-25.31","UTIL","INSTALL 9\" SLIC SPLICE CASE",456.84500000000003]
["773-25.32","UTIL","INSTALL AKF25-24(.25M) COMM. CA.",3.7850000000000001]
["773-25.33","UTIL","INSTALL AKF25-24(10M) COMM. CA.",3.7849999999999997]
["773-25.34","UTIL","INSTALL AKF50-24(10M) COMM. CA.",5.15]
["773-25.35","UTIL","INSTALL AKF100-24(10M) COMM. CA.",7.1099999999999994]
["773-25.36","UTIL","INSTALL AKF100-24(E) COMM. CA.",5.9950000000000001]
["773-25.38","UTIL","INSTALL AKF300-24(10M) COMM. CA.",15.705000000000002]
["773-25.39","UTIL","INSTALL AKF400-24(10M) COMM. CA.",17.065000000000001]
["773-25.40","UTIL","INSTALL AKF400-26(10M) COMM. CA.",18.985000000000003]
["773-25.41","UTIL","INSTALL AKF600-24(10M) COMM. CA.",25.844999999999999]
["773-25.43","UTIL","INSTALL BM80 1 INCH RISER GUARD",53.86]
["773-25.44","UTIL","INSTALL BM83 SERVICE GUARD",35.1]
["773-25.45","UTIL","INSTALL FOSB(A)2 SNOW SHOE",120.57499999999999]
["773-25.46","UTIL","INSTALL HACO(12) FIBER SPLICE CASE",1066.425]
["773-25.47","UTIL","INSTALL HACO(24) FIBER SPLICE CASE",1113.3150000000001]
["773-25.48","UTIL","INSTALL HACO(72) FIBER SPLICE CASE",1160.2049999999999]
["773-25.50","UTIL","INSTALL HO1 FIBER CA. SPLICING",40.46]
["773-25.51","UTIL","INSTALL PE1-3G DOWN GUY ASSEMBLY",110.66499999999999]
["773-25.52","UTIL","INSTALL PE2-3G OVHD GUY ASSEMBLY",163.98500000000001]
["773-25.53","UTIL","INSTALL PF1-5A ANCHOR ASSEMBLY",235.79]
["773-25.54","UTIL","INSTALL PF3-5A SCREW IN ANCHOR ASSMBLY",254.55]
["773-25.55","UTIL","INSTALL PF5-3A ROCK ANCHOR ASSMBLY",267.94499999999999]
["773-25.56","UTIL","INSTALL PG31-100(88) LOAD COIL",2798.5249999999996]
["773-25.57","UTIL","INSTALL PG32-12(88) LOAD COIL",827.39499999999998]
["773-25.58","UTIL","INTALL PM11 GUY GUARD ASSEMBLY",18.380000000000003]
["773-25.59","UTIL","INSTALL PM2A POLE GRND ASSMBLY",42.115000000000002]
["773-25.60","UTIL","INSTALL PM52 POLE NUMBER",43.565000000000005]
["773-25.61","UTIL","INSTALL PM91-25-24-20 CABLE STUB",72.615000000000009]
["773-25.62","UTIL","INSTALL PM91-50-24-20 CABLE STUB",91.37]
["773-25.63","UTIL","INSTALL PM91-200-24-24 CABLE STUB",251.87]
["773-25.64","UTIL","INSTALL SEA2-22 AERIAL DROP",1.9200000000000002]
["773-25.65","UTIL","INSTALL SEB2-22 BURIED DROP",2.68]
["773-25.66","UTIL","INSTALL SEB5-22 BURIED DROP",2.87]
["773-25.67","UTIL","INSTALL UO12 UNDGRD FIBER CABLE",1.9950000000000001]
["773-25.68","UTIL","INSTALL YFD12-SMDE(10M) FIBER CA.",2.5249999999999999]
["773-25.69","UTIL","INSTALL YFD12-SMDE(E) FIBER CA.",1.7250000000000001]
["773-25.70","UTIL","INSTALL YFD12-SMDE LOOP FIBER CA.",1.7250000000000001]
["773-25.71","UTIL","INSTALL YFD24-SMDE(.25M) FIBER CA.",2.665]
["773-25.72","UTIL","INSTALL YFD24-SMDE LOOP FIBER CA.",1.865]
["773-25.73","UTIL","INSTALL YFD72-SMDE(10M) FIBER CA.",3.27]
["773-25.74","UTIL","INSTALL YFD72-SMDE LOOP FIBER CA.",2.4649999999999999]
["773-25.75","UTIL","REARRANGE EXISTING BURIED CA.",158.08500000000001]
["773-25.76","UTIL","REARRANGE CABLE STRAIGHT LINE POLE",70.204999999999998]
["773-25.77","UTIL","REARRANGE CABLE ANGLE POLE",92.444999999999993]
["773-25.78","UTIL","REARRANGE COMM. CABLE",0.85499999999999998]
["773-25.79","UTIL","REARRANGE COMM. CA. SPLICING",5.42]
["773-25.80","UTIL","REARRANGE FIBER CA. SPLICING",53.32]
["773-25.81","UTIL","REARRANGE COMM. SPLICE CASE",66.180000000000007]
["773-25.82","UTIL","REARRANGE PM4 CABLE ARM",175.505]
["773-25.83","UTIL","REARRANGE AERIAL DROP WIRE",53.860000000000007]
["773-25.84","UTIL","REARRANGE RISER GUARD",60.29]
["773-25.85","UTIL","REARRANGE WIRE TERMINAL",129.08500000000001]
["773-25.86","UTIL","REMOVE COMM. CABLE",1.095]
["773-25.87","UTIL","REMOVE DISTRIBUTION WIRE",32.155000000000001]
["773-25.88","UTIL","REMOVE COMM. SPLICE CASE",19.29]
["773-25.89","UTIL","REMOVE GUY ASSEMBLY",19.29]
["773-25.90","UTIL","REMOVE ANCHOR ASSEMBLY",25.719999999999995]
["773-25.91","UTIL","REMOVE PM4 CROSS ARM",64.304999999999993]
["773-25.92","UTIL","REMOVE SYP POLE",64.304999999999993]
["773-25.93","UTIL","REMOVE AERIAL DROP",25.72]
["773-25.94","UTIL","REMOVE RISER GUARD",25.72]
["773-25.95","UTIL","REMOVE WIRE TERMINAL",19.285]
["773-25.96","UTIL","INSTALL AKFS104-24(10M) COMM. CA.",6.955000000000001]
["773-25.97","UTIL","INSTALL AKF200-24(10M) COMM. CA.",11.58]
["773-25.98","UTIL","INSTALL HC3 COMM. CA. SPLICING",5.1049999999999995]
["790-01.05","UTIL","POLE 30FT CLASS 6 WOOD",1102.8371428571429]
["790-02.04","UTIL","POLE 35FT CLASS 5 WOOD",1322.2282352941174]
["790-03.02","UTIL","POLE 40FT CLASS 3 WOOD",2484.6188000000002]
["790-06.02","UTIL","POLE 55FT CLASS 2 WOOD",2979.5647619047622]
["790-07.01","UTIL","POLE 60FT CLASS 1 WOOD",4771.7002631578953]
["790-10.05","UTIL","POLE 75FT CLASS H2 METAL",9244.9825000000001]
["790-10.07","UTIL","POLE 75FT CLASS H4 METAL",10436.7325]
["790-11.05","UTIL","POLE 80FT CLASS H2 METAL",10360.073333333332]
["790-11.06","UTIL","POLE 80FT CLASS H3 METAL",10820.785]
["790-12.05","UTIL","POLE 85FT CLASS H2 METAL",10495.098]
["790-12.07","UTIL","POLE 85FT CLASS H4 METAL",20863.118571428571]
["790-13.05","UTIL","POLE 90FT CLASS H2 METAL",11589.29]
["790-13.06","UTIL","POLE 90FT CLASS H3 METAL",10716.534285714286]
["790-14.06","UTIL","POLE 95FT CLASS H3 METAL",10682.555]
["790-14.07","UTIL","POLE 95FT CLASS H4 METAL",18274.068571428572]
["790-15.01","UTIL","POLE 100FT CLASS H4 METAL",9377.2133333333331]
["790-16.01","UTIL","POLE 105FT CLASS H4 METAL",11329.545]
["790-17.01","UTIL","POLE 110FT CLASS H4 METAL",14626.55]
["790-17.02","UTIL","POLE 110FT CLASS H5 METAL",13842.958333333334]
["790-18.01","UTIL","POLE 115FT CLASS H4 METAL",15841.44]
["790-20.02","UTIL","POLE (H1-95)",9868.5212499999998]
["790-20.03","UTIL","POLE (H2-100)",9359.0836363636354]
["790-20.04","UTIL","POLE (H2-105)",10644.436]
["790-20.05","UTIL","POLE (H2-110)",9478.9437500000004]
["790-20.06","UTIL","POLE (H3-100)",9645.067500000001]
["790-20.07","UTIL","POLE (H3-110)",10346.637500000001]
["790-20.08","UTIL","POLE (H2-85)",11770.135714285716]
["790-22.01","UTIL","1PH SGL PRIMARY SUPPORT 25KV",268.45828571428569]
["790-22.10","UTIL","1PH SUSPENSION ANGLE 25KV",396.05]
["790-22.11","UTIL","1PH DDE ANGLE 25KV",405.27839999999998]
["790-22.12","UTIL","1PH DEAD END MISC 25KV",413.1399193548387]
["790-22.13","UTIL","1PH DEAD END 25KV",306.11857142857144]
["790-22.14","UTIL","1PH DEAD END TAP 25KV",400.36]
["790-22.16","UTIL","1PH DDE TANGENT 25KV",594.64567567567565]
["790-24.08","UTIL","2PH DEAD END CROSSARM 25KV",772.94200000000001]
["790-24.10","UTIL","2PH DDE XARM 25KV",1152.0066666666667]
["790-26.02","UTIL","3PH CROSSARM DBL LRG COND 25KV",1421.783090909091]
["790-26.03","UTIL","3PH CROSSARM SGL LRG COND 25KV",1276.7444479495268]
["790-26.15","UTIL","3PH XARM DBL 10FT LRG COND SM ANGLE 25KV",2350.5161538461539]
["790-26.18","UTIL","3PH VERTICAL SM ANGLE SUSP BKT 25KV",3276.2250000000004]
["790-26.20","UTIL","3PH VERTICAL ANGLE LRG COND 25KV",1504.348979591837]
["790-26.21","UTIL","3PH VERTICAL DDE ANGLE 25KV",2045.47]
["790-26.24","UTIL","3PH VERTICAL DEAD END LRG COND 25KV",1462.8576]
["790-26.26","UTIL","3PH CROSSARM DEAD END 25KV",2188.436296296296]
["790-26.27","UTIL","3PH CROSSARM DBL DDE 25KV",2600.4182089552237]
["790-26.28","UTIL","3PH DBL 10FT XARM DDE 25KV",4830.41]
["790-30.03","UTIL","SECONDARY ASSEMBLIES DEADEND",248.41317124735735]
["790-31.02","UTIL","SERVICE ASSEMBLY-POLE TYPE",142.4412351190476]
["790-31.04","UTIL","SERVICE CONDUCTOR 6 AL DUPLEX",2.5515954991344487]
["790-31.11","UTIL","SERVICE CONDUCTOR 2 AL TRIPLEX",6.9985945054712726]
["790-31.13","UTIL","SERVICE CONDUCTOR 2/0 AL TRIPLEX",6.7549999999999999]
["790-31.20","UTIL","SERVICE CONDUCTOR 1/0 AL QPLEX",10.179929648241206]
["790-32.06","UTIL","DOWN GUY - INSULATED",356.1535114503817]
["790-32.23","UTIL","GUY GUARD",30.033523600439075]
["790-33.18","UTIL","ROCK ANCHOR GUY BOLT TYPE",473.59465116279068]
["790-40.02","UTIL","OH COND 2 7/1 ACSR SPARATE",3.1599859227139615]
["790-40.05","UTIL","OH COND 3/0 6/1 ACSR PIGEON",3.3389454636932161]
["790-40.10","UTIL","OH COND 336.4 26/7 ACSR LINNET",3.9450000000000003]
["790-40.24","UTIL","OH COND 795 26/7 ACSR DRAKE",6.3225531064686793]
["790-40.76","UTIL","OH STATIC COND _____ _____ ___________ (SEE PLANS)",2.7954092751013055]
["790-43.59","UTIL","SECONDARY RISER (SEE PLANS)",756.42000000000007]
["790-46.01","UTIL","1PH TRANSFORMER",899.43667731629409]
["790-49.01","UTIL","3PH XFMR BNK POLE MTD NO FUSE/ARRESTERS",8740.98]
["790-58.06","UTIL","GOAB SWITCH 15KV",11744.675909090909]
["790-60.04","UTIL","2 - 1PH SECTIONALIZERS OR RECLOSERS 15KV",6518.38]
["790-61.01","UTIL","1PH FUSE CUTOUT XARM MOUNT 25KV",541.45821958456975]
["790-61.05","UTIL","2 - 1PH SECTIONALIZERS OR RECLOSERS 25KV",6978.4400000000005]
["790-61.10","UTIL","3PH SECTLR OR RECL W/ BYPASS SW 25KV",22100.242352941175]
["790-62.03","UTIL","1PH HYDR RECL 50A CONT 1250A INT 15KV",2491.2649999999999]
["790-62.08","UTIL","1PH HYDR RECL 560A CONT 10000A INT 15KV",5790.0150000000003]
["790-64.01","UTIL","SEC MTG 1PH 120/240 VOLTS",1064.4199999999998]
["790-64.10","UTIL","SEC MTG 3PH 120/240 VOLTS (4 WIRE ?)",4449.9650000000001]
["790-64.14","UTIL","PRI MTG 3PH CLUSTER MOUNT",20265.690999999999]
["790-65.06","UTIL","LIGHTNING ARRESTER POLE MTD 18 KV",283.83606060606058]
["790-68.12","UTIL","LARGE BRACES",245.10999999999999]
["790-69.21","UTIL","1-SGL PHASE RECLOSER",3472.5074999999997]
["790-70.12","UTIL","STREET LIGHT - HPS  (SEE PLANS)",1105.0444444444445]
["790-70.13","UTIL","STREET LIGHT - HPS  (SEE PLANS)",858.32999999999993]
["790-70.14","UTIL","STREET LIGHT - HPS  (SEE PLANS)",882.17000000000007]
["790-70.20","UTIL","STREET LIGHT (SEE PLANS)",801.10489208633089]
["790-70.21","UTIL","STREET LIGHT (SEE PLANS)",882.17000000000007]
["790-71.66","UTIL","TANGENT W/ UPSWEPT ARMS 161KV MAX",5960.7300000000005]
["790-71.67","UTIL","HORIZ POST TANGENT 161KV MAX",5801.6781818181817]
["790-71.68","UTIL","HORIZ POST SM ANG 161KV MAX",7464.3580000000002]
["790-71.69","UTIL","VERTICAL DDE 161KV MAX",12002.235000000002]
["790-71.70","UTIL","INTERMEDIATE ANGLE SINGLE POLE 161KV ASSEMBLY",8764.5166666666682]
["790-71.71","UTIL","LARGE ANGLE SINGLE POLE 161KV ASSEMBLY",6035.72]
["790-72.15","UTIL","MEDIUM DUTY GUYING TEE",756.0576842105263]
["790-73.02","UTIL","INS STRING W/ CUSHIONED SUSP",1310.7049999999999]
["791-02.05","UTIL","6IN MDPE GAS MAIN",62.698534923339011]
["793-02.90","UTIL","GUY WIRE (SEE PLANS)",251.3310175438597]
["795-03.02","UTIL","2IN PVC WATER LINE",25.630568499534018]
["795-03.04","UTIL","4IN PVC WATER LINE",35.841888020833338]
["795-03.06","UTIL","8IN PVC WATER LINE",41.436980707186628]
["795-03.07","UTIL","10IN PVC WATER LINE",54.071127310596196]
["795-05.74","UTIL","BORE/JACK 6IN STEEL CASING PIPE-ROCK.",242.04180451127817]
["795-05.75","UTIL","BORE/JACK 8IN STEEL CASING PIPE-ROCK.",295.28000000000003]
["795-05.76","UTIL","BORE/JACK 10IN STEEL CASING PIPE-ROCK.",385.04232876712331]
["795-05.79","UTIL","BORE/JACK 16IN STEEL CASING PIPE-ROCK.",565.3903460837887]
["795-05.80","UTIL","BORE/JACK 18IN STEEL CASING PIPE-ROCK.",350.31555555555553]
["795-05.81","UTIL","BORE/JACK 20IN STEEL CASING PIPE-ROCK.",578.56111111111113]
["795-06.01","UTIL","CONNECT TO 2IN WATER LINE",1288.8025]
["795-06.03","UTIL","CONNECT TO 4IN WATER LINE",2655.3658333333333]
["795-06.06","UTIL","CONNECT TO 10IN WATER LINE",3457.4490909090905]
["795-06.07","UTIL","CONNECT TO 12IN WATER LINE",3596.35]
["795-07.01","UTIL","4IN X 4IN TAPPING SLEEVE AND VALVE",2925.9294117647059]
["795-07.04","UTIL","8IN X 4IN TAPPING SLEEVE AND VALVE",4052.1849999999999]
["795-07.05","UTIL","8IN X 6IN TAPPING SLEEVE AND VALVE",7105.6045454545447]
["795-07.08","UTIL","10IN X 6IN TAPPING SLEEVE AND VALVE",4865.3999999999996]
["795-08.01","UTIL","2IN GATE VALVE ASSEMBLY",656.68942307692316]
["795-08.06","UTIL","10IN GATE VALVE ASSEMBLY",2659.430625]
["795-08.25","UTIL","ELECTRONIC CONTROL VALVE VAULT W/BYPASS",51276.904999999999]
["795-09.10","UTIL","SAMPLE TAP",727.81622857142861]
["797-06.72","UTIL","BORE/JACK 6IN STEEL CASING PIPE-ROCK.",244.09153846153851]
["797-06.74","UTIL","BORE/JACK 10IN STEEL CASING PIPE-ROCK.",391.9]
["797-08.02","UTIL","PVC FITTINGS",7.7358768873403019]
["797-09.28","UTIL","4IN AIR/VAC VALVE ASSEMBLY",3348.33]
["801-01.16","EROS","BONDED FIBER MATRIX HYDROMULCH (W/PERMANENT SEED)",90.537362637362634]
["801-02.01","LAND","CROWN VETCH MIXTURE (WITHOUT MULCH)",27.651564033627789]
["801-07","LAND","SEED (SUPPLEMENTAL APPLICATION)",4.4611610491384992]
["801-07.01","LAND","CROWN VETCH SEED (SUPPLEMENTAL APPLICATION)",6.5933387563015806]
["801-08","LAND","FERTILIZER (SUPPLEMENTAL APPLICATION)",434.49144307639807]
["802-11.02","LAND","ACER RUBRUM (RED MAPLE 2-5FT CNTNR GRWN)",29.958034557235422]
["802-11.11","LAND","CERCIS CANADENSIS (REDBUD 2-5FT CNTNR GRWN)",36.772093023255813]
["802-11.39","LAND","QUERCUS RUBRA (NORTHERN RED OAK 2-5FT CNTNR GRWN)",26.402424242424242]
["802-12.01","LAND","ACER NEGUNDO (BOX ELDER SEEDLNG B.R.)",8.1849553571428562]
["802-12.02","LAND","ACER RUBRUM (RED MAPLE SEEDLNG B.R.)",20.836513157894739]
["802-12.40","LAND","SALIX NIGRA (BLACK WILLOW SEEDLNG B.R.)",8.1972658227848108]
["802-13.57","LAND","ILEX OPACA (AMERICAN HOLLY SDLNG BARE ROOT)",6.2121212121212119]
["805-01.02","LAND","TURF REINFORCEMENT MAT (CLASS II)",3.3093589644072625]
["106-04.01","MISC","SMPLNG & TSTNG OF POTENTIALLY ACIDIC MAT.",118.45]
["202-01.56","ERTH","REMOVAL OF STRUCTURES & OBSTRUCTIONS (10'X4' RCBC)",94577.043333333335]
["202-02.01","ERTH","REMOVAL OF PIPE (15\" CMP,STA. 260+39)",31.808682817589577]
["202-02.02","ERTH","REMOVAL OF PIPE (18\" CMP,STA. 263+47)",22.728657921291624]
["202-02.03","ERTH","REMOVAL OF PIPE (18\" CMP,STA. 270+29)",13.712352024922119]
["202-02.04","ERTH","REMOVAL OF PIPE (18\" PL,STA. 270+71)",14.879689922480619]
["202-02.05","ERTH","REMOVAL OF PIPE (18\" CMP,STA. 281+01)",12.968231611893584]
["202-02.06","ERTH","REMOVAL OF PIPE (18\" CMP,STA. 288+01)",16.598911174785101]
["202-02.07","ERTH","REMOVAL OF PIPE (18\" CMP,STA. 290+59)",13.389808173477899]
["202-02.08","ERTH","REMOVAL OF PIPE (30\" RCP,STA. 297+81)",18.818167202572347]
["202-02.09","ERTH","REMOVAL OF PIPE (30\" CMP,STA. 299+30)",22.753154362416108]
["202-02.10","ERTH","REMOVAL OF PIPE (18\" CMP,STA. 304+87)",12.544155844155844]
["202-02.11","ERTH","REMOVAL OF PIPE (18\" CMP,STA. 313+53)",18.42546762589928]
["202-02.12","ERTH","REMOVAL OF PIPE (24\" RCP,STA. 314+43)",11.542553191489361]
["202-02.13","ERTH","REMOVAL OF PIPE (18\" RCP,STA. 325+24)",14.097938144329897]
["202-02.14","ERTH","REMOVAL OF PIPE (86\" CMP,STA. 58+40 HANGING ROCK RD.)",37.122641509433961]
["202-02.15","ERTH","REMOVAL OF PIPE (24\" CMP,STA. 332+30)",45.172753623188406]
["202-02.17","ERTH","REMOVAL OF PIPE (24\" RCP,STA. 80+85 S.R. 328)",25.880281690140844]
["202-02.18","ERTH","REMOVAL OF PIPE (30\" CMP,STA. 357+26)",14.218487394957982]
["202-02.19","ERTH","REMOVAL OF PIPE (18\" CMP,STA. 338+18)",8.4782608695652169]
["203-01.09","ERTH","ACID PRODUCING MATERIAL HAUL & TIP FEE",25.966500157084511]
["209-01.31","EROS","TEMPORARY MULCH FILTER BERM",4.59]
["209-02.04","EROS","10\" TEMPORARY SLOPE DRAIN",11.53304190751445]
["209-02.05","EROS","12\" TEMPORARY SLOPE DRAIN",15.041570018153637]
["209-02.06","EROS","15\" TEMPORARY SLOPE DRAIN",15.896306095979249]
["209-03.31","EROS","STREAM MITIGATION-COCONUT FIBER ROLLS",21.323456790123458]
["209-03.34","EROS","STREAM MITIGATION-LOG VANES",214.37871080139374]
["209-03.35","EROS","STREAM MITIGATION-LOG DROP STRUCTURE",929.21]
["209-03.44","EROS","STREAM MITIGATION - WILLOW POLES (SPECIES)",25.386416861826699]
["209-03.55","EROS","STREAM MITIGATION (DESCRIPTION)",4074.79]
["209-03.56","EROS","STREAM MITIGATION (ROCK RIFFLES)",3841.99]
["209-04","EROS","BRUSH BARRIERS",11.41]
["209-09.24","EROS","JUTE MESH FABRIC",3.0383333333333336]
["209-40.48","EROS","CATCH BASIN FILTER ASSEMBLY(TYPE 8)",908.47086206896552]
["209-65.01","EROS","TEMPORARY STREAM DIVERSION (DESCRIPTION)",33706.478000000003]
["209-65.02","EROS","TEMPORARY STREAM DIVERSION (DESCRIPTION)",34325.199999999997]
["209-65.14","EROS","TEMPORARY STREAM DIVERSION",36657.379999999997]
["604-07.11","WALL","RETAINING WALL (WALL NO. 1)",86.246427272254849]
["604-07.12","WALL","RETAINING WALL (WALL NO. 2)",81.026517427884613]
["604-07.13","WALL","RETAINING WALL (WALL NO. 3)",100.42255475708937]
["604-07.14","WALL","RETAINING WALL (WALL NO. 4)",79.400821454457599]
["611-02.11","STDR","JUNCTION BOX, TYPE 2",3994.5691379310342]
["611-02.12","STDR","JUNCTION BOX, TYPE 3",5456.5]
["611-07.32","STDR","24IN ENDWALL (SIDE DRAIN)",3375.8192631578945]
["611-07.33","STDR","30IN ENDWALL (SIDE DRAIN)",3663.9242857142858]
["611-07.34","STDR","36IN ENDWALL (SIDE DRAIN)",6620.3845454545453]
["611-07.70","STDR","48IN ENDWALL (CROSS DRAIN) 4:1",7865.8]
["611-38.03","STDR","CATCH BASINS, TYPE 38, > 8' - 12' DEPTH",6522.5123076923082]
["611-39.02","STDR","CATCH BASINS, TYPE 39, > 4' - 8' DEPTH",6596.6906250000002]
["611-39.07","STDR","CATCH BASINS, TYPE 39, > 24' - 28' DEPTH",4635]
["611-40.05","STDR","CATCH BASINS, TYPE 40, > 16' - 20' DEPTH",6695]
["705-04.02","GAT","GUARDRAIL TERMINAL (TYPE 12)",1028.7142857142858]
["707-01.50","FNCE","CHAIN-LINK FENCE (8 FOOT)",17.3]
["707-01.51","FNCE","END & CORNER POST ASSEMBLY (CHAIN-LINK FENCE __') (CHAIN-LINK FENCE 8')",283.25]
["707-01.52","FNCE","GATE - CHAIN-LINK FENCE (8 FOOT - 4' WIDE)",1287.5]
["708-01.01","MISC","MONUMENTS (R.O.W.)",262.05]
["709-05.09","RIPR","MACHINED RIP-RAP (CLASS C)",38.382335134071475]
["710-10.08","DRNG","18\" PERFORATED PLASTIC PIPE",40.067331954498449]
["710-13.03","DRNG","FILTER CLOTH",6.1026495726495726]
["740-11.02","EROS","TEMPORARY SEDIMENT TUBE 12IN (SEE PLANS)",2.8657942363564102]
["790-04.02","UTIL","POLE 45FT CLASS 2 WOOD",1553.7224210526315]
["790-05.03","UTIL","POLE 50FT CLASS 3 WOOD",1432.1063768115941]
["790-21.05","UTIL","1PH DBL PRIMARY SUPPORT 15KV",298.84842105263158]
["790-21.07","UTIL","1PH PRIMARY LG ANGLE 15KV",404.36222222222221]
["790-21.09","UTIL","1PH PRIMARY TAP 15KV",385.02772277227717]
["790-21.10","UTIL","1PH VERTICAL DDE 15KV",450.17739130434785]
["790-25.08","UTIL","3PH CROSSARM SGL LRG COND 15KV",974.12107142857144]
["790-25.11","UTIL","3PH CROSSARM DBL PRIM SUP LRG COND 15KV",1732.0977192982457]
["790-25.23","UTIL","3PH CROSSARM DDE 15KV",3287.0623287671233]
["790-31.12","UTIL","SERVICE CONDUCTOR 1/0 AL TRIPLEX",4.9913807614146242]
["790-32.07","UTIL","OH GUY - THROUGH BOLT TYPE",552.96472727272726]
["790-33.20","UTIL","ANCHOR TRIPLE EYE POWER INSTALLED",687.6900970873786]
["790-40.42","UTIL","OH COND 336.4 19 AAC TULIP",3.4609566015353974]
["790-40.73","UTIL","OH PRI COND _____ _____ ____ ________ (SEE PLANS)",4.6421587323131215]
["790-42.12","UTIL","CONDUIT - POLE MTD - 2IN SCH 80 PVC",106.74112595419848]
["790-47.02","UTIL","2PH XFMR BNK POLE MTD W/ FUSE/ARRESTERS",2856.1142857142854]
["790-58.05","UTIL","GOLB SWITCH 15KV",11358.011666666667]
["790-65.03","UTIL","LIGHTNING ARRESTER ARM MTD 9 KV",268.77322834645673]
["790-68.02","UTIL","POLE GROUND PLATE TYPE",205.55483870967743]
["790-68.07","UTIL","POLE GROUND FOR AIR BREAK SWITCH",954.78500000000008]
["790-69.22","UTIL","POLE TOP PIN",111.89277777777778]
["790-70.01","UTIL","STREET LIGHT ON WOOD POLE",332.50526315789472]
["790-98.20","UTIL","TREE AND BRUSH REMOVAL OFF ROW",25124.419374999998]
["793-01.33","UTIL","POLE (NUMBERING ONLY)",404.48]
["793-01.39","UTIL","ANCHOR 5/8IN",243.59999999999997]
["793-01.40","UTIL","ANCHOR 3/4IN",311.98692737430167]
["793-01.41","UTIL","ANCHOR 1IN",484.60590909090905]
["793-02.08","UTIL","GUY WIRE 10M OR 3/8IN",124.0287351778656]
["793-03.02","UTIL","6M STRAND",1.6200000000000003]
["793-03.03","UTIL","10M STRAND",2.1346888923169058]
["793-03.13","UTIL","75  PAIR CABLE",7.75]
["793-03.41","UTIL","AERIAL CABLE (DESCRIPTION)",2.8944454566158049]
["793-04.01","UTIL","RELASH/DELASH CABLE",2.1063345983554713]
["793-04.02","UTIL","2 PAIR AERIAL DROP",2.0387842383469486]
["793-04.07","UTIL","AERIAL SPLICE CLOSURE",536.43939393939399]
["793-04.08","UTIL","TRANSFER AERIAL CABLE",127.22975000000001]
["793-04.09","UTIL","TRANSFER AERIAL DROP",60.124285714285712]
["793-04.25","UTIL","HOT SPLICE EXISTING CABLES",5.3262914562914565]
["793-07.01","UTIL","12 FIBER (MATERIAL ONLY)",0.41336382445823805]
["793-07.02","UTIL","24 FIBER(MATERIAL ONLY)",1.0903369323050556]
["793-07.04","UTIL","48 FIBER(MATERIAL ONLY)",0.82100308770758579]
["793-07.05","UTIL","96 FIBER(MATERIAL ONLY)",1.6609156674927994]
["793-07.07","UTIL","144 FIBER(MATERIAL ONLY)",3.22]
["793-07.16","UTIL","12-96 FIBER(INSTALLATION ONLY)",2.60051500777295]
["793-07.17","UTIL","108-144 FIBER(INSTALLATION ONLY)",3.67]
["793-07.25","UTIL","SINGLE FIBER OPTIC CABLE SPLICE",41.375736434108525]
["793-07.31","UTIL","SINGLE FIBER AERIAL DROP",1.86]
["793-15.01","UTIL","TRANSFER CABLE ATTACHMENT",125.18851485148514]
["793-15.04","UTIL","TRANSFER DOWN GUY ATTACHMENT",102.18]
["793-98.01","UTIL","REMOVE  AERIAL CABLE AND WIRE",1.6518334044221852]
["793-98.08","UTIL","REMOVE ANCHOR (ANY SIZE)",55.546541666666663]
["795-01.09","UTIL","12IN DIP RESTRAINED JOINT WATER LINE",74.219168276831198]
["795-01.10","UTIL","12IN DIP SLIP JOINT WATER LINE",70.167849103520481]
["795-05.01","UTIL","HDD 2IN HDPE CARRIER PIPE-UNCON",35.815836073867949]
["795-05.15","UTIL","HDD 2IN HDPE CARRIER PIPE-ROCK",97.145454545454541]
["795-05.63","UTIL","BORE/JACK 12IN STEEL CASING PIPE-UNCON.",213.44529067147363]
["795-05.68","UTIL","BORE/JACK 24IN STEEL CASING PIPE-UNCON.",416.66148936170214]
["795-07.11","UTIL","12IN X 4IN TAPPING SLEEVE AND VALVE",4120]
["795-08.09","UTIL","12IN GATE VALVE ASSEMBLY",3170.0969767441857]
["795-09.01","UTIL","3/4IN WATER SERVICE METER ASSEMBLY",966.16632538569422]
["795-09.14","UTIL","3/4IN HDPE SERVICE PIPE",14.445697896749522]
["795-09.28","UTIL","3/4IN COPPER SERVICE PIPE",20.058604388056082]
["795-09.29","UTIL","1IN COPPER SERVICE PIPE",27.59220440134278]
["795-15.02","UTIL","12IN STEEL CASING PIPE OPEN CUT METHOD",152.95456899741029]
["795-15.07","UTIL","24IN STEEL CASING PIPE OPEN CUT METHOD",250.74315068493149]
["801-01.13","EROS","BONDED FIBER MATRIX HYDROMULCH (WITHOUT SEED)",92.7]
["801-01.30","LAND","COVER CROP SEED MIX (RIPZN/FLPL) W/MULCH",55.443797691254154]
["801-01.34","LAND","GRASS SEED MIX (RIPZN/FLPL)",87.142168674698794]
["801-09","LAND","AGRICULTURAL LIME",32.383928571428569]
["802-02.01","LAND","SEEDLINGS (HAZEL ALDER)",7.2099999999999991]
["802-02.02","LAND","SEEDLINGS (PAWPAW)",7.2099999999999991]
["802-11.06","LAND","ASIMINA TRILOBA (PAWPAW 2-5FT CNTNR GRWN)",36.049999999999997]
["802-11.45","LAND","CARPINUS CAROLINIANA (AMERICAN HORNBEAM 2-5FT CONTAINER GR)",31.706410256410255]
["802-12.18","LAND","LIQUIDAMBER STYRACIFLUA (SWEETGUM SEEDLNG B.R.)",13.609171270718232]
["802-13.07","LAND","ILEX OPACA (AMERICAN HOLLY 2-5FT CNTNR GRWN)",36.049999999999997]
["805-12.01","LAND","EROSION CONTROL BLANKET (TYPE I)",0.87716677507859941]
["203-01.11","ERTH","PRESPLITTING OF ROCK EXCAVATION",17.288034733153491]
["203-01.29","ERTH","ROCK EXCAVATION",16.976286266924564]
["203-02.02","ERTH","BORROW EXCAVATION (GRADED SOLID ROCK)",34.701435774946923]
["203-10.15","ERTH","WASTE MATERIAL",10.607411882588707]
["209-20.04","EROS","POLYETHYLENE SHEETING (10 MIL.)",4.1591780821917812]
["604-01.20","INCI","BOX TUBE SAFETY RAIL",138.12977577977577]
["604-02.41","STBR","ENERGY DISSIPATER (26'x12' CONTRA COSTA)",19116.666666666668]
["604-02.42","STBR","ENERGY DISSIPATER (34'x8' CONTRA COSTA)",33375]
["611-01.20","STDR","ADJUSTMENT OF EXISTING MANHOLE",1172.3030303030303]
["620-05","BARR","CONCRETE PARAPET WITH STRUCTURAL TUBING",175.08330262225371]
["621-03.09","DRNG","60\" TEMPORARY DRAINAGE PIPE",108.76973760932945]
["702-01.01","FLAT","EXTRUDED MOUNTABLE CURB",13.651334805932471]
["705-01.04","GAT","METAL BEAM GUARD FENCE",72.647209728469107]
["713-14.21","TRFP","STREET NAME SIGN (RIGID 0.100IN THICK",36.820465500165071]
["716-04.13","PVMK","PLASTIC PAVEMENT MARKING (BIKELANE SYMBOL & ARROW)",406.1014503816794]
["716-08.20","PVMK","REMOVAL OF PAVEMENT MARKING (LINE)",4225.665034610839]
["730-12.03","TRFP","CONDUIT 3\" DIAMETER (PVC)",16.781180127263827]
["730-12.09","TRFP","CONDUIT 3\" DIAMETER (RGS)",25.79826594998832]
["730-23.36","TRFP","CANTILEVER SIGNAL SUPPORT (2 @ 54' & 62')",19747.948999999997]
["730-23.37","TRFP","CANTILEVER SIGNAL SUPPORT (2 @ 52' & 64')",21298.042142857139]
["730-23.97","TRFP","CANTILEVER SIGNAL SUPPORT (1 ARM @ 68')",20795.766800000001]
["730-23.98","TRFP","CANTILEVER SIGNAL SUPPORT (1 ARM @ 72')",21578.098636363637]
["730-23.99","TRFP","CANTILEVER SIGNAL SUPPORT (1 ARM @ 90')",19990.056250000001]
["790-02.07","UTIL","POLE 35FT CLASS 2 METAL",3760]
["790-03.06","UTIL","POLE 40FT CLASS 2 METAL",4057.5474999999997]
["790-04.06","UTIL","POLE 45FT CLASS 1 METAL",4484.6578947368425]
["790-04.07","UTIL","POLE 45FT CLASS 2 METAL",4341.9330188679251]
["790-05.05","UTIL","POLE 50FT CLASS 1 METAL",5350]
["790-21.06","UTIL","1PH PRIMARY MED ANGLE 15KV",527.4375]
["790-23.01","UTIL","2PH CROSSARM SGL PRIM SUPPORT 15KV",612.5]
["790-23.07","UTIL","2PH CROSSARM CONST DEADEND (SGL) 15KV",931.89555555555546]
["790-23.08","UTIL","2PH CROSSARM CONST DEADEND (DBL) 15KV",1582.5]
["790-25.01","UTIL","3PH CROSSARM SGL 15KV",1108.55432]
["790-25.02","UTIL","3PH NARROW PROFILE SGL 15KV",1582.104]
["790-25.10","UTIL","3PH CROSSARM DBL DBL PRIM SUPPORT 15KV",1646.5410714285715]
["790-25.22","UTIL","3PH XARM DEADEND SGL NARROW PROFILE 15KV",1505]
["790-25.25","UTIL","3PH CROSSARM DDE NARROW PROFILE 15KV",2830]
["790-25.28","UTIL","3PH CROSSARM SGL 10FT 15KV",1460.8888888888889]
["790-30.07","UTIL","SECONDARY CONDUCTOR 4 AL DUPLEX",2.8778325123152708]
["790-42.13","UTIL","CONDUIT - POLE MTD - 3IN SCH 80 PVC",41.600762910798117]
["790-49.02","UTIL","3PH XFMR BNK POLE MTD W/ FUSE/ARRESTERS",6637.8019047619046]
["790-65.16","UTIL","3PH CAPACITOR ASSEMBLY SWITCHED 15KV",4480]
["790-68.10","UTIL","MISCELLANEOUS ASSEMBLIES",375.36676829268293]
["791-01.01","UTIL","<2IN STEEL GAS MAIN",52.390625]
["791-01.23","UTIL","2IN POWERCRETE COATED STL GAS MAIN-OPEN CUT",72]
["791-01.26","UTIL","4IN PWRCRETE CTD STL GAS MN-OPN CUT",121]
["791-04.53","UTIL","HDD 4IN POWERCRETE COATED STEEL GAS MN",225]
["791-06.11","UTIL","CONNECT TO 4IN EX. STL MAIN",7937.0133333333333]
["791-06.17","UTIL","CONNECT TO __IN EX. STL MAIN (SEE PLANS)",521.25]
["791-06.32","UTIL","CONNECT TO 4IN EX. STL MAIN W/ STOPPLE",19327.7]
["791-08.12","UTIL","3/4IN STEEL SERVICE PIPE",60.673275862068962]
["791-08.13","UTIL","1IN STEEL SERVICE PIPE",37.901096491228067]
["791-08.22","UTIL","HDD 3/4IN STEEL SERVICE PIPE",53.085838779956426]
["791-08.23","UTIL","HDD 1IN STEEL SERVICE PIPE",99.878260869565224]
["793-01.08","UTIL","POLE 35FT CLASS 5 WOOD",1210.3898305084747]
["793-01.12","UTIL","POLE 40FT CLASS 4 WOOD",1674.867741935484]
["793-01.18","UTIL","POLE 45FT CLASS 4 WOOD",1490.25]
["793-01.24","UTIL","POLE 55FT CLASS 2 WOOD",2322]
["793-14.19","UTIL","4IN SCH 80 ORANGE FLEXPIPE",15.593030164533822]
["793-16.04","UTIL","DIRECTIONAL BORE 4IN/FLEX SLEEVE",27.355607356715144]
["795-01.04","UTIL","6IN DIP SLIP JOINT WATER LINE",36.958206939538748]
["795-01.06","UTIL","8IN DIP SLIP JOINT WATER LINE",70.146462608967596]
["795-01.14","UTIL","16IN DIP SLIP JOINT WATER LINE",99.316734693877549]
["795-01.20","UTIL","24IN DIP SLIP JOINT WATER LINE",199.25]
["795-01.23","UTIL","36IN DIP RESTRAINED JOINT WATER LINE",293.25]
["795-01.24","UTIL","36IN DIP SLIP JOINT WATER LINE",315.5]
["795-02.01","UTIL","2IN HDPE WATER LINE",12.525259304453936]
["795-05.77","UTIL","BORE/JACK 12IN STEEL CASING PIPE-ROCK.",435.70584249084249]
["795-07.29","UTIL","24IN X 24IN TPPNG SLVE & VLVE",28075]
["795-08.22","UTIL","36IN BUTTERFLY VALVE ASSEMBLY",20005]
["795-10.09","UTIL","4IN AUTO AIR RELEASE VALVE ASSEMBLY",6210]
["795-11.01","UTIL","BLOW-OFF ASSEMBLY",2392.6096551724136]
["795-14.02","UTIL","CLASS B CONCRETE",204.30482905982907]
["795-14.08","UTIL","RESTORE ASPHALT",46.629649441703457]
["795-14.10","UTIL","RESTORE GRAVEL",21.335640207419225]
["795-15.13","UTIL","48IN STEEL CASING PIPE OPEN CUT METHOD",318.75]
["797-05.01","UTIL","8IN DIP GRAVITY SEWER 0FT-6FT DEPTH",108.77295918367346]
["797-05.04","UTIL","8IN DIP GRAVITY SEWER >18FT DEPTH",157.57258064516128]
["797-05.12","UTIL","12IN DIP GRAVITY SEWER >18FT DEPTH",216.74681135225376]
["797-05.18","UTIL","18IN DIP GRAVITY SEWER 6FT-12FT DEPTH",198.47457627118644]
["797-05.54","UTIL","8IN PVC GRAVITY SEWER >18FT DEPTH",143.24367704280155]
["797-06.81","UTIL","BORE/JACK 30IN STEEL CASING PIPE-ROCK.",765.8796208530805]
["797-06.94","UTIL","OPEN CUT 30IN STEEL CASING PIPE",234.3854961832061]
["797-07.01","UTIL","48IN MANHOLE 0FT-4FT DEPTH",3105.1582352941173]
["797-07.02","UTIL","48IN MANHOLE 4FT-6FT DEPTH",3616.0161194029847]
["797-07.09","UTIL","48IN MANHOLE 20FT-24FT DEPTH",9782.3222222222212]
["797-07.14","UTIL","60IN MANHOLE 6FT-8FT DEPTH",5210]
["797-07.17","UTIL","60IN MANHOLE 12FT-14FT DEPTH",7656.4285714285716]
["797-07.19","UTIL","60IN MANHOLE 16FT-20FT DEPTH",10377.5]
["797-07.21","UTIL","60IN MANHOLE 24FT-28FT DEPTH",18230]
["797-07.22","UTIL","60IN MANHOLE >28FT DEPTH",17760]
["797-07.56","UTIL","MANHOLE DROP CONNECTION ASSEMBLY",2804.9382352941175]
["797-08.04","UTIL","4IN PVC PIPE FOR SERVICE LATERAL",25.253981264637002]
["797-08.07","UTIL","4IN CLEAN OUT ASSEMBLY",244.12890410958903]
["797-08.20","UTIL","CONNECT SERVICE LINES (ALL SIZES)",616.3568181818182]
["797-10.05","UTIL","CONNECT 4IN LATERAL TO SEWER LINE",526.66666666666663]
["797-11.40","UTIL","RESTORE ASPHALT",39.485566027745421]
["797-11.41","UTIL","RESTORE CONCRETE",76.10888517279821]
["797-11.42","UTIL","RESTORE GRAVEL",14.12279569892473]
["202-03","ERTH","REMOVAL OF RIGID PAVEMENT, SIDEWALK, ETC.",6.4069377033755428]
["203-10","ERTH","EMBANKMENT (COMPACTED IN PLACE)",8.6038775327038177]
["307-01.02","ASPH","ASPHALT CEMENT (PG64-22) (BPMB-HM) GRADING A-S",617.61494295567365]
["307-01.03","ASPH","AGGREGATE (BPMB-HM) GRADING A-S MIX",63.851355463616891]
["607-07.03","DRNG","36\" CONCRETE PIPE CULVERT (CLASS IV)",105.23850574712644]
["607-08.30","DRNG","42\" PIPE CULVERT",166.1968845315904]
["607-09.03","DRNG","48\" CONCRETE PIPE CULVERT (CLASS IV)",213.55128205128204]
["607-10.04","DRNG","54\" CONCRETE PIPE CULVERT (CLASS V)",188]
["607-39.01","DRNG","15\" PIPE CULVERT (SIDE DRAIN)",34.917772151898738]
["607-39.06","DRNG","42\" PIPE CULVERT (SIDE DRAIN)",161.46808510638297]
["610-07.03","DRNG","18\" PIPE DRAIN (BRIDGE DRAIN)",41.482654338549075]
["611-07.30","STDR","15IN ENDWALL (SIDE DRAIN)",1455]
["611-07.66","STDR","42IN ENDWALL (CROSS DRAIN) 3:1",5985.2941176470586]
["611-07.69","STDR","48IN ENDWALL (CROSS DRAIN) 3:1",6173.1742857142863]
["611-38.04","STDR","CATCH BASINS, TYPE 38, > 12' - 16' DEPTH",9118.6175000000003]
["621-01.01","DRNG","TEMPORARY STRUCTURE (56' OF 18\" PIPE - STA 14+29.50)",81752.850000000006]
["621-01.02","DRNG","TEMPORARY STRUCTURE (90' OF 18\" PIPE - STA 15+12.00)",20533.333333333332]
["621-01.03","DRNG","TEMPORARY STRUCTURE (80' OF 18\" PIPE - STA 19+85.00)",23100]
["707-04","FNCE","WATER CROSSING",17.038205980066444]
["707-05","FNCE","WATER GATE",25]
["709-01.01","RIPR","RUBBLE STONE RIP-RAP",193.6058093797277]
["713-11.21","TRFP","P POST SLIP BASE",358.25550179211473]
["713-17.02","TRFP","INSTALL AUXILIARY SUPPORT FOR EXIT NUMBER PANEL",128.83095238095237]
["790-03.01","UTIL","POLE 40FT CLASS 2 WOOD",1295.1277272727273]
["790-04.04","UTIL","POLE 45FT CLASS 4 WOOD",1639.0990163934428]
["790-09.05","UTIL","POLE 70FT CLASS H2 METAL",8426.5233333333344]
["790-11.07","UTIL","POLE 80FT CLASS H4 METAL",20710]
["790-20.09","UTIL","POLE (SPECIFY POLE LENGTH, CLASS, AND MATERIAL) (80FT SELF SUPPORTING METAL)",59735]
["790-20.10","UTIL","POLE (SPECIFY POLE LENGTH, CLASS, AND MATERIAL) (80FT CLASS 1 METAL)",9775]
["790-20.11","UTIL","POLE (SPECIFY POLE LENGTH, CLASS, AND MATERIAL) (85FT CLASS H1 METAL)",10730]
["790-20.12","UTIL","POLE (SPECIFY POLE LENGTH, CLASS, AND MATERIAL) (90FT CLASS 1 METAL)",11100]
["790-20.13","UTIL","POLE (SPECIFY POLE LENGTH, CLASS, AND MATERIAL) (90FT CLASS H1 METAL)",11440]
["790-20.14","UTIL","POLE (SPECIFY POLE LENGTH, CLASS, AND MATERIAL) (92FT SELF SUPPORTING METAL)",64305]
["790-20.30","UTIL","TOP EXISTING POLE",280]
["790-20.31","UTIL","FIELD POLE MODIFICTION",55]
["790-20.51","UTIL","4 FT. DIA DRILLED PIER FOUNDATION",1775]
["790-20.52","UTIL","5 FT. DIA DRILLED PIER FOUNDATION",2575]
["790-20.53","UTIL","6 FT. DIA DRILLED PIER FOUNDATION",3440]
["790-25.17","UTIL","3PH VERTICAL DEADEND LARGE ANGLE 15KV",2237.83]
["790-25.29","UTIL","3PH CROSSARM SGL 10FT LRG COND 15KV",1083.0320512820513]
["790-25.30","UTIL","3PH CROSSARM DBL 10FT LRG COND 15KV",1977.8304347826086]
["790-25.37","UTIL","3PH 8FT FIBERGLASS CROSSARM DEADEND 15kV",1402.175]
["790-25.38","UTIL","3PH 10FT FIBERGLASS CROSSARM DEADEND 15kV",2123.542857142857]
["790-25.39","UTIL","3PH 8FT FIBERGLASS DOUBLE DEADEND 15kV",3004.19]
["790-25.40","UTIL","3PH 10FT FIBERGLASS DOUBLE DEADEND 15kV",3330]
["790-25.41","UTIL","3PH FIBERGLASS 8FT CROSSARM DOUBLE SUPPORT",1585]
["790-25.43","UTIL","3PH FIBERGLASS DOUBLE 10FT LARGE CONDUCTOR 15kV",1880]
["790-25.46","UTIL","3PH FIBERGLASS WITH NEUTRAL ON ARM",1935]
["790-33.21","UTIL","ANCHOR TWIN EYE POWER INSTALLED",582.28677325581396]
["790-40.09","UTIL","OH COND 336.4 18/1 ACSR MERLIN",3.4787772333048168]
["790-40.74","UTIL","OH PRI COND _____ _____ ____ ________ (3/8\" HIGH STRENGTH STEEL OHGW)",4.513175885643256]
["790-46.03","UTIL","1PH TRANSFORMER CONV W/XARM MTD FUSE & LA",1121.5820895522388]
["790-68.08","UTIL","POLE GROUND W/ PLTFM FOR AIR BREAK SWCH",1785]
["790-68.13","UTIL","SGL PHASE MOUNTING BRACKET - FIBERGLASS",300.63042016806719]
["790-69.11","UTIL","GROUND-GROUND ROD FOR ST POLE",292.49774774774772]
["790-69.18","UTIL","GND ASSY GOLB ON ST POLE",1730]
["790-69.28","UTIL","EXTENSION LINK - EPOXY -6FT",147.91081081081083]
["790-71.20","UTIL","TANGENT HOR LN POSTS 69KV MAX",2635.530303030303]
["790-71.21","UTIL","SML ANGLE HOR LINE POSTS 69KV MAX",3088.6363636363635]
["790-71.33","UTIL","DDE LRG VERT ANG 69KV MAX",6826.833333333333]
["790-71.50","UTIL","DDE 2 POLE 69KV MAX",10945]
["790-72.06","UTIL","GUY 3 BOLT CLAMP W/ THIMBLE CLEVIS",445]
["790-72.07","UTIL","GUY FACTORY FORMED WITH THIMBLE CLEVIS",321.88235294117646]
["790-72.10","UTIL","LIGHT DUTY GUYING PLATE - GUY ATTACHMENT",220]
["790-72.17","UTIL","MEDIUM DUTY POLE EYE PLATES",125]
["790-73.03","UTIL","LINE POST",1221.8125]
["790-73.15","UTIL","SWITCH GOAB 1W 1200A 69KV MAX",18505]
["791-05.02","UTIL","BORE/JACK 6IN - STEEL CASING PIPE - UNCON.",225]
["791-05.52","UTIL","6IN STEEL CASING OPEN CUT",130]
["791-06.10","UTIL","CONNECT TO 2IN EX. STL MAIN",5493.75]
["791-08.40","UTIL","RECONNECT SERVICE ASSEMBLY",700]
["795-13.05","UTIL","CREEK CROSSING",14415.051666666666]
["795-15.25","UTIL","16IN STEEL CASING PIPE OPEN CUT METHOD",172.56466828971395]
["805-01.03","LAND","TURF REINFORCEMENT MAT (CLASS III)",3.9683033472754339]
["707-01.01","FNCE","CHAIN-LINK FENCE (4-FOOT)",12.368830947511929]
["707-01.02","FNCE","END & CORNER POST ASSEMBLY(CHAIN-LINK FENCE 4')",211.89655172413794]
["712-09.02","TRFT","REMOVABLE PAVEMENT MARKING (8\" BARRIER LINE)",3.1815200357655478]
["714-08.20","LITE","FOUNDATION (ONLY) FOR LIGHT STANDARD",1372.8057553956835]
["714-08.30","LITE","REMOVE & RELOCATE LIGHT STANDARD",627.5]
["716-01.07","PVMK","TEMPORARY RAISED PAVEMENT MARKER,YELLOW",9.6554613920383989]
["725-20.23","ITS","STEEL OVERHEAD SIGN STRUCTURE (SPANS 71FT TO 90FT)",200000]
["725-20.43","ITS","PULL BOX (TYPE C)",698.33823529411768]
["725-20.44","ITS","PULL BOX (TYPE D)",1709.2142857142858]
["725-20.45","ITS","PULL BOX (TYPE E)",1838.6]
["725-20.56","ITS","CABLE (1/C #4 AWG.)",2.2999999999999998]
["725-21.05","ITS","DYNAMIC MESSAGE SIGN REMOVE & REPLACE",17720]
["725-22.24","ITS","CONDUIT BANK (TYPE 4)",9.1756812819249625]
["725-22.50","ITS","DMS CONDUIT BANK",13.65]
["725-23.01","ITS","ITS CABLE MARKER",156.72043010752688]
["725-23.10","ITS","FIBER OPTIC CABLE (72 F)",4.0080638387232259]
["725-23.21","ITS","FIBER OPTIC DROP CABLE (12 F)",2.0044585987261145]
["725-23.27","ITS","FIBER OPTIC CLOSURE (96F)",1000]
["725-23.28","ITS","FIBER OPTIC SPLICE FUSION",59.19178082191781]
["725-24.41","ITS","BURN-IN PERIOD",3341.5]
["725-24.51","ITS","SYSTEM INTEGRATION",9001.5]
["725-24.55","ITS","AS-BUILT PLANS",4005.7599999999998]
["797-11.30","UTIL","RETIREIN PLACE EXISTING SEWER <8IN",3.0277711561382596]
["802-13.11","LAND","ARONIA MELANOCARPA (BLCK CHOKEBERRY 2-5FT C.G.)",47.25]
["802-13.15","LAND","PHYSOCARPUS OPULIFOLIUS (NINEBARK) 2-5FT C.G.",34.445121951219512]
["202-01.13","ERTH","REMOVAL OF PIPE (24\",SIA RD. STA. 115+87)",46.02316602316602]
["407-20.05","ASPH","SAW CUTTING ASPHALT PAVEMENT",2.607442607008077]
["607-03.30","DRNG","18\" PIPE CULVERT",50.576195491972413]
["204-01","ERTH","CULVERT EXCAVATION (UNCLASSIFIED)",4.9361784424961321]
["730-40.01","TRFT","PORTABLE TRAFFIC SIGNAL SYSTEM",19500]
["202-13","ERTH","WATER WELL ABANDONMENT",3460.5650000000001]
["209-03.23","EROS","FILTER SOCK (24 INCH)",8.1312720396217912]
["209-08.09","EROS","FILTER SOCK CHECK DAM",205.62098814229248]
["604-15.01","MISC","PORTLAND CEMENT GROUT",237.34173076923076]
["606-24.12","INCI","TEMPORARY SHEET PILES",16.697957740733692]
["607-08.02","DRNG","42\" CONCRETE PIPE CULVERT (CLASS III)",121.17722974261203]
["707-03.01","FNCE","STOCK FENCE",5.5587376521776095]
["707-03.02","FNCE","END, BRACED LINE, CORNER POST ASSEMBLY(STOCK FENCE)",182.4651329787234]
["707-08.02","FNCE","GATE (POWER)",5805]
["712-09.07","TRFT","REMOVABLE PAVEMENT MARKING (STOP AHEAD)",300]
["730-02.13","TRFP","SIGNAL HEAD ASSEMBLY (140 A1)",866]
["730-10.02","TRFP","MESSENGER CABLE - 1/4\" DIAMETER",2.0860800000000004]
["730-11.10","TRFP","RISER ASSEMBLY (1'',RGS)",327.44666666666666]
["730-12.07","TRFP","CONDUIT 1\" DIAMETER (RGS)",14.799912434325744]
["730-13.01","TRFP","VEHICLE LOOP DETECTOR (SHELF MOUNT)",197.31677018633539]
["730-13.02","TRFP","VEHICLE DETECTOR (VIDEO)",7818.9428571428571]
["730-18.01","TRFP","MASTER CONTROLLER",5700.7900000000009]
["795-01.15","UTIL","18IN DIP RESTRAINED JOINT WATER LINE",149.12494553376905]
["795-01.16","UTIL","18IN DIP SLIP JOINT WATER LINE",110.37761674718196]
["795-01.17","UTIL","20IN DIP RESTRAINED JOINT WATER LINE",144.20882352941177]
["795-05.14","UTIL","HDD __IN HDPE CASING PIPE-UNCON (SEE PLANS)",46.959849999999996]
["795-05.69","UTIL","BORE/JACK 30IN STEEL CASING PIPE-UNCON.",482.33498920086396]
["795-08.16","UTIL","18IN GATE VALVE ASSEMBLY",16238.861428571428]
["795-08.18","UTIL","20IN GATE VALVE ASSEMBLY",17000]
["795-09.62","UTIL","1IN PEXa SERVICE PIPE",18.709580838323355]
["795-14.05","UTIL","CONCRETE ENCASEMENT",60.242266666666666]
["795-15.05","UTIL","20IN STEEL CASING PIPE OPEN CUT METHOD",173.17109929078015]
["797-03.08","UTIL","6IN PVC FORCE MAIN",43.912188527039135]
["797-06.75","UTIL","BORE/JACK 12IN STEEL CASING PIPE-ROCK.",368.53527777777782]
["797-09.22","UTIL","4IN COMBO AIR RELEASE VALVE ASSEMBLY",6019.4800000000005]
["797-10.10","UTIL","CONNECT EX.10-18IN SEWER TO NEW MANHOLE",2306.4100000000003]
["797-10.17","UTIL","CONNECT TO 6IN FORCE MAIN",2336.75]
["797-30.24","UTIL","OPEN CUT 12IN PVC CASING PIPE",126.80444444444444]
["202-08.15","RMVL","REMOVAL OF CURB AND GUTTER (STA. 11+22.29 TO 12+76.13)",6.2830417881438292]
["209-09.40","EROS","CURB INLET PROTECTION (TYPE 1)",209.2491]
["701-01.03","FLAT","CONCRETE SIDEWALK - 4 \" (STA. 11+22.29 TO 12+76.13)",10.3]
["716-01.30","PVMK","REMOVAL OF SNOWPLOWABLE REFLECTIVE MARKER",10.072626735063366]
["730-12.14","TRFP","CONDUIT 3\" DIAMETER (JACK AND BORE)",23.665461476261989]
["611-02.10","STDR","JUNCTION BOX, TYPE 1",4889.217391304348]
["621-05.02","INCI","TEMPORARY SHORING",150328.28]
["710-06.10","DRNG","LATERAL UNDERDRAIN ENDWALL (1:1)",450]
["713-02.04","TRFP","DELINEATOR (MILE MARKER) & STEEL POST",167.3321333333333]
["713-15.36","TRFP","REMOVE SIGN, SUPPORT & FOOTING",32.700000000000003]
["716-01.06","PVMK","TEMPORARY RAISED PAVEMENT MARKER,WHITE",9.4852956010086871]
["611-43.02","STDR","CATCH BASINS, TYPE 43, > 4' - 8' DEPTH",6469.3899999999994]
["611-43.03","STDR","CATCH BASINS, TYPE 43, > 8' - 12' DEPTH",6500]
["705-04.21","GAT","GUARDRAIL DELINEATION ENHANCEMENT",4.4150246305418719]
["713-02.33","TRFP","FLEXIBLE DELINEATOR (RED)",42]
["713-11.03","TRFP","2 1/2\" DIA ROUND STEEL TUBE SIGN POST",7.7414124466137899]
["716-08.06","PVMK","REMOVAL OF PAVEMENT MARKING (TURN LANE ARROW)",95.965077519379832]
["725-02.41","ITS","FIBER OPTIC TERMINATION SPLICE UNIT",1090]
["730-02.10","TRFP","SIGNAL HEAD ASSEMBLY (130 A2)",720.48780487804879]
["730-02.31","TRFP","SIGNAL HEAD ASSEMBLY (130A2 WITH BACKPLATE)",900.06591836734685]
["730-12.16","TRFP","CONDUIT (2\" SCHEDULE 80 PVC, DIRECTIONAL BORE)",8.6141647543395123]
["730-13.05","TRFP","VEHICLE DETECTOR (EXT. CALL - DELAY CALL)",199.76470588235293]
["730-23.38","TRFP","CANTILEVER SIGNAL SUPPORT (2 @ 45' & 55')",24752.924736842102]
["716-13.06","PVMK","SPRAY THERMO PVMT MRKNG (40 mil) (4IN LINE)",2145.9870224673537]
["795-05.91","UTIL","2IN PVC CASING PIPE OPEN CUT",26.06]
["795-06.33","UTIL","CUT AND CAP 6IN WATERLINE",1384.4325000000001]
["795-10.07","UTIL","3IN AUTOMATIC AIR RELEASE VALVE ASSEMBLY",4690.91]
["797-11.15","UTIL","48IN MH ADJUSTMENT INCREASE HEIGHT",697.38659574468079]
["607-16.06","DRNG","45\"X 29\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",134.6189078097475]
["793-01.01","UTIL","POLE 30FT CLASS 4 WOOD",1388.5142857142857]
["793-01.07","UTIL","POLE 35FT CLASS 4 WOOD",1192.5985135135136]
["793-03.12","UTIL","50 PAIR CABLE",4.546212482134349]
["793-04.06","UTIL","READY ACCESS CLOSURE",322.66435897435895]
["793-07.23","UTIL","FIBER OPTIC MAINTENANCE LOOP",245.3301282051282]
["793-07.41","UTIL","HOT SPLICE EXISTING FIBER CABLES",49.060846560846564]
["793-11.13","UTIL","BURIED RISER GUARD",123.96739726027398]
["793-12.17","UTIL","UG CABLE(DESCRIPTION)",2.2282352941176469]
["793-13.01","UTIL","2IN CASING",15]
["793-14.22","UTIL","UNDERGROUND CABLE",4.99509696969697]
["793-98.21","UTIL","TRIM UTILITY RIGHT-OF-WAY",8.5017391304347836]
["202-04.50","RMVL","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",26820.953333333335]
["202-04.51","RMVL","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",13550]
["303-10.04","BASE","MINERAL AGGREGATE (SIZE   )",44.06178053830228]
["604-01.04","STBR","1-1/2\" STEEL PIPE HANDRAIL",99.677419354838705]
["604-10.90","STBR","MISCELLANEOUS BRIDGE ITEMS",165500]
["611-01.04","STDR","MANHOLES, > 12' - 16' DEPTH",12735.791999999999]
["611-09.01","STDR","ADJUSTMENT OF EXISTING CATCHBASIN",1075.0961538461538]
["611-09.03","STDR","CAPPING EXISTING CATCHBASIN",1142.8948]
["621-05.01","INCI","TEMPORARY SHORING",15.014111559719337]
["701-01.02","FLAT","CONCRETE SIDEWALK (6 \")",7.8025700586208799]
["705-08.50","GAT","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-2",4368.9655172413795]
["705-05.09","GAT","BOLT SIDE GUIDE",50]
["713-15.07","TRFP","SUSPENDED FLAT SHEET ALUMINUM SIGN (0.080\" THICK)",310.30568807339444]
["713-16.06","TRFP","DEAD END SIGN AND SUPPORT",218.234375]
["714-14.03","LITE","MASTARM (DESCRIPTION)",1021.7142857142857]
["714-14.04","LITE","MASTARM (DESCRIPTION)",750]
["714-14.05","LITE","MASTARM (DESCRIPTION)",250]
["714-14.06","LITE","MASTARM (DESCRIPTION)",300]
["716-03.02","PVMK","PLASTIC WORD PAVEMENT MARKING (RXR)",446.42857142857144]
["716-04.12","PVMK","PLASTIC PAVEMENT MARKING (YIELD LINE)",22.18715201781669]
["716-13.03","PVMK","SPRAY THERMO PVMT MRKNG (60 mil) (8IN BARRIER LINE)",1.2875000000000001]
["725-02.16","ITS","CONDUIT (STRUCTURES - DESCRIPTION)",15]
["725-03.60","ITS","CABLE MARKER",224]
["725-05.04","ITS","SPLICE ENCLOSURE (UNDER GRADE)",700]
["725-05.06","ITS","FUSION SPLICE",72]
["730-02.08","TRFP","SIGNAL HEAD ASSEMBLY (130 POLE MOUNTED)",742.08749999999998]
["730-02.32","TRFP","SIGNAL HEAD ASSEMBLY (DESCRIPTION)",792.32615384615383]
["730-08.05","TRFP","SIGNAL CABLE - 12 CONDUCTOR",1.6900082491235306]
["730-08.10","TRFP","SIGNAL CABLE - (DESCRIPTION)",0.9799027593931372]
["730-08.31","TRFP","INTERCONNECT CABLE (12 FIBER MULTI-MODE)",2.1361650485436892]
["730-12.18","TRFP","CONDUIT (DESCRIPTION)",8]
["730-13.09","TRFP","VEHICLE DETECTOR (DESCRIPTION)",10884.2325]
["730-13.10","TRFP","VEHICLE DETECTOR (DESCRIPTION)",17066.666666666668]
["730-13.11","TRFP","VEHICLE DETECTOR (DESCRIPTION)",30000]
["730-23.31","TRFP","PEDESTAL POLE (DESCRIPTION)",2377.3333333333335]
["730-23.39","TRFP","CANTILEVER SIGNAL SUPPORT (DESCRIPTION)",25885.831999999999]
["730-26.05","TRFP","COUNTDOWN PEDESTRIAN SIGNAL",1060]
["730-26.06","TRFP","PEDESTRIAN PUSHBUTTON POST",1337.5625]
["730-26.09","TRFP","PEDESTRIAN PUSHBUTTON WITH 15IN SIGN",250]
["802-13.02","LAND","CALYCANTHUS FLORIDUS (SWEETSHRUB 2-5FT CNTNR GRWN)",20.357142857142858]
["802-13.06","LAND","HYDRANGEA QUERCIFOLIA (OAKLF HYDRANGEA 2-5FT CNTNR GRWN)",20.357142857142858]
["802-13.09","LAND","LINDERA BENZOIN (SPICEBUSH 2-5FT CNTNR GRWN)",30.471014492753625]
["802-13.16","LAND","CORYLUS AMERICANA (HAZELNUT) 2-5FT C.G.",20.26063829787234]
["802-13.21","LAND","VACCINIUM ARBOREUM (FARKLEBERRY 2-5FT C.G.)",18]
["802-13.54","LAND","CORNUS AMOMUM (SILKY DOGWOOD SDLNG BARE ROOT)",13.663043478260869]
["802-13.62","LAND","ILEX VERTICILLATA (CMMN WINTERBERRY SDLNG B.R.)",7.1609195402298846]
["204-03.01","STBR","WET EXCAVATION (BRIDGES)",39.187933774834434]
["204-10.01","STBR","FOUNDATION PREPARATION(PR NO.  ,STA          )",37853.983333333337]
["602-10.60","STBR","BEARING DEVICE (DESCRIPTION)",5941.8918918918916]
["606-03.03","STBR","STEEL PILES (12 INCH)",69.239492753623182]
["606-03.06","STBR","PILE TIPS (STEEL PILES, 12 INCH)",163.45538116591931]
["707-07.01","FNCE","CHAIN-LINK FENCE (BRIDGES)",22.978876308646761]
["307-01.07","ASPH","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING B-M",250]
["607-37.04","DRNG","30\" CORRUGATED METAL PIPE CULVERT",76.923913043478265]
["790-05.06","UTIL","POLE 50FT CLASS 2 METAL",4870.3506451612902]
["790-06.06","UTIL","POLE 55 FT CLASS 2 METAL",7388.5714285714284]
["790-07.02","UTIL","POLE 60FT CLASS 2 WOOD",2697.67]
["790-14.05","UTIL","POLE 95FT CLASS H2 METAL",8758.3333333333339]
["790-15.03","UTIL","POLE 100FT CLASS H6 METAL",7420]
["790-21.01","UTIL","1PH SGL PRIMARY SUPPORT 15KV",415.67413793103447]
["790-30.14","UTIL","SECONDARY CONDUCTOR 1/0 AL TRIPLEX",4.4323615743829228]
["790-30.22","UTIL","SECONDARY CONDUCTOR 1/0 AL QPLEX",9.5248837209302337]
["790-30.25","UTIL","SECONDARY CONDUCTOR 4/0 AL QPLEX",229.73036437246964]
["790-32.24","UTIL","GUY (DESCRIPTION)",433.54365853658538]
["790-32.25","UTIL","ANCHOR (DESCRIPTION)",776.38719512195121]
["790-36.13","UTIL","TRANSFER STREET LIGHT",365.32727272727271]
["790-58.03","UTIL","CUTOUT KNIFE SWITCH, SNGL LOADBREAK 15KV",2759.0333333333333]
["790-58.09","UTIL","3PH FUSE CUTOUT BRKT MT 15kV",1725]
["791-01.05","UTIL","6IN STEEL GAS MAIN",70.580361399391251]
["791-02.06","UTIL","8IN MDPE GAS MAIN",76.907142857142858]
["791-05.73","UTIL","12IN STEEL CASING",157.16999999999999]
["791-05.76","UTIL","6IN STEEL CASING",88.86]
["791-06.01","UTIL","CONNECT TO 1-1/4IN EX. PE MAIN",1350]
["791-06.05","UTIL","CONNECT TO 8IN EX. PE MAIN",2461.1999999999998]
["791-06.12","UTIL","CONNECT TO 6IN EX. STL MAIN",8692.1428571428569]
["791-07.04","UTIL","8IN PE GAS VALVE ASSEMBLY",3126.6538461538462]
["791-07.11","UTIL","6IN STEEL GAS VALVE ASSEMBLY",5175.82]
["791-08.06","UTIL","1/2IN PE SERVICE PIPE",21.815187752744077]
["791-08.09","UTIL","1-1/4IN PE SERVICE PIPE",66.715835601524233]
["791-08.10","UTIL","2IN PE SERVICE PIPE",61.917263751763045]
["791-09.31","UTIL","9LB MAGNESIUM ANODE",167]
["791-10.03","UTIL","RET. IN PLACE 1-1/4IN SERV CUT & PLUG",181.81818181818181]
["793-01.17","UTIL","POLE 45FT CLASS 3 WOOD",1751.25]
["793-13.32","UTIL","6 DUCT FORMATION @ 36IN DEPTH",53.627951711329267]
["793-14.09","UTIL","BRIDGE CONDUIT HANGER SYSTEM",131307.60399999999]
["793-14.14","UTIL","MULTI DUCT",5.2150818604247187]
["793-14.20","UTIL","PLACE MANHOLE OVER EXISTING CABLE",14951.492857142859]
["793-14.21","UTIL","ROD DUCTS",1.2868828595689619]
["793-16.22","UTIL","GROUND BED",712.94117647058829]
["795-01.19","UTIL","24IN DIP RESTRAINED JOINT WATER LINE",202.88659685863874]
["795-06.12","UTIL","CONNECT TO 24IN WATER LINE",7114]
["795-08.19","UTIL","24IN BUTTERFLY VALVE ASSEMBLY",7885.4444444444443]
["795-09.18","UTIL","3IN HDPE SERVICE PIPE",27.25]
["795-10.05","UTIL","2IN AUTO AIR RELEASE VALVE ASSEMBLY",3179.7184210526316]
["795-15.12","UTIL","42IN STEEL CASING PIPE OPEN CUT METHOD",444.4320224719101]
["797-07.08","UTIL","48IN MANHOLE 16FT-20FT DEPTH",8853.1176470588234]
["795-12.03","UTIL","PIPE GROUTING",48963.333333333336]
["797-10.11","UTIL","CONNECT EX. >18IN SEWER TO NEW MANHOLE",2407.8285714285712]
["798-05.03","UTIL","FIBER OPTIC CABLE SPLICE",5412]
["798-05.29","UTIL","COMMUNICATION ASSEMBLY (CSC)",71.730769230769226]
["798-05.32","UTIL","COMMUNICATION ASSEMBLY (DDE)",92]
["798-05.40","UTIL","COMMUNICATION ASSEMBLY (FOSS)",1068]
["798-06.13","UTIL","FIBER OPTIC CABLE (DESCRIPTION)",2.925854513584575]
["798-09.02","UTIL","REMOVE AERIAL CABLE/TERMINALS",1.2936318023928985]
["798-09.03","UTIL","REMOVE POLES, GUYS, ANCHORS",248.35294117647058]
["411-02.11","ASPH","ACS MIX(PG70-22) GRADING E RWDY",129.53394495412843]
["501-01.01","CONC","PORTLAND CEMENT CONCRETE PAVEMENT (PLAIN) 8\"",61]
["502-08.01","CONC","RESEALING JOINTS (HOT POURED ELASTIC)",1.7]
["713-11.23","TRFP","ROUND POST SLIP BASE",421.69890909090907]
["714-01","LITE","STRUCTURAL LIGHTING",8784.1333333333332]
["714-09.01","LITE","LUMINAIRES (150 WATT)",1600]
["716-04.07","PVMK","PLASTIC PAVEMENT MARKING (EXIT ONLY ARROW)",276.54374999999999]
["716-08.32","PVMK","HYDROBLAST REMOVAL OF PAVEMENT MARKING (DESCRIPTION)",1.9942021083242458]
["716-12.08","PVMK","ENHANCED FLAT LINE THERMO (12IN BARRIER LINE)",5.6934673366834172]
["716-12.10","PVMK","ENHANCED FLAT LINE THERMO (12IN DOTTED)",6.6618037703196959]
["730-08.04","TRFP","SIGNAL CABLE - 9 CONDUCTOR",1.3733825776872135]
["730-12.13","TRFP","CONDUIT 2\" DIAMETER (JACK AND BORE)",23.095259846591397]
["730-14.11","TRFP","PREFORMED DETECTION LOOP(DESCRIPTION)",1450]
["607-05.03","DRNG","24\" CONCRETE PIPE CULVERT (CLASS IV)",59.173374613003098]
["604-04.02","STBR","APPLIED TEXTURE FINISH (EXISTING STRUCTURES)",11.530844881537774]
["604-36","STBR","SCARIFYING",7.6638949671772432]
["615-02.17","STBR","PRESTRESSED CONCRETE BOX BEAM (36\" X 36\")",279.17391304347825]
["615-02.19","STBR","PRESTRESSED CONCRETE BOX BEAM (24\" X 36\")",210]
["303-01.09","BASE","MINERAL AGGREGATE, TYPE A BASE,GRADING D LIMESTONE",29.999031745982741]
["307-01.15","ASPH","ASC MIX (PG64-22) (BPMLC-HM) GRADING CS",98.61]
["411-03.23","ASPH","ACS MIX (PG76-22) OGFC",109.83280906264611]
["607-11.03","DRNG","60\" CONCRETE PIPE CULVERT (CLASS III)",342.51349823321556]
["607-13.03","DRNG","72\" CONCRETE PIPE CULVERT (CLASS III)",309.81818181818181]
["607-14.03","DRNG","78\" CONCRETE PIPE CULVERT (CLASS III)",415]
["611-02.14","STDR","JUNCTION BOX, TYPE 5",10652.5]
["713-16.50","TRFP","REMOVE AND REPLACE SIGN (DESCRIPTION)",2291.5]
["209-09.02","EROS","TEMPORARY SEDIMENT FILTER BAG (14'6\" X 2'0\" X 13'3\")",424.66]
["611-02.01","STDR","SPRING DRAIN BOX, TYPE 1",3974.6520000000005]
["712-04.02","TRFT","FLEXIBLE DRUMS (CHANNELIZATION)",21.585488505747126]
["716-09.33","PVMK","6 INCH DOTTED LINE",3.5826821192052982]
["797-03.38","UTIL","4IN PVC FORCE MAIN (0-8FT)",36.409999999999997]
["607-16.09","DRNG","60\"X 38\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",189.96666666666667]
["607-50.07","DRNG","PRECAST CONCRETE BOX CULVERT (12' X 6')",1400]
["607-50.12","DRNG","PRECAST CONCRETE BOX CULVERT (12'x7')",686.94825806451615]
["611-02.13","STDR","JUNCTION BOX, TYPE 4",10142.264999999999]
["705-02.10","GAT","GUARDRAIL TRANSITION 27IN TO 31IN",321.51851851851853]
["709-05.21","RIPR","DUMPED RIP-RAP",25]
["713-16.41","TRFP","RELOCATE SIGN",3190]
["716-01.12","PVMK","RAISED PVMT MARKERS (MONO-DIRECTIONAL) (1 COLOR LENS)",12.227701149425286]
["716-04.11","PVMK","PLASTIC PAVEMENT MARKING (BICYCLE SYMBOL W/RIDER)",290.11627906976742]
["801-02.08","LAND","TEMPORARY SEEDING (WITHOUT MULCH)",20.31873022512081]
["203-03.10","ERTH","SELECT GRANULAR MATERIAL",14.572596308897239]
["209-09.23","EROS","POLYACRYLAMIDE LIQUID",51.453804347826086]
["209-11.01","EROS","SEDIMENT BASIN RISER (24\")",3000]
["309-01.01","BASE","MINERAL AGGREGATE (A-CBC)",18.277470296848765]
["309-01.02","BASE","PORTLAND CEMENT (A-CBC)",213.19971147376387]
["309-02","ASPH","BITUMINOUS MATERIAL (A-CBC)",480.62708451874568]
["607-08.05","DRNG","42\" CONCRETE PIPE CULVERT(CLASS IV)JACKED-IN-PLACE",1239.2161016949153]
["607-39.07","DRNG","48\" PIPE CULVERT (SIDE DRAIN)",96.476190476190482]
["611-07.68","STDR","42IN ENDWALL (CROSS DRAIN) 6:1",8684.7222222222226]
["703-02","FLAT","CEMENT CONCRETE DITCH PAVING (REINFORCED)",517.96875]
["712-01.51","BARR","PORTABLE BARRIER RAIL DELINEATOR (DOUBLE)",7.7609756097560973]
["713-05","TRFP","STEEL HOLLOW SQUARE POST (BREAKAWAY) SIGN SUPPORTS",5.6544446147306564]
["713-15.35","TRFP","METAL BARRICADE (TYPE III)",568.86363636363637]
["714-03","LITE","JACKED OR BORED CONDUIT",19.365814446519611]
["714-06.07","LITE","CABLE (1/C # 2 AWG)",2.79688585884867]
["714-08.05","LITE","LIGHT STANDARDS (ALUMINUM)",3155.1724137931033]
["790-02.05","UTIL","POLE 35FT CLASS 6 WOOD",675]
["790-06.03","UTIL","POLE 55FT CLASS 3 WOOD",2174.2275]
["790-25.15","UTIL","3PH VERTICAL 15KV",1904.4642857142858]
["790-33.01","UTIL","EXPANDING TYPE ANCHOR 6,000LB-8,000LB",212.99928571428572]
["801-01.06","LAND","SEEDING (SPECIAL MIXTURE)",29.770309760374051]
["802-02.30","LAND","CUTTINGS: SALIX NIGRA (18IN-24IN LENGTH)",12.115120274914089]
["802-11.16","LAND","FRAXINUS PENNSYLVANICA (GREEN ASH 2-5FT CNTNR GRWN)",20.246710526315791]
["802-11.18","LAND","LIQUIDAMBER STYRACIFLUA (SWEETGUM 2-5FT CNTNR GRWN)",28.452991452991451]
["802-11.26","LAND","PLATANUS OCCIDENTALIS (SYCAMORE 2-5FT CNTNR GRWN)",27.092307692307692]
["802-11.31","LAND","QUERCUS FALCATA (SOUTHERN RED OAK 2-5FT CNTNR GRWN)",21.418967136150233]
["802-11.40","LAND","SALIX NIGRA (BLACK WILLOW 2-5FT CNTNR GRWN)",26.188481675392669]
["802-12.16","LAND","FRAXINUS PENNSYLVANICA (GREEN ASH SEEDLNG B.R.)",10.13187969924812]
["802-12.26","LAND","PLATANUS OCCIDENTALIS (SYCAMORE SEEDLNG B.R.)",14.510821428571429]
["802-12.31","LAND","QUERCUS FALCATA (SOUTHERN RED OAK SEEDLNG B.R.)",36.975853658536586]
["806-02.11","MOWL","PROJECT MOWING",700]
["202-01.03","ERTH","REMOVAL OF TRASH AND DEBRIS",3500]
["203-70.07","ERTH","STANDPIPE",3400]
["701-01.07","FLAT","EXPOSED AGGREGATE CONCRETE DRIVEWAY",12.877078085642319]
["713-14.22","TRFP","STREET NAME SIGN (SUSPENDED 0.100IN THICK)",53.472535940195506]
["725-03.44","ITS","FIBER OPTIC MODEM TRANSCEIVER (TYPE I)",4260]
["730-05.04","TRFP","MODIFY EXISTING ELECTRICAL SERVICE CONNECTION (SEE PLANS)",1683.25]
["730-08.41","TRFP","INTERCONNECT CABLE - FIBER OPTIC (24F, SINGLE MODE)",2.7349728456951885]
["730-23.03","TRFP","STEEL STRAIN POLE (38' SIGNAL SUPPORT)",14716.48]
["730-23.04","TRFP","STEEL STRAIN POLE (SIGNAL SUPPORT W/LUMINAIRE ARM)",10142.75]
["790-02.02","UTIL","POLE 35FT CLASS 3 WOOD",1118.5]
["790-04.01","UTIL","POLE 45FT CLASS 1 WOOD",1996.0763636363636]
["790-05.07","UTIL","POLE 50FT CLASS H1 METAL",5120.5261261261267]
["790-06.07","UTIL","POLE 55FT CLASS H1 METAL",5425.931818181818]
["790-07.07","UTIL","POLE 60FT CLASS H1 METAL",5007.088235294118]
["790-08.04","UTIL","POLE 65FT CLASS H2 METAL",7999]
["790-25.18","UTIL","3PH VERTICAL DEADEND LRG ANG LG COND 15KV",1749.9042857142856]
["790-25.20","UTIL","3PH VERTICAL DEADEND LG COND 15KV",2575]
["790-25.27","UTIL","3PH CROSSARM DDE 10FT ARMS LRG COND 15KV",2929.6666666666665]
["790-27.01","UTIL","DBL CKT CROSSARM 15KV",3285]
["790-27.06","UTIL","DBL CKT DBL XARM SM ANG 15KV",4170]
["790-30.01","UTIL","SECONDARY ASSEMBLIES SMALL ANGLE",195]
["790-32.19","UTIL","DN GUY HVY CONST - 1 PREFORM",549.25765306122446]
["790-32.20","UTIL","DN GUY HVY CONST-3 BOLT CLAMPS",419.55696202531647]
["790-32.21","UTIL","OH GUY HVY CONST -THROUGH BOLT TYPE",505.09375]
["790-33.31","UTIL","SCREW TYPE ANCHOR 23,000LB (F1-5D-P)",684.11864406779659]
["790-33.32","UTIL","SCREW TYPE ANCHOR 36,000LB (F1-6T-P)",734.58888888888885]
["790-58.04","UTIL","HOOK STICK SWITH LINE TENSION, SNGL 15KV",4415]
["790-60.01","UTIL","1PH FUSE CUTOUT XARM MOUNT 15KV",488.69874999999996]
["790-68.14","UTIL","3 MOUNTING BRACKET - FIBERGLASS",245]
["790-69.03","UTIL","10FT DBL CROSSARM",1253.8499999999999]
["790-69.27","UTIL","EXTENSION LINK - EPOXY -4FT",177.17227722772279]
["790-70.11","UTIL","STREET LIGHT - HPS  (250W)",833.08888888888885]
["791-01.08","UTIL","12IN STEEL GAS MAIN",181.35018275461039]
["791-04.20","UTIL","HDD 2IN STEEL PIPE - UNCONSOLIDATED",90.65836012861736]
["791-04.23","UTIL","HDD 6IN STEEL PIPE - UNCONSOLIDATED",124.5743626062323]
["791-04.25","UTIL","HDD 12IN STEEL PIPE - UNCONSOLIDATED",217.9367088607595]
["791-05.03","UTIL","BORE/JACK 8IN - STEEL CASING PIPE - UNCON.",134.12962962962962]
["791-06.33","UTIL","CONNECT TO 6IN EX. STL MAIN W/ STOPPLE",17990.650000000001]
["791-06.35","UTIL","CONNECT TO 12IN EX. STL MAIN W/ STOPPLE",55021.777777777781]
["791-08.03","UTIL","1IN SERVICE ASSEMBLY",1611.1197826086955]
["791-08.05","UTIL","2IN SERVICE ASSEMBLY",3277.0833333333335]
["791-09.04","UTIL","REGULATOR STATION",48753.857142857145]
["791-09.08","UTIL","REMOVE REGULATOR STATION",6043.5555555555557]
["791-10.02","UTIL","RETIRE IN PLACE 1IN SERV CUT & PLUG",1138.3333333333333]
["791-10.06","UTIL","RETIRE IN PLACE 6IN SERV CUT & PLUG",1675.3645833333333]
["791-10.08","UTIL","RETIRE IN PLACE 12IN SERV CUT & PLUG",1641.7142857142858]
["793-10.02","UTIL","BURIED CABLE @ 36IN DEPTH",20.054343971631205]
["795-01.07","UTIL","10IN DIP RESTRAINED JOINT WATER LINE",77.630017761989336]
["795-05.64","UTIL","BORE/JACK 14IN STEEL CASING PIPE-UNCON.",225.18878706199459]
["795-05.67","UTIL","BORE/JACK 20IN STEEL CASING PIPE-UNCON.",345.83884565499352]
["795-06.36","UTIL","CUT & CAP 10IN WATERLINE",1319.2124999999999]
["795-07.06","UTIL","8IN X 8IN TAPPING SLEEVE AND VALVE",4844.5851428571423]
["795-07.10","UTIL","10IN X 10IN TAPPING SLEEVE AND VALVE",5215.8474999999999]
["795-09.35","UTIL","(TI) OF 3IN PVC CASING FOR SERVICE PIPE-UNCON",12.25]
["795-09.60","UTIL","3/4IN PEXa SERVICE PIPE",16.857898832684825]
["795-10.06","UTIL","2IN MANUAL AIR RELEASE VALVE ASSEMBLY",4015]
["795-14.09","UTIL","RESTORE CONCRETE",74.799550449550452]
["795-15.03","UTIL","14IN STEEL CASING PIPE OPEN CUT METHOD",193.88888888888889]
["797-03.10","UTIL","12IN PVC FORCE MAIN",48.789289046878473]
["797-06.66","UTIL","BORE/JACK 20IN STEEL CASING PIPE-UNCON.",533.0535549399815]
["797-10.20","UTIL","CONNECT TO 12IN FORCE MAIN",3325.0833333333335]
["202-08.10","RMVL","REMOVAL OF CURB (FOR DRIVES AND RAISED ISLANDS)",4.1912754214863535]
["204-05.20","MISC","GROUT CASING INSTALLATION",61.87]
["502-04.01","CONC","SAWING CONCRETE PAVEMENT (FULL DEPTH)",6.1573410404624278]
["602-01","STBR","STRUCTURAL STEEL",1.5007252673796792]
["604-04.41","CONC","THREE STAR STATE EMBLEM",1419.881754385965]
["604-10.07","STBR","CONCRETE REMOVAL",10000]
["604-15.20","MISC","COMPACTION GROUT",51.14]
["607-09.05","DRNG","48\" CONCRETE PIPE CULVERT(CLASS IV)JACKED-IN-PLACE",2192.1296296296296]
["607-50.60","DRNG","THREE SIDED PRECAST CULVERT STRUCTURE - BARREL (27’ x 9.39583’)",3455]
["611-07.67","STDR","42IN ENDWALL (CROSS DRAIN) 4:1",5200.8999999999996]
["611-16.02","STDR","CATCH BASINS, TYPE 16, > 4' - 8' DEPTH",8041.1647058823519]
["615-01.10","STBR","PRESTRESSED CONCRETE BULB TEE BEAM (6\" WEB)(BT-54)",249.33342820549311]
["617-02","STBR","BRIDGE DECK CRACK SEALING",3.243551797040169]
["617-05","STBR","SEALANT (HMWM)",288.48837209302326]
["625-02.01","STBR","DRILLED SHAFT-SOIL (DIA.)",1076.367790335152]
["625-02.13","STBR","DRILLED SHAFT-ROCK (DIA.)",985.07883026064849]
["701-02.02","FLAT","CONCRETE DRIVEWAY (8\")",10.972768205559223]
["706-06.03","GAT","RADIUS RAIL",27.691368301026227]
["706-06.05","GAT","RADIUS RAIL LONG POST (6-9 FT)",27.110000000000003]
["712-08.01","NBI","UNIFORMED POLICE OFFICER",1]
["712-12.47","TRFT","BRIDGE MOUNTED INTERCONNECTED PORTABLE BARRIER RAIL",59.580876288659795]
["713-11.04","TRFP","SURFACE MNT BREAKAWAY BASE FOR SIGN POST",240]
["713-16.42","TRFP","RELOCATE SIGN & REWIRE",4244]
["730-01.01","TRFP","REMOVE & RELOCATE EXISTING TRAFFIC SIGNAL EQUIPMENT",640]
["730-08.11","TRFP","SIGNAL CABLE - (VIDEO DETECTION CABLE)",2.81]
["730-09.02","TRFP","SPAN WIRE ASSEMBLY (60,000 LBS. MIN. BRK STRENGTH)",3.672204334365325]
["730-11.01","TRFP","STEEL CONDUIT RISER ASSEMBLY",353.16]
["730-40.02","TRFT","TEMPORARY TRAFFIC SIGNAL SYSTEM",47436]
["790-06.05","UTIL","POLE 55 FT CLASS 1 METAL",5388.5442553191488]
["790-07.03","UTIL","POLE 60FT CLASS 3 WOOD",3013]
["790-08.01","UTIL","POLE 65FT CLASS 2 WOOD",3356.0225]
["790-08.02","UTIL","POLE 65FT CLASS 3 WOOD",3650]
["790-10.02","UTIL","POLE 75FT CLASS 2 WOOD",5146]
["790-25.06","UTIL","3PH CROSSARM DBL 15KV",1703]
["790-26.22","UTIL","3PH VERTICAL DDE ANGLE LRG COND 25KV",2341.9949999999999]
["790-26.29","UTIL","3PH DDE UNBALANCED LOAD 25KV",2884.3125]
["790-26.32","UTIL","3PH CROSSARM 10FT FBRGLS X-ARM DDE 25KV",2978.3333333333335]
["790-27.10","UTIL","DBL CKT CROSSARM DDE 15KV",6695]
["790-27.11","UTIL","DBL CKT CROSSARM 3PH TAP 15KV",3204]
["790-31.21","UTIL","SERVICE CONDUCTOR 2/0 AL QPLEX",10.46]
["790-33.19","UTIL","ROCK ANCHOR TRIPLE EYE 53IN EXPANDING",880.36363636363637]
["790-41.05","UTIL","UG PRI COND 3/0 AL 15KV",9.77]
["790-41.63","UTIL","UG SEC COND QDLX ____ __ __ (1/0AL)",7.97]
["790-42.17","UTIL","2 DUCT BANK @ 36IN-48IN DEPTH",240]
["790-43.47","UTIL","PRIMARY PULLBOX",4430.8243750000001]
["790-43.52","UTIL","SECONDARY RISER W/ 4IN CONDUIT",1604.3125]
["790-43.60","UTIL","PRIMARY RISER (THREE PHASE SINGLE CONDUCTOR)",9200.6380769230764]
["790-54.01","UTIL","1.5KVA 1PH OH  XFORMER 14 .4KV 120/240",2011]
["790-59.02","UTIL","HOOK STICK SWITCH VERTICAL - SINGLE 25KV",4226.7]
["790-63.15","UTIL","3PH ELECTR RECL 800A CONT 16000A INT 25KV",31960.666666666668]
["790-65.05","UTIL","LIGHTNING ARRESTER ARM MTD 18 KV",395.24117647058824]
["790-65.17","UTIL","3PH CAPACITOR ASSEMBLY 25KV",12671.701666666666]
["790-69.08","UTIL","GROUND-GROUND ROD",329.69654867256645]
["790-69.31","UTIL","STICK PIN",453.916]
["790-70.22","UTIL","STREET LIGHT (METAL POLE MOUNTED)",1032.7777777777778]
["790-70.23","UTIL","STREET LIGHT (RENTAL LIGHT)",973.75]
["791-03.05","UTIL","6IN HDPE GAS MAIN",67.398826836123675]
["791-03.06","UTIL","8IN HDPE GAS MAIN",110]
["791-05.01","UTIL","BORE/JACK 4IN - STEEL CASING PIPE - UNCON.",170]
["791-05.04","UTIL","BORE/JACK 12IN - STEEL CASING PIPE - UNCON.",207.75949367088609]
["791-05.07","UTIL","BORE/JACK___IN - STEEL CASING PIPE - UNCON. (BORE/JACK 2IN - STEEL CASING PIPE - UNC ON.)",170]
["791-05.14","UTIL","BORE/JACK ___IN - STEEL CASING PIPE - UNCON. (BORE/JACK 10IN - STEEL CASING PIPE - UN CON.)",380]
["791-08.01","UTIL","1/2IN SERVICE ASSEMBLY",1140]
["791-08.04","UTIL","1-1/4IN SERVICE ASSEMBLY",960]
["791-08.08","UTIL","1IN PE SERVICE PIPE",26.633323917137478]
["793-01.03","UTIL","POLE 30FT CLASS 6 WOOD",2202]
["793-02.93","UTIL","OVERHEAD GUY WIRE (SEE PLANS)",202.73000000000002]
["793-07.22","UTIL","FIBER SPLICE-12 FIBER RIBBON",606.89655172413791]
["793-15.02","UTIL","TRANSFER DROP ATTACHMENT",45.425125000000001]
["795-01.02","UTIL","4IN DIP SLIP JOINT WATER LINE",76.999985569985583]
["795-05.78","UTIL","BORE/JACK 14IN STEEL CASING PIPE-ROCK.",358.02510460251045]
["795-09.04","UTIL","2IN WATER SERVICE METER ASSEMBLY",4273.3131818181819]
["795-09.05","UTIL","3IN WATER SERVICE METER ASSEMBLY",10953]
["795-09.06","UTIL","4IN WATER SERVICE METER ASSEMBLY",19324]
["795-09.11","UTIL","1-1/2IN COPPER SERVICE PIPE",55.125]
["795-09.12","UTIL","2IN COPPER SERVICE PIPE",55.822093023255817]
["795-10.04","UTIL","1IN MANUAL AIR RELEASE VALVE ASSEMBLY",890]
["797-01.02","UTIL","6IN DIP FORCE MAIN",140]
["797-05.09","UTIL","12IN DIP GRAVITY SEWER 0FT-6FT DEPTH",121.71978021978022]
["797-05.11","UTIL","12IN DIP GRAVITY SEWER 12FT-18FT DEPTH",205.7661714285714]
["797-05.17","UTIL","18IN DIP GRAVITY SEWER 0FT-6FT DEPTH",198.33333333333334]
["797-05.19","UTIL","18IN DIP GRAVITY SEWER 12FT-18FT DEPTH",264.70384615384614]
["797-05.59","UTIL","12IN PVC GRAVITY SEWER 0FT-6FT DEPTH",73.353072625698317]
["797-06.77","UTIL","BORE/JACK 16IN STEEL CASING PIPE-ROCK.",1048.01812849162]
["797-06.79","UTIL","BORE/JACK 20IN STEEL CASING PIPE-ROCK.",1238]
["797-06.84","UTIL","BORE/JACK __IN STEEL CASING PIPE-ROCK (28)",1245.264375]
["797-06.91","UTIL","OPEN CUT 18IN STEEL CASING PIPE",256.31578947368422]
["797-06.92","UTIL","OPEN CUT 20IN STEEL CASING PIPE",271.6572463768116]
["797-09.26","UTIL","2IN AIR/VAC VALVE ASSEMBLY",4676.5311111111114]
["797-10.08","UTIL","CONNECT EX. 6IN SEWER TO NEW MANHOLE",1588]
["797-11.20","UTIL","48IN MH ADJUSTMENT DECREASE HEIGHT",777.58620689655174]
["797-11.32","UTIL","RETIREIN PLACE EXISTING SEWER 15IN-24IN",9.4163975155279509]
["209-09.42","EROS","CURB INLET PROTECTION (TYPE 3)",332.3]
["303-02","BASE","MINERAL AGGREGATE, TYPE B BASE, GRADING (D)",26.285097192224622]
["307-01.20","ASPH","ASP. CONC. MIX(PG64-22) (BPMB-HM) GR. A-S",73.840334714695558]
["415-01.03","ASPH","COLD PLANING BITUMINOUS PAVEMENT",20.74209940652819]
["607-20.04","DRNG","36\" CROSSDRAIN PIPE CULVERT(COLLECTORS & LOCAL ROADS)",81]
["790-30.08","UTIL","SECONDARY CONDUCTOR 2 AL DUPLEX",2.71]
["791-10.05","UTIL","RETIRE IN PLACE 4IN SERV CUT & PLUG",2098.5192307692309]
["795-07.32","UTIL","INSERTION VALVE (8IN)",6636.363636363636]
["795-09.17","UTIL","2IN HDPE SERVICE PIPE",15.759777123633306]
["795-13.02","UTIL","HDPE FITTINGS",6.7071428571428573]
["502-03.13","CONC","CONCRETE PAVEMENT REMOVAL",17.782213955026457]
["714-06.04","LITE","CABLE (1/C # 8 AWG)",0.76610625568636093]
["714-08.46","LITE","FOUNDATION (ONLY) FOR HIGH MAST LIGHT STANDARD",9748.4166666666661]
["714-09.06","LITE","LUMINAIRES (1000 WATT - HIGH MAST)",1750]
["714-12.10","LITE","RELOCATION OF CONTROL CENTER",2500]
["607-16.01","DRNG","23\"X 14\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",72.691972789115638]
["611-26.02","STDR","CATCH BASINS, TYPE 26, > 4' - 8' DEPTH",6432.1500000000005]
["611-39.03","STDR","CATCH BASINS, TYPE 39, > 8' - 12' DEPTH",9407.2228571428568]
["611-40.02","STDR","CATCH BASINS, TYPE 40, > 4' - 8' DEPTH",7023.2174999999997]
["611-43.01","STDR","CATCH BASINS, TYPE 43, 0' - 4' DEPTH",6312.69]
["713-15.06","TRFP","MILE POST SIGN",173.27076923076922]
["730-08.32","TRFP","INTERCONNECT CABLE (6 FIBER MULTIMODE)",3]
["790-28.02","UTIL","DBL CKT LRG COND CONST 25KV",3102.9]
["790-30.12","UTIL","SECONDARY CONDUCTOR 4 AL TRIPLEX",1.973438101347017]
["790-30.24","UTIL","SECONDARY CONDUCTOR 3/0 AL QPLEX",7.94]
["790-32.28","UTIL","DOUBLE OVERHEAD GUY LIGHT CONSTRUCTION - PREFORM",225.84]
["790-41.06","UTIL","UG PRI COND 4/0 AL 15KV",75.630342270393612]
["790-64.09","UTIL","SEC MTG 3PH W/ TRANSFORMER CABINET",4083.83]
["790-69.23","UTIL","PAIR OF 10IN OR THREE 6IN BELLS",118.976]
["791-04.11","UTIL","HDD 2IN PE PIPE - ROCK",147.36186770428014]
["791-04.13","UTIL","HDD 4IN PE PIPE - ROCK",99.749253731343288]
["791-04.14","UTIL","HDD 6IN PE PIPE - ROCK",254.88644992880873]
["793-01.05","UTIL","POLE 35FT CLASS 2 WOOD",975.22749999999996]
["793-02.92","UTIL","OVERHEAD GUY WIRE (SEE PLANS)",146.97]
["793-03.01","UTIL","25 PAIR GROUP AERIAL SPLICE",4.0460965184954922]
["793-03.04","UTIL","16M STRAND",3.41]
["793-03.08","UTIL","1200 PAIR OR GREATER CABLE",49.63]
["793-03.11","UTIL","25 PAIR CABLE",3.9308762886597939]
["793-03.14","UTIL","100 PAIR CABLE",6.1651202277464279]
["793-03.16","UTIL","200 PAIRCABLE",9.66]
["793-03.17","UTIL","300 PAIR CABLE",13.117948717948718]
["793-03.19","UTIL","600 PAIR CABLE",18.64]
["793-03.20","UTIL","900 PAIR CABLE",25.39]
["793-03.21","UTIL","1200 PAIR CABLE",49.31]
["793-04.12","UTIL","UNDERGROUND SPLICE CLOSURE",1567.2]
["793-07.51","UTIL","72 FIBER (MATERIAL ONLY)",2.37]
["793-09.01","UTIL","25 PAIR BURIED CABLE",5.0962499999999995]
["793-09.02","UTIL","50 PAIR BURIED CABLE",6.2282758620689656]
["793-09.04","UTIL","100 PAIR BURIED CABLE",7.8216788321167892]
["793-09.07","UTIL","300 PAIR BURIED CABLE",14.638749999999998]
["793-10.20","UTIL","EXPOSE EXISTING CABLE/CONDUIT (ALL DEPTHS)",19.706637931034482]
["793-11.06","UTIL","8IN PEDESTAL",311.49727272727273]
["793-11.15","UTIL","5 PAIR BURIED DROP",2.8127091633466135]
["793-12.02","UTIL","REARRANGEMENT EXISTING CABLE",172.18154929577463]
["793-12.08","UTIL","600 PAIR UG CABLE",25.940000000000005]
["793-12.12","UTIL","1800 PAIR UG CABLE",88.239999999999981]
["793-12.15","UTIL","3000 PAIR UG CABLE",102.01000000000002]
["793-13.09","UTIL","2IN SCHEDULE 40 PVC",9.6871428571428559]
["793-13.10","UTIL","3IN SCHEDULE 40 PVC",19.72]
["793-14.26","UTIL","UNDERGROUND TO OVERHEAD RISER",186.38]
["793-16.02","UTIL","DIRECTIONAL BORE 2IN/FLEX SLEEVE",24.236502946954815]
["793-98.03","UTIL","REMOVE CARRIER CABINET",315.02]
["795-10.24","UTIL","12IN PRV ASSEMBLY",44763.66]
["795-14.07","UTIL","CONCRETE VAULT",9445.5933333333323]
["797-11.10","UTIL","48IN MANHOLE REHABILITATION",2664.5]
["713-15.04","TRFP","INSTALLATION OF LETTERS & ARROWS",2100]
["716-04.04","PVMK","PLASTIC PAVEMENT MARKING (TRANSVERSE SHOULDER)",8.1072918245804004]
["716-08.08","PVMK","REMOVAL OF PAVEMENT MARKING (DOUBLE TURNING ARROW)",78.75]
["790-21.02","UTIL","1PH SGL PRIMARY SUPPORT MISC 15KV",148.92714285714285]
["790-33.15","UTIL","1IN TRIPLE EYE",547.23]
["790-36.04","UTIL","TRANSFER SERVICE",97.514463276836167]
["790-36.05","UTIL","TRANSFER SECONDARY",149.375]
["790-36.08","UTIL","TRANSFER SECONDARY/SERVICE ASSEMBLY",261.39333333333337]
["790-36.14","UTIL","TRANSFER CONDUCTOR",200.70620253164554]
["790-40.38","UTIL","OH COND 3/0 7 AAC PHLOX",3.2981494661921711]
["790-40.46","UTIL","OH COND 556.5 19 AAC DAHLIA",4.8011917098445593]
["790-41.03","UTIL","UG PRI COND 1/0 AL 15KV",10.782130872483222]
["790-42.08","UTIL","2IN DIA PVC PIPE",8.3092913385826783]
["790-42.16","UTIL","1 DUCT @ 36IN-48IN DEPTH",112.6636966126657]
["790-43.45","UTIL","FIBERGLASS VAULT-TRANS PAD-SMALL",1181.9100000000001]
["790-43.50","UTIL","SECONDARY RISER W/ 2IN CONDUIT",1236.3458536585367]
["790-50.01","UTIL","1PH PAD MTD TRANSFORMER RADIAL FEED",2961.44]
["790-74.25","UTIL","FIBER SPLICE-12 FIBER RIBBON",1361.6605555555554]
["791-04.02","UTIL","HDD 2IN PE PIPE - UNCONSOLIDATED",52.611619718309861]
["791-04.04","UTIL","HDD 4IN PE PIPE - UNCONSOLIDATED",81.914824846514989]
["791-04.05","UTIL","HDD 6IN PE PIPE - UNCONSOLIDATED",55.692373750320435]
["791-06.39","UTIL","CONNECT TO 4IN EX. CI/DI MAIN W/ STOPPLE",8400]
["791-08.17","UTIL","HDD 3/4IN PE SERVICE PIPE",54.849813722446449]
["791-08.18","UTIL","HDD 1IN PE SERVICE PIPE",16.776315789473685]
["793-01.14","UTIL","POLE 45FT CLASS 1 WOOD",1928.57]
["793-01.19","UTIL","POLE 50FT CLASS 1 WOOD",2357.14]
["795-02.04","UTIL","6IN HDPE WATER LINE",30.119819819819821]
["795-02.05","UTIL","8IN HDPE WATER LINE",31.5]
["795-02.08","UTIL","14IN HDPE WATER LINE",61.95]
["795-05.06","UTIL","HDD 12IN HDPE CASING PIPE-UNCON",96.538461538461533]
["795-05.08","UTIL","HDD 16IN HDPE CASING PIPE-UNCON",131.25]
["795-06.08","UTIL","CONNECT TO 14IN WATER LINE",3150]
["795-06.09","UTIL","CONNECT TO 16IN WATER LINE",3268.8888888888887]
["795-06.31","UTIL","CUT AND CAP 2IN WATER LINE",620]
["795-06.32","UTIL","CUT AND CAP 4IN WATERLINE",1073.5174999999999]
["795-06.34","UTIL","CUT AND CAP 8IN WATERLINE",1606.9285714285713]
["795-06.35","UTIL","CUT AND CAP SERVICE LINE",105]
["795-06.38","UTIL","CUT AND CAP 14IN WATERLINE",1470]
["795-06.39","UTIL","CUT AND CAP 16IN WATER LINE",2247.1428571428573]
["795-07.21","UTIL","16IN X 16IN TAPPING SLEEVE AND VALVE",15330]
["795-07.22","UTIL","14IN X 6IN TAPPING SLEEVE AND VALVE",4200]
["795-08.12","UTIL","14IN GATE VALVE ASSEMBLY",8925]
["795-08.13","UTIL","16IN BUTTERFLY VALVE ASSEMBLY",9000]
["795-11.12","UTIL","RETIRE IN PLACE EXISTING WATER MAIN",1.6377777777777778]
["795-13.06","UTIL","CREEK CROSSING (#) (2)",4463.333333333333]
["795-13.07","UTIL","CREEK CROSSING (#) (3)",5875]
["795-13.08","UTIL","CREEK CROSSING (#) (4)",5875]
["795-15.09","UTIL","28IN STEEL CASING PIPE OPEN CUT METHOD",236.25]
["795-15.22","UTIL","6IN STEEL CASING PIPE OPEN CUT METHOD",63]
["797-02.04","UTIL","2IN HDPE FORCE MAIN",13.65]
["797-03.07","UTIL","8IN PVC FORCE MAIN",36.088883208808497]
["797-06.68","UTIL","BORE/JACK 30IN STEEL CASING PIPE-UNCON.",526.05906354515048]
["797-06.71","UTIL","BORE/JACK __IN STEEL CASING PIPE-UNCON. (6'')",423.64682926829272]
["797-06.93","UTIL","OPEN CUT 24IN STEEL CASING PIPE",178.72617187500001]
["797-07.80","UTIL","REMOVE SEWER MANHOLE",915.40918367346933]
["797-08.34","UTIL","8IN INSERTION VALVE",10389.75]
["797-08.36","UTIL","12IN INSERTION VALVE",13991.25]
["797-09.04","UTIL","2IN PVC BALL VALVE",600.60833333333335]
["797-09.08","UTIL","8IN PLUG VALVE ASSEMBLY",3072.5]
["797-09.10","UTIL","12IN PLUG VALVE ASSEMBLY",5872.666666666667]
["797-09.20","UTIL","2IN COMBO AIR RELEASE VALVE ASSEMBLY",5214.5969999999998]
["797-09.40","UTIL","CUT AND CAP (ALL LINES)",1088.7941176470588]
["797-10.18","UTIL","CONNECT TO 8IN FORCE MAIN",2047.3333333333333]
["797-10.31","UTIL","RESIDENTIAL GRINDER PUMP STATION",10990.18375]
["797-11.39","UTIL","TV INSPECTION",2.0492987955782871]
["797-11.44","UTIL","STREAM CROSSING (#)",3281.25]
["805-12.03","LAND","EROSION CONTROL BLANKET (TYPE III)",1.4844338891990851]
["209-03.21","EROS","FILTER SOCK (12 INCH)",3.9762458680041028]
["604-10.51","STBR","SCARIFYING",25.244730679156909]
["202-02.20","ERTH","REMOVAL OF PIPE (18'', STA. 116+40)",9.0123456790123448]
["202-02.21","ERTH","REMOVAL OF PIPE (18'', STA. 119+90)",15.988448793227585]
["202-02.22","ERTH","REMOVAL OF PIPE (18\", STA. 109+60)",15.070214415962777]
["607-50.13","DRNG","PRECAST CONCRETE BOX CULVERT (8'-0\" x 8'-0\")",598.57000000000005]
["611-13.01","STDR","CATCH BASINS, TYPE 13, 0' - 4' DEPTH",3779.37]
["611-13.02","STDR","CATCH BASINS, TYPE 13, > 4' - 8' DEPTH",3684.78]
["701-02.01","FLAT","CONCRETE CURB RAMP (RETROFIT)",27.661379800853485]
["705-06.20","GAT","TANGENT ENERGY ABSORBING TERM MASH TL-3",2657.9695189873419]
["791-06.24","UTIL","CONNECT TO 4IN EX. PE MAIN",4233.9285714285716]
["793-98.05","UTIL","RETIRE BURIED FACILITIES IN PLACE",3.5]
["795-05.82","UTIL","BORE/JACK 24IN STEEL CASING PIPE-ROCK.",591.73801662707842]
["795-21.02","UTIL","RETIRE WATER VALVES AND HYDRANTS",4888.88]
["797-05.21","UTIL","24IN DIP GRAVITY SEWER 0FT-6FT DEPTH",306.18]
["797-05.22","UTIL","24IN DIP GRAVITY SEWER 6FT-12FT DEPTH",242.84000000000003]
["797-05.23","UTIL","24IN DIP GRAVITY SEWER 12FT-18FT DEPTH",131.76]
["797-05.24","UTIL","24IN DIP GRAVITY SEWER >18FT DEPTH",136.52000000000001]
["797-05.30","UTIL","__IN DIP GRAVITY SEWER 6FT-12FT DEPTH (SEE PLANS)",101.42749999999999]
["797-05.31","UTIL","__IN DIP GRAVITY SEWER 12FT-18FT DEPTH (SEE PLANS)",250.51]
["797-05.32","UTIL","__IN DIP GRAVITY SEWER >18FT DEPTH (SEE PLANS)",88.52]
["797-05.61","UTIL","12IN PVC GRAVITY SEWER 12FT-18FT DEPTH",80.501525204653177]
["797-07.27","UTIL","72IN MANHOLE 10FT-12FT DEPTH",6663.55]
["797-07.28","UTIL","72IN MANHOLE 12FT-14FT DEPTH",8216.4699999999993]
["797-08.10","UTIL","2IN LOW PRESS SERVICE ASSEMBLY",1018.2599999999999]
["797-08.12","UTIL","2IN END OF LINE FLUSHING ASSEMBLY",1392.97]
["920-08.22","INCI","TEMPORARY SHORING",27.621674237508113]
["607-20.01","DRNG","18\" CROSSDRAIN PIPE CULVERT(COLLECTORS & LOCAL ROADS)",51.462311557788944]
["607-20.02","DRNG","24\" CROSSDRAIN PIPE CULVERT(COLLECTORS & LOCAL ROADS)",101]
["713-02.21","TRFP","SIGN POST DELINEATION ENHANCEMENT",6.6384598776538333]
["713-11.22","TRFP","U POST SLIP BASE",332.49074074074076]
["790-01.04","UTIL","POLE 30FT CLASS 5 WOOD",656.56666666666661]
["790-02.03","UTIL","POLE 35FT CLASS 4 WOOD",1157.7023076923076]
["790-22.02","UTIL","1PH DBL PRIMARY SUPPORT 25KV",306.25]
["790-22.07","UTIL","1PH DBL PTS ANGLE 25KV",322.54636363636359]
["790-22.15","UTIL","1PH DEAD END TAP W/ EXTENSION 25KV",946.30116279069773]
["790-24.02","UTIL","2PH DBL CROSSARM, ANGLE 25KV",685]
["790-26.13","UTIL","3PH CROSSARM DBL SM ANGLE LRG COND 25KV",1192.5048275862068]
["790-26.37","UTIL","3PH XARM DBL 10FT LG COND NOX SM ANG 25KV",1259.9000000000001]
["790-26.38","UTIL","3PH CROSSARM 10FT LRG COND 25KV",1000]
["790-32.12","UTIL","OH GUY - CROSSARM DEADEND HEAVY DUTY",954]
["791-06.13","UTIL","CONNECT TO 8IN EX. STL MAIN",3762.8571428571427]
["791-07.12","UTIL","8IN STEEL GAS VALVE ASSEMBLY",17491.090909090908]
["791-10.07","UTIL","RETIRE IN PLACE 8IN SERV CUT & PLUG",908.14814814814815]
["795-05.04","UTIL","HDD 8IN HDPE CASING PIPE-UNCON",165.6]
["797-06.61","UTIL","BORE/JACK 10IN STEEL CASING PIPE-UNCON.",182]
["202-01.02","STBR","REMOVAL OF ASBESTOS",12975]
["202-04.04","RMVL","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",163800]
["202-04.05","RMVL","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",190800]
["202-04.06","RMVL","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",7166.666666666667]
["202-04.07","RMVL","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",2000]
["202-04.08","RMVL","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",1500]
["202-04.09","RMVL","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",12200]
["202-04.10","RMVL","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",4300]
["202-04.11","RMVL","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",2000]
["204-14","STBR","CORE DRILLING FOR PILES(ROCK)",285.04371584699453]
["204-15","STBR","CORE DRILLING FOR PILES(SOIL)",139.61690962099127]
["307-01.21","ASPH","ASP. CONC. MIX(PG70-22) (BPMB-HM) GR. A-S",67.992288287175825]
["307-03.10","ASPH","ASPHALT CONC MIX (PG76-22)(BPMB-HM) GR CS",92.466408945814948]
["602-10.17","STBR","STEEL PILING",125]
["604-03.07","STBR","CLASS A CONCRETE (DESCRIPTION)",528.18891335844683]
["606-04.03","STBR","STEEL PILES (14 INCH)",93.386773547094194]
["607-10.02","DRNG","54\" CONCRETE PIPE CULVERT (CLASS III)",162.84585218702864]
["607-16.05","DRNG","45\"X 29\" HORIZONTAL OVAL CONCRETE PIPE CULVERT (CLASS__)",130]
["607-16.08","DRNG","53\"X 34\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",174.404296875]
["611-42.04","STDR","CATCH BASINS, TYPE 42, > 12' - 16' DEPTH",7613.333333333333]
["611-44.02","STDR","CATCH BASINS, TYPE 44, > 4' - 8' DEPTH",17533.333333333332]
["624-03.01","WALL","RETAINING WALL REINFORCING STEEL",0.85000000000000009]
["705-06.01","GAT","W BEAM GR (TYPE 2) MASH TL3",18.934014321298928]
["705-06.10","GAT","GR TERMINALTRAILING END (TYPE 13) MASH TL3",1006.3581564245809]
["705-06.11","GAT","GR TERMINAL (IN-INLINE) MASH TL3",674.51374999999996]
["705-06.30","GAT","GR TERMINAL (TYPE 21) MASH TL2",2386.525352112676]
["705-20.25","GAT","TEMPORARY CRASH CUSHION (MASH TL-3)",6230.7616525423728]
["725-02.79","ITS","FIBER SPLICE ENCLOSURE(DESCRIPTION)",1073.6333333333334]
["725-20.75","ITS","COMMUNICATION CONNECTION (DESCRIPTION)",2500]
["725-20.91","ITS","CCTV CAMERA SYSTEM (PAN TILT & ZOOM)",9500]
["725-21.15","ITS","NETWORK SWITCH (DESCRIPTION)",10320]
["725-23.24","ITS","FIBER OPTIC DROP CABLE (DESCRIPTION)",450]
["725-23.32","ITS","FIBER OPTIC SPLICE MODIFICATION",625]
["730-13.06","TRFP","VEHICLE DETECTOR (OPTICALLY ACTIVATED PRIORITY CONTROL)",4763.125]
["730-23.88","TRFP","CANTILEVER SIGNAL SUPPORT (1 ARM @ 45')",14663.571428571429]
["730-35.01","TRFP","RF DATA SYSTEM (DESCRIPTION)",4750]
["790-05.08","UTIL","POLE 50FT CLASS H2 METAL",5359.4]
["790-06.08","UTIL","POLE 55FT CLASS H2 METAL",6747.2972972972975]
["790-07.09","UTIL","POLE 60FT CLASS H3 METAL",9632.1428571428569]
["790-08.05","UTIL","POLE 65FT CLASS H3 METAL",9305]
["790-26.01","UTIL","3PH CROSSARM 25KV",1332.1604938271605]
["790-26.07","UTIL","3PH CROSSARM SGL LRG COND ON ST PL 25KV",1432.8243243243244]
["790-26.09","UTIL","3PH CROSSARM SGL ON ST POLE 25KV",3050]
["790-26.14","UTIL","3PH CROSSARM DBL 10FT SM ANGLE 25KV",2237.1428571428573]
["790-26.16","UTIL","3PH XARM FBRGLS LRG COND MED ANGLE 25KV",2049.0476190476193]
["790-26.25","UTIL","3PH CROSSARM DDE 25KV",2402.0179310344829]
["790-31.05","UTIL","SERVICE CONDUCTOR 4 AL DUPLEX",3.0200000000000005]
["790-32.26","UTIL","DOWN GUY LIGHT CONSTRUCTION - PREFORM",315]
["790-32.27","UTIL","OVERHEAD GUY LIGHT CONSTRUCTION - PREFORM",530]
["790-32.30","UTIL","OVERHEAD GUY HEAVY CONSTRUCTION - PREFORM",731.66666666666663]
["790-32.31","UTIL","DOUBLE OVERHEAD GUY HEAVY CONSTRUCTION - PREFORM",705]
["790-33.25","UTIL","SCREW TYPE ANCHOR 15,000LB",710.85185185185185]
["790-33.26","UTIL","SCREW TYPE ANCHOR 28,000LB",816.68888888888887]
["790-36.02","UTIL","TRANSFER CAPACITOR BANK",3852.7925]
["790-40.06","UTIL","OH COND 4/0 6/1 ACSR PENGUIN",4.7238549259346341]
["790-41.13","UTIL","UG PRI COND 1/0 AL 25KV",16.079999999999998]
["790-41.46","UTIL","UG SEC COND 1/0 AL TPLX",11.133904555314535]
["790-43.27","UTIL","OUTDOOR TERMINATOR URD 25KV",918.21428571428567]
["790-43.46","UTIL","SECONDARY PULLBOX LARGE",2384.0145714285713]
["790-43.51","UTIL","SECONDARY RISER W/ 3IN CONDUIT",1495.6666666666667]
["790-43.58","UTIL","3PH PRIMARY RISER W/ 6IN CONDUIT",7919.0625]
["790-52.06","UTIL","25KVA 1PH OH XFORMER 7.2KV 120/240",923.16176470588232]
["790-59.03","UTIL","CUTOUT KNIFE SWITCH-SNGL LOADBREAK 25KV",1120.7446808510638]
["790-65.07","UTIL","LIGHTNING ARRESTOR 18KV INTERMEDIATE",550.38461538461536]
["790-69.04","UTIL","FIBERGLASS CROSSARM ASSEMBLY",1227.8571428571429]
["790-69.06","UTIL","HARDWARE FOR SGL PH CONV TRANS",743.18172043010748]
["790-69.26","UTIL","EXTENSION LINK - EPOXY -1FT",80]
["791-01.22","UTIL","8IN POWERCRETE CTD HP STL GAS MN-DIR  DRILL",259.16129032258067]
["791-04.19","UTIL","HDD <2IN STEEL PIPE - UNCONSOLIDATED",128.12456747404843]
["793-01.06","UTIL","POLE 35FT CLASS 3 WOOD",1000]
["793-01.16","UTIL","POLE 45FT CLASS 2 WOOD",1800]
["793-11.07","UTIL","8IN PEDESTAL W/TERMINAL",460]
["793-11.19","UTIL","MARKER POST",286.11764705882354]
["793-14.13","UTIL","1 1/2IN INNERDUCT",5.0729729729729724]
["793-16.06","UTIL","STRAIGHT BORE/SLEEVE 4IN",86]
["793-16.21","UTIL","ADJUST MANHOLE LID",2265.1923076923076]
["795-01.01","UTIL","4IN DIP RESTRAINED JOINT WATER LINE",156.63131578947369]
["795-06.10","UTIL","CONNECT TO 18IN WATER LINE",3927.75]
["795-07.13","UTIL","12IN X 8IN TAPPING SLEEVE AND VALVE",4787.5]
["795-07.23","UTIL","18IN X 12IN TAPPING SLEEVE & VALVE",7900]
["795-09.07","UTIL","6IN WATER SERVICE METER ASSEMBLY",34525]
["795-09.08","UTIL","8IN WATER SERVICE METER ASSEMBLY",44630]
["795-09.27","UTIL","TI OF 2IN PVC CASING FOR SERVICE PIPE-ROCK",61.494791666666664]
["795-09.31","UTIL","2IN TYPE \"K\" COPPER WATER LINE",27.45]
["795-12.04","UTIL","REMOVE EX BACKFLOW APPARATUS",1510]
["795-12.26","UTIL","REMOVE 6IN METER ASSEMBLY",3828]
["795-15.11","UTIL","36IN STEEL CASING PIPE OPEN CUT METHOD",478.5]
["795-16.36","UTIL","6IN BACKFLOW PREVENTER ASSEMBLY",21865]
["797-06.87","UTIL","OPEN CUT 8IN STEEL CASING PIPE",131.80000000000001]
["797-07.18","UTIL","60IN MANHOLE 14FT-16FT DEPTH",8410.7916666666661]
["797-09.07","UTIL","6IN PLUG VALVE ASSEMBLY",2408.3854545454542]
["797-11.45","UTIL","PIPE CHECK DAM",206]
["797-11.46","UTIL","CONCRETE CAP",210]
["795-01.13","UTIL","16IN DIP RESTRAINED JOINT WATER LINE",89.07069191824489]
["795-05.28","UTIL","HDD __IN HDPE CASING PIPE-ROCK",155.71428571428572]
["795-08.14","UTIL","16IN GATE VALVE ASSEMBLY",8640.5882352941171]
["795-14.15","UTIL","SUPPORT STRUCTURE FOR UNSTABLE SUBGRADE",15000]
["204-09.01","STBR","COFFERDAM (PIER NO. ,STA.)",266000.33333333331]
["209-13.04","EROS","TURBIDITY CURTAIN(DESCRIPTION)",36.147903556771546]
["607-15.04","DRNG","84\" CONCRETE PIPE CULVERT (CLASS IV)",2000]
["202-01.57","ERTH","REMOVAL OF STRUCTURES & OBSTRUCTIONS (CATCH BASIN 87+45)",3250]
["209-40.31","EROS","CATCH BASIN PROTECTION (TYPE B)",402]
["607-50.05","DRNG","PRECAST CONCRETE BOX CULVERT (8' X 4')",616]
["702-01.02","FLAT","CONCRETE CURB",24.19242902208202]
["711-01","BARR","CONCRETE MEDIAN BARRIER",110]
["712-09.05","TRFT","REMOVABLE PAVEMENT MARKING (ARROW)",142.80000000000001]
["713-16.26","TRFP","SIGNS (OM4-1 - OBJECT MARKER)",218.07692307692307]
["713-16.27","TRFP","SIGNS (OM1-1 - OBJECT MARKER)",171.66666666666666]
["713-16.28","TRFP","SIGNS (CLAIM CAR)",150]
["713-16.29","TRFP","SIGNS (Bus Stop)",191.42857142857142]
["730-03.32","TRFP","FIBER OPTIC DROP CABLE",3.1718475073313779]
["730-03.33","TRFP","FIBER OFPTIC SPLICE FUSION",79]
["730-03.34","TRFP","FIBER OPTIC TERMINATION CABINET",3640]
["730-13.13","TRFP","VEHICLE DETECTOR (RADAR)",10147.75]
["791-08.15","UTIL","2IN STEEL SERVICE PIPE",88.333333333333329]
["795-06.02","UTIL","CONNECT TO 3IN WATER LINE",2638.9349999999999]
["795-08.02","UTIL","3IN GATE VALVE ASSEMBLY",1181.915]
["795-09.13","UTIL","3IN COPPER SERVICE PIPE",116]
["209-03.40","EROS","STREAM MITIGATION - LOG RIFFLE",219.83867631851086]
["709-05.81","RIPR","ROCK RIFFLES",78182.481249999997]
["797-13.05","UTIL","CREEK CROSSING (#) (SEE PLANS)",12333.333333333334]
["802-11.19","LAND","LIRIODENDRON TULIPIFERA (TULIP POPLAR 2-5FT CNTNR GRWN)",33.034836065573771]
["802-12.19","LAND","LIRIODENDRON TULIPIFERA (TULIP POPLAR SEEDLNG B.R.)",21.72532283464567]
["207-20.01","MISC","ROADWAY SUBGRADE TIMBER MAT(TEMP)",66.035560588901475]
["615-01.03","STBR","PRESTRESSED CONCRETE I-BEAM (TYPE III)",200.70298700009923]
["707-06.03","FNCE","REMOVAL AND RESET FENCE (BARB WIRE)",10]
["801-01.36","LAND","SPECIAL WETLAND SEED MIXTURE",70.642151515151511]
["802-11.61","LAND","ALNUS SERRULATA (HAZEL ALDER 2-5FT CNTNR GRWN)",50]
["802-13.03","LAND","CEPHALANTHUS OCCIDENTALIS (BUTTONBUSH 2-5FT CNTNR GRWN)",50.986842105263158]
["307-01.22","ASPH","ASP. CONC. MIX(PG76-22) (BPMB-HM) GR. A-S",76.871930465744668]
["602-03","STBR","STEEL STRUCTURES",71000]
["603-02.20","BRPT","SPOT PAINTING EXISTING STEEL STRUCTURES",9]
["604-10.34","STBR","CONCRETE OVERLAYED BRIDGE DECK REPAIR (FULL DEPTH)",700]
["604-10.56","STBR","CONCRETE OVERLAYED BRIDGE DECK REPAIR (PARTIAL DEPTH)",244]
["607-02.02","DRNG","15\" CONCRETE PIPE CULVERT(CLASS III)",96.817021276595739]
["607-05.05","DRNG","24\" CONCRETE PIPE CULVERT(CLASS IV)JACKED-IN-PLACE",599.37641723356012]
["607-06.05","DRNG","30\" CONCRETE PIPE CULVERT(CLASS IV)JACKED-IN-PLACE",772.88196891191706]
["617-01","STBR","BRIDGE DECK SEALANT",21.491917973462002]
["705-80.01","GAT","LONGITUDINAL CABLE BARRIER",15.214508376310379]
["705-80.03","GAT","LONGITUDINAL CABLE BARRIER (END TERMINAL) TL-3",5300]
["203-08","ERTH","CHANNEL EXCAVATION (UNCLASSIFIED)",15.805743740795288]
["204-11","STBR","BRIDGE EXCAVATION (UNCLASSIFIED)",70]
["209-03.36","EROS","STREAM MITIGATION-STEP POOL",3783.9047619047619]
["209-03.38","EROS","STREAM MITIGATION -J -HOOK",3560]
["209-03.57","EROS","STREAM MITIGATION (DESCRIPTION)",280]
["209-03.58","EROS","STREAM MITIGATION (DESCRIPTION)",260]
["607-16.07","DRNG","49\"X 32\" HORIZONTAL OVAL CONCRETE PIPE CULVERT",190]
["607-45.02","DRNG","18\" SLOTTED DRAIN PIPE",110]
["607-50.09","DRNG","PRECAST CONCRETE BOX CULVERT (6' X 4')",600]
["611-01.01","STDR","MANHOLES, 0' - 4' DEPTH",2962.5]
["611-10.01","STDR","CATCH BASINS, TYPE 10, 0' - 4' DEPTH",3280]
["611-10.02","STDR","CATCH BASINS, TYPE 10, > 4' - 8' DEPTH",4080]
["615-02.04","STBR","PRESTRESSED CONCRETE BOX BEAM (27\" X 36\")",260]
["716-13.04","PVMK","SPRAY THERMO PVMT MRKNG (60 mil) (4IN DOTTED LINE)",1.3315241183623836]
["730-01.08","TRFP","SCHOOL SPEED LIMIT FLASHING SIGNAL INSTALLED",6840]
["730-16.25","TRFP","INSTALLATION OF CABINET AND CONTROLLER",2190]
["730-23.64","TRFP","CANTILEVER SIGNAL SUPPORT (1 ARM @ 30')",5880]
["730-24.02","TRFP","FOUNDATION (TRAFFIC SIGNAL CONTROLLER)",1650]
["730-24.03","TRFP","FOUNDATION - CANTILEVER SIGNAL SUPPORT, (_____)",4610]
["730-26.03","TRFP","PEDESTRIAN SIGNAL HEAD, PUSHBUTTON & 12\" SIGN",1270]
["795-01.08","UTIL","10IN DIP SLIP JOINT WATER LINE",59.143094209161625]
["795-03.11","UTIL","18IN PVC WATER LINE",100]
["795-05.71","UTIL","BORE/JACK __IN STEEL CASING PIPE-UNCON (22IN)",635.32661870503603]
["795-08.08","UTIL","12IN BUTTERFLY VALVE ASSEMBLY",3168.1828125000002]
["795-08.15","UTIL","18IN BUTTERFLY VALVE ASSEMBLY",6846.875]
["795-09.51","UTIL","RECONNECT SERVICE ASSEMBLY",196.38888888888889]
["795-12.05","UTIL","REMOVE BLOW-OFF ASSEMBLY",1760]
["795-12.20","UTIL","ADJUST EXISTING VALVE BOXES",415.83333333333331]
["795-13.04","UTIL","BRIDGE HANGER SYSTEM",113127.5]
["795-15.06","UTIL","22IN STEEL CASING PIPE OPEN CUT METHOD",150]
["797-40.01","UTIL","Concrete Encasement",82]
["801-01.04","LAND","SEEDING (WILDFLOWER MIXTURE)",43.415496556320818]
["802-02.36","LAND","CUTTINGS: CORNUS SERICEA (18IN-24IN)",9]
["802-03.01","LAND","SHRUBS (BLACKHAW SEEDLING B.R.)",62.457336621454992]
["802-03.02","LAND","SHRUBS (CAROLINA BUCKTHORN SEEDLING B.R.)",9.6999999999999993]
["802-03.03","LAND","SHRUBS (BLADDERNUT SEEDLING B.R.)",15.854743083003953]
["802-12.17","LAND","JUGLANS NIGRA (BLACK WALNUT SEEDLNG B.R.)",16.5]
["802-12.44","LAND","ULMUS AMERICANA (AMERICAN ELM SEEDLNG B.R.)",14.25]
["802-12.45","LAND","CARPINUS CAROLINIANA (AMERICAN HORNBEAM SEEDLING B.R.)",23.850656455142232]
["802-12.46","LAND","QUERCUS SHUMARDII (SHUMARD OAK SEEDLING B.R.)",23.817073170731707]
["802-12.55","LAND","CARYA LACINIOSA (SHELLBARK HICKORY SEEDLING B.R.)",5.3666666666666663]
["802-13.66","LAND","CORNUS DRUMMONDII (ROUGH LEAF DOGWOOD SDLING B.R.)",14.25]
["202-02.23","ERTH","REMOVAL OF PIPE (24 INCH)",14.89090448756957]
["202-02.24","ERTH","REMOVAL OF PIPE (30 INCH)",14.309373226303414]
["202-02.25","ERTH","REMOVAL OF PIPE (36 INCH)",15.563233376792699]
["202-02.26","ERTH","REMOVAL OF PIPE (SEE PLANS)",26.933986013986011]
["202-08.28","RMVL","REMOVAL OF MEDIAN BARRIER (S.R. 186)",24.77124183006536]
["602-10.61","STBR","BEARING DEVICE (LR SEISMIC ISOLATION BEARING, BENT NO. 1 & 2)",4943.2432432432433]
["604-03.32","STBR","CLASS DS CONCRETE",706.15714342137744]
["604-07.15","WALL","RETAINING WALL (NO. 15)",130]
["604-07.16","WALL","RETAINING WALL (NO. 16)",95]
["604-07.17","WALL","RETAINING WALL (NO. 17)",100]
["604-07.18","WALL","RETAINING WALL (NO. 18)",105]
["604-07.19","WALL","RETAINING WALL (NO. 19)",95]
["604-07.20","WALL","RETAINING WALL (NO. 20)",125]
["604-07.21","WALL","RETAINING WALL (NO. 21)",80]
["606-22.01","STBR","STEEL PIPE PILES (20 IN)",102.13325183374083]
["606-22.03","STBR","TEST PILES (STEEL PIPE PILES 20 IN)",109.63414634146342]
["606-22.04","STBR","LOAD TESTING (STEEL PIPE PILES 20 IN)",4733.333333333333]
["607-03.05","DRNG","18\" CONCRETE PIPE CULVERT(CLASS IV)JACKED-IN-PLACE",522.63305978898006]
["607-11.06","DRNG","60\" CONCRETE PIPE CULVERT(CLASS IV)JACKED-IN-PLACE",1612.7943262411347]
["611-01.05","STDR","MANHOLES, > 16' - 20' DEPTH",14328.333333333334]
["611-01.06","STDR","MANHOLES, > 20' - 24' DEPTH",21156.573333333334]
["611-01.07","STDR","MANHOLES, > 24' - 28' DEPTH",34358.51]
["611-12.05","STDR","CATCH BASINS, TYPE 12, > 16' - 20' DEPTH",12701.596666666668]
["611-31.03","STDR","CATCH BASINS, TYPE 31, > 8' - 12' DEPTH",11792.222222222223]
["611-31.04","STDR","CATCH BASINS, TYPE 31, > 12' - 16' DEPTH",12789.322]
["611-31.06","STDR","CATCH BASINS, TYPE 31, > 20' - 24' DEPTH",42000]
["611-31.07","STDR","CATCH BASINS, TYPE 31, > 24' - 28' DEPTH",42000]
["705-20.20","GAT","LOW MAINT CRASH CUSHN NARROW (MASH TL-3)",28722.022857142856]
["705-80.18","GAT","CABLE BARRIER TERMINAL",4896.875]
["711-05.74","BARR","CONC MEDIAN BARR SING SLOPE (STD-1-3SS)",121.54929577464789]
["712-02.47","TRFT","BRIDGE MOUNTED INTERCONNECTED PORTABLE BARRIER RAIL",70.133872565203035]
["713-09.06","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 81')",48257.573333333334]
["713-09.07","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 97')",53500]
["713-09.08","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 99.5')",58400]
["713-09.09","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 92.50')",57125]
["713-09.10","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 92.50')",60575]
["713-09.11","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 165.50')",56262.5]
["713-09.12","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 80.50')",41100]
["713-09.13","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 187')",100000]
["713-09.14","TRFP","STEEL OVERHEAD SIGN STRUCTURE (SPAN 175')",100000]
["713-11.05","TRFP","SQUARE TUBE SIGN SUPPORT",6.6084604661659245]
["713-17.50","TRFP","SIGN MOUNTED ON BRIDGE PARAPET",4025]
["713-20.30","TRFP","SIGN ADJUSTMENTS",125]
["714-02.04","LITE","ENCASED CONDUIT (CONDUIT IN MEDIAN BARRIER)",7.6159552774066519]
["714-03.02","LITE","DIRECT BURIAL CONDUIT (3\" PVC, SCHEDULE 40)",10.508083140877599]
["714-08.08","LITE","LIGHT STANDARDS (NEW MEDIAN BARRIER MOUNTED)",2388.3362903225807]
["714-08.11","LITE","LIGHT STANDARDS (35' POLE W/TENON)",8526.2331460674159]
["714-08.26","LITE","FOUNDATION FOR LIGHT STANDARDS(MEDIAN BARRIER)",350]
["714-08.27","LITE","FOUNDATION  FOR LIGHT STANDARDS - HIGH MAST (SEE PLANS)",5500]
["716-01.14","PVMK","RAISED PAVEMENT MARKER REMOVAL",6.6158004158004156]
["716-03.06","PVMK","PLASTIC WORD PAVEMENT MARKING (SIGNAL AHEAD)",640]
["716-04.08","PVMK","PLASTIC PAVEMENT MARKING (OPTION LANE ARROW)",356.82692307692309]
["716-06.01","PVMK","PAINTED WORD PVMT MARK (           )",168.65952380952382]
["716-12.09","PVMK","ENHANCED FLAT LINE THERMO (12IN LINE)",5.9658275766195441]
["725-21.11","ITS","NETWORK SWITCH (TYPE A)",3200]
["725-22.34","ITS","CONDUIT BANK BORED (TYPE 4)",28.435855263157894]
["725-22.74","ITS","2IN CONDUIT W/BANK",3.981858634263221]
["725-22.75","ITS","2IN CONDUIT BORED W/BANK",5.0575916230366493]
["730-03.11","TRFP","INSTALL SPLICE BOX (FIBER OPTIC CLOSURE)",1038.4615384615386]
["730-41.50","TRFP","BRIDGE SUSPENDED SIGNALS",38000]
["790-09.01","UTIL","POLE 70FT CLASS 1 WOOD",12055]
["790-33.22","UTIL","SWAMP ANCHOR 10IN",2045]
["790-41.64","UTIL","UG SEC COND SGL COND ____ __ __ (WS004IC-ST)",16.86]
["790-43.48","UTIL","SEC PULLBOX SMALL (REPLACE ONLY)",1149.1666666666667]
["790-70.04","UTIL","STREET LIGHT W/ FRNG ANC BASE & MTL POLE",3420]
["790-70.06","UTIL","STREET LIGHT BASE, POWER INSTALLED",1505]
["790-70.10","UTIL","FLOOD LIGHT",851.31333333333339]
["790-74.20","UTIL","108-144 FIBER(INSTALLATION ONLY)",705]
["790-98.04","UTIL","REMOVE FIBER OPTIC CABLE",1.3584476534296028]
["791-01.03","UTIL","3IN STEEL GAS MAIN",408]
["791-04.22","UTIL","HDD 4IN STEEL PIPE - UNCONSOLIDATED",186]
["791-06.38","UTIL","CONNECT TO __IN EX. STL MAIN W/ STOPPLE (SEE PLANS)",36582]
["791-07.16","UTIL","__IN STEEL GAS VALVE ASSEMBLY (SEE PLANS)",3012.6666666666665]
["791-08.50","UTIL","1-1/2IN STEEL SERVICE PIPE",60]
["791-08.51","UTIL","1-1/2IN STEEL SERVICE ASSEMBLY",4580]
["791-10.11","UTIL","RETIRE IN PLACE 3IN SERV CUT & PLUG",1000]
["797-05.07","UTIL","10IN DIP GRAVITY SEWER 12FT-18FT DEPTH",275]
["797-05.08","UTIL","10IN DIP GRAVITY SEWER >18FT DEPTH",310]
["202-01.08","STBR","REMOVAL OF ASBESTOS (SEE PLANS)",24354]
["205-02.01","ERTH","RSS BACKFILL MATERIAL",10]
["615-02.28","STBR","PRESTRESSED CONCRETE BOX BEAM (24\" X 48\")",235]
["680-02.01","SALT","BUILDING (DESCRIPTION)",110200]
["709-01.02","RIPR","RUBBLE STONE RIP-RAP",48.28125]
["713-16.05","TRFP","RAILROAD CROSS-BUCK SIGN & SUPPORT",210]
["713-16.09","TRFP","RAILROAD ADVANCE WARNING SIGN AND SUPPORT",175]
["716-02.13","PVMK","PLASTIC PAVEMENT MARKING (CROSSWALK)",16]
["730-01.04","TRFP","MODIFICATION OF EXISTING TRAFFIC SIGNAL EQUIPMENT",6783.333333333333]
["730-23.95","TRFP","CANTILEVER SIGNAL SUPPORT (2 @ 45' & 45')",16855.5]
["740-07.01","BASE","GEO GRID REINFORCEMENT",2.4852584710510368]
["740-07.06","ERTH","GEOGRID REINFORCEMENT TYPE 4",6]
["771-04.52","UTIL","REMOVE FARM TAP",470]
["790-60.09","UTIL","3PH SECTIONALIZER OR RECL 15KV",8924]
["790-71.29","UTIL","MED VERT ANG 69KV MAX",4465]
["790-74.26","UTIL","FIBER OPTIC MAINTENANCE LOOP",740]
["790-99.01","UTIL","RESERVED FOR TDOT USE ONLY",100000]
["790-99.02","UTIL","RESERVED FOR TDOT USE ONLY",4.53]
["791-01.09","UTIL","__IN STEEL GAS MAIN (SEE PLANS)",36]
["791-03.09","UTIL","__IN HDPE GAS MAIN (SEE PLANS)",19]
["791-03.10","UTIL","__IN HDPE GAS MAIN (0.75\" HDPE GAS MAIN)",17]
["791-04.09","UTIL","HDD __IN PE PIPE - UNCONSOLIDATED (SEE PLANS)",46]
["791-04.27","UTIL","HDD __IN STEEL PIPE - UNCONSOLIDATED (SEE PLANS)",52]
["791-06.09","UTIL","CONNECT TO __IN EX. PE MAIN (SEE PLANS)",775]
["791-06.47","UTIL","CONNECT TO 3/4IN EX. PE MAIN",725]
["791-06.48","UTIL","CONNECT TO 3/4IN EX. STEEL MAIN",1015]
["791-07.21","UTIL","EXCESS FLOW VALVE (EFV)",569.23214285714289]
["791-07.25","UTIL","1IN PE GAS VALVE ASSEMBLY",590]
["791-09.21","UTIL","Cathodic Protection Junction Box",532]
["795-09.24","UTIL","TI OF 2IN HDPE CASING FOR SERVICE PIPE-UNCON",35]
["795-11.03","UTIL","RECONNECT FIRE HYDRANT",2100]
["795-14.01","UTIL","CLASS A CONCRETE",150]
["797-02.03","UTIL","1-1/2IN HDPE FORCE MAIN",25]
["797-03.03","UTIL","1-1/2IN PVC FORCE MAIN",11]
["797-05.29","UTIL","__IN DIP GRAVITY SEWER 0FT-6FT DEPTH (SEE PLANS)",139.90707964601771]
["797-05.67","UTIL","18IN PVC GRAVITY SEWER 0FT-6FT DEPTH",87.452830188679243]
["797-05.68","UTIL","18IN PVC GRAVITY SEWER 6FT-12FT DEPTH",121.05072463768116]
["403-02","ASPH","ASPHALT CEMENT FOR TACK COAT (TC)",370]
["604-10.30","STBR","BRIDGE DECK REPAIRS (FULL DEPTH OF SLAB)",861.5]
["604-10.50","STBR","BRIDGE DECK REPAIRS (PARTIAL DEPTH OF SLAB)",445.75471698113205]
["604-10.54","STBR","CONCRETE REPAIRS",205.68524096385542]
["607-50.10","DRNG","PRECAST CONCRETE BOX CULVERT (10' X 8')",940]
["615-01.02","STBR","PRESTRESSED CONCRETE I-BEAM (TYPE II)",137.56642646804087]
["713-02.11","TRFP","REMOVAL OF EXISTING DELINEATORS",4]
["713-15.01","TRFP","REMOVAL OF EXISTING SIGN POST",50]
["607-12.30","DRNG","66\" PIPE CULVERT",200]
["790-30.02","UTIL","SECONDARY ASSEMBLIES LRG ANGLE",432.48133333333334]
["790-32.17","UTIL","DOWN GUY - FOUR GUYS LG COND",550.45000000000005]
["790-36.11","UTIL","TRANSFER EXISTING 1PH TRANSFORMER/RECLOSER",880.52]
["802-13.01","LAND","ALNUS SERRULATA (HAZEL ALDER 2-5FT CNTNR GRWN)",22.7]
["802-13.04","LAND","CORNUS AMOMUM (SILKY DOGWOOD 2-5FT CNTNR GRWN)",39.789115646258502]
["802-13.10","LAND","SAMBUCUS CANADENSIS ( ELDERBERRY 2-5FT CNTNR GRWN)",63]
["707-01.22","FNCE","TEMP GATE - CHAIN LINK FENCE-6FT (DESCRIPTION)",500]
["707-06.05","FNCE","REMOVAL OF FENCE (CHAIN LINK)",2500]
["712-09.03","TRFT","REMOVABLE PAVEMENT MARKING(CHANNELIZING STRIPING)",56.761467889908253]
["716-08.11","PVMK","REMOVAL OF WORD PAVEMENT MARKING (ONLY)",120.15625]
["709-05.07","RIPR","MACHINED RIP-RAP (CLASS A-2)",40]
["791-01.40","UTIL","RELOCATE SERVICE",1001.7857142857143]
["791-04.29","UTIL","HDD 2IN STEEL PIPE - ROCK",136.80000000000001]
["791-04.34","UTIL","HDD 12IN STEEL PIPE - ROCK",359.55]
["791-06.14","UTIL","CONNECT TO 12IN EX. STL MAIN",26825]
["791-06.51","UTIL","2IN PE HOT TAP CONNECTION",1500]
["791-07.13","UTIL","12IN STEEL GAS VALVE ASSEMBLY",23875.333333333332]
["795-05.16","UTIL","HDD 4IN HDPE CASING PIPE-ROCK",165]
["795-05.83","UTIL","BORE/JACK 30IN STEEL CASING PIPE-ROCK.",735]
["795-06.30","UTIL","CUT/CAP EXISTING LINES (ALL SIZES)",886]
["795-07.61","UTIL","__IN X __IN TAPPING SLEEVE AND VALVE (SEE PLANS)",10400]
["795-09.19","UTIL","3/4IN PVC SERVICE PIPE",28]
["795-09.20","UTIL","1IN PVC SERVICE PIPE",30]
["795-09.22","UTIL","2IN PVC SERVICE PIPE",35]
["795-10.20","UTIL","2IN PRV ASSEMBLY",1800]
["795-10.31","UTIL","2IN BLOW-OFF ASSEMBLY",1793]
["795-21.11","UTIL","RETIRE IN PLACE EXISTING WATER LINE",6.5]
["797-05.20","UTIL","18IN DIP GRAVITY SEWER >18FT DEPTH",200]
["797-05.62","UTIL","12IN PVC GRAVITY SEWER >18FT DEPTH",85]
["797-05.69","UTIL","18IN PVC GRAVITY SEWER 12FT-18FT DEPTH",160]
["797-05.70","UTIL","18IN PVC GRAVITY SEWER >18FT DEPTH",220]
["797-06.65","UTIL","BORE/JACK 18IN STEEL CASING PIPE-UNCON.",662]
["797-06.78","UTIL","BORE/JACK 18IN STEEL CASING PIPE-ROCK.",662]
["797-06.80","UTIL","BORE/JACK 24IN STEEL CASING PIPE-ROCK.",750]
["797-07.10","UTIL","48IN MANHOLE 24FT-28FT DEPTH",11000]
["797-07.11","UTIL","48IN MANHOLE >28FT DEPTH",12000]
["797-08.06","UTIL","8IN PVC PIPE FOR SERVICE LATERAL",40]
["797-08.09","UTIL","8IN CLEAN OUT ASSEMBLY",300]
["797-10.07","UTIL","CONNECT 8IN LATERAL TO SEWER LINE",400]
["797-11.36","UTIL","REMOVE EXISTING SEWER 15IN-24IN",21.004225352112677]
["203-04.01","ERTH","PLACING SPREADING SOIL FOR LANDSCAPING",40]
["203-50","ERTH","CONSTRUCTION OF HAUL ROAD",298214.28571428574]
["204-10.02","STBR","FOUNDATION PREPARATION (PIER NO. 1 - STATION 552+71.81 RL)",49284.397142857146]
["209-03.45","EROS","STREAM MITIGATION - LIVE FASCINES (SPECIES)",3]
["209-06.02","EROS","12\" DIA COIR LOG (FOR LOW CHANNEL FLOW)",10.340527383367141]
["209-10.02","EROS","8IN SKIMMER W/6IN HEAD",6500]
["405-01.01","ASPH","BITUMINOUS MATERIAL (BSC)",970.17999999999984]
["405-01.02","ASPH","MINERAL AGGREGATE (BSC)",105.8]
["604-02.43","STBR","ENERGY DISSIPATER (TYPE USBR VI, 30\" RCP)",5300]
["604-02.44","STBR","ENERGY DISSIPATER (TYPE USBR VI, 36\" PIPE)",6600]
["604-02.45","STBR","ENERGY DISSIPATER (TYPE USBR VI, 42\" PIPE)",9900]
["604-02.46","STBR","ENERGY DISSIPATER (TYPE USBR VI, 48\" PIPE)",18400]
["604-02.48","STBR","ENERGY DISSIPATER (TYPE USBR VI, 60\" PIPE)",15300]
["604-12.04","STBR","STONE VENEER FINISH",25]
["607-07.05","DRNG","36\" CONCRETE PIPE CULVERT(CLASS IV)JACKED-IN-PLACE",1012.9032258064516]
["607-11.05","DRNG","60\" CONCRETE PIPE CULVERT (CLASS V)",196]
["705-11.01","GAT","GUARDRAIL AT BRIDGE ENDS (POWDER COATED)",112.86666666666667]
["705-11.03","GAT","SINGLE GUARDRAIL (TYPE 2) (POWDER COATED)",31.800893655049148]
["705-11.08","GAT","GUARDRAIL TERMINAL (TYPE 13) (POWDER COATED)",1971.8]
["705-11.11","GAT","TAN ENERGY ABSORB  TERMINAL (NCHRP 350, TL 3)(POWDER COATED)",4244.545454545455]
["705-20.22","GAT","REUSABLE CRSH CUSHION NARW (MASH TL-3)",22600]
["707-06.04","FNCE","REMOVAL AND RESET GATE (METAL STOCK, DRIVE ENT. GATE)",750]
["710-06.14","DRNG","LATERAL UNDERDRAIN ENDWALL (5:1)",718.75]
["721-01.03","LAND","IRRIGATION SYSTEM",10000]
["790-22.18","UTIL","1PH SGL DEAD END XARM 25KV",990]
["790-26.30","UTIL","3PH CROSSARM DBL-DDE-INV ARM 25KV",2893]
["790-33.14","UTIL","3/4IN TWIN EYE",533.47107438016531]
["790-41.49","UTIL","UG SEC COND 4/0 AL TPLX",10.111822173435785]
["790-54.04","UTIL","15KVA 1PH OH XFORMER 14.4KV 120/240",1805]
["790-54.06","UTIL","25KVA 1PH OH XFORMER 14.4KV 120/240",1931.25]
["790-54.09","UTIL","37.5KVA 1PH OH XFORMER 14.4KV 120/240",2172.5]
["790-61.02","UTIL","1PH FUSE CUTOUT BRKT MOUNT 25KV",529.16666666666663]
["795-05.18","UTIL","HDD 8IN HDPE CASING PIPE-ROCK",233.25]
["802-06.03","LAND","MULCH (3IN SHREDDED PINE BARK MULCH)",55.805626598465473]
["802-07.01","LAND","FLOWER (SEE PLANS)",20]
["802-11.04","LAND","ACER SACCHARUM (SUGAR MAPLE 2-5FT CNTNR GRWN)",29.152416356877325]
["802-11.09","LAND","CARYA OVATA (SHAGBARK HICKORY 2-5FT CNTNR GRWN)",28.775933609958507]
["920-10.05","UNKN","(SEE PLANS)",25000]
["713-02.30","TRFP","FLEXIBLE TUBULAR DELINEATOR",49.678193832599113]
["611-07.35","STDR","42IN ENDWALL (SIDE DRAIN)",9985.5439999999999]
["707-02.11","FNCE","CHAIN-LINK FENCE (6 FOOT) (VINYL COATED)",16.64]
["790-09.02","UTIL","POLE 70FT CLASS 2 WOOD",4027.31]
["790-25.03","UTIL","3PH NARROW PROFILE SGL LG COND 15KV",1307.29]
["790-30.42","UTIL","SECONDARY CONDUCTOR___ SGL COND (SEE PLANS)",12.55]
["790-36.10","UTIL","TRANSFER - LIGHT ASSEMBLY",163.41]
["790-36.12","UTIL","TRANSFER EXISTING 3PH TRANSFORMER/RECLOSER",4427.92]
["790-40.43","UTIL","OH COND 397.5 19 AAC CANNA",3.73]
["790-42.10","UTIL","4IN DIA PVC PIPE",11.122809667673716]
["790-42.14","UTIL","CONDUIT - POLE MTD - 4IN SCH 80 PVC",39.9]
["790-43.01","UTIL","LOADBREAK ELBOW 200A 15KV",458.62222222222226]
["790-43.10","UTIL","SPLICE 200A 15KV",685.27]
["790-52.09","UTIL","37.5KVA 1PH OH XFORMER 7.2KV 120/240",911.94]
["790-52.11","UTIL","50KVA 1PH OH XFORMER 7.2KV 120/240",1033.18]
["790-52.16","UTIL","75KKVA 1PH OH XFORMER 7.2KV 120/240",1096.44]
["791-02.30","UTIL","<=2 IN PE TEMP. BY-PASS FOR TIE-IN",525]
["791-03.01","UTIL","<2IN HDPE GAS MAIN",9.19]
["791-07.30","UTIL","4WAY PE VALVE SYSTEM (4-6IN)",5565]
["791-07.31","UTIL","4WAY PE VALVE SYSTEM (2 - 6 IN, 2 - 4 IN)",5145]
["791-07.32","UTIL","4WAY PE VALVE SYSTEM (2-6IN,1-4IN,1-2IN)",4620]
["791-07.33","UTIL","3WAY PE VALVE SYSTEM (3 - 6 IN)",5040]
["791-07.34","UTIL","3WAY PE VALVE SYSTEM (3 - 4 IN)",4305]
["791-07.35","UTIL","2WAY PE VALVE SYSTEM (2 - 6 IN)",2782.5]
["791-09.15","UTIL","2IN PE TIE-IN (2X2IN TO EXIST)",1627.5]
["791-09.16","UTIL","4 IN PE TIE-IN (4X4IN OR 4X2IN NEW TO EXIST)",1732.5]
["791-09.17","UTIL","6 IN PE TIE-IN (6X4IN OR 6X2IN NEW TO EXIST)",2940]
["791-09.18","UTIL","2X2 IN PE BRANCH TIE-IN W/ 2 IN VALVE",1979.25]
["791-09.19","UTIL","4X2 IN PE BRANCH TIE-IN W/ 2 IN VALVE",2031.75]
["791-09.20","UTIL","6X2 IN PE BRANCH TIE-IN W/ 2 IN VALVE",2047.5]
["793-11.21","UTIL","HANDHOLE (36IN X 24IN X 24IN)",2732.1]
["793-11.25","UTIL","CONCRETE HANDHOLE 4FT X 4FT X 4FT",8802.5550000000021]
["793-14.05","UTIL","MH PRECAST 4-FT W X 8-FT L X 6-FT H",15687.364285714286]
["795-07.35","UTIL","2IN X 2IN TAPPING SADDLE AND VALVE",2152.5]
["795-11.40","UTIL","RESTORE ASPHALT",52.354999999999997]
["795-11.41","UTIL","RESTORE CONCRETE",63]
["795-11.42","UTIL","RESTORE GRAVEL",10.5]
["797-01.13","UTIL","6IN EPOXY COATED DIP FORCE MAIN",74.55]
["797-03.02","UTIL","1-1/4IN PVC FORCE MAIN",21]
["797-03.05","UTIL","3IN PVC FORCE MAIN",31.5]
["797-09.02","UTIL","1-1/4IN BALL VALVE",420]
["797-09.05","UTIL","3IN PVC BALL VALVE",525]
["797-09.19","UTIL","1IN COMBO AIR RELEASE VALVE ASSEMBLY",2310]
["797-10.12","UTIL","CONNECT TO EXISTING PUMP STATION",6625]
["209-40.50","EROS","CATCH BASIN FILTER ASSEMBLY(TYPE 10)",970]
["606-24.13","INCI","TEMPORARY SHEET PILES",12200]
["610-10.45","STBR","DECK DRAINS (GRATE TYPE 2)",1968.1632653061224]
["713-15.41","TRFP","SIGN REMOVAL (DESCRIPTION)",765]
["790-32.03","UTIL","DOWN GUY - THROUGH BOLT ST PL",351.52222222222218]
["790-69.12","UTIL","GROUND ASSEMBLY GROUND PLATE TYPE",450]
["791-05.20","UTIL","BORE/JACK 10IN - STEEL CASING PIPE - ROCK",440]
["791-06.25","UTIL","CONNECT TO 6IN EX. PE MAIN",4200]
["793-11.20","UTIL","HANDHOLE 30INX48IN",3528.8485714285712]
["793-13.52","UTIL","___DUCT FORMATION @ ___IN DEPTH (1.25\")",24.5]
["798-05.02","UTIL","FIBER OPTIC CABLE ENCLOSURE",1850]
["411-33.34","ASPH","STAMPED ASPHALT PATTERN",20]
["611-07.52","STDR","15IN ENDWALL (CROSS DRAIN) 4:1",1508.3333333333333]
["706-06.06","GAT","RADIUS RAIL LONG POST (9-12 FT)",32.782377049180333]
["708-03.10","MISC","SIGN WALLS",30000]
["708-03.11","MISC","CONCRETE PAD",15000]
["713-14.01","TRFP","EXTRUDED ALUMINUM PANEL SIGNS (ANODIZED)",18]
["713-15.08","TRFP","SUSPENDED FLAT SHEET ALUMINUM SIGN (0.100\" THICK)",290]
["713-16.04","TRFT","CHANGEABLE MESSAGE SIGN UNIT  (DESCRIPT)",5871]
["714-06.05","LITE","CABLE (1/C # 6 AWG)",1.1351620310234729]
["714-08.34","LITE","REMOVAL OF LIGHT STANDARD",375.49180327868851]
["714-09.14","LITE","LUMINAIRES (165W LED, LCUB POLE MOUNTED)",630.35]
["714-09.15","LITE","LUMINAIRES (LED TEARDROP)",1990]
["721-01.01","MISC","BENCH (6')",2500]
["721-01.02","MISC","TRASH RECEPTACLE",2000]
["730-23.20","TRFP","CANTILEVER SIGNAL SUPPORT (1 ARM @ 65')",19013.5]
["793-11.31","UTIL","REMOVE HANDHOLE",265]
["793-13.37","UTIL","9 DUCT FORMATION @ 36IN DEPTH",143.09615384615384]
["793-13.42","UTIL","12 DUCT FORMATION @ 36IN DEPTH",175]
["795-09.03","UTIL","1-1/2IN WATER SERVICE METER ASSEMBLY",1900]
["797-10.01","UTIL","CONNECT 6IN SEWER TO EXIST. MANHOLE",2700]
["802-04.70","LAND","GROUND COVER (1 GAL., @ 12\" O.C.)",6.5]
["802-04.71","LAND","GROUND COVER (1 GAL., @ 18\" O.C.)",7.5]
["802-04.72","LAND","GROUND COVER (1 GAL., @ 36\" O.C.)",8.5]
["802-04.73","LAND","GROUND COVER (3 GAL., @ 36\" O.C.)",11.5]
["802-50.99","LAND","PLANTING SOIL",45]
["202-01.05","STBR","REMOVAL OF ASBESTOS (BRIDGE NO. 1)",8244]
["202-01.06","STBR","REMOVAL OF ASBESTOS (BRIDGE NO. 2)",8244]
["202-01.07","STBR","REMOVAL OF ASBESTOS (BRIDGE NO. 3)",8244]
["202-11","ERTH","CONSTRUCTION & REMOVAL OF TEMPORARY STRUCTURES",1540000]
["202-12","ERTH","CONSTRUCTION & REMOVAL OF TEMPORARY RUNAROUND",20000]
["602-02.01","STBR","STRUCTURAL STEEL (WALL 13 SOLDIER PILES)",0.90000000000000013]
["602-02.10","STBR","STRUCTURAL STEEL (INSTALLATION OF SOLDIER PILES)",26000]
["602-04.98","STBR","STEEL STRUCTURES (WB POPLAR, MATERIAL ONLY, 1,228,215 LBS .)",1271916]
["602-04.99","STBR","STEEL STRUCTURES (EB POPLAR, MATERIAL ONLY, 573,770 LBS.)",600000]
["602-10.05","STBR","BRACING REPAIRS",0.01]
["603-01","BRPT","PAINT STEEL STRUCTURE",72000]
["604-02.10","STBR","REINFORCEMENT STEEL (ASTM A706)",1.1000000000000001]
["604-03.08","STBR","CLASS A CONCRETE (SOLDIER PILE FOOTING)",520]
["604-03.40","STBR","SEISMIC MODIFICATION (STEEL RESTRAINER ASSEMBLY)",420]
["604-03.74","STBR","CLASS X CONCRETE",671.89781021897807]
["604-04.03","STBR","BRIDGE END DRAINS(2'X8')",7714.2857142857147]
["604-09.10","STBR","CLASS A CONCRETE (RETAINING WALLS)",720]
["604-10.29","STBR","CONCRETE SLOPE PAVING REPAIRS",120]
["604-10.39","STBR","PRECAST REINFORCED CONCRETE UNITS",31]
["604-10.43","STBR","PENETRATING WATER REPELLENT CONCRETE SEAL",25]
["604-10.44","STBR","EXPANSION JOINT REPAIRS",200]
["604-12.15","STBR","DRILL & GROUT STEEL BARS",38]
["604-36.10","STBR","BRIDGE DECK REPAIRS",1000]
["604-50.10","STBR","MECHANICAL COUPLER",93]
["605-03","STBR","WATERPROOFING RAILROAD BRIDGE DECK",10]
["605-05","STBR","DAMPPROOFING (RAILROAD STRUCTURES)",10]
["606-02.01","STBR","TEST PILES (STEEL PILES, 10 INCH)",250]
["606-02.02","STBR","LOADING TEST (STEEL PILES, 10 INCH)",5800]
["606-03.01","STBR","TEST PILES (STEEL PILES, 12 INCH)",200]
["606-03.02","STBR","LOADING TEST (STEEL PILES, 12 INCH)",5800]
["606-04.01","STBR","TEST PILES (STEEL PILES, 14 INCH)",270]
["606-04.02","STBR","LOADING TEST (STEEL PILES, 14 INCH)",5800]
["606-04.06","STBR","PILE TIPS (STEEL PILES, 14 INCH)",120]
["606-27.11","STBR","TEST PILES (7.625 INCH MICROPILE)",200]
["606-27.12","STBR","VERIFICATION LOADING TEST (7.625 INCH MICROPILE)",14000]
["606-27.13","STBR","MICROPILE TYPE B (7.625 INCH)",125]
["606-27.14","STBR","PROOF LOADING TEST MICROPILE (7.625 IN)",2500]
["606-28.01","STBR","TEST PILES (7 5/8\" S .500\" MICROPILE)",200]
["606-28.02","STBR","VERIFICATION LOADING TEST (7 5/8\" s .500\" MICROPILE)",14000]
["606-28.03","STBR","MICROPILE(7 5/8\" s .500\" MICROPILE)",125]
["606-28.04","STBR","PROOF LOADING TEST (7 5/8\" s .500\" MICROPILE)",2500]
["607-07.04","DRNG","36\" CONCRETE PIPE CULVERT (CLASS V)",119.13533834586467]
["607-60.18","DRNG","36\" STEEL PIPE CULVERT (JACK-IN-PLACE)",790]
["610-10.04","STDR","DRAINAGE SYSTEM - BRIDGE DECK (CLOSED SYSTEM)",90000]
["610-10.14","STDR","DRAINAGE SYSTEM - BRIDGE DECK (CLOSED SYSTEM RAILROAD)",474398]
["610-12.02","DRNG","HORIZONTAL DRAINS",19]
["622-01.01","INCI","SHOTCRETE BUTTRESS",900]
["622-01.02","INCI","STEEL REINFORCEMENT- SHOTCRETE BUTTRESS",8]
["705-03.04","GAT","MEDIAN DIVIDER GUARDRAIL AT CONCRETE BARRIER",39]
["707-11.01","FNCE","PEDESTRIAN CONSTRUCTION BARRIER FENCE",8.5]
["710-04.01","DRNG","GEOCOMPOSITE EDGE DRAIN",5]
["711-01.01","BARR","CONCRETE MEDIAN BARRIER (MODIFIED)",320]
["711-05.01","BARR","REMOVAL & DISPOSAL OF CONCRETE MEDIAN BARRIER",30]
["713-13.04","TRFP","FLAT SHEET ALUMINUM SIGNS (0.125\" THICK)",50]
["713-30.10","TRFP","BARRIER MOUNTED SIGN SUPPORT (PERF/KNOCKOUT) (LARGE)",479.21999999999997]
["714-04.02","LITE","CONDUIT (STRUCTURES - 2\" RGS)",57.439180537772089]
["714-05.07","LITE","PULL BOXES (MEMPHIS STANDARD)",500]
["714-09.07","LITE","LUMINAIRES (150 WATT - UNDERPASS)",1600]
["714-30","LITE","AS-BUILT PLANS",3397]
["725-03.28","ITS","RAILROAD FLAGMAN",0.01]
["725-21.91","ITS","RADAR DETECTION SYSTEM",18000]
["725-21.96","ITS","RDS COMM CABLE",7]
["725-22.21","ITS","CONDUIT BANK (TYPE 1)",8]
["725-22.32","ITS","CONDUIT BANK BORED (TYPE 2)",12]
["725-23.11","ITS","FIBER OPTIC CABLE (60 F)",2.5]
["725-23.23","ITS","FIBER OPTIC DROP CABLE ( 4 F )",1.5]
["725-23.25","ITS","FIBER OPTIC CLOSURE (72 F )",1123.5]
["725-23.31","ITS","FIBER OPTIC DROP PANEL ( 12 F )",792]
["725-24.01","ITS","CABINET (TYPE A)",4500]
["805-05.02","LAND","SOIL NAIL STABILIZATION",40]
["908-21.02","STBR","BEARINGS (NSR BRIDGE SPANS 1 & 5 EXPANSION BEARIN G)",7058.4482758620688]
["908-21.03","STBR","BEARINGS (NSR BRIDGE SPANS 2 - 4 FIXED BEARING)",6157.894736842105]
["908-21.04","STBR","BEARINGS (NSR BRIDGE SPANS 2 - 4 EXPANSION BEARIN G)",5000]
["908-21.05","STBR","BEARINGS (NSR BRIDGE RE-SET SPANS 1 & 5 FIXED BEA RING)",2000]
["908-21.06","STBR","BEARINGS (NSR BRIDGE RE-SET SPANS 1 & 5 EXPANSION BEARING)",2000]
["908-21.07","STBR","BEARINGS (NSR BRIDGE RE-SET SPANS 2 - 4 FIXED BEA RING)",2000]
["908-21.08","STBR","BEARINGS (NSR BRIDGE RE-SET SPANS 2 - 4 EXPANSION BEARING)",2000]
["915-01.01","","6 IN CORRUGATED PIPE DRAIN SYSTEM",18]
["915-01.02","","6 IN CORRUGATED PIPE UNDERDRAIN",23]
["924-01.01","UNKN","DECK REMOVAL AND REPAIR (SEE PLANS)",890]
["925-01.01","","RAILROAD SELECT BACKFILL",38]
["930-08.26","","LOADING TEST (SOIL NAILS)",1500]
["945-01.01","CONC","4,000 PSI STRUCTURAL CONCRETE",660]
["945-01.02","CONC","6,000 PSI STRUCTURAL CONCRETE",470]
["955-01.01","MISC","STEEL STRUCTURES MATERIAL",3301496]
["955-01.02","MISC","STEEL STRUCTURES",950000]
["955-01.03","MISC","MASONRY PLATE ANCHORS",48]
["955-02.01","FNCE","FENCE",140]
["955-02.02","STBR","WINGWALL HANDRAIL",140]
["955-03.01","MISC","BRIDGE LATERAL SLIDE 1",160000]
["955-03.02","MISC","BRIDGE LATERAL SLIDE 2",160000]
["965-01.01","STBR","TEMPORARY BALLAST RETAINER TIMBERS",100]
["965-01.02","STBR","CENTER DECK JOINT PLACEMENT",300]
["970-06.17","STBR","COLUMN RETROFIT",17500]
["985-01.01","MISC","REMOVAL AND DISPOSAL OF BALLAST",119500]
["985-02.01","MISC","PLACING BALLAST",28]
["999-99.92","MISC","PAYMENT & PERFORMANCE BOND(ESTIMATED REIMBURSABLE COST)",216390]
["999-99.93","MISC","ON-SITE CONSTRUCTION MANAGEMENT AND SUPPORT STAFF",3239000]
["999-99.94","MISC","GENERAL CONDITIONS DIRECT COST",2686000]
["999-99.95","MISC","CM/GC FEE(5% OF COST OF WORK)",2565790]
["202-01.09","STBR","REMOVAL OF ASBESTOS (BRIDGE NO. 5)",4488]
["202-02.27","ERTH","REMOVAL OF PIPE (48\")",24.239263803680981]
["202-02.29","ERTH","REMOVAL OF PIPE (60\")",25.593103448275862]
["209-03.42","EROS","STREAM MITIGATION - LIVE BRUSH LAYERING",153.87553041018387]
["209-03.59","EROS","STREAM MITIGATION - BRUSH MATTRESS",93.763102409638563]
["209-03.67","EROS","Stream Mitigation – Wood Toe W/Reinforced Earth",85.98885542168675]
["606-10.01","STBR","TEST PILES (PRECAST CONCRETE, SIZE 2)",57]
["606-10.02","STBR","LOADING TEST (PRECAST CONCRETE, SIZE 2)",5500]
["606-10.03","STBR","PRECAST CONCRETE PILES (SIZE 2)",53]
["626-01.01","ENGR","AGGREGATE FOUNDATION SYSTEMS",1068021]
["705-08.11","GAT","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",6261.1785714285716]
["716-05.51","PVMK","PAINTED PAVEMENT MARKINGS(12\" LINE)",3.0599686847599163]
["730-02.18","TRFP","SIGNAL HEAD ASSEMBLY (150 A2V)",1093.7083333333333]
["730-26.08","TRFP","FLASHING WARNING BEACON (DESCRIPTION)",3233.6054545454549]
["801-01.35","LAND","GRASS SEED MIX (RIPZN/FLPL) W/MULCH",54.869533678756476]
["802-12.07","LAND","BETULA NIGRA (RIVER BIRCH SEEDLNG B.R.)",5.1544852941176469]
["802-12.27","LAND","POPULUS DELTOIDES (COTTONWOOD SEEDLNG B.R.)",4.34]
["802-12.51","LAND","CORNUS AMOMUM (SILKY DOGWOOD SEEDLING B.R.)",15.316426799007445]
["607-05.04","DRNG","24\" CONCRETE PIPE CULVERT (CLASS V)",91.310000000000016]
["607-06.04","DRNG","30\" CONCRETE PIPE CULVERT (CLASS V)",110.68]
["607-08.03","DRNG","42\" CONCRETE PIPE CULVERT (CLASS IV)",131.18]
["607-08.04","DRNG","42\" CONCRETE PIPE CULVERT (CLASS V)",158.97370370370371]
["607-13.30","DRNG","72\" PIPE CULVERT",242.23]
["607-41.02","DRNG","15\" SLOPE DRAIN PIPE",32.450000000000003]
["607-41.03","DRNG","18\" SLOPE DRAIN PIPE",36.25]
["607-41.04","DRNG","24\" SLOPE DRAIN PIPE",53.07]
["611-01.10","STDR","MANHOLES,( __' - __' DEPTH) ( 40' - 44' DEPTH)",25505.49]
["710-10.01","DRNG","4\" PERFORATED PLASTIC PIPE",6.53899721448468]
["790-41.43","UTIL","UG PRI COND ____ __ __ ____ ________ (1/0 CU. URD)",31.24]
["790-42.04","UTIL","2IN DIA GALVINIZED METAL PIPE",33.57]
["790-43.53","UTIL","1PH PRIMARY RISER W/ 3IN CONDUIT",2988.9]
["793-13.02","UTIL","4IN CASING",43.48]
["801-01.10","LAND","SEEDING (WITH BONDED FIBER MATRIX)",59.283249258160239]
["805-01.04","LAND","TURF REINFORCEMENT MAT (CLASS IV)",4.32]
["204-05.01","STBR","CORE DRILLING AND SAMPLING",70.949124513618671]
["303-20.02","DRNG","RIVER GRAVEL",25.597977243994944]
["404-01.01","ASPH","BITUMINOUS MATERIAL (DBST)",900]
["404-01.02","ASPH","MINERAL AGGREGATE (DBST)",20]
["604-11.02","STBR","EXPANSION DEVICE (PIER NO. 3, 10\" MOVEMENT)",1560.9153393665158]
["607-06.03","DRNG","30\" CONCRETE PIPE CULVERT (CLASS IV)",200]
["607-11.02","DRNG","60\" CONCRETE PIPE CULVERT (CLASS II)",296.80790476190475]
["607-65.78","SLIP","54IN MIN I.D. to SLIP LINE 60IN CMP",50]
["625-02.14","STBR","DRILLED SHAFT-ROCK (DIA.)",2232.1597701149426]
["625-02.25","STBR","DRILLED SHAFT CASING-PERMANENT (DIA.)",1207.9871645274213]
["625-02.40","STBR","DRILLED SHAFT (SH-SCC) CONCRETE",371.70557133121309]
["625-02.43","STBR","CONCRETE CORING",69.015760441292358]
["705-04.10","GAT","EARTH PAD FOR GUARD RAIL END TREATMENT",894.33333333333337]
["714-16.01","LITE","NAVIGATIONAL LIGHTING",116800]
["725-03.50","ITS","RADAR DETECTION SYSTEM",8049]
["730-09.03","TRFP","SPAN WIRE ASSEMBLY (26,800 LBS.MIN.BRK STRENGTH)",4.0999999999999996]
["790-04.08","UTIL","POLE 45FT CLASS H1 METAL",5570]
["790-26.12","UTIL","3PH CROSSARM DBL SM ANGLE 25KV",1810.5877272727273]
["790-26.17","UTIL","3PH VERTICAL MED ANGLE 25KV",1650]
["790-30.15","UTIL","SECONDARY CONDUCTOR 2/0 AL TRIPLEX",8.3699999999999992]
["790-41.47","UTIL","UG SEC COND 2/0 AL TPLX",8.2642348754448403]
["790-59.04","UTIL","HOOK STICK SWITH LINE TENSION-SNGL 25KV",2400]
["793-01.04","UTIL","POLE 30FT CLASS 7 WOOD",932]
["795-03.03","UTIL","3IN PVC WATER LINE",20.68]
["795-05.61","UTIL","BORE/JACK 8IN STEEL CASING PIPE-UNCON.",169.22]
["795-10.01","UTIL","3/4IN AUTO AIR RELEASE VALVE ASSEMBLY",1600]
["797-03.09","UTIL","10IN PVC FORCE MAIN",34.39]
["797-07.62","UTIL","MANHOLE MODIFICATION",4064.5]
["797-10.19","UTIL","CONNECT TO 10IN FORCE MAIN",4280]
["797-10.32","UTIL","PUMP STATION",517500]
["797-10.36","UTIL","PUMP STATION RETIRE IN PLACE",11066]
["802-11.01","LAND","ACER NEGUNDO (BOX ELDER 2-5FT CNTNR GRWN)",32.875]
["802-11.15","LAND","FAGUS GRANDIFOLIA (BEECH 2-5FT CNTNR GRWN)",21.875]
["411-12.04","ASPH","SCORING FOR RUMBLE STRIPE (NON-CONTINUOUS) (4IN WIDTH)",859.72849462365593]
["713-02.26","TRFP","CONCRETE BARRIER/PARAPET DELINEATOR",10.598400932400931]
["775-60.01","UTIL","18IN BALL AND SOCKET RESTRAINED DUCTILE IRON PIPE",662.49]
["775-60.02","UTIL","12IN BALL AND SOCKET RESTRAINED DUCTILE IRON PIPE",215.14]
["790-02.01","UTIL","POLE 35FT CLASS 2 WOOD",1268.4166666666667]
["790-26.23","UTIL","3PH VERTICAL DEAD END 25KV",1657.6737499999999]
["790-33.16","UTIL","ROCK ANCHOR TRIPLE EYE",657]
["790-41.55","UTIL","UG SEC COND 1/0 AL QPLX",11.1]
["790-61.09","UTIL","3PH SECTIONALIZER OR RECL 25KV",11470]
["790-61.11","UTIL","3PH SECTLR OR RECL W/ BYP SW ELECTC 25KV",10609]
["790-69.07","UTIL","HARDWARE FOR SGL PH CONV TRANS DE",932.14285714285711]
["791-04.06","UTIL","HDD 8IN PE PIPE - UNCONSOLIDATED",266.45476772616138]
["795-01.90","UTIL","MASTER METER VAULT W/BYPASS",50000]
["611-03.04","STDR","GRAY IRON CASTINGS (CATCHBASIN)",4]
["714-09.04","LITE","LUMINAIRES (400 WATT)",1255.047619047619]
["203-40.03","MISC","ROCK ANCHORS (UNTENSIONED ROCK DOWEL)",152]
["204-09.02","STBR","COFFERDAM (PIER NO. 1 - STA. 22+25.00)",124000.5]
["204-09.03","STBR","COFFERDAM (PIER NO. 1 - STA. 22+25.00)",248000]
["204-09.04","STBR","COFFERDAM (PIER NO. 1 - STA. 22+25.00)",248000]
["604-03.25","STBR","CLASS S CONCRETE (FOUNDATION SEAL)",475]
["607-40.05","DRNG","CORRUGATED METAL PIPE ARCH (SIZE EQUIV. 30\" ROUND)",170]
["611-44.04","STDR","CATCH BASINS, TYPE 44, > 12' - 16' DEPTH",14915]
["706-10.26","GAT","ROUNDED END ELEMENT",60.333333333333336]
["725-21.07","ITS","PORTABLE SMART WORK ZONE SYSTEM",305.96759916492692]
["790-26.11","UTIL","3PH VERTICAL TANGENT SM ANGLE 25KV",1646.25]
["790-31.16","UTIL","SERVICE CONDUCTOR__ AL TRIPLEX (SEE PLANS)",3.49]
["790-41.12","UTIL","UG PRI COND 1 AL 25KV",11.508291457286433]
["790-59.05","UTIL","GOLB SWITCH 25KV",33971.5]
["790-61.03","UTIL","1PH SECTIONALIZERS OR RECLOSER 25KV",1128.3333333333333]
["790-63.16","UTIL","3PH OVR-3SP ELECTRONIC RECLOSER 25KV",8330]
["790-63.17","UTIL","3PH TYPE SDR ELECTRONIC RECLOSER 25KV",10100]
["790-69.02","UTIL","CROSSARM - 10FT",675]
["791-01.20","UTIL","8IN HIGH PRESSURE STEEL GAS MAIN",115]
["791-01.21","UTIL","8IN PWRCRETE COATED HP STL GAS MN- OPEN CUT",137]
["791-06.34","UTIL","CONNECT TO 8IN EX. STL MAIN W/ STOPPLE",39000]
["795-01.99","UTIL","12IN DIP SLIP JOINT W/GEOTECH FABRIC STONE",99]
["795-02.07","UTIL","12IN HDPE WATER LINE",294]
["795-09.25","UTIL","TI OF 2IN HDPE CASING FOR SERVICE PIPE-ROCK",57.537735849056602]
["795-09.36","UTIL","TI OF 4IN HDPE CASING FOR SERVICE PIPE-ROCK",72]
["795-09.37","UTIL","3/4IN SERVICE PIPE",15.528530805687204]
["795-09.38","UTIL","1N SERVICE PIPE",19]
["795-09.39","UTIL","2N SERVICE PIPE",29.571428571428573]
["797-06.99","UTIL","HDD 10IN HDPE CARRIER PIPE-ROCK",294]
["802-11.30","LAND","QUERCUS BICOLOR (SWAMP WHITE OAK 2-5FT CNTNR GRWN)",11]
["802-11.33","LAND","QUERCUS MICHAUXII (SWMP CHSTNT OAK 2-5FT CNTNR GRWN)",19.444444444444443]
["802-11.41","LAND","SASSAFRAS ALBIDUM (SASSAFRAS 2-5FT CNTNR GRWN)",13.702586206896552]
["802-12.35","LAND","QUERCUS NIGRA (WATER OAK SEEDLNG B.R.)",10.80281690140845]
["802-12.37","LAND","QUERCUS PALUSTRIS (PIN OAK SEEDLNG B.R.)",7.6115107913669062]
["802-13.37","LAND","VIBURNUM NUDUM (POSSUMHAW VIBURNUM 2-5 FT CNTNR GRWN)",11]
["802-13.53","LAND","CEPHALANTHUS OCCIDENTALIS (BUTTONBUSH SDLNG BARE ROOT)",11]
["209-08.04","EROS","TEMPORARY ENHANCED SILT FENCE",10.487269815852683]
["607-06.08","DRNG","36\" CONCRETE PIPE CULVERT CLASS V (JACKED-IN-PLACE) (SEE PLANS)",875]
["607-08.06","DRNG","42\" CONCRETE PIPE CULVERT (CLASS V) JACKED-IN-PLACE",1235]
["607-37.11","DRNG","72\" CORRUGATED METAL PIPE CULVERT",247.28571428571428]
["611-07.51","STDR","15IN ENDWALL (CROSS DRAIN) 3:1",1300]
["611-38.05","STDR","CATCH BASINS, TYPE 38, > 16' - 20' DEPTH",9250]
["611-38.06","STDR","CATCH BASINS, TYPE 38, > 20' - 24' DEPTH",14800]
["611-38.08","STDR","CATCH BASINS, TYPE 38, >(  ' -   ' DEPTH) (28' - 32' DEPTH)",11600]
["713-02.27","TRFP","CONCRETE BARRIER/PARAPET DELINEATOR (BI-DIRECTIONAL)",9.8740737659456475]
["795-01.18","UTIL","20IN DIP SLIP JOINT WATER LINE",79.789674160371362]
["795-03.34","UTIL","6IN C900 PVC WATER LINE",20.45]
["795-03.35","UTIL","8IN C900 PVC WATER LINE",24.12]
["795-03.36","UTIL","10IN C900 PVC WATER LINE",25.74]
["795-03.37","UTIL","12IN C900 PVC WATER LINE",31.55]
["795-06.11","UTIL","CONNECT TO 20IN WATER LINE",5254.7033333333338]
["795-08.17","UTIL","20IN BUTTERFLY VALVE ASSEMBLY",6158.19]
["802-11.13","LAND","CRATAEGUS PHAENOPYRUM (WSHNGTN HAWTHORN 2-5FT CNTNR GRWN)",56.5]
["802-11.57","LAND","VIBURNUM RUFIDULUM (RUSTY BLACKHAW 2-5FT C.G.)",65]
["204-10.03","STBR","FOUNDATION PREPARATION(PR NO.  ,STA          )",76767.539999999994]
["204-10.04","STBR","FOUNDATION PREPARATION(PR NO.  ,STA          )",76767.539999999994]
["607-50.69","DRNG","DEEP CORRUGATED STRUCTURE PLATE BRIDGE",1561.32]
["716-13.08","PVMK","SPRAY THERMO PVMT MRKNG (40 mil) (8IN BARRIER LINE)",1.075]
["201-07.01","ERTH","REMOVAL AND DISPOSAL OF BRUSH & TREES",5000]
["707-03.20","FNCE","DRIVE GATE (STOCK FENCE) (DESCRIPTION)",905]
["802-02.37","LAND","CUTTINGS: ALNUS SERRULATA (18IN-24IN)",17]
["802-11.14","LAND","DIOSPYROS VIRGINIANA (PERSIMMON 2-5FT CNTNR GRWN)",30.863636363636363]
["802-11.32","LAND","QUERCUS LYRATA (OVERCUP OAK 2-5FT CNTNR GRWN)",30]
["802-11.38","LAND","QUERCUS PHELLOS (WILLOW OAK 2-5FT CNTNR GRWN)",30]
["802-11.46","LAND","QUERCUS SHUMARDII (SHUMARD OAK 2-5 FT CNTNR GRWN)",30]
["802-11.63","LAND","HAMAMELIS VIRGINIANA (AMERICAN WITCHHAZEL 2-5FT CNTNR GRWN)",30]
["802-12.14","LAND","DIOSPYROS VIRGINIANA (PERSIMMON SEEDLNG B.R.)",21.475728155339805]
["802-12.32","LAND","QUERCUS LYRATA (OVERCUP OAK SEEDLNG B.R.)",24]
["802-12.33","LAND","QUERCUS MICHAUXII (SWMP CHSTNT OAK SEEDLNG B.R.)",21.606741573033709]
["802-12.38","LAND","QUERCUS PHELLOS (WILLOW OAK SEEDLNG B.R.)",20.460176991150444]
["802-13.59","LAND","LINDERA BENZOIN (SPICEBUSH SDLNG BARE ROOT)",21.186666666666667]
["802-15.06","LAND","CASTANEA DENTATA (AMERICAN CHESTNUT)",125]
["805-12.08","LAND","700 GRAM COIR FIBER EROSION BLANKET",7.0709332725338196]
["202-01.51","ERTH","REMOVAL OF STRUCTURES AND OBSTRUCTIONS",2000]
["202-01.52","ERTH","REMOVAL OF STRUCTURES AND OBSTRUCTIONS",2000]
["202-01.53","ERTH","REMOVAL OF STRUCTURES AND OBSTRUCTIONS",1000]
["209-03.41","EROS","STREAM MITIGATION - BOULDER RIFFLE",500]
["209-03.60","EROS","STREAM MITIGATION - ROCK VANE",7500]
["701-01.09","FLAT","ORNAMENTAL CONCRETE (DESCRIPTION)",15]
["707-03.03","FNCE","STOCK FENCE GATE (DESCRIPTION)",883.7]
["712-09.21","TRFT","REMOVABLE WET REFLECTIVE PAVEMENT MARKING TAPE",2.8374977848662057]
["716-08.02","PVMK","REMOVAL OF PAVEMENT MARKING (8\" BARRIER LINE)",1.3623153976933327]
["716-08.09","PVMK","REMOVAL OF PAVEMENT MARKING (DOTTED LINE)",0.86480787253983127]
["716-16.10","PVMK","PREFORMED  YIELD WORD (8FT W/ 1 Â½IN BLACK CONTRAST)",1200]
["719-01.01","SWDR","SWEEPING",500]
["725-03.53","ITS","VIDEO DETECTION SYSTEM",32117]
["725-03.80","ITS","CCTV CAMERA SYSTEM",10260]
["730-03.25","TRFP","INSTALL PULL BOX (DESCRIPTION)",510.90000000000003]
["730-15.42","TRFP","MASTER CONTROLLER (FIBER)",6881]
["730-24.41","TRFT","CANTILEVER SIGNAL SUPPORT (DESCRIPTION)",20724.383333333335]
["730-24.42","TRFT","CANTILEVER SIGNAL SUPPORT (DESCRIPTION)",17450]
["730-24.43","TRFT","CANTILEVER SIGNAL SUPPORT (DESCRIPTION)",19354]
["730-24.44","TRFT","CANTILEVER SIGNAL SUPPORT (DESCRIPTION)",21369]
["730-24.45","TRFT","CANTILEVER SIGNAL SUPPORT (DESCRIPTION)",22012]
["730-24.46","TRFT","CANTILEVER SIGNAL SUPPORT (DESCRIPTION)",25278]
["730-24.47","TRFT","CANTILEVER SIGNAL SUPPORT (DESCRIPTION)",25867]
["730-24.48","TRFT","CANTILEVER SIGNAL SUPPORT (DESCRIPTION)",25906]
["801-01.08","LAND","SEEDING (SPECIAL MIXTURE) WITH MULCH",40.340484429065739]
["202-04.52","RMVL","REMOVAL OF STRUCTURES (DESCRIPTION, STA.)",14500]
["615-02.37","STBR","PRESTRESSED CONCRETE BOX BEAM (30\" X 36\")",325]
["790-07.08","UTIL","POLE 60FT CLASS H2 METAL",7534.0576923076924]
["790-41.30","UTIL","UG PRI COND 500MCM CU 15KV",102.12]
["790-42.11","UTIL","6IN DIA PVC PIPE",20]
["790-64.11","UTIL","SEC MTG 3PH 240 OR 480 VOLTS (3 W GRD ?)",1845]
["790-69.30","UTIL","POLE TOP PIN FOR ST POLE",180]
["795-09.63","UTIL","1 1/4 IN PEXa SERVICE PIPE",34]
["797-06.69","UTIL","BORE/JACK 36IN STEEL CASING PIPE-UNCON.",926.88679245283015]
["607-57.02","DRNG","REINFORCED CONCRETE PIPE ARCH (29\" X 18\")",105]
["607-57.03","DRNG","REINFORCED CONCRETE PIPE ARCH (36\" X 23\")",115]
["607-57.01","DRNG","REINFORCED CONCRETE PIPE ARCH (22\" X 13\")",135]
["730-09.20","TRFP","SPAN WIRE ASSEMBLY",3.6321714990746452]
["730-50","TRFT","TEMPORARY TRAFFIC SIGNAL SYSTEM (RADIO CONTROLLED)",33700]
["797-01.16","UTIL","12IN EPOXY COATED DIP FORCE MAIN",135.44444444444446]
["797-13.06","UTIL","CREEK CROSSING (#)",6500]
["611-16.03","STDR","CATCH BASINS, TYPE 16, > 8' - 12' DEPTH",10283.304]
["615-01.04","STBR","PRESTRESSED CONCRETE I-BEAM (TYPE IV)",238]
["790-05.04","UTIL","POLE 50FT CLASS 4 WOOD",1755]
["790-31.14","UTIL","SERVICE CONDUCTOR 3/0 AL TRIPLEX",13.580000000000002]
["790-31.19","UTIL","SERVICE CONDUCTOR 2 AL QPLEX",7.8128571428571432]
["790-33.17","UTIL","ROCK ANCHOR EXPANDING TYPE",605]
["790-42.09","UTIL","3IN DIA PVC PIPE",25]
["790-61.06","UTIL","1PH SECTLR OR RECL W/ BYPASS SW 25KV",6270]
["790-63.05","UTIL","1PH ELECTR RECL 800A CONT 10000A INT 25KV",8160]
["790-69.01","UTIL","CROSSARM - 8FT",205]
["793-13.11","UTIL","1 DUCT FORMATION @ 24IN DEPTH",21.937642585551334]
["611-05.01","STDR","TRENCH DRAINS",188.84699453551912]
["611-41.05","STDR","CATCH BASINS, TYPE 41, > 16' - 20' DEPTH",7500]
["611-42.05","STDR","CATCH BASINS, TYPE 42, > 16' - 20' DEPTH",8100]
["611-42.07","STDR","CATCH BASINS, TYPE 42, > 24' - 28' DEPTH",11100]
["611-43.04","STDR","CATCH BASINS, TYPE 43, > 12' - 16' DEPTH",10300]
["611-45.02","STDR","CATCH BASINS, TYPE 45, > 4' - 8' DEPTH",7300]
["705-06.02","GAT","W BEAM GR (TYPE 2) MASH TL3 (LONG POST)",22.200522041763339]
["713-09.20","TRFP","STEEL OVERHEAD SIGN STRUCTURE",33950]
["713-16.51","TRFP","REMOVE AND REPLACE SIGN (DESCRIPTION)",80]
["713-16.52","TRFP","REMOVE AND REPLACE SIGN (DESCRIPTION)",67]
["713-16.53","TRFP","REMOVE AND REPLACE SIGN (DESCRIPTION)",67]
["714-08.12","LITE","LIGHT STANDARDS (DESCRIPTION)",16819.0625]
["716-04.09","PVMK","PLASTIC PAVEMENT MARKING (H.O.V. DIAMOND)",450]
["716-09.32","PVMK","EXIT ONLY ARROW",350]
["716-12.06","PVMK","ENHANCED FLAT LINE THERMO (8IN LINE)",2.9716122794295381]
["725-20.04","ITS","CCTV POLE REMOVE AND RELOCATE",15076]
["725-20.54","ITS","CABLE (1/C #8 AWG.)",1.4]
["725-20.55","ITS","CABLE (1/C #6 AWG.)",1.7]
["725-20.72","ITS","ELECTRICAL CONNECTION (DESCRIPTION)",3796]
["725-20.73","ITS","ELECTRICAL CONNECTION (DESCRIPTION)",6464]
["725-21.52","ITS","REMOVAL & REPLACE TYPE B CABINET",814]
["725-21.94","ITS","RADAR DETECTION SYSTEM REMOVE & RELOCATE",2344]
["725-21.95","ITS","RADAR DETECTION SYSTEM REMOVAL",6131]
["725-22.23","ITS","CONDUIT BANK (TYPE 3)",13]
["725-22.71","ITS","2IN CONDUIT",6.4]
["725-22.72","ITS","2IN CONDUIT BORED",33.5]
["725-22.73","ITS","2IN STRUCTURE CONDUIT",22]
["725-23.02","ITS","FIBER OPTIC TESTING",4833.1000000000004]
["730-05.03","TRFP","SERVICE CABLE (DESCRIPTION)",1.2268964633521271]
["730-08.42","TRFP","INTERCONNECT CABLE - FIBER OPTIC (DESCRIPTION)",2.7]
["730-12.17","TRFP","CONDUIT (DESCRIPTION)",19.600000000000001]
["730-13.12","TRFP","VEHICLE DETECTOR (DESCRIPTION)",7293]
["730-15.07","TRFP","CABINET (DESCRIPTION)",12784.23076923077]
["730-16.14","TRFP","CONTROLLER (DESCRIPTION)",4578]
["730-23.87","TRFP","CANTILEVER SIGNAL SUPPORT (2 @ 40' & 45')",19989]
["730-23.91","TRFP","CANTILEVER SIGNAL SUPPORT ()",17763]
["802-01.15","LAND","TREES (DESCRIPTION)",443.9964705882353]
["802-03.04","LAND","SHRUBS (DESCRIPTION)",39]
["802-13.08","LAND","ITEA VIRGINICA (VIRGINIA SWEETSPIRE 2-5FT CNTNR GRWN)",28.5]
["802-13.28","LAND","AMORPHA FRUTICOSA (INDIGOBUSH 2-5 FT CNTNR GRWN)",28.5]
["805-01.65","LAND","TEMPORARY MULCH",16.5]
["603-02.01","BRPT","REPAINTING EXISTING STEEL STRUCTURES (LOC. & DES.)",257000]
["603-05.20","BRPT","CONTAINMENT & DISPOSAL OF WASTE(LOCATION & DESCRP)",150000]
["604-10.05","STBR","CONCRETE",229.27884615384616]
["625-02.02","STBR","DRILLED SHAFT-SOIL (DIA.)",522.27628205128212]
["625-02.44","STBR","DRILLED SHAFT REINFORCING STEEL",1.3173674012544965]
["625-02.46","STBR","SONIC LOGGING TESTING",7127.5]
["711-02.05","BARR","REINFORCED CONCRETE MEDIAN BARRIER (DESCRIPTION)",172]
["202-13.01","ERTH","WELL ABANDONMENT (DESCR)",4200]
["202-13.02","ERTH","WELL ABANDONMENT (DESCR)",2824.88]
["712-02.36","TRFT","REMOVE AND RELOCATE PORTABLE BARRIER RAIL",1.667738402854682]
["712-07.01","TRFT","TEMPORARY BARRICADES (TYPE I)",10.5]
["714-03.03","LITE","DIRECT BURIAL CONDUIT (DESCRIPTION)",10.5]
["722-01.02","MISC","FIELD OFFICE (TYPE 2)",42545]
["604-11.03","STBR","EXPANSION DEVICE (DESCRIPTION)",366.79]
["620-05.02","BARR","STANDARD CONCRETE CLASSIC PARAPET RAIL",368.73]
["625-01.11","STBR","CAMERA INSPECTION - DRILLED SHAFT (UNDERWATER)",1312.5]
["625-02.26","STBR","DRILLED SHAFT CASING-PERMANENT (DIA.)",761.25]
["791-03.40","UTIL","CABLE (1/C # 2 AWG)",15.75]
["797-05.14","UTIL","16IN DIP GRAVITY SEWER 6FT-12FT DEPTH",184.4]
["502-04.02","CONC","LOAD TRANSFER DOWELS",46.44]
["607-02.30","DRNG","15IN PIPE CULVERT",45.685185185185183]
["607-11.04","DRNG","60\" CONCRETE PIPE CULVERT (CLASS IV)",264.44438661710035]
["607-37.05","DRNG","36\" CORRUGATED METAL PIPE CULVERT",121]
["611-12.07","STDR","CATCH BASINS, TYPE 12, > 24' - 28' DEPTH",21200]
["611-25.05","STDR","CATCH BASINS, TYPE 25, > 16' - 20' DEPTH",16300]
["714-10.02","LITE","OVERHEAD CONDUCTORS (GAUGE & TYPE) (#2 TRIPLEX)",1]
["716-08.07","PVMK","REMOVAL OF PAVEMENT MARKING (STRAIGHT-TURN ARROW)",72.833333333333329]
["790-04.21","UTIL","POLE 45FT CLASS 3 MATERIAL",1370]
["790-05.16","UTIL","POLE 50FT CLASS 3 METAL",1650]
["790-07.06","UTIL","POLE 60FT CLASS 2 METAL",2200]
["790-08.13","UTIL","POLE 65FT CLASS 2 METAL",2740]
["790-08.14","UTIL","POLE 65FT CLASS H1 METAL",3430]
["790-13.08","UTIL","POLE 90FT CLASS H5 METAL",14700]
["790-13.14","UTIL","POLE 90FT CLASS 1 METAL",23457.142857142859]
["790-33.30","UTIL","SCREW TYPE ANCHOR 16,000LB (F1-2D-P)",394]
["790-42.18","UTIL","3 DUCT BANK @ 36IN-48IN DEPTH",142.44894026974953]
["790-43.06","UTIL","LOADBREAK JUNCTION 4 PT 200A 15KV",1340]
["790-43.08","UTIL","ELBOW ARRESTER 200A 15KV",520]
["790-73.01","UTIL","INS STRING W/ SUSPENSIONS CLAMP",677]
["790-73.04","UTIL","OHGW CUSHIONED SUSP & SUSP CLAMP",293]
["790-73.17","UTIL","SWITCH GOAB 3W 1200A 69KV MAX",49400]
["791-02.27","UTIL","<=2 IN PE TEMP. BY-PASS FOR TIE-IN",637]
["791-08.33","UTIL","1IN HDPE SERVICE PIPE",10.5]
["791-08.41","UTIL","GAS MAIN REMOVAL",1.05]
["797-05.50","UTIL","30IN DIP AERIAL GRAVITY SEWER (FLANGED & FLANGED)",1770]
["797-07.47","UTIL","96IN MANHOLE 6FT-8FT DEPTH",30300]
["797-07.85","UTIL","CAST-IN-PLACE PIERS",6650]
["797-07.86","UTIL","CAST-IN-PLACE MANHOLE",17400]
["797-11.28","UTIL","RETIREIN PLACE 84IN MANHOLE",6570]
["797-11.33","UTIL","RETIREIN PLACE EXISTING SEWER >24IN",35.5]
["208-02.01","ERTH","DITCH (RIPRAP, SAND & PLASTIC SHEETING)",25]
["209-11.20","EROS","SEDIMENT BASIN BAFFLES",32]
["209-20.21","EROS","SEDIMENT POND OUTLET STRUCTURE (DISCR.)",1]
["606-19.01","STBR","TEST PILES (STEEL PIPE PILES, 16-INCH)",133.94202898550725]
["606-19.02","STBR","LOADING TEST (STEEL PIPE PILES, 16-INCH)",6833.333333333333]
["606-19.03","STBR","STEEL PIPE PILES (16-INCH)",90.175182481751818]
["607-50.11","DRNG","PRECAST CONCRETE BOX CULVERT (8' X 6')",690]
["627-01.02","ENGR","PREFABRICATED VERTICAL DRAIN",0.71]
["627-01.03","ENGR","DRAINAGE LAYER MATERIAL",40]
["710-10.02","DRNG","6\" PERFORATED PLASTIC PIPE",25.899795501022496]
["712-09.08","TRFT","REMOVABLE PAVEMENT MARKING (6\" line)",1.4334460338101429]
["716-03.03","PVMK","PLASTIC WORD PAVEMENT MARKING (STOP AHEAD)",412.08333333333331]
["716-08.33","PVMK","HYDROBLAST REMOVAL OF PAVEMENT MARKING (MERGE ARROW)",156.25]
["730-02.01","TRFP","SIGNAL HEAD ASSEMBLY (110)",475]
["730-02.27","TRFP","SIGNAL HEAD ASSEMBLY (440)",1100]
["730-16.03","TRFP","CONTROLLER (FLASHING BEACON)",150]
["730-21.03","TRFP","WOOD POLE (SIGNAL SUPPORT) CLASS 3, 45' LENGTH",2000]
["730-22.02","TRFP","GUYING DEVICE (ANGLE ANCHOR)",400]
["790-21.03","UTIL","1PH SGL SUPPORT NARROW PROFILE 15KV",273.61]
["790-21.13","UTIL","1PH CROSSARM DBL LINE ARM 15KV",1148.22]
["790-40.15","UTIL","OH COND 477 18/1 ACSR PELICAN",8.3314980118477653]
["790-60.12","UTIL","3PH SECTLR OR RECL W/ BYP SW ELECTNC 15KV",57676.72]
["790-74.19","UTIL","12-96 FIBER(INSTALLATION ONLY)",3.07]
["797-01.08","UTIL","20IN DIP FORCE MAIN",125]
["797-09.13","UTIL","20IN PLUG VALVE ASSEMBLY",20000]
["797-09.27","UTIL","3IN AIR/VAC VALVE ASSEMBLY",9500]
["802-01.13","LAND","TREES (RED MAPLE)",259.41436363636365]
["802-01.14","LAND","TREES (EASTERN REDBUD)",260.2041379310345]
["802-12.06","LAND","ASIMINA TRILOBA (PAWPAW SEEDLNG B.R.)",4]
["802-12.61","LAND","ALNUS SERRULATA (HAZEL ALDER SEEDLING B.R.)",6.7060810810810807]
["202-02.28","ERTH","REMOVAL OF PIPE (24\"X36\" CMP)",17]
["203-04.02","ERTH","STRIPPING & STOCKPILE TOPSOIL",3]
["604-10.13","STBR","CONCRETE SLAB REMOVAL",9875]
["607-57.04","DRNG","REINFORCED CONCRETE PIPE ARCH (44\" X 27\")",107.54999999999998]
["611-28.02","STDR","CATCH BASINS, TYPE 28, > 4' - 8' DEPTH",4225]
["611-39.06","STDR","CATCH BASINS, TYPE 39, > 20' - 24' DEPTH",29445]
["611-51.01","STDR","CATCH BASINS, TYPE 51, 0' - 4' DEPTH",6200]
["611-51.05","STDR","CATCH BASINS, TYPE 51, > 16' - 20' DEPTH",20915]
["611-51.06","STDR","CATCH BASINS, TYPE 51, > 20' - 24' DEPTH",25350]
["621-03.01","DRNG","15\" TEMPORARY DRAINAGE PIPE",31.154889364739471]
["621-03.12","DRNG","TEMPORARY DRAINAGE PIPE ARCH (22\" x 13\")",69.04485714285714]
["621-03.13","DRNG","TEMPORARY DRAINAGE PIPE ARCH (30\" x 48\")",95]
["714-12.04","LITE","CONTROL CENTER (NO. 4)",24684.575000000001]
["714-12.05","LITE","CONTROL CENTER (NO. 5)",40000]
["716-05.03","PVMK","PAINTED PAVEMENT MARKING (CROSS-WALK)",8]
["725-03.46","ITS","DEMARCATION POINT RISER ASSEMBLY",1000]
["725-03.47","ITS","GROUND MOUNTED DEMARCATION POINT ASSEMBLY",500]
["730-03.31","TRFP","FIBER DISTRIBUTION BOX",400]
["730-12.42","TRFP","CURB MARKER (SIGNAL & F.O. CABLE IDENTIFICATION)",25]
["790-03.04","UTIL","POLE 40FT CLASS 5 WOOD",1590.175]
["790-30.45","UTIL","CONDUCTOR 1 #2 WP ACSR EL. SVC (CDR2 WACSR ESC) (#2 WACSR)",16]
["790-41.33","UTIL","UG PRI COND 2 CU 25KV",69]
["790-41.41","UTIL","UG PRI COND 750MCM CU 25KV",92]
["790-42.19","UTIL","4 DUCT BANK @ 36IN-48IN DEPTH",38.656126482213438]
["790-42.21","UTIL","8 DUCT BANK @ 36IN-48IN DEPTH",108]
["790-42.31","UTIL","MH 2WAY SM MONOLITHIC PC DIRT E (MH2WSM)",70000]
["790-42.32","UTIL","MH 2WAY MD MONOLITHIC PC DIRT E (MH2WMD)",70000]
["790-42.33","UTIL","MH 3WAY MD MONOLITHIC PC DIRT E (MH3WMD)",75000]
["790-43.26","UTIL","SPLICE 200A 25KV",2550]
["790-43.32","UTIL","SPLICE 900A 25KV",3075]
["790-65.09","UTIL","LIGHTNING ARRESTER 3PH 18 KV",810]
["790-72.01","UTIL","ANCHOR POWER SCREW",865]
["791-04.07","UTIL","HDD 12IN PE PIPE - UNCONSOLIDATED",146]
["791-04.24","UTIL","HDD 8IN STEEL PIPE - UNCONSOLIDATED",134]
["791-06.06","UTIL","CONNECT TO 12IN EX. PE MAIN",9800]
["791-08.20","UTIL","HDD 2IN PE SERVICE PIPE",95]
["791-08.26","UTIL","HDD 5/8 PE SERVICE PIPE",75]
["791-08.27","UTIL","5/8IN SERVICE ASSEMBLY",2400]
["793-13.18","UTIL","2 DUCT FORMATION @ 48IN DEPTH",40]
["793-13.23","UTIL","3 DUCT FORMATION @ 48IN DEPTH",45]
["793-13.28","UTIL","4 DUCT FORMATION @ 48IN DEPTH",50]
["793-13.29","UTIL","4 DUCT FORMATION @ 60IN DEPTH",50]
["793-13.33","UTIL","6 DUCT FORMATION @ 48IN DEPTH",75]
["795-06.37","UTIL","CUT AND CAP 12IN WATERLINE",2560.5309090909091]
["795-07.12","UTIL","12IN X 6IN TAPPING SLEEVE AND VALVE",7302.5]
["795-07.27","UTIL","20IN X 20IN TPPNG SLVE & VLVE",37280]
["795-07.62","UTIL","__IN X __IN TAPPING SLEEVE AND VALVE (20IN x 12IN)",17200]
["795-08.26","UTIL","12 IN CHECK VALVE ASSEMBLY",6110]
["797-07.60","UTIL","ADJUST EXISTING MANHOLE",1597.2785714285715]
["202-08.25","RMVL","REMOVAL OF MEDIAN BARRIER (STA. 117+40 TO 124+30, STA. 135+85 TO 1 38+20)",30771.99]
["209-03.37","EROS","STREAM MITIGATION CROSS VANE STRUCTURE",1147.2466666666667]
["607-37.10","DRNG","66\" CORRUGATED METAL PIPE CULVERT",280.02999999999997]
["716-13.05","PVMK","SPRAY THERMO PVMT MRKNG (60 mil) (6IN DOTTED LINE)",1.58]
["802-02.40","LAND","CUTTINGS: SALIX NIGRA (24-48IN LENGTH)",9.3934474327628372]
["802-02.42","LAND","CUTTINGS: CORNUS AMOMUM (24-48IN)",14.149136842105264]
["802-02.43","LAND","CUTTINGS: SAMBUCUS CANADENSIS (24-48IN)",14.149136842105264]
["802-02.45","LAND","CUTTINGS: CEPHALANTHUS OCCIDENTALIS (24-48IN)",43.62]
["802-02.47","LAND","CUTTINGS: ALNUS SERRULATA (24-48IN)",43.62]
["802-12.11","LAND","CERCIS CANADENSIS (REDBUD SEEDLNG B.R.)",14.034107142857144]
["303-10.02","BASE","MINERAL AGGREGATE (SIZE 2)",46.523931623931624]
["802-11.62","LAND","CORNUS ALTERNIFOLIA (ALTERNATE LEAF DGWOOD 2-5FT CNTNR GRWN)",36.75]
["802-11.64","LAND","ILEX DECIDUA (DECIDUOUS HOLLY 2-5FT CNTNR GRWN)",36.75]
["607-12.03","DRNG","66\" CONCRETE PIPE CULVERT (CLASS III)",687.45]
["716-08.13","PVMK","REMOVAL OF WORD PAVEMENT MARKING (STOP AHEAD)",100]
["791-01.12","UTIL","8IN PVC CASING OPEN CUT",83]
["791-06.52","UTIL","4IN PE HOT TAP CONNECTION",1200]
["791-11.01","UTIL","CLASS A CONCRETE",350]
["795-05.19","UTIL","HDD 10IN HDPE CASING PIPE-ROCK",460.69]
["797-06.19","UTIL","HDD 8IN HDPE CASING PIPE-ROCK",369.38]
["208-01.04","ERTH","ENGINEERED AGGREGATE-TOPSOIL (EAT) MIX",21.05]
["602-04.04","STBR","STEEL STRUCTURES (EASTBOUND, UNIT 3)",2275500]
["611-25.04","STDR","CATCH BASINS, TYPE 25, > 12' - 16' DEPTH",13560]
["620-03.11","BARR","CONCRETE PARAPET (PEDESTRIAN RAILING)",384.55]
["625-02.15","STBR","DRILLED SHAFT-ROCK (DIA.) (84\" DIA)",1773.25]
["625-02.16","STBR","DRILLED SHAFT-ROCK (DIA.) (90\" DIA)",2036.5]
["707-03.08","FNCE","TEMPORARY STOCK FENCE",10.6]
["710-04","DRNG","FILTER CLOTH UNDERDRAIN (WITH PIPE)",6.8]
["714-01.38","LITE","LIGHT POLE RELOCATION",4862.25]
["714-02.03","LITE","ENCASED CONDUIT (3\" PVC, SCHEDULE 40)",41.35]
["714-05.02","LITE","PULL BOXES (TYPE A)",568.15]
["714-08.28","LITE","FOUNDATION  FOR LIGHT STANDARDS - ROADWAY (ROADWAY)",1087]
["716-03.05","PVMK","PLASTIC WORD PAVEMENT MARKING (BIKE LANE)",615.35]
["725-05.02","ITS","FIBER OPTIC CABLE (60 STRAND SINGLE MODE)",3.6]
["740-08.01","STBR","CELLULAR CONFINEMENT SYSTEM (GRASS SHOULDERS)",16.3]
["740-10.02","EROS","GEOTEXTILE (TYPE II)(SEDIMENT CONTROL)",1.6]
["790-04.09","UTIL","POLE 45FT CLASS H2 METAL",6210]
["790-65.18","UTIL","CAPACITOR RADIO SWITCH",1081.25]
["791-04.33","UTIL","HDD 8IN STEEL PIPE - ROCK",360.75]
["795-05.70","UTIL","BORE/JACK 36IN STEEL CASING PIPE-UNCON.",942.15]
["795-14.06","UTIL","CONCRETE PIERS",988.75]
["797-01.07","UTIL","16IN DIP FORCE MAIN",112.25]
["797-06.95","UTIL","OPEN CUT 36IN STEEL CASING PIPE",269.05]
["797-07.13","UTIL","60IN MANHOLE 4FT-6FT DEPTH",4207.75]
["797-07.15","UTIL","60IN MANHOLE 8FT-10FT DEPTH",5598.5]
["797-10.21","UTIL","CONNECT TO 16IN FORCE MAIN",2935.75]
["797-13.04","UTIL","16IN BUTTERFLY VALVE ASSEMBLY",5473]
["802-11.12","LAND","CORNUS FLORIDA (FLOWERING DOGWOOD 2-5FT CNTNR GRWN)",39.5]
["802-12.12","LAND","CORNUS FLORIDA (FLOWERING DOGWOOD SEEDLNG B.R.)",11.276250000000001]
["802-12.13","LAND","CRATAEGUS PHAENOPYRUM (WSHNGTN HAWTHORN SEEDLNG B.R.)",22.55]
["802-12.41","LAND","SASSAFRAS ALBIDUM (SASSAFRAS SEEDLNG B.R.)",22.55]
["802-13.56","LAND","HYDRANGEA QUERCIFOLIA (OAKLF HYDRANGEA SDLNG BARE ROOT)",21.22]
["802-13.58","LAND","ITEA VIRGINICA (VIRGINIA SWEETSPIRE SDLNG BARE ROOT)",20.5]
["802-13.60","LAND","SAMBUCUS CANADENSIS ( ELDERBERRY SDLNG BARE ROOT)",20.5]
["717-01.10","MOBL","MOBILIZATION (GAS)",5250]
["791-06.26","UTIL","CONNECT TO 8IN EX. PE MAIN",4725]
["802-13.31","LAND","RHODODENDRON MAXIMUM (RHODODENDRON 2-5 FT CNTNR GRWN)",26.25]
["802-15.01","LAND","ELEOCHARIS ACICULARIS (SLENDER SPIKERUSH)",26.25]
["203-03.51","ERTH","BORROW EXCAVATION (UNCLASSIFIED)",2]
["204-02.10","STBR","DRILLED CAISSON - EARTH (42\" DIA)",91.11]
["204-02.11","STBR","DRILLED CAISSON - EARTH (48\" DIA.)",123.25]
["204-02.20","STBR","DRILLED CAISSON - ROCK (42\" DIA.)",271.12]
["204-02.21","STBR","DRILLED CAISSON - ROCK (48\" DIA.)",373.05]
["209-40.32","EROS","CATCH BASIN PROTECTION (TYPE C)",233.4]
["611-41.04","STDR","CATCH BASINS, TYPE 41, > 12' - 16' DEPTH",7274.29]
["711-02.03","BARR","REINFORCED CONCRETE MEDIAN BARRIER (BRIDGES)",72.959999999999994]
["713-10.01","TRFP","STEEL CANTILEVER SIGN STRUCTURE (SIGN NO. P-8)",46931.82]
["713-10.02","TRFP","STEEL CANTILEVER SIGN STRUCTURE (SIGN NO. P-9)",48690.31]
["713-10.03","TRFP","STEEL CANTILEVER SIGN STRUCTURE (SIGN NO. P-10)",48690.31]
["714-01.37","LITE","LIGHT STANDARDS (PEDESTRIAN/STREET LIGHT)",2065.35]
["714-04.04","LITE","CONDUIT (STRUCTURES - 2\" PVC, SCHEDULE 40)",4.2]
["718-01.01","WALL","NOISE BARRIER (NOISE BARRIER NO. 1)",31.5]
["725-10.85","ITS","CONDUIT & PULL BOX NETWORK",365925]
["790-25.33","UTIL","3PH COVERED AERIAL CBL TANGET BRKT 15KV",478.8]
["790-25.35","UTIL","3PH COVERED AERIAL CBL ANGLE ASSMBLY 15KV",800.1]
["790-25.36","UTIL","3PH COVERED AERIAL CBL DE ASSEMBLY 15KV",2592.4499999999998]
["790-41.45","UTIL","UG SEC COND 2 AL TPLX",4.62]
["790-42.26","UTIL","__ DUCT BANK @ __IN-__IN DEPTH (ENCASED)",41.58]
["790-43.38","UTIL","PAD MTD SW 4-600A 15KV",50579.55]
["790-65.04","UTIL","LIGHTNING ARRESTER POLE MTD 9 KV",330.75]
["791-06.23","UTIL","CONNECT TO 2IN EX. PE MAIN",4492.5]
["793-16.23","UTIL","BORE/JACK 18IN CASING - UNCONSOLIDATED",273]
["795-12.08","UTIL","REMOVE WATER METER",579.16]
["802-01.16","LAND","TREES (CARYA OVATA 1.5 - 2\" CAL. B&B)",323.98]
["202-02","ERTH","REMOVAL OF STRUCTURE COMPONENTS & OBSTRUCTIONS",5000]
["606-20.10","STBR","TEST PILES (STEEL PIPE PILES, SIZE)",190]
["606-20.20","STBR","LOADING TEST (STEEL PIPE PILES, SIZE)",8500]
["606-20.30","STBR","STEEL PIPE PILES (20 INCH)",112]
["607-06.07","DRNG","36\" PIPE CULVERT (JACKED-IN-PLACE)",1150]
["730-02.33","TRFP","SIGNAL HEAD ASSEMBLY (150 A2V POLE MOUNTED)",1104.57]
["740-07.03","ERTH","GEOGRID REINFORCEMENT TYPE 1",4.5]
["802-11.44","LAND","ULMUS AMERICANA (AMERICAN ELM 2-5FT CNTNR GRWN)",20]
["604-10.02","STBR","CONCRETE REPAIRS",1350]
["604-10.42","STBR","CONCRETE REPAIRS",480]
["607-37.01","DRNG","15\" CORRUGATED METAL PIPE CULVERT",40]
["607-45.01","DRNG","15\" SLOTTED DRAIN PIPE",230]
["607-65.65","SLIP","24\" MINIMUM ID PIPE TO SLIP LINE 30\" PIPE",221]
["607-65.67","SLIP","33\" MINIMUM ID PIPE TO SLIP LINE 42\" PIPE",355]
["607-65.69","SLIP","42\" MINIMUM ID PIPE TO SLIP LINE 54\" PIPE",365]
["607-65.71","SLIP","60\" MINIMUM ID PIPE TO SLIP LINE 72\" PIPE",488]
["611-31.05","STDR","CATCH BASINS, TYPE 31, > 16' - 20' DEPTH",22600]
["615-01.01","STBR","PRESTRESSED CONCRETE I-BEAM (TYPE I)",180]
["713-17.60","TRFP","SIGN MOUNTED ON CONCRETE MEDIAN BARRIER (W4-2L)",335]
["713-17.61","TRFP","SIGN MOUNTED ON CONCRETE MEDIAN BARRIER (TN-60D)",335]
["713-17.62","TRFP","SIGN MOUNTED ON CONCRETE MEDIAN BARRIER (TN-60F)",335]
["725-22.64","ITS","STRUCTURE CONDUIT BANK (TYPE 4)",90]
["725-22.76","ITS","2IN CONDUIT STRUCTURE W/BANK",16]
["802-02.34","LAND","CUTTINGS: SALIX INTERIOR (18IN-24IN)",50]
["208-01.05","ERTH","BROOMING & DEGRASSING SHOULDERS",2525.7820895522386]
["730-26.07","TRFP","FLASHING WARNING BEACON (DESCRIPTION)",2185]
["607-50.04","DRNG","PRECAST CONCRETE BOX CULVERT (10' X 4')",1200]
["209-08.06","EROS","ENHANCED SILT FENCE CHECK (TRAPEZOIDAL)",727]
["303-10.05","BASE","MINERAL AGGREGATE (SIZE   )",56]
["307-01.09","ASPH","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING C",159]
["307-03.06","ASPH","ASPHALT CONCRETE MIX (PG76-22) (BPMB-HM) GRADING B",129]
["411-01.11","ASPH","ACS MIX(PG64-22) GRADING E RDWY",182]
["611-05.02","DRNG","12IN PVC PIPE FOR TRENCH DRAINS",62.5]
["611-09.04","STDR","CATCHBASIN RETROFIT",1030]
["611-17.05","STDR","CATCH BASINS, TYPE 17, > 16' - 20' DEPTH",18300]
["701-01.04","FLAT","CAST-IN-PLACE TACTILE WARNING SYSTEM",868]
["707-01.03","FNCE","GATE - CHAIN-LINK FENCE-4 FOOT (DESCRIPTION)",993]
["707-10.08","MISC","WIRE MESH (DESCRIPTION)",4.8499999999999996]
["709-02.01","RIPR","RUBBLE STONE RIP-RAP (GROUTED)",105]
["716-05.08","PVMK","PAINTED PAVEMENT MARKING (PARKING LINE)",0.5]
["797-11.34","UTIL","REMOVE EXISTING SEWER <8IN",15.5]
["798-05.27","UTIL","COMMUNICATION ASSEMBLY (BOND)",187]
["707-01.23","FNCE","CHAIN LINK (8FT) (VINYL COATED) W/3STRAND B.WIRE",23.5]
["707-01.25","FNCE","GATE - CHAIN-LINK 8F (VNL CTD)(DESCRIPTION)",111]
["707-01.28","FNCE","END & CORNER POST ASSEMBLY (DESCRIPTION)",279]
["714-06.12","LITE","CABLE (DESCRIPTION)",1.85]
["714-08.29","LITE","REMOVE & RELOCATE LIGHT STANDARD",14930]
["790-03.31","UTIL","POLE 40FT CLASS 3 METAL",5380]
["790-05.09","UTIL","POLE 50FT CLASS H3 METAL",7680]
["790-07.18","UTIL","POLE 60FT CLASS H5 METAL",11550]
["790-08.31","UTIL","POLE 65FT CLASS H5 METAL",13340]
["790-09.06","UTIL","POLE 70FT CLASS H3 METAL",13120]
["790-09.08","UTIL","POLE 70FT CLASS H5 METAL",14930]
["790-10.06","UTIL","POLE 75FT CLASS H3 METAL",14320]
["790-11.15","UTIL","POLE 80FT CLASS H9 METAL",26390]
["790-13.07","UTIL","POLE 90FT CLASS H4 METAL",23470]
["790-13.15","UTIL","POLE 90FT CLASS H9 METAL",29080]
["790-15.04","UTIL","POLE 100FT CLASS H7 METAL",29150]
["790-15.05","UTIL","POLE 100FT CLASS H9 METAL",31900]
["790-26.44","UTIL","3PH ALLEY ARM 25KV",2600]
["790-32.29","UTIL","DOWN GUY HEAVY CONSTRUCTION - PREFORM",1170]
["790-33.27","UTIL","SCREW TYPE ANCHOR 32,000LB",1040]
["790-40.23","UTIL","OH COND 795 36/1 ACSR COOT",6]
["790-69.42","UTIL","EXTENSION LINK - EPOXY -10FT",315]
["793-11.17","UTIL","COMPOSITE HANDHOLE 5FTX3FTX3FT",3780]
["793-13.19","UTIL","2 DUCT FORMATION @ 60IN DEPTH",39]
["793-13.24","UTIL","3 DUCT FORMATION @ 60IN DEPTH",53]
["793-13.38","UTIL","9 DUCT FORMATION @ 48IN DEPTH",111]
["793-13.43","UTIL","12 DUCT FORMATION @ 48IN DEPTH",152]
["795-01.31","UTIL","3IN DIP RESTRAINED JOINT WATER LINE",239]
["202-06.11","RMVL","REMOVAL OF BUILDINGS (TRACT NO. 23)",1]
["202-06.12","RMVL","REMOVAL OF BUILDINGS (TRACT NO. 24)",1]
["203-20.01","ERTH","CHANNEL SUBSTRATE",85]
["204-10.07","STBR","FOUNDATION PREPARATION (PIER NO. 2, STA. 112+15.00)",50000]
["303-01.04","BASE","SELECT SAND BACKFILL (A-1-a, A-1-b, or A-3).",19]
["790-01.02","UTIL","POLE 30FT CLASS 3 WOOD",477.33]
["790-22.17","UTIL","1PH DDE FEED THROUGH 25KV",215.12000000000003]
["790-26.33","UTIL","3PH XARM DBL DDE UNBAL LOAD INV ARM 25KV",740.91]
["790-26.34","UTIL","3PH CROSSARM TPL DDE 25KV",1070.0899999999999]
["790-32.04","UTIL","DOWN GUY - WRAP TYPE",273.62]
["790-36.09","UTIL","TRANSFER - 1TR XFMR ASSEMBLY",135.16]
["790-41.25","UTIL","UG PRI COND 2/0 CU 15KV",25.41]
["790-52.03","UTIL","10KVA 1PH OH XFORMER 7.2KV 120/240",737.99]
["790-60.08","UTIL","3 - 1PH SECTLR OR RECL W/ BYPASS SW 15KV",3603.15]
["793-04.04","UTIL","10 PAIR AERIAL TERMINAL",284]
["793-04.21","UTIL","3 PAIR AERIAL DROP",1.88]
["793-06.02","UTIL","POLE MOUNTED XBOX",5637.54]
["793-07.27","UTIL","60 FIBER(MATERIAL ONLY)",0.66]
["793-09.05","UTIL","150 PAIR BURIED CABLE",11.12]
["793-09.09","UTIL","600 PAIR BURIED CABLE",18.010000000000002]
["793-10.08","UTIL","BURIED CABLE @___IN DEPTH",4.41]
["793-11.04","UTIL","6IN PEDESTAL",207.28]
["793-11.08","UTIL","10IN PEDESTAL",341.3]
["793-11.36","UTIL","3 PAIR BURIED DROP",3.49]
["793-12.06","UTIL","300 PAIR UG CABLE",15.840000000000002]
["793-12.18","UTIL","UG CABLE (SEB6-22)",5.88]
["793-16.03","UTIL","DIRECTIONAL BORE 3IN/FLEX SLEEVE",29.2]
["795-05.17","UTIL","HDD 6IN HDPE CASING PIPE-ROCK",150]
["795-09.26","UTIL","TI OF 2IN PVC CASING FOR SERVICE PIPE-UNCON",30]
["797-05.05","UTIL","10IN DIP GRAVITY SEWER 0FT-6FT DEPTH",158.26117647058823]
["797-06.85","UTIL","BORE/JACK __IN STEEL CASING PIPE-ROCK (16)",500]
["798-05.04","UTIL","1/4IN EHS STEEL STRAND",2.34]
["798-05.34","UTIL","COMMUNICATION ASSEMBLY (E1-2)",125]
["798-05.38","UTIL","COMMUNICATION ASSEMBLY (FP2)",304.47000000000003]
["798-09.01","UTIL","REMOVE STEEL STRAND",1]
["802-12.29","LAND","QUERCUS ALBA (WHITE OAK SEEDLNG B.R.)",7]
["802-13.55","LAND","HAMAMELIS VIRGINIANA (WITCH HAZEL SDLNG BARE ROOT)",22]
["725-23.12","ITS","FIBER OPTIC CABLE (48 F)",3.21]
["725-23.13","ITS","FIBER OPTIC CABLE (12 F)",3.21]
["773-26.56","UTIL","PM11   GUY GUARD",53.44]
["773-26.57","UTIL","PM2A   GROUND WIRE ELECTRIC NEUTRAL",83.36]
["773-26.69","UTIL","XXPE   REMOVE ANY SIZE DOWN OR OVERHEAD GUY",34.200000000000003]
["773-26.71","UTIL","XXSEA    REMOVE ANY SIZE AERIAL DROP",138.94]
["790-06.19","UTIL","POLE 55FT CLASS H1 WOOD",3022.6]
["790-25.05","UTIL","3PH DBL ALLEY ARM 15KV",1741.81]
["790-31.09","UTIL","SERVICE CONDUCTOR 6 AL TRIPLEX",13.72]
["790-31.27","UTIL","SERVICE CONDUCTOR 2 AL SGL COND",45.58]
["790-31.41","UTIL","SERVICE CONDUCTOR 500 CU QPLEX",37.520000000000003]
["790-42.15","UTIL","CONDUIT - POLE MTD - 6IN SCH 80 PVC",55.530000000000008]
["793-02.07","UTIL","GUY WIRE 6.6M OR 1/4IN",16.03]
["793-11.50","UTIL","REARRANGE EXISTING SPLICE CASE",374.04]
["793-11.51","UTIL","REARRANGE WORKING FIBER SPLICE",42.75]
["793-11.52","UTIL","REMOVE FIBER SPLICE CASE",374.04]
["793-11.58","UTIL","REMOVE HANDHOLE",534.35]
["793-11.60","UTIL","LONG EXTENSION ARM",149.62]
["793-98.07","UTIL","REMOVE UNDERGROUND TO OVERHEAD RISER",96.18]
["793-98.20","UTIL","TREE AND BRUSH REMOVAL OFF ROW",6979.67]
["795-07.02","UTIL","6IN X 4IN TAPPING SLEEVE AND VALVE",4767.74]
["795-07.51","UTIL","FLOW METER",7943.14]
["795-08.27","UTIL","4 IN CHECK VALVE",2690.12]
["795-08.28","UTIL","6 IN CHECK VALVE",3723.18]
["795-08.42","UTIL","CELLULAR RTU SIGNAL CONTROL",8267.6]
["795-16.02","UTIL","PRESSURE TRANSDUCER AND METER STATION",41654.9]
["795-16.14","UTIL","RELOCATE WATER PUMPING STATION FACILITIES",220177.28]
["795-20.01","UTIL","RECONNECT SERVICE ASSEMBLY",2904.28]
["797-02.01","UTIL","1IN HDPE FORCE MAIN",5.13]
["797-09.01","UTIL","1IN BALL VALVE",134.57]
["797-09.44","UTIL","CUT AND CAP 8IN GRAVITY",1326.21]
["208-01.02","ERTH","SHOULDER PREPARATION",1933.5700000000002]
["604-10.22","BARR","CONCRETE PARAPET REPAIR",157.5]
["604-10.89","STBR","MISCELLANEOUS BRIDGE ITEMS (Description) (INSPECTION HATCH)",77700]
["620-09","STBR","REMOVAL & REPLACEMENT OF EXISTING BRIDGE RAIL",315]
["713-04.02","TRFP","STEEL I-BEAMS & W-F BEAMS FOR SIGN SUPPORTS",4.05]
["716-05.64","PVMK","RETRACING PAVEMENT MARKINGS - PAINTED(6\" DOTTED LINE)",0.53]
["203-01.04","ERTH","REMOVAL OF ROCK PAD",30]
["712-09.09","TRFT","REMOVABLE PAVEMENT MARKING (4\" line)",3]

{"sheet":"Prelim Plans Est (STID Only)","index":15,"n_rows":2049,"n_cols":8,"rows_kept":2049,"cut":false,"hidden":true,"merged":[]}
["Category","Price"]
["Removal Items",{"$f":"SUMIF(F:F,A2,H:H)","v":0}]
["Asphalt Paving",0]
["Concrete Pavement",0]
["Drainage",0]
["Appurtenances",0]
["Structures",0]
["Fencing",0]
["Signalization & Lighting",0]
["Railroad Crossing",0]
["Earthwork",0]
["Clearing and Grubbing",0]
["Seeding & Sodding",0]
["Rip-Rap or Slope Protection",0]
["Guardrail ",0]
["Signing ",0]
["Pavement Markings ",0]
["Maintenance of Traffic",0]
["Mobilization",0]
["Other Items",0]
["Total:",{"$f":"SUM(B2:B20)","v":0}]
[]
[]
["ITEM NO.","DESCRIPTION","UNIT","QUANTITY","Item Class","Category","Average Unit Price","Item Price"]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A25,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E25,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A25,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D25*G25),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A26,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E26,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A26,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A27,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E27,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A27,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D27*G27),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A28,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E28,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A28,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A29,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E29,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A29,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A30,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E30,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A30,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A31,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E31,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A31,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A32,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E32,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A32,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A33,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E33,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A33,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A34,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E34,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A34,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A35,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E35,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A35,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A36,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E36,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A36,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A37,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E37,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A37,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A38,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E38,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A38,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A39,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E39,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A39,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A40,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E40,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A40,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A41,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E41,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A41,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A42,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E42,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A42,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A43,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E43,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A43,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A44,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E44,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A44,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A45,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E45,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A45,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A46,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E46,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A46,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A47,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E47,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A47,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A48,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E48,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A48,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A49,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E49,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A49,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A50,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E50,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A50,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A51,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E51,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A51,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A52,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E52,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A52,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A53,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E53,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A53,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A54,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E54,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A54,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A55,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E55,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A55,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A56,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E56,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A56,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A57,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E57,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A57,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A58,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E58,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A58,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A59,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E59,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A59,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A60,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E60,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A60,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A61,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E61,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A61,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A62,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E62,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A62,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A63,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E63,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A63,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A64,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E64,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A64,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A65,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E65,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A65,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A66,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E66,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A66,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A67,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E67,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A67,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A68,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E68,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A68,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A69,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E69,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A69,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A70,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E70,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A70,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A71,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E71,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A71,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A72,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E72,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A72,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A73,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E73,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A73,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A74,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E74,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A74,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A75,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E75,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A75,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A76,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E76,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A76,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A77,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E77,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A77,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A78,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E78,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A78,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A79,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E79,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A79,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A80,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E80,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A80,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A81,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E81,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A81,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A82,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E82,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A82,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A83,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E83,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A83,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A84,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E84,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A84,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A85,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E85,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A85,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A86,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E86,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A86,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A87,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E87,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A87,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A88,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E88,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A88,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A89,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E89,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A89,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A90,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E90,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A90,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A91,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E91,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A91,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D91*G91),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A92,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E92,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A92,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A93,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E93,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A93,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A94,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E94,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A94,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A95,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E95,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A95,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A96,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E96,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A96,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A97,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E97,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A97,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A98,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E98,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A98,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A99,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E99,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A99,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A100,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E100,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A100,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D100*G100),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A101,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E101,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A101,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A102,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E102,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A102,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A103,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E103,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A103,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A104,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E104,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A104,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A105,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E105,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A105,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A106,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E106,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A106,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A107,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E107,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A107,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A108,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E108,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A108,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A109,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E109,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A109,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A110,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E110,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A110,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A111,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E111,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A111,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A112,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E112,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A112,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A113,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E113,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A113,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A114,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E114,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A114,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A115,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E115,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A115,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A116,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E116,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A116,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A117,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E117,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A117,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A118,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E118,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A118,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A119,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E119,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A119,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A120,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E120,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A120,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A121,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E121,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A121,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A122,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E122,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A122,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A123,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E123,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A123,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A124,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E124,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A124,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A125,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E125,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A125,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A126,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E126,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A126,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A127,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E127,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A127,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A128,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E128,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A128,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A129,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E129,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A129,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A130,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E130,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A130,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A131,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E131,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A131,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A132,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E132,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A132,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A133,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E133,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A133,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A134,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E134,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A134,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A135,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E135,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A135,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A136,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E136,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A136,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A137,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E137,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A137,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A138,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E138,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A138,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A139,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E139,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A139,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A140,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E140,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A140,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A141,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E141,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A141,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A142,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E142,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A142,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A143,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E143,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A143,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A144,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E144,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A144,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A145,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E145,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A145,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A146,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E146,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A146,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A147,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E147,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A147,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A148,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E148,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A148,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A149,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E149,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A149,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A150,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E150,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A150,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A151,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E151,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A151,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A152,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E152,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A152,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A153,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E153,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A153,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A154,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E154,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A154,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A155,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E155,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A155,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A156,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E156,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A156,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A157,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E157,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A157,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A158,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E158,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A158,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A159,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E159,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A159,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A160,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E160,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A160,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A161,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E161,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A161,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A162,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E162,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A162,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A163,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E163,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A163,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A164,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E164,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A164,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D164*G164),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A165,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E165,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A165,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A166,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E166,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A166,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A167,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E167,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A167,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A168,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E168,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A168,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A169,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E169,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A169,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A170,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E170,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A170,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A171,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E171,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A171,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A172,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E172,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A172,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A173,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E173,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A173,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A174,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E174,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A174,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A175,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E175,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A175,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A176,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E176,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A176,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A177,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E177,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A177,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A178,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E178,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A178,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A179,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E179,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A179,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A180,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E180,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A180,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A181,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E181,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A181,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A182,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E182,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A182,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A183,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E183,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A183,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A184,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E184,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A184,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A185,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E185,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A185,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A186,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E186,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A186,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A187,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E187,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A187,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A188,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E188,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A188,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A189,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E189,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A189,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A190,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E190,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A190,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A191,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E191,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A191,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A192,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E192,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A192,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A193,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E193,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A193,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A194,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E194,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A194,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A195,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E195,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A195,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A196,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E196,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A196,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A197,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E197,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A197,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A198,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E198,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A198,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A199,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E199,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A199,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A200,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E200,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A200,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A201,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E201,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A201,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A202,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E202,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A202,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A203,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E203,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A203,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A204,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E204,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A204,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A205,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E205,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A205,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A206,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E206,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A206,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A207,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E207,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A207,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A208,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E208,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A208,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A209,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E209,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A209,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A210,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E210,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A210,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A211,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E211,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A211,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A212,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E212,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A212,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A213,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E213,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A213,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A214,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E214,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A214,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A215,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E215,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A215,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A216,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E216,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A216,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A217,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E217,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A217,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A218,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E218,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A218,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A219,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E219,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A219,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A220,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E220,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A220,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A221,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E221,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A221,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A222,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E222,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A222,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A223,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E223,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A223,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A224,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E224,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A224,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A225,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E225,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A225,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A226,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E226,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A226,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A227,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E227,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A227,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A228,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E228,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A228,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D228*G228),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A229,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E229,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A229,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A230,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E230,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A230,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A231,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E231,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A231,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A232,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E232,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A232,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A233,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E233,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A233,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A234,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E234,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A234,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A235,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E235,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A235,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A236,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E236,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A236,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A237,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E237,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A237,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A238,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E238,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A238,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A239,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E239,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A239,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A240,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E240,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A240,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A241,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E241,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A241,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A242,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E242,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A242,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A243,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E243,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A243,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A244,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E244,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A244,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A245,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E245,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A245,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A246,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E246,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A246,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A247,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E247,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A247,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A248,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E248,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A248,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A249,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E249,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A249,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A250,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E250,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A250,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A251,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E251,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A251,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A252,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E252,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A252,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A253,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E253,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A253,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A254,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E254,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A254,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A255,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E255,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A255,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A256,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E256,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A256,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A257,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E257,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A257,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A258,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E258,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A258,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A259,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E259,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A259,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A260,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E260,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A260,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A261,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E261,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A261,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A262,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E262,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A262,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A263,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E263,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A263,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A264,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E264,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A264,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A265,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E265,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A265,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A266,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E266,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A266,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A267,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E267,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A267,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A268,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E268,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A268,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A269,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E269,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A269,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A270,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E270,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A270,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A271,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E271,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A271,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A272,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E272,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A272,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A273,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E273,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A273,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A274,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E274,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A274,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A275,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E275,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A275,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A276,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E276,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A276,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A277,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E277,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A277,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A278,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E278,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A278,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A279,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E279,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A279,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A280,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E280,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A280,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A281,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E281,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A281,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A282,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E282,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A282,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A283,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E283,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A283,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A284,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E284,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A284,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A285,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E285,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A285,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A286,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E286,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A286,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A287,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E287,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A287,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A288,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E288,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A288,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A289,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E289,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A289,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A290,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E290,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A290,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A291,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E291,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A291,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A292,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E292,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A292,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D292*G292),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A293,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E293,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A293,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A294,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E294,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A294,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A295,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E295,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A295,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A296,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E296,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A296,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A297,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E297,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A297,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A298,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E298,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A298,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A299,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E299,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A299,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A300,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E300,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A300,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A301,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E301,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A301,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A302,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E302,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A302,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A303,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E303,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A303,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A304,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E304,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A304,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A305,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E305,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A305,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A306,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E306,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A306,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A307,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E307,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A307,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A308,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E308,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A308,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A309,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E309,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A309,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A310,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E310,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A310,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A311,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E311,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A311,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A312,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E312,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A312,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A313,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E313,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A313,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A314,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E314,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A314,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A315,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E315,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A315,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A316,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E316,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A316,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A317,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E317,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A317,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A318,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E318,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A318,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A319,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E319,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A319,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A320,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E320,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A320,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A321,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E321,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A321,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A322,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E322,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A322,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A323,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E323,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A323,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A324,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E324,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A324,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A325,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E325,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A325,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A326,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E326,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A326,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A327,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E327,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A327,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A328,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E328,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A328,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A329,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E329,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A329,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A330,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E330,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A330,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A331,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E331,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A331,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A332,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E332,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A332,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A333,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E333,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A333,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A334,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E334,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A334,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A335,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E335,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A335,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A336,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E336,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A336,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A337,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E337,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A337,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A338,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E338,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A338,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A339,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E339,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A339,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A340,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E340,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A340,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A341,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E341,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A341,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A342,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E342,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A342,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A343,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E343,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A343,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A344,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E344,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A344,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A345,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E345,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A345,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A346,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E346,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A346,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A347,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E347,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A347,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A348,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E348,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A348,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A349,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E349,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A349,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A350,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E350,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A350,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A351,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E351,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A351,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A352,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E352,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A352,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A353,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E353,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A353,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A354,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E354,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A354,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A355,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E355,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A355,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A356,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E356,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A356,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D356*G356),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A357,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E357,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A357,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A358,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E358,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A358,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A359,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E359,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A359,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A360,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E360,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A360,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A361,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E361,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A361,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A362,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E362,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A362,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A363,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E363,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A363,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A364,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E364,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A364,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A365,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E365,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A365,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A366,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E366,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A366,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A367,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E367,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A367,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A368,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E368,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A368,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A369,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E369,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A369,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A370,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E370,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A370,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A371,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E371,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A371,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A372,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E372,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A372,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A373,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E373,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A373,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A374,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E374,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A374,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A375,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E375,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A375,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A376,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E376,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A376,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A377,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E377,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A377,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A378,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E378,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A378,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A379,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E379,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A379,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A380,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E380,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A380,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A381,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E381,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A381,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A382,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E382,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A382,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A383,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E383,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A383,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A384,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E384,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A384,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A385,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E385,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A385,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A386,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E386,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A386,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A387,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E387,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A387,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A388,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E388,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A388,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A389,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E389,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A389,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A390,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E390,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A390,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A391,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E391,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A391,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A392,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E392,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A392,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A393,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E393,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A393,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A394,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E394,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A394,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A395,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E395,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A395,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A396,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E396,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A396,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A397,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E397,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A397,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A398,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E398,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A398,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A399,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E399,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A399,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A400,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E400,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A400,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A401,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E401,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A401,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A402,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E402,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A402,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A403,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E403,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A403,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A404,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E404,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A404,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A405,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E405,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A405,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A406,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E406,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A406,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A407,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E407,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A407,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A408,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E408,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A408,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A409,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E409,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A409,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A410,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E410,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A410,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A411,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E411,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A411,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A412,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E412,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A412,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A413,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E413,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A413,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A414,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E414,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A414,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A415,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E415,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A415,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A416,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E416,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A416,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A417,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E417,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A417,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A418,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E418,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A418,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A419,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E419,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A419,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A420,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E420,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A420,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D420*G420),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A421,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E421,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A421,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A422,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E422,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A422,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A423,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E423,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A423,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A424,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E424,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A424,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A425,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E425,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A425,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A426,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E426,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A426,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A427,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E427,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A427,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A428,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E428,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A428,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A429,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E429,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A429,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A430,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E430,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A430,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A431,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E431,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A431,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A432,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E432,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A432,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A433,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E433,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A433,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A434,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E434,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A434,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A435,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E435,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A435,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A436,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E436,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A436,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A437,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E437,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A437,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A438,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E438,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A438,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A439,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E439,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A439,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A440,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E440,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A440,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A441,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E441,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A441,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A442,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E442,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A442,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A443,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E443,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A443,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A444,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E444,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A444,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A445,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E445,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A445,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A446,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E446,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A446,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A447,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E447,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A447,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A448,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E448,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A448,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A449,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E449,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A449,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A450,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E450,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A450,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A451,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E451,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A451,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A452,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E452,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A452,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A453,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E453,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A453,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A454,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E454,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A454,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A455,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E455,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A455,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A456,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E456,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A456,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A457,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E457,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A457,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A458,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E458,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A458,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A459,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E459,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A459,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A460,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E460,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A460,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A461,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E461,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A461,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A462,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E462,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A462,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A463,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E463,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A463,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A464,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E464,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A464,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A465,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E465,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A465,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A466,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E466,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A466,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A467,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E467,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A467,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A468,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E468,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A468,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A469,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E469,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A469,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A470,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E470,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A470,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A471,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E471,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A471,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A472,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E472,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A472,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A473,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E473,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A473,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A474,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E474,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A474,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A475,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E475,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A475,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A476,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E476,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A476,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A477,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E477,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A477,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A478,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E478,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A478,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A479,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E479,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A479,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A480,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E480,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A480,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A481,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E481,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A481,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A482,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E482,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A482,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A483,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E483,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A483,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A484,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E484,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A484,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D484*G484),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A485,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E485,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A485,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A486,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E486,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A486,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A487,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E487,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A487,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A488,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E488,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A488,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A489,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E489,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A489,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A490,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E490,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A490,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A491,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E491,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A491,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A492,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E492,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A492,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A493,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E493,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A493,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A494,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E494,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A494,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A495,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E495,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A495,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A496,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E496,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A496,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A497,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E497,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A497,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A498,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E498,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A498,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A499,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E499,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A499,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A500,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E500,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A500,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A501,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E501,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A501,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A502,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E502,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A502,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A503,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E503,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A503,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A504,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E504,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A504,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A505,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E505,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A505,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A506,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E506,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A506,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A507,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E507,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A507,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A508,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E508,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A508,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A509,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E509,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A509,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A510,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E510,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A510,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A511,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E511,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A511,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A512,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E512,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A512,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A513,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E513,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A513,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A514,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E514,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A514,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A515,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E515,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A515,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A516,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E516,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A516,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A517,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E517,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A517,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A518,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E518,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A518,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A519,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E519,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A519,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A520,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E520,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A520,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A521,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E521,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A521,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A522,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E522,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A522,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A523,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E523,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A523,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A524,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E524,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A524,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A525,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E525,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A525,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A526,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E526,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A526,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A527,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E527,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A527,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A528,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E528,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A528,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A529,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E529,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A529,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A530,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E530,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A530,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A531,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E531,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A531,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A532,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E532,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A532,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A533,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E533,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A533,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A534,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E534,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A534,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A535,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E535,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A535,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A536,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E536,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A536,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A537,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E537,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A537,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A538,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E538,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A538,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A539,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E539,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A539,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A540,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E540,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A540,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A541,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E541,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A541,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A542,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E542,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A542,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A543,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E543,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A543,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A544,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E544,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A544,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A545,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E545,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A545,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A546,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E546,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A546,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A547,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E547,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A547,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A548,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E548,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A548,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D548*G548),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A549,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E549,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A549,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A550,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E550,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A550,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A551,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E551,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A551,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A552,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E552,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A552,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A553,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E553,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A553,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A554,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E554,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A554,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A555,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E555,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A555,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A556,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E556,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A556,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A557,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E557,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A557,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A558,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E558,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A558,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A559,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E559,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A559,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A560,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E560,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A560,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A561,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E561,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A561,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A562,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E562,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A562,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A563,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E563,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A563,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A564,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E564,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A564,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A565,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E565,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A565,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A566,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E566,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A566,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A567,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E567,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A567,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A568,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E568,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A568,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A569,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E569,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A569,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A570,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E570,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A570,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A571,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E571,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A571,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A572,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E572,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A572,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A573,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E573,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A573,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A574,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E574,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A574,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A575,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E575,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A575,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A576,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E576,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A576,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A577,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E577,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A577,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A578,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E578,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A578,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A579,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E579,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A579,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A580,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E580,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A580,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A581,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E581,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A581,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A582,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E582,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A582,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A583,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E583,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A583,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A584,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E584,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A584,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A585,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E585,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A585,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A586,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E586,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A586,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A587,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E587,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A587,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A588,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E588,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A588,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A589,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E589,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A589,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A590,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E590,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A590,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A591,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E591,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A591,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A592,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E592,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A592,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A593,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E593,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A593,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A594,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E594,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A594,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A595,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E595,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A595,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A596,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E596,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A596,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A597,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E597,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A597,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A598,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E598,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A598,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A599,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E599,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A599,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A600,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E600,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A600,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A601,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E601,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A601,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A602,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E602,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A602,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A603,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E603,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A603,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A604,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E604,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A604,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A605,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E605,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A605,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A606,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E606,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A606,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A607,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E607,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A607,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A608,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E608,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A608,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A609,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E609,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A609,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A610,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E610,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A610,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A611,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E611,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A611,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A612,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E612,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A612,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D612*G612),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A613,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E613,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A613,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A614,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E614,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A614,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A615,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E615,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A615,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A616,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E616,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A616,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A617,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E617,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A617,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A618,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E618,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A618,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A619,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E619,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A619,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A620,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E620,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A620,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A621,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E621,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A621,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A622,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E622,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A622,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A623,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E623,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A623,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A624,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E624,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A624,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A625,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E625,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A625,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A626,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E626,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A626,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A627,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E627,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A627,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A628,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E628,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A628,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A629,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E629,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A629,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A630,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E630,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A630,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A631,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E631,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A631,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A632,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E632,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A632,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A633,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E633,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A633,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A634,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E634,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A634,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A635,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E635,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A635,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A636,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E636,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A636,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A637,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E637,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A637,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A638,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E638,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A638,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A639,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E639,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A639,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A640,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E640,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A640,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A641,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E641,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A641,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A642,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E642,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A642,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A643,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E643,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A643,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A644,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E644,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A644,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A645,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E645,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A645,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A646,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E646,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A646,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A647,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E647,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A647,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A648,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E648,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A648,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A649,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E649,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A649,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A650,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E650,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A650,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A651,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E651,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A651,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A652,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E652,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A652,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A653,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E653,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A653,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A654,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E654,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A654,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A655,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E655,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A655,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A656,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E656,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A656,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A657,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E657,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A657,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A658,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E658,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A658,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A659,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E659,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A659,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A660,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E660,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A660,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A661,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E661,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A661,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A662,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E662,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A662,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A663,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E663,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A663,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A664,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E664,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A664,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A665,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E665,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A665,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A666,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E666,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A666,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A667,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E667,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A667,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A668,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E668,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A668,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A669,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E669,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A669,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A670,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E670,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A670,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A671,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E671,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A671,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A672,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E672,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A672,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A673,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E673,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A673,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A674,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E674,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A674,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A675,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E675,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A675,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A676,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E676,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A676,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D676*G676),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A677,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E677,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A677,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A678,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E678,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A678,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A679,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E679,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A679,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A680,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E680,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A680,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A681,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E681,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A681,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A682,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E682,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A682,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A683,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E683,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A683,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A684,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E684,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A684,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A685,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E685,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A685,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A686,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E686,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A686,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A687,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E687,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A687,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A688,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E688,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A688,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A689,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E689,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A689,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A690,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E690,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A690,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A691,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E691,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A691,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A692,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E692,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A692,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A693,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E693,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A693,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A694,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E694,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A694,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A695,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E695,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A695,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A696,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E696,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A696,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A697,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E697,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A697,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A698,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E698,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A698,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A699,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E699,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A699,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A700,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E700,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A700,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A701,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E701,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A701,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A702,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E702,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A702,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A703,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E703,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A703,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A704,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E704,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A704,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A705,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E705,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A705,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A706,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E706,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A706,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A707,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E707,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A707,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A708,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E708,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A708,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A709,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E709,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A709,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A710,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E710,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A710,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A711,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E711,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A711,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A712,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E712,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A712,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A713,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E713,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A713,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A714,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E714,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A714,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A715,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E715,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A715,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A716,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E716,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A716,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A717,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E717,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A717,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A718,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E718,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A718,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A719,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E719,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A719,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A720,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E720,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A720,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A721,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E721,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A721,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A722,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E722,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A722,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A723,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E723,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A723,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A724,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E724,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A724,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A725,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E725,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A725,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A726,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E726,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A726,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A727,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E727,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A727,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A728,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E728,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A728,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A729,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E729,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A729,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A730,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E730,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A730,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A731,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E731,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A731,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A732,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E732,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A732,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A733,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E733,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A733,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A734,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E734,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A734,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A735,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E735,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A735,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A736,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E736,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A736,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A737,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E737,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A737,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A738,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E738,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A738,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A739,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E739,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A739,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A740,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E740,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A740,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D740*G740),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A741,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E741,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A741,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A742,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E742,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A742,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A743,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E743,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A743,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A744,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E744,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A744,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A745,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E745,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A745,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A746,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E746,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A746,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A747,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E747,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A747,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A748,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E748,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A748,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A749,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E749,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A749,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A750,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E750,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A750,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A751,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E751,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A751,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A752,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E752,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A752,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A753,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E753,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A753,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A754,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E754,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A754,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A755,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E755,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A755,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A756,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E756,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A756,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A757,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E757,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A757,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A758,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E758,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A758,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A759,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E759,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A759,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A760,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E760,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A760,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A761,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E761,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A761,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A762,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E762,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A762,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A763,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E763,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A763,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A764,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E764,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A764,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A765,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E765,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A765,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A766,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E766,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A766,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A767,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E767,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A767,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A768,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E768,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A768,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A769,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E769,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A769,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A770,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E770,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A770,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A771,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E771,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A771,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A772,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E772,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A772,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A773,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E773,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A773,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A774,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E774,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A774,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A775,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E775,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A775,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A776,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E776,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A776,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A777,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E777,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A777,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A778,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E778,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A778,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A779,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E779,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A779,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A780,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E780,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A780,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A781,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E781,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A781,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A782,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E782,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A782,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A783,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E783,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A783,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A784,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E784,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A784,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A785,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E785,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A785,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A786,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E786,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A786,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A787,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E787,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A787,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A788,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E788,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A788,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A789,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E789,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A789,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A790,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E790,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A790,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A791,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E791,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A791,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A792,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E792,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A792,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A793,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E793,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A793,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A794,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E794,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A794,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A795,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E795,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A795,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A796,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E796,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A796,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A797,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E797,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A797,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A798,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E798,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A798,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A799,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E799,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A799,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A800,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E800,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A800,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A801,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E801,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A801,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A802,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E802,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A802,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A803,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E803,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A803,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A804,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E804,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A804,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D804*G804),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A805,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E805,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A805,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A806,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E806,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A806,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A807,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E807,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A807,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A808,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E808,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A808,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A809,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E809,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A809,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A810,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E810,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A810,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A811,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E811,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A811,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A812,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E812,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A812,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A813,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E813,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A813,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A814,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E814,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A814,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A815,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E815,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A815,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A816,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E816,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A816,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A817,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E817,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A817,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A818,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E818,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A818,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A819,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E819,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A819,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A820,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E820,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A820,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A821,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E821,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A821,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A822,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E822,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A822,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A823,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E823,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A823,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A824,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E824,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A824,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A825,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E825,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A825,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A826,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E826,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A826,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A827,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E827,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A827,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A828,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E828,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A828,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A829,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E829,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A829,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A830,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E830,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A830,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A831,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E831,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A831,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A832,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E832,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A832,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A833,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E833,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A833,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A834,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E834,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A834,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A835,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E835,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A835,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A836,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E836,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A836,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A837,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E837,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A837,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A838,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E838,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A838,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A839,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E839,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A839,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A840,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E840,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A840,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A841,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E841,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A841,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A842,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E842,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A842,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A843,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E843,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A843,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A844,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E844,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A844,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A845,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E845,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A845,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A846,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E846,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A846,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A847,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E847,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A847,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A848,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E848,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A848,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A849,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E849,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A849,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A850,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E850,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A850,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A851,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E851,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A851,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A852,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E852,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A852,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A853,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E853,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A853,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A854,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E854,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A854,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A855,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E855,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A855,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A856,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E856,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A856,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A857,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E857,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A857,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A858,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E858,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A858,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A859,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E859,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A859,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A860,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E860,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A860,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A861,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E861,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A861,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A862,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E862,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A862,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A863,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E863,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A863,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A864,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E864,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A864,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A865,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E865,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A865,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A866,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E866,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A866,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A867,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E867,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A867,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A868,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E868,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A868,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D868*G868),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A869,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E869,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A869,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A870,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E870,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A870,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A871,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E871,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A871,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A872,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E872,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A872,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A873,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E873,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A873,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A874,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E874,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A874,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A875,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E875,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A875,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A876,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E876,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A876,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A877,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E877,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A877,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A878,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E878,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A878,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A879,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E879,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A879,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A880,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E880,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A880,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A881,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E881,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A881,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A882,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E882,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A882,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A883,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E883,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A883,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A884,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E884,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A884,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A885,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E885,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A885,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A886,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E886,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A886,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A887,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E887,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A887,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A888,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E888,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A888,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A889,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E889,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A889,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A890,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E890,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A890,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A891,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E891,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A891,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A892,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E892,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A892,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A893,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E893,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A893,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A894,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E894,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A894,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A895,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E895,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A895,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A896,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E896,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A896,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A897,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E897,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A897,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A898,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E898,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A898,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A899,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E899,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A899,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A900,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E900,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A900,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A901,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E901,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A901,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A902,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E902,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A902,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A903,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E903,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A903,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A904,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E904,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A904,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A905,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E905,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A905,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A906,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E906,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A906,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A907,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E907,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A907,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A908,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E908,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A908,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A909,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E909,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A909,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A910,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E910,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A910,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A911,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E911,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A911,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A912,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E912,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A912,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A913,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E913,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A913,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A914,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E914,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A914,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A915,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E915,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A915,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A916,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E916,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A916,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A917,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E917,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A917,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A918,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E918,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A918,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A919,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E919,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A919,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A920,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E920,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A920,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A921,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E921,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A921,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A922,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E922,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A922,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A923,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E923,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A923,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A924,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E924,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A924,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A925,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E925,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A925,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A926,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E926,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A926,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A927,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E927,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A927,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A928,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E928,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A928,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A929,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E929,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A929,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A930,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E930,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A930,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A931,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E931,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A931,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A932,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E932,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A932,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D932*G932),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A933,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E933,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A933,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A934,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E934,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A934,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A935,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E935,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A935,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A936,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E936,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A936,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A937,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E937,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A937,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A938,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E938,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A938,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A939,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E939,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A939,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A940,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E940,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A940,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A941,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E941,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A941,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A942,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E942,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A942,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A943,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E943,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A943,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A944,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E944,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A944,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A945,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E945,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A945,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A946,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E946,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A946,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A947,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E947,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A947,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A948,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E948,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A948,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A949,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E949,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A949,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A950,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E950,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A950,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A951,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E951,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A951,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A952,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E952,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A952,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A953,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E953,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A953,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A954,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E954,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A954,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A955,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E955,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A955,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A956,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E956,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A956,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A957,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E957,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A957,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A958,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E958,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A958,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A959,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E959,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A959,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A960,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E960,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A960,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A961,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E961,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A961,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A962,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E962,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A962,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A963,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E963,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A963,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A964,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E964,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A964,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A965,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E965,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A965,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A966,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E966,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A966,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A967,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E967,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A967,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A968,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E968,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A968,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A969,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E969,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A969,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A970,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E970,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A970,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A971,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E971,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A971,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A972,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E972,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A972,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A973,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E973,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A973,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A974,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E974,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A974,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A975,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E975,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A975,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A976,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E976,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A976,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A977,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E977,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A977,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A978,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E978,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A978,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A979,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E979,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A979,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A980,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E980,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A980,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A981,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E981,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A981,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A982,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E982,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A982,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A983,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E983,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A983,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A984,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E984,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A984,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A985,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E985,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A985,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A986,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E986,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A986,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A987,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E987,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A987,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A988,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E988,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A988,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A989,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E989,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A989,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A990,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E990,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A990,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A991,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E991,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A991,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A992,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E992,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A992,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A993,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E993,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A993,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A994,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E994,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A994,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A995,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E995,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A995,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A996,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E996,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A996,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D996*G996),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A997,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E997,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A997,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A998,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E998,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A998,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A999,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E999,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A999,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1000,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1000,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1000,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1001,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1001,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1001,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1002,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1002,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1002,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1003,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1003,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1003,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1004,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1004,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1004,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1005,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1005,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1005,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1006,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1006,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1006,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1007,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1007,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1007,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1008,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1008,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1008,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1009,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1009,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1009,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1010,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1010,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1010,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1011,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1011,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1011,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1012,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1012,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1012,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1013,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1013,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1013,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1014,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1014,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1014,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1015,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1015,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1015,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1016,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1016,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1016,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1017,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1017,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1017,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1018,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1018,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1018,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1019,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1019,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1019,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1020,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1020,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1020,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1021,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1021,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1021,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1022,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1022,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1022,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1023,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1023,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1023,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1024,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1024,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1024,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1025,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1025,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1025,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1026,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1026,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1026,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1027,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1027,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1027,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1028,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1028,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1028,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1029,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1029,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1029,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1030,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1030,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1030,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1031,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1031,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1031,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1032,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1032,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1032,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1033,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1033,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1033,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1034,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1034,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1034,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1035,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1035,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1035,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1036,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1036,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1036,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1037,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1037,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1037,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1038,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1038,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1038,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1039,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1039,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1039,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1040,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1040,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1040,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1041,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1041,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1041,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1042,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1042,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1042,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1043,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1043,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1043,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1044,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1044,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1044,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1045,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1045,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1045,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1046,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1046,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1046,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1047,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1047,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1047,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1048,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1048,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1048,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1049,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1049,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1049,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1050,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1050,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1050,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1051,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1051,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1051,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1052,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1052,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1052,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1053,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1053,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1053,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1054,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1054,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1054,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1055,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1055,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1055,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1056,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1056,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1056,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1057,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1057,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1057,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1058,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1058,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1058,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1059,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1059,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1059,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1060,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1060,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1060,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D1060*G1060),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1061,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1061,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1061,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1062,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1062,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1062,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1063,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1063,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1063,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1064,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1064,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1064,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1065,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1065,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1065,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1066,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1066,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1066,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1067,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1067,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1067,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1068,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1068,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1068,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1069,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1069,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1069,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1070,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1070,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1070,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1071,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1071,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1071,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1072,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1072,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1072,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1073,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1073,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1073,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1074,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1074,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1074,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1075,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1075,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1075,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1076,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1076,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1076,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1077,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1077,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1077,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1078,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1078,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1078,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1079,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1079,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1079,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1080,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1080,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1080,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1081,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1081,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1081,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1082,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1082,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1082,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1083,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1083,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1083,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1084,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1084,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1084,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1085,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1085,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1085,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1086,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1086,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1086,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1087,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1087,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1087,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1088,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1088,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1088,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1089,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1089,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1089,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1090,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1090,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1090,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1091,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1091,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1091,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1092,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1092,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1092,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1093,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1093,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1093,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1094,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1094,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1094,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1095,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1095,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1095,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1096,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1096,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1096,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1097,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1097,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1097,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1098,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1098,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1098,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1099,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1099,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1099,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1100,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1100,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1100,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1101,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1101,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1101,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1102,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1102,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1102,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1103,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1103,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1103,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1104,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1104,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1104,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1105,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1105,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1105,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1106,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1106,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1106,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1107,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1107,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1107,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1108,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1108,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1108,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1109,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1109,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1109,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1110,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1110,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1110,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1111,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1111,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1111,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1112,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1112,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1112,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1113,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1113,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1113,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1114,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1114,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1114,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1115,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1115,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1115,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1116,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1116,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1116,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1117,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1117,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1117,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1118,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1118,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1118,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1119,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1119,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1119,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1120,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1120,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1120,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1121,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1121,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1121,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1122,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1122,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1122,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1123,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1123,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1123,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1124,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1124,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1124,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D1124*G1124),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1125,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1125,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1125,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1126,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1126,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1126,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1127,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1127,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1127,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1128,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1128,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1128,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1129,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1129,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1129,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1130,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1130,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1130,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1131,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1131,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1131,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1132,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1132,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1132,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1133,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1133,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1133,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1134,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1134,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1134,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1135,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1135,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1135,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1136,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1136,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1136,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1137,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1137,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1137,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1138,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1138,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1138,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1139,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1139,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1139,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1140,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1140,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1140,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1141,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1141,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1141,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1142,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1142,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1142,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1143,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1143,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1143,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1144,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1144,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1144,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1145,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1145,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1145,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1146,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1146,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1146,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1147,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1147,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1147,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1148,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1148,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1148,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1149,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1149,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1149,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1150,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1150,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1150,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1151,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1151,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1151,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1152,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1152,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1152,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1153,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1153,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1153,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1154,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1154,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1154,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1155,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1155,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1155,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1156,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1156,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1156,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1157,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1157,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1157,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1158,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1158,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1158,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1159,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1159,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1159,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1160,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1160,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1160,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1161,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1161,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1161,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1162,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1162,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1162,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1163,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1163,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1163,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1164,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1164,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1164,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1165,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1165,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1165,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1166,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1166,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1166,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1167,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1167,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1167,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1168,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1168,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1168,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1169,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1169,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1169,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1170,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1170,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1170,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1171,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1171,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1171,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1172,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1172,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1172,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1173,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1173,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1173,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1174,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1174,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1174,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1175,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1175,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1175,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1176,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1176,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1176,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1177,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1177,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1177,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1178,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1178,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1178,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1179,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1179,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1179,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1180,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1180,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1180,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1181,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1181,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1181,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1182,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1182,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1182,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1183,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1183,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1183,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1184,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1184,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1184,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1185,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1185,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1185,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1186,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1186,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1186,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1187,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1187,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1187,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1188,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1188,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1188,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D1188*G1188),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1189,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1189,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1189,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1190,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1190,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1190,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1191,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1191,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1191,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1192,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1192,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1192,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1193,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1193,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1193,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1194,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1194,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1194,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1195,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1195,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1195,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1196,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1196,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1196,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1197,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1197,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1197,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1198,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1198,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1198,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1199,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1199,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1199,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1200,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1200,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1200,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1201,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1201,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1201,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1202,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1202,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1202,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1203,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1203,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1203,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1204,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1204,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1204,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1205,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1205,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1205,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1206,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1206,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1206,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1207,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1207,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1207,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1208,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1208,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1208,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1209,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1209,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1209,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1210,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1210,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1210,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1211,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1211,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1211,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1212,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1212,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1212,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1213,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1213,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1213,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1214,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1214,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1214,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1215,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1215,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1215,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1216,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1216,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1216,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1217,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1217,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1217,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1218,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1218,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1218,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1219,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1219,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1219,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1220,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1220,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1220,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1221,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1221,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1221,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1222,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1222,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1222,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1223,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1223,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1223,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1224,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1224,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1224,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1225,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1225,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1225,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1226,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1226,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1226,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1227,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1227,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1227,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1228,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1228,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1228,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1229,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1229,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1229,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1230,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1230,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1230,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1231,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1231,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1231,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1232,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1232,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1232,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1233,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1233,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1233,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1234,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1234,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1234,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1235,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1235,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1235,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1236,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1236,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1236,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1237,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1237,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1237,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1238,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1238,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1238,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1239,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1239,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1239,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1240,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1240,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1240,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1241,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1241,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1241,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1242,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1242,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1242,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1243,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1243,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1243,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1244,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1244,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1244,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1245,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1245,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1245,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1246,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1246,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1246,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1247,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1247,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1247,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1248,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1248,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1248,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1249,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1249,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1249,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1250,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1250,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1250,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1251,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1251,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1251,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1252,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1252,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1252,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D1252*G1252),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1253,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1253,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1253,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1254,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1254,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1254,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1255,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1255,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1255,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1256,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1256,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1256,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1257,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1257,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1257,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1258,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1258,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1258,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1259,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1259,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1259,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1260,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1260,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1260,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1261,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1261,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1261,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1262,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1262,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1262,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1263,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1263,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1263,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1264,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1264,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1264,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1265,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1265,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1265,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1266,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1266,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1266,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1267,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1267,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1267,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1268,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1268,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1268,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1269,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1269,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1269,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1270,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1270,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1270,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1271,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1271,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1271,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1272,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1272,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1272,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1273,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1273,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1273,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1274,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1274,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1274,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1275,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1275,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1275,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1276,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1276,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1276,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1277,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1277,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1277,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1278,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1278,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1278,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1279,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1279,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1279,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1280,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1280,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1280,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1281,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1281,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1281,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1282,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1282,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1282,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1283,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1283,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1283,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1284,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1284,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1284,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1285,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1285,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1285,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1286,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1286,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1286,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1287,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1287,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1287,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1288,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1288,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1288,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1289,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1289,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1289,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1290,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1290,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1290,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1291,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1291,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1291,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1292,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1292,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1292,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1293,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1293,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1293,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1294,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1294,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1294,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1295,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1295,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1295,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1296,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1296,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1296,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1297,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1297,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1297,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1298,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1298,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1298,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1299,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1299,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1299,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1300,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1300,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1300,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1301,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1301,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1301,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1302,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1302,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1302,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1303,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1303,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1303,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1304,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1304,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1304,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1305,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1305,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1305,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1306,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1306,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1306,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1307,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1307,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1307,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1308,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1308,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1308,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1309,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1309,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1309,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1310,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1310,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1310,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1311,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1311,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1311,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1312,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1312,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1312,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1313,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1313,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1313,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1314,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1314,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1314,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1315,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1315,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1315,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1316,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1316,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1316,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D1316*G1316),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1317,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1317,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1317,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1318,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1318,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1318,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1319,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1319,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1319,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1320,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1320,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1320,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1321,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1321,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1321,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1322,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1322,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1322,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1323,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1323,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1323,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1324,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1324,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1324,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1325,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1325,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1325,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1326,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1326,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1326,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1327,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1327,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1327,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1328,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1328,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1328,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1329,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1329,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1329,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1330,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1330,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1330,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1331,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1331,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1331,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1332,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1332,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1332,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1333,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1333,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1333,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1334,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1334,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1334,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1335,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1335,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1335,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1336,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1336,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1336,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1337,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1337,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1337,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1338,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1338,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1338,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1339,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1339,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1339,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1340,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1340,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1340,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1341,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1341,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1341,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1342,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1342,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1342,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1343,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1343,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1343,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1344,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1344,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1344,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1345,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1345,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1345,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1346,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1346,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1346,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1347,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1347,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1347,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1348,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1348,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1348,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1349,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1349,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1349,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1350,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1350,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1350,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1351,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1351,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1351,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1352,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1352,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1352,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1353,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1353,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1353,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1354,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1354,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1354,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1355,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1355,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1355,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1356,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1356,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1356,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1357,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1357,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1357,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1358,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1358,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1358,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1359,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1359,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1359,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1360,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1360,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1360,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1361,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1361,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1361,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1362,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1362,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1362,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1363,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1363,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1363,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1364,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1364,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1364,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1365,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1365,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1365,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1366,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1366,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1366,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1367,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1367,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1367,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1368,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1368,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1368,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1369,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1369,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1369,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1370,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1370,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1370,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1371,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1371,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1371,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1372,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1372,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1372,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1373,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1373,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1373,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1374,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1374,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1374,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1375,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1375,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1375,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1376,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1376,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1376,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1377,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1377,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1377,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1378,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1378,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1378,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1379,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1379,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1379,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1380,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1380,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1380,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D1380*G1380),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1381,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1381,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1381,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1382,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1382,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1382,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1383,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1383,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1383,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1384,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1384,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1384,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1385,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1385,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1385,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1386,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1386,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1386,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1387,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1387,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1387,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1388,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1388,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1388,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1389,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1389,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1389,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1390,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1390,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1390,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1391,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1391,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1391,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1392,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1392,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1392,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1393,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1393,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1393,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1394,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1394,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1394,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1395,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1395,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1395,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1396,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1396,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1396,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1397,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1397,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1397,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1398,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1398,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1398,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1399,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1399,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1399,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1400,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1400,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1400,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1401,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1401,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1401,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1402,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1402,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1402,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1403,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1403,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1403,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1404,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1404,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1404,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1405,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1405,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1405,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1406,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1406,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1406,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1407,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1407,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1407,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1408,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1408,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1408,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1409,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1409,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1409,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1410,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1410,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1410,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1411,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1411,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1411,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1412,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1412,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1412,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1413,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1413,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1413,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1414,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1414,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1414,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1415,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1415,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1415,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1416,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1416,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1416,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1417,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1417,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1417,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1418,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1418,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1418,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1419,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1419,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1419,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1420,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1420,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1420,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1421,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1421,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1421,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1422,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1422,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1422,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1423,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1423,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1423,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1424,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1424,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1424,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1425,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1425,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1425,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1426,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1426,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1426,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1427,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1427,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1427,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1428,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1428,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1428,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1429,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1429,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1429,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1430,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1430,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1430,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1431,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1431,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1431,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1432,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1432,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1432,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1433,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1433,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1433,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1434,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1434,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1434,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1435,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1435,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1435,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1436,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1436,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1436,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1437,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1437,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1437,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1438,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1438,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1438,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1439,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1439,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1439,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1440,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1440,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1440,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1441,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1441,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1441,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1442,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1442,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1442,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1443,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1443,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1443,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1444,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1444,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1444,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D1444*G1444),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1445,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1445,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1445,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1446,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1446,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1446,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1447,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1447,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1447,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1448,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1448,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1448,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1449,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1449,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1449,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1450,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1450,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1450,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1451,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1451,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1451,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1452,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1452,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1452,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1453,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1453,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1453,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1454,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1454,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1454,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1455,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1455,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1455,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1456,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1456,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1456,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1457,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1457,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1457,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1458,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1458,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1458,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1459,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1459,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1459,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1460,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1460,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1460,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1461,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1461,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1461,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1462,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1462,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1462,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1463,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1463,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1463,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1464,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1464,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1464,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1465,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1465,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1465,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1466,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1466,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1466,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1467,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1467,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1467,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1468,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1468,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1468,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1469,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1469,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1469,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1470,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1470,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1470,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1471,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1471,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1471,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1472,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1472,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1472,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1473,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1473,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1473,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1474,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1474,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1474,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1475,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1475,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1475,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1476,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1476,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1476,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1477,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1477,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1477,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1478,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1478,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1478,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1479,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1479,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1479,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1480,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1480,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1480,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1481,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1481,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1481,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1482,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1482,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1482,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1483,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1483,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1483,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1484,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1484,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1484,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1485,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1485,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1485,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1486,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1486,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1486,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1487,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1487,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1487,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1488,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1488,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1488,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1489,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1489,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1489,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1490,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1490,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1490,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1491,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1491,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1491,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1492,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1492,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1492,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1493,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1493,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1493,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1494,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1494,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1494,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1495,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1495,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1495,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1496,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1496,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1496,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1497,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1497,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1497,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1498,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1498,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1498,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1499,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1499,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1499,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1500,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1500,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1500,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1501,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1501,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1501,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1502,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1502,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1502,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1503,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1503,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1503,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1504,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1504,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1504,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1505,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1505,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1505,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1506,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1506,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1506,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1507,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1507,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1507,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1508,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1508,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1508,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D1508*G1508),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1509,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1509,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1509,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1510,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1510,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1510,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1511,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1511,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1511,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1512,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1512,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1512,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1513,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1513,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1513,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1514,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1514,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1514,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1515,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1515,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1515,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1516,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1516,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1516,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1517,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1517,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1517,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1518,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1518,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1518,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1519,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1519,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1519,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1520,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1520,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1520,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1521,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1521,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1521,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1522,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1522,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1522,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1523,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1523,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1523,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1524,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1524,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1524,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1525,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1525,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1525,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1526,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1526,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1526,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1527,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1527,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1527,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1528,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1528,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1528,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1529,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1529,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1529,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1530,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1530,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1530,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1531,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1531,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1531,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1532,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1532,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1532,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1533,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1533,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1533,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1534,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1534,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1534,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1535,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1535,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1535,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1536,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1536,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1536,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1537,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1537,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1537,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1538,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1538,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1538,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1539,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1539,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1539,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1540,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1540,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1540,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1541,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1541,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1541,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1542,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1542,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1542,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1543,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1543,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1543,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1544,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1544,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1544,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1545,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1545,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1545,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1546,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1546,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1546,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1547,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1547,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1547,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1548,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1548,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1548,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1549,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1549,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1549,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1550,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1550,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1550,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1551,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1551,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1551,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1552,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1552,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1552,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1553,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1553,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1553,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1554,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1554,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1554,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1555,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1555,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1555,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1556,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1556,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1556,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1557,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1557,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1557,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1558,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1558,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1558,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1559,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1559,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1559,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1560,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1560,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1560,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1561,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1561,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1561,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1562,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1562,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1562,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1563,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1563,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1563,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1564,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1564,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1564,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1565,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1565,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1565,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1566,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1566,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1566,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1567,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1567,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1567,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1568,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1568,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1568,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1569,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1569,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1569,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1570,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1570,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1570,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1571,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1571,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1571,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1572,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1572,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1572,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D1572*G1572),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1573,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1573,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1573,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1574,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1574,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1574,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1575,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1575,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1575,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1576,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1576,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1576,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1577,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1577,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1577,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1578,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1578,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1578,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1579,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1579,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1579,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1580,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1580,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1580,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1581,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1581,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1581,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1582,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1582,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1582,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1583,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1583,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1583,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1584,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1584,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1584,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1585,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1585,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1585,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1586,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1586,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1586,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1587,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1587,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1587,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1588,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1588,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1588,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1589,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1589,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1589,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1590,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1590,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1590,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1591,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1591,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1591,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1592,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1592,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1592,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1593,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1593,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1593,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1594,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1594,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1594,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1595,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1595,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1595,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1596,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1596,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1596,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1597,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1597,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1597,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1598,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1598,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1598,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1599,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1599,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1599,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1600,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1600,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1600,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1601,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1601,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1601,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1602,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1602,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1602,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1603,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1603,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1603,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1604,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1604,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1604,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1605,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1605,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1605,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1606,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1606,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1606,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1607,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1607,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1607,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1608,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1608,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1608,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1609,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1609,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1609,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1610,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1610,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1610,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1611,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1611,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1611,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1612,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1612,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1612,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1613,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1613,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1613,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1614,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1614,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1614,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1615,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1615,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1615,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1616,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1616,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1616,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1617,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1617,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1617,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1618,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1618,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1618,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1619,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1619,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1619,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1620,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1620,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1620,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1621,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1621,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1621,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1622,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1622,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1622,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1623,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1623,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1623,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1624,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1624,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1624,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1625,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1625,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1625,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1626,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1626,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1626,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1627,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1627,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1627,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1628,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1628,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1628,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1629,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1629,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1629,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1630,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1630,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1630,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1631,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1631,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1631,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1632,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1632,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1632,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1633,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1633,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1633,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1634,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1634,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1634,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1635,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1635,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1635,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1636,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1636,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1636,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D1636*G1636),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1637,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1637,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1637,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1638,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1638,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1638,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1639,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1639,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1639,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1640,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1640,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1640,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1641,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1641,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1641,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1642,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1642,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1642,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1643,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1643,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1643,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1644,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1644,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1644,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1645,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1645,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1645,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1646,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1646,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1646,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1647,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1647,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1647,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1648,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1648,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1648,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1649,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1649,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1649,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1650,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1650,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1650,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1651,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1651,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1651,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1652,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1652,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1652,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1653,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1653,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1653,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1654,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1654,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1654,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1655,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1655,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1655,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1656,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1656,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1656,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1657,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1657,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1657,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1658,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1658,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1658,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1659,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1659,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1659,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1660,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1660,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1660,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1661,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1661,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1661,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1662,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1662,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1662,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1663,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1663,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1663,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1664,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1664,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1664,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1665,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1665,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1665,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1666,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1666,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1666,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1667,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1667,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1667,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1668,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1668,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1668,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1669,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1669,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1669,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1670,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1670,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1670,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1671,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1671,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1671,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1672,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1672,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1672,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1673,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1673,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1673,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1674,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1674,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1674,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1675,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1675,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1675,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1676,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1676,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1676,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1677,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1677,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1677,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1678,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1678,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1678,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1679,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1679,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1679,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1680,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1680,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1680,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1681,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1681,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1681,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1682,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1682,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1682,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1683,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1683,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1683,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1684,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1684,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1684,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1685,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1685,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1685,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1686,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1686,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1686,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1687,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1687,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1687,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1688,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1688,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1688,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1689,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1689,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1689,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1690,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1690,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1690,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1691,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1691,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1691,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1692,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1692,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1692,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1693,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1693,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1693,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1694,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1694,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1694,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1695,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1695,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1695,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1696,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1696,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1696,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1697,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1697,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1697,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1698,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1698,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1698,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1699,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1699,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1699,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1700,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1700,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1700,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D1700*G1700),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1701,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1701,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1701,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1702,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1702,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1702,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1703,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1703,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1703,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1704,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1704,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1704,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1705,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1705,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1705,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1706,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1706,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1706,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1707,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1707,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1707,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1708,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1708,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1708,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1709,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1709,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1709,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1710,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1710,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1710,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1711,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1711,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1711,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1712,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1712,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1712,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1713,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1713,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1713,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1714,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1714,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1714,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1715,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1715,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1715,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1716,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1716,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1716,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1717,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1717,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1717,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1718,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1718,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1718,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1719,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1719,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1719,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1720,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1720,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1720,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1721,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1721,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1721,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1722,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1722,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1722,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1723,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1723,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1723,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1724,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1724,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1724,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1725,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1725,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1725,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1726,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1726,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1726,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1727,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1727,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1727,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1728,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1728,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1728,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1729,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1729,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1729,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1730,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1730,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1730,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1731,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1731,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1731,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1732,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1732,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1732,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1733,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1733,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1733,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1734,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1734,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1734,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1735,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1735,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1735,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1736,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1736,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1736,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1737,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1737,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1737,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1738,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1738,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1738,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1739,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1739,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1739,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1740,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1740,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1740,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1741,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1741,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1741,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1742,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1742,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1742,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1743,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1743,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1743,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1744,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1744,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1744,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1745,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1745,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1745,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1746,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1746,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1746,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1747,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1747,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1747,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1748,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1748,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1748,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1749,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1749,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1749,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1750,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1750,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1750,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1751,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1751,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1751,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1752,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1752,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1752,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1753,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1753,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1753,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1754,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1754,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1754,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1755,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1755,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1755,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1756,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1756,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1756,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1757,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1757,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1757,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1758,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1758,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1758,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1759,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1759,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1759,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1760,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1760,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1760,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1761,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1761,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1761,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1762,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1762,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1762,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1763,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1763,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1763,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1764,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1764,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1764,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D1764*G1764),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1765,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1765,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1765,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1766,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1766,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1766,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1767,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1767,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1767,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1768,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1768,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1768,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1769,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1769,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1769,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1770,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1770,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1770,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1771,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1771,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1771,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1772,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1772,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1772,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1773,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1773,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1773,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1774,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1774,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1774,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1775,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1775,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1775,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1776,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1776,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1776,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1777,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1777,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1777,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1778,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1778,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1778,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1779,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1779,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1779,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1780,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1780,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1780,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1781,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1781,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1781,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1782,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1782,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1782,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1783,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1783,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1783,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1784,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1784,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1784,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1785,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1785,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1785,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1786,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1786,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1786,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1787,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1787,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1787,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1788,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1788,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1788,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1789,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1789,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1789,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1790,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1790,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1790,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1791,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1791,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1791,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1792,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1792,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1792,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1793,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1793,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1793,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1794,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1794,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1794,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1795,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1795,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1795,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1796,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1796,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1796,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1797,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1797,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1797,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1798,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1798,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1798,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1799,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1799,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1799,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1800,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1800,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1800,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1801,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1801,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1801,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1802,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1802,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1802,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1803,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1803,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1803,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1804,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1804,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1804,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1805,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1805,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1805,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1806,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1806,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1806,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1807,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1807,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1807,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1808,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1808,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1808,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1809,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1809,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1809,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1810,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1810,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1810,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1811,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1811,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1811,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1812,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1812,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1812,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1813,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1813,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1813,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1814,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1814,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1814,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1815,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1815,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1815,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1816,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1816,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1816,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1817,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1817,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1817,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1818,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1818,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1818,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1819,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1819,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1819,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1820,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1820,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1820,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1821,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1821,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1821,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1822,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1822,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1822,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1823,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1823,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1823,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1824,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1824,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1824,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1825,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1825,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1825,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1826,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1826,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1826,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1827,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1827,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1827,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1828,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1828,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1828,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D1828*G1828),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1829,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1829,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1829,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1830,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1830,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1830,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1831,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1831,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1831,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1832,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1832,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1832,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1833,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1833,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1833,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1834,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1834,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1834,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1835,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1835,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1835,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1836,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1836,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1836,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1837,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1837,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1837,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1838,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1838,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1838,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1839,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1839,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1839,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1840,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1840,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1840,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1841,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1841,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1841,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1842,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1842,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1842,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1843,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1843,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1843,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1844,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1844,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1844,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1845,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1845,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1845,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1846,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1846,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1846,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1847,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1847,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1847,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1848,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1848,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1848,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1849,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1849,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1849,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1850,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1850,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1850,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1851,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1851,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1851,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1852,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1852,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1852,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1853,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1853,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1853,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1854,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1854,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1854,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1855,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1855,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1855,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1856,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1856,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1856,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1857,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1857,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1857,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1858,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1858,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1858,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1859,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1859,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1859,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1860,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1860,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1860,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1861,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1861,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1861,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1862,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1862,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1862,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1863,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1863,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1863,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1864,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1864,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1864,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1865,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1865,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1865,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1866,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1866,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1866,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1867,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1867,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1867,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1868,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1868,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1868,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1869,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1869,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1869,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1870,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1870,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1870,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1871,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1871,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1871,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1872,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1872,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1872,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1873,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1873,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1873,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1874,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1874,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1874,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1875,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1875,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1875,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1876,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1876,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1876,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1877,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1877,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1877,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1878,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1878,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1878,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1879,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1879,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1879,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1880,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1880,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1880,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1881,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1881,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1881,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1882,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1882,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1882,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1883,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1883,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1883,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1884,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1884,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1884,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1885,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1885,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1885,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1886,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1886,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1886,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1887,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1887,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1887,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1888,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1888,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1888,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1889,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1889,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1889,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1890,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1890,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1890,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1891,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1891,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1891,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1892,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1892,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1892,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D1892*G1892),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1893,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1893,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1893,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1894,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1894,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1894,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1895,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1895,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1895,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1896,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1896,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1896,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1897,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1897,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1897,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1898,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1898,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1898,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1899,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1899,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1899,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1900,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1900,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1900,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1901,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1901,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1901,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1902,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1902,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1902,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1903,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1903,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1903,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1904,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1904,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1904,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1905,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1905,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1905,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1906,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1906,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1906,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1907,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1907,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1907,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1908,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1908,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1908,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1909,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1909,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1909,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1910,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1910,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1910,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1911,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1911,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1911,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1912,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1912,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1912,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1913,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1913,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1913,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1914,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1914,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1914,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1915,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1915,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1915,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1916,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1916,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1916,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1917,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1917,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1917,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1918,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1918,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1918,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1919,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1919,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1919,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1920,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1920,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1920,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1921,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1921,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1921,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1922,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1922,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1922,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1923,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1923,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1923,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1924,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1924,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1924,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1925,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1925,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1925,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1926,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1926,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1926,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1927,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1927,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1927,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1928,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1928,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1928,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1929,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1929,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1929,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1930,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1930,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1930,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1931,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1931,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1931,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1932,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1932,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1932,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1933,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1933,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1933,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1934,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1934,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1934,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1935,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1935,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1935,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1936,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1936,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1936,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1937,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1937,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1937,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1938,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1938,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1938,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1939,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1939,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1939,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1940,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1940,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1940,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1941,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1941,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1941,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1942,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1942,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1942,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1943,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1943,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1943,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1944,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1944,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1944,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1945,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1945,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1945,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1946,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1946,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1946,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1947,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1947,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1947,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1948,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1948,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1948,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1949,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1949,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1949,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1950,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1950,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1950,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1951,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1951,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1951,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1952,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1952,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1952,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1953,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1953,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1953,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1954,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1954,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1954,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1955,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1955,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1955,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1956,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1956,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1956,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D1956*G1956),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1957,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1957,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1957,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1958,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1958,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1958,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1959,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1959,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1959,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1960,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1960,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1960,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1961,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1961,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1961,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1962,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1962,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1962,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1963,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1963,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1963,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1964,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1964,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1964,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1965,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1965,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1965,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1966,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1966,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1966,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1967,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1967,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1967,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1968,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1968,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1968,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1969,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1969,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1969,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1970,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1970,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1970,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1971,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1971,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1971,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1972,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1972,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1972,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1973,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1973,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1973,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1974,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1974,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1974,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1975,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1975,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1975,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1976,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1976,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1976,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1977,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1977,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1977,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1978,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1978,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1978,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1979,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1979,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1979,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1980,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1980,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1980,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1981,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1981,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1981,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1982,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1982,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1982,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1983,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1983,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1983,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1984,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1984,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1984,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1985,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1985,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1985,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1986,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1986,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1986,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1987,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1987,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1987,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1988,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1988,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1988,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1989,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1989,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1989,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1990,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1990,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1990,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1991,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1991,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1991,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1992,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1992,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1992,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1993,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1993,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1993,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1994,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1994,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1994,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1995,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1995,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1995,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1996,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1996,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1996,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1997,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1997,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1997,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1998,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1998,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1998,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A1999,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E1999,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A1999,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2000,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2000,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2000,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2001,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2001,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2001,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2002,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2002,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2002,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2003,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2003,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2003,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2004,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2004,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2004,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2005,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2005,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2005,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2006,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2006,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2006,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2007,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2007,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2007,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2008,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2008,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2008,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2009,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2009,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2009,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2010,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2010,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2010,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2011,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2011,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2011,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2012,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2012,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2012,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2013,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2013,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2013,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2014,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2014,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2014,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2015,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2015,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2015,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2016,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2016,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2016,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2017,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2017,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2017,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2018,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2018,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2018,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2019,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2019,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2019,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2020,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2020,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2020,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D2020*G2020),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2021,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2021,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2021,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2022,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2022,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2022,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2023,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2023,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2023,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2024,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2024,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2024,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2025,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2025,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2025,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2026,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2026,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2026,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2027,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2027,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2027,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2028,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2028,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2028,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2029,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2029,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2029,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2030,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2030,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2030,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2031,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2031,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2031,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2032,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2032,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2032,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2033,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2033,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2033,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2034,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2034,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2034,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2035,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2035,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2035,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2036,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2036,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2036,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2037,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2037,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2037,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2038,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2038,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2038,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2039,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2039,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2039,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2040,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2040,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2040,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2041,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2041,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2041,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2042,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2042,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2042,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2043,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2043,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2043,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2044,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2044,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2044,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2045,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2045,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2045,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2046,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2046,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2046,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2047,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2047,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2047,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2048,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2048,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2048,'Average Unit Price'!A:D,4,0),\"\")","v":""},{"$f":"IFERROR((D2048*G2048),\"\")","v":""}]
[null,null,null,null,{"$f":"IFERROR(VLOOKUP(A2049,'Average Unit Price'!A:B,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(E2049,'IT CLASS'!B:C,2,0),\"\")","v":""},{"$f":"IFERROR(VLOOKUP(A2049,'Average Unit Price'!A:D,4,0),\"\")","v":""},""]

{"sheet":"IT CLASS","index":16,"n_rows":35,"n_cols":6,"rows_kept":35,"cut":false,"hidden":true,"merged":[]}
[null,"ITEM CLASSES","CATEGORY"]
[null,"ASPH","Asphalt Paving",null,null,"Asphalt Paving"]
[null,"BARR","Appurtenances",null,null,"Appurtenances"]
[null,"BASE","Asphalt Paving",null,null,"Fencing"]
[null,"BRPT","Fencing",null,null,"Concrete Pavement"]
[null,"CONC","Concrete Pavement",null,null,"   Drainage"]
[null,"DRNG","   Drainage",null,null,"Other Items"]
[null,"ENGR","Other Items",null,null,"Drainage"]
[null,"EROS","Drainage",null,null,"Earthwork"]
[null,"ERTH","Earthwork",null,null,"Guardrail "]
[null,"FLAT","Appurtenances",null,null,"Signalization "]
[null,"FNCE","Fencing",null,null,"Seeding & Sodding"]
[null,"GAT","Guardrail ",null,null,"Signalization & Lighting"]
[null,"INCI","Earthwork",null,null,"Mobilization"]
[null,"ITS","Signalization ",null,null,"Pavement Markings "]
[null,"LAND","Seeding & Sodding",null,null,"Rip-Rap or Slope Protection"]
[null,"LITE","Signalization & Lighting",null,null,"Removal Items"]
[null,"MISC","Other Items",null,null,"Structures"]
[null,"MOBL","Mobilization",null,null,"Maintenance of Traffic"]
[null,"MOWL","Other Items",null,null,"Utilities"]
[null,"NBI","Other Items"]
[null,"NONR","Other Items"]
[null,"PVMK","Pavement Markings "]
[null,"RIPR","Rip-Rap or Slope Protection"]
[null,"RMVL","Removal Items"]
[null,"SALT","Other Items"]
[null,"SLIP","Other Items"]
[null,"STBR","Structures"]
[null,"STDR","Drainage"]
[null,"SWDR","Other Items"]
[null,"TRFP","Signalization & Lighting"]
[null,"TRFT","Maintenance of Traffic"]
[null,"UNKN","Other Items"]
[null,"UTIL","Utilities"]
[null,"WALL","Structures"]

{"sheet":"ROW Statistics","index":17,"n_rows":18,"n_cols":8,"rows_kept":18,"cut":false,"hidden":true,"merged":[[1,1,2,1],[1,2,2,2],[0,1,0,7],[9,1,9,7]]}
[]
[null,"ROW Impacts","Average Project Length","Distressed","At-Risk","Transitional ","Competitive","Attainment"]
[null,null,null,"Avg Bottom 15%","<- Midpoint ->","Weighted Average","<- Midpoint ->","Avg Top 15%"]
[null,"Tier 1 - Very Low Impacts (0-20%)",3.8729999999999998,80000,211000,343000,536000,729000]
[null,"Tier 2 - Low Impacts (20% - 40%)",3.5453333333333337,843000,948000,1052000,1153000,1253000]
[null,"Tier 3 - Moderate Impacts (40% - 60%)",3.3347142857142851,1450000,1650000,1840000,2040000,2240000]
[null,"Tier 4 - High Impacts (60% - 80%)",2.6525333333333339,2770000,3050000,3330000,3700000,4060000]
[null,"Tier 5 - Very High Impacts (80% - 100%)",1.9821428571428572,4970000,6920000,8880000,14850000,20830000]
[]
[null,"73 PROJECT INVESTIGATED"]
[null,"ROW Impacts","Distressed","At-Risk","Transitional","Competitive","Attainment","Total"]
[null,"Tier 1 - Very Low Impacts (0-20%)",2,4,6,0,0,{"$f":"SUM(C12:G12)","v":12}]
[null,"Tier 2 - Low Impacts (20% - 40%)",0,2,8,1,1,{"$f":"SUM(C13:G13)","v":12}]
[null,"Tier 3 - Moderate Impacts (40% - 60%)",2,3,7,1,0,13]
[null,"Tier 4 - High Impacts (60% - 80%)",0,3,9,3,1,16]
[null,"Tier 5 - Very High Impacts (80% - 100%)",1,0,12,6,1,20]
[null,"Total:",5,12,42,11,3,{"$f":"SUM(H12:H16)","v":73}]
[null,"Percentage:",6.8493150684931503E-2,0.16438356164383561,0.57534246575342463,0.15068493150684931,4.1095890410958902E-2]

{"sheet":"Housing Index","index":18,"n_rows":42,"n_cols":8,"rows_kept":42,"cut":false,"hidden":true,"merged":[]}
["Year","# Years (inflation)","# Years (since ROW Acquisition)","TN House Price Index","HPI Annual Difference","Year-over-Year Increase to Current Year","Current Year =",2025]
[2000,0,{"$f":"IF((YEAR(TODAY())-A2)<0,0,(YEAR(TODAY())-A2))","v":25},214.35,null,{"$f":"IF(A2>($H$1-1),\"\",((VLOOKUP($H$1,A:D,4,0)-D2)/($H$1-A2))/D2)","v":8.8154886867273158E-2}]
[2001,1,{"$f":"IF((YEAR(TODAY())-A3)<0,0,(YEAR(TODAY())-A3))","v":24},225.1,{"$f":"D3-D2","v":10.75},8.5452761735524949E-2,"https://fred.stlouisfed.org/series/TNSTHPI"]
[2002,2,23,231.44,{"$f":"D4-D3","v":6.3400000000000034},8.5534423420850936E-2]
[2003,3,22,238.88,7.4399999999999977,8.522156426962188E-2]
[2004,4,21,247.13,8.25,8.4709609170419267E-2]
[2005,5,20,260.13,13,8.2001307038788301E-2]
[2006,6,19,280.02999999999997,19.899999999999977,7.6442937504816219E-2]
[2007,7,18,297.19,17.160000000000025,7.2822848084465236E-2]
[2008,8,17,304.48,7.2900000000000205,7.3852044759049162E-2]
[2009,9,16,302.73,-1.75,7.9282694149902549E-2]
[2010,10,15,287.16000000000003,-15.569999999999993,{"$f":"IF(A12>($H$1-1),\"\",((VLOOKUP($H$1,A:D,4,0)-D12)/($H$1-A12))/D12)","v":9.2768259274736489E-2}]
[2011,11,14,280.99,-6.1700000000000159,0.10314551102479498]
[2012,12,13,278.89,-2.1000000000000227,0.11249541451413159]
[2013,13,12,281.54000000000002,2.6500000000000341,0.11993855224834836]
[2014,14,11,288,6.4599999999999795,0.12586805555555555]
[2015,15,10,303.06,15.060000000000002,0.12660529268131723]
[2016,16,9,319.02,15.95999999999998,0.12807626132809508]
[2017,17,8,339.23,20.210000000000036,0.1280547121422044]
[2018,18,7,364.79,25.560000000000002,0.12608428332543575]
[2019,19,6,386.3,21.509999999999991,0.12962723272068338]
[2020,20,5,410.47,24.170000000000016,0.13461641532876945]
[2021,21,4,446.55,36.079999999999984,{"$f":"IF(A23>($H$1-1),\"\",((VLOOKUP($H$1,A:D,4,0)-D23)/($H$1-A23))/D23)","v":0.13447542268502966}]
[2022,22,3,558.84,{"$f":"D24-D23","v":112.29000000000002},{"$f":"IF(A24>($H$1-1),\"\",((VLOOKUP($H$1,A:D,4,0)-D24)/($H$1-A24))/D24)","v":7.6294944289361274E-2}]
[2023,23,2,623.45000000000005,{"$f":"1.9711*B25-7.0087","v":38.326600000000006},{"$f":"IF(A25>($H$1-1),\"\",((VLOOKUP($H$1,A:D,4,0)-D25)/($H$1-A25))/D25)","v":5.0765899430587819E-2}]
[2024,24,1,662.25,{"$f":"1.9711*B26-7.0087","v":40.297700000000006},{"$f":"IF(A26>($H$1-1),\"\",((VLOOKUP($H$1,A:D,4,0)-D26)/($H$1-A26))/D26)","v":3.6995092487731217E-2}]
[2025,25,0,686.75,42.268800000000006,{"$f":"IF(A27>($H$1-1),\"\",((VLOOKUP($H$1,A:D,4,0)-D27)/($H$1-A27))/D27)","v":""}]
[2026,26,0,{"$f":"D27+E28","v":730.98990000000003},44.239900000000006,""]
[2027,27,0,777.20090000000005,46.211000000000006,""]
[2028,28,0,825.38300000000004,48.182100000000005,""]
[2029,29,0,875.53620000000001,50.153200000000005,""]
[2030,30,0,927.66049999999996,52.124300000000005,""]
[2031,31,0,981.7559,54.095400000000005,""]
[2032,32,0,1037.8224,56.066500000000005,""]
[2033,33,0,1095.8600000000001,58.037600000000005,""]
[2034,34,0,1155.8687000000002,60.008700000000012,""]
[2035,35,0,1217.8485000000003,61.979800000000004,""]
[2036,36,0,1281.7994000000003,63.950900000000011,""]
[2037,37,0,1347.7214000000004,65.921999999999997,""]
[2038,38,0,1415.6145000000004,67.893100000000004,""]
[2039,39,0,1485.4787000000003,69.864199999999997,""]
[2040,40,0,1557.3140000000003,71.835300000000004,""]

{"sheet":"Update Notes","index":19,"n_rows":34,"n_cols":4,"rows_kept":34,"cut":false,"hidden":true,"merged":[[1,1,1,2],[21,1,27,1]]}
[]
[null,"Update Notes"]
[null,"Date","Note"]
[null,"2018-02-14","Issue with Non-Symmetrical Widening Earthwork Volumes Fixed"]
[null,"2019-06-24","Reconfigured how Roadway Templates are input."]
[null,"2019-06-24","Added the ability to replace existing pavement with Full Depth Pavement"]
[null,"2019-06-24","Added the ability to widen to both sides or just one."]
[null,"2019-06-24","Added Terrain Depth Overrides"]
[null,"2019-06-24","Added the ability to add Concrete Islands"]
[null,"2019-06-24","All costs are rounded to the three (3) significant figures"]
[null,"2019-08-08","Adjusted all rounding to 3 significant figures"]
[null,"2019-08-08","PE Cost for RSA No Plans and LRSI now default to fixed numbers"]
[null,"2019-08-13","Updated Item Numbers and Average Unit Costs"]
[null,"2019-08-15","Added Preliminary Estimates Tab (For STID Use Only)"]
[null,"2019-08-16","Incorporated CEI Cost into Construction Estimate"]
[null,"2020-04-21","Fixed Issue with \"Inflated Cost\" sheet not calculating Construction Cost Correctly"]
[null,"2020-05-06","Fixed issue with tool not calculating sidewalk quantities for C&G 1-side and Sidewalk 1-side"]
[null,"2020-07-06","Updated Utility Per Mile Costs"]
[null,"2020-08-03","Adjustments Made to SIA Typical Section and Error Flags Based on direction from TDOT Chief Engineering"]
[null,"2020-08-25","Fixed issues with resurfacing segments calculating earthwork and drainage quantities.  Added the ability to set graded solid rock to \"None\". Rounding for Local/State/Federal Cost Contributions have been adjusted to add up correctly."]
[null,"2021-01-12","Categories of Items less than (<) 0 in Finalize Items will now default 0.  "]
[null,"2021-08-16","(1) Added a Visual Guidance for TDOT Cost Estimate Tool"]
[null,null,"(2) Roadway Segments: Added slope rates to the segments, added sidewalk and grass strip width."]
[null,null,"(3) Interface: Moved # of Traffic Signals and ITS to top of the page.  Removed High-Level Interchange Costs and Roundabouts from User Inputs."]
[null,null,"(4) Updated Median Types and autopopulate inputs according to TDOT Standards"]
[null,null,"(5) Updated Average Bid Prices based on 2018, 2019, & 2020 Cost Data, with each data set inflated to 2021 at 5% per year."]
[null,null,"(6) Added new guardrail assumptions based on Foreslope Rate and Tool Generated Quantities can be toggled on and off."]
[null,null,"(7) Terrain Depth Assumptions have been calibrated based on 36 TDOT projects that involved widening from 2 to 5 lanes."]
[null,"2022-06-30","Updated Average Bid Prices based on 2018, 2019, 2020 & 2021 Cost Data, with each data set indexed to 2022 value."]
[null,"2022-08-31","Right-of-Way estimating has been altered to a \"Per-Mile\" type methodology."]
[null,"2022-09-02","All SIAs need to populate a minimum ROW of $5000","still need to update"]
[null,"2022-09-30","Clearing and Curbing estimates have been updated to per-mile methdology."]
[null,"Idea","100% Eligible Item Breakdown Functionality"]
[null,"Idea","Force Rounding to work"]

{"sheet":"Projects","index":20,"n_rows":48,"n_cols":27,"rows_kept":48,"cut":false,"hidden":true,"merged":[[4,3,7,3],[7,15,7,16],[0,15,0,18]]}
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Earthwork Distribution"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Item Number","Description","Volume","Percent",null,null,"Access Database Query"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"203-01","ROAD & DRAINAGE EXCAVATION (UNCLASSIFIED)",{"$f":"SUM(P12:P48)","v":9376655.3635499999},{"$f":"R3/$R$8","v":0.79187627835989927},null,null,"=\"CND159\"or=\"CNH654\"or=\"CNN201\"or=\"CNR280\"or=\"CNM019\"or=\"CNR136\"or=\"CND431\"or=\"CNH658\"or=\"CNU057\"or=\"CNH670\"or=\"CNK901\"or=\"CNQ172\"or=\"CNS182\"or=\"CNT925\"or=\"CNK821\"or=\"CNQ346\"or=\"CNR277\"or=\"CNJ363\"or=\"CNR040\"or=\"CNQ297\"or=\"CNS127\"or=\"CNP927\"or=\"CNJ202\"or=\"CNR220\"or=\"CNR252\"or=\"CNQ076\"or=\"CNR279\"or=\"CNK916\"or=\"CNQ340\"or=\"CNJ331\"or=\"CNU032\"or=\"CNV012\"or=\"CNU922\"or=\"CNL258\"or=\"CNR273\"or=\"CNT336\"or=\"CNG917\""]
[null,"Terrain Type","Average Earthwork","Total Earthwork","Average Guardrail","Average End Terminals",null,"Guardrail/End Terminal",null,null,"Start Year",2000,214.35,null,null,"203-03","BORROW EXCAVATION (UNCLASSIFIED)",{"$f":"SUM(Q12:Q48)","v":1002751.5529499999},{"$f":"R4/$R$8","v":8.4684265026567673E-2},null,null,{"$f":"CONCATENATE(J12,\"or\",J13,\"or\",J14,\"or\",J15,\"or\",J16,\"or\",J17,\"or\",J18,\"or\",J19,\"or\",J20,\"or\",J21,\"or\",J22,\"or\",J23,\"or\",J24,\"or\",J25,\"or\",J26,\"or\",J27,\"or\",J28,\"or\",J29,\"or\",J30,\"or\",J31,\"or\",J32,\"or\",J33,\"or\",J34,\"or\",J35,\"or\",J36,\"or\",J37,\"or\",J38,\"or\",J39,\"or\",J40,\"or\",J41,\"or\",J42,\"or\",J43,\"or\",J44,\"or\",J45,\"or\",J46,\"or\",J47,\"or\",J48)","v":"=\"CND159\"or=\"CNH654\"or=\"CNN201\"or=\"CNR280\"or=\"CNM019\"or=\"CNR136\"or=\"CND431\"or=\"CNH658\"or=\"CNU057\"or=\"CNH670\"or=\"CNK901\"or=\"CNQ172\"or=\"CNS182\"or=\"CNT925\"or=\"CNK821\"or=\"CNQ346\"or=\"CNR277\"or=\"CNJ363\"or=\"CNR040\"or=\"CNQ297\"or=\"CNS127\"or=\"CNP927\"or=\"CNJ202\"or=\"CNR220\"or=\"CNR252\"or=\"CNQ076\"or=\"CNR279\"or=\"CNK916\"or=\"CNQ340\"or=\"CNJ331\"or=\"CNU032\"or=\"CNV012\"or=\"CNU922\"or=\"CNL258\"or=\"CNR273\"or=\"CNT336\"or=\"CNG917\""}]
[null,{"$f":"\"4:1\"","v":"4:1"},{"$f":"AVERAGE(W12:W20)","v":34210.457446346569},{"$f":"'Finalize Items'!E380+'Finalize Items'!E388","v":0},{"$f":"AVERAGE(Y12:Y20)","v":576.12069472323765},{"$f":"AVERAGE(AA12:AA20)","v":63.621308918460826},null,{"$f":"AVERAGE(AA12:AA48)","v":142.17130249148832},null,null,"End Year",2021,558.84,null,null,"203-01.11","Presplitting of Rock Excavation",{"$f":"SUM(R12:R48)","v":134234.77799999999},1.1336380863726566E-2]
[null,{"$f":"\"3:1\"","v":"3:1"},{"$f":"AVERAGE(W21:W32)","v":68100.581350283916},null,{"$f":"AVERAGE(Y21:Y32)","v":1379.373778274422},{"$f":"AVERAGE(AA21:AA32)","v":131.7310941834148},null,null,null,null,null,null,null,null,null,"203-02.01","BORROW EXCAVATION (GRADED SOLID ROCK)",{"$f":"SUM(S12:S48)","v":1188555.3648999999},0.10037574833350493]
[null,{"$f":"\"2:1\"","v":"2:1"},{"$f":"AVERAGE(W33:W41)","v":120729.39598514592},null,{"$f":"AVERAGE(Y33:Y41)","v":1936.3413423151931},{"$f":"AVERAGE(AA33:AA41)","v":168.60990167236409},null,null,null,null,{"$f":"((M8*(L5-L4)+1)*M4)","v":558.83999999999992},null,{"$f":"(M5-M4)/(L5-L4)","v":16.404285714285713},null,null,"203-01.09","ACID PRODUCING MATERIAL HAUL & TIP FEE",{"$f":"SUM(T12:T48)","v":138864},1.1727327416301354E-2]
[null,{"$f":"\"1:1\"","v":"1:1"},{"$f":"AVERAGE(W42:W48)","v":206795.78252885511},null,{"$f":"AVERAGE(Y42:Y48)","v":2785.2792890928163},{"$f":"AVERAGE(AA42:AA48)","v":227.06916666666666},null,null,null,null,null,null,{"$f":"M7/M4","v":7.653037422106701E-2},null,null,"Total",null,{"$f":"SUM(R3:R7)","v":11841061.059400002}]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"203-01","203-03","203-01.11","203-02.01","203-01.09"]
["Project #","Description","PIN","County","Route","Length",null,"Contract #",null,null,"Let Date","Years","ROW Cost","Inflated ROW","ROW/Mile","ROAD & DRAINAGE EXCAVATION (UNCLASSIFIED)","BORROW EXCAVATION (UNCLASSIFIED)","Presplitting of Rock Excavation","BORROW EXCAVATION (GRADED SOLID ROCK)","ACID PRODUCING MATERIAL HAUL & TIP FEE","Total Volume","Project #","Volume Per Mile","Guardrail (All Types)","Guardrail/Mile","End Terminals (All Types)","Guardrail/End Terminal"]
[{"$f":"V12","v":1},"converted from m3 to CY",101138,"Madison","SR-5",0.77,null,"CND159",{"$f":"F12","v":0.77},{"$f":"CONCATENATE(\"=\",CHAR(34),H12,CHAR(34))","v":"=\"CND159\""},"2005-03-11",{"$f":"IFERROR(YEAR(TODAY())-YEAR(K12),\"\")","v":20},294299.74,{"$f":"(($M$8*(L12)+1)*M12)","v":744757.12470725446},{"$f":"N12/F12","v":967217.04507435637},{"$f":"8369*1.30795","v":10946.233549999999},500,null,null,null,{"$f":"SUM(P12:S12)","v":11446.233549999999},1,{"$f":"U12/F12","v":14865.238376623374},{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H12,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H12,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H12,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":0},{"$f":"X12/F12","v":0},{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H12,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H12,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H12,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H12,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H12,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H12,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H12,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H12,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H12,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H12,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":0},{"$f":"IFERROR(X12/Z12,0)","v":0}]
[{"$f":"V13","v":2},"From 3 to 5 lanes",103210,"Wilson","SR-171",2.2000000000000002,null,"CNH654",{"$f":"F13","v":2.2000000000000002},{"$f":"CONCATENATE(\"=\",CHAR(34),H13,CHAR(34))","v":"=\"CNH654\""},"2009-06-12",{"$f":"IFERROR(YEAR(TODAY())-YEAR(K13),\"\")","v":16},4585978.5,{"$f":"(($M$8*(L13)+1)*M13)","v":10201444.91239628},{"$f":"N13/F13","v":4637020.4147255812},45543,16602,null,null,null,62145,2,28247.727272727272,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H13,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H13,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H13,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":43.75},{"$f":"X13/F13","v":19.886363636363633},{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H13,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H13,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H13,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H13,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H13,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H13,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H13,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H13,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H13,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H13,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":4},{"$f":"IFERROR(X13/Z13,0)","v":10.9375}]
[3,"WIDEN FROM 2 LANES TO 4/5 LANES",103779,"Roane","SR-29",0.89,null,"CNN201",0.89,"=\"CNN201\"","2014-07-11",11,4081353.06,7517175.3071110668,8446264.3900124338,22681,2500,null,1323,null,26504,3,29779.775280898877,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H14,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H14,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H14,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":18.75},21.067415730337078,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H14,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H14,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H14,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H14,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H14,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H14,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H14,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H14,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H14,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H14,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":1},18.75]
[4,null,100282.02,"Rutherford","SR-96",0.34,null,"CNR280",0.34,"=\"CNR280\"","2017-10-06",8,279922.40999999997,451302.94432130357,1327361.6009450103,2764,8747,null,null,null,11511,4,33855.882352941175,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H15,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H15,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H15,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":0},0,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H15,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H15,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H15,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H15,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H15,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H15,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H15,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H15,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H15,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H15,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":4},0]
[5,null,101285.01,"Montgomery","SR-112",3.1349999999999998,null,"CNM019",3.1349999999999998,"=\"CNM019\"","2013-12-06",12,8909630.9499999993,17091919.639301207,5451967.9870179296,83525,25664,null,3897,null,113086,5,36072.089314194578,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H16,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H16,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H16,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":2247},716.74641148325361,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H16,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H16,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H16,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H16,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H16,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H16,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H16,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H16,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H16,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H16,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":14},160.5]
[6,"Widen from 2 to 5 lanes, including curb and gutter, with a separated 10' multi-use path on the east side",105717,"Williamson","SR-6",2.59,null,"CNR136",2.59,"=\"CNR136\"","2017-06-23",8,{"$f":"1881219.02+426706.26","v":2307925.2800000003},3720936.3628212875,1436654.9663402655,80505,18827,null,2097,null,101429,6,39161.776061776065,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H17,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H17,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H17,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":1272},491.11969111969114,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H17,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H17,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H17,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H17,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H17,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H17,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H17,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H17,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H17,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H17,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":9},141.33333333333334]
[7,"convert from m3 to CY",101460,"Montgomery","SR-236",3.03,null,"CND431",3.03,"=\"CND431\"","2005-12-09",20,4576914.63,11582374.418235529,3822565.8145991848,72547,44704,null,2511,null,119762,7,39525.412541254125,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H18,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H18,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H18,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":656},216.50165016501651,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H18,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H18,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H18,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H18,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H18,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H18,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H18,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H18,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H18,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H18,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":65},10.092307692307692]
[8,"Widen from 2 lanes to 5 lanes",106879,"Rutherford","Waldron Road",1.98,null,"CNH658",1.98,"=\"CNH658\"","2009-10-30",16,{"$f":"619716.03","v":619716.03},1378549.624987104,696237.1843369212,43600,35753,null,null,null,79353,8,40077.272727272728,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H19,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H19,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H19,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":3350},1691.9191919191919,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H19,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H19,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H19,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H19,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H19,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H19,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H19,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H19,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H19,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H19,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":32},104.6875]
[9,null,101407.01,"Campbell","SR-63",4.92,null,"CNU057",4.92,"=\"CNU057\"","2020-06-26",5,4781000,6610458.5957546066,1343589.1454785785,226358,null,null,1482,null,227840,9,46308.943089430897,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H20,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H20,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H20,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":9977},2027.8455284552847,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H20,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H20,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H20,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H20,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H20,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H20,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H20,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H20,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H20,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H20,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":79},126.29113924050633]
[10,"From 3 to 5 lanes C&G/sidewalks/bike lanes",103587,"Knox",null,0.90100000000000002,null,"CNH670",0.90100000000000002,"=\"CNH670\"","2009-06-12",16,1708691.97,3800961.3442821153,4218603.0458181081,45196,null,null,null,null,45196,10,50162.042175360708,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H21,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H21,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H21,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":150},166.48168701442842,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H21,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H21,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H21,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H21,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H21,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H21,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H21,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H21,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H21,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H21,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":3},50]
[11,null,101397,"Sullivan, Washington","SR-75",3.86,null,"CNK901",3.86,"=\"CNK901\"","2011-02-11",14,{"$f":"2893179.39+118913.57","v":3012092.96},6239325.3798441803,1616405.5388197359,199139,null,3952,11411,null,214502,11,55570.466321243526,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H22,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H22,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H22,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":10108.959999999999},2618.9015544041449,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H22,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H22,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H22,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H22,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H22,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H22,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H22,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H22,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H22,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H22,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":37},273.21513513513509]
[12,null,100286,"Sumner","SR-109",1.3,null,"CNQ172",1.3,"=\"CNQ172\"","2016-05-13",9,{"$f":"354829.51+2257407.1","v":2612236.6100000003},4411475.6178554436,3393442.7829657258,{"$f":"65027+3077","v":68104},null,400,5333,null,73837,12,56797.692307692305,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H23,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H23,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H23,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":650},500,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H23,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H23,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H23,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H23,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H23,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H23,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H23,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H23,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H23,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H23,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":12},54.166666666666664]
[13,null,100352.01,"Bedford","SR-16",2.1800000000000002,5.72,"CNS182",2.1800000000000002,"=\"CNS182\"","2018-08-17",7,{"$f":"3230101.09","v":3230101.09},4960507.0063270349,2275461.9295078139,110455,null,null,18982,null,129437,13,59374.770642201831,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H24,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H24,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H24,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":2938},1347.7064220183486,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H24,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H24,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H24,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H24,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H24,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H24,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H24,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H24,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H24,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H24,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":17},172.8235294117647]
[14,"Widen to 5-ln curb & gutter section",103764,"Davidson","SR-112",2.15,null,"CNT925",2.15,"=\"CNT925\"","2019-10-04",6,5990288.2800000003,8740922.302562831,4065545.2570059681,84920,44871,null,null,null,129791,14,60367.906976744191,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H25,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H25,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H25,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":1621},753.95348837209303,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H25,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H25,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H25,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H25,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H25,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H25,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H25,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H25,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H25,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H25,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":10},162.1]
[15,null,101398,"Washington","SR-36",4.0999999999999996,null,"CNK821",4.0999999999999996,"=\"CNK821\"","2011-12-09",14,5117054.6100000003,10599596.068981105,2585267.3338978309,275776,null,2484,625,null,278885,15,68020.731707317085,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H26,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H26,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H26,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":6154},1500.9756097560976,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H26,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H26,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H26,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H26,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H26,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H26,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H26,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H26,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H26,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H26,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":85},72.400000000000006]
[16,null,101887,"Marshall","SR-50",2.17,null,"CNQ346",2.17,"=\"CNQ346\"","2016-12-02",9,2335815.56,3944663.1102637211,1817817.101504019,48063,null,null,{"$f":"103752+1400","v":105152},null,153215,16,70605.990783410147,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H27,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H27,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H27,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":3690},1700.4608294930877,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H27,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H27,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H27,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H27,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H27,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H27,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H27,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H27,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H27,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H27,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":28},131.78571428571428]
[17,null,101886.01,"Henry","SR-54",2.66,null,"CNR277",2.66,"=\"CNR277\"","2017-08-18",8,5859331.1799999997,9446665.6431245282,3551378.0613250104,116155,{"$f":"76390","v":76390},null,null,null,192545,17,72385.338345864657,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H28,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H28,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H28,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":1507},566.54135338345861,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H28,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H28,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H28,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H28,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H28,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H28,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H28,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H28,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H28,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H28,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":10},150.69999999999999]
[18,null,100990,"Knox","SR-62",3.9,null,"CNJ363",3.9,"=\"CNJ363\"","2010-12-10",15,9813668.1199999992,21079323.525574327,5404954.7501472635,206277,76414,null,null,null,282691,18,72484.871794871797,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H29,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H29,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H29,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":9886},2534.8717948717949,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H29,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H29,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H29,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H29,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H29,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H29,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H29,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H29,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H29,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H29,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":87},113.63218390804597]
[19,null,101244.02,"Roane","SR-1",2.12,null,"CNR040",2.12,"=\"CNR040\"","2017-02-10",8,2062826.38,3325777.3785159118,1568762.9143942979,151425,null,null,10823,null,162248,19,76532.075471698103,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H30,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H30,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H30,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":5125},2417.4528301886789,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H30,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H30,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H30,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H30,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H30,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H30,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H30,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H30,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H30,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H30,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":32},160.15625]
[20,null,101204,"Knox","SR-62",0.99,null,"CNQ297",0.99,"=\"CNQ297\"","2016-10-07",9,10302779.77,17399060.091838047,17574808.173573785,66988,{"$f":"11101*1.30795","v":14519.552949999999},null,{"$f":"222*1.30795","v":290.36489999999998},null,81797.917849999998,20,82624.159444444449,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H31,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H31,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H31,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":1363},1376.7676767676767,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H31,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H31,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H31,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H31,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H31,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H31,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H31,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H31,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H31,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H31,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":18},75.722222222222229]
[21,"Widen to 5-ln curb & gutter section",104004.01,"Rutherford","SR-99",2.15,null,"CNS127",2.15,"=\"CNS127\"","2018-03-23",7,2738555.51,4205634.2560382551,1956108.9562968628,41211,104281,null,52912,null,198404,21,92280.930232558138,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H32,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H32,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H32,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":2297},1068.372093023256,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H32,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H32,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H32,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H32,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H32,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H32,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H32,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H32,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H32,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H32,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":14},164.07142857142858]
[22,null,101591,"Giles","SR-75",2.31,null,"CNP927",2.31,"=\"CNP927\"","2015-12-04",10,4544779.91,8022916.9826468723,3473124.2349120658,229113,6500,null,null,null,235613,22,101996.9696969697,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H33,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H33,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H33,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":1576},682.25108225108227,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H33,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H33,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H33,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H33,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H33,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H33,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H33,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H33,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H33,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H33,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":23},68.521739130434781]
[23,null,100317,"Hardeman","SR-15",5.4710000000000001,null,"CNJ202",5.4710000000000001,"=\"CNJ202\"","2010-08-06",15,2213234.2000000002,4753928.8234729581,868932.3384158212,470853,null,11146,88506,null,570505,23,104278.01133248035,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H34,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H34,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H34,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":2000},365.56388228842991,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H34,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H34,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H34,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H34,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H34,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H34,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H34,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H34,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H34,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H34,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":56},35.714285714285715]
[24,null,100290,"Montgomery","SR-374",1.724,null,"CNR220",1.724,"=\"CNR220\"","2010-01-01",15,872101.09,1873234.4316445065,1086562.8953854446,170262,null,2127.7779999999998,8014,null,180403.77799999999,24,104642.5626450116,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H35,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H35,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H35,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":3093.75},1794.5185614849188,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H35,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H35,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H35,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H35,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H35,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H35,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H35,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H35,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H35,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H35,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":15},206.25]
[25,null,101608.02,"Shelby","SR-149",3.8,6.13,"CNR252",3.8,"=\"CNR252\"","2015-12-17",10,2773241.04,4895612.7859642105,1288319.154201108,190846,208485,null,null,null,399331,25,105087.10526315789,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H36,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H36,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H36,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":6370},1676.3157894736844,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H36,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H36,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H36,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H36,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H36,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H36,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H36,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H36,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H36,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H36,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":11},579.09090909090912]
[26,"4-lane divided, ACID PRODUCING",101411.05,"Morgan","SR-29",1.91,2.4500000000000002,"CNQ076",1.91,"=\"CNQ076\"","2015-02-13",10,1570437.33,2772298.895556333,1451465.39034363,138478,89992,null,3420,138864,231890,26,121408.37696335079,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H37,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H37,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H37,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":6798},3559.1623036649216,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H37,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H37,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H37,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H37,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H37,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H37,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H37,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H37,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H37,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H37,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":37},183.72972972972974]
[27,null,101463.05,"Montgomery","SR-149",3.1,null,"CNR279",3.1,"=\"CNR279\"","2017-12-08",8,2150696.0499999998,3467444.6383381649,1118530.5284961823,327898,14842,3567,47498,null,393805,27,127033.87096774192,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H38,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H38,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H38,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":7306},2356.7741935483868,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H38,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H38,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H38,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H38,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H38,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H38,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H38,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H38,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H38,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H38,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":41},178.19512195121951]
[28,null,100301.01,"Lewis","SR-99",3.206,6.5,"CNK916",3.206,"=\"CNK916\"","2011-05-06",14,3819014,7910801.9880569158,2467499.060529294,333111,null,3125,104174,null,440410,28,137370.55520898316,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H39,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H39,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H39,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":6644},2072.3643169058018,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H39,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H39,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H39,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H39,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H39,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H39,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H39,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H39,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H39,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H39,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":57},116.56140350877193]
[29,"Widen from 2-ln to 5-ln rural section",119830,"Montgomery","SR-13",1.35,null,"CNQ340",1.35,"=\"CNQ340\"","2016-12-02",9,3520500.47,5945327.4357308811,4403946.2486895416,134752,8158,null,47557,null,190467,29,141086.66666666666,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H40,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H40,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H40,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":0},0,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H40,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H40,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H40,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H40,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H40,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H40,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H40,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H40,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H40,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H40,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":0},0]
[30,null,101244.01,"Roane","SR-1",1.64,null,"CNJ331",1.64,"=\"CNJ331\"","2010-09-17",15,1622975.44,3486079.2066220134,2125658.0528183011,235603.13,null,null,null,null,235603.13,30,143660.44512195123,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H41,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H41,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H41,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":8069},4920.1219512195121,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H41,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H41,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H41,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H41,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H41,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H41,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H41,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H41,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H41,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H41,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":54},149.42592592592592]
[31,null,100288,"Williamson","SR-96",5.6,null,"CNU032",5.6,"=\"CNU032\"","2020-06-26",5,11426667.24,15799102.839884035,2821268.3642650065,798807,null,71932,null,null,870739,31,155489.10714285716,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H42,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H42,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H42,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":15606.25},2786.8303571428573,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H42,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H42,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H42,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H42,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H42,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H42,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H42,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H42,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H42,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H42,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":84},185.78869047619048]
[32,null,100261.03,"Dekalb","SR-26",4.0999999999999996,6.16,"CNV012",4.0999999999999996,"=\"CNV012\"","2021-03-26",4,4472509.66,5841641.0119485492,1424790.4907191584,635870,null,21298,21072,null,678240,32,165424.39024390245,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H43,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H43,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H43,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":9625},2347.5609756097565,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H43,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H43,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H43,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H43,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H43,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H43,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H43,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H43,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H43,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H43,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":52},185.09615384615384]
[33,"Widen from 2 lanes to 5 lanes.",107045,"Rutherford","SR-266",3.94,null,"CNU922",3.94,"=\"CNU922\"","2020-12-11",5,3089998.37,4272392.0279929359,1084363.4588814557,359562,{"$f":"199827+1725*3","v":205002},2268,89072,null,655904,33,166473.09644670051,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H44,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H44,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H44,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":7232},1835.5329949238578,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H44,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H44,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H44,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H44,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H44,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H44,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H44,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H44,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H44,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H44,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":25},289.27999999999997]
[34,null,100301.02,"Lewis","SR-99",3.24,null,"CNL258",3.24,"=\"CNL258\"","N/A","","N/A",{"$error":"#VALUE!"},{"$error":"#VALUE!"},470853,null,11146,88506,null,570505,34,176081.79012345677,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H45,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H45,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H45,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":12366},3816.6666666666665,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H45,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H45,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H45,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H45,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H45,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H45,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H45,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H45,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H45,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H45,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":80},154.57499999999999]
[35,null,100281.02,"Wilson","SR-109",3.387,null,"CNR273",3.387,"=\"CNR273\"","2017-12-08",8,5381362.5899999999,8676064.1326556038,2561577.8366269865,560117,null,789,146104,null,707010,35,208742.24977856511,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H46,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H46,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H46,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":13656},4031.8866253321526,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H46,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H46,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H46,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H46,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H46,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H46,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H46,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H46,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H46,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H46,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":56},243.85714285714286]
[36,"Widen existing 2 lanes to four 12' travel lanes with a continuous 12' center turn lane along with curb and gutter, 4' paved shoulders; bike path and 5' sidewalks on both sides.",112524.01,"Hamilton","SR-317",3.08,null,"CNT336",3.08,"=\"CNT336\"","2019-12-13",6,12306279.27,17957104.216812354,5830228.6418221928,790203,null,null,71203,null,861406,36,279677.27272727271,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H47,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H47,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H47,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":13207},4287.9870129870133,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H47,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H47,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H47,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H47,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H47,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H47,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H47,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H47,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H47,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H47,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":30},440.23333333333335]
[37,null,100313,"Hardin","SR-15",6.0359999999999996,null,"CNG917",6.0359999999999996,"=\"CNG917\"","2008-08-01",17,11015558.220000001,25346979.698119365,4199300.811484322,1528149,null,null,256591,null,1784740,37,295682.57123923127,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H48,Guardrail!$B$16:$B$1000,Guardrail!$A$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H48,Guardrail!$B$16:$B$1000,Guardrail!$A$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H48,Guardrail!$B$16:$B$1000,Guardrail!$A$4)","v":2357},390.49039098740889,{"$f":"SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H48,Guardrail!$B$16:$B$1000,Guardrail!$C$2)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H48,Guardrail!$B$16:$B$1000,Guardrail!$C$3)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H48,Guardrail!$B$16:$B$1000,Guardrail!$C$4)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H48,Guardrail!$B$16:$B$1000,Guardrail!$C$5)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H48,Guardrail!$B$16:$B$1000,Guardrail!$C$6)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H48,Guardrail!$B$16:$B$1000,Guardrail!$C$7)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H48,Guardrail!$B$16:$B$1000,Guardrail!$C$8)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H48,Guardrail!$B$16:$B$1000,Guardrail!$C$9)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H48,Guardrail!$B$16:$B$1000,Guardrail!$C$10)+SUMIFS(Guardrail!$G$16:$G$1000,Guardrail!$A$16:$A$1000,Projects!H48,Guardrail!$B$16:$B$1000,Guardrail!$C$11)","v":26},90.65384615384616]

{"sheet":"Guardrail","index":21,"n_rows":262,"n_cols":8,"rows_kept":262,"cut":false,"hidden":true,"merged":[[0,0,0,1],[0,2,0,3]]}
["Guardrail",null,"End Terminals"]
["705-02.02",{"$f":"SUMIF($B$16:$B$1008,A2,$G$16:$G$1008)","v":93791.459999999992},"705M04.04",{"$f":"SUMIF($B$16:$B$1008,C2,$G$16:$G$1008)","v":2}]
["705-06.01",{"$f":"SUMIF(B16:B1008,A3,G16:G1008)","v":84962},"705M04.05",{"$f":"SUMIF($B$16:$B$1008,C3,$G$16:$G$1008)","v":8}]
["705-02.03",{"$f":"SUMIF(B16:B1008,A4,G16:G1008)","v":207},"705M04.07",92]
[null,null,"705-04.07",258]
[null,null,"705-04.04",60]
[null,null,"705-04.07",258]
[null,null,"705-04.05",99]
[null,null,"705-06.11",139]
[null,null,"705-06.20",234]
[null,null,"705-06.30",58]
[]
[]
[]
["ContId","Item","Itemclss","Iunits","Itemdesc","IpLineNo","BtoQty","Bid1"]
["CND431","705M01.01","GAT","m","GUARDRAIL AT BRIDGE ENDS",560,33,145]
["CND431","705-02.02","GAT","m","SINGLE GUARDRAIL (TYPE 2)",570,{"$f":"200*3.28","v":656},48.5]
["CND431","705M04.04","GAT","EACH","GUARDRAIL TERMINAL (TYPE 21)",580,2,1700]
["CND431","705M04.05","GAT","EACH","GUARDRAIL TERMINAL (TYPE-IN-LINE)",590,2,500]
["CND431","705M04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",600,61,2104]
["CND431","705M08.65","GAT","EACH","ENERGY ABSORBING TERMINAL (PORTABLE)",610,20,8500]
["CND431","706M01","GAT","m","GUARDRAIL REMOVED",620,{"$f":"461*3.28","v":1512.08},6]
["CNG917","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",1270,350,68.5]
["CNG917","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",1280,2357,22]
["CNG917","705-04.03","GAT","EACH","GUARDRAIL TERMINAL (TYPE 13)",1290,2,625]
["CNG917","705-04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",1300,13,2600]
["CNG917","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",1320,6,7000]
["CNH670","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",600,150,17.66]
["CNH670","705-04.04","GAT","EACH","GUARDRAIL TERMINAL (TYPE 21)",610,3,2428.2600000000002]
["CNH670","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",620,2,2980.13]
["CNH654","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",930,53.8,46]
["CNH654","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",940,43.75,20]
["CNH654","705-04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",950,2,2600]
["CNH654","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",960,8,5000]
["CNH654","706-01","GAT","L.F.","GUARDRAIL REMOVED",970,232,2]
["CNH658","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",800,208,55]
["CNH658","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",810,3350,16.5]
["CNH658","705-04.05","GAT","EACH","GUARDRAIL TERMINAL (TYPE-IN-LINE)",820,4,575]
["CNH658","705-04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",830,14,2000]
["CNH658","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",840,2,5500]
["CNH658","706-10.24","GAT","EACH","FLARED END ELEMENT",850,4,50]
["CNJ202","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",620,860,58]
["CNJ202","705-01.04","GAT","L.F.","METAL BEAM GUARD FENCE",630,74,62.75]
["CNJ202","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",640,2000,17.5]
["CNJ202","705-04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",650,28,2250]
["CNJ202","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",660,10,12400]
["CNJ331","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",760,8069,15]
["CNJ331","705-04.03","GAT","EACH","GUARDRAIL TERMINAL (TYPE 13)",770,5,575]
["CNJ331","705-04.04","GAT","EACH","GUARDRAIL TERMINAL (TYPE 21)",780,4,1750]
["CNJ331","705-04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",790,25,2000]
["CNJ331","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",810,12,7200]
["CNJ363","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",1230,9886,15.31]
["CNJ363","705-04.04","GAT","EACH","GUARDRAIL TERMINAL (TYPE 21)",1240,24,1403.19]
["CNJ363","705-04.05","GAT","EACH","GUARDRAIL TERMINAL (TYPE-IN-LINE)",1250,19,408.2]
["CNJ363","705-04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",1260,22,2092.0300000000002]
["CNJ363","705-04.09","GAT","EACH","EARTH PAD FOR TYPE 38 GR END TREATMENT",1270,22,1224.5999999999999]
["CNJ363","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",1280,12,3367.66]
["CNK901","705M01.01","GAT","m","GUARDRAIL AT BRIDGE ENDS",770,2,200]
["CNK901","705-02.02","GAT","m","SINGLE GUARDRAIL (TYPE 2)",780,{"$f":"3082*3.28","v":10108.959999999999},54]
["CNK901","705M04.02","GAT","EACH","GUARDRAIL TERMINAL (TYPE 12)",790,1,600]
["CNK901","705M04.03","GAT","EACH","GUARDRAIL TERMINAL (TYPE 13)",800,1,600]
["CNK901","705M04.05","GAT","EACH","GUARDRAIL TERMINAL (TYPE-IN-LINE)",810,6,600]
["CNK901","705M04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",820,31,2200]
["CNK901","705M08.50","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-2",830,17,5400]
["CNK916","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",780,323,68.180000000000007]
["CNK916","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",790,6644,16.78]
["CNK916","705-04.05","GAT","EACH","GUARDRAIL TERMINAL (TYPE-IN-LINE)",800,3,576.91]
["CNK916","705-04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",810,27,2202.75]
["CNK916","705-08.11","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",820,10,6083.78]
["CNK821","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",840,6154,16]
["CNK821","705-04.03","GAT","EACH","GUARDRAIL TERMINAL (TYPE 13)",850,3,575]
["CNK821","705-04.04","GAT","EACH","GUARDRAIL TERMINAL (TYPE 21)",860,5,1800]
["CNK821","705-04.05","GAT","EACH","GUARDRAIL TERMINAL (TYPE-IN-LINE)",870,8,625]
["CNK821","705-04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",880,36,2210]
["CNK821","705-07.11","GAT","EACH","TRUCK MOUNTED ENERGY ATTENUATOR",890,1,4745]
["CNK821","705-08.11","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",900,10,5150]
["CNK821","706-01","GAT","L.F.","GUARDRAIL REMOVED",910,3040,1]
["CNL258","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",900,135,49]
["CNL258","705-01.04","GAT","L.F.","METAL BEAM GUARD FENCE",910,132,53]
["CNL258","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",920,12366,15]
["CNL258","705-04.05","GAT","EACH","GUARDRAIL TERMINAL (TYPE-IN-LINE)",930,4,500]
["CNL258","705-04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",940,38,1900]
["CNL258","705-08.11","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",950,13,6000]
["CNM019","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",830,2247,16.25]
["CNM019","705-04.03","GAT","EACH","GUARDRAIL TERMINAL (TYPE 13)",840,3,500]
["CNM019","705-04.04","GAT","EACH","GUARDRAIL TERMINAL (TYPE 21)",850,3,1650]
["CNM019","705-04.05","GAT","EACH","GUARDRAIL TERMINAL (TYPE-IN-LINE)",860,7,500]
["CNM019","705-04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",870,2,2050]
["CNM019","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",880,8,6000]
["CNN201","705-01.04","GAT","L.F.","METAL BEAM GUARD FENCE",770,18.75,72.5]
["CNN201","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",780,18.75,20.5]
["CNN201","705-04.04","GAT","EACH","GUARDRAIL TERMINAL (TYPE 21)",790,1,2150]
["CNN201","705-08.11","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",800,2,6325]
["CNN201","706-02.01","GAT","L.F.","GUARDRAIL REMOVED AND RESET",810,75,7]
["CNN201","706-03.01","GAT","EACH","POSTS FURNISHED",820,8,100]
["CNN201","706-03.10","GAT","EACH","POST BLOCKOUTS & BACKUP PLATES",830,8,125]
["CNN201","706-10.26","GAT","EACH","ROUNDED END ELEMENT",840,1,100]
["CNP927","705-01.04","GAT","L.F.","METAL BEAM GUARD FENCE",810,127,77.11]
["CNP927","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",820,1576,17.63]
["CNP927","705-04.04","GAT","EACH","GUARDRAIL TERMINAL (TYPE 21)",830,1,2065.5500000000002]
["CNP927","705-04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",840,11,2148.17]
["CNP927","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",860,15,6389.44]
["CNQ076","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",1240,189,70.040000000000006]
["CNQ076","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",1250,6798,15.76]
["CNQ076","705-04.02","GAT","EACH","GUARDRAIL TERMINAL (TYPE 12)",1260,1,1236]
["CNQ076","705-04.03","GAT","EACH","GUARDRAIL TERMINAL (TYPE 13)",1270,6,592.25]
["CNQ076","705-04.04","GAT","EACH","GUARDRAIL TERMINAL (TYPE 21)",1280,1,1957]
["CNQ076","705-04.05","GAT","EACH","GUARDRAIL TERMINAL (TYPE-IN-LINE)",1290,6,592.25]
["CNQ076","705-04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",1300,15,2060]
["CNQ076","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",1310,8,5045.96]
["CNQ076","706-01","GAT","L.F.","GUARDRAIL REMOVED",1320,885,1.55]
["CNQ172","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",970,54,66.900000000000006]
["CNQ172","705-01.04","GAT","L.F.","METAL BEAM GUARD FENCE",980,69,77]
["CNQ172","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",990,650,17.350000000000001]
["CNQ172","705-04.03","GAT","EACH","GUARDRAIL TERMINAL (TYPE 13)",1000,2,625]
["CNQ172","705-04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",1010,6,2090]
["CNQ172","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",1020,16,6100]
["CNQ297","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",870,243,65]
["CNQ297","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",880,1363,15.6]
["CNQ297","705-04.03","GAT","EACH","GUARDRAIL TERMINAL (TYPE 13)",890,2,575]
["CNQ297","705-04.04","GAT","EACH","GUARDRAIL TERMINAL (TYPE 21)",900,12,2050]
["CNQ297","705-04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",910,3,2200]
["CNQ297","705-08.50","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-2",920,2,7500]
["CNQ297","706-01","GAT","L.F.","GUARDRAIL REMOVED",930,360,1.5]
["CNQ297","705-05.09","GAT","EACH","BOLT SIDE GUIDE",1021,341,50]
["CNQ340","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",670,3,6500]
["CNQ346","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",1130,108,83.66]
["CNQ346","705-01.04","GAT","L.F.","METAL BEAM GUARD FENCE",1140,25,130]
["CNQ346","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",1150,3483,18.510000000000002]
["CNQ346","705-02.03","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2) LONG POST",1155,207,24.56]
["CNQ346","705-04.04","GAT","EACH","GUARDRAIL TERMINAL (TYPE 21)",1160,1,2037]
["CNQ346","705-04.05","GAT","EACH","GUARDRAIL TERMINAL (TYPE-IN-LINE)",1170,7,670]
["CNQ346","705-04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",1180,10,2266]
["CNQ346","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",1200,6,5462]
["CNQ346","706-01","GAT","L.F.","GUARDRAIL REMOVED",1210,5730,1.1100000000000001]
["CNQ346","706-06.03","GAT","L.F.","RADIUS RAIL",1220,138,28.54]
["CNQ346","706-06.05","GAT","L.F.","RADIUS RAIL LONG POST (6-9 FT)",1225,38,27.11]
["CNR040","705-01.04","GAT","L.F.","METAL BEAM GUARD FENCE",730,25,68.25]
["CNR040","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",740,5125,16.54]
["CNR040","705-04.04","GAT","EACH","GUARDRAIL TERMINAL (TYPE 21)",750,5,2310]
["CNR040","705-04.05","GAT","EACH","GUARDRAIL TERMINAL (TYPE-IN-LINE)",760,15,603.75]
["CNR040","705-04.07","GAT","EACH","TAN ENERGY ABSORBING TERM (NCHRP 350, TL3)",770,6,2520]
["CNR040","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",780,8,4725]
["CNR136","705-06.01","GAT","L.F.","W BEAM GR (TYPE 2) MASH TL3",1422,1272,17.850000000000001]
["CNR136","705-06.10","GAT","EACH","GR TERMINALTRAILING END (TYPE 13) MASH TL3",1425,3,835]
["CNR136","705-06.11","GAT","EACH","GR TERMINAL (IN-INLINE) MASH TL3",1426,4,820]
["CNR136","705-06.20","GAT","EACH","TANGENT ENERGY ABSORBING TERM MASH TL-3",1430,3,2465]
["CNR136","705-06.30","GAT","EACH","GR TERMINAL (TYPE 21) MASH TL2",1435,2,2290]
["CNR136","705-20.25","GAT","EACH","TEMPORARY CRASH CUSHION (MASH TL-3)",1445,5,6000]
["CNR277","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",960,216,63.37]
["CNR277","705-06.01","GAT","L.F.","W BEAM GR (TYPE 2) MASH TL3",970,1507,21.2]
["CNR277","705-06.11","GAT","EACH","GR TERMINAL (IN-INLINE) MASH TL3",980,2,735]
["CNR277","705-06.20","GAT","EACH","TANGENT ENERGY ABSORBING TERM MASH TL-3",990,7,2694]
["CNR277","705-06.30","GAT","EACH","GR TERMINAL (TYPE 21) MASH TL2",995,1,2212]
["CNR277","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",1000,11,8000]
["CNR277","706-01","GAT","L.F.","GUARDRAIL REMOVED",1010,2162,1.1000000000000001]
["CNR220","705-02.10","GAT","EACH","GUARDRAIL TRANSITION 27IN TO 31IN",960,6,200]
["CNR220","705-06.01","GAT","L.F.","W BEAM GR (TYPE 2) MASH TL3",970,3093.75,18]
["CNR220","705-06.10","GAT","EACH","GR TERMINALTRAILING END (TYPE 13) MASH TL3",980,5,600]
["CNR220","705-06.11","GAT","EACH","GR TERMINAL (IN-INLINE) MASH TL3",990,1,600]
["CNR220","705-06.20","GAT","EACH","TANGENT ENERGY ABSORBING TERM MASH TL-3",1000,6,2500]
["CNR220","705-06.30","GAT","EACH","GR TERMINAL (TYPE 21) MASH TL2",1010,8,2000]
["CNR220","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",1020,6,4500]
["CNR220","706-01","GAT","L.F.","GUARDRAIL REMOVED",1030,2741,2]
["CNR280","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",540,108,79.599999999999994]
["CNR280","705-06.20","GAT","EACH","TANGENT ENERGY ABSORBING TERM MASH TL-3",550,4,3060]
["CNR280","706-01","GAT","L.F.","GUARDRAIL REMOVED",560,301,10]
["CNR252","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",700,458,59.16]
["CNR252","705-06.01","GAT","L.F.","W BEAM GR (TYPE 2) MASH TL3",710,6370,18.11]
["CNR252","705-06.10","GAT","EACH","GR TERMINALTRAILING END (TYPE 13) MASH TL3",720,11,1018.98]
["CNR252","705-06.20","GAT","EACH","TANGENT ENERGY ABSORBING TERM MASH TL-3",730,11,2499]
["CNR252","705-08.11","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",740,6,4743]
["CNR279","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",990,162,65]
["CNR279","705-04.09","GAT","EACH","EARTH PAD FOR TYPE 38 GR END TREATMENT",1000,22,895]
["CNR279","705-04.10","GAT","EACH","EARTH PAD FOR GUARD RAIL END TREATMENT",1010,2,895]
["CNR279","705-06.01","GAT","L.F.","W BEAM GR (TYPE 2) MASH TL3",1020,7306,21]
["CNR279","705-06.10","GAT","EACH","GR TERMINALTRAILING END (TYPE 13) MASH TL3",1030,1,1040]
["CNR279","705-06.11","GAT","EACH","GR TERMINAL (IN-INLINE) MASH TL3",1040,17,500]
["CNR279","705-06.20","GAT","EACH","TANGENT ENERGY ABSORBING TERM MASH TL-3",1050,22,2450]
["CNR279","705-06.30","GAT","EACH","GR TERMINAL (TYPE 21) MASH TL2",1060,2,2250]
["CNR279","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",1070,6,7500]
["CNR279","706-01","GAT","L.F.","GUARDRAIL REMOVED",1080,10868,4]
["CNR273","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",1190,216,63]
["CNR273","705-01.04","GAT","L.F.","METAL BEAM GUARD FENCE",1200,38,90]
["CNR273","705-06.01","GAT","L.F.","W BEAM GR (TYPE 2) MASH TL3",1210,13656,19]
["CNR273","705-06.10","GAT","EACH","GR TERMINALTRAILING END (TYPE 13) MASH TL3",1220,3,1040]
["CNR273","705-06.11","GAT","EACH","GR TERMINAL (IN-INLINE) MASH TL3",1230,22,500]
["CNR273","705-06.20","GAT","EACH","TANGENT ENERGY ABSORBING TERM MASH TL-3",1240,29,2550]
["CNR273","705-06.30","GAT","EACH","GR TERMINAL (TYPE 21) MASH TL2",1250,5,2300]
["CNR273","705-20.25","GAT","EACH","TEMPORARY CRASH CUSHION (MASH TL-3)",1260,19,4500]
["CNR273","706-01","GAT","L.F.","GUARDRAIL REMOVED",1270,6121,5]
["CNR273","706-06.06","GAT","L.F.","RADIUS RAIL LONG POST (9-12 FT)",1280,300,24.75]
["CNR273","706-10.26","GAT","EACH","ROUNDED END ELEMENT",1290,15,75]
["CNS127","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",950,108,72.5]
["CNS127","705-01.04","GAT","L.F.","METAL BEAM GUARD FENCE",960,435,69]
["CNS127","705-06.01","GAT","L.F.","W BEAM GR (TYPE 2) MASH TL3",970,2297,19]
["CNS127","705-06.10","GAT","EACH","GR TERMINALTRAILING END (TYPE 13) MASH TL3",980,2,1100]
["CNS127","705-06.11","GAT","EACH","GR TERMINAL (IN-INLINE) MASH TL3",990,2,900]
["CNS127","705-06.20","GAT","EACH","TANGENT ENERGY ABSORBING TERM MASH TL-3",1000,12,2650]
["CNS127","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",1010,36,4000]
["CNS182","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",800,108,72.95]
["CNS182","705-01.04","GAT","L.F.","METAL BEAM GUARD FENCE",810,38,72.95]
["CNS182","705-06.01","GAT","L.F.","W BEAM GR (TYPE 2) MASH TL3",820,2938,19]
["CNS182","705-06.10","GAT","EACH","GR TERMINALTRAILING END (TYPE 13) MASH TL3",830,3,1200]
["CNS182","705-06.11","GAT","EACH","GR TERMINAL (IN-INLINE) MASH TL3",840,6,900]
["CNS182","705-06.20","GAT","EACH","TANGENT ENERGY ABSORBING TERM MASH TL-3",850,8,2600]
["CNS182","705-06.30","GAT","EACH","GR TERMINAL (ENERGY ABSORBING) MASH TL2",860,3,2200]
["CNS182","705-20.25","GAT","EACH","TEMPORARY CRASH CUSHION (MASH TL-3)",870,52,4600]
["CNS182","706-01","GAT","L.F.","GUARDRAIL REMOVED",880,2623,1]
["CNT925","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",1010,108,69.5]
["CNT925","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",1020,1621,17.5]
["CNT925","705-06.20","GAT","EACH","TANGENT ENERGY ABSORBING TERM MASH TL-3",1030,10,2525]
["CNT925","705-08.11","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",1040,12,6970]
["CNT925","706-01","GAT","L.F.","GUARDRAIL REMOVED",1050,1843,1.05]
["CNT336","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",1230,663,73.25]
["CNT336","705-04.02","GAT","EACH","GUARDRAIL TERMINAL (TYPE 12)",1240,12,770]
["CNT336","705-06.01","GAT","L.F.","W BEAM GR (TYPE 2) MASH TL3",1250,13207,18.600000000000001]
["CNT336","705-06.10","GAT","EACH","GR TERMINALTRAILING END (TYPE 13) MASH TL3",1260,14,1220]
["CNT336","705-06.20","GAT","EACH","TANGENT ENERGY ABSORBING TERM MASH TL-3",1270,22,2810]
["CNT336","705-06.30","GAT","EACH","GR TERMINAL (ENERGY ABSORBING) MASH TL2",1280,8,2180]
["CNT336","705-08.10","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-2",1290,8,7650]
["CNU032","705-01.01","GAT","L.F.","GUARDRAIL AT BRIDGE ENDS",1340,215,70.5]
["CNU032","705-01.04","GAT","L.F.","METAL BEAM GUARD FENCE",1350,50,70.5]
["CNU032","705-06.01","GAT","L.F.","W BEAM GR (TYPE 2) MASH TL3",1360,15606.25,15.1]
["CNU032","705-06.10","GAT","EACH","GR TERMINALTRAILING END (TYPE 13) MASH TL3",1370,35,1200]
["CNU032","705-06.11","GAT","EACH","GR TERMINAL (IN-INLINE) MASH TL3",1380,41,800]
["CNU032","705-06.20","GAT","EACH","TANGENT ENERGY ABSORBING TERM MASH TL-3",1390,36,2500]
["CNU032","705-06.30","GAT","EACH","GR TERMINAL (ENERGY ABSORBING) MASH TL2",1400,7,2200]
["CNU032","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",1410,76,1000]
["CNU032","706-01","GAT","L.F.","GUARDRAIL REMOVED",1420,2750,1]
["CNU032","706-06.03","GAT","L.F.","RADIUS RAIL",1425,893.75,22.5]
["CNU057","705-06.01","GAT","L.F.","W BEAM GR (TYPE 2) MASH TL3",540,9977,18]
["CNU057","705-06.10","GAT","EACH","GR TERMINALTRAILING END (TYPE 13) MASH TL3",550,25,800]
["CNU057","705-06.11","GAT","EACH","GR TERMINAL (IN-INLINE) MASH TL3",560,36,525]
["CNU057","705-06.20","GAT","EACH","TANGENT ENERGY ABSORBING TERM MASH TL-3",570,29,2600]
["CNU057","705-06.30","GAT","EACH","GR TERMINAL (ENERGY ABSORBING) MASH TL2",580,14,1995]
["CNU057","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",590,2,4000]
["CNU057","706-06.03","GAT","L.F.","RADIUS RAIL",593,1168,21.5]
["CNU922","705-02.10","GAT","EACH","GUARDRAIL TRANSITION 27IN TO 31IN",1470,7,190]
["CNU922","705-04.09","GAT","EACH","EARTH PAD FOR TYPE 38 GR END TREATMENT",1480,2,1221.5899999999999]
["CNU922","705-04.10","GAT","EACH","EARTH PAD FOR GUARD RAIL END TREATMENT",1490,2,1221.5899999999999]
["CNU922","705-06.01","GAT","L.F.","W BEAM GR (TYPE 2) MASH TL-3",1500,7232,24.94]
["CNU922","705-06.10","GAT","EACH","GR TERMINALTRAILING END (TYPE 13) MASH TL-3",1510,16,1297.94]
["CNU922","705-06.11","GAT","EACH","GR TERMINAL (IN-INLINE) MASH TL-3",1520,8,738.05]
["CNU922","705-06.20","GAT","EACH","TANGENT ENERGY ABSORBING TERM MASH TL-3",1530,15,2723.14]
["CNU922","705-06.25","GAT","EACH","THRIE BEAM BRIDGE TRANSITION MASH TL-3",1540,4,2315.94]
["CNU922","705-06.30","GAT","EACH","GR TERMINAL (ENERGY ABSORBING) MASH TL-2",1550,2,2697.69]
["CNU922","705-20.25","GAT","EACH","TEMPORARY CRASH CUSHION (MASH TL-3)",1560,93,6992.29]
["CNU922","706-01","GAT","L.F.","GUARDRAIL REMOVED",1570,7783,6.11]
["CNU922","706-10.80","GAT","EACH","MICHIGAN AND MODIFIED MICHIGAN END SHOE",1580,4,188.33]
["CNV012","705-02.02","GAT","L.F.","SINGLE GUARDRAIL (TYPE 2)",1110,9125,18.600000000000001]
["CNV012","705-04.02","GAT","EACH","GUARDRAIL TERMINAL (TYPE 12)",1120,1,1033.5999999999999]
["CNV012","705-04.05","GAT","EACH","GUARDRAIL TERMINAL (TYPE-IN-LINE)",1130,26,620.16]
["CNV012","705-04.09","GAT","EACH","EARTH PAD FOR TYPE 38 GR END TREATMENT",1140,20,826.88]
["CNV012","705-04.10","GAT","EACH","EARTH PAD FOR GUARD RAIL END TREATMENT",1150,6,775.2]
["CNV012","705-06.01","GAT","L.F.","W BEAM GR (TYPE 2) MASH TL-3",1160,500,20.16]
["CNV012","705-06.20","GAT","EACH","TANGENT ENERGY ABSORBING TERM MASH TL-3",1170,20,25.32]
["CNV012","705-06.30","GAT","EACH","GR TERMINAL (ENERGY ABSORBING) MASH TL-2",1180,6,2377.2800000000002]
["CNV012","705-08.51","GAT","EACH","PORTABLE IMPACT ATTENUATOR NCHRP350 TL-3",1190,16,7441.91]
["CNV012","706-01","GAT","L.F.","GUARDRAIL REMOVED",1210,975,1.03]
["CNV012","706-06.03","GAT","L.F.","RADIUS RAIL",1215,75,23.77]
["CNV012","706-10.26","GAT","EACH","ROUNDED END ELEMENT",1220,18,77.52]

{"sheet":"CLS","index":22,"n_rows":141,"n_cols":22,"rows_kept":141,"cut":false,"hidden":true,"merged":[[0,0,0,1],[1,0,1,1],[2,0,2,1]]}
["Construction Lines and Stakes"]
["vs"]
["Contract Award Amount"]
["Contract Amount","Unit Price","Contract"]
[125537,8386,"CNW229"]
[127803.5,6625,"CNW356"]
[145330,10000,"CNW366"]
[251971,5556,"CNV256"]
[272775.08,7887,"CNV173"]
[291634,7500,"CNV306"]
[296524.60000000003,9480,"CNW325"]
[408231.5,12500,"CNV211"]
[418601.75,1660.81,"CNW262"]
[459032.58,26700,"CNX022"]
[471846.25,13000,"CNW327"]
[481328.5,25000,"CNV064"]
[483810,7000,"CNW218"]
[496482.7,30000,"CNW073"]
[517277.65,9425,"CNW370"]
[523619.45,6500,"CNV132"]
[556078.75,21000,"CNW385"]
[573000,16000,"CNX064"]
[605168.25,15000,"CNW211"]
[630757.89,10098.85,"CNV305"]
[685983,10000,"CNV301"]
[686614.05,8718.7099999999991,"CNW220"]
[722245.85,15000,"CNV265"]
[730645.26,24700,"CNW276"]
[745076.70000000007,7000,"CNW329"]
[807073.55,22000,"CNW078"]
[814041.65,24000,"CNV135"]
[823426.12,3244.16,"CNV275"]
[837418.33000000007,30562.5,"CNW205"]
[872248.86,13700,"CNW312"]
[874385.17,13772.76,"CNW128"]
[889899.95000000007,15000,"CNW083"]
[979574.5,10000,"CNW282"]
[993279,50000,"CNX054"]
[997178.04,25000,"CNW333"]
[1003449.5,35000,"CNV250"]
[1022137.65,31964.19,"CNV065",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3.9999999999999998E-11]
[1073671.3,33093,"CNW052"]
[1083430.8500000001,18500,"CNW226"]
[1097669.71,21985.71,"CNV207"]
[1101263.97,15250,"CNV108"]
[1118709.6100000001,2950.37,"CNW006"]
[1120101.19,8796,"CNX041"]
[1167486.7,30150.75,"CNV098"]
[1182966.24,12000,"CNV290"]
[1197907.98,9600,"CNV276"]
[1199999,25000,"CNW014"]
[1223430.45,25000,"CNV322"]
[1322657.6499999999,25329.15,"CNV145"]
[1328131.8999999999,10250,"CNV259"]
[1391040.03,6250,"CNX040"]
[1396799.2,35000,"CNV902"]
[1435959.26,120000,"CNW917"]
[1483886.73,35200,"CNV096"]
[1484538.76,25000,"CNW111"]
[1512259.7,35000,"CNW909"]
[1524684.35,31000,"CNV077"]
[1553274.25,15000,"CNW263"]
[1601686.35,27000,"CNW070"]
[1645415.96,113452.06,"CNW912"]
[1765096.08,28200,"CNW386"]
[1945828.46,27500,"CNV295"]
[1968343.83,32650,"CNW012"]
[1970738.67,21160,"CNW133"]
[1985058,35000,"CNW307"]
[2072516.68,35000,"CNW348"]
[2124241.5499999998,77000,"CNW345"]
[2173935.16,33000,"CNW299"]
[2184933.17,20664.77,"CNW036"]
[2226886.65,10300,"CNW199"]
[2330894.34,65000,"CNW264"]
[2380374.2999999998,22000,"CNW237"]
[2461723,65000,"CNW341"]
[2475274.41,47705,"CNX073"]
[2494843.1800000002,17750,"CNW069"]
[2584219.34,60000,"CNX903"]
[2683017.13,35000,"CNV303"]
[2817260.25,90000,"CNW151"]
[2976489,45000,"CNW328"]
[3161700.43,175000,"CNW279"]
[3196410.65,17500,"CNW358"]
[3205861.87,61342,"CNW258"]
[3493087.65,5000,"CNV289"]
[3536597.18,41000,"CNW346"]
[3538808.3,120000,"CNW322"]
[3617035.94,51263.43,"CNX033"]
[3739930.52,40000,"CNW153"]
[3812304.2,60000,"CNV344"]
[3939497.21,55850,"CNW074"]
[4069547.63,63000,"CNV061"]
[4153272.09,25500,"CNW373"]
[4233674.0999999996,35000,"CNV269"]
[4699949.63,31150,"CNV230"]
[4822308.96,75000,"CNV150"]
[4833329.3499999996,80000,"CNW275"]
[4838194.57,50000,"CNW269"]
[4855277.46,75000,"CNW212"]
[5042963.3499999996,31400,"CNW001"]
[5104638.47,80000,"CNW132"]
[5137452,18300,"CNW265"]
[5341970,15000,"CNV153"]
[5487640.5999999996,38800,"CNV124"]
[5888289.4800000004,53000,"CNV268"]
[5921705.3600000003,230000,"CNW320"]
[5980903.3200000003,40000,"CNV288"]
[6191582.8700000001,220000,"CNW926"]
[6980098,35000,"CNV915"]
[9321952.1600000001,105000,"CNV312"]
[9399030.6300000008,100000,"CNV066"]
[9399119.1099999994,27385.96,"CNW342"]
[9846894.4700000007,60000,"CNV307"]
[9884012.8800000008,200000,"CNV237"]
[9912391.0600000005,27000,"CNV337"]
[13997072.15,313452.06,"CNW231"]
[14956056.140000001,39500,"CNW046"]
[14992098.99,188000,"CNV203"]
[16681584.59,126220,"CNV914"]
[18767773.940000001,136749,"CNW907"]
[18840591.07,800000,"CNW919"]
[19534844.75,398530.44,"CNV010"]
[21166331.899999999,40000,"CNW075"]
[28637629,319670,"CNV176"]
[29718879.300000001,300000,"CNW110"]
[29734482.550000001,330000,"CNV282"]
[30875122.710000001,284868.38,"CNV012"]
[31959341.07,368000,"CNV183"]
[38381574.079999998,750000,"CNW134"]
[39602652.649999999,592376.01,"CNV284"]
[49299885.590000004,758566.12,"CNV257"]
[50280578.07,285442.5,"CNW068"]
[53992362.200000003,503600,"CNV130"]
[66969669.710000001,325000,"CNV233"]
[71830149.920000002,710500,"CMGC04"]
[85391056.980000004,825000,"CNV300"]
[110644798.5,1972393.1,"CNW055"]
[135971408.03,2650000,"CNW181"]
[160226914.61000001,2000000,"CNV281"]

{"sheet":"SUP 2022","index":23,"n_rows":53,"n_cols":20,"rows_kept":53,"cut":false,"hidden":true,"merged":[[1,12,1,13],[1,14,1,15],[1,2,1,3],[1,4,1,5],[1,6,1,7],[1,8,1,9],[1,10,1,11]]}
[1,{"$f":"A1+1","v":2},{"$f":"B1+1","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20]
[null,null,"R1",null,"R2",null,"R3",null,"R4",null,"Statewide",null,"AUP",null,"AQ"]
["Item Number","Description","AUP","AQ","AUP","AQ","AUP","AQ","AUP","AQ","AUP","AQ","Min","Max","Min","Max","Slope","Input","SUP","Y-Intercept"]
["402-01","BITUMINOUS MATERIAL FOR PRIME COAT (PC)",552.08000000000004,251.91,1110,24.52,992.7,24.06,1020,24.93,668.09,76.84,{"$f":"MIN(C4,E4,G4,I4,K4)","v":552.08000000000004},{"$f":"MAX(C4,E4,G4,I4,K4)","v":1110},{"$f":"IFERROR(VLOOKUP(N4,C:D,2,0),0)+IFERROR(VLOOKUP(N4,E:F,2,0),0)+IFERROR(VLOOKUP(N4,G:H,2,0),0)+IFERROR(VLOOKUP(N4,I:J,2,0),0)+IFERROR(VLOOKUP(N4,K:L,2,0),0)","v":24.52},{"$f":"IFERROR(VLOOKUP(M4,C:D,2,0),0)+IFERROR(VLOOKUP(M4,E:F,2,0),0)+IFERROR(VLOOKUP(M4,G:H,2,0),0)+IFERROR(VLOOKUP(M4,I:J,2,0),0)+IFERROR(VLOOKUP(M4,K:L,2,0),0)","v":251.91},{"$f":"IFERROR(IF((N4-M4)/(O4-P4)>0,0,(N4-M4)/(O4-P4)),0)","v":-2.4535819517129163},{"$f":"IFERROR(VLOOKUP(A4,'Finalize Items'!B:H,6,0),0)","v":0},{"$f":"IF(Q4=0,0,IF((R4*Q4+T4)<M4,M4,(R4*Q4+T4)))","v":1170.1618294560008},{"$f":"N4+Q4*(-1)*O4","v":1170.1618294560008}]
["402-02","AGGREGATE FOR COVER MATERIAL (PC)",262.69,2.23,165.5,85.56,56.22,83.52,53.24,84.57,72.239999999999995,72.05,{"$f":"MIN(C5,E5,G5,I5,K5)","v":53.24},{"$f":"MAX(C5,E5,G5,I5,K5)","v":262.69},{"$f":"IFERROR(VLOOKUP(N5,C:D,2,0),0)+IFERROR(VLOOKUP(N5,E:F,2,0),0)+IFERROR(VLOOKUP(N5,G:H,2,0),0)+IFERROR(VLOOKUP(N5,I:J,2,0),0)+IFERROR(VLOOKUP(N5,K:L,2,0),0)","v":2.23},{"$f":"IFERROR(VLOOKUP(M5,C:D,2,0),0)+IFERROR(VLOOKUP(M5,E:F,2,0),0)+IFERROR(VLOOKUP(M5,G:H,2,0),0)+IFERROR(VLOOKUP(M5,I:J,2,0),0)+IFERROR(VLOOKUP(M5,K:L,2,0),0)","v":84.57},-2.5437211561816859,{"$f":"IFERROR(VLOOKUP(A5,'Finalize Items'!B:H,6,0),0)","v":0},{"$f":"IF(Q5=0,0,IF((R5*Q5+T5)<M5,M5,(R5*Q5+T5)))","v":268.36249817828514},{"$f":"N5+Q5*(-1)*O5","v":268.36249817828514}]
["403-01","BITUMINOUS MATERIAL FOR TACK COAT (TC)",821.01,112.07,878.1,9.24,878,59,996.61,26.87,861.05,59.5,821.01,996.61,26.87,112.07,-2.0610328638497659,{"$f":"IFERROR(VLOOKUP(A6,'Finalize Items'!B:H,6,0),0)","v":0},1051.9899530516432,1051.9899530516432]
["411-01.07","ACS MIX (PG64-22) GRADING E SHOULDER",97.5,2799.3,121.63,1792.75,null,null,120.63,1601.61,108.95,2120.34,97.5,121.63,1792.75,2799.3,-2.3972977000645761E-2,{"$f":"IFERROR(VLOOKUP(A7,'Finalize Items'!B:H,6,0),0)","v":0},164.60755451790769,164.60755451790769]
["411-01.10","ACS MIX(PG64-22) GRADING D",156.87,1490.79,136.59,2001,103.09,3691.07,151.49,1907.1,122.29,2551.38,103.09,156.87,1490.79,3691.07,-2.4442343701710691E-2,{"$f":"IFERROR(VLOOKUP(A8,'Finalize Items'!B:H,6,0),0)","v":0},193.30840156707328,193.30840156707328]
["411-02.10","ACS MIX(PG70-22) GRADING D",125.39,7152.79,144.62,4073.37,112.03,7487.69,177.41,1848.11,125.39,5488.21,112.03,177.41,1848.11,7487.69,-1.1593061894680099E-2,{"$f":"IFERROR(VLOOKUP(A9,'Finalize Items'!B:H,6,0),0)","v":0},198.83525361817723,198.83525361817723]
["411-03.10","ACS MIX(PG76-22) GRADING D",144.57,10233,141.47,10577.22,145.49,12169.18,147.38,3525.86,141.49,9591.09,141.47,147.38,3525.86,10577.22,-8.3813618933085217E-4,{"$f":"IFERROR(VLOOKUP(A10,'Finalize Items'!B:H,6,0),0)","v":0},150.33515086451408,150.33515086451408]
["411-(01 & 02 & 03).10","ACS MIX(ALL GRADES) GRADING D",{"$f":"((C8*D8)+(C9*D9)+(C10*D10))/(SUM(D8:D10))","v":138.27363724784891},{"$f":"AVERAGE(D8:D10)","v":6292.1933333333336},{"$f":"((E8*F8)+(E9*F9)+(E10*F10))/(SUM(F8:F10))","v":141.65414070368053},{"$f":"AVERAGE(F8:F10)","v":5550.53},{"$f":"((G8*H8)+(G9*H9)+(G10*H10))/(SUM(H8:H10))","v":128.05636451010238},{"$f":"AVERAGE(H8:H10)","v":7782.6466666666674},{"$f":"((I8*J8)+(I9*J9)+(I10*J10))/(SUM(J8:J10))","v":156.07884842475079},{"$f":"AVERAGE(J8:J10)","v":2427.0233333333331},{"$f":"((K8*L8)+(K9*L9)+(K10*L10))/(SUM(L8:L10))","v":133.699791284284},{"$f":"AVERAGE(L8:L10)","v":5876.8933333333334},128.05636451010238,156.07884842475079,2427.0233333333331,7782.6466666666674,-5.2323477904498627E-3,{"$f":"IFERROR(VLOOKUP(A11,'Finalize Items'!B:H,6,0),0)","v":0},168.77787860028772,168.77787860028772]
["307-01.20","AGGREGATE (PG64-22)(BPMB-HM) GRADING A-S MIX",null,null,124.7,5160.3999999999996,null,null,135.04,687.14,126.32,2551,124.7,135.04,687.14,5160.3999999999996,-2.3115133034967766E-3,{"$f":"IFERROR(VLOOKUP(A12,'Finalize Items'!B:H,6,0),0)","v":0},136.62833325136478,136.62833325136478]
["307-01.21","AGGREGATE (PG70-22)(BPMB-HM) GRADING A-S MIX",180.08,522.66999999999996,215.65,279.60000000000002,117.12,7007.33,115.29,1906.43,119.31,2478.9299999999998,115.29,215.65,279.60000000000002,1906.43,-6.1690526975774977E-2,{"$f":"IFERROR(VLOOKUP(A13,'Finalize Items'!B:H,6,0),0)","v":0},232.8986713424267,232.8986713424267]
["307-01.22","AGGREGATE (PG76-22)(BPMB-HM) GRADING A-S MIX",247.9,161,null,null,113.14,2126,115.09,2265.75,122.37,1925.14,113.14,247.9,161,2126,-6.8580152671755726E-2,{"$f":"IFERROR(VLOOKUP(A14,'Finalize Items'!B:H,6,0),0)","v":0},258.94140458015266,258.94140458015266]
["307-01.(20 & 21 & 22)","AGGREGATE (ALL GRADES)(BPMB-HM) GRADING A-S MIX",{"$f":"((C12*D12)+(C13*D13)+(C14*D14))/(SUM(D12:D14))","v":196.05118492840114},{"$f":"AVERAGE(D12:D14)","v":341.83499999999998},{"$f":"((E12*F12)+(E13*F13)+(E14*F14))/(SUM(F12:F14))","v":129.3745625},{"$f":"AVERAGE(F12:F14)","v":2720},{"$f":"((G12*H12)+(G13*H13)+(G14*H14))/(SUM(H12:H14))","v":116.19356024582493},{"$f":"AVERAGE(H12:H14)","v":4566.665},{"$f":"((I12*J12)+(I13*J13)+(I14*J14))/(SUM(J12:J14))","v":117.98952688853585},{"$f":"AVERAGE(J12:J14)","v":1619.7733333333333},{"$f":"((K12*L12)+(K13*L13)+(K14*L14))/(SUM(L12:L14))","v":122.72814509415434},{"$f":"AVERAGE(L12:L14)","v":2318.356666666667},116.19356024582493,196.05118492840114,341.83499999999998,4566.665,-1.8901973495401285E-2,{"$f":"IFERROR(VLOOKUP(A15,'Finalize Items'!B:H,6,0),0)","v":0},202.51254103820165,202.51254103820165]
["303-01","MINERAL AGGREGATE, TYPE A BASE, GRADING D",34.21,10619.14,35.44,3613.94,34.25,6176.58,39.83,9418.68,35.409999999999997,6878.83,34.21,39.83,9418.68,10619.14,-4.6815387434816667E-3,{"$f":"IFERROR(VLOOKUP(A16,'Finalize Items'!B:H,6,0),0)","v":0},83.923915332455906,83.923915332455906]
["307-01.08","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING B-M2",166.04,465.23,121.47,1082.06,121.19,423.8,122.78,1765.46,126.52,801.9,121.19,166.04,5256.8600000000006,423.8,0,{"$f":"IFERROR(VLOOKUP(A17,'Finalize Items'!B:H,6,0),0)","v":0},0,166.04]
["307-03.08","ASPHALT CONCRETE MIX (PG76-22) (BPMB-HM) GRADING B-M2",86.87,10955.71,107.43,6778.5,101.12,5289.61,166.04,4791.63,92.36,5882.66,86.87,166.04,5256.8600000000006,10955.71,-1.3892276511927846E-2,{"$f":"IFERROR(VLOOKUP(A18,'Finalize Items'!B:H,6,0),0)","v":0},239.069752704493,239.069752704493]
["307-02.08","ASPHALT CONCRETE MIX (PG70-22) (BPMB-HM) GRADING B-M2",92.42,3578.94,123.78,1884.08,117.11,1828.17,145.6,1182.5,117.11,1828.17,92.42,145.6,1182.5,3578.94,-2.2191250354692792E-2,{"$f":"IFERROR(VLOOKUP(A19,'Finalize Items'!B:H,6,0),0)","v":0},171.84115354442423,171.84115354442423]
["307-(01 & 02 & 03).08","ASPHALT CONCRETE MIX (ALL GRADES) (BPMB-HM) GRADING B-M2",{"$f":"((C17*D17)+(C18*D18)+(C19*D19))/(SUM(D17:D19))","v":90.64972197777584},{"$f":"AVERAGE(D17:D19)","v":4999.96},{"$f":"((E17*F17)+(E18*F18)+(E19*F19))/(SUM(F17:F19))","v":112.15021854065415},{"$f":"AVERAGE(F17:F19)","v":3248.2133333333331},{"$f":"((G17*H17)+(G18*H18)+(G19*H19))/(SUM(H17:H19))","v":106.12400503607998},{"$f":"AVERAGE(H17:H19)","v":2513.86},{"$f":"((I17*J17)+(I18*J18)+(I19*J19))/(SUM(J17:J19))","v":153.04911810573947},{"$f":"AVERAGE(J17:J19)","v":2579.8633333333332},{"$f":"((K17*L17)+(K18*L18)+(K19*L19))/(SUM(L17:L19))","v":100.89311587469591},{"$f":"AVERAGE(L17:L19)","v":2837.5766666666664},90.64972197777584,153.04911810573947,2579.8633333333332,4999.96,-2.5783844499860317E-2,{"$f":"IFERROR(VLOOKUP(A20,'Finalize Items'!B:H,6,0),0)","v":0},219.56791312329744,219.56791312329744]
["307-02.01","ASPHALT CONCRETE MIX (PG70-22) (BPMB-HM) GRADING A",86.73,7801.13,125.61,1118.76,105.4,3483.75,121.08,1927.35,105.4,3483.75,86.73,125.61,1118.76,7801.13,-5.8182950061130998E-3,{"$f":"IFERROR(VLOOKUP(A21,'Finalize Items'!B:H,6,0),0)","v":0},132.11927572103909,132.11927572103909]
["307-03.01","ASPHALT CONCRETE MIX (PG76-22) (BPMB-HM) GRADING A",184.53,506,null,null,114.7,6471.68,110.7,6906.73,114.7,6471.68,110.7,184.53,506,6906.73,-1.1534621832197266E-2,{"$f":"IFERROR(VLOOKUP(A22,'Finalize Items'!B:H,6,0),0)","v":0},190.36651864709182,190.36651864709182]
["307-01.01","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING A",206.46,417.18,105.27,2432.83,121.73,986.2,126.69,785.78,121.73,986.2,105.27,206.46,417.18,2432.83,-5.0202168035125158E-2,{"$f":"IFERROR(VLOOKUP(A23,'Finalize Items'!B:H,6,0),0)","v":0},227.40334046089353,227.40334046089353]
["307-(01, 02, 03).01","ASPHALT CONCRETE MIX (ALL GRADES) (BPMB-HM) GRADING A",{"$f":"((C21*D21)+(C22*D22)+(C23*D23))/(SUM(D21:D23))","v":98.127550224602288},{"$f":"AVERAGE(D21:D23)","v":2908.1033333333339},{"$f":"((E21*F21)+(E22*F22)+(E23*F23))/(SUM(F21:F23))","v":111.67715240216353},{"$f":"AVERAGE(F21:F23)","v":1775.7950000000001},{"$f":"((G21*H21)+(G22*H22)+(G23*H23))/(SUM(H21:H23))","v":112.3725689865221},{"$f":"AVERAGE(H21:H23)","v":3647.2100000000005},{"$f":"((I21*J21)+(I22*J22)+(I23*J23))/(SUM(J21:J23))","v":114.08575771372971},{"$f":"AVERAGE(J21:J23)","v":3206.6200000000003},{"$f":"((K21*L21)+(K22*L22)+(K23*L23))/(SUM(L21:L23))","v":112.3725689865221},{"$f":"AVERAGE(L21:L23)","v":3647.2100000000005},98.127550224602288,114.08575771372971,3206.6200000000003,2908.1033333333339,0,{"$f":"IFERROR(VLOOKUP(A24,'Finalize Items'!B:H,6,0),0)","v":0},0,114.08575771372971]
["313-03","TREATED PERMEABLE BASE",111.64,1050.78,null,null,31.79,16780.060000000001,34.49,15459.8,35.950000000000003,10827.52,31.79,111.64,1050.78,16780.060000000001,-5.0765197135533213E-3,{"$f":"IFERROR(VLOOKUP(A25,'Finalize Items'!B:H,6,0),0)","v":0},116.97430538460756,116.97430538460756]
["501-01.03","PORTLAND CEMENT CONCRETE PAVEMENT (PLAIN) 10\"",239.22,788.43,null,null,163.72,13044.04,141.33000000000001,13880,159.09,8921.77,141.33000000000001,239.22,788.43,13880,-7.4773308319781347E-3,{"$f":"IFERROR(VLOOKUP(A26,'Finalize Items'!B:H,6,0),0)","v":0},245.11535194785651,245.11535194785651]
["604-01.01","CLASS A CONCRETE (ROADWAY)",1170,750.29,1040,23.8,1270,152.5,911.78,996.44,1010,579.63,911.78,1270,152.5,996.44,-0.42446145460577767,{"$f":"IFERROR(VLOOKUP(A27,'Finalize Items'!B:H,6,0),0)","v":0},1334.7303718273811,1334.7303718273811]
["701-01.01","CONCRETE SIDEWALK (4 \")",11.75,1637,9.6300000000000008,10507.75,9.6,2257.67,9.33,12816.78,9.51,8814.02,9.33,11.75,1637,12816.78,-2.1646222018680152E-4,{"$f":"IFERROR(VLOOKUP(A28,'Finalize Items'!B:H,6,0),0)","v":0},12.104348654445793,12.104348654445793]
["702-03","CONCRETE COMBINED CURB & GUTTER",754.15,47.13,600.39,210.25,476.92,408.91,537.34,335.67,527.89,252.62,476.92,754.15,47.13,408.91,-0.76629443308087775,{"$f":"IFERROR(VLOOKUP(A29,'Finalize Items'!B:H,6,0),0)","v":0},790.26545663110176,790.26545663110176]
["711-05.71","51IN SINGLE SLOPE CONCRETE BARRIER WALL",302.17,55,null,null,276.8,2570,166.02,2215.12,214.54,2147.79,166.02,302.17,55,2215.12,-6.3028905801529547E-2,{"$f":"IFERROR(VLOOKUP(A30,'Finalize Items'!B:H,6,0),0)","v":0},305.63658981908412,305.63658981908412]
["712-02.02","INTERCONNECTED PORTABLE BARRIER RAIL",53.1,5090.6899999999996,38.97,1406.7,44.58,6302.77,48.46,4839.0200000000004,47.1,4420.45,38.97,53.1,5090.6899999999996,1406.7,0,{"$f":"IFERROR(VLOOKUP(A31,'Finalize Items'!B:H,6,0),0)","v":0},0,53.1]
["203-03","BORROW EXCAVATION (UNCLASSIFIED)",63.8,976,38.5,2198.1999999999998,17.690000000000001,36805.300000000003,9.6199999999999992,87002.69,13.22,41996.13,9.6199999999999992,63.8,976,87002.69,-6.2980454089306469E-4,{"$f":"IFERROR(VLOOKUP(A32,'Finalize Items'!B:H,6,0),0)","v":0},64.414689231911623,64.414689231911623]
["203-01","ROAD & DRAINAGE EXCAVATION (UNCLASSIFIED)",11.34,72076.679999999993,28.89,8919.93,18.440000000000001,67350.710000000006,7.93,58534.36,14.06,54480.15,7.93,28.89,8919.93,60989.33,-4.0253968741717786E-4,{"$f":"IFERROR(VLOOKUP(A33,'Finalize Items'!B:H,6,0),0)","v":0},32.480625833983105,32.480625833983105]
["203-02.01","BORROW EXCAVATION (GRADED SOLID ROCK)",33.840000000000003,16782.13,37,2120,27.68,76642.42,59.8,5380,28.65,47223.38,27.68,59.8,5380,76642.42,-4.5072844845852835E-4,{"$f":"IFERROR(VLOOKUP(A34,'Finalize Items'!B:H,6,0),0)","v":0},62.224919052706881,62.224919052706881]
["105-01","CONSTRUCTION STAKES, LINES AND GRADES",89270,1,77710,1,173450,1,314340,1,157490,1,77710,314340,1,1,{"$f":"IFERROR(IF((N35-M35)/(O35-P35)>0,0,(N35-M35)/(O35-P35)),0)","v":0},{"$f":"IFERROR(VLOOKUP(A35,'Finalize Items'!B:H,6,0),0)","v":1},0]
["710-02","Aggregate Underdrains (with pipe)",12.47,9663.89,11.12,4013.55,15.5,953.4,12.25,6630.23,12.2,6044.65,11.12,{"$f":"MAX(C36,E36,G36,I36,K36)","v":15.5},953.4,4013.55,-1.4313023871378855E-3,{"$f":"IFERROR(VLOOKUP(A36,'Finalize Items'!B:H,6,0),0)","v":0},16.864603695897259,{"$f":"N36+Q36*(-1)*O36","v":16.864603695897259}]
["611-12.02","CATCH BASINS, TYPE 12, > 4' - 8' DEPTH",null,null,7710,5.64,13750,37.880000000000003,6180,20.25,11530,19.39,6180,13750,37.880000000000003,20.25,0,{"$f":"IFERROR(VLOOKUP(A37,'Finalize Items'!B:H,6,0),0)","v":0},0,13750]
["611-07.01","CLASS A CONCRETE (PIPE ENDWALLS)",1640,36.549999999999997,2060,4.53,1780,12.16,1.39,8.3000000000000007,1700,14.92,1.39,2060,4.53,8.3000000000000007,-546.0503978779841,{"$f":"IFERROR(VLOOKUP(A38,'Finalize Items'!B:H,6,0),0)","v":0},4533.6083023872679,4533.6083023872679]
["611-07.02","STEEL BAR REINFORCEMENT (PIPE ENDWALLS)",3.62,880.91,5.57,301,4.05,422.94,3.44,380.4,3.96,482.56,3.44,5.57,301,380.4,-2.6826196473551649E-2,{"$f":"IFERROR(VLOOKUP(A39,'Finalize Items'!B:H,6,0),0)","v":0},13.644685138539046,13.644685138539046]
["611-42.02","CATCH BASINS, TYPE 42, > 4' - 8' DEPTH",11670,2.25,8880,2,12480,4.2699999999999996,null,null,12120,3.53,8880,12480,4.2699999999999996,2,0,{"$f":"IFERROR(VLOOKUP(A40,'Finalize Items'!B:H,6,0),0)","v":0},0,12480]
["611-14.02","CATCH BASINS, TYPE 14, > 4' - 8' DEPTH",null,null,9940,2.67,17590,2.38,9150,4,12410,2.75,9150,17590,2.38,4,-5209.8765432098762,{"$f":"IFERROR(VLOOKUP(A41,'Finalize Items'!B:H,6,0),0)","v":0},29989.506172839505,29989.506172839505]
["607-05.02","24\" CONCRETE PIPE CULVERT (CLASS III)",129.69,176.78,173.02,210.71,157.01,298.45999999999998,102.05,619.36,128.35,343.98,102.05,173.02,210.71,619.36,-0.17366939924140468,{"$f":"IFERROR(VLOOKUP(A42,'Finalize Items'!B:H,6,0),0)","v":0},209.61387911415639,209.61387911415639]
["415-01.02","COLD PLANING BITUMINOUS PAVEMENT",7.93,2454.9699999999998,7.82,6125.19,6.85,3715,8.3000000000000007,5587.78,7.85,4113.3599999999997,6.85,8.3000000000000007,5587.78,3715,0,{"$f":"IFERROR(VLOOKUP(A43,'Finalize Items'!B:H,6,0),0)","v":0},0,8.3000000000000007]
["202-03.01","REMOVAL OF ASPHALT PAVEMENT",21.29,740.63,3.94,17385,13.63,28865,30,1234.7,15.41,5323.07,3.94,30,1234.7,17385,-1.6135923171705789E-3,{"$f":"IFERROR(VLOOKUP(A44,'Finalize Items'!B:H,6,0),0)","v":0},31.992302434010515,31.992302434010515]
["202-03","REMOVAL OF RIGID PAVEMENT",109.05,116.25,42.27,155,16.190000000000001,916,27.86,1577.53,28.33,1016.79,16.190000000000001,109.05,116.25,916,-0.11611128477649266,{"$f":"IFERROR(VLOOKUP(A45,'Finalize Items'!B:H,6,0),0)","v":0},122.54793685526727,122.54793685526727]
["801-01","SEEDING (WITH MULCH)",51.66,263.69,98.17,11.93,54.75,328.24,40.36,88.22,53.46,202.14,40.36,98.17,11.93,88.22,-0.75776641761698793,{"$f":"IFERROR(VLOOKUP(A46,'Finalize Items'!B:H,6,0),0)","v":0},107.21015336217067,107.21015336217067]
["801-01.07","TEMPORARY SEEDING (WITH MULCH)",33.94,289.36,52.83,49.88,32.549999999999997,1136.49,28.66,166.37,32.67,532.30999999999995,28.66,52.83,49.88,166.37,-0.20748562108335475,{"$f":"IFERROR(VLOOKUP(A47,'Finalize Items'!B:H,6,0),0)","v":0},63.179382779637734,63.179382779637734]
["801-02","SEEDING (WITHOUT MULCH)",35.21,318.47000000000003,42.48,36.67,43.34,175.74,65.98,93.47,39.25,204.75,35.21,65.98,93.47,318.47000000000003,-0.13675555555555555,{"$f":"IFERROR(VLOOKUP(A48,'Finalize Items'!B:H,6,0),0)","v":0},78.762541777777784,78.762541777777784]
["716-12.02","ENHANCED FLAT THERMO P.M. (6IN) ",6201.25,16.23,5787.01,17.86,6161.06,19.489999999999998,7065.2,15.76,6217.76,17.73,5787.01,7065.2,15.76,17.86,-608.66190476190468,{"$f":"IFERROR(VLOOKUP(A49,'Finalize Items'!B:H,6,0),0)","v":0},16657.711619047619,16657.711619047619]
["709-05.05","Machined Rip-Rap (Class A-3)",72.8,293.68,51.99,177,57.77,303.7,56.76,423.29,59.84,308.45999999999998,51.99,72.8,293.68,177,0,{"$f":"IFERROR(VLOOKUP(A50,'Finalize Items'!B:H,6,0),0)","v":0},0,72.8]
["705-01.01","GUARDRAIL AT BRIDGE ENDS",68,375,85,270,79.5,350,122.04,91.3,88.84,194.31,68,122.04,91.3,375,-0.19048290447655977,{"$f":"IFERROR(VLOOKUP(A51,'Finalize Items'!B:H,6,0),0)","v":0},139.43108917870993,139.43108917870993]
["705-06.01 ","W Beam GR (Type 2) Mash TL3",32.97,2790.58,34.81,1255.73,36.770000000000003,2115.98,35.590000000000003,1914,34.979999999999997,2000.99,32.97,36.770000000000003,2115.98,2790.58,-5.6329676845538164E-3,{"$f":"IFERROR(VLOOKUP(A52,'Finalize Items'!B:H,6,0),0)","v":0},48.689246961162183,48.689246961162183]
["705-06.20 ","Tangent Energy Absorbing Term Mash TL-3",3040,30.88,3460,23.22,3290,27.02,3700,14.69,3340,23.14,3040,3700,14.69,30.88,-40.765904879555286,{"$f":"IFERROR(VLOOKUP(A53,'Finalize Items'!B:H,6,0),0)","v":0},4298.8511426806672,4298.8511426806672]

{"sheet":"Inflated Cost","index":24,"n_rows":57,"n_cols":19,"rows_kept":57,"cut":false,"hidden":false,"merged":[[56,1,56,2],[55,1,55,3],[1,0,1,7],[4,0,4,7],[7,0,7,7],[11,0,11,7],[25,0,25,7],[39,0,39,7]]}
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Threshold","Round to"]
[{"$f":"CONCATENATE(\"COST ESTIMATE SUMMARY (\",YEAR(TODAY()),\") - DESIGN-BID-BUILD\")","v":"COST ESTIMATE SUMMARY (2025) - DESIGN-BID-BUILD"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,"TIER 1","<",1000,1]
["PIN","Project Type of Work","Starting Inflation","Preliminary Engineering:","Right-of-Way:","Utilities:","Construction:",{"$f":"CONCATENATE(\"Total Project Cost (\", YEAR(TODAY()), \"):\")","v":"Total Project Cost (2025):"},null,null,null,null,null,null,null,"TIER 2","<",10000,10]
[{"$f":"IF(Tool!H55=\"\",\"\",Tool!H55)","v":""},{"$f":"IF('Cost Estimate'!C4=\"\",\"\",'Cost Estimate'!C4)","v":""},{"$f":"D57","v":5.5E-2},{"$f":"'Cost Estimate'!J54","v":0},{"$f":"'Cost Estimate'!J50","v":0},{"$f":"'Cost Estimate'!J51","v":0},{"$f":"'Cost Estimate'!J38","v":0},{"$f":"'Cost Estimate'!J57","v":0},null,null,null,null,null,null,null,"TIER 3","<",100000,100]
[{"$f":"CONCATENATE(\"COST ESTIMATE SUMMARY (\",YEAR(TODAY()),\") - DESIGN-BUILD\")","v":"COST ESTIMATE SUMMARY (2025) - DESIGN-BUILD"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,"TIER 4","<",1000000,1000]
["PIN","Project Type of Work","Starting Inflation","Preliminary Engineering:","Right-of-Way:","Utilities:","Construction:",{"$f":"CONCATENATE(\"Total Project Cost (\", YEAR(TODAY()), \"):\")","v":"Total Project Cost (2025):"},null,null,null,null,null,null,null,"TIER 5","<",10000000,10000]
[{"$f":"IF(Tool!H55=\"\",\"\",Tool!H55)","v":""},{"$f":"IF('Cost Estimate'!C4=\"\",\"\",'Cost Estimate'!C4)","v":""},{"$f":"D57","v":5.5E-2},{"$f":"'Cost Estimate'!J55","v":0},{"$f":"'Cost Estimate'!J50","v":0},{"$f":"'Cost Estimate'!J51","v":0},{"$f":"'Cost Estimate'!J38","v":0},{"$f":"'Cost Estimate'!J58","v":0},null,null,null,null,null,null,null,"TIER 6","<",100000000,100000]
[{"$f":"CONCATENATE(\"COST ESTIMATE SUMMARY (\",YEAR(TODAY()),\") - CMGC & HIGH RISK SCENARIOS\")","v":"COST ESTIMATE SUMMARY (2025) - CMGC & HIGH RISK SCENARIOS"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,"TIER 7",">",100000000,1000000]
["PIN","Project Type of Work","Starting Inflation","Preliminary Engineering:","Right-of-Way:","Utilities:","Construction:",{"$f":"CONCATENATE(\"Total Project Cost (\", YEAR(TODAY()), \"):\")","v":"Total Project Cost (2025):"}]
[{"$f":"IF(Tool!H55=\"\",\"\",Tool!H55)","v":""},{"$f":"IF('Cost Estimate'!C4=\"\",\"\",'Cost Estimate'!C4)","v":""},{"$f":"D57","v":5.5E-2},{"$f":"'Cost Estimate'!J56","v":0},{"$f":"'Cost Estimate'!J50","v":0},{"$f":"'Cost Estimate'!J51","v":0},{"$f":"'Cost Estimate'!J44","v":0},{"$f":"'Cost Estimate'!J59","v":0}]
[]
["DESIGN-BID-BUILD - INFLATED COST"]
["No. of Years","Year","Inflation","Preliminary Engineering:","Right-of-Way:","Utilities:","Construction:","Total Inflated Project Cost"]
[0,{"$f":"YEAR(TODAY())","v":2025},null,{"$f":"$D$4","v":0},{"$f":"E4","v":0},0,{"$f":"G4","v":0},0]
[1,{"$f":"B14+1","v":2026},{"$f":"$D$57","v":5.5E-2},{"$f":"IF(I15<=$R$2,MROUND(I15,$S$2),IF(AND(I15>$R$2,I15<$R$3),MROUND(I15,$S$3),IF(AND(I15>$R$3,I15<$R$4),MROUND(I15,$S$4),IF(AND(I15>$R$4,I15<$R$5),MROUND(I15,$S$5),IF(AND(I15>$R$5,I15<$R$6),MROUND(I15,$S$6),IF(AND(I15>$R$6,I15<$R$7),MROUND(I15,$S$7),IF(I15>=$R$8,MROUND(I15,$S$8))))))))","v":0},{"$f":"IF(J15<=$R$2,MROUND(J15,$S$2),IF(AND(J15>$R$2,J15<$R$3),MROUND(J15,$S$3),IF(AND(J15>$R$3,J15<$R$4),MROUND(J15,$S$4),IF(AND(J15>$R$4,J15<$R$5),MROUND(J15,$S$5),IF(AND(J15>$R$5,J15<$R$6),MROUND(J15,$S$6),IF(AND(J15>$R$6,J15<$R$7),MROUND(J15,$S$7),IF(J15>=$R$8,MROUND(J15,$S$8))))))))","v":0},{"$f":"IF(K15<=$R$2,MROUND(K15,$S$2),IF(AND(K15>$R$2,K15<$R$3),MROUND(K15,$S$3),IF(AND(K15>$R$3,K15<$R$4),MROUND(K15,$S$4),IF(AND(K15>$R$4,K15<$R$5),MROUND(K15,$S$5),IF(AND(K15>$R$5,K15<$R$6),MROUND(K15,$S$6),IF(AND(K15>$R$6,K15<$R$7),MROUND(K15,$S$7),IF(K15>=$R$8,MROUND(K15,$S$8))))))))","v":0},{"$f":"IF(L15<=$R$2,MROUND(L15,$S$2),IF(AND(L15>$R$2,L15<$R$3),MROUND(L15,$S$3),IF(AND(L15>$R$3,L15<$R$4),MROUND(L15,$S$4),IF(AND(L15>$R$4,L15<$R$5),MROUND(L15,$S$5),IF(AND(L15>$R$5,L15<$R$6),MROUND(L15,$S$6),IF(AND(L15>$R$6,L15<$R$7),MROUND(L15,$S$7),IF(L15>=$R$8,MROUND(L15,$S$8))))))))","v":0},{"$f":"IF(M15<=$R$2,MROUND(M15,$S$2),IF(AND(M15>$R$2,M15<$R$3),MROUND(M15,$S$3),IF(AND(M15>$R$3,M15<$R$4),MROUND(M15,$S$4),IF(AND(M15>$R$4,M15<$R$5),MROUND(M15,$S$5),IF(AND(M15>$R$5,M15<$R$6),MROUND(M15,$S$6),IF(AND(M15>$R$6,M15<$R$7),MROUND(M15,$S$7),IF(M15>=$R$8,MROUND(M15,$S$8))))))))","v":0},{"$f":"D$4*(1+C15)^($A15)","v":0},{"$f":"E$4*(1+C15)^($A15)","v":0},{"$f":"F$4*(1+C15)^($A15)","v":0},{"$f":"G$4*(1+C15)^($A15)","v":0},{"$f":"H$4*(1+C15)^($A15)","v":0}]
[2,{"$f":"B15+1","v":2027},5.5E-2,0,0,0,0,0,{"$f":"D$4*(1+C16)^($A16)","v":0},{"$f":"E$4*(1+C16)^($A16)","v":0},{"$f":"F$4*(1+C16)^($A16)","v":0},{"$f":"G$4*(1+C16)^($A16)","v":0},{"$f":"H$4*(1+C16)^($A16)","v":0}]
[3,2028,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[4,2029,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[5,{"$f":"B18+1","v":2030},5.5E-2,0,0,0,0,0,0,0,0,0,0]
[6,2031,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[7,2032,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[8,2033,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[9,2034,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[10,2035,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[]
["DESIGN-BUILD -  INFLATED COST"]
["No. of Years","Year","Inflation","Preliminary Engineering:","Right-of-Way:","Utilities:","Construction:","Total Inflated Project Cost"]
[0,{"$f":"YEAR(TODAY())","v":2025},null,{"$f":"D7","v":0},{"$f":"E7","v":0},{"$f":"F7","v":0},{"$f":"G7","v":0},{"$f":"H7","v":0}]
[1,{"$f":"B28+1","v":2026},{"$f":"IF(IF(C28>=$D$57,C28-0.01,IF(C28<=$D$57,C28+0.01,\"\"))<=$D$57,$D$57,IF(C28>=$D$57,C28-0.01,IF(C28<=$D$57,C28+0.01)))","v":5.5E-2},{"$f":"IF(I29<=$R$2,MROUND(I29,$S$2),IF(AND(I29>$R$2,I29<$R$3),MROUND(I29,$S$3),IF(AND(I29>$R$3,I29<$R$4),MROUND(I29,$S$4),IF(AND(I29>$R$4,I29<$R$5),MROUND(I29,$S$5),IF(AND(I29>$R$5,I29<$R$6),MROUND(I29,$S$6),IF(AND(I29>$R$6,I29<$R$7),MROUND(I29,$S$7),IF(I29>=$R$8,MROUND(I29,$S$8))))))))","v":0},{"$f":"IF(J29<=$R$2,MROUND(J29,$S$2),IF(AND(J29>$R$2,J29<$R$3),MROUND(J29,$S$3),IF(AND(J29>$R$3,J29<$R$4),MROUND(J29,$S$4),IF(AND(J29>$R$4,J29<$R$5),MROUND(J29,$S$5),IF(AND(J29>$R$5,J29<$R$6),MROUND(J29,$S$6),IF(AND(J29>$R$6,J29<$R$7),MROUND(J29,$S$7),IF(J29>=$R$8,MROUND(J29,$S$8))))))))","v":0},{"$f":"IF(K29<=$R$2,MROUND(K29,$S$2),IF(AND(K29>$R$2,K29<$R$3),MROUND(K29,$S$3),IF(AND(K29>$R$3,K29<$R$4),MROUND(K29,$S$4),IF(AND(K29>$R$4,K29<$R$5),MROUND(K29,$S$5),IF(AND(K29>$R$5,K29<$R$6),MROUND(K29,$S$6),IF(AND(K29>$R$6,K29<$R$7),MROUND(K29,$S$7),IF(K29>=$R$8,MROUND(K29,$S$8))))))))","v":0},{"$f":"IF(L29<=$R$2,MROUND(L29,$S$2),IF(AND(L29>$R$2,L29<$R$3),MROUND(L29,$S$3),IF(AND(L29>$R$3,L29<$R$4),MROUND(L29,$S$4),IF(AND(L29>$R$4,L29<$R$5),MROUND(L29,$S$5),IF(AND(L29>$R$5,L29<$R$6),MROUND(L29,$S$6),IF(AND(L29>$R$6,L29<$R$7),MROUND(L29,$S$7),IF(L29>=$R$8,MROUND(L29,$S$8))))))))","v":0},{"$f":"IF(M29<=$R$2,MROUND(M29,$S$2),IF(AND(M29>$R$2,M29<$R$3),MROUND(M29,$S$3),IF(AND(M29>$R$3,M29<$R$4),MROUND(M29,$S$4),IF(AND(M29>$R$4,M29<$R$5),MROUND(M29,$S$5),IF(AND(M29>$R$5,M29<$R$6),MROUND(M29,$S$6),IF(AND(M29>$R$6,M29<$R$7),MROUND(M29,$S$7),IF(M29>=$R$8,MROUND(M29,$S$8))))))))","v":0},{"$f":"D$7*(1+C29)^($A29)","v":0},{"$f":"E$7*(1+C29)^($A29)","v":0},{"$f":"F$7*(1+C29)^($A29)","v":0},{"$f":"G$7*(1+C29)^($A29)","v":0},{"$f":"H$7*(1+C29)^($A29)","v":0}]
[2,{"$f":"B29+1","v":2027},{"$f":"IF(IF(C29>=$D$57,C29-0.01,IF(C29<=$D$57,C29+0.01,\"\"))<=$D$57,$D$57,IF(C29>=$D$57,C29-0.01,IF(C29<=$D$57,C29+0.01)))","v":5.5E-2},0,0,0,0,0,{"$f":"D$7*(1+C30)^($A30)","v":0},{"$f":"E$7*(1+C30)^($A30)","v":0},{"$f":"F$7*(1+C30)^($A30)","v":0},{"$f":"G$7*(1+C30)^($A30)","v":0},{"$f":"H$7*(1+C30)^($A30)","v":0}]
[3,2028,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[4,2029,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[5,{"$f":"B32+1","v":2030},5.5E-2,0,0,0,0,0,0,0,0,0,0]
[6,2031,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[7,2032,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[8,2033,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[9,2034,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[10,2035,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[]
["CMGC (HIGH RISK) -  INFLATED COST"]
["No. of Years","Year","Inflation","Preliminary Engineering:","Right-of-Way:","Utilities:","Construction:","Total Inflated Project Cost"]
[0,{"$f":"YEAR(TODAY())","v":2025},null,{"$f":"D21","v":0},{"$f":"E21","v":0},{"$f":"F21","v":0},{"$f":"G21","v":0},{"$f":"H21","v":0}]
[1,{"$f":"B42+1","v":2026},{"$f":"IF(IF(C42>=$D$57,C42-0.01,IF(C42<=$D$57,C42+0.01,\"\"))<=$D$57,$D$57,IF(C42>=$D$57,C42-0.01,IF(C42<=$D$57,C42+0.01)))","v":5.5E-2},{"$f":"IF(I43<=$R$2,MROUND(I43,$S$2),IF(AND(I43>$R$2,I43<$R$3),MROUND(I43,$S$3),IF(AND(I43>$R$3,I43<$R$4),MROUND(I43,$S$4),IF(AND(I43>$R$4,I43<$R$5),MROUND(I43,$S$5),IF(AND(I43>$R$5,I43<$R$6),MROUND(I43,$S$6),IF(AND(I43>$R$6,I43<$R$7),MROUND(I43,$S$7),IF(I43>=$R$8,MROUND(I43,$S$8))))))))","v":0},{"$f":"IF(J43<=$R$2,MROUND(J43,$S$2),IF(AND(J43>$R$2,J43<$R$3),MROUND(J43,$S$3),IF(AND(J43>$R$3,J43<$R$4),MROUND(J43,$S$4),IF(AND(J43>$R$4,J43<$R$5),MROUND(J43,$S$5),IF(AND(J43>$R$5,J43<$R$6),MROUND(J43,$S$6),IF(AND(J43>$R$6,J43<$R$7),MROUND(J43,$S$7),IF(J43>=$R$8,MROUND(J43,$S$8))))))))","v":0},{"$f":"IF(K43<=$R$2,MROUND(K43,$S$2),IF(AND(K43>$R$2,K43<$R$3),MROUND(K43,$S$3),IF(AND(K43>$R$3,K43<$R$4),MROUND(K43,$S$4),IF(AND(K43>$R$4,K43<$R$5),MROUND(K43,$S$5),IF(AND(K43>$R$5,K43<$R$6),MROUND(K43,$S$6),IF(AND(K43>$R$6,K43<$R$7),MROUND(K43,$S$7),IF(K43>=$R$8,MROUND(K43,$S$8))))))))","v":0},{"$f":"IF(L43<=$R$2,MROUND(L43,$S$2),IF(AND(L43>$R$2,L43<$R$3),MROUND(L43,$S$3),IF(AND(L43>$R$3,L43<$R$4),MROUND(L43,$S$4),IF(AND(L43>$R$4,L43<$R$5),MROUND(L43,$S$5),IF(AND(L43>$R$5,L43<$R$6),MROUND(L43,$S$6),IF(AND(L43>$R$6,L43<$R$7),MROUND(L43,$S$7),IF(L43>=$R$8,MROUND(L43,$S$8))))))))","v":0},{"$f":"IF(M43<=$R$2,MROUND(M43,$S$2),IF(AND(M43>$R$2,M43<$R$3),MROUND(M43,$S$3),IF(AND(M43>$R$3,M43<$R$4),MROUND(M43,$S$4),IF(AND(M43>$R$4,M43<$R$5),MROUND(M43,$S$5),IF(AND(M43>$R$5,M43<$R$6),MROUND(M43,$S$6),IF(AND(M43>$R$6,M43<$R$7),MROUND(M43,$S$7),IF(M43>=$R$8,MROUND(M43,$S$8))))))))","v":0},{"$f":"D$10*(1+C43)^($A43)","v":0},{"$f":"E$10*(1+C43)^($A43)","v":0},{"$f":"F$10*(1+C43)^($A43)","v":0},{"$f":"G$10*(1+C43)^($A43)","v":0},{"$f":"H$10*(1+C43)^($A43)","v":0}]
[2,{"$f":"B43+1","v":2027},{"$f":"IF(IF(C43>=$D$57,C43-0.01,IF(C43<=$D$57,C43+0.01,\"\"))<=$D$57,$D$57,IF(C43>=$D$57,C43-0.01,IF(C43<=$D$57,C43+0.01)))","v":5.5E-2},0,0,0,0,0,{"$f":"D$10*(1+C44)^($A44)","v":0},{"$f":"E$10*(1+C44)^($A44)","v":0},{"$f":"F$10*(1+C44)^($A44)","v":0},{"$f":"G$10*(1+C44)^($A44)","v":0},{"$f":"H$10*(1+C44)^($A44)","v":0}]
[3,2028,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[4,2029,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[5,{"$f":"B46+1","v":2030},5.5E-2,0,0,0,0,0,0,0,0,0,0]
[6,2031,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[7,2032,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[8,2033,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[9,2034,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[10,2035,5.5E-2,0,0,0,0,0,0,0,0,0,0]
[]
[]
[]
[null,"INFLATION INPUTS"]
[null,"Long Term Inflation:",null,5.5E-2]

{"sheet":"Retaining Wall Data","index":25,"n_rows":200,"n_cols":14,"rows_kept":200,"cut":false,"hidden":true,"merged":[[1,0,1,3],[1,4,1,6],[1,7,1,9],[1,10,1,13]]}
[]
["Wall Information",null,null,null,"Length",null,null,"Maximum Height",null,null,"Bid Results"]
["Job","Reg.","Wall","SF","BST","EST","Distance","BOW","TOW","Height","$/SF","Total Cost","Bids","DATE"]
["CNS202",3,2,5642,17767.28,18200,432.72000000000116,562,578.75,16.75,60,338520,5,"2018-08-17"]
["CNS202",3,3,9510,9600,10234.81,634.80999999999949,580,599.75,19.75,59,561090,5,"2018-08-17"]
["CNS289",4,6,6125,0,257.27999999999997,257.27999999999997,330,357,27,165,1010625,3,"2018-10-05"]
["CNS289",4,3,8017,0,556.37,556.37,337.10999999999996,357.71,20.600000000000023,110,881870,3,"2018-10-05"]
["CNS289",4,1,10293,0,843.85,843.85,355.96,374.96,19,145,1492485,3,"2018-10-05"]
["CNS060",3,2,2838,1000,1330.97,330.97,631.5,643.59,12.090000000000032,100,283800,5,"2018-12-07"]
["CNS060",3,1,664,95447.5,95529.5,82,630,639.19000000000005,9.1900000000000546,90.7,60224.800000000003,5,"2018-12-07"]
["CNS272",1,2,353,21190.28,21248.52,58.240000000001601,919.87,928.74,8.8700000000000045,97.58,34445.74,2,"2018-12-07"]
["CNS272",1,3,854,2300,2385.75,85.75,926.21,940.14,13.92999999999995,74.34,63486.36,2,"2018-12-07"]
["CNS272",1,4,1064,1532.45,1669.82,137.36999999999989,943,951.67,8.6699999999999591,91.76,97632.639999999999,2,"2018-12-07"]
["CNS338",3,1,13465,55350,56075,725,648.66999999999996,676.78,28.110000000000014,120,1615800,2,"2018-12-07"]
["CNS338",3,2,8256,57375,57775,400,709.51,735.13,25.620000000000005,125,1032000,2,"2018-12-07"]
["CNS338",3,3,3516,58124.2,58275.8,151.60000000000582,717.46,741.26,23.799999999999955,130,457080,2,"2018-12-07"]
["CNS338",3,4,2741,59140,59370,230,641,658.25,17.25,195,534495,2,"2018-12-07"]
["CNS338",3,5,2267,63000,63170,170,601.5,618.4,16.899999999999977,157,355919,2,"2018-12-07"]
["CNT021",1,1,208,110.13,155.13,45,1774.61,1781.11,6.5,146,30368,2,"2019-02-08"]
["CNT021",1,2,156,31976.89,32044.240000000002,67.350000000002183,1773.89,1776.89,3,65,10140,2,"2019-02-08"]
["CNT079",1,3,2903,120800,121100,300,1522.5,1534.5,12,135,391905,2,"2019-03-29"]
["CNT014",1,1,2393,2213.42,2392.67,179.25,880.5,899.7,19.200000000000045,185,442705,4,"2019-05-10"]
["CNT015",1,1,2574,44510,44800,290,979.87,990.11,10.240000000000009,104.43706293706293,268821,3,"2019-08-09"]
["CNT015",1,2,1658,44650,44750,100,976.01,992.62,16.610000000000014,102,169116,3,"2019-08-09"]
["CNT023",1,"1B",3849,3150,3397.19,247.19000000000005,850.91,874.26,23.350000000000023,83.69,322122.81,4,"2019-08-09"]
["CNT023",1,"2B",4994,10441,11013.16,572.15999999999985,845.53,859.58,14.050000000000068,78.03,389681.82,4,"2019-08-09"]
["CNT023",1,3,5660,10975,11375,400,834.61,857,22.389999999999986,82.07,464516.19999999995,4,"2019-08-09"]
["CNT023",1,5,3266,37525,37696.53,171.52999999999884,826.36,854.41,28.049999999999955,116.17,379411.22000000003,4,"2019-08-09"]
["CNT023",1,"6A",2022,19400,19628.509999999998,228.5099999999984,845.55,855.99,10.440000000000055,79.17,160081.74,4,"2019-08-09"]
["CNT023",1,7,19246,16725,17700,975,809,832.38,23.379999999999995,108.54,2088960.84,4,"2019-08-09"]
["CNT023",1,"7A",10626,17165.82,18025,859.18000000000029,818,838.53,20.529999999999973,78.09,829784.34000000008,4,"2019-08-09"]
["CNT023",1,"7B",3041,17103.73,17274.53,170.79999999999927,808,827.07,19.07000000000005,94.22,286523.02,4,"2019-08-09"]
["CNT273",2,1,1353,7000,7220.76,220.76000000000022,678.75,686.33,7.5800000000000409,105,142065,2,"2019-08-09"]
["CNT273",2,2,685,7273.73,7395,121.27000000000044,680.42,687.39,6.9700000000000273,105,71925,2,"2019-08-09"]
["CNT925",3,1,1384,9895,10020,125,508.54,520.37,11.829999999999984,72.5,100340,4,"2019-10-01"]
["CNT925",3,2,3023,10355,10636,281,519.44000000000005,531.07000000000005,11.629999999999995,73,220679,4,"2019-10-01"]
["CNT925",3,3,1617,10677.07,10958.5,281.43000000000029,519.73,527.65,7.9199999999999591,74,119658,4,"2019-10-01"]
["CNT925",3,4,567,16961.84,17080.66,118.81999999999971,515.15,520.15,5,88,49896,4,"2019-10-01"]
["CNT925",3,5,1030,18176.93,18340.93,164,487.86,495.08,7.2199999999999704,74,76220,4,"2019-10-01"]
["CNT290",1,1,4072,10660,10820,160,958.23,984,25.769999999999982,95,386840,4,"2019-10-04"]
["CNT290",1,2,1780,10680,10790,110,985,1003,18,95,169100,4,"2019-10-04"]
["CNT336",2,1,30291,11573.3,12525.64,952.34000000000015,765.66,806.59,40.930000000000064,116,3513756,3,"2019-12-13"]
["CNT336",2,2,19572,12325,13130,805,787.33,826.18,38.849999999999909,127,2485644,3,"2019-12-13"]
["CNT336",2,3,7447,760,1080,320,776.46,809.73,33.269999999999982,127,945769,3,"2019-12-13"]
["CNT336",2,4,3087,1020,1260,240,781.15,799.8,18.649999999999977,131,404397,3,"2019-12-13"]
["CNT336",2,5,4780,1000,1338.52,338.52,777.59,794.78,17.189999999999941,116,554480,3,"2019-12-13"]
["CNT336",2,8,2429,17893,18106,213,787,799.15,12.149999999999977,123,298767,3,"2019-12-13"]
["CNT359",4,1,5268,0,240.56,240.56,526.09,552.04999999999995,25.959999999999923,66,347688,4,"2019-12-13"]
["CNU093",1,1,2650,22230,22460,230,1299,1316.51,17.509999999999991,90.95,241017.5,1,"2020-05-15"]
["CNU910",1,1,1670,10300,10400,100,1910,1929,19,500,835000,2,"2020-05-15"]
["CNU011",2,2,1225,14376.59,14554,177.40999999999985,676.61,689.75,13.139999999999986,228,279300,5,"2020-06-26"]
["CNU011",2,4,5450,14625,14960.38,335.3799999999992,665.15,688,22.850000000000023,220,1199000,5,"2020-06-26"]
["CNU011",2,3,442,14554,14625,71,665.92,675.13,9.2100000000000364,205,90610,5,"2020-06-26"]
["CNU011",2,5,5732,14374.55,14912.97,538.42000000000007,664.77,684.35,19.580000000000041,180,1031760,5,"2020-06-26"]
["CNU011",2,1,1463,13140,13206.5,66.5,671.08,695.57,24.490000000000009,162,237006,5,"2020-06-26"]
["CNU011",2,7,106,4939.58,4953.7299999999996,14.149999999999636,658.83999999999992,666.33,7.4900000000001228,85.25,9036.5,5,"2020-06-26"]
["CNU011",2,6,1143,40220,40397.5,177.5,684.94,691.94,7,62.25,71151.75,5,"2020-06-26"]
["CNU221",2,1,878,13010,13125,115,756.12,766.62,10.5,110.81,97291.180000000008,2,"2020-08-14"]
["CNU264",3,1,471,1084.6099999999999,1164,79.3900000000001,660.68,666.79,6.1100000000000136,64.510000000000005,30384.210000000003,3,"2020-10-09"]
["CNU315",4,4,7340,39550,40050,500,442.88,461.89,19.009999999999991,105,770700,3,"2020-10-09"]
["CNU315",4,1,3365,31350,31650,300,491.07,504.69,13.620000000000005,70,235550,3,"2020-10-09"]
["CNU315",4,2,4685,32050,32650,600,471.93,483.68,11.75,53,248305,3,"2020-10-09"]
["CNU315",4,5,3205,39600,40050,450,468.94,477.47,8.5300000000000296,53,169865,3,"2020-10-09"]
["CNU315",4,6,4475,45750,46250,500,481.15,491.91,10.760000000000048,53,237175,3,"2020-10-09"]
["CNU315",4,7,7170,52750,53350,600,482.79,498.02,15.229999999999961,53,380010,3,"2020-10-09"]
["CNU315",4,8,2800,52950,53200,250,487.33,499.46,12.129999999999995,53,148400,3,"2020-10-09"]
["CNU315",4,9,6790,55500,56000,500,464.81,484.75,19.939999999999998,53,359870,3,"2020-10-09"]
["CNU367",1,3,1476,1000,1087.8,87.799999999999955,980,1007.58,27.580000000000041,129.97,191835.72,3,"2020-12-11"]
["CNU367",1,1,5146,1000,1204.3499999999999,204.34999999999991,1068,1106.29,38.289999999999964,114.25,587930.5,3,"2020-12-11"]
["CNU367",1,2,12048,1000,1482,482,979.7,1009.96,30.259999999999991,105.36,1269377.28,3,"2020-12-11"]
["CNV012",2,2,719,30300,30400,100,744.65,758.15,13.5,105.51,75861.69,5,"2021-03-26"]
["CNV012",2,1,3418,18430,18800,370,686.27,698.97,12.700000000000045,91.77,313669.86,5,"2021-03-26"]
["CNV237",3,1,1435,56888,57125,237,546,553.72,7.7200000000000273,75,107625,2,"2021-06-18"]
["CNV237",3,2,4555,2200,2588.11,388.11000000000013,540,552.58000000000004,12.580000000000041,72,327960,2,"2021-06-18"]
["CNV281",2,11,366,87550,87600,50,752,759.32,7.32000000000005,143,52338,4,"2021-08-20"]
["CNV281",2,1,3340,50190.81,50345.599999999999,154.79000000000087,727,752.68,25.67999999999995,70,233800,4,"2021-08-20"]
["CNV281",2,2,2860,50205.06,50351.99,146.93000000000029,728,750.71,22.710000000000036,70,200200,4,"2021-08-20"]
["CNV281",2,3,2956,76590.070000000007,76771.05,180.97999999999593,714,732.93,18.92999999999995,70,206920,4,"2021-08-20"]
["CNV281",2,4,3039,76654.7,76837.45,182.75,716,735.31,19.309999999999945,70,212730,4,"2021-08-20"]
["CNV281",2,5,3196,76684.34,76868.95,184.61000000000058,716,736.79,20.789999999999964,70,223720,4,"2021-08-20"]
["CNV281",2,6,3306,76742.649999999994,76930.12,187.47000000000116,716.5,736.8,20.299999999999955,70,231420,4,"2021-08-20"]
["CNV281",2,7,2652,82274.22,82413.13,138.91000000000349,757.9,777.88,19.980000000000018,70,185640,4,"2021-08-20"]
["CNV281",2,8,2954,82375.91,82522.02,146.11000000000058,756.41,779.56,23.149999999999977,70,206780,4,"2021-08-20"]
["CNV281",2,9,2144,88795.74,88929.15,133.40999999998894,724.8,743.49,18.690000000000055,70,150080,4,"2021-08-20"]
["CNV281",2,10,2073,89756.53,89887.47,130.94000000000233,716,743.67,27.669999999999959,70,145110,4,"2021-08-20"]
["CNV281",2,12,2438,1339.82,1555.74,215.92000000000007,684,699.7,15.700000000000045,70,170660,4,"2021-08-20"]
["CNV281",2,13,2334,1372.04,1578.06,206.01999999999998,684,697.9,13.899999999999977,70,163380,4,"2021-08-20"]
["CNV281",2,14,3065,2133.16,2373.34,240.18000000000029,731,746.55,15.549999999999955,70,214550,4,"2021-08-20"]
["CNV281",2,15,4264,2124.38,2366.38,242,723,745.33,22.330000000000041,70,298480,4,"2021-08-20"]
["CNV281",2,16,725,3321.98,3433.61,111.63000000000011,777.47,786.67,9.1999999999999318,70,50750,4,"2021-08-20"]
["CNV281",2,17,3487,3188.95,3426.77,237.82000000000016,768.5,784.42,15.919999999999959,70,244090,4,"2021-08-20"]
["CNV130",2,1,738,3260,3400,140,741.12,747.95,6.8300000000000409,157,115866,2,"2021-09-10"]
["CNV130",2,2,2425,15100,15340,240,732.44,743.71,11.269999999999982,117,283725,2,"2021-09-10"]
["CNV284",2,1,1202,0,212.44,212.44,929,935.5,6.5,91.5,109983,3,"2021-09-10"]
["CNV203",3,1,1520,57169,57434,265,585,593.08000000000004,8.0800000000000409,79,120080,3,"2021-10-08"]
["CNV203",3,2,1338,57420,57660,240,583,591.6,8.6000000000000227,79,105702,3,"2021-10-08"]
["CNV203",3,3,909,13117,13257,140,568.52,577.25,8.7300000000000182,79,71811,3,"2021-10-08"]
["CNV268",3,1,18978,10800,12586.72,1786.7199999999993,515.72,529.75,14.029999999999973,121.5,2305827,3,"2021-10-08"]
["CNV269",3,1,2687,15442,15833.9,391.89999999999964,677.55,684.91,7.3600000000000136,108.93,292694.91000000003,2,"2021-10-08"]
["CNV914",1,1,3177,21825,22075,250,1317.4,1332.17,14.769999999999982,108.5,344704.5,1,"2021-12-10"]
["CNV300",2,1,15813,1153.21,1787.87,634.65999999999985,1571.62,1618.11,46.490000000000009,30,474390,5,"2021-12-21"]
["CNV300",2,2,936,1925,2047.22,122.22000000000003,1536.66,1549.25,12.589999999999918,30,28080,5,"2021-12-21"]
["CNV300",2,3,17100,3937.67,4325,387.32999999999993,1583.43,1662.54,79.1099999999999,21,359100,5,"2021-12-21"]
["CNV300",2,4,4054,1440,1790,350,1569.91,1586.6,16.689999999999827,21,85134,5,"2021-12-21"]
["CNV300",2,5,3699,3175,3440,265,1659.59,1676.24,16.650000000000091,21,77679,5,"2021-12-21"]
["CNW070",3,1,832,100,181.95,81.949999999999989,500.18,511.06,10.879999999999995,140,116480,5,"2022-02-11"]
["CNW055",1,1,11280,2008.51,2815.91,807.39999999999986,273.76,294.52,20.759999999999991,120,1353600,3,"2022-03-25"]
["CNW055",1,5,9076,1000,1444.74,444.74,268.43,292.23,23.800000000000011,117,1061892,3,"2022-03-25"]
["CNW055",1,2,4346,1000,1385.56,385.55999999999995,278.11,292.57,14.45999999999998,109.84,477364.64,3,"2022-03-25"]
["CNW055",1,7,1369,1000,1094,94,264,280.83999999999997,16.839999999999975,99.29,135928.01,3,"2022-03-25"]
["CNW055",1,13,1051,1000,1180.58,180.57999999999993,290.14999999999998,298.58,8.4300000000000068,96.76,101694.76000000001,3,"2022-03-25"]
["CNW055",1,10,3418,1000,1402.75,402.75,284.99,294.20999999999998,9.2199999999999704,94.9,324368.2,3,"2022-03-25"]
["CNW132",3,1,560,1000,1106.92,106.92000000000007,942.7,948.8,6.0999999999999091,118,66080,4,"2022-03-25"]
["CNW132",3,2,2220,2000,2245.4499999999998,245.44999999999982,931.8,944.12,12.32000000000005,118,261960,4,"2022-03-25"]
["CNW181",3,4,5061,50,354,304,498.58,518.5,19.920000000000016,120,607320,4,"2022-05-03"]
["CNW181",3,3,15440,11.98,982,970.02,506,528.34,22.340000000000032,88,1358720,4,"2022-05-03"]
["CNW181",3,2,3852,28.9,447.96,419.06,507.76,519.62,11.860000000000014,75,288900,4,"2022-05-03"]
["CNW181",3,1,12048,50,1097.48,1047.48,501.91,518.74,16.829999999999984,66,795168,4,"2022-05-03"]
["CNW134",4,1,11260,5100,5912.67,812.67000000000007,342.77,361.79,19.020000000000039,89.85,1011710.9999999999,3,"2022-06-17"]
["CNW134",4,2,4096,60100,60546.09,446.08999999999651,340.58,352.89,12.310000000000002,89.85,368025.59999999998,3,"2022-06-17"]
["CNW134",4,3,7046,7058.53,7523.23,464.69999999999982,342.09,359.56,17.470000000000027,89.85,633083.1,3,"2022-06-17"]
["CNW134",4,4,8231,8062.39,8562,499.60999999999967,342.86,361.05,18.189999999999998,89.85,739555.35,3,"2022-06-17"]
["CNW919",1,1,1397,38675,38823,148,977.35,986.79,9.4399999999999409,425.14,593920.57999999996,1,"2022-08-19"]
["CNW919",1,7,732,41002,41150,148,955.71,961.46,5.75,402.69,294769.08,1,"2022-08-19"]
["CNW919",1,6,572,40420,40573.699999999997,153.69999999999709,924.64,935.34,10.700000000000045,395.53,226243.15999999997,1,"2022-08-19"]
["CNW919",1,5,6338,40475,41045,570,944.61,964.61,20,371.12,2352158.56,1,"2022-08-19"]
["CNW919",1,2,1109,39535,39676,141,934.93,952.13,17.200000000000045,316.52999999999997,351031.76999999996,1,"2022-08-19"]
["CNW919",1,3,1321,39560,39710,150,940.88,952.88,12,277.83999999999997,367026.63999999996,1,"2022-08-19"]
["CNW919",1,8,372,38850,38892,42,968.3,978.5,10.200000000000045,244.97,91128.84,1,"2022-08-19"]
["CNW919",1,4,1039,40225,40475,250,925.20999999999992,936.79,11.580000000000041,130,135070,1,"2022-08-19"]
["CNX903",2,1,131,0,16.25,16.25,1781.38,1793.18,11.799999999999955,655,85805,2,"2023-03-10"]
["CNX903",2,2,239,1,123.78,122.78,1781.38,1793.18,11.799999999999955,655,156545,2,"2023-03-10"]
["CNX267",3,6,1191,45710,45815,105,664.69,675.26,10.569999999999936,535,637185,3,"2023-10-06"]
["CNX267",3,4,4046,51220,51704.42,484.41999999999825,644.22,657.52,13.299999999999955,480,1942080,3,"2023-10-06"]
["CNX267",3,3,8204,50940,51575,635,652.27,669.15,16.879999999999995,465,3814860,3,"2023-10-06"]
["CNX358",2,"5B",903,52793,52850.92,57.919999999998254,718,733.79,15.789999999999964,450.4,406711.19999999995,4,"2023-10-06"]
["CNX267",3,2,2570,49715,49968.14,253.13999999999942,710.1,723.58,13.480000000000018,445,1143650,3,"2023-10-06"]
["CNX267",3,5,5748,51739.4,52200,460.59999999999854,631.49,645.52,14.029999999999973,445,2557860,3,"2023-10-06"]
["CNX074",1,"9B",891,19575,19740,165,933.31,939.11,5.8000000000000682,436.14,388600.74,1,"2023-05-12"]
["CNX074",1,2,1281,125,175,50,833.6,861.16,27.559999999999945,380.01,486792.81,1,"2023-05-12"]
["CNX074",1,8,15880,800,920.64,120.63999999999999,862.01,908.29,46.279999999999973,311.86,4952336.8,1,"2023-05-12"]
["CNY069",1,1,10220,10550,11350,800,1013.1,1028.97,15.870000000000005,310,3168200,4,"2024-02-09"]
["CNX267",3,7,483,53480,53650,170,618.9,621.75,2.8500000000000227,296,142968,3,"2023-10-06"]
["CNX267",3,1,1416,47365,47720,355,667.06,670.99,3.9300000000000637,285,403560,3,"2023-10-06"]
["CNX074",1,17,3151,13075,13375,300,840.38,853,12.620000000000005,275.70999999999998,868762.21,1,"2023-05-12"]
["CNX074",1,16,684,9438.9500000000007,9530.0400000000009,91.090000000000146,917.5,928.5,11,262.10000000000002,179276.40000000002,1,"2023-05-12"]
["CNX229",3,1,1828,11989,12250,261,606,613,7,250,457000,2,"2023-06-23"]
["CNY312",1,1,484,1057,1137,80,2929,2937,8,240,116160,1,"2024-10-25"]
["CNY312",1,2,626,16300,16409,109,29000,29009.5,9.5,240,150240,1,"2024-10-25"]
["CNX185",1,1,7715,33735,34060,325,1260.08,1297,36.920000000000073,210,1620150,3,"2024-08-16"]
["CNX358",2,6,15742,51000,51332,332,708,736,28,207.89,3272604.38,4,"2023-10-06"]
["CNZ042",2,1,1137,9600,9750,150,1602,1610,8,199,226263,4,"2025-02-07"]
["CNX358",2,"4B",376,44038.25,44066.25,28,712,730,18,197.06,74094.559999999998,4,"2023-10-06"]
["CNX358",2,"4A",739,43889.25,43939.25,50,712,730,18,197.06,145627.34,4,"2023-10-06"]
["CNX358",2,"5A",749,52689.919999999998,52751.92,62,718,733.79,15.789999999999964,197.06,147597.94,4,"2023-10-06"]
["CNY172",1,1,870,11900,12100,200,1553,1558,5,195,169650,4,"2024-06-21"]
["CNX308",1,1,2989,26400,26550,150,835.37,844.57,9.2000000000000455,188.05,562081.45000000007,2,"2023-08-18"]
["CNX074",1,12,741.5,50,200,150,918.9,926.15,7.25,183,135694.5,1,"2023-05-12"]
["CNX308",1,2,8511,1150,2200,1050,887.64,900.18,12.539999999999964,181.5,1544746.5,2,"2023-08-18"]
["CNX074",1,"9A",2116,19307.82,19575,267.18000000000029,924.1,937.65,13.549999999999955,180.05,380985.80000000005,1,"2023-05-12"]
["CNY146",4,2,1192,40930,41207.550000000003,277.55000000000291,308,312.8,4.8000000000000114,175,208600,2,"2024-05-10"]
["CNZ028",3,7,3434,40097.47,40318.68,221.20999999999913,433,452,19,175,600950,5,"2025-02-07"]
["CNZ028",3,8,3586,40105.730000000003,40325.07,219.33999999999651,433,452,19,175,627550,5,"2025-02-07"]
["CNY146",4,3,11466,41650,42322.8,672.80000000000291,307,336.34,29.339999999999975,175,2006550,2,"2024-05-10"]
["CNY311",1,1,13632,10260,11160,900,1960,1978,18,174,2371968,2,"2024-10-25"]
["CNY146",4,5,8994,1370.82,1868.34,497.52,298,325,27,170,1528980,2,"2024-05-10"]
["CNY146",4,11,2057,42260.84,42396.17,135.33000000000175,319,335.5,16.5,165,339405,2,"2024-05-10"]
["CNY146",4,12,2061,43051,43186.2,135.19999999999709,320,336.8,16.800000000000011,165,340065,2,"2024-05-10"]
["CNY146",4,6,6366,43025.53,43374.5,348.97000000000116,311,336,25,165,1050390,2,"2024-05-10"]
["CNX074",1,1,10293,13630,14600,970,828,838.84,10.840000000000032,160.62,1653261.6600000001,1,"2023-05-12"]
["CNY146",4,1,1879,40565,40831.93,266.93000000000029,308,315.5,7.5,160,300640,2,"2024-05-10"]
["CNY146",4,7,5220,43134.28,43400.07,265.79000000000087,308,334.5,26.5,160,835200,2,"2024-05-10"]
["CNY146",4,4,6035,41950,42420.11,470.11000000000058,315,337,22,160,965600,2,"2024-05-10"]
["CNX358",2,7,14476,2231.75,2996.91,765.15999999999985,746,771,25,155.72999999999999,2254347.48,4,"2023-10-06"]
["CNY146",4,8,9048,43483.19,44270,786.80999999999767,300,324.56,24.560000000000002,155,1402440,2,"2024-05-10"]
["CNX086",3,1,565,5750,5850,100,475,481,6,150,84750,2,"2023-05-12"]
["CNY146",4,9,1159,43584.5,43735,150.5,314.5,325,10.5,150,173850,2,"2024-05-10"]
["CNX074",1,13,2060,10175,10550,375,866,873,7,147.55000000000001,303953,1,"2023-05-12"]
["CNX074",1,5,2470,17087,17250,163,850.78,865.38,14.600000000000023,140.32,346590.39999999997,1,"2023-05-12"]
["CNZ028",3,3,726,114467.83,114692.93,225.09999999999127,475,478,3,140,101640,5,"2025-02-07"]
["CNZ028",3,4,2021,115008.45,115286.24,277.79000000000815,470,481,11,140,282940,5,"2025-02-07"]
["CNZ028",3,6,2423,78150,78400,250,463,474,11,140,339220,5,"2025-02-07"]
["CNZ028",3,1,2689,101750,102375,625,536,541,5,140,376460,5,"2025-02-07"]
["CNY146",4,10,2727,44700,45100,400,311.5,318.45,6.9499999999999886,140,381780,2,"2024-05-10"]
["CNZ028",3,5,4734,67750,68500,750,467,476,9,140,662760,5,"2025-02-07"]
["CNZ028",3,2,9966,101700,102800,1100,536,547,11,140,1395240,5,"2025-02-07"]
["CNZ029",2,3,1391,7950,8118.95,168.94999999999982,1092,1100,8,125,173875,4,"2025-02-07"]
["CNZ029",2,4,7623,10500,11300,800,1077,1094,17,125,952875,4,"2025-02-07"]
["CNZ029",2,2,8622,8300,8995,695,1085,1107,22,125,1077750,4,"2025-02-07"]
["CNZ029",2,1,9095,11438.8,12247,808.20000000000073,1080,1095,15,125,1136875,4,"2025-02-07"]
["CNX358",2,1,14654,43399,43650,251,711,733,22,108.02,1582925.0799999998,4,"2023-10-06"]
["CNX358",2,3,14303,50800,51332,532,712,735,23,104.99,1501671.97,4,"2023-10-06"]
["CNX358",2,2,15950,43399,43900,501,708,733,25,104.88,1672836,4,"2023-10-06"]
["CNY172",1,2,11785,12825,13550,725,1580,1601,21,101.82,1199948.7,4,"2024-06-21"]
["CNY223",1,2,3926,158180,158482,302,1802,1818,16,100,392600,2,"2024-10-04"]
["CNX308",1,4,3399,1750,2225,475,856,875.56,19.559999999999945,99.44,337996.56,2,"2023-08-18"]
["CNY228",1,1,533,3600,3700,100,1147,1154,7,90,47970,1,"2024-12-06"]
["CNX308",1,6,3399,1000,1075,75,832,847.71,15.710000000000036,84.8,288235.2,2,"2023-08-18"]
["CNX308",1,5,4380,1100,1500,400,849.5,873.98,24.480000000000018,83.05,363759,2,"2023-08-18"]
["CNX308",1,3,11523,3450,3700,250,894,902,8,76.52,881739.96,2,"2023-08-18"]

{"sheet":"AUP Data","index":26,"n_rows":53,"n_cols":35,"rows_kept":53,"cut":false,"hidden":true,"merged":[[1,30,1,32],[1,28,1,29],[1,4,1,7],[1,8,1,11],[1,12,1,15],[1,16,1,19],[1,20,1,23],[1,24,1,27]]}
[1,{"$f":"A1+1","v":2},{"$f":"B1+1","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,{"$f":"X1+1","v":25},{"$f":"Y1+1","v":26},{"$f":"Z1+1","v":27},{"$f":"AA1+1","v":28},{"$f":"AB1+1","v":29},{"$f":"AC1+1","v":30},{"$f":"AD1+1","v":31},{"$f":"AE1+1","v":32}]
[null,null,null,null,2018,null,null,null,2019,null,null,null,2020,null,null,null,2021,null,null,null,2023,null,null,null,2024,null,null,null,"2018-2021 Average",null,"2022 Results"]
["Item Number","Description","Quantity","Average Quantity","Unit Price","Quantity","Cost/Item","Increase","Unit Price","Quantity","Cost/Item","Increase","Unit Price","Quantity","Cost/Item","Increase","Unit Price","Quantity","Cost/Item","Increase","Unit Price","Average Quantity","Cost/Item","Increase","Unit Price","Average Quantity","Cost/Item","Increase (Decrease)","Unit Price","Cost/Item","2020-2022 Average","Unit Price","% Increase",null,{"$f":"((M4*N4*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q4*R4*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U4*V4*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N4+R4+V4)","v":1155.7158771670149}]
["402-01","BITUMINOUS MATERIAL FOR PRIME COAT (PC)",{"$f":"'Finalize Items'!$G$55","v":0},{"$f":"AVERAGE(F4,J4,N4,R4)","v":132198.48499999999},644.44000000000005,2590.1,{"$f":"C4*E4","v":0},null,535.33000000000004,2728.94,{"$f":"C4*I4","v":0},{"$f":"IFERROR(IF((K4/G4)-1<#REF!,\"\",(K4/G4)-1),\"\")","v":""},770.79,518127,{"$f":"C4*M4","v":0},{"$f":"IFERROR(IF((O4/K4)-1<#REF!,\"\",(O4/K4)-1),\"\")","v":""},754.57,5347.9,{"$f":"C4*Q4","v":0},{"$f":"IFERROR(IF((S4/O4)-1<#REF!,\"\",(S4/O4)-1),\"\")","v":""},598.1,100.36,{"$f":"C4*U4","v":0},null,978.2,36,null,{"$f":"Y4/U4-1","v":0.63551245611101814},{"$f":"((E4*F4*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I4*J4*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M4*N4*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q4*R4*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F4+J4+N4+R4)","v":1153.4117275741473},{"$f":"C4*AC4","v":0},{"$f":"((M4*N4*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q4*R4*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U4*V4*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N4+R4+V4)","v":1155.7158771670149},{"$f":"IF(AE4>U4,AE4,U4)","v":1155.7158771670149},{"$f":"AE4/U4-1","v":0.9323121169821349}]
["402-02","AGGREGATE FOR COVER MATERIAL (PC)",{"$f":"'Finalize Items'!$G$56","v":0},{"$f":"AVERAGE(F5,J5,N5,R5)","v":874355.57750000001},47.15,7844.4,0,null,27.85,9486.91,{"$f":"C5*I5","v":0},{"$f":"IFERROR(IF((K5/G5)-1<#REF!,\"\",(K5/G5)-1),\"\")","v":""},54.57,3463886.1,0,{"$f":"IFERROR(IF((O5/K5)-1<#REF!,\"\",(O5/K5)-1),\"\")","v":""},44.63,16204.9,{"$f":"C5*Q5","v":0},{"$f":"IFERROR(IF((S5/O5)-1<#REF!,\"\",(S5/O5)-1),\"\")","v":""},89,68.569999999999993,{"$f":"C5*U5","v":0},null,75.900000000000006,143.28,null,{"$f":"Y5/U5-1","v":-0.14719101123595502},{"$f":"((E5*F5*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I5*J5*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M5*N5*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q5*R5*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F5+J5+N5+R5)","v":81.743485850971297},0,{"$f":"((M5*N5*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q5*R5*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U5*V5*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N5+R5+V5)","v":81.866337177172667},{"$f":"IF(AE5>U5,AE5,U5)","v":89},{"$f":"AE5/U5-1","v":-8.0153514863228414E-2}]
["403-01","BITUMINOUS MATERIAL FOR TACK COAT (TC)",{"$f":"'Finalize Items'!$G$57","v":0},9270.4724999999999,673.44,13792.5,0,null,652.74,9791.67,0,{"$f":"IFERROR(IF((K6/G6)-1<#REF!,\"\",(K6/G6)-1),\"\")","v":""},679.93,2294.59,0,{"$f":"IFERROR(IF((O6/K6)-1<#REF!,\"\",(O6/K6)-1),\"\")","v":""},711.43,11203.13,0,{"$f":"IFERROR(IF((S6/O6)-1<#REF!,\"\",(S6/O6)-1),\"\")","v":""},924.09,50.24,0,null,974.85,45.54,null,5.4929714638184635E-2,{"$f":"((E6*F6*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I6*J6*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M6*N6*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q6*R6*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F6+J6+N6+R6)","v":989.87941163870141},0,{"$f":"((M6*N6*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q6*R6*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U6*V6*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N6+R6+V6)","v":904.61842961796401},924.09,-2.1071075741579293E-2]
["411-01.07","ACS MIX (PG64-22) GRADING E SHOULDER",{"$f":"'Finalize Items'!$G$69","v":0},166576.25,92.9,168795,0,null,93.34,87638,0,{"$f":"IFERROR(IF((K7/G7)-1<#REF!,\"\",(K7/G7)-1),\"\")","v":""},90.51,294370,0,{"$f":"IFERROR(IF((O7/K7)-1<#REF!,\"\",(O7/K7)-1),\"\")","v":""},94.48,115502,0,{"$f":"IFERROR(IF((S7/O7)-1<#REF!,\"\",(S7/O7)-1),\"\")","v":""},124.81,2150.62,0,null,128.63,1766.02,null,3.060652191330826E-2,{"$f":"((E7*F7*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I7*J7*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M7*N7*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q7*R7*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F7+J7+N7+R7)","v":136.41676521314307},0,{"$f":"((M7*N7*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q7*R7*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U7*V7*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N7+R7+V7)","v":130.67233670503776},130.67233670503776,4.6970088174327129E-2]
["411-01.10","ACS MIX(PG64-22) GRADING D",0,319870.05499999999,91.19,350392,0,null,97.79,335052.37,0,{"$f":"IFERROR(IF((K8/G8)-1<#REF!,\"\",(K8/G8)-1),\"\")","v":""},98.19,238965.25,0,{"$f":"IFERROR(IF((O8/K8)-1<#REF!,\"\",(O8/K8)-1),\"\")","v":""},97.18,355070.6,0,{"$f":"IFERROR(IF((S8/O8)-1<#REF!,\"\",(S8/O8)-1),\"\")","v":""},135.63,1941.18,0,null,141.99,2877.94,null,4.6892280468922909E-2,{"$f":"((E8*F8*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I8*J8*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M8*N8*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q8*R8*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F8+J8+N8+R8)","v":139.71158468080463},0,{"$f":"((M8*N8*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q8*R8*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U8*V8*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N8+R8+V8)","v":131.27561066800669},135.63,-3.2104912865835722E-2]
["411-02.10","ACS MIX(PG70-22) GRADING D",0,416304.64500000002,94.18,450096.72,0,null,102.52,427487.5,0,{"$f":"IFERROR(IF((K9/G9)-1<#REF!,\"\",(K9/G9)-1),\"\")","v":""},98.98,351176.36,0,{"$f":"IFERROR(IF((O9/K9)-1<#REF!,\"\",(O9/K9)-1),\"\")","v":""},105.08,436458,0,{"$f":"IFERROR(IF((S9/O9)-1<#REF!,\"\",(S9/O9)-1),\"\")","v":""},145.31,5123.5200000000004,0,null,144.19999999999999,6268.17,null,-7.6388410983415644E-3,{"$f":"((E9*F9*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I9*J9*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M9*N9*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q9*R9*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F9+J9+N9+R9)","v":146.08433380882752},0,{"$f":"((M9*N9*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q9*R9*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U9*V9*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N9+R9+V9)","v":138.52157931202692},145.31,-4.6716817066775107E-2]
["411-03.10","ACS MIX(PG76-22) GRADING D",0,192533,109.08,224088,0,null,97.6,93088,0,{"$f":"IFERROR(IF((K10/G10)-1<#REF!,\"\",(K10/G10)-1),\"\")","v":""},99.21,136541,0,{"$f":"IFERROR(IF((O10/K10)-1<#REF!,\"\",(O10/K10)-1),\"\")","v":""},109.62,316415,0,{"$f":"IFERROR(IF((S10/O10)-1<#REF!,\"\",(S10/O10)-1),\"\")","v":""},148.61000000000001,8297.17,0,null,153.88,4548.71,null,3.5461947379045622E-2,{"$f":"((E10*F10*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I10*J10*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M10*N10*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q10*R10*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F10+J10+N10+R10)","v":150.46475170664311},0,{"$f":"((M10*N10*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q10*R10*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U10*V10*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N10+R10+V10)","v":140.23584482676898},{"$f":"IF(AE10>U10,AE10,U10)","v":148.61000000000001},-5.6349876678763455E-2]
["411-(01 & 02 & 03).10","ACS MIX(ALL GRADES) GRADING D",{"$f":"'Finalize Items'!$G$71","v":0},928707.7,{"$f":"((E8*F8)+(E9*F9)+(E10*F10))/(SUM(F8:F10))","v":96.416278723959309},{"$f":"SUM(F8:F10)","v":1024576.72},0,null,{"$f":"((I8*J8)+(I9*J9)+(I10*J10))/(SUM(J8:J10))","v":100.1325243908897},{"$f":"SUM(J8:J10)","v":855627.87},0,{"$f":"IFERROR(IF((K11/G11)-1<#REF!,\"\",(K11/G11)-1),\"\")","v":""},{"$f":"((M8*N8)+(M9*N9)+(M10*N10))/(SUM(N8:N10))","v":98.763429360584254},{"$f":"SUM(N8:N10)","v":726682.61},0,{"$f":"IFERROR(IF((O11/K11)-1<#REF!,\"\",(O11/K11)-1),\"\")","v":""},{"$f":"((Q8*R8)+(Q9*R9)+(Q10*R10))/(SUM(R8:R10))","v":103.84479846086029},{"$f":"SUM(R8:R10)","v":1107943.6000000001},0,{"$f":"IFERROR(IF((S11/O11)-1<#REF!,\"\",(S11/O11)-1),\"\")","v":""},{"$f":"VLOOKUP(A11,'SUP 2022'!A:L,11,0)","v":133.699791284284},{"$f":"SUM(V8:V10)","v":15361.87},0,null,{"$f":"SUMPRODUCT(Y8:Y10,Z8:Z10)/SUM(Z8:Z10)","v":146.95076747266484},{"$f":"SUM(Z8:Z10)","v":13694.82},null,9.910992426461962E-2,{"$f":"((E11*F11*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I11*J11*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M11*N11*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q11*R11*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F11+J11+N11+R11)","v":144.79751706879},0,{"$f":"((M11*N11*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q11*R11*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U11*V11*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N11+R11+V11)","v":136.49734943342571},136.49734943342571,2.0924177384789688E-2]
["307-01.20","AGGREGATE (PG64-22)(BPMB-HM) GRADING A-S MIX",0,23342.25,101.05,8091,0,null,70.41,34372,0,{"$f":"IFERROR(IF((K12/G12)-1<#REF!,\"\",(K12/G12)-1),\"\")","v":""},94.9,772,0,{"$f":"IFERROR(IF((O12/K12)-1<#REF!,\"\",(O12/K12)-1),\"\")","v":""},81.63,50134,0,{"$f":"IFERROR(IF((S12/O12)-1<#REF!,\"\",(S12/O12)-1),\"\")","v":""},101.79,4805.54,0,null,114.68,4930.62,null,0.12663326456429913,{"$f":"((E12*F12*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I12*J12*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M12*N12*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q12*R12*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F12+J12+N12+R12)","v":109.00256440019881},0,{"$f":"((M12*N12*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q12*R12*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U12*V12*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N12+R12+V12)","v":103.02478137943076},103.02478137943076,1.2130674716875456E-2]
["307-01.21","AGGREGATE (PG70-22)(BPMB-HM) GRADING A-S MIX",0,84778.107499999998,79.89,90519.43,0,null,82.74,60952,0,{"$f":"IFERROR(IF((K13/G13)-1<#REF!,\"\",(K13/G13)-1),\"\")","v":""},71.05,87304,0,{"$f":"IFERROR(IF((O13/K13)-1<#REF!,\"\",(O13/K13)-1),\"\")","v":""},88.32,100337,0,{"$f":"IFERROR(IF((S13/O13)-1<#REF!,\"\",(S13/O13)-1),\"\")","v":""},134.94999999999999,2871.79,0,null,130.05000000000001,7725.87,null,-3.6309744349758977E-2,{"$f":"((E13*F13*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I13*J13*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M13*N13*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q13*R13*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F13+J13+N13+R13)","v":116.36700850340654},0,{"$f":"((M13*N13*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q13*R13*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U13*V13*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N13+R13+V13)","v":108.81273100782633},134.94999999999999,-0.19368113369524753]
["307-01.22","AGGREGATE (PG76-22)(BPMB-HM) GRADING A-S MIX",0,50073,80.56,53399,0,null,81.61,23835,0,{"$f":"IFERROR(IF((K14/G14)-1<#REF!,\"\",(K14/G14)-1),\"\")","v":""},80.14,29174,0,{"$f":"IFERROR(IF((O14/K14)-1<#REF!,\"\",(O14/K14)-1),\"\")","v":""},66.3,93884,0,{"$f":"IFERROR(IF((S14/O14)-1<#REF!,\"\",(S14/O14)-1),\"\")","v":""},{"$f":"VLOOKUP(A14,'SUP 2022'!A:L,11,0)","v":122.37},1925.14,0,null,125,3553.66,null,2.1492195799624136E-2,{"$f":"((E14*F14*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I14*J14*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M14*N14*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q14*R14*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F14+J14+N14+R14)","v":104.86651035632416},0,{"$f":"((M14*N14*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q14*R14*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U14*V14*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N14+R14+V14)","v":91.891851107539878},122.37,-0.24906552988853581]
["307-01.(20 & 21 & 22)","AGGREGATE (ALL GRADES)(BPMB-HM) GRADING A-S MIX",{"$f":"'Finalize Items'!$G$45","v":0},158193.35749999998,{"$f":"((E12*F12)+(E13*F13)+(E14*F14))/(SUM(F12:F14))","v":81.251645063730592},{"$f":"SUM(F12:F14)","v":152009.43},0,null,{"$f":"((I12*J12)+(I13*J13)+(I14*J14))/(SUM(J12:J14))","v":78.95732047096736},{"$f":"SUM(J12:J14)","v":119159},0,{"$f":"IFERROR(IF((K15/G15)-1<#REF!,\"\",(K15/G15)-1),\"\")","v":""},{"$f":"((M12*N12)+(M13*N13)+(M14*N14))/(SUM(N12:N14))","v":73.468796247334751},{"$f":"SUM(N12:N14)","v":117250},0,{"$f":"IFERROR(IF((O15/K15)-1<#REF!,\"\",(O15/K15)-1),\"\")","v":""},{"$f":"((Q12*R12)+(Q13*R13)+(Q14*R14))/(SUM(R12:R14))","v":78.487084201264551},{"$f":"SUM(R12:R14)","v":244355},0,{"$f":"IFERROR(IF((S15/O15)-1<#REF!,\"\",(S15/O15)-1),\"\")","v":""},{"$f":"VLOOKUP(A15,'SUP 2022'!A:L,11,0)","v":122.72814509415434},{"$f":"SUM(V12:V14)","v":9602.4699999999993},0,null,{"$f":"SUMPRODUCT(Y12:Y14,Z12:Z14)/SUM(Z12:Z14)","v":124.26784422722803},{"$f":"SUM(Z12:Z14)","v":16210.15},null,1.2545607463491537E-2,{"$f":"((E15*F15*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I15*J15*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M15*N15*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q15*R15*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F15+J15+N15+R15)","v":111.64008980780358},0,{"$f":"((M15*N15*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q15*R15*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U15*V15*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N15+R15+V15)","v":102.45403075045529},122.72814509415434,-0.16519531300782875]
["303-01","MINERAL AGGREGATE, TYPE A BASE, GRADING D",{"$f":"'Finalize Items'!E37","v":0},1755873.3025,24.13,1551727.3,0,null,23.7,1420410.78,0,{"$f":"IFERROR(IF((K16/G16)-1<#REF!,\"\",(K16/G16)-1),\"\")","v":""},22.31,1090571,0,{"$f":"IFERROR(IF((O16/K16)-1<#REF!,\"\",(O16/K16)-1),\"\")","v":""},24.59,2960784.13,0,{"$f":"IFERROR(IF((S16/O16)-1<#REF!,\"\",(S16/O16)-1),\"\")","v":""},37.18,6613.85,0,null,40.6,10372.39,null,9.1984938138784278E-2,{"$f":"((E16*F16*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I16*J16*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M16*N16*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q16*R16*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F16+J16+N16+R16)","v":33.815146184828883},0,{"$f":"((M16*N16*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q16*R16*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U16*V16*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N16+R16+V16)","v":31.269101808778483},37.18,-0.15898058610063248]
["307-01.08","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING B-M2",0,121243.45250000001,87.86,121610,0,null,91.14,120569.71,0,{"$f":"IFERROR(IF((K17/G17)-1<#REF!,\"\",(K17/G17)-1),\"\")","v":""},97.5,62649.52,0,{"$f":"IFERROR(IF((O17/K17)-1<#REF!,\"\",(O17/K17)-1),\"\")","v":""},86.69,180144.58,0,{"$f":"IFERROR(IF((S17/O17)-1<#REF!,\"\",(S17/O17)-1),\"\")","v":""},133.72,804.12,0,null,130.91999999999999,1570.2,null,-2.0939276099312121E-2,{"$f":"((E17*F17*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I17*J17*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M17*N17*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q17*R17*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F17+J17+N17+R17)","v":128.37433187212065},0,{"$f":"((M17*N17*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q17*R17*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U17*V17*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N17+R17+V17)","v":117.47839091710435},133.72,-0.12145983460137344]
["307-03.08","ASPHALT CONCRETE MIX (PG76-22) (BPMB-HM) GRADING B-M2",0,141502.04999999999,89.69,166508,0,null,78.55,97874,0,{"$f":"IFERROR(IF((K18/G18)-1<#REF!,\"\",(K18/G18)-1),\"\")","v":""},83.21,147436.20000000001,0,{"$f":"IFERROR(IF((O18/K18)-1<#REF!,\"\",(O18/K18)-1),\"\")","v":""},89.16,154190,0,{"$f":"IFERROR(IF((S18/O18)-1<#REF!,\"\",(S18/O18)-1),\"\")","v":""},132.80000000000001,2092.71,0,null,135.74,2433.02,null,2.2138554216867501E-2,{"$f":"((E18*F18*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I18*J18*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M18*N18*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q18*R18*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F18+J18+N18+R18)","v":125.20268610299591},0,{"$f":"((M18*N18*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q18*R18*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U18*V18*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N18+R18+V18)","v":117.73601996004896},132.80000000000001,-0.11343358463818554]
["307-02.08","ASPHALT CONCRETE MIX (PG70-22) (BPMB-HM) GRADING B-M2",0,113720.495,88.08,102132.88,0,null,93.55,88572.1,0,{"$f":"IFERROR(IF((K19/G19)-1<#REF!,\"\",(K19/G19)-1),\"\")","v":""},79.84,95134,0,{"$f":"IFERROR(IF((O19/K19)-1<#REF!,\"\",(O19/K19)-1),\"\")","v":""},81.680000000000007,169043,0,{"$f":"IFERROR(IF((S19/O19)-1<#REF!,\"\",(S19/O19)-1),\"\")","v":""},128.69,1690.2,0,null,127.05,2913.53,null,-1.274380293729116E-2,{"$f":"((E19*F19*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I19*J19*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M19*N19*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q19*R19*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F19+J19+N19+R19)","v":121.87017136151648},0,{"$f":"((M19*N19*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q19*R19*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U19*V19*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N19+R19+V19)","v":108.10632575038011},128.69,-0.15994773680643326]
["307-(01 & 02 & 03).08","ASPHALT CONCRETE MIX (ALL GRADES) (BPMB-HM) GRADING B-M2",{"$f":"'Finalize Items'!$G$46","v":0},376465.9975,{"$f":"((E17*F17)+(E18*F18)+(E19*F19))/(SUM(F17:F19))","v":88.698380873349976},{"$f":"SUM(F17:F19)","v":390250.88},0,null,{"$f":"((I17*J17)+(I18*J18)+(I19*J19))/(SUM(J17:J19))","v":87.821685874743707},{"$f":"SUM(J17:J19)","v":307015.81000000006},0,{"$f":"IFERROR(IF((K20/G20)-1<#REF!,\"\",(K20/G20)-1),\"\")","v":""},{"$f":"((M17*N17)+(M18*N18)+(M19*N19))/(SUM(N17:N19))","v":85.092775008115467},{"$f":"SUM(N17:N19)","v":305219.71999999997},0,{"$f":"IFERROR(IF((O20/K20)-1<#REF!,\"\",(O20/K20)-1),\"\")","v":""},{"$f":"((Q17*R17)+(Q18*R18)+(Q19*R19))/(SUM(R17:R19))","v":85.764142058531888},{"$f":"SUM(R17:R19)","v":503377.57999999996},0,{"$f":"IFERROR(IF((S20/O20)-1<#REF!,\"\",(S20/O20)-1),\"\")","v":""},{"$f":"VLOOKUP(A20,'SUP 2022'!A:L,11,0)","v":100.89311587469591},{"$f":"SUM(V17:V19)","v":4587.03},0,null,{"$f":"SUMPRODUCT(Y17:Y19,Z17:Z19)/SUM(Z17:Z19)","v":130.98531901543353},{"$f":"SUM(Z17:Z19)","v":6916.75},null,0.29825823972084087,{"$f":"((E20*F20*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I20*J20*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M20*N20*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q20*R20*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F20+J20+N20+R20)","v":125.21747112261741},0,{"$f":"((M20*N20*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q20*R20*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U20*V20*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N20+R20+V20)","v":114.31032490779603},114.31032490779603,0.13298438567170034]
["307-02.01","ASPHALT CONCRETE MIX (PG70-22) (BPMB-HM) GRADING A",0,147117.8725,79.010000000000005,152039.19,0,null,83.6,98964.3,0,{"$f":"IFERROR(IF((K21/G21)-1<#REF!,\"\",(K21/G21)-1),\"\")","v":""},73.209999999999994,140241,0,{"$f":"IFERROR(IF((O21/K21)-1<#REF!,\"\",(O21/K21)-1),\"\")","v":""},80.09,197227,0,{"$f":"IFERROR(IF((S21/O21)-1<#REF!,\"\",(S21/O21)-1),\"\")","v":""},131.22,2318.33,0,null,125.18,4720.62,null,-4.6029568663313425E-2,{"$f":"((E21*F21*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I21*J21*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M21*N21*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q21*R21*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F21+J21+N21+R21)","v":113.2865484415458},0,{"$f":"((M21*N21*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q21*R21*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U21*V21*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N21+R21+V21)","v":103.93572330627971},131.22,-0.20792772971894746]
["307-03.01","ASPHALT CONCRETE MIX (PG76-22) (BPMB-HM) GRADING A",0,145716.25,75.989999999999995,120391,0,null,86.66,63855,0,{"$f":"IFERROR(IF((K22/G22)-1<#REF!,\"\",(K22/G22)-1),\"\")","v":""},71.98,130519,0,{"$f":"IFERROR(IF((O22/K22)-1<#REF!,\"\",(O22/K22)-1),\"\")","v":""},77.73,268100,0,{"$f":"IFERROR(IF((S22/O22)-1<#REF!,\"\",(S22/O22)-1),\"\")","v":""},115.22,6540.68,0,null,123.85,7421.05,null,7.4900190939072964E-2,{"$f":"((E22*F22*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I22*J22*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M22*N22*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q22*R22*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F22+J22+N22+R22)","v":107.84281641680522},0,{"$f":"((M22*N22*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q22*R22*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U22*V22*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N22+R22+V22)","v":100.61481048602045},115.22,-0.12675915217826383]
["307-01.01","ASPHALT CONCRETE MIX (PG64-22) (BPMB-HM) GRADING A",0,91339.842499999999,88.53,61227,0,null,81.83,111066,0,{"$f":"IFERROR(IF((K23/G23)-1<#REF!,\"\",(K23/G23)-1),\"\")","v":""},98.53,41219.06,0,{"$f":"IFERROR(IF((O23/K23)-1<#REF!,\"\",(O23/K23)-1),\"\")","v":""},77.150000000000006,151847.31,0,{"$f":"IFERROR(IF((S23/O23)-1<#REF!,\"\",(S23/O23)-1),\"\")","v":""},128.61000000000001,928.63,0,null,123.51,1695.41,null,-3.9654770235596049E-2,{"$f":"((E23*F23*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I23*J23*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M23*N23*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q23*R23*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F23+J23+N23+R23)","v":117.99325237415435},0,{"$f":"((M23*N23*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q23*R23*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U23*V23*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N23+R23+V23)","v":106.8586677617279},128.61000000000001,-0.16912629063270435]
["307-(01, 02, 03).01","ASPHALT CONCRETE MIX (ALL GRADES) (BPMB-HM) GRADING A",{"$f":"'Finalize Items'!$G$44","v":0},384173.96500000003,{"$f":"((E21*F21)+(E22*F22)+(E23*F23))/(SUM(F21:F23))","v":79.667262083877162},{"$f":"SUM(F21:F23)","v":333657.19},0,null,{"$f":"((I21*J21)+(I22*J22)+(I23*J23))/(SUM(J21:J23))","v":83.595653216875817},{"$f":"SUM(J21:J23)","v":273885.3},0,{"$f":"IFERROR(IF((K24/G24)-1<#REF!,\"\",(K24/G24)-1),\"\")","v":""},{"$f":"((M21*N21)+(M22*N22)+(M23*N23))/(SUM(N21:N23))","v":76.040729181631619},{"$f":"SUM(N21:N23)","v":311979.06},0,{"$f":"IFERROR(IF((O24/K24)-1<#REF!,\"\",(O24/K24)-1),\"\")","v":""},{"$f":"((Q21*R21)+(Q22*R22)+(Q23*R23))/(SUM(R21:R23))","v":78.341471142083009},{"$f":"SUM(R21:R23)","v":617174.31000000006},0,{"$f":"IFERROR(IF((S24/O24)-1<#REF!,\"\",(S24/O24)-1),\"\")","v":""},{"$f":"VLOOKUP(A24,'SUP 2022'!A:L,11,0)","v":112.3725689865221},{"$f":"SUM(V21:V23)","v":9787.64},0,null,{"$f":"SUMPRODUCT(Y21:Y23,Z21:Z23)/SUM(Z21:Z23)","v":124.26208009204254},{"$f":"SUM(Z21:Z23)","v":13837.08},null,0.10580438992140917,{"$f":"((E24*F24*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I24*J24*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M24*N24*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q24*R24*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F24+J24+N24+R24)","v":112.34080340452456},0,{"$f":"((M24*N24*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q24*R24*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U24*V24*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N24+R24+V24)","v":103.01091830325868},112.3725689865221,-8.3309038564262528E-2]
["313-03","TREATED PERMEABLE BASE",{"$f":"'Finalize Items'!G91","v":0},86877.5,20.28,62695,{"$f":"C25*E25","v":0},null,20.39,108656,0,{"$f":"IFERROR(IF((K25/G25)-1<#REF!,\"\",(K25/G25)-1),\"\")","v":""},20.39,108656,0,{"$f":"IFERROR(IF((O25/K25)-1<#REF!,\"\",(O25/K25)-1),\"\")","v":""},18.38,67503,0,{"$f":"IFERROR(IF((S25/O25)-1<#REF!,\"\",(S25/O25)-1),\"\")","v":""},37.15,7012.5,0,null,32.69,18157.66,null,-0.12005383580080753,{"$f":"((E25*F25*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I25*J25*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M25*N25*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q25*R25*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F25+J25+N25+R25)","v":29.563591405215092},0,{"$f":"((M25*N25*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q25*R25*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U25*V25*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N25+R25+V25)","v":28.201892346252762},37.15,-0.24086427062576676]
["501-01.03","PORTLAND CEMENT CONCRETE PAVEMENT (PLAIN) 10\"",{"$f":"'Finalize Items'!G94","v":0},60346,105.91,62246,0,null,104.95,66706,0,{"$f":"IFERROR(IF((K26/G26)-1<#REF!,\"\",(K26/G26)-1),\"\")","v":""},104.95,66706,0,{"$f":"IFERROR(IF((O26/K26)-1<#REF!,\"\",(O26/K26)-1),\"\")","v":""},117.14,45726,0,{"$f":"IFERROR(IF((S26/O26)-1<#REF!,\"\",(S26/O26)-1),\"\")","v":""},168.77,6641.49,0,null,155.51,13127.49,null,-7.8568465959590106E-2,{"$f":"((E26*F26*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I26*J26*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M26*N26*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q26*R26*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F26+J26+N26+R26)","v":158.73192035213879},0,{"$f":"((M26*N26*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q26*R26*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U26*V26*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N26+R26+V26)","v":154.90408606451177},168.77,-8.2158641556486556E-2]
["604-01.01","CLASS A CONCRETE (ROADWAY)",{"$f":"'Finalize Items'!G104","v":0},5068.7950000000001,898.09,1746.98,0,null,717.57,6393.07,0,{"$f":"IFERROR(IF((K27/G27)-1<#REF!,\"\",(K27/G27)-1),\"\")","v":""},717.57,6393.07,0,{"$f":"IFERROR(IF((O27/K27)-1<#REF!,\"\",(O27/K27)-1),\"\")","v":""},1000.44,5742.06,0,{"$f":"IFERROR(IF((S27/O27)-1<#REF!,\"\",(S27/O27)-1),\"\")","v":""},1147.29,275.85000000000002,0,null,1333.8,364.46,null,0.16256569829772771,{"$f":"((E27*F27*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I27*J27*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M27*N27*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q27*R27*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F27+J27+N27+R27)","v":1159.8738470675812},0,{"$f":"((M27*N27*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q27*R27*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U27*V27*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N27+R27+V27)","v":1157.4507431185352},1157.4507431185352,8.8562988595171088E-3]
["701-01.01","CONCRETE SIDEWALK (4 \")",{"$f":"'Finalize Items'!$E$362","v":0},548097.66249999998,5.27,423466.15,{"$f":"C28*E28","v":0},null,6.97,607309,0,{"$f":"IFERROR(IF((K28/G28)-1<#REF!,\"\",(K28/G28)-1),\"\")","v":""},5.84,364268.5,0,{"$f":"IFERROR(IF((O28/K28)-1<#REF!,\"\",(O28/K28)-1),\"\")","v":""},6.44,797347,0,{"$f":"IFERROR(IF((S28/O28)-1<#REF!,\"\",(S28/O28)-1),\"\")","v":""},10.53,6266.39,0,null,9.89,16807.8,null,-6.0778727445394032E-2,{"$f":"((E28*F28*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I28*J28*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M28*N28*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q28*R28*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F28+J28+N28+R28)","v":8.927038015073709},0,{"$f":"((M28*N28*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q28*R28*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U28*V28*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N28+R28+V28)","v":8.2404181099686387},10.53,-0.21743417759082251]
["702-03","CONCRETE COMBINED CURB & GUTTER",{"$f":"'Finalize Items'!$E$372","v":0},9209.5600000000013,324.55,7806,0,null,396.48,7917,0,{"$f":"IFERROR(IF((K29/G29)-1<#REF!,\"\",(K29/G29)-1),\"\")","v":""},373.12,8869.44,0,{"$f":"IFERROR(IF((O29/K29)-1<#REF!,\"\",(O29/K29)-1),\"\")","v":""},417.09,12245.8,0,{"$f":"IFERROR(IF((S29/O29)-1<#REF!,\"\",(S29/O29)-1),\"\")","v":""},552.34,220.38,0,null,603.04,367.09,null,9.1791287974797964E-2,{"$f":"((E29*F29*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I29*J29*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M29*N29*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q29*R29*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F29+J29+N29+R29)","v":545.99809388064455},0,{"$f":"((M29*N29*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q29*R29*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U29*V29*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N29+R29+V29)","v":535.7600410814548},552.34,-3.0017668317603663E-2]
["711-05.71","51IN SINGLE SLOPE CONCRETE BARRIER WALL",{"$f":"'Finalize Items'!E376","v":0},19417.125,90.06,28217.5,0,null,81.96,11413,0,{"$f":"IFERROR(IF((K30/G30)-1<#REF!,\"\",(K30/G30)-1),\"\")","v":""},81.96,11413,0,{"$f":"IFERROR(IF((O30/K30)-1<#REF!,\"\",(O30/K30)-1),\"\")","v":""},137.75,26625,0,{"$f":"IFERROR(IF((S30/O30)-1<#REF!,\"\",(S30/O30)-1),\"\")","v":""},217.47,3014.74,0,null,281.13,1455.83,null,0.2927300317285142,{"$f":"((E30*F30*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I30*J30*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M30*N30*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q30*R30*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F30+J30+N30+R30)","v":146.76114599828719},0,{"$f":"((M30*N30*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q30*R30*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U30*V30*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N30+R30+V30)","v":163.27466761307741},217.47,-0.24920831556960765]
["203-03","BORROW EXCAVATION (UNCLASSIFIED)",{"$f":"'Finalize Items'!$E$388","v":0},883592.95,5.62,1133349.8,0,null,3.63,1534528,0,{"$f":"IFERROR(IF((K31/G31)-1<#REF!,\"\",(K31/G31)-1),\"\")","v":""},11.33,518127,0,{"$f":"IFERROR(IF((O31/K31)-1<#REF!,\"\",(O31/K31)-1),\"\")","v":""},8.5,348367,0,{"$f":"IFERROR(IF((S31/O31)-1<#REF!,\"\",(S31/O31)-1),\"\")","v":""},12.41,37036.19,0,null,19.3,24690.11,null,0.55519742143432715,{"$f":"((E31*F31*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I31*J31*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M31*N31*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q31*R31*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F31+J31+N31+R31)","v":8.8014465322070414},0,{"$f":"((M31*N31*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q31*R31*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U31*V31*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N31+R31+V31)","v":14.40596797906513},14.40596797906513,0.1608354535910661]
["203-01","ROAD & DRAINAGE EXCAVATION (UNCLASSIFIED)",{"$f":"'Finalize Items'!$E$380","v":0},4492863.6349999998,8.5,2240736.44,0,null,7.02,5546458,0,{"$f":"IFERROR(IF((K32/G32)-1<#REF!,\"\",(K32/G32)-1),\"\")","v":""},9.68,3463886.1,0,{"$f":"IFERROR(IF((O32/K32)-1<#REF!,\"\",(O32/K32)-1),\"\")","v":""},8.25,6720374,0,{"$f":"IFERROR(IF((S32/O32)-1<#REF!,\"\",(S32/O32)-1),\"\")","v":""},14.81,54855.41,0,null,17.18,40134.28,null,0.16002700877785281,{"$f":"((E32*F32*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I32*J32*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M32*N32*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q32*R32*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F32+J32+N32+R32)","v":11.619222132422525},0,{"$f":"((M32*N32*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q32*R32*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U32*V32*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N32+R32+V32)","v":11.70951910603654},14.81,-0.20935049925479143]
["203-02.01","BORROW EXCAVATION (GRADED SOLID ROCK)",{"$f":"'Finalize Items'!E386","v":0},855664.75,19.79,162380,0,null,30.31,801679,0,{"$f":"IFERROR(IF((K33/G33)-1<#REF!,\"\",(K33/G33)-1),\"\")","v":""},30.31,801679,0,{"$f":"IFERROR(IF((O33/K33)-1<#REF!,\"\",(O33/K33)-1),\"\")","v":""},20.05,1656921,0,{"$f":"IFERROR(IF((S33/O33)-1<#REF!,\"\",(S33/O33)-1),\"\")","v":""},32.33,42054.73,0,null,60.67,9885.18,null,0.8765852149706157,{"$f":"((E33*F33*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I33*J33*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M33*N33*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q33*R33*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F33+J33+N33+R33)","v":35.045809159891199},0,{"$f":"((M33*N33*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q33*R33*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U33*V33*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N33+R33+V33)","v":31.662133804145714},32.33,-2.0657785210463464E-2]
["105-01","CONSTRUCTION STAKES, LINES AND GRADES",0,89,58428.47,76,0,null,46057.85,109,0,{"$f":"IFERROR(IF((K34/G34)-1<#REF!,\"\",(K34/G34)-1),\"\")","v":""},46057.85,109,0,{"$f":"IFERROR(IF((O34/K34)-1<#REF!,\"\",(O34/K34)-1),\"\")","v":""},154524.46,62,0,{"$f":"IFERROR(IF((S34/O34)-1<#REF!,\"\",(S34/O34)-1),\"\")","v":""},{"$f":"VLOOKUP(A34,'SUP 2022'!A:L,11,0)","v":157490},73.5,0,null,170364.78,1,null,8.1749825385738717E-2,{"$f":"((E34*F34*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I34*J34*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M34*N34*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q34*R34*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F34+J34+N34+R34)","v":95844.330329713965},0,{"$f":"((M34*N34*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q34*R34*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U34*V34*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N34+R34+V34)","v":134289.49358616918},157490,-0.1473141559072374]
["710-02","Aggregate Underdrains (with pipe)",{"$f":"'Finalize Items'!$E$334","v":0},362221.19,6.76,308515,0,null,5.96,277866,0,{"$f":"IFERROR(IF((K35/G35)-1<#REF!,\"\",(K35/G35)-1),\"\")","v":""},6.57,294370,0,{"$f":"IFERROR(IF((O35/K35)-1<#REF!,\"\",(O35/K35)-1),\"\")","v":""},6.99,568133.76,0,{"$f":"IFERROR(IF((S35/O35)-1<#REF!,\"\",(S35/O35)-1),\"\")","v":""},13.48,5293.28,0,null,13.31,13226.34,null,-1.2611275964391711E-2,{"$f":"((E35*F35*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I35*J35*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M35*N35*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q35*R35*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F35+J35+N35+R35)","v":9.4269728134751389},0,{"$f":"((M35*N35*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q35*R35*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U35*V35*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N35+R35+V35)","v":9.1039517581764784},13.48,-0.32463265888898529]
["611-12.02","CATCH BASINS, TYPE 12, > 4' - 8' DEPTH",{"$f":"'Finalize Items'!$E$254","v":0},295.5,4204.17,280,0,null,4164.6400000000003,243,{"$f":"C36*I36","v":0},{"$f":"IFERROR(IF((K36/G36)-1<#REF!,\"\",(K36/G36)-1),\"\")","v":""},4524.8999999999996,245,{"$f":"C36*M36","v":0},{"$f":"IFERROR(IF((O36/K36)-1<#REF!,\"\",(O36/K36)-1),\"\")","v":""},6324.61,414,{"$f":"C36*Q36","v":0},{"$f":"IFERROR(IF((S36/O36)-1<#REF!,\"\",(S36/O36)-1),\"\")","v":""},11799.31,16.68,0,null,8113.47,29.78,null,-0.31237758818100381,{"$f":"((E36*F36*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I36*J36*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M36*N36*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q36*R36*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F36+J36+N36+R36)","v":7038.5037738381079},0,{"$f":"((M36*N36*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q36*R36*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U36*V36*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N36+R36+V36)","v":7596.2803042145779},11799.31,-0.35620978648627943]
["611-07.01","CLASS A CONCRETE (PIPE ENDWALLS)",{"$f":"'Finalize Items'!$E$238","v":0},611.88,1215.5999999999999,385.43,0,null,1269.71,762.16,0,{"$f":"IFERROR(IF((K37/G37)-1<#REF!,\"\",(K37/G37)-1),\"\")","v":""},1405.43,655,0,{"$f":"IFERROR(IF((O37/K37)-1<#REF!,\"\",(O37/K37)-1),\"\")","v":""},1605.84,644.92999999999995,0,{"$f":"IFERROR(IF((S37/O37)-1<#REF!,\"\",(S37/O37)-1),\"\")","v":""},1782.22,14.82,0,null,2156.1799999999998,16.38,null,0.20982819180572543,{"$f":"((E37*F37*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I37*J37*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M37*N37*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q37*R37*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F37+J37+N37+R37)","v":1997.864133089711},0,{"$f":"((M37*N37*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q37*R37*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U37*V37*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N37+R37+V37)","v":2049.5951925546037},2049.5951925546037,0.15002367415616691]
["611-07.02","STEEL BAR REINFORCEMENT (PIPE ENDWALLS)",{"$f":"'Finalize Items'!$E$239","v":0},27891,2.4,16392,0,null,2.74,30147,0,{"$f":"IFERROR(IF((K38/G38)-1<#REF!,\"\",(K38/G38)-1),\"\")","v":""},3.31,25298,0,{"$f":"IFERROR(IF((O38/K38)-1<#REF!,\"\",(O38/K38)-1),\"\")","v":""},2.34,39727,0,{"$f":"IFERROR(IF((S38/O38)-1<#REF!,\"\",(S38/O38)-1),\"\")","v":""},{"$f":"VLOOKUP(A38,'SUP 2022'!A:L,11,0)","v":3.96},604.64,0,null,4.08,731.51,null,3.0303030303030276E-2,{"$f":"((E38*F38*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I38*J38*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M38*N38*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q38*R38*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F38+J38+N38+R38)","v":3.8519987174585903},0,{"$f":"((M38*N38*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q38*R38*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U38*V38*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N38+R38+V38)","v":3.7112614560429771},3.96,-6.2812763625510804E-2]
["611-42.02","CATCH BASINS, TYPE 42, > 4' - 8' DEPTH",{"$f":"'Finalize Items'!$E$301","v":0},29.5,4987.7,19,0,null,5204.43,17,0,{"$f":"IFERROR(IF((K39/G39)-1<#REF!,\"\",(K39/G39)-1),\"\")","v":""},5029.08,26,0,{"$f":"IFERROR(IF((O39/K39)-1<#REF!,\"\",(O39/K39)-1),\"\")","v":""},5762.77,56,0,{"$f":"IFERROR(IF((S39/O39)-1<#REF!,\"\",(S39/O39)-1),\"\")","v":""},12425.36,5,0,null,8249.02,3.66,null,-0.33611420514174239,{"$f":"((E39*F39*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I39*J39*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M39*N39*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q39*R39*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F39+J39+N39+R39)","v":7468.5824776814898},0,{"$f":"((M39*N39*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q39*R39*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U39*V39*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N39+R39+V39)","v":7675.166566022177},12425.36,-0.38229825405282614]
["611-14.02","CATCH BASINS, TYPE 14, > 4' - 8' DEPTH",{"$f":"'Finalize Items'!$E$260","v":0},64.75,7081.15,50,0,null,9018.06,75,0,{"$f":"IFERROR(IF((K40/G40)-1<#REF!,\"\",(K40/G40)-1),\"\")","v":""},7989.43,53,0,{"$f":"IFERROR(IF((O40/K40)-1<#REF!,\"\",(O40/K40)-1),\"\")","v":""},9098.6200000000008,81,0,{"$f":"IFERROR(IF((S40/O40)-1<#REF!,\"\",(S40/O40)-1),\"\")","v":""},12478.19,3.06,0,null,11628.28,12.93,null,-6.8111641191550998E-2,{"$f":"((E40*F40*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I40*J40*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M40*N40*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q40*R40*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F40+J40+N40+R40)","v":12144.615229556974},0,{"$f":"((M40*N40*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q40*R40*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U40*V40*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N40+R40+V40)","v":11615.846862535207},12478.19,-6.9108030689129851E-2]
["607-05.02","24\" CONCRETE PIPE CULVERT (CLASS III)",{"$f":"'Finalize Items'!$E$179","v":0},17681.127499999999,80.209999999999994,13815,0,null,79.84,21629,0,{"$f":"IFERROR(IF((K41/G41)-1<#REF!,\"\",(K41/G41)-1),\"\")","v":""},75.19,13948,0,{"$f":"IFERROR(IF((O41/K41)-1<#REF!,\"\",(O41/K41)-1),\"\")","v":""},99.65,21332.51,0,{"$f":"IFERROR(IF((S41/O41)-1<#REF!,\"\",(S41/O41)-1),\"\")","v":""},172.02,123.03,0,null,137.55000000000001,915.32,null,-0.20038367631670739,{"$f":"((E41*F41*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I41*J41*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M41*N41*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q41*R41*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F41+J41+N41+R41)","v":121.70228773235458},0,{"$f":"((M41*N41*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q41*R41*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U41*V41*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N41+R41+V41)","v":119.46565282403023},172.02,-0.30551300532478654]
["415-01.02","COLD PLANING BITUMINOUS PAVEMENT",{"$f":"'Finalize Items'!$E$31","v":0},2544481.75,2.08,4423644,0,null,2.34,4023940,0,{"$f":"IFERROR(IF((K42/G42)-1<#REF!,\"\",(K42/G42)-1),\"\")","v":""},3.1,1167507.78,0,{"$f":"IFERROR(IF((O42/K42)-1<#REF!,\"\",(O42/K42)-1),\"\")","v":""},4.1100000000000003,562835.22,0,{"$f":"IFERROR(IF((S42/O42)-1<#REF!,\"\",(S42/O42)-1),\"\")","v":""},9.94,2966,0,null,9.6,3494.73,null,-3.4205231388329982E-2,{"$f":"((E42*F42*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I42*J42*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M42*N42*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q42*R42*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F42+J42+N42+R42)","v":3.6652192951120321},0,{"$f":"((M42*N42*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q42*R42*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U42*V42*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N42+R42+V42)","v":4.8076864457504156},9.94,-0.51632933141343906]
["202-03.01","REMOVAL OF ASPHALT PAVEMENT",{"$f":"'Finalize Items'!$G$22","v":0},118440.77499999999,11.41,92603.1,0,null,19.23,95807,0,{"$f":"IFERROR(IF((K43/G43)-1<#REF!,\"\",(K43/G43)-1),\"\")","v":""},6.36,222923,0,{"$f":"IFERROR(IF((O43/K43)-1<#REF!,\"\",(O43/K43)-1),\"\")","v":""},22.93,62430,0,{"$f":"IFERROR(IF((S43/O43)-1<#REF!,\"\",(S43/O43)-1),\"\")","v":""},16.37,5064.74,0,null,20.64,2204.52,null,0.26084300549786188,{"$f":"((E43*F43*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I43*J43*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M43*N43*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q43*R43*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F43+J43+N43+R43)","v":17.727780575305445},0,{"$f":"((M43*N43*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q43*R43*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U43*V43*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N43+R43+V43)","v":13.762962955000921},16.37,-0.15925699725101283]
["202-03","REMOVAL OF RIGID PAVEMENT",{"$f":"'Finalize Items'!G23","v":0},37248.050000000003,6.11,33932,0,null,7.49,20853,0,{"$f":"IFERROR(IF((K44/G44)-1<#REF!,\"\",(K44/G44)-1),\"\")","v":""},11.3,64027,0,{"$f":"IFERROR(IF((O44/K44)-1<#REF!,\"\",(O44/K44)-1),\"\")","v":""},12.22,30180.2,0,{"$f":"IFERROR(IF((S44/O44)-1<#REF!,\"\",(S44/O44)-1),\"\")","v":""},{"$f":"VLOOKUP(A44,'SUP 2022'!A:L,11,0)","v":28.33},11811,0,null,45.23,643.52,null,0.5965407695022944,{"$f":"((E44*F44*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I44*J44*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M44*N44*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q44*R44*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F44+J44+N44+R44)","v":14.167906770008987},0,{"$f":"((M44*N44*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q44*R44*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U44*V44*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N44+R44+V44)","v":18.220843075097637},28.33,-0.35683575449708305]
["801-01","SEEDING (WITH MULCH)",{"$f":"'Finalize Items'!G513","v":0},7093.3850000000002,26.96,6421.95,0,null,30.97,5456,0,{"$f":"IFERROR(IF((K45/G45)-1<#REF!,\"\",(K45/G45)-1),\"\")","v":""},30.97,5456.4,0,{"$f":"IFERROR(IF((O45/K45)-1<#REF!,\"\",(O45/K45)-1),\"\")","v":""},30.5,11039.19,0,{"$f":"IFERROR(IF((S45/O45)-1<#REF!,\"\",(S45/O45)-1),\"\")","v":""},54.58,207.44,0,null,65.16,64.91,null,0.19384389886405273,{"$f":"((E45*F45*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I45*J45*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M45*N45*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q45*R45*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F45+J45+N45+R45)","v":42.41720731891148},0,{"$f":"((M45*N45*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q45*R45*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U45*V45*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N45+R45+V45)","v":40.919145744193159},54.58,-0.2502904773874467]
["801-01.07","TEMPORARY SEEDING (WITH MULCH)",{"$f":"'Finalize Items'!G515","v":0},30655.75,21.89,28984,0,null,21.82,24378,0,{"$f":"IFERROR(IF((K46/G46)-1<#REF!,\"\",(K46/G46)-1),\"\")","v":""},21.82,24378,0,{"$f":"IFERROR(IF((O46/K46)-1<#REF!,\"\",(O46/K46)-1),\"\")","v":""},25.52,44883,0,{"$f":"IFERROR(IF((S46/O46)-1<#REF!,\"\",(S46/O46)-1),\"\")","v":""},35.33,635.4,0,null,45.9,520.54999999999995,null,0.29917916784602316,{"$f":"((E46*F46*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I46*J46*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M46*N46*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q46*R46*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F46+J46+N46+R46)","v":32.913496113462536},0,{"$f":"((M46*N46*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q46*R46*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U46*V46*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N46+R46+V46)","v":32.075266133051166},35.33,-9.2123800366511022E-2]
["801-02","SEEDING (WITHOUT MULCH)",{"$f":"'Finalize Items'!G516","v":0},9824.4825000000001,19.28,2815,0,null,21.22,8880.5,0,{"$f":"IFERROR(IF((K47/G47)-1<#REF!,\"\",(K47/G47)-1),\"\")","v":""},21.22,8880.5,0,{"$f":"IFERROR(IF((O47/K47)-1<#REF!,\"\",(O47/K47)-1),\"\")","v":""},22.33,18721.93,0,{"$f":"IFERROR(IF((S47/O47)-1<#REF!,\"\",(S47/O47)-1),\"\")","v":""},42.37,255.52,0,null,42.23,342.94,null,-3.3042246872787562E-3,{"$f":"((E47*F47*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I47*J47*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M47*N47*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q47*R47*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F47+J47+N47+R47)","v":29.90269289743329},0,{"$f":"((M47*N47*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q47*R47*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U47*V47*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N47+R47+V47)","v":29.175498649774305},42.37,-0.31141140784105958]
["712-02.02","INTERCONNECTED PORTABLE BARRIER RAIL",{"$f":"'Finalize Items'!G550","v":0},269719.25,30.75,351701,0,null,29.69,214233,0,{"$f":"IFERROR(IF((K48/G48)-1<#REF!,\"\",(K48/G48)-1),\"\")","v":""},29.69,214233,0,{"$f":"IFERROR(IF((O48/K48)-1<#REF!,\"\",(O48/K48)-1),\"\")","v":""},42.34,298710,0,{"$f":"IFERROR(IF((S48/O48)-1<#REF!,\"\",(S48/O48)-1),\"\")","v":""},46.05,3792.51,0,null,47.43,4680.26,null,2.9967426710097778E-2,{"$f":"((E48*F48*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I48*J48*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M48*N48*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q48*R48*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F48+J48+N48+R48)","v":48.265669542668945},0,{"$f":"((M48*N48*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q48*R48*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U48*V48*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N48+R48+V48)","v":49.158477882387984},49.158477882387984,6.7502234145233153E-2]
["716-12.02","ENHANCED FLAT THERMO P.M. (6IN) ",{"$f":"'Finalize Items'!G733","v":0},2971.8824999999997,4801.9399999999996,2666.44,0,null,4938.01,2625.53,0,{"$f":"IFERROR(IF((K49/G49)-1<#REF!,\"\",(K49/G49)-1),\"\")","v":""},5006.8599999999997,2981.61,0,{"$f":"IFERROR(IF((O49/K49)-1<#REF!,\"\",(O49/K49)-1),\"\")","v":""},5166.9399999999996,3613.95,0,{"$f":"IFERROR(IF((S49/O49)-1<#REF!,\"\",(S49/O49)-1),\"\")","v":""},7419.17,15.68,0,null,7529.96,14.13,null,1.4932937242306155E-2,{"$f":"((E49*F49*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I49*J49*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M49*N49*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q49*R49*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F49+J49+N49+R49)","v":7207.2226068181335},0,{"$f":"((M49*N49*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q49*R49*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U49*V49*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N49+R49+V49)","v":6906.4279961165812},7419.17,-6.9110426622306709E-2]
["709-05.05","Machined Rip-Rap (Class A-3)",{"$f":"'Finalize Items'!G767","v":0},49209.26,34.99,60140.04,0,null,39.21,52068,0,{"$f":"IFERROR(IF((K50/G50)-1<#REF!,\"\",(K50/G50)-1),\"\")","v":""},39.21,52068,0,{"$f":"IFERROR(IF((O50/K50)-1<#REF!,\"\",(O50/K50)-1),\"\")","v":""},40.880000000000003,32561,0,{"$f":"IFERROR(IF((S50/O50)-1<#REF!,\"\",(S50/O50)-1),\"\")","v":""},58.81,272.23,0,null,67.8,477.37,null,0.15286515898656683,{"$f":"((E50*F50*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I50*J50*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M50*N50*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q50*R50*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F50+J50+N50+R50)","v":56.776564300659658},0,{"$f":"((M50*N50*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q50*R50*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U50*V50*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N50+R50+V50)","v":55.739598491633465},58.81,-5.2208833673976107E-2]
["705-01.01","GUARDRAIL AT BRIDGE ENDS",{"$f":"'Finalize Items'!G477","v":0},4539.2924999999996,75.790000000000006,5109.17,0,null,75.52,5749,0,{"$f":"IFERROR(IF((K51/G51)-1<#REF!,\"\",(K51/G51)-1),\"\")","v":""},75.52,5749,0,{"$f":"IFERROR(IF((O51/K51)-1<#REF!,\"\",(O51/K51)-1),\"\")","v":""},72.09,1550,0,{"$f":"IFERROR(IF((S51/O51)-1<#REF!,\"\",(S51/O51)-1),\"\")","v":""},95.65,242.04,0,null,112.09,179.13,null,0.17187663355985361,{"$f":"((E51*F51*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I51*J51*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M51*N51*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q51*R51*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F51+J51+N51+R51)","v":113.96696584140972},0,{"$f":"((M51*N51*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q51*R51*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U51*V51*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N51+R51+V51)","v":108.39489090249624},108.39489090249624,0.13324506955040505]
["705-06.01 ","W Beam GR (Type 2) Mash TL3",{"$f":"'Finalize Items'!G479","v":0},133209.5625,20.190000000000001,77231.25,0,null,19.239999999999998,152466.75,0,{"$f":"IFERROR(IF((K52/G52)-1<#REF!,\"\",(K52/G52)-1),\"\")","v":""},19.239999999999998,152466.75,0,{"$f":"IFERROR(IF((O52/K52)-1<#REF!,\"\",(O52/K52)-1),\"\")","v":""},26.06,150673.5,0,{"$f":"IFERROR(IF((S52/O52)-1<#REF!,\"\",(S52/O52)-1),\"\")","v":""},{"$f":"VLOOKUP(A52,'SUP 2022'!A:L,11,0)","v":34.979999999999997},1593.66,0,null,34.659999999999997,1924.37,null,-9.1480846197827814E-3,{"$f":"((E52*F52*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I52*J52*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M52*N52*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q52*R52*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F52+J52+N52+R52)","v":30.461399512899028},0,{"$f":"((M52*N52*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q52*R52*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U52*V52*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N52+R52+V52)","v":30.612372943680416},34.979999999999997,-0.12486069343395034]
["705-06.20 ","Tangent Energy Absorbing Term Mash TL-3",{"$f":"'Finalize Items'!G486","v":0},3114,2696.69,2932,0,null,2629.08,2772,0,{"$f":"IFERROR(IF((K53/G53)-1<#REF!,\"\",(K53/G53)-1),\"\")","v":""},2629.08,2772,0,{"$f":"IFERROR(IF((O53/K53)-1<#REF!,\"\",(O53/K53)-1),\"\")","v":""},2768.31,3980,0,{"$f":"IFERROR(IF((S53/O53)-1<#REF!,\"\",(S53/O53)-1),\"\")","v":""},3457.56,17.39,0,null,3697.01,15.94,null,6.925404042156913E-2,{"$f":"((E53*F53*(1+('Const Index'!$E$13*(YEAR(TODAY())-2018))))+(I53*J53*(1+('Const Index'!$E$14*(YEAR(TODAY())-2019))))+(M53*N53*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q53*R53*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021)))))/(F53+J53+N53+R53)","v":3875.1840867862929},0,{"$f":"((M53*N53*(1+('Const Index'!$E$15*(YEAR(TODAY())-2020))))+(Q53*R53*(1+('Const Index'!$E$16*(YEAR(TODAY())-2021))))+(U53*V53*(1+('Const Index'!$E$17*(YEAR(TODAY())-2022)))))/(N53+R53+V53)","v":3640.9053721111818},3640.9053721111818,5.3027386975549762E-2]

{"sheet":"PE","index":27,"n_rows":671,"n_cols":20,"rows_kept":671,"cut":false,"hidden":true,"merged":[[7,20,7,21]]}
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"12620/17.8","v":708.98876404494376}]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,"Widen",38912,null,17112272.66,null,1163945.79]
["PIN","Project Type","Let Year","Year","PE","PE","Construction Let Price","Construction Expenditures","PE (2023)","Construction (2023)","%","Regression Equation","Difference"]
[100234.05,"Widen","2006-07-14",null,17112272.66,17112272.66,1163945.79,null,null,null,{"$f":"F35/G35","v":14.701949873455876},{"$f":"8.4856*G35^-0.305","v":0.11983207123385468},{"$f":"ABS(L35-K35)","v":14.582117802222021},1,{"$f":"N35/637","v":1.5698587127158557E-3}]
[100234.06,"Widen","2006-10-27",null,17112272.66,17112272.66,5311222.1100000003,null,null,null,3.2219086879799117,7.5422034706759011E-2,3.1464866532731528,{"$f":"N35+1","v":2},{"$f":"N36/637","v":3.1397174254317113E-3}]
[100234.02,"Modify Interchange","2006-10-27",null,17112272.66,17112272.66,14588777.880000001,null,null,null,1.1729750634876346,5.5418757894439979E-2,1.1175563055931945,{"$f":"N36+1","v":3},4.7095761381475663E-3]
[106015,"Bridge Replacement","2012-05-04",null,288764.65999999997,288764.65999999997,237173.8,null,null,null,1.2175234363998046,0.19466470175013448,1.0228587346496703,4,6.2794348508634227E-3]
[43803,"Construction-New","1999-06-11",null,13455709,13455709,13197460,null,null,null,1.0195680835554721,5.7139047668422149E-2,0.96242903588704998,5,7.8492935635792772E-3]
[105949,"Bridge Replacement","2011-09-16",null,159896,159896,138960.70000000001,null,null,null,1.1506562646849072,0.22913978324219186,0.92151648144271536,6,9.4191522762951327E-3]
[103948,"Bridge Replacement","2011-02-11",null,313884.34999999998,313884.34999999998,303443.75,null,null,null,1.0344070359003934,0.18057129214858827,0.85383574375180515,7,1.098901098901099E-2]
[11034,"Bridge Replacement","2011-05-06",null,340433.07,340433.07,341552.33,null,null,null,0.9967230204519465,0.17417190176288974,0.82255111868905673,8,1.2558869701726845E-2]
[101638,"Bridge Replacement","2009-03-20",null,345751.02,345751.02,390625.58,null,null,null,0.88512129697189823,0.16718432211316084,0.71793697485873742,9,1.4128728414442701E-2]
[10974,"Bridge Replacement","2011-08-05",null,134994.70000000001,134994.70000000001,177314.5,null,null,null,0.76132916371757531,0.21272354364669335,0.54860562007088198,10,1.5698587127158554E-2]
[40503,"Bridge Replacement","2012-12-07",null,169362.83,169362.83,249519.48,null,null,null,0.67875594322335064,0.19167509913940392,0.4870808440839467,11,1.726844583987441E-2]
[102230,"Bridge Replacement","2009-05-08",null,309197.99,309197.99,484056.3,null,null,null,0.63876451974697979,0.15659911861914852,0.48216540112783124,12,1.8838304552590265E-2]
[101631,"Bridge Replacement","2010-06-18",null,318123.57,318123.57,515652.77,null,null,null,0.61693369745691462,0.15360790377468383,0.46332579368223081,13,2.0408163265306121E-2]
[103879,"Bridge Replacement","2007-12-07",null,175432.83,175432.83,271490.98,null,null,null,0.64618290449281224,0.18680442402394154,0.4593784804688707,14,2.197802197802198E-2]
[101923,"Bridge Replacement","2010-10-29",null,246586.77,246586.77,406819.5,null,null,null,0.60613311308823692,0.16512583187376353,0.44100728121447341,15,2.3547880690737835E-2]
[106090,"Bridge Replacement","2010-12-10",null,166023.35999999999,166023.35999999999,268819.84000000003,null,null,null,0.61760084374724711,0.18736861811000041,0.43023222563724672,16,2.5117739403453691E-2]
[102223,"Bridge Replacement","2008-09-19",null,261259.49,261259.49,443877.23,null,null,null,0.5885850238364333,0.16079309004579481,0.42779193379063851,17,2.6687598116169546E-2]
[103855,"Bridge Replacement","2011-02-11",null,292071.67,292071.67,505991.03,null,null,null,0.57722697179038918,0.15449662490670413,0.42273034688368505,18,2.8257456828885402E-2]
[101922,"Bridge Replacement","2011-04-01",null,128590.18,128590.18,221478.1,null,null,null,0.58059997805652108,0.19877266714422431,0.38182731091229677,19,2.9827315541601257E-2]
[103856,"Bridge Replacement","2011-02-11",null,326933.19,326933.19,623963,null,null,null,0.52396246251780954,0.14493027304644943,0.37903218947136008,20,3.1397174254317109E-2]
[100410,"Bridge Replacement","2004-12-03",null,424510.68,424510.68,830353.42,null,null,null,0.51124096050570844,0.13283341784668032,0.3784075426590281,21,3.2967032967032968E-2]
[40522,"Bridge Replacement","2009-12-11",null,196844.09,196844.09,368845.15,null,null,null,0.53367677465733243,0.1701355668103661,0.36354120784696631,22,3.453689167974882E-2]
[103797,"Bridge Replacement","2011-09-16",null,126228.95,126228.95,228728,null,null,null,0.55187362281836938,0.19682948648169754,0.35504413633667187,23,3.6106750392464679E-2]
[101983,"Bridge Replacement","2007-08-31",null,202748.19,202748.19,391827.14,null,null,null,0.51744294690765935,0.16702778775073607,0.35041515915692328,24,3.7676609105180531E-2]
[103897,"Bridge Replacement","2011-12-09",null,256909.02,256909.02,509704,null,null,null,0.50403571484626364,0.15415249315340473,0.3498832216928589,25,3.924646781789639E-2]
[101173,"Bridge Replacement","2010-12-10",null,1264878.6499999999,1264878.6499999999,2985493.91,null,null,null,0.42367483844574311,8.9908886281541547E-2,0.33376595216420157,26,4.0816326530612242E-2]
[101944,"Bridge Replacement","2011-05-06",null,100713.8,100713.8,186266.47,null,null,null,0.54069742128038401,0.20955183932317326,0.33114558195721078,27,4.2386185243328101E-2]
[103460,"Bridge Replacement","2012-12-07",null,248355.8,248355.8,513699.92,null,null,null,0.48346474338559364,0.15378577263538026,0.32967897075021335,28,4.3956043956043959E-2]
[107683,"Bridge Replacement","2011-09-16",null,138959.93,138959.93,271706.17,null,null,null,0.51143457655010194,0.18675928739250569,0.32467528915759625,29,4.5525902668759811E-2]
[100428,"Bridge Replacement","2008-06-20",null,417179.02,417179.02,921984.28,null,null,null,0.45247953685284092,0.12865950712961716,0.32382002972322377,30,4.709576138147567E-2]
[10964,"Bridge Replacement","2009-06-12",null,354232.95,354232.95,810176.04,null,null,null,0.43722960506212943,0.13383380956405946,0.30339579549806994,31,4.8665620094191522E-2]
[103871,"Bridge Replacement","2009-03-20",null,195600.14,195600.14,425820.65,null,null,null,0.4593486483100338,0.16284274204622237,0.29650590626381146,32,5.0235478806907381E-2]
[40433,"Bridge Replacement","2011-02-11",null,119823.87,119823.87,249885.3,null,null,null,{"$f":"F67/G67","v":0.47951548170300534},0.19158947162549322,0.28792601007751212,33,5.1805337519623233E-2]
[103798,"Bridge Replacement","2009-06-12",null,93733.33,93733.33,193483.5,null,null,null,0.48445128395961412,0.20713627203109361,0.27731501192852048,34,5.3375196232339092E-2]
[101882,"Bridge Replacement","2006-12-08",null,88000.95,88000.95,180060.65,null,null,null,0.48872949197950799,0.21172874227809005,0.27700074970141797,35,5.4945054945054944E-2]
[102408,"Bridge Replacement","2012-03-23",null,105902.65,105902.65,224262.52,null,null,null,0.47222625519413586,0.19801667463443723,0.27420958055969863,36,5.6514913657770803E-2]
[103952,"Bridge Replacement","2011-04-01",null,135823.98000000001,135823.98000000001,305554.3,null,null,null,0.44451667019577212,0.18018996208340554,0.26432670811236658,37,5.8084772370486655E-2]
[101943,"Bridge Replacement","2007-07-13",null,136647.28,136647.28,310491.40000000002,null,null,null,0.44010004785961859,0.1793112075601884,0.26078884029943017,38,5.9654631083202514E-2]
[10947,"Bridge Replacement","2009-05-08",null,88276.7,88276.7,188104.5,null,null,null,0.46929605618153736,0.20892518930225218,0.26037086687928518,39,6.1224489795918366E-2]
[102032,"Bridge Replacement","2011-08-05",null,265761.55,265761.55,661848.19999999995,null,null,null,0.40154456867904154,0.1423479595559366,0.25919660912310494,40,6.2794348508634218E-2]
[102040,"Bridge Replacement","2011-06-17",null,321556.67,321556.67,836349.04,null,null,null,0.38447664147495164,0.13254225318302149,0.25193438829193016,41,6.4364207221350084E-2]
[100622,"Bridge Replacement","2015-07-10",null,172859.94,172859.94,424227.85,null,null,null,0.40746957089215152,0.16302897842371508,0.24444059246843644,42,6.5934065934065936E-2]
[102072,"Bridge Replacement","2009-03-20",null,77333.539999999994,77333.539999999994,169068.75,null,null,null,0.45740883516321018,0.21583567836038942,0.24157315680282077,43,6.7503924646781788E-2]
[40478,"Bridge Replacement","2007-12-07",null,269855.74,269855.74,713230.16,null,null,null,0.37835716313510914,0.13913855778344975,0.2392186053516594,44,6.907378335949764E-2]
[100353,"Reconstruction","2004-06-11",null,2478088.3199999998,2478088.3199999998,8118635.4500000002,null,null,null,0.30523458471090725,6.6265919473854018E-2,0.23896866523705323,45,7.0643642072213506E-2]
[103882,"Bridge Replacement","2008-02-15",null,130876.78,130876.78,314711,null,null,null,0.41586337941794216,0.17857449035814096,0.23728888905980119,46,7.2213500784929358E-2]
[100426,"Bridge Replacement","2007-10-19",null,312644.74,312644.74,848496.79,null,null,null,0.36846897205114937,0.13196058851356537,0.23650838353758399,47,7.378335949764521E-2]
[105360,"Bridge Replacement","2011-08-05",null,1737946.34,1737946.34,5605912.8399999999,null,null,null,0.31002022143462371,7.4190008664464777E-2,0.23583021277015892,48,7.5353218210361061E-2]
[46227,"Reconstruction","1999-10-22",null,2760441.66,2760441.66,9219889,null,null,null,0.29940074766626801,6.374427993383304E-2,0.23565646773243498,49,7.6923076923076927E-2]
[103973,"Bridge Replacement","2014-10-17",null,113015.16,113015.16,269730.37,null,null,null,0.41899308557653336,0.18717547855301961,0.23181760702351376,50,7.8492935635792779E-2]
[11028,"Bridge Replacement","2009-05-08",null,83171.820000000007,83171.820000000007,190090.23999999999,null,null,null,0.43753861323969084,0.20825709738251222,0.22928151585717862,51,8.0062794348508631E-2]
[40510,"Bridge Replacement","2011-06-17",null,330034.02,330034.02,929736.51,null,null,null,0.3549758630001526,0.12833135821356925,0.22664450478658335,52,8.1632653061224483E-2]
[102059,"Bridge Replacement","2007-04-27",null,197782.1,197782.1,525024.35,null,null,null,0.37671033733959197,0.15276639310792667,0.2239439442316653,53,8.3202511773940349E-2]
[40540,"Bridge Replacement","2011-05-06",null,347229.94,347229.94,994838.92,null,null,null,0.34903131855758113,0.12570946028038218,0.22332185827719894,54,8.4772370486656201E-2]
[40431,"Bridge Replacement","2009-05-08",null,183543.88,183543.88,485984.55,null,null,null,0.37767431083971703,0.15640934765711886,0.22126496318259817,55,8.6342229199372053E-2]
[101417,"Widen","2009-09-18",null,3520303.51,3520303.51,12773746.27,null,null,null,0.27558896470862809,5.7710585283235798E-2,0.21787837942539229,56,8.7912087912087919E-2]
[101643,"Bridge Replacement","2009-05-08",null,338389.11,338389.11,1010617.29,null,null,null,0.33483407947631688,0.12510757468579586,0.20972650479052102,57,8.9481946624803771E-2]
[40432,"Bridge Replacement","2010-08-06",null,213562.67,213562.67,599960.62,null,null,null,0.35596114624989889,0.146674669581564,0.20928647666833489,58,9.1051805337519623E-2]
[101728,"Bridge Replacement","2007-06-01",null,214529.26,214529.26,607287.68999999994,null,null,null,0.35325804150583068,0.14613264331932449,0.20712539818650619,59,9.2621664050235475E-2]
[102058,"Bridge Replacement","2007-04-27",null,164169.17000000001,164169.17000000001,446987.4,null,null,null,0.36727918952525285,0.16045102473730377,0.20682816478794908,60,9.4191522762951341E-2]
[106053,"Bridge Replacement","2007-10-19",null,180540.16,180540.16,507990.33,null,null,null,0.35540078095581074,0.15431091450078802,0.20108986645502272,61,9.5761381475667193E-2]
[40443,"Bridge Replacement","2008-03-28",null,114644.28,114644.28,303303,null,null,null,0.37798597442161797,0.1805968456384871,0.19738912878313086,62,9.7331240188383045E-2]
[103880,"Bridge Replacement","2012-06-15",null,168577.91,168577.91,478388.2,null,null,null,0.35238726624109873,0.15716271255682884,0.19522455368426989,63,9.8901098901098897E-2]
[102189,"Reconstruction","1995-04-28",{"$f":"YEAR(C98)","v":1995},1067774.77,1067774.77,8750104,null,null,null,{"$f":"F98/G98+0.02","v":0.14202995187257203},6.4769198870220729E-2,{"$f":"ABS(L98-K98)","v":7.7260753002351301E-2},64,0.10047095761381476]
[40198,"Bridge Replacement","1997-07-18",1997,41332.339999999997,41332.339999999997,282461,null,null,null,0.16632936936426621,{"$f":"8.4856*G99^-0.305","v":0.1845611194352306},1.8231750070964392E-2,65,0.10204081632653061]
[40144,"Bridge Replacement","1997-12-12",1997,104092.6,104092.6,1100387,null,null,null,0.11459635564578645,0.12190210169730692,7.3057460515204703E-3,66,{"$f":"N100/637","v":0.10361067503924647}]
[41127,"Widen","1998-12-11",1998,6008853.21,6008853.21,25676938,null,null,null,0.25401751447154641,4.6641431371356422E-2,0.20737608310018998,{"$f":"N100+1","v":67},0.10518053375196232]
[43791,"Construction-New","1999-12-10",1999,349206.2,349206.2,8113926,null,null,null,6.303788326390948E-2,6.6277647951397872E-2,3.2397646874883917E-3,68,0.10675039246467818]
[45538,"Widen","2000-09-15",2000,1497936.02,1497936.02,7542958,null,null,null,0.21858734729796983,6.7769197131285208E-2,0.15081815016668462,69,0.10832025117739404]
[45619,"Reconstruction","2000-05-12",2000,7914.67,7914.67,6699353,null,null,null,2.1181408115082158E-2,7.0265563409207921E-2,4.9084155294125763E-2,70,0.10989010989010989]
[40200,"Bridge Replacement","2000-08-11",2000,34024.97,34024.97,286446,null,null,null,0.13878319124721589,0.18377418838590126,4.4990997138685374E-2,71,0.11145996860282574]
[46452,"Construction-New","2000-12-08",2000,300046.64,300046.64,29986834,null,null,null,3.0005945942809434E-2,4.4485524775847253E-2,1.4479578833037819E-2,72,0.11302982731554161]
[45148,"Construction-New","2000-02-11",2000,522114.64,522114.64,4683273,null,null,null,0.1314849892372279,7.8372728380322013E-2,5.3112260856905888E-2,73,0.11459968602825746]
[40099,"Bridge Replacement","2000-10-27",2000,160057.82,160057.82,2188888,null,null,null,9.3122891623509299E-2,9.8835821423253201E-2,5.7129297997439016E-3,74,0.11616954474097331]
[40088,"Bridge Replacement","2000-12-08",2000,329644.21999999997,329644.21999999997,5987530,null,null,null,7.5055126237363309E-2,7.2714664825910102E-2,2.3404614114532069E-3,75,0.11773940345368916]
[41139,"Reconstruction","2000-08-11",2000,483385.94,483385.94,7768958,null,null,null,8.2220176759869215E-2,6.7161735476971338E-2,1.5058441282897878E-2,76,0.11930926216640503]
[44182,"Widen","2001-10-26",2001,664273.22,664273.22,4460813,null,null,null,0.16891303894603965,7.954470589470336E-2,8.9368333051336291E-2,77,0.12087912087912088]
[41393,"Widen","2001-10-26",2001,289223.03000000003,289223.03000000003,12964719,null,null,null,4.2308468853046489E-2,5.7449970211416859E-2,1.514150135837037E-2,78,0.12244897959183673]
[45616,"Widen","2001-10-26",2001,903645.79,903645.79,12347938.59,null,null,null,9.318191481222779E-2,5.8310430160612645E-2,3.4871484651615145E-2,79,0.12401883830455258]
[40067,"Bridge Replacement","2001-06-15",2001,588973.02,588973.02,10223778,null,null,null,7.7608158158363763E-2,6.1766227342602821E-2,1.5841930815760942E-2,80,0.12558869701726844]
[101459,"Widen","2002-07-26",2002,1307856.75,1307856.75,5462687.9100000001,null,null,null,0.25941634073691755,7.4777958961224161E-2,0.18463838177569339,81,0.1271585557299843]
[101039,"Widen","2002-03-15",2002,1300150.24,1300150.24,9777941.7599999998,null,null,null,0.15296768092020216,6.2611929096551722E-2,9.0355751823650438E-2,82,0.12872841444270017]
[45315,"Construction-New","2002-09-13",2002,1696222.6,1696222.6,14137513.470000001,null,null,null,0.13998026411075809,5.595240791685293E-2,8.4027856193905154E-2,83,0.13029827315541601]
[101191,"Bridge Replacement","2002-06-14",2002,72994.14,72994.14,881181.38,null,null,null,0.10283668000338364,0.13044806332346626,2.7611383320082616E-2,84,0.13186813186813187]
[100422,"Bridge Replacement","2002-07-26",2002,214653.78,214653.78,7010409.4500000002,null,null,null,5.0619292857423615E-2,6.9299615292219244E-2,1.8680322434795629E-2,85,0.13343799058084774]
[100363,"Bridge Replacement","2002-09-13",2002,126904.75,126904.75,1787877.5,null,null,null,9.0980674011502463E-2,0.10512827524967752,1.4147601238175059E-2,86,0.13500784929356358]
[100543,"Bridge Replacement","2002-03-15",2002,56035.83,56035.83,417947.07,null,null,null,0.15407398692853619,0.1637723436207536,9.6983566922174136E-3,87,0.13657770800627944]
[100527,"Bridge Replacement","2002-12-06",2002,265803.46999999997,265803.46999999997,2096638.97,null,null,null,0.14677598470851658,0.10014236449552508,4.66336202129915E-2,88,0.13814756671899528]
[101560,"Bridge Replacement","2002-09-13",2002,612116.22,612116.22,6609990.1299999999,null,null,null,0.11260471013744161,7.0553946021862213E-2,4.2050764115579398E-2,89,0.13971742543171115]
[41391,"Widen","2002-02-01",2002,1287498.29,1287498.29,20656513.140000001,null,null,null,8.2328926536339914E-2,4.9841392417542256E-2,3.2487534118797658E-2,90,0.14128728414442701]
[101045,"Widen","2003-10-24",2003,295636.38,295636.38,1033211.5,null,null,null,0.30613345863842983,0.12426672140760976,0.18186673723082009,91,0.14285714285714285]
[101557,"Bridge Replacement","2003-10-24",2003,163302.20000000001,163302.20000000001,629812.87,null,null,null,0.2792868576979064,0.1445183647726225,0.13476849292528389,92,0.14442700156985872]
[100646,"Bridge Replacement","2003-02-14",2003,71353.38,71353.38,258717.25,null,null,null,0.29579676268203997,0.18957052508298319,0.10622623759905678,93,0.14599686028257458]
[101693,"Bridge Replacement","2003-09-05",2003,545515.17000000004,545515.17000000004,3482870.87,null,null,null,0.17662802049276091,8.5781109094629465E-2,9.0846911398131447E-2,94,0.14756671899529042]
[101175,"Bridge Replacement","2003-09-05",2003,127416.6,127416.6,605062.94999999995,null,null,null,0.23058403923095938,0.14629631429635892,8.4287724934600461E-2,95,0.14913657770800628]
[100606,"Bridge Replacement","2003-09-05",2003,135042.14000000001,135042.14000000001,664420.19999999995,null,null,null,{"$f":"F130/G130+0.02","v":0.22324809510607899},0.14217966722846914,{"$f":"ABS(L130-K130)","v":8.1068427877609844E-2},96,0.15070643642072212]
[100600,"Bridge Replacement","2003-12-05",2003,332776.39,332776.39,2149992.7200000002,null,null,null,0.17478024037216272,9.9377776171923046E-2,7.5402464200239674E-2,97,0.15227629513343799]
[100357,"Reconstruction","2003-12-05",2003,470704.72,470704.72,3540248.01,null,null,null,0.1529581200724974,8.5354668742605333E-2,6.7603451329892067E-2,98,0.15384615384615385]
[101564,"Bridge Replacement","2003-03-21",2003,80412.100000000006,80412.100000000006,1037857.12,null,null,null,9.747896935948179E-2,0.12409680414210331,2.6617834782621516E-2,99,0.15541601255886969]
[101171,"Bridge Replacement","2003-12-05",2003,187288.12,187288.12,1171003.92,null,null,null,0.17993808116372487,0.11961131346101478,6.0326767702710088E-2,100,0.15698587127158556]
[101579,"Widen","2003-05-02",2003,1206641.51,1206641.51,12469849.51,null,null,null,0.11676472110047141,5.8135965048873181E-2,5.862875605159823E-2,101,0.15855572998430142]
[100662,"Bridge Replacement","2003-09-05",2003,207805.73,207805.73,3484647.92,null,null,null,7.9634641654127286E-2,8.5767764382265924E-2,6.1331227281386375E-3,102,0.16012558869701726]
[101212,"Construction-New","2003-12-05",2003,452746.48,452746.48,4242724.4400000004,null,null,null,0.12671126216247972,8.0770148989408985E-2,4.594111317307073E-2,103,0.16169544740973313]
[101562,"Bridge Replacement","2003-12-05",2003,228434.56,228434.56,3539430.65,null,null,null,8.4539916893130826E-2,8.5360680095798114E-2,8.2076320266728786E-4,104,0.16326530612244897]
[100501,"Bridge Replacement","2003-09-05",2003,398406.83,398406.83,9222523.4499999993,null,null,null,6.3199329571777887E-2,6.37387256973585E-2,5.393961255806129E-4,105,0.16483516483516483]
[101172,"Bridge Replacement","2003-09-05",2003,64028.09,64028.09,462956.71,null,null,null,0.15830254236945823,0.15874232578766334,4.3978341820510858E-4,106,0.1664050235478807]
[100513,"Bridge Replacement","2003-09-05",2003,148715.81,148715.81,1102226.28,null,null,null,0.15492312123060609,0.12184002335387965,3.3083097876726433E-2,107,0.16797488226059654]
[100598,"Bridge Replacement","2003-02-14",2003,176829.51,176829.51,1418165.12,null,null,null,0.14468894313237657,0.11282514022523621,3.1863802907140359E-2,108,0.1695447409733124]
[100274,"Reconstruction","2003-12-05",2003,536754.46,536754.46,10951846.25,null,null,null,6.9010408633156259E-2,6.0483778974218909E-2,8.52662965893735E-3,109,0.17111459968602827]
[100636,"Bridge Replacement","2003-07-25",2003,252775.5,252775.5,3232420.86,null,null,null,9.8200058392148862E-2,8.7755944763042687E-2,1.0444113629106175E-2,110,0.17268445839874411]
[100360,"Bridge Replacement","2003-10-24",2003,144542.81,144542.81,1381513.03,null,null,null,0.12462645437372386,0.11372980258718941,1.0896651786534442E-2,111,0.17425431711145997]
[101174,"Bridge Replacement","2003-02-14",2003,135902.76999999999,135902.76999999999,1042588.84,null,null,null,0.15035126100141258,0.12392475498483832,2.6426506016574258E-2,112,0.17582417582417584]
[100678,"Bridge Replacement","2003-09-05",2003,123172.99,123172.99,953219.11,null,null,null,0.1492179192672711,0.12735874475297823,2.1859174514292867E-2,113,0.17739403453689168]
[100383,"Bridge Replacement","2004-10-29",2004,352172.63,352172.63,1168140.3899999999,null,null,null,0.32148142553310743,0.11970066647320043,0.201780759059907,114,0.17896389324960754]
[100608,"Bridge Replacement","2004-10-29",2004,164386.18,164386.18,492156.9,null,null,null,0.35401173487560572,0.15580843467892622,0.1982033001966795,115,0.18053375196232338]
[101559,"Bridge Replacement","2004-09-03",2004,543119.04,543119.04,1974117.35,null,null,null,0.29511993651238616,0.10199850384159363,0.19312143267079251,116,0.18210361067503925]
[101561,"Bridge Replacement","2004-02-06",2004,230343.11,230343.11,1008212.38,null,null,null,0.24846685338261765,0.12519851796209214,0.12326833542052551,117,0.18367346938775511]
[101464,"Reconstruction","2004-12-03",2004,404729,404729,2380907.5499999998,null,null,null,0.18998938073004976,9.633322142459888E-2,9.3656159305450876E-2,118,0.18524332810047095]
[100602,"Bridge Replacement","2004-12-03",2004,43985.16,43985.16,538727.48,null,null,null,0.10164640125653142,0.15157060058726043,4.9924199330729016E-2,119,0.18681318681318682]
[100617,"Bridge Replacement","2004-10-29",2004,103827.59,103827.59,524959.07999999996,null,null,null,0.21778225380919214,0.15277218602166839,6.5010067787523745E-2,120,0.18838304552590268]
[101587,"Reconstruction","2004-06-11",2004,1240388.03,1240388.03,12582576.359999999,null,null,null,0.11857981342701743,5.7976612377303866E-2,6.0603201049713562E-2,121,0.18995290423861852]
[100276,"Reconstruction","2004-02-06",2004,841589.89,841589.89,8041000.54,null,null,null,0.12466233471985316,6.646040416213729E-2,5.8201930557715872E-2,122,0.19152276295133439]
[100562,"Bridge Replacement","2004-02-06",2004,388119.09,388119.09,3143495.1,null,null,null,0.14346737553368541,8.8505784427573994E-2,5.4961591106111415E-2,123,0.19309262166405022]
[100315,"Reconstruction","2004-02-06",2004,1076268.25,1076268.25,11860395.32,null,null,null,0.11074471979741735,5.903129498875425E-2,5.1713424808663096E-2,124,0.19466248037676609]
[100319,"Reconstruction","2004-05-07",2004,824478.74,824478.74,8738290.1699999999,null,null,null,0.1143524103640518,6.4795893794486775E-2,4.9556516569565029E-2,125,0.19623233908948196]
[100664,"Bridge Replacement","2004-09-03",2004,230632.02,230632.02,4734779.1900000004,null,null,null,6.8710195501218291E-2,7.8111708701404006E-2,9.4015132001857155E-3,126,0.19780219780219779]
[100405,"Bridge Replacement","2004-07-16",2004,60689.99,60689.99,287975.11,null,null,null,0.23074734549107387,0.18347601343973161,4.7271332051342263E-2,127,0.19937205651491366]
[101554,"Bridge Replacement","2004-12-03",{"$f":"YEAR(C162)","v":2004},872256.97,872256.97,9963887.9399999995,null,null,null,{"$f":"F162/G162+0.02","v":0.10754182857660682},6.2253211601322272E-2,{"$f":"ABS(L162-K162)","v":4.5288616975284551E-2},128,0.20094191522762953]
[101122,"Reconstruction","2004-12-03",2004,714044.32,714044.32,7833819.6299999999,null,null,null,0.11114893547785194,{"$f":"8.4856*G163^-0.305","v":6.6991641217686318E-2},4.4157294260165625E-2,129,0.20251177394034536]
[101433,"Widen","2004-07-16",2004,1028667.36,1028667.36,13279291.970000001,null,null,null,9.7464021600241993E-2,5.7031422663810345E-2,4.0432598936431648E-2,130,{"$f":"N164/637","v":0.20408163265306123}]
[101746,"Bridge Replacement","2004-02-06",2004,250340.06,250340.06,2084301.48,null,null,null,0.14010741363576634,0.10032278782912249,3.9784625806643853E-2,{"$f":"N164+1","v":131},0.20565149136577707]
[100559,"Bridge Replacement","2004-12-03",2004,97975.360000000001,97975.360000000001,591391.03,null,null,null,0.18566933725727966,0.14731967845296232,3.8349658804317344E-2,132,0.20722135007849293]
[102247,"Widen","2004-12-03",2004,278127.32,278127.32,4253579.38,null,null,null,8.5386653252019482E-2,8.0707226031803359E-2,4.679427220216123E-3,133,0.2087912087912088]
[100275,"Construction-New","2004-12-03",2004,934095.03,934095.03,13597816.470000001,null,null,null,8.8694487240715061E-2,5.6620598722573884E-2,3.2073888518141178E-2,134,0.21036106750392464]
[100401,"Bridge Replacement","2004-03-26",2004,44434.7,44434.7,245108.65,null,null,null,0.201285727778273,0.19272061427636958,8.5651135019034208E-3,135,0.2119309262166405]
[100597,"Bridge Replacement","2004-12-03",2004,110100.14,110100.14,751613.27,null,null,null,0.16648509332465616,0.13693177944798177,2.9553313876674397E-2,136,0.21350078492935637]
[100291,"Widen","2004-10-29",2004,1050232.3600000001,1050232.3600000001,29881812.109999999,null,null,null,5.5146207202358327E-2,4.4533152713229482E-2,1.0613054489128845E-2,137,0.21507064364207221]
[100949,"Widen","2004-07-16",2004,670883.32999999996,670883.32999999996,14069265,null,null,null,6.7684319685498845E-2,5.6035051555957713E-2,1.1649268129541132E-2,138,0.21664050235478807]
[100526,"Bridge Replacement","2004-12-03",2004,265777.27,265777.27,2651942.83,null,null,null,0.12021983392454957,9.3217078536654299E-2,2.7002755387895275E-2,139,0.21821036106750394]
[102023,"Bridge Replacement","2004-12-03",2004,187297.23,187297.23,1626795.3,null,null,null,0.13513263531066264,0.10819969052553524,2.6932944785127394E-2,140,0.21978021978021978]
[100390,"Bridge Replacement","2004-05-07",2004,48770.82,48770.82,244521.3,null,null,null,0.21945428067002751,0.19286168799632544,2.6592592673702065E-2,141,0.22135007849293564]
[101270,"Widen","2004-10-29",2004,687645.09,687645.09,13319415.949999999,null,null,null,7.1627270488538203E-2,5.697896752569357E-2,1.4648302962844632E-2,142,0.22291993720565148]
[100415,"Bridge Replacement","2004-06-11",2004,95122.77,95122.77,662739.76,null,null,null,0.16352959599104178,0.1422895260740325,2.1240069917009274E-2,143,0.22448979591836735]
[100621,"Bridge Replacement","2005-06-03",2005,134716.57999999999,134716.57999999999,387152.65,null,null,null,0.3679676039928953,0.16764031714766869,0.2003272868452266,144,0.22605965463108321]
[100234.01,"Reconstruction","2005-03-11",2005,17112272.66,17112272.66,81943459.069999993,null,null,null,0.2288302453205189,3.2738644686036308E-2,0.19609160063448261,145,0.22762951334379905]
[100551,"Bridge Replacement","2005-02-04",2005,195554.11,195554.11,654709.9,null,null,null,0.31868818235374169,0.14281954294362831,0.17586863941011338,146,0.22919937205651492]
[100566,"Bridge Replacement","2005-02-04",2005,160940.79,160940.79,520830.25,null,null,null,0.3290081461282251,0.15314055431797599,0.17586759181024911,147,0.23076923076923078]
[100400,"Bridge Replacement","2005-09-02",2005,140168.19,140168.19,470519.15,null,null,null,0.31790113749886695,0.15795976472061396,0.15994137277825299,148,0.23233908948194662]
[100430,"Bridge Replacement","2005-09-02",2005,273231.63,273231.63,1066541.48,null,null,null,0.27618471960415458,0.12306918989982418,0.1531155297043304,149,0.23390894819466249]
[100427,"Bridge Replacement","2005-03-11",2005,191686,191686,702621.95,null,null,null,0.29281527427373999,0.13977594378527369,0.1530393304884663,150,0.23547880690737832]
[100408,"Bridge Replacement","2005-09-02",2005,170755.54,170755.54,621495.18000000005,null,null,null,0.29474958051967515,0.14510555464851554,0.1496440258711596,151,0.23704866562009419]
[100411,"Bridge Replacement","2005-09-02",2005,189774.53,189774.53,979832.07,null,null,null,0.21368066815775891,0.1262935882647043,8.7387079893054609E-2,152,0.23861852433281006]
[101029,"Widen","2005-10-21",2005,5617.03,5617.03,7845031.0499999998,null,null,null,2.0715998440821979E-2,6.6962426465229374E-2,4.6246428024407399E-2,153,0.24018838304552589]
[100545,"Bridge Replacement","2005-04-22",2005,147850.15,147850.15,787763.38,null,null,null,0.20768345134296542,0.13498385917188913,7.2699592171076299E-2,154,0.24175824175824176]
[101951,"Bridge Replacement","2005-09-02",2005,99074.85,99074.85,492761.5,null,null,null,0.22106045216600728,0.15575010260238528,6.5310349563622E-2,155,0.24332810047095763]
[102024,"Bridge Replacement","2005-02-04",2005,134156.54999999999,134156.54999999999,2859935.69,null,null,null,6.690893941045227E-2,9.109486451744013E-2,2.418592510698786E-2,156,0.24489795918367346]
[100374,"Bridge Replacement","2005-12-09",2005,266793.11,266793.11,1835707.46,null,null,null,0.16533530849190969,0.10428515635944446,6.105015213246523E-2,157,0.24646781789638933]
[100613,"Bridge Replacement","2005-02-04",2005,110319.28,110319.28,596243.92000000004,null,null,null,0.20502373994857673,0.14695292910796331,5.8070810840613413E-2,158,0.24803767660910517]
[100478,"Bridge Replacement","2005-02-04",2005,240136.43,240136.43,4923307.5599999996,null,null,null,6.8775427306434628E-2,7.7187003411763266E-2,8.4115761053286386E-3,159,0.24960753532182103]
[100412,"Bridge Replacement","2005-12-09",2005,47646.34,47646.34,315140,null,null,null,{"$f":"F194/G194+0.02","v":0.17119102621057306},0.17850031176822509,{"$f":"ABS(L194-K194)","v":7.3092855576520344E-3},160,0.25117739403453687]
[100417,"Bridge Replacement","2005-03-11",2005,346670.15,346670.15,3137701.8,null,null,null,0.13048537180939249,8.8555593379252742E-2,4.1929778430139744E-2,161,0.25274725274725274]
[100416,"Bridge Replacement","2005-07-15",2005,276455.56,276455.56,4771771.91,null,null,null,7.7935619139851128E-2,7.7926515046127659E-2,9.1040937234693198E-6,162,0.2543171114599686]
[101792,"Bridge Replacement","2005-03-11",2005,670803.68999999994,670803.68999999994,7898573.5999999996,null,null,null,0.10492719368975685,6.6823652767690131E-2,3.810354092206672E-2,163,0.25588697017268447]
[100604,"Bridge Replacement","2005-02-04",2005,111912.34,111912.34,903567.61,null,null,null,0.14385607757675156,0.12945372635972524,1.4402351217026321E-2,164,0.25745682888540034]
[100242,"Reconstruction","2005-10-14",2005,906444.65,906444.65,15525214.75,null,null,null,7.8385321207875724E-2,5.437710507243404E-2,2.4008216135441685E-2,165,0.25902668759811615]
[100302,"Widen","2005-02-04",2005,1241475.8500000001,1241475.8500000001,28755902.609999999,null,null,null,6.3172904945375322E-2,4.5057886800124687E-2,1.8115018145250635E-2,166,0.26059654631083201]
[100300,"Construction-New","2005-06-03",2005,602687.74,602687.74,9684205.1500000004,null,null,null,8.223409465876505E-2,6.2796153394104354E-2,1.9437941264660696E-2,167,0.26216640502354788]
[102061,"Bridge Replacement","2006-03-17",2006,169719.54,169719.54,487429.28,null,null,null,0.36819315737454261,0.15626780561516054,{"$f":"ABS(L202-K202)+0.02","v":0.23192535175938206},168,0.26373626373626374]
[102021,"Bridge Replacement","2006-12-08",2006,139874.5,139874.5,440886.81,null,null,null,0.33725716630080183,0.16112494734636995,{"$f":"ABS(L203-K203)","v":0.17613221895443187},169,0.26530612244897961]
[101624,"Bridge Replacement","2006-12-08",2006,203594.26,203594.26,707698.49,null,null,null,0.30768502812546628,0.13946936828628728,0.16821565983917899,170,0.26687598116169547]
[100572,"Bridge Replacement","2006-07-14",2006,147006.98000000001,147006.98000000001,499037.83,null,null,null,0.31458083368148665,0.1551500242552919,0.15943080942619475,171,0.26844583987441129]
[100560,"Bridge Replacement","2006-02-03",2006,357506.15,357506.15,1572188.5,null,null,null,0.24739394799033324,0.10933234124491549,0.13806160674541773,172,0.27001569858712715]
[10933,"Bridge Replacement","2006-09-01",2006,122903.44,122903.44,456980.6,null,null,null,0.28894673428149908,0.15937262943000394,0.12957410485149515,173,0.27158555729984302]
[101900,"Bridge Replacement","2006-12-08",2006,159320.56,159320.56,641546.30000000005,null,null,null,0.26833836622547741,0.14370703018057759,0.12463133604489982,174,0.27315541601255888]
[101634,"Bridge Replacement","2006-02-03",2006,204147.29,204147.29,884149.97,null,null,null,0.25089667695176193,0.13031432091485623,0.1205823560369057,175,0.27472527472527475]
[100378,"Bridge Replacement","2006-03-17",2006,353253.98,353253.98,1805881.04,null,null,null,0.21561309531219175,0.10480750165937597,0.11080559365281578,176,0.27629513343799056]
[101001,"Construction-New","2006-12-08",2006,486572.26,486572.26,2780810.65,null,null,null,0.19497496997862834,9.187773353094443E-2,0.10309723644768391,177,0.27786499215070642]
[102069,"Bridge Replacement","2006-12-08",2006,158336.51,158336.51,759919.2,null,null,null,0.22835966508018221,0.13647355150611817,9.1886113574064038E-2,178,0.27943485086342229]
[101924,"Bridge Replacement","2006-10-27",2006,118941.77,118941.77,580895.91,null,null,null,0.22475573670332777,0.14812643430708972,7.6629302396238053E-2,179,0.28100470957613816]
[102308,"Reconstruction","2006-04-28",2006,1800092.52,1800092.52,16420746.08,null,null,null,0.12962306531202386,5.3454925150558753E-2,7.6168140161465114E-2,180,0.28257456828885402]
[102025,"Bridge Replacement","2006-10-27",2006,114731.46,114731.46,566730,null,null,null,0.22244465618548515,0.14924603908871356,7.3198617096771584E-2,181,0.28414442700156983]
[102028,"Bridge Replacement","2006-10-27",2006,441292.83,441292.83,3408619.73,null,null,null,0.14946379031843485,8.6346770121497884E-2,6.3117020196936963E-2,182,0.2857142857142857]
[100499,"Bridge Replacement","2006-06-02",2006,304570.8,304570.8,2211929.87,null,null,null,0.15769460059780283,9.8520655575982108E-2,5.9173945021820717E-2,183,0.28728414442700156]
[100406,"Bridge Replacement","2006-12-08",2006,85909.95,85909.95,929101.46,null,null,null,0.11246562802732007,0.12835810516456278,1.5892477137242705E-2,184,0.28885400313971743]
[100407,"Bridge Replacement","2006-02-03",2006,70172.13,70172.13,588567.36,null,null,null,0.13922531687791861,0.14753488510546692,8.3095682275483029E-3,185,0.2904238618524333]
[100516,"Bridge Replacement","2006-10-27",2006,228806.51,228806.51,1714412.67,null,null,null,0.15346058040973298,0.10648228662938421,4.6978293780348776E-2,186,0.29199372056514916]
[102037,"Bridge Replacement","2006-06-02",2006,204720.72,204720.72,3317902.35,null,null,null,8.1701852075302936E-2,8.7060099230748603E-2,5.3582471554456668E-3,187,0.29356357927786497]
[101641,"Bridge Replacement","2006-04-28",2006,135364.94,135364.94,865710.21,null,null,null,0.17636287805823614,0.13115472201689643,4.5208156041339709E-2,188,0.29513343799058084]
[101269,"Widen","2006-09-01",2006,1532316.82,1532316.82,20999632.350000001,null,null,null,9.2968745093292074E-2,4.9591585106742359E-2,4.3377159986549715E-2,189,0.2967032967032967]
[101647,"Bridge Replacement","2006-03-17",2006,77820.38,77820.38,646370.22,null,null,null,0.14039598606507583,0.14337906614310095,2.9830800780251132E-3,190,0.29827315541601257]
[101620,"Bridge Replacement","2006-04-28",2006,54651.57,54651.57,354988.95,null,null,null,0.17395287656136901,0.17213414680589836,1.8187297554706494E-3,191,0.29984301412872844]
[100525,"Bridge Replacement","2006-12-08",{"$f":"YEAR(C226)","v":2006},409598.16,409598.16,4219605.0999999996,null,null,null,{"$f":"F226/G226+0.02","v":0.11707025901547044},8.0904868108128317E-2,3.6165390907342124E-2,192,0.30141287284144425]
[101077,"Reconstruction","2006-04-28",2006,1599079.94,1599079.94,25438841.260000002,null,null,null,8.2859779014950299E-2,{"$f":"8.4856*G227^-0.305","v":4.6774146507216473E-2},3.6085632507733827E-2,193,0.30298273155416011]
[100391,"Bridge Replacement","2006-10-27",2006,130106.07,130106.07,893598.78,null,null,null,0.16559785992545781,0.12989249917558532,3.5705360749872489E-2,194,{"$f":"N228/637","v":0.30455259026687598}]
[101588,"Widen","2006-12-08",2006,951550.52,951550.52,33735910.170000002,null,null,null,4.8205864765616308E-2,4.2915518521966851E-2,5.2903462436494561E-3,{"$f":"N228+1","v":195},0.30612244897959184]
[100998,"Widen","2006-02-03",2006,1084523.18,1084523.18,16979138.800000001,null,null,null,8.3873862671998409E-2,5.2912499816298475E-2,3.0961362855699934E-2,196,0.30769230769230771]
[101793,"Widen","2006-10-27",2006,255547.59,255547.59,2580666,null,null,null,0.11902389150707608,9.3994914424510634E-2,2.5028977082565448E-2,197,0.30926216640502358]
[101393,"Construction-New","2006-03-17",2006,415051.15,415051.15,5743515.46,null,null,null,9.2264304482258683E-2,7.3643314801298904E-2,1.8620989680959779E-2,198,0.31083202511773939]
[100488,"Bridge Replacement","2006-12-08",2006,233169.09,233169.09,2393628.0699999998,null,null,null,0.11741241461961967,9.6176788625824169E-2,2.1235625993795498E-2,199,0.31240188383045525]
[101639,"Bridge Replacement","2006-07-14",2006,173570.85,173570.85,1618775.72,null,null,null,0.1272235318676512,0.10836289970653695,1.8860632161114249E-2,200,0.31397174254317112]
[103885,"Bridge Replacement","2007-12-07",2007,107455.67999999999,107455.67999999999,293302.92,null,null,null,0.38636416712114563,0.1824530206814382,0.20391114643970742,201,0.31554160125588698]
[101952,"Bridge Replacement","2007-06-01",2007,258688.98,258688.98,816863.09,null,null,null,0.33668584756351277,0.13349869723918165,0.20318715032433113,202,0.31711145996860285]
[101986,"Bridge Replacement","2007-02-02",2007,131681.19,131681.19,425597.47,null,null,null,0.32940313155526985,0.16286878230873431,0.16653434924653554,203,0.31868131868131866]
[101967,"Bridge Replacement","2007-12-07",2007,262711.13,262711.13,978003.31,null,null,null,0.28861987818834683,0.12636556887731251,0.16225430931103432,204,0.32025117739403453]
[100505,"Bridge Replacement","2007-07-13",2007,279398.2,279398.2,1110380.6299999999,null,null,null,0.27162380579351431,0.12156642166110904,0.15005738413240527,205,0.32182103610675039]
[100580,"Bridge Replacement","2007-03-16",2007,87623.98,87623.98,285151.8,null,null,null,0.32728888963702846,0.18402818380574598,0.14326070583128248,206,0.32339089481946626]
[101902,"Bridge Replacement","2007-08-31",2007,79869.63,79869.63,255504.69,null,null,null,0.33259555352976106,0.19029435203300535,0.14230120149675571,207,0.32496075353218212]
[101552,"Bridge Replacement","2007-10-19",2007,658574.56999999995,658574.56999999995,3331987.94,null,null,null,0.21765214696425339,8.6947682833594914E-2,0.13070446413065848,208,0.32653061224489793]
[10945,"Bridge Replacement","2007-06-01",2007,121248.54,121248.54,453976.32000000001,null,null,null,0.28708119930132037,0.15969357001066065,0.12738762929065972,209,0.3281004709576138]
[40322,"Bridge Replacement","2007-02-02",2007,73971.399999999994,73971.399999999994,271693.15000000002,null,null,null,0.29226082070895049,0.18676201704342299,0.1054988036655275,210,0.32967032967032966]
[102060,"Bridge Replacement","2007-06-01",2007,165450.04999999999,165450.04999999999,753959.25,null,null,null,0.23944163427930618,0.13680168742056789,0.10263994685873828,211,0.33124018838304553]
[102043,"Bridge Replacement","2007-03-16",2007,201672.9,201672.9,1068811.1000000001,null,null,null,0.20868900220066947,0.12298942310988323,8.5699579090786238E-2,212,0.3328100470957614]
[102026,"Bridge Replacement","2007-12-07",2007,308193.34999999998,308193.34999999998,1811798.82,null,null,null,0.19010351623918154,0.1047029731841153,8.5400543055066239E-2,213,0.33437990580847726]
[101950,"Bridge Replacement","2007-03-16",2007,209535.05,209535.05,1136059.7,null,null,null,0.2044401751069948,0.12072166144136401,8.3718513665630795E-2,214,0.33594976452119307]
[40486,"Bridge Replacement","2007-07-13",2007,108292.59,108292.59,496576,null,null,null,0.23807858213042915,0.15538421907202765,8.2694363058401499E-2,215,0.33751962323390894]
[103461,"Bridge Replacement","2007-02-02",2007,108146.17,108146.17,509679.19,null,null,null,0.23218478627703046,0.15415478176929326,7.80300045077372E-2,216,0.3390894819466248]
[102215,"Bridge Replacement","2007-12-07",2007,173675.36,173675.36,994847.6,null,null,null,0.19457483940253761,0.12570912575252671,6.8865713650010901E-2,217,0.34065934065934067]
[102033,"Bridge Replacement","2007-02-02",2007,91728.2,91728.2,457093.58,null,null,null,0.22067706923383171,0.15936061377827079,6.1316455455560914E-2,218,0.34222919937205654]
[100355,"Widen","2007-10-19",2007,1192004.53,1192004.53,12238016.59,null,null,null,0.11740177431807192,5.84696762832254E-2,5.8932098034846517E-2,219,0.34379905808477235]
[100324,"Reconstruction","2007-06-01",2007,1247747.8700000001,1247747.8700000001,13176895.880000001,null,null,null,0.1146920945086803,5.7166230486053501E-2,5.7525864022626799E-2,220,0.34536891679748821]
[102036,"Bridge Replacement","2007-12-07",2007,157448.42000000001,157448.42000000001,966874.74,null,null,null,0.18284262426795844,0.12680741238806542,5.6035211879893021E-2,221,0.34693877551020408]
[103898,"Reconstruction","2007-02-02",2007,273293.18,273293.18,10851867.18,null,null,null,4.5183977601907954E-2,6.0653196350966464E-2,1.546921874905851E-2,222,0.34850863422291994]
[101965,"Bridge Replacement","2007-04-27",2007,53743.25,53743.25,417138.15,null,null,null,0.1488380120590744,0.16386914323499327,1.5031131175918866E-2,223,0.35007849293563581]
[101619,"Bridge Replacement","2007-04-27",2007,247315.9,247315.9,1758532.56,null,null,null,{"$f":"F258/G258+0.02","v":0.16063765757058257},0.10566026111481523,5.4977396455767338E-2,224,0.35164835164835168]
[101799,"Bridge Replacement","2007-02-02",2007,168639.67,168639.67,1114203.31,null,null,null,0.17135448664211919,0.12143906095859061,4.991542568352858E-2,225,0.35321821036106749]
[40509,"Bridge Replacement","2007-07-13",2007,82221.11,82221.11,434176.21,null,null,null,0.20937267428816514,0.16188045587240404,4.7492218415761095E-2,226,0.35478806907378335]
[100524,"Bridge Replacement","2007-07-13",2007,219269.75,219269.75,1632747.28,null,null,null,0.1542949718464697,0.10807923706286833,4.6215734783601373E-2,227,0.35635792778649922]
[100547,"Bridge Replacement","2007-08-31",2007,367553.02,367553.02,3515484.58,null,null,null,0.12455259058482344,8.5537601955996287E-2,3.9014988628827157E-2,228,0.35792778649921508]
[100373,"Bridge Replacement","2007-03-16",2007,560602.6,560602.6,6169454.2000000002,null,null,null,0.11086745469315584,7.2053867861960483E-2,3.881358683119536E-2,229,0.35949764521193095]
[101461,"Reconstruction","2007-12-14",2007,816132,816132,10439057.439999999,null,null,null,9.8180621640491725E-2,6.1374909285795802E-2,3.6805712354695923E-2,230,0.36106750392464676]
[100528,"Bridge Replacement","2007-07-13",2007,232216.34,232216.34,2107165.89,null,null,null,0.13020316013182995,9.9989510884746668E-2,3.021364924708328E-2,231,0.36263736263736263]
[101648,"Bridge Replacement","2007-12-07",2007,668928.05000000005,668928.05000000005,13723802.949999999,null,null,null,6.8742178275009419E-2,5.646155585026829E-2,1.2280622424741129E-2,232,0.36420722135007849]
[101801,"Bridge Replacement","2007-08-31",2007,70810.990000000005,70810.990000000005,460000.99,null,null,null,0.17393660348426643,0.15905273158026223,{"$f":"ABS(L267-K267)","v":1.4883871904004198E-2},233,0.36577708006279436]
[101909,"Bridge Replacement","2007-08-31",2007,402238.98,402238.98,5579898.8799999999,null,null,null,9.2087145063101936E-2,7.4295331632999936E-2,1.7791813430101999E-2,234,0.36734693877551022]
[101596,"Widen","2007-10-19",2007,1205309.3899999999,1205309.3899999999,26547131.829999998,null,null,null,6.5402621937407243E-2,4.6169714165824619E-2,1.9232907771582625E-2,235,0.36891679748822603]
[101124,"Widen","2007-12-07",2007,1250978.29,1250978.29,27206528.300000001,null,null,null,6.5980812994798757E-2,4.5825504208316652E-2,2.0155308786482105E-2,236,0.3704866562009419]
[40542,"Bridge Replacement","2008-03-28",2008,120574.08,120574.08,329654.67,{"$f":"G271+(G271*0.15)","v":379102.87049999996},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D271,'Const Index'!A:F,4,0))*F271","v":241810.65494505494},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D271,'Const Index'!A:F,4,0))*G271","v":661120.62939560437},{"$f":"I271/J271+0.02","v":0.38575874990637932},0.17606559143909511,0.2096931584672842,237,0.37205651491365777]
[40440,"Bridge Replacement","2008-02-15",2008,78466.73,78466.73,214291.71,{"$f":"G272+(G272*0.15)","v":246435.46649999998},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D272,'Const Index'!A:F,4,0))*F272","v":157364.59587912087},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D272,'Const Index'!A:F,4,0))*G272","v":429760.84697802196},{"$f":"I272/J272+0.02","v":0.38616782795750709},0.20078252792787915,0.18538530002962794,238,0.37362637362637363]
[101903,"Bridge Replacement","2008-02-15",2008,112904.93,112904.93,366030,420934.5,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D273,'Const Index'!A:F,4,0))*F273","v":226430.21675824173},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D273,'Const Index'!A:F,4,0))*G273","v":734071.15384615387},0.32845813184711631,0.17053360301534329,0.15792452883177302,239,0.3751962323390895]
[100297,"Reconstruction","2008-12-12",2008,3719684.83,3719684.83,21327410.399999999,24526521.959999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D274,'Const Index'!A:F,4,0))*F274","v":7459807.4887362635},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D274,'Const Index'!A:F,4,0))*G274","v":42772004.373626374},0.19440864878747771,4.9357871999489246E-2,0.14505077678798847,240,0.37676609105180536]
[103886,"Bridge Replacement","2008-02-15",2008,138911.69,138911.69,519157.28,597030.87199999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D275,'Const Index'!A:F,4,0))*F275","v":278586.63104395603},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D275,'Const Index'!A:F,4,0))*G275","v":1041167.0725274726},0.28757149586730246,0.15329090089470038,0.13428059497260209,241,0.37833594976452117]
[100968,"Reconstruction","2008-02-15",2008,3287537.35,3287537.35,26126673.469999999,30045674.490499999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D276,'Const Index'!A:F,4,0))*F276","v":6593138.0920329671},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D276,'Const Index'!A:F,4,0))*G276","v":52396900.090934061},0.14583068999484075,4.6395077017345347E-2,9.9435612977495397E-2,242,0.37990580847723704]
[104111,"Bridge Replacement","2008-06-20",2008,167054.64000000001,167054.64000000001,778774.75,895590.96250000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D277,'Const Index'!A:F,4,0))*F277","v":335027.16263736266},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D277,'Const Index'!A:F,4,0))*G277","v":1561828.482142857},0.23450957417404714,0.13545715126132279,9.9052422912724342E-2,243,0.38147566718995291]
[100280,"Widen","2008-09-19",2008,1874299.14,1874299.14,15559389.210000001,17893297.591499999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D278,'Const Index'!A:F,4,0))*F278","v":3758896.6269230768},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D278,'Const Index'!A:F,4,0))*G278","v":31204269.569505498},0.14046097148822462,5.4340650098099214E-2,8.6120321390125404E-2,244,0.38304552590266877]
[101993,"Widen","2008-12-12",2008,477776.47,477776.47,3467815.01,3987987.2614999996,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D279,'Const Index'!A:F,4,0))*F279","v":958178.08543956035},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D279,'Const Index'!A:F,4,0))*G279","v":6954683.948626373},0.15777449737724042,8.5894528412206031E-2,7.1879968965034388E-2,245,0.38461538461538464]
[102034,"Bridge Replacement","2008-05-09",2008,226107.93,226107.93,1427911.42,1642098.1329999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D280,'Const Index'!A:F,4,0))*F280","v":453458.21126373624},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D280,'Const Index'!A:F,4,0))*G280","v":2863668.5071428572},0.17834870905367503,0.11258970193941137,6.5759007114263662E-2,246,0.38618524332810045]
[101926,"Bridge Replacement","2008-03-28",2008,83718.53,83718.53,433341.36,498342.56400000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D281,'Const Index'!A:F,4,0))*F281","v":167897.05192307691},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D281,'Const Index'!A:F,4,0))*G281","v":869063.7164835165},0.21319302916296748,0.16197551242025338,5.1217516742714103E-2,247,0.38775510204081631]
[105359,"Bridge Replacement","2008-12-12",2008,124609.81,124609.81,758379.05,872135.90750000009,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D282,'Const Index'!A:F,4,0))*F282","v":249904.28928571427},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D282,'Const Index'!A:F,4,0))*G282","v":1520925.017857143},0.18431072298212875,0.13655802467364328,4.7752698308485469E-2,248,0.38932496075353218]
[101586,"Reconstruction","2008-12-12",2008,853083.32,853083.32,9424223.6999999993,10837857.254999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D283,'Const Index'!A:F,4,0))*F283","v":1710853.9109890109},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D283,'Const Index'!A:F,4,0))*G283","v":18900228.848901097},0.11052027489542721,6.3319525545755637E-2,4.720074934967157E-2,249,0.39089481946624804]
[100313,"Widen","2008-08-01",2008,2541235.79,2541235.79,45752533.310000002,52615413.306500003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D284,'Const Index'!A:F,4,0))*F284","v":5096434.4140109895},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D284,'Const Index'!A:F,4,0))*G284","v":91756454.165659338},7.5543061906138645E-2,3.9107129216414689E-2,3.6435932689723956E-2,250,0.39246467817896391]
[100303,"Reconstruction","2008-08-01",2008,1752537.09,1752537.09,29364437.760000002,33769103.424000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D285,'Const Index'!A:F,4,0))*F285","v":3514703.5046703299},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D285,'Const Index'!A:F,4,0))*G285","v":58890218.584615387},7.9682296808260084E-2,4.4771015009721929E-2,3.4911281798538155E-2,251,0.39403453689167978]
[101316,"Widen","2008-06-20",2008,959963.35,959963.35,24985767.370000001,28733632.475500003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D286,'Const Index'!A:F,4,0))*F286","v":1925201.2239010988},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D286,'Const Index'!A:F,4,0))*G286","v":50108819.176098906},5.8420406937455607E-2,4.7031224348006578E-2,1.1389182589449029E-2,252,0.39560439560439559]
[102035,"Bridge Replacement","2008-12-12",2008,163150.22,163150.22,1643553.85,1890086.9275000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D287,'Const Index'!A:F,4,0))*F287","v":327196.8697802198},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D287,'Const Index'!A:F,4,0))*G287","v":3296138.2156593408},0.11926673227043945,0.10786199650712713,1.1404735763312315E-2,253,0.39717425431711145]
[100496,"Bridge Replacement","2008-02-15",2008,238246.82,238246.82,2258273.85,2597014.9275000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D288,'Const Index'!A:F,4,0))*F288","v":477802.68846153846},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D288,'Const Index'!A:F,4,0))*G288","v":4528955.798076923},0.1254995256664731,9.7899549005514605E-2,2.7599976660958495E-2,254,0.39874411302982732]
[101019,"Reconstruction","2008-06-20",2008,1477702.96,1477702.96,28616725.129999999,32909233.899499997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D289,'Const Index'!A:F,4,0))*F289","v":2963525.1670329669},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D289,'Const Index'!A:F,4,0))*G289","v":57390685.013461538},7.1637738185871866E-2,4.5124611572633005E-2,2.651312661323886E-2,255,0.40031397174254318]
[100332,"Modify Interchange","2008-02-15",{"$f":"YEAR(C290)","v":2008},1978635.74,1978635.74,43459910.759999998,49978897.373999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D290,'Const Index'!A:F,4,0))*F290","v":3968143.1049450547},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D290,'Const Index'!A:F,4,0))*G290","v":87158612.238461539},6.5527837158402852E-2,3.9725142396465518E-2,2.5802694761937334E-2,256,0.40188383045525905]
[101444,"Construction-New","2008-08-01",2008,408283.68,408283.68,5274217.25,6065349.8375000004,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D291,'Const Index'!A:F,4,0))*F291","v":818810.67692307686},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D291,'Const Index'!A:F,4,0))*G291","v":10577413.715659341},9.7411236710053986E-2,{"$f":"8.4856*G291^-0.305","v":7.5583041005427967E-2},2.1828195704626019E-2,257,0.40345368916797486]
[104124.01,"Reconstruction","2008-06-20",2008,336200.81,336200.81,4087539.94,4700670.9309999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D292,'Const Index'!A:F,4,0))*F292","v":674248.87719780218},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D292,'Const Index'!A:F,4,0))*G292","v":8197538.8906593407},0.10225015900395092,8.169333823957603E-2,2.0556820764374886E-2,258,{"$f":"N292/637","v":0.40502354788069073}]
[105338,"Bridge Replacement","2008-02-15",2008,340003.42,340003.42,4210865.3,4842495.0949999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D293,'Const Index'!A:F,4,0))*F293","v":681874.99065934063},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D293,'Const Index'!A:F,4,0))*G293","v":8444867.2225274723},0.10074431162640135,8.0956047091963315E-2,1.9788264534438035E-2,{"$f":"N292+1","v":259},0.40659340659340659]
[102009,"Bridge Replacement","2009-05-08",2009,98173.89,98173.89,260666.86,299766.88899999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D294,'Const Index'!A:F,4,0))*F294","v":191009.96721748402},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D294,'Const Index'!A:F,4,0))*G294","v":507161.0015991471},0.39662589713168761,0.18913694966490577,0.20748894746678184,260,0.40816326530612246]
[100385,"Bridge Replacement","2009-03-20",2009,448632.24,448632.24,1547982.09,1780179.4035,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D295,'Const Index'!A:F,4,0))*F295","v":872871.89552238805},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D295,'Const Index'!A:F,4,0))*G295","v":3011798.8424840085},0.30981746164776364,0.10985098278345455,0.19996647886430907,261,0.40973312401883832]
[103875,"Bridge Replacement","2009-03-20",2009,272633.31,272633.31,924418.01,1063080.7115,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D296,'Const Index'!A:F,4,0))*F296","v":530443.27372068225},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D296,'Const Index'!A:F,4,0))*G296","v":1798574.4864072495},0.31492427348965213,0.12855610167397982,0.18636817181567231,262,0.41130298273155413]
[101908,"Bridge Replacement","2009-06-12",2009,104133.17,104133.17,314488.43,361661.69449999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D297,'Const Index'!A:F,4,0))*F297","v":202604.51519189766},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D297,'Const Index'!A:F,4,0))*G297","v":611877.80890191894},0.35111924022133345,0.17861302705034821,0.17250621317098525,263,0.41287284144427]
[103893,"Bridge Replacement","2009-05-08",2009,92279.6,92279.6,272819.65000000002,313742.59750000003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D298,'Const Index'!A:F,4,0))*F298","v":179541.8656716418},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D298,'Const Index'!A:F,4,0))*G298","v":530805.82222814509},0.35824396446516954,0.18652647518042731,0.17171748928474223,264,0.41444270015698587]
[101042,"Construction-New","2009-08-07",2009,1171535.04,1171535.04,5142197.3899999997,5913526.9984999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D299,'Const Index'!A:F,4,0))*F299","v":2279372.5458422177},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D299,'Const Index'!A:F,4,0))*G299","v":10004808.354744136},0.24782770694067038,7.6169690170004328E-2,0.17165801677066606,265,0.41601255886970173]
[11024,"Bridge Replacement","2009-06-12",2009,133867.35,133867.35,426216.17,490148.5955,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D300,'Const Index'!A:F,4,0))*F300","v":260456.19802771855},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D300,'Const Index'!A:F,4,0))*G300","v":829258.53971215349},0.33408322682830172,0.1627966371687645,0.17128658965953722,266,0.4175824175824176]
[102030,"Bridge Replacement","2009-10-30",2009,147769.29999999999,147769.29999999999,514912.72,592149.62800000003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D301,'Const Index'!A:F,4,0))*F301","v":287504.23507462686},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D301,'Const Index'!A:F,4,0))*G301","v":1001829.119402985},0.30697931564013414,0.15367520516915326,0.15330411047098089,267,0.41915227629513346]
[103831,"Bridge Replacement","2009-05-08",2009,132162.81,132162.81,465538.22,535368.95299999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D302,'Const Index'!A:F,4,0))*F302","v":257139.79557569296},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D302,'Const Index'!A:F,4,0))*G302","v":905764.66044776118},0.30389250188738531,0.15847332736153702,0.14541917452584829,268,0.42072213500784927]
[40348,"Bridge Replacement","2009-05-08",2009,63488.3,63488.3,190809.7,219431.15500000003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D303,'Const Index'!A:F,4,0))*F303","v":123524.6775053305},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D303,'Const Index'!A:F,4,0))*G303","v":371244.88539445633},0.35273098799484515,0.20801728271620987,0.14471370527863528,269,0.42229199372056514]
[102042,"Bridge Replacement","2009-05-08",2009,218585.06,218585.06,867132.23,997202.06449999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D304,'Const Index'!A:F,4,0))*F304","v":425285.43123667379},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D304,'Const Index'!A:F,4,0))*G304","v":1687117.611673774},0.2720781173132038,0.1310890845523667,0.1409890327608371,270,0.42386185243328101]
[103966,"Bridge Replacement","2009-05-08",2009,149763.76999999999,149763.76999999999,555752.5,639115.375,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D305,'Const Index'!A:F,4,0))*F305","v":291384.73374200426},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D305,'Const Index'!A:F,4,0))*G305","v":1081288.1796375266},0.28947925560388843,0.15013906993402065,0.13934018566986778,271,0.42543171114599687]
[40468,"Bridge Replacement","2009-05-08",2009,148527.04000000001,148527.04000000001,551027.9,633682.08499999996,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D306,'Const Index'!A:F,4,0))*F306","v":288978.51599147124},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D306,'Const Index'!A:F,4,0))*G306","v":1072095.8608742005},0.28954540777336324,0.1505305371055437,0.13901487066781953,272,0.42700156985871274]
[40504,"Bridge Replacement","2009-06-12",2009,80959.960000000006,80959.960000000006,263431.78999999998,302946.55849999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D307,'Const Index'!A:F,4,0))*F307","v":157518.04584221749},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D307,'Const Index'!A:F,4,0))*G307","v":512540.52958422172},0.32732798042331951,0.18852925878086532,0.13879872164245419,273,0.42857142857142855]
[40505,"Bridge Replacement","2009-06-12",2009,124267.1,124267.1,445056.1,511814.51499999996,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D308,'Const Index'!A:F,4,0))*F308","v":241777.67324093817},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D308,'Const Index'!A:F,4,0))*G308","v":865914.05383795302},0.29921670998330324,0.16066306753589107,0.13855364244741217,274,0.43014128728414441]
[103942,"Bridge Replacement","2009-05-08",2009,85917.46,85917.46,286785.03000000003,329802.78450000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D309,'Const Index'!A:F,4,0))*F309","v":167163.50159914713},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D309,'Const Index'!A:F,4,0))*G309","v":557977.27052238816},0.31958837112243965,0.18370789892334907,0.13588047219909058,275,0.43171114599686028]
[100388,"Bridge Replacement","2009-03-20",2009,131923.51,131923.51,499484.6,574407.28999999992,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D310,'Const Index'!A:F,4,0))*F310","v":256674.20655650322},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D310,'Const Index'!A:F,4,0))*G310","v":971811.72174840083},0.28411927414779159,0.15510768447259921,0.12901158967519238,276,0.43328100470957615]
[101871,"Bridge Replacement","2009-03-20",2009,169334.43,169334.43,685709.85,788566.32750000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D311,'Const Index'!A:F,4,0))*F311","v":329461.97734541574},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D311,'Const Index'!A:F,4,0))*G311","v":1334136.968283582},0.26694764119255393,0.14081850765309387,0.12612913353946006,277,0.43485086342229201]
[105325,"Bridge Replacement","2009-06-12",2009,337647.35999999999,337647.35999999999,1579079.1,1815940.9650000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D312,'Const Index'!A:F,4,0))*F312","v":656936.49466950959},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D312,'Const Index'!A:F,4,0))*G312","v":3072302.0868869936},0.23382548853949114,0.10918660709755086,0.12463888144194028,278,0.43642072213500788]
[102039,"Bridge Replacement","2009-05-08",2009,285202.65999999997,285202.65999999997,1301357.83,1496561.5045,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D313,'Const Index'!A:F,4,0))*F313","v":554898.56556503195},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D313,'Const Index'!A:F,4,0))*G313","v":2531959.53065032},0.23915775463540259,0.11582213157067069,0.12333562306473191,279,0.43799058084772369]
[102005,"Bridge Replacement","2009-06-12",2009,404991.6,404991.6,2012000,2313800,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D314,'Const Index'!A:F,4,0))*F314","v":787963.40085287846},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D314,'Const Index'!A:F,4,0))*G314","v":3914605.5437100213},0.22128807157057653,0.10140888859871455,0.11987918297186198,280,0.43956043956043955]
[40487,"Bridge Replacement","2009-05-08",2009,28762.46,28762.46,459149.86,528022.33899999992,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D315,'Const Index'!A:F,4,0))*F315","v":55961.076226012789},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D315,'Const Index'!A:F,4,0))*G315","v":893335.28198294237},8.2642859131003554E-2,0.15914259912150244,7.6499739990498888E-2,281,0.44113029827315542]
[102392,"Bridge Replacement","2009-05-08",2009,28323.919999999998,28323.919999999998,385157.25,442930.83750000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D316,'Const Index'!A:F,4,0))*F316","v":55107.84008528784},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D316,'Const Index'!A:F,4,0))*G316","v":749373.11433901917},9.3538587161477546E-2,0.16790473448054852,7.4366147319070972E-2,282,0.44270015698587128]
[101199,"Bridge Replacement","2009-06-12",2009,120298.07,120298.07,488597.2,561886.78,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D317,'Const Index'!A:F,4,0))*F317","v":234055.41337953095},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D317,'Const Index'!A:F,4,0))*G317","v":950628.88059701491},0.2662111326057538,0.15615378259022011,0.11005735001553368,283,0.44427001569858715]
[40368,"Bridge Replacement","2009-05-08",2009,86497.97,86497.97,325303.15999999997,374098.63399999996,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D318,'Const Index'!A:F,4,0))*F318","v":168292.95868869938},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D318,'Const Index'!A:F,4,0))*G318","v":632919.26119402982},0.28589956888214679,0.17678061068200385,0.10911895820014295,284,0.44583987441130296]
[101621,"Bridge Replacement","2009-12-11",2009,169168.96,169168.96,768884.45,884217.11749999993,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D319,'Const Index'!A:F,4,0))*F319","v":329140.03411513858},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D319,'Const Index'!A:F,4,0))*G319","v":1495963.8819296374},0.24001870372069561,0.13598622790035408,0.10403247582034153,285,0.44740973312401883]
[100356,"Reconstruction","2009-09-18",2009,1987924.1,1987924.1,14545847.75,16727724.9125,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D320,'Const Index'!A:F,4,0))*F320","v":3867762.7745202561},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D320,'Const Index'!A:F,4,0))*G320","v":28300823.180970151},0.15666608740628402,5.5468592943961295E-2,0.10119749446232272,286,0.44897959183673469]
[102393,"Bridge Replacement","2009-06-12",2009,33494.14,33494.14,375336.3,431636.745,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D321,'Const Index'!A:F,4,0))*F321","v":65167.17004264392},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D321,'Const Index'!A:F,4,0))*G321","v":730265.18923240935},0.10923767831675221,0.16923269963529014,5.9995021318537928E-2,287,0.45054945054945056]
[40367,"Bridge Replacement","2009-05-08",2009,248096.49,248096.49,1260585.25,1449673.0375000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D322,'Const Index'!A:F,4,0))*F322","v":482703.72521321959},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D322,'Const Index'!A:F,4,0))*G322","v":2452631.216684435},0.21681056080895755,0.11695210106309516,9.9858459745862396E-2,288,0.45211930926216642]
[100500,"Bridge Replacement","2009-10-30",2009,141951.99,141951.99,650698,748302.7,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D323,'Const Index'!A:F,4,0))*F323","v":276185.90804904047},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D323,'Const Index'!A:F,4,0))*G323","v":1266016.8976545841},0.23815341371880655,0.14308753989677037,9.5065873822036184E-2,289,0.45368916797488223]
[109563,"Bridge Replacement","2009-05-01",2009,363345.12,363345.12,2082749.75,2395162.2124999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D324,'Const Index'!A:F,4,0))*F324","v":706934.80170575692},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D324,'Const Index'!A:F,4,0))*G324","v":4052258.3089019191},0.19445452580176759,0.10034557897130143,9.4108946830466153E-2,290,0.4552590266875981]
[101260,"Modify Interchange","2009-12-11",2009,1034847.55,1034847.55,7544358.1500000004,8676011.8725000005,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D325,'Const Index'!A:F,4,0))*F325","v":2013429.4016524521},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D325,'Const Index'!A:F,4,0))*G325","v":14678521.9869403},0.15716840179439251,6.7765360832202512E-2,8.9403040962189997E-2,291,0.45682888540031397]
[40439,"Bridge Replacement","2009-05-08",2009,74546.45,74546.45,296765.43,341280.24449999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D326,'Const Index'!A:F,4,0))*F326","v":145039.73480810234},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D326,'Const Index'!A:F,4,0))*G326","v":577395.42617270793},0.2711965426700812,0.18180109581808129,8.9395446851999905E-2,292,0.45839874411302983]
[40442,"Bridge Replacement","2009-03-20",2009,71477.759999999995,71477.759999999995,281265.25,323455.03749999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D327,'Const Index'!A:F,4,0))*F327","v":139069.20255863538},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D327,'Const Index'!A:F,4,0))*G327","v":547237.82649253728},0.27412936720764475,0.18480007867704717,8.9329288530597573E-2,293,0.4599686028257457]
[105348,"Bridge Replacement","2009-10-30",2009,131138.16,131138.16,620479.23,713551.11450000003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D328,'Const Index'!A:F,4,0))*F328","v":255146.20682302772},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D328,'Const Index'!A:F,4,0))*G328","v":1207222.3824626866},0.23134979812297662,0.14517797856636852,8.6171819556608104E-2,294,0.46153846153846156]
[100259.2,"Construction-New","2009-09-18",2009,3212975.79,3212975.79,30805076.890000001,35425838.423500001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D329,'Const Index'!A:F,4,0))*F329","v":6251258.8664712152},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D329,'Const Index'!A:F,4,0))*G329","v":59935250.878731348},0.12430020354998697,4.4121752610409459E-2,8.0178450939577511E-2,295,0.46310832025117737]
[103984,"Bridge Replacement","2009-12-11",2009,81485.710000000006,81485.710000000006,356149.6,409572.04,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D330,'Const Index'!A:F,4,0))*F330","v":158540.96028784651},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D330,'Const Index'!A:F,4,0))*G330","v":692934.98933901917},0.24879629796018307,0.17196285833370742,7.6833439626475653E-2,296,0.46467817896389324]
[101644,"Bridge Replacement","2009-08-07",2009,325811.21000000002,325811.21000000002,2090675.38,2404276.6869999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D331,'Const Index'!A:F,4,0))*F331","v":633907.73800639668},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D331,'Const Index'!A:F,4,0))*G331","v":4067678.6444562897},0.1758401716099991,0.10022940248410458,{"$f":"ABS(L331-K331)","v":7.5610769125894511E-2},297,0.46624803767660911]
[101594,"Widen","2009-09-18",2009,984958.53,984958.53,8119118.4400000004,9336986.2060000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D332,'Const Index'!A:F,4,0))*F332","v":1916363.8776652452},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D332,'Const Index'!A:F,4,0))*G332","v":15796792.273987208},0.14131348215681405,6.6264717131051504E-2,7.5048765025762548E-2,298,0.46781789638932497]
[100351,"Construction-New","2009-05-08",2009,940357.38,940357.38,8020611.7199999997,9223703.4780000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D333,'Const Index'!A:F,4,0))*F333","v":1829586.5868869936},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D333,'Const Index'!A:F,4,0))*G333","v":15605134.743070362},0.13724260104190655,6.6511887199088293E-2,7.073071384281826E-2,299,0.46938775510204084]
[102027,"Bridge Replacement","2009-06-12",2009,246678.54,246678.54,1537372.6,1767978.4900000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D334,'Const Index'!A:F,4,0))*F334","v":479944.92057569296},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D334,'Const Index'!A:F,4,0))*G334","v":2991156.7110874201},0.18045462238627122,0.110081647129096,7.0372975257175216E-2,300,0.47095761381475665]
[101627,"Bridge Replacement","2009-08-07",2009,694644.91,694644.91,5655973.7699999996,6504369.8354999991,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D335,'Const Index'!A:F,4,0))*F335","v":1351521.2801172708},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D335,'Const Index'!A:F,4,0))*G335","v":11004426.578091683},0.14281614771349976,7.3989109928620289E-2,6.8827037784879475E-2,301,0.47252747252747251]
[100650,"Bridge Replacement","2009-05-08",2009,123171.07,123171.07,651602.36,{"$f":"G336+(G336*0.15)","v":749342.71399999992},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D336,'Const Index'!A:F,4,0))*F336","v":239645.20549040515},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D336,'Const Index'!A:F,4,0))*G336","v":1267776.4466950959},{"$f":"I336/J336+0.02","v":0.20902796791589279},0.14302694027338675,6.6001027642506038E-2,302,0.47409733124018838]
[108882,"Bridge Replacement","2009-05-08",2009,136542.29999999999,136542.29999999999,3105049.67,3570807.1204999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D337,'Const Index'!A:F,4,0))*F337","v":265660.65831556503},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D337,'Const Index'!A:F,4,0))*G337","v":6041274.6777718551},6.3974272398676313E-2,8.8838588060636409E-2,2.4864315661960096E-2,303,0.47566718995290425]
[102391,"Bridge Replacement","2009-05-08",2009,158428.54999999999,158428.54999999999,926638.39,1065634.1485000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D338,'Const Index'!A:F,4,0))*F338","v":308243.18097014923},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D338,'Const Index'!A:F,4,0))*G338","v":1802894.5221215351},0.19097127823508367,0.1284620705744681,6.2509207660615573E-2,304,0.47723704866562011]
[101692,"Bridge Replacement","2009-12-11",2009,745534.66,745534.66,6679960.2000000002,7681954.2300000004,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D339,'Const Index'!A:F,4,0))*F339","v":1450533.8534115138},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D339,'Const Index'!A:F,4,0))*G339","v":12996724.269722816},0.13160764999767513,7.0327717737869194E-2,6.1279932259805936E-2,305,0.47880690737833598]
[100347,"Construction-New","2009-06-12",2009,1364117.05,1364117.05,14283873.359999999,16426454.364,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D340,'Const Index'!A:F,4,0))*F340","v":2654065.688965885},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D340,'Const Index'!A:F,4,0))*G340","v":27791118.211087421},0.1155005001528521,5.5776919960571811E-2,5.9723580192280287E-2,306,0.48037676609105179]
[107637.02,"Construction-New","2009-08-05",2009,786275.27,786275.27,7312885.3600000003,8409818.1640000008,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D341,'Const Index'!A:F,4,0))*F341","v":1529799.965618337},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D341,'Const Index'!A:F,4,0))*G341","v":14228161.814498935},0.12751915711693859,6.8412503352239779E-2,5.9106653764698813E-2,307,0.48194662480376765]
[40467,"Bridge Replacement","2009-03-20",2009,67641.75,67641.75,310453.05,357021.00750000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D342,'Const Index'!A:F,4,0))*F342","v":131605.75026652453},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D342,'Const Index'!A:F,4,0))*G342","v":604026.4565565032},0.23788077134368626,0.17931796306908512,5.8562808274601141E-2,308,0.48351648351648352]
[102381,"Bridge Replacement","2009-10-30",2009,91762.94,91762.94,469125.39,539494.19850000006,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D343,'Const Index'!A:F,4,0))*F343","v":178536.63699360343},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D343,'Const Index'!A:F,4,0))*G343","v":912743.96242004272},0.2156042924899034,0.15810275203988614,5.7501540450017263E-2,309,0.48508634222919939]
[104206,"Construction-New","2009-06-12",2009,1374841.85,1374841.85,14943362.869999999,17184867.300499998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D344,'Const Index'!A:F,4,0))*F344","v":2674932.1708422177},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D344,'Const Index'!A:F,4,0))*G344","v":29074240.125533048},0.11200351098748365,5.5014327865894844E-2,5.6989183121588807E-2,310,0.48665620094191525]
[101633,"Bridge Replacement","2009-05-08",2009,574907.76,574907.76,5066313.4800000004,5826260.5020000003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D345,'Const Index'!A:F,4,0))*F345","v":1118557.2089552239},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D345,'Const Index'!A:F,4,0))*G345","v":9857166.4189765472},0.13347654705330234,7.6515862494715745E-2,5.6960684558586591E-2,311,0.48822605965463106]
[101429,"Reconstruction","2009-10-30",2009,1386631.76,1386631.76,15399831.9,17709806.685000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D346,'Const Index'!A:F,4,0))*F346","v":2697870.9616204691},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D346,'Const Index'!A:F,4,0))*G346","v":29962359.50692964},0.11004200623774341,5.4511757203656107E-2,5.5530249034087299E-2,312,0.48979591836734693]
[100270,"Reconstruction","2009-06-12",2009,1819198.63,1819198.63,21991685.210000001,25290437.991500001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D347,'Const Index'!A:F,4,0))*F347","v":3539485.6074093813},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D347,'Const Index'!A:F,4,0))*G347","v":42787660.456556506},0.10272211122650932,4.8898294313200912E-2,5.3823816913308405E-2,313,0.49136577708006279]
[101994,"Bridge Replacement","2009-05-08",2009,180467.95,180467.95,1217045.25,1399602.0375000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D348,'Const Index'!A:F,4,0))*F348","v":351123.67670575698},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D348,'Const Index'!A:F,4,0))*G348","v":2367918.530117271},0.16828368131751881,0.11821266398727268,5.0071017330246131E-2,314,0.49293563579277866]
[101743,"Bridge Replacement","2009-06-12",2009,307521.31,307521.31,2448984.29,2816331.9335000003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D349,'Const Index'!A:F,4,0))*F349","v":598322.3781982942},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D349,'Const Index'!A:F,4,0))*G349","v":4764814.8499466954},0.14557096068590947,9.5508456401267566E-2,5.0062504284641901E-2,315,0.49450549450549453]
[100413,"Bridge Replacement","2009-08-07",2009,243802.21,243802.21,1829628.9,2104073.2349999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D350,'Const Index'!A:F,4,0))*F350","v":474348.64952025586},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D350,'Const Index'!A:F,4,0))*G350","v":3559779.0431769723},0.15325227317955023,0.10439070661555784,4.886156656399239E-2,316,0.49607535321821034]
[100519,"Bridge Replacement","2009-08-07",2009,433417.54,433417.54,4146763.83,4768778.4045000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D351,'Const Index'!A:F,4,0))*F351","v":843269.73400852876},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D351,'Const Index'!A:F,4,0))*G351","v":8068063.9549573567},0.1245194657251556,8.1335701894099097E-2,4.3183763831056501E-2,317,0.4976452119309262]
[103210,"Reconstruction","2009-06-12",2009,370741.37,370741.37,8954170.3599999994,10297295.913999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D352,'Const Index'!A:F,4,0))*F352","v":721325.16018123669},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D352,'Const Index'!A:F,4,0))*G352","v":17421493.504264392},6.1404323917732567E-2,6.4315377518659456E-2,2.9110536009268884E-3,318,0.49921507064364207]
[100503,"Bridge Replacement","2009-08-07",2009,333178.03999999998,333178.03999999998,2948015.55,3390217.8824999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D353,'Const Index'!A:F,4,0))*F353","v":648240.85607675905},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D353,'Const Index'!A:F,4,0))*G353","v":5735744.5402452024},0.13301773493019736,9.025597789147416E-2,4.2761757038723203E-2,319,0.50078492935635788]
[103943,"Bridge Replacement","2009-06-12",{"$f":"YEAR(C354)","v":2009},66527.19,66527.19,341777.54,393044.17099999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D354,'Const Index'!A:F,4,0))*F354","v":129437.23001066099},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D354,'Const Index'!A:F,4,0))*G354","v":664972.2926439232},0.21465056129785476,0.17413688938920766,4.0513671908647103E-2,320,0.50235478806907374]
[100311,"Widen","2009-05-08",2009,1200045.0900000001,1200045.0900000001,16987294.170000002,19535388.295500003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D355,'Const Index'!A:F,4,0))*F355","v":2334842.5258528786},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D355,'Const Index'!A:F,4,0))*G355","v":33050972.132462692},9.0643686863285763E-2,{"$f":"8.4856*G355^-0.305","v":5.2904750738019687E-2},3.7738936125266076E-2,321,0.50392464678178961]
[100349,"Reconstruction","2009-08-07",2009,1037231.12,1037231.12,14323132.810000001,16471602.7315,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D356,'Const Index'!A:F,4,0))*F356","v":2018066.9445628999},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D356,'Const Index'!A:F,4,0))*G356","v":27867502.535447761},9.2416498105486744E-2,5.5730245998803489E-2,3.6686252106683255E-2,322,{"$f":"N356/637","v":0.50549450549450547}]
[101271,"Reconstruction","2009-07-17",2009,1260717.75,1260717.75,18702099.41,21507414.3215,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D357,'Const Index'!A:F,4,0))*F357","v":2452889.0125266523},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D357,'Const Index'!A:F,4,0))*G357","v":36387346.933102347},8.7410493461813968E-2,5.13754922070375E-2,3.6035001254776468E-2,{"$f":"N356+1","v":323},0.50706436420722134]
[103817,"Bridge Replacement","2009-03-20",2009,153859.25,153859.25,1638921,1884759.15,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D358,'Const Index'!A:F,4,0))*F358","v":299353.01839019189},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D358,'Const Index'!A:F,4,0))*G358","v":3188732.2228144989},0.11387838095917985,0.10795490007133737,5.923480887842475E-3,324,0.50863422291993721]
[101870,"Bridge Replacement","2009-05-08",2009,68345.929999999993,68345.929999999993,467216.55,537299.03249999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D359,'Const Index'!A:F,4,0))*F359","v":132975.82329424305},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D359,'Const Index'!A:F,4,0))*G359","v":909030.06796375266},0.16628319566162625,0.15829948402751695,7.9837116341092973E-3,325,0.51020408163265307]
[100364,"Bridge Replacement","2009-10-30",2009,240189.57,240189.57,2242683.0099999998,2579085.4614999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D360,'Const Index'!A:F,4,0))*F360","v":467319.79237739876},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D360,'Const Index'!A:F,4,0))*G360","v":4363429.0972814495},0.12709920614237855,9.8106627899547605E-2,2.8992578242830941E-2,326,0.51177394034536894]
[101632,"Bridge Replacement","2009-05-08",2009,327257.59000000003,327257.59000000003,3457005.83,3975556.7045,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D361,'Const Index'!A:F,4,0))*F361","v":636721.85687633266},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D361,'Const Index'!A:F,4,0))*G361","v":6726050.7886460554},0.11466503850240832,8.5976353536190972E-2,2.8688684966217348E-2,327,0.5133437990580848]
[101405,"Reconstruction","2009-09-18",2009,927534.43,927534.43,14957234.48,17200819.651999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D362,'Const Index'!A:F,4,0))*F362","v":1804637.8835287848},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D362,'Const Index'!A:F,4,0))*G362","v":29101229.132196162},8.2012428249369801E-2,5.4998761356679068E-2,2.7013666892690733E-2,328,0.51491365777080067]
[102067,"Bridge Replacement","2009-06-12",2009,411575.53,411575.53,4961058.7699999996,5705217.5854999991,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D363,'Const Index'!A:F,4,0))*F363","v":800773.28598081029},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D363,'Const Index'!A:F,4,0))*G363","v":9652379.8030383792},0.10296122845567501,7.7007384374167875E-2,2.5953844081507138E-2,329,0.51648351648351654]
[102019,"Bridge Replacement","2009-05-08",2009,238851.42,238851.42,2331197.6,2680877.2400000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D364,'Const Index'!A:F,4,0))*F364","v":464716.24893390195},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D364,'Const Index'!A:F,4,0))*G364","v":4535645.6503198296},0.12245867617571329,9.6955161523206324E-2,2.550351465250697E-2,330,0.51805337519623229]
[101630,"Bridge Replacement","2009-08-07",2009,451080.23,451080.23,5726188.6200000001,6585116.9129999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D365,'Const Index'!A:F,4,0))*F365","v":877634.77585287846},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D365,'Const Index'!A:F,4,0))*G365","v":11141038.626332622},9.8774951356736834E-2,7.3711208702371162E-2,2.5063742654365673E-2,331,0.51962323390894816]
[100325,"Reconstruction","2009-06-12",2009,1525416.06,1525416.06,31761564.120000001,36525798.737999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D366,'Const Index'!A:F,4,0))*F366","v":2967893.720149254},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D366,'Const Index'!A:F,4,0))*G366","v":61796220.169509597},6.8027107677592555E-2,4.3712181609063615E-2,2.431492606852894E-2,332,0.52119309262166402]
[101622,"Bridge Replacement","2009-07-17",2009,351131.72,351131.72,4705895.87,5411780.2505000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D367,'Const Index'!A:F,4,0))*F367","v":683172.05650319823},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D367,'Const Index'!A:F,4,0))*G367","v":9155927.4656183366},9.4615276176946095E-2,7.825762261613968E-2,1.6357653560806415E-2,333,0.52276295133437989]
[101574,"Widen","2009-05-08",2009,1184230.05,1184230.05,23243355.66,26729859.009,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D368,'Const Index'!A:F,4,0))*F368","v":2304072.3254264393},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D368,'Const Index'!A:F,4,0))*G368","v":45222946.779850744},7.0949185966205711E-2,4.8079662829682408E-2,2.2869523136523302E-2,334,0.52433281004709575]
[101453,"Bridge Replacement","2009-10-30",2009,206973.76,206973.76,1985815.26,2283687.5490000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D369,'Const Index'!A:F,4,0))*F369","v":402694.14925373136},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D369,'Const Index'!A:F,4,0))*G369","v":3863659.7542643924},0.12422608999388997,0.10181486939836623,2.2411220595523737E-2,335,0.52590266875981162]
[40347,"Bridge Replacement","2009-03-20",2009,47300.49,47300.49,248819.74,286142.701,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D370,'Const Index'!A:F,4,0))*F370","v":92029.20495735608},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D370,'Const Index'!A:F,4,0))*G370","v":484110.90138592751},0.2100994269988386,0.19183934463033234,1.8260082368506264E-2,336,0.52747252747252749]
[103138,"Bridge Replacement","2009-08-07",2009,296152.49,296152.49,3522375.97,4050732.3655000003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D371,'Const Index'!A:F,4,0))*F371","v":576202.87233475479},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D371,'Const Index'!A:F,4,0))*G371","v":6853236.8286247337},0.10407747853219655,8.5486525175022143E-2,1.8590953357174408E-2,337,0.52904238618524335]
[100491,"Bridge Replacement","2009-10-30",2009,313234.34999999998,313234.34999999998,3669574.61,4220010.8015000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D372,'Const Index'!A:F,4,0))*F372","v":609437.8344882729},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D372,'Const Index'!A:F,4,0))*G372","v":7139630.7710554367},0.10535985319562695,8.4425717567781777E-2,2.0934135627845171E-2,338,0.53061224489795922]
[101404,"Widen","2009-06-12",2009,1622779.7,1622779.7,38698150.68,44502873.281999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D373,'Const Index'!A:F,4,0))*F373","v":3157327.2414712152},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D373,'Const Index'!A:F,4,0))*G373","v":75292244.12686567},6.1934295863876665E-2,4.115636796016052E-2,2.0777927903716145E-2,339,0.53218210361067508]
[101635,"Bridge Replacement","2009-12-11",2009,469613.09,469613.09,6777255.1100000003,7793843.3765000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D374,'Const Index'!A:F,4,0))*F374","v":913692.84568230284},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D374,'Const Index'!A:F,4,0))*G374","v":13186024.067963753},8.929252070016884E-2,7.0018231384163104E-2,1.9274289316005735E-2,340,0.53375196232339095]
[100649,"Bridge Replacement","2009-06-12",2009,96332.73,96332.73,685805.25,788676.03749999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D375,'Const Index'!A:F,4,0))*F375","v":187427.7529317697},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D375,'Const Index'!A:F,4,0))*G375","v":1334322.5812899787},0.1604665974779283,0.1408125327874904,1.96540646904379E-2,341,0.5353218210361067]
[40488,"Bridge Replacement","2010-08-06",2010,107353.96,107353.96,288032,331236.8,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D376,'Const Index'!A:F,4,0))*F376","v":203237.52800829877},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D376,'Const Index'!A:F,4,0))*G376","v":545288.79668049794},0.39271539273414069,0.18346495982969993,0.20925043290444076,342,0.53689167974882257]
[101800,"Bridge Replacement","2010-06-18",2010,90514.54,90514.54,258176.25,296902.6875,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D377,'Const Index'!A:F,4,0))*F377","v":171357.92064315351},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D377,'Const Index'!A:F,4,0))*G377","v":488767.27826763486},0.3705920470996073,0.18969159483298426,0.18090045226662305,343,0.53846153846153844]
[40398,"Bridge Replacement","2010-03-19",2010,203020.92,203020.92,680545.59,782627.42849999992,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D378,'Const Index'!A:F,4,0))*F378","v":384349.77074688795},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D378,'Const Index'!A:F,4,0))*G378","v":1288377.2839730289},0.31832082226849789,0.14114357145799095,0.17717725081050695,344,0.5400313971742543]
[103894,"Bridge Replacement","2010-12-10",2010,148862.76999999999,148862.76999999999,483802.1,556372.41499999992,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D379,'Const Index'!A:F,4,0))*F379","v":281820.07806016592},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D379,'Const Index'!A:F,4,0))*G379","v":915911.65197095426},0.32769351765939003,0.15662420960184462,0.17106930805754542,345,0.54160125588697017]
[112550,"Turn Lanes","2010-10-29",2010,135565.09,135565.09,439499.93,505424.91949999996,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D380,'Const Index'!A:F,4,0))*F380","v":256645.52826763483},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D380,'Const Index'!A:F,4,0))*G380","v":832040.84258298751},0.3284530411643069,0.16127985292455191,0.16717318823975499,346,0.54317111459968603]
[103949,"Bridge Replacement","2010-12-10",2010,291059.15000000002,291059.15000000002,1112357.6000000001,1279211.2400000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D381,'Const Index'!A:F,4,0))*F381","v":551019.65637966804},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D381,'Const Index'!A:F,4,0))*G381","v":2105863.7136929464},0.28165969468811108,0.12150048339327492,0.16015921129483618,347,0.5447409733124019]
[106088,"Bridge Replacement","2010-12-10",2010,213778.99,213778.99,778365.41,895120.22149999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D382,'Const Index'!A:F,4,0))*F382","v":404716.44891078834},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D382,'Const Index'!A:F,4,0))*G382","v":1473565.221213693},0.29465119499593384,0.13547887442547063,0.15917232057046321,348,0.54631083202511777]
[103877,"Bridge Replacement","2010-10-29",2010,70974.98,70974.98,218146.51,250868.4865,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D383,'Const Index'!A:F,4,0))*F383","v":134366.53371369294},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D383,'Const Index'!A:F,4,0))*G383","v":412984.83480290457},0.3453546435375015,0.19969368614317418,0.14566095739432733,349,0.54788069073783363]
[103965,"Bridge Replacement","2010-10-29",2010,263998.55,263998.55,1160000,1334000,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D384,'Const Index'!A:F,4,0))*F384","v":499789.78604771779},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D384,'Const Index'!A:F,4,0))*G384","v":2196058.0912863072},0.24758495689655166,0.11995624681864427,0.12762871007790738,350,0.5494505494505495]
[105354,"Bridge Replacement","2010-04-30",2010,125676.4,125676.4,505381.49,581188.71349999995,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D385,'Const Index'!A:F,4,0))*F385","v":237924.71991701244},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D385,'Const Index'!A:F,4,0))*G385","v":956764.75025933608},0.26867630193579112,0.15455343425138798,0.11412286768440313,351,0.55102040816326525]
[101981,"Bridge Replacement","2010-12-10",2010,125759.49,125759.49,513520,590548,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D386,'Const Index'!A:F,4,0))*F386","v":238082.02204356846},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D386,'Const Index'!A:F,4,0))*G386","v":972172.19917012448},0.26489696603832374,0.15380220443797929,0.11109476160034445,352,0.55259026687598112]
[105353,"Bridge Replacement","2010-09-17",2010,269129.3,269129.3,1318778.6499999999,1516595.4474999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D387,'Const Index'!A:F,4,0))*F387","v":509503.08350622404},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D387,'Const Index'!A:F,4,0))*G387","v":2496650.4525414933},0.22407465650130143,0.11535332676958115,0.10872132973172027,353,0.55416012558869698]
[100257,"Reconstruction","2010-10-29",2010,1623995.25,1623995.25,11431908.699999999,13146695.004999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D388,'Const Index'!A:F,4,0))*F388","v":3074472.3353215768},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D388,'Const Index'!A:F,4,0))*G388","v":21642358.275414936},0.16205810181111752,5.9697526624711582E-2,0.10236057518640593,354,0.55572998430141285]
[105339,"Bridge Replacement","2010-10-29",2010,270636.68,270636.68,1465045.23,1684802.0145,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D389,'Const Index'!A:F,4,0))*F389","v":512356.78526970954},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D389,'Const Index'!A:F,4,0))*G389","v":2773555.5443464727},0.20472923187497769,0.11171152766000664,9.3017704214971048E-2,355,0.55729984301412872]
[100425,"Bridge Replacement","2010-06-18",2010,731387.52,731387.52,5085758.91,5848622.7465000004,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D390,'Const Index'!A:F,4,0))*F390","v":1384628.8630705394},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D390,'Const Index'!A:F,4,0))*G390","v":9628122.4177904557},0.16381089094921333,7.6426513226811793E-2,8.7384377722401541E-2,356,0.55886970172684458]
[103678.02,"Construction-New","2010-10-29",2010,1770938.75,1770938.75,14657837.810000001,16856513.4815,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D391,'Const Index'!A:F,4,0))*F391","v":3352658.940612033},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D391,'Const Index'!A:F,4,0))*G391","v":27749537.347769711},0.14081855270576224,5.533899053690515E-2,8.547956216885709E-2,357,0.56043956043956045]
[102198,"Bridge Replacement","2010-10-29",2010,279675.26,279675.26,1618339.32,1861090.2180000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D392,'Const Index'!A:F,4,0))*F392","v":529468.20487551868},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D392,'Const Index'!A:F,4,0))*G392","v":3063764.7914937758},0.19281620519484133,0.10837181129086594,8.4444393903975387E-2,358,0.56200941915227631]
[100518,"Bridge Replacement","2010-10-29",2010,387907.37,387907.37,2453763.27,2821827.7604999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D393,'Const Index'!A:F,4,0))*F393","v":734368.20565352694},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D393,'Const Index'!A:F,4,0))*G393","v":4645350.5889522824},0.17808671306747531,9.5451683855398428E-2,8.2635029212076883E-2,359,0.56357927786499218]
[105349,"Bridge Replacement","2010-08-06",2010,401668.26,401668.26,2663594.12,3063133.2379999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D394,'Const Index'!A:F,4,0))*F394","v":760419.68309128634},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D394,'Const Index'!A:F,4,0))*G394","v":5042592.6026970958},0.17079934926421897,9.3092523131703686E-2,7.7706826132515283E-2,360,0.56514913657770804]
[101982,"Bridge Replacement","2010-12-10",2010,88858.82,88858.82,397888.2,457571.43,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D395,'Const Index'!A:F,4,0))*F395","v":168223.38848547719},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D395,'Const Index'!A:F,4,0))*G395","v":753263.44917012448},0.24332610014571934,0.16624761846403152,{"$f":"ABS(L395-K395)","v":7.7078481681687822E-2},361,0.56671899529042391]
[112229,"Bridge Replacement","2010-09-17",2010,182195.83,182195.83,1016830.82,1169355.443,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D396,'Const Index'!A:F,4,0))*F396","v":344924.67816390039},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D396,'Const Index'!A:F,4,0))*G396","v":1925016.8532157675},0.19918008228743497,0.12487390758873509,7.4306174698699878E-2,362,0.56828885400313967]
[101328,"Reconstruction","2010-12-10",2010,606264.43000000005,606264.43000000005,4567228.03,5252312.2345000003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D397,'Const Index'!A:F,4,0))*F397","v":1147751.6439315353},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D397,'Const Index'!A:F,4,0))*G397","v":8646463.8534751032},0.15274231678771685,7.8974790727821292E-2,7.3767526059895561E-2,363,0.56985871271585553]
[100647,"Bridge Replacement","2010-08-06",2010,180471.59,180471.59,1016098.24,1168512.976,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D398,'Const Index'!A:F,4,0))*F398","v":341660.42712655599},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D398,'Const Index'!A:F,4,0))*G398","v":1923629.9668049791},0.19761234386155416,0.12490136010284332,7.2710983758710837E-2,364,0.5714285714285714]
[40369,"Bridge Replacement","2010-10-29",2010,167705.54,167705.54,941155.28,1082328.5719999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D399,'Const Index'!A:F,4,0))*F399","v":317492.33454356849},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D399,'Const Index'!A:F,4,0))*G399","v":1781751.4377593361},0.19819114822370226,0.12785445476555024,7.0336693458152022E-2,365,0.57299843014128726]
[101003,"Construction-New","2010-02-05",2010,124993.58,124993.58,9702714.8200000003,{"$f":"G400+(G400*0.15)","v":11158122.043},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D400,'Const Index'!A:F,4,0))*F400","v":236632.03682572613},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D400,'Const Index'!A:F,4,0))*G400","v":18368728.78267635},{"$f":"I400/J400+0.02","v":3.2882330597035936E-2},6.2759591691888619E-2,2.9877261094852683E-2,366,0.57456828885400313]
[100512,"Bridge Replacement","2010-04-30",2010,61618.63,61618.63,583672.66,671223.55900000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D401,'Const Index'!A:F,4,0))*F401","v":116653.52671161825},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D401,'Const Index'!A:F,4,0))*G401","v":1104981.9548755188},0.1255705264659818,0.14791114664175262,2.234062017577082E-2,367,0.57613814756671899]
[102236,"Modify Interchange","2010-06-18",2010,1257147.52,1257147.52,13570825.43,15606449.2445,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D402,'Const Index'!A:F,4,0))*F402","v":2379973.2614107882},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D402,'Const Index'!A:F,4,0))*G402","v":25691656.026711617},0.11263603945718134,5.6654921918956755E-2,5.5981117538224587E-2,368,0.57770800627943486]
[101590,"Reconstruction","2010-10-29",2010,1095504.83,1095504.83,11472141.23,13192962.4145,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D403,'Const Index'!A:F,4,0))*F403","v":2073958.8327282157},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D403,'Const Index'!A:F,4,0))*G403","v":21718524.631483402},0.11549262060470641,5.9633594516269747E-2,5.5859026088436667E-2,369,0.57927786499215073]
[100990,"Reconstruction","2010-12-10",2010,2362909.63,2362909.63,31422740.719999999,36136151.828000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D404,'Const Index'!A:F,4,0))*F404","v":4473350.699948132},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D404,'Const Index'!A:F,4,0))*G404","v":59488072.421161823},9.5197439047576493E-2,4.3855404084421845E-2,5.1342034963154648E-2,370,0.58084772370486659]
[101687,"Bridge Replacement","2010-09-17",2010,408477.95,408477.95,3509070.94,4035431.5809999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D405,'Const Index'!A:F,4,0))*F405","v":773311.47173236508},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D405,'Const Index'!A:F,4,0))*G405","v":6643210.0264522815},0.13640629584992089,8.5585255335082544E-2,5.082104051483835E-2,371,0.58241758241758246]
[105343,"Bridge Replacement","2010-06-18",2010,191344.72,191344.72,1320998.01,1519147.7115,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D406,'Const Index'!A:F,4,0))*F406","v":362244.93153526972},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D406,'Const Index'!A:F,4,0))*G406","v":2500852.0417531119},0.1648486057901026,0.11529418296314663,4.9554422826955977E-2,372,0.58398744113029832]
[105345,"Bridge Replacement","2010-09-17",2010,132218.78,132218.78,1605938.12,1846828.838,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D407,'Const Index'!A:F,4,0))*F407","v":250310.44968879668},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D407,'Const Index'!A:F,4,0))*G407","v":3040287.4159751036},0.10233117973437234,0.10862637071751487,6.2951909831425318E-3,373,0.58555729984301408]
[100331,"Widen","2010-12-10",2010,2667531.42,2667531.42,40605155.490000002,46695928.813500002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D408,'Const Index'!A:F,4,0))*F408","v":5050046.5160788381},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D408,'Const Index'!A:F,4,0))*G408","v":76871793.329097509},8.569440229472694E-2,4.0556950862748874E-2,4.5137451431978066E-2,374,0.58712715855572994]
[103934,"Bridge Replacement","2010-10-29",2010,54673.919999999998,54673.919999999998,256171.7,294597.45500000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D409,'Const Index'!A:F,4,0))*F409","v":103506.12448132779},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D409,'Const Index'!A:F,4,0))*G409","v":484972.35736514523},0.23342685394210208,0.19014309335992235,4.3283760582179726E-2,375,0.58869701726844581]
[101628,"Bridge Replacement","2010-12-10",2010,441748.27,441748.27,4714345.3600000003,5421497.1640000008,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D410,'Const Index'!A:F,4,0))*F410","v":836297.2953838174},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D410,'Const Index'!A:F,4,0))*G410","v":8924979.5456431545},0.11370299294322382,7.8214816456239386E-2,3.5488176486984435E-2,376,0.59026687598116168]
[105327,"Bridge Replacement","2010-08-06",2010,84057.13,84057.13,658213.39,756945.39850000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D411,'Const Index'!A:F,4,0))*F411","v":159133.05212655602},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D411,'Const Index'!A:F,4,0))*G411","v":1246099.0007780083},0.14770498333374835,0.14258725502782435,5.1177283059239964E-3,377,0.59183673469387754]
[105460,"Bridge Replacement","2010-10-29",2010,424871.08,424871.08,4578010.55,5264712.1324999994,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D412,'Const Index'!A:F,4,0))*F412","v":804346.18360995851},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D412,'Const Index'!A:F,4,0))*G412","v":8666876.8192427382},0.1128069246148854,7.8918011747661151E-2,3.3888912867224244E-2,378,0.59340659340659341]
[101626,"Bridge Replacement","2010-12-10",2010,777558.97,777558.97,21546182.890000001,24778110.3235,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D413,'Const Index'!A:F,4,0))*F413","v":1472038.5064834023},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D413,'Const Index'!A:F,4,0))*G413","v":40790232.130964734},5.6088014938408412E-2,4.9204474909741572E-2,6.8835400286668402E-3,379,0.59497645211930927]
[100243,"Construction-New","2010-10-29",2010,904657.02,904657.02,13494558.949999999,15518742.792499999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D414,'Const Index'!A:F,4,0))*F414","v":1712654.6281120332},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D414,'Const Index'!A:F,4,0))*G414","v":25547271.871109955},8.7038650418434033E-2,5.6752389781186616E-2,3.0286260637247417E-2,380,0.59654631083202514]
[105340,"Bridge Replacement","2010-02-05",2010,111241.82,111241.82,759171.79,873047.55850000004,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D415,'Const Index'!A:F,4,0))*F415","v":210597.84387966804},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D415,'Const Index'!A:F,4,0))*G415","v":1437228.7518153528},0.16653049739901424,0.13651451704321896,3.001598035579528E-2,381,0.59811616954474101]
[102063,"Reconstruction","2010-12-10",2010,548986.34,548986.34,6987009.25,8035060.6375000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D416,'Const Index'!A:F,4,0))*F416","v":1039315.4258298754},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D416,'Const Index'!A:F,4,0))*G416","v":13227481.204616182},9.8572436411186945E-2,6.9370320945255928E-2,2.9202115465931017E-2,382,0.59968602825745687]
[103139,"Bridge Replacement","2010-10-29",2010,1499593.76,1499593.76,29562269.579999998,33996610.016999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D417,'Const Index'!A:F,4,0))*F417","v":2838961.2157676346},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D417,'Const Index'!A:F,4,0))*G417","v":55965914.920643151},7.0726611363240266E-2,4.4679420856473022E-2,2.6047190506767244E-2,383,0.60125588697017274]
[105346,"Bridge Replacement","2010-06-18",{"$f":"YEAR(C418)","v":2010},379815.72,379815.72,5547289.6600000001,6379383.1090000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D418,'Const Index'!A:F,4,0))*F418","v":719049.46991701238},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D418,'Const Index'!A:F,4,0))*G418","v":10501870.984958505},8.8468701524412552E-2,7.442826555317178E-2,1.4040435971240772E-2,384,0.60282574568288849]
[100634,"Bridge Replacement","2010-04-30",2010,296354.48,296354.48,3794993.51,4364242.5364999995,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D419,'Const Index'!A:F,4,0))*F419","v":561044.52904564305},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D419,'Const Index'!A:F,4,0))*G419","v":7184505.3482883815},9.8090905615277321E-2,{"$f":"8.4856*G419^-0.305","v":8.356476369166739E-2},1.4526141923609931E-2,385,0.60439560439560436]
[100350,"Reconstruction","2010-09-17",2010,1516869.52,1516869.52,31597391.140000001,36336999.811000004,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D420,'Const Index'!A:F,4,0))*F420","v":2871666.8817427387},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D420,'Const Index'!A:F,4,0))*G420","v":59818712.479771785},6.8006163334154296E-2,4.378132811396631E-2,2.4224835220187986E-2,386,{"$f":"N420/637","v":0.60596546310832022}]
[100317,"Widen","2010-08-06",2010,1592808.69,1592808.69,36548219.630000003,42030452.574500002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D421,'Const Index'!A:F,4,0))*F421","v":3015431.3892634851},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D421,'Const Index'!A:F,4,0))*G421","v":69191390.897043571},6.3581019981957462E-2,4.1880162381415932E-2,2.170085760054153E-2,{"$f":"N420+1","v":387},0.60753532182103609]
[105331,"Bridge Replacement","2010-06-18",2010,79066.47,79066.47,516413.22,593875.20299999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D422,'Const Index'!A:F,4,0))*F422","v":149684.96654564314},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D422,'Const Index'!A:F,4,0))*G422","v":977649.50881742733},0.173106982815041,0.15353887835152707,1.9568104463513925E-2,388,0.60910518053375196]
[105969,"Bridge Replacement","2011-05-06",2011,103025.08,103025.08,283333.5,325833.52500000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D423,'Const Index'!A:F,4,0))*F423","v":186159.1792079208},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D423,'Const Index'!A:F,4,0))*G423","v":511963.99752475251},0.38361771551899088,0.18438759011662331,0.19923012540236756,389,0.61067503924646782]
[104313,"Bridge Replacement","2011-12-09",2011,178544.78,178544.78,554066.59,637176.57849999995,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D424,'Const Index'!A:F,4,0))*F424","v":322618.04306930694},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D424,'Const Index'!A:F,4,0))*G424","v":1001159.9274752475},0.34224426309480238,0.15027825970479186,0.19196600339001052,390,0.61224489795918369]
[107720,"Bridge Replacement","2011-04-01",2011,125143.03,125143.03,395797,455166.55,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D425,'Const Index'!A:F,4,0))*F425","v":226124.78193069308},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D425,'Const Index'!A:F,4,0))*G425","v":715177.74752475251},0.33617983461218759,0.16651503152378863,0.16966480308839896,391,0.61381475667189955]
[100379,"Bridge Replacement","2011-10-28",2011,719069.96,719069.96,3070498.17,3531072.8955000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D426,'Const Index'!A:F,4,0))*F426","v":1299309.5811881188},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D426,'Const Index'!A:F,4,0))*G426","v":5548177.3863861384},0.2541867411046202,8.9142304812410297E-2,0.16504443629220988,392,0.61538461538461542]
[101948,"Bridge Replacement","2011-06-17",2011,238933.16,238933.16,909395.65,1045804.9975000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D427,'Const Index'!A:F,4,0))*F427","v":431735.6603960396},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D427,'Const Index'!A:F,4,0))*G427","v":1643214.912128713},0.28273840214652446,0.12920012378159645,0.153538278364928,393,0.61695447409733128]
[103884,"Bridge Replacement","2011-05-06",2011,69638.350000000006,69638.350000000006,209812,241283.8,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D428,'Const Index'!A:F,4,0))*F428","v":125831.67202970298},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D428,'Const Index'!A:F,4,0))*G428","v":379115.74257425743},0.35190832745505507,0.20208045317381107,0.149827874281244,394,0.61852433281004715]
[40492,"Bridge Replacement","2011-08-05",2011,221994.33,221994.33,953506.42,1096532.3829999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D429,'Const Index'!A:F,4,0))*F429","v":401128.36856435641},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D429,'Const Index'!A:F,4,0))*G429","v":1722920.0163366338},0.25281891484275476,0.12734703895001384,0.12547187589274092,395,0.62009419152276291]
[115332,"Construction-New","2011-09-16",2011,7824.46,7824.46,3847537.37,4424667.9754999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D430,'Const Index'!A:F,4,0))*F430","v":14138.256930693069},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D430,'Const Index'!A:F,4,0))*G430","v":6952233.3665841585},2.2033628071038074E-2,8.3215032589561005E-2,6.1181404518522928E-2,396,0.62166405023547877]
[114169,"Widen","2011-12-28",2011,6527348.3700000001,6527348.3700000001,56592101,65080916.149999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D431,'Const Index'!A:F,4,0))*F431","v":11794466.114108911},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D431,'Const Index'!A:F,4,0))*G431","v":102258004.28217822},0.13534027284125746,3.6651523478480129E-2,9.8688749362777328E-2,397,0.62323390894819464]
[40435,"Bridge Replacement","2011-10-28",2011,112342.74,112342.74,480305.9,552351.78500000003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D432,'Const Index'!A:F,4,0))*F432","v":202995.54504950496},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D432,'Const Index'!A:F,4,0))*G432","v":867879.47277227731},0.25389831355392467,0.15697105956305585,9.6927253990868822E-2,398,0.6248037676609105]
[40028.01,"Construction-New","2011-06-17",2011,1309393.83,1309393.83,9526090.2699999996,10955003.8105,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D433,'Const Index'!A:F,4,0))*F433","v":2365983.9007425746},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D433,'Const Index'!A:F,4,0))*G433","v":17212984.893811882},0.15745343502817763,6.3112237098065266E-2,9.4341197930112364E-2,399,0.62637362637362637]
[103945,"Bridge Replacement","2011-09-16",2011,105124.45,105124.45,456468.82,524939.14300000004,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D434,'Const Index'!A:F,4,0))*F434","v":189952.59529702971},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D434,'Const Index'!A:F,4,0))*G434","v":824807.52128712879},0.25029930061816708,0.15942710686355444,9.087219375461264E-2,400,0.62794348508634223]
[105330,"Bridge Replacement","2011-02-11",2011,407936.36,407936.36,2536968.7799999998,2917514.0969999996,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D435,'Const Index'!A:F,4,0))*F435","v":737112.72970297025},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D435,'Const Index'!A:F,4,0))*G435","v":4584126.7559405938},0.18079675998220204,9.4485777992344255E-2,8.6310981989857788E-2,401,0.6295133437990581]
[113898.01,"Widen","2011-08-05",2011,26338.54,26338.54,7602690.04,8743093.5460000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D436,'Const Index'!A:F,4,0))*F436","v":47591.916336633665},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D436,'Const Index'!A:F,4,0))*G436","v":13737533.983168317},2.3464371145137466E-2,6.7606356935593373E-2,4.4141985790455904E-2,402,0.63108320251177397]
[107370,"Reconstruction","2011-12-09",2011,80291.839999999997,80291.839999999997,2778185.8,3194913.67,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D437,'Const Index'!A:F,4,0))*F437","v":145081.7900990099},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D437,'Const Index'!A:F,4,0))*G437","v":5019989.1930693071},4.8900817216760664E-2,9.1904200900454633E-2,4.3003383683693969E-2,403,0.63265306122448983]
[107715,"Bridge Replacement","2011-02-11",2011,108602.47,108602.47,519050.95,596908.59250000003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D438,'Const Index'!A:F,4,0))*F438","v":196237.13638613862},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D438,'Const Index'!A:F,4,0))*G438","v":937889.09282178222},0.22923277377683249,0.15330047793083237,7.5932295846000114E-2,404,0.6342229199372057]
[40441,"Bridge Replacement","2011-10-28",2011,121614.92,121614.92,622251.78,715589.54700000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D439,'Const Index'!A:F,4,0))*F439","v":219749.73168316833},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D439,'Const Index'!A:F,4,0))*G439","v":1124365.8400990099},0.21544326574686537,0.14505171928437074,7.0391546462494625E-2,405,0.63579277864992145]
[101637,"Bridge Replacement","2011-08-05",2011,338443.63,338443.63,2360780.4500000002,2714897.5175000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D440,'Const Index'!A:F,4,0))*F440","v":611544.18292079214},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D440,'Const Index'!A:F,4,0))*G440","v":4265766.6547029708},0.16336090846567286,9.6582979267832478E-2,6.6777929197840383E-2,406,0.63736263736263732]
[106092,"Bridge Replacement","2011-02-11",2011,151102.56,151102.56,848796.14,976115.56099999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D441,'Const Index'!A:F,4,0))*F441","v":273031.85346534656},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D441,'Const Index'!A:F,4,0))*G441","v":1533715.7975247526},0.19801984820524748,0.13194639227849941,6.607345592674807E-2,407,0.63893249607535318]
[40507,"Bridge Replacement","2011-12-09",2011,61234.01,61234.01,271909.32,312695.71799999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D442,'Const Index'!A:F,4,0))*F442","v":110645.61212871288},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D442,'Const Index'!A:F,4,0))*G442","v":491321.296039604},0.24520011450876342,0.18671671896893452,5.8483395539828897E-2,408,0.64050235478806905]
[108894,"Bridge Replacement","2011-08-05",2011,127712.37,127712.37,751469.3,864189.69500000007,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D443,'Const Index'!A:F,4,0))*F443","v":230767.40123762377},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D443,'Const Index'!A:F,4,0))*G443","v":1357852.9430693071},0.18995021619645669,0.13693978029454371,5.3010435901912983E-2,409,0.64207221350078492]
[105356,"Bridge Replacement","2011-02-11",2011,213547.89,213547.89,1508642.56,1734938.9440000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D444,'Const Index'!A:F,4,0))*F444","v":385866.23688118818},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D444,'Const Index'!A:F,4,0))*G444","v":2726012.5465346538},0.16154969219481652,0.11071684904849723,5.0832843146319293E-2,410,0.64364207221350078]
[112757,"Bridge Replacement","2011-02-11",2011,74629.06,74629.06,376427.29,432891.3835,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D445,'Const Index'!A:F,4,0))*F445","v":134849.53910891089},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D445,'Const Index'!A:F,4,0))*G445","v":680178.02400990098},0.21825624226128768,0.16908295140888269,4.9173290852404988E-2,411,0.64521193092621665]
[107639,"Bridge Replacement","2011-08-05",2011,296853.89,296853.89,2428402.6,2792662.99,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D446,'Const Index'!A:F,4,0))*F446","v":536394.40519801981},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D446,'Const Index'!A:F,4,0))*G446","v":4387955.1930693071},0.1422424527135657,9.5754621877440244E-2,4.6487830836125454E-2,412,0.64678178963893251]
[113427,"Bridge Replacement","2011-09-16",2011,127111.25,127111.25,790642.25,909238.58750000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D447,'Const Index'!A:F,4,0))*F447","v":229681.21905940594},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D447,'Const Index'!A:F,4,0))*G447","v":1428635.7487623764},0.18076961482895706,0.13483376147893469,4.5935853350022371E-2,413,0.64835164835164838]
[40491,"Bridge Replacement","2011-04-01",2011,100137.15,100137.15,574957.68999999994,661201.34349999996,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D448,'Const Index'!A:F,4,0))*F448","v":180940.88985148515},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D448,'Const Index'!A:F,4,0))*G448","v":1038908.6972772276},0.19416438068686412,0.14859137801692177,4.5573002669942353E-2,414,0.64992150706436425]
[101202,"Widen","2011-09-16",2011,1632477.35,1632477.35,22491186.190000001,25864864.118500002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D449,'Const Index'!A:F,4,0))*F449","v":2949773.4294554456},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D449,'Const Index'!A:F,4,0))*G449","v":40640014.650247529},9.2582981449232313E-2,4.8564484793490265E-2,4.4018496655742048E-2,415,0.65149136577708011]
[101636,"Bridge Replacement","2011-09-16",2011,767411.86,767411.86,8813498.7100000009,10135523.516500002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D450,'Const Index'!A:F,4,0))*F450","v":1386660.044059406},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D450,'Const Index'!A:F,4,0))*G450","v":15925381.332425745},0.1070723290773591,6.4626749136620323E-2,4.2445579940738776E-2,416,0.65306122448979587]
[100541,"Bridge Replacement","2011-02-11",2011,200714.84,200714.84,2686330.45,3089280.0175000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D451,'Const Index'!A:F,4,0))*F451","v":362677.80495049508},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D451,'Const Index'!A:F,4,0))*G451","v":4854012.9418316837},9.4717107122841121E-2,9.2851500878981086E-2,1.8656062438600352E-3,417,0.65463108320251173]
[101625,"Bridge Replacement","2011-02-11",2011,167740.4,167740.4,1956114.73,2249531.9394999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D452,'Const Index'!A:F,4,0))*F452","v":303095.27722772275},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D452,'Const Index'!A:F,4,0))*G452","v":3534563.7448019804},0.105751820906742,0.10228390194075911,3.4679189659828913E-3,418,0.6562009419152276]
[105423,"Bridge Replacement","2011-08-05",2011,433216.56,433216.56,4588498.53,5276773.3095000004,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D453,'Const Index'!A:F,4,0))*F453","v":782792.29900990101},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D453,'Const Index'!A:F,4,0))*G453","v":8291098.8289603963},0.11441357715766774,7.8862950951058539E-2,3.5550626206609204E-2,419,0.65777080062794346]
[101398,"Widen","2011-12-09",2011,1154039.3999999999,1154039.3999999999,41996771.649999999,48296287.397500001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D454,'Const Index'!A:F,4,0))*F454","v":2085269.212871287},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D454,'Const Index'!A:F,4,0))*G454","v":75885255.704207927},4.7479240776356194E-2,4.0142249345606472E-2,7.3369914307497217E-3,420,0.65934065934065933]
[107384,"Reconstruction","2011-12-09",2011,943310.8,943310.8,14487703.439999999,16660858.956,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D455,'Const Index'!A:F,4,0))*F455","v":1704497.2376237626},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D455,'Const Index'!A:F,4,0))*G455","v":26178276.017821781},8.5111133997646221E-2,5.553639610262133E-2,2.9574737895024891E-2,421,0.6609105180533752]
[101203,"Modify Interchange","2011-06-17",2011,1151148.02,1151148.02,20281305.25,23323501.037500001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D456,'Const Index'!A:F,4,0))*F456","v":2080044.6896039604},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D456,'Const Index'!A:F,4,0))*G456","v":36646912.951732673},7.6759069784229E-2,5.0120835951751097E-2,2.6638233832477903E-2,422,0.66248037676609106]
[100514,"Bridge Replacement","2011-08-05",2011,237709.13,237709.13,2334800.4300000002,2685020.4945,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D457,'Const Index'!A:F,4,0))*F457","v":429523.92301980202},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D457,'Const Index'!A:F,4,0))*G457","v":4218822.5591584165},0.12181132697495692,9.6909505529410342E-2,2.4901821445546576E-2,423,0.66405023547880693]
[100256,"Reconstruction","2011-02-11",2011,710832.53,710832.53,13186938.199999999,15164978.93,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D458,'Const Index'!A:F,4,0))*F458","v":1284425.1160891091},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D458,'Const Index'!A:F,4,0))*G458","v":23827883.381188117},7.3904289170021301E-2,5.71529490681012E-2,1.6751340101920101E-2,424,0.66562009419152279]
[112758,"Bridge Replacement","2011-02-11",2011,68280.960000000006,68280.960000000006,405588.62,466426.913,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D459,'Const Index'!A:F,4,0))*F459","v":123378.96237623764},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D459,'Const Index'!A:F,4,0))*G459","v":732870.52623762377},0.18835028556767694,0.16527851370177424,{"$f":"ABS(L459-K459)","v":2.3071771865902702E-2},425,0.66718995290423866]
[100651,"Bridge Replacement","2011-12-09",2011,117998.55,117998.55,889562.94,1022997.3809999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D460,'Const Index'!A:F,4,0))*F460","v":213215.20173267327},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D460,'Const Index'!A:F,4,0))*G460","v":1607378.5797029703},0.15264778094285267,0.13007195505420166,2.2575825888651008E-2,426,0.66875981161695452]
[100633,"Bridge Replacement","2011-08-05",2011,177858.37,177858.37,1600354.1,1840407.2150000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D461,'Const Index'!A:F,4,0))*F461","v":321377.74777227722},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D461,'Const Index'!A:F,4,0))*G461","v":2891728.9430693071},0.1311368852680791,0.10874183299453881,2.2395052273540286E-2,427,0.67032967032967028]
[102031,"Bridge Replacement","2011-08-05",2011,132704.79999999999,132704.79999999999,1102506.05,1267881.9575,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D462,'Const Index'!A:F,4,0))*F462","v":239788.37623762374},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D462,'Const Index'!A:F,4,0))*G462","v":1992152.0210396042},0.14036650501827175,0.12183059255952719,1.8535912458744558E-2,428,0.67189952904238615]
[101397,"Reconstruction","2011-02-11",2011,1235311.78,1235311.78,26326649.899999999,30275647.384999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D463,'Const Index'!A:F,4,0))*F463","v":2232122.7707920792},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D463,'Const Index'!A:F,4,0))*G463","v":47570431.75},6.6922482909608644E-2,4.6287305316332177E-2,2.0635177593276467E-2,429,0.67346938775510201]
[100259.1,"Construction-New","2011-02-11",2011,1158434.55,1158434.55,24592431.600000001,{"$f":"G464+(G464*0.15)","v":28281296.340000004},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D464,'Const Index'!A:F,4,0))*F464","v":2093210.9443069308},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D464,'Const Index'!A:F,4,0))*G464","v":44436819.475247532},{"$f":"I464/J464+0.02","v":6.7105327722045985E-2},4.7259389473201033E-2,1.9845938248844952E-2,430,0.67503924646781788]
[106119,"Bridge Replacement","2012-05-04",2012,311896.49,311896.49,990577.47,1139164.0904999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D465,'Const Index'!A:F,4,0))*F465","v":549431.55815637065},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D465,'Const Index'!A:F,4,0))*G465","v":1744984.4428088805},0.33486329887959193,0.12587415838384688,0.20898914049574505,431,0.67660910518053374]
[106007,"Bridge Replacement","2012-03-23",2012,197194.55,197194.55,618071.69999999995,710782.45499999996,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D466,'Const Index'!A:F,4,0))*F466","v":347374.5692567568},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D466,'Const Index'!A:F,4,0))*G466","v":1088784.6066602317},0.33904801659742717,0.14535022350522533,0.19369779309220184,432,0.67817896389324961]
[112531,"Reconstruction","2012-02-10",2012,7970.23,7970.23,650075.46,747586.77899999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D467,'Const Index'!A:F,4,0))*F467","v":14040.221766409268},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D467,'Const Index'!A:F,4,0))*G467","v":1145161.8865830116},3.2260468961557168E-2,0.14312931915017685,0.11086885018861968,433,0.67974882260596547]
[112540,"Reconstruction","2012-08-03",2012,7850.05,7850.05,677318.55,778916.33250000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D468,'Const Index'!A:F,4,0))*F468","v":13828.514720077223},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D468,'Const Index'!A:F,4,0))*G468","v":1193152.8511100388},3.1589893706587546E-2,0.14134833593733342,0.10975844223074588,434,0.68131868131868134]
[100481,"Bridge Replacement","2012-09-14",2012,1027085.68,1027085.68,5321465.59,6119685.4284999995,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D469,'Const Index'!A:F,4,0))*F469","v":1809296.6853281856},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D469,'Const Index'!A:F,4,0))*G469","v":9374203.3800675683},0.21300804686778027,7.5377724367558033E-2,0.13763032250022222,435,0.68288854003139721]
[112530,"Reconstruction","2012-02-10",2012,2008.45,2008.45,1334383.81,1534541.3815000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D470,'Const Index'!A:F,4,0))*F470","v":3538.0513996139002},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D470,'Const Index'!A:F,4,0))*G470","v":2350627.8506274135},2.1505151654979987E-2,0.11494019320364676,9.3435041548666775E-2,436,0.68445839874411307]
[10969,"Bridge Replacement","2012-02-10",2012,207773.19,207773.19,858978.74,987825.55099999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D471,'Const Index'!A:F,4,0))*F471","v":366009.72176640929},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D471,'Const Index'!A:F,4,0))*G471","v":1513162.3556949808},0.26188397258819235,0.13146735313359459,0.13041661945459776,437,0.68602825745682894]
[102038,"Bridge Replacement","2012-06-15",2012,283024.07,283024.07,1302285.1499999999,1497627.9224999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D472,'Const Index'!A:F,4,0))*F472","v":498570.39358108112},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D472,'Const Index'!A:F,4,0))*G472","v":2294083.3964768341},0.2373288008390482,0.11579697088774552,0.12153182995130268,438,0.68759811616954469]
[103975,"Bridge Replacement","2012-06-15",2012,118921.06,118921.06,468286.5,538529.47499999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D473,'Const Index'!A:F,4,0))*F473","v":209489.31901544402},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D473,'Const Index'!A:F,4,0))*G473","v":824925.54295366805},0.27394936646689577,0.15818908218758918,0.1157602842793066,439,0.68916797488226056]
[107685,"Bridge Replacement","2012-06-15",2012,643416.14,643416.14,3632142.9,4176964.335,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D474,'Const Index'!A:F,4,0))*F474","v":1133430.9416023167},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D474,'Const Index'!A:F,4,0))*G474","v":6398321.2282818537},0.19714505120379486,8.4690142419197104E-2,0.11245490878459775,440,0.69073783359497642]
[103972,"Bridge Replacement","2012-03-23",2012,208907.27,208907.27,956510.84,1099987.466,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D475,'Const Index'!A:F,4,0))*F475","v":368007.49782818533},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D475,'Const Index'!A:F,4,0))*G475","v":1684973.2461389962},0.23840554363189442,0.1272249056598386,0.11118063797205582,441,0.69230769230769229]
[111240,"Bridge Replacement","2012-10-26",2012,54254.14,54254.14,771952.18,887745.0070000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D476,'Const Index'!A:F,4,0))*F476","v":95573.171332046346},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D476,'Const Index'!A:F,4,0))*G476","v":1359857.8460424712},9.0281736881680938E-2,0.13582117537238406,4.5539438490703119E-2,442,0.69387755102040816]
[100304,"Widen","2012-08-03",2012,2366987.64,2366987.64,31727611.219999999,36486752.902999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D477,'Const Index'!A:F,4,0))*F477","v":4169645.2152509661},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D477,'Const Index'!A:F,4,0))*G477","v":55890820.923262551},9.4603399026395418E-2,4.3726443607543977E-2,5.0876955418851441E-2,443,0.69544740973312402]
[101216,"Reconstruction","2012-02-10",2012,2601182.84,2601182.84,36721438.43,42229654.194499999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D478,'Const Index'!A:F,4,0))*F478","v":4582199.5009652516},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D478,'Const Index'!A:F,4,0))*G478","v":64687862.099179544},9.0835537800581748E-2,4.1819809675417222E-2,4.9015728125164526E-2,444,0.69701726844583989]
[100489,"Reconstruction","2012-06-15",2012,912746.43,912746.43,69361720.700000003,79765978.805000007,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D479,'Const Index'!A:F,4,0))*F479","v":1607878.6049710428},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D479,'Const Index'!A:F,4,0))*G479","v":122186428.83928573},3.3159224148255596E-2,3.4446174633847811E-2,1.2869504855922143E-3,445,0.69858712715855575]
[101646,"Bridge Replacement","2012-06-15",2012,490674.2,490674.2,13498511.15,15523287.8225,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D480,'Const Index'!A:F,4,0))*F480","v":864363.33494208509},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D480,'Const Index'!A:F,4,0))*G480","v":23778747.923503865},5.635024593064103E-2,5.6747321260430625E-2,3.9707532978959514E-4,446,0.70015698587127162]
[105326,"Bridge Replacement","2012-03-23",2012,370296.73,370296.73,3821199.68,4394379.6320000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D481,'Const Index'!A:F,4,0))*F481","v":652308.4288127413},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D481,'Const Index'!A:F,4,0))*G481","v":6731360.4401544416},0.11690588323298508,8.3389551369994458E-2,3.351633186299062E-2,447,0.70172684458398749]
[101402,"Reconstruction","2012-06-15",{"$f":"YEAR(C482)","v":2012},1594122.21,1594122.21,27869927.640000001,32050416.785999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D482,'Const Index'!A:F,4,0))*F482","v":2808178.6035231664},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D482,'Const Index'!A:F,4,0))*G482","v":49095191.064671822},7.7198649045362208E-2,4.5490019636189982E-2,3.1708629409172226E-2,448,0.70329670329670335]
[101890,"Construction-New","2012-12-07",2012,667887.12,667887.12,9379378.8100000005,10786285.6315,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D483,'Const Index'!A:F,4,0))*F483","v":1176538.6042471044},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D483,'Const Index'!A:F,4,0))*G483","v":16522554.370897686},9.1208033445447326E-2,{"$f":"8.4856*G483^-0.305","v":6.3411709674418226E-2},2.7796323771029099E-2,449,0.70486656200941911]
[100328.04,"Construction-New","2012-09-14",2012,1911790.89,1911790.89,41093395.619999997,47257404.963,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D484,'Const Index'!A:F,4,0))*F484","v":3367778.3535231664},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D484,'Const Index'!A:F,4,0))*G484","v":72389427.612451747},6.6523069246425051E-2,4.0409370676033098E-2,2.6113698570391954E-2,450,{"$f":"N484/637","v":0.70643642072213497}]
[100997,"Construction-New","2012-02-10",2012,940309.31,940309.31,15660653.109999999,18009751.076499999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D485,'Const Index'!A:F,4,0))*F485","v":1656432.9061293439},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D485,'Const Index'!A:F,4,0))*G485","v":27587540.468870658},8.0042790258828489E-2,5.4233239340810611E-2,2.5809550918017878E-2,{"$f":"N484+1","v":451},0.70800627943485084]
[102020,"Bridge Replacement","2012-03-23",2012,562563.52,562563.52,7906716.0999999996,9092723.5149999987,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D486,'Const Index'!A:F,4,0))*F486","v":991002.33976833988},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D486,'Const Index'!A:F,4,0))*G486","v":13928336.759169886},9.1150084672952908E-2,6.6802656255737544E-2,2.4347428417215364E-2,452,0.7095761381475667]
[102488.06,"Widen","2012-08-03",2012,1648320.46,1648320.46,47227599.460000001,54311739.379000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D487,'Const Index'!A:F,4,0))*F487","v":2903653.3199806954},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D487,'Const Index'!A:F,4,0))*G487","v":83195336.886583015},5.4901635459919274E-2,3.8730474267186454E-2,1.6171161192732819E-2,453,0.71114599686028257]
[114219,"Modify Interchange","2012-11-02",2012,582334.98,582334.98,9949785.5500000007,11442253.3825,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D488,'Const Index'!A:F,4,0))*F488","v":1025831.4078185329},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D488,'Const Index'!A:F,4,0))*G488","v":17527373.193774134},7.8527390070231212E-2,6.2280110024142105E-2,1.6247280046089108E-2,454,0.71271585557299844]
[100520,"Bridge Replacement","2012-09-14",2012,413854.31,413854.31,5784162.7300000004,6651787.1395000005,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D489,'Const Index'!A:F,4,0))*F489","v":729038.72176640935},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D489,'Const Index'!A:F,4,0))*G489","v":10189282.801399617},9.1549562022782152E-2,7.3485085277022411E-2,1.8064476745759742E-2,455,0.7142857142857143]
[101642,"Bridge Replacement","2013-02-15",2013,362530.71,362530.71,1243902.3,1430487.645,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D490,'Const Index'!A:F,4,0))*F490","v":616606.28681267484},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D490,'Const Index'!A:F,4,0))*G490","v":2115677.2576887235},0.31144628963223236,0.11742829176846631,0.19401799786376606,456,0.71585557299843017]
[101610,"Widen","2013-04-05",2013,792514.69,792514.69,3955923.74,4549312.301,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D491,'Const Index'!A:F,4,0))*F491","v":1347939.7103914258},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D491,'Const Index'!A:F,4,0))*G491","v":6728388.4673811747},0.22033618999945631,8.2512917461208451E-2,0.13782327253824786,457,0.71742543171114603]
[113823,"Reconstruction","2013-07-12",2013,1195219.67,1195219.67,6368984.6500000004,7324332.3475000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D492,'Const Index'!A:F,4,0))*F492","v":2032875.9531686858},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D492,'Const Index'!A:F,4,0))*G492","v":10832616.017008388},0.20766251383570217,7.1357749416131114E-2,0.13630476441957107,458,0.7189952904238619]
[108892,"Bridge Replacement","2013-04-05",2013,375903.63,375903.63,1851013.4,2128665.4099999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D493,'Const Index'!A:F,4,0))*F493","v":639351.46761416586},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D493,'Const Index'!A:F,4,0))*G493","v":3148275.3541472508},0.22307990747122627,0.10402138674502702,0.11905852072619925,459,0.72056514913657765]
[112534,"Reconstruction","2013-08-30",2013,11393.3,11393.3,2162652.65,2487050.5474999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D494,'Const Index'!A:F,4,0))*F494","v":19378.166356011181},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D494,'Const Index'!A:F,4,0))*G494","v":3678323.472739981},2.5268206154141305E-2,9.919998134130574E-2,7.3931775187164428E-2,460,0.72213500784929352]
[108888,"Bridge Replacement","2013-07-12",2013,40746.089999999997,40746.089999999997,1271254.01,1461942.1115000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D495,'Const Index'!A:F,4,0))*F495","v":69302.529589934755},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D495,'Const Index'!A:F,4,0))*G495","v":2162198.106477167},5.2051887096898911E-2,0.11665186683552886,6.4599979738629951E-2,461,0.72370486656200939]
[112526,"Reconstruction","2013-07-12",2013,32321.95,32321.95,3611905.58,4153691.4169999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D496,'Const Index'!A:F,4,0))*F496","v":54974.42567567568},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D496,'Const Index'!A:F,4,0))*G496","v":6143269.0433364399},2.894872506606333E-2,8.4834588438686784E-2,5.5885863372623454E-2,462,0.72527472527472525]
[112525,"Modify Interchange","2013-07-12",2013,52419.17,52419.17,2280964.54,2623109.2209999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D497,'Const Index'!A:F,4,0))*F497","v":89156.556616961781},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D497,'Const Index'!A:F,4,0))*G497","v":3879552.9221808016},4.2981142004075171E-2,9.7601479958652301E-2,5.4620337954577131E-2,463,0.72684458398744112]
[101211,"Widen","2013-02-15",2013,1750864.66,1750864.66,13798189.67,15867918.1205,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D498,'Const Index'!A:F,4,0))*F498","v":2977938.494408201},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D498,'Const Index'!A:F,4,0))*G498","v":23468495.94384902},0.14689089669543584,5.6368543353205937E-2,9.0522353342229911E-2,464,0.72841444270015698]
[112455,"Modify Interchange","2013-10-18",2013,306923.31,306923.31,13258952.720000001,15247795.628,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D499,'Const Index'!A:F,4,0))*F499","v":522027.06500465982},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D499,'Const Index'!A:F,4,0))*G499","v":22551340.833178006},4.3148382566975466E-2,5.7058091765578044E-2,1.3909709198602578E-2,465,0.72998430141287285]
[108890,"Bridge Replacement","2013-02-15",2013,246830.07999999999,246830.07999999999,1860758.48,2139872.2519999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D500,'Const Index'!A:F,4,0))*F500","v":419818.16961789376},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D500,'Const Index'!A:F,4,0))*G500","v":3164850.1640260951},0.15265025131042262,0.10385492674812809,4.8795324562294531E-2,466,0.73155416012558871]
[100942.01,"Construction-New","2013-05-24",2013,583009.38,583009.38,16972818.440000001,19518741.206,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D501,'Const Index'!A:F,4,0))*F501","v":991604.95666356012},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D501,'Const Index'!A:F,4,0))*G501","v":28868027.635601122},5.4349591498959085E-2,5.2918508644386082E-2,1.4310828545730028E-3,467,0.73312401883830458]
[112517,"Modify Interchange","2013-05-24",2013,976207.96,976207.96,12863363.359999999,14792867.864,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D502,'Const Index'!A:F,4,0))*F502","v":1660372.3457595527},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D502,'Const Index'!A:F,4,0))*G502","v":21878507.112767939},9.5890568638962878E-2,5.7587658670807111E-2,3.8302909968155767E-2,468,0.73469387755102045]
[102240,"Modify Interchange","2013-09-20",2013,4570449.88,4570449.88,109341119.20999999,125742287.09149998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D503,'Const Index'!A:F,4,0))*F503","v":7773598.3513513515},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D503,'Const Index'!A:F,4,0))*G503","v":185971614.6861603},6.1799918576121549E-2,2.9981515642740243E-2,3.1818402933381305E-2,469,0.73626373626373631]
[101629,"Bridge Replacement","2013-04-05",2013,1234392.68,1234392.68,38903917.399999999,44739505.009999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D504,'Const Index'!A:F,4,0))*F504","v":2099502.9273066167},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D504,'Const Index'!A:F,4,0))*G504","v":66169291.011183597},5.1729264364518718E-2,4.1089853119535412E-2,1.0639411244983306E-2,470,0.73783359497645207]
[112368,"Bridge Replacement","2013-02-15",2013,242589.23,242589.23,2298046.37,2642753.3255000003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D505,'Const Index'!A:F,4,0))*F505","v":412605.16752096929},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D505,'Const Index'!A:F,4,0))*G505","v":3908606.3609040077},0.12556324413941222,9.7379631239943434E-2,2.8183612899468788E-2,471,0.73940345368916793]
[108893,"Bridge Replacement","2013-02-15",2013,120498.66,120498.66,968968.13,1114313.3495,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D506,'Const Index'!A:F,4,0))*F506","v":204948.79263746506},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D506,'Const Index'!A:F,4,0))*G506","v":1648058.5622087605},0.14435771236356348,0.12672379213941171,1.7633920224151778E-2,472,0.7409733124018838]
[101230,"Reconstruction","2013-10-18",2013,1357951.85,1357951.85,29986969.690000001,34485015.1435,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D507,'Const Index'!A:F,4,0))*F507","v":2309657.1540074558},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D507,'Const Index'!A:F,4,0))*G507","v":51003000.637698047},6.5284730802687513E-2,4.4485463380635443E-2,2.079926742205207E-2,473,0.74254317111459966]
[103874,"Bridge Replacement","2014-08-29",2014,226319.6,226319.6,896274.19,1030715.3184999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D508,'Const Index'!A:F,4,0))*F508","v":372437.57439134351},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D508,'Const Index'!A:F,4,0))*G508","v":1474932.7292605948},0.27251156680078004,0.12977411752566462,0.14273744927511542,474,0.74411302982731553]
[112528,"Construction-New","2014-10-17",2014,1281195.68,1281195.68,8198556.0999999996,9428339.5149999987,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D509,'Const Index'!A:F,4,0))*F509","v":2108369.8070333633},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D509,'Const Index'!A:F,4,0))*G509","v":13491762.743462577},0.17627089262705661,6.606822774117968E-2,0.11020266488587693,475,0.7456828885400314]
[112532,"Reconstruction","2014-04-04",2014,7965.65,7965.65,2866184.68,3296112.3820000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D510,'Const Index'!A:F,4,0))*F510","v":13108.486248872858},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D510,'Const Index'!A:F,4,0))*G510","v":4716670.0099188453},2.2779182393787688E-2,9.103424273368739E-2,6.8255060339899698E-2,476,0.74725274725274726]
[115641,"Bridge Replacement","2014-10-17",2014,39892.79,39892.79,2338996.33,2689845.7795000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D511,'Const Index'!A:F,4,0))*F511","v":65648.639990982861},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D511,'Const Index'!A:F,4,0))*G511","v":3849114.7901262399},3.7055516286338075E-2,9.6856449746812998E-2,5.9800933460474923E-2,477,0.74882260596546313]
[113069,"Bridge Replacement","2014-05-23",2014,36975.11,36975.11,3543974.64,4075570.8360000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D512,'Const Index'!A:F,4,0))*F512","v":60847.227908025241},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D512,'Const Index'!A:F,4,0))*G512","v":5832059.2587917037},3.0433232106875346E-2,8.532728381786471E-2,5.4894051710989364E-2,478,0.75039246467817899]
[100314,"Widen","2014-10-17",2014,4590162.5,4590162.5,44245385.950000003,50882193.842500001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D513,'Const Index'!A:F,4,0))*F513","v":7553693.9247069424},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D513,'Const Index'!A:F,4,0))*G513","v":72811388.060189366},0.12374330343026421,3.9508707254348796E-2,8.4234596175915416E-2,479,0.75196232339089486]
[103773.02,"Reconstruction","2014-05-23",2014,1642671.03,1642671.03,15419073.300000001,17731934.295000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D514,'Const Index'!A:F,4,0))*F514","v":2703223.2910279529},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D514,'Const Index'!A:F,4,0))*G514","v":25374038.568530206},0.12653500363086023,5.449100057396393E-2,7.2044003056896302E-2,480,0.75353218210361073]
[109842,"Modify Interchange","2014-02-14",2014,111914.74,111914.74,15647551.6,17994684.34,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D515,'Const Index'!A:F,4,0))*F515","v":184169.88322813346},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D515,'Const Index'!A:F,4,0))*G515","v":25750028.557258788},2.7152220542925071E-2,5.424708501236962E-2,2.7094864469444549E-2,481,0.75510204081632648]
[115777,"Modify Interchange","2014-12-05",2014,116158.32,116158.32,2018980.32,2321827.3680000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D516,'Const Index'!A:F,4,0))*F516","v":191153.23174030657},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D516,'Const Index'!A:F,4,0))*G516","v":3322487.9026149684},7.7533161095894185E-2,0.10130182506084867,2.3768663964954487E-2,482,0.75667189952904235]
[101431,"Widen","2014-12-05",2014,2096607.65,2096607.65,22908363.52,26344618.048,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D517,'Const Index'!A:F,4,0))*F517","v":3450233.5087917037},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D517,'Const Index'!A:F,4,0))*G517","v":37698614.449053198},0.11152149380594428,4.8293020097040659E-2,6.3228473708903624E-2,483,0.75824175824175821]
[105351,"Bridge Replacement","2014-12-05",2014,672872.12,672872.12,6713924.2300000004,7721012.8645000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D518,'Const Index'!A:F,4,0))*F518","v":1107296.3201082055},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D518,'Const Index'!A:F,4,0))*G518","v":11048612.912308386},0.1202203922697531,7.0219016594757835E-2,5.0001375674995269E-2,484,0.75981161695447408]
[117402,"Reconstruction","2014-10-17",2014,1113744.95,1113744.95,13796636.199999999,15866131.629999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D519,'Const Index'!A:F,4,0))*F519","v":1832808.4163660954},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D519,'Const Index'!A:F,4,0))*G519","v":22704112.772768255},0.1007258330113829,5.6370479103426407E-2,4.4355353907956488E-2,485,0.76138147566718994]
[107847,"Reconstruction","2014-07-11",2014,265923.94,265923.94,2274415.25,2615577.5375000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D520,'Const Index'!A:F,4,0))*F520","v":437611.53336339042},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D520,'Const Index'!A:F,4,0))*G520","v":3742838.4411632097},0.13691969617245575,9.7687114035427972E-2,3.923258213702778E-2,486,0.76295133437990581]
[119831,"Widen","2014-10-17",2014,514239.32,514239.32,12862245.41,14791582.2215,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D521,'Const Index'!A:F,4,0))*F521","v":846245.95040577091},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D521,'Const Index'!A:F,4,0))*G521","v":21166454.349188458},5.998052467574555E-2,5.7589185258416331E-2,2.3913394173292191E-3,487,0.76452119309262168,null,null,null,{"$f":"506-(506*0.66)","v":172.03999999999996}]
[103779,"Widen","2014-07-11",2014,668298.23,668298.23,9681753.4199999999,11134016.433,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D522,'Const Index'!A:F,4,0))*F522","v":1099769.4046438232},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D522,'Const Index'!A:F,4,0))*G522","v":15932551.84084761},8.9026569982609619E-2,6.280100307642858E-2,2.6225566906181039E-2,488,0.76609105180533754,null,null,null,{"$f":"S521/2","v":86.019999999999982}]
[101604,"Modify Interchange","2014-05-23",2014,1329023.1499999999,1329023.1499999999,28282839.75,32525265.712499999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D523,'Const Index'!A:F,4,0))*F523","v":2187075.9682146073},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D523,'Const Index'!A:F,4,0))*G523","v":46542995.981740303},6.6990442322892974E-2,4.5286424891635903E-2,{"$f":"ABS(L523-K523)","v":2.1704017431257071E-2},489,0.76766091051805341]
[100623,"Bridge Replacement","2015-07-10",2015,175476.07,175476.07,575505.28,661831.07200000004,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D524,'Const Index'!A:F,4,0))*F524","v":281162.27194907813},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D524,'Const Index'!A:F,4,0))*G524","v":922122.15627743641},0.32490783681428603,0.14854824167666636,0.17635959513761967,490,0.76923076923076927]
[115690,"Bridge Replacement","2015-08-28",2015,16716.009999999998,16716.009999999998,1005181.6,1155958.8399999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D525,'Const Index'!A:F,4,0))*F525","v":26783.773705004387},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D525,'Const Index'!A:F,4,0))*G525","v":1610585.0921861283},3.662984081682355E-2,0.12531353294157374,8.8683692124750191E-2,491,0.77080062794348514]
[115688,"Bridge Replacement","2015-02-13",2015,28776.91,28776.91,796754.5,916267.67500000005,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D526,'Const Index'!A:F,4,0))*F526","v":46108.745171202812},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D526,'Const Index'!A:F,4,0))*G526","v":1276625.954784899},5.6117662341411315E-2,0.13451743443960443,7.8399772098193113E-2,492,0.77237048665620089]
[115358,"Modify Interchange","2015-08-28",2015,14479.73,14479.73,2638639.4,3034435.31,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D527,'Const Index'!A:F,4,0))*F527","v":23200.620939420543},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D527,'Const Index'!A:F,4,0))*G527","v":4227846.2730465317},2.548757439155953E-2,9.3360171908702203E-2,6.7872597517142669E-2,493,0.77394034536891676]
[115689,"Bridge Replacement","2015-05-15",2015,33657.69,33657.69,400663.13,{"$f":"G528+(G528*0.15)","v":460762.59950000001},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D528,'Const Index'!A:F,4,0))*F528","v":53929.134547848997},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D528,'Const Index'!A:F,4,0))*G528","v":641975.60338015808},{"$f":"I528/J528+0.02","v":0.1040049594780533},0.16589559144495691,6.1890631966903614E-2,494,0.77551020408163263]
[115642,"Bridge Replacement","2015-05-15",2015,8146.81,8146.81,5269406.1500000004,6059817.0725000007,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D529,'Const Index'!A:F,4,0))*F529","v":13053.492756804215},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D529,'Const Index'!A:F,4,0))*G529","v":8443078.3351624236},2.1546058468087527E-2,7.5604082140703702E-2,5.4058023672616175E-2,495,0.77708006279434849]
[115778.01,"Widen","2015-07-10",2015,60403.56,60403.56,6957018.79,8000571.6085000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D530,'Const Index'!A:F,4,0))*F530","v":96783.579455662853},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D530,'Const Index'!A:F,4,0))*G530","v":11147110.879499562},2.8682391383910578E-2,6.9461392764255087E-2,4.0779001380344508E-2,496,0.77864992150706436]
[115673,"Bridge Replacement","2015-12-04",2015,71303.679999999993,71303.679999999993,6555000,7538250,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D531,'Const Index'!A:F,4,0))*F531","v":114248.6532045654},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D531,'Const Index'!A:F,4,0))*G531","v":10502963.125548728},3.0877754385964913E-2,7.0733945515271304E-2,3.9856191129306391E-2,497,0.78021978021978022]
[112529,"Modify Interchange","2015-12-04",2015,93312.73,93312.73,1997681,2297333.15,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D532,'Const Index'!A:F,4,0))*F532","v":149513.37335381913},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D532,'Const Index'!A:F,4,0))*G532","v":3200849.7146619842},6.6710525854728558E-2,0.10163003694022107,3.4919511085492516E-2,498,0.78178963893249609]
[115686,"Bridge Replacement","2015-12-04",2015,93390.45,93390.45,1486196.34,1709125.7910000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D533,'Const Index'!A:F,4,0))*F533","v":149637.90276558383},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D533,'Const Index'!A:F,4,0))*G533","v":2381306.6905179983},8.2838568153114953E-2,0.11122420716601292,2.8385639012897965E-2,499,0.78335949764521196]
[103917,"Widen","2015-10-16",2015,8233711.5499999998,8233711.5499999998,104957486.83,120701109.8545,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D534,'Const Index'!A:F,4,0))*F534","v":13192733.607330993},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D534,'Const Index'!A:F,4,0))*G534","v":168171565.81628621},9.8448063103265537E-2,3.0358021331139958E-2,6.8090041772125576E-2,500,0.78492935635792782]
[105549,"Bridge Replacement","2015-02-13",2015,439055.25,439055.25,3519192.86,4047071.7889999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D535,'Const Index'!A:F,4,0))*F535","v":703490.63323090435},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D535,'Const Index'!A:F,4,0))*G535","v":5638741.8520632135},0.144760212772198,8.5510101148073656E-2,5.9250111624124344E-2,501,0.78649921507064369]
[105769,"Construction-New","2015-07-10",2015,873219.27,873219.27,8337568.04,9588203.2459999993,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D536,'Const Index'!A:F,4,0))*F536","v":1399144.1332309044},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D536,'Const Index'!A:F,4,0))*G536","v":13359141.064969271},0.12473309072989587,6.5730288969342576E-2,5.9002801760553295E-2,502,0.78806907378335955]
[103774,"Construction-New","2015-08-28",2015,1098658.1599999999,1098658.1599999999,12240282.67,14076325.070499999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D537,'Const Index'!A:F,4,0))*F537","v":1760360.9675153643},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D537,'Const Index'!A:F,4,0))*G537","v":19612393.215759438},0.10975758073730825,5.8466374547863756E-2,5.1291206189444494E-2,503,0.78963893249607531]
[100494,"Bridge Replacement","2015-10-16",2015,2194586.42,2194586.42,29106151.809999999,33472074.581499998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D538,'Const Index'!A:F,4,0))*F538","v":3516347.8634767337},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D538,'Const Index'!A:F,4,0))*G538","v":46636283.628841087},9.5399401278667348E-2,4.489181813456071E-2,5.0507583144106638E-2,504,0.79120879120879117]
[107349,"Reconstruction","2015-02-13",2015,1157837.2,1157837.2,14792379.359999999,17011236.263999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D539,'Const Index'!A:F,4,0))*F539","v":1855182.5197541702},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D539,'Const Index'!A:F,4,0))*G539","v":23701573.601404741},9.8272546412033063E-2,5.5184988304736636E-2,4.3087558107296427E-2,505,0.79277864992150704]
[112584,"Widen","2015-10-16",2015,594141.86,594141.86,21365926.98,24570816.026999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D540,'Const Index'!A:F,4,0))*F540","v":951983.22607550479},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D540,'Const Index'!A:F,4,0))*G540","v":34234255.257682182},4.7807914000462429E-2,4.9330716706236871E-2,1.5228027057744425E-3,506,0.79434850863422291]
[107338,"Construction-New","2015-02-13",2015,2645605.6800000002,2645605.6800000002,45956687.649999999,52850190.797499999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D541,'Const Index'!A:F,4,0))*F541","v":4239008.223002634},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D541,'Const Index'!A:F,4,0))*G541","v":73635605.760535553},7.7567370828563187E-2,3.9054060661136127E-2,3.851331016742706E-2,507,0.79591836734693877]
[117847,"Bridge Replacement","2015-03-13",2015,1340451.46,1340451.46,61859996,71138995.400000006,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D542,'Const Index'!A:F,4,0))*F542","v":2147782.1900790166},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D542,'Const Index'!A:F,4,0))*G542","v":99117201.668129936},4.1669116499781216E-2,3.5669953249143301E-2,5.999163250637915E-3,508,0.79748822605965464]
[107351.01,"Widen","2015-08-28",2015,908901.22,908901.22,22435346.600000001,25800648.590000004,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D543,'Const Index'!A:F,4,0))*F543","v":1456316.7045654082},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D543,'Const Index'!A:F,4,0))*G543","v":35947767.818261638},6.0512020438320296E-2,4.8601319126327452E-2,1.1910701311992844E-2,509,0.7990580847723705]
[101591,"Widen","2015-12-04",2015,807641.72,807641.72,15592254.289999999,17931092.433499999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D544,'Const Index'!A:F,4,0))*F544","v":1294070.3590869184},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D544,'Const Index'!A:F,4,0))*G544","v":24983199.367208075},7.1797623677672853E-2,5.4305690307918125E-2,1.7491933369754728E-2,510,0.80062794348508637]
[102239,"Reconstruction","2015-08-28",2015,997323.09,997323.09,19217578.449999999,22100215.217499997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D545,'Const Index'!A:F,4,0))*F545","v":1597993.5375329235},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D545,'Const Index'!A:F,4,0))*G545","v":30791993.565627743},7.1896397488102878E-2,5.0951205490563423E-2,2.0945191997539456E-2,511,0.80219780219780223]
[101878.01,"Bridge Replacement","2016-02-12",{"$f":"YEAR(C546)","v":2016},3681.12,3681.12,522626.9,601020.93500000006,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D546,'Const Index'!A:F,4,0))*F546","v":5717.4842553191484},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D546,'Const Index'!A:F,4,0))*G546","v":811739.6531914894},2.7043495082247009E-2,0.15297979309973253,0.12593629801748552,512,0.8037676609105181]
[116915,"Bridge Replacement","2016-08-19",2016,24605.21,24605.21,445177.9,511954.58500000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D547,'Const Index'!A:F,4,0))*F547","v":38216.602765957447},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D547,'Const Index'!A:F,4,0))*G547","v":691446.5255319149},7.5270510957529568E-2,{"$f":"8.4856*G547^-0.305","v":0.1606496593234911},8.5379148365961527E-2,513,0.80533751962323386]
[115674,"Bridge Replacement","2016-10-07",2016,28472.1,28472.1,899999.99,1034999.9885,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D548,'Const Index'!A:F,4,0))*F548","v":44222.623404255311},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D548,'Const Index'!A:F,4,0))*G548","v":1397872.3248936168},5.1635667018174083E-2,0.12961002426836007,7.7974357250185991E-2,514,{"$f":"N548/637","v":0.80690737833594972}]
[115675,"Bridge Replacement","2016-12-02",2016,247647.1,247647.1,1136379.6299999999,1306836.5744999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D549,'Const Index'!A:F,4,0))*F549","v":384643.36808510637},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D549,'Const Index'!A:F,4,0))*G549","v":1765015.1699999997},0.23792638081694584,0.12071129429900873,0.11721508651793711,{"$f":"N548+1","v":515},0.80847723704866559]
[115687,"Bridge Replacement","2016-10-07",2016,23496.11,23496.11,2917277.65,3354869.2974999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D550,'Const Index'!A:F,4,0))*F550","v":36493.95808510638},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D550,'Const Index'!A:F,4,0))*G550","v":4531090.8180851061},2.8054121965387833E-2,9.0544971753674125E-2,6.2490849788286291E-2,516,0.81004709576138145]
[115681,"Bridge Replacement","2016-06-24",2016,45259.19,45259.19,989797.1,1138266.665,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D551,'Const Index'!A:F,4,0))*F551","v":70296.188723404252},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D551,'Const Index'!A:F,4,0))*G551","v":1537344.4319148934},6.5725724999598403E-2,0.12590441858835319,6.0178693588754786E-2,517,0.81161695447409732]
[112457,"Widen","2016-10-07",2016,25905.919999999998,25905.919999999998,3422244.16,3935580.784,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D552,'Const Index'!A:F,4,0))*F552","v":40236.854468085105},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D552,'Const Index'!A:F,4,0))*G552","v":5315400.5038297875},2.756986316253952E-2,8.6241778402068189E-2,5.8671915239528666E-2,518,0.81318681318681318]
[108884,"Bridge Replacement","2016-06-24",2016,44297.94,44297.94,697868.54,802548.821,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D553,'Const Index'!A:F,4,0))*F553","v":68803.183404255324},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D553,'Const Index'!A:F,4,0))*G553","v":1083923.4770212765},8.3476052380868193E-2,0.14006563725743681,5.6589584876568622E-2,519,0.81475667189952905]
[112521,"Modify Interchange","2016-06-24",2016,51496.59,51496.59,2073192.15,2384170.9724999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D554,'Const Index'!A:F,4,0))*F554","v":79984.065319148925},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D554,'Const Index'!A:F,4,0))*G554","v":3220064.4031914892},4.4839275028125104E-2,0.1004864471458049,5.5647172117679798E-2,520,0.81632653061224492]
[115680,"Bridge Replacement","2016-10-07",2016,20684.48,20684.48,4494046.8099999996,5168153.8314999994,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D555,'Const Index'!A:F,4,0))*F555","v":32126.958297872337},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D555,'Const Index'!A:F,4,0))*G555","v":6980115.2580851056},2.4602640086875287E-2,7.9364830007739209E-2,5.4762189920863923E-2,521,0.81789638932496078]
[114156,"Widen","2016-08-19",2016,17638.259999999998,17638.259999999998,6320635.7199999997,7268731.0779999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D556,'Const Index'!A:F,4,0))*F556","v":27395.595319148932},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D556,'Const Index'!A:F,4,0))*G556","v":9817157.6076595727},2.2790583223169836E-2,7.1523790708806004E-2,4.8733207485636171E-2,522,0.81946624803767665]
[115676,"Bridge Replacement","2016-04-01",2016,52214.05,52214.05,750768.87,863384.20050000004,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D557,'Const Index'!A:F,4,0))*F557","v":81098.418085106387},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D557,'Const Index'!A:F,4,0))*G557","v":1166087.8193617021},8.9547436083757717E-2,0.13697873385876513,4.7431297775007417E-2,523,0.82103610675039251]
[83843.009999999995,"Bridge Replacement","2016-06-24",2016,69205.2,69205.2,2942314.51,3383661.6864999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D558,'Const Index'!A:F,4,0))*F558","v":107488.92765957446},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D558,'Const Index'!A:F,4,0))*G558","v":4569977.8559574466},4.3520667068320987E-2,9.0309280518451857E-2,4.678861345013087E-2,524,0.82260596546310827]
[115691,"Bridge Replacement","2016-10-07",2016,72488.429999999993,72488.429999999993,3045866.94,3502746.9809999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D559,'Const Index'!A:F,4,0))*F559","v":112588.41255319148},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D559,'Const Index'!A:F,4,0))*G559","v":4730814.6089361701},4.3798948354585705E-2,8.9361556164457123E-2,4.5562607809871418E-2,525,0.82417582417582413]
[114171,"Widen","2016-10-07",2016,42263.31,42263.31,6691081.6200000001,7694743.8629999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D560,'Const Index'!A:F,4,0))*F560","v":65643.013404255311},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D560,'Const Index'!A:F,4,0))*G560","v":10392531.02680851},2.6316364438549473E-2,7.0292044602255951E-2,4.3975680163706482E-2,526,0.82574568288854]
[114173,"Widen","2016-10-07",2016,44346.22,44346.22,8369782.3499999996,9625249.7024999987,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D561,'Const Index'!A:F,4,0))*F561","v":68878.171489361703},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D561,'Const Index'!A:F,4,0))*G561","v":12999874.713829786},2.5298371946314711E-2,6.5653024150685746E-2,4.0354652204371039E-2,527,0.82731554160125587]
[115677,"Bridge Replacement","2016-10-07",2016,85552.49,85552.49,2263715.73,2603273.0894999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D562,'Const Index'!A:F,4,0))*F562","v":132879.39936170212},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D562,'Const Index'!A:F,4,0))*G562","v":3515984.0061702128},5.7792947615379245E-2,9.7827708274398753E-2,4.0034760659019508E-2,528,0.82888540031397173]
[116956,"Bridge Replacement","2016-12-02",2016,61978.17,61978.17,845782.06,972649.36900000006,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D563,'Const Index'!A:F,4,0))*F563","v":96263.966170212763},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D563,'Const Index'!A:F,4,0))*G563","v":1313661.4974468085},9.327912583059518E-2,0.13208962973345389,3.8810503902858715E-2,529,0.8304552590266876]
[117283,"Bridge Replacement","2016-12-02",2016,46796.32,46796.32,455475.85,523797.22749999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D564,'Const Index'!A:F,4,0))*F564","v":72683.645957446803},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D564,'Const Index'!A:F,4,0))*G564","v":707441.21382978722},0.12274160529037928,0.15953303322306317,3.679142793268389E-2,530,0.83202511773940346]
[114152,"Widen","2016-10-07",2016,90063.46,90063.46,8268516.6600000001,9508794.159,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D565,'Const Index'!A:F,4,0))*F565","v":139885.79957446808},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D565,'Const Index'!A:F,4,0))*G565","v":12842589.705957446},3.0892335796539352E-2,6.5897226469989842E-2,3.5004890673450487E-2,531,0.83359497645211933]
[115685,"Bridge Replacement","2016-04-01",2016,104076.1,104076.1,6488539.5899999999,7461820.5285,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D566,'Const Index'!A:F,4,0))*F566","v":161650.11276595746},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D566,'Const Index'!A:F,4,0))*G566","v":10077944.469574466},3.6039988437521431E-2,7.0954138831465202E-2,3.4914150393943771E-2,532,0.8351648351648352]
[103029,"Modify Interchange","2016-02-12",2016,2130552.62,2130552.62,22217026.43,25549580.394499999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D567,'Const Index'!A:F,4,0))*F567","v":3309156.1970212767},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D567,'Const Index'!A:F,4,0))*G567","v":34507296.369999997},0.11589728970763979,4.8746489660585625E-2,6.7150800047054177E-2,533,0.83673469387755106]
[115692,"Bridge Replacement","2016-02-12",2016,99611.76,99611.76,1590945.9,1829587.7849999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D568,'Const Index'!A:F,4,0))*F568","v":154716.13787234042},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D568,'Const Index'!A:F,4,0))*G568","v":2471043.6319148932},8.2611657630847171E-2,0.10893756291196884,2.6325905281121664E-2,534,0.83830455259026693]
[115672,"Bridge Replacement","2016-06-24",2016,142529.68,142529.68,812441,934307.15,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D569,'Const Index'!A:F,4,0))*F569","v":221375.88595744679},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D569,'Const Index'!A:F,4,0))*G569","v":1261876.4468085105},0.19543388381433235,0.13371990120958624,6.1713982604746115E-2,535,0.83987441130298268]
[115778,"Widen","2016-02-12",2016,372074.68,372074.68,12949952.939999999,14892445.880999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D570,'Const Index'!A:F,4,0))*F570","v":577903.22638297873},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D570,'Const Index'!A:F,4,0))*G570","v":20113756.694042552},4.8731739931712835E-2,5.746994186757632E-2,8.7382019358634849E-3,536,0.84144427001569855]
[101204,"Reconstruction","2016-10-07",2016,2280314.7400000002,2280314.7400000002,38449919.619999997,44217407.562999994,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D571,'Const Index'!A:F,4,0))*F571","v":3541765.4472340429},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D571,'Const Index'!A:F,4,0))*G571","v":59720087.920425527},7.9306099012333917E-2,4.1237226464221212E-2,3.8068872548112705E-2,537,0.84301412872841441]
[100286,"Widen","2016-05-13",2016,637607.52,637607.52,15580919.01,17918056.861499999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D572,'Const Index'!A:F,4,0))*F572","v":990326.5736170212},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D572,'Const Index'!A:F,4,0))*G572","v":24200150.802765954},6.092233067836221E-2,5.4317737188285198E-2,6.6045934900770126E-3,538,0.84458398744113028]
[115683,"Bridge Replacement","2016-02-12",2016,414479.45,414479.45,7633810.5999999996,8778882.1899999995,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D573,'Const Index'!A:F,4,0))*F573","v":643765.95425531908},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D573,'Const Index'!A:F,4,0))*G573","v":11856769.655319147},7.4295223148449607E-2,6.752217680009194E-2,6.7730463483576669E-3,539,0.84615384615384615]
[119830,"Widen","2016-12-02",2016,499535.35999999999,499535.35999999999,9484069.6699999999,10906680.1205,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D574,'Const Index'!A:F,4,0))*F574","v":775874.06978723395},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D574,'Const Index'!A:F,4,0))*G574","v":14730576.295957446},7.2670992240823545E-2,6.3197392738942856E-2,9.473599501880689E-3,540,0.84772370486656201]
[101887,"Reconstruction","2016-12-02",2016,1931858.32,1931858.32,37154959.009999998,42728202.861499995,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D575,'Const Index'!A:F,4,0))*F575","v":3000545.9012765959},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D575,'Const Index'!A:F,4,0))*G575","v":57708766.121914886},7.1994629289728301E-2,4.1670377607669548E-2,3.0324251682058753E-2,541,0.84929356357927788]
[100241.04,"Widen","2016-02-12",2016,3135916.79,3135916.79,70944183.280000001,81585810.772,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D576,'Const Index'!A:F,4,0))*F576","v":4870679.269574468},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D576,'Const Index'!A:F,4,0))*G576","v":110189901.69021276},6.4202592023975727E-2,3.4209988945904476E-2,2.999260307807125E-2,542,0.85086342229199374]
[100409,"Bridge Replacement","2016-04-01",2016,183155.7,183155.7,1619859.8,1862838.77,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D577,'Const Index'!A:F,4,0))*F577","v":284475.87446808512},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D577,'Const Index'!A:F,4,0))*G577","v":2515952.455319149},0.13306885941610502,0.10834077561795394,2.4728083798151085E-2,543,0.85243328100470961]
[117274,"Bridge Replacement","2017-08-18",2017,141723,141723,431001.59999999998,495651.83999999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D578,'Const Index'!A:F,4,0))*F578","v":211483.62632869993},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D578,'Const Index'!A:F,4,0))*G578","v":643154.47260834009},0.34882244520669997,0.16224319745236057,0.1865792477543394,544,0.85400313971742547]
[118495,"Widen","2017-10-06",2017,176506.25,176506.25,584291,671934.65,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D579,'Const Index'!A:F,4,0))*F579","v":263388.31255110382},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D579,'Const Index'!A:F,4,0))*G579","v":871897.85363859357},0.32208620362114082,0.14786338726331313,0.17422281635782769,545,0.85557299843014134]
[117018,"Bridge Replacement","2017-08-18",2017,4607.1400000000003,4607.1400000000003,616910.25,709446.78749999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D580,'Const Index'!A:F,4,0))*F580","v":6874.9227309893713},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D580,'Const Index'!A:F,4,0))*G580","v":920573.34934587078},2.7468087943100315E-2,0.14543363197510042,0.1179655440320001,546,0.8571428571428571]
[117017,"Bridge Replacement","2017-08-18",2017,14002.05,14002.05,723454.5,831972.67500000005,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D581,'Const Index'!A:F,4,0))*F581","v":20894.310098119378},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D581,'Const Index'!A:F,4,0))*G581","v":1079562.111610793},3.9354430720936841E-2,0.13853583702183922,9.9181406300902386E-2,547,0.85871271585557296]
[10716,"Bridge Replacement","2017-06-23",2017,20520.61,20520.61,596161.25,685585.4375,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D582,'Const Index'!A:F,4,0))*F582","v":30621.515331152903},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D582,'Const Index'!A:F,4,0))*G582","v":889611.023098937},5.4421240897492076E-2,0.14695914411111874,9.2537903213626663E-2,548,0.86028257456828883]
[117433.01,"Bridge Replacement","2017-08-18",2017,27148.22,27148.22,1330785.1000000001,1530402.8650000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D583,'Const Index'!A:F,4,0))*F583","v":40511.448487326248},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D583,'Const Index'!A:F,4,0))*G583","v":1985840.3986099756},4.0400153262912242E-2,0.11503490476660241,7.4634751503690172E-2,549,0.86185243328100469]
[114170,"Widen","2017-08-18",2017,111382.33,111382.33,5975335.4199999999,6871635.733,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D584,'Const Index'!A:F,4,0))*F584","v":166208.30110384303},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D584,'Const Index'!A:F,4,0))*G584","v":8916588.0143090766},3.8640347724613597E-2,7.2759893999722394E-2,3.4119546275108797E-2,550,0.86342229199372056]
[115165.01,"Bridge Replacement","2017-02-10",2017,116876.9,116876.9,5381168.0499999998,6188343.2574999994,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D585,'Const Index'!A:F,4,0))*F585","v":174407.47547015536},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D585,'Const Index'!A:F,4,0))*G585","v":8029952.3231807025},4.1719615316603988E-2,7.51216652582231E-2,3.3402049941619112E-2,551,0.86499215070643642]
[101886.01,"Widen","2017-08-18",2017,2499387.0099999998,2499387.0099999998,24933424.989999998,28673438.738499999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D586,'Const Index'!A:F,4,0))*F586","v":3729665.8162305802},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D586,'Const Index'!A:F,4,0))*G586","v":37206460.021872446},0.12024242602058979,4.7061315657800293E-2,7.31811103627895E-2,552,0.86656200941915229]
[123399,"Reconstruction","2017-12-15",2017,1768106.29,1768106.29,17134607.550000001,19704798.682500001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D587,'Const Index'!A:F,4,0))*F587","v":2638425.1670073592},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D587,'Const Index'!A:F,4,0))*G587","v":25568813.392273102},0.12318919093072546,5.2765606755388328E-2,{"$f":"ABS(L587-K587)","v":7.0423584175337131E-2},553,0.86813186813186816]
[115679,"Bridge Replacement","2017-08-18",2017,98905.99,98905.99,1450354.12,1667907.2380000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D588,'Const Index'!A:F,4,0))*F588","v":147590.70461978743},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D588,'Const Index'!A:F,4,0))*G588","v":2164265.1422730992},8.8194373109375529E-2,0.11205544630436097,2.3861073194985441E-2,554,0.86970172684458402]
[112752,"Reconstruction","2017-08-18",2017,190152.78,190152.78,7298798.4500000002,8393618.2175000012,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D589,'Const Index'!A:F,4,0))*F589","v":283752.10425183974},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D589,'Const Index'!A:F,4,0))*G589","v":10891502.18417825},4.6052614180625853E-2,6.8452748046749667E-2,2.2400133866123814E-2,555,0.87127158555729989]
[115682,"Bridge Replacement","2017-03-31",2017,81788.17,81788.17,911415.07,1048127.3304999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D590,'Const Index'!A:F,4,0))*F590","v":122046.94215044971},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D590,'Const Index'!A:F,4,0))*G590","v":1360042.9294766965},0.10973756600272147,0.12911274461577135,1.9375178613049882E-2,556,0.87284144427001575]
[105765,"Reconstruction","2017-12-08",2017,2277284.21,2277284.21,28296971.510000002,32541517.236500002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D591,'Const Index'!A:F,4,0))*F591","v":3398236.8628372853},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D591,'Const Index'!A:F,4,0))*G591","v":42225652.498569094},0.10047801897087184,4.5279525678588915E-2,5.5198493292282928E-2,557,0.87441130298273151]
[103899,"Widen","2017-10-06",2017,717760.93,717760.93,6941516.9500000002,{"$f":"G592+(G592*0.15)","v":7982744.4924999997},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D592,'Const Index'!A:F,4,0))*F592","v":1071065.9830335241},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D592,'Const Index'!A:F,4,0))*G592","v":10358355.219746524},{"$f":"I592/J592+0.02","v":0.1234011636318197},6.9508668190427503E-2,5.3892495441392199E-2,558,0.87598116169544737]
[100281.03,"Reconstruction","2017-12-08",2017,2283272.2400000002,2283272.2400000002,30962980.670000002,35607427.770500004,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D593,'Const Index'!A:F,4,0))*F593","v":3407172.3941128375},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D593,'Const Index'!A:F,4,0))*G593","v":46203957.254905969},9.3742003857279169E-2,4.4053002477537746E-2,4.9689001379741422E-2,559,0.87755102040816324]
[118737,"Bridge Replacement","2017-11-15",2017,3594944.57,3594944.57,54098033.759999998,62212738.824000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D594,'Const Index'!A:F,4,0))*F594","v":5364492.1015944397},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D594,'Const Index'!A:F,4,0))*G594","v":80726828.791496322},8.6452407234402964E-2,3.7158844812767482E-2,4.9293562421635483E-2,560,0.87912087912087911]
[105717,"Reconstruction","2017-06-23",2017,468022.91,468022.91,26718576.68,30726363.182,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D595,'Const Index'!A:F,4,0))*F595","v":698398.86406377761},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D595,'Const Index'!A:F,4,0))*G595","v":39870320.883892067},3.7516760552231632E-2,4.6079153630719509E-2,8.5623930784878774E-3,561,0.88069073783359497]
[115678,"Bridge Replacement","2017-10-06",2017,115519.93,115519.93,1270414.26,1460976.399,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D596,'Const Index'!A:F,4,0))*F596","v":172382.56112019622},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D596,'Const Index'!A:F,4,0))*G596","v":1895753.0862632871},0.11093091414134472,0.11667537920805665,5.7444650667119318E-3,562,0.88226059654631084]
[104959.01,"Reconstruction","2017-10-06",2017,445260.57,445260.57,12889769.710000001,14823235.1665,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D597,'Const Index'!A:F,4,0))*F597","v":664432.16700735898},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D597,'Const Index'!A:F,4,0))*G597","v":19234529.616312347},5.4543718004097685E-2,5.7551650430365996E-2,3.0079324262683102E-3,563,0.8838304552590267]
[101463.05,"Widen","2017-12-08",2017,3020617.06,3020617.06,65171415.990000002,74947128.388500005,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D598,'Const Index'!A:F,4,0))*F598","v":4507462.0887162713},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D598,'Const Index'!A:F,4,0))*G598","v":97250886.493663132},6.6348802064750106E-2,3.510711346820676E-2,3.1241688596543346E-2,564,0.88540031397174257]
[100290,"Widen","2017-05-12",2017,1185562.29,1185562.29,21525605.5,24754446.324999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D599,'Const Index'!A:F,4,0))*F599","v":1769134.2430498775},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D599,'Const Index'!A:F,4,0))*G599","v":32121201.993049879},7.5076838140511304E-2,4.9218816428244806E-2,2.5858021712266498E-2,565,0.88697017268445844]
[100281.02,"Reconstruction","2017-12-08",2017,1085816.58,1085816.58,19961636.140000001,22955881.561000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D600,'Const Index'!A:F,4,0))*F600","v":1620290.4811937858},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D600,'Const Index'!A:F,4,0))*G600","v":29787396.529435813},7.4395169433240663E-2,5.0364292169494826E-2,2.4030877263745837E-2,566,0.8885400313971743]
[103203.02,"Widen","2017-12-08",2017,615956.64,615956.64,9465251.2899999991,10885038.983499998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D601,'Const Index'!A:F,4,0))*F601","v":919150.34178250202},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D601,'Const Index'!A:F,4,0))*G601","v":14124352.906173343},8.50755718076662E-2,6.3235688373715751E-2,2.1839883433950449E-2,567,0.89010989010989006]
[103169,"Widen","2017-08-18",2017,1337374.93,1337374.93,28540005.129999999,32821005.899499997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D602,'Const Index'!A:F,4,0))*F602","v":1995673.9552330335},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D602,'Const Index'!A:F,4,0))*G602","v":42588315.095870808},6.6859659762086382E-2,4.516157418006865E-2,2.1698085582017732E-2,568,0.89167974882260592]
[117328,"Bridge Replacement","2018-03-23",2018,4454.88,4454.88,257107.5,295673.625,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D603,'Const Index'!A:F,4,0))*F603","v":6215.7155963302748},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D603,'Const Index'!A:F,4,0))*G603","v":358731.79472477059},3.7326915784253671E-2,0.18993174505412666,0.15260482926987298,569,0.89324960753532179]
[117487,"Bridge Replacement","2018-12-07",2018,10121.92,10121.92,471831.63,542606.37450000003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D604,'Const Index'!A:F,4,0))*F604","v":14122.709480122323},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D604,'Const Index'!A:F,4,0))*G604","v":658327.77121559624},4.1452398178562125E-2,0.15782562042157361,0.11637322224301148,570,0.89481946624803765]
[125325,"Reconstruction","2018-07-13",2018,18580053.5,18580053.5,152959352,175903254.80000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D605,'Const Index'!A:F,4,0))*F605","v":25924004.310015287},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D605,'Const Index'!A:F,4,0))*G605","v":213418056.11620793},0.14147052963456591,2.7063680960664943E-2,0.11440684867390097,571,0.89638932496075352]
[84964.02,"Bridge Replacement","2018-02-09",2018,35998.480000000003,35998.480000000003,1599444.3,1839360.9450000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D606,'Const Index'!A:F,4,0))*F606","v":50227.237003058101},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D606,'Const Index'!A:F,4,0))*G606","v":2231640.5561926602},4.2506866916215844E-2,0.10876069498298813,6.6253828066772283E-2,572,0.89795918367346939]
[107719,"Bridge Replacement","2018-05-11",2018,49230.93,49230.93,475546,546877.9,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D607,'Const Index'!A:F,4,0))*F607","v":68689.944380733941},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D607,'Const Index'!A:F,4,0))*G607","v":663510.28287461761},0.12352506382137587,0.15744861085513998,3.3923547033764101E-2,573,0.89952904238618525]
[123055,"Modify Interchange","2018-08-17",2018,68026.880000000005,68026.880000000005,28942937.710000001,33284378.366500001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D608,'Const Index'!A:F,4,0))*F608","v":94915.180428134554},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D608,'Const Index'!A:F,4,0))*G608","v":40382921.499044336},2.2350379242135336E-2,4.4968878829676547E-2,2.261849958754121E-2,574,0.90109890109890112]
[114174,"Modify Interchange","2018-11-30",2018,9012294.2200000007,9012294.2200000007,132644398,152541057.69999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D609,'Const Index'!A:F,4,0))*F609","v":12574493.082186544},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D609,'Const Index'!A:F,4,0))*G609","v":185073414.64067277},8.7943270548070954E-2,2.8265875215726498E-2,5.9677395332344452E-2,575,0.90266875981161698]
[115791,"Widen","2018-12-07",{"$f":"YEAR(C610)","v":2018},381717.53,381717.53,38372518.600000001,44128396.390000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D610,'Const Index'!A:F,4,0))*F610","v":532595.17756116204},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D610,'Const Index'!A:F,4,0))*G610","v":53539637.954892963},2.9947679848150492E-2,4.1262578421311591E-2,1.1314898573161099E-2,576,0.90423861852433285]
[114172,"Widen","2018-10-05",2018,334609,334609,12357135.92,14210706.308,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D611,'Const Index'!A:F,4,0))*F611","v":466866.53287461767},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D611,'Const Index'!A:F,4,0))*G611","v":17241416.707951069},4.7078200172455495E-2,{"$f":"8.4856*G611^-0.305","v":5.829718972146529E-2},1.1218989549009795E-2,577,0.90580847723704871]
[117272,"Bridge Replacement","2018-06-22",2018,85270.92,85270.92,805988,926886.2,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D612,'Const Index'!A:F,4,0))*F612","v":118975.09862385319},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D612,'Const Index'!A:F,4,0))*G612","v":1124562.7675840978},0.12579676124210284,0.13404553124051607,8.2487699984132301E-3,578,{"$f":"N612/637","v":0.90737833594976447}]
[83910.01,"Bridge Replacement","2018-08-17",2018,514972.3,514972.3,27735269.710000001,31895560.166500002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D613,'Const Index'!A:F,4,0))*F613","v":718520.21980122314},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D613,'Const Index'!A:F,4,0))*G613","v":38697910.719227828},3.8567416339720176E-2,4.5557268379215407E-2,6.9898520394952313E-3,{"$f":"N612+1","v":579},0.90894819466248034]
[101454.01,"Construction-New","2018-12-07",2018,2583242.6,2583242.6,45122600,51890990,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D614,'Const Index'!A:F,4,0))*F614","v":3604294.9120795103},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D614,'Const Index'!A:F,4,0))*G614","v":62957756.116207942},7.7249418251607846E-2,3.9272843815711174E-2,3.7976574435896672E-2,580,0.9105180533751962]
[117923,"Bridge Replacement","2019-12-13",2019,13496.62,13496.62,604938.1,695678.81499999994,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D615,'Const Index'!A:F,4,0))*F615","v":18245.430740740743},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D615,'Const Index'!A:F,4,0))*G615","v":817786.69074074074},4.2310745512640052E-2,0.14630552260120591,0.10399477708856586,581,0.91208791208791207]
[113057,"Bridge Replacement","2019-03-29",2019,6941.77,6941.77,943235.35,1084720.6524999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D616,'Const Index'!A:F,4,0))*F616","v":9384.2446296296312},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D616,'Const Index'!A:F,4,0))*G616","v":1275114.4546296296},2.7359531213498309E-2,0.12776839370699,0.10040886249349169,582,0.91365777080062793]
[117282,"Bridge Replacement","2019-03-29",2019,14716.94,14716.94,756764.65,870279.34750000003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D617,'Const Index'!A:F,4,0))*F617","v":19895.122592592594},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D617,'Const Index'!A:F,4,0))*G617","v":1023033.6935185186},3.944718215894466E-2,0.13664681091984587,9.7199628760901213E-2,583,0.9152276295133438]
[105764,"Reconstruction","2019-06-21",2019,748569.33,748569.33,3902040.62,4487346.7130000005,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D618,'Const Index'!A:F,4,0))*F618","v":1011954.835},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D618,'Const Index'!A:F,4,0))*G618","v":5274980.8381481487},0.21184047602251763,8.285878506952328E-2,0.12898169095299433,584,0.91679748822605966]
[101623,"Bridge Replacement","2019-05-10",2019,2248192.9900000002,2248192.9900000002,17356589.84,19960078.316,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D619,'Const Index'!A:F,4,0))*F619","v":3039223.856851852},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D619,'Const Index'!A:F,4,0))*G619","v":23463538.117037036},0.14952964901082205,5.2558857196703584E-2,9.6970791814118468E-2,585,0.91836734693877553]
[124102,"Bridge Replacement","2019-10-18",2019,1700012.17,1700012.17,12633000,14527950,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D620,'Const Index'!A:F,4,0))*F620","v":2298164.6001851852},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D620,'Const Index'!A:F,4,0))*G620","v":17077944.444444444},0.1545691577614185,5.7905934468714039E-2,9.6663223292704464E-2,586,0.9199372056514914]
[100263,"Widen","2019-06-21",2019,3030442.35,3030442.35,26213794.149999999,30145863.272499997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D621,'Const Index'!A:F,4,0))*F621","v":4096709.1027777777},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D621,'Const Index'!A:F,4,0))*G621","v":35437166.165740736},0.13560487324571444,4.6347993886567858E-2,8.9256879359146585E-2,587,0.92150706436420726]
[100262,"Reconstruction","2019-06-21",2019,2015754.42,2015754.42,17478154.239999998,20099877.375999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D622,'Const Index'!A:F,4,0))*F622","v":2725001.3455555555},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D622,'Const Index'!A:F,4,0))*G622","v":23627875.176296294},0.13532993657801706,5.244709134618946E-2,8.2882845231827595E-2,588,0.92307692307692313]
[105763,"Reconstruction","2019-12-13",2019,1227529.82,1227529.82,10566684.02,12151686.623,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D623,'Const Index'!A:F,4,0))*F623","v":1659438.4603703704},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D623,'Const Index'!A:F,4,0))*G623","v":14284591.36037037},0.13616982372867434,6.1147857669355078E-2,7.5021966059319267E-2,589,0.92464678178963888]
[112456,"Modify Interchange","2019-03-29",2019,275514.84999999998,275514.84999999998,14444783.560000001,16611501.094000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D624,'Const Index'!A:F,4,0))*F624","v":372455.26018518518},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D624,'Const Index'!A:F,4,0))*G624","v":19527207.405185185},3.9073657203348225E-2,5.5586673998266882E-2,1.6513016794918657E-2,590,0.92621664050235475]
[103764,"Reconstruction","2019-10-04",2019,2232853.9700000002,2232853.9700000002,32746398.43,37658358.194499999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D625,'Const Index'!A:F,4,0))*F625","v":3018487.7742592595},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D625,'Const Index'!A:F,4,0))*G625","v":44268279.359074071},8.818624572632125E-2,4.3306957689114821E-2,4.4879288037206429E-2,591,0.92778649921507061]
[100241.02,"Widen","2019-08-09",2019,3385495.17,3385495.17,64487767.369999997,74160932.475500003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D626,'Const Index'!A:F,4,0))*F626","v":4576687.915},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D626,'Const Index'!A:F,4,0))*G626","v":87177907.740925923},7.2498253669965748E-2,3.5220212073987713E-2,3.7278041595978036E-2,592,0.92935635792778648]
[101885.01,"Widen","2020-10-09",2020,1312453.3500000001,1312453.3500000001,5073915.0199999996,5835002.2729999991,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D627,'Const Index'!A:F,4,0))*F627","v":1738191.120283019},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D627,'Const Index'!A:F,4,0))*G627","v":6719807.628084179},0.27866679769500757,7.6480881194766939E-2,0.20218591650024065,593,0.93092621664050235]
[123036,"Bridge Replacement","2020-05-15",2020,3305.93,3305.93,474461.84,545631.11600000004,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D628,'Const Index'!A:F,4,0))*F628","v":4378.3180333817127},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D628,'Const Index'!A:F,4,0))*G628","v":628369.27285921632},2.6967746868747127E-2,0.15755825519597166,0.13059050832722455,594,0.93249607535321821]
[124377,"Bridge Replacement","2020-12-11",2020,50553.23,50553.23,920351.5,1058404.2250000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D629,'Const Index'!A:F,4,0))*F629","v":66951.846698113208},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D629,'Const Index'!A:F,4,0))*G629","v":1218898.031567489},7.4928176897630969E-2,0.12872908131275854,5.3800904415127568E-2,595,0.93406593406593408]
[82443.009999999995,"Bridge Replacement","2020-03-27",2020,96065.33,96065.33,3380674.76,3887775.9739999995,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D630,'Const Index'!A:F,4,0))*F630","v":127227.30569666183},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D630,'Const Index'!A:F,4,0))*G630","v":4477308.735123367},4.8416022486587856E-2,8.6563841573755088E-2,3.8147819087167231E-2,596,0.93563579277864994]
[100288,"Reconstruction","2020-06-26",2020,3790293.57,3790293.57,49721564.960000001,57179799.704000004,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D631,'Const Index'!A:F,4,0))*F631","v":5019800.9907474592},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D631,'Const Index'!A:F,4,0))*G631","v":65850403.521044992},9.6230375553328112E-2,3.8127330152773815E-2,5.8103045400554297E-2,597,0.93720565149136581]
[101895.01,"Bridge Replacement","2020-03-27",2020,198945.28,198945.28,5181747.8499999996,5959010.0274999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D632,'Const Index'!A:F,4,0))*F632","v":263479.77939042088},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D632,'Const Index'!A:F,4,0))*G632","v":6862619.6126632793},5.8393469879087223E-2,7.5991897993915244E-2,1.7598428114828021E-2,598,0.93877551020408168]
[112833,"Modify Interchange","2020-06-26",2020,491900.84,491900.84,31994789.600000001,36794008.039999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D633,'Const Index'!A:F,4,0))*F633","v":651465.19085631357},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D633,'Const Index'!A:F,4,0))*G633","v":42373360.682148039},3.5374404587426952E-2,4.3614749451803908E-2,8.2403448643769556E-3,599,0.94034536891679754]
[128113,"Bridge Replacement","2020-03-20",2020,700420.27,700420.27,7917588.2599999998,9105226.4989999998,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D634,'Const Index'!A:F,4,0))*F634","v":927624.81331640063},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D634,'Const Index'!A:F,4,0))*G634","v":10485920.59107402},0.10846384113437089,6.6774664906128128E-2,4.1689176228242766E-2,600,0.9419152276295133]
[107045,"Widen","2020-12-11",2020,3038074.87,3038074.87,61044027.07,70200631.130500004,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D635,'Const Index'!A:F,4,0))*F635","v":4023575.2088171262},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D635,'Const Index'!A:F,4,0))*G635","v":80845681.714622632},6.9768585328032165E-2,3.5814705724632627E-2,3.3953879603399538E-2,601,0.94348508634222916]
[114149.01,"Widen","2020-10-09",2020,2307482.83,2307482.83,87990625.450000003,101189219.2675,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D636,'Const Index'!A:F,4,0))*F636","v":3055991.4112844705},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D636,'Const Index'!A:F,4,0))*G636","v":116533302.93632075},4.6224189431534494E-2,3.2035348464982953E-2,1.4188840966551541E-2,602,0.94505494505494503]
[124069,"Bridge Replacement","2020-01-31",2020,1607535.97,1607535.97,32917144.600000001,37854716.289999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D637,'Const Index'!A:F,4,0))*F637","v":2128993.5742017417},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D637,'Const Index'!A:F,4,0))*G637","v":43594912.115384616},6.8835826725991298E-2,4.3238318719583196E-2,2.5597508006408101E-2,603,0.94662480376766089]
[101409,"Widen","2021-12-10",2021,3004735.55,3004735.55,25795408.66,29664719.958999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D638,'Const Index'!A:F,4,0))*F638","v":3275772.0303166062},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D638,'Const Index'!A:F,4,0))*G638","v":28122234.650238946},0.13648334746715346,4.6575992700149914E-2,8.9907354767003539E-2,604,0.94819466248037676]
[43975.01,"Reconstruction","2021-12-10",2021,1299775.76,1299775.76,9843196.4000000004,11319675.859999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D639,'Const Index'!A:F,4,0))*F639","v":1417019.571087216},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D639,'Const Index'!A:F,4,0))*G639","v":10731083.291517323},0.15204813834660455,6.248503679627454E-2,8.956310155033001E-2,605,0.94976452119309263]
[105360.01,"Bridge Replacement","2021-06-18",2021,26012.46,26012.46,9399030.6300000008,10808885.2245,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D640,'Const Index'!A:F,4,0))*F640","v":28358.864695340497},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D640,'Const Index'!A:F,4,0))*G640","v":10246852.389336918},2.2767568382740765E-2,6.3371242319699345E-2,4.060367393695858E-2,606,0.95133437990580849]
[124013,"Widen","2021-03-26",2021,102326.21,102326.21,4578016.0999999996,5264718.5149999997,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D641,'Const Index'!A:F,4,0))*F641","v":111556.35200119474},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D641,'Const Index'!A:F,4,0))*G641","v":4990967.3730585417},4.2351649222028734E-2,7.8917982567221961E-2,3.6566333345193228E-2,607,0.95290423861852436]
[117922,"Bridge Replacement","2021-03-26",2021,84623.31,84623.31,1483886.73,1706469.7394999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D642,'Const Index'!A:F,4,0))*F642","v":92256.595430107511},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D642,'Const Index'!A:F,4,0))*G642","v":1617737.9224910391},7.7028146616015633E-2,0.11127697901419589,3.4248832398180259E-2,608,0.95447409733124022]
[124046,"Bridge Replacement","2021-10-08",2021,125469.8,125469.8,2683017.13,3085469.6995000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D643,'Const Index'!A:F,4,0))*F643","v":136787.56571087215},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D643,'Const Index'!A:F,4,0))*G643","v":2925033.609468339},6.6764442387291054E-2,9.2886458544508485E-2,2.6122016157217431E-2,609,0.95604395604395609]
[115786,"Modify Interchange","2021-05-07",2021,236210.51,236210.51,28637629,32933273.350000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D644,'Const Index'!A:F,4,0))*F644","v":257517.43175029865},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D644,'Const Index'!A:F,4,0))*G644","v":31220832.093787331},2.8248256515928744E-2,4.5114562797081197E-2,1.6866306281152453E-2,610,0.95761381475667195]
[104963.01,"Construction-New","2021-05-07",2021,1673143.11,1673143.11,19534844.75,22465071.462499999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D645,'Const Index'!A:F,4,0))*F645","v":1824065.8158602149},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D645,'Const Index'!A:F,4,0))*G645","v":21296948.428166065},0.10564916340069712,5.0697380102028004E-2,5.4951783298669114E-2,611,0.95918367346938771]
[114379.01,"Bridge Replacement","2021-12-10",2021,201810.89,201810.89,3812304.2,4384149.83,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D646,'Const Index'!A:F,4,0))*F646","v":220014.8591696535},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D646,'Const Index'!A:F,4,0))*G646","v":4156185.881123058},7.2936722625649861E-2,8.3448849567634514E-2,1.0512126941984654E-2,612,0.96075353218210358]
[100260.05,"Widen","2021-12-21",2021,5026541.08,5026541.08,84641124.989999995,97337293.738499999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D647,'Const Index'!A:F,4,0))*F647","v":5479950.6995221023},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D647,'Const Index'!A:F,4,0))*G647","v":92276017.387544781},7.9386510760506387E-2,3.2416805897742929E-2,4.6969704862763459E-2,613,0.96232339089481944]
[101399,"Construction-New","2021-10-08",2021,3811300.32,3811300.32,66969669.710000001,77015120.166500002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D648,'Const Index'!A:F,4,0))*F648","v":4155091.448028673},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D648,'Const Index'!A:F,4,0))*G648","v":73010541.947879329},7.691084242320656E-2,3.4816869361105632E-2,4.2093973062100928E-2,614,0.96389324960753531]
[100326.01,"Reconstruction","2021-10-08",2021,1958285.03,1958285.03,29734482.550000001,34194654.932500005,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D649,'Const Index'!A:F,4,0))*F649","v":2134928.422789725},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D649,'Const Index'!A:F,4,0))*G649","v":32416625.241188765},8.5859058643682373E-2,4.4600336806853297E-2,4.1258721836829076E-2,615,0.96546310832025117]
[124263.03999999999,"Widen","2021-08-20",2021,1270902.8500000001,1270902.8500000001,160226914.61000001,184260951.80150002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D650,'Const Index'!A:F,4,0))*F650","v":1385542.234916368},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D650,'Const Index'!A:F,4,0))*G650","v":174679880.02583632},2.7931893671506055E-2,2.6683220037613069E-2,1.2486736338929855E-3,616,0.96703296703296704]
[112538,"Widen","2021-09-10",2021,1958254.29,1958254.29,39602652.649999999,45543050.547499999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D651,'Const Index'!A:F,4,0))*F651","v":2134894.9099462363},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D651,'Const Index'!A:F,4,0))*G651","v":43174934.938022695},6.9447553609770632E-2,4.0867366392912566E-2,{"$f":"ABS(L651-K651)","v":2.8580187216858066E-2},617,0.9686028257456829]
[100260.01,"Widen","2021-02-05",2021,2487066.54,2487066.54,62976602.670000002,72423093.070500001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D652,'Const Index'!A:F,4,0))*F652","v":2711407.6675627236},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D652,'Const Index'!A:F,4,0))*G652","v":68657287.85707885},5.9491913417945574E-2,3.5475856633820406E-2,2.4016056784125168E-2,618,0.97017268445839877]
[123388,"Bridge Replacement","2022-02-11",2022,1326.07,1326.07,1601686.35,1841939.3025000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D653,'Const Index'!A:F,4,0))*F653","v":1357.3066461020749},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D653,'Const Index'!A:F,4,0))*G653","v":1639415.3610487941},2.0827921146983615E-2,0.10871423799989963,8.7886316852916008E-2,619,0.97174254317111464]
[103801,"Bridge Replacement","2022-05-13",2022,25618.99,25618.99,620968.81000000006,714114.13150000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D654,'Const Index'!A:F,4,0))*F654","v":26222.465928210877},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D654,'Const Index'!A:F,4,0))*G654","v":635596.2300897364},6.1256484363522212E-2,0.14514305862648769,8.3886574262965474E-2,620,0.9733124018838305]
[124012,"Bridge Replacement","2022-05-13",2022,21965.61,21965.61,1024447.15,1178114.2225000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D655,'Const Index'!A:F,4,0))*F655","v":22483.027621985417},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D655,'Const Index'!A:F,4,0))*G655","v":1048578.8271172179},4.1441428188852894E-2,0.12459001567681974,8.3148587487966844E-2,621,0.97488226059654626]
[124509,"Bridge Replacement","2022-12-09",2022,20023.2,20023.2,3739930.52,{"$f":"G656+(G656*0.15)","v":4300920.0980000002},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D656,'Const Index'!A:F,4,0))*F656","v":20494.862591138528},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D656,'Const Index'!A:F,4,0))*G656","v":3828027.5933819399},{"$f":"I656/J656+0.02","v":2.5353896253666231E-2},8.393810841864123E-2,5.8584212164975003E-2,622,0.97645211930926212]
[123070,"Widen","2022-12-09",2022,8660.84,8660.84,6191582.8700000001,7120320.3004999999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D657,'Const Index'!A:F,4,0))*F657","v":8864.8530566461013},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D657,'Const Index'!A:F,4,0))*G657","v":6337430.5876332019},2.1398808702369834E-2,7.1975226524031946E-2,5.0576417821662112E-2,623,0.97802197802197799]
[133132,"Bridge Replacement","2022-08-12",2022,55020.08,55020.08,997178.04,1146754.746,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D658,'Const Index'!A:F,4,0))*F658","v":56316.122265844075},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D658,'Const Index'!A:F,4,0))*G658","v":1020667.3712843521},7.5175783855007478E-2,0.12561944796448235,5.0443664109474873E-2,624,0.97959183673469385]
[124507,"Bridge Replacement","2022-02-11",2022,60392.67,60392.67,1073671.3,1234721.9950000001,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D659,'Const Index'!A:F,4,0))*F659","v":61815.267947279855},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D659,'Const Index'!A:F,4,0))*G659","v":1098962.4915872125},7.6248751363662229E-2,0.1228193503447025,4.6570598981040268E-2,625,0.98116169544740972]
[101742,"Modify Interchange","2022-03-25",2022,8733644.5999999996,8733644.5999999996,98558199.799999997,113341929.77,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D660,'Const Index'!A:F,4,0))*F660","v":8939372.6275939401},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D660,'Const Index'!A:F,4,0))*G660","v":100879817.51822768},0.1086140840409303,3.094612413675531E-2,7.7667959904174994E-2,626,0.98273155416012559]
[121363,"Bridge Replacement","2022-02-11",2022,449132.14,449132.14,3939497.21,4530421.7915000003,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D661,'Const Index'!A:F,4,0))*F661","v":459711.80902972515},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D661,'Const Index'!A:F,4,0))*G661","v":4032295.237380818},0.13400747761920614,8.2617702326670525E-2,5.1389775292535619E-2,627,0.98430141287284145]
[124411,"Bridge Replacement","2022-08-19",2022,274488.99,274488.99,4838194.57,5563923.7555,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D662,'Const Index'!A:F,4,0))*F662","v":280954.79907459335},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D662,'Const Index'!A:F,4,0))*G662","v":4952162.1369882217},7.6733764223128373E-2,7.7598645438454961E-2,8.6488121532658779E-4,628,0.98587127158555732]
[114174.01,"Modify Interchange","2022-10-21",2022,7327973.4199999999,7327973.4199999999,160954545,185097726.75,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D663,'Const Index'!A:F,4,0))*F663","v":7500589.7316320799},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D663,'Const Index'!A:F,4,0))*G663","v":164745958.84744808},6.5528216801830616E-2,2.6646370747445927E-2,3.8881846054384689E-2,629,0.98744113029827318]
[116896,"Modify Interchange","2022-05-13",2022,1751445.57,1751445.57,135971408.03,156367119.23449999,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D664,'Const Index'!A:F,4,0))*F664","v":1792702.2800056082},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D664,'Const Index'!A:F,4,0))*G664","v":139174323.97910821},3.288098428467822E-2,2.8053111600103507E-2,4.8278726845747133E-3,630,0.98901098901098905]
[124572,"Bridge Replacement","2022-02-11",2022,190646.85,190646.85,1968343.83,2263595.4045000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D665,'Const Index'!A:F,4,0))*F665","v":195137.68998878292},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D665,'Const Index'!A:F,4,0))*G665","v":2014709.7530846884},0.11685647755961417,0.10208966108644819,1.4766816473165981E-2,631,0.99058084772370492]
[124238,"Bridge Replacement","2022-10-26",2022,2562455.15,2562455.15,71830149.920000002,82604672.408000007,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D666,'Const Index'!A:F,4,0))*F666","v":2622815.8433819399},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D666,'Const Index'!A:F,4,0))*G666","v":73522166.911946148},5.5673810410446098E-2,3.4080737961465955E-2,2.1593072448980143E-2,632,0.99215070643642067]
[124442,"Bridge Replacement","2022-12-09",2022,214414.71,214414.71,2173935.16,2500025.4340000004,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D667,'Const Index'!A:F,4,0))*F667","v":219465.42106001117},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D667,'Const Index'!A:F,4,0))*G667","v":2225143.9523275378},0.11862976318024129,9.9042671674348007E-2,1.9587091505893287E-2,633,0.99372056514913654]
[124605,"Bridge Replacement","2023-03-31",2023,43782.59,43782.59,3598643.83,4138440.4045000002,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D668,'Const Index'!A:F,4,0))*F668","v":43782.59},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D668,'Const Index'!A:F,4,0))*G668","v":3598643.83},3.2166413812616736E-2,8.4929819671519469E-2,5.2763405858902733E-2,634,0.9952904238618524]
[124362,"Bridge Replacement","2023-03-31",2023,116831.63,116831.63,2251466,2589185.9,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D669,'Const Index'!A:F,4,0))*F669","v":116831.63},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D669,'Const Index'!A:F,4,0))*G669","v":2251466},7.1891358785786688E-2,9.7989741275963396E-2,2.6098382490176708E-2,635,0.99686028257456827]
[124425,"Bridge Replacement","2023-03-31",2023,172344.61,172344.61,5669713.7400000002,6520170.801,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D670,'Const Index'!A:F,4,0))*F670","v":172344.61},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D670,'Const Index'!A:F,4,0))*G670","v":5669713.7400000002},5.0397409446636364E-2,7.3934375779074205E-2,2.3536966332437841E-2,636,0.99843014128728413]
[124424,"Bridge Replacement","2023-03-31",2023,178382.98,178382.98,5911546.6799999997,6798278.682,{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D671,'Const Index'!A:F,4,0))*F671","v":178382.98},{"$f":"(VLOOKUP(2023,'Const Index'!A:F,4,0)/VLOOKUP(D671,'Const Index'!A:F,4,0))*G671","v":5911546.6799999997},5.0175348289730498E-2,7.2998462528231237E-2,2.2823114238500739E-2,637,1]

{"sheet":"Clr&Grb","index":28,"n_rows":35,"n_cols":15,"rows_kept":35,"cut":false,"hidden":true,"merged":[[0,13,0,14]]}
["ContId","Item","Itemdesc","Project Length","BtoQty","Bid1","letdate","Years Since Letting","Inflated Cost","Cost Per Mile",null,null,"Clearing and Grubbing","Average"]
["CNQ297","201-01","CLEARING AND GRUBBING",0.99,1,2850000,"2016-10-07",{"$f":"YEAR(TODAY())-YEAR(G2)","v":9},{"$f":"F2*(1+H2*VLOOKUP(H2,'Const Index'!C:E,3,0))","v":5021884.0767578697},{"$f":"I2/D2","v":5072610.1785433032},null,null,"Tier 1 - Very Low Impacts",{"$f":"MROUND(SUMPRODUCT(D29:D35,J29:J35)/SUM(D29:D35),10000)","v":80000},"/mile"]
["CNS182","201-01","CLEARING AND GRUBBING",2.1800000000000002,1,1523000,"2018-08-17",7,{"$f":"F3*(1+H3*VLOOKUP(H3,'Const Index'!C:E,3,0))","v":2410748.189940481},1105847.7935506792,null,null,"Tier 2 - Low Impacts",{"$f":"MROUND(SUMPRODUCT(D22:D28,J22:J28)/SUM(D22:D28),10000)","v":170000},"/mile"]
["CNS127","201-01","CLEARING AND GRUBBING",2.15,1,999500,"2018-03-23",7,{"$f":"F4*(1+H4*VLOOKUP(H4,'Const Index'!C:E,3,0))","v":1582102.9650988253},735861.84423201182,null,null,"Tier 3 - Moderate Impacts",{"$f":"MROUND(SUMPRODUCT(D15:D21,J15:J21)/SUM(D15:D21),10000)","v":240000},"/mile"]
["CNQ172","201-01","CLEARING AND GRUBBING",1.3,1,500000,"2016-05-13",9,{"$f":"F5*(1+H5*VLOOKUP(H5,'Const Index'!C:E,3,0))","v":881032.29416804726},677717.14936003636,null,null,"Tier 4 - High Impacts",{"$f":"MROUND(SUMPRODUCT(D8:D14,J8:J14)/SUM(D8:D14),10000)","v":360000},"/mile"]
["CNQ076","201-01","CLEARING AND GRUBBING",1.91,1,725000,"2016-04-01",9,{"$f":"F6*(1+H6*VLOOKUP(H6,'Const Index'!C:E,3,0))","v":1277496.8265436685},668846.50604380551,null,null,"Tier 5 - Very High Impacts",{"$f":"MROUND(SUMPRODUCT(D2:D7,J2:J7)/SUM(D2:D7),10000)","v":1130000},"/mile"]
["CNT336","201-01","CLEARING AND GRUBBING",3.08,1,1249400,"2019-12-13",6,{"$f":"F7*(1+H7*VLOOKUP(H7,'Const Index'!C:E,3,0))","v":1916140.8211732311},622123.64323806204]
["CNR273","201-01","CLEARING AND GRUBBING",3.387,1,850000,"2017-12-08",8,{"$f":"F8*(1+H8*VLOOKUP(H8,'Const Index'!C:E,3,0))","v":1438971.3880626936},424851.31032261398]
["CNR040","201-01","CLEARING AND GRUBBING",2.12,1,470075,"2017-02-10",8,{"$f":"F9*(1+H9*VLOOKUP(H9,'Const Index'!C:E,3,0))","v":795793.50028655387},375374.2925879971]
["CNL258","201-01","CLEARING AND GRUBBING",3.24,1,562000,"2012-12-07",13,{"$f":"F10*(1+H10*VLOOKUP(H10,'Const Index'!C:E,3,0))","v":1123146.0916097877},346650.02827462577]
["CNR220","201-01","CLEARING AND GRUBBING",1.724,1,349000,"2017-05-12",8,{"$f":"F11*(1+H11*VLOOKUP(H11,'Const Index'!C:E,3,0))","v":590824.72286338836},342705.75572122296]
["CNR136","201-01","CLEARING AND GRUBBING",2.59,1,500000,"2017-06-23",8,{"$f":"F12*(1+H12*VLOOKUP(H12,'Const Index'!C:E,3,0))","v":846453.75768393744},326816.1226578909]
["CNQ340","201-01","CLEARING AND GRUBBING",1.35,1,250000,"2016-12-02",9,{"$f":"F13*(1+H13*VLOOKUP(H13,'Const Index'!C:E,3,0))","v":440516.14708402363},326308.25709927676]
["CNN201","201-01","CLEARING AND GRUBBING",0.89,1,155000,"2014-07-11",11,{"$f":"F14*(1+H14*VLOOKUP(H14,'Const Index'!C:E,3,0))","v":289374.22285907232},325139.57624614867]
["CNV012","201-01","CLEARING AND GRUBBING",4.0999999999999996,1,1000000,"2021-03-26",4,{"$f":"F15*(1+H15*VLOOKUP(H15,'Const Index'!C:E,3,0))","v":1236813.5551343556},301661.84271569649]
["CNU032","201-01","CLEARING AND GRUBBING",5.6,1,925000,"2020-06-26",5,{"$f":"F16*(1+H16*VLOOKUP(H16,'Const Index'!C:E,3,0))","v":1389799.6730390368},248178.51304268517]
["CNR277","201-01","CLEARING AND GRUBBING",2.66,1,350000,"2017-08-18",8,{"$f":"F17*(1+H17*VLOOKUP(H17,'Const Index'!C:E,3,0))","v":592517.63037875621},222750.98886419405]
["CNH658","201-01","CLEARING AND GRUBBING",1.98,1,195000,"2009-10-30",16,{"$f":"F18*(1+H18*VLOOKUP(H18,'Const Index'!C:E,3,0))","v":430419.02857410203},217383.347764698]
["CNK821","201-01","CLEARING AND GRUBBING",4.0999999999999996,1,430000,"2011-12-09",14,{"$f":"F19*(1+H19*VLOOKUP(H19,'Const Index'!C:E,3,0))","v":881468.44876912062},214992.30457783432]
["CNT925","201-01","CLEARING AND GRUBBING",2.15,1,279652,"2019-10-04",6,{"$f":"F20*(1+H20*VLOOKUP(H20,'Const Index'!C:E,3,0))","v":428887.95655733667},199482.7704917845]
["CNR280","201-01","CLEARING AND GRUBBING",0.34,1,40000,"2017-10-06",8,{"$f":"F21*(1+H21*VLOOKUP(H21,'Const Index'!C:E,3,0))","v":67716.300614715001},199165.5900432794]
["CNR279","201-01","CLEARING AND GRUBBING",3.1,1,350000,"2017-12-08",8,{"$f":"F22*(1+H22*VLOOKUP(H22,'Const Index'!C:E,3,0))","v":592517.63037875621},191134.71947701814]
["CNU922","201-01","CLEARING AND GRUBBING",3.94,1,485250,"2020-12-11",5,{"$f":"F23*(1+H23*VLOOKUP(H23,'Const Index'!C:E,3,0))","v":729081.39604561357},185046.03960548568]
["CNG917","201-01","CLEARING AND GRUBBING",6.0359999999999996,1,465000,"2008-08-01",17,{"$f":"F24*(1+H24*VLOOKUP(H24,'Const Index'!C:E,3,0))","v":1057964.8785188282},175275.82480431217]
["CNH654","201-01","CLEARING AND GRUBBING",2.2000000000000002,1,170000,"2009-06-12",16,{"$f":"F25*(1+H25*VLOOKUP(H25,'Const Index'!C:E,3,0))","v":375237.10183383257},170562.31901537842]
["CNJ363","201-01","CLEARING AND GRUBBING",3.9,1,300000,"2010-12-10",15,{"$f":"F26*(1+H26*VLOOKUP(H26,'Const Index'!C:E,3,0))","v":644323.41015401797},165211.13080872255]
["CNJ331","201-01","CLEARING AND GRUBBING",1.64,1,125000,"2010-09-17",15,{"$f":"F27*(1+H27*VLOOKUP(H27,'Const Index'!C:E,3,0))","v":268468.0875641742},163700.05339278915]
["CNP927","201-01","CLEARING AND GRUBBING",2.31,1,165244.03,"2015-12-04",10,{"$f":"F28*(1+H28*VLOOKUP(H28,'Const Index'!C:E,3,0))","v":300373.58919570938},130031.85679467938]
["CNH670","201-01","CLEARING AND GRUBBING",0.90100000000000002,1,50000,"2009-06-12",16,{"$f":"F29*(1+H29*VLOOKUP(H29,'Const Index'!C:E,3,0))","v":110363.85348053899},122490.40341902219]
["CNR252","201-01","CLEARING AND GRUBBING",3.8,1,261678,"2017-12-08",8,{"$f":"F30*(1+H30*VLOOKUP(H30,'Const Index'!C:E,3,0))","v":442996.65280643478},116578.06652800916]
["CNQ346","201-01","CLEARING AND GRUBBING",2.17,1,138250,"2016-12-02",9,{"$f":"F31*(1+H31*VLOOKUP(H31,'Const Index'!C:E,3,0))","v":243605.42933746509},112260.56651496087]
["CNM019","201-01","CLEARING AND GRUBBING",3.1349999999999998,1,170000,"2013-12-06",12,{"$f":"F32*(1+H32*VLOOKUP(H32,'Const Index'!C:E,3,0))","v":328026.46926387225},104633.6425084122]
["CNJ202","201-01","CLEARING AND GRUBBING",5.4710000000000001,1,150000,"2010-08-06",15,{"$f":"F33*(1+H33*VLOOKUP(H33,'Const Index'!C:E,3,0))","v":322161.70507700898},58885.341816305794]
["CNK916","201-01","CLEARING AND GRUBBING",3.206,1,90207.82,"2011-05-06",14,{"$f":"F34*(1+H34*VLOOKUP(H34,'Const Index'!C:E,3,0))","v":184919.41200521874},57679.167811983389]
["CNU057","201-01","CLEARING AND GRUBBING",4.92,1,165000,"2020-06-26",5,{"$f":"F35*(1+H35*VLOOKUP(H35,'Const Index'!C:E,3,0))","v":247910.21194750385},50388.25446087477]

{"sheet":"Estimate Process","index":29,"n_rows":8,"n_cols":5,"rows_kept":8,"cut":false,"hidden":true,"merged":[[4,1,4,2],[7,1,7,2],[5,1,5,4],[1,1,1,2],[2,1,2,2],[3,1,3,2]]}
[]
[null,"ROLE",null,"NAME/ORGANIZATION","Date Completed"]
[null,"Primary Cost Estimator:",null,"Michael Cloud","2023-06-17"]
[null,"Independent Cost Estimator:",null,"David Duncan","2023-06-18"]
[null,"QA/QC peformed by:",null,"John Davey","2023-06-22"]
[]
[null,null,null,"NAME","STAMP"]
[null,"Verified By Manager:",null,"David Duncan"]

{"sheet":"ROW_New","index":30,"n_rows":97,"n_cols":27,"rows_kept":97,"cut":false,"hidden":true,"merged":[[33,9,33,10],[34,9,34,10],[28,9,28,12],[29,9,29,10],[30,9,30,10],[31,9,31,10],[32,9,32,10],[25,18,25,22],[9,9,9,11],[0,9,0,10],[20,9,20,12],[21,9,21,10],[22,9,22,10],[23,9,23,10],[24,9,24,10],[25,9,25,10]]}
[null,null,null,null,null,null,null,null,null,"Bridge Projects"]
["Distressed",3,2,null,"County","Category",null,null,null,"ROW Impacts","Average",null,null,null,null,null,null,null,null,"ROW Impacts","At Risk","Transitional","Competitive","Attainment","Attainment x2","Attainment x3"]
["At-Risk",4,3,null,"Anderson","Transitional",null,{"$f":"VLOOKUP(Tool!H53,ROW_New!E:F,2,0)","v":{"$error":"#N/A"}},{"$f":"VLOOKUP(H3,A2:B6,2,0)","v":{"$error":"#N/A"}},"Very Low",{"$f":"MROUND(Bridges_Projects_ROW!B2*1.3,1000)","v":69000},null,null,null,null,null,null,null,null,"Tier 1 - Very Low Impacts",{"$f":"(L3/K3)","v":0},{"$f":"(M3/L3)","v":{"$error":"#DIV/0!"}},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$f":"2.859*EXP(-0.247*5)","v":0.83149658560968776},{"$f":"2.859*EXP(-0.247*6)","v":0.64951581955212301}]
["Transitional",5,4,null,"Bedford","Transitional",null,null,{"$f":"VLOOKUP(H3,A2:C6,3,0)","v":{"$error":"#N/A"}},"Low",{"$f":"MROUND(Bridges_Projects_ROW!B3*1.3,10000)","v":150000},null,null,null,null,null,null,null,null,"Tier 2 - Low Impacts",0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$f":"1.2416*EXP(-0.019*5)","v":1.1290774354357562},{"$f":"1.2416*EXP(-0.019*6)","v":1.1078274780235982}]
["Competitive",6,5,null,"Benton","At-Risk",null,null,null,"Moderate",{"$f":"MROUND(Bridges_Projects_ROW!B4*1.3,10000)","v":290000},null,null,null,null,null,null,null,null,"Tier 3 - Moderate Impacts",0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$f":"-0.0003*5+1.1255","v":1.1239999999999999},{"$f":"-0.0003*6+1.1255","v":1.1236999999999999}]
["Attainment",7,6,null,"Bledsoe","Distressed","Distressed",{"$f":"COUNTIF($F$3:$F$97,G6)","v":10},{"$f":"H6/95","v":0.10526315789473684},"High",{"$f":"MROUND(Bridges_Projects_ROW!B5*1.3,10000)","v":890000},null,null,null,null,null,null,null,null,"Tier 4 - High Impacts",0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},1.1499999999999999,1.1499999999999999]
[null,null,null,null,"Blount","Transitional","At-Risk",31,{"$f":"H7/95","v":0.32631578947368423},"Very High",{"$f":"MROUND(Bridges_Projects_ROW!B6*1.3,100000)","v":4500000},null,null,null,null,null,null,null,null,"Tier 5 - Very High Impacts",0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},1.62,1]
[null,null,null,null,"Bradley","Transitional","Transitional",48,0.50526315789473686,null,null,null,null,null,null,null,null,null,null,"All Impacts",{"$f":"AVERAGE(U3:U7)","v":0},{"$f":"AVERAGE(V3:V7)","v":{"$error":"#DIV/0!"}},{"$f":"AVERAGE(W3:W7)","v":{"$error":"#DIV/0!"}},{"$error":"#DIV/0!"},{"$f":"1.769*EXP(-0.074*5)","v":1.2219090308974803},{"$f":"1.769*EXP(-0.074*6)","v":1.1347523294435289},{"$f":"1.769*EXP(-0.074*6)","v":1.1347523294435289}]
["Bridge Replacement",null,null,null,"Campbell","At-Risk","Competitive",{"$f":"COUNTIF($F$3:$F$97,G9)","v":5},5.2631578947368418E-2]
["Corridor Project",null,null,null,"Cannon","Transitional","Attainment",{"$f":"COUNTIF($F$3:$F$97,G10)","v":1},1.0526315789473684E-2,"Corridor Widening and New Location",null,null,null,null,null,null,null,null,null,"ROW Impacts","At Risk","Transitional","Competitive","Attainment","Attainment x2","Attainment x3","Attainment x4"]
[null,null,null,null,"Carroll","At-Risk",null,null,null,"ROW Impacts","Average Project Length","Average",null,null,null,null,null,null,null,"Tier 1 - Very Low Impacts",{"$f":"M12/L12","v":0},{"$f":"N12/M12","v":{"$error":"#DIV/0!"}},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"}]
["Tier 1 - Very Low Impacts",null,null,null,"Carter","At-Risk",null,null,null,"Very Low",{"$f":"Corridor_Proj_ROW!B10","v":2.641833333333333},{"$f":"MROUND(Corridor_Proj_ROW!C10,10000)*1.3","v":104000},null,null,null,null,null,null,null,"Tier 2 - Low Impacts",0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"}]
["Tier 2 - Low Impacts",null,null,null,"Cheatham","Transitional",null,null,null,"Low",{"$f":"Corridor_Proj_ROW!B11","v":1.9090666666666665},{"$f":"MROUND(Corridor_Proj_ROW!C11,100000)*1.3","v":390000},null,null,null,null,null,null,null,"Tier 3 - Moderate Impacts",0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"}]
["Tier 3 - Moderate Impacts",null,null,null,"Chester","Transitional",null,null,null,"Moderate",{"$f":"Corridor_Proj_ROW!B12","v":2.1468928571428569},{"$f":"MROUND(Corridor_Proj_ROW!C12,100000)*1.3","v":4940000},null,null,null,null,null,null,null,"Tier 4 - High Impacts",0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"}]
["Tier 4 - High Impacts",null,null,null,"Claiborne","At-Risk",null,null,null,"High",{"$f":"Corridor_Proj_ROW!B13","v":1.8234166666666667},{"$f":"MROUND(Corridor_Proj_ROW!C13,100000)","v":10000000},null,null,null,null,null,null,null,"Tier 5 - Very High Impacts",0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"}]
["Tier 5 - Very High Impacts",null,null,null,"Clay","Distressed",null,null,null,"Very High",{"$f":"Corridor_Proj_ROW!B14","v":1.6779999999999997},{"$f":"MROUND(Corridor_Proj_ROW!C14,100000)","v":28300000},null,null,null,null,null,null,null,"All Impacts",{"$f":"AVERAGE(U11:U15)","v":0},{"$f":"AVERAGE(V11:V15)","v":{"$error":"#DIV/0!"}},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$f":"2.0973*EXP(-0.149*5)","v":0.99566024726397839},{"$f":"2.0973*EXP(-0.149*6)","v":0.85783011797530395},{"$f":"2.0973*EXP(-0.149*7)","v":0.7390799354776515}]
[null,null,null,null,"Cocke","Distressed",null,null,null,null,null,null,null,null,null,null,null,null,null,"Avg(Corridor and Bridges)",{"$f":"AVERAGE(U16,U8)","v":0},{"$f":"AVERAGE(V16,V8)","v":{"$error":"#DIV/0!"}},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},1.1087846390807292,0.99629122370941636,0.93691613246059013]
["Default",2,null,null,"Coffee","Transitional",null,null,null,"Type of Project",{"$f":"Tool!I226","v":"Corridor Project"}]
["Medium",3,null,null,"Crockett","Transitional",null,null,null,"Length of Impact",{"$f":"Tool!I227","v":1}]
["High",4,null,null,"Cumberland","Transitional",null,null,null,"Calibration Factor",{"$f":"Tool!E232/Tool!E229","v":1},null,null,null,null,null,null,null,"Economic Status","Default","Medium","High","Very High"]
["Very High",5,null,null,"Davidson","Competitive",null,null,null,"Corridor",null,null,null,null,null,null,null,null,"Distressed",0.15,{"$f":"U17-T21","v":-0.15},{"$f":"V17","v":{"$error":"#DIV/0!"}},{"$f":"W17","v":{"$error":"#DIV/0!"}}]
[null,null,null,null,"Decatur","At-Risk",null,null,null,"Very Low",null,{"$f":"Tool!I229","v":0},{"$f":"MROUND(L22*$K$19*$K$20*L12,1000)","v":0},null,null,null,null,null,"At Risk",0.15,{"$f":"V17-T22","v":{"$error":"#DIV/0!"}},{"$f":"W17","v":{"$error":"#DIV/0!"}},{"$f":"X17","v":{"$error":"#DIV/0!"}}]
[null,null,null,null,"Dekalb","At-Risk",null,null,null,"Low",null,{"$f":"Tool!I230","v":0},{"$f":"MROUND(L23*$K$19*$K$20*L13,1000)","v":0},null,null,null,null,null,"Transitional",0.15,{"$f":"W17-T23","v":{"$error":"#DIV/0!"}},{"$f":"X17","v":{"$error":"#DIV/0!"}},{"$f":"Y17","v":1.1087846390807292}]
[null,null,null,null,"Dickson","Transitional",null,null,null,"Moderate",null,{"$f":"Tool!I231","v":0},0,null,null,null,null,null,"Competitive",0.15,{"$f":"X17-T24","v":{"$error":"#DIV/0!"}},{"$f":"Y17","v":1.1087846390807292},{"$f":"Z17","v":0.99629122370941636}]
[null,null,null,null,"Dyer","Transitional",null,null,null,"High",null,{"$f":"Tool!I232","v":0},0,null,null,null,null,null,"Attainment",0.15,{"$f":"Y17-T25","v":0.9587846390807292},{"$f":"Z17","v":0.99629122370941636},{"$f":"AA17","v":0.93691613246059013}]
[null,null,null,null,"Fayette","Transitional",null,null,null,"Very High",null,{"$f":"Tool!I233","v":0},0,null,null,null,null,null,"Cumulative"]
[null,null,null,null,"Fentress","At-Risk",null,null,null,null,null,null,null,null,null,null,null,null,1,2,3,4,5]
[null,null,null,null,"Franklin","Transitional",null,null,null,null,null,null,null,null,null,null,null,null,"Economic Status","Default","Medium","High","Very High"]
[null,null,null,null,"Gibson","Transitional",null,null,null,"Bridge",null,null,null,null,null,null,null,null,"Distressed",0.15,{"$f":"T29+U21","v":0},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"}]
[null,null,null,null,"Giles","Transitional",null,null,null,"Very Low",null,{"$f":"Tool!I229","v":0},{"$f":"MROUND(L30*$K$20*K3,1000)","v":0},null,null,null,null,null,"At Risk",0.15,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"}]
[null,null,null,null,"Grainger","At-Risk",null,null,null,"Low",null,{"$f":"Tool!I230","v":0},{"$f":"MROUND(L31*$K$20*K4,1000)","v":0},null,null,null,null,null,"Transitional",0.15,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"}]
[null,null,null,null,"Greene","At-Risk",null,null,null,"Moderate",null,{"$f":"Tool!I231","v":0},0,null,null,null,null,null,"Competitive",0.15,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"}]
[null,null,null,null,"Grundy","Distressed",null,null,null,"High",null,{"$f":"Tool!I232","v":0},0,null,null,null,null,null,"Attainment",0.15,1.1087846390807292,2.1050758627901454,3.0419919952507355]
[null,null,null,null,"Hamblen","Transitional",null,null,null,"Very High",null,{"$f":"Tool!I233","v":0},0]
[null,null,null,null,"Hamilton","Transitional"]
[null,null,null,null,"Hancock","Distressed"]
[null,null,null,null,"Hardeman","Distressed"]
[null,null,null,null,"Hardin","Transitional"]
[null,null,null,null,"Hawkins","At-Risk"]
[null,null,null,null,"Haywood","Transitional"]
[null,null,null,null,"Henderson","At-Risk"]
[null,null,null,null,"Henry","At-Risk"]
[null,null,null,null,"Hickman","Transitional"]
[null,null,null,null,"Houston","At-Risk"]
[null,null,null,null,"Humphreys","Transitional"]
[null,null,null,null,"Jackson","At-Risk"]
[null,null,null,null,"Jefferson","Transitional"]
[null,null,null,null,"Johnson","At-Risk"]
[null,null,null,null,"Knox","Competitive"]
[null,null,null,null,"Lake","Distressed"]
[null,null,null,null,"Lauderdale","At-Risk"]
[null,null,null,null,"Lawerence","At-Risk"]
[null,null,null,null,"Lewis","At-Risk"]
[null,null,null,null,"Lincoln","Transitional"]
[null,null,null,null,"Loudon","Transitional"]
[null,null,null,null,"Macon","Transitional"]
[null,null,null,null,"Madison","Transitional"]
[null,null,null,null,"Marion","Transitional"]
[null,null,null,null,"Marshall","Transitional"]
[null,null,null,null,"Maury","Transitional"]
[null,null,null,null,"McMinn","Transitional"]
[null,null,null,null,"McNairy","At-Risk"]
[null,null,null,null,"Meigs","At-Risk"]
[null,null,null,null,"Monroe","At-Risk"]
[null,null,null,null,"Montgomery","Transitional"]
[null,null,null,null,"Moore","Transitional"]
[null,null,null,null,"Morgan","Distressed"]
[null,null,null,null,"Obion","Transitional"]
[null,null,null,null,"Overton","At-Risk"]
[null,null,null,null,"Perry","Distressed"]
[null,null,null,null,"Pickett","At-Risk"]
[null,null,null,null,"Polk","Transitional"]
[null,null,null,null,"Putnam","Transitional"]
[null,null,null,null,"Rhea","At-Risk"]
[null,null,null,null,"Roane","Transitional"]
[null,null,null,null,"Robertson","Transitional"]
[null,null,null,null,"Rutherford","Transitional"]
[null,null,null,null,"Scott","Distressed"]
[null,null,null,null,"Sequathchie","At-Risk"]
[null,null,null,null,"Sevier","Transitional"]
[null,null,null,null,"Shelby","Competitive"]
[null,null,null,null,"Smith","Transitional"]
[null,null,null,null,"Stewart","Transitional"]
[null,null,null,null,"Sullivan","Transitional"]
[null,null,null,null,"Sumner","Competitive"]
[null,null,null,null,"Tipton","Transitional"]
[null,null,null,null,"Trousdale","Transitional"]
[null,null,null,null,"Unicoi","At-Risk"]
[null,null,null,null,"Union","At-Risk"]
[null,null,null,null,"Van Buren","At-Risk"]
[null,null,null,null,"Warren","At-Risk"]
[null,null,null,null,"Washington","Transitional"]
[null,null,null,null,"Wayne","At-Risk"]
[null,null,null,null,"Weakley","Transitional"]
[null,null,null,null,"White","Transitional"]
[null,null,null,null,"Williamson","Attainment"]
[null,null,null,null,"Wilson","Competitive"]

{"sheet":"Roadway","index":31,"n_rows":245,"n_cols":37,"rows_kept":245,"cut":false,"hidden":true,"merged":[[116,24,116,25],[115,13,115,25],[116,14,116,15],[116,16,116,17],[116,18,116,19],[116,20,116,21],[116,22,116,23],[97,13,97,20],[92,13,92,14],[32,12,32,18],[50,25,50,35],[52,25,52,36],[66,25,66,36],[26,12,26,13],[27,12,27,13],[29,12,29,13],[75,13,75,21],[42,12,42,20],[30,15,30,20],[52,12,52,22],[66,12,66,22],[6,1,6,3],[4,1,4,4],[5,1,5,4],[25,12,25,20],[6,12,6,14],[6,16,6,18],[206,1,206,4],[17,16,17,18],[85,1,85,4],[125,1,125,4],[165,1,165,4],[205,1,205,4],[86,1,86,4],[126,1,126,4],[166,1,166,4],[45,1,45,4],[46,1,46,4],[47,1,47,3],[182,17,188,23],[30,12,30,13],[80,13,80,18],[28,12,28,13]]}
[]
[null,null,"Project Length:",{"$f":"IF((Tool!$J$54-Tool!$J$52)>0,(Tool!$J$54-Tool!$J$52),0)","v":0}]
[]
[]
[null,"Proposed Pavement Width"]
[null,"Local"]
[null,"Segments:",null,null,{"$f":"Tool!$J$61","v":1},null,null,null,null,null,null,null,"Roadway Item Summary",null,null,null,"Shoulder Item Summary"]
[null,"Segments","Begin","End","Pavement Type","Total Pavement Width(ft)","Outside Shoulder Width (ft)","Existing Pavement Width","Replace Existing Pavement?","Length","Widen to One Side or Both?","Perimeter Length","Pay Item #","Description","UNIT",null,"Pay Item #","Description","UNIT"]
[null,{"$f":"IF(AND(E7>=1,E7<=30),1,\"\")","v":1},{"$f":"IF(Tool!D64<>\"\",IF(B9<>\"\",IF(Tool!D64=0,Tool!D64,Tool!D64-Tool!D64),\"\"),\"\")","v":""},{"$f":"IF(C9=\"\",\"\",IF((Tool!E65-Tool!D64)<(Tool!E64-Tool!D64),D2,IF(B9<>\"\",IF(Tool!E64<>\"\",IF(AND(B10=\"\",Tool!E64-Tool!D64<$D$2),$D$2,IF(B9=1,IF($D$2<(Tool!E64-Tool!$D$64),$D$2,IF(Tool!D64<>0,(Tool!E64-Tool!D64),Tool!E64)),\"\")),\"\"),\"\")))","v":""},{"$f":"IF(C9=\"\",\"\",IF(B9<>\"\",IF(Tool!F64=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E9=\"Local\",IF(Tool!I64>Tool!G64,0,IF(Tool!G64>0,Tool!G64,\"\")),\"\")","v":""},{"$f":"IF(AND(E9=Tool!$G$7,Tool!H64>0),Tool!H64,\"\")","v":""},{"$f":"IF(E9=\"Local\",IF(Tool!I64>Tool!G64,Tool!G64,IF(Tool!I64>=0,Tool!I64)),\"\")","v":""},{"$f":"IF(E9=\"Local\",Tool!J64,\"\")","v":""},{"$f":"IF(F9<>\"\",IF(OR(C9=\"\",D9=\"\"),\"\",IF(E9=\"Local\",D9-C9,\"\")),\"\")","v":""},{"$f":"IF(E9=\"Local\",Tool!O64,\"\")","v":""},{"$f":"IFERROR(IF(AND(K9=\"One Side\",OR((F9-H9)>0,G9<>\"\")),J9,IF(AND(K9=\"Both Sides\",OR((F9-H9)>0,G9<>\"\")),J9*2,0)),\"\")","v":""},"411-03.10","\"D\" mix (TON)",{"$f":"(Q27+Q29)*W55","v":0},null,"411-01","\"E\" mix (TON)",{"$f":"(S27*W69)+Q107","v":0}]
[null,{"$f":"IF(AND(E7>=2,E7<=30),2,\"\")","v":""},{"$f":"IF(B10<>\"\",IF(D9>=$D$2,\"\",IF($D$2<(Tool!E64-Tool!$D$64),\"\",IF(Tool!D65<>\"\",IF(Tool!$D$64<>0,Tool!E64-Tool!$D$64,Tool!E64),\"\"))),\"\")","v":""},{"$f":"IF(C10=\"\",\"\",IF(B11=\"\",$D$2,IF((D9-$C$9)>=$D$2,\"\",IF(Tool!E64<>\"\",IF(AND($D$2>=(Tool!E65-Tool!$D$64),(Tool!E66-Tool!$D$64)>=(Tool!E65-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E65-Tool!$D$64,Tool!E65),$D$2),\"\"))))","v":""},{"$f":"IF(C10=\"\",\"\",IF(B10<>\"\",IF(Tool!F65=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E10=\"Local\",IF(Tool!I65>Tool!G65,0,IF(Tool!G65>0,Tool!G65,\"\")),\"\")","v":""},{"$f":"IF(AND(E10=Tool!$G$7,Tool!H65>0),Tool!H65,\"\")","v":""},{"$f":"IF(E10=\"Local\",IF(Tool!I65>Tool!G65,Tool!G65,IF(Tool!I65>=0,Tool!I65)),\"\")","v":""},{"$f":"IF(E10=\"Local\",Tool!J65,\"\")","v":""},{"$f":"IF(F10<>\"\",IF(OR(C10=\"\",D10=\"\"),\"\",IF(E10=\"Local\",D10-C10,\"\")),\"\")","v":""},{"$f":"IF(E10=\"Local\",Tool!O65,\"\")","v":""},{"$f":"IFERROR(IF(AND(K10=\"One Side\",OR((F10-H10)>0,G10<>\"\")),J10,IF(AND(K10=\"Both Sides\",OR((F10-H10)>0,G10<>\"\")),J10*2,0)),\"\")","v":""},"307-02.08","\"BM-2\" mix (TON)",{"$f":"Q27*W57","v":0},null,"403-01","Tack (TON)",{"$f":"(S27*W70)+Q108","v":0}]
[null,{"$f":"IF(AND(E7>=3,E7<=30),3,\"\")","v":""},{"$f":"IF(B11<>\"\",IF(D10>=$D$2,\"\",IF($D$2<(Tool!E65-Tool!$D$64),\"\",IF(Tool!D66<>\"\",IF(Tool!$D$64<>0,Tool!E65-Tool!$D$64,Tool!E65),\"\"))),\"\")","v":""},{"$f":"IF(C11=\"\",\"\",IF(B12=\"\",$D$2,IF((D10-$C$9)>=$D$2,\"\",IF(Tool!E65<>\"\",IF(AND($D$2>=(Tool!E66-Tool!$D$64),(Tool!E67-Tool!$D$64)>=(Tool!E66-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E66-Tool!$D$64,Tool!E66),$D$2),\"\"))))","v":""},{"$f":"IF(C11=\"\",\"\",IF(B11<>\"\",IF(Tool!F66=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E11=\"Local\",IF(Tool!I66>Tool!G66,0,IF(Tool!G66>0,Tool!G66,\"\")),\"\")","v":""},{"$f":"IF(AND(E11=Tool!$G$7,Tool!H66>0),Tool!H66,\"\")","v":""},{"$f":"IF(E11=\"Local\",IF(Tool!I66>Tool!G66,Tool!G66,IF(Tool!I66>=0,Tool!I66)),\"\")","v":""},{"$f":"IF(E11=\"Local\",Tool!J66,\"\")","v":""},"",{"$f":"IF(E11=\"Local\",Tool!O66,\"\")","v":""},"","307-02.01","\"A\" mix (TON)",{"$f":"Q27*W59","v":0},null,"307-02.08","\"BM-2\" mix (TON)",{"$f":"(S27*W71)+Q109","v":0}]
[null,{"$f":"IF(AND(E7>=4,E7<=30),4,\"\")","v":""},{"$f":"IF(B12<>\"\",IF(D11>=$D$2,\"\",IF($D$2<(Tool!E66-Tool!$D$64),\"\",IF(Tool!D67<>\"\",IF(Tool!$D$64<>0,Tool!E66-Tool!$D$64,Tool!E66),\"\"))),\"\")","v":""},{"$f":"IF(C12=\"\",\"\",IF(B13=\"\",$D$2,IF((D11-$C$9)>=$D$2,\"\",IF(Tool!E66<>\"\",IF(AND($D$2>=(Tool!E67-Tool!$D$64),(Tool!E68-Tool!$D$64)>=(Tool!E67-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E67-Tool!$D$64,Tool!E67),$D$2),\"\"))))","v":""},{"$f":"IF(C12=\"\",\"\",IF(B12<>\"\",IF(Tool!F67=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E12=\"Local\",IF(Tool!I67>Tool!G67,0,IF(Tool!G67>0,Tool!G67,\"\")),\"\")","v":""},{"$f":"IF(AND(E12=Tool!$G$7,Tool!H67>0),Tool!H67,\"\")","v":""},{"$f":"IF(E12=\"Local\",IF(Tool!I67>Tool!G67,Tool!G67,IF(Tool!I67>=0,Tool!I67)),\"\")","v":""},{"$f":"IF(E12=\"Local\",Tool!J67,\"\")","v":""},"",{"$f":"IF(E12=\"Local\",Tool!O67,\"\")","v":""},"","307-02.21","GR \"A-S\" Mix (TON)",{"$f":"Q27*W61","v":0},null,"402-01","Prime Coat (TON)",{"$f":"(S27*W72)+Q110","v":0}]
[null,{"$f":"IF(AND(E7>=5,E7<=30),5,\"\")","v":""},{"$f":"IF(B13<>\"\",IF(D12>=$D$2,\"\",IF($D$2<(Tool!E67-Tool!$D$64),\"\",IF(Tool!D68<>\"\",IF(Tool!$D$64<>0,Tool!E67-Tool!$D$64,Tool!E67),\"\"))),\"\")","v":""},{"$f":"IF(C13=\"\",\"\",IF(B14=\"\",$D$2,IF((D12-$C$9)>=$D$2,\"\",IF(Tool!E67<>\"\",IF(AND($D$2>=(Tool!E68-Tool!$D$64),(Tool!E69-Tool!$D$64)>=(Tool!E68-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E68-Tool!$D$64,Tool!E68),$D$2),\"\"))))","v":""},{"$f":"IF(C13=\"\",\"\",IF(B13<>\"\",IF(Tool!F68=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E13=\"Local\",IF(Tool!I68>Tool!G68,0,IF(Tool!G68>0,Tool!G68,\"\")),\"\")","v":""},{"$f":"IF(AND(E13=Tool!$G$7,Tool!H68>0),Tool!H68,\"\")","v":""},{"$f":"IF(E13=\"Local\",IF(Tool!I68>Tool!G68,Tool!G68,IF(Tool!I68>=0,Tool!I68)),\"\")","v":""},{"$f":"IF(E13=\"Local\",Tool!J68,\"\")","v":""},{"$f":"IF(F13<>\"\",IF(OR(C13=\"\",D13=\"\"),\"\",IF(E13=\"Local\",D13-C13,\"\")),\"\")","v":""},{"$f":"IF(E13=\"Local\",Tool!O68,\"\")","v":""},"","307-02.02","GR \"A-S\" Cement (TON)",{"$f":"Q27*W62","v":0},null,"402-02","Agg. Cover (TON)",{"$f":"(S27*W73)+Q111","v":0}]
[null,{"$f":"IF(AND(E7>=6,E7<=30),6,\"\")","v":""},{"$f":"IF(B14<>\"\",IF(D13>=$D$2,\"\",IF($D$2<(Tool!E68-Tool!$D$64),\"\",IF(Tool!D69<>\"\",IF(Tool!$D$64<>0,Tool!E68-Tool!$D$64,Tool!E68),\"\"))),\"\")","v":""},{"$f":"IF(C14=\"\",\"\",IF(B15=\"\",$D$2,IF((D13-$C$9)>=$D$2,\"\",IF(Tool!E68<>\"\",IF(AND($D$2>=(Tool!E69-Tool!$D$64),(Tool!E70-Tool!$D$64)>=(Tool!E69-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E69-Tool!$D$64,Tool!E69),$D$2),\"\"))))","v":""},{"$f":"IF(C14=\"\",\"\",IF(B14<>\"\",IF(Tool!F69=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E14=\"Local\",IF(Tool!I69>Tool!G69,0,IF(Tool!G69>0,Tool!G69,\"\")),\"\")","v":""},{"$f":"IF(AND(E14=Tool!$G$7,Tool!H69>0),Tool!H69,\"\")","v":""},{"$f":"IF(E14=\"Local\",IF(Tool!I69>Tool!G69,Tool!G69,IF(Tool!I69>=0,Tool!I69)),\"\")","v":""},{"$f":"IF(E14=\"Local\",Tool!J69,\"\")","v":""},"",{"$f":"IF(E14=\"Local\",Tool!O69,\"\")","v":""},"","403-01","Tack (TON)",{"$f":"Q27*(W56+W58+W60)+Q29*(W56)","v":0},null,"303-01","Stone (Asphalt) (TON)",{"$f":"(S27*W74)+Q112","v":0}]
[null,{"$f":"IF(AND(E7>=7,E7<=30),7,\"\")","v":""},{"$f":"IF(B15<>\"\",IF(D14>=$D$2,\"\",IF($D$2<(Tool!E69-Tool!$D$64),\"\",IF(Tool!D70<>\"\",IF(Tool!$D$64<>0,Tool!E69-Tool!$D$64,Tool!E69),\"\"))),\"\")","v":""},{"$f":"IF(C15=\"\",\"\",IF(B16=\"\",$D$2,IF((D14-$C$9)>=$D$2,\"\",IF(Tool!E69<>\"\",IF(AND($D$2>=(Tool!E70-Tool!$D$64),(Tool!E71-Tool!$D$64)>=(Tool!E70-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E70-Tool!$D$64,Tool!E70),$D$2),\"\"))))","v":""},{"$f":"IF(C15=\"\",\"\",IF(B15<>\"\",IF(Tool!F70=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E15=\"Local\",IF(Tool!I70>Tool!G70,0,IF(Tool!G70>0,Tool!G70,\"\")),\"\")","v":""},{"$f":"IF(AND(E15=Tool!$G$7,Tool!H70>0),Tool!H70,\"\")","v":""},{"$f":"IF(E15=\"Local\",IF(Tool!I70>Tool!G70,Tool!G70,IF(Tool!I70>=0,Tool!I70)),\"\")","v":""},{"$f":"IF(E15=\"Local\",Tool!J70,\"\")","v":""},"",{"$f":"IF(E15=\"Local\",Tool!O70,\"\")","v":""},"","402-01","Prime Coat (TON)",{"$f":"Q27*W63","v":0},null,"501-01.03","Concrete Pvmt 10\" (SY)",{"$f":"S28/9","v":0}]
[null,{"$f":"IF(AND(E7>=8,E7<=30),8,\"\")","v":""},{"$f":"IF(B16<>\"\",IF(D15>=$D$2,\"\",IF($D$2<(Tool!E70-Tool!$D$64),\"\",IF(Tool!D71<>\"\",IF(Tool!$D$64<>0,Tool!E70-Tool!$D$64,Tool!E70),\"\"))),\"\")","v":""},{"$f":"IF(C16=\"\",\"\",IF(B17=\"\",$D$2,IF((D15-$C$9)>=$D$2,\"\",IF(Tool!E70<>\"\",IF(AND($D$2>=(Tool!E71-Tool!$D$64),(Tool!E72-Tool!$D$64)>=(Tool!E71-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E71-Tool!$D$64,Tool!E71),$D$2),\"\"))))","v":""},{"$f":"IF(C16=\"\",\"\",IF(B16<>\"\",IF(Tool!F71=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E16=\"Local\",IF(Tool!I71>Tool!G71,0,IF(Tool!G71>0,Tool!G71,\"\")),\"\")","v":""},{"$f":"IF(AND(E16=Tool!$G$7,Tool!H71>0),Tool!H71,\"\")","v":""},{"$f":"IF(E16=\"Local\",IF(Tool!I71>Tool!G71,Tool!G71,IF(Tool!I71>=0,Tool!I71)),\"\")","v":""},{"$f":"IF(E16=\"Local\",Tool!J71,\"\")","v":""},"",{"$f":"IF(E16=\"Local\",Tool!O71,\"\")","v":""},"","402-02","Agg. Cover (TON)",{"$f":"Q27*W64","v":0},null,"313-03","Treated Permeable Base",{"$f":"S15","v":0}]
[null,{"$f":"IF(AND(E7>=9,F7<=20),9,\"\")","v":""},{"$f":"IF(B17<>\"\",IF(D16>=$D$2,\"\",IF($D$2<(Tool!E71-Tool!$D$64),\"\",IF(Tool!D72<>\"\",IF(Tool!$D$64<>0,Tool!E71-Tool!$D$64,Tool!E71),\"\"))),\"\")","v":""},{"$f":"IF(C17=\"\",\"\",IF(B18=\"\",$D$2,IF((D16-$C$9)>=$D$2,\"\",IF(Tool!E71<>\"\",IF(AND($D$2>=(Tool!E72-Tool!$D$64),(Tool!E73-Tool!$D$64)>=(Tool!E72-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E72-Tool!$D$64,Tool!E72),$D$2),\"\"))))","v":""},{"$f":"IF(C17=\"\",\"\",IF(B17<>\"\",IF(Tool!F72=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E17=\"Local\",IF(Tool!I72>Tool!G72,0,IF(Tool!G72>0,Tool!G72,\"\")),\"\")","v":""},{"$f":"IF(AND(E17=Tool!$G$7,Tool!H72>0),Tool!H72,\"\")","v":""},{"$f":"IF(E17=\"Local\",IF(Tool!I72>Tool!G72,Tool!G72,IF(Tool!I72>=0,Tool!I72)),\"\")","v":""},{"$f":"IF(E17=\"Local\",Tool!J72,\"\")","v":""},"",{"$f":"IF(E17=\"Local\",Tool!O72,\"\")","v":""},"","303-01","Stone (Asphalt) (TON)",{"$f":"Q27*W65+V78+V79","v":0}]
[null,{"$f":"IF(AND(E7>=10,E7<=30),10,\"\")","v":""},{"$f":"IF(B18<>\"\",IF(D17>=$D$2,\"\",IF($D$2<(Tool!E72-Tool!$D$64),\"\",IF(Tool!D73<>\"\",IF(Tool!$D$64<>0,Tool!E72-Tool!$D$64,Tool!E72),\"\"))),\"\")","v":""},{"$f":"IF(C18=\"\",\"\",IF(B19=\"\",$D$2,IF((D17-$C$9)>=$D$2,\"\",IF(Tool!E72<>\"\",IF(AND($D$2>=(Tool!E73-Tool!$D$64),(Tool!E74-Tool!$D$64)>=(Tool!E73-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E73-Tool!$D$64,Tool!E73),$D$2),\"\"))))","v":""},{"$f":"IF(C18=\"\",\"\",IF(B18<>\"\",IF(Tool!F73=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E18=\"Local\",IF(Tool!I73>Tool!G73,0,IF(Tool!G73>0,Tool!G73,\"\")),\"\")","v":""},{"$f":"IF(AND(E18=Tool!$G$7,Tool!H73>0),Tool!H73,\"\")","v":""},{"$f":"IF(E18=\"Local\",IF(Tool!I73>Tool!G73,Tool!G73,IF(Tool!I73>=0,Tool!I73)),\"\")","v":""},{"$f":"IF(E18=\"Local\",Tool!J73,\"\")","v":""},"",{"$f":"IF(E18=\"Local\",Tool!O73,\"\")","v":""},"","501-01.03","Concrete Pvmt 10\" (SY)",{"$f":"Q28/9","v":0},null,"Concrete Islands"]
[null,{"$f":"IF(AND(E7>=11,E7<=30),11,\"\")","v":""},{"$f":"IF(B19<>\"\",IF(D18>=$D$2,\"\",IF($D$2<(Tool!E73-Tool!$D$64),\"\",IF(Tool!D74<>\"\",IF(Tool!$D$64<>0,Tool!E73-Tool!$D$64,Tool!E73),\"\"))),\"\")","v":""},{"$f":"IF(C19=\"\",\"\",IF(B20=\"\",$D$2,IF((D18-$C$9)>=$D$2,\"\",IF(Tool!E73<>\"\",IF(AND($D$2>=(Tool!E74-Tool!$D$64),(Tool!E75-Tool!$D$64)>=(Tool!E74-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E74-Tool!$D$64,Tool!E74),$D$2),\"\"))))","v":""},{"$f":"IF(C19=\"\",\"\",IF(B19<>\"\",IF(Tool!F74=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E19=\"Local\",IF(Tool!I74>Tool!G74,0,IF(Tool!G74>0,Tool!G74,\"\")),\"\")","v":""},{"$f":"IF(AND(E19=Tool!$G$7,Tool!H74>0),Tool!H74,\"\")","v":""},{"$f":"IF(E19=\"Local\",IF(Tool!I74>Tool!G74,Tool!G74,IF(Tool!I74>=0,Tool!I74)),\"\")","v":""},{"$f":"IF(E19=\"Local\",Tool!J74,\"\")","v":""},"",{"$f":"IF(E19=\"Local\",Tool!O74,\"\")","v":""},"","313-03","Treated Permeable Base",{"$f":"O18","v":0},null,"604-01.01","CLASS A CONCRETE (ROADWAY)",{"$f":"O96","v":0}]
[null,{"$f":"IF(AND(E7>=12,F7<=30),12,\"\")","v":""},{"$f":"IF(B20<>\"\",IF(D19>=$D$2,\"\",IF($D$2<(Tool!E74-Tool!$D$64),\"\",IF(Tool!D75<>\"\",IF(Tool!$D$64<>0,Tool!E74-Tool!$D$64,Tool!E74),\"\"))),\"\")","v":""},{"$f":"IF(C20=\"\",\"\",IF(B21=\"\",$D$2,IF((D19-$C$9)>=$D$2,\"\",IF(Tool!E74<>\"\",IF(AND($D$2>=(Tool!E75-Tool!$D$64),(Tool!E76-Tool!$D$64)>=(Tool!E75-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E75-Tool!$D$64,Tool!E75),$D$2),\"\"))))","v":""},{"$f":"IF(C20=\"\",\"\",IF(B20<>\"\",IF(Tool!F75=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E20=\"Local\",IF(Tool!I75>Tool!G75,0,IF(Tool!G75>0,Tool!G75,\"\")),\"\")","v":""},{"$f":"IF(AND(E20=Tool!$G$7,Tool!H75>0),Tool!H75,\"\")","v":""},{"$f":"IF(E20=\"Local\",IF(Tool!I75>Tool!G75,Tool!G75,IF(Tool!I75>=0,Tool!I75)),\"\")","v":""},{"$f":"IF(E20=\"Local\",Tool!J75,\"\")","v":""},"",{"$f":"IF(E20=\"Local\",Tool!O75,\"\")","v":""},"","71-02","Agg. Underdrains (LF)",{"$f":"O30","v":0}]
[null,{"$f":"IF(AND(E7>=13,E7<=30),13,\"\")","v":""},{"$f":"IF(B21<>\"\",IF(D20>=$D$2,\"\",IF($D$2<(Tool!E75-Tool!$D$64),\"\",IF(Tool!D76<>\"\",IF(Tool!$D$64<>0,Tool!E75-Tool!$D$64,Tool!E75),\"\"))),\"\")","v":""},{"$f":"IF(C21=\"\",\"\",IF(B22=\"\",$D$2,IF((D20-$C$9)>=$D$2,\"\",IF(Tool!E75<>\"\",IF(AND($D$2>=(Tool!E76-Tool!$D$64),(Tool!E77-Tool!$D$64)>=(Tool!E76-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E76-Tool!$D$64,Tool!E76),$D$2),\"\"))))","v":""},{"$f":"IF(C21=\"\",\"\",IF(B21<>\"\",IF(Tool!F76=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E21=\"Local\",IF(Tool!I76>Tool!G76,0,IF(Tool!G76>0,Tool!G76,\"\")),\"\")","v":""},{"$f":"IF(AND(E21=Tool!$G$7,Tool!H76>0),Tool!H76,\"\")","v":""},{"$f":"IF(E21=\"Local\",IF(Tool!I76>Tool!G76,Tool!G76,IF(Tool!I76>=0,Tool!I76)),\"\")","v":""},{"$f":"IF(E21=\"Local\",Tool!J76,\"\")","v":""},"",{"$f":"IF(E21=\"Local\",Tool!O76,\"\")","v":""},"","415-01.01","Cold Planing (SY)",{"$f":"Q29/9","v":0}]
[null,{"$f":"IF(AND(E7>=14,E7<=30),14,\"\")","v":""},{"$f":"IF(B22<>\"\",IF(D21>=$D$2,\"\",IF($D$2<(Tool!E76-Tool!$D$64),\"\",IF(Tool!D77<>\"\",IF(Tool!$D$64<>0,Tool!E76-Tool!$D$64,Tool!E76),\"\"))),\"\")","v":""},{"$f":"IF(C22=\"\",\"\",IF(B23=\"\",$D$2,IF((D21-$C$9)>=$D$2,\"\",IF(Tool!E76<>\"\",IF(AND($D$2>=(Tool!E77-Tool!$D$64),(Tool!E78-Tool!$D$64)>=(Tool!E77-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E77-Tool!$D$64,Tool!E77),$D$2),\"\"))))","v":""},{"$f":"IF(C22=\"\",\"\",IF(B22<>\"\",IF(Tool!F77=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E22=\"Local\",IF(Tool!I77>Tool!G77,0,IF(Tool!G77>0,Tool!G77,\"\")),\"\")","v":""},{"$f":"IF(AND(E22=Tool!$G$7,Tool!H77>0),Tool!H77,\"\")","v":""},{"$f":"IF(E22=\"Local\",IF(Tool!I77>Tool!G77,Tool!G77,IF(Tool!I77>=0,Tool!I77)),\"\")","v":""},{"$f":"IF(E22=\"Local\",Tool!J77,\"\")","v":""},"",{"$f":"IF(E22=\"Local\",Tool!O77,\"\")","v":""},"","202-03.01","Asphalt Removal (SY)",{"$f":"(U27/9)","v":0}]
[null,{"$f":"IF(AND(E7>=15,E7<=30),15,\"\")","v":""},{"$f":"IF(B23<>\"\",IF(D22>=$D$2,\"\",IF($D$2<(Tool!E77-Tool!$D$64),\"\",IF(Tool!D78<>\"\",IF(Tool!$D$64<>0,Tool!E77-Tool!$D$64,Tool!E77),\"\"))),\"\")","v":""},{"$f":"IF(C23=\"\",\"\",IF(B24=\"\",$D$2,IF((D22-$C$9)>=$D$2,\"\",IF(Tool!E77<>\"\",IF(AND($D$2>=(Tool!E78-Tool!$D$64),(Tool!E79-Tool!$D$64)>=(Tool!E78-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E78-Tool!$D$64,Tool!E78),$D$2),\"\"))))","v":""},{"$f":"IF(C23=\"\",\"\",IF(B23<>\"\",IF(Tool!F78=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E23=\"Local\",IF(Tool!I78>Tool!G78,0,IF(Tool!G78>0,Tool!G78,\"\")),\"\")","v":""},{"$f":"IF(AND(E23=Tool!$G$7,Tool!H78>0),Tool!H78,\"\")","v":""},{"$f":"IF(E23=\"Local\",IF(Tool!I78>Tool!G78,Tool!G78,IF(Tool!I78>=0,Tool!I78)),\"\")","v":""},{"$f":"IF(E23=\"Local\",Tool!J78,\"\")","v":""},"",{"$f":"IF(E23=\"Local\",Tool!O78,\"\")","v":""},"","202-03.02","Concrete Removal (CY)",{"$f":"(U28*10/12)/27","v":0}]
[null,{"$f":"IF(AND(E7>=16,E7<=30),16,\"\")","v":""},{"$f":"IF(B24<>\"\",IF(D23>=$D$2,\"\",IF($D$2<(Tool!E78-Tool!$D$64),\"\",IF(Tool!D79<>\"\",IF(Tool!$D$64<>0,Tool!E78-Tool!$D$64,Tool!E78),\"\"))),\"\")","v":""},{"$f":"IF(C24=\"\",\"\",IF(B25=\"\",$D$2,IF((D23-$C$9)>=$D$2,\"\",IF(Tool!E78<>\"\",IF(AND($D$2>=(Tool!E79-Tool!$D$64),(Tool!E80-Tool!$D$64)>=(Tool!E79-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E79-Tool!$D$64,Tool!E79),$D$2),\"\"))))","v":""},{"$f":"IF(C24=\"\",\"\",IF(B24<>\"\",IF(Tool!F79=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E24=\"Local\",IF(Tool!I79>Tool!G79,0,IF(Tool!G79>0,Tool!G79,\"\")),\"\")","v":""},{"$f":"IF(AND(E24=Tool!$G$7,Tool!H79>0),Tool!H79,\"\")","v":""},{"$f":"IF(E24=\"Local\",IF(Tool!I79>Tool!G79,Tool!G79,IF(Tool!I79>=0,Tool!I79)),\"\")","v":""},{"$f":"IF(E24=\"Local\",Tool!J79,\"\")","v":""},"",{"$f":"IF(E24=\"Local\",Tool!O79,\"\")","v":""},"","502-04.01","Sawing Concrete Pvmt"]
[null,{"$f":"IF(AND(E7>=17,E7<=30),17,\"\")","v":""},{"$f":"IF(B25<>\"\",IF(D24>=$D$2,\"\",IF($D$2<(Tool!E79-Tool!$D$64),\"\",IF(Tool!D80<>\"\",IF(Tool!$D$64<>0,Tool!E79-Tool!$D$64,Tool!E79),\"\"))),\"\")","v":""},{"$f":"IF(C25=\"\",\"\",IF(B26=\"\",$D$2,IF((D24-$C$9)>=$D$2,\"\",IF(Tool!E79<>\"\",IF(AND($D$2>=(Tool!E80-Tool!$D$64),(Tool!E81-Tool!$D$64)>=(Tool!E80-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E80-Tool!$D$64,Tool!E80),$D$2),\"\"))))","v":""},{"$f":"IF(C25=\"\",\"\",IF(B25<>\"\",IF(Tool!F80=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E25=\"Local\",IF(Tool!I80>Tool!G80,0,IF(Tool!G80>0,Tool!G80,\"\")),\"\")","v":""},{"$f":"IF(AND(E25=Tool!$G$7,Tool!H80>0),Tool!H80,\"\")","v":""},{"$f":"IF(E25=\"Local\",IF(Tool!I80>Tool!G80,Tool!G80,IF(Tool!I80>=0,Tool!I80)),\"\")","v":""},{"$f":"IF(E25=\"Local\",Tool!J80,\"\")","v":""},"",{"$f":"IF(E25=\"Local\",Tool!O80,\"\")","v":""},""]
[null,{"$f":"IF(AND(E7>=18,E7<=30),18,\"\")","v":""},{"$f":"IF(B26<>\"\",IF(D25>=$D$2,\"\",IF($D$2<(Tool!E80-Tool!$D$64),\"\",IF(Tool!D81<>\"\",IF(Tool!$D$64<>0,Tool!E80-Tool!$D$64,Tool!E80),\"\"))),\"\")","v":""},{"$f":"IF(C26=\"\",\"\",IF(B27=\"\",$D$2,IF((D25-$C$9)>=$D$2,\"\",IF(Tool!E80<>\"\",IF(AND($D$2>=(Tool!E81-Tool!$D$64),(Tool!E82-Tool!$D$64)>=(Tool!E81-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E81-Tool!$D$64,Tool!E81),$D$2),\"\"))))","v":""},{"$f":"IF(C26=\"\",\"\",IF(B26<>\"\",IF(Tool!F81=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E26=\"Local\",IF(Tool!I81>Tool!G81,0,IF(Tool!G81>0,Tool!G81,\"\")),\"\")","v":""},{"$f":"IF(AND(E26=Tool!$G$7,Tool!H81>0),Tool!H81,\"\")","v":""},{"$f":"IF(E26=\"Local\",IF(Tool!I81>Tool!G81,Tool!G81,IF(Tool!I81>=0,Tool!I81)),\"\")","v":""},{"$f":"IF(E26=\"Local\",Tool!J81,\"\")","v":""},"",{"$f":"IF(E26=\"Local\",Tool!O81,\"\")","v":""},"","Pavement Properties Table"]
[null,{"$f":"IF(AND(E7>=19,E7<=30),19,\"\")","v":""},{"$f":"IF(B27<>\"\",IF(D26>=$D$2,\"\",IF($D$2<(Tool!E81-Tool!$D$64),\"\",IF(Tool!D82<>\"\",IF(Tool!$D$64<>0,Tool!E81-Tool!$D$64,Tool!E81),\"\"))),\"\")","v":""},{"$f":"IF(C27=\"\",\"\",IF(B28=\"\",$D$2,IF((D26-$C$9)>=$D$2,\"\",IF(Tool!E81<>\"\",IF(AND($D$2>=(Tool!E82-Tool!$D$64),(Tool!E83-Tool!$D$64)>=(Tool!E82-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E82-Tool!$D$64,Tool!E82),$D$2),\"\"))))","v":""},{"$f":"IF(C27=\"\",\"\",IF(B27<>\"\",IF(Tool!F82=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E27=\"Local\",IF(Tool!I82>Tool!G82,0,IF(Tool!G82>0,Tool!G82,\"\")),\"\")","v":""},{"$f":"IF(AND(E27=Tool!$G$7,Tool!H82>0),Tool!H82,\"\")","v":""},{"$f":"IF(E27=\"Local\",IF(Tool!I82>Tool!G82,Tool!G82,IF(Tool!I82>=0,Tool!I82)),\"\")","v":""},{"$f":"IF(E27=\"Local\",Tool!J82,\"\")","v":""},"",{"$f":"IF(E27=\"Local\",Tool!O82,\"\")","v":""},"","Total Length Asphalt:",null,{"$f":"H43+H84+H124+H164+H204","v":0},"Req. Area Asphalt:",{"$f":"R45+R46+R47+R48+R49","v":0},"Req. Area Asphalt Shldr.",{"$f":"T50","v":0},"Area Remove Asphalt:",{"$f":"Tool!D122+L40+L81+L121+L161+L201","v":0}]
[null,{"$f":"IF(AND(E7>=20,E7<=30),20,\"\")","v":""},{"$f":"IF(B28<>\"\",IF(D27>=$D$2,\"\",IF($D$2<(Tool!E82-Tool!$D$64),\"\",IF(Tool!D83<>\"\",IF(Tool!$D$64<>0,Tool!E82-Tool!$D$64,Tool!E82),\"\"))),\"\")","v":""},{"$f":"IF(C28=\"\",\"\",IF(B29=\"\",$D$2,IF((D27-$C$9)>=$D$2,\"\",IF(Tool!E82<>\"\",IF(AND($D$2>=(Tool!E83-Tool!$D$64),(Tool!E84-Tool!$D$64)>=(Tool!E83-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E83-Tool!$D$64,Tool!E83),$D$2),\"\"))))","v":""},{"$f":"IF(C28=\"\",\"\",IF(B28<>\"\",IF(Tool!F83=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E28=\"Local\",IF(Tool!I83>Tool!G83,0,IF(Tool!G83>0,Tool!G83,\"\")),\"\")","v":""},{"$f":"IF(AND(E28=Tool!$G$7,Tool!H83>0),Tool!H83,\"\")","v":""},{"$f":"IF(E28=\"Local\",IF(Tool!I83>Tool!G83,Tool!G83,IF(Tool!I83>=0,Tool!I83)),\"\")","v":""},{"$f":"IF(E28=\"Local\",Tool!J83,\"\")","v":""},"",{"$f":"IF(E28=\"Local\",Tool!O83,\"\")","v":""},"","Total Length Concrete:",null,{"$f":"H244","v":0},"Req Area Concrete:",{"$f":"R51","v":0},"Req. Area Concrete Shldr.",{"$f":"T51","v":0},"Area Remove Concrete:",{"$f":"Tool!D123+L241","v":0}]
[null,{"$f":"IF(AND(E7>=21,E7<=30),21,\"\")","v":""},{"$f":"IF(B29<>\"\",IF(D28>=$D$2,\"\",IF($D$2<(Tool!E83-Tool!$D$64),\"\",IF(Tool!D84<>\"\",IF(Tool!$D$64<>0,Tool!E83-Tool!$D$64,Tool!E83),\"\"))),\"\")","v":""},{"$f":"IF(C29=\"\",\"\",IF(B30=\"\",$D$2,IF((D28-$C$9)>=$D$2,\"\",IF(Tool!E83<>\"\",IF(AND($D$2>=(Tool!E84-Tool!$D$64),(Tool!E85-Tool!$D$64)>=(Tool!E84-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E84-Tool!$D$64,Tool!E84),$D$2),\"\"))))","v":""},{"$f":"IF(C29=\"\",\"\",IF(B29<>\"\",IF(Tool!F84=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E29=\"Local\",IF(Tool!I84>Tool!G84,0,IF(Tool!G84>0,Tool!G84,\"\")),\"\")","v":""},{"$f":"IF(AND(E29=Tool!$G$7,Tool!H84>0),Tool!H84,\"\")","v":""},{"$f":"IF(E29=\"Local\",IF(Tool!I84>Tool!G84,Tool!G84,IF(Tool!I84>=0,Tool!I84)),\"\")","v":""},{"$f":"IF(E29=\"Local\",Tool!J84,\"\")","v":""},"",{"$f":"IF(E29=\"Local\",Tool!O84,\"\")","v":""},"","Project Length:",null,{"$f":"O27+O28","v":0},"Asphalt Retained:",{"$f":"P45+P46+P47+P48+P49","v":0},"Percent Asphalt:",{"$f":"IF((Q27+Q28)>0,Q27/(Q27+Q28),0)","v":0},"Avg. Pavement Width:"]
[null,{"$f":"IF(AND(E7>=22,E7<=30),22,\"\")","v":""},{"$f":"IF(B30<>\"\",IF(D29>=$D$2,\"\",IF($D$2<(Tool!E84-Tool!$D$64),\"\",IF(Tool!D85<>\"\",IF(Tool!$D$64<>0,Tool!E84-Tool!$D$64,Tool!E84),\"\"))),\"\")","v":""},{"$f":"IF(C30=\"\",\"\",IF(B31=\"\",$D$2,IF((D29-$C$9)>=$D$2,\"\",IF(Tool!E84<>\"\",IF(AND($D$2>=(Tool!E85-Tool!$D$64),(Tool!E86-Tool!$D$64)>=(Tool!E85-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E85-Tool!$D$64,Tool!E85),$D$2),\"\"))))","v":""},{"$f":"IF(C30=\"\",\"\",IF(B30<>\"\",IF(Tool!F85=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E30=\"Local\",IF(Tool!I85>Tool!G85,0,IF(Tool!G85>0,Tool!G85,\"\")),\"\")","v":""},{"$f":"IF(AND(E30=Tool!$G$7,Tool!H85>0),Tool!H85,\"\")","v":""},{"$f":"IF(E30=\"Local\",IF(Tool!I85>Tool!G85,Tool!G85,IF(Tool!I85>=0,Tool!I85)),\"\")","v":""},{"$f":"IF(E30=\"Local\",Tool!J85,\"\")","v":""},"",{"$f":"IF(E30=\"Local\",Tool!O85,\"\")","v":""},"","Project Perimeter:",null,{"$f":"(H44+H85+H125+H165+H205+H245)*5280","v":0},"Concrete Retained:",{"$f":"P51","v":0},"Percent Concrete:",{"$f":"IF((Q27+Q28)>0,Q28/(Q27+Q28),0)","v":0},"Avg. Shldr. Width:"]
[null,{"$f":"IF(AND(E7>=23,E7<=30),23,\"\")","v":""},{"$f":"IF(B31<>\"\",IF(D30>=$D$2,\"\",IF($D$2<(Tool!E85-Tool!$D$64),\"\",IF(Tool!D86<>\"\",IF(Tool!$D$64<>0,Tool!E85-Tool!$D$64,Tool!E85),\"\"))),\"\")","v":""},{"$f":"IF(C31=\"\",\"\",IF(B32=\"\",$D$2,IF((D30-$C$9)>=$D$2,\"\",IF(Tool!E85<>\"\",IF(AND($D$2>=(Tool!E86-Tool!$D$64),(Tool!E87-Tool!$D$64)>=(Tool!E86-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E86-Tool!$D$64,Tool!E86),$D$2),\"\"))))","v":""},{"$f":"IF(C31=\"\",\"\",IF(B31<>\"\",IF(Tool!F86=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E31=\"Local\",IF(Tool!I86>Tool!G86,0,IF(Tool!G86>0,Tool!G86,\"\")),\"\")","v":""},{"$f":"IF(AND(E31=Tool!$G$7,Tool!H86>0),Tool!H86,\"\")","v":""},{"$f":"IF(E31=\"Local\",IF(Tool!I86>Tool!G86,Tool!G86,IF(Tool!I86>=0,Tool!I86)),\"\")","v":""},{"$f":"IF(E31=\"Local\",Tool!J86,\"\")","v":""},"",{"$f":"IF(E31=\"Local\",Tool!O86,\"\")","v":""},"","Total Required Road Width:",null,{"$f":"IF(O29>0,((H40+H41)*H43+(H81+H82)*H84+(H121+H122)*H124+(H161+H162)*H164+(H201+H202)*H204+(H241+H242)*H244)/O29,0)","v":0}]
[null,{"$f":"IF(AND(E7>=24,E7<=30),24,\"\")","v":""},{"$f":"IF(B32<>\"\",IF(D31>=$D$2,\"\",IF($D$2<(Tool!E86-Tool!$D$64),\"\",IF(Tool!D87<>\"\",IF(Tool!$D$64<>0,Tool!E86-Tool!$D$64,Tool!E86),\"\"))),\"\")","v":""},{"$f":"IF(C32=\"\",\"\",IF(B33=\"\",$D$2,IF((D31-$C$9)>=$D$2,\"\",IF(Tool!E86<>\"\",IF(AND($D$2>=(Tool!E87-Tool!$D$64),(Tool!E88-Tool!$D$64)>=(Tool!E87-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E87-Tool!$D$64,Tool!E87),$D$2),\"\"))))","v":""},{"$f":"IF(C32=\"\",\"\",IF(B32<>\"\",IF(Tool!F87=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E32=\"Local\",IF(Tool!I87>Tool!G87,0,IF(Tool!G87>0,Tool!G87,\"\")),\"\")","v":""},{"$f":"IF(AND(E32=Tool!$G$7,Tool!H87>0),Tool!H87,\"\")","v":""},{"$f":"IF(E32=\"Local\",IF(Tool!I87>Tool!G87,Tool!G87,IF(Tool!I87>=0,Tool!I87)),\"\")","v":""},{"$f":"IF(E32=\"Local\",Tool!J87,\"\")","v":""},"",{"$f":"IF(E32=\"Local\",Tool!O87,\"\")","v":""},""]
[null,{"$f":"IF(AND(E7>=25,E7<=30),25,\"\")","v":""},{"$f":"IF(B33<>\"\",IF(D32>=$D$2,\"\",IF($D$2<(Tool!E87-Tool!$D$64),\"\",IF(Tool!D88<>\"\",IF(Tool!$D$64<>0,Tool!E87-Tool!$D$64,Tool!E87),\"\"))),\"\")","v":""},{"$f":"IF(C33=\"\",\"\",IF(B34=\"\",$D$2,IF((D32-$C$9)>=$D$2,\"\",IF(Tool!E87<>\"\",IF(AND($D$2>=(Tool!E88-Tool!$D$64),(Tool!E89-Tool!$D$64)>=(Tool!E88-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E88-Tool!$D$64,Tool!E88),$D$2),\"\"))))","v":""},{"$f":"IF(C33=\"\",\"\",IF(B33<>\"\",IF(Tool!F88=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E33=\"Local\",IF(Tool!I88>Tool!G88,0,IF(Tool!G88>0,Tool!G88,\"\")),\"\")","v":""},{"$f":"IF(AND(E33=Tool!$G$7,Tool!H88>0),Tool!H88,\"\")","v":""},{"$f":"IF(E33=\"Local\",IF(Tool!I88>Tool!G88,Tool!G88,IF(Tool!I88>=0,Tool!I88)),\"\")","v":""},{"$f":"IF(E33=\"Local\",Tool!J88,\"\")","v":""},"",{"$f":"IF(E33=\"Local\",Tool!O88,\"\")","v":""},"","Average Width Summary Table"]
[null,{"$f":"IF(AND(E7>=26,E7<=30),26,\"\")","v":""},{"$f":"IF(B34<>\"\",IF(D33>=$D$2,\"\",IF($D$2<(Tool!E88-Tool!$D$64),\"\",IF(Tool!D89<>\"\",IF(Tool!$D$64<>0,Tool!E88-Tool!$D$64,Tool!E88),\"\"))),\"\")","v":""},{"$f":"IF(C34=\"\",\"\",IF(B35=\"\",$D$2,IF((D33-$C$9)>=$D$2,\"\",IF(Tool!E88<>\"\",IF(AND($D$2>=(Tool!E89-Tool!$D$64),(Tool!E90-Tool!$D$64)>=(Tool!E89-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E89-Tool!$D$64,Tool!E89),$D$2),\"\"))))","v":""},{"$f":"IF(C34=\"\",\"\",IF(B34<>\"\",IF(Tool!F89=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E34=\"Local\",IF(Tool!I89>Tool!G89,0,IF(Tool!G89>0,Tool!G89,\"\")),\"\")","v":""},{"$f":"IF(AND(E34=Tool!$G$7,Tool!H89>0),Tool!H89,\"\")","v":""},{"$f":"IF(E34=\"Local\",IF(Tool!I89>Tool!G89,Tool!G89,IF(Tool!I89>=0,Tool!I89)),\"\")","v":""},{"$f":"IF(E34=\"Local\",Tool!J89,\"\")","v":""},"",{"$f":"IF(E34=\"Local\",Tool!O89,\"\")","v":""},"",null,"Avg. Pav. Width","Avg. Shldr. Width","Avg. Prop. Width","Length","Average Full Depth Width","Average Facility Width"]
[null,{"$f":"IF(AND(E7>=27,E7<=30),27,\"\")","v":""},{"$f":"IF(B35<>\"\",IF(D34>=$D$2,\"\",IF($D$2<(Tool!E89-Tool!$D$64),\"\",IF(Tool!D90<>\"\",IF(Tool!$D$64<>0,Tool!E89-Tool!$D$64,Tool!E89),\"\"))),\"\")","v":""},{"$f":"IF(C35=\"\",\"\",IF(B36=\"\",$D$2,IF((D34-$C$9)>=$D$2,\"\",IF(Tool!E89<>\"\",IF(AND($D$2>=(Tool!E90-Tool!$D$64),(Tool!E91-Tool!$D$64)>=(Tool!E90-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E90-Tool!$D$64,Tool!E90),$D$2),\"\"))))","v":""},{"$f":"IF(C35=\"\",\"\",IF(B35<>\"\",IF(Tool!F90=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E35=\"Local\",IF(Tool!I90>Tool!G90,0,IF(Tool!G90>0,Tool!G90,\"\")),\"\")","v":""},{"$f":"IF(AND(E35=Tool!$G$7,Tool!H90>0),Tool!H90,\"\")","v":""},{"$f":"IF(E35=\"Local\",IF(Tool!I90>Tool!G90,Tool!G90,IF(Tool!I90>=0,Tool!I90)),\"\")","v":""},{"$f":"IF(E35=\"Local\",Tool!J90,\"\")","v":""},"",{"$f":"IF(E35=\"Local\",Tool!O90,\"\")","v":""},"","Local:",{"$f":"J41","v":0},{"$f":"H41","v":0},{"$f":"IF(J41-H42>0,J41-H42,0)","v":0},{"$f":"H43","v":0},{"$f":"N35+O35","v":0},{"$f":"J42","v":0}]
[null,{"$f":"IF(AND(E7>=28,E7<=30),28,\"\")","v":""},{"$f":"IF(B36<>\"\",IF(D35>=$D$2,\"\",IF($D$2<(Tool!E90-Tool!$D$64),\"\",IF(Tool!D91<>\"\",IF(Tool!$D$64<>0,Tool!E90-Tool!$D$64,Tool!E90),\"\"))),\"\")","v":""},{"$f":"IF(C36=\"\",\"\",IF(B37=\"\",$D$2,IF((D35-$C$9)>=$D$2,\"\",IF(Tool!E90<>\"\",IF(AND($D$2>=(Tool!E91-Tool!$D$64),(Tool!E92-Tool!$D$64)>=(Tool!E91-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E91-Tool!$D$64,Tool!E91),$D$2),\"\"))))","v":""},{"$f":"IF(C36=\"\",\"\",IF(B36<>\"\",IF(Tool!F91=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E36=\"Local\",IF(Tool!I91>Tool!G91,0,IF(Tool!G91>0,Tool!G91,\"\")),\"\")","v":""},{"$f":"IF(AND(E36=Tool!$G$7,Tool!H91>0),Tool!H91,\"\")","v":""},{"$f":"IF(E36=\"Local\",IF(Tool!I91>Tool!G91,Tool!G91,IF(Tool!I91>=0,Tool!I91)),\"\")","v":""},{"$f":"IF(E36=\"Local\",Tool!J91,\"\")","v":""},"",{"$f":"IF(E36=\"Local\",Tool!O91,\"\")","v":""},"","SIA:",{"$f":"J82","v":0},{"$f":"H82","v":0},{"$f":"IF(J82-H83>0,J82-H83,0)","v":0},{"$f":"H84","v":0},0,{"$f":"J83","v":0}]
[null,{"$f":"IF(AND(E7>=29,E7<=30),29,\"\")","v":""},{"$f":"IF(B37<>\"\",IF(D36>=$D$2,\"\",IF($D$2<(Tool!E91-Tool!$D$64),\"\",IF(Tool!D92<>\"\",IF(Tool!$D$64<>0,Tool!E91-Tool!$D$64,Tool!E91),\"\"))),\"\")","v":""},{"$f":"IF(C37=\"\",\"\",IF(B38=\"\",$D$2,IF((D36-$C$9)>=$D$2,\"\",IF(Tool!E91<>\"\",IF(AND($D$2>=(Tool!E92-Tool!$D$64),(Tool!E93-Tool!$D$64)>=(Tool!E92-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E92-Tool!$D$64,Tool!E92),$D$2),\"\"))))","v":""},{"$f":"IF(C37=\"\",\"\",IF(B37<>\"\",IF(Tool!F92=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E37=\"Local\",IF(Tool!I92>Tool!G92,0,IF(Tool!G92>0,Tool!G92,\"\")),\"\")","v":""},{"$f":"IF(AND(E37=Tool!$G$7,Tool!H92>0),Tool!H92,\"\")","v":""},{"$f":"IF(E37=\"Local\",IF(Tool!I92>Tool!G92,Tool!G92,IF(Tool!I92>=0,Tool!I92)),\"\")","v":""},{"$f":"IF(E37=\"Local\",Tool!J92,\"\")","v":""},"",{"$f":"IF(E37=\"Local\",Tool!O92,\"\")","v":""},"","Collector:",{"$f":"J122","v":0},{"$f":"H122","v":0},{"$f":"IF(J122-H123>0,J122-H123,0)","v":0},{"$f":"H124","v":0},0,{"$f":"J123","v":0}]
[null,{"$f":"IF(E7=30,30,\"\")","v":""},{"$f":"IF(B38<>\"\",IF(D37>=$D$2,\"\",IF($D$2<(Tool!E92-Tool!$D$64),\"\",IF(Tool!D93<>\"\",IF(Tool!$D$64<>0,Tool!E92-Tool!$D$64,Tool!E92),\"\"))),\"\")","v":""},{"$f":"IF(C38=\"\",\"\",IF(B39=\"\",$D$2,IF((D37-$C$9)>=$D$2,\"\",IF(Tool!E92<>\"\",IF(AND($D$2>=(Tool!E93-Tool!$D$64),(Tool!E94-Tool!$D$64)>=(Tool!E93-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E93-Tool!$D$64,Tool!E93),$D$2),\"\"))))","v":""},{"$f":"IF(C38=\"\",\"\",IF(B38<>\"\",IF(Tool!F93=Tool!$G$7,\"Local\",\"\"),\"\"))","v":""},{"$f":"IF(E38=\"Local\",IF(Tool!I93>Tool!G93,0,IF(Tool!G93>0,Tool!G93,\"\")),\"\")","v":""},{"$f":"IF(AND(E38=Tool!$G$7,Tool!H93>0),Tool!H93,\"\")","v":""},{"$f":"IF(E38=\"Local\",IF(Tool!I93>Tool!G93,Tool!G93,IF(Tool!I93>=0,Tool!I93)),\"\")","v":""},{"$f":"IF(E38=\"Local\",Tool!J93,\"\")","v":""},"",{"$f":"IF(E38=\"Local\",Tool!O93,\"\")","v":""},"","Arterial:",{"$f":"J162","v":0},{"$f":"H162","v":0},{"$f":"IF(J162-H163>0,J162-H163,0)","v":0},{"$f":"H164","v":0},{"$f":"N38+O38","v":0},{"$f":"J163","v":0}]
[null,null,null,null,null,null,null,null,null,null,null,null,"Freeway:",{"$f":"J202","v":0},{"$f":"H202","v":0},{"$f":"IF(J202-H203>0,J202-H203,0)","v":0},{"$f":"H204","v":0},0,{"$f":"J203","v":0}]
[null,null,null,null,null,null,"Average Width of New Pavement:",{"$f":"IFERROR((SUMPRODUCT(F9:F38,J9:J38)/SUM(J9:J38))-(SUMPRODUCT(H9:H38,J9:J38)/SUM(J9:J38)),0)","v":0},"Average Additional Full Depth:",{"$f":"IFERROR(SUMPRODUCT(--(I9:I38=\"Yes\"),H9:H38,J9:J38)/SUM(J9:J38),0)","v":0},"Area",{"$f":"H43*J40*5280","v":0},"Concrete",{"$f":"J242","v":0},{"$f":"H242","v":0},{"$f":"IF(J242-H243>0,J242-H243,0)","v":0},{"$f":"H244","v":0},0,{"$f":"J243","v":0}]
[null,null,null,null,null,null,"Average Shoulder Width:",{"$f":"IF(SUM(J9:J38)>0,(SUMPRODUCT(G9:G38,J9:J38)/SUM(J9:J38))*2,0)","v":0},"Total Full Depth Width:",{"$f":"H40+J40","v":0},null,null,"Overall:",{"$f":"IF(SUM($Q$35:$Q$40)>0,SUMPRODUCT(N35:N40,$Q$35:$Q$40)/SUM($Q$35:$Q$40),0)","v":0},{"$f":"IF(SUM($Q$35:$Q$40)>0,SUMPRODUCT(O35:O40,$Q$35:$Q$40)/SUM($Q$35:$Q$40),0)","v":0},{"$f":"IF(SUM($Q$35:$Q$40)>0,SUMPRODUCT(P35:P40,$Q$35:$Q$40)/SUM($Q$35:$Q$40),0)","v":0},{"$f":"SUM(Q35:Q40)","v":0},{"$f":"IF(SUM($Q$35:$Q$40)>0,SUMPRODUCT(R35:R40,$Q$35:$Q$40)/SUM($Q$35:$Q$40),0)","v":0},{"$f":"IF(SUM($Q$35:$Q$40)>0,SUMPRODUCT(S35:S40,$Q$35:$Q$40)/SUM($Q$35:$Q$40),0)","v":0}]
[null,null,null,null,null,null,"Average Resurface Pavement:",{"$f":"IFERROR(SUMPRODUCT(--(I9:I38=\"No\"),H9:H38,J9:J38)/SUM(J9:J38),0)","v":0},"Average Roadway Width:",{"$f":"IFERROR(SUMPRODUCT(O119:O138,P119:P138)/SUM(P119:P138),0)","v":0}]
[null,null,null,null,null,null,"Length:",{"$f":"SUM(J9:J38)","v":0},null,null,null,null,"Proposed Area Summary Table"]
[null,null,null,null,null,null,"Perimeter Length",{"$f":"SUM(L9:L38)","v":0},null,null,null,null,null,"Area Prop. Seg.","Area Prop. Optional","Area Resurface","Area Ret. Opt.","New Pavement Area","Percent Type","Area Shoulder","Percent Type"]
[null,null,null,null,null,null,null,null,null,null,null,null,"Local:",{"$f":"J41*(5280*H43)","v":0},null,{"$f":"H42*(5280*H43)","v":0},null,{"$f":"IF((N45+O45)>0,(N45+O45),0)","v":0},{"$f":"IF(R50>0,R45/R50,0)","v":0},{"$f":"(H41*(5280*H43))","v":0},{"$f":"IF(T50>0,T45/T50,0)","v":0}]
[null,"Proposed Pavement Width",null,null,null,null,null,null,null,null,null,null,"SIA:",{"$f":"J82*(H84*5280)","v":0},null,{"$f":"H83*(H84*5280)","v":0},null,{"$f":"IF((N46+O46)>0,(N46+O46),0)","v":0},{"$f":"IF(R50>0,R46/R50,0)","v":0},{"$f":"(H82*(H84*5280))","v":0},{"$f":"IF(T50>0,T46/T50,0)","v":0}]
[null,"SIA",null,null,null,null,null,null,null,null,null,null,"Collector:",{"$f":"J122*(H124*5280)","v":0},null,{"$f":"H123*(H124*5280)","v":0},null,{"$f":"IF((N47+O47)>0,(N47+O47),0)","v":0},{"$f":"IF(R50>0,R47/R50,0)","v":0},{"$f":"(H122*(H124*5280))","v":0},{"$f":"IF(T50>0,T47/T50,0)","v":0}]
[null,"Segments:",null,null,{"$f":"Tool!$J$61","v":1},null,null,null,null,null,null,null,"Arterial:",{"$f":"J162*H164*5280","v":0},null,{"$f":"H163*H164*5280","v":0},null,{"$f":"IF((N48+O48)>0,(N48+O48),0)","v":0},{"$f":"IF(R50>0,R48/R50,0)","v":0},{"$f":"(H162*H164*5280)","v":0},{"$f":"IF(T50>0,T48/T50,0)","v":0}]
[null,"Segments","Begin","End","Pavement Type","Total Pavement Width(ft)","Outside Shoulder Width (ft)","Existing Pavement Width","Replace Existing Pavement?","Length","Widen to One Side or Both?","Perimeter Length","Freeway:",{"$f":"J202*H204*5280","v":0},null,{"$f":"H203*H204*5280","v":0},null,{"$f":"IF((N49+O49)>0,(N49+O49),0)","v":0},{"$f":"IF(R50>0,R49/R50,0)","v":0},{"$f":"(H202*H204*5280)","v":0},{"$f":"IF(T50>0,T49/T50,0)","v":0}]
[null,{"$f":"IF(AND(E48>=1,E48<=30),1,\"\")","v":1},{"$f":"IF(Tool!D64<>\"\",IF(B9<>\"\",IF(Tool!D64=0,Tool!D64,Tool!D64-Tool!D64),\"\"),\"\")","v":""},{"$f":"IF(C9=\"\",\"\",IF((Tool!E65-Tool!D64)<(Tool!E64-Tool!D64),D2,IF(B9<>\"\",IF(Tool!E64<>\"\",IF(AND(B10=\"\",Tool!E64-Tool!D64<$D$2),$D$2,IF(B9=1,IF($D$2<(Tool!E64-Tool!$D$64),$D$2,IF(Tool!D64<>0,(Tool!E64-Tool!D64),Tool!E64)),\"\")),\"\"),\"\")))","v":""},{"$f":"IF(C50=\"\",\"\",IF(B50<>\"\",IF(Tool!F64=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E50=\"SIA\",IF(Tool!I64>Tool!G64,0,IF(Tool!G64>0,Tool!G64,\"\")),\"\")","v":""},{"$f":"IF(AND(E50=Tool!$G$8,Tool!H64>0),Tool!H64,\"\")","v":""},{"$f":"IF(E50=\"SIA\",IF(Tool!I64>Tool!G64,Tool!G64,IF(Tool!I64>=0,Tool!I64)),\"\")","v":""},{"$f":"IF(E50=\"SIA\",Tool!J64,\"\")","v":""},{"$f":"IF(F50<>\"\",IF(OR(C50=\"\",D50=\"\"),\"\",IF(E50=\"SIA\",D50-C50,\"\")),\"\")","v":""},{"$f":"IF(E50=\"SIA\",Tool!O64,\"\")","v":""},{"$f":"IFERROR(IF(AND(K50=\"One Side\",OR((F50-H50)>0,G50<>\"\")),J50,IF(AND(K50=\"Both Sides\",OR((F50-H50)>0,G50<>\"\")),J50*2,0)),\"\")","v":""},"Total Area:",{"$f":"SUM(N45:N49)","v":0},null,0,null,0,0,0,0]
[null,{"$f":"IF(AND(E48>=2,E48<=30),2,\"\")","v":""},{"$f":"IF(D9>=$D$2,\"\",IF($D$2<(Tool!E64-Tool!$D$64),\"\",IF(Tool!D65<>\"\",IF(Tool!$D$64<>0,Tool!E64-Tool!$D$64,Tool!E64),\"\")))","v":""},{"$f":"IF(C10=\"\",\"\",IF(B52=\"\",$D$2,IF((D9-$C$9)>=$D$2,\"\",IF(Tool!E64<>\"\",IF(AND($D$2>=(Tool!E65-Tool!$D$64),(Tool!E66-Tool!$D$64)>=(Tool!E65-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E65-Tool!$D$64,Tool!E65),$D$2),\"\"))))","v":""},{"$f":"IF(C51=\"\",\"\",IF(B51<>\"\",IF(Tool!F65=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E51=\"SIA\",IF(Tool!I65>Tool!G65,0,IF(Tool!G65>0,Tool!G65,\"\")),\"\")","v":""},{"$f":"IF(AND(E51=Tool!$G$8,Tool!H65>0),Tool!H65,\"\")","v":""},{"$f":"IF(E51=\"SIA\",IF(Tool!I65>Tool!G65,Tool!G65,IF(Tool!I65>=0,Tool!I65)),\"\")","v":""},{"$f":"IF(E51=\"SIA\",Tool!J65,\"\")","v":""},{"$f":"IF(F51<>\"\",IF(OR(C51=\"\",D51=\"\"),\"\",IF(E51=\"SIA\",D51-C51,\"\")),\"\")","v":""},{"$f":"IF(E51=\"SIA\",Tool!O65,\"\")","v":""},{"$f":"IFERROR(IF(AND(K51=\"One Side\",OR((F51-H51)>0,G51<>\"\")),J51,IF(AND(K51=\"Both Sides\",OR((F51-H51)>0,G51<>\"\")),J51*2,0)),\"\")","v":""},"Concrete",{"$f":"J242*H244*5280","v":0},null,{"$f":"H243*H244*5280","v":0},null,{"$f":"IF(N51>0,N51,0)","v":0},null,{"$f":"H242*H244*5280","v":0},null,null,null,null,null,"Pavement Calculator"]
[null,{"$f":"IF(AND(E48>=3,E48<=30),3,\"\")","v":""},{"$f":"IF(D10>=$D$2,\"\",IF($D$2<(Tool!E65-Tool!$D$64),\"\",IF(Tool!D66<>\"\",IF(Tool!$D$64<>0,Tool!E65-Tool!$D$64,Tool!E65),\"\")))","v":""},{"$f":"IF(C11=\"\",\"\",IF(B53=\"\",$D$2,IF((D10-$C$9)>=$D$2,\"\",IF(Tool!E65<>\"\",IF(AND($D$2>=(Tool!E66-Tool!$D$64),(Tool!E67-Tool!$D$64)>=(Tool!E66-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E66-Tool!$D$64,Tool!E66),$D$2),\"\"))))","v":""},{"$f":"IF(C52=\"\",\"\",IF(B52<>\"\",IF(Tool!F66=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E52=\"SIA\",IF(Tool!I66>Tool!G66,0,IF(Tool!G66>0,Tool!G66,\"\")),\"\")","v":""},{"$f":"IF(AND(E52=Tool!$G$8,Tool!H66>0),Tool!H66,\"\")","v":""},{"$f":"IF(E52=\"SIA\",IF(Tool!I66>Tool!G66,Tool!G66,IF(Tool!I66>=0,Tool!I66)),\"\")","v":""},{"$f":"IF(E52=\"SIA\",Tool!J66,\"\")","v":""},{"$f":"IF(F52<>\"\",IF(OR(C52=\"\",D52=\"\"),\"\",IF(E52=\"SIA\",D52-C52,\"\")),\"\")","v":""},{"$f":"IF(E52=\"SIA\",Tool!O66,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Area",{"$f":"Tool!M25","v":0}]
[null,{"$f":"IF(AND(E48>=4,E48<=30),4,\"\")","v":""},{"$f":"IF(D11>=$D$2,\"\",IF($D$2<(Tool!E66-Tool!$D$64),\"\",IF(Tool!D67<>\"\",IF(Tool!$D$64<>0,Tool!E66-Tool!$D$64,Tool!E66),\"\")))","v":""},{"$f":"IF(C12=\"\",\"\",IF(B54=\"\",$D$2,IF((D11-$C$9)>=$D$2,\"\",IF(Tool!E66<>\"\",IF(AND($D$2>=(Tool!E67-Tool!$D$64),(Tool!E68-Tool!$D$64)>=(Tool!E67-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E67-Tool!$D$64,Tool!E67),$D$2),\"\"))))","v":""},{"$f":"IF(C53=\"\",\"\",IF(B53<>\"\",IF(Tool!F67=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E53=\"SIA\",IF(Tool!I67>Tool!G67,0,IF(Tool!G67>0,Tool!G67,\"\")),\"\")","v":""},{"$f":"IF(AND(E53=Tool!$G$8,Tool!H67>0),Tool!H67,\"\")","v":""},{"$f":"IF(E53=\"SIA\",IF(Tool!I67>Tool!G67,Tool!G67,IF(Tool!I67>=0,Tool!I67)),\"\")","v":""},{"$f":"IF(E53=\"SIA\",Tool!J67,\"\")","v":""},{"$f":"IF(F53<>\"\",IF(OR(C53=\"\",D53=\"\"),\"\",IF(E53=\"SIA\",D53-C53,\"\")),\"\")","v":""},{"$f":"IF(E53=\"SIA\",Tool!O67,\"\")","v":""},"","Full Depth Paving Calculations",null,null,null,null,null,null,null,null,null,null,null,null,"Full Depth Paving Calculations"]
[null,{"$f":"IF(AND(E48>=5,E48<=30),5,\"\")","v":""},{"$f":"IF(D12>=$D$2,\"\",IF($D$2<(Tool!E67-Tool!$D$64),\"\",IF(Tool!D68<>\"\",IF(Tool!$D$64<>0,Tool!E67-Tool!$D$64,Tool!E67),\"\")))","v":""},{"$f":"IF(C13=\"\",\"\",IF(B55=\"\",$D$2,IF((D12-$C$9)>=$D$2,\"\",IF(Tool!E67<>\"\",IF(AND($D$2>=(Tool!E68-Tool!$D$64),(Tool!E69-Tool!$D$64)>=(Tool!E68-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E68-Tool!$D$64,Tool!E68),$D$2),\"\"))))","v":""},{"$f":"IF(C54=\"\",\"\",IF(B54<>\"\",IF(Tool!F68=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E54=\"SIA\",IF(Tool!I68>Tool!G68,0,IF(Tool!G68>0,Tool!G68,\"\")),\"\")","v":""},{"$f":"IF(AND(E54=Tool!$G$8,Tool!H68>0),Tool!H68,\"\")","v":""},{"$f":"IF(E54=\"SIA\",IF(Tool!I68>Tool!G68,Tool!G68,IF(Tool!I68>=0,Tool!I68)),\"\")","v":""},{"$f":"IF(E54=\"SIA\",Tool!J68,\"\")","v":""},{"$f":"IF(F54<>\"\",IF(OR(C54=\"\",D54=\"\"),\"\",IF(E54=\"SIA\",D54-C54,\"\")),\"\")","v":""},{"$f":"IF(E54=\"SIA\",Tool!O68,\"\")","v":""},"","Paving","Description","Area (s.f.)","Thk (inches)","Thk. (ft.)","C.F.","S.Y.","C.Y.","C.F.","lb/ton","Tons/sf",null,null,"Paving","Description","Area (s.f.)","Thk (inches)","Thk. (ft.)","C.F.","S.Y.","C.Y.","C.F.","lb/ton","Tons/sf","Tons"]
[null,{"$f":"IF(AND(E48>=6,E48<=30),6,\"\")","v":""},{"$f":"IF(D13>=$D$2,\"\",IF($D$2<(Tool!E68-Tool!$D$64),\"\",IF(Tool!D69<>\"\",IF(Tool!$D$64<>0,Tool!E68-Tool!$D$64,Tool!E68),\"\")))","v":""},{"$f":"IF(C14=\"\",\"\",IF(B56=\"\",$D$2,IF((D13-$C$9)>=$D$2,\"\",IF(Tool!E68<>\"\",IF(AND($D$2>=(Tool!E69-Tool!$D$64),(Tool!E70-Tool!$D$64)>=(Tool!E69-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E69-Tool!$D$64,Tool!E69),$D$2),\"\"))))","v":""},{"$f":"IF(C55=\"\",\"\",IF(B55<>\"\",IF(Tool!F69=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E55=\"SIA\",IF(Tool!I69>Tool!G69,0,IF(Tool!G69>0,Tool!G69,\"\")),\"\")","v":""},{"$f":"IF(AND(E55=Tool!$G$8,Tool!H69>0),Tool!H69,\"\")","v":""},{"$f":"IF(E55=\"SIA\",IF(Tool!I69>Tool!G69,Tool!G69,IF(Tool!I69>=0,Tool!I69)),\"\")","v":""},{"$f":"IF(E55=\"SIA\",Tool!J69,\"\")","v":""},"",{"$f":"IF(E55=\"SIA\",Tool!O69,\"\")","v":""},"","411-03.10","\"D\" mix",1,1.25,{"$f":"P55/12","v":0.10416666666666667},27,null,{"$f":"(O55*Q55)/R55","v":3.8580246913580249E-3},{"$f":"(132.5*R55)/(9*Q55)","v":3816},2000,{"$f":"(115*P55)/(2000*9)","v":7.9861111111111105E-3},null,null,"411-03.10","\"D\" mix",1,{"$f":"Tool!N29","v":2},{"$f":"AC55/12","v":0.16666666666666666},27,null,{"$f":"(AB55*AD55)/AE55","v":6.1728395061728392E-3},{"$f":"(132.5*AE55)/(9*AD55)","v":2385},2000,{"$f":"(115*AC55)/(2000*9)","v":1.2777777777777779E-2},{"$f":"$AB$52*AJ55","v":0}]
[null,{"$f":"IF(AND(E48>=7,E48<=30),7,\"\")","v":""},{"$f":"IF(D14>=$D$2,\"\",IF($D$2<(Tool!E69-Tool!$D$64),\"\",IF(Tool!D70<>\"\",IF(Tool!$D$64<>0,Tool!E69-Tool!$D$64,Tool!E69),\"\")))","v":""},{"$f":"IF(C15=\"\",\"\",IF(B57=\"\",$D$2,IF((D14-$C$9)>=$D$2,\"\",IF(Tool!E69<>\"\",IF(AND($D$2>=(Tool!E70-Tool!$D$64),(Tool!E71-Tool!$D$64)>=(Tool!E70-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E70-Tool!$D$64,Tool!E70),$D$2),\"\"))))","v":""},{"$f":"IF(C56=\"\",\"\",IF(B56<>\"\",IF(Tool!F70=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E56=\"SIA\",IF(Tool!I70>Tool!G70,0,IF(Tool!G70>0,Tool!G70,\"\")),\"\")","v":""},{"$f":"IF(AND(E56=Tool!$G$8,Tool!H70>0),Tool!H70,\"\")","v":""},{"$f":"IF(E56=\"SIA\",IF(Tool!I70>Tool!G70,Tool!G70,IF(Tool!I70>=0,Tool!I70)),\"\")","v":""},{"$f":"IF(E56=\"SIA\",Tool!J70,\"\")","v":""},"",{"$f":"IF(E56=\"SIA\",Tool!O70,\"\")","v":""},"","403-01","Tack",1,null,null,9,{"$f":"O56/R56","v":0.1111111111111111},null,7.0000000000000007E-2,231,{"$f":"(S56*U56)/V56","v":3.3670033670033675E-5},null,null,"403-01","Tack",1,null,null,9,{"$f":"AB56/AE56","v":0.1111111111111111},null,7.0000000000000007E-2,231,{"$f":"(AF56*AH56)/AI56","v":3.3670033670033675E-5},{"$f":"$AB$52*AJ56","v":0}]
[null,{"$f":"IF(AND(E48>=8,E48<=30),8,\"\")","v":""},{"$f":"IF(D15>=$D$2,\"\",IF($D$2<(Tool!E70-Tool!$D$64),\"\",IF(Tool!D71<>\"\",IF(Tool!$D$64<>0,Tool!E70-Tool!$D$64,Tool!E70),\"\")))","v":""},{"$f":"IF(C16=\"\",\"\",IF(B58=\"\",$D$2,IF((D15-$C$9)>=$D$2,\"\",IF(Tool!E70<>\"\",IF(AND($D$2>=(Tool!E71-Tool!$D$64),(Tool!E72-Tool!$D$64)>=(Tool!E71-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E71-Tool!$D$64,Tool!E71),$D$2),\"\"))))","v":""},{"$f":"IF(C57=\"\",\"\",IF(B57<>\"\",IF(Tool!F71=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E57=\"SIA\",IF(Tool!I71>Tool!G71,0,IF(Tool!G71>0,Tool!G71,\"\")),\"\")","v":""},{"$f":"IF(AND(E57=Tool!$G$8,Tool!H71>0),Tool!H71,\"\")","v":""},{"$f":"IF(E57=\"SIA\",IF(Tool!I71>Tool!G71,Tool!G71,IF(Tool!I71>=0,Tool!I71)),\"\")","v":""},{"$f":"IF(E57=\"SIA\",Tool!J71,\"\")","v":""},"",{"$f":"IF(E57=\"SIA\",Tool!O71,\"\")","v":""},"","307-02.08","\"BM-2\" mix",1,2,{"$f":"P57/12","v":0.16666666666666666},27,null,{"$f":"(O57*Q57)/R57","v":6.1728395061728392E-3},{"$f":"(226*27)/(Q57*9)","v":4068},2000,{"$f":"(113*P57)/(2000*9)","v":1.2555555555555556E-2},null,null,"307-02.08","\"BM-2\" mix",1,{"$f":"Tool!N31","v":2},{"$f":"AC57/12","v":0.16666666666666666},27,null,{"$f":"(AB57*AD57)/AE57","v":6.1728395061728392E-3},{"$f":"(226*27)/(AD57*9)","v":4068},2000,{"$f":"(113*AC57)/(2000*9)","v":1.2555555555555556E-2},0]
[null,{"$f":"IF(AND(E48>=9,F48<=20),9,\"\")","v":""},{"$f":"IF(D16>=$D$2,\"\",IF($D$2<(Tool!E71-Tool!$D$64),\"\",IF(Tool!D72<>\"\",IF(Tool!$D$64<>0,Tool!E71-Tool!$D$64,Tool!E71),\"\")))","v":""},{"$f":"IF(C17=\"\",\"\",IF(B59=\"\",$D$2,IF((D16-$C$9)>=$D$2,\"\",IF(Tool!E71<>\"\",IF(AND($D$2>=(Tool!E72-Tool!$D$64),(Tool!E73-Tool!$D$64)>=(Tool!E72-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E72-Tool!$D$64,Tool!E72),$D$2),\"\"))))","v":""},{"$f":"IF(C58=\"\",\"\",IF(B58<>\"\",IF(Tool!F72=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E58=\"SIA\",IF(Tool!I72>Tool!G72,0,IF(Tool!G72>0,Tool!G72,\"\")),\"\")","v":""},{"$f":"IF(AND(E58=Tool!$G$8,Tool!H72>0),Tool!H72,\"\")","v":""},{"$f":"IF(E58=\"SIA\",IF(Tool!I72>Tool!G72,Tool!G72,IF(Tool!I72>=0,Tool!I72)),\"\")","v":""},{"$f":"IF(E58=\"SIA\",Tool!J72,\"\")","v":""},"",{"$f":"IF(E58=\"SIA\",Tool!O72,\"\")","v":""},"","403-01","Tack",1,null,null,9,{"$f":"O58/R58","v":0.1111111111111111},null,7.0000000000000007E-2,231,{"$f":"(S58*U58)/V58","v":3.3670033670033675E-5},null,null,"403-01","Tack",1,null,null,9,{"$f":"AB58/AE58","v":0.1111111111111111},null,7.0000000000000007E-2,231,{"$f":"(AF58*AH58)/AI58","v":3.3670033670033675E-5},0]
[null,{"$f":"IF(AND(E48>=10,E48<=30),10,\"\")","v":""},{"$f":"IF(D17>=$D$2,\"\",IF($D$2<(Tool!E72-Tool!$D$64),\"\",IF(Tool!D73<>\"\",IF(Tool!$D$64<>0,Tool!E72-Tool!$D$64,Tool!E72),\"\")))","v":""},{"$f":"IF(C18=\"\",\"\",IF(B60=\"\",$D$2,IF((D17-$C$9)>=$D$2,\"\",IF(Tool!E72<>\"\",IF(AND($D$2>=(Tool!E73-Tool!$D$64),(Tool!E74-Tool!$D$64)>=(Tool!E73-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E73-Tool!$D$64,Tool!E73),$D$2),\"\"))))","v":""},{"$f":"IF(C59=\"\",\"\",IF(B59<>\"\",IF(Tool!F73=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E59=\"SIA\",IF(Tool!I73>Tool!G73,0,IF(Tool!G73>0,Tool!G73,\"\")),\"\")","v":""},{"$f":"IF(AND(E59=Tool!$G$8,Tool!H73>0),Tool!H73,\"\")","v":""},{"$f":"IF(E59=\"SIA\",IF(Tool!I73>Tool!G73,Tool!G73,IF(Tool!I73>=0,Tool!I73)),\"\")","v":""},{"$f":"IF(E59=\"SIA\",Tool!J73,\"\")","v":""},"",{"$f":"IF(E59=\"SIA\",Tool!O73,\"\")","v":""},"","307-02.01","\"A\" mix",1,{"$f":"IF(S50>0,((S45*O86)+(S46*P86)+(S47*Q86)+(S48*R86)+(S49*S86))/S50,3)","v":3},{"$f":"P59/12","v":0.25},27,null,{"$f":"(O59*Q59)/R59","v":9.2592592592592587E-3},{"$f":"(345*R59)/((0.25/Q59)*0.25*9)","v":4140},2000,{"$f":"(115*P59)/(2000*9)","v":1.9166666666666665E-2},null,null,"307-02.01","\"A\" mix",1,{"$f":"Tool!N33","v":3.5},{"$f":"AC59/12","v":0.29166666666666669},27,null,{"$f":"(AB59*AD59)/AE59","v":1.080246913580247E-2},{"$f":"(345*AE59)/((0.25/AD59)*0.25*9)","v":4830.0000000000009},2000,{"$f":"(115*AC59)/(2000*9)","v":2.2361111111111109E-2},0]
[null,{"$f":"IF(AND(E48>=11,E48<=30),11,\"\")","v":""},{"$f":"IF(D18>=$D$2,\"\",IF($D$2<(Tool!E73-Tool!$D$64),\"\",IF(Tool!D74<>\"\",IF(Tool!$D$64<>0,Tool!E73-Tool!$D$64,Tool!E73),\"\")))","v":""},{"$f":"IF(C19=\"\",\"\",IF(B61=\"\",$D$2,IF((D18-$C$9)>=$D$2,\"\",IF(Tool!E73<>\"\",IF(AND($D$2>=(Tool!E74-Tool!$D$64),(Tool!E75-Tool!$D$64)>=(Tool!E74-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E74-Tool!$D$64,Tool!E74),$D$2),\"\"))))","v":""},{"$f":"IF(C60=\"\",\"\",IF(B60<>\"\",IF(Tool!F74=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E60=\"SIA\",IF(Tool!I74>Tool!G74,0,IF(Tool!G74>0,Tool!G74,\"\")),\"\")","v":""},{"$f":"IF(AND(E60=Tool!$G$8,Tool!H74>0),Tool!H74,\"\")","v":""},{"$f":"IF(E60=\"SIA\",IF(Tool!I74>Tool!G74,Tool!G74,IF(Tool!I74>=0,Tool!I74)),\"\")","v":""},{"$f":"IF(E60=\"SIA\",Tool!J74,\"\")","v":""},"",{"$f":"IF(E60=\"SIA\",Tool!O74,\"\")","v":""},"","403-01","Tack",1,null,null,9,{"$f":"O60/R60","v":0.1111111111111111},null,7.0000000000000007E-2,231,{"$f":"(S60*U60)/V60","v":3.3670033670033675E-5},null,null,"403-01","Tack",1,null,null,9,{"$f":"AB60/AE60","v":0.1111111111111111},null,7.0000000000000007E-2,231,{"$f":"(AF60*AH60)/AI60","v":3.3670033670033675E-5},0]
[null,{"$f":"IF(AND(E48>=12,F48<=30),12,\"\")","v":""},{"$f":"IF(D19>=$D$2,\"\",IF($D$2<(Tool!E74-Tool!$D$64),\"\",IF(Tool!D75<>\"\",IF(Tool!$D$64<>0,Tool!E74-Tool!$D$64,Tool!E74),\"\")))","v":""},{"$f":"IF(C20=\"\",\"\",IF(B62=\"\",$D$2,IF((D19-$C$9)>=$D$2,\"\",IF(Tool!E74<>\"\",IF(AND($D$2>=(Tool!E75-Tool!$D$64),(Tool!E76-Tool!$D$64)>=(Tool!E75-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E75-Tool!$D$64,Tool!E75),$D$2),\"\"))))","v":""},{"$f":"IF(C61=\"\",\"\",IF(B61<>\"\",IF(Tool!F75=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E61=\"SIA\",IF(Tool!I75>Tool!G75,0,IF(Tool!G75>0,Tool!G75,\"\")),\"\")","v":""},{"$f":"IF(AND(E61=Tool!$G$8,Tool!H75>0),Tool!H75,\"\")","v":""},{"$f":"IF(E61=\"SIA\",IF(Tool!I75>Tool!G75,Tool!G75,IF(Tool!I75>=0,Tool!I75)),\"\")","v":""},{"$f":"IF(E61=\"SIA\",Tool!J75,\"\")","v":""},"",{"$f":"IF(E61=\"SIA\",Tool!O75,\"\")","v":""},"","307-02.21","GR \"A-S\" Mix",1,{"$f":"IF(S50>0,((S45*O87)+(S46*P87)+(S47*Q87)+(S48*R87)+(S49*S87))/S50,3)","v":3},{"$f":"P61/12","v":0.25},27,null,{"$f":"(O61*Q61)/R61","v":9.2592592592592587E-3},{"$f":"(270*R61)/((0.25/Q61)*0.25*9)","v":3240},2000,{"$f":"((90*P61)/(2000*9))*O61","v":1.4999999999999999E-2},null,null,"307-02.03","GR \"A-S\" Mix",1,{"$f":"Tool!N35","v":3},{"$f":"AC61/12","v":0.25},27,null,{"$f":"(AB61*AD61)/AE61","v":9.2592592592592587E-3},{"$f":"(270*AE61)/((0.25/AD61)*0.25*9)","v":3240},2000,{"$f":"((90*AC61)/(2000*9))*AB61","v":1.4999999999999999E-2},0]
[null,{"$f":"IF(AND(E48>=13,E48<=30),13,\"\")","v":""},{"$f":"IF(D20>=$D$2,\"\",IF($D$2<(Tool!E75-Tool!$D$64),\"\",IF(Tool!D76<>\"\",IF(Tool!$D$64<>0,Tool!E75-Tool!$D$64,Tool!E75),\"\")))","v":""},{"$f":"IF(C21=\"\",\"\",IF(B63=\"\",$D$2,IF((D20-$C$9)>=$D$2,\"\",IF(Tool!E75<>\"\",IF(AND($D$2>=(Tool!E76-Tool!$D$64),(Tool!E77-Tool!$D$64)>=(Tool!E76-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E76-Tool!$D$64,Tool!E76),$D$2),\"\"))))","v":""},{"$f":"IF(C62=\"\",\"\",IF(B62<>\"\",IF(Tool!F76=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E62=\"SIA\",IF(Tool!I76>Tool!G76,0,IF(Tool!G76>0,Tool!G76,\"\")),\"\")","v":""},{"$f":"IF(AND(E62=Tool!$G$8,Tool!H76>0),Tool!H76,\"\")","v":""},{"$f":"IF(E62=\"SIA\",IF(Tool!I76>Tool!G76,Tool!G76,IF(Tool!I76>=0,Tool!I76)),\"\")","v":""},{"$f":"IF(E62=\"SIA\",Tool!J76,\"\")","v":""},"",{"$f":"IF(E62=\"SIA\",Tool!O76,\"\")","v":""},"","307-02.02","GR \"A-S\" Cement",0,{"$f":"IF(S50>0,((S45*O87)+(S46*P87)+(S47*Q87)+(S48*R87)+(S49*S87))/S50,3)","v":3},{"$f":"P62/12","v":0.25},27,null,{"$f":"(O62*Q62)/R62","v":0},{"$f":"(270*R62)/((0.25/Q62)*0.25*9)","v":3240},2000,{"$f":"((90*P62)/(2000*9))*O62","v":0},null,null,"307-02.02","GR \"A-S\" Cement",0,{"$f":"Tool!#REF!","v":{"$error":"#REF!"}},{"$f":"AC62/12","v":{"$error":"#REF!"}},27,null,{"$f":"(AB62*AD62)/AE62","v":{"$error":"#REF!"}},{"$f":"(270*AE62)/((0.25/AD62)*0.25*9)","v":{"$error":"#REF!"}},2000,{"$f":"((90*AC62)/(2000*9))*AB62","v":{"$error":"#REF!"}},{"$error":"#REF!"}]
[null,{"$f":"IF(AND(E48>=14,E48<=30),14,\"\")","v":""},{"$f":"IF(D21>=$D$2,\"\",IF($D$2<(Tool!E76-Tool!$D$64),\"\",IF(Tool!D77<>\"\",IF(Tool!$D$64<>0,Tool!E76-Tool!$D$64,Tool!E76),\"\")))","v":""},{"$f":"IF(C22=\"\",\"\",IF(B64=\"\",$D$2,IF((D21-$C$9)>=$D$2,\"\",IF(Tool!E76<>\"\",IF(AND($D$2>=(Tool!E77-Tool!$D$64),(Tool!E78-Tool!$D$64)>=(Tool!E77-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E77-Tool!$D$64,Tool!E77),$D$2),\"\"))))","v":""},{"$f":"IF(C63=\"\",\"\",IF(B63<>\"\",IF(Tool!F77=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E63=\"SIA\",IF(Tool!I77>Tool!G77,0,IF(Tool!G77>0,Tool!G77,\"\")),\"\")","v":""},{"$f":"IF(AND(E63=Tool!$G$8,Tool!H77>0),Tool!H77,\"\")","v":""},{"$f":"IF(E63=\"SIA\",IF(Tool!I77>Tool!G77,Tool!G77,IF(Tool!I77>=0,Tool!I77)),\"\")","v":""},{"$f":"IF(E63=\"SIA\",Tool!J77,\"\")","v":""},"",{"$f":"IF(E63=\"SIA\",Tool!O77,\"\")","v":""},"","402-01","Prime Coat",1,null,null,9,{"$f":"O63/R63","v":0.1111111111111111},null,0.32,231,{"$f":"(S63*U63)/V63","v":1.5392015392015393E-4},null,null,"402-01","Prime Coat",1,null,null,9,{"$f":"AB63/AE63","v":0.1111111111111111},null,0.32,231,{"$f":"(AF63*AH63)/AI63","v":1.5392015392015393E-4},0]
[null,{"$f":"IF(AND(E48>=15,E48<=30),15,\"\")","v":""},{"$f":"IF(D22>=$D$2,\"\",IF($D$2<(Tool!E77-Tool!$D$64),\"\",IF(Tool!D78<>\"\",IF(Tool!$D$64<>0,Tool!E77-Tool!$D$64,Tool!E77),\"\")))","v":""},{"$f":"IF(C23=\"\",\"\",IF(B65=\"\",$D$2,IF((D22-$C$9)>=$D$2,\"\",IF(Tool!E77<>\"\",IF(AND($D$2>=(Tool!E78-Tool!$D$64),(Tool!E79-Tool!$D$64)>=(Tool!E78-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E78-Tool!$D$64,Tool!E78),$D$2),\"\"))))","v":""},{"$f":"IF(C64=\"\",\"\",IF(B64<>\"\",IF(Tool!F78=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E64=\"SIA\",IF(Tool!I78>Tool!G78,0,IF(Tool!G78>0,Tool!G78,\"\")),\"\")","v":""},{"$f":"IF(AND(E64=Tool!$G$8,Tool!H78>0),Tool!H78,\"\")","v":""},{"$f":"IF(E64=\"SIA\",IF(Tool!I78>Tool!G78,Tool!G78,IF(Tool!I78>=0,Tool!I78)),\"\")","v":""},{"$f":"IF(E64=\"SIA\",Tool!J78,\"\")","v":""},"",{"$f":"IF(E64=\"SIA\",Tool!O78,\"\")","v":""},"","402-02","Agg. Cover",1,null,null,9,{"$f":"O64/R64","v":0.1111111111111111},null,10,2000,{"$f":"(S64*U64)/V64","v":5.5555555555555556E-4},null,null,"402-02","Agg. Cover",1,null,null,9,{"$f":"AB64/AE64","v":0.1111111111111111},null,10,2000,{"$f":"(AF64*AH64)/AI64","v":5.5555555555555556E-4},0]
[null,{"$f":"IF(AND(E48>=16,E48<=30),16,\"\")","v":""},{"$f":"IF(D23>=$D$2,\"\",IF($D$2<(Tool!E78-Tool!$D$64),\"\",IF(Tool!D79<>\"\",IF(Tool!$D$64<>0,Tool!E78-Tool!$D$64,Tool!E78),\"\")))","v":""},{"$f":"IF(C24=\"\",\"\",IF(B66=\"\",$D$2,IF((D23-$C$9)>=$D$2,\"\",IF(Tool!E78<>\"\",IF(AND($D$2>=(Tool!E79-Tool!$D$64),(Tool!E80-Tool!$D$64)>=(Tool!E79-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E79-Tool!$D$64,Tool!E79),$D$2),\"\"))))","v":""},{"$f":"IF(C65=\"\",\"\",IF(B65<>\"\",IF(Tool!F79=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E65=\"SIA\",IF(Tool!I79>Tool!G79,0,IF(Tool!G79>0,Tool!G79,\"\")),\"\")","v":""},{"$f":"IF(AND(E65=Tool!$G$8,Tool!H79>0),Tool!H79,\"\")","v":""},{"$f":"IF(E65=\"SIA\",IF(Tool!I79>Tool!G79,Tool!G79,IF(Tool!I79>=0,Tool!I79)),\"\")","v":""},{"$f":"IF(E65=\"SIA\",Tool!J79,\"\")","v":""},"",{"$f":"IF(E65=\"SIA\",Tool!O79,\"\")","v":""},"","303-01","Stone (Asphalt)",1,{"$f":"IF(S50>0,((S45*O88)+(S46*P88)+(S47*Q88)+(S48*R88)+(S49*S88))/S50,12)","v":12},{"$f":"P65/12","v":1},27,null,{"$f":"(O65*Q65)/27","v":3.7037037037037035E-2},2.0299999999999998,null,{"$f":"T65*U65","v":7.5185185185185174E-2},null,null,"303-01","Stone (Asphalt)",1,{"$f":"Tool!N38","v":4},{"$f":"AC65/12","v":0.33333333333333331},27,null,{"$f":"(AB65*AD65)/27","v":1.2345679012345678E-2},2.0299999999999998,null,{"$f":"AG65*AH65","v":2.5061728395061725E-2},0]
[null,{"$f":"IF(AND(E48>=17,E48<=30),17,\"\")","v":""},{"$f":"IF(D24>=$D$2,\"\",IF($D$2<(Tool!E79-Tool!$D$64),\"\",IF(Tool!D80<>\"\",IF(Tool!$D$64<>0,Tool!E79-Tool!$D$64,Tool!E79),\"\")))","v":""},{"$f":"IF(C25=\"\",\"\",IF(B67=\"\",$D$2,IF((D24-$C$9)>=$D$2,\"\",IF(Tool!E79<>\"\",IF(AND($D$2>=(Tool!E80-Tool!$D$64),(Tool!E81-Tool!$D$64)>=(Tool!E80-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E80-Tool!$D$64,Tool!E80),$D$2),\"\"))))","v":""},{"$f":"IF(C66=\"\",\"\",IF(B66<>\"\",IF(Tool!F80=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E66=\"SIA\",IF(Tool!I80>Tool!G80,0,IF(Tool!G80>0,Tool!G80,\"\")),\"\")","v":""},{"$f":"IF(AND(E66=Tool!$G$8,Tool!H80>0),Tool!H80,\"\")","v":""},{"$f":"IF(E66=\"SIA\",IF(Tool!I80>Tool!G80,Tool!G80,IF(Tool!I80>=0,Tool!I80)),\"\")","v":""},{"$f":"IF(E66=\"SIA\",Tool!J80,\"\")","v":""},"",{"$f":"IF(E66=\"SIA\",Tool!O80,\"\")","v":""},"",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Area",{"$f":"Tool!M40","v":0}]
[null,{"$f":"IF(AND(E48>=18,E48<=30),18,\"\")","v":""},{"$f":"IF(D25>=$D$2,\"\",IF($D$2<(Tool!E80-Tool!$D$64),\"\",IF(Tool!D81<>\"\",IF(Tool!$D$64<>0,Tool!E80-Tool!$D$64,Tool!E80),\"\")))","v":""},{"$f":"IF(C26=\"\",\"\",IF(B68=\"\",$D$2,IF((D25-$C$9)>=$D$2,\"\",IF(Tool!E80<>\"\",IF(AND($D$2>=(Tool!E81-Tool!$D$64),(Tool!E82-Tool!$D$64)>=(Tool!E81-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E81-Tool!$D$64,Tool!E81),$D$2),\"\"))))","v":""},{"$f":"IF(C67=\"\",\"\",IF(B67<>\"\",IF(Tool!F81=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E67=\"SIA\",IF(Tool!I81>Tool!G81,0,IF(Tool!G81>0,Tool!G81,\"\")),\"\")","v":""},{"$f":"IF(AND(E67=Tool!$G$8,Tool!H81>0),Tool!H81,\"\")","v":""},{"$f":"IF(E67=\"SIA\",IF(Tool!I81>Tool!G81,Tool!G81,IF(Tool!I81>=0,Tool!I81)),\"\")","v":""},{"$f":"IF(E67=\"SIA\",Tool!J81,\"\")","v":""},"",{"$f":"IF(E67=\"SIA\",Tool!O81,\"\")","v":""},"","Shoulder Calculations",null,null,null,null,null,null,null,null,null,null,null,null,"Shoulder Calculations"]
[null,{"$f":"IF(AND(E48>=19,E48<=30),19,\"\")","v":""},{"$f":"IF(D26>=$D$2,\"\",IF($D$2<(Tool!E81-Tool!$D$64),\"\",IF(Tool!D82<>\"\",IF(Tool!$D$64<>0,Tool!E81-Tool!$D$64,Tool!E81),\"\")))","v":""},{"$f":"IF(C27=\"\",\"\",IF(B69=\"\",$D$2,IF((D26-$C$9)>=$D$2,\"\",IF(Tool!E81<>\"\",IF(AND($D$2>=(Tool!E82-Tool!$D$64),(Tool!E83-Tool!$D$64)>=(Tool!E82-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E82-Tool!$D$64,Tool!E82),$D$2),\"\"))))","v":""},{"$f":"IF(C68=\"\",\"\",IF(B68<>\"\",IF(Tool!F82=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E68=\"SIA\",IF(Tool!I82>Tool!G82,0,IF(Tool!G82>0,Tool!G82,\"\")),\"\")","v":""},{"$f":"IF(AND(E68=Tool!$G$8,Tool!H82>0),Tool!H82,\"\")","v":""},{"$f":"IF(E68=\"SIA\",IF(Tool!I82>Tool!G82,Tool!G82,IF(Tool!I82>=0,Tool!I82)),\"\")","v":""},{"$f":"IF(E68=\"SIA\",Tool!J82,\"\")","v":""},"",{"$f":"IF(E68=\"SIA\",Tool!O82,\"\")","v":""},"","Pay Item #","Description","Area (s.f.)","Thk (inches)","Thk. (ft.)","C.F.","S.Y.","C.Y.","C.F.","lb/ton","Tons",null,null,"Pay Item #","Description","Area (s.f.)","Thk (inches)","Thk. (ft.)","C.F.","S.Y.","C.Y.","C.F.","lb/ton","Tons/sf","Tons"]
[null,{"$f":"IF(AND(E48>=20,E48<=30),20,\"\")","v":""},{"$f":"IF(D27>=$D$2,\"\",IF($D$2<(Tool!E82-Tool!$D$64),\"\",IF(Tool!D83<>\"\",IF(Tool!$D$64<>0,Tool!E82-Tool!$D$64,Tool!E82),\"\")))","v":""},{"$f":"IF(C28=\"\",\"\",IF(B70=\"\",$D$2,IF((D27-$C$9)>=$D$2,\"\",IF(Tool!E82<>\"\",IF(AND($D$2>=(Tool!E83-Tool!$D$64),(Tool!E84-Tool!$D$64)>=(Tool!E83-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E83-Tool!$D$64,Tool!E83),$D$2),\"\"))))","v":""},{"$f":"IF(C69=\"\",\"\",IF(B69<>\"\",IF(Tool!F83=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E69=\"SIA\",IF(Tool!I83>Tool!G83,0,IF(Tool!G83>0,Tool!G83,\"\")),\"\")","v":""},{"$f":"IF(AND(E69=Tool!$G$8,Tool!H83>0),Tool!H83,\"\")","v":""},{"$f":"IF(E69=\"SIA\",IF(Tool!I83>Tool!G83,Tool!G83,IF(Tool!I83>=0,Tool!I83)),\"\")","v":""},{"$f":"IF(E69=\"SIA\",Tool!J83,\"\")","v":""},"",{"$f":"IF(E69=\"SIA\",Tool!O83,\"\")","v":""},"","411-01","\"E\" mix",{"$f":"(1*U45+1*U47+1*U48+1*U49+1*U46)/1","v":0},1.5,{"$f":"P69/12","v":0.125},27,null,{"$f":"(O69*Q69)/R69","v":0},3870,2000,{"$f":"(T69*U69)/V69","v":0},null,null,"411-01","\"E\" mix",1,{"$f":"Tool!N42","v":1.5},{"$f":"AC69/12","v":0.125},27,null,{"$f":"(AB69*AD69)/AE69","v":4.6296296296296294E-3},3870,2000,{"$f":"(AG69*AH69)/AI69","v":8.958333333333332E-3},{"$f":"AJ69*$AB$66","v":0}]
[null,{"$f":"IF(AND(E48>=21,E48<=30),21,\"\")","v":""},{"$f":"IF(D28>=$D$2,\"\",IF($D$2<(Tool!E83-Tool!$D$64),\"\",IF(Tool!D84<>\"\",IF(Tool!$D$64<>0,Tool!E83-Tool!$D$64,Tool!E83),\"\")))","v":""},{"$f":"IF(C29=\"\",\"\",IF(B71=\"\",$D$2,IF((D28-$C$9)>=$D$2,\"\",IF(Tool!E83<>\"\",IF(AND($D$2>=(Tool!E84-Tool!$D$64),(Tool!E85-Tool!$D$64)>=(Tool!E84-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E84-Tool!$D$64,Tool!E84),$D$2),\"\"))))","v":""},{"$f":"IF(C70=\"\",\"\",IF(B70<>\"\",IF(Tool!F84=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E70=\"SIA\",IF(Tool!I84>Tool!G84,0,IF(Tool!G84>0,Tool!G84,\"\")),\"\")","v":""},{"$f":"IF(AND(E70=Tool!$G$8,Tool!H84>0),Tool!H84,\"\")","v":""},{"$f":"IF(E70=\"SIA\",IF(Tool!I84>Tool!G84,Tool!G84,IF(Tool!I84>=0,Tool!I84)),\"\")","v":""},{"$f":"IF(E70=\"SIA\",Tool!J84,\"\")","v":""},"",{"$f":"IF(E70=\"SIA\",Tool!O84,\"\")","v":""},"","403-01","Tack",1,null,null,9,{"$f":"O70/R70","v":0.1111111111111111},null,7.0000000000000007E-2,231,{"$f":"(S70*U70)/V70","v":3.3670033670033675E-5},null,null,"403-01","Tack",1,null,null,9,{"$f":"AB70/AE70","v":0.1111111111111111},null,7.0000000000000007E-2,231,{"$f":"(AF70*AH70)/AI70","v":3.3670033670033675E-5},{"$f":"AJ70*$AB$66","v":0}]
[null,{"$f":"IF(AND(E48>=22,E48<=30),22,\"\")","v":""},{"$f":"IF(D29>=$D$2,\"\",IF($D$2<(Tool!E84-Tool!$D$64),\"\",IF(Tool!D85<>\"\",IF(Tool!$D$64<>0,Tool!E84-Tool!$D$64,Tool!E84),\"\")))","v":""},{"$f":"IF(C30=\"\",\"\",IF(B72=\"\",$D$2,IF((D29-$C$9)>=$D$2,\"\",IF(Tool!E84<>\"\",IF(AND($D$2>=(Tool!E85-Tool!$D$64),(Tool!E86-Tool!$D$64)>=(Tool!E85-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E85-Tool!$D$64,Tool!E85),$D$2),\"\"))))","v":""},{"$f":"IF(C71=\"\",\"\",IF(B71<>\"\",IF(Tool!F85=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E71=\"SIA\",IF(Tool!I85>Tool!G85,0,IF(Tool!G85>0,Tool!G85,\"\")),\"\")","v":""},{"$f":"IF(AND(E71=Tool!$G$8,Tool!H85>0),Tool!H85,\"\")","v":""},{"$f":"IF(E71=\"SIA\",IF(Tool!I85>Tool!G85,Tool!G85,IF(Tool!I85>=0,Tool!I85)),\"\")","v":""},{"$f":"IF(E71=\"SIA\",Tool!J85,\"\")","v":""},"",{"$f":"IF(E71=\"SIA\",Tool!O85,\"\")","v":""},"","307-02.08","\"BM-2\" mix",{"$f":"U50","v":0},2,{"$f":"P71/12","v":0.16666666666666666},27,null,{"$f":"(O71*Q71)/R71","v":0},4068,2000,{"$f":"(T71*U71)/V71","v":0},null,null,"307-02.08","\"BM-2\" mix",1,{"$f":"Tool!N44","v":2},{"$f":"AC71/12","v":0.16666666666666666},27,null,{"$f":"(AB71*AD71)/AE71","v":6.1728395061728392E-3},4068,2000,{"$f":"(AG71*AH71)/AI71","v":1.2555555555555556E-2},0]
[null,{"$f":"IF(AND(E48>=23,E48<=30),23,\"\")","v":""},{"$f":"IF(D30>=$D$2,\"\",IF($D$2<(Tool!E85-Tool!$D$64),\"\",IF(Tool!D86<>\"\",IF(Tool!$D$64<>0,Tool!E85-Tool!$D$64,Tool!E85),\"\")))","v":""},{"$f":"IF(C31=\"\",\"\",IF(B73=\"\",$D$2,IF((D30-$C$9)>=$D$2,\"\",IF(Tool!E85<>\"\",IF(AND($D$2>=(Tool!E86-Tool!$D$64),(Tool!E87-Tool!$D$64)>=(Tool!E86-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E86-Tool!$D$64,Tool!E86),$D$2),\"\"))))","v":""},{"$f":"IF(C72=\"\",\"\",IF(B72<>\"\",IF(Tool!F86=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E72=\"SIA\",IF(Tool!I86>Tool!G86,0,IF(Tool!G86>0,Tool!G86,\"\")),\"\")","v":""},{"$f":"IF(AND(E72=Tool!$G$8,Tool!H86>0),Tool!H86,\"\")","v":""},{"$f":"IF(E72=\"SIA\",IF(Tool!I86>Tool!G86,Tool!G86,IF(Tool!I86>=0,Tool!I86)),\"\")","v":""},{"$f":"IF(E72=\"SIA\",Tool!J86,\"\")","v":""},"",{"$f":"IF(E72=\"SIA\",Tool!O86,\"\")","v":""},"","402-01","Prime Coat",{"$f":"(1*U45+1*U47+1*U48+1*U49+1*U46)/1","v":0},null,null,9,{"$f":"O72/R72","v":0},null,0.32,231,{"$f":"(S72*U72)/V72","v":0},null,null,"402-01","Prime Coat",1,null,null,9,{"$f":"AB72/AE72","v":0.1111111111111111},null,0.32,231,{"$f":"(AF72*AH72)/AI72","v":1.5392015392015393E-4},0]
[null,{"$f":"IF(AND(E48>=24,E48<=30),24,\"\")","v":""},{"$f":"IF(D31>=$D$2,\"\",IF($D$2<(Tool!E86-Tool!$D$64),\"\",IF(Tool!D87<>\"\",IF(Tool!$D$64<>0,Tool!E86-Tool!$D$64,Tool!E86),\"\")))","v":""},{"$f":"IF(C32=\"\",\"\",IF(B74=\"\",$D$2,IF((D31-$C$9)>=$D$2,\"\",IF(Tool!E86<>\"\",IF(AND($D$2>=(Tool!E87-Tool!$D$64),(Tool!E88-Tool!$D$64)>=(Tool!E87-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E87-Tool!$D$64,Tool!E87),$D$2),\"\"))))","v":""},{"$f":"IF(C73=\"\",\"\",IF(B73<>\"\",IF(Tool!F87=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E73=\"SIA\",IF(Tool!I87>Tool!G87,0,IF(Tool!G87>0,Tool!G87,\"\")),\"\")","v":""},{"$f":"IF(AND(E73=Tool!$G$8,Tool!H87>0),Tool!H87,\"\")","v":""},{"$f":"IF(E73=\"SIA\",IF(Tool!I87>Tool!G87,Tool!G87,IF(Tool!I87>=0,Tool!I87)),\"\")","v":""},{"$f":"IF(E73=\"SIA\",Tool!J87,\"\")","v":""},"",{"$f":"IF(E73=\"SIA\",Tool!O87,\"\")","v":""},"","402-02","Agg. Cover",{"$f":"(1*U45+1*U47+1*U48+1*U49+1*U46)/1","v":0},null,null,9,{"$f":"O73/R73","v":0},null,10,2000,{"$f":"(S73*U73)/V73","v":0},null,null,"402-02","Agg. Cover",1,null,null,9,{"$f":"AB73/AE73","v":0.1111111111111111},null,10,2000,{"$f":"(AF73*AH73)/AI73","v":5.5555555555555556E-4},0]
[null,{"$f":"IF(AND(E48>=25,E48<=30),25,\"\")","v":""},{"$f":"IF(D32>=$D$2,\"\",IF($D$2<(Tool!E87-Tool!$D$64),\"\",IF(Tool!D88<>\"\",IF(Tool!$D$64<>0,Tool!E87-Tool!$D$64,Tool!E87),\"\")))","v":""},{"$f":"IF(C33=\"\",\"\",IF(B75=\"\",$D$2,IF((D32-$C$9)>=$D$2,\"\",IF(Tool!E87<>\"\",IF(AND($D$2>=(Tool!E88-Tool!$D$64),(Tool!E89-Tool!$D$64)>=(Tool!E88-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E88-Tool!$D$64,Tool!E88),$D$2),\"\"))))","v":""},{"$f":"IF(C74=\"\",\"\",IF(B74<>\"\",IF(Tool!F88=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E74=\"SIA\",IF(Tool!I88>Tool!G88,0,IF(Tool!G88>0,Tool!G88,\"\")),\"\")","v":""},{"$f":"IF(AND(E74=Tool!$G$8,Tool!H88>0),Tool!H88,\"\")","v":""},{"$f":"IF(E74=\"SIA\",IF(Tool!I88>Tool!G88,Tool!G88,IF(Tool!I88>=0,Tool!I88)),\"\")","v":""},{"$f":"IF(E74=\"SIA\",Tool!J88,\"\")","v":""},"",{"$f":"IF(E74=\"SIA\",Tool!O88,\"\")","v":""},"","303-01","Stone (Asphalt)",1,{"$f":"IF(U50>0,((U45*O90)+(U46*P90)+(U47*Q90)+(U48*R90)+(U49*S90))/U50,20.25)","v":20.25},{"$f":"P74/12","v":1.6875},27,null,{"$f":"(O74*Q74)/27","v":6.25E-2},2.0299999999999998,null,{"$f":"T74*U74","v":0.12687499999999999},null,null,"303-01","Stone (Asphalt)",1,{"$f":"Tool!N47","v":20.25},{"$f":"AC74/12","v":1.6875},27,null,{"$f":"(AB74*AD74)/27","v":6.25E-2},2.0299999999999998,null,{"$f":"AG74*AH74","v":0.12687499999999999},0]
[null,{"$f":"IF(AND(E48>=26,E48<=30),26,\"\")","v":""},{"$f":"IF(D33>=$D$2,\"\",IF($D$2<(Tool!E88-Tool!$D$64),\"\",IF(Tool!D89<>\"\",IF(Tool!$D$64<>0,Tool!E88-Tool!$D$64,Tool!E88),\"\")))","v":""},{"$f":"IF(C34=\"\",\"\",IF(B76=\"\",$D$2,IF((D33-$C$9)>=$D$2,\"\",IF(Tool!E88<>\"\",IF(AND($D$2>=(Tool!E89-Tool!$D$64),(Tool!E90-Tool!$D$64)>=(Tool!E89-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E89-Tool!$D$64,Tool!E89),$D$2),\"\"))))","v":""},{"$f":"IF(C75=\"\",\"\",IF(B75<>\"\",IF(Tool!F89=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E75=\"SIA\",IF(Tool!I89>Tool!G89,0,IF(Tool!G89>0,Tool!G89,\"\")),\"\")","v":""},{"$f":"IF(AND(E75=Tool!$G$8,Tool!H89>0),Tool!H89,\"\")","v":""},{"$f":"IF(E75=\"SIA\",IF(Tool!I89>Tool!G89,Tool!G89,IF(Tool!I89>=0,Tool!I89)),\"\")","v":""},{"$f":"IF(E75=\"SIA\",Tool!J89,\"\")","v":""},"",{"$f":"IF(E75=\"SIA\",Tool!O89,\"\")","v":""},""]
[null,{"$f":"IF(AND(E48>=27,E48<=30),27,\"\")","v":""},{"$f":"IF(D34>=$D$2,\"\",IF($D$2<(Tool!E89-Tool!$D$64),\"\",IF(Tool!D90<>\"\",IF(Tool!$D$64<>0,Tool!E89-Tool!$D$64,Tool!E89),\"\")))","v":""},{"$f":"IF(C35=\"\",\"\",IF(B77=\"\",$D$2,IF((D34-$C$9)>=$D$2,\"\",IF(Tool!E89<>\"\",IF(AND($D$2>=(Tool!E90-Tool!$D$64),(Tool!E91-Tool!$D$64)>=(Tool!E90-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E90-Tool!$D$64,Tool!E90),$D$2),\"\"))))","v":""},{"$f":"IF(C76=\"\",\"\",IF(B76<>\"\",IF(Tool!F90=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E76=\"SIA\",IF(Tool!I90>Tool!G90,0,IF(Tool!G90>0,Tool!G90,\"\")),\"\")","v":""},{"$f":"IF(AND(E76=Tool!$G$8,Tool!H90>0),Tool!H90,\"\")","v":""},{"$f":"IF(E76=\"SIA\",IF(Tool!I90>Tool!G90,Tool!G90,IF(Tool!I90>=0,Tool!I90)),\"\")","v":""},{"$f":"IF(E76=\"SIA\",Tool!J90,\"\")","v":""},"",{"$f":"IF(E76=\"SIA\",Tool!O90,\"\")","v":""},"",null,"Aggregate Runout"]
[null,{"$f":"IF(AND(E48>=28,E48<=30),28,\"\")","v":""},{"$f":"IF(D35>=$D$2,\"\",IF($D$2<(Tool!E90-Tool!$D$64),\"\",IF(Tool!D91<>\"\",IF(Tool!$D$64<>0,Tool!E90-Tool!$D$64,Tool!E90),\"\")))","v":""},{"$f":"IF(C36=\"\",\"\",IF(B78=\"\",$D$2,IF((D35-$C$9)>=$D$2,\"\",IF(Tool!E90<>\"\",IF(AND($D$2>=(Tool!E91-Tool!$D$64),(Tool!E92-Tool!$D$64)>=(Tool!E91-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E91-Tool!$D$64,Tool!E91),$D$2),\"\"))))","v":""},{"$f":"IF(C77=\"\",\"\",IF(B77<>\"\",IF(Tool!F91=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E77=\"SIA\",IF(Tool!I91>Tool!G91,0,IF(Tool!G91>0,Tool!G91,\"\")),\"\")","v":""},{"$f":"IF(AND(E77=Tool!$G$8,Tool!H91>0),Tool!H91,\"\")","v":""},{"$f":"IF(E77=\"SIA\",IF(Tool!I91>Tool!G91,Tool!G91,IF(Tool!I91>=0,Tool!I91)),\"\")","v":""},{"$f":"IF(E77=\"SIA\",Tool!J91,\"\")","v":""},"",{"$f":"IF(E77=\"SIA\",Tool!O91,\"\")","v":""},"",null,"Pay Item #","Description","Width (ft.)","Thk (inches)","Thk. (ft.)","C.F.","C.Y.","C.F.","Tons"]
[null,{"$f":"IF(AND(E48>=29,E48<=30),29,\"\")","v":""},{"$f":"IF(D36>=$D$2,\"\",IF($D$2<(Tool!E91-Tool!$D$64),\"\",IF(Tool!D92<>\"\",IF(Tool!$D$64<>0,Tool!E91-Tool!$D$64,Tool!E91),\"\")))","v":""},{"$f":"IF(C37=\"\",\"\",IF(B79=\"\",$D$2,IF((D36-$C$9)>=$D$2,\"\",IF(Tool!E91<>\"\",IF(AND($D$2>=(Tool!E92-Tool!$D$64),(Tool!E93-Tool!$D$64)>=(Tool!E92-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E92-Tool!$D$64,Tool!E92),$D$2),\"\"))))","v":""},{"$f":"IF(C78=\"\",\"\",IF(B78<>\"\",IF(Tool!F92=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E78=\"SIA\",IF(Tool!I92>Tool!G92,0,IF(Tool!G92>0,Tool!G92,\"\")),\"\")","v":""},{"$f":"IF(AND(E78=Tool!$G$8,Tool!H92>0),Tool!H92,\"\")","v":""},{"$f":"IF(E78=\"SIA\",IF(Tool!I92>Tool!G92,Tool!G92,IF(Tool!I92>=0,Tool!I92)),\"\")","v":""},{"$f":"IF(E78=\"SIA\",Tool!J92,\"\")","v":""},"",{"$f":"IF(E78=\"SIA\",Tool!O92,\"\")","v":""},"",null,"303-01","Gravel Shoulder",{"$f":"IF(S50>0,(2*SUM(S45,S46,S47,S48,S49))/S50,2)","v":2},{"$f":"IF(U50>0,((U45*O90)+(U46*P90)+(U47*Q90)+(U48*R90)+(U49*S90))/U50,20.25)","v":20.25},{"$f":"Q78/12","v":1.6875},27,{"$f":"(P78*R78*$O$30)/S78","v":0},2.0299999999999998,{"$f":"T78*U78","v":0}]
[null,{"$f":"IF(E48=30,30,\"\")","v":""},{"$f":"IF(D37>=$D$2,\"\",IF($D$2<(Tool!E92-Tool!$D$64),\"\",IF(Tool!D93<>\"\",IF(Tool!$D$64<>0,Tool!E92-Tool!$D$64,Tool!E92),\"\")))","v":""},{"$f":"IF(C38=\"\",\"\",IF(B80=\"\",$D$2,IF((D37-$C$9)>=$D$2,\"\",IF(Tool!E92<>\"\",IF(AND($D$2>=(Tool!E93-Tool!$D$64),(Tool!E94-Tool!$D$64)>=(Tool!E93-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E93-Tool!$D$64,Tool!E93),$D$2),\"\"))))","v":""},{"$f":"IF(C79=\"\",\"\",IF(B79<>\"\",IF(Tool!F93=Tool!$G$8,\"SIA\",\"\"),\"\"))","v":""},{"$f":"IF(E79=\"SIA\",IF(Tool!I93>Tool!G93,0,IF(Tool!G93>0,Tool!G93,\"\")),\"\")","v":""},{"$f":"IF(AND(E79=Tool!$G$8,Tool!H93>0),Tool!H93,\"\")","v":""},{"$f":"IF(E79=\"SIA\",IF(Tool!I93>Tool!G93,Tool!G93,IF(Tool!I93>=0,Tool!I93)),\"\")","v":""},{"$f":"IF(E79=\"SIA\",Tool!J93,\"\")","v":""},"",{"$f":"IF(E79=\"SIA\",Tool!O93,\"\")","v":""},"",null,"303-01","6:1 Aggregate Slope",{"$f":"6*R79*0.5","v":5.0625},{"$f":"IF(U50>0,((U45*O90)+(U46*P90)+(U47*Q90)+(U48*R90)+(U49*S90))/U50,20.25)","v":20.25},{"$f":"Q79/12","v":1.6875},27,{"$f":"(P79*R79*$O$30)/S79","v":0},2.0299999999999998,{"$f":"T79*U79","v":0}]
[]
[null,null,null,null,null,null,"Average Width:",{"$f":"IFERROR((SUMPRODUCT(F50:F79,J50:J79)/SUM(J50:J79))-(SUMPRODUCT(H50:H79,J50:J79)/SUM(J50:J79)),0)","v":0},"Average Additional Full Depth:",{"$f":"IFERROR(SUMPRODUCT(--(I50:I79=\"Yes\"),H50:H79,J50:J79)/SUM(J50:J79),0)","v":0},"Area",{"$f":"H84*J81*5280","v":0},null,"Thickness Table"]
[null,null,null,null,null,null,"Average Shoulder Width:",{"$f":"IF(SUM(J50:J79)>0,(SUMPRODUCT(G50:G79,J50:J79)/SUM(J50:J79))*2,0)","v":0},"Total Full Depth Width:",{"$f":"H81+J81","v":0},null,null,null,"Item","Local (in)","SIA (in)","Collector (in)","Arterial (in)","Freeway (in)"]
[null,null,null,null,null,null,"Average Resurface Pavement:",{"$f":"IFERROR(SUMPRODUCT(--(I50:I79=\"No\"),H50:H79,J50:J79)/SUM(J50:J79),0)","v":0},"Average Roadway Width:",{"$f":"IFERROR(SUMPRODUCT(Q119:Q138,R119:R138)/SUM(R119:R138),0)","v":0},null,null,null,"D mix",1.25,1.25,1.25,1.25,1.25]
[null,null,null,null,null,null,"Length:",{"$f":"SUM(J50:J79)","v":0},null,null,null,null,null,"BM2",2,2,2,2,2]
[null,null,null,null,null,null,"Perimeter Length",{"$f":"SUM(L50:L79)","v":0},null,null,null,null,null,"BM2 (Shoulder)",0,0,0,0,2]
[null,"Proposed Pavement Width",null,null,null,null,null,null,null,null,null,null,null,"A mix",3,3,3,3.5,8]
[null,"Collector",null,null,null,null,null,null,null,null,null,null,null,"A-S mix",0,0,3,3,3.75]
[null,"Segments:",null,null,{"$f":"Tool!$J$61","v":1},null,null,null,null,null,null,null,null,"Stone (Road)",8,10,10,12,12]
[null,"Segments","Begin","End","Pavement Type","Total Pavement Width(ft)","Outside Shoulder Width (ft)","Existing Pavement Width","Replace Existing Pavement?","Length","Widen to One Side or Both?","Perimeter Length",null,"GR-E",1.5,0,1.5,1.5,1.5]
[null,{"$f":"IF(AND(E88>=1,E88<=30),1,\"\")","v":1},{"$f":"IF(Tool!D64<>\"\",IF(B9<>\"\",IF(Tool!D64=0,Tool!D64,Tool!D64-Tool!D64),\"\"),\"\")","v":""},{"$f":"IF(C9=\"\",\"\",IF((Tool!E65-Tool!D64)<(Tool!E64-Tool!D64),D2,IF(B9<>\"\",IF(Tool!E64<>\"\",IF(AND(B10=\"\",Tool!E64-Tool!D64<$D$2),$D$2,IF(B9=1,IF($D$2<(Tool!E64-Tool!$D$64),$D$2,IF(Tool!D64<>0,(Tool!E64-Tool!D64),Tool!E64)),\"\")),\"\"),\"\")))","v":""},{"$f":"IF(C90=\"\",\"\",IF(B90<>\"\",IF(Tool!F64=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E90=\"Collector\",IF(Tool!I64>Tool!G64,0,IF(Tool!G64>0,Tool!G64,\"\")),\"\")","v":""},{"$f":"IF(AND(E90=Tool!$G$9,Tool!H64>0),Tool!H64,\"\")","v":""},{"$f":"IF(E90=\"Collector\",IF(Tool!I64>Tool!G64,Tool!G64,IF(Tool!I64>=0,Tool!I64,0)),\"\")","v":""},{"$f":"IF(E90=\"Collector\",Tool!J64,\"\")","v":""},{"$f":"IF(F90<>\"\",IF(OR(C90=\"\",D90=\"\"),\"\",IF(E90=\"Collector\",D90-C90,\"\")),\"\")","v":""},{"$f":"IF(E90=\"Collector\",Tool!O64,\"\")","v":""},{"$f":"IFERROR(IF(AND(K90=\"One Side\",OR((F90-H90)>0,G90<>\"\")),J90,IF(AND(K90=\"Both Sides\",OR((F90-H90)>0,G90<>\"\")),J90*2,0)),\"\")","v":""},null,"Stone (Shldr)",12.75,16.25,17.75,20.25,25.5]
[null,{"$f":"IF(AND(E88>=2,E88<=30),2,\"\")","v":""},{"$f":"IF(D9>=$D$2,\"\",IF($D$2<(Tool!E64-Tool!$D$64),\"\",IF(Tool!D65<>\"\",IF(Tool!$D$64<>0,Tool!E64-Tool!$D$64,Tool!E64),\"\")))","v":""},{"$f":"IF(C10=\"\",\"\",IF(B92=\"\",$D$2,IF((D9-$C$9)>=$D$2,\"\",IF(Tool!E64<>\"\",IF(AND($D$2>=(Tool!E65-Tool!$D$64),(Tool!E66-Tool!$D$64)>=(Tool!E65-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E65-Tool!$D$64,Tool!E65),$D$2),\"\"))))","v":""},{"$f":"IF(C91=\"\",\"\",IF(B91<>\"\",IF(Tool!F65=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E91=\"Collector\",IF(Tool!I65>Tool!G65,0,IF(Tool!G65>0,Tool!G65,\"\")),\"\")","v":""},{"$f":"IF(AND(E91=Tool!$G$9,Tool!H65>0),Tool!H65,\"\")","v":""},{"$f":"IF(E91=\"Collector\",IF(Tool!I65>Tool!G65,Tool!G65,IF(Tool!I65>=0,Tool!I65,0)),\"\")","v":""},{"$f":"IF(E91=\"Collector\",Tool!J65,\"\")","v":""},{"$f":"IF(F91<>\"\",IF(OR(C91=\"\",D91=\"\"),\"\",IF(E91=\"Collector\",D91-C91,\"\")),\"\")","v":""},{"$f":"IF(E91=\"Collector\",Tool!O65,\"\")","v":""},{"$f":"IFERROR(IF(AND(K91=\"One Side\",OR((F91-H91)>0,G91<>\"\")),J91,IF(AND(K91=\"Both Sides\",OR((F91-H91)>0,G91<>\"\")),J91*2,0)),\"\")","v":""}]
[null,{"$f":"IF(AND(E88>=3,E88<=30),3,\"\")","v":""},{"$f":"IF(D10>=$D$2,\"\",IF($D$2<(Tool!E65-Tool!$D$64),\"\",IF(Tool!D66<>\"\",IF(Tool!$D$64<>0,Tool!E65-Tool!$D$64,Tool!E65),\"\")))","v":""},{"$f":"IF(C11=\"\",\"\",IF(B93=\"\",$D$2,IF((D10-$C$9)>=$D$2,\"\",IF(Tool!E65<>\"\",IF(AND($D$2>=(Tool!E66-Tool!$D$64),(Tool!E67-Tool!$D$64)>=(Tool!E66-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E66-Tool!$D$64,Tool!E66),$D$2),\"\"))))","v":""},{"$f":"IF(C92=\"\",\"\",IF(B92<>\"\",IF(Tool!F66=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E92=\"Collector\",IF(Tool!I66>Tool!G66,0,IF(Tool!G66>0,Tool!G66,\"\")),\"\")","v":""},{"$f":"IF(AND(E92=Tool!$G$9,Tool!H66>0),Tool!H66,\"\")","v":""},{"$f":"IF(E92=\"Collector\",IF(Tool!I66>Tool!G66,Tool!G66,IF(Tool!I66>=0,Tool!I66,0)),\"\")","v":""},{"$f":"IF(E92=\"Collector\",Tool!J66,\"\")","v":""},"",{"$f":"IF(E92=\"Collector\",Tool!O66,\"\")","v":""},""]
[null,{"$f":"IF(AND(E88>=4,E88<=30),4,\"\")","v":""},{"$f":"IF(D11>=$D$2,\"\",IF($D$2<(Tool!E66-Tool!$D$64),\"\",IF(Tool!D67<>\"\",IF(Tool!$D$64<>0,Tool!E66-Tool!$D$64,Tool!E66),\"\")))","v":""},{"$f":"IF(C12=\"\",\"\",IF(B94=\"\",$D$2,IF((D11-$C$9)>=$D$2,\"\",IF(Tool!E66<>\"\",IF(AND($D$2>=(Tool!E67-Tool!$D$64),(Tool!E68-Tool!$D$64)>=(Tool!E67-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E67-Tool!$D$64,Tool!E67),$D$2),\"\"))))","v":""},{"$f":"IF(C93=\"\",\"\",IF(B93<>\"\",IF(Tool!F67=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E93=\"Collector\",IF(Tool!I67>Tool!G67,0,IF(Tool!G67>0,Tool!G67,\"\")),\"\")","v":""},{"$f":"IF(AND(E93=Tool!$G$9,Tool!H67>0),Tool!H67,\"\")","v":""},{"$f":"IF(E93=\"Collector\",IF(Tool!I67>Tool!G67,Tool!G67,IF(Tool!I67>=0,Tool!I67,0)),\"\")","v":""},{"$f":"IF(E93=\"Collector\",Tool!J67,\"\")","v":""},"",{"$f":"IF(E93=\"Collector\",Tool!O67,\"\")","v":""},"",null,"Concrete Islands"]
[null,{"$f":"IF(AND(E88>=5,E88<=30),5,\"\")","v":""},{"$f":"IF(D12>=$D$2,\"\",IF($D$2<(Tool!E67-Tool!$D$64),\"\",IF(Tool!D68<>\"\",IF(Tool!$D$64<>0,Tool!E67-Tool!$D$64,Tool!E67),\"\")))","v":""},{"$f":"IF(C13=\"\",\"\",IF(B95=\"\",$D$2,IF((D12-$C$9)>=$D$2,\"\",IF(Tool!E67<>\"\",IF(AND($D$2>=(Tool!E68-Tool!$D$64),(Tool!E69-Tool!$D$64)>=(Tool!E68-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E68-Tool!$D$64,Tool!E68),$D$2),\"\"))))","v":""},{"$f":"IF(C94=\"\",\"\",IF(B94<>\"\",IF(Tool!F68=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E94=\"Collector\",IF(Tool!I68>Tool!G68,0,IF(Tool!G68>0,Tool!G68,\"\")),\"\")","v":""},{"$f":"IF(AND(E94=Tool!$G$9,Tool!H68>0),Tool!H68,\"\")","v":""},{"$f":"IF(E94=\"Collector\",IF(Tool!I68>Tool!G68,Tool!G68,IF(Tool!I68>=0,Tool!I68,0)),\"\")","v":""},{"$f":"IF(E94=\"Collector\",Tool!J68,\"\")","v":""},{"$f":"IF(F94<>\"\",IF(OR(C94=\"\",D94=\"\"),\"\",IF(E94=\"Collector\",D94-C94,\"\")),\"\")","v":""},{"$f":"IF(E94=\"Collector\",Tool!O68,\"\")","v":""},"",null,"Depth:",0.5]
[null,{"$f":"IF(AND(E88>=6,E88<=30),6,\"\")","v":""},{"$f":"IF(D13>=$D$2,\"\",IF($D$2<(Tool!E68-Tool!$D$64),\"\",IF(Tool!D69<>\"\",IF(Tool!$D$64<>0,Tool!E68-Tool!$D$64,Tool!E68),\"\")))","v":""},{"$f":"IF(C14=\"\",\"\",IF(B96=\"\",$D$2,IF((D13-$C$9)>=$D$2,\"\",IF(Tool!E68<>\"\",IF(AND($D$2>=(Tool!E69-Tool!$D$64),(Tool!E70-Tool!$D$64)>=(Tool!E69-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E69-Tool!$D$64,Tool!E69),$D$2),\"\"))))","v":""},{"$f":"IF(C95=\"\",\"\",IF(B95<>\"\",IF(Tool!F69=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E95=\"Collector\",IF(Tool!I69>Tool!G69,0,IF(Tool!G69>0,Tool!G69,\"\")),\"\")","v":""},{"$f":"IF(AND(E95=Tool!$G$9,Tool!H69>0),Tool!H69,\"\")","v":""},{"$f":"IF(E95=\"Collector\",IF(Tool!I69>Tool!G69,Tool!G69,IF(Tool!I69>=0,Tool!I69,0)),\"\")","v":""},{"$f":"IF(E95=\"Collector\",Tool!J69,\"\")","v":""},"",{"$f":"IF(E95=\"Collector\",Tool!O69,\"\")","v":""},"",null,"Area:",{"$f":"Tool!G122","v":0}]
[null,{"$f":"IF(AND(E88>=7,E88<=30),7,\"\")","v":""},{"$f":"IF(D14>=$D$2,\"\",IF($D$2<(Tool!E69-Tool!$D$64),\"\",IF(Tool!D70<>\"\",IF(Tool!$D$64<>0,Tool!E69-Tool!$D$64,Tool!E69),\"\")))","v":""},{"$f":"IF(C15=\"\",\"\",IF(B97=\"\",$D$2,IF((D14-$C$9)>=$D$2,\"\",IF(Tool!E69<>\"\",IF(AND($D$2>=(Tool!E70-Tool!$D$64),(Tool!E71-Tool!$D$64)>=(Tool!E70-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E70-Tool!$D$64,Tool!E70),$D$2),\"\"))))","v":""},{"$f":"IF(C96=\"\",\"\",IF(B96<>\"\",IF(Tool!F70=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E96=\"Collector\",IF(Tool!I70>Tool!G70,0,IF(Tool!G70>0,Tool!G70,\"\")),\"\")","v":""},{"$f":"IF(AND(E96=Tool!$G$9,Tool!H70>0),Tool!H70,\"\")","v":""},{"$f":"IF(E96=\"Collector\",IF(Tool!I70>Tool!G70,Tool!G70,IF(Tool!I70>=0,Tool!I70,0)),\"\")","v":""},{"$f":"IF(E96=\"Collector\",Tool!J70,\"\")","v":""},"",{"$f":"IF(E96=\"Collector\",Tool!O70,\"\")","v":""},"",null,"Volume:",{"$f":"(O94*O95)/27","v":0}]
[null,{"$f":"IF(AND(E88>=8,E88<=30),8,\"\")","v":""},{"$f":"IF(D15>=$D$2,\"\",IF($D$2<(Tool!E70-Tool!$D$64),\"\",IF(Tool!D71<>\"\",IF(Tool!$D$64<>0,Tool!E70-Tool!$D$64,Tool!E70),\"\")))","v":""},{"$f":"IF(C16=\"\",\"\",IF(B98=\"\",$D$2,IF((D15-$C$9)>=$D$2,\"\",IF(Tool!E70<>\"\",IF(AND($D$2>=(Tool!E71-Tool!$D$64),(Tool!E72-Tool!$D$64)>=(Tool!E71-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E71-Tool!$D$64,Tool!E71),$D$2),\"\"))))","v":""},{"$f":"IF(C97=\"\",\"\",IF(B97<>\"\",IF(Tool!F71=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E97=\"Collector\",IF(Tool!I71>Tool!G71,0,IF(Tool!G71>0,Tool!G71,\"\")),\"\")","v":""},{"$f":"IF(AND(E97=Tool!$G$9,Tool!H71>0),Tool!H71,\"\")","v":""},{"$f":"IF(E97=\"Collector\",IF(Tool!I71>Tool!G71,Tool!G71,IF(Tool!I71>=0,Tool!I71,0)),\"\")","v":""},{"$f":"IF(E97=\"Collector\",Tool!J71,\"\")","v":""},"",{"$f":"IF(E97=\"Collector\",Tool!O71,\"\")","v":""},""]
[null,{"$f":"IF(AND(E88>=9,F88<=20),9,\"\")","v":""},{"$f":"IF(D16>=$D$2,\"\",IF($D$2<(Tool!E71-Tool!$D$64),\"\",IF(Tool!D72<>\"\",IF(Tool!$D$64<>0,Tool!E71-Tool!$D$64,Tool!E71),\"\")))","v":""},{"$f":"IF(C17=\"\",\"\",IF(B99=\"\",$D$2,IF((D16-$C$9)>=$D$2,\"\",IF(Tool!E71<>\"\",IF(AND($D$2>=(Tool!E72-Tool!$D$64),(Tool!E73-Tool!$D$64)>=(Tool!E72-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E72-Tool!$D$64,Tool!E72),$D$2),\"\"))))","v":""},{"$f":"IF(C98=\"\",\"\",IF(B98<>\"\",IF(Tool!F72=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E98=\"Collector\",IF(Tool!I72>Tool!G72,0,IF(Tool!G72>0,Tool!G72,\"\")),\"\")","v":""},{"$f":"IF(AND(E98=Tool!$G$9,Tool!H72>0),Tool!H72,\"\")","v":""},{"$f":"IF(E98=\"Collector\",IF(Tool!I72>Tool!G72,Tool!G72,IF(Tool!I72>=0,Tool!I72,0)),\"\")","v":""},{"$f":"IF(E98=\"Collector\",Tool!J72,\"\")","v":""},"",{"$f":"IF(E98=\"Collector\",Tool!O72,\"\")","v":""},"",null,"Shared Use Path"]
[null,{"$f":"IF(AND(E88>=10,E88<=30),10,\"\")","v":""},{"$f":"IF(D17>=$D$2,\"\",IF($D$2<(Tool!E72-Tool!$D$64),\"\",IF(Tool!D73<>\"\",IF(Tool!$D$64<>0,Tool!E72-Tool!$D$64,Tool!E72),\"\")))","v":""},{"$f":"IF(C18=\"\",\"\",IF(B100=\"\",$D$2,IF((D17-$C$9)>=$D$2,\"\",IF(Tool!E72<>\"\",IF(AND($D$2>=(Tool!E73-Tool!$D$64),(Tool!E74-Tool!$D$64)>=(Tool!E73-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E73-Tool!$D$64,Tool!E73),$D$2),\"\"))))","v":""},{"$f":"IF(C99=\"\",\"\",IF(B99<>\"\",IF(Tool!F73=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E99=\"Collector\",IF(Tool!I73>Tool!G73,0,IF(Tool!G73>0,Tool!G73,\"\")),\"\")","v":""},{"$f":"IF(AND(E99=Tool!$G$9,Tool!H73>0),Tool!H73,\"\")","v":""},{"$f":"IF(E99=\"Collector\",IF(Tool!I73>Tool!G73,Tool!G73,IF(Tool!I73>=0,Tool!I73,0)),\"\")","v":""},{"$f":"IF(E99=\"Collector\",Tool!J73,\"\")","v":""},"",{"$f":"IF(E99=\"Collector\",Tool!O73,\"\")","v":""},"",null,"Terrain Type","Length (ft)","Grass Strip Width","Width (ft)","Area Grass Strip","Area Pvmt","Depth","Volume (CY)"]
[null,{"$f":"IF(AND(E88>=11,E88<=30),11,\"\")","v":""},{"$f":"IF(D18>=$D$2,\"\",IF($D$2<(Tool!E73-Tool!$D$64),\"\",IF(Tool!D74<>\"\",IF(Tool!$D$64<>0,Tool!E73-Tool!$D$64,Tool!E73),\"\")))","v":""},{"$f":"IF(C19=\"\",\"\",IF(B101=\"\",$D$2,IF((D18-$C$9)>=$D$2,\"\",IF(Tool!E73<>\"\",IF(AND($D$2>=(Tool!E74-Tool!$D$64),(Tool!E75-Tool!$D$64)>=(Tool!E74-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E74-Tool!$D$64,Tool!E74),$D$2),\"\"))))","v":""},{"$f":"IF(C100=\"\",\"\",IF(B100<>\"\",IF(Tool!F74=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E100=\"Collector\",IF(Tool!I74>Tool!G74,0,IF(Tool!G74>0,Tool!G74,\"\")),\"\")","v":""},{"$f":"IF(AND(E100=Tool!$G$9,Tool!H74>0),Tool!H74,\"\")","v":""},{"$f":"IF(E100=\"Collector\",IF(Tool!I74>Tool!G74,Tool!G74,IF(Tool!I74>=0,Tool!I74,0)),\"\")","v":""},{"$f":"IF(E100=\"Collector\",Tool!J74,\"\")","v":""},"",{"$f":"IF(E100=\"Collector\",Tool!O74,\"\")","v":""},"",null,"Flat:",{"$f":"Tool!N122*5280","v":0},{"$f":"Tool!O122","v":0},{"$f":"Tool!P122","v":0},{"$f":"O100*P100","v":0},{"$f":"O100*Q100","v":0},{"$f":"Terrain!AG25","v":3},{"$f":"((S100*T100)+(R100*(T100+2)))/27","v":0}]
[null,{"$f":"IF(AND(E88>=12,F88<=30),12,\"\")","v":""},{"$f":"IF(D19>=$D$2,\"\",IF($D$2<(Tool!E74-Tool!$D$64),\"\",IF(Tool!D75<>\"\",IF(Tool!$D$64<>0,Tool!E74-Tool!$D$64,Tool!E74),\"\")))","v":""},{"$f":"IF(C20=\"\",\"\",IF(B102=\"\",$D$2,IF((D19-$C$9)>=$D$2,\"\",IF(Tool!E74<>\"\",IF(AND($D$2>=(Tool!E75-Tool!$D$64),(Tool!E76-Tool!$D$64)>=(Tool!E75-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E75-Tool!$D$64,Tool!E75),$D$2),\"\"))))","v":""},{"$f":"IF(C101=\"\",\"\",IF(B101<>\"\",IF(Tool!F75=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E101=\"Collector\",IF(Tool!I75>Tool!G75,0,IF(Tool!G75>0,Tool!G75,\"\")),\"\")","v":""},{"$f":"IF(AND(E101=Tool!$G$9,Tool!H75>0),Tool!H75,\"\")","v":""},{"$f":"IF(E101=\"Collector\",IF(Tool!I75>Tool!G75,Tool!G75,IF(Tool!I75>=0,Tool!I75,0)),\"\")","v":""},{"$f":"IF(E101=\"Collector\",Tool!J75,\"\")","v":""},"",{"$f":"IF(E101=\"Collector\",Tool!O75,\"\")","v":""},"",null,"Rolling:",{"$f":"Tool!N123*5280","v":0},{"$f":"Tool!O123","v":0},{"$f":"Tool!P123","v":0},{"$f":"O101*P101","v":0},{"$f":"O101*Q101","v":0},{"$f":"Terrain!AG26","v":4.9804691576092077},{"$f":"((S101*T101)+(R101*(T101+2)))/27","v":0}]
[null,{"$f":"IF(AND(E88>=13,E88<=30),13,\"\")","v":""},{"$f":"IF(D20>=$D$2,\"\",IF($D$2<(Tool!E75-Tool!$D$64),\"\",IF(Tool!D76<>\"\",IF(Tool!$D$64<>0,Tool!E75-Tool!$D$64,Tool!E75),\"\")))","v":""},{"$f":"IF(C21=\"\",\"\",IF(B103=\"\",$D$2,IF((D20-$C$9)>=$D$2,\"\",IF(Tool!E75<>\"\",IF(AND($D$2>=(Tool!E76-Tool!$D$64),(Tool!E77-Tool!$D$64)>=(Tool!E76-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E76-Tool!$D$64,Tool!E76),$D$2),\"\"))))","v":""},{"$f":"IF(C102=\"\",\"\",IF(B102<>\"\",IF(Tool!F76=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E102=\"Collector\",IF(Tool!I76>Tool!G76,0,IF(Tool!G76>0,Tool!G76,\"\")),\"\")","v":""},{"$f":"IF(AND(E102=Tool!$G$9,Tool!H76>0),Tool!H76,\"\")","v":""},{"$f":"IF(E102=\"Collector\",IF(Tool!I76>Tool!G76,Tool!G76,IF(Tool!I76>=0,Tool!I76,0)),\"\")","v":""},{"$f":"IF(E102=\"Collector\",Tool!J76,\"\")","v":""},"",{"$f":"IF(E102=\"Collector\",Tool!O76,\"\")","v":""},"",null,"Mountainous",{"$f":"Tool!N124*5280","v":0},{"$f":"Tool!O124","v":0},{"$f":"Tool!P124","v":0},0,{"$f":"O102*Q102","v":0},{"$f":"Terrain!AG27","v":9},0]
[null,{"$f":"IF(AND(E88>=14,E88<=30),14,\"\")","v":""},{"$f":"IF(D21>=$D$2,\"\",IF($D$2<(Tool!E76-Tool!$D$64),\"\",IF(Tool!D77<>\"\",IF(Tool!$D$64<>0,Tool!E76-Tool!$D$64,Tool!E76),\"\")))","v":""},{"$f":"IF(C22=\"\",\"\",IF(B104=\"\",$D$2,IF((D21-$C$9)>=$D$2,\"\",IF(Tool!E76<>\"\",IF(AND($D$2>=(Tool!E77-Tool!$D$64),(Tool!E78-Tool!$D$64)>=(Tool!E77-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E77-Tool!$D$64,Tool!E77),$D$2),\"\"))))","v":""},{"$f":"IF(C103=\"\",\"\",IF(B103<>\"\",IF(Tool!F77=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E103=\"Collector\",IF(Tool!I77>Tool!G77,0,IF(Tool!G77>0,Tool!G77,\"\")),\"\")","v":""},{"$f":"IF(AND(E103=Tool!$G$9,Tool!H77>0),Tool!H77,\"\")","v":""},{"$f":"IF(E103=\"Collector\",IF(Tool!I77>Tool!G77,Tool!G77,IF(Tool!I77>=0,Tool!I77,0)),\"\")","v":""},{"$f":"IF(E103=\"Collector\",Tool!J77,\"\")","v":""},"",{"$f":"IF(E103=\"Collector\",Tool!O77,\"\")","v":""},"",null,"Heavy Mountainous:",{"$f":"Tool!N125*5280","v":0},{"$f":"Tool!O125","v":0},{"$f":"Tool!P125","v":0},0,{"$f":"O103*Q103","v":0},{"$f":"Terrain!AG28","v":16.018039252929434},0]
[null,{"$f":"IF(AND(E88>=15,E88<=30),15,\"\")","v":""},{"$f":"IF(D22>=$D$2,\"\",IF($D$2<(Tool!E77-Tool!$D$64),\"\",IF(Tool!D78<>\"\",IF(Tool!$D$64<>0,Tool!E77-Tool!$D$64,Tool!E77),\"\")))","v":""},{"$f":"IF(C23=\"\",\"\",IF(B105=\"\",$D$2,IF((D22-$C$9)>=$D$2,\"\",IF(Tool!E77<>\"\",IF(AND($D$2>=(Tool!E78-Tool!$D$64),(Tool!E79-Tool!$D$64)>=(Tool!E78-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E78-Tool!$D$64,Tool!E78),$D$2),\"\"))))","v":""},{"$f":"IF(C104=\"\",\"\",IF(B104<>\"\",IF(Tool!F78=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E104=\"Collector\",IF(Tool!I78>Tool!G78,0,IF(Tool!G78>0,Tool!G78,\"\")),\"\")","v":""},{"$f":"IF(AND(E104=Tool!$G$9,Tool!H78>0),Tool!H78,\"\")","v":""},{"$f":"IF(E104=\"Collector\",IF(Tool!I78>Tool!G78,Tool!G78,IF(Tool!I78>=0,Tool!I78,0)),\"\")","v":""},{"$f":"IF(E104=\"Collector\",Tool!J78,\"\")","v":""},"",{"$f":"IF(E104=\"Collector\",Tool!O78,\"\")","v":""},"",null,"Total:",{"$f":"SUM(O100:O103)","v":0},null,{"$f":"SUM(Q100:Q103)","v":0},0,{"$f":"O104*Q104","v":0},null,{"$f":"SUM(U100:U103)","v":0}]
[null,{"$f":"IF(AND(E88>=16,E88<=30),16,\"\")","v":""},{"$f":"IF(D23>=$D$2,\"\",IF($D$2<(Tool!E78-Tool!$D$64),\"\",IF(Tool!D79<>\"\",IF(Tool!$D$64<>0,Tool!E78-Tool!$D$64,Tool!E78),\"\")))","v":""},{"$f":"IF(C24=\"\",\"\",IF(B106=\"\",$D$2,IF((D23-$C$9)>=$D$2,\"\",IF(Tool!E78<>\"\",IF(AND($D$2>=(Tool!E79-Tool!$D$64),(Tool!E80-Tool!$D$64)>=(Tool!E79-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E79-Tool!$D$64,Tool!E79),$D$2),\"\"))))","v":""},{"$f":"IF(C105=\"\",\"\",IF(B105<>\"\",IF(Tool!F79=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E105=\"Collector\",IF(Tool!I79>Tool!G79,0,IF(Tool!G79>0,Tool!G79,\"\")),\"\")","v":""},{"$f":"IF(AND(E105=Tool!$G$9,Tool!H79>0),Tool!H79,\"\")","v":""},{"$f":"IF(E105=\"Collector\",IF(Tool!I79>Tool!G79,Tool!G79,IF(Tool!I79>=0,Tool!I79,0)),\"\")","v":""},{"$f":"IF(E105=\"Collector\",Tool!J79,\"\")","v":""},"",{"$f":"IF(E105=\"Collector\",Tool!O79,\"\")","v":""},""]
[null,{"$f":"IF(AND(E88>=17,E88<=30),17,\"\")","v":""},{"$f":"IF(D24>=$D$2,\"\",IF($D$2<(Tool!E79-Tool!$D$64),\"\",IF(Tool!D80<>\"\",IF(Tool!$D$64<>0,Tool!E79-Tool!$D$64,Tool!E79),\"\")))","v":""},{"$f":"IF(C25=\"\",\"\",IF(B107=\"\",$D$2,IF((D24-$C$9)>=$D$2,\"\",IF(Tool!E79<>\"\",IF(AND($D$2>=(Tool!E80-Tool!$D$64),(Tool!E81-Tool!$D$64)>=(Tool!E80-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E80-Tool!$D$64,Tool!E80),$D$2),\"\"))))","v":""},{"$f":"IF(C106=\"\",\"\",IF(B106<>\"\",IF(Tool!F80=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E106=\"Collector\",IF(Tool!I80>Tool!G80,0,IF(Tool!G80>0,Tool!G80,\"\")),\"\")","v":""},{"$f":"IF(AND(E106=Tool!$G$9,Tool!H80>0),Tool!H80,\"\")","v":""},{"$f":"IF(E106=\"Collector\",IF(Tool!I80>Tool!G80,Tool!G80,IF(Tool!I80>=0,Tool!I80,0)),\"\")","v":""},{"$f":"IF(E106=\"Collector\",Tool!J80,\"\")","v":""},"",{"$f":"IF(E106=\"Collector\",Tool!O80,\"\")","v":""},"",null,"Pay Item #","Description","Tons/sf","Tons"]
[null,{"$f":"IF(AND(E88>=18,E88<=30),18,\"\")","v":""},{"$f":"IF(D25>=$D$2,\"\",IF($D$2<(Tool!E80-Tool!$D$64),\"\",IF(Tool!D81<>\"\",IF(Tool!$D$64<>0,Tool!E80-Tool!$D$64,Tool!E80),\"\")))","v":""},{"$f":"IF(C26=\"\",\"\",IF(B108=\"\",$D$2,IF((D25-$C$9)>=$D$2,\"\",IF(Tool!E80<>\"\",IF(AND($D$2>=(Tool!E81-Tool!$D$64),(Tool!E82-Tool!$D$64)>=(Tool!E81-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E81-Tool!$D$64,Tool!E81),$D$2),\"\"))))","v":""},{"$f":"IF(C107=\"\",\"\",IF(B107<>\"\",IF(Tool!F81=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E107=\"Collector\",IF(Tool!I81>Tool!G81,0,IF(Tool!G81>0,Tool!G81,\"\")),\"\")","v":""},{"$f":"IF(AND(E107=Tool!$G$9,Tool!H81>0),Tool!H81,\"\")","v":""},{"$f":"IF(E107=\"Collector\",IF(Tool!I81>Tool!G81,Tool!G81,IF(Tool!I81>=0,Tool!I81,0)),\"\")","v":""},{"$f":"IF(E107=\"Collector\",Tool!J81,\"\")","v":""},"",{"$f":"IF(E107=\"Collector\",Tool!O81,\"\")","v":""},"",null,"411-01","\"E\" mix",8.958333333333332E-3,{"$f":"$S$104*P107","v":0}]
[null,{"$f":"IF(AND(E88>=19,E88<=30),19,\"\")","v":""},{"$f":"IF(D26>=$D$2,\"\",IF($D$2<(Tool!E81-Tool!$D$64),\"\",IF(Tool!D82<>\"\",IF(Tool!$D$64<>0,Tool!E81-Tool!$D$64,Tool!E81),\"\")))","v":""},{"$f":"IF(C27=\"\",\"\",IF(B109=\"\",$D$2,IF((D26-$C$9)>=$D$2,\"\",IF(Tool!E81<>\"\",IF(AND($D$2>=(Tool!E82-Tool!$D$64),(Tool!E83-Tool!$D$64)>=(Tool!E82-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E82-Tool!$D$64,Tool!E82),$D$2),\"\"))))","v":""},{"$f":"IF(C108=\"\",\"\",IF(B108<>\"\",IF(Tool!F82=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E108=\"Collector\",IF(Tool!I82>Tool!G82,0,IF(Tool!G82>0,Tool!G82,\"\")),\"\")","v":""},{"$f":"IF(AND(E108=Tool!$G$9,Tool!H82>0),Tool!H82,\"\")","v":""},{"$f":"IF(E108=\"Collector\",IF(Tool!I82>Tool!G82,Tool!G82,IF(Tool!I82>=0,Tool!I82,0)),\"\")","v":""},{"$f":"IF(E108=\"Collector\",Tool!J82,\"\")","v":""},"",{"$f":"IF(E108=\"Collector\",Tool!O82,\"\")","v":""},"",null,"403-01","Tack",3.3670033670033675E-5,0]
[null,{"$f":"IF(AND(E88>=20,E88<=30),20,\"\")","v":""},{"$f":"IF(D27>=$D$2,\"\",IF($D$2<(Tool!E82-Tool!$D$64),\"\",IF(Tool!D83<>\"\",IF(Tool!$D$64<>0,Tool!E82-Tool!$D$64,Tool!E82),\"\")))","v":""},{"$f":"IF(C28=\"\",\"\",IF(B110=\"\",$D$2,IF((D27-$C$9)>=$D$2,\"\",IF(Tool!E82<>\"\",IF(AND($D$2>=(Tool!E83-Tool!$D$64),(Tool!E84-Tool!$D$64)>=(Tool!E83-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E83-Tool!$D$64,Tool!E83),$D$2),\"\"))))","v":""},{"$f":"IF(C109=\"\",\"\",IF(B109<>\"\",IF(Tool!F83=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E109=\"Collector\",IF(Tool!I83>Tool!G83,0,IF(Tool!G83>0,Tool!G83,\"\")),\"\")","v":""},{"$f":"IF(AND(E109=Tool!$G$9,Tool!H83>0),Tool!H83,\"\")","v":""},{"$f":"IF(E109=\"Collector\",IF(Tool!I83>Tool!G83,Tool!G83,IF(Tool!I83>=0,Tool!I83,0)),\"\")","v":""},{"$f":"IF(E109=\"Collector\",Tool!J83,\"\")","v":""},"",{"$f":"IF(E109=\"Collector\",Tool!O83,\"\")","v":""},"",null,"307-02.08","\"BM-2\" mix",1.2555555555555556E-2,0]
[null,{"$f":"IF(AND(E88>=21,E88<=30),21,\"\")","v":""},{"$f":"IF(D28>=$D$2,\"\",IF($D$2<(Tool!E83-Tool!$D$64),\"\",IF(Tool!D84<>\"\",IF(Tool!$D$64<>0,Tool!E83-Tool!$D$64,Tool!E83),\"\")))","v":""},{"$f":"IF(C29=\"\",\"\",IF(B111=\"\",$D$2,IF((D28-$C$9)>=$D$2,\"\",IF(Tool!E83<>\"\",IF(AND($D$2>=(Tool!E84-Tool!$D$64),(Tool!E85-Tool!$D$64)>=(Tool!E84-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E84-Tool!$D$64,Tool!E84),$D$2),\"\"))))","v":""},{"$f":"IF(C110=\"\",\"\",IF(B110<>\"\",IF(Tool!F84=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E110=\"Collector\",IF(Tool!I84>Tool!G84,0,IF(Tool!G84>0,Tool!G84,\"\")),\"\")","v":""},{"$f":"IF(AND(E110=Tool!$G$9,Tool!H84>0),Tool!H84,\"\")","v":""},{"$f":"IF(E110=\"Collector\",IF(Tool!I84>Tool!G84,Tool!G84,IF(Tool!I84>=0,Tool!I84,0)),\"\")","v":""},{"$f":"IF(E110=\"Collector\",Tool!J84,\"\")","v":""},"",{"$f":"IF(E110=\"Collector\",Tool!O84,\"\")","v":""},"",null,"402-01","Prime Coat",1.5392015392015393E-4,0]
[null,{"$f":"IF(AND(E88>=22,E88<=30),22,\"\")","v":""},{"$f":"IF(D29>=$D$2,\"\",IF($D$2<(Tool!E84-Tool!$D$64),\"\",IF(Tool!D85<>\"\",IF(Tool!$D$64<>0,Tool!E84-Tool!$D$64,Tool!E84),\"\")))","v":""},{"$f":"IF(C30=\"\",\"\",IF(B112=\"\",$D$2,IF((D29-$C$9)>=$D$2,\"\",IF(Tool!E84<>\"\",IF(AND($D$2>=(Tool!E85-Tool!$D$64),(Tool!E86-Tool!$D$64)>=(Tool!E85-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E85-Tool!$D$64,Tool!E85),$D$2),\"\"))))","v":""},{"$f":"IF(C111=\"\",\"\",IF(B111<>\"\",IF(Tool!F85=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E111=\"Collector\",IF(Tool!I85>Tool!G85,0,IF(Tool!G85>0,Tool!G85,\"\")),\"\")","v":""},{"$f":"IF(AND(E111=Tool!$G$9,Tool!H85>0),Tool!H85,\"\")","v":""},{"$f":"IF(E111=\"Collector\",IF(Tool!I85>Tool!G85,Tool!G85,IF(Tool!I85>=0,Tool!I85,0)),\"\")","v":""},{"$f":"IF(E111=\"Collector\",Tool!J85,\"\")","v":""},"",{"$f":"IF(E111=\"Collector\",Tool!O85,\"\")","v":""},"",null,"402-02","Agg. Cover",5.5555555555555556E-4,0]
[null,{"$f":"IF(AND(E88>=23,E88<=30),23,\"\")","v":""},{"$f":"IF(D30>=$D$2,\"\",IF($D$2<(Tool!E85-Tool!$D$64),\"\",IF(Tool!D86<>\"\",IF(Tool!$D$64<>0,Tool!E85-Tool!$D$64,Tool!E85),\"\")))","v":""},{"$f":"IF(C31=\"\",\"\",IF(B113=\"\",$D$2,IF((D30-$C$9)>=$D$2,\"\",IF(Tool!E85<>\"\",IF(AND($D$2>=(Tool!E86-Tool!$D$64),(Tool!E87-Tool!$D$64)>=(Tool!E86-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E86-Tool!$D$64,Tool!E86),$D$2),\"\"))))","v":""},{"$f":"IF(C112=\"\",\"\",IF(B112<>\"\",IF(Tool!F86=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E112=\"Collector\",IF(Tool!I86>Tool!G86,0,IF(Tool!G86>0,Tool!G86,\"\")),\"\")","v":""},{"$f":"IF(AND(E112=Tool!$G$9,Tool!H86>0),Tool!H86,\"\")","v":""},{"$f":"IF(E112=\"Collector\",IF(Tool!I86>Tool!G86,Tool!G86,IF(Tool!I86>=0,Tool!I86,0)),\"\")","v":""},{"$f":"IF(E112=\"Collector\",Tool!J86,\"\")","v":""},"",{"$f":"IF(E112=\"Collector\",Tool!O86,\"\")","v":""},"",null,"303-01","Stone (Asphalt)",0.12687499999999999,0]
[null,{"$f":"IF(AND(E88>=24,E88<=30),24,\"\")","v":""},{"$f":"IF(D31>=$D$2,\"\",IF($D$2<(Tool!E86-Tool!$D$64),\"\",IF(Tool!D87<>\"\",IF(Tool!$D$64<>0,Tool!E86-Tool!$D$64,Tool!E86),\"\")))","v":""},{"$f":"IF(C32=\"\",\"\",IF(B114=\"\",$D$2,IF((D31-$C$9)>=$D$2,\"\",IF(Tool!E86<>\"\",IF(AND($D$2>=(Tool!E87-Tool!$D$64),(Tool!E88-Tool!$D$64)>=(Tool!E87-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E87-Tool!$D$64,Tool!E87),$D$2),\"\"))))","v":""},{"$f":"IF(C113=\"\",\"\",IF(B113<>\"\",IF(Tool!F87=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E113=\"Collector\",IF(Tool!I87>Tool!G87,0,IF(Tool!G87>0,Tool!G87,\"\")),\"\")","v":""},{"$f":"IF(AND(E113=Tool!$G$9,Tool!H87>0),Tool!H87,\"\")","v":""},{"$f":"IF(E113=\"Collector\",IF(Tool!I87>Tool!G87,Tool!G87,IF(Tool!I87>=0,Tool!I87,0)),\"\")","v":""},{"$f":"IF(E113=\"Collector\",Tool!J87,\"\")","v":""},"",{"$f":"IF(E113=\"Collector\",Tool!O87,\"\")","v":""},""]
[null,{"$f":"IF(AND(E88>=25,E88<=30),25,\"\")","v":""},{"$f":"IF(D32>=$D$2,\"\",IF($D$2<(Tool!E87-Tool!$D$64),\"\",IF(Tool!D88<>\"\",IF(Tool!$D$64<>0,Tool!E87-Tool!$D$64,Tool!E87),\"\")))","v":""},{"$f":"IF(C33=\"\",\"\",IF(B115=\"\",$D$2,IF((D32-$C$9)>=$D$2,\"\",IF(Tool!E87<>\"\",IF(AND($D$2>=(Tool!E88-Tool!$D$64),(Tool!E89-Tool!$D$64)>=(Tool!E88-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E88-Tool!$D$64,Tool!E88),$D$2),\"\"))))","v":""},{"$f":"IF(C114=\"\",\"\",IF(B114<>\"\",IF(Tool!F88=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E114=\"Collector\",IF(Tool!I88>Tool!G88,0,IF(Tool!G88>0,Tool!G88,\"\")),\"\")","v":""},{"$f":"IF(AND(E114=Tool!$G$9,Tool!H88>0),Tool!H88,\"\")","v":""},{"$f":"IF(E114=\"Collector\",IF(Tool!I88>Tool!G88,Tool!G88,IF(Tool!I88>=0,Tool!I88,0)),\"\")","v":""},{"$f":"IF(E114=\"Collector\",Tool!J88,\"\")","v":""},"",{"$f":"IF(E114=\"Collector\",Tool!O88,\"\")","v":""},""]
[null,{"$f":"IF(AND(E88>=26,E88<=30),26,\"\")","v":""},{"$f":"IF(D33>=$D$2,\"\",IF($D$2<(Tool!E88-Tool!$D$64),\"\",IF(Tool!D89<>\"\",IF(Tool!$D$64<>0,Tool!E88-Tool!$D$64,Tool!E88),\"\")))","v":""},{"$f":"IF(C34=\"\",\"\",IF(B116=\"\",$D$2,IF((D33-$C$9)>=$D$2,\"\",IF(Tool!E88<>\"\",IF(AND($D$2>=(Tool!E89-Tool!$D$64),(Tool!E90-Tool!$D$64)>=(Tool!E89-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E89-Tool!$D$64,Tool!E89),$D$2),\"\"))))","v":""},{"$f":"IF(C115=\"\",\"\",IF(B115<>\"\",IF(Tool!F89=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E115=\"Collector\",IF(Tool!I89>Tool!G89,0,IF(Tool!G89>0,Tool!G89,\"\")),\"\")","v":""},{"$f":"IF(AND(E115=Tool!$G$9,Tool!H89>0),Tool!H89,\"\")","v":""},{"$f":"IF(E115=\"Collector\",IF(Tool!I89>Tool!G89,Tool!G89,IF(Tool!I89>=0,Tool!I89,0)),\"\")","v":""},{"$f":"IF(E115=\"Collector\",Tool!J89,\"\")","v":""},"",{"$f":"IF(E115=\"Collector\",Tool!O89,\"\")","v":""},""]
[null,{"$f":"IF(AND(E88>=27,E88<=30),27,\"\")","v":""},{"$f":"IF(D34>=$D$2,\"\",IF($D$2<(Tool!E89-Tool!$D$64),\"\",IF(Tool!D90<>\"\",IF(Tool!$D$64<>0,Tool!E89-Tool!$D$64,Tool!E89),\"\")))","v":""},{"$f":"IF(C35=\"\",\"\",IF(B117=\"\",$D$2,IF((D34-$C$9)>=$D$2,\"\",IF(Tool!E89<>\"\",IF(AND($D$2>=(Tool!E90-Tool!$D$64),(Tool!E91-Tool!$D$64)>=(Tool!E90-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E90-Tool!$D$64,Tool!E90),$D$2),\"\"))))","v":""},{"$f":"IF(C116=\"\",\"\",IF(B116<>\"\",IF(Tool!F90=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E116=\"Collector\",IF(Tool!I90>Tool!G90,0,IF(Tool!G90>0,Tool!G90,\"\")),\"\")","v":""},{"$f":"IF(AND(E116=Tool!$G$9,Tool!H90>0),Tool!H90,\"\")","v":""},{"$f":"IF(E116=\"Collector\",IF(Tool!I90>Tool!G90,Tool!G90,IF(Tool!I90>=0,Tool!I90,0)),\"\")","v":""},{"$f":"IF(E116=\"Collector\",Tool!J90,\"\")","v":""},"",{"$f":"IF(E116=\"Collector\",Tool!O90,\"\")","v":""},"",null,"Average Facility Width Table - Remove Resurfaced Segments"]
[null,{"$f":"IF(AND(E88>=28,E88<=30),28,\"\")","v":""},{"$f":"IF(D35>=$D$2,\"\",IF($D$2<(Tool!E90-Tool!$D$64),\"\",IF(Tool!D91<>\"\",IF(Tool!$D$64<>0,Tool!E90-Tool!$D$64,Tool!E90),\"\")))","v":""},{"$f":"IF(C36=\"\",\"\",IF(B118=\"\",$D$2,IF((D35-$C$9)>=$D$2,\"\",IF(Tool!E90<>\"\",IF(AND($D$2>=(Tool!E91-Tool!$D$64),(Tool!E92-Tool!$D$64)>=(Tool!E91-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E91-Tool!$D$64,Tool!E91),$D$2),\"\"))))","v":""},{"$f":"IF(C117=\"\",\"\",IF(B117<>\"\",IF(Tool!F91=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E117=\"Collector\",IF(Tool!I91>Tool!G91,0,IF(Tool!G91>0,Tool!G91,\"\")),\"\")","v":""},{"$f":"IF(AND(E117=Tool!$G$9,Tool!H91>0),Tool!H91,\"\")","v":""},{"$f":"IF(E117=\"Collector\",IF(Tool!I91>Tool!G91,Tool!G91,IF(Tool!I91>=0,Tool!I91,0)),\"\")","v":""},{"$f":"IF(E117=\"Collector\",Tool!J91,\"\")","v":""},"",{"$f":"IF(E117=\"Collector\",Tool!O91,\"\")","v":""},"",null,null,"Local",null,"SIA",null,"Collector",null,"Arterial",null,"Freeway",null,"Concrete"]
[null,{"$f":"IF(AND(E88>=29,E88<=30),29,\"\")","v":""},{"$f":"IF(D36>=$D$2,\"\",IF($D$2<(Tool!E91-Tool!$D$64),\"\",IF(Tool!D92<>\"\",IF(Tool!$D$64<>0,Tool!E91-Tool!$D$64,Tool!E91),\"\")))","v":""},{"$f":"IF(C37=\"\",\"\",IF(B119=\"\",$D$2,IF((D36-$C$9)>=$D$2,\"\",IF(Tool!E91<>\"\",IF(AND($D$2>=(Tool!E92-Tool!$D$64),(Tool!E93-Tool!$D$64)>=(Tool!E92-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E92-Tool!$D$64,Tool!E92),$D$2),\"\"))))","v":""},{"$f":"IF(C118=\"\",\"\",IF(B118<>\"\",IF(Tool!F92=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E118=\"Collector\",IF(Tool!I92>Tool!G92,0,IF(Tool!G92>0,Tool!G92,\"\")),\"\")","v":""},{"$f":"IF(AND(E118=Tool!$G$9,Tool!H92>0),Tool!H92,\"\")","v":""},{"$f":"IF(E118=\"Collector\",IF(Tool!I92>Tool!G92,Tool!G92,IF(Tool!I92>=0,Tool!I92,0)),\"\")","v":""},{"$f":"IF(E118=\"Collector\",Tool!J92,\"\")","v":""},"",{"$f":"IF(E118=\"Collector\",Tool!O92,\"\")","v":""},"",null,null,"Total Pavement Width","Length","Total Pavement Width","Length","Total Pavement Width","Length","Total Pavement Width","Length","Total Pavement Width","Length","Total Pavement Width","Length"]
[null,{"$f":"IF(E88=30,30,\"\")","v":""},{"$f":"IF(D37>=$D$2,\"\",IF($D$2<(Tool!E92-Tool!$D$64),\"\",IF(Tool!D93<>\"\",IF(Tool!$D$64<>0,Tool!E92-Tool!$D$64,Tool!E92),\"\")))","v":""},{"$f":"IF(C38=\"\",\"\",IF(B120=\"\",$D$2,IF((D37-$C$9)>=$D$2,\"\",IF(Tool!E92<>\"\",IF(AND($D$2>=(Tool!E93-Tool!$D$64),(Tool!E94-Tool!$D$64)>=(Tool!E93-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E93-Tool!$D$64,Tool!E93),$D$2),\"\"))))","v":""},{"$f":"IF(C119=\"\",\"\",IF(B119<>\"\",IF(Tool!F93=Tool!$G$9,Tool!$G$9,\"\"),\"\"))","v":""},{"$f":"IF(E119=\"Collector\",IF(Tool!I93>Tool!G93,0,IF(Tool!G93>0,Tool!G93,\"\")),\"\")","v":""},{"$f":"IF(AND(E119=Tool!$G$9,Tool!H93>0),Tool!H93,\"\")","v":""},{"$f":"IF(E119=\"Collector\",IF(Tool!I93>Tool!G93,Tool!G93,IF(Tool!I93>=0,Tool!I93,0)),\"\")","v":""},{"$f":"IF(E119=\"Collector\",Tool!J93,\"\")","v":""},"",{"$f":"IF(E119=\"Collector\",Tool!O93,\"\")","v":""},"",null,1,{"$f":"IF(F9<>H9,F9,\"\")","v":""},{"$f":"IF(F9<>H9,J9,\"\")","v":""},{"$f":"IF(F50<>H50,F50,\"\")","v":""},{"$f":"IF(F50<>H50,J50,\"\")","v":""},{"$f":"IF(F90<>H90,F90,\"\")","v":""},{"$f":"IF(F90<>H90,J90,\"\")","v":""},{"$f":"IF(F130<>H130,F130,\"\")","v":""},{"$f":"IF(F130<>H130,J130,\"\")","v":""},{"$f":"IF(F170<>H170,F170,\"\")","v":""},{"$f":"IF(F170<>H170,J170,\"\")","v":""},{"$f":"IF(F210<>H210,F210,\"\")","v":""},{"$f":"IF(F210<>H210,J210,\"\")","v":""}]
[null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"N119+1","v":2},{"$f":"IF(F10<>H10,F10,\"\")","v":""},{"$f":"IF(F10<>H10,J10,\"\")","v":""},{"$f":"IF(F51<>H51,F51,\"\")","v":""},{"$f":"IF(F51<>H51,J51,\"\")","v":""},{"$f":"IF(F91<>H91,F91,\"\")","v":""},{"$f":"IF(F91<>H91,J91,\"\")","v":""},{"$f":"IF(F131<>H131,F131,\"\")","v":""},{"$f":"IF(F131<>H131,J131,\"\")","v":""},{"$f":"IF(F171<>H171,F171,\"\")","v":""},{"$f":"IF(F171<>H171,J171,\"\")","v":""},{"$f":"IF(F211<>H211,F211,\"\")","v":""},{"$f":"IF(F211<>H211,J211,\"\")","v":""}]
[null,null,null,null,null,null,"Average Width:",{"$f":"IFERROR((SUMPRODUCT(F90:F119,J90:J119)/SUM(J90:J119))-(SUMPRODUCT(H90:H119,J90:J119)/SUM(J90:J119)),0)","v":0},"Average Additional Full Depth:",{"$f":"IFERROR(SUMPRODUCT(--(I90:I119=\"Yes\"),H90:H119,J90:J119)/SUM(J90:J119),0)","v":0},"Area",{"$f":"H124*J121*5280","v":0},null,{"$f":"N120+1","v":3},"","","","","","","","","","","",""]
[null,null,null,null,null,null,"Average Shoulder Width:",{"$f":"IF(SUM(J90:J119)>0,(SUMPRODUCT(G90:G119,J90:J119)/SUM(J90:J119))*2,0)","v":0},"Total Full Depth Width:",{"$f":"H121+J121","v":0},null,null,null,4,"","","","","","","","","","","",""]
[null,null,null,null,null,null,"Average Resurface Pavement:",{"$f":"IFERROR(SUMPRODUCT(--(I90:I119=\"No\"),H90:H119,J90:J119)/SUM(J90:J119),0)","v":0},"Average Roadway Width:",{"$f":"IFERROR(SUMPRODUCT(S119:S138,T119:T138)/SUM(T119:T138),0)","v":0},null,null,null,5,"","","","","","","","","","","",""]
[null,null,null,null,null,null,"Length:",{"$f":"SUM(J90:J119)","v":0},null,null,null,null,null,6,"","","","","","","","","","","",""]
[null,null,null,null,null,null,"Perimeter Length",{"$f":"SUM(L90:L119)","v":0},null,null,null,null,null,7,"","","","","","","","","","","",""]
[null,"Proposed Pavement Width",null,null,null,null,null,null,null,null,null,null,null,8,"","","","","","","","","","","",""]
[null,"Arterial",null,null,null,null,null,null,null,null,null,null,null,9,"","","","","","","","","","","",""]
[null,"Segments:",null,null,{"$f":"Tool!$J$61","v":1},null,null,null,null,null,null,null,null,10,"","","","","","","","","","","",""]
[null,"Segments","Begin","End","Pavement Type","Total Pavement Width(ft)","Outside Shoulder Width (ft)","Existing Pavement Width","Replace Existing Pavement?","Length","Widen to One Side or Both?","Perimeter Length",null,11,"","","","","","","","","","","",""]
[null,{"$f":"IF(AND(E128>=1,E128<=30),1,\"\")","v":1},{"$f":"IF(Tool!D64<>\"\",IF(B9<>\"\",IF(Tool!D64=0,Tool!D64,Tool!D64-Tool!D64),\"\"),\"\")","v":""},{"$f":"IF(C9=\"\",\"\",IF((Tool!E65-Tool!D64)<(Tool!E64-Tool!D64),D2,IF(B9<>\"\",IF(Tool!E64<>\"\",IF(AND(B10=\"\",Tool!E64-Tool!D64<$D$2),$D$2,IF(B9=1,IF($D$2<(Tool!E64-Tool!$D$64),$D$2,IF(Tool!D64<>0,(Tool!E64-Tool!D64),Tool!E64)),\"\")),\"\"),\"\")))","v":""},{"$f":"IF(C130=\"\",\"\",IF(B130<>\"\",IF(Tool!F64=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E130=\"Arterial\",IF(Tool!I64>Tool!G64,0,IF(Tool!G64>0,Tool!G64,\"\")),\"\")","v":""},{"$f":"IF(AND($E130=Tool!$G$10,Tool!H64>0),Tool!H64,\"\")","v":""},{"$f":"IF(E130=\"Arterial\",IF(Tool!I64>Tool!G64,Tool!G64,IF(Tool!I64>=0,Tool!I64,0)),\"\")","v":""},{"$f":"IF(E130=\"Arterial\",Tool!J64,\"\")","v":""},{"$f":"IF(F130<>\"\",IF(OR(C130=\"\",D130=\"\"),\"\",IF(E130=\"Arterial\",D130-C130,\"\")),\"\")","v":""},{"$f":"IF(E130=\"Arterial\",Tool!O64,\"\")","v":""},{"$f":"IFERROR(IF(AND(K130=\"One Side\",OR((F130-H130)>0,G130<>\"\")),J130,IF(AND(K130=\"Both Sides\",OR((F130-H130)>0,G130<>\"\")),J130*2,0)),\"\")","v":""},null,12,"","","","","","","","","","","",""]
[null,{"$f":"IF(AND(E128>=2,E128<=30),2,\"\")","v":""},{"$f":"IF(D9>=$D$2,\"\",IF($D$2<(Tool!E64-Tool!$D$64),\"\",IF(Tool!D65<>\"\",IF(Tool!$D$64<>0,Tool!E64-Tool!$D$64,Tool!E64),\"\")))","v":""},{"$f":"IF(C10=\"\",\"\",IF(B132=\"\",$D$2,IF((D9-$C$9)>=$D$2,\"\",IF(Tool!E64<>\"\",IF(AND($D$2>=(Tool!E65-Tool!$D$64),(Tool!E66-Tool!$D$64)>=(Tool!E65-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E65-Tool!$D$64,Tool!E65),$D$2),\"\"))))","v":""},{"$f":"IF(C131=\"\",\"\",IF(B131<>\"\",IF(Tool!F65=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E131=\"Arterial\",IF(Tool!I65>Tool!G65,0,IF(Tool!G65>0,Tool!G65,\"\")),\"\")","v":""},{"$f":"IF(AND(E131=Tool!$G$10,Tool!H65>0),Tool!H65,\"\")","v":""},{"$f":"IF(E131=\"Arterial\",IF(Tool!I65>Tool!G65,Tool!G65,IF(Tool!I65>=0,Tool!I65,0)),\"\")","v":""},{"$f":"IF(E131=\"Arterial\",Tool!J65,\"\")","v":""},{"$f":"IF(F131<>\"\",IF(OR(C131=\"\",D131=\"\"),\"\",IF(E131=\"Arterial\",D131-C131,\"\")),\"\")","v":""},{"$f":"IF(E131=\"Arterial\",Tool!O65,\"\")","v":""},{"$f":"IFERROR(IF(AND(K131=\"One Side\",OR((F131-H131)>0,G131<>\"\")),J131,IF(AND(K131=\"Both Sides\",OR((F131-H131)>0,G131<>\"\")),J131*2,0)),\"\")","v":""},null,13,"","","","","","","","","","","",""]
[null,{"$f":"IF(AND(E128>=3,E128<=30),3,\"\")","v":""},{"$f":"IF(D10>=$D$2,\"\",IF($D$2<(Tool!E65-Tool!$D$64),\"\",IF(Tool!D66<>\"\",IF(Tool!$D$64<>0,Tool!E65-Tool!$D$64,Tool!E65),\"\")))","v":""},{"$f":"IF(C11=\"\",\"\",IF(B133=\"\",$D$2,IF((D10-$C$9)>=$D$2,\"\",IF(Tool!E65<>\"\",IF(AND($D$2>=(Tool!E66-Tool!$D$64),(Tool!E67-Tool!$D$64)>=(Tool!E66-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E66-Tool!$D$64,Tool!E66),$D$2),\"\"))))","v":""},{"$f":"IF(C132=\"\",\"\",IF(B132<>\"\",IF(Tool!F66=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E132=\"Arterial\",IF(Tool!I66>Tool!G66,0,IF(Tool!G66>0,Tool!G66,\"\")),\"\")","v":""},{"$f":"IF(AND(E132=Tool!$G$10,Tool!H66>0),Tool!H66,\"\")","v":""},{"$f":"IF(E132=\"Arterial\",IF(Tool!I66>Tool!G66,Tool!G66,IF(Tool!I66>=0,Tool!I66,0)),\"\")","v":""},{"$f":"IF(E132=\"Arterial\",Tool!J66,\"\")","v":""},"",{"$f":"IF(E132=\"Arterial\",Tool!O66,\"\")","v":""},"",null,14,"","","","","","","","","","","",""]
[null,{"$f":"IF(AND(E128>=4,E128<=30),4,\"\")","v":""},{"$f":"IF(D11>=$D$2,\"\",IF($D$2<(Tool!E66-Tool!$D$64),\"\",IF(Tool!D67<>\"\",IF(Tool!$D$64<>0,Tool!E66-Tool!$D$64,Tool!E66),\"\")))","v":""},{"$f":"IF(C12=\"\",\"\",IF(B134=\"\",$D$2,IF((D11-$C$9)>=$D$2,\"\",IF(Tool!E66<>\"\",IF(AND($D$2>=(Tool!E67-Tool!$D$64),(Tool!E68-Tool!$D$64)>=(Tool!E67-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E67-Tool!$D$64,Tool!E67),$D$2),\"\"))))","v":""},{"$f":"IF(C133=\"\",\"\",IF(B133<>\"\",IF(Tool!F67=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E133=\"Arterial\",IF(Tool!I67>Tool!G67,0,IF(Tool!G67>0,Tool!G67,\"\")),\"\")","v":""},{"$f":"IF(AND(E133=Tool!$G$10,Tool!H67>0),Tool!H67,\"\")","v":""},{"$f":"IF(E133=\"Arterial\",IF(Tool!I67>Tool!G67,Tool!G67,IF(Tool!I67>=0,Tool!I67,0)),\"\")","v":""},{"$f":"IF(E133=\"Arterial\",Tool!J67,\"\")","v":""},"",{"$f":"IF(E133=\"Arterial\",Tool!O67,\"\")","v":""},"",null,15,"","","","","","","","","","","",""]
[null,{"$f":"IF(AND(E128>=5,E128<=30),5,\"\")","v":""},{"$f":"IF(D12>=$D$2,\"\",IF($D$2<(Tool!E67-Tool!$D$64),\"\",IF(Tool!D68<>\"\",IF(Tool!$D$64<>0,Tool!E67-Tool!$D$64,Tool!E67),\"\")))","v":""},{"$f":"IF(C13=\"\",\"\",IF(B135=\"\",$D$2,IF((D12-$C$9)>=$D$2,\"\",IF(Tool!E67<>\"\",IF(AND($D$2>=(Tool!E68-Tool!$D$64),(Tool!E69-Tool!$D$64)>=(Tool!E68-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E68-Tool!$D$64,Tool!E68),$D$2),\"\"))))","v":""},{"$f":"IF(C134=\"\",\"\",IF(B134<>\"\",IF(Tool!F68=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E134=\"Arterial\",IF(Tool!I68>Tool!G68,0,IF(Tool!G68>0,Tool!G68,\"\")),\"\")","v":""},{"$f":"IF(AND(E134=Tool!$G$10,Tool!H68>0),Tool!H68,\"\")","v":""},{"$f":"IF(E134=\"Arterial\",IF(Tool!I68>Tool!G68,Tool!G68,IF(Tool!I68>=0,Tool!I68,0)),\"\")","v":""},{"$f":"IF(E134=\"Arterial\",Tool!J68,\"\")","v":""},{"$f":"IF(F134<>\"\",IF(OR(C134=\"\",D134=\"\"),\"\",IF(E134=\"Arterial\",D134-C134,\"\")),\"\")","v":""},{"$f":"IF(E134=\"Arterial\",Tool!O68,\"\")","v":""},"",null,16,"","","","","","","","","","","",""]
[null,{"$f":"IF(AND(E128>=6,E128<=30),6,\"\")","v":""},{"$f":"IF(D13>=$D$2,\"\",IF($D$2<(Tool!E68-Tool!$D$64),\"\",IF(Tool!D69<>\"\",IF(Tool!$D$64<>0,Tool!E68-Tool!$D$64,Tool!E68),\"\")))","v":""},{"$f":"IF(C14=\"\",\"\",IF(B136=\"\",$D$2,IF((D13-$C$9)>=$D$2,\"\",IF(Tool!E68<>\"\",IF(AND($D$2>=(Tool!E69-Tool!$D$64),(Tool!E70-Tool!$D$64)>=(Tool!E69-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E69-Tool!$D$64,Tool!E69),$D$2),\"\"))))","v":""},{"$f":"IF(C135=\"\",\"\",IF(B135<>\"\",IF(Tool!F69=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E135=\"Arterial\",IF(Tool!I69>Tool!G69,0,IF(Tool!G69>0,Tool!G69,\"\")),\"\")","v":""},{"$f":"IF(AND(E135=Tool!$G$10,Tool!H69>0),Tool!H69,\"\")","v":""},{"$f":"IF(E135=\"Arterial\",IF(Tool!I69>Tool!G69,Tool!G69,IF(Tool!I69>=0,Tool!I69,0)),\"\")","v":""},{"$f":"IF(E135=\"Arterial\",Tool!J69,\"\")","v":""},"",{"$f":"IF(E135=\"Arterial\",Tool!O69,\"\")","v":""},"",null,17,"","","","","","","","","","","",""]
[null,{"$f":"IF(AND(E128>=7,E128<=30),7,\"\")","v":""},{"$f":"IF(D14>=$D$2,\"\",IF($D$2<(Tool!E69-Tool!$D$64),\"\",IF(Tool!D70<>\"\",IF(Tool!$D$64<>0,Tool!E69-Tool!$D$64,Tool!E69),\"\")))","v":""},{"$f":"IF(C15=\"\",\"\",IF(B137=\"\",$D$2,IF((D14-$C$9)>=$D$2,\"\",IF(Tool!E69<>\"\",IF(AND($D$2>=(Tool!E70-Tool!$D$64),(Tool!E71-Tool!$D$64)>=(Tool!E70-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E70-Tool!$D$64,Tool!E70),$D$2),\"\"))))","v":""},{"$f":"IF(C136=\"\",\"\",IF(B136<>\"\",IF(Tool!F70=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E136=\"Arterial\",IF(Tool!I70>Tool!G70,0,IF(Tool!G70>0,Tool!G70,\"\")),\"\")","v":""},{"$f":"IF(AND(E136=Tool!$G$10,Tool!H70>0),Tool!H70,\"\")","v":""},{"$f":"IF(E136=\"Arterial\",IF(Tool!I70>Tool!G70,Tool!G70,IF(Tool!I70>=0,Tool!I70,0)),\"\")","v":""},{"$f":"IF(E136=\"Arterial\",Tool!J70,\"\")","v":""},"",{"$f":"IF(E136=\"Arterial\",Tool!O70,\"\")","v":""},"",null,{"$f":"N135+1","v":18},"","","","","","","","","","","",""]
[null,{"$f":"IF(AND(E128>=8,E128<=30),8,\"\")","v":""},{"$f":"IF(D15>=$D$2,\"\",IF($D$2<(Tool!E70-Tool!$D$64),\"\",IF(Tool!D71<>\"\",IF(Tool!$D$64<>0,Tool!E70-Tool!$D$64,Tool!E70),\"\")))","v":""},{"$f":"IF(C16=\"\",\"\",IF(B138=\"\",$D$2,IF((D15-$C$9)>=$D$2,\"\",IF(Tool!E70<>\"\",IF(AND($D$2>=(Tool!E71-Tool!$D$64),(Tool!E72-Tool!$D$64)>=(Tool!E71-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E71-Tool!$D$64,Tool!E71),$D$2),\"\"))))","v":""},{"$f":"IF(C137=\"\",\"\",IF(B137<>\"\",IF(Tool!F71=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E137=\"Arterial\",IF(Tool!I71>Tool!G71,0,IF(Tool!G71>0,Tool!G71,\"\")),\"\")","v":""},{"$f":"IF(AND(E137=Tool!$G$10,Tool!H71>0),Tool!H71,\"\")","v":""},{"$f":"IF(E137=\"Arterial\",IF(Tool!I71>Tool!G71,Tool!G71,IF(Tool!I71>=0,Tool!I71,0)),\"\")","v":""},{"$f":"IF(E137=\"Arterial\",Tool!J71,\"\")","v":""},"",{"$f":"IF(E137=\"Arterial\",Tool!O71,\"\")","v":""},"",null,19,"","","","","","","","","","","",""]
[null,{"$f":"IF(AND(E128>=9,F128<=20),9,\"\")","v":""},{"$f":"IF(D16>=$D$2,\"\",IF($D$2<(Tool!E71-Tool!$D$64),\"\",IF(Tool!D72<>\"\",IF(Tool!$D$64<>0,Tool!E71-Tool!$D$64,Tool!E71),\"\")))","v":""},{"$f":"IF(C17=\"\",\"\",IF(B139=\"\",$D$2,IF((D16-$C$9)>=$D$2,\"\",IF(Tool!E71<>\"\",IF(AND($D$2>=(Tool!E72-Tool!$D$64),(Tool!E73-Tool!$D$64)>=(Tool!E72-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E72-Tool!$D$64,Tool!E72),$D$2),\"\"))))","v":""},{"$f":"IF(C138=\"\",\"\",IF(B138<>\"\",IF(Tool!F72=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E138=\"Arterial\",IF(Tool!I72>Tool!G72,0,IF(Tool!G72>0,Tool!G72,\"\")),\"\")","v":""},{"$f":"IF(AND(E138=Tool!$G$10,Tool!H72>0),Tool!H72,\"\")","v":""},{"$f":"IF(E138=\"Arterial\",IF(Tool!I72>Tool!G72,Tool!G72,IF(Tool!I72>=0,Tool!I72,0)),\"\")","v":""},{"$f":"IF(E138=\"Arterial\",Tool!J72,\"\")","v":""},"",{"$f":"IF(E138=\"Arterial\",Tool!O72,\"\")","v":""},"",null,20,"","","","","","","","","","","",""]
[null,{"$f":"IF(AND(E128>=10,E128<=30),10,\"\")","v":""},{"$f":"IF(D17>=$D$2,\"\",IF($D$2<(Tool!E72-Tool!$D$64),\"\",IF(Tool!D73<>\"\",IF(Tool!$D$64<>0,Tool!E72-Tool!$D$64,Tool!E72),\"\")))","v":""},{"$f":"IF(C18=\"\",\"\",IF(B140=\"\",$D$2,IF((D17-$C$9)>=$D$2,\"\",IF(Tool!E72<>\"\",IF(AND($D$2>=(Tool!E73-Tool!$D$64),(Tool!E74-Tool!$D$64)>=(Tool!E73-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E73-Tool!$D$64,Tool!E73),$D$2),\"\"))))","v":""},{"$f":"IF(C139=\"\",\"\",IF(B139<>\"\",IF(Tool!F73=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E139=\"Arterial\",IF(Tool!I73>Tool!G73,0,IF(Tool!G73>0,Tool!G73,\"\")),\"\")","v":""},{"$f":"IF(AND(E139=Tool!$G$10,Tool!H73>0),Tool!H73,\"\")","v":""},{"$f":"IF(E139=\"Arterial\",IF(Tool!I73>Tool!G73,Tool!G73,IF(Tool!I73>=0,Tool!I73,0)),\"\")","v":""},{"$f":"IF(E139=\"Arterial\",Tool!J73,\"\")","v":""},"",{"$f":"IF(E139=\"Arterial\",Tool!O73,\"\")","v":""},"",null,null,{"$f":"IF(F29<>H29,F29,\"\")","v":""},null,{"$f":"IF(F70<>H70,F70,\"\")","v":""},null,"","","","","","","",""]
[null,{"$f":"IF(AND(E128>=11,E128<=30),11,\"\")","v":""},{"$f":"IF(D18>=$D$2,\"\",IF($D$2<(Tool!E73-Tool!$D$64),\"\",IF(Tool!D74<>\"\",IF(Tool!$D$64<>0,Tool!E73-Tool!$D$64,Tool!E73),\"\")))","v":""},{"$f":"IF(C19=\"\",\"\",IF(B141=\"\",$D$2,IF((D18-$C$9)>=$D$2,\"\",IF(Tool!E73<>\"\",IF(AND($D$2>=(Tool!E74-Tool!$D$64),(Tool!E75-Tool!$D$64)>=(Tool!E74-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E74-Tool!$D$64,Tool!E74),$D$2),\"\"))))","v":""},{"$f":"IF(C140=\"\",\"\",IF(B140<>\"\",IF(Tool!F74=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E140=\"Arterial\",IF(Tool!I74>Tool!G74,0,IF(Tool!G74>0,Tool!G74,\"\")),\"\")","v":""},{"$f":"IF(AND(E140=Tool!$G$10,Tool!H74>0),Tool!H74,\"\")","v":""},{"$f":"IF(E140=\"Arterial\",IF(Tool!I74>Tool!G74,Tool!G74,IF(Tool!I74>=0,Tool!I74,0)),\"\")","v":""},{"$f":"IF(E140=\"Arterial\",Tool!J74,\"\")","v":""},"",{"$f":"IF(E140=\"Arterial\",Tool!O74,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=12,F128<=30),12,\"\")","v":""},{"$f":"IF(D19>=$D$2,\"\",IF($D$2<(Tool!E74-Tool!$D$64),\"\",IF(Tool!D75<>\"\",IF(Tool!$D$64<>0,Tool!E74-Tool!$D$64,Tool!E74),\"\")))","v":""},{"$f":"IF(C20=\"\",\"\",IF(B142=\"\",$D$2,IF((D19-$C$9)>=$D$2,\"\",IF(Tool!E74<>\"\",IF(AND($D$2>=(Tool!E75-Tool!$D$64),(Tool!E76-Tool!$D$64)>=(Tool!E75-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E75-Tool!$D$64,Tool!E75),$D$2),\"\"))))","v":""},{"$f":"IF(C141=\"\",\"\",IF(B141<>\"\",IF(Tool!F75=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E141=\"Arterial\",IF(Tool!I75>Tool!G75,0,IF(Tool!G75>0,Tool!G75,\"\")),\"\")","v":""},{"$f":"IF(AND(E141=Tool!$G$10,Tool!H75>0),Tool!H75,\"\")","v":""},{"$f":"IF(E141=\"Arterial\",IF(Tool!I75>Tool!G75,Tool!G75,IF(Tool!I75>=0,Tool!I75,0)),\"\")","v":""},{"$f":"IF(E141=\"Arterial\",Tool!J75,\"\")","v":""},"",{"$f":"IF(E141=\"Arterial\",Tool!O75,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=13,E128<=30),13,\"\")","v":""},{"$f":"IF(D20>=$D$2,\"\",IF($D$2<(Tool!E75-Tool!$D$64),\"\",IF(Tool!D76<>\"\",IF(Tool!$D$64<>0,Tool!E75-Tool!$D$64,Tool!E75),\"\")))","v":""},{"$f":"IF(C21=\"\",\"\",IF(B143=\"\",$D$2,IF((D20-$C$9)>=$D$2,\"\",IF(Tool!E75<>\"\",IF(AND($D$2>=(Tool!E76-Tool!$D$64),(Tool!E77-Tool!$D$64)>=(Tool!E76-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E76-Tool!$D$64,Tool!E76),$D$2),\"\"))))","v":""},{"$f":"IF(C142=\"\",\"\",IF(B142<>\"\",IF(Tool!F76=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E142=\"Arterial\",IF(Tool!I76>Tool!G76,0,IF(Tool!G76>0,Tool!G76,\"\")),\"\")","v":""},{"$f":"IF(AND(E142=Tool!$G$10,Tool!H76>0),Tool!H76,\"\")","v":""},{"$f":"IF(E142=\"Arterial\",IF(Tool!I76>Tool!G76,Tool!G76,IF(Tool!I76>=0,Tool!I76,0)),\"\")","v":""},{"$f":"IF(E142=\"Arterial\",Tool!J76,\"\")","v":""},"",{"$f":"IF(E142=\"Arterial\",Tool!O76,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=14,E128<=30),14,\"\")","v":""},{"$f":"IF(D21>=$D$2,\"\",IF($D$2<(Tool!E76-Tool!$D$64),\"\",IF(Tool!D77<>\"\",IF(Tool!$D$64<>0,Tool!E76-Tool!$D$64,Tool!E76),\"\")))","v":""},{"$f":"IF(C22=\"\",\"\",IF(B144=\"\",$D$2,IF((D21-$C$9)>=$D$2,\"\",IF(Tool!E76<>\"\",IF(AND($D$2>=(Tool!E77-Tool!$D$64),(Tool!E78-Tool!$D$64)>=(Tool!E77-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E77-Tool!$D$64,Tool!E77),$D$2),\"\"))))","v":""},{"$f":"IF(C143=\"\",\"\",IF(B143<>\"\",IF(Tool!F77=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E143=\"Arterial\",IF(Tool!I77>Tool!G77,0,IF(Tool!G77>0,Tool!G77,\"\")),\"\")","v":""},{"$f":"IF(AND(E143=Tool!$G$10,Tool!H77>0),Tool!H77,\"\")","v":""},{"$f":"IF(E143=\"Arterial\",IF(Tool!I77>Tool!G77,Tool!G77,IF(Tool!I77>=0,Tool!I77,0)),\"\")","v":""},{"$f":"IF(E143=\"Arterial\",Tool!J77,\"\")","v":""},"",{"$f":"IF(E143=\"Arterial\",Tool!O77,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=15,E128<=30),15,\"\")","v":""},{"$f":"IF(D22>=$D$2,\"\",IF($D$2<(Tool!E77-Tool!$D$64),\"\",IF(Tool!D78<>\"\",IF(Tool!$D$64<>0,Tool!E77-Tool!$D$64,Tool!E77),\"\")))","v":""},{"$f":"IF(C23=\"\",\"\",IF(B145=\"\",$D$2,IF((D22-$C$9)>=$D$2,\"\",IF(Tool!E77<>\"\",IF(AND($D$2>=(Tool!E78-Tool!$D$64),(Tool!E79-Tool!$D$64)>=(Tool!E78-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E78-Tool!$D$64,Tool!E78),$D$2),\"\"))))","v":""},{"$f":"IF(C144=\"\",\"\",IF(B144<>\"\",IF(Tool!F78=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E144=\"Arterial\",IF(Tool!I78>Tool!G78,0,IF(Tool!G78>0,Tool!G78,\"\")),\"\")","v":""},{"$f":"IF(AND(E144=Tool!$G$10,Tool!H78>0),Tool!H78,\"\")","v":""},{"$f":"IF(E144=\"Arterial\",IF(Tool!I78>Tool!G78,Tool!G78,IF(Tool!I78>=0,Tool!I78,0)),\"\")","v":""},{"$f":"IF(E144=\"Arterial\",Tool!J78,\"\")","v":""},"",{"$f":"IF(E144=\"Arterial\",Tool!O78,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=16,E128<=30),16,\"\")","v":""},{"$f":"IF(D23>=$D$2,\"\",IF($D$2<(Tool!E78-Tool!$D$64),\"\",IF(Tool!D79<>\"\",IF(Tool!$D$64<>0,Tool!E78-Tool!$D$64,Tool!E78),\"\")))","v":""},{"$f":"IF(C24=\"\",\"\",IF(B146=\"\",$D$2,IF((D23-$C$9)>=$D$2,\"\",IF(Tool!E78<>\"\",IF(AND($D$2>=(Tool!E79-Tool!$D$64),(Tool!E80-Tool!$D$64)>=(Tool!E79-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E79-Tool!$D$64,Tool!E79),$D$2),\"\"))))","v":""},{"$f":"IF(C145=\"\",\"\",IF(B145<>\"\",IF(Tool!F79=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E145=\"Arterial\",IF(Tool!I79>Tool!G79,0,IF(Tool!G79>0,Tool!G79,\"\")),\"\")","v":""},{"$f":"IF(AND(E145=Tool!$G$10,Tool!H79>0),Tool!H79,\"\")","v":""},{"$f":"IF(E145=\"Arterial\",IF(Tool!I79>Tool!G79,Tool!G79,IF(Tool!I79>=0,Tool!I79,0)),\"\")","v":""},{"$f":"IF(E145=\"Arterial\",Tool!J79,\"\")","v":""},"",{"$f":"IF(E145=\"Arterial\",Tool!O79,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=17,E128<=30),17,\"\")","v":""},{"$f":"IF(D24>=$D$2,\"\",IF($D$2<(Tool!E79-Tool!$D$64),\"\",IF(Tool!D80<>\"\",IF(Tool!$D$64<>0,Tool!E79-Tool!$D$64,Tool!E79),\"\")))","v":""},{"$f":"IF(C25=\"\",\"\",IF(B147=\"\",$D$2,IF((D24-$C$9)>=$D$2,\"\",IF(Tool!E79<>\"\",IF(AND($D$2>=(Tool!E80-Tool!$D$64),(Tool!E81-Tool!$D$64)>=(Tool!E80-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E80-Tool!$D$64,Tool!E80),$D$2),\"\"))))","v":""},{"$f":"IF(C146=\"\",\"\",IF(B146<>\"\",IF(Tool!F80=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E146=\"Arterial\",IF(Tool!I80>Tool!G80,0,IF(Tool!G80>0,Tool!G80,\"\")),\"\")","v":""},{"$f":"IF(AND(E146=Tool!$G$10,Tool!H80>0),Tool!H80,\"\")","v":""},{"$f":"IF(E146=\"Arterial\",IF(Tool!I80>Tool!G80,Tool!G80,IF(Tool!I80>=0,Tool!I80,0)),\"\")","v":""},{"$f":"IF(E146=\"Arterial\",Tool!J80,\"\")","v":""},"",{"$f":"IF(E146=\"Arterial\",Tool!O80,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=18,E128<=30),18,\"\")","v":""},{"$f":"IF(D25>=$D$2,\"\",IF($D$2<(Tool!E80-Tool!$D$64),\"\",IF(Tool!D81<>\"\",IF(Tool!$D$64<>0,Tool!E80-Tool!$D$64,Tool!E80),\"\")))","v":""},{"$f":"IF(C26=\"\",\"\",IF(B148=\"\",$D$2,IF((D25-$C$9)>=$D$2,\"\",IF(Tool!E80<>\"\",IF(AND($D$2>=(Tool!E81-Tool!$D$64),(Tool!E82-Tool!$D$64)>=(Tool!E81-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E81-Tool!$D$64,Tool!E81),$D$2),\"\"))))","v":""},{"$f":"IF(C147=\"\",\"\",IF(B147<>\"\",IF(Tool!F81=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E147=\"Arterial\",IF(Tool!I81>Tool!G81,0,IF(Tool!G81>0,Tool!G81,\"\")),\"\")","v":""},{"$f":"IF(AND(E147=Tool!$G$10,Tool!H81>0),Tool!H81,\"\")","v":""},{"$f":"IF(E147=\"Arterial\",IF(Tool!I81>Tool!G81,Tool!G81,IF(Tool!I81>=0,Tool!I81,0)),\"\")","v":""},{"$f":"IF(E147=\"Arterial\",Tool!J81,\"\")","v":""},"",{"$f":"IF(E147=\"Arterial\",Tool!O81,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=19,E128<=30),19,\"\")","v":""},{"$f":"IF(D26>=$D$2,\"\",IF($D$2<(Tool!E81-Tool!$D$64),\"\",IF(Tool!D82<>\"\",IF(Tool!$D$64<>0,Tool!E81-Tool!$D$64,Tool!E81),\"\")))","v":""},{"$f":"IF(C27=\"\",\"\",IF(B149=\"\",$D$2,IF((D26-$C$9)>=$D$2,\"\",IF(Tool!E81<>\"\",IF(AND($D$2>=(Tool!E82-Tool!$D$64),(Tool!E83-Tool!$D$64)>=(Tool!E82-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E82-Tool!$D$64,Tool!E82),$D$2),\"\"))))","v":""},{"$f":"IF(C148=\"\",\"\",IF(B148<>\"\",IF(Tool!F82=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E148=\"Arterial\",IF(Tool!I82>Tool!G82,0,IF(Tool!G82>0,Tool!G82,\"\")),\"\")","v":""},{"$f":"IF(AND(E148=Tool!$G$10,Tool!H82>0),Tool!H82,\"\")","v":""},{"$f":"IF(E148=\"Arterial\",IF(Tool!I82>Tool!G82,Tool!G82,IF(Tool!I82>=0,Tool!I82,0)),\"\")","v":""},{"$f":"IF(E148=\"Arterial\",Tool!J82,\"\")","v":""},"",{"$f":"IF(E148=\"Arterial\",Tool!O82,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=20,E128<=30),20,\"\")","v":""},{"$f":"IF(D27>=$D$2,\"\",IF($D$2<(Tool!E82-Tool!$D$64),\"\",IF(Tool!D83<>\"\",IF(Tool!$D$64<>0,Tool!E82-Tool!$D$64,Tool!E82),\"\")))","v":""},{"$f":"IF(C28=\"\",\"\",IF(B150=\"\",$D$2,IF((D27-$C$9)>=$D$2,\"\",IF(Tool!E82<>\"\",IF(AND($D$2>=(Tool!E83-Tool!$D$64),(Tool!E84-Tool!$D$64)>=(Tool!E83-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E83-Tool!$D$64,Tool!E83),$D$2),\"\"))))","v":""},{"$f":"IF(C149=\"\",\"\",IF(B149<>\"\",IF(Tool!F83=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E149=\"Arterial\",IF(Tool!I83>Tool!G83,0,IF(Tool!G83>0,Tool!G83,\"\")),\"\")","v":""},{"$f":"IF(AND(E149=Tool!$G$10,Tool!H83>0),Tool!H83,\"\")","v":""},{"$f":"IF(E149=\"Arterial\",IF(Tool!I83>Tool!G83,Tool!G83,IF(Tool!I83>=0,Tool!I83,0)),\"\")","v":""},{"$f":"IF(E149=\"Arterial\",Tool!J83,\"\")","v":""},"",{"$f":"IF(E149=\"Arterial\",Tool!O83,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=21,E128<=30),21,\"\")","v":""},{"$f":"IF(D28>=$D$2,\"\",IF($D$2<(Tool!E83-Tool!$D$64),\"\",IF(Tool!D84<>\"\",IF(Tool!$D$64<>0,Tool!E83-Tool!$D$64,Tool!E83),\"\")))","v":""},{"$f":"IF(C29=\"\",\"\",IF(B151=\"\",$D$2,IF((D28-$C$9)>=$D$2,\"\",IF(Tool!E83<>\"\",IF(AND($D$2>=(Tool!E84-Tool!$D$64),(Tool!E85-Tool!$D$64)>=(Tool!E84-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E84-Tool!$D$64,Tool!E84),$D$2),\"\"))))","v":""},{"$f":"IF(C150=\"\",\"\",IF(B150<>\"\",IF(Tool!F84=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E150=\"Arterial\",IF(Tool!I84>Tool!G84,0,IF(Tool!G84>0,Tool!G84,\"\")),\"\")","v":""},{"$f":"IF(AND(E150=Tool!$G$10,Tool!H84>0),Tool!H84,\"\")","v":""},{"$f":"IF(E150=\"Arterial\",IF(Tool!I84>Tool!G84,Tool!G84,IF(Tool!I84>=0,Tool!I84,0)),\"\")","v":""},{"$f":"IF(E150=\"Arterial\",Tool!J84,\"\")","v":""},"",{"$f":"IF(E150=\"Arterial\",Tool!O84,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=22,E128<=30),22,\"\")","v":""},{"$f":"IF(D29>=$D$2,\"\",IF($D$2<(Tool!E84-Tool!$D$64),\"\",IF(Tool!D85<>\"\",IF(Tool!$D$64<>0,Tool!E84-Tool!$D$64,Tool!E84),\"\")))","v":""},{"$f":"IF(C30=\"\",\"\",IF(B152=\"\",$D$2,IF((D29-$C$9)>=$D$2,\"\",IF(Tool!E84<>\"\",IF(AND($D$2>=(Tool!E85-Tool!$D$64),(Tool!E86-Tool!$D$64)>=(Tool!E85-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E85-Tool!$D$64,Tool!E85),$D$2),\"\"))))","v":""},{"$f":"IF(C151=\"\",\"\",IF(B151<>\"\",IF(Tool!F85=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E151=\"Arterial\",IF(Tool!I85>Tool!G85,0,IF(Tool!G85>0,Tool!G85,\"\")),\"\")","v":""},{"$f":"IF(AND(E151=Tool!$G$10,Tool!H85>0),Tool!H85,\"\")","v":""},{"$f":"IF(E151=\"Arterial\",IF(Tool!I85>Tool!G85,Tool!G85,IF(Tool!I85>=0,Tool!I85,0)),\"\")","v":""},{"$f":"IF(E151=\"Arterial\",Tool!J85,\"\")","v":""},"",{"$f":"IF(E151=\"Arterial\",Tool!O85,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=23,E128<=30),23,\"\")","v":""},{"$f":"IF(D30>=$D$2,\"\",IF($D$2<(Tool!E85-Tool!$D$64),\"\",IF(Tool!D86<>\"\",IF(Tool!$D$64<>0,Tool!E85-Tool!$D$64,Tool!E85),\"\")))","v":""},{"$f":"IF(C31=\"\",\"\",IF(B153=\"\",$D$2,IF((D30-$C$9)>=$D$2,\"\",IF(Tool!E85<>\"\",IF(AND($D$2>=(Tool!E86-Tool!$D$64),(Tool!E87-Tool!$D$64)>=(Tool!E86-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E86-Tool!$D$64,Tool!E86),$D$2),\"\"))))","v":""},{"$f":"IF(C152=\"\",\"\",IF(B152<>\"\",IF(Tool!F86=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E152=\"Arterial\",IF(Tool!I86>Tool!G86,0,IF(Tool!G86>0,Tool!G86,\"\")),\"\")","v":""},{"$f":"IF(AND(E152=Tool!$G$10,Tool!H86>0),Tool!H86,\"\")","v":""},{"$f":"IF(E152=\"Arterial\",IF(Tool!I86>Tool!G86,Tool!G86,IF(Tool!I86>=0,Tool!I86,0)),\"\")","v":""},{"$f":"IF(E152=\"Arterial\",Tool!J86,\"\")","v":""},"",{"$f":"IF(E152=\"Arterial\",Tool!O86,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=24,E128<=30),24,\"\")","v":""},{"$f":"IF(D31>=$D$2,\"\",IF($D$2<(Tool!E86-Tool!$D$64),\"\",IF(Tool!D87<>\"\",IF(Tool!$D$64<>0,Tool!E86-Tool!$D$64,Tool!E86),\"\")))","v":""},{"$f":"IF(C32=\"\",\"\",IF(B154=\"\",$D$2,IF((D31-$C$9)>=$D$2,\"\",IF(Tool!E86<>\"\",IF(AND($D$2>=(Tool!E87-Tool!$D$64),(Tool!E88-Tool!$D$64)>=(Tool!E87-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E87-Tool!$D$64,Tool!E87),$D$2),\"\"))))","v":""},{"$f":"IF(C153=\"\",\"\",IF(B153<>\"\",IF(Tool!F87=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E153=\"Arterial\",IF(Tool!I87>Tool!G87,0,IF(Tool!G87>0,Tool!G87,\"\")),\"\")","v":""},{"$f":"IF(AND(E153=Tool!$G$10,Tool!H87>0),Tool!H87,\"\")","v":""},{"$f":"IF(E153=\"Arterial\",IF(Tool!I87>Tool!G87,Tool!G87,IF(Tool!I87>=0,Tool!I87,0)),\"\")","v":""},{"$f":"IF(E153=\"Arterial\",Tool!J87,\"\")","v":""},"",{"$f":"IF(E153=\"Arterial\",Tool!O87,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=25,E128<=30),25,\"\")","v":""},{"$f":"IF(D32>=$D$2,\"\",IF($D$2<(Tool!E87-Tool!$D$64),\"\",IF(Tool!D88<>\"\",IF(Tool!$D$64<>0,Tool!E87-Tool!$D$64,Tool!E87),\"\")))","v":""},{"$f":"IF(C33=\"\",\"\",IF(B155=\"\",$D$2,IF((D32-$C$9)>=$D$2,\"\",IF(Tool!E87<>\"\",IF(AND($D$2>=(Tool!E88-Tool!$D$64),(Tool!E89-Tool!$D$64)>=(Tool!E88-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E88-Tool!$D$64,Tool!E88),$D$2),\"\"))))","v":""},{"$f":"IF(C154=\"\",\"\",IF(B154<>\"\",IF(Tool!F88=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E154=\"Arterial\",IF(Tool!I88>Tool!G88,0,IF(Tool!G88>0,Tool!G88,\"\")),\"\")","v":""},{"$f":"IF(AND(E154=Tool!$G$10,Tool!H88>0),Tool!H88,\"\")","v":""},{"$f":"IF(E154=\"Arterial\",IF(Tool!I88>Tool!G88,Tool!G88,IF(Tool!I88>=0,Tool!I88,0)),\"\")","v":""},{"$f":"IF(E154=\"Arterial\",Tool!J88,\"\")","v":""},"",{"$f":"IF(E154=\"Arterial\",Tool!O88,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=26,E128<=30),26,\"\")","v":""},{"$f":"IF(D33>=$D$2,\"\",IF($D$2<(Tool!E88-Tool!$D$64),\"\",IF(Tool!D89<>\"\",IF(Tool!$D$64<>0,Tool!E88-Tool!$D$64,Tool!E88),\"\")))","v":""},{"$f":"IF(C34=\"\",\"\",IF(B156=\"\",$D$2,IF((D33-$C$9)>=$D$2,\"\",IF(Tool!E88<>\"\",IF(AND($D$2>=(Tool!E89-Tool!$D$64),(Tool!E90-Tool!$D$64)>=(Tool!E89-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E89-Tool!$D$64,Tool!E89),$D$2),\"\"))))","v":""},{"$f":"IF(C155=\"\",\"\",IF(B155<>\"\",IF(Tool!F89=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E155=\"Arterial\",IF(Tool!I89>Tool!G89,0,IF(Tool!G89>0,Tool!G89,\"\")),\"\")","v":""},{"$f":"IF(AND(E155=Tool!$G$10,Tool!H89>0),Tool!H89,\"\")","v":""},{"$f":"IF(E155=\"Arterial\",IF(Tool!I89>Tool!G89,Tool!G89,IF(Tool!I89>=0,Tool!I89,0)),\"\")","v":""},{"$f":"IF(E155=\"Arterial\",Tool!J89,\"\")","v":""},"",{"$f":"IF(E155=\"Arterial\",Tool!O89,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=27,E128<=30),27,\"\")","v":""},{"$f":"IF(D34>=$D$2,\"\",IF($D$2<(Tool!E89-Tool!$D$64),\"\",IF(Tool!D90<>\"\",IF(Tool!$D$64<>0,Tool!E89-Tool!$D$64,Tool!E89),\"\")))","v":""},{"$f":"IF(C35=\"\",\"\",IF(B157=\"\",$D$2,IF((D34-$C$9)>=$D$2,\"\",IF(Tool!E89<>\"\",IF(AND($D$2>=(Tool!E90-Tool!$D$64),(Tool!E91-Tool!$D$64)>=(Tool!E90-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E90-Tool!$D$64,Tool!E90),$D$2),\"\"))))","v":""},{"$f":"IF(C156=\"\",\"\",IF(B156<>\"\",IF(Tool!F90=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E156=\"Arterial\",IF(Tool!I90>Tool!G90,0,IF(Tool!G90>0,Tool!G90,\"\")),\"\")","v":""},{"$f":"IF(AND(E156=Tool!$G$10,Tool!H90>0),Tool!H90,\"\")","v":""},{"$f":"IF(E156=\"Arterial\",IF(Tool!I90>Tool!G90,Tool!G90,IF(Tool!I90>=0,Tool!I90,0)),\"\")","v":""},{"$f":"IF(E156=\"Arterial\",Tool!J90,\"\")","v":""},"",{"$f":"IF(E156=\"Arterial\",Tool!O90,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=28,E128<=30),28,\"\")","v":""},{"$f":"IF(D35>=$D$2,\"\",IF($D$2<(Tool!E90-Tool!$D$64),\"\",IF(Tool!D91<>\"\",IF(Tool!$D$64<>0,Tool!E90-Tool!$D$64,Tool!E90),\"\")))","v":""},{"$f":"IF(C36=\"\",\"\",IF(B158=\"\",$D$2,IF((D35-$C$9)>=$D$2,\"\",IF(Tool!E90<>\"\",IF(AND($D$2>=(Tool!E91-Tool!$D$64),(Tool!E92-Tool!$D$64)>=(Tool!E91-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E91-Tool!$D$64,Tool!E91),$D$2),\"\"))))","v":""},{"$f":"IF(C157=\"\",\"\",IF(B157<>\"\",IF(Tool!F91=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E157=\"Arterial\",IF(Tool!I91>Tool!G91,0,IF(Tool!G91>0,Tool!G91,\"\")),\"\")","v":""},{"$f":"IF(AND(E157=Tool!$G$10,Tool!H91>0),Tool!H91,\"\")","v":""},{"$f":"IF(E157=\"Arterial\",IF(Tool!I91>Tool!G91,Tool!G91,IF(Tool!I91>=0,Tool!I91,0)),\"\")","v":""},{"$f":"IF(E157=\"Arterial\",Tool!J91,\"\")","v":""},"",{"$f":"IF(E157=\"Arterial\",Tool!O91,\"\")","v":""},""]
[null,{"$f":"IF(AND(E128>=29,E128<=30),29,\"\")","v":""},{"$f":"IF(D36>=$D$2,\"\",IF($D$2<(Tool!E91-Tool!$D$64),\"\",IF(Tool!D92<>\"\",IF(Tool!$D$64<>0,Tool!E91-Tool!$D$64,Tool!E91),\"\")))","v":""},{"$f":"IF(C37=\"\",\"\",IF(B159=\"\",$D$2,IF((D36-$C$9)>=$D$2,\"\",IF(Tool!E91<>\"\",IF(AND($D$2>=(Tool!E92-Tool!$D$64),(Tool!E93-Tool!$D$64)>=(Tool!E92-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E92-Tool!$D$64,Tool!E92),$D$2),\"\"))))","v":""},{"$f":"IF(C158=\"\",\"\",IF(B158<>\"\",IF(Tool!F92=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E158=\"Arterial\",IF(Tool!I92>Tool!G92,0,IF(Tool!G92>0,Tool!G92,\"\")),\"\")","v":""},{"$f":"IF(AND(E158=Tool!$G$10,Tool!H92>0),Tool!H92,\"\")","v":""},{"$f":"IF(E158=\"Arterial\",IF(Tool!I92>Tool!G92,Tool!G92,IF(Tool!I92>=0,Tool!I92,0)),\"\")","v":""},{"$f":"IF(E158=\"Arterial\",Tool!J92,\"\")","v":""},"",{"$f":"IF(E158=\"Arterial\",Tool!O92,\"\")","v":""},""]
[null,{"$f":"IF(E128=30,30,\"\")","v":""},{"$f":"IF(D37>=$D$2,\"\",IF($D$2<(Tool!E92-Tool!$D$64),\"\",IF(Tool!D93<>\"\",IF(Tool!$D$64<>0,Tool!E92-Tool!$D$64,Tool!E92),\"\")))","v":""},{"$f":"IF(C38=\"\",\"\",IF(B160=\"\",$D$2,IF((D37-$C$9)>=$D$2,\"\",IF(Tool!E92<>\"\",IF(AND($D$2>=(Tool!E93-Tool!$D$64),(Tool!E94-Tool!$D$64)>=(Tool!E93-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E93-Tool!$D$64,Tool!E93),$D$2),\"\"))))","v":""},{"$f":"IF(C159=\"\",\"\",IF(B159<>\"\",IF(Tool!F93=Tool!$G$10,\"Arterial\",\"\"),\"\"))","v":""},{"$f":"IF(E159=\"Arterial\",IF(Tool!I93>Tool!G93,0,IF(Tool!G93>0,Tool!G93,\"\")),\"\")","v":""},{"$f":"IF(AND(E159=Tool!$G$10,Tool!H93>0),Tool!H93,\"\")","v":""},{"$f":"IF(E159=\"Arterial\",IF(Tool!I93>Tool!G93,Tool!G93,IF(Tool!I93>=0,Tool!I93,0)),\"\")","v":""},{"$f":"IF(E159=\"Arterial\",Tool!J93,\"\")","v":""},"",{"$f":"IF(E159=\"Arterial\",Tool!O93,\"\")","v":""},""]
[]
[null,null,null,null,null,null,"Average Widening Width",{"$f":"IFERROR((SUMPRODUCT(F130:F159,J130:J159)/SUM(J130:J159))-(SUMPRODUCT(H130:H159,J130:J159)/SUM(J130:J159)),0)","v":0},"Average Additional Full Depth:",{"$f":"IFERROR(SUMPRODUCT(--(I130:I159=\"Yes\"),H130:H159,J130:J159)/SUM(J130:J159),0)","v":0},"Area",{"$f":"H164*J161*5280","v":0}]
[null,null,null,null,null,null,"Average Shoulder Width:",{"$f":"IF(SUM(J130:J159)>0,(SUMPRODUCT(G130:G159,J130:J159)/SUM(J130:J159))*2,0)","v":0},"Total Full Depth Width:",{"$f":"H161+J161","v":0}]
[null,null,null,null,null,null,"Average Resurface Pavement:",{"$f":"IFERROR(SUMPRODUCT(--(I130:I159=\"No\"),H130:H159,J130:J159)/SUM(J130:J159),0)","v":0},"Average Roadway Width:",{"$f":"IFERROR(SUMPRODUCT(U119:U138,V119:V138)/SUM(V119:V138),0)","v":0}]
[null,null,null,null,null,null,"Length:",{"$f":"SUM(J130:J159)","v":0}]
[null,null,null,null,null,null,"Perimeter Length",{"$f":"SUM(L130:L159)","v":0}]
[null,"Proposed Pavement Width"]
[null,"Freeway"]
[null,"Segments:",null,null,{"$f":"Tool!$J$61","v":1}]
[null,"Segments","Begin","End","Pavement Type","Total Pavement Width(ft)","Outside Shoulder Width (ft)","Existing Pavement Width","Replace Existing Pavement?","Length","Widen to One Side or Both?","Perimeter Length"]
[null,{"$f":"IF(AND(E168>=1,E168<=30),1,\"\")","v":1},{"$f":"IF(Tool!D64<>\"\",IF(B9<>\"\",IF(Tool!D64=0,Tool!D64,Tool!D64-Tool!D64),\"\"),\"\")","v":""},{"$f":"IF(C9=\"\",\"\",IF((Tool!E65-Tool!D64)<(Tool!E64-Tool!D64),D2,IF(B9<>\"\",IF(Tool!E64<>\"\",IF(AND(B10=\"\",Tool!E64-Tool!D64<$D$2),$D$2,IF(B9=1,IF($D$2<(Tool!E64-Tool!$D$64),$D$2,IF(Tool!D64<>0,(Tool!E64-Tool!D64),Tool!E64)),\"\")),\"\"),\"\")))","v":""},{"$f":"IF(B170<>\"\",IF(Tool!F64=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E170=\"Freeway\",IF(Tool!I64>Tool!G64,0,IF(Tool!G64>0,Tool!G64,\"\")),\"\")","v":""},{"$f":"IF(AND($E170=Tool!$G$11,Tool!H64>0),Tool!H64,\"\")","v":""},{"$f":"IF(E170=\"Freeway\",IF(Tool!I64>Tool!G64,Tool!G64,IF(Tool!I64>=0,Tool!I64,0)),\"\")","v":""},{"$f":"IF(E170=\"Freeway\",Tool!J64,\"\")","v":""},{"$f":"IF(F170<>\"\",IF(OR(C170=\"\",D170=\"\"),\"\",IF(E170=\"Freeway\",D170-C170,\"\")),\"\")","v":""},{"$f":"IF(E170=\"Freeway\",Tool!O64,\"\")","v":""},{"$f":"IFERROR(IF(AND(K170=\"One Side\",OR((F170-H170)>0,G170<>\"\")),J170,IF(AND(K170=\"Both Sides\",OR((F170-H170)>0,G170<>\"\")),J170*2,0)),\"\")","v":""}]
[null,{"$f":"IF(AND(E168>=2,E168<=30),2,\"\")","v":""},{"$f":"IF(D9>=$D$2,\"\",IF($D$2<(Tool!E64-Tool!$D$64),\"\",IF(Tool!D65<>\"\",IF(Tool!$D$64<>0,Tool!E64-Tool!$D$64,Tool!E64),\"\")))","v":""},{"$f":"IF(C10=\"\",\"\",IF(B172=\"\",$D$2,IF((D9-$C$9)>=$D$2,\"\",IF(Tool!E64<>\"\",IF(AND($D$2>=(Tool!E65-Tool!$D$64),(Tool!E66-Tool!$D$64)>=(Tool!E65-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E65-Tool!$D$64,Tool!E65),$D$2),\"\"))))","v":""},{"$f":"IF(B171<>\"\",IF(Tool!F65=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E171=\"Freeway\",IF(Tool!I65>Tool!G65,0,IF(Tool!G65>0,Tool!G65,\"\")),\"\")","v":""},{"$f":"IF(AND(E171=Tool!$G$11,Tool!H65>0),Tool!H65,\"\")","v":""},{"$f":"IF(E171=\"Freeway\",IF(Tool!I65>Tool!G65,Tool!G65,IF(Tool!I65>=0,Tool!I65,0)),\"\")","v":""},{"$f":"IF(E171=\"Freeway\",Tool!J65,\"\")","v":""},{"$f":"IF(F171<>\"\",IF(OR(C171=\"\",D171=\"\"),\"\",IF(E171=\"Freeway\",D171-C171,\"\")),\"\")","v":""},{"$f":"IF(E171=\"Freeway\",Tool!O65,\"\")","v":""},{"$f":"IFERROR(IF(AND(K171=\"One Side\",OR((F171-H171)>0,G171<>\"\")),J171,IF(AND(K171=\"Both Sides\",OR((F171-H171)>0,G171<>\"\")),J171*2,0)),\"\")","v":""}]
[null,{"$f":"IF(AND(E168>=3,E168<=30),3,\"\")","v":""},{"$f":"IF(D10>=$D$2,\"\",IF($D$2<(Tool!E65-Tool!$D$64),\"\",IF(Tool!D66<>\"\",IF(Tool!$D$64<>0,Tool!E65-Tool!$D$64,Tool!E65),\"\")))","v":""},{"$f":"IF(C11=\"\",\"\",IF(B173=\"\",$D$2,IF((D10-$C$9)>=$D$2,\"\",IF(Tool!E65<>\"\",IF(AND($D$2>=(Tool!E66-Tool!$D$64),(Tool!E67-Tool!$D$64)>=(Tool!E66-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E66-Tool!$D$64,Tool!E66),$D$2),\"\"))))","v":""},{"$f":"IF(B172<>\"\",IF(Tool!F66=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E172=\"Freeway\",IF(Tool!I66>Tool!G66,0,IF(Tool!G66>0,Tool!G66,\"\")),\"\")","v":""},{"$f":"IF(AND(E172=Tool!$G$11,Tool!H66>0),Tool!H66,\"\")","v":""},{"$f":"IF(E172=\"Freeway\",IF(Tool!I66>Tool!G66,Tool!G66,IF(Tool!I66>=0,Tool!I66,0)),\"\")","v":""},{"$f":"IF(E172=\"Freeway\",Tool!J66,\"\")","v":""},{"$f":"IF(F172<>\"\",IF(OR(C172=\"\",D172=\"\"),\"\",IF(E172=\"Freeway\",D172-C172,\"\")),\"\")","v":""},{"$f":"IF(E172=\"Freeway\",Tool!O66,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=4,E168<=30),4,\"\")","v":""},{"$f":"IF(D11>=$D$2,\"\",IF($D$2<(Tool!E66-Tool!$D$64),\"\",IF(Tool!D67<>\"\",IF(Tool!$D$64<>0,Tool!E66-Tool!$D$64,Tool!E66),\"\")))","v":""},{"$f":"IF(C12=\"\",\"\",IF(B174=\"\",$D$2,IF((D11-$C$9)>=$D$2,\"\",IF(Tool!E66<>\"\",IF(AND($D$2>=(Tool!E67-Tool!$D$64),(Tool!E68-Tool!$D$64)>=(Tool!E67-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E67-Tool!$D$64,Tool!E67),$D$2),\"\"))))","v":""},{"$f":"IF(B173<>\"\",IF(Tool!F67=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E173=\"Freeway\",IF(Tool!I67>Tool!G67,0,IF(Tool!G67>0,Tool!G67,\"\")),\"\")","v":""},{"$f":"IF(AND(E173=Tool!$G$11,Tool!H67>0),Tool!H67,\"\")","v":""},{"$f":"IF(E173=\"Freeway\",IF(Tool!I67>Tool!G67,Tool!G67,IF(Tool!I67>=0,Tool!I67,0)),\"\")","v":""},{"$f":"IF(E173=\"Freeway\",Tool!J67,\"\")","v":""},"",{"$f":"IF(E173=\"Freeway\",Tool!O67,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=5,E168<=30),5,\"\")","v":""},{"$f":"IF(D12>=$D$2,\"\",IF($D$2<(Tool!E67-Tool!$D$64),\"\",IF(Tool!D68<>\"\",IF(Tool!$D$64<>0,Tool!E67-Tool!$D$64,Tool!E67),\"\")))","v":""},{"$f":"IF(C13=\"\",\"\",IF(B175=\"\",$D$2,IF((D12-$C$9)>=$D$2,\"\",IF(Tool!E67<>\"\",IF(AND($D$2>=(Tool!E68-Tool!$D$64),(Tool!E69-Tool!$D$64)>=(Tool!E68-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E68-Tool!$D$64,Tool!E68),$D$2),\"\"))))","v":""},{"$f":"IF(B174<>\"\",IF(Tool!F68=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E174=\"Freeway\",IF(Tool!I68>Tool!G68,0,IF(Tool!G68>0,Tool!G68,\"\")),\"\")","v":""},{"$f":"IF(AND(E174=Tool!$G$11,Tool!H68>0),Tool!H68,\"\")","v":""},{"$f":"IF(E174=\"Freeway\",IF(Tool!I68>Tool!G68,Tool!G68,IF(Tool!I68>=0,Tool!I68,0)),\"\")","v":""},{"$f":"IF(E174=\"Freeway\",Tool!J68,\"\")","v":""},"",{"$f":"IF(E174=\"Freeway\",Tool!O68,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=6,E168<=30),6,\"\")","v":""},{"$f":"IF(D13>=$D$2,\"\",IF($D$2<(Tool!E68-Tool!$D$64),\"\",IF(Tool!D69<>\"\",IF(Tool!$D$64<>0,Tool!E68-Tool!$D$64,Tool!E68),\"\")))","v":""},{"$f":"IF(C14=\"\",\"\",IF(B176=\"\",$D$2,IF((D13-$C$9)>=$D$2,\"\",IF(Tool!E68<>\"\",IF(AND($D$2>=(Tool!E69-Tool!$D$64),(Tool!E70-Tool!$D$64)>=(Tool!E69-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E69-Tool!$D$64,Tool!E69),$D$2),\"\"))))","v":""},{"$f":"IF(B175<>\"\",IF(Tool!F69=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E175=\"Freeway\",IF(Tool!I69>Tool!G69,0,IF(Tool!G69>0,Tool!G69,\"\")),\"\")","v":""},{"$f":"IF(AND(E175=Tool!$G$11,Tool!H69>0),Tool!H69,\"\")","v":""},{"$f":"IF(E175=\"Freeway\",IF(Tool!I69>Tool!G69,Tool!G69,IF(Tool!I69>=0,Tool!I69,0)),\"\")","v":""},{"$f":"IF(E175=\"Freeway\",Tool!J69,\"\")","v":""},"",{"$f":"IF(E175=\"Freeway\",Tool!O69,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=7,E168<=30),7,\"\")","v":""},{"$f":"IF(D14>=$D$2,\"\",IF($D$2<(Tool!E69-Tool!$D$64),\"\",IF(Tool!D70<>\"\",IF(Tool!$D$64<>0,Tool!E69-Tool!$D$64,Tool!E69),\"\")))","v":""},{"$f":"IF(C15=\"\",\"\",IF(B177=\"\",$D$2,IF((D14-$C$9)>=$D$2,\"\",IF(Tool!E69<>\"\",IF(AND($D$2>=(Tool!E70-Tool!$D$64),(Tool!E71-Tool!$D$64)>=(Tool!E70-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E70-Tool!$D$64,Tool!E70),$D$2),\"\"))))","v":""},{"$f":"IF(B176<>\"\",IF(Tool!F70=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E176=\"Freeway\",IF(Tool!I70>Tool!G70,0,IF(Tool!G70>0,Tool!G70,\"\")),\"\")","v":""},{"$f":"IF(AND(E176=Tool!$G$11,Tool!H70>0),Tool!H70,\"\")","v":""},{"$f":"IF(E176=\"Freeway\",IF(Tool!I70>Tool!G70,Tool!G70,IF(Tool!I70>=0,Tool!I70,0)),\"\")","v":""},{"$f":"IF(E176=\"Freeway\",Tool!J70,\"\")","v":""},"",{"$f":"IF(E176=\"Freeway\",Tool!O70,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=8,E168<=30),8,\"\")","v":""},{"$f":"IF(D15>=$D$2,\"\",IF($D$2<(Tool!E70-Tool!$D$64),\"\",IF(Tool!D71<>\"\",IF(Tool!$D$64<>0,Tool!E70-Tool!$D$64,Tool!E70),\"\")))","v":""},{"$f":"IF(C16=\"\",\"\",IF(B178=\"\",$D$2,IF((D15-$C$9)>=$D$2,\"\",IF(Tool!E70<>\"\",IF(AND($D$2>=(Tool!E71-Tool!$D$64),(Tool!E72-Tool!$D$64)>=(Tool!E71-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E71-Tool!$D$64,Tool!E71),$D$2),\"\"))))","v":""},{"$f":"IF(B177<>\"\",IF(Tool!F71=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E177=\"Freeway\",IF(Tool!I71>Tool!G71,0,IF(Tool!G71>0,Tool!G71,\"\")),\"\")","v":""},{"$f":"IF(AND(E177=Tool!$G$11,Tool!H71>0),Tool!H71,\"\")","v":""},{"$f":"IF(E177=\"Freeway\",IF(Tool!I71>Tool!G71,Tool!G71,IF(Tool!I71>=0,Tool!I71,0)),\"\")","v":""},{"$f":"IF(E177=\"Freeway\",Tool!J71,\"\")","v":""},"",{"$f":"IF(E177=\"Freeway\",Tool!O71,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=9,F168<=20),9,\"\")","v":""},{"$f":"IF(D16>=$D$2,\"\",IF($D$2<(Tool!E71-Tool!$D$64),\"\",IF(Tool!D72<>\"\",IF(Tool!$D$64<>0,Tool!E71-Tool!$D$64,Tool!E71),\"\")))","v":""},{"$f":"IF(C17=\"\",\"\",IF(B179=\"\",$D$2,IF((D16-$C$9)>=$D$2,\"\",IF(Tool!E71<>\"\",IF(AND($D$2>=(Tool!E72-Tool!$D$64),(Tool!E73-Tool!$D$64)>=(Tool!E72-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E72-Tool!$D$64,Tool!E72),$D$2),\"\"))))","v":""},{"$f":"IF(B178<>\"\",IF(Tool!F72=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E178=\"Freeway\",IF(Tool!I72>Tool!G72,0,IF(Tool!G72>0,Tool!G72,\"\")),\"\")","v":""},{"$f":"IF(AND(E178=Tool!$G$11,Tool!H72>0),Tool!H72,\"\")","v":""},{"$f":"IF(E178=\"Freeway\",IF(Tool!I72>Tool!G72,Tool!G72,IF(Tool!I72>=0,Tool!I72,0)),\"\")","v":""},{"$f":"IF(E178=\"Freeway\",Tool!J72,\"\")","v":""},"",{"$f":"IF(E178=\"Freeway\",Tool!O72,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=10,E168<=30),10,\"\")","v":""},{"$f":"IF(D17>=$D$2,\"\",IF($D$2<(Tool!E72-Tool!$D$64),\"\",IF(Tool!D73<>\"\",IF(Tool!$D$64<>0,Tool!E72-Tool!$D$64,Tool!E72),\"\")))","v":""},{"$f":"IF(C18=\"\",\"\",IF(B180=\"\",$D$2,IF((D17-$C$9)>=$D$2,\"\",IF(Tool!E72<>\"\",IF(AND($D$2>=(Tool!E73-Tool!$D$64),(Tool!E74-Tool!$D$64)>=(Tool!E73-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E73-Tool!$D$64,Tool!E73),$D$2),\"\"))))","v":""},{"$f":"IF(B179<>\"\",IF(Tool!F73=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E179=\"Freeway\",IF(Tool!I73>Tool!G73,0,IF(Tool!G73>0,Tool!G73,\"\")),\"\")","v":""},{"$f":"IF(AND(E179=Tool!$G$11,Tool!H73>0),Tool!H73,\"\")","v":""},{"$f":"IF(E179=\"Freeway\",IF(Tool!I73>Tool!G73,Tool!G73,IF(Tool!I73>=0,Tool!I73,0)),\"\")","v":""},{"$f":"IF(E179=\"Freeway\",Tool!J73,\"\")","v":""},"",{"$f":"IF(E179=\"Freeway\",Tool!O73,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=11,E168<=30),11,\"\")","v":""},{"$f":"IF(D18>=$D$2,\"\",IF($D$2<(Tool!E73-Tool!$D$64),\"\",IF(Tool!D74<>\"\",IF(Tool!$D$64<>0,Tool!E73-Tool!$D$64,Tool!E73),\"\")))","v":""},{"$f":"IF(C19=\"\",\"\",IF(B181=\"\",$D$2,IF((D18-$C$9)>=$D$2,\"\",IF(Tool!E73<>\"\",IF(AND($D$2>=(Tool!E74-Tool!$D$64),(Tool!E75-Tool!$D$64)>=(Tool!E74-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E74-Tool!$D$64,Tool!E74),$D$2),\"\"))))","v":""},{"$f":"IF(B180<>\"\",IF(Tool!F74=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E180=\"Freeway\",IF(Tool!I74>Tool!G74,0,IF(Tool!G74>0,Tool!G74,\"\")),\"\")","v":""},{"$f":"IF(AND(E180=Tool!$G$11,Tool!H74>0),Tool!H74,\"\")","v":""},{"$f":"IF(E180=\"Freeway\",IF(Tool!I74>Tool!G74,Tool!G74,IF(Tool!I74>=0,Tool!I74,0)),\"\")","v":""},{"$f":"IF(E180=\"Freeway\",Tool!J74,\"\")","v":""},"",{"$f":"IF(E180=\"Freeway\",Tool!O74,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=12,F168<=30),12,\"\")","v":""},{"$f":"IF(D19>=$D$2,\"\",IF($D$2<(Tool!E74-Tool!$D$64),\"\",IF(Tool!D75<>\"\",IF(Tool!$D$64<>0,Tool!E74-Tool!$D$64,Tool!E74),\"\")))","v":""},{"$f":"IF(C20=\"\",\"\",IF(B182=\"\",$D$2,IF((D19-$C$9)>=$D$2,\"\",IF(Tool!E74<>\"\",IF(AND($D$2>=(Tool!E75-Tool!$D$64),(Tool!E76-Tool!$D$64)>=(Tool!E75-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E75-Tool!$D$64,Tool!E75),$D$2),\"\"))))","v":""},{"$f":"IF(B181<>\"\",IF(Tool!F75=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E181=\"Freeway\",IF(Tool!I75>Tool!G75,0,IF(Tool!G75>0,Tool!G75,\"\")),\"\")","v":""},{"$f":"IF(AND(E181=Tool!$G$11,Tool!H75>0),Tool!H75,\"\")","v":""},{"$f":"IF(E181=\"Freeway\",IF(Tool!I75>Tool!G75,Tool!G75,IF(Tool!I75>=0,Tool!I75,0)),\"\")","v":""},{"$f":"IF(E181=\"Freeway\",Tool!J75,\"\")","v":""},"",{"$f":"IF(E181=\"Freeway\",Tool!O75,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=13,E168<=30),13,\"\")","v":""},{"$f":"IF(D20>=$D$2,\"\",IF($D$2<(Tool!E75-Tool!$D$64),\"\",IF(Tool!D76<>\"\",IF(Tool!$D$64<>0,Tool!E75-Tool!$D$64,Tool!E75),\"\")))","v":""},{"$f":"IF(C21=\"\",\"\",IF(B183=\"\",$D$2,IF((D20-$C$9)>=$D$2,\"\",IF(Tool!E75<>\"\",IF(AND($D$2>=(Tool!E76-Tool!$D$64),(Tool!E77-Tool!$D$64)>=(Tool!E76-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E76-Tool!$D$64,Tool!E76),$D$2),\"\"))))","v":""},{"$f":"IF(B182<>\"\",IF(Tool!F76=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E182=\"Freeway\",IF(Tool!I76>Tool!G76,0,IF(Tool!G76>0,Tool!G76,\"\")),\"\")","v":""},{"$f":"IF(AND(E182=Tool!$G$11,Tool!H76>0),Tool!H76,\"\")","v":""},{"$f":"IF(E182=\"Freeway\",IF(Tool!I76>Tool!G76,Tool!G76,IF(Tool!I76>=0,Tool!I76,0)),\"\")","v":""},{"$f":"IF(E182=\"Freeway\",Tool!J76,\"\")","v":""},"",{"$f":"IF(E182=\"Freeway\",Tool!O76,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=14,E168<=30),14,\"\")","v":""},{"$f":"IF(D21>=$D$2,\"\",IF($D$2<(Tool!E76-Tool!$D$64),\"\",IF(Tool!D77<>\"\",IF(Tool!$D$64<>0,Tool!E76-Tool!$D$64,Tool!E76),\"\")))","v":""},{"$f":"IF(C22=\"\",\"\",IF(B184=\"\",$D$2,IF((D21-$C$9)>=$D$2,\"\",IF(Tool!E76<>\"\",IF(AND($D$2>=(Tool!E77-Tool!$D$64),(Tool!E78-Tool!$D$64)>=(Tool!E77-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E77-Tool!$D$64,Tool!E77),$D$2),\"\"))))","v":""},{"$f":"IF(B183<>\"\",IF(Tool!F77=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E183=\"Freeway\",IF(Tool!I77>Tool!G77,0,IF(Tool!G77>0,Tool!G77,\"\")),\"\")","v":""},{"$f":"IF(AND(E183=Tool!$G$11,Tool!H77>0),Tool!H77,\"\")","v":""},{"$f":"IF(E183=\"Freeway\",IF(Tool!I77>Tool!G77,Tool!G77,IF(Tool!I77>=0,Tool!I77,0)),\"\")","v":""},{"$f":"IF(E183=\"Freeway\",Tool!J77,\"\")","v":""},"",{"$f":"IF(E183=\"Freeway\",Tool!O77,\"\")","v":""},"",null,null,null,null,null,"Roadway Surface Design"]
[null,{"$f":"IF(AND(E168>=15,E168<=30),15,\"\")","v":""},{"$f":"IF(D22>=$D$2,\"\",IF($D$2<(Tool!E77-Tool!$D$64),\"\",IF(Tool!D78<>\"\",IF(Tool!$D$64<>0,Tool!E77-Tool!$D$64,Tool!E77),\"\")))","v":""},{"$f":"IF(C23=\"\",\"\",IF(B185=\"\",$D$2,IF((D22-$C$9)>=$D$2,\"\",IF(Tool!E77<>\"\",IF(AND($D$2>=(Tool!E78-Tool!$D$64),(Tool!E79-Tool!$D$64)>=(Tool!E78-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E78-Tool!$D$64,Tool!E78),$D$2),\"\"))))","v":""},{"$f":"IF(B184<>\"\",IF(Tool!F78=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E184=\"Freeway\",IF(Tool!I78>Tool!G78,0,IF(Tool!G78>0,Tool!G78,\"\")),\"\")","v":""},{"$f":"IF(AND(E184=Tool!$G$11,Tool!H78>0),Tool!H78,\"\")","v":""},{"$f":"IF(E184=\"Freeway\",IF(Tool!I78>Tool!G78,Tool!G78,IF(Tool!I78>=0,Tool!I78,0)),\"\")","v":""},{"$f":"IF(E184=\"Freeway\",Tool!J78,\"\")","v":""},"",{"$f":"IF(E184=\"Freeway\",Tool!O78,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=16,E168<=30),16,\"\")","v":""},{"$f":"IF(D23>=$D$2,\"\",IF($D$2<(Tool!E78-Tool!$D$64),\"\",IF(Tool!D79<>\"\",IF(Tool!$D$64<>0,Tool!E78-Tool!$D$64,Tool!E78),\"\")))","v":""},{"$f":"IF(C24=\"\",\"\",IF(B186=\"\",$D$2,IF((D23-$C$9)>=$D$2,\"\",IF(Tool!E78<>\"\",IF(AND($D$2>=(Tool!E79-Tool!$D$64),(Tool!E80-Tool!$D$64)>=(Tool!E79-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E79-Tool!$D$64,Tool!E79),$D$2),\"\"))))","v":""},{"$f":"IF(B185<>\"\",IF(Tool!F79=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E185=\"Freeway\",IF(Tool!I79>Tool!G79,0,IF(Tool!G79>0,Tool!G79,\"\")),\"\")","v":""},{"$f":"IF(AND(E185=Tool!$G$11,Tool!H79>0),Tool!H79,\"\")","v":""},{"$f":"IF(E185=\"Freeway\",IF(Tool!I79>Tool!G79,Tool!G79,IF(Tool!I79>=0,Tool!I79,0)),\"\")","v":""},{"$f":"IF(E185=\"Freeway\",Tool!J79,\"\")","v":""},"",{"$f":"IF(E185=\"Freeway\",Tool!O79,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=17,E168<=30),17,\"\")","v":""},{"$f":"IF(D24>=$D$2,\"\",IF($D$2<(Tool!E79-Tool!$D$64),\"\",IF(Tool!D80<>\"\",IF(Tool!$D$64<>0,Tool!E79-Tool!$D$64,Tool!E79),\"\")))","v":""},{"$f":"IF(C25=\"\",\"\",IF(B187=\"\",$D$2,IF((D24-$C$9)>=$D$2,\"\",IF(Tool!E79<>\"\",IF(AND($D$2>=(Tool!E80-Tool!$D$64),(Tool!E81-Tool!$D$64)>=(Tool!E80-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E80-Tool!$D$64,Tool!E80),$D$2),\"\"))))","v":""},{"$f":"IF(B186<>\"\",IF(Tool!F80=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E186=\"Freeway\",IF(Tool!I80>Tool!G80,0,IF(Tool!G80>0,Tool!G80,\"\")),\"\")","v":""},{"$f":"IF(AND(E186=Tool!$G$11,Tool!H80>0),Tool!H80,\"\")","v":""},{"$f":"IF(E186=\"Freeway\",IF(Tool!I80>Tool!G80,Tool!G80,IF(Tool!I80>=0,Tool!I80,0)),\"\")","v":""},{"$f":"IF(E186=\"Freeway\",Tool!J80,\"\")","v":""},"",{"$f":"IF(E186=\"Freeway\",Tool!O80,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=18,E168<=30),18,\"\")","v":""},{"$f":"IF(D25>=$D$2,\"\",IF($D$2<(Tool!E80-Tool!$D$64),\"\",IF(Tool!D81<>\"\",IF(Tool!$D$64<>0,Tool!E80-Tool!$D$64,Tool!E80),\"\")))","v":""},{"$f":"IF(C26=\"\",\"\",IF(B188=\"\",$D$2,IF((D25-$C$9)>=$D$2,\"\",IF(Tool!E80<>\"\",IF(AND($D$2>=(Tool!E81-Tool!$D$64),(Tool!E82-Tool!$D$64)>=(Tool!E81-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E81-Tool!$D$64,Tool!E81),$D$2),\"\"))))","v":""},{"$f":"IF(B187<>\"\",IF(Tool!F81=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E187=\"Freeway\",IF(Tool!I81>Tool!G81,0,IF(Tool!G81>0,Tool!G81,\"\")),\"\")","v":""},{"$f":"IF(AND(E187=Tool!$G$11,Tool!H81>0),Tool!H81,\"\")","v":""},{"$f":"IF(E187=\"Freeway\",IF(Tool!I81>Tool!G81,Tool!G81,IF(Tool!I81>=0,Tool!I81,0)),\"\")","v":""},{"$f":"IF(E187=\"Freeway\",Tool!J81,\"\")","v":""},"",{"$f":"IF(E187=\"Freeway\",Tool!O81,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=19,E168<=30),19,\"\")","v":""},{"$f":"IF(D26>=$D$2,\"\",IF($D$2<(Tool!E81-Tool!$D$64),\"\",IF(Tool!D82<>\"\",IF(Tool!$D$64<>0,Tool!E81-Tool!$D$64,Tool!E81),\"\")))","v":""},{"$f":"IF(C27=\"\",\"\",IF(B189=\"\",$D$2,IF((D26-$C$9)>=$D$2,\"\",IF(Tool!E81<>\"\",IF(AND($D$2>=(Tool!E82-Tool!$D$64),(Tool!E83-Tool!$D$64)>=(Tool!E82-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E82-Tool!$D$64,Tool!E82),$D$2),\"\"))))","v":""},{"$f":"IF(B188<>\"\",IF(Tool!F82=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E188=\"Freeway\",IF(Tool!I82>Tool!G82,0,IF(Tool!G82>0,Tool!G82,\"\")),\"\")","v":""},{"$f":"IF(AND(E188=Tool!$G$11,Tool!H82>0),Tool!H82,\"\")","v":""},{"$f":"IF(E188=\"Freeway\",IF(Tool!I82>Tool!G82,Tool!G82,IF(Tool!I82>=0,Tool!I82,0)),\"\")","v":""},{"$f":"IF(E188=\"Freeway\",Tool!J82,\"\")","v":""},"",{"$f":"IF(E188=\"Freeway\",Tool!O82,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=20,E168<=30),20,\"\")","v":""},{"$f":"IF(D27>=$D$2,\"\",IF($D$2<(Tool!E82-Tool!$D$64),\"\",IF(Tool!D83<>\"\",IF(Tool!$D$64<>0,Tool!E82-Tool!$D$64,Tool!E82),\"\")))","v":""},{"$f":"IF(C28=\"\",\"\",IF(B190=\"\",$D$2,IF((D27-$C$9)>=$D$2,\"\",IF(Tool!E82<>\"\",IF(AND($D$2>=(Tool!E83-Tool!$D$64),(Tool!E84-Tool!$D$64)>=(Tool!E83-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E83-Tool!$D$64,Tool!E83),$D$2),\"\"))))","v":""},{"$f":"IF(B189<>\"\",IF(Tool!F83=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E189=\"Freeway\",IF(Tool!I83>Tool!G83,0,IF(Tool!G83>0,Tool!G83,\"\")),\"\")","v":""},{"$f":"IF(AND(E189=Tool!$G$11,Tool!H83>0),Tool!H83,\"\")","v":""},{"$f":"IF(E189=\"Freeway\",IF(Tool!I83>Tool!G83,Tool!G83,IF(Tool!I83>=0,Tool!I83,0)),\"\")","v":""},{"$f":"IF(E189=\"Freeway\",Tool!J83,\"\")","v":""},"",{"$f":"IF(E189=\"Freeway\",Tool!O83,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=21,E168<=30),21,\"\")","v":""},{"$f":"IF(D28>=$D$2,\"\",IF($D$2<(Tool!E83-Tool!$D$64),\"\",IF(Tool!D84<>\"\",IF(Tool!$D$64<>0,Tool!E83-Tool!$D$64,Tool!E83),\"\")))","v":""},{"$f":"IF(C29=\"\",\"\",IF(B191=\"\",$D$2,IF((D28-$C$9)>=$D$2,\"\",IF(Tool!E83<>\"\",IF(AND($D$2>=(Tool!E84-Tool!$D$64),(Tool!E85-Tool!$D$64)>=(Tool!E84-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E84-Tool!$D$64,Tool!E84),$D$2),\"\"))))","v":""},{"$f":"IF(B190<>\"\",IF(Tool!F84=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E190=\"Freeway\",IF(Tool!I84>Tool!G84,0,IF(Tool!G84>0,Tool!G84,\"\")),\"\")","v":""},{"$f":"IF(AND(E190=Tool!$G$11,Tool!H84>0),Tool!H84,\"\")","v":""},{"$f":"IF(E190=\"Freeway\",IF(Tool!I84>Tool!G84,Tool!G84,IF(Tool!I84>=0,Tool!I84,0)),\"\")","v":""},{"$f":"IF(E190=\"Freeway\",Tool!J84,\"\")","v":""},"",{"$f":"IF(E190=\"Freeway\",Tool!O84,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=22,E168<=30),22,\"\")","v":""},{"$f":"IF(D29>=$D$2,\"\",IF($D$2<(Tool!E84-Tool!$D$64),\"\",IF(Tool!D85<>\"\",IF(Tool!$D$64<>0,Tool!E84-Tool!$D$64,Tool!E84),\"\")))","v":""},{"$f":"IF(C30=\"\",\"\",IF(B192=\"\",$D$2,IF((D29-$C$9)>=$D$2,\"\",IF(Tool!E84<>\"\",IF(AND($D$2>=(Tool!E85-Tool!$D$64),(Tool!E86-Tool!$D$64)>=(Tool!E85-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E85-Tool!$D$64,Tool!E85),$D$2),\"\"))))","v":""},{"$f":"IF(B191<>\"\",IF(Tool!F85=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E191=\"Freeway\",IF(Tool!I85>Tool!G85,0,IF(Tool!G85>0,Tool!G85,\"\")),\"\")","v":""},{"$f":"IF(AND(E191=Tool!$G$11,Tool!H85>0),Tool!H85,\"\")","v":""},{"$f":"IF(E191=\"Freeway\",IF(Tool!I85>Tool!G85,Tool!G85,IF(Tool!I85>=0,Tool!I85,0)),\"\")","v":""},{"$f":"IF(E191=\"Freeway\",Tool!J85,\"\")","v":""},"",{"$f":"IF(E191=\"Freeway\",Tool!O85,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=23,E168<=30),23,\"\")","v":""},{"$f":"IF(D30>=$D$2,\"\",IF($D$2<(Tool!E85-Tool!$D$64),\"\",IF(Tool!D86<>\"\",IF(Tool!$D$64<>0,Tool!E85-Tool!$D$64,Tool!E85),\"\")))","v":""},{"$f":"IF(C31=\"\",\"\",IF(B193=\"\",$D$2,IF((D30-$C$9)>=$D$2,\"\",IF(Tool!E85<>\"\",IF(AND($D$2>=(Tool!E86-Tool!$D$64),(Tool!E87-Tool!$D$64)>=(Tool!E86-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E86-Tool!$D$64,Tool!E86),$D$2),\"\"))))","v":""},{"$f":"IF(B192<>\"\",IF(Tool!F86=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E192=\"Freeway\",IF(Tool!I86>Tool!G86,0,IF(Tool!G86>0,Tool!G86,\"\")),\"\")","v":""},{"$f":"IF(AND(E192=Tool!$G$11,Tool!H86>0),Tool!H86,\"\")","v":""},{"$f":"IF(E192=\"Freeway\",IF(Tool!I86>Tool!G86,Tool!G86,IF(Tool!I86>=0,Tool!I86,0)),\"\")","v":""},{"$f":"IF(E192=\"Freeway\",Tool!J86,\"\")","v":""},"",{"$f":"IF(E192=\"Freeway\",Tool!O86,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=24,E168<=30),24,\"\")","v":""},{"$f":"IF(D31>=$D$2,\"\",IF($D$2<(Tool!E86-Tool!$D$64),\"\",IF(Tool!D87<>\"\",IF(Tool!$D$64<>0,Tool!E86-Tool!$D$64,Tool!E86),\"\")))","v":""},{"$f":"IF(C32=\"\",\"\",IF(B194=\"\",$D$2,IF((D31-$C$9)>=$D$2,\"\",IF(Tool!E86<>\"\",IF(AND($D$2>=(Tool!E87-Tool!$D$64),(Tool!E88-Tool!$D$64)>=(Tool!E87-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E87-Tool!$D$64,Tool!E87),$D$2),\"\"))))","v":""},{"$f":"IF(B193<>\"\",IF(Tool!F87=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E193=\"Freeway\",IF(Tool!I87>Tool!G87,0,IF(Tool!G87>0,Tool!G87,\"\")),\"\")","v":""},{"$f":"IF(AND(E193=Tool!$G$11,Tool!H87>0),Tool!H87,\"\")","v":""},{"$f":"IF(E193=\"Freeway\",IF(Tool!I87>Tool!G87,Tool!G87,IF(Tool!I87>=0,Tool!I87,0)),\"\")","v":""},{"$f":"IF(E193=\"Freeway\",Tool!J87,\"\")","v":""},"",{"$f":"IF(E193=\"Freeway\",Tool!O87,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=25,E168<=30),25,\"\")","v":""},{"$f":"IF(D32>=$D$2,\"\",IF($D$2<(Tool!E87-Tool!$D$64),\"\",IF(Tool!D88<>\"\",IF(Tool!$D$64<>0,Tool!E87-Tool!$D$64,Tool!E87),\"\")))","v":""},{"$f":"IF(C33=\"\",\"\",IF(B195=\"\",$D$2,IF((D32-$C$9)>=$D$2,\"\",IF(Tool!E87<>\"\",IF(AND($D$2>=(Tool!E88-Tool!$D$64),(Tool!E89-Tool!$D$64)>=(Tool!E88-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E88-Tool!$D$64,Tool!E88),$D$2),\"\"))))","v":""},{"$f":"IF(B194<>\"\",IF(Tool!F88=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E194=\"Freeway\",IF(Tool!I88>Tool!G88,0,IF(Tool!G88>0,Tool!G88,\"\")),\"\")","v":""},{"$f":"IF(AND(E194=Tool!$G$11,Tool!H88>0),Tool!H88,\"\")","v":""},{"$f":"IF(E194=\"Freeway\",IF(Tool!I88>Tool!G88,Tool!G88,IF(Tool!I88>=0,Tool!I88,0)),\"\")","v":""},{"$f":"IF(E194=\"Freeway\",Tool!J88,\"\")","v":""},"",{"$f":"IF(E194=\"Freeway\",Tool!O88,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=26,E168<=30),26,\"\")","v":""},{"$f":"IF(D33>=$D$2,\"\",IF($D$2<(Tool!E88-Tool!$D$64),\"\",IF(Tool!D89<>\"\",IF(Tool!$D$64<>0,Tool!E88-Tool!$D$64,Tool!E88),\"\")))","v":""},{"$f":"IF(C34=\"\",\"\",IF(B196=\"\",$D$2,IF((D33-$C$9)>=$D$2,\"\",IF(Tool!E88<>\"\",IF(AND($D$2>=(Tool!E89-Tool!$D$64),(Tool!E90-Tool!$D$64)>=(Tool!E89-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E89-Tool!$D$64,Tool!E89),$D$2),\"\"))))","v":""},{"$f":"IF(B195<>\"\",IF(Tool!F89=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E195=\"Freeway\",IF(Tool!I89>Tool!G89,0,IF(Tool!G89>0,Tool!G89,\"\")),\"\")","v":""},{"$f":"IF(AND(E195=Tool!$G$11,Tool!H89>0),Tool!H89,\"\")","v":""},{"$f":"IF(E195=\"Freeway\",IF(Tool!I89>Tool!G89,Tool!G89,IF(Tool!I89>=0,Tool!I89,0)),\"\")","v":""},{"$f":"IF(E195=\"Freeway\",Tool!J89,\"\")","v":""},"",{"$f":"IF(E195=\"Freeway\",Tool!O89,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=27,E168<=30),27,\"\")","v":""},{"$f":"IF(D34>=$D$2,\"\",IF($D$2<(Tool!E89-Tool!$D$64),\"\",IF(Tool!D90<>\"\",IF(Tool!$D$64<>0,Tool!E89-Tool!$D$64,Tool!E89),\"\")))","v":""},{"$f":"IF(C35=\"\",\"\",IF(B197=\"\",$D$2,IF((D34-$C$9)>=$D$2,\"\",IF(Tool!E89<>\"\",IF(AND($D$2>=(Tool!E90-Tool!$D$64),(Tool!E91-Tool!$D$64)>=(Tool!E90-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E90-Tool!$D$64,Tool!E90),$D$2),\"\"))))","v":""},{"$f":"IF(B196<>\"\",IF(Tool!F90=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E196=\"Freeway\",IF(Tool!I90>Tool!G90,0,IF(Tool!G90>0,Tool!G90,\"\")),\"\")","v":""},{"$f":"IF(AND(E196=Tool!$G$11,Tool!H90>0),Tool!H90,\"\")","v":""},{"$f":"IF(E196=\"Freeway\",IF(Tool!I90>Tool!G90,Tool!G90,IF(Tool!I90>=0,Tool!I90,0)),\"\")","v":""},{"$f":"IF(E196=\"Freeway\",Tool!J90,\"\")","v":""},"",{"$f":"IF(E196=\"Freeway\",Tool!O90,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=28,E168<=30),28,\"\")","v":""},{"$f":"IF(D35>=$D$2,\"\",IF($D$2<(Tool!E90-Tool!$D$64),\"\",IF(Tool!D91<>\"\",IF(Tool!$D$64<>0,Tool!E90-Tool!$D$64,Tool!E90),\"\")))","v":""},{"$f":"IF(C36=\"\",\"\",IF(B198=\"\",$D$2,IF((D35-$C$9)>=$D$2,\"\",IF(Tool!E90<>\"\",IF(AND($D$2>=(Tool!E91-Tool!$D$64),(Tool!E92-Tool!$D$64)>=(Tool!E91-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E91-Tool!$D$64,Tool!E91),$D$2),\"\"))))","v":""},{"$f":"IF(B197<>\"\",IF(Tool!F91=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E197=\"Freeway\",IF(Tool!I91>Tool!G91,0,IF(Tool!G91>0,Tool!G91,\"\")),\"\")","v":""},{"$f":"IF(AND(E197=Tool!$G$11,Tool!H91>0),Tool!H91,\"\")","v":""},{"$f":"IF(E197=\"Freeway\",IF(Tool!I91>Tool!G91,Tool!G91,IF(Tool!I91>=0,Tool!I91,0)),\"\")","v":""},{"$f":"IF(E197=\"Freeway\",Tool!J91,\"\")","v":""},"",{"$f":"IF(E197=\"Freeway\",Tool!O91,\"\")","v":""},""]
[null,{"$f":"IF(AND(E168>=29,E168<=30),29,\"\")","v":""},{"$f":"IF(D36>=$D$2,\"\",IF($D$2<(Tool!E91-Tool!$D$64),\"\",IF(Tool!D92<>\"\",IF(Tool!$D$64<>0,Tool!E91-Tool!$D$64,Tool!E91),\"\")))","v":""},{"$f":"IF(C37=\"\",\"\",IF(B199=\"\",$D$2,IF((D36-$C$9)>=$D$2,\"\",IF(Tool!E91<>\"\",IF(AND($D$2>=(Tool!E92-Tool!$D$64),(Tool!E93-Tool!$D$64)>=(Tool!E92-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E92-Tool!$D$64,Tool!E92),$D$2),\"\"))))","v":""},{"$f":"IF(B198<>\"\",IF(Tool!F92=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E198=\"Freeway\",IF(Tool!I92>Tool!G92,0,IF(Tool!G92>0,Tool!G92,\"\")),\"\")","v":""},{"$f":"IF(AND(E198=Tool!$G$11,Tool!H92>0),Tool!H92,\"\")","v":""},{"$f":"IF(E198=\"Freeway\",IF(Tool!I92>Tool!G92,Tool!G92,IF(Tool!I92>=0,Tool!I92,0)),\"\")","v":""},{"$f":"IF(E198=\"Freeway\",Tool!J92,\"\")","v":""},"",{"$f":"IF(E198=\"Freeway\",Tool!O92,\"\")","v":""},""]
[null,{"$f":"IF(E168=30,30,\"\")","v":""},{"$f":"IF(D37>=$D$2,\"\",IF($D$2<(Tool!E92-Tool!$D$64),\"\",IF(Tool!D93<>\"\",IF(Tool!$D$64<>0,Tool!E92-Tool!$D$64,Tool!E92),\"\")))","v":""},{"$f":"IF(C38=\"\",\"\",IF(B200=\"\",$D$2,IF((D37-$C$9)>=$D$2,\"\",IF(Tool!E92<>\"\",IF(AND($D$2>=(Tool!E93-Tool!$D$64),(Tool!E94-Tool!$D$64)>=(Tool!E93-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E93-Tool!$D$64,Tool!E93),$D$2),\"\"))))","v":""},{"$f":"IF(B199<>\"\",IF(Tool!F93=Tool!$G$11,\"Freeway\",\"\"),\"\")","v":""},{"$f":"IF(E199=\"Freeway\",IF(Tool!I93>Tool!G93,0,IF(Tool!G93>0,Tool!G93,\"\")),\"\")","v":""},{"$f":"IF(AND(E199=Tool!$G$11,Tool!H93>0),Tool!H93,\"\")","v":""},{"$f":"IF(E199=\"Freeway\",IF(Tool!I93>Tool!G93,Tool!G93,IF(Tool!I93>=0,Tool!I93,0)),\"\")","v":""},{"$f":"IF(E199=\"Freeway\",Tool!J93,\"\")","v":""},"",{"$f":"IF(E199=\"Freeway\",Tool!O93,\"\")","v":""},""]
[]
[null,null,null,null,null,null,"Average Width:",{"$f":"IFERROR((SUMPRODUCT(F170:F199,J170:J199)/SUM(J170:J199))-(SUMPRODUCT(H170:H199,J170:J199)/SUM(J170:J199)),0)","v":0},"Average Additional Full Depth:",{"$f":"IFERROR(SUMPRODUCT(--(I170:I199=\"Yes\"),H170:H199,J170:J199)/SUM(J170:J199),0)","v":0},"Area",{"$f":"H204*J201*5280","v":0}]
[null,null,null,null,null,null,"Average Shoulder Width:",{"$f":"IF(SUM(J170:J199)>0,(SUMPRODUCT(G170:G199,J170:J199)/SUM(J170:J199))*2,0)","v":0},"Total Full Depth Width:",{"$f":"H201+J201","v":0}]
[null,null,null,null,null,null,"Average Resurface Pavement:",{"$f":"IFERROR(SUMPRODUCT(--(I170:I199=\"No\"),H170:H199,J170:J199)/SUM(J170:J199),0)","v":0},"Average Roadway Width:",{"$f":"IFERROR(SUMPRODUCT(W119:W138,X119:X138)/SUM(X119:X138),0)","v":0}]
[null,null,null,null,null,null,"Length:",{"$f":"SUM(J170:J199)","v":0}]
[null,null,null,null,null,null,"Perimeter Length",{"$f":"SUM(L170:L199)","v":0}]
[null,"Proposed Pavement Width"]
[null,"Concrete"]
[null,"Segments:",null,null,{"$f":"Tool!$J$61","v":1}]
[null,"Segments","Begin","End","Pavement Type","Total Pavement Width(ft)","Outside Shoulder Width (ft)","Existing Pavement Width","Replace Existing Pavement?","Length","Widen to One Side or Both?","Perimeter Length"]
[null,{"$f":"IF(AND(E208>=1,E208<=30),1,\"\")","v":1},{"$f":"IF(Tool!D64<>\"\",IF(B9<>\"\",IF(Tool!D64=0,Tool!D64,Tool!D64-Tool!D64),\"\"),\"\")","v":""},{"$f":"IF((Tool!E65-Tool!D64)<(Tool!E64-Tool!D64),D2,IF(B9<>\"\",IF(Tool!E64<>\"\",IF(AND(B10=\"\",Tool!E64-Tool!D64<$D$2),$D$2,IF(B9=1,IF($D$2<(Tool!E64-Tool!$D$64),$D$2,IF(Tool!D64<>0,(Tool!E64-Tool!D64),Tool!E64)),\"\")),\"\"),\"\"))","v":""},{"$f":"IF(C210=\"\",\"\",IF(B210<>\"\",IF(Tool!F64=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E210=\"Concrete\",IF(Tool!I64>Tool!G64,0,IF(Tool!G64>0,Tool!G64,\"\")),\"\")","v":""},{"$f":"IF(AND($E210=Tool!$G$12,Tool!H64>0),Tool!H64,\"\")","v":""},{"$f":"IF(E210=\"Concrete\",IF(Tool!I64>Tool!G64,Tool!G64,IF(Tool!I64>=0,Tool!I64,0)),\"\")","v":""},{"$f":"IF(E210=\"Concrete\",Tool!J64,\"\")","v":""},{"$f":"IF(F210<>\"\",IF(OR(C210=\"\",D210=\"\"),\"\",IF(E210=\"Concrete\",D210-C210,\"\")),\"\")","v":""},{"$f":"IF(E210=\"Concrete\",Tool!O64,\"\")","v":""},{"$f":"IFERROR(IF(AND(K210=\"One Side\",OR((F210-H210)>0,G210<>\"\")),J210,IF(AND(K210=\"Both Sides\",OR((F210-H210)>0,G210<>\"\")),J210*2,0)),\"\")","v":""}]
[null,{"$f":"IF(AND(E208>=2,E208<=30),2,\"\")","v":""},{"$f":"IF(D9>=$D$2,\"\",IF($D$2<(Tool!E64-Tool!$D$64),\"\",IF(Tool!D65<>\"\",IF(Tool!$D$64<>0,Tool!E64-Tool!$D$64,Tool!E64),\"\")))","v":""},{"$f":"IF(C10=\"\",\"\",IF(B212=\"\",$D$2,IF((D9-$C$9)>=$D$2,\"\",IF(Tool!E64<>\"\",IF(AND($D$2>=(Tool!E65-Tool!$D$64),(Tool!E66-Tool!$D$64)>=(Tool!E65-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E65-Tool!$D$64,Tool!E65),$D$2),\"\"))))","v":""},{"$f":"IF(C211=\"\",\"\",IF(B211<>\"\",IF(Tool!F65=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E211=\"Concrete\",IF(Tool!I65>Tool!G65,0,IF(Tool!G65>0,Tool!G65,\"\")),\"\")","v":""},{"$f":"IF(AND(E211=Tool!$G$12,Tool!H65>0),Tool!H65,\"\")","v":""},{"$f":"IF(E211=\"Concrete\",IF(Tool!I65>Tool!G65,Tool!G65,IF(Tool!I65>=0,Tool!I65,0)),\"\")","v":""},{"$f":"IF(E211=\"Concrete\",Tool!J65,\"\")","v":""},{"$f":"IF(F211<>\"\",IF(OR(C211=\"\",D211=\"\"),\"\",IF(E211=\"Concrete\",D211-C211,\"\")),\"\")","v":""},{"$f":"IF(E211=\"Concrete\",Tool!O65,\"\")","v":""},{"$f":"IFERROR(IF(AND(K211=\"One Side\",OR((F211-H211)>0,G211<>\"\")),J211,IF(AND(K211=\"Both Sides\",OR((F211-H211)>0,G211<>\"\")),J211*2,0)),\"\")","v":""}]
[null,{"$f":"IF(AND(E208>=3,E208<=30),3,\"\")","v":""},{"$f":"IF(D10>=$D$2,\"\",IF($D$2<(Tool!E65-Tool!$D$64),\"\",IF(Tool!D66<>\"\",IF(Tool!$D$64<>0,Tool!E65-Tool!$D$64,Tool!E65),\"\")))","v":""},{"$f":"IF(C11=\"\",\"\",IF(B213=\"\",$D$2,IF((D10-$C$9)>=$D$2,\"\",IF(Tool!E65<>\"\",IF(AND($D$2>=(Tool!E66-Tool!$D$64),(Tool!E67-Tool!$D$64)>=(Tool!E66-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E66-Tool!$D$64,Tool!E66),$D$2),\"\"))))","v":""},{"$f":"IF(C212=\"\",\"\",IF(B212<>\"\",IF(Tool!F66=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E212=\"Concrete\",IF(Tool!I66>Tool!G66,0,IF(Tool!G66>0,Tool!G66,\"\")),\"\")","v":""},{"$f":"IF(AND(E212=Tool!$G$12,Tool!H66>0),Tool!H66,\"\")","v":""},{"$f":"IF(E212=\"Concrete\",IF(Tool!I66>Tool!G66,Tool!G66,IF(Tool!I66>=0,Tool!I66,0)),\"\")","v":""},{"$f":"IF(E212=\"Concrete\",Tool!J66,\"\")","v":""},"",{"$f":"IF(E212=\"Concrete\",Tool!O66,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=4,E208<=30),4,\"\")","v":""},{"$f":"IF(D11>=$D$2,\"\",IF($D$2<(Tool!E66-Tool!$D$64),\"\",IF(Tool!D67<>\"\",IF(Tool!$D$64<>0,Tool!E66-Tool!$D$64,Tool!E66),\"\")))","v":""},{"$f":"IF(C12=\"\",\"\",IF(B214=\"\",$D$2,IF((D11-$C$9)>=$D$2,\"\",IF(Tool!E66<>\"\",IF(AND($D$2>=(Tool!E67-Tool!$D$64),(Tool!E68-Tool!$D$64)>=(Tool!E67-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E67-Tool!$D$64,Tool!E67),$D$2),\"\"))))","v":""},{"$f":"IF(C213=\"\",\"\",IF(B213<>\"\",IF(Tool!F67=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E213=\"Concrete\",IF(Tool!I67>Tool!G67,0,IF(Tool!G67>0,Tool!G67,\"\")),\"\")","v":""},{"$f":"IF(AND(E213=Tool!$G$12,Tool!H67>0),Tool!H67,\"\")","v":""},{"$f":"IF(E213=\"Concrete\",IF(Tool!I67>Tool!G67,Tool!G67,IF(Tool!I67>=0,Tool!I67,0)),\"\")","v":""},{"$f":"IF(E213=\"Concrete\",Tool!J67,\"\")","v":""},{"$f":"IF(F213<>\"\",IF(OR(C213=\"\",D213=\"\"),\"\",IF(E213=\"Concrete\",D213-C213,\"\")),\"\")","v":""},{"$f":"IF(E213=\"Concrete\",Tool!O67,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=5,E208<=30),5,\"\")","v":""},{"$f":"IF(D12>=$D$2,\"\",IF($D$2<(Tool!E67-Tool!$D$64),\"\",IF(Tool!D68<>\"\",IF(Tool!$D$64<>0,Tool!E67-Tool!$D$64,Tool!E67),\"\")))","v":""},{"$f":"IF(C13=\"\",\"\",IF(B215=\"\",$D$2,IF((D12-$C$9)>=$D$2,\"\",IF(Tool!E67<>\"\",IF(AND($D$2>=(Tool!E68-Tool!$D$64),(Tool!E69-Tool!$D$64)>=(Tool!E68-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E68-Tool!$D$64,Tool!E68),$D$2),\"\"))))","v":""},{"$f":"IF(C214=\"\",\"\",IF(B214<>\"\",IF(Tool!F68=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E214=\"Concrete\",IF(Tool!I68>Tool!G68,0,IF(Tool!G68>0,Tool!G68,\"\")),\"\")","v":""},{"$f":"IF(AND(E214=Tool!$G$12,Tool!H68>0),Tool!H68,\"\")","v":""},{"$f":"IF(E214=\"Concrete\",IF(Tool!I68>Tool!G68,Tool!G68,IF(Tool!I68>=0,Tool!I68,0)),\"\")","v":""},{"$f":"IF(E214=\"Concrete\",Tool!J68,\"\")","v":""},"",{"$f":"IF(E214=\"Concrete\",Tool!O68,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=6,E208<=30),6,\"\")","v":""},{"$f":"IF(D13>=$D$2,\"\",IF($D$2<(Tool!E68-Tool!$D$64),\"\",IF(Tool!D69<>\"\",IF(Tool!$D$64<>0,Tool!E68-Tool!$D$64,Tool!E68),\"\")))","v":""},{"$f":"IF(C14=\"\",\"\",IF(B216=\"\",$D$2,IF((D13-$C$9)>=$D$2,\"\",IF(Tool!E68<>\"\",IF(AND($D$2>=(Tool!E69-Tool!$D$64),(Tool!E70-Tool!$D$64)>=(Tool!E69-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E69-Tool!$D$64,Tool!E69),$D$2),\"\"))))","v":""},{"$f":"IF(C215=\"\",\"\",IF(B215<>\"\",IF(Tool!F69=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E215=\"Concrete\",IF(Tool!I69>Tool!G69,0,IF(Tool!G69>0,Tool!G69,\"\")),\"\")","v":""},{"$f":"IF(AND(E215=Tool!$G$12,Tool!H69>0),Tool!H69,\"\")","v":""},{"$f":"IF(E215=\"Concrete\",IF(Tool!I69>Tool!G69,Tool!G69,IF(Tool!I69>=0,Tool!I69,0)),\"\")","v":""},{"$f":"IF(E215=\"Concrete\",Tool!J69,\"\")","v":""},"",{"$f":"IF(E215=\"Concrete\",Tool!O69,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=7,E208<=30),7,\"\")","v":""},{"$f":"IF(D14>=$D$2,\"\",IF($D$2<(Tool!E69-Tool!$D$64),\"\",IF(Tool!D70<>\"\",IF(Tool!$D$64<>0,Tool!E69-Tool!$D$64,Tool!E69),\"\")))","v":""},{"$f":"IF(C15=\"\",\"\",IF(B217=\"\",$D$2,IF((D14-$C$9)>=$D$2,\"\",IF(Tool!E69<>\"\",IF(AND($D$2>=(Tool!E70-Tool!$D$64),(Tool!E71-Tool!$D$64)>=(Tool!E70-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E70-Tool!$D$64,Tool!E70),$D$2),\"\"))))","v":""},{"$f":"IF(C216=\"\",\"\",IF(B216<>\"\",IF(Tool!F70=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E216=\"Concrete\",IF(Tool!I70>Tool!G70,0,IF(Tool!G70>0,Tool!G70,\"\")),\"\")","v":""},{"$f":"IF(AND(E216=Tool!$G$12,Tool!H70>0),Tool!H70,\"\")","v":""},{"$f":"IF(E216=\"Concrete\",IF(Tool!I70>Tool!G70,Tool!G70,IF(Tool!I70>=0,Tool!I70,0)),\"\")","v":""},{"$f":"IF(E216=\"Concrete\",Tool!J70,\"\")","v":""},"",{"$f":"IF(E216=\"Concrete\",Tool!O70,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=8,E208<=30),8,\"\")","v":""},{"$f":"IF(D15>=$D$2,\"\",IF($D$2<(Tool!E70-Tool!$D$64),\"\",IF(Tool!D71<>\"\",IF(Tool!$D$64<>0,Tool!E70-Tool!$D$64,Tool!E70),\"\")))","v":""},{"$f":"IF(C16=\"\",\"\",IF(B218=\"\",$D$2,IF((D15-$C$9)>=$D$2,\"\",IF(Tool!E70<>\"\",IF(AND($D$2>=(Tool!E71-Tool!$D$64),(Tool!E72-Tool!$D$64)>=(Tool!E71-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E71-Tool!$D$64,Tool!E71),$D$2),\"\"))))","v":""},{"$f":"IF(C217=\"\",\"\",IF(B217<>\"\",IF(Tool!F71=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E217=\"Concrete\",IF(Tool!I71>Tool!G71,0,IF(Tool!G71>0,Tool!G71,\"\")),\"\")","v":""},{"$f":"IF(AND(E217=Tool!$G$12,Tool!H71>0),Tool!H71,\"\")","v":""},{"$f":"IF(E217=\"Concrete\",IF(Tool!I71>Tool!G71,Tool!G71,IF(Tool!I71>=0,Tool!I71,0)),\"\")","v":""},{"$f":"IF(E217=\"Concrete\",Tool!J71,\"\")","v":""},"",{"$f":"IF(E217=\"Concrete\",Tool!O71,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=9,F208<=20),9,\"\")","v":""},{"$f":"IF(D16>=$D$2,\"\",IF($D$2<(Tool!E71-Tool!$D$64),\"\",IF(Tool!D72<>\"\",IF(Tool!$D$64<>0,Tool!E71-Tool!$D$64,Tool!E71),\"\")))","v":""},{"$f":"IF(C17=\"\",\"\",IF(B219=\"\",$D$2,IF((D16-$C$9)>=$D$2,\"\",IF(Tool!E71<>\"\",IF(AND($D$2>=(Tool!E72-Tool!$D$64),(Tool!E73-Tool!$D$64)>=(Tool!E72-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E72-Tool!$D$64,Tool!E72),$D$2),\"\"))))","v":""},{"$f":"IF(C218=\"\",\"\",IF(B218<>\"\",IF(Tool!F72=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E218=\"Concrete\",IF(Tool!I72>Tool!G72,0,IF(Tool!G72>0,Tool!G72,\"\")),\"\")","v":""},{"$f":"IF(AND(E218=Tool!$G$12,Tool!H72>0),Tool!H72,\"\")","v":""},{"$f":"IF(E218=\"Concrete\",IF(Tool!I72>Tool!G72,Tool!G72,IF(Tool!I72>=0,Tool!I72,0)),\"\")","v":""},{"$f":"IF(E218=\"Concrete\",Tool!J72,\"\")","v":""},"",{"$f":"IF(E218=\"Concrete\",Tool!O72,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=10,E208<=30),10,\"\")","v":""},{"$f":"IF(D17>=$D$2,\"\",IF($D$2<(Tool!E72-Tool!$D$64),\"\",IF(Tool!D73<>\"\",IF(Tool!$D$64<>0,Tool!E72-Tool!$D$64,Tool!E72),\"\")))","v":""},{"$f":"IF(C18=\"\",\"\",IF(B220=\"\",$D$2,IF((D17-$C$9)>=$D$2,\"\",IF(Tool!E72<>\"\",IF(AND($D$2>=(Tool!E73-Tool!$D$64),(Tool!E74-Tool!$D$64)>=(Tool!E73-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E73-Tool!$D$64,Tool!E73),$D$2),\"\"))))","v":""},{"$f":"IF(C219=\"\",\"\",IF(B219<>\"\",IF(Tool!F73=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E219=\"Concrete\",IF(Tool!I73>Tool!G73,0,IF(Tool!G73>0,Tool!G73,\"\")),\"\")","v":""},{"$f":"IF(AND(E219=Tool!$G$12,Tool!H73>0),Tool!H73,\"\")","v":""},{"$f":"IF(E219=\"Concrete\",IF(Tool!I73>Tool!G73,Tool!G73,IF(Tool!I73>=0,Tool!I73,0)),\"\")","v":""},{"$f":"IF(E219=\"Concrete\",Tool!J73,\"\")","v":""},"",{"$f":"IF(E219=\"Concrete\",Tool!O73,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=11,E208<=30),11,\"\")","v":""},{"$f":"IF(D18>=$D$2,\"\",IF($D$2<(Tool!E73-Tool!$D$64),\"\",IF(Tool!D74<>\"\",IF(Tool!$D$64<>0,Tool!E73-Tool!$D$64,Tool!E73),\"\")))","v":""},{"$f":"IF(C19=\"\",\"\",IF(B221=\"\",$D$2,IF((D18-$C$9)>=$D$2,\"\",IF(Tool!E73<>\"\",IF(AND($D$2>=(Tool!E74-Tool!$D$64),(Tool!E75-Tool!$D$64)>=(Tool!E74-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E74-Tool!$D$64,Tool!E74),$D$2),\"\"))))","v":""},{"$f":"IF(C220=\"\",\"\",IF(B220<>\"\",IF(Tool!F74=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E220=\"Concrete\",IF(Tool!I74>Tool!G74,0,IF(Tool!G74>0,Tool!G74,\"\")),\"\")","v":""},{"$f":"IF(AND(E220=Tool!$G$12,Tool!H74>0),Tool!H74,\"\")","v":""},{"$f":"IF(E220=\"Concrete\",IF(Tool!I74>Tool!G74,Tool!G74,IF(Tool!I74>=0,Tool!I74,0)),\"\")","v":""},{"$f":"IF(E220=\"Concrete\",Tool!J74,\"\")","v":""},"",{"$f":"IF(E220=\"Concrete\",Tool!O74,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=12,F208<=30),12,\"\")","v":""},{"$f":"IF(D19>=$D$2,\"\",IF($D$2<(Tool!E74-Tool!$D$64),\"\",IF(Tool!D75<>\"\",IF(Tool!$D$64<>0,Tool!E74-Tool!$D$64,Tool!E74),\"\")))","v":""},{"$f":"IF(C20=\"\",\"\",IF(B222=\"\",$D$2,IF((D19-$C$9)>=$D$2,\"\",IF(Tool!E74<>\"\",IF(AND($D$2>=(Tool!E75-Tool!$D$64),(Tool!E76-Tool!$D$64)>=(Tool!E75-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E75-Tool!$D$64,Tool!E75),$D$2),\"\"))))","v":""},{"$f":"IF(C221=\"\",\"\",IF(B221<>\"\",IF(Tool!F75=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E221=\"Concrete\",IF(Tool!I75>Tool!G75,0,IF(Tool!G75>0,Tool!G75,\"\")),\"\")","v":""},{"$f":"IF(AND(E221=Tool!$G$12,Tool!H75>0),Tool!H75,\"\")","v":""},{"$f":"IF(E221=\"Concrete\",IF(Tool!I75>Tool!G75,Tool!G75,IF(Tool!I75>=0,Tool!I75,0)),\"\")","v":""},{"$f":"IF(E221=\"Concrete\",Tool!J75,\"\")","v":""},"",{"$f":"IF(E221=\"Concrete\",Tool!O75,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=13,E208<=30),13,\"\")","v":""},{"$f":"IF(D20>=$D$2,\"\",IF($D$2<(Tool!E75-Tool!$D$64),\"\",IF(Tool!D76<>\"\",IF(Tool!$D$64<>0,Tool!E75-Tool!$D$64,Tool!E75),\"\")))","v":""},{"$f":"IF(C21=\"\",\"\",IF(B223=\"\",$D$2,IF((D20-$C$9)>=$D$2,\"\",IF(Tool!E75<>\"\",IF(AND($D$2>=(Tool!E76-Tool!$D$64),(Tool!E77-Tool!$D$64)>=(Tool!E76-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E76-Tool!$D$64,Tool!E76),$D$2),\"\"))))","v":""},{"$f":"IF(C222=\"\",\"\",IF(B222<>\"\",IF(Tool!F76=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E222=\"Concrete\",IF(Tool!I76>Tool!G76,0,IF(Tool!G76>0,Tool!G76,\"\")),\"\")","v":""},{"$f":"IF(AND(E222=Tool!$G$12,Tool!H76>0),Tool!H76,\"\")","v":""},{"$f":"IF(E222=\"Concrete\",IF(Tool!I76>Tool!G76,Tool!G76,IF(Tool!I76>=0,Tool!I76,0)),\"\")","v":""},{"$f":"IF(E222=\"Concrete\",Tool!J76,\"\")","v":""},"",{"$f":"IF(E222=\"Concrete\",Tool!O76,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=14,E208<=30),14,\"\")","v":""},{"$f":"IF(D21>=$D$2,\"\",IF($D$2<(Tool!E76-Tool!$D$64),\"\",IF(Tool!D77<>\"\",IF(Tool!$D$64<>0,Tool!E76-Tool!$D$64,Tool!E76),\"\")))","v":""},{"$f":"IF(C22=\"\",\"\",IF(B224=\"\",$D$2,IF((D21-$C$9)>=$D$2,\"\",IF(Tool!E76<>\"\",IF(AND($D$2>=(Tool!E77-Tool!$D$64),(Tool!E78-Tool!$D$64)>=(Tool!E77-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E77-Tool!$D$64,Tool!E77),$D$2),\"\"))))","v":""},{"$f":"IF(C223=\"\",\"\",IF(B223<>\"\",IF(Tool!F77=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E223=\"Concrete\",IF(Tool!I77>Tool!G77,0,IF(Tool!G77>0,Tool!G77,\"\")),\"\")","v":""},{"$f":"IF(AND(E223=Tool!$G$12,Tool!H77>0),Tool!H77,\"\")","v":""},{"$f":"IF(E223=\"Concrete\",IF(Tool!I77>Tool!G77,Tool!G77,IF(Tool!I77>=0,Tool!I77,0)),\"\")","v":""},{"$f":"IF(E223=\"Concrete\",Tool!J77,\"\")","v":""},"",{"$f":"IF(E223=\"Concrete\",Tool!O77,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=15,E208<=30),15,\"\")","v":""},{"$f":"IF(D22>=$D$2,\"\",IF($D$2<(Tool!E77-Tool!$D$64),\"\",IF(Tool!D78<>\"\",IF(Tool!$D$64<>0,Tool!E77-Tool!$D$64,Tool!E77),\"\")))","v":""},{"$f":"IF(C23=\"\",\"\",IF(B225=\"\",$D$2,IF((D22-$C$9)>=$D$2,\"\",IF(Tool!E77<>\"\",IF(AND($D$2>=(Tool!E78-Tool!$D$64),(Tool!E79-Tool!$D$64)>=(Tool!E78-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E78-Tool!$D$64,Tool!E78),$D$2),\"\"))))","v":""},{"$f":"IF(C224=\"\",\"\",IF(B224<>\"\",IF(Tool!F78=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E224=\"Concrete\",IF(Tool!I78>Tool!G78,0,IF(Tool!G78>0,Tool!G78,\"\")),\"\")","v":""},{"$f":"IF(AND(E224=Tool!$G$12,Tool!H78>0),Tool!H78,\"\")","v":""},{"$f":"IF(E224=\"Concrete\",IF(Tool!I78>Tool!G78,Tool!G78,IF(Tool!I78>=0,Tool!I78,0)),\"\")","v":""},{"$f":"IF(E224=\"Concrete\",Tool!J78,\"\")","v":""},"",{"$f":"IF(E224=\"Concrete\",Tool!O78,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=16,E208<=30),16,\"\")","v":""},{"$f":"IF(D23>=$D$2,\"\",IF($D$2<(Tool!E78-Tool!$D$64),\"\",IF(Tool!D79<>\"\",IF(Tool!$D$64<>0,Tool!E78-Tool!$D$64,Tool!E78),\"\")))","v":""},{"$f":"IF(C24=\"\",\"\",IF(B226=\"\",$D$2,IF((D23-$C$9)>=$D$2,\"\",IF(Tool!E78<>\"\",IF(AND($D$2>=(Tool!E79-Tool!$D$64),(Tool!E80-Tool!$D$64)>=(Tool!E79-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E79-Tool!$D$64,Tool!E79),$D$2),\"\"))))","v":""},{"$f":"IF(C225=\"\",\"\",IF(B225<>\"\",IF(Tool!F79=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E225=\"Concrete\",IF(Tool!I79>Tool!G79,0,IF(Tool!G79>0,Tool!G79,\"\")),\"\")","v":""},{"$f":"IF(AND(E225=Tool!$G$12,Tool!H79>0),Tool!H79,\"\")","v":""},{"$f":"IF(E225=\"Concrete\",IF(Tool!I79>Tool!G79,Tool!G79,IF(Tool!I79>=0,Tool!I79,0)),\"\")","v":""},{"$f":"IF(E225=\"Concrete\",Tool!J79,\"\")","v":""},"",{"$f":"IF(E225=\"Concrete\",Tool!O79,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=17,E208<=30),17,\"\")","v":""},{"$f":"IF(D24>=$D$2,\"\",IF($D$2<(Tool!E79-Tool!$D$64),\"\",IF(Tool!D80<>\"\",IF(Tool!$D$64<>0,Tool!E79-Tool!$D$64,Tool!E79),\"\")))","v":""},{"$f":"IF(C25=\"\",\"\",IF(B227=\"\",$D$2,IF((D24-$C$9)>=$D$2,\"\",IF(Tool!E79<>\"\",IF(AND($D$2>=(Tool!E80-Tool!$D$64),(Tool!E81-Tool!$D$64)>=(Tool!E80-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E80-Tool!$D$64,Tool!E80),$D$2),\"\"))))","v":""},{"$f":"IF(C226=\"\",\"\",IF(B226<>\"\",IF(Tool!F80=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E226=\"Concrete\",IF(Tool!I80>Tool!G80,0,IF(Tool!G80>0,Tool!G80,\"\")),\"\")","v":""},{"$f":"IF(AND(E226=Tool!$G$12,Tool!H80>0),Tool!H80,\"\")","v":""},{"$f":"IF(E226=\"Concrete\",IF(Tool!I80>Tool!G80,Tool!G80,IF(Tool!I80>=0,Tool!I80,0)),\"\")","v":""},{"$f":"IF(E226=\"Concrete\",Tool!J80,\"\")","v":""},"",{"$f":"IF(E226=\"Concrete\",Tool!O80,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=18,E208<=30),18,\"\")","v":""},{"$f":"IF(D25>=$D$2,\"\",IF($D$2<(Tool!E80-Tool!$D$64),\"\",IF(Tool!D81<>\"\",IF(Tool!$D$64<>0,Tool!E80-Tool!$D$64,Tool!E80),\"\")))","v":""},{"$f":"IF(C26=\"\",\"\",IF(B228=\"\",$D$2,IF((D25-$C$9)>=$D$2,\"\",IF(Tool!E80<>\"\",IF(AND($D$2>=(Tool!E81-Tool!$D$64),(Tool!E82-Tool!$D$64)>=(Tool!E81-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E81-Tool!$D$64,Tool!E81),$D$2),\"\"))))","v":""},{"$f":"IF(C227=\"\",\"\",IF(B227<>\"\",IF(Tool!F81=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E227=\"Concrete\",IF(Tool!I81>Tool!G81,0,IF(Tool!G81>0,Tool!G81,\"\")),\"\")","v":""},{"$f":"IF(AND(E227=Tool!$G$12,Tool!H81>0),Tool!H81,\"\")","v":""},{"$f":"IF(E227=\"Concrete\",IF(Tool!I81>Tool!G81,Tool!G81,IF(Tool!I81>=0,Tool!I81,0)),\"\")","v":""},{"$f":"IF(E227=\"Concrete\",Tool!J81,\"\")","v":""},"",{"$f":"IF(E227=\"Concrete\",Tool!O81,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=19,E208<=30),19,\"\")","v":""},{"$f":"IF(D26>=$D$2,\"\",IF($D$2<(Tool!E81-Tool!$D$64),\"\",IF(Tool!D82<>\"\",IF(Tool!$D$64<>0,Tool!E81-Tool!$D$64,Tool!E81),\"\")))","v":""},{"$f":"IF(C27=\"\",\"\",IF(B229=\"\",$D$2,IF((D26-$C$9)>=$D$2,\"\",IF(Tool!E81<>\"\",IF(AND($D$2>=(Tool!E82-Tool!$D$64),(Tool!E83-Tool!$D$64)>=(Tool!E82-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E82-Tool!$D$64,Tool!E82),$D$2),\"\"))))","v":""},{"$f":"IF(C228=\"\",\"\",IF(B228<>\"\",IF(Tool!F82=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E228=\"Concrete\",IF(Tool!I82>Tool!G82,0,IF(Tool!G82>0,Tool!G82,\"\")),\"\")","v":""},{"$f":"IF(AND(E228=Tool!$G$12,Tool!H82>0),Tool!H82,\"\")","v":""},{"$f":"IF(E228=\"Concrete\",IF(Tool!I82>Tool!G82,Tool!G82,IF(Tool!I82>=0,Tool!I82,0)),\"\")","v":""},{"$f":"IF(E228=\"Concrete\",Tool!J82,\"\")","v":""},"",{"$f":"IF(E228=\"Concrete\",Tool!O82,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=20,E208<=30),20,\"\")","v":""},{"$f":"IF(D27>=$D$2,\"\",IF($D$2<(Tool!E82-Tool!$D$64),\"\",IF(Tool!D83<>\"\",IF(Tool!$D$64<>0,Tool!E82-Tool!$D$64,Tool!E82),\"\")))","v":""},{"$f":"IF(C28=\"\",\"\",IF(B230=\"\",$D$2,IF((D27-$C$9)>=$D$2,\"\",IF(Tool!E82<>\"\",IF(AND($D$2>=(Tool!E83-Tool!$D$64),(Tool!E84-Tool!$D$64)>=(Tool!E83-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E83-Tool!$D$64,Tool!E83),$D$2),\"\"))))","v":""},{"$f":"IF(C229=\"\",\"\",IF(B229<>\"\",IF(Tool!F83=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E229=\"Concrete\",IF(Tool!I83>Tool!G83,0,IF(Tool!G83>0,Tool!G83,\"\")),\"\")","v":""},{"$f":"IF(AND(E229=Tool!$G$12,Tool!H83>0),Tool!H83,\"\")","v":""},{"$f":"IF(E229=\"Concrete\",IF(Tool!I83>Tool!G83,Tool!G83,IF(Tool!I83>=0,Tool!I83,0)),\"\")","v":""},{"$f":"IF(E229=\"Concrete\",Tool!J83,\"\")","v":""},"",{"$f":"IF(E229=\"Concrete\",Tool!O83,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=21,E208<=30),21,\"\")","v":""},{"$f":"IF(D28>=$D$2,\"\",IF($D$2<(Tool!E83-Tool!$D$64),\"\",IF(Tool!D84<>\"\",IF(Tool!$D$64<>0,Tool!E83-Tool!$D$64,Tool!E83),\"\")))","v":""},{"$f":"IF(C29=\"\",\"\",IF(B231=\"\",$D$2,IF((D28-$C$9)>=$D$2,\"\",IF(Tool!E83<>\"\",IF(AND($D$2>=(Tool!E84-Tool!$D$64),(Tool!E85-Tool!$D$64)>=(Tool!E84-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E84-Tool!$D$64,Tool!E84),$D$2),\"\"))))","v":""},{"$f":"IF(C230=\"\",\"\",IF(B230<>\"\",IF(Tool!F84=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E230=\"Concrete\",IF(Tool!I84>Tool!G84,0,IF(Tool!G84>0,Tool!G84,\"\")),\"\")","v":""},{"$f":"IF(AND(E230=Tool!$G$12,Tool!H84>0),Tool!H84,\"\")","v":""},{"$f":"IF(E230=\"Concrete\",IF(Tool!I84>Tool!G84,Tool!G84,IF(Tool!I84>=0,Tool!I84,0)),\"\")","v":""},{"$f":"IF(E230=\"Concrete\",Tool!J84,\"\")","v":""},"",{"$f":"IF(E230=\"Concrete\",Tool!O84,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=22,E208<=30),22,\"\")","v":""},{"$f":"IF(D29>=$D$2,\"\",IF($D$2<(Tool!E84-Tool!$D$64),\"\",IF(Tool!D85<>\"\",IF(Tool!$D$64<>0,Tool!E84-Tool!$D$64,Tool!E84),\"\")))","v":""},{"$f":"IF(C30=\"\",\"\",IF(B232=\"\",$D$2,IF((D29-$C$9)>=$D$2,\"\",IF(Tool!E84<>\"\",IF(AND($D$2>=(Tool!E85-Tool!$D$64),(Tool!E86-Tool!$D$64)>=(Tool!E85-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E85-Tool!$D$64,Tool!E85),$D$2),\"\"))))","v":""},{"$f":"IF(C231=\"\",\"\",IF(B231<>\"\",IF(Tool!F85=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E231=\"Concrete\",IF(Tool!I85>Tool!G85,0,IF(Tool!G85>0,Tool!G85,\"\")),\"\")","v":""},{"$f":"IF(AND(E231=Tool!$G$12,Tool!H85>0),Tool!H85,\"\")","v":""},{"$f":"IF(E231=\"Concrete\",IF(Tool!I85>Tool!G85,Tool!G85,IF(Tool!I85>=0,Tool!I85,0)),\"\")","v":""},{"$f":"IF(E231=\"Concrete\",Tool!J85,\"\")","v":""},"",{"$f":"IF(E231=\"Concrete\",Tool!O85,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=23,E208<=30),23,\"\")","v":""},{"$f":"IF(D30>=$D$2,\"\",IF($D$2<(Tool!E85-Tool!$D$64),\"\",IF(Tool!D86<>\"\",IF(Tool!$D$64<>0,Tool!E85-Tool!$D$64,Tool!E85),\"\")))","v":""},{"$f":"IF(C31=\"\",\"\",IF(B233=\"\",$D$2,IF((D30-$C$9)>=$D$2,\"\",IF(Tool!E85<>\"\",IF(AND($D$2>=(Tool!E86-Tool!$D$64),(Tool!E87-Tool!$D$64)>=(Tool!E86-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E86-Tool!$D$64,Tool!E86),$D$2),\"\"))))","v":""},{"$f":"IF(C232=\"\",\"\",IF(B232<>\"\",IF(Tool!F86=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E232=\"Concrete\",IF(Tool!I86>Tool!G86,0,IF(Tool!G86>0,Tool!G86,\"\")),\"\")","v":""},{"$f":"IF(AND(E232=Tool!$G$12,Tool!H86>0),Tool!H86,\"\")","v":""},{"$f":"IF(E232=\"Concrete\",IF(Tool!I86>Tool!G86,Tool!G86,IF(Tool!I86>=0,Tool!I86,0)),\"\")","v":""},{"$f":"IF(E232=\"Concrete\",Tool!J86,\"\")","v":""},"",{"$f":"IF(E232=\"Concrete\",Tool!O86,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=24,E208<=30),24,\"\")","v":""},{"$f":"IF(D31>=$D$2,\"\",IF($D$2<(Tool!E86-Tool!$D$64),\"\",IF(Tool!D87<>\"\",IF(Tool!$D$64<>0,Tool!E86-Tool!$D$64,Tool!E86),\"\")))","v":""},{"$f":"IF(C32=\"\",\"\",IF(B234=\"\",$D$2,IF((D31-$C$9)>=$D$2,\"\",IF(Tool!E86<>\"\",IF(AND($D$2>=(Tool!E87-Tool!$D$64),(Tool!E88-Tool!$D$64)>=(Tool!E87-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E87-Tool!$D$64,Tool!E87),$D$2),\"\"))))","v":""},{"$f":"IF(C233=\"\",\"\",IF(B233<>\"\",IF(Tool!F87=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E233=\"Concrete\",IF(Tool!I87>Tool!G87,0,IF(Tool!G87>0,Tool!G87,\"\")),\"\")","v":""},{"$f":"IF(AND(E233=Tool!$G$12,Tool!H87>0),Tool!H87,\"\")","v":""},{"$f":"IF(E233=\"Concrete\",IF(Tool!I87>Tool!G87,Tool!G87,IF(Tool!I87>=0,Tool!I87,0)),\"\")","v":""},{"$f":"IF(E233=\"Concrete\",Tool!J87,\"\")","v":""},"",{"$f":"IF(E233=\"Concrete\",Tool!O87,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=25,E208<=30),25,\"\")","v":""},{"$f":"IF(D32>=$D$2,\"\",IF($D$2<(Tool!E87-Tool!$D$64),\"\",IF(Tool!D88<>\"\",IF(Tool!$D$64<>0,Tool!E87-Tool!$D$64,Tool!E87),\"\")))","v":""},{"$f":"IF(C33=\"\",\"\",IF(B235=\"\",$D$2,IF((D32-$C$9)>=$D$2,\"\",IF(Tool!E87<>\"\",IF(AND($D$2>=(Tool!E88-Tool!$D$64),(Tool!E89-Tool!$D$64)>=(Tool!E88-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E88-Tool!$D$64,Tool!E88),$D$2),\"\"))))","v":""},{"$f":"IF(C234=\"\",\"\",IF(B234<>\"\",IF(Tool!F88=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E234=\"Concrete\",IF(Tool!I88>Tool!G88,0,IF(Tool!G88>0,Tool!G88,\"\")),\"\")","v":""},{"$f":"IF(AND(E234=Tool!$G$12,Tool!H88>0),Tool!H88,\"\")","v":""},{"$f":"IF(E234=\"Concrete\",IF(Tool!I88>Tool!G88,Tool!G88,IF(Tool!I88>=0,Tool!I88,0)),\"\")","v":""},{"$f":"IF(E234=\"Concrete\",Tool!J88,\"\")","v":""},"",{"$f":"IF(E234=\"Concrete\",Tool!O88,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=26,E208<=30),26,\"\")","v":""},{"$f":"IF(D33>=$D$2,\"\",IF($D$2<(Tool!E88-Tool!$D$64),\"\",IF(Tool!D89<>\"\",IF(Tool!$D$64<>0,Tool!E88-Tool!$D$64,Tool!E88),\"\")))","v":""},{"$f":"IF(C34=\"\",\"\",IF(B236=\"\",$D$2,IF((D33-$C$9)>=$D$2,\"\",IF(Tool!E88<>\"\",IF(AND($D$2>=(Tool!E89-Tool!$D$64),(Tool!E90-Tool!$D$64)>=(Tool!E89-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E89-Tool!$D$64,Tool!E89),$D$2),\"\"))))","v":""},{"$f":"IF(C235=\"\",\"\",IF(B235<>\"\",IF(Tool!F89=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E235=\"Concrete\",IF(Tool!I89>Tool!G89,0,IF(Tool!G89>0,Tool!G89,\"\")),\"\")","v":""},{"$f":"IF(AND(E235=Tool!$G$12,Tool!H89>0),Tool!H89,\"\")","v":""},{"$f":"IF(E235=\"Concrete\",IF(Tool!I89>Tool!G89,Tool!G89,IF(Tool!I89>=0,Tool!I89,0)),\"\")","v":""},{"$f":"IF(E235=\"Concrete\",Tool!J89,\"\")","v":""},"",{"$f":"IF(E235=\"Concrete\",Tool!O89,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=27,E208<=30),27,\"\")","v":""},{"$f":"IF(D34>=$D$2,\"\",IF($D$2<(Tool!E89-Tool!$D$64),\"\",IF(Tool!D90<>\"\",IF(Tool!$D$64<>0,Tool!E89-Tool!$D$64,Tool!E89),\"\")))","v":""},{"$f":"IF(C35=\"\",\"\",IF(B237=\"\",$D$2,IF((D34-$C$9)>=$D$2,\"\",IF(Tool!E89<>\"\",IF(AND($D$2>=(Tool!E90-Tool!$D$64),(Tool!E91-Tool!$D$64)>=(Tool!E90-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E90-Tool!$D$64,Tool!E90),$D$2),\"\"))))","v":""},{"$f":"IF(C236=\"\",\"\",IF(B236<>\"\",IF(Tool!F90=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E236=\"Concrete\",IF(Tool!I90>Tool!G90,0,IF(Tool!G90>0,Tool!G90,\"\")),\"\")","v":""},{"$f":"IF(AND(E236=Tool!$G$12,Tool!H90>0),Tool!H90,\"\")","v":""},{"$f":"IF(E236=\"Concrete\",IF(Tool!I90>Tool!G90,Tool!G90,IF(Tool!I90>=0,Tool!I90,0)),\"\")","v":""},{"$f":"IF(E236=\"Concrete\",Tool!J90,\"\")","v":""},"",{"$f":"IF(E236=\"Concrete\",Tool!O90,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=28,E208<=30),28,\"\")","v":""},{"$f":"IF(D35>=$D$2,\"\",IF($D$2<(Tool!E90-Tool!$D$64),\"\",IF(Tool!D91<>\"\",IF(Tool!$D$64<>0,Tool!E90-Tool!$D$64,Tool!E90),\"\")))","v":""},{"$f":"IF(C36=\"\",\"\",IF(B238=\"\",$D$2,IF((D35-$C$9)>=$D$2,\"\",IF(Tool!E90<>\"\",IF(AND($D$2>=(Tool!E91-Tool!$D$64),(Tool!E92-Tool!$D$64)>=(Tool!E91-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E91-Tool!$D$64,Tool!E91),$D$2),\"\"))))","v":""},{"$f":"IF(C237=\"\",\"\",IF(B237<>\"\",IF(Tool!F91=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E237=\"Concrete\",IF(Tool!I91>Tool!G91,0,IF(Tool!G91>0,Tool!G91,\"\")),\"\")","v":""},{"$f":"IF(AND(E237=Tool!$G$12,Tool!H91>0),Tool!H91,\"\")","v":""},{"$f":"IF(E237=\"Concrete\",IF(Tool!I91>Tool!G91,Tool!G91,IF(Tool!I91>=0,Tool!I91,0)),\"\")","v":""},{"$f":"IF(E237=\"Concrete\",Tool!J91,\"\")","v":""},"",{"$f":"IF(E237=\"Concrete\",Tool!O91,\"\")","v":""},""]
[null,{"$f":"IF(AND(E208>=29,E208<=30),29,\"\")","v":""},{"$f":"IF(D36>=$D$2,\"\",IF($D$2<(Tool!E91-Tool!$D$64),\"\",IF(Tool!D92<>\"\",IF(Tool!$D$64<>0,Tool!E91-Tool!$D$64,Tool!E91),\"\")))","v":""},{"$f":"IF(C37=\"\",\"\",IF(B239=\"\",$D$2,IF((D36-$C$9)>=$D$2,\"\",IF(Tool!E91<>\"\",IF(AND($D$2>=(Tool!E92-Tool!$D$64),(Tool!E93-Tool!$D$64)>=(Tool!E92-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E92-Tool!$D$64,Tool!E92),$D$2),\"\"))))","v":""},{"$f":"IF(C238=\"\",\"\",IF(B238<>\"\",IF(Tool!F92=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E238=\"Concrete\",IF(Tool!I92>Tool!G92,0,IF(Tool!G92>0,Tool!G92,\"\")),\"\")","v":""},{"$f":"IF(AND(E238=Tool!$G$12,Tool!H92>0),Tool!H92,\"\")","v":""},{"$f":"IF(E238=\"Concrete\",IF(Tool!I92>Tool!G92,Tool!G92,IF(Tool!I92>=0,Tool!I92,0)),\"\")","v":""},{"$f":"IF(E238=\"Concrete\",Tool!J92,\"\")","v":""},"",{"$f":"IF(E238=\"Concrete\",Tool!O92,\"\")","v":""},""]
[null,{"$f":"IF(E208=30,30,\"\")","v":""},{"$f":"IF(D37>=$D$2,\"\",IF($D$2<(Tool!E92-Tool!$D$64),\"\",IF(Tool!D93<>\"\",IF(Tool!$D$64<>0,Tool!E92-Tool!$D$64,Tool!E92),\"\")))","v":""},{"$f":"IF(C38=\"\",\"\",IF(B240=\"\",$D$2,IF((D37-$C$9)>=$D$2,\"\",IF(Tool!E92<>\"\",IF(AND($D$2>=(Tool!E93-Tool!$D$64),(Tool!E94-Tool!$D$64)>=(Tool!E93-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E93-Tool!$D$64,Tool!E93),$D$2),\"\"))))","v":""},{"$f":"IF(C239=\"\",\"\",IF(B239<>\"\",IF(Tool!F93=Tool!$G$12,\"Concrete\",\"\"),\"\"))","v":""},{"$f":"IF(E239=\"Concrete\",IF(Tool!I93>Tool!G93,0,IF(Tool!G93>0,Tool!G93,\"\")),\"\")","v":""},{"$f":"IF(AND(E239=Tool!$G$12,Tool!H93>0),Tool!H93,\"\")","v":""},{"$f":"IF(E239=\"Concrete\",IF(Tool!I93>Tool!G93,Tool!G93,IF(Tool!I93>=0,Tool!I93,0)),\"\")","v":""},{"$f":"IF(E239=\"Concrete\",Tool!J93,\"\")","v":""},"",{"$f":"IF(E239=\"Concrete\",Tool!O93,\"\")","v":""},""]
[]
[null,null,null,null,null,null,"Average Width:",{"$f":"IFERROR((SUMPRODUCT(F210:F239,J210:J239)/SUM(J210:J239))-(SUMPRODUCT(H210:H239,J210:J239)/SUM(J210:J239)),0)","v":0},"Average Additional Full Depth:",{"$f":"IFERROR(SUMPRODUCT(--(I210:I239=\"Yes\"),H210:H239,J210:J239)/SUM(J210:J239),0)","v":0},"Area",{"$f":"H244*J241*5280","v":0}]
[null,null,null,null,null,null,"Average Shoulder Width:",{"$f":"IF(SUM(J210:J239)>0,(SUMPRODUCT(G210:G239,J210:J239)/SUM(J210:J239))*2,0)","v":0},"Total Full Depth Width:",{"$f":"H241+J241","v":0}]
[null,null,null,null,null,null,"Average Resurface Pavement:",{"$f":"IFERROR(SUMPRODUCT(--(I210:I239=\"No\"),H210:H239,J210:J239)/SUM(J210:J239),0)","v":0},"Average Roadway Width:",{"$f":"IFERROR(SUMPRODUCT(Y119:Y138,Z119:Z138)/SUM(Z119:Z138),0)","v":0}]
[null,null,null,null,null,null,"Length:",{"$f":"SUM(J210:J239)","v":0}]
[null,null,null,null,null,null,"Perimeter Length",{"$f":"SUM(L210:L239)","v":0}]

{"sheet":"Drainage","index":32,"n_rows":80,"n_cols":20,"rows_kept":80,"cut":false,"hidden":true,"merged":[[73,19,79,26],[1,1,1,2],[5,1,5,3],[5,9,5,11],[50,9,50,10],[44,9,44,11],[20,9,20,10],[43,1,43,3],[6,1,6,3],[30,15,32,15],[37,9,37,10],[37,13,37,15],[25,9,25,10],[55,18,56,18],[55,14,56,14],[54,16,54,17],[55,13,56,13],[55,15,56,15],[83,1,83,3],[84,1,84,2],[59,12,59,13],[59,14,59,15],[58,9,58,15],[60,13,63,13],[60,15,63,15]]}
[]
[null,"Project Length:",null,{"$f":"IF((Tool!$J$54-Tool!$J$52)>0,(Tool!$J$54-Tool!$J$52),0)","v":0}]
[]
[]
[]
[null,"Rural",null,null,null,null,null,null,null,"Overall Summary"]
[null,"Segments:",null,null,{"$f":"Tool!$J$61","v":1},null,null,null,null,"Item #","Description","Quantity"]
[null,"Segments","Begin","End","Ditch Sections","Length",null,null,null,"701-01.01","Concrete Sidewalk (4\")",{"$f":"K47","v":0}]
[null,{"$f":"IF(AND(E7>=1,E7<=30),1,\"\")","v":1},{"$f":"IF(Tool!D64<>\"\",IF(B9<>\"\",IF(Tool!D64=0,Tool!D64,Tool!D64-Tool!D64),\"\"),\"\")","v":""},{"$f":"IF(C9=\"\",\"\",IF((Tool!E65-Tool!D64)<(Tool!E64-Tool!D64),D2,IF(B9<>\"\",IF(Tool!E64<>\"\",IF(AND(B10=\"\",Tool!E64-Tool!D64<$D$2),$D$2,IF(B9=1,IF($D$2<(Tool!E64-Tool!$D$64),$D$2,IF(Tool!D64<>0,(Tool!E64-Tool!D64),Tool!E64)),\"\")),\"\"),\"\")))","v":""},{"$f":"IF(AND(B9<>\"\",Tool!K64=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G64=Tool!I64,Tool!H64=0),\"\",IF(AND(B9<>\"\",D9<>\"\"),IF(E9=\"TRUE\",D9-C9,\"\"),\"\"))","v":""},null,null,null,"702-03","Concrete Combined Curb & Gutter",{"$f":"L49","v":0}]
[null,{"$f":"IF(AND(E7>=2,E7<=30),2,\"\")","v":""},{"$f":"IF(B10<>\"\",IF(D9>=$D$2,\"\",IF($D$2<(Tool!E64-Tool!$D$64),\"\",IF(Tool!D65<>\"\",IF(Tool!$D$64<>0,Tool!E64-Tool!$D$64,Tool!E64),\"\"))),\"\")","v":""},{"$f":"IF(C10=\"\",\"\",IF(B11=\"\",$D$2,IF((D9-$C$9)>=$D$2,\"\",IF(Tool!E64<>\"\",IF(AND($D$2>=(Tool!E65-Tool!$D$64),(Tool!E66-Tool!$D$64)>=(Tool!E65-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E65-Tool!$D$64,Tool!E65),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B10<>\"\",Tool!K65=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G65=Tool!I65,Tool!H65=0),\"\",IF(AND(B10<>\"\",D10<>\"\"),IF(E10=\"TRUE\",D10-C10,\"\"),\"\"))","v":""},null,null,null,"611-12.03","Catch Basins, Type 12, > 8' - 12' Depth",{"$f":"P34","v":0}]
[null,{"$f":"IF(AND(E7>=3,E7<=30),3,\"\")","v":""},{"$f":"IF(B11<>\"\",IF(D10>=$D$2,\"\",IF($D$2<(Tool!E65-Tool!$D$64),\"\",IF(Tool!D66<>\"\",IF(Tool!$D$64<>0,Tool!E65-Tool!$D$64,Tool!E65),\"\"))),\"\")","v":""},{"$f":"IF(C11=\"\",\"\",IF(B12=\"\",$D$2,IF((D10-$C$9)>=$D$2,\"\",IF(Tool!E65<>\"\",IF(AND($D$2>=(Tool!E66-Tool!$D$64),(Tool!E67-Tool!$D$64)>=(Tool!E66-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E66-Tool!$D$64,Tool!E66),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B11<>\"\",Tool!K66=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G66=Tool!I66,Tool!H66=0),\"\",IF(AND(B11<>\"\",D11<>\"\"),IF(E11=\"TRUE\",D11-C11,\"\"),\"\"))","v":""},null,null,null,"611-14.03","Catch Basins, Type 14, > 8' - 12' Depth",{"$f":"P35","v":0}]
[null,{"$f":"IF(AND(E7>=4,E7<=30),4,\"\")","v":""},{"$f":"IF(B12<>\"\",IF(D11>=$D$2,\"\",IF($D$2<(Tool!E66-Tool!$D$64),\"\",IF(Tool!D67<>\"\",IF(Tool!$D$64<>0,Tool!E66-Tool!$D$64,Tool!E66),\"\"))),\"\")","v":""},{"$f":"IF(C12=\"\",\"\",IF(B13=\"\",$D$2,IF((D11-$C$9)>=$D$2,\"\",IF(Tool!E66<>\"\",IF(AND($D$2>=(Tool!E67-Tool!$D$64),(Tool!E68-Tool!$D$64)>=(Tool!E67-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E67-Tool!$D$64,Tool!E67),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B12<>\"\",Tool!K67=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G67=Tool!I67,Tool!H67=0),\"\",IF(AND(B12<>\"\",D12<>\"\"),IF(E12=\"TRUE\",D12-C12,\"\"),\"\"))","v":""},null,null,null,"611-42.02","Catch Basins, Type 42, > 4' - 8' Depth",{"$f":"P36","v":0}]
[null,{"$f":"IF(AND(E7>=5,E7<=30),5,\"\")","v":""},{"$f":"IF(B13<>\"\",IF(D12>=$D$2,\"\",IF($D$2<(Tool!E67-Tool!$D$64),\"\",IF(Tool!D68<>\"\",IF(Tool!$D$64<>0,Tool!E67-Tool!$D$64,Tool!E67),\"\"))),\"\")","v":""},{"$f":"IF(C13=\"\",\"\",IF(B14=\"\",$D$2,IF((D12-$C$9)>=$D$2,\"\",IF(Tool!E67<>\"\",IF(AND($D$2>=(Tool!E68-Tool!$D$64),(Tool!E69-Tool!$D$64)>=(Tool!E68-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E68-Tool!$D$64,Tool!E68),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B13<>\"\",Tool!K68=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G68=Tool!I68,Tool!H68=0),\"\",IF(AND(B13<>\"\",D13<>\"\"),IF(E13=\"TRUE\",D13-C13,\"\"),\"\"))","v":""},null,null,null,"607-05.02","24\" Concrete Pipe Culvert (Class III)",{"$f":"K39+K40","v":0}]
[null,{"$f":"IF(AND(E7>=6,E7<=30),6,\"\")","v":""},{"$f":"IF(B14<>\"\",IF(D13>=$D$2,\"\",IF($D$2<(Tool!E68-Tool!$D$64),\"\",IF(Tool!D69<>\"\",IF(Tool!$D$64<>0,Tool!E68-Tool!$D$64,Tool!E68),\"\"))),\"\")","v":""},{"$f":"IF(C14=\"\",\"\",IF(B15=\"\",$D$2,IF((D13-$C$9)>=$D$2,\"\",IF(Tool!E68<>\"\",IF(AND($D$2>=(Tool!E69-Tool!$D$64),(Tool!E70-Tool!$D$64)>=(Tool!E69-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E69-Tool!$D$64,Tool!E69),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B14<>\"\",Tool!K69=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G69=Tool!I69,Tool!H69=0),\"\",IF(AND(B14<>\"\",D14<>\"\"),IF(E14=\"TRUE\",D14-C14,\"\"),\"\"))","v":""},null,null,null,"611-07.01","Class A Concrete (Pipe Endwalls)",{"$f":"P39","v":0}]
[null,{"$f":"IF(AND(E7>=7,E7<=30),7,\"\")","v":""},{"$f":"IF(B15<>\"\",IF(D14>=$D$2,\"\",IF($D$2<(Tool!E69-Tool!$D$64),\"\",IF(Tool!D70<>\"\",IF(Tool!$D$64<>0,Tool!E69-Tool!$D$64,Tool!E69),\"\"))),\"\")","v":""},{"$f":"IF(C15=\"\",\"\",IF(B16=\"\",$D$2,IF((D14-$C$9)>=$D$2,\"\",IF(Tool!E69<>\"\",IF(AND($D$2>=(Tool!E70-Tool!$D$64),(Tool!E71-Tool!$D$64)>=(Tool!E70-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E70-Tool!$D$64,Tool!E70),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B15<>\"\",Tool!K70=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G70=Tool!I70,Tool!H70=0),\"\",IF(AND(B15<>\"\",D15<>\"\"),IF(E15=\"TRUE\",D15-C15,\"\"),\"\"))","v":""},null,null,null,"611-07.02","Steel Bar Reinforcement (Pipe Endwalls)",{"$f":"P40","v":0}]
[null,{"$f":"IF(AND(E7>=8,E7<=30),8,\"\")","v":""},{"$f":"IF(B16<>\"\",IF(D15>=$D$2,\"\",IF($D$2<(Tool!E70-Tool!$D$64),\"\",IF(Tool!D71<>\"\",IF(Tool!$D$64<>0,Tool!E70-Tool!$D$64,Tool!E70),\"\"))),\"\")","v":""},{"$f":"IF(C16=\"\",\"\",IF(B17=\"\",$D$2,IF((D15-$C$9)>=$D$2,\"\",IF(Tool!E70<>\"\",IF(AND($D$2>=(Tool!E71-Tool!$D$64),(Tool!E72-Tool!$D$64)>=(Tool!E71-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E71-Tool!$D$64,Tool!E71),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B16<>\"\",Tool!K71=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G71=Tool!I71,Tool!H71=0),\"\",IF(AND(B16<>\"\",D16<>\"\"),IF(E16=\"TRUE\",D16-C16,\"\"),\"\"))","v":""},null,null,null,"801-01","Seeding (With Mulch)",{"$f":"1.25*S56/1000","v":0}]
[null,{"$f":"IF(AND(E7>=9,F7<=20),9,\"\")","v":""},{"$f":"IF(B17<>\"\",IF(D16>=$D$2,\"\",IF($D$2<(Tool!E71-Tool!$D$64),\"\",IF(Tool!D72<>\"\",IF(Tool!$D$64<>0,Tool!E71-Tool!$D$64,Tool!E71),\"\"))),\"\")","v":""},{"$f":"IF(C17=\"\",\"\",IF(B18=\"\",$D$2,IF((D16-$C$9)>=$D$2,\"\",IF(Tool!E71<>\"\",IF(AND($D$2>=(Tool!E72-Tool!$D$64),(Tool!E73-Tool!$D$64)>=(Tool!E72-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E72-Tool!$D$64,Tool!E72),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B17<>\"\",Tool!K72=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G72=Tool!I72,Tool!H72=0),\"\",IF(AND(B17<>\"\",D17<>\"\"),IF(E17=\"TRUE\",D17-C17,\"\"),\"\"))","v":""},null,null,null,"801-01.07","Temporary Seeding (With Mulch)",{"$f":"0.75*L16","v":0}]
[null,{"$f":"IF(AND(E7>=10,E7<=30),10,\"\")","v":""},{"$f":"IF(B18<>\"\",IF(D17>=$D$2,\"\",IF($D$2<(Tool!E72-Tool!$D$64),\"\",IF(Tool!D73<>\"\",IF(Tool!$D$64<>0,Tool!E72-Tool!$D$64,Tool!E72),\"\"))),\"\")","v":""},{"$f":"IF(C18=\"\",\"\",IF(B19=\"\",$D$2,IF((D17-$C$9)>=$D$2,\"\",IF(Tool!E72<>\"\",IF(AND($D$2>=(Tool!E73-Tool!$D$64),(Tool!E74-Tool!$D$64)>=(Tool!E73-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E73-Tool!$D$64,Tool!E73),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B18<>\"\",Tool!K73=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G73=Tool!I73,Tool!H73=0),\"\",IF(AND(B18<>\"\",D18<>\"\"),IF(E18=\"TRUE\",D18-C18,\"\"),\"\"))","v":""},null,null,null,"801-02","Seeding (Without Mulch)",{"$f":"0.75*L16","v":0}]
[null,{"$f":"IF(AND(E7>=11,E7<=30),11,\"\")","v":""},{"$f":"IF(B19<>\"\",IF(D18>=$D$2,\"\",IF($D$2<(Tool!E73-Tool!$D$64),\"\",IF(Tool!D74<>\"\",IF(Tool!$D$64<>0,Tool!E73-Tool!$D$64,Tool!E73),\"\"))),\"\")","v":""},{"$f":"IF(C19=\"\",\"\",IF(B20=\"\",$D$2,IF((D18-$C$9)>=$D$2,\"\",IF(Tool!E73<>\"\",IF(AND($D$2>=(Tool!E74-Tool!$D$64),(Tool!E75-Tool!$D$64)>=(Tool!E74-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E74-Tool!$D$64,Tool!E74),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B19<>\"\",Tool!K74=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G74=Tool!I74,Tool!H74=0),\"\",IF(AND(B19<>\"\",D19<>\"\"),IF(E19=\"TRUE\",D19-C19,\"\"),\"\"))","v":""},null,null,null,"303-01","Stone (CY)",{"$f":"L47","v":0}]
[null,{"$f":"IF(AND(E7>=12,F7<=30),12,\"\")","v":""},{"$f":"IF(B20<>\"\",IF(D19>=$D$2,\"\",IF($D$2<(Tool!E74-Tool!$D$64),\"\",IF(Tool!D75<>\"\",IF(Tool!$D$64<>0,Tool!E74-Tool!$D$64,Tool!E74),\"\"))),\"\")","v":""},{"$f":"IF(C20=\"\",\"\",IF(B21=\"\",$D$2,IF((D19-$C$9)>=$D$2,\"\",IF(Tool!E74<>\"\",IF(AND($D$2>=(Tool!E75-Tool!$D$64),(Tool!E76-Tool!$D$64)>=(Tool!E75-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E75-Tool!$D$64,Tool!E75),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B20<>\"\",Tool!K75=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G75=Tool!I75,Tool!H75=0),\"\",IF(AND(B20<>\"\",D20<>\"\"),IF(E20=\"TRUE\",D20-C20,\"\"),\"\"))","v":""}]
[null,{"$f":"IF(AND(E7>=13,E7<=30),13,\"\")","v":""},{"$f":"IF(B21<>\"\",IF(D20>=$D$2,\"\",IF($D$2<(Tool!E75-Tool!$D$64),\"\",IF(Tool!D76<>\"\",IF(Tool!$D$64<>0,Tool!E75-Tool!$D$64,Tool!E75),\"\"))),\"\")","v":""},{"$f":"IF(C21=\"\",\"\",IF(B22=\"\",$D$2,IF((D20-$C$9)>=$D$2,\"\",IF(Tool!E75<>\"\",IF(AND($D$2>=(Tool!E76-Tool!$D$64),(Tool!E77-Tool!$D$64)>=(Tool!E76-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E76-Tool!$D$64,Tool!E76),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B21<>\"\",Tool!K76=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G76=Tool!I76,Tool!H76=0),\"\",IF(AND(B21<>\"\",D21<>\"\"),IF(E21=\"TRUE\",D21-C21,\"\"),\"\"))","v":""},null,null,null,"Roadway Width Properties"]
[null,{"$f":"IF(AND(E7>=14,E7<=30),14,\"\")","v":""},{"$f":"IF(B22<>\"\",IF(D21>=$D$2,\"\",IF($D$2<(Tool!E76-Tool!$D$64),\"\",IF(Tool!D77<>\"\",IF(Tool!$D$64<>0,Tool!E76-Tool!$D$64,Tool!E76),\"\"))),\"\")","v":""},{"$f":"IF(C22=\"\",\"\",IF(B23=\"\",$D$2,IF((D21-$C$9)>=$D$2,\"\",IF(Tool!E76<>\"\",IF(AND($D$2>=(Tool!E77-Tool!$D$64),(Tool!E78-Tool!$D$64)>=(Tool!E77-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E77-Tool!$D$64,Tool!E77),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B22<>\"\",Tool!K77=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G77=Tool!I77,Tool!H77=0),\"\",IF(AND(B22<>\"\",D22<>\"\"),IF(E22=\"TRUE\",D22-C22,\"\"),\"\"))","v":""},null,null,null,"Average Full Depth Width:",{"$f":"Roadway!S41","v":0}]
[null,{"$f":"IF(AND(E7>=15,E7<=30),15,\"\")","v":""},{"$f":"IF(B23<>\"\",IF(D22>=$D$2,\"\",IF($D$2<(Tool!E77-Tool!$D$64),\"\",IF(Tool!D78<>\"\",IF(Tool!$D$64<>0,Tool!E77-Tool!$D$64,Tool!E77),\"\"))),\"\")","v":""},{"$f":"IF(C23=\"\",\"\",IF(B24=\"\",$D$2,IF((D22-$C$9)>=$D$2,\"\",IF(Tool!E77<>\"\",IF(AND($D$2>=(Tool!E78-Tool!$D$64),(Tool!E79-Tool!$D$64)>=(Tool!E78-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E78-Tool!$D$64,Tool!E78),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B23<>\"\",Tool!K78=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G78=Tool!I78,Tool!H78=0),\"\",IF(AND(B23<>\"\",D23<>\"\"),IF(E23=\"TRUE\",D23-C23,\"\"),\"\"))","v":""},null,null,null,"Average Median Width:",{"$f":"Median!L21","v":0}]
[null,{"$f":"IF(AND(E7>=16,E7<=30),16,\"\")","v":""},{"$f":"IF(B24<>\"\",IF(D23>=$D$2,\"\",IF($D$2<(Tool!E78-Tool!$D$64),\"\",IF(Tool!D79<>\"\",IF(Tool!$D$64<>0,Tool!E78-Tool!$D$64,Tool!E78),\"\"))),\"\")","v":""},{"$f":"IF(C24=\"\",\"\",IF(B25=\"\",$D$2,IF((D23-$C$9)>=$D$2,\"\",IF(Tool!E78<>\"\",IF(AND($D$2>=(Tool!E79-Tool!$D$64),(Tool!E80-Tool!$D$64)>=(Tool!E79-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E79-Tool!$D$64,Tool!E79),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B24<>\"\",Tool!K79=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G79=Tool!I79,Tool!H79=0),\"\",IF(AND(B24<>\"\",D24<>\"\"),IF(E24=\"TRUE\",D24-C24,\"\"),\"\"))","v":""},null,null,null,"Average Sidewalk/C&G Width:",{"$f":"G78+G79","v":0}]
[null,{"$f":"IF(AND(E7>=17,E7<=30),17,\"\")","v":""},{"$f":"IF(B25<>\"\",IF(D24>=$D$2,\"\",IF($D$2<(Tool!E79-Tool!$D$64),\"\",IF(Tool!D80<>\"\",IF(Tool!$D$64<>0,Tool!E79-Tool!$D$64,Tool!E79),\"\"))),\"\")","v":""},{"$f":"IF(C25=\"\",\"\",IF(B26=\"\",$D$2,IF((D24-$C$9)>=$D$2,\"\",IF(Tool!E79<>\"\",IF(AND($D$2>=(Tool!E80-Tool!$D$64),(Tool!E81-Tool!$D$64)>=(Tool!E80-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E80-Tool!$D$64,Tool!E80),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B25<>\"\",Tool!K80=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G80=Tool!I80,Tool!H80=0),\"\",IF(AND(B25<>\"\",D25<>\"\"),IF(E25=\"TRUE\",D25-C25,\"\"),\"\"))","v":""},null,null,null,"Average Facility Width:",{"$f":"SUM(K22:K24)","v":0}]
[null,{"$f":"IF(AND(E7>=18,E7<=30),18,\"\")","v":""},{"$f":"IF(B26<>\"\",IF(D25>=$D$2,\"\",IF($D$2<(Tool!E80-Tool!$D$64),\"\",IF(Tool!D81<>\"\",IF(Tool!$D$64<>0,Tool!E80-Tool!$D$64,Tool!E80),\"\"))),\"\")","v":""},{"$f":"IF(C26=\"\",\"\",IF(B27=\"\",$D$2,IF((D25-$C$9)>=$D$2,\"\",IF(Tool!E80<>\"\",IF(AND($D$2>=(Tool!E81-Tool!$D$64),(Tool!E82-Tool!$D$64)>=(Tool!E81-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E81-Tool!$D$64,Tool!E81),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B26<>\"\",Tool!K81=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G81=Tool!I81,Tool!H81=0),\"\",IF(AND(B26<>\"\",D26<>\"\"),IF(E26=\"TRUE\",D26-C26,\"\"),\"\"))","v":""},null,null,null,"Drainage Breakdown"]
[null,{"$f":"IF(AND(E7>=19,E7<=30),19,\"\")","v":""},{"$f":"IF(B27<>\"\",IF(D26>=$D$2,\"\",IF($D$2<(Tool!E81-Tool!$D$64),\"\",IF(Tool!D82<>\"\",IF(Tool!$D$64<>0,Tool!E81-Tool!$D$64,Tool!E81),\"\"))),\"\")","v":""},{"$f":"IF(C27=\"\",\"\",IF(B28=\"\",$D$2,IF((D26-$C$9)>=$D$2,\"\",IF(Tool!E81<>\"\",IF(AND($D$2>=(Tool!E82-Tool!$D$64),(Tool!E83-Tool!$D$64)>=(Tool!E82-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E82-Tool!$D$64,Tool!E82),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B27<>\"\",Tool!K82=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G82=Tool!I82,Tool!H82=0),\"\",IF(AND(B27<>\"\",D27<>\"\"),IF(E27=\"TRUE\",D27-C27,\"\"),\"\"))","v":""},null,null,null,"Rural",{"$f":"IF(D2>0,$F$40/$D$2,0)","v":0}]
[null,{"$f":"IF(AND(E7>=20,E7<=30),20,\"\")","v":""},{"$f":"IF(B28<>\"\",IF(D27>=$D$2,\"\",IF($D$2<(Tool!E82-Tool!$D$64),\"\",IF(Tool!D83<>\"\",IF(Tool!$D$64<>0,Tool!E82-Tool!$D$64,Tool!E82),\"\"))),\"\")","v":""},{"$f":"IF(C28=\"\",\"\",IF(B29=\"\",$D$2,IF((D27-$C$9)>=$D$2,\"\",IF(Tool!E82<>\"\",IF(AND($D$2>=(Tool!E83-Tool!$D$64),(Tool!E84-Tool!$D$64)>=(Tool!E83-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E83-Tool!$D$64,Tool!E83),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B28<>\"\",Tool!K83=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G83=Tool!I83,Tool!H83=0),\"\",IF(AND(B28<>\"\",D28<>\"\"),IF(E28=\"TRUE\",D28-C28,\"\"),\"\"))","v":""},null,null,null,"Urban",{"$f":"IF(D2>0,$E$77/$D$2,0)","v":0}]
[null,{"$f":"IF(AND(E7>=21,E7<=30),21,\"\")","v":""},{"$f":"IF(B29<>\"\",IF(D28>=$D$2,\"\",IF($D$2<(Tool!E83-Tool!$D$64),\"\",IF(Tool!D84<>\"\",IF(Tool!$D$64<>0,Tool!E83-Tool!$D$64,Tool!E83),\"\"))),\"\")","v":""},{"$f":"IF(C29=\"\",\"\",IF(B30=\"\",$D$2,IF((D28-$C$9)>=$D$2,\"\",IF(Tool!E83<>\"\",IF(AND($D$2>=(Tool!E84-Tool!$D$64),(Tool!E85-Tool!$D$64)>=(Tool!E84-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E84-Tool!$D$64,Tool!E84),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B29<>\"\",Tool!K84=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G84=Tool!I84,Tool!H84=0),\"\",IF(AND(B29<>\"\",D29<>\"\"),IF(E29=\"TRUE\",D29-C29,\"\"),\"\"))","v":""}]
[null,{"$f":"IF(AND(E7>=22,E7<=30),22,\"\")","v":""},{"$f":"IF(B30<>\"\",IF(D29>=$D$2,\"\",IF($D$2<(Tool!E84-Tool!$D$64),\"\",IF(Tool!D85<>\"\",IF(Tool!$D$64<>0,Tool!E84-Tool!$D$64,Tool!E84),\"\"))),\"\")","v":""},{"$f":"IF(C30=\"\",\"\",IF(B31=\"\",$D$2,IF((D29-$C$9)>=$D$2,\"\",IF(Tool!E84<>\"\",IF(AND($D$2>=(Tool!E85-Tool!$D$64),(Tool!E86-Tool!$D$64)>=(Tool!E85-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E85-Tool!$D$64,Tool!E85),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B30<>\"\",Tool!K85=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G85=Tool!I85,Tool!H85=0),\"\",IF(AND(B30<>\"\",D30<>\"\"),IF(E30=\"TRUE\",D30-C30,\"\"),\"\"))","v":""}]
[null,{"$f":"IF(AND(E7>=23,E7<=30),23,\"\")","v":""},{"$f":"IF(B31<>\"\",IF(D30>=$D$2,\"\",IF($D$2<(Tool!E85-Tool!$D$64),\"\",IF(Tool!D86<>\"\",IF(Tool!$D$64<>0,Tool!E85-Tool!$D$64,Tool!E85),\"\"))),\"\")","v":""},{"$f":"IF(C31=\"\",\"\",IF(B32=\"\",$D$2,IF((D30-$C$9)>=$D$2,\"\",IF(Tool!E85<>\"\",IF(AND($D$2>=(Tool!E86-Tool!$D$64),(Tool!E87-Tool!$D$64)>=(Tool!E86-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E86-Tool!$D$64,Tool!E86),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B31<>\"\",Tool!K86=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G86=Tool!I86,Tool!H86=0),\"\",IF(AND(B31<>\"\",D31<>\"\"),IF(E31=\"TRUE\",D31-C31,\"\"),\"\"))","v":""},null,null,null,null,"Terrain Type:","Flat","Rolling","Mountainous","Heavy Mountainous","Total"]
[null,{"$f":"IF(AND(E7>=24,E7<=30),24,\"\")","v":""},{"$f":"IF(B32<>\"\",IF(D31>=$D$2,\"\",IF($D$2<(Tool!E86-Tool!$D$64),\"\",IF(Tool!D87<>\"\",IF(Tool!$D$64<>0,Tool!E86-Tool!$D$64,Tool!E86),\"\"))),\"\")","v":""},{"$f":"IF(C32=\"\",\"\",IF(B33=\"\",$D$2,IF((D31-$C$9)>=$D$2,\"\",IF(Tool!E86<>\"\",IF(AND($D$2>=(Tool!E87-Tool!$D$64),(Tool!E88-Tool!$D$64)>=(Tool!E87-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E87-Tool!$D$64,Tool!E87),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B32<>\"\",Tool!K87=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G87=Tool!I87,Tool!H87=0),\"\",IF(AND(B32<>\"\",D32<>\"\"),IF(E32=\"TRUE\",D32-C32,\"\"),\"\"))","v":""},null,null,null,null,"Adjustment Factor:",1.2,1,0.9,0.8]
[null,{"$f":"IF(AND(E7>=25,E7<=30),25,\"\")","v":""},{"$f":"IF(B33<>\"\",IF(D32>=$D$2,\"\",IF($D$2<(Tool!E87-Tool!$D$64),\"\",IF(Tool!D88<>\"\",IF(Tool!$D$64<>0,Tool!E87-Tool!$D$64,Tool!E87),\"\"))),\"\")","v":""},{"$f":"IF(C33=\"\",\"\",IF(B34=\"\",$D$2,IF((D32-$C$9)>=$D$2,\"\",IF(Tool!E87<>\"\",IF(AND($D$2>=(Tool!E88-Tool!$D$64),(Tool!E89-Tool!$D$64)>=(Tool!E88-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E88-Tool!$D$64,Tool!E88),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B33<>\"\",Tool!K88=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G88=Tool!I88,Tool!H88=0),\"\",IF(AND(B33<>\"\",D33<>\"\"),IF(E33=\"TRUE\",D33-C33,\"\"),\"\"))","v":""},null,null,null,null,"Percent Terrain Type:",{"$f":"Terrain!AC32","v":0},{"$f":"Terrain!AC33","v":0},{"$f":"Terrain!AC34","v":0},{"$f":"Terrain!AC35","v":0}]
[null,{"$f":"IF(AND(E7>=26,E7<=30),26,\"\")","v":""},{"$f":"IF(B34<>\"\",IF(D33>=$D$2,\"\",IF($D$2<(Tool!E88-Tool!$D$64),\"\",IF(Tool!D89<>\"\",IF(Tool!$D$64<>0,Tool!E88-Tool!$D$64,Tool!E88),\"\"))),\"\")","v":""},{"$f":"IF(C34=\"\",\"\",IF(B35=\"\",$D$2,IF((D33-$C$9)>=$D$2,\"\",IF(Tool!E88<>\"\",IF(AND($D$2>=(Tool!E89-Tool!$D$64),(Tool!E90-Tool!$D$64)>=(Tool!E89-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E89-Tool!$D$64,Tool!E89),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B34<>\"\",Tool!K89=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G89=Tool!I89,Tool!H89=0),\"\",IF(AND(B34<>\"\",D34<>\"\"),IF(E34=\"TRUE\",D34-C34,\"\"),\"\"))","v":""},null,null,null,"Type 12",{"$f":"(E78*0.5*5280/300)","v":0},{"$f":"$K$34*L32*L33","v":0},{"$f":"$K$34*M32*M33","v":0},{"$f":"$K$34*N32*N33","v":0},{"$f":"$K$34*O32*O33","v":0},{"$f":"SUM(L34:O34)","v":0}]
[null,{"$f":"IF(AND(E7>=27,E7<=30),27,\"\")","v":""},{"$f":"IF(B35<>\"\",IF(D34>=$D$2,\"\",IF($D$2<(Tool!E89-Tool!$D$64),\"\",IF(Tool!D90<>\"\",IF(Tool!$D$64<>0,Tool!E89-Tool!$D$64,Tool!E89),\"\"))),\"\")","v":""},{"$f":"IF(C35=\"\",\"\",IF(B36=\"\",$D$2,IF((D34-$C$9)>=$D$2,\"\",IF(Tool!E89<>\"\",IF(AND($D$2>=(Tool!E90-Tool!$D$64),(Tool!E91-Tool!$D$64)>=(Tool!E90-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E90-Tool!$D$64,Tool!E90),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B35<>\"\",Tool!K90=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G90=Tool!I90,Tool!H90=0),\"\",IF(AND(B35<>\"\",D35<>\"\"),IF(E35=\"TRUE\",D35-C35,\"\"),\"\"))","v":""},null,null,null,"Type 14",{"$f":"(E78*0.5*5280/600)","v":0},{"$f":"$K$35*L32*L33","v":0},{"$f":"$K$35*M32*M33","v":0},{"$f":"$K$35*N32*N33","v":0},{"$f":"$K$35*O32*O33","v":0},{"$f":"SUM(L35:O35)","v":0}]
[null,{"$f":"IF(AND(E7>=28,E7<=30),28,\"\")","v":""},{"$f":"IF(B36<>\"\",IF(D35>=$D$2,\"\",IF($D$2<(Tool!E90-Tool!$D$64),\"\",IF(Tool!D91<>\"\",IF(Tool!$D$64<>0,Tool!E90-Tool!$D$64,Tool!E90),\"\"))),\"\")","v":""},{"$f":"IF(C36=\"\",\"\",IF(B37=\"\",$D$2,IF((D35-$C$9)>=$D$2,\"\",IF(Tool!E90<>\"\",IF(AND($D$2>=(Tool!E91-Tool!$D$64),(Tool!E92-Tool!$D$64)>=(Tool!E91-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E91-Tool!$D$64,Tool!E91),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B36<>\"\",Tool!K91=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G91=Tool!I91,Tool!H91=0),\"\",IF(AND(B36<>\"\",D36<>\"\"),IF(E36=\"TRUE\",D36-C36,\"\"),\"\"))","v":""},null,null,null,"Type 42",{"$f":"(E78*0.5*4)","v":0},{"$f":"$K$36*L32*L33","v":0},{"$f":"$K$36*M32*M33","v":0},{"$f":"$K$36*N32*N33","v":0},{"$f":"$K$36*O32*O33","v":0},{"$f":"SUM(L36:O36)","v":0}]
[null,{"$f":"IF(AND(E7>=29,E7<=30),29,\"\")","v":""},{"$f":"IF(B37<>\"\",IF(D36>=$D$2,\"\",IF($D$2<(Tool!E91-Tool!$D$64),\"\",IF(Tool!D92<>\"\",IF(Tool!$D$64<>0,Tool!E91-Tool!$D$64,Tool!E91),\"\"))),\"\")","v":""},{"$f":"IF(C37=\"\",\"\",IF(B38=\"\",$D$2,IF((D36-$C$9)>=$D$2,\"\",IF(Tool!E91<>\"\",IF(AND($D$2>=(Tool!E92-Tool!$D$64),(Tool!E93-Tool!$D$64)>=(Tool!E92-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E92-Tool!$D$64,Tool!E92),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B37<>\"\",Tool!K92=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G92=Tool!I92,Tool!H92=0),\"\",IF(AND(B37<>\"\",D37<>\"\"),IF(E37=\"TRUE\",D37-C37,\"\"),\"\"))","v":""}]
[null,{"$f":"IF(E7=30,30,\"\")","v":""},{"$f":"IF(B38<>\"\",IF(D37>=$D$2,\"\",IF($D$2<(Tool!E92-Tool!$D$64),\"\",IF(Tool!D93<>\"\",IF(Tool!$D$64<>0,Tool!E92-Tool!$D$64,Tool!E92),\"\"))),\"\")","v":""},{"$f":"IF(C38=\"\",\"\",IF(B39=\"\",$D$2,IF((D37-$C$9)>=$D$2,\"\",IF(Tool!E92<>\"\",IF(AND($D$2>=(Tool!E93-Tool!$D$64),(Tool!E94-Tool!$D$64)>=(Tool!E93-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E93-Tool!$D$64,Tool!E93),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B38<>\"\",Tool!K93=Tool!$B$7),\"TRUE\",\"\")","v":""},{"$f":"IF(AND(Tool!G93=Tool!I93,Tool!H93=0),\"\",IF(AND(B38<>\"\",D38<>\"\"),IF(E38=\"TRUE\",D38-C38,\"\"),\"\"))","v":""},null,null,null,"Drainage - 24\" RCP",null,null,null,"Drainage - Endwalls"]
[null,null,null,null,null,null,null,null,null,"Rural",{"$f":"K27*D2*10*(K25+L56)","v":0},null,null,"Conc (PEnd)","CY",{"$f":"((F40+G77)*10*2*1.61)","v":0}]
[null,null,null,null,"Ditch Length:",{"$f":"IF(SUM(F9:F38)>0,SUM(F9:F38),0)","v":0},null,null,null,"Urban",{"$f":"((D2*5280)+(D2*5280/200)*(K25))*K28","v":0},null,null,"Steel (PEnd)","LB",{"$f":"((F40+G77)*10*2*153)","v":0}]
[null,null,null,null,"Eff Rural Ditch Length:",{"$f":"F40*2","v":0}]
[]
[null,"Urban"]
[null,"Segments:",null,null,{"$f":"Tool!$J$61","v":1}]
[null,"Segments","Begin","End","C&G","C&G Sides","Sidewalk","Length",null,"Urban Typical Section for Curb and Sidewalk"]
[null,{"$f":"IF(AND(E44>=1,E44<=30),1,\"\")","v":1},{"$f":"IF(Tool!D64<>\"\",IF(B9<>\"\",IF(Tool!D64=0,Tool!D64,Tool!D64-Tool!D64),\"\"),\"\")","v":""},{"$f":"IF(C9=\"\",\"\",IF((Tool!E65-Tool!D64)<(Tool!E64-Tool!D64),D2,IF(B9<>\"\",IF(Tool!E64<>\"\",IF(AND(B10=\"\",Tool!E64-Tool!D64<$D$2),$D$2,IF(B9=1,IF($D$2<(Tool!E64-Tool!$D$64),$D$2,IF(Tool!D64<>0,(Tool!E64-Tool!D64),Tool!E64)),\"\")),\"\"),\"\")))","v":""},{"$f":"IF(AND(B9<>\"\",Tool!K64=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E46=\"TRUE\",IF(Tool!L64=\"Both Sides\",2,IF(Tool!L64=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E46=\"TRUE\",IF(AND(F46=1,Tool!M64=\"Both Sides\"),1,IF(AND(F46=2,Tool!M64=\"Both Sides\"),2,IF(AND(F46=2,Tool!M64=\"One Side\"),1,IF(AND(F46=1,Tool!M64=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G64=Tool!I64,Tool!H64=0),\"\",IF(AND(B46<>\"\",D46<>\"\"),IF(E46=\"TRUE\",D46-C46,\"\"),\"\"))","v":""},null,"SIDEWALK (4 \")","AREA (SQFT)","Stone CY"]
[null,{"$f":"IF(AND(E44>=2,E44<=30),2,\"\")","v":""},{"$f":"IF(B10<>\"\",IF(D9>=$D$2,\"\",IF($D$2<(Tool!E64-Tool!$D$64),\"\",IF(Tool!D65<>\"\",IF(Tool!$D$64<>0,Tool!E64-Tool!$D$64,Tool!E64),\"\"))),\"\")","v":""},{"$f":"IF(C10=\"\",\"\",IF(B11=\"\",$D$2,IF((D9-$C$9)>=$D$2,\"\",IF(Tool!E64<>\"\",IF(AND($D$2>=(Tool!E65-Tool!$D$64),(Tool!E66-Tool!$D$64)>=(Tool!E65-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E65-Tool!$D$64,Tool!E65),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B10<>\"\",Tool!K65=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E47=\"TRUE\",IF(Tool!L65=\"Both Sides\",2,IF(Tool!L65=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E47=\"TRUE\",IF(AND(F47=1,Tool!M65=\"Both Sides\"),1,IF(AND(F47=2,Tool!M65=\"Both Sides\"),2,IF(AND(F47=2,Tool!M65=\"One Side\"),1,IF(AND(F47=1,Tool!M65=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G65=Tool!I65,Tool!H65=0),\"\",IF(AND(B47<>\"\",D47<>\"\"),IF(E47=\"TRUE\",D47-C47,\"\"),\"\"))","v":""},null,"Total:",{"$f":"E80*Tool!M61*5280","v":0},{"$f":"(K47*0.5)/27","v":0}]
[null,{"$f":"IF(AND(E44>=3,E44<=30),3,\"\")","v":""},{"$f":"IF(B11<>\"\",IF(D10>=$D$2,\"\",IF($D$2<(Tool!E65-Tool!$D$64),\"\",IF(Tool!D66<>\"\",IF(Tool!$D$64<>0,Tool!E65-Tool!$D$64,Tool!E65),\"\"))),\"\")","v":""},{"$f":"IF(C11=\"\",\"\",IF(B12=\"\",$D$2,IF((D10-$C$9)>=$D$2,\"\",IF(Tool!E65<>\"\",IF(AND($D$2>=(Tool!E66-Tool!$D$64),(Tool!E67-Tool!$D$64)>=(Tool!E66-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E66-Tool!$D$64,Tool!E66),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B11<>\"\",Tool!K66=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E48=\"TRUE\",IF(Tool!L66=\"Both Sides\",2,IF(Tool!L66=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E48=\"TRUE\",IF(AND(F48=1,Tool!M66=\"Both Sides\"),1,IF(AND(F48=2,Tool!M66=\"Both Sides\"),2,IF(AND(F48=2,Tool!M66=\"One Side\"),1,IF(AND(F48=1,Tool!M66=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G66=Tool!I66,Tool!H66=0),\"\",IF(AND(B48<>\"\",D48<>\"\"),IF(E48=\"TRUE\",D48-C48,\"\"),\"\"))","v":""},null,"C&G","LF","CY"]
[null,{"$f":"IF(AND(E44>=4,E44<=30),4,\"\")","v":""},{"$f":"IF(B12<>\"\",IF(D11>=$D$2,\"\",IF($D$2<(Tool!E66-Tool!$D$64),\"\",IF(Tool!D67<>\"\",IF(Tool!$D$64<>0,Tool!E66-Tool!$D$64,Tool!E66),\"\"))),\"\")","v":""},{"$f":"IF(C12=\"\",\"\",IF(B13=\"\",$D$2,IF((D11-$C$9)>=$D$2,\"\",IF(Tool!E66<>\"\",IF(AND($D$2>=(Tool!E67-Tool!$D$64),(Tool!E68-Tool!$D$64)>=(Tool!E67-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E67-Tool!$D$64,Tool!E67),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B12<>\"\",Tool!K67=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E49=\"TRUE\",IF(Tool!L67=\"Both Sides\",2,IF(Tool!L67=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E49=\"TRUE\",IF(AND(F49=1,Tool!M67=\"Both Sides\"),1,IF(AND(F49=2,Tool!M67=\"Both Sides\"),2,IF(AND(F49=2,Tool!M67=\"One Side\"),1,IF(AND(F49=1,Tool!M67=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G67=Tool!I67,Tool!H67=0),\"\",IF(AND(B49<>\"\",D49<>\"\"),IF(E49=\"TRUE\",D49-C49,\"\"),\"\"))","v":""},null,"Total:",{"$f":"(E78)*5280","v":0},{"$f":"K49*0.07181","v":0}]
[null,{"$f":"IF(AND(E44>=5,E44<=30),5,\"\")","v":""},{"$f":"IF(B13<>\"\",IF(D12>=$D$2,\"\",IF($D$2<(Tool!E67-Tool!$D$64),\"\",IF(Tool!D68<>\"\",IF(Tool!$D$64<>0,Tool!E67-Tool!$D$64,Tool!E67),\"\"))),\"\")","v":""},{"$f":"IF(C13=\"\",\"\",IF(B14=\"\",$D$2,IF((D12-$C$9)>=$D$2,\"\",IF(Tool!E67<>\"\",IF(AND($D$2>=(Tool!E68-Tool!$D$64),(Tool!E69-Tool!$D$64)>=(Tool!E68-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E68-Tool!$D$64,Tool!E68),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B13<>\"\",Tool!K68=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E50=\"TRUE\",IF(Tool!L68=\"Both Sides\",2,IF(Tool!L68=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E50=\"TRUE\",IF(AND(F50=1,Tool!M68=\"Both Sides\"),1,IF(AND(F50=2,Tool!M68=\"Both Sides\"),2,IF(AND(F50=2,Tool!M68=\"One Side\"),1,IF(AND(F50=1,Tool!M68=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G68=Tool!I68,Tool!H68=0),\"\",IF(AND(B50<>\"\",D50<>\"\"),IF(E50=\"TRUE\",D50-C50,\"\"),\"\"))","v":""}]
[null,{"$f":"IF(AND(E44>=6,E44<=30),6,\"\")","v":""},{"$f":"IF(B14<>\"\",IF(D13>=$D$2,\"\",IF($D$2<(Tool!E68-Tool!$D$64),\"\",IF(Tool!D69<>\"\",IF(Tool!$D$64<>0,Tool!E68-Tool!$D$64,Tool!E68),\"\"))),\"\")","v":""},{"$f":"IF(C14=\"\",\"\",IF(B15=\"\",$D$2,IF((D13-$C$9)>=$D$2,\"\",IF(Tool!E68<>\"\",IF(AND($D$2>=(Tool!E69-Tool!$D$64),(Tool!E70-Tool!$D$64)>=(Tool!E69-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E69-Tool!$D$64,Tool!E69),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B14<>\"\",Tool!K69=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E51=\"TRUE\",IF(Tool!L69=\"Both Sides\",2,IF(Tool!L69=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E51=\"TRUE\",IF(AND(F51=1,Tool!M69=\"Both Sides\"),1,IF(AND(F51=2,Tool!M69=\"Both Sides\"),2,IF(AND(F51=2,Tool!M69=\"One Side\"),1,IF(AND(F51=1,Tool!M69=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G69=Tool!I69,Tool!H69=0),\"\",IF(AND(B51<>\"\",D51<>\"\"),IF(E51=\"TRUE\",D51-C51,\"\"),\"\"))","v":""},null,"Drainage - 24\" RCP",null,"LF"]
[null,{"$f":"IF(AND(E44>=7,E44<=30),7,\"\")","v":""},{"$f":"IF(B15<>\"\",IF(D14>=$D$2,\"\",IF($D$2<(Tool!E69-Tool!$D$64),\"\",IF(Tool!D70<>\"\",IF(Tool!$D$64<>0,Tool!E69-Tool!$D$64,Tool!E69),\"\"))),\"\")","v":""},{"$f":"IF(C15=\"\",\"\",IF(B16=\"\",$D$2,IF((D14-$C$9)>=$D$2,\"\",IF(Tool!E69<>\"\",IF(AND($D$2>=(Tool!E70-Tool!$D$64),(Tool!E71-Tool!$D$64)>=(Tool!E70-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E70-Tool!$D$64,Tool!E70),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B15<>\"\",Tool!K70=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E52=\"TRUE\",IF(Tool!L70=\"Both Sides\",2,IF(Tool!L70=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E52=\"TRUE\",IF(AND(F52=1,Tool!M70=\"Both Sides\"),1,IF(AND(F52=2,Tool!M70=\"Both Sides\"),2,IF(AND(F52=2,Tool!M70=\"One Side\"),1,IF(AND(F52=1,Tool!M70=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G70=Tool!I70,Tool!H70=0),\"\",IF(AND(B52<>\"\",D52<>\"\"),IF(E52=\"TRUE\",D52-C52,\"\"),\"\"))","v":""},null,"Rural",{"$f":"IF(D2>0,F41/($D$2*2),0)","v":0},{"$f":"K25*D2*10*K52","v":0}]
[null,{"$f":"IF(AND(E44>=8,E44<=30),8,\"\")","v":""},{"$f":"IF(B16<>\"\",IF(D15>=$D$2,\"\",IF($D$2<(Tool!E70-Tool!$D$64),\"\",IF(Tool!D71<>\"\",IF(Tool!$D$64<>0,Tool!E70-Tool!$D$64,Tool!E70),\"\"))),\"\")","v":""},{"$f":"IF(C16=\"\",\"\",IF(B17=\"\",$D$2,IF((D15-$C$9)>=$D$2,\"\",IF(Tool!E70<>\"\",IF(AND($D$2>=(Tool!E71-Tool!$D$64),(Tool!E72-Tool!$D$64)>=(Tool!E71-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E71-Tool!$D$64,Tool!E71),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B16<>\"\",Tool!K71=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E53=\"TRUE\",IF(Tool!L71=\"Both Sides\",2,IF(Tool!L71=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E53=\"TRUE\",IF(AND(F53=1,Tool!M71=\"Both Sides\"),1,IF(AND(F53=2,Tool!M71=\"Both Sides\"),2,IF(AND(F53=2,Tool!M71=\"One Side\"),1,IF(AND(F53=1,Tool!M71=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G71=Tool!I71,Tool!H71=0),\"\",IF(AND(B53<>\"\",D53<>\"\"),IF(E53=\"TRUE\",D53-C53,\"\"),\"\"))","v":""},null,"Urban",{"$f":"IF(D2>0,E78/($D$2*2),0)","v":0},{"$f":"((D2*5280)+(D2*5280/200)*(K25))*K53","v":0}]
[null,{"$f":"IF(AND(E44>=9,F44<=20),9,\"\")","v":""},{"$f":"IF(B17<>\"\",IF(D16>=$D$2,\"\",IF($D$2<(Tool!E71-Tool!$D$64),\"\",IF(Tool!D72<>\"\",IF(Tool!$D$64<>0,Tool!E71-Tool!$D$64,Tool!E71),\"\"))),\"\")","v":""},{"$f":"IF(C17=\"\",\"\",IF(B18=\"\",$D$2,IF((D16-$C$9)>=$D$2,\"\",IF(Tool!E71<>\"\",IF(AND($D$2>=(Tool!E72-Tool!$D$64),(Tool!E73-Tool!$D$64)>=(Tool!E72-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E72-Tool!$D$64,Tool!E72),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B17<>\"\",Tool!K72=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E54=\"TRUE\",IF(Tool!L72=\"Both Sides\",2,IF(Tool!L72=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E54=\"TRUE\",IF(AND(F54=1,Tool!M72=\"Both Sides\"),1,IF(AND(F54=2,Tool!M72=\"Both Sides\"),2,IF(AND(F54=2,Tool!M72=\"One Side\"),1,IF(AND(F54=1,Tool!M72=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G72=Tool!I72,Tool!H72=0),\"\",IF(AND(B54<>\"\",D54<>\"\"),IF(E54=\"TRUE\",D54-C54,\"\"),\"\"))","v":""}]
[null,{"$f":"IF(AND(E44>=10,E44<=30),10,\"\")","v":""},{"$f":"IF(B18<>\"\",IF(D17>=$D$2,\"\",IF($D$2<(Tool!E72-Tool!$D$64),\"\",IF(Tool!D73<>\"\",IF(Tool!$D$64<>0,Tool!E72-Tool!$D$64,Tool!E72),\"\"))),\"\")","v":""},{"$f":"IF(C18=\"\",\"\",IF(B19=\"\",$D$2,IF((D17-$C$9)>=$D$2,\"\",IF(Tool!E72<>\"\",IF(AND($D$2>=(Tool!E73-Tool!$D$64),(Tool!E74-Tool!$D$64)>=(Tool!E73-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E73-Tool!$D$64,Tool!E73),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B18<>\"\",Tool!K73=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E55=\"TRUE\",IF(Tool!L73=\"Both Sides\",2,IF(Tool!L73=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E55=\"TRUE\",IF(AND(F55=1,Tool!M73=\"Both Sides\"),1,IF(AND(F55=2,Tool!M73=\"Both Sides\"),2,IF(AND(F55=2,Tool!M73=\"One Side\"),1,IF(AND(F55=1,Tool!M73=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G73=Tool!I73,Tool!H73=0),\"\",IF(AND(B55<>\"\",D55<>\"\"),IF(E55=\"TRUE\",D55-C55,\"\"),\"\"))","v":""},null,null,"Length","Add. Width","Percent Type","Avg. Add. Slope Width","Avg. Facility Width","Rec. Avg. ROW Width","Avg. Interior Grass Median Area",null,"Avg. Seed Area"]
[null,{"$f":"IF(AND(E44>=11,E44<=30),11,\"\")","v":""},{"$f":"IF(B19<>\"\",IF(D18>=$D$2,\"\",IF($D$2<(Tool!E73-Tool!$D$64),\"\",IF(Tool!D74<>\"\",IF(Tool!$D$64<>0,Tool!E73-Tool!$D$64,Tool!E73),\"\"))),\"\")","v":""},{"$f":"IF(C19=\"\",\"\",IF(B20=\"\",$D$2,IF((D18-$C$9)>=$D$2,\"\",IF(Tool!E73<>\"\",IF(AND($D$2>=(Tool!E74-Tool!$D$64),(Tool!E75-Tool!$D$64)>=(Tool!E74-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E74-Tool!$D$64,Tool!E74),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B19<>\"\",Tool!K74=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E56=\"TRUE\",IF(Tool!L74=\"Both Sides\",2,IF(Tool!L74=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E56=\"TRUE\",IF(AND(F56=1,Tool!M74=\"Both Sides\"),1,IF(AND(F56=2,Tool!M74=\"Both Sides\"),2,IF(AND(F56=2,Tool!M74=\"One Side\"),1,IF(AND(F56=1,Tool!M74=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G74=Tool!I74,Tool!H74=0),\"\",IF(AND(B56<>\"\",D56<>\"\"),IF(E56=\"TRUE\",D56-C56,\"\"),\"\"))","v":""},null,"Average Ditch Length:",{"$f":"F41+E79","v":0},{"$f":"N61","v":0},{"$f":"IF(D2>0,K56/(D2*2),0)","v":0},{"$f":"(L56*M56)+(L57*M57)","v":0},{"$f":"K25","v":0},{"$f":"K25+N56*2","v":0},"Depressed Grass:",{"$f":"Median!H31","v":0},{"$f":"(D2*2*5280*N56)+R56+R57","v":0}]
[null,{"$f":"IF(AND(E44>=12,F44<=30),12,\"\")","v":""},{"$f":"IF(B20<>\"\",IF(D19>=$D$2,\"\",IF($D$2<(Tool!E74-Tool!$D$64),\"\",IF(Tool!D75<>\"\",IF(Tool!$D$64<>0,Tool!E74-Tool!$D$64,Tool!E74),\"\"))),\"\")","v":""},{"$f":"IF(C20=\"\",\"\",IF(B21=\"\",$D$2,IF((D19-$C$9)>=$D$2,\"\",IF(Tool!E74<>\"\",IF(AND($D$2>=(Tool!E75-Tool!$D$64),(Tool!E76-Tool!$D$64)>=(Tool!E75-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E75-Tool!$D$64,Tool!E75),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B20<>\"\",Tool!K75=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E57=\"TRUE\",IF(Tool!L75=\"Both Sides\",2,IF(Tool!L75=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E57=\"TRUE\",IF(AND(F57=1,Tool!M75=\"Both Sides\"),1,IF(AND(F57=2,Tool!M75=\"Both Sides\"),2,IF(AND(F57=2,Tool!M75=\"One Side\"),1,IF(AND(F57=1,Tool!M75=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G75=Tool!I75,Tool!H75=0),\"\",IF(AND(B57<>\"\",D57<>\"\"),IF(E57=\"TRUE\",D57-C57,\"\"),\"\"))","v":""},null,"Average C&G Length:",{"$f":"E78","v":0},{"$f":"P61","v":0},{"$f":"IF(D2>0,K57/(D2*2),0)","v":0},null,null,null,"Raised Grass:",{"$f":"Median!H59","v":0}]
[null,{"$f":"IF(AND(E44>=13,E44<=30),13,\"\")","v":""},{"$f":"IF(B21<>\"\",IF(D20>=$D$2,\"\",IF($D$2<(Tool!E75-Tool!$D$64),\"\",IF(Tool!D76<>\"\",IF(Tool!$D$64<>0,Tool!E75-Tool!$D$64,Tool!E75),\"\"))),\"\")","v":""},{"$f":"IF(C21=\"\",\"\",IF(B22=\"\",$D$2,IF((D20-$C$9)>=$D$2,\"\",IF(Tool!E75<>\"\",IF(AND($D$2>=(Tool!E76-Tool!$D$64),(Tool!E77-Tool!$D$64)>=(Tool!E76-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E76-Tool!$D$64,Tool!E76),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B21<>\"\",Tool!K76=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E58=\"TRUE\",IF(Tool!L76=\"Both Sides\",2,IF(Tool!L76=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E58=\"TRUE\",IF(AND(F58=1,Tool!M76=\"Both Sides\"),1,IF(AND(F58=2,Tool!M76=\"Both Sides\"),2,IF(AND(F58=2,Tool!M76=\"One Side\"),1,IF(AND(F58=1,Tool!M76=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G76=Tool!I76,Tool!H76=0),\"\",IF(AND(B58<>\"\",D58<>\"\"),IF(E58=\"TRUE\",D58-C58,\"\"),\"\"))","v":""}]
[null,{"$f":"IF(AND(E44>=14,E44<=30),14,\"\")","v":""},{"$f":"IF(B22<>\"\",IF(D21>=$D$2,\"\",IF($D$2<(Tool!E76-Tool!$D$64),\"\",IF(Tool!D77<>\"\",IF(Tool!$D$64<>0,Tool!E76-Tool!$D$64,Tool!E76),\"\"))),\"\")","v":""},{"$f":"IF(C22=\"\",\"\",IF(B23=\"\",$D$2,IF((D21-$C$9)>=$D$2,\"\",IF(Tool!E76<>\"\",IF(AND($D$2>=(Tool!E77-Tool!$D$64),(Tool!E78-Tool!$D$64)>=(Tool!E77-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E77-Tool!$D$64,Tool!E77),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B22<>\"\",Tool!K77=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E59=\"TRUE\",IF(Tool!L77=\"Both Sides\",2,IF(Tool!L77=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E59=\"TRUE\",IF(AND(F59=1,Tool!M77=\"Both Sides\"),1,IF(AND(F59=2,Tool!M77=\"Both Sides\"),2,IF(AND(F59=2,Tool!M77=\"One Side\"),1,IF(AND(F59=1,Tool!M77=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G77=Tool!I77,Tool!H77=0),\"\",IF(AND(B59<>\"\",D59<>\"\"),IF(E59=\"TRUE\",D59-C59,\"\"),\"\"))","v":""},null,"Roadway Terrain Summary"]
[null,{"$f":"IF(AND(E44>=15,E44<=30),15,\"\")","v":""},{"$f":"IF(B23<>\"\",IF(D22>=$D$2,\"\",IF($D$2<(Tool!E77-Tool!$D$64),\"\",IF(Tool!D78<>\"\",IF(Tool!$D$64<>0,Tool!E77-Tool!$D$64,Tool!E77),\"\"))),\"\")","v":""},{"$f":"IF(C23=\"\",\"\",IF(B24=\"\",$D$2,IF((D22-$C$9)>=$D$2,\"\",IF(Tool!E77<>\"\",IF(AND($D$2>=(Tool!E78-Tool!$D$64),(Tool!E79-Tool!$D$64)>=(Tool!E78-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E78-Tool!$D$64,Tool!E78),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B23<>\"\",Tool!K78=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E60=\"TRUE\",IF(Tool!L78=\"Both Sides\",2,IF(Tool!L78=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E60=\"TRUE\",IF(AND(F60=1,Tool!M78=\"Both Sides\"),1,IF(AND(F60=2,Tool!M78=\"Both Sides\"),2,IF(AND(F60=2,Tool!M78=\"One Side\"),1,IF(AND(F60=1,Tool!M78=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G78=Tool!I78,Tool!H78=0),\"\",IF(AND(B60<>\"\",D60<>\"\"),IF(E60=\"TRUE\",D60-C60,\"\"),\"\"))","v":""},null,null,"Roadway Length","Percent Type","Additional Width Rural",null,"Additional Width Urban"]
[null,{"$f":"IF(AND(E44>=16,E44<=30),16,\"\")","v":""},{"$f":"IF(B24<>\"\",IF(D23>=$D$2,\"\",IF($D$2<(Tool!E78-Tool!$D$64),\"\",IF(Tool!D79<>\"\",IF(Tool!$D$64<>0,Tool!E78-Tool!$D$64,Tool!E78),\"\"))),\"\")","v":""},{"$f":"IF(C24=\"\",\"\",IF(B25=\"\",$D$2,IF((D23-$C$9)>=$D$2,\"\",IF(Tool!E78<>\"\",IF(AND($D$2>=(Tool!E79-Tool!$D$64),(Tool!E80-Tool!$D$64)>=(Tool!E79-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E79-Tool!$D$64,Tool!E79),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B24<>\"\",Tool!K79=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E61=\"TRUE\",IF(Tool!L79=\"Both Sides\",2,IF(Tool!L79=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E61=\"TRUE\",IF(AND(F61=1,Tool!M79=\"Both Sides\"),1,IF(AND(F61=2,Tool!M79=\"Both Sides\"),2,IF(AND(F61=2,Tool!M79=\"One Side\"),1,IF(AND(F61=1,Tool!M79=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G79=Tool!I79,Tool!H79=0),\"\",IF(AND(B61<>\"\",D61<>\"\"),IF(E61=\"TRUE\",D61-C61,\"\"),\"\"))","v":""},null,"Flat:",{"$f":"Terrain!AB32","v":0},{"$f":"IF(SUM($K$61:$K$64)>0,K61/SUM($K$61:$K$64),0)","v":0},30,{"$f":"L61*M61+L62*M62+L63*M63+L64*M64","v":0},10,{"$f":"L61*O61+L62*O62+L63*O63+L64*O64","v":0}]
[null,{"$f":"IF(AND(E44>=17,E44<=30),17,\"\")","v":""},{"$f":"IF(B25<>\"\",IF(D24>=$D$2,\"\",IF($D$2<(Tool!E79-Tool!$D$64),\"\",IF(Tool!D80<>\"\",IF(Tool!$D$64<>0,Tool!E79-Tool!$D$64,Tool!E79),\"\"))),\"\")","v":""},{"$f":"IF(C25=\"\",\"\",IF(B26=\"\",$D$2,IF((D24-$C$9)>=$D$2,\"\",IF(Tool!E79<>\"\",IF(AND($D$2>=(Tool!E80-Tool!$D$64),(Tool!E81-Tool!$D$64)>=(Tool!E80-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E80-Tool!$D$64,Tool!E80),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B25<>\"\",Tool!K80=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E62=\"TRUE\",IF(Tool!L80=\"Both Sides\",2,IF(Tool!L80=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E62=\"TRUE\",IF(AND(F62=1,Tool!M80=\"Both Sides\"),1,IF(AND(F62=2,Tool!M80=\"Both Sides\"),2,IF(AND(F62=2,Tool!M80=\"One Side\"),1,IF(AND(F62=1,Tool!M80=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G80=Tool!I80,Tool!H80=0),\"\",IF(AND(B62<>\"\",D62<>\"\"),IF(E62=\"TRUE\",D62-C62,\"\"),\"\"))","v":""},null,"Rolling:",{"$f":"Terrain!AB33","v":0},{"$f":"IF(SUM($K$61:$K$64)>0,K62/SUM($K$61:$K$64),0)","v":0},35,null,15]
[null,{"$f":"IF(AND(E44>=18,E44<=30),18,\"\")","v":""},{"$f":"IF(B26<>\"\",IF(D25>=$D$2,\"\",IF($D$2<(Tool!E80-Tool!$D$64),\"\",IF(Tool!D81<>\"\",IF(Tool!$D$64<>0,Tool!E80-Tool!$D$64,Tool!E80),\"\"))),\"\")","v":""},{"$f":"IF(C26=\"\",\"\",IF(B27=\"\",$D$2,IF((D25-$C$9)>=$D$2,\"\",IF(Tool!E80<>\"\",IF(AND($D$2>=(Tool!E81-Tool!$D$64),(Tool!E82-Tool!$D$64)>=(Tool!E81-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E81-Tool!$D$64,Tool!E81),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B26<>\"\",Tool!K81=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E63=\"TRUE\",IF(Tool!L81=\"Both Sides\",2,IF(Tool!L81=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E63=\"TRUE\",IF(AND(F63=1,Tool!M81=\"Both Sides\"),1,IF(AND(F63=2,Tool!M81=\"Both Sides\"),2,IF(AND(F63=2,Tool!M81=\"One Side\"),1,IF(AND(F63=1,Tool!M81=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G81=Tool!I81,Tool!H81=0),\"\",IF(AND(B63<>\"\",D63<>\"\"),IF(E63=\"TRUE\",D63-C63,\"\"),\"\"))","v":""},null,"Mountainous:",{"$f":"Terrain!AB34","v":0},{"$f":"IF(SUM($K$61:$K$64)>0,K63/SUM($K$61:$K$64),0)","v":0},45,null,25]
[null,{"$f":"IF(AND(E44>=19,E44<=30),19,\"\")","v":""},{"$f":"IF(B27<>\"\",IF(D26>=$D$2,\"\",IF($D$2<(Tool!E81-Tool!$D$64),\"\",IF(Tool!D82<>\"\",IF(Tool!$D$64<>0,Tool!E81-Tool!$D$64,Tool!E81),\"\"))),\"\")","v":""},{"$f":"IF(C27=\"\",\"\",IF(B28=\"\",$D$2,IF((D26-$C$9)>=$D$2,\"\",IF(Tool!E81<>\"\",IF(AND($D$2>=(Tool!E82-Tool!$D$64),(Tool!E83-Tool!$D$64)>=(Tool!E82-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E82-Tool!$D$64,Tool!E82),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B27<>\"\",Tool!K82=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E64=\"TRUE\",IF(Tool!L82=\"Both Sides\",2,IF(Tool!L82=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E64=\"TRUE\",IF(AND(F64=1,Tool!M82=\"Both Sides\"),1,IF(AND(F64=2,Tool!M82=\"Both Sides\"),2,IF(AND(F64=2,Tool!M82=\"One Side\"),1,IF(AND(F64=1,Tool!M82=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G82=Tool!I82,Tool!H82=0),\"\",IF(AND(B64<>\"\",D64<>\"\"),IF(E64=\"TRUE\",D64-C64,\"\"),\"\"))","v":""},null,"Heavy Mountainous:",{"$f":"Terrain!AB35","v":0},{"$f":"IF(SUM($K$61:$K$64)>0,K64/SUM($K$61:$K$64),0)","v":0},60,null,35]
[null,{"$f":"IF(AND(E44>=20,E44<=30),20,\"\")","v":""},{"$f":"IF(B28<>\"\",IF(D27>=$D$2,\"\",IF($D$2<(Tool!E82-Tool!$D$64),\"\",IF(Tool!D83<>\"\",IF(Tool!$D$64<>0,Tool!E82-Tool!$D$64,Tool!E82),\"\"))),\"\")","v":""},{"$f":"IF(C28=\"\",\"\",IF(B29=\"\",$D$2,IF((D27-$C$9)>=$D$2,\"\",IF(Tool!E82<>\"\",IF(AND($D$2>=(Tool!E83-Tool!$D$64),(Tool!E84-Tool!$D$64)>=(Tool!E83-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E83-Tool!$D$64,Tool!E83),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B28<>\"\",Tool!K83=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E65=\"TRUE\",IF(Tool!L83=\"Both Sides\",2,IF(Tool!L83=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E65=\"TRUE\",IF(AND(F65=1,Tool!M83=\"Both Sides\"),1,IF(AND(F65=2,Tool!M83=\"Both Sides\"),2,IF(AND(F65=2,Tool!M83=\"One Side\"),1,IF(AND(F65=1,Tool!M83=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G83=Tool!I83,Tool!H83=0),\"\",IF(AND(B65<>\"\",D65<>\"\"),IF(E65=\"TRUE\",D65-C65,\"\"),\"\"))","v":""}]
[null,{"$f":"IF(AND(E44>=21,E44<=30),21,\"\")","v":""},{"$f":"IF(B29<>\"\",IF(D28>=$D$2,\"\",IF($D$2<(Tool!E83-Tool!$D$64),\"\",IF(Tool!D84<>\"\",IF(Tool!$D$64<>0,Tool!E83-Tool!$D$64,Tool!E83),\"\"))),\"\")","v":""},{"$f":"IF(C29=\"\",\"\",IF(B30=\"\",$D$2,IF((D28-$C$9)>=$D$2,\"\",IF(Tool!E83<>\"\",IF(AND($D$2>=(Tool!E84-Tool!$D$64),(Tool!E85-Tool!$D$64)>=(Tool!E84-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E84-Tool!$D$64,Tool!E84),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B29<>\"\",Tool!K84=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E66=\"TRUE\",IF(Tool!L84=\"Both Sides\",2,IF(Tool!L84=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E66=\"TRUE\",IF(AND(F66=1,Tool!M84=\"Both Sides\"),1,IF(AND(F66=2,Tool!M84=\"Both Sides\"),2,IF(AND(F66=2,Tool!M84=\"One Side\"),1,IF(AND(F66=1,Tool!M84=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G84=Tool!I84,Tool!H84=0),\"\",IF(AND(B66<>\"\",D66<>\"\"),IF(E66=\"TRUE\",D66-C66,\"\"),\"\"))","v":""}]
[null,{"$f":"IF(AND(E44>=22,E44<=30),22,\"\")","v":""},{"$f":"IF(B30<>\"\",IF(D29>=$D$2,\"\",IF($D$2<(Tool!E84-Tool!$D$64),\"\",IF(Tool!D85<>\"\",IF(Tool!$D$64<>0,Tool!E84-Tool!$D$64,Tool!E84),\"\"))),\"\")","v":""},{"$f":"IF(C30=\"\",\"\",IF(B31=\"\",$D$2,IF((D29-$C$9)>=$D$2,\"\",IF(Tool!E84<>\"\",IF(AND($D$2>=(Tool!E85-Tool!$D$64),(Tool!E86-Tool!$D$64)>=(Tool!E85-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E85-Tool!$D$64,Tool!E85),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B30<>\"\",Tool!K85=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E67=\"TRUE\",IF(Tool!L85=\"Both Sides\",2,IF(Tool!L85=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E67=\"TRUE\",IF(AND(F67=1,Tool!M85=\"Both Sides\"),1,IF(AND(F67=2,Tool!M85=\"Both Sides\"),2,IF(AND(F67=2,Tool!M85=\"One Side\"),1,IF(AND(F67=1,Tool!M85=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G85=Tool!I85,Tool!H85=0),\"\",IF(AND(B67<>\"\",D67<>\"\"),IF(E67=\"TRUE\",D67-C67,\"\"),\"\"))","v":""}]
[null,{"$f":"IF(AND(E44>=23,E44<=30),23,\"\")","v":""},{"$f":"IF(B31<>\"\",IF(D30>=$D$2,\"\",IF($D$2<(Tool!E85-Tool!$D$64),\"\",IF(Tool!D86<>\"\",IF(Tool!$D$64<>0,Tool!E85-Tool!$D$64,Tool!E85),\"\"))),\"\")","v":""},{"$f":"IF(C31=\"\",\"\",IF(B32=\"\",$D$2,IF((D30-$C$9)>=$D$2,\"\",IF(Tool!E85<>\"\",IF(AND($D$2>=(Tool!E86-Tool!$D$64),(Tool!E87-Tool!$D$64)>=(Tool!E86-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E86-Tool!$D$64,Tool!E86),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B31<>\"\",Tool!K86=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E68=\"TRUE\",IF(Tool!L86=\"Both Sides\",2,IF(Tool!L86=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E68=\"TRUE\",IF(AND(F68=1,Tool!M86=\"Both Sides\"),1,IF(AND(F68=2,Tool!M86=\"Both Sides\"),2,IF(AND(F68=2,Tool!M86=\"One Side\"),1,IF(AND(F68=1,Tool!M86=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G86=Tool!I86,Tool!H86=0),\"\",IF(AND(B68<>\"\",D68<>\"\"),IF(E68=\"TRUE\",D68-C68,\"\"),\"\"))","v":""}]
[null,{"$f":"IF(AND(E44>=24,E44<=30),24,\"\")","v":""},{"$f":"IF(B32<>\"\",IF(D31>=$D$2,\"\",IF($D$2<(Tool!E86-Tool!$D$64),\"\",IF(Tool!D87<>\"\",IF(Tool!$D$64<>0,Tool!E86-Tool!$D$64,Tool!E86),\"\"))),\"\")","v":""},{"$f":"IF(C32=\"\",\"\",IF(B33=\"\",$D$2,IF((D31-$C$9)>=$D$2,\"\",IF(Tool!E86<>\"\",IF(AND($D$2>=(Tool!E87-Tool!$D$64),(Tool!E88-Tool!$D$64)>=(Tool!E87-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E87-Tool!$D$64,Tool!E87),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B32<>\"\",Tool!K87=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E69=\"TRUE\",IF(Tool!L87=\"Both Sides\",2,IF(Tool!L87=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E69=\"TRUE\",IF(AND(F69=1,Tool!M87=\"Both Sides\"),1,IF(AND(F69=2,Tool!M87=\"Both Sides\"),2,IF(AND(F69=2,Tool!M87=\"One Side\"),1,IF(AND(F69=1,Tool!M87=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G87=Tool!I87,Tool!H87=0),\"\",IF(AND(B69<>\"\",D69<>\"\"),IF(E69=\"TRUE\",D69-C69,\"\"),\"\"))","v":""}]
[null,{"$f":"IF(AND(E44>=25,E44<=30),25,\"\")","v":""},{"$f":"IF(B33<>\"\",IF(D32>=$D$2,\"\",IF($D$2<(Tool!E87-Tool!$D$64),\"\",IF(Tool!D88<>\"\",IF(Tool!$D$64<>0,Tool!E87-Tool!$D$64,Tool!E87),\"\"))),\"\")","v":""},{"$f":"IF(C33=\"\",\"\",IF(B34=\"\",$D$2,IF((D32-$C$9)>=$D$2,\"\",IF(Tool!E87<>\"\",IF(AND($D$2>=(Tool!E88-Tool!$D$64),(Tool!E89-Tool!$D$64)>=(Tool!E88-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E88-Tool!$D$64,Tool!E88),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B33<>\"\",Tool!K88=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E70=\"TRUE\",IF(Tool!L88=\"Both Sides\",2,IF(Tool!L88=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E70=\"TRUE\",IF(AND(F70=1,Tool!M88=\"Both Sides\"),1,IF(AND(F70=2,Tool!M88=\"Both Sides\"),2,IF(AND(F70=2,Tool!M88=\"One Side\"),1,IF(AND(F70=1,Tool!M88=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G88=Tool!I88,Tool!H88=0),\"\",IF(AND(B70<>\"\",D70<>\"\"),IF(E70=\"TRUE\",D70-C70,\"\"),\"\"))","v":""}]
[null,{"$f":"IF(AND(E44>=26,E44<=30),26,\"\")","v":""},{"$f":"IF(B34<>\"\",IF(D33>=$D$2,\"\",IF($D$2<(Tool!E88-Tool!$D$64),\"\",IF(Tool!D89<>\"\",IF(Tool!$D$64<>0,Tool!E88-Tool!$D$64,Tool!E88),\"\"))),\"\")","v":""},{"$f":"IF(C34=\"\",\"\",IF(B35=\"\",$D$2,IF((D33-$C$9)>=$D$2,\"\",IF(Tool!E88<>\"\",IF(AND($D$2>=(Tool!E89-Tool!$D$64),(Tool!E90-Tool!$D$64)>=(Tool!E89-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E89-Tool!$D$64,Tool!E89),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B34<>\"\",Tool!K89=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E71=\"TRUE\",IF(Tool!L89=\"Both Sides\",2,IF(Tool!L89=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E71=\"TRUE\",IF(AND(F71=1,Tool!M89=\"Both Sides\"),1,IF(AND(F71=2,Tool!M89=\"Both Sides\"),2,IF(AND(F71=2,Tool!M89=\"One Side\"),1,IF(AND(F71=1,Tool!M89=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G89=Tool!I89,Tool!H89=0),\"\",IF(AND(B71<>\"\",D71<>\"\"),IF(E71=\"TRUE\",D71-C71,\"\"),\"\"))","v":""}]
[null,{"$f":"IF(AND(E44>=27,E44<=30),27,\"\")","v":""},{"$f":"IF(B35<>\"\",IF(D34>=$D$2,\"\",IF($D$2<(Tool!E89-Tool!$D$64),\"\",IF(Tool!D90<>\"\",IF(Tool!$D$64<>0,Tool!E89-Tool!$D$64,Tool!E89),\"\"))),\"\")","v":""},{"$f":"IF(C35=\"\",\"\",IF(B36=\"\",$D$2,IF((D34-$C$9)>=$D$2,\"\",IF(Tool!E89<>\"\",IF(AND($D$2>=(Tool!E90-Tool!$D$64),(Tool!E91-Tool!$D$64)>=(Tool!E90-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E90-Tool!$D$64,Tool!E90),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B35<>\"\",Tool!K90=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E72=\"TRUE\",IF(Tool!L90=\"Both Sides\",2,IF(Tool!L90=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E72=\"TRUE\",IF(AND(F72=1,Tool!M90=\"Both Sides\"),1,IF(AND(F72=2,Tool!M90=\"Both Sides\"),2,IF(AND(F72=2,Tool!M90=\"One Side\"),1,IF(AND(F72=1,Tool!M90=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G90=Tool!I90,Tool!H90=0),\"\",IF(AND(B72<>\"\",D72<>\"\"),IF(E72=\"TRUE\",D72-C72,\"\"),\"\"))","v":""}]
[null,{"$f":"IF(AND(E44>=28,E44<=30),28,\"\")","v":""},{"$f":"IF(B36<>\"\",IF(D35>=$D$2,\"\",IF($D$2<(Tool!E90-Tool!$D$64),\"\",IF(Tool!D91<>\"\",IF(Tool!$D$64<>0,Tool!E90-Tool!$D$64,Tool!E90),\"\"))),\"\")","v":""},{"$f":"IF(C36=\"\",\"\",IF(B37=\"\",$D$2,IF((D35-$C$9)>=$D$2,\"\",IF(Tool!E90<>\"\",IF(AND($D$2>=(Tool!E91-Tool!$D$64),(Tool!E92-Tool!$D$64)>=(Tool!E91-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E91-Tool!$D$64,Tool!E91),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B36<>\"\",Tool!K91=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E73=\"TRUE\",IF(Tool!L91=\"Both Sides\",2,IF(Tool!L91=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E73=\"TRUE\",IF(AND(F73=1,Tool!M91=\"Both Sides\"),1,IF(AND(F73=2,Tool!M91=\"Both Sides\"),2,IF(AND(F73=2,Tool!M91=\"One Side\"),1,IF(AND(F73=1,Tool!M91=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G91=Tool!I91,Tool!H91=0),\"\",IF(AND(B73<>\"\",D73<>\"\"),IF(E73=\"TRUE\",D73-C73,\"\"),\"\"))","v":""}]
[null,{"$f":"IF(AND(E44>=29,E44<=30),29,\"\")","v":""},{"$f":"IF(B37<>\"\",IF(D36>=$D$2,\"\",IF($D$2<(Tool!E91-Tool!$D$64),\"\",IF(Tool!D92<>\"\",IF(Tool!$D$64<>0,Tool!E91-Tool!$D$64,Tool!E91),\"\"))),\"\")","v":""},{"$f":"IF(C37=\"\",\"\",IF(B38=\"\",$D$2,IF((D36-$C$9)>=$D$2,\"\",IF(Tool!E91<>\"\",IF(AND($D$2>=(Tool!E92-Tool!$D$64),(Tool!E93-Tool!$D$64)>=(Tool!E92-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E92-Tool!$D$64,Tool!E92),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B37<>\"\",Tool!K92=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E74=\"TRUE\",IF(Tool!L92=\"Both Sides\",2,IF(Tool!L92=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E74=\"TRUE\",IF(AND(F74=1,Tool!M92=\"Both Sides\"),1,IF(AND(F74=2,Tool!M92=\"Both Sides\"),2,IF(AND(F74=2,Tool!M92=\"One Side\"),1,IF(AND(F74=1,Tool!M92=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G92=Tool!I92,Tool!H92=0),\"\",IF(AND(B74<>\"\",D74<>\"\"),IF(E74=\"TRUE\",D74-C74,\"\"),\"\"))","v":""},null,null,null,null,null,null,null,null,null,null,null,"DRAINAGE DESIGN"]
[null,{"$f":"IF(E44=30,30,\"\")","v":""},{"$f":"IF(B38<>\"\",IF(D37>=$D$2,\"\",IF($D$2<(Tool!E92-Tool!$D$64),\"\",IF(Tool!D93<>\"\",IF(Tool!$D$64<>0,Tool!E92-Tool!$D$64,Tool!E92),\"\"))),\"\")","v":""},{"$f":"IF(C38=\"\",\"\",IF(B39=\"\",$D$2,IF((D37-$C$9)>=$D$2,\"\",IF(Tool!E92<>\"\",IF(AND($D$2>=(Tool!E93-Tool!$D$64),(Tool!E94-Tool!$D$64)>=(Tool!E93-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E93-Tool!$D$64,Tool!E93),$D$2),\"\"))))","v":""},{"$f":"IF(AND(B38<>\"\",Tool!K93=Tool!$B$8),\"TRUE\",\"\")","v":""},{"$f":"IF(E75=\"TRUE\",IF(Tool!L93=\"Both Sides\",2,IF(Tool!L93=\"One Side\",1,\"\")),\"\")","v":""},{"$f":"IF(E75=\"TRUE\",IF(AND(F75=1,Tool!M93=\"Both Sides\"),1,IF(AND(F75=2,Tool!M93=\"Both Sides\"),2,IF(AND(F75=2,Tool!M93=\"One Side\"),1,IF(AND(F75=1,Tool!M93=\"One Side\"),1,\"\")))),\"\")","v":""},{"$f":"IF(AND(Tool!G93=Tool!I93,Tool!H93=0),\"\",IF(AND(B75<>\"\",D75<>\"\"),IF(E75=\"TRUE\",D75-C75,\"\"),\"\"))","v":""}]
[]
[null,null,null,"Urban/C&G Length:",{"$f":"SUM(H46:H75)","v":0}]
[null,null,null,"Curb & Gutter Length:",{"$f":"SUMPRODUCT(F46:F75,H46:H75)","v":0},"Avg. C&G Width:",{"$f":"IF(D2>0,(E78*2.5)/D2,0)","v":0}]
[null,null,null,"Urban Eff. Ditch Length:",{"$f":"SUM(H46:H75)*2-E78","v":0},"Avg. Sidewalk Width:",{"$f":"IF(D2>0,(SUMPRODUCT(G46:G75,H46:H75)*5)/D2,0)","v":0}]
[null,null,null,"Sidewalk Length:",{"$f":"SUMPRODUCT(G46:G75,H46:H75)","v":0}]

{"sheet":"Terrain","index":33,"n_rows":164,"n_cols":40,"rows_kept":164,"cut":false,"hidden":true,"merged":[[121,30,127,36],[94,17,94,18],[64,17,64,18],[65,26,65,30],[54,26,54,33],[34,17,34,18],[3,1,4,11],[3,17,4,24],[7,26,7,28],[16,26,16,27],[5,17,5,18],[22,26,22,27],[6,1,6,3],[45,1,45,3],[5,1,5,3],[85,1,85,3],[125,1,125,3],[124,1,124,3],[84,1,84,3],[44,1,44,3]]}
[]
[null,"Project Length:",{"$f":"IF(B9<>\"\",IF((Tool!$J$54-Tool!$J$52)>0,(Tool!$J$54-Tool!$J$52),0),0)","v":0}]
[]
[null,"Roadway Filters",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Median Filters",null,null,null,null,null,null,null,null,null,"Graded Solid Rock:",{"$f":"Tool!F35","v":"Low"},null,null,null,null,null,null,null,null,null,"6H:1V",6]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"5H:1V",5]
[null,"Flat Terrain",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Flat Terrain",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"4H:1V",4]
[null,"Segments:",null,null,{"$f":"Tool!$J$61","v":1},null,null,null,null,null,null,null,null,null,null,null,null,"Segments:",{"$f":"Tool!$J$96","v":1},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"3H:1V",3]
[null,"Segments","Begin (mi)","End (mi)","Terrain Type","Total Pavement Width (ft)","Outside Shldr Width (ft)","Existing Pavement Width","Widen to One Side or Both?","Grass Strip","Rural/Urban","Sidewalks","Slope Length","Slope Rate","Slope Area (ft-mi)","Guardrail Length","Length","Segments","Begin (mi)","End (mi)","Terrain Type","Inside Shldr. Width (ft)","Interior Width (ft)","Median Type","Length",null,"Overall Summary",null,null,null,null,null,null,null,null,null,null,null,"2H:1V",2]
[null,{"$f":"IF(AND(E7>=1,E7<=30),1,\"\")","v":1},{"$f":"IF(Tool!D64<>\"\",IF(B9<>\"\",IF(Tool!D64=0,Tool!D64,Tool!D64-Tool!D64),\"\"),\"\")","v":""},{"$f":"IF(C9=\"\",\"\",IF((Tool!E65-Tool!D64)<(Tool!E64-Tool!D64),C2,IF(B9<>\"\",IF(Tool!E64<>\"\",IF(AND(B10=\"\",Tool!E64-Tool!D64<$C$2),$C$2,IF(B9=1,IF($C$2<(Tool!E64-Tool!$D$64),$C$2,IF(Tool!D64<>0,(Tool!E64-Tool!D64),Tool!E64)),\"\")),\"\"),\"\")))","v":""},{"$f":"IF(C9=\"\",\"\",IF(B9<>\"\",IF(Tool!N64=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E9=\"Flat\",IF(Tool!I64>Tool!G64,0,IF(Tool!G64>0,Tool!G64+J9,\"\")),\"\"))","v":""},{"$f":"IF(E9=\"Flat\",IF(Tool!H64>0,Tool!H64,\"\"),\"\")","v":""},{"$f":"IF(E9=\"Flat\",IF(Tool!I64>Tool!G64,Tool!G64,IF(Tool!I64>=0,Tool!I64)),\"\")","v":""},{"$f":"IF(E9=\"Flat\",Tool!O64,\"\")","v":""},{"$f":"IF(AND(K9=\"Urban/C&G\",E9=\"Flat\",Tool!L64=\"Both Sides\",Tool!M64=\"Both Sides\"),Tool!$M$62*2,IF(AND(K9=\"Urban/C&G\",E9=\"Flat\",Tool!L64=\"Both Sides\",Tool!M64=\"One Side\"),Tool!$M$62,IF(AND(K9=\"Urban/C&G\",E9=\"Flat\",Tool!L64=\"One Side\",Tool!M64=\"Both Sides\"),Tool!$M$62,IF(AND(K9=\"Urban/C&G\",E9=\"Flat\",Tool!L64=\"One Side\",Tool!M64=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E9=\"Flat\",Tool!K64,\"\")","v":""},{"$f":"IF(E9<>\"\",Drainage!G46,\"\")","v":""},{"$f":"IF(AND(F9=H9,G9=\"\"),\"\",D9-C9)","v":""},{"$f":"IF(AND(F9=H9,G9=\"\"),\"\",VLOOKUP(Tool!P64,$AM$4:$AN$9,2,0))","v":""},{"$f":"IF(AND(F9=H9,G9=\"\"),\"\",M9*N9)","v":""},{"$f":"IF(AND(N9=4,I9=\"Both Sides\"),M9*0.2,IF(AND(N9=4,I9=\"One Side\"),M9*0.1,IF(AND(N9=3,I9=\"One Side\"),M9*0.3,IF(AND(N9=3,I9=\"Both Sides\"),M9*0.5,IF(AND(N9=2,I9=\"One Side\"),M9*0.5,IF(AND(N9=2,I9=\"Both Sides\"),M9,IF(AND(N9=1,I9=\"One Side\"),M9*0.75,IF(AND(N9=1,I9=\"Both Sides\"),M9,\"\"))))))))","v":""},{"$f":"IF(E9=\"Flat\",D9-C9,\"\")","v":""},{"$f":"IF(AND(S7>=1,S7<=20),1,\"\")","v":1},{"$f":"IF(Tool!D98<>\"\",IF(R9<>\"\",IF(Tool!D98=0,Tool!D98,Tool!D98-Tool!D98),\"\"),\"\")","v":""},{"$f":"IF(Tool!E98<>\"\",IF(R9=1,IF($C$2<(Tool!E98-Tool!$D$98),$C$2,IF(Tool!D98<>0,(Tool!E98-Tool!D98),Tool!E98)),\"\"),\"\")","v":""},{"$f":"IF(R9<>\"\",IF(Tool!H98=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U9=\"flat\",Tool!I98>0),Tool!I98,\"\")","v":""},{"$f":"IF(U9=\"Flat\",IF(Tool!J98>0,IF(Tool!F98=\"Barrier Wall\",3,IF(Tool!F98=\"Depressed Grass\",Tool!J98*0.5,Tool!J98)),\"\"),\"\")","v":""},{"$f":"IF(R9<>\"\",IF(U9=\"Flat\",Tool!F98,\"\"),\"\")","v":""},{"$f":"IF(U9=\"Flat\",T9-S9,\"\")","v":""},null,"Item #","Description","Quantity",null,null,null,null,null,null,null,null,null,"1H:1V",1]
[null,{"$f":"IF(AND(E7>=2,E7<=30),2,\"\")","v":""},{"$f":"IF(D9>=$C$2,\"\",IF($C$2<(Tool!E64-Tool!$D$64),\"\",IF(Tool!D65<>\"\",IF(Tool!$D$64<>0,Tool!E64-Tool!$D$64,Tool!E64),\"\")))","v":""},{"$f":"IF(C10=\"\",\"\",IF(B11=\"\",$C$2,IF((D9-$C$9)>=$C$2,\"\",IF(Tool!E64<>\"\",IF(AND($C$2>=(Tool!E65-Tool!$D$64),(Tool!E66-Tool!$D$64)>=(Tool!E65-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E65-Tool!$D$64,Tool!E65),$C$2),\"\"))))","v":""},{"$f":"IF(C10=\"\",\"\",IF(B10<>\"\",IF(Tool!N65=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E10=\"Flat\",IF(Tool!I65>Tool!G65,0,IF(Tool!G65>0,Tool!G65+J10,\"\")),\"\"))","v":""},{"$f":"IF(E10=\"Flat\",IF(Tool!H65>0,Tool!H65,\"\"),\"\")","v":""},{"$f":"IF(E10=\"Flat\",IF(Tool!I65>Tool!G65,Tool!G65,IF(Tool!I65>=0,Tool!I65)),\"\")","v":""},{"$f":"IF(E10=\"Flat\",Tool!O65,\"\")","v":""},{"$f":"IF(AND(K10=\"Urban/C&G\",E10=\"Flat\",Tool!L65=\"Both Sides\",Tool!M65=\"Both Sides\"),Tool!$M$62*2,IF(AND(K10=\"Urban/C&G\",E10=\"Flat\",Tool!L65=\"Both Sides\",Tool!M65=\"One Side\"),Tool!$M$62,IF(AND(K10=\"Urban/C&G\",E10=\"Flat\",Tool!L65=\"One Side\",Tool!M65=\"Both Sides\"),Tool!$M$62,IF(AND(K10=\"Urban/C&G\",E10=\"Flat\",Tool!L65=\"One Side\",Tool!M65=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E10=\"Flat\",Tool!K65,\"\")","v":""},{"$f":"IF(E10<>\"\",Drainage!G47,\"\")","v":""},{"$f":"IF(AND(F10=H10,G10=\"\"),\"\",D10-C10)","v":""},{"$f":"IF(AND(F10=H10,G10=\"\"),\"\",VLOOKUP(Tool!P65,$AM$4:$AN$9,2,0))","v":""},"",{"$f":"IF(AND(N10=4,I10=\"Both Sides\"),M10*0.2,IF(AND(N10=4,I10=\"One Side\"),M10*0.1,IF(AND(N10=3,I10=\"One Side\"),M10*0.3,IF(AND(N10=3,I10=\"Both Sides\"),M10*0.5,IF(AND(N10=2,I10=\"One Side\"),M10*0.5,IF(AND(N10=2,I10=\"Both Sides\"),M10,IF(AND(N10=1,I10=\"One Side\"),M10*0.75,IF(AND(N10=1,I10=\"Both Sides\"),M10,\"\"))))))))","v":""},{"$f":"IF(E10=\"Flat\",D10-C10,\"\")","v":""},{"$f":"IF(AND(S7>=2,S7<=20),2,\"\")","v":""},{"$f":"IF(R10<>\"\",IF(T9>=$C$2,\"\",IF($C$2<(Tool!E98-Tool!$D$98),\"\",IF(Tool!D99<>\"\",IF(Tool!$D$98<>0,Tool!E98-Tool!$D$98,Tool!E98),\"\"))),\"\")","v":""},{"$f":"IF(S10=\"\",\"\",IF(R10=\"\",\"\",IF(Tool!E98<>\"\",IF(AND($C$2>=(Tool!E99-Tool!$D$98),(Tool!E100-Tool!$D$98)>=(Tool!E99-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E99-Tool!$D$98,Tool!E99),$C$2),\"\")))","v":""},{"$f":"IF(R10<>\"\",IF(Tool!H99=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U10=\"flat\",Tool!I99>0),Tool!I99,\"\")","v":""},{"$f":"IF(U10=\"Flat\",IF(Tool!J99>0,IF(Tool!F99=\"Barrier Wall\",3,IF(Tool!F99=\"Depressed Grass\",Tool!J99*0.5,Tool!J99)),\"\"),\"\")","v":""},{"$f":"IF(R10<>\"\",IF(U10=\"Flat\",Tool!F99,\"\"),\"\")","v":""},{"$f":"IF(U10=\"Flat\",T10-S10,\"\")","v":""},null,"203-01","R&D Excav. (UnC)",{"$f":"IF(AC4=\"None\",(SUM(AH25:AH28)+AI45+AE72+Roadway!U104)*0.8,IF(AC4=\"Low\",(SUM(AH25:AH28)+AI45+AE72+Roadway!U104)*0.8,IF(AC4=\"Moderate\",(SUM(AH25:AH28)+AI45+AE72+Roadway!U104)*0.8,IF(AC4=\"High\",(SUM(AH25:AH28)+AI45+AE72+Roadway!U104)*0.8)))*1.3)","v":0}]
[null,{"$f":"IF(AND(E7>=3,E7<=30),3,\"\")","v":""},{"$f":"IF(D10>=$C$2,\"\",IF($C$2<(Tool!E65-Tool!$D$64),\"\",IF(Tool!D66<>\"\",IF(Tool!$D$64<>0,Tool!E65-Tool!$D$64,Tool!E65),\"\")))","v":""},{"$f":"IF(C11=\"\",\"\",IF(B12=\"\",$C$2,IF((D10-$C$9)>=$C$2,\"\",IF(Tool!E65<>\"\",IF(AND($C$2>=(Tool!E66-Tool!$D$64),(Tool!E67-Tool!$D$64)>=(Tool!E66-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E66-Tool!$D$64,Tool!E66),$C$2),\"\"))))","v":""},{"$f":"IF(C11=\"\",\"\",IF(B11<>\"\",IF(Tool!N66=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E11=\"Flat\",IF(Tool!I66>Tool!G66,0,IF(Tool!G66>0,Tool!G66+J11,\"\")),\"\"))","v":""},{"$f":"IF(E11=\"Flat\",IF(Tool!H66>0,Tool!H66,\"\"),\"\")","v":""},{"$f":"IF(E11=\"Flat\",IF(Tool!I66>Tool!G66,Tool!G66,IF(Tool!I66>=0,Tool!I66)),\"\")","v":""},{"$f":"IF(E11=\"Flat\",Tool!O66,\"\")","v":""},{"$f":"IF(AND(K11=\"Urban/C&G\",E11=\"Flat\",Tool!L66=\"Both Sides\",Tool!M66=\"Both Sides\"),Tool!$M$62*2,IF(AND(K11=\"Urban/C&G\",E11=\"Flat\",Tool!L66=\"Both Sides\",Tool!M66=\"One Side\"),Tool!$M$62,IF(AND(K11=\"Urban/C&G\",E11=\"Flat\",Tool!L66=\"One Side\",Tool!M66=\"Both Sides\"),Tool!$M$62,IF(AND(K11=\"Urban/C&G\",E11=\"Flat\",Tool!L66=\"One Side\",Tool!M66=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E11=\"Flat\",Tool!K66,\"\")","v":""},{"$f":"IF(E11<>\"\",Drainage!G48,\"\")","v":""},"",{"$f":"IF(AND(F11=H11,G11=\"\"),\"\",VLOOKUP(Tool!P66,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7>=3,S7<=20),3,\"\")","v":""},{"$f":"IF(R11<>\"\",IF(T10>=$C$2,\"\",IF($C$2<(Tool!E99-Tool!$D$98),\"\",IF(Tool!D100<>\"\",IF(Tool!$D$98<>0,Tool!E99-Tool!$D$98,Tool!E99),\"\"))),\"\")","v":""},{"$f":"IF(S11=\"\",\"\",IF(R11=\"\",\"\",IF(Tool!E99<>\"\",IF(AND($C$2>=(Tool!E100-Tool!$D$98),(Tool!E101-Tool!$D$98)>=(Tool!E100-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E100-Tool!$D$98,Tool!E100),$C$2),\"\")))","v":""},{"$f":"IF(R11<>\"\",IF(Tool!H100=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U11=\"flat\",Tool!I100>0),Tool!I100,\"\")","v":""},{"$f":"IF(U11=\"Flat\",IF(Tool!J100>0,IF(Tool!F100=\"Barrier Wall\",3,IF(Tool!F100=\"Depressed Grass\",Tool!J100*0.5,Tool!J100)),\"\"),\"\")","v":""},{"$f":"IF(R11<>\"\",IF(U11=\"Flat\",Tool!F100,\"\"),\"\")","v":""},"",null,"203-03","Borrow Excav. (UnC)",{"$f":"IF(AC4=\"None\",(SUM(AH25:AH28)+AI45+AE72+Roadway!U104)*0.5,IF(AC4=\"Low\",(SUM(AH25:AH28)+AI45+AE72+Roadway!U104)*0.4,IF(AC4=\"Moderate\",(SUM(AH25:AH28)+AI45+AE72+Roadway!U104)*0.25,IF(AC4=\"High\",(SUM(AH25:AH28)+AI45+AE72+Roadway!U104)*0.1))))*1.3","v":0},{"$f":"SUM(AC11+AC12)","v":0},"GSR Tons/CY =",1.7636000000000001]
[null,{"$f":"IF(AND(E7>=4,E7<=30),4,\"\")","v":""},{"$f":"IF(D11>=$C$2,\"\",IF($C$2<(Tool!E66-Tool!$D$64),\"\",IF(Tool!D67<>\"\",IF(Tool!$D$64<>0,Tool!E66-Tool!$D$64,Tool!E66),\"\")))","v":""},{"$f":"IF(C12=\"\",\"\",IF(B13=\"\",$C$2,IF((D11-$C$9)>=$C$2,\"\",IF(Tool!E66<>\"\",IF(AND($C$2>=(Tool!E67-Tool!$D$64),(Tool!E68-Tool!$D$64)>=(Tool!E67-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E67-Tool!$D$64,Tool!E67),$C$2),\"\"))))","v":""},{"$f":"IF(C12=\"\",\"\",IF(B12<>\"\",IF(Tool!N67=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E12=\"Flat\",IF(Tool!I67>Tool!G67,0,IF(Tool!G67>0,Tool!G67+J12,\"\")),\"\"))","v":""},{"$f":"IF(E12=\"Flat\",IF(Tool!H67>0,Tool!H67,\"\"),\"\")","v":""},{"$f":"IF(E12=\"Flat\",IF(Tool!I67>Tool!G67,Tool!G67,IF(Tool!I67>=0,Tool!I67)),\"\")","v":""},{"$f":"IF(E12=\"Flat\",Tool!O67,\"\")","v":""},{"$f":"IF(AND(K12=\"Urban/C&G\",E12=\"Flat\",Tool!L67=\"Both Sides\",Tool!M67=\"Both Sides\"),Tool!$M$62*2,IF(AND(K12=\"Urban/C&G\",E12=\"Flat\",Tool!L67=\"Both Sides\",Tool!M67=\"One Side\"),Tool!$M$62,IF(AND(K12=\"Urban/C&G\",E12=\"Flat\",Tool!L67=\"One Side\",Tool!M67=\"Both Sides\"),Tool!$M$62,IF(AND(K12=\"Urban/C&G\",E12=\"Flat\",Tool!L67=\"One Side\",Tool!M67=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E12=\"Flat\",Tool!K67,\"\")","v":""},{"$f":"IF(E12<>\"\",Drainage!G49,\"\")","v":""},"",{"$f":"IF(AND(F12=H12,G12=\"\"),\"\",VLOOKUP(Tool!P67,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7>=4,S7<=20),4,\"\")","v":""},{"$f":"IF(R12<>\"\",IF(T11>=$C$2,\"\",IF($C$2<(Tool!E100-Tool!$D$98),\"\",IF(Tool!D101<>\"\",IF(Tool!$D$98<>0,Tool!E100-Tool!$D$98,Tool!E100),\"\"))),\"\")","v":""},{"$f":"IF(S12=\"\",\"\",IF(R12=\"\",\"\",IF(Tool!E100<>\"\",IF(AND($C$2>=(Tool!E101-Tool!$D$98),(Tool!E102-Tool!$D$98)>=(Tool!E101-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E101-Tool!$D$98,Tool!E101),$C$2),\"\")))","v":""},{"$f":"IF(R12<>\"\",IF(Tool!H101=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U12=\"flat\",Tool!I101>0),Tool!I101,\"\")","v":""},{"$f":"IF(U12=\"Flat\",IF(Tool!J101>0,IF(Tool!F101=\"Barrier Wall\",3,IF(Tool!F101=\"Depressed Grass\",Tool!J101*0.5,Tool!J101)),\"\"),\"\")","v":""},{"$f":"IF(R12<>\"\",IF(U12=\"Flat\",Tool!F101,\"\"),\"\")","v":""},"",null,"203-02.02","Borrow Excav (GSR)",{"$f":"IF(AC4=\"None\",0,IF(AC4=\"Low\",(SUM(AH25:AH28)+AI45+AE72+Roadway!U104)*0.1,IF(AC4=\"Moderate\",(SUM(AH25:AH28)+AI45+AE72+Roadway!U104)*0.25,IF(AC4=\"High\",(SUM(AH25:AH28)+AI45+AE72+Roadway!U104)*0.6))))*1.3","v":0}]
[null,{"$f":"IF(AND(E7>=5,E7<=30),5,\"\")","v":""},{"$f":"IF(D12>=$C$2,\"\",IF($C$2<(Tool!E67-Tool!$D$64),\"\",IF(Tool!D68<>\"\",IF(Tool!$D$64<>0,Tool!E67-Tool!$D$64,Tool!E67),\"\")))","v":""},{"$f":"IF(C13=\"\",\"\",IF(B14=\"\",$C$2,IF((D12-$C$9)>=$C$2,\"\",IF(Tool!E67<>\"\",IF(AND($C$2>=(Tool!E68-Tool!$D$64),(Tool!E69-Tool!$D$64)>=(Tool!E68-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E68-Tool!$D$64,Tool!E68),$C$2),\"\"))))","v":""},{"$f":"IF(C13=\"\",\"\",IF(B13<>\"\",IF(Tool!N68=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E13=\"Flat\",IF(Tool!I68>Tool!G68,0,IF(Tool!G68>0,Tool!G68+J13,\"\")),\"\"))","v":""},{"$f":"IF(E13=\"Flat\",IF(Tool!H68>0,Tool!H68,\"\"),\"\")","v":""},{"$f":"IF(E13=\"Flat\",IF(Tool!I68>Tool!G68,Tool!G68,IF(Tool!I68>=0,Tool!I68)),\"\")","v":""},{"$f":"IF(E13=\"Flat\",Tool!O68,\"\")","v":""},{"$f":"IF(AND(K13=\"Urban/C&G\",E13=\"Flat\",Tool!L68=\"Both Sides\",Tool!M68=\"Both Sides\"),Tool!$M$62*2,IF(AND(K13=\"Urban/C&G\",E13=\"Flat\",Tool!L68=\"Both Sides\",Tool!M68=\"One Side\"),Tool!$M$62,IF(AND(K13=\"Urban/C&G\",E13=\"Flat\",Tool!L68=\"One Side\",Tool!M68=\"Both Sides\"),Tool!$M$62,IF(AND(K13=\"Urban/C&G\",E13=\"Flat\",Tool!L68=\"One Side\",Tool!M68=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E13=\"Flat\",Tool!K68,\"\")","v":""},{"$f":"IF(E13<>\"\",Drainage!G50,\"\")","v":""},"",{"$f":"IF(AND(F13=H13,G13=\"\"),\"\",VLOOKUP(Tool!P68,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7>=5,S7<=20),5,\"\")","v":""},{"$f":"IF(R13<>\"\",IF(T12>=$C$2,\"\",IF($C$2<(Tool!E101-Tool!$D$98),\"\",IF(Tool!D102<>\"\",IF(Tool!$D$98<>0,Tool!E101-Tool!$D$98,Tool!E101),\"\"))),\"\")","v":""},{"$f":"IF(S13=\"\",\"\",IF(R13=\"\",\"\",IF(Tool!E101<>\"\",IF(AND($C$2>=(Tool!E102-Tool!$D$98),(Tool!E103-Tool!$D$98)>=(Tool!E102-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E102-Tool!$D$98,Tool!E102),$C$2),\"\")))","v":""},{"$f":"IF(R13<>\"\",IF(Tool!H102=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U13=\"flat\",Tool!I102>0),Tool!I102,\"\")","v":""},{"$f":"IF(U13=\"Flat\",IF(Tool!J102>0,IF(Tool!F102=\"Barrier Wall\",3,IF(Tool!F102=\"Depressed Grass\",Tool!J102*0.5,Tool!J102)),\"\"),\"\")","v":""},{"$f":"IF(R13<>\"\",IF(U13=\"Flat\",Tool!F102,\"\"),\"\")","v":""},"",null,"705-02.02","Single Guardrail (Type 2)",{"$f":"SUM(P40+P79+P119+P159)*5280","v":0}]
[null,{"$f":"IF(AND(E7>=6,E7<=30),6,\"\")","v":""},{"$f":"IF(D13>=$C$2,\"\",IF($C$2<(Tool!E68-Tool!$D$64),\"\",IF(Tool!D69<>\"\",IF(Tool!$D$64<>0,Tool!E68-Tool!$D$64,Tool!E68),\"\")))","v":""},{"$f":"IF(C14=\"\",\"\",IF(B15=\"\",$C$2,IF((D13-$C$9)>=$C$2,\"\",IF(Tool!E68<>\"\",IF(AND($C$2>=(Tool!E69-Tool!$D$64),(Tool!E70-Tool!$D$64)>=(Tool!E69-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E69-Tool!$D$64,Tool!E69),$C$2),\"\"))))","v":""},{"$f":"IF(C14=\"\",\"\",IF(B14<>\"\",IF(Tool!N69=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E14=\"Flat\",IF(Tool!I69>Tool!G69,0,IF(Tool!G69>0,Tool!G69+J14,\"\")),\"\"))","v":""},{"$f":"IF(E14=\"Flat\",IF(Tool!H69>0,Tool!H69,\"\"),\"\")","v":""},{"$f":"IF(E14=\"Flat\",IF(Tool!I69>Tool!G69,Tool!G69,IF(Tool!I69>=0,Tool!I69)),\"\")","v":""},{"$f":"IF(E14=\"Flat\",Tool!O69,\"\")","v":""},{"$f":"IF(AND(K14=\"Urban/C&G\",E14=\"Flat\",Tool!L69=\"Both Sides\",Tool!M69=\"Both Sides\"),Tool!$M$62*2,IF(AND(K14=\"Urban/C&G\",E14=\"Flat\",Tool!L69=\"Both Sides\",Tool!M69=\"One Side\"),Tool!$M$62,IF(AND(K14=\"Urban/C&G\",E14=\"Flat\",Tool!L69=\"One Side\",Tool!M69=\"Both Sides\"),Tool!$M$62,IF(AND(K14=\"Urban/C&G\",E14=\"Flat\",Tool!L69=\"One Side\",Tool!M69=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E14=\"Flat\",Tool!K69,\"\")","v":""},{"$f":"IF(E14<>\"\",Drainage!G51,\"\")","v":""},"",{"$f":"IF(AND(F14=H14,G14=\"\"),\"\",VLOOKUP(Tool!P69,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7>=6,S7<=20),6,\"\")","v":""},{"$f":"IF(R14<>\"\",IF(T13>=$C$2,\"\",IF($C$2<(Tool!E102-Tool!$D$98),\"\",IF(Tool!D103<>\"\",IF(Tool!$D$98<>0,Tool!E102-Tool!$D$98,Tool!E102),\"\"))),\"\")","v":""},{"$f":"IF(S14=\"\",\"\",IF(R14=\"\",\"\",IF(Tool!E102<>\"\",IF(AND($C$2>=(Tool!E103-Tool!$D$98),(Tool!E104-Tool!$D$98)>=(Tool!E103-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E103-Tool!$D$98,Tool!E103),$C$2),\"\")))","v":""},{"$f":"IF(R14<>\"\",IF(Tool!H103=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U14=\"flat\",Tool!I103>0),Tool!I103,\"\")","v":""},{"$f":"IF(U14=\"Flat\",IF(Tool!J103>0,IF(Tool!F103=\"Barrier Wall\",3,IF(Tool!F103=\"Depressed Grass\",Tool!J103*0.5,Tool!J103)),\"\"),\"\")","v":""},{"$f":"IF(R14<>\"\",IF(U14=\"Flat\",Tool!F103,\"\"),\"\")","v":""},"",null,"705-04.07","Type 38",{"$f":"MROUND(AC13/150,1)","v":0}]
[null,{"$f":"IF(AND(E7>=7,E7<=30),7,\"\")","v":""},{"$f":"IF(D14>=$C$2,\"\",IF($C$2<(Tool!E69-Tool!$D$64),\"\",IF(Tool!D70<>\"\",IF(Tool!$D$64<>0,Tool!E69-Tool!$D$64,Tool!E69),\"\")))","v":""},{"$f":"IF(C15=\"\",\"\",IF(B16=\"\",$C$2,IF((D14-$C$9)>=$C$2,\"\",IF(Tool!E69<>\"\",IF(AND($C$2>=(Tool!E70-Tool!$D$64),(Tool!E71-Tool!$D$64)>=(Tool!E70-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E70-Tool!$D$64,Tool!E70),$C$2),\"\"))))","v":""},{"$f":"IF(C15=\"\",\"\",IF(B15<>\"\",IF(Tool!N70=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E15=\"Flat\",IF(Tool!I70>Tool!G70,0,IF(Tool!G70>0,Tool!G70+J15,\"\")),\"\"))","v":""},{"$f":"IF(E15=\"Flat\",IF(Tool!H70>0,Tool!H70,\"\"),\"\")","v":""},{"$f":"IF(E15=\"Flat\",IF(Tool!I70>Tool!G70,Tool!G70,IF(Tool!I70>=0,Tool!I70)),\"\")","v":""},{"$f":"IF(E15=\"Flat\",Tool!O70,\"\")","v":""},{"$f":"IF(AND(K15=\"Urban/C&G\",E15=\"Flat\",Tool!L70=\"Both Sides\",Tool!M70=\"Both Sides\"),Tool!$M$62*2,IF(AND(K15=\"Urban/C&G\",E15=\"Flat\",Tool!L70=\"Both Sides\",Tool!M70=\"One Side\"),Tool!$M$62,IF(AND(K15=\"Urban/C&G\",E15=\"Flat\",Tool!L70=\"One Side\",Tool!M70=\"Both Sides\"),Tool!$M$62,IF(AND(K15=\"Urban/C&G\",E15=\"Flat\",Tool!L70=\"One Side\",Tool!M70=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E15=\"Flat\",Tool!K70,\"\")","v":""},{"$f":"IF(E15<>\"\",Drainage!G52,\"\")","v":""},"",{"$f":"IF(AND(F15=H15,G15=\"\"),\"\",VLOOKUP(Tool!P70,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7>=7,S7<=20),7,\"\")","v":""},{"$f":"IF(R15<>\"\",IF(T14>=$C$2,\"\",IF($C$2<(Tool!E103-Tool!$D$98),\"\",IF(Tool!D104<>\"\",IF(Tool!$D$98<>0,Tool!E103-Tool!$D$98,Tool!E103),\"\"))),\"\")","v":""},{"$f":"IF(S15=\"\",\"\",IF(R15=\"\",\"\",IF(Tool!E103<>\"\",IF(AND($C$2>=(Tool!E104-Tool!$D$98),(Tool!E105-Tool!$D$98)>=(Tool!E104-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E104-Tool!$D$98,Tool!E104),$C$2),\"\")))","v":""},{"$f":"IF(R15<>\"\",IF(Tool!H104=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U15=\"flat\",Tool!I104>0),Tool!I104,\"\")","v":""},{"$f":"IF(U15=\"Flat\",IF(Tool!J104>0,IF(Tool!F104=\"Barrier Wall\",3,IF(Tool!F104=\"Depressed Grass\",Tool!J104*0.5,Tool!J104)),\"\"),\"\")","v":""},{"$f":"IF(R15<>\"\",IF(U15=\"Flat\",Tool!F104,\"\"),\"\")","v":""},"",null,"705-04.09","Earth Pad For Type 38"]
[null,{"$f":"IF(AND(E7>=8,E7<=30),8,\"\")","v":""},{"$f":"IF(D15>=$C$2,\"\",IF($C$2<(Tool!E70-Tool!$D$64),\"\",IF(Tool!D71<>\"\",IF(Tool!$D$64<>0,Tool!E70-Tool!$D$64,Tool!E70),\"\")))","v":""},{"$f":"IF(C16=\"\",\"\",IF(B17=\"\",$C$2,IF((D15-$C$9)>=$C$2,\"\",IF(Tool!E70<>\"\",IF(AND($C$2>=(Tool!E71-Tool!$D$64),(Tool!E72-Tool!$D$64)>=(Tool!E71-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E71-Tool!$D$64,Tool!E71),$C$2),\"\"))))","v":""},{"$f":"IF(C16=\"\",\"\",IF(B16<>\"\",IF(Tool!N71=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E16=\"Flat\",IF(Tool!I71>Tool!G71,0,IF(Tool!G71>0,Tool!G71+J16,\"\")),\"\"))","v":""},{"$f":"IF(E16=\"Flat\",IF(Tool!H71>0,Tool!H71,\"\"),\"\")","v":""},{"$f":"IF(E16=\"Flat\",IF(Tool!I71>Tool!G71,Tool!G71,IF(Tool!I71>=0,Tool!I71)),\"\")","v":""},{"$f":"IF(E16=\"Flat\",Tool!O71,\"\")","v":""},{"$f":"IF(AND(K16=\"Urban/C&G\",E16=\"Flat\",Tool!L71=\"Both Sides\",Tool!M71=\"Both Sides\"),Tool!$M$62*2,IF(AND(K16=\"Urban/C&G\",E16=\"Flat\",Tool!L71=\"Both Sides\",Tool!M71=\"One Side\"),Tool!$M$62,IF(AND(K16=\"Urban/C&G\",E16=\"Flat\",Tool!L71=\"One Side\",Tool!M71=\"Both Sides\"),Tool!$M$62,IF(AND(K16=\"Urban/C&G\",E16=\"Flat\",Tool!L71=\"One Side\",Tool!M71=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E16=\"Flat\",Tool!K71,\"\")","v":""},{"$f":"IF(E16<>\"\",Drainage!G53,\"\")","v":""},"",{"$f":"IF(AND(F16=H16,G16=\"\"),\"\",VLOOKUP(Tool!P71,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7>=8,S7<=20),8,\"\")","v":""},{"$f":"IF(R16<>\"\",IF(T15>=$C$2,\"\",IF($C$2<(Tool!E104-Tool!$D$98),\"\",IF(Tool!D105<>\"\",IF(Tool!$D$98<>0,Tool!E104-Tool!$D$98,Tool!E104),\"\"))),\"\")","v":""},{"$f":"IF(S16=\"\",\"\",IF(R16=\"\",\"\",IF(Tool!E104<>\"\",IF(AND($C$2>=(Tool!E105-Tool!$D$98),(Tool!E106-Tool!$D$98)>=(Tool!E105-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E105-Tool!$D$98,Tool!E105),$C$2),\"\")))","v":""},{"$f":"IF(R16<>\"\",IF(Tool!H105=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U16=\"flat\",Tool!I105>0),Tool!I105,\"\")","v":""},{"$f":"IF(U16=\"Flat\",IF(Tool!J105>0,IF(Tool!F105=\"Barrier Wall\",3,IF(Tool!F105=\"Depressed Grass\",Tool!J105*0.5,Tool!J105)),\"\"),\"\")","v":""},{"$f":"IF(R16<>\"\",IF(U16=\"Flat\",Tool!F105,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E7>=9,F7<=20),9,\"\")","v":""},{"$f":"IF(D16>=$C$2,\"\",IF($C$2<(Tool!E71-Tool!$D$64),\"\",IF(Tool!D72<>\"\",IF(Tool!$D$64<>0,Tool!E71-Tool!$D$64,Tool!E71),\"\")))","v":""},{"$f":"IF(C17=\"\",\"\",IF(B18=\"\",$C$2,IF((D16-$C$9)>=$C$2,\"\",IF(Tool!E71<>\"\",IF(AND($C$2>=(Tool!E72-Tool!$D$64),(Tool!E73-Tool!$D$64)>=(Tool!E72-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E72-Tool!$D$64,Tool!E72),$C$2),\"\"))))","v":""},{"$f":"IF(C17=\"\",\"\",IF(B17<>\"\",IF(Tool!N72=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E17=\"Flat\",IF(Tool!I72>Tool!G72,0,IF(Tool!G72>0,Tool!G72+J17,\"\")),\"\"))","v":""},{"$f":"IF(E17=\"Flat\",IF(Tool!H72>0,Tool!H72,\"\"),\"\")","v":""},{"$f":"IF(E17=\"Flat\",IF(Tool!I72>Tool!G72,Tool!G72,IF(Tool!I72>=0,Tool!I72)),\"\")","v":""},{"$f":"IF(E17=\"Flat\",Tool!O72,\"\")","v":""},{"$f":"IF(AND(K17=\"Urban/C&G\",E17=\"Flat\",Tool!L72=\"Both Sides\",Tool!M72=\"Both Sides\"),Tool!$M$62*2,IF(AND(K17=\"Urban/C&G\",E17=\"Flat\",Tool!L72=\"Both Sides\",Tool!M72=\"One Side\"),Tool!$M$62,IF(AND(K17=\"Urban/C&G\",E17=\"Flat\",Tool!L72=\"One Side\",Tool!M72=\"Both Sides\"),Tool!$M$62,IF(AND(K17=\"Urban/C&G\",E17=\"Flat\",Tool!L72=\"One Side\",Tool!M72=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E17=\"Flat\",Tool!K72,\"\")","v":""},{"$f":"IF(E17<>\"\",Drainage!G54,\"\")","v":""},"",{"$f":"IF(AND(F17=H17,G17=\"\"),\"\",VLOOKUP(Tool!P72,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7>=9,S7<=20),9,\"\")","v":""},{"$f":"IF(R17<>\"\",IF(T16>=$C$2,\"\",IF($C$2<(Tool!E105-Tool!$D$98),\"\",IF(Tool!D106<>\"\",IF(Tool!$D$98<>0,Tool!E105-Tool!$D$98,Tool!E105),\"\"))),\"\")","v":""},{"$f":"IF(S17=\"\",\"\",IF(R17=\"\",\"\",IF(Tool!E105<>\"\",IF(AND($C$2>=(Tool!E106-Tool!$D$98),(Tool!E107-Tool!$D$98)>=(Tool!E106-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E106-Tool!$D$98,Tool!E106),$C$2),\"\")))","v":""},{"$f":"IF(R17<>\"\",IF(Tool!H106=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U17=\"flat\",Tool!I106>0),Tool!I106,\"\")","v":""},{"$f":"IF(U17=\"Flat\",IF(Tool!J106>0,IF(Tool!F106=\"Barrier Wall\",3,IF(Tool!F106=\"Depressed Grass\",Tool!J106*0.5,Tool!J106)),\"\"),\"\")","v":""},{"$f":"IF(R17<>\"\",IF(U17=\"Flat\",Tool!F106,\"\"),\"\")","v":""},"",null,"Facility Properties"]
[null,{"$f":"IF(AND(E7>=10,E7<=30),10,\"\")","v":""},{"$f":"IF(D17>=$C$2,\"\",IF($C$2<(Tool!E72-Tool!$D$64),\"\",IF(Tool!D73<>\"\",IF(Tool!$D$64<>0,Tool!E72-Tool!$D$64,Tool!E72),\"\")))","v":""},{"$f":"IF(C18=\"\",\"\",IF(B19=\"\",$C$2,IF((D17-$C$9)>=$C$2,\"\",IF(Tool!E72<>\"\",IF(AND($C$2>=(Tool!E73-Tool!$D$64),(Tool!E74-Tool!$D$64)>=(Tool!E73-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E73-Tool!$D$64,Tool!E73),$C$2),\"\"))))","v":""},{"$f":"IF(C18=\"\",\"\",IF(B18<>\"\",IF(Tool!N73=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E18=\"Flat\",IF(Tool!I73>Tool!G73,0,IF(Tool!G73>0,Tool!G73+J18,\"\")),\"\"))","v":""},{"$f":"IF(E18=\"Flat\",IF(Tool!H73>0,Tool!H73,\"\"),\"\")","v":""},{"$f":"IF(E18=\"Flat\",IF(Tool!I73>Tool!G73,Tool!G73,IF(Tool!I73>=0,Tool!I73)),\"\")","v":""},{"$f":"IF(E18=\"Flat\",Tool!O73,\"\")","v":""},{"$f":"IF(AND(K18=\"Urban/C&G\",E18=\"Flat\",Tool!L73=\"Both Sides\",Tool!M73=\"Both Sides\"),Tool!$M$62*2,IF(AND(K18=\"Urban/C&G\",E18=\"Flat\",Tool!L73=\"Both Sides\",Tool!M73=\"One Side\"),Tool!$M$62,IF(AND(K18=\"Urban/C&G\",E18=\"Flat\",Tool!L73=\"One Side\",Tool!M73=\"Both Sides\"),Tool!$M$62,IF(AND(K18=\"Urban/C&G\",E18=\"Flat\",Tool!L73=\"One Side\",Tool!M73=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E18=\"Flat\",Tool!K73,\"\")","v":""},{"$f":"IF(E18<>\"\",Drainage!G55,\"\")","v":""},"",{"$f":"IF(AND(F18=H18,G18=\"\"),\"\",VLOOKUP(Tool!P73,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7>=10,S7<=20),10,\"\")","v":""},{"$f":"IF(R18<>\"\",IF(T17>=$C$2,\"\",IF($C$2<(Tool!E106-Tool!$D$98),\"\",IF(Tool!D107<>\"\",IF(Tool!$D$98<>0,Tool!E106-Tool!$D$98,Tool!E106),\"\"))),\"\")","v":""},{"$f":"IF(S18=\"\",\"\",IF(R18=\"\",\"\",IF(Tool!E106<>\"\",IF(AND($C$2>=(Tool!E107-Tool!$D$98),(Tool!E108-Tool!$D$98)>=(Tool!E107-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E107-Tool!$D$98,Tool!E107),$C$2),\"\")))","v":""},{"$f":"IF(R18<>\"\",IF(Tool!H107=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U18=\"flat\",Tool!I107>0),Tool!I107,\"\")","v":""},{"$f":"IF(U18=\"Flat\",IF(Tool!J107>0,IF(Tool!F107=\"Barrier Wall\",3,IF(Tool!F107=\"Depressed Grass\",Tool!J107*0.5,Tool!J107)),\"\"),\"\")","v":""},{"$f":"IF(R18<>\"\",IF(U18=\"Flat\",Tool!F107,\"\"),\"\")","v":""},"",null,"Length:",{"$f":"C2","v":0}]
[null,{"$f":"IF(AND(E7>=11,E7<=30),11,\"\")","v":""},{"$f":"IF(D18>=$C$2,\"\",IF($C$2<(Tool!E73-Tool!$D$64),\"\",IF(Tool!D74<>\"\",IF(Tool!$D$64<>0,Tool!E73-Tool!$D$64,Tool!E73),\"\")))","v":""},{"$f":"IF(C19=\"\",\"\",IF(B20=\"\",$C$2,IF((D18-$C$9)>=$C$2,\"\",IF(Tool!E73<>\"\",IF(AND($C$2>=(Tool!E74-Tool!$D$64),(Tool!E75-Tool!$D$64)>=(Tool!E74-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E74-Tool!$D$64,Tool!E74),$C$2),\"\"))))","v":""},{"$f":"IF(C19=\"\",\"\",IF(B19<>\"\",IF(Tool!N74=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E19=\"Flat\",IF(Tool!I74>Tool!G74,0,IF(Tool!G74>0,Tool!G74+J19,\"\")),\"\"))","v":""},{"$f":"IF(E19=\"Flat\",IF(Tool!H74>0,Tool!H74,\"\"),\"\")","v":""},{"$f":"IF(E19=\"Flat\",IF(Tool!I74>Tool!G74,Tool!G74,IF(Tool!I74>=0,Tool!I74)),\"\")","v":""},{"$f":"IF(E19=\"Flat\",Tool!O74,\"\")","v":""},{"$f":"IF(AND(K19=\"Urban/C&G\",E19=\"Flat\",Tool!L74=\"Both Sides\",Tool!M74=\"Both Sides\"),Tool!$M$62*2,IF(AND(K19=\"Urban/C&G\",E19=\"Flat\",Tool!L74=\"Both Sides\",Tool!M74=\"One Side\"),Tool!$M$62,IF(AND(K19=\"Urban/C&G\",E19=\"Flat\",Tool!L74=\"One Side\",Tool!M74=\"Both Sides\"),Tool!$M$62,IF(AND(K19=\"Urban/C&G\",E19=\"Flat\",Tool!L74=\"One Side\",Tool!M74=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E19=\"Flat\",Tool!K74,\"\")","v":""},{"$f":"IF(E19<>\"\",Drainage!G56,\"\")","v":""},"",{"$f":"IF(AND(F19=H19,G19=\"\"),\"\",VLOOKUP(Tool!P74,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7>=11,S7<=20),11,\"\")","v":""},{"$f":"IF(R19<>\"\",IF(T18>=$C$2,\"\",IF($C$2<(Tool!E107-Tool!$D$98),\"\",IF(Tool!D108<>\"\",IF(Tool!$D$98<>0,Tool!E107-Tool!$D$98,Tool!E107),\"\"))),\"\")","v":""},{"$f":"IF(S19=\"\",\"\",IF(R19=\"\",\"\",IF(Tool!E107<>\"\",IF(AND($C$2>=(Tool!E108-Tool!$D$98),(Tool!E109-Tool!$D$98)>=(Tool!E108-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E108-Tool!$D$98,Tool!E108),$C$2),\"\")))","v":""},{"$f":"IF(R19<>\"\",IF(Tool!H108=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U19=\"flat\",Tool!I108>0),Tool!I108,\"\")","v":""},{"$f":"IF(U19=\"Flat\",IF(Tool!J108>0,IF(Tool!F108=\"Barrier Wall\",3,IF(Tool!F108=\"Depressed Grass\",Tool!J108*0.5,Tool!J108)),\"\"),\"\")","v":""},{"$f":"IF(R19<>\"\",IF(U19=\"Flat\",Tool!F108,\"\"),\"\")","v":""},"",null,"Avg. Prop. Rd Width:",{"$f":"Roadway!R41","v":0}]
[null,{"$f":"IF(AND(E7>=12,F7<=30),12,\"\")","v":""},{"$f":"IF(D19>=$C$2,\"\",IF($C$2<(Tool!E74-Tool!$D$64),\"\",IF(Tool!D75<>\"\",IF(Tool!$D$64<>0,Tool!E74-Tool!$D$64,Tool!E74),\"\")))","v":""},{"$f":"IF(C20=\"\",\"\",IF(B21=\"\",$C$2,IF((D19-$C$9)>=$C$2,\"\",IF(Tool!E74<>\"\",IF(AND($C$2>=(Tool!E75-Tool!$D$64),(Tool!E76-Tool!$D$64)>=(Tool!E75-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E75-Tool!$D$64,Tool!E75),$C$2),\"\"))))","v":""},{"$f":"IF(C20=\"\",\"\",IF(B20<>\"\",IF(Tool!N75=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E20=\"Flat\",IF(Tool!I75>Tool!G75,0,IF(Tool!G75>0,Tool!G75+J20,\"\")),\"\"))","v":""},{"$f":"IF(E20=\"Flat\",IF(Tool!H75>0,Tool!H75,\"\"),\"\")","v":""},{"$f":"IF(E20=\"Flat\",IF(Tool!I75>Tool!G75,Tool!G75,IF(Tool!I75>=0,Tool!I75)),\"\")","v":""},{"$f":"IF(E20=\"Flat\",Tool!O75,\"\")","v":""},{"$f":"IF(AND(K20=\"Urban/C&G\",E20=\"Flat\",Tool!L75=\"Both Sides\",Tool!M75=\"Both Sides\"),Tool!$M$62*2,IF(AND(K20=\"Urban/C&G\",E20=\"Flat\",Tool!L75=\"Both Sides\",Tool!M75=\"One Side\"),Tool!$M$62,IF(AND(K20=\"Urban/C&G\",E20=\"Flat\",Tool!L75=\"One Side\",Tool!M75=\"Both Sides\"),Tool!$M$62,IF(AND(K20=\"Urban/C&G\",E20=\"Flat\",Tool!L75=\"One Side\",Tool!M75=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E20=\"Flat\",Tool!K75,\"\")","v":""},{"$f":"IF(E20<>\"\",Drainage!G57,\"\")","v":""},"",{"$f":"IF(AND(F20=H20,G20=\"\"),\"\",VLOOKUP(Tool!P75,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7>=12,S7<=20),12,\"\")","v":""},{"$f":"IF(R20<>\"\",IF(T19>=$C$2,\"\",IF($C$2<(Tool!E108-Tool!$D$98),\"\",IF(Tool!D109<>\"\",IF(Tool!$D$98<>0,Tool!E108-Tool!$D$98,Tool!E108),\"\"))),\"\")","v":""},{"$f":"IF(S20=\"\",\"\",IF(R20=\"\",\"\",IF(Tool!E108<>\"\",IF(AND($C$2>=(Tool!E109-Tool!$D$98),(Tool!E110-Tool!$D$98)>=(Tool!E109-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E109-Tool!$D$98,Tool!E109),$C$2),\"\")))","v":""},{"$f":"IF(R20<>\"\",IF(Tool!H109=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U20=\"flat\",Tool!I109>0),Tool!I109,\"\")","v":""},{"$f":"IF(U20=\"Flat\",IF(Tool!J109>0,IF(Tool!F109=\"Barrier Wall\",3,IF(Tool!F109=\"Depressed Grass\",Tool!J109*0.5,Tool!J109)),\"\"),\"\")","v":""},{"$f":"IF(R20<>\"\",IF(U20=\"Flat\",Tool!F109,\"\"),\"\")","v":""},"",null,"Eff. Med. Width:",{"$f":"Median!L21","v":0}]
[null,{"$f":"IF(AND(E7>=13,E7<=30),13,\"\")","v":""},{"$f":"IF(D20>=$C$2,\"\",IF($C$2<(Tool!E75-Tool!$D$64),\"\",IF(Tool!D76<>\"\",IF(Tool!$D$64<>0,Tool!E75-Tool!$D$64,Tool!E75),\"\")))","v":""},{"$f":"IF(C21=\"\",\"\",IF(B22=\"\",$C$2,IF((D20-$C$9)>=$C$2,\"\",IF(Tool!E75<>\"\",IF(AND($C$2>=(Tool!E76-Tool!$D$64),(Tool!E77-Tool!$D$64)>=(Tool!E76-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E76-Tool!$D$64,Tool!E76),$C$2),\"\"))))","v":""},{"$f":"IF(C21=\"\",\"\",IF(B21<>\"\",IF(Tool!N76=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E21=\"Flat\",IF(Tool!I76>Tool!G76,0,IF(Tool!G76>0,Tool!G76+J21,\"\")),\"\"))","v":""},{"$f":"IF(E21=\"Flat\",IF(Tool!H76>0,Tool!H76,\"\"),\"\")","v":""},{"$f":"IF(E21=\"Flat\",IF(Tool!I76>Tool!G76,Tool!G76,IF(Tool!I76>=0,Tool!I76)),\"\")","v":""},{"$f":"IF(E21=\"Flat\",Tool!O76,\"\")","v":""},{"$f":"IF(AND(K21=\"Urban/C&G\",E21=\"Flat\",Tool!L76=\"Both Sides\",Tool!M76=\"Both Sides\"),Tool!$M$62*2,IF(AND(K21=\"Urban/C&G\",E21=\"Flat\",Tool!L76=\"Both Sides\",Tool!M76=\"One Side\"),Tool!$M$62,IF(AND(K21=\"Urban/C&G\",E21=\"Flat\",Tool!L76=\"One Side\",Tool!M76=\"Both Sides\"),Tool!$M$62,IF(AND(K21=\"Urban/C&G\",E21=\"Flat\",Tool!L76=\"One Side\",Tool!M76=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E21=\"Flat\",Tool!K76,\"\")","v":""},{"$f":"IF(E21<>\"\",Drainage!G58,\"\")","v":""},"",{"$f":"IF(AND(F21=H21,G21=\"\"),\"\",VLOOKUP(Tool!P76,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7>=13,S7<=20),13,\"\")","v":""},{"$f":"IF(R21<>\"\",IF(T20>=$C$2,\"\",IF($C$2<(Tool!E109-Tool!$D$98),\"\",IF(Tool!D110<>\"\",IF(Tool!$D$98<>0,Tool!E109-Tool!$D$98,Tool!E109),\"\"))),\"\")","v":""},{"$f":"IF(S21=\"\",\"\",IF(R21=\"\",\"\",IF(Tool!E109<>\"\",IF(AND($C$2>=(Tool!E110-Tool!$D$98),(Tool!E111-Tool!$D$98)>=(Tool!E110-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E110-Tool!$D$98,Tool!E110),$C$2),\"\")))","v":""},{"$f":"IF(R21<>\"\",IF(Tool!H110=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U21=\"flat\",Tool!I110>0),Tool!I110,\"\")","v":""},{"$f":"IF(U21=\"Flat\",IF(Tool!J110>0,IF(Tool!F110=\"Barrier Wall\",3,IF(Tool!F110=\"Depressed Grass\",Tool!J110*0.5,Tool!J110)),\"\"),\"\")","v":""},{"$f":"IF(R21<>\"\",IF(U21=\"Flat\",Tool!F110,\"\"),\"\")","v":""},"",null,"Avg. Facility Width:",{"$f":"Drainage!K25","v":0}]
[null,{"$f":"IF(AND(E7>=14,E7<=30),14,\"\")","v":""},{"$f":"IF(D21>=$C$2,\"\",IF($C$2<(Tool!E76-Tool!$D$64),\"\",IF(Tool!D77<>\"\",IF(Tool!$D$64<>0,Tool!E76-Tool!$D$64,Tool!E76),\"\")))","v":""},{"$f":"IF(C22=\"\",\"\",IF(B23=\"\",$C$2,IF((D21-$C$9)>=$C$2,\"\",IF(Tool!E76<>\"\",IF(AND($C$2>=(Tool!E77-Tool!$D$64),(Tool!E78-Tool!$D$64)>=(Tool!E77-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E77-Tool!$D$64,Tool!E77),$C$2),\"\"))))","v":""},{"$f":"IF(C22=\"\",\"\",IF(B22<>\"\",IF(Tool!N77=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E22=\"Flat\",IF(Tool!I77>Tool!G77,0,IF(Tool!G77>0,Tool!G77+J22,\"\")),\"\"))","v":""},{"$f":"IF(E22=\"Flat\",IF(Tool!H77>0,Tool!H77,\"\"),\"\")","v":""},{"$f":"IF(E22=\"Flat\",IF(Tool!I77>Tool!G77,Tool!G77,IF(Tool!I77>=0,Tool!I77)),\"\")","v":""},{"$f":"IF(E22=\"Flat\",Tool!O77,\"\")","v":""},{"$f":"IF(AND(K22=\"Urban/C&G\",E22=\"Flat\",Tool!L77=\"Both Sides\",Tool!M77=\"Both Sides\"),Tool!$M$62*2,IF(AND(K22=\"Urban/C&G\",E22=\"Flat\",Tool!L77=\"Both Sides\",Tool!M77=\"One Side\"),Tool!$M$62,IF(AND(K22=\"Urban/C&G\",E22=\"Flat\",Tool!L77=\"One Side\",Tool!M77=\"Both Sides\"),Tool!$M$62,IF(AND(K22=\"Urban/C&G\",E22=\"Flat\",Tool!L77=\"One Side\",Tool!M77=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E22=\"Flat\",Tool!K77,\"\")","v":""},{"$f":"IF(E22<>\"\",Drainage!G59,\"\")","v":""},"",{"$f":"IF(AND(F22=H22,G22=\"\"),\"\",VLOOKUP(Tool!P77,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7>=14,S7<=20),14,\"\")","v":""},{"$f":"IF(R22<>\"\",IF(T21>=$C$2,\"\",IF($C$2<(Tool!E110-Tool!$D$98),\"\",IF(Tool!D111<>\"\",IF(Tool!$D$98<>0,Tool!E110-Tool!$D$98,Tool!E110),\"\"))),\"\")","v":""},{"$f":"IF(S22=\"\",\"\",IF(R22=\"\",\"\",IF(Tool!E110<>\"\",IF(AND($C$2>=(Tool!E111-Tool!$D$98),(Tool!E112-Tool!$D$98)>=(Tool!E111-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E111-Tool!$D$98,Tool!E111),$C$2),\"\")))","v":""},{"$f":"IF(R22<>\"\",IF(Tool!H111=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U22=\"flat\",Tool!I111>0),Tool!I111,\"\")","v":""},{"$f":"IF(U22=\"Flat\",IF(Tool!J111>0,IF(Tool!F111=\"Barrier Wall\",3,IF(Tool!F111=\"Depressed Grass\",Tool!J111*0.5,Tool!J111)),\"\"),\"\")","v":""},{"$f":"IF(R22<>\"\",IF(U22=\"Flat\",Tool!F111,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E7>=15,E7<=30),15,\"\")","v":""},{"$f":"IF(D22>=$C$2,\"\",IF($C$2<(Tool!E77-Tool!$D$64),\"\",IF(Tool!D78<>\"\",IF(Tool!$D$64<>0,Tool!E77-Tool!$D$64,Tool!E77),\"\")))","v":""},{"$f":"IF(C23=\"\",\"\",IF(B24=\"\",$C$2,IF((D22-$C$9)>=$C$2,\"\",IF(Tool!E77<>\"\",IF(AND($C$2>=(Tool!E78-Tool!$D$64),(Tool!E79-Tool!$D$64)>=(Tool!E78-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E78-Tool!$D$64,Tool!E78),$C$2),\"\"))))","v":""},{"$f":"IF(C23=\"\",\"\",IF(B23<>\"\",IF(Tool!N78=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E23=\"Flat\",IF(Tool!I78>Tool!G78,0,IF(Tool!G78>0,Tool!G78+J23,\"\")),\"\"))","v":""},{"$f":"IF(E23=\"Flat\",IF(Tool!H78>0,Tool!H78,\"\"),\"\")","v":""},{"$f":"IF(E23=\"Flat\",IF(Tool!I78>Tool!G78,Tool!G78,IF(Tool!I78>=0,Tool!I78)),\"\")","v":""},{"$f":"IF(E23=\"Flat\",Tool!O78,\"\")","v":""},{"$f":"IF(AND(K23=\"Urban/C&G\",E23=\"Flat\",Tool!L78=\"Both Sides\",Tool!M78=\"Both Sides\"),Tool!$M$62*2,IF(AND(K23=\"Urban/C&G\",E23=\"Flat\",Tool!L78=\"Both Sides\",Tool!M78=\"One Side\"),Tool!$M$62,IF(AND(K23=\"Urban/C&G\",E23=\"Flat\",Tool!L78=\"One Side\",Tool!M78=\"Both Sides\"),Tool!$M$62,IF(AND(K23=\"Urban/C&G\",E23=\"Flat\",Tool!L78=\"One Side\",Tool!M78=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E23=\"Flat\",Tool!K78,\"\")","v":""},{"$f":"IF(E23<>\"\",Drainage!G60,\"\")","v":""},"",{"$f":"IF(AND(F23=H23,G23=\"\"),\"\",VLOOKUP(Tool!P78,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7>=15,S7<=20),15,\"\")","v":""},{"$f":"IF(R23<>\"\",IF(T22>=$C$2,\"\",IF($C$2<(Tool!E111-Tool!$D$98),\"\",IF(Tool!D112<>\"\",IF(Tool!$D$98<>0,Tool!E111-Tool!$D$98,Tool!E111),\"\"))),\"\")","v":""},{"$f":"IF(S23=\"\",\"\",IF(R23=\"\",\"\",IF(Tool!E111<>\"\",IF(AND($C$2>=(Tool!E112-Tool!$D$98),(Tool!E113-Tool!$D$98)>=(Tool!E112-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E112-Tool!$D$98,Tool!E112),$C$2),\"\")))","v":""},{"$f":"IF(R23<>\"\",IF(Tool!H112=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U23=\"flat\",Tool!I112>0),Tool!I112,\"\")","v":""},{"$f":"IF(U23=\"Flat\",IF(Tool!J112>0,IF(Tool!F112=\"Barrier Wall\",3,IF(Tool!F112=\"Depressed Grass\",Tool!J112*0.5,Tool!J112)),\"\"),\"\")","v":""},{"$f":"IF(R23<>\"\",IF(U23=\"Flat\",Tool!F112,\"\"),\"\")","v":""},"",null,"Road & Median Earthwork"]
[null,{"$f":"IF(AND(E7>=16,E7<=30),16,\"\")","v":""},{"$f":"IF(D23>=$C$2,\"\",IF($C$2<(Tool!E78-Tool!$D$64),\"\",IF(Tool!D79<>\"\",IF(Tool!$D$64<>0,Tool!E78-Tool!$D$64,Tool!E78),\"\")))","v":""},{"$f":"IF(C24=\"\",\"\",IF(B25=\"\",$C$2,IF((D23-$C$9)>=$C$2,\"\",IF(Tool!E78<>\"\",IF(AND($C$2>=(Tool!E79-Tool!$D$64),(Tool!E80-Tool!$D$64)>=(Tool!E79-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E79-Tool!$D$64,Tool!E79),$C$2),\"\"))))","v":""},{"$f":"IF(C24=\"\",\"\",IF(B24<>\"\",IF(Tool!N79=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E24=\"Flat\",IF(Tool!I79>Tool!G79,0,IF(Tool!G79>0,Tool!G79+J24,\"\")),\"\"))","v":""},{"$f":"IF(E24=\"Flat\",IF(Tool!H79>0,Tool!H79,\"\"),\"\")","v":""},{"$f":"IF(E24=\"Flat\",IF(Tool!I79>Tool!G79,Tool!G79,IF(Tool!I79>=0,Tool!I79)),\"\")","v":""},{"$f":"IF(E24=\"Flat\",Tool!O79,\"\")","v":""},{"$f":"IF(AND(K24=\"Urban/C&G\",E24=\"Flat\",Tool!L79=\"Both Sides\",Tool!M79=\"Both Sides\"),Tool!$M$62*2,IF(AND(K24=\"Urban/C&G\",E24=\"Flat\",Tool!L79=\"Both Sides\",Tool!M79=\"One Side\"),Tool!$M$62,IF(AND(K24=\"Urban/C&G\",E24=\"Flat\",Tool!L79=\"One Side\",Tool!M79=\"Both Sides\"),Tool!$M$62,IF(AND(K24=\"Urban/C&G\",E24=\"Flat\",Tool!L79=\"One Side\",Tool!M79=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E24=\"Flat\",Tool!K79,\"\")","v":""},{"$f":"IF(E24<>\"\",Drainage!G61,\"\")","v":""},"",{"$f":"IF(AND(F24=H24,G24=\"\"),\"\",VLOOKUP(Tool!P79,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7>=16,S7<=20),16,\"\")","v":""},{"$f":"IF(R24<>\"\",IF(T23>=$C$2,\"\",IF($C$2<(Tool!E112-Tool!$D$98),\"\",IF(Tool!D113<>\"\",IF(Tool!$D$98<>0,Tool!E112-Tool!$D$98,Tool!E112),\"\"))),\"\")","v":""},{"$f":"IF(S24=\"\",\"\",IF(R24=\"\",\"\",IF(Tool!E112<>\"\",IF(AND($C$2>=(Tool!E113-Tool!$D$98),(Tool!E114-Tool!$D$98)>=(Tool!E113-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E113-Tool!$D$98,Tool!E113),$C$2),\"\")))","v":""},{"$f":"IF(R24<>\"\",IF(Tool!H113=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U24=\"flat\",Tool!I113>0),Tool!I113,\"\")","v":""},{"$f":"IF(U24=\"Flat\",IF(Tool!J113>0,IF(Tool!F113=\"Barrier Wall\",3,IF(Tool!F113=\"Depressed Grass\",Tool!J113*0.5,Tool!J113)),\"\"),\"\")","v":""},{"$f":"IF(R24<>\"\",IF(U24=\"Flat\",Tool!F113,\"\"),\"\")","v":""},"",null,"Terrian Type","Area Road","Area Median","Area Sidewalk","Area Total","Percent Type","Depth","R&M Volume","Road Length","Med. Length"]
[null,{"$f":"IF(AND(E7>=17,E7<=30),17,\"\")","v":""},{"$f":"IF(D24>=$C$2,\"\",IF($C$2<(Tool!E79-Tool!$D$64),\"\",IF(Tool!D80<>\"\",IF(Tool!$D$64<>0,Tool!E79-Tool!$D$64,Tool!E79),\"\")))","v":""},{"$f":"IF(C25=\"\",\"\",IF(B26=\"\",$C$2,IF((D24-$C$9)>=$C$2,\"\",IF(Tool!E79<>\"\",IF(AND($C$2>=(Tool!E80-Tool!$D$64),(Tool!E81-Tool!$D$64)>=(Tool!E80-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E80-Tool!$D$64,Tool!E80),$C$2),\"\"))))","v":""},{"$f":"IF(C25=\"\",\"\",IF(B25<>\"\",IF(Tool!N80=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E25=\"Flat\",IF(Tool!I80>Tool!G80,0,IF(Tool!G80>0,Tool!G80+J25,\"\")),\"\"))","v":""},{"$f":"IF(E25=\"Flat\",IF(Tool!H80>0,Tool!H80,\"\"),\"\")","v":""},{"$f":"IF(E25=\"Flat\",IF(Tool!I80>Tool!G80,Tool!G80,IF(Tool!I80>=0,Tool!I80)),\"\")","v":""},{"$f":"IF(E25=\"Flat\",Tool!O80,\"\")","v":""},{"$f":"IF(AND(K25=\"Urban/C&G\",E25=\"Flat\",Tool!L80=\"Both Sides\",Tool!M80=\"Both Sides\"),Tool!$M$62*2,IF(AND(K25=\"Urban/C&G\",E25=\"Flat\",Tool!L80=\"Both Sides\",Tool!M80=\"One Side\"),Tool!$M$62,IF(AND(K25=\"Urban/C&G\",E25=\"Flat\",Tool!L80=\"One Side\",Tool!M80=\"Both Sides\"),Tool!$M$62,IF(AND(K25=\"Urban/C&G\",E25=\"Flat\",Tool!L80=\"One Side\",Tool!M80=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E25=\"Flat\",Tool!K80,\"\")","v":""},{"$f":"IF(E25<>\"\",Drainage!G62,\"\")","v":""},"",{"$f":"IF(AND(F25=H25,G25=\"\"),\"\",VLOOKUP(Tool!P80,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7>=17,S7<=20),17,\"\")","v":""},{"$f":"IF(R25<>\"\",IF(T24>=$C$2,\"\",IF($C$2<(Tool!E113-Tool!$D$98),\"\",IF(Tool!D114<>\"\",IF(Tool!$D$98<>0,Tool!E113-Tool!$D$98,Tool!E113),\"\"))),\"\")","v":""},{"$f":"IF(S25=\"\",\"\",IF(R25=\"\",\"\",IF(Tool!E113<>\"\",IF(AND($C$2>=(Tool!E114-Tool!$D$98),(Tool!E115-Tool!$D$98)>=(Tool!E114-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E114-Tool!$D$98,Tool!E114),$C$2),\"\")))","v":""},{"$f":"IF(R25<>\"\",IF(Tool!H114=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U25=\"flat\",Tool!I114>0),Tool!I114,\"\")","v":""},{"$f":"IF(U25=\"Flat\",IF(Tool!J114>0,IF(Tool!F114=\"Barrier Wall\",3,IF(Tool!F114=\"Depressed Grass\",Tool!J114*0.5,Tool!J114)),\"\"),\"\")","v":""},{"$f":"IF(R25<>\"\",IF(U25=\"Flat\",Tool!F114,\"\"),\"\")","v":""},"",null,"Flat",{"$f":"I44","v":0},{"$f":"Y33","v":0},{"$f":"(F40*5280)*Tool!$M$61","v":0},{"$f":"AB25+AC25+AD25","v":0},{"$f":"IF(SUM($AE$25:$AE$28)>0,AE25/SUM($AE$25:$AE$28),0)","v":0},{"$f":"Tool!J122","v":3},{"$f":"(AE25*AG25)/27","v":0},{"$f":"I45","v":0},{"$f":"Y34","v":0}]
[null,{"$f":"IF(AND(E7>=18,E7<=30),18,\"\")","v":""},{"$f":"IF(D25>=$C$2,\"\",IF($C$2<(Tool!E80-Tool!$D$64),\"\",IF(Tool!D81<>\"\",IF(Tool!$D$64<>0,Tool!E80-Tool!$D$64,Tool!E80),\"\")))","v":""},{"$f":"IF(C26=\"\",\"\",IF(B27=\"\",$C$2,IF((D25-$C$9)>=$C$2,\"\",IF(Tool!E80<>\"\",IF(AND($C$2>=(Tool!E81-Tool!$D$64),(Tool!E82-Tool!$D$64)>=(Tool!E81-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E81-Tool!$D$64,Tool!E81),$C$2),\"\"))))","v":""},{"$f":"IF(C26=\"\",\"\",IF(B26<>\"\",IF(Tool!N81=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E26=\"Flat\",IF(Tool!I81>Tool!G81,0,IF(Tool!G81>0,Tool!G81+J26,\"\")),\"\"))","v":""},{"$f":"IF(E26=\"Flat\",IF(Tool!H81>0,Tool!H81,\"\"),\"\")","v":""},{"$f":"IF(E26=\"Flat\",IF(Tool!I81>Tool!G81,Tool!G81,IF(Tool!I81>=0,Tool!I81)),\"\")","v":""},{"$f":"IF(E26=\"Flat\",Tool!O81,\"\")","v":""},{"$f":"IF(AND(K26=\"Urban/C&G\",E26=\"Flat\",Tool!L81=\"Both Sides\",Tool!M81=\"Both Sides\"),Tool!$M$62*2,IF(AND(K26=\"Urban/C&G\",E26=\"Flat\",Tool!L81=\"Both Sides\",Tool!M81=\"One Side\"),Tool!$M$62,IF(AND(K26=\"Urban/C&G\",E26=\"Flat\",Tool!L81=\"One Side\",Tool!M81=\"Both Sides\"),Tool!$M$62,IF(AND(K26=\"Urban/C&G\",E26=\"Flat\",Tool!L81=\"One Side\",Tool!M81=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E26=\"Flat\",Tool!K81,\"\")","v":""},{"$f":"IF(E26<>\"\",Drainage!G63,\"\")","v":""},"",{"$f":"IF(AND(F26=H26,G26=\"\"),\"\",VLOOKUP(Tool!P81,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7>=18,S7<=20),18,\"\")","v":""},{"$f":"IF(R26<>\"\",IF(T25>=$C$2,\"\",IF($C$2<(Tool!E114-Tool!$D$98),\"\",IF(Tool!D115<>\"\",IF(Tool!$D$98<>0,Tool!E114-Tool!$D$98,Tool!E114),\"\"))),\"\")","v":""},{"$f":"IF(S26=\"\",\"\",IF(R26=\"\",\"\",IF(Tool!E114<>\"\",IF(AND($C$2>=(Tool!E115-Tool!$D$98),(Tool!E116-Tool!$D$98)>=(Tool!E115-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E115-Tool!$D$98,Tool!E115),$C$2),\"\")))","v":""},{"$f":"IF(R26<>\"\",IF(Tool!H115=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U26=\"flat\",Tool!I115>0),Tool!I115,\"\")","v":""},{"$f":"IF(U26=\"Flat\",IF(Tool!J115>0,IF(Tool!F115=\"Barrier Wall\",3,IF(Tool!F115=\"Depressed Grass\",Tool!J115*0.5,Tool!J115)),\"\"),\"\")","v":""},{"$f":"IF(R26<>\"\",IF(U26=\"Flat\",Tool!F115,\"\"),\"\")","v":""},"",null,"Rolling",{"$f":"I83","v":0},{"$f":"Y62","v":0},{"$f":"(F79*5280)*Tool!$M$61","v":0},{"$f":"AB26+AC26+AD26","v":0},{"$f":"IF(SUM($AE$25:$AE$28)>0,AE26/SUM($AE$25:$AE$28),0)","v":0},{"$f":"Tool!J123","v":4.9804691576092077},{"$f":"(AE26*AG26)/27","v":0},{"$f":"I84","v":0},{"$f":"Y63","v":0}]
[null,{"$f":"IF(AND(E7>=19,E7<=30),19,\"\")","v":""},{"$f":"IF(D26>=$C$2,\"\",IF($C$2<(Tool!E81-Tool!$D$64),\"\",IF(Tool!D82<>\"\",IF(Tool!$D$64<>0,Tool!E81-Tool!$D$64,Tool!E81),\"\")))","v":""},{"$f":"IF(C27=\"\",\"\",IF(B28=\"\",$C$2,IF((D26-$C$9)>=$C$2,\"\",IF(Tool!E81<>\"\",IF(AND($C$2>=(Tool!E82-Tool!$D$64),(Tool!E83-Tool!$D$64)>=(Tool!E82-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E82-Tool!$D$64,Tool!E82),$C$2),\"\"))))","v":""},{"$f":"IF(C27=\"\",\"\",IF(B27<>\"\",IF(Tool!N82=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E27=\"Flat\",IF(Tool!I82>Tool!G82,0,IF(Tool!G82>0,Tool!G82+J27,\"\")),\"\"))","v":""},{"$f":"IF(E27=\"Flat\",IF(Tool!H82>0,Tool!H82,\"\"),\"\")","v":""},{"$f":"IF(E27=\"Flat\",IF(Tool!I82>Tool!G82,Tool!G82,IF(Tool!I82>=0,Tool!I82)),\"\")","v":""},{"$f":"IF(E27=\"Flat\",Tool!O82,\"\")","v":""},{"$f":"IF(AND(K27=\"Urban/C&G\",E27=\"Flat\",Tool!L82=\"Both Sides\",Tool!M82=\"Both Sides\"),Tool!$M$62*2,IF(AND(K27=\"Urban/C&G\",E27=\"Flat\",Tool!L82=\"Both Sides\",Tool!M82=\"One Side\"),Tool!$M$62,IF(AND(K27=\"Urban/C&G\",E27=\"Flat\",Tool!L82=\"One Side\",Tool!M82=\"Both Sides\"),Tool!$M$62,IF(AND(K27=\"Urban/C&G\",E27=\"Flat\",Tool!L82=\"One Side\",Tool!M82=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E27=\"Flat\",Tool!K82,\"\")","v":""},{"$f":"IF(E27<>\"\",Drainage!G64,\"\")","v":""},"",{"$f":"IF(AND(F27=H27,G27=\"\"),\"\",VLOOKUP(Tool!P82,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7>=19,S7<=20),19,\"\")","v":""},{"$f":"IF(R27<>\"\",IF(T26>=$C$2,\"\",IF($C$2<(Tool!E115-Tool!$D$98),\"\",IF(Tool!D116<>\"\",IF(Tool!$D$98<>0,Tool!E115-Tool!$D$98,Tool!E115),\"\"))),\"\")","v":""},{"$f":"IF(S27=\"\",\"\",IF(R27=\"\",\"\",IF(Tool!E115<>\"\",IF(AND($C$2>=(Tool!E116-Tool!$D$98),(Tool!E117-Tool!$D$98)>=(Tool!E116-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E116-Tool!$D$98,Tool!E116),$C$2),\"\")))","v":""},{"$f":"IF(R27<>\"\",IF(Tool!H116=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U27=\"flat\",Tool!I116>0),Tool!I116,\"\")","v":""},{"$f":"IF(U27=\"Flat\",IF(Tool!J116>0,IF(Tool!F116=\"Barrier Wall\",3,IF(Tool!F116=\"Depressed Grass\",Tool!J116*0.5,Tool!J116)),\"\"),\"\")","v":""},{"$f":"IF(R27<>\"\",IF(U27=\"Flat\",Tool!F116,\"\"),\"\")","v":""},"",null,"Mountainous",{"$f":"I123","v":0},{"$f":"Y92","v":0},{"$f":"(F119*5280)*Tool!$M$61","v":0},{"$f":"AB27+AC27+AD27","v":0},{"$f":"IF(SUM($AE$25:$AE$28)>0,AE27/SUM($AE$25:$AE$28),0)","v":0},{"$f":"Tool!J124","v":9},{"$f":"(AE27*AG27)/27","v":0},{"$f":"I124","v":0},{"$f":"Y93","v":0}]
[null,{"$f":"IF(AND(E7>=20,E7<=30),20,\"\")","v":""},{"$f":"IF(D27>=$C$2,\"\",IF($C$2<(Tool!E82-Tool!$D$64),\"\",IF(Tool!D83<>\"\",IF(Tool!$D$64<>0,Tool!E82-Tool!$D$64,Tool!E82),\"\")))","v":""},{"$f":"IF(C28=\"\",\"\",IF(B29=\"\",$C$2,IF((D27-$C$9)>=$C$2,\"\",IF(Tool!E82<>\"\",IF(AND($C$2>=(Tool!E83-Tool!$D$64),(Tool!E84-Tool!$D$64)>=(Tool!E83-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E83-Tool!$D$64,Tool!E83),$C$2),\"\"))))","v":""},{"$f":"IF(C28=\"\",\"\",IF(B28<>\"\",IF(Tool!N83=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E28=\"Flat\",IF(Tool!I83>Tool!G83,0,IF(Tool!G83>0,Tool!G83+J28,\"\")),\"\"))","v":""},{"$f":"IF(E28=\"Flat\",IF(Tool!H83>0,Tool!H83,\"\"),\"\")","v":""},{"$f":"IF(E28=\"Flat\",IF(Tool!I83>Tool!G83,Tool!G83,IF(Tool!I83>=0,Tool!I83)),\"\")","v":""},{"$f":"IF(E28=\"Flat\",Tool!O83,\"\")","v":""},{"$f":"IF(AND(K28=\"Urban/C&G\",E28=\"Flat\",Tool!L83=\"Both Sides\",Tool!M83=\"Both Sides\"),Tool!$M$62*2,IF(AND(K28=\"Urban/C&G\",E28=\"Flat\",Tool!L83=\"Both Sides\",Tool!M83=\"One Side\"),Tool!$M$62,IF(AND(K28=\"Urban/C&G\",E28=\"Flat\",Tool!L83=\"One Side\",Tool!M83=\"Both Sides\"),Tool!$M$62,IF(AND(K28=\"Urban/C&G\",E28=\"Flat\",Tool!L83=\"One Side\",Tool!M83=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E28=\"Flat\",Tool!K83,\"\")","v":""},{"$f":"IF(E28<>\"\",Drainage!G65,\"\")","v":""},"",{"$f":"IF(AND(F28=H28,G28=\"\"),\"\",VLOOKUP(Tool!P83,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S7=20),20,\"\")","v":""},{"$f":"IF(R28<>\"\",IF(T27>=$C$2,\"\",IF($C$2<(Tool!E116-Tool!$D$98),\"\",IF(Tool!D117<>\"\",IF(Tool!$D$98<>0,Tool!E116-Tool!$D$98,Tool!E116),\"\"))),\"\")","v":""},{"$f":"IF(S28=\"\",\"\",IF(R28=\"\",\"\",IF(Tool!E116<>\"\",IF(AND($C$2>=(Tool!E117-Tool!$D$98),(Tool!E118-Tool!$D$98)>=(Tool!E117-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E117-Tool!$D$98,Tool!E117),$C$2),\"\")))","v":""},{"$f":"IF(R28<>\"\",IF(Tool!H117=\"Flat\",\"Flat\",\"\"),\"\")","v":""},{"$f":"IF(AND(U28=\"flat\",Tool!I117>0),Tool!I117,\"\")","v":""},{"$f":"IF(U28=\"Flat\",IF(Tool!J117>0,IF(Tool!F117=\"Barrier Wall\",3,IF(Tool!F117=\"Depressed Grass\",Tool!J117*0.5,Tool!J117)),\"\"),\"\")","v":""},{"$f":"IF(R28<>\"\",IF(U28=\"Flat\",Tool!F117,\"\"),\"\")","v":""},"",null,"Heavy Mountainous",{"$f":"I163","v":0},{"$f":"Y122","v":0},{"$f":"(F159*5280)*Tool!$M$61","v":0},0,{"$f":"IF(SUM($AE$25:$AE$28)>0,AE28/SUM($AE$25:$AE$28),0)","v":0},{"$f":"Tool!J125","v":16.018039252929434},{"$f":"(AE28*AG28)/27","v":0},{"$f":"I164","v":0},{"$f":"Y123","v":0}]
[null,{"$f":"IF(AND(E7>=21,E7<=30),21,\"\")","v":""},{"$f":"IF(D28>=$C$2,\"\",IF($C$2<(Tool!E83-Tool!$D$64),\"\",IF(Tool!D84<>\"\",IF(Tool!$D$64<>0,Tool!E83-Tool!$D$64,Tool!E83),\"\")))","v":""},{"$f":"IF(C29=\"\",\"\",IF(B30=\"\",$C$2,IF((D28-$C$9)>=$C$2,\"\",IF(Tool!E83<>\"\",IF(AND($C$2>=(Tool!E84-Tool!$D$64),(Tool!E85-Tool!$D$64)>=(Tool!E84-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E84-Tool!$D$64,Tool!E84),$C$2),\"\"))))","v":""},{"$f":"IF(C29=\"\",\"\",IF(B29<>\"\",IF(Tool!N84=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E29=\"Flat\",IF(Tool!I84>Tool!G84,0,IF(Tool!G84>0,Tool!G84+J29,\"\")),\"\"))","v":""},{"$f":"IF(E29=\"Flat\",IF(Tool!H84>0,Tool!H84,\"\"),\"\")","v":""},{"$f":"IF(E29=\"Flat\",IF(Tool!I84>Tool!G84,Tool!G84,IF(Tool!I84>=0,Tool!I84)),\"\")","v":""},{"$f":"IF(E29=\"Flat\",Tool!O84,\"\")","v":""},{"$f":"IF(AND(K29=\"Urban/C&G\",E29=\"Flat\",Tool!L84=\"Both Sides\",Tool!M84=\"Both Sides\"),Tool!$M$62*2,IF(AND(K29=\"Urban/C&G\",E29=\"Flat\",Tool!L84=\"Both Sides\",Tool!M84=\"One Side\"),Tool!$M$62,IF(AND(K29=\"Urban/C&G\",E29=\"Flat\",Tool!L84=\"One Side\",Tool!M84=\"Both Sides\"),Tool!$M$62,IF(AND(K29=\"Urban/C&G\",E29=\"Flat\",Tool!L84=\"One Side\",Tool!M84=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E29=\"Flat\",Tool!K84,\"\")","v":""},{"$f":"IF(E29<>\"\",Drainage!G66,\"\")","v":""},"",{"$f":"IF(AND(F29=H29,G29=\"\"),\"\",VLOOKUP(Tool!P84,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E7>=22,E7<=30),22,\"\")","v":""},{"$f":"IF(D29>=$C$2,\"\",IF($C$2<(Tool!E84-Tool!$D$64),\"\",IF(Tool!D85<>\"\",IF(Tool!$D$64<>0,Tool!E84-Tool!$D$64,Tool!E84),\"\")))","v":""},{"$f":"IF(C30=\"\",\"\",IF(B31=\"\",$C$2,IF((D29-$C$9)>=$C$2,\"\",IF(Tool!E84<>\"\",IF(AND($C$2>=(Tool!E85-Tool!$D$64),(Tool!E86-Tool!$D$64)>=(Tool!E85-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E85-Tool!$D$64,Tool!E85),$C$2),\"\"))))","v":""},{"$f":"IF(C30=\"\",\"\",IF(B30<>\"\",IF(Tool!N85=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E30=\"Flat\",IF(Tool!I85>Tool!G85,0,IF(Tool!G85>0,Tool!G85+J30,\"\")),\"\"))","v":""},{"$f":"IF(E30=\"Flat\",IF(Tool!H85>0,Tool!H85,\"\"),\"\")","v":""},{"$f":"IF(E30=\"Flat\",IF(Tool!I85>Tool!G85,Tool!G85,IF(Tool!I85>=0,Tool!I85)),\"\")","v":""},{"$f":"IF(E30=\"Flat\",Tool!O85,\"\")","v":""},{"$f":"IF(AND(K30=\"Urban/C&G\",E30=\"Flat\",Tool!L85=\"Both Sides\",Tool!M85=\"Both Sides\"),Tool!$M$62*2,IF(AND(K30=\"Urban/C&G\",E30=\"Flat\",Tool!L85=\"Both Sides\",Tool!M85=\"One Side\"),Tool!$M$62,IF(AND(K30=\"Urban/C&G\",E30=\"Flat\",Tool!L85=\"One Side\",Tool!M85=\"Both Sides\"),Tool!$M$62,IF(AND(K30=\"Urban/C&G\",E30=\"Flat\",Tool!L85=\"One Side\",Tool!M85=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E30=\"Flat\",Tool!K85,\"\")","v":""},{"$f":"IF(E30<>\"\",Drainage!G67,\"\")","v":""},"",{"$f":"IF(AND(F30=H30,G30=\"\"),\"\",VLOOKUP(Tool!P85,$AM$4:$AN$9,2,0))","v":""},"","","",null,null,null,null,null,null,"Avg. Inside Shldr. Width:",{"$f":"IF(SUM(Y9:Y28),SUMPRODUCT(V9:V28,Y9:Y28)/SUM(Y9:Y28),0)","v":0},null,"Facility Terrain Breakdown"]
[null,{"$f":"IF(AND(E7>=23,E7<=30),23,\"\")","v":""},{"$f":"IF(D30>=$C$2,\"\",IF($C$2<(Tool!E85-Tool!$D$64),\"\",IF(Tool!D86<>\"\",IF(Tool!$D$64<>0,Tool!E85-Tool!$D$64,Tool!E85),\"\")))","v":""},{"$f":"IF(C31=\"\",\"\",IF(B32=\"\",$C$2,IF((D30-$C$9)>=$C$2,\"\",IF(Tool!E85<>\"\",IF(AND($C$2>=(Tool!E86-Tool!$D$64),(Tool!E87-Tool!$D$64)>=(Tool!E86-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E86-Tool!$D$64,Tool!E86),$C$2),\"\"))))","v":""},{"$f":"IF(C31=\"\",\"\",IF(B31<>\"\",IF(Tool!N86=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E31=\"Flat\",IF(Tool!I86>Tool!G86,0,IF(Tool!G86>0,Tool!G86+J31,\"\")),\"\"))","v":""},{"$f":"IF(E31=\"Flat\",IF(Tool!H86>0,Tool!H86,\"\"),\"\")","v":""},{"$f":"IF(E31=\"Flat\",IF(Tool!I86>Tool!G86,Tool!G86,IF(Tool!I86>=0,Tool!I86)),\"\")","v":""},{"$f":"IF(E31=\"Flat\",Tool!O86,\"\")","v":""},{"$f":"IF(AND(K31=\"Urban/C&G\",E31=\"Flat\",Tool!L86=\"Both Sides\",Tool!M86=\"Both Sides\"),Tool!$M$62*2,IF(AND(K31=\"Urban/C&G\",E31=\"Flat\",Tool!L86=\"Both Sides\",Tool!M86=\"One Side\"),Tool!$M$62,IF(AND(K31=\"Urban/C&G\",E31=\"Flat\",Tool!L86=\"One Side\",Tool!M86=\"Both Sides\"),Tool!$M$62,IF(AND(K31=\"Urban/C&G\",E31=\"Flat\",Tool!L86=\"One Side\",Tool!M86=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E31=\"Flat\",Tool!K86,\"\")","v":""},{"$f":"IF(E31<>\"\",Drainage!G68,\"\")","v":""},"",{"$f":"IF(AND(F31=H31,G31=\"\"),\"\",VLOOKUP(Tool!P86,$AM$4:$AN$9,2,0))","v":""},"","","",null,null,null,null,null,null,"Avg. Interior Width:",{"$f":"IF(SUM(Y9:Y28)>0,SUMPRODUCT(W9:W28,Y9:Y28)/SUM(Y9:Y28),0)","v":0},null,null,"Roadway Length","Percent Type"]
[null,{"$f":"IF(AND(E7>=24,E7<=30),24,\"\")","v":""},{"$f":"IF(D31>=$C$2,\"\",IF($C$2<(Tool!E86-Tool!$D$64),\"\",IF(Tool!D87<>\"\",IF(Tool!$D$64<>0,Tool!E86-Tool!$D$64,Tool!E86),\"\")))","v":""},{"$f":"IF(C32=\"\",\"\",IF(B33=\"\",$C$2,IF((D31-$C$9)>=$C$2,\"\",IF(Tool!E86<>\"\",IF(AND($C$2>=(Tool!E87-Tool!$D$64),(Tool!E88-Tool!$D$64)>=(Tool!E87-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E87-Tool!$D$64,Tool!E87),$C$2),\"\"))))","v":""},{"$f":"IF(C32=\"\",\"\",IF(B32<>\"\",IF(Tool!N87=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E32=\"Flat\",IF(Tool!I87>Tool!G87,0,IF(Tool!G87>0,Tool!G87+J32,\"\")),\"\"))","v":""},{"$f":"IF(E32=\"Flat\",IF(Tool!H87>0,Tool!H87,\"\"),\"\")","v":""},{"$f":"IF(E32=\"Flat\",IF(Tool!I87>Tool!G87,Tool!G87,IF(Tool!I87>=0,Tool!I87)),\"\")","v":""},{"$f":"IF(E32=\"Flat\",Tool!O87,\"\")","v":""},{"$f":"IF(AND(K32=\"Urban/C&G\",E32=\"Flat\",Tool!L87=\"Both Sides\",Tool!M87=\"Both Sides\"),Tool!$M$62*2,IF(AND(K32=\"Urban/C&G\",E32=\"Flat\",Tool!L87=\"Both Sides\",Tool!M87=\"One Side\"),Tool!$M$62,IF(AND(K32=\"Urban/C&G\",E32=\"Flat\",Tool!L87=\"One Side\",Tool!M87=\"Both Sides\"),Tool!$M$62,IF(AND(K32=\"Urban/C&G\",E32=\"Flat\",Tool!L87=\"One Side\",Tool!M87=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E32=\"Flat\",Tool!K87,\"\")","v":""},{"$f":"IF(E32<>\"\",Drainage!G69,\"\")","v":""},"",{"$f":"IF(AND(F32=H32,G32=\"\"),\"\",VLOOKUP(Tool!P87,$AM$4:$AN$9,2,0))","v":""},"","","",null,null,null,null,null,null,"Avg. Fill Width:",{"$f":"Y30+Y31","v":0},null,"Flat:",{"$f":"I45","v":0},{"$f":"IF(SUM($AB$32:$AB$35)>0,AB32/SUM($AB$32:$AB$35),0)","v":0}]
[null,{"$f":"IF(AND(E7>=25,E7<=30),25,\"\")","v":""},{"$f":"IF(D32>=$C$2,\"\",IF($C$2<(Tool!E87-Tool!$D$64),\"\",IF(Tool!D88<>\"\",IF(Tool!$D$64<>0,Tool!E87-Tool!$D$64,Tool!E87),\"\")))","v":""},{"$f":"IF(C33=\"\",\"\",IF(B34=\"\",$C$2,IF((D32-$C$9)>=$C$2,\"\",IF(Tool!E87<>\"\",IF(AND($C$2>=(Tool!E88-Tool!$D$64),(Tool!E89-Tool!$D$64)>=(Tool!E88-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E88-Tool!$D$64,Tool!E88),$C$2),\"\"))))","v":""},{"$f":"IF(C33=\"\",\"\",IF(B33<>\"\",IF(Tool!N88=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E33=\"Flat\",IF(Tool!I88>Tool!G88,0,IF(Tool!G88>0,Tool!G88+J33,\"\")),\"\"))","v":""},{"$f":"IF(E33=\"Flat\",IF(Tool!H88>0,Tool!H88,\"\"),\"\")","v":""},{"$f":"IF(E33=\"Flat\",IF(Tool!I88>Tool!G88,Tool!G88,IF(Tool!I88>=0,Tool!I88)),\"\")","v":""},{"$f":"IF(E33=\"Flat\",Tool!O88,\"\")","v":""},{"$f":"IF(AND(K33=\"Urban/C&G\",E33=\"Flat\",Tool!L88=\"Both Sides\",Tool!M88=\"Both Sides\"),Tool!$M$62*2,IF(AND(K33=\"Urban/C&G\",E33=\"Flat\",Tool!L88=\"Both Sides\",Tool!M88=\"One Side\"),Tool!$M$62,IF(AND(K33=\"Urban/C&G\",E33=\"Flat\",Tool!L88=\"One Side\",Tool!M88=\"Both Sides\"),Tool!$M$62,IF(AND(K33=\"Urban/C&G\",E33=\"Flat\",Tool!L88=\"One Side\",Tool!M88=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E33=\"Flat\",Tool!K88,\"\")","v":""},{"$f":"IF(E33<>\"\",Drainage!G70,\"\")","v":""},"",{"$f":"IF(AND(F33=H33,G33=\"\"),\"\",VLOOKUP(Tool!P88,$AM$4:$AN$9,2,0))","v":""},"","","",null,null,null,null,null,null,"Avg. Fill Area:",{"$f":"Y32*SUM(Y9:Y28)*5280","v":0},null,"Rolling:",{"$f":"I84","v":0},{"$f":"IF(SUM($AB$32:$AB$35)>0,AB33/SUM($AB$32:$AB$35),0)","v":0}]
[null,{"$f":"IF(AND(E7>=26,E7<=30),26,\"\")","v":""},{"$f":"IF(D33>=$C$2,\"\",IF($C$2<(Tool!E88-Tool!$D$64),\"\",IF(Tool!D89<>\"\",IF(Tool!$D$64<>0,Tool!E88-Tool!$D$64,Tool!E88),\"\")))","v":""},{"$f":"IF(C34=\"\",\"\",IF(B35=\"\",$C$2,IF((D33-$C$9)>=$C$2,\"\",IF(Tool!E88<>\"\",IF(AND($C$2>=(Tool!E89-Tool!$D$64),(Tool!E90-Tool!$D$64)>=(Tool!E89-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E89-Tool!$D$64,Tool!E89),$C$2),\"\"))))","v":""},{"$f":"IF(C34=\"\",\"\",IF(B34<>\"\",IF(Tool!N89=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E34=\"Flat\",IF(Tool!I89>Tool!G89,0,IF(Tool!G89>0,Tool!G89+J34,\"\")),\"\"))","v":""},{"$f":"IF(E34=\"Flat\",IF(Tool!H89>0,Tool!H89,\"\"),\"\")","v":""},{"$f":"IF(E34=\"Flat\",IF(Tool!I89>Tool!G89,Tool!G89,IF(Tool!I89>=0,Tool!I89)),\"\")","v":""},{"$f":"IF(E34=\"Flat\",Tool!O89,\"\")","v":""},{"$f":"IF(AND(K34=\"Urban/C&G\",E34=\"Flat\",Tool!L89=\"Both Sides\",Tool!M89=\"Both Sides\"),Tool!$M$62*2,IF(AND(K34=\"Urban/C&G\",E34=\"Flat\",Tool!L89=\"Both Sides\",Tool!M89=\"One Side\"),Tool!$M$62,IF(AND(K34=\"Urban/C&G\",E34=\"Flat\",Tool!L89=\"One Side\",Tool!M89=\"Both Sides\"),Tool!$M$62,IF(AND(K34=\"Urban/C&G\",E34=\"Flat\",Tool!L89=\"One Side\",Tool!M89=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E34=\"Flat\",Tool!K89,\"\")","v":""},{"$f":"IF(E34<>\"\",Drainage!G71,\"\")","v":""},"",{"$f":"IF(AND(F34=H34,G34=\"\"),\"\",VLOOKUP(Tool!P89,$AM$4:$AN$9,2,0))","v":""},"","","",null,null,null,null,null,null,"Length:",{"$f":"SUM(Y9:Y28)","v":0},null,"Mountainous:",{"$f":"I124","v":0},{"$f":"IF(SUM($AB$32:$AB$35)>0,AB34/SUM($AB$32:$AB$35),0)","v":0}]
[null,{"$f":"IF(AND(E7>=27,E7<=30),27,\"\")","v":""},{"$f":"IF(D34>=$C$2,\"\",IF($C$2<(Tool!E89-Tool!$D$64),\"\",IF(Tool!D90<>\"\",IF(Tool!$D$64<>0,Tool!E89-Tool!$D$64,Tool!E89),\"\")))","v":""},{"$f":"IF(C35=\"\",\"\",IF(B36=\"\",$C$2,IF((D34-$C$9)>=$C$2,\"\",IF(Tool!E89<>\"\",IF(AND($C$2>=(Tool!E90-Tool!$D$64),(Tool!E91-Tool!$D$64)>=(Tool!E90-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E90-Tool!$D$64,Tool!E90),$C$2),\"\"))))","v":""},{"$f":"IF(C35=\"\",\"\",IF(B35<>\"\",IF(Tool!N90=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E35=\"Flat\",IF(Tool!I90>Tool!G90,0,IF(Tool!G90>0,Tool!G90+J35,\"\")),\"\"))","v":""},{"$f":"IF(E35=\"Flat\",IF(Tool!H90>0,Tool!H90,\"\"),\"\")","v":""},{"$f":"IF(E35=\"Flat\",IF(Tool!I90>Tool!G90,Tool!G90,IF(Tool!I90>=0,Tool!I90)),\"\")","v":""},{"$f":"IF(E35=\"Flat\",Tool!O90,\"\")","v":""},{"$f":"IF(AND(K35=\"Urban/C&G\",E35=\"Flat\",Tool!L90=\"Both Sides\",Tool!M90=\"Both Sides\"),Tool!$M$62*2,IF(AND(K35=\"Urban/C&G\",E35=\"Flat\",Tool!L90=\"Both Sides\",Tool!M90=\"One Side\"),Tool!$M$62,IF(AND(K35=\"Urban/C&G\",E35=\"Flat\",Tool!L90=\"One Side\",Tool!M90=\"Both Sides\"),Tool!$M$62,IF(AND(K35=\"Urban/C&G\",E35=\"Flat\",Tool!L90=\"One Side\",Tool!M90=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E35=\"Flat\",Tool!K90,\"\")","v":""},{"$f":"IF(E35<>\"\",Drainage!G72,\"\")","v":""},"",{"$f":"IF(AND(F35=H35,G35=\"\"),\"\",VLOOKUP(Tool!P90,$AM$4:$AN$9,2,0))","v":""},"","","","Rolling Terrain",null,null,null,null,null,null,null,null,"Heavy Mountainous:",{"$f":"I164","v":0},{"$f":"IF(SUM($AB$32:$AB$35)>0,AB35/SUM($AB$32:$AB$35),0)","v":0}]
[null,{"$f":"IF(AND(E7>=28,E7<=30),28,\"\")","v":""},{"$f":"IF(D35>=$C$2,\"\",IF($C$2<(Tool!E90-Tool!$D$64),\"\",IF(Tool!D91<>\"\",IF(Tool!$D$64<>0,Tool!E90-Tool!$D$64,Tool!E90),\"\")))","v":""},{"$f":"IF(C36=\"\",\"\",IF(B37=\"\",$C$2,IF((D35-$C$9)>=$C$2,\"\",IF(Tool!E90<>\"\",IF(AND($C$2>=(Tool!E91-Tool!$D$64),(Tool!E92-Tool!$D$64)>=(Tool!E91-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E91-Tool!$D$64,Tool!E91),$C$2),\"\"))))","v":""},{"$f":"IF(C36=\"\",\"\",IF(B36<>\"\",IF(Tool!N91=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E36=\"Flat\",IF(Tool!I91>Tool!G91,0,IF(Tool!G91>0,Tool!G91+J36,\"\")),\"\"))","v":""},{"$f":"IF(E36=\"Flat\",IF(Tool!H91>0,Tool!H91,\"\"),\"\")","v":""},{"$f":"IF(E36=\"Flat\",IF(Tool!I91>Tool!G91,Tool!G91,IF(Tool!I91>=0,Tool!I91)),\"\")","v":""},{"$f":"IF(E36=\"Flat\",Tool!O91,\"\")","v":""},{"$f":"IF(AND(K36=\"Urban/C&G\",E36=\"Flat\",Tool!L91=\"Both Sides\",Tool!M91=\"Both Sides\"),Tool!$M$62*2,IF(AND(K36=\"Urban/C&G\",E36=\"Flat\",Tool!L91=\"Both Sides\",Tool!M91=\"One Side\"),Tool!$M$62,IF(AND(K36=\"Urban/C&G\",E36=\"Flat\",Tool!L91=\"One Side\",Tool!M91=\"Both Sides\"),Tool!$M$62,IF(AND(K36=\"Urban/C&G\",E36=\"Flat\",Tool!L91=\"One Side\",Tool!M91=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E36=\"Flat\",Tool!K91,\"\")","v":""},{"$f":"IF(E36<>\"\",Drainage!G73,\"\")","v":""},"",{"$f":"IF(AND(F36=H36,G36=\"\"),\"\",VLOOKUP(Tool!P91,$AM$4:$AN$9,2,0))","v":""},"","","","Segments:",{"$f":"Tool!$J$96","v":1}]
[null,{"$f":"IF(AND(E7>=29,E7<=30),29,\"\")","v":""},{"$f":"IF(D36>=$C$2,\"\",IF($C$2<(Tool!E91-Tool!$D$64),\"\",IF(Tool!D92<>\"\",IF(Tool!$D$64<>0,Tool!E91-Tool!$D$64,Tool!E91),\"\")))","v":""},{"$f":"IF(C37=\"\",\"\",IF(B38=\"\",$C$2,IF((D36-$C$9)>=$C$2,\"\",IF(Tool!E91<>\"\",IF(AND($C$2>=(Tool!E92-Tool!$D$64),(Tool!E93-Tool!$D$64)>=(Tool!E92-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E92-Tool!$D$64,Tool!E92),$C$2),\"\"))))","v":""},{"$f":"IF(C37=\"\",\"\",IF(B37<>\"\",IF(Tool!N92=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E37=\"Flat\",IF(Tool!I92>Tool!G92,0,IF(Tool!G92>0,Tool!G92+J37,\"\")),\"\"))","v":""},{"$f":"IF(E37=\"Flat\",IF(Tool!H92>0,Tool!H92,\"\"),\"\")","v":""},{"$f":"IF(E37=\"Flat\",IF(Tool!I92>Tool!G92,Tool!G92,IF(Tool!I92>=0,Tool!I92)),\"\")","v":""},{"$f":"IF(E37=\"Flat\",Tool!O92,\"\")","v":""},{"$f":"IF(AND(K37=\"Urban/C&G\",E37=\"Flat\",Tool!L92=\"Both Sides\",Tool!M92=\"Both Sides\"),Tool!$M$62*2,IF(AND(K37=\"Urban/C&G\",E37=\"Flat\",Tool!L92=\"Both Sides\",Tool!M92=\"One Side\"),Tool!$M$62,IF(AND(K37=\"Urban/C&G\",E37=\"Flat\",Tool!L92=\"One Side\",Tool!M92=\"Both Sides\"),Tool!$M$62,IF(AND(K37=\"Urban/C&G\",E37=\"Flat\",Tool!L92=\"One Side\",Tool!M92=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E37=\"Flat\",Tool!K92,\"\")","v":""},{"$f":"IF(E37<>\"\",Drainage!G74,\"\")","v":""},"",{"$f":"IF(AND(F37=H37,G37=\"\"),\"\",VLOOKUP(Tool!P92,$AM$4:$AN$9,2,0))","v":""},"","","","Segments","Begin (mi)","End (mi)","Terrain Type","Inside Shldr. Width (ft)","Interior Width (ft)","Median Type","Length",null,"Roadway Terrain Summary"]
[null,{"$f":"IF(E7=30,30,\"\")","v":""},{"$f":"IF(D37>=$C$2,\"\",IF($C$2<(Tool!E92-Tool!$D$64),\"\",IF(Tool!D93<>\"\",IF(Tool!$D$64<>0,Tool!E92-Tool!$D$64,Tool!E92),\"\")))","v":""},{"$f":"IF(C38=\"\",\"\",IF(B39=\"\",$C$2,IF((D37-$C$9)>=$C$2,\"\",IF(Tool!E92<>\"\",IF(AND($C$2>=(Tool!E93-Tool!$D$64),(Tool!E94-Tool!$D$64)>=(Tool!E93-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E93-Tool!$D$64,Tool!E93),$C$2),\"\"))))","v":""},{"$f":"IF(C38=\"\",\"\",IF(B38<>\"\",IF(Tool!N93=Tool!$E$7,\"Flat\",\"\"),\"\"))","v":""},{"$f":"(IF(E38=\"Flat\",IF(Tool!I93>Tool!G93,0,IF(Tool!G93>0,Tool!G93+J38,\"\")),\"\"))","v":""},{"$f":"IF(E38=\"Flat\",IF(Tool!H93>0,Tool!H93,\"\"),\"\")","v":""},{"$f":"IF(E38=\"Flat\",IF(Tool!I93>Tool!G93,Tool!G93,IF(Tool!I93>=0,Tool!I93)),\"\")","v":""},{"$f":"IF(E38=\"Flat\",Tool!O93,\"\")","v":""},{"$f":"IF(AND(K38=\"Urban/C&G\",E38=\"Flat\",Tool!L93=\"Both Sides\",Tool!M93=\"Both Sides\"),Tool!$M$62*2,IF(AND(K38=\"Urban/C&G\",E38=\"Flat\",Tool!L93=\"Both Sides\",Tool!M93=\"One Side\"),Tool!$M$62,IF(AND(K38=\"Urban/C&G\",E38=\"Flat\",Tool!L93=\"One Side\",Tool!M93=\"Both Sides\"),Tool!$M$62,IF(AND(K38=\"Urban/C&G\",E38=\"Flat\",Tool!L93=\"One Side\",Tool!M93=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E38=\"Flat\",Tool!K93,\"\")","v":""},{"$f":"IF(E38<>\"\",Drainage!G75,\"\")","v":""},"",{"$f":"IF(AND(F38=H38,G38=\"\"),\"\",VLOOKUP(Tool!P93,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S36>=1,S36<=20),1,\"\")","v":1},{"$f":"IF(Tool!D98<>\"\",IF(R9<>\"\",IF(Tool!D98=0,Tool!D98,Tool!D98-Tool!D98),\"\"),\"\")","v":""},{"$f":"IF(Tool!E98<>\"\",IF(R38=1,IF($C$2<(Tool!E98-Tool!$D$98),$C$2,IF(Tool!D98<>0,(Tool!E98-Tool!D98),Tool!E98)),\"\"),\"\")","v":""},{"$f":"IF(R38<>\"\",IF(Tool!H98=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U38=\"Rolling\",Tool!I98>0),Tool!I98,\"\")","v":""},{"$f":"IF(U38=\"Rolling\",IF(Tool!J98>0,IF(Tool!F98=\"Barrier Wall\",3,IF(Tool!F98=\"Depressed Grass\",Tool!J98*0.5,Tool!J98)),\"\"),\"\")","v":""},{"$f":"IF(R9<>\"\",IF(U38=\"Rolling\",Tool!F98,\"\"),\"\")","v":""},{"$f":"IF(U38=\"Rolling\",T38-S38,\"\")","v":""},null,null,"Roadway Length","Percent Type","Length - Both Sides","Length - One Side","Rural - Slope Width","Average","Additional Width Urban","Average"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(S36>=2,S36<=20),2,\"\")","v":""},{"$f":"IF(R10<>\"\",IF(T9>=$C$2,\"\",IF($C$2<(Tool!E98-Tool!$D$98),\"\",IF(Tool!D99<>\"\",IF(Tool!$D$98<>0,Tool!E98-Tool!$D$98,Tool!E98),\"\"))),\"\")","v":""},{"$f":"IF(S39=\"\",\"\",IF(R10=\"\",\"\",IF(Tool!E98<>\"\",IF(AND($C$2>=(Tool!E99-Tool!$D$98),(Tool!E100-Tool!$D$98)>=(Tool!E99-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E99-Tool!$D$98,Tool!E99),$C$2),\"\")))","v":""},{"$f":"IF(R39<>\"\",IF(Tool!H99=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U39=\"Rolling\",Tool!I99>0),Tool!I99,\"\")","v":""},{"$f":"IF(U39=\"Rolling\",IF(Tool!J99>0,IF(Tool!F99=\"Barrier Wall\",3,IF(Tool!F99=\"Depressed Grass\",Tool!J99*0.5,Tool!J99)),\"\"),\"\")","v":""},{"$f":"IF(R10<>\"\",IF(U39=\"Rolling\",Tool!F99,\"\"),\"\")","v":""},{"$f":"IF(U39=\"Rolling\",T39-S39,\"\")","v":""},null,"Flat:",{"$f":"AB32","v":0},{"$f":"IF(SUM($AB$39:$AB$42)>0,AB39/SUM($AB$39:$AB$42),0)","v":0},{"$f":"C41","v":0},{"$f":"C40","v":0},{"$f":"AG25*9","v":27},{"$f":"AC39*AF39+AC40*AF40+AC41*AF41+AC42*AF42","v":0},{"$f":"AG25*6","v":18},{"$f":"AC39*AH39+AC40*AH40+AC41*AH41+AC42*AH42","v":0}]
[null,"Rural - Length - One Side",{"$f":"SUMIFS(Q9:Q38,K9:K38,\"Rural/Ditch\",I9:I38,\"One Side\")","v":0},null,"Sidewalk Length - Flat:",{"$f":"SUMPRODUCT(L9:L38,Q9:Q38)","v":0},null,"Avg. Rd. Width:",{"$f":"IF(SUM(Q9:Q38),SUMPRODUCT(F9:F38,Q9:Q38)/SUM(Q9:Q38),0)","v":0},null,null,"Rural - Slope Rate - One Side:",{"$f":"IFERROR(SUMIFS(O9:O38,I9:I38,\"One Side\",K9:K38,\"Rural/Ditch\")/SUMIFS(M9:M38,I9:I38,\"One Side\",K9:K38,\"Rural/Ditch\"),0)","v":0},null,"Guardrail Length",{"$f":"SUM(P9:P38)","v":0},null,{"$f":"IF(AND(S36>=3,S36<=20),3,\"\")","v":""},{"$f":"IF(R11<>\"\",IF(T10>=$C$2,\"\",IF($C$2<(Tool!E99-Tool!$D$98),\"\",IF(Tool!D100<>\"\",IF(Tool!$D$98<>0,Tool!E99-Tool!$D$98,Tool!E99),\"\"))),\"\")","v":""},{"$f":"IF(S40=\"\",\"\",IF(R11=\"\",\"\",IF(Tool!E99<>\"\",IF(AND($C$2>=(Tool!E100-Tool!$D$98),(Tool!E101-Tool!$D$98)>=(Tool!E100-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E100-Tool!$D$98,Tool!E100),$C$2),\"\")))","v":""},{"$f":"IF(R40<>\"\",IF(Tool!H100=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U40=\"Rolling\",Tool!I100>0),Tool!I100,\"\")","v":""},{"$f":"IF(U40=\"Rolling\",IF(Tool!J100>0,IF(Tool!F100=\"Barrier Wall\",3,IF(Tool!F100=\"Depressed Grass\",Tool!J100*0.5,Tool!J100)),\"\"),\"\")","v":""},{"$f":"IF(R11<>\"\",IF(U40=\"Rolling\",Tool!F100,\"\"),\"\")","v":""},"",null,"Rolling:",{"$f":"AB33","v":0},{"$f":"IF(SUM($AB$39:$AB$42)>0,AB40/SUM($AB$39:$AB$42),0)","v":0},{"$f":"C80","v":0},{"$f":"C79","v":0},{"$f":"AG26*9","v":44.824222418482869},null,{"$f":"AG26*6","v":29.882814945655248}]
[null,"Rural - Length - Both Sides",{"$f":"SUMIFS(Q9:Q38,K9:K38,\"Rural/Ditch\",I9:I38,\"Both Sides\")","v":0},null,"Rural Slope Length - One Sides:",{"$f":"SUMIFS(M9:M38,I9:I38,\"One Side\",K9:K38,\"Rural/Ditch\")","v":0},null,"Avg. Retained Width:",{"$f":"IF(SUM(Q9:Q38)>0,SUMPRODUCT(H9:H38,Q9:Q38)/SUM(Q9:Q38),0)","v":0},null,null,"Rural - Slope Rate - Both Sides:",{"$f":"IFERROR(SUMIFS(O9:O38,I9:I38,\"Both Sides\",K9:K38,\"Rural/Ditch\")/SUMIFS(M9:M38,I9:I38,\"Both Sides\",K9:K38,\"Rural/Ditch\"),0)","v":0},null,null,null,null,{"$f":"IF(AND(S36>=4,S36<=20),4,\"\")","v":""},{"$f":"IF(R12<>\"\",IF(T11>=$C$2,\"\",IF($C$2<(Tool!E100-Tool!$D$98),\"\",IF(Tool!D101<>\"\",IF(Tool!$D$98<>0,Tool!E100-Tool!$D$98,Tool!E100),\"\"))),\"\")","v":""},{"$f":"IF(S41=\"\",\"\",IF(R12=\"\",\"\",IF(Tool!E100<>\"\",IF(AND($C$2>=(Tool!E101-Tool!$D$98),(Tool!E102-Tool!$D$98)>=(Tool!E101-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E101-Tool!$D$98,Tool!E101),$C$2),\"\")))","v":""},{"$f":"IF(R41<>\"\",IF(Tool!H101=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U41=\"Rolling\",Tool!I101>0),Tool!I101,\"\")","v":""},{"$f":"IF(U41=\"Rolling\",IF(Tool!J101>0,IF(Tool!F101=\"Barrier Wall\",3,IF(Tool!F101=\"Depressed Grass\",Tool!J101*0.5,Tool!J101)),\"\"),\"\")","v":""},{"$f":"IF(R12<>\"\",IF(U41=\"Rolling\",Tool!F101,\"\"),\"\")","v":""},"",null,"Mountainous:",{"$f":"AB34","v":0},{"$f":"IF(SUM($AB$39:$AB$42)>0,AB41/SUM($AB$39:$AB$42),0)","v":0},{"$f":"C120","v":0},{"$f":"C119","v":0},{"$f":"AG27*9","v":81},null,{"$f":"AG27*6","v":54}]
[null,"Urban - Length - One Side",{"$f":"SUMIFS(Q9:Q38,K9:K38,\"Urban/C&G\",I9:I38,\"One Side\")","v":0},null,"Rural Slope Length - Both Sides:",{"$f":"SUMIFS(M9:M38,I9:I38,\"Both Sides\",K9:K38,\"Rural/Ditch\")*2","v":0},null,"Avg. Shoulder Width:",{"$f":"IF(SUM(Q9:Q38),SUMPRODUCT(G9:G38,Q9:Q38)/SUM(Q9:Q38),0)","v":0},null,null,"Urban - Slope Rate - One Side:",{"$f":"IFERROR(SUMIFS(O9:O38,I9:I38,\"One Side\",K9:K38,\"Urban/C&G\")/SUMIFS(M9:M38,I9:I38,\"One Side\",K9:K38,\"Urban/C&G\"),0)","v":0},null,null,null,null,{"$f":"IF(AND(S36>=5,S36<=20),5,\"\")","v":""},{"$f":"IF(R13<>\"\",IF(T12>=$C$2,\"\",IF($C$2<(Tool!E101-Tool!$D$98),\"\",IF(Tool!D102<>\"\",IF(Tool!$D$98<>0,Tool!E101-Tool!$D$98,Tool!E101),\"\"))),\"\")","v":""},{"$f":"IF(S42=\"\",\"\",IF(R13=\"\",\"\",IF(Tool!E101<>\"\",IF(AND($C$2>=(Tool!E102-Tool!$D$98),(Tool!E103-Tool!$D$98)>=(Tool!E102-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E102-Tool!$D$98,Tool!E102),$C$2),\"\")))","v":""},{"$f":"IF(R42<>\"\",IF(Tool!H102=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U42=\"Rolling\",Tool!I102>0),Tool!I102,\"\")","v":""},{"$f":"IF(U42=\"Rolling\",IF(Tool!J102>0,IF(Tool!F102=\"Barrier Wall\",3,IF(Tool!F102=\"Depressed Grass\",Tool!J102*0.5,Tool!J102)),\"\"),\"\")","v":""},{"$f":"IF(R13<>\"\",IF(U42=\"Rolling\",Tool!F102,\"\"),\"\")","v":""},"",null,"Heavy Mountainous:",{"$f":"AB35","v":0},{"$f":"IF(SUM($AB$39:$AB$42)>0,AB42/SUM($AB$39:$AB$42),0)","v":0},{"$f":"C160","v":0},{"$f":"C159","v":0},{"$f":"AG28*9","v":144.16235327636491},null,{"$f":"AG28*6","v":96.108235517576603}]
[null,"Urban - Length - Both Sides",{"$f":"SUMIFS(Q9:Q38,K9:K38,\"Urban/C&G\",I9:I38,\"Both Sides\")","v":0},null,"Urban Slope Length - One Sides:",{"$f":"SUMIFS(M9:M38,I9:I38,\"One Side\",K9:K38,\"Urban/C&G\")","v":0},null,"Avg. Fill Width:",{"$f":"IF(I40>=I41,(I40+I42*2)-I41,0)","v":0},null,null,"Urban - Slope Rate - Both Sides:",{"$f":"IFERROR(SUMIFS(O9:O38,I9:I38,\"Both Sides\",K9:K38,\"Urban/C&G\")/SUMIFS(M9:M38,I9:I38,\"Both Sides\",K9:K38,\"Urban/C&G\"),0)","v":0},null,null,null,null,{"$f":"IF(AND(S36>=6,S36<=20),6,\"\")","v":""},{"$f":"IF(R14<>\"\",IF(T13>=$C$2,\"\",IF($C$2<(Tool!E102-Tool!$D$98),\"\",IF(Tool!D103<>\"\",IF(Tool!$D$98<>0,Tool!E102-Tool!$D$98,Tool!E102),\"\"))),\"\")","v":""},{"$f":"IF(S43=\"\",\"\",IF(R14=\"\",\"\",IF(Tool!E102<>\"\",IF(AND($C$2>=(Tool!E103-Tool!$D$98),(Tool!E104-Tool!$D$98)>=(Tool!E103-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E103-Tool!$D$98,Tool!E103),$C$2),\"\")))","v":""},{"$f":"IF(R43<>\"\",IF(Tool!H103=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U43=\"Rolling\",Tool!I103>0),Tool!I103,\"\")","v":""},{"$f":"IF(U43=\"Rolling\",IF(Tool!J103>0,IF(Tool!F103=\"Barrier Wall\",3,IF(Tool!F103=\"Depressed Grass\",Tool!J103*0.5,Tool!J103)),\"\"),\"\")","v":""},{"$f":"IF(R14<>\"\",IF(U43=\"Rolling\",Tool!F103,\"\"),\"\")","v":""},""]
[null,null,null,null,"Urban Slope Length - Both Sides:",{"$f":"SUMIFS(M9:M38,I9:I38,\"Both Sides\",K9:K38,\"Urban/C&G\")*2","v":0},null,"Avg. Fill Area:",{"$f":"I43*SUM(Q9:Q38)*5280","v":0},null,null,null,null,null,null,null,null,{"$f":"IF(AND(S36>=7,S36<=20),7,\"\")","v":""},{"$f":"IF(R15<>\"\",IF(T14>=$C$2,\"\",IF($C$2<(Tool!E103-Tool!$D$98),\"\",IF(Tool!D104<>\"\",IF(Tool!$D$98<>0,Tool!E103-Tool!$D$98,Tool!E103),\"\"))),\"\")","v":""},{"$f":"IF(S44=\"\",\"\",IF(R15=\"\",\"\",IF(Tool!E103<>\"\",IF(AND($C$2>=(Tool!E104-Tool!$D$98),(Tool!E105-Tool!$D$98)>=(Tool!E104-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E104-Tool!$D$98,Tool!E104),$C$2),\"\")))","v":""},{"$f":"IF(R44<>\"\",IF(Tool!H104=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U44=\"Rolling\",Tool!I104>0),Tool!I104,\"\")","v":""},{"$f":"IF(U44=\"Rolling\",IF(Tool!J104>0,IF(Tool!F104=\"Barrier Wall\",3,IF(Tool!F104=\"Depressed Grass\",Tool!J104*0.5,Tool!J104)),\"\"),\"\")","v":""},{"$f":"IF(R15<>\"\",IF(U44=\"Rolling\",Tool!F104,\"\"),\"\")","v":""},"",null,null,"Length","Add. Width","Percent Type","Avg. Add. Slope Width","Avg. Facility Width","Avg. Slope Area","Average Depth","Volume Slope"]
[null,"Rolling Terrain",null,null,null,null,null,"Length:",{"$f":"SUM(Q9:Q38)","v":0},null,null,null,null,null,null,null,null,{"$f":"IF(AND(S36>=8,S36<=20),8,\"\")","v":""},{"$f":"IF(R16<>\"\",IF(T15>=$C$2,\"\",IF($C$2<(Tool!E104-Tool!$D$98),\"\",IF(Tool!D105<>\"\",IF(Tool!$D$98<>0,Tool!E104-Tool!$D$98,Tool!E104),\"\"))),\"\")","v":""},{"$f":"IF(S45=\"\",\"\",IF(R16=\"\",\"\",IF(Tool!E104<>\"\",IF(AND($C$2>=(Tool!E105-Tool!$D$98),(Tool!E106-Tool!$D$98)>=(Tool!E105-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E105-Tool!$D$98,Tool!E105),$C$2),\"\")))","v":""},{"$f":"IF(R45<>\"\",IF(Tool!H105=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U45=\"Rolling\",Tool!I105>0),Tool!I105,\"\")","v":""},{"$f":"IF(U45=\"Rolling\",IF(Tool!J105>0,IF(Tool!F105=\"Barrier Wall\",3,IF(Tool!F105=\"Depressed Grass\",Tool!J105*0.5,Tool!J105)),\"\"),\"\")","v":""},{"$f":"IF(R16<>\"\",IF(U45=\"Rolling\",Tool!F105,\"\"),\"\")","v":""},"",null,"Average Ditch Length:",{"$f":"Drainage!F41+Drainage!E79","v":0},{"$f":"AG39","v":0},{"$f":"IF($C$2>0,AB45/($C$2*2),0)","v":0},{"$f":"(AC45*AD45)+(AC46*AD46)","v":0},{"$f":"Drainage!K25","v":0},{"$f":"IF(SUM(AB25:AB28)<=0,0,AE45*C2*5280*2)","v":0},{"$f":"(AG25*AC39)+(AG26*AC40)+(AG27*AC41)+(AG28*AC42)","v":0},{"$f":"SUM(AD57:AD64)+SUM(AH57:AH64)","v":0}]
[null,"Segments:",null,null,{"$f":"Tool!$J$61","v":1},null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(S36>=9,S36<=20),9,\"\")","v":""},{"$f":"IF(R17<>\"\",IF(T16>=$C$2,\"\",IF($C$2<(Tool!E105-Tool!$D$98),\"\",IF(Tool!D106<>\"\",IF(Tool!$D$98<>0,Tool!E105-Tool!$D$98,Tool!E105),\"\"))),\"\")","v":""},{"$f":"IF(S46=\"\",\"\",IF(R17=\"\",\"\",IF(Tool!E105<>\"\",IF(AND($C$2>=(Tool!E106-Tool!$D$98),(Tool!E107-Tool!$D$98)>=(Tool!E106-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E106-Tool!$D$98,Tool!E106),$C$2),\"\")))","v":""},{"$f":"IF(R46<>\"\",IF(Tool!H106=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U46=\"Rolling\",Tool!I106>0),Tool!I106,\"\")","v":""},{"$f":"IF(U46=\"Rolling\",IF(Tool!J106>0,IF(Tool!F106=\"Barrier Wall\",3,IF(Tool!F106=\"Depressed Grass\",Tool!J106*0.5,Tool!J106)),\"\"),\"\")","v":""},{"$f":"IF(R17<>\"\",IF(U46=\"Rolling\",Tool!F106,\"\"),\"\")","v":""},"",null,"Average C&G Length:",{"$f":"Drainage!E79","v":0},{"$f":"AI39","v":0},{"$f":"IF($C$2>0,AB46/($C$2*2),0)","v":0}]
[null,"Segments","Begin (mi)","End (mi)","Terrain Type","Total Pavement Width (ft)","Outside Shldr Width (ft)","Existing Pavement Width","Widen to One Side or Both?","Grass Strip","Rural/Urban","Sidewalks","Slope Length","Slope Rate","Slope Area (ft-mi)","Guardrail Length","Length",{"$f":"IF(AND(S36>=10,S36<=20),10,\"\")","v":""},{"$f":"IF(R18<>\"\",IF(T17>=$C$2,\"\",IF($C$2<(Tool!E106-Tool!$D$98),\"\",IF(Tool!D107<>\"\",IF(Tool!$D$98<>0,Tool!E106-Tool!$D$98,Tool!E106),\"\"))),\"\")","v":""},{"$f":"IF(S47=\"\",\"\",IF(R18=\"\",\"\",IF(Tool!E106<>\"\",IF(AND($C$2>=(Tool!E107-Tool!$D$98),(Tool!E108-Tool!$D$98)>=(Tool!E107-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E107-Tool!$D$98,Tool!E107),$C$2),\"\")))","v":""},{"$f":"IF(R47<>\"\",IF(Tool!H107=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U47=\"Rolling\",Tool!I107>0),Tool!I107,\"\")","v":""},{"$f":"IF(U47=\"Rolling\",IF(Tool!J107>0,IF(Tool!F107=\"Barrier Wall\",3,IF(Tool!F107=\"Depressed Grass\",Tool!J107*0.5,Tool!J107)),\"\"),\"\")","v":""},{"$f":"IF(R18<>\"\",IF(U47=\"Rolling\",Tool!F107,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E46>=1,E46<=30),1,\"\")","v":1},{"$f":"IF(Tool!D64<>\"\",IF(B9<>\"\",IF(Tool!D64=0,Tool!D64,Tool!D64-Tool!D64),\"\"),\"\")","v":""},{"$f":"IF(C48=\"\",\"\",IF((Tool!E65-Tool!D64)<(Tool!E64-Tool!D64),C2,IF(B9<>\"\",IF(Tool!E64<>\"\",IF(AND(B10=\"\",Tool!E64-Tool!D64<$C$2),$C$2,IF(B9=1,IF($C$2<(Tool!E64-Tool!$D$64),$C$2,IF(Tool!D64<>0,(Tool!E64-Tool!D64),Tool!E64)),\"\")),\"\"),\"\")))","v":""},{"$f":"IF(C48=\"\",\"\",IF(B48<>\"\",IF(Tool!N64=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E48=\"Rolling\",IF(Tool!I64>Tool!G64,0,IF(Tool!G64>0,Tool!G64+J48,\"\")),\"\")","v":""},{"$f":"IF(E48=\"Rolling\",IF(Tool!H64>0,Tool!H64,\"\"),\"\")","v":""},{"$f":"IF(E48=\"Rolling\",IF(Tool!I64>Tool!G64,Tool!G64,IF(Tool!I64>=0,Tool!I64)),\"\")","v":""},{"$f":"IF(E48=\"Rolling\",Tool!O64,\"\")","v":""},{"$f":"IF(AND(K48=\"Urban/C&G\",E48=\"Rolling\",Tool!L64=\"Both Sides\",Tool!M64=\"Both Sides\"),Tool!$M$62*2,IF(AND(K48=\"Urban/C&G\",E48=\"Rolling\",Tool!L64=\"Both Sides\",Tool!M64=\"One Side\"),Tool!$M$62,IF(AND(K48=\"Urban/C&G\",E48=\"Rolling\",Tool!L64=\"One Side\",Tool!M64=\"Both Sides\"),Tool!$M$62,IF(AND(K48=\"Urban/C&G\",E48=\"Rolling\",Tool!L64=\"One Side\",Tool!M64=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E48=\"Rolling\",Tool!K64,\"\")","v":""},{"$f":"IF(E48<>\"\",Drainage!G46,\"\")","v":""},{"$f":"IF(AND(F48=H48,G48=\"\"),\"\",D48-C48)","v":""},{"$f":"IF(AND(F48=H48,G48=\"\"),\"\",VLOOKUP(Tool!P64,$AM$4:$AN$9,2,0))","v":""},{"$f":"IF(AND(F48=H48,G48=\"\"),\"\",M48*N48)","v":""},{"$f":"IF(AND(N48=4,I48=\"Both Sides\"),M48*0.2,IF(AND(N48=4,I48=\"One Side\"),M48*0.1,IF(AND(N48=3,I48=\"One Side\"),M48*0.3,IF(AND(N48=3,I48=\"Both Sides\"),M48*0.5,IF(AND(N48=2,I48=\"One Side\"),M48*0.5,IF(AND(N48=2,I48=\"Both Sides\"),M48,IF(AND(N48=1,I48=\"One Side\"),M48*0.75,IF(AND(N48=1,I48=\"Both Sides\"),M48,\"\"))))))))","v":""},{"$f":"IF(E48=\"Rolling\",D48-C48,\"\")","v":""},{"$f":"IF(AND(S36>=11,S36<=20),11,\"\")","v":""},{"$f":"IF(R19<>\"\",IF(T18>=$C$2,\"\",IF($C$2<(Tool!E107-Tool!$D$98),\"\",IF(Tool!D108<>\"\",IF(Tool!$D$98<>0,Tool!E107-Tool!$D$98,Tool!E107),\"\"))),\"\")","v":""},{"$f":"IF(S48=\"\",\"\",IF(R19=\"\",\"\",IF(Tool!E107<>\"\",IF(AND($C$2>=(Tool!E108-Tool!$D$98),(Tool!E109-Tool!$D$98)>=(Tool!E108-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E108-Tool!$D$98,Tool!E108),$C$2),\"\")))","v":""},{"$f":"IF(R48<>\"\",IF(Tool!H108=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U48=\"Rolling\",Tool!I108>0),Tool!I108,\"\")","v":""},{"$f":"IF(U48=\"Rolling\",IF(Tool!J108>0,IF(Tool!F108=\"Barrier Wall\",3,IF(Tool!F108=\"Depressed Grass\",Tool!J108*0.5,Tool!J108)),\"\"),\"\")","v":""},{"$f":"IF(R19<>\"\",IF(U48=\"Rolling\",Tool!F108,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E46>=2,E46<=30),2,\"\")","v":""},{"$f":"IF(D9>=$C$2,\"\",IF($C$2<(Tool!E64-Tool!$D$64),\"\",IF(Tool!D65<>\"\",IF(Tool!$D$64<>0,Tool!E64-Tool!$D$64,Tool!E64),\"\")))","v":""},{"$f":"IF(C10=\"\",\"\",IF(B11=\"\",$C$2,IF((D9-$C$9)>=$C$2,\"\",IF(Tool!E64<>\"\",IF(AND($C$2>=(Tool!E65-Tool!$D$64),(Tool!E66-Tool!$D$64)>=(Tool!E65-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E65-Tool!$D$64,Tool!E65),$C$2),\"\"))))","v":""},{"$f":"IF(C49=\"\",\"\",IF(B49<>\"\",IF(Tool!N65=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E49=\"Rolling\",IF(Tool!I65>Tool!G65,0,IF(Tool!G65>0,Tool!G65+J49,\"\")),\"\")","v":""},{"$f":"IF(E49=\"Rolling\",IF(Tool!H65>0,Tool!H65,\"\"),\"\")","v":""},{"$f":"IF(E49=\"Rolling\",IF(Tool!I65>Tool!G65,Tool!G65,IF(Tool!I65>=0,Tool!I65)),\"\")","v":""},{"$f":"IF(E49=\"Rolling\",Tool!O65,\"\")","v":""},{"$f":"IF(AND(K49=\"Urban/C&G\",E49=\"Rolling\",Tool!L65=\"Both Sides\",Tool!M65=\"Both Sides\"),Tool!$M$62*2,IF(AND(K49=\"Urban/C&G\",E49=\"Rolling\",Tool!L65=\"Both Sides\",Tool!M65=\"One Side\"),Tool!$M$62,IF(AND(K49=\"Urban/C&G\",E49=\"Rolling\",Tool!L65=\"One Side\",Tool!M65=\"Both Sides\"),Tool!$M$62,IF(AND(K49=\"Urban/C&G\",E49=\"Rolling\",Tool!L65=\"One Side\",Tool!M65=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E49=\"Rolling\",Tool!K65,\"\")","v":""},{"$f":"IF(E49<>\"\",Drainage!G47,\"\")","v":""},"",{"$f":"IF(AND(F49=H49,G49=\"\"),\"\",VLOOKUP(Tool!P65,$AM$4:$AN$9,2,0))","v":""},"",{"$f":"IF(AND(N49=4,I49=\"Both Sides\"),M49*0.2,IF(AND(N49=4,I49=\"One Side\"),M49*0.1,IF(AND(N49=3,I49=\"One Side\"),M49*0.3,IF(AND(N49=3,I49=\"Both Sides\"),M49*0.5,IF(AND(N49=2,I49=\"One Side\"),M49*0.5,IF(AND(N49=2,I49=\"Both Sides\"),M49,IF(AND(N49=1,I49=\"One Side\"),M49*0.75,IF(AND(N49=1,I49=\"Both Sides\"),M49,\"\"))))))))","v":""},"",{"$f":"IF(AND(S36>=12,S36<=20),12,\"\")","v":""},{"$f":"IF(R20<>\"\",IF(T19>=$C$2,\"\",IF($C$2<(Tool!E108-Tool!$D$98),\"\",IF(Tool!D109<>\"\",IF(Tool!$D$98<>0,Tool!E108-Tool!$D$98,Tool!E108),\"\"))),\"\")","v":""},{"$f":"IF(S49=\"\",\"\",IF(R20=\"\",\"\",IF(Tool!E108<>\"\",IF(AND($C$2>=(Tool!E109-Tool!$D$98),(Tool!E110-Tool!$D$98)>=(Tool!E109-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E109-Tool!$D$98,Tool!E109),$C$2),\"\")))","v":""},{"$f":"IF(R49<>\"\",IF(Tool!H109=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U49=\"Rolling\",Tool!I109>0),Tool!I109,\"\")","v":""},{"$f":"IF(U49=\"Rolling\",IF(Tool!J109>0,IF(Tool!F109=\"Barrier Wall\",3,IF(Tool!F109=\"Depressed Grass\",Tool!J109*0.5,Tool!J109)),\"\"),\"\")","v":""},{"$f":"IF(R20<>\"\",IF(U49=\"Rolling\",Tool!F109,\"\"),\"\")","v":""},"",null,"Guardrail Factor"]
[null,{"$f":"IF(AND(E46>=3,E46<=30),3,\"\")","v":""},{"$f":"IF(D10>=$C$2,\"\",IF($C$2<(Tool!E65-Tool!$D$64),\"\",IF(Tool!D66<>\"\",IF(Tool!$D$64<>0,Tool!E65-Tool!$D$64,Tool!E65),\"\")))","v":""},{"$f":"IF(C11=\"\",\"\",IF(B12=\"\",$C$2,IF((D10-$C$9)>=$C$2,\"\",IF(Tool!E65<>\"\",IF(AND($C$2>=(Tool!E66-Tool!$D$64),(Tool!E67-Tool!$D$64)>=(Tool!E66-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E66-Tool!$D$64,Tool!E66),$C$2),\"\"))))","v":""},{"$f":"IF(C50=\"\",\"\",IF(B50<>\"\",IF(Tool!N66=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E50=\"Rolling\",IF(Tool!I66>Tool!G66,0,IF(Tool!G66>0,Tool!G66+J50,\"\")),\"\")","v":""},{"$f":"IF(E50=\"Rolling\",IF(Tool!H66>0,Tool!H66,\"\"),\"\")","v":""},{"$f":"IF(E50=\"Rolling\",IF(Tool!I66>Tool!G66,Tool!G66,IF(Tool!I66>=0,Tool!I66)),\"\")","v":""},{"$f":"IF(E50=\"Rolling\",Tool!O66,\"\")","v":""},{"$f":"IF(AND(K50=\"Urban/C&G\",E50=\"Rolling\",Tool!L66=\"Both Sides\",Tool!M66=\"Both Sides\"),Tool!$M$62*2,IF(AND(K50=\"Urban/C&G\",E50=\"Rolling\",Tool!L66=\"Both Sides\",Tool!M66=\"One Side\"),Tool!$M$62,IF(AND(K50=\"Urban/C&G\",E50=\"Rolling\",Tool!L66=\"One Side\",Tool!M66=\"Both Sides\"),Tool!$M$62,IF(AND(K50=\"Urban/C&G\",E50=\"Rolling\",Tool!L66=\"One Side\",Tool!M66=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E50=\"Rolling\",Tool!K66,\"\")","v":""},{"$f":"IF(E50<>\"\",Drainage!G48,\"\")","v":""},"",{"$f":"IF(AND(F50=H50,G50=\"\"),\"\",VLOOKUP(Tool!P66,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S36>=13,S36<=20),13,\"\")","v":""},{"$f":"IF(R21<>\"\",IF(T20>=$C$2,\"\",IF($C$2<(Tool!E109-Tool!$D$98),\"\",IF(Tool!D110<>\"\",IF(Tool!$D$98<>0,Tool!E109-Tool!$D$98,Tool!E109),\"\"))),\"\")","v":""},{"$f":"IF(S50=\"\",\"\",IF(R21=\"\",\"\",IF(Tool!E109<>\"\",IF(AND($C$2>=(Tool!E110-Tool!$D$98),(Tool!E111-Tool!$D$98)>=(Tool!E110-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E110-Tool!$D$98,Tool!E110),$C$2),\"\")))","v":""},{"$f":"IF(R50<>\"\",IF(Tool!H110=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U50=\"Rolling\",Tool!I110>0),Tool!I110,\"\")","v":""},{"$f":"IF(U50=\"Rolling\",IF(Tool!J110>0,IF(Tool!F110=\"Barrier Wall\",3,IF(Tool!F110=\"Depressed Grass\",Tool!J110*0.5,Tool!J110)),\"\"),\"\")","v":""},{"$f":"IF(R21<>\"\",IF(U50=\"Rolling\",Tool!F110,\"\"),\"\")","v":""},"",null,"Rolling (50% Factor)",{"$f":"IF(SUM($AI$25:$AI$28)>0,(AI26/SUM($AI$25:$AI$28))*0.5,0)","v":0},null,{"$f":"\"4:1\"","v":"4:1"}]
[null,{"$f":"IF(AND(E46>=4,E46<=30),4,\"\")","v":""},{"$f":"IF(D11>=$C$2,\"\",IF($C$2<(Tool!E66-Tool!$D$64),\"\",IF(Tool!D67<>\"\",IF(Tool!$D$64<>0,Tool!E66-Tool!$D$64,Tool!E66),\"\")))","v":""},{"$f":"IF(C12=\"\",\"\",IF(B13=\"\",$C$2,IF((D11-$C$9)>=$C$2,\"\",IF(Tool!E66<>\"\",IF(AND($C$2>=(Tool!E67-Tool!$D$64),(Tool!E68-Tool!$D$64)>=(Tool!E67-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E67-Tool!$D$64,Tool!E67),$C$2),\"\"))))","v":""},{"$f":"IF(C51=\"\",\"\",IF(B51<>\"\",IF(Tool!N67=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E51=\"Rolling\",IF(Tool!I67>Tool!G67,0,IF(Tool!G67>0,Tool!G67+J51,\"\")),\"\")","v":""},{"$f":"IF(E51=\"Rolling\",IF(Tool!H67>0,Tool!H67,\"\"),\"\")","v":""},{"$f":"IF(E51=\"Rolling\",IF(Tool!I67>Tool!G67,Tool!G67,IF(Tool!I67>=0,Tool!I67)),\"\")","v":""},{"$f":"IF(E51=\"Rolling\",Tool!O67,\"\")","v":""},{"$f":"IF(AND(K51=\"Urban/C&G\",E51=\"Rolling\",Tool!L67=\"Both Sides\",Tool!M67=\"Both Sides\"),Tool!$M$62*2,IF(AND(K51=\"Urban/C&G\",E51=\"Rolling\",Tool!L67=\"Both Sides\",Tool!M67=\"One Side\"),Tool!$M$62,IF(AND(K51=\"Urban/C&G\",E51=\"Rolling\",Tool!L67=\"One Side\",Tool!M67=\"Both Sides\"),Tool!$M$62,IF(AND(K51=\"Urban/C&G\",E51=\"Rolling\",Tool!L67=\"One Side\",Tool!M67=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E51=\"Rolling\",Tool!K67,\"\")","v":""},{"$f":"IF(E51<>\"\",Drainage!G49,\"\")","v":""},"",{"$f":"IF(AND(F51=H51,G51=\"\"),\"\",VLOOKUP(Tool!P67,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S36>=14,S36<=20),14,\"\")","v":""},{"$f":"IF(R22<>\"\",IF(T21>=$C$2,\"\",IF($C$2<(Tool!E110-Tool!$D$98),\"\",IF(Tool!D111<>\"\",IF(Tool!$D$98<>0,Tool!E110-Tool!$D$98,Tool!E110),\"\"))),\"\")","v":""},{"$f":"IF(S51=\"\",\"\",IF(R22=\"\",\"\",IF(Tool!E110<>\"\",IF(AND($C$2>=(Tool!E111-Tool!$D$98),(Tool!E112-Tool!$D$98)>=(Tool!E111-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E111-Tool!$D$98,Tool!E111),$C$2),\"\")))","v":""},{"$f":"IF(R51<>\"\",IF(Tool!H111=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U51=\"Rolling\",Tool!I111>0),Tool!I111,\"\")","v":""},{"$f":"IF(U51=\"Rolling\",IF(Tool!J111>0,IF(Tool!F111=\"Barrier Wall\",3,IF(Tool!F111=\"Depressed Grass\",Tool!J111*0.5,Tool!J111)),\"\"),\"\")","v":""},{"$f":"IF(R22<>\"\",IF(U51=\"Rolling\",Tool!F111,\"\"),\"\")","v":""},"",null,"Mountainous (100% Factor)",{"$f":"IF(SUM($AI$25:$AI$28)>0,(AI27/SUM($AI$25:$AI$28))*1,0)","v":0},null,{"$f":"\"3:1\"","v":"3:1"}]
[null,{"$f":"IF(AND(E46>=5,E46<=30),5,\"\")","v":""},{"$f":"IF(D12>=$C$2,\"\",IF($C$2<(Tool!E67-Tool!$D$64),\"\",IF(Tool!D68<>\"\",IF(Tool!$D$64<>0,Tool!E67-Tool!$D$64,Tool!E67),\"\")))","v":""},{"$f":"IF(C13=\"\",\"\",IF(B14=\"\",$C$2,IF((D12-$C$9)>=$C$2,\"\",IF(Tool!E67<>\"\",IF(AND($C$2>=(Tool!E68-Tool!$D$64),(Tool!E69-Tool!$D$64)>=(Tool!E68-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E68-Tool!$D$64,Tool!E68),$C$2),\"\"))))","v":""},{"$f":"IF(C52=\"\",\"\",IF(B52<>\"\",IF(Tool!N68=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E52=\"Rolling\",IF(Tool!I68>Tool!G68,0,IF(Tool!G68>0,Tool!G68+J52,\"\")),\"\")","v":""},{"$f":"IF(E52=\"Rolling\",IF(Tool!H68>0,Tool!H68,\"\"),\"\")","v":""},{"$f":"IF(E52=\"Rolling\",IF(Tool!I68>Tool!G68,Tool!G68,IF(Tool!I68>=0,Tool!I68)),\"\")","v":""},{"$f":"IF(E52=\"Rolling\",Tool!O68,\"\")","v":""},{"$f":"IF(AND(K52=\"Urban/C&G\",E52=\"Rolling\",Tool!L68=\"Both Sides\",Tool!M68=\"Both Sides\"),Tool!$M$62*2,IF(AND(K52=\"Urban/C&G\",E52=\"Rolling\",Tool!L68=\"Both Sides\",Tool!M68=\"One Side\"),Tool!$M$62,IF(AND(K52=\"Urban/C&G\",E52=\"Rolling\",Tool!L68=\"One Side\",Tool!M68=\"Both Sides\"),Tool!$M$62,IF(AND(K52=\"Urban/C&G\",E52=\"Rolling\",Tool!L68=\"One Side\",Tool!M68=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E52=\"Rolling\",Tool!K68,\"\")","v":""},{"$f":"IF(E52<>\"\",Drainage!G50,\"\")","v":""},"",{"$f":"IF(AND(F52=H52,G52=\"\"),\"\",VLOOKUP(Tool!P68,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S36>=15,S36<=20),15,\"\")","v":""},{"$f":"IF(R23<>\"\",IF(T22>=$C$2,\"\",IF($C$2<(Tool!E111-Tool!$D$98),\"\",IF(Tool!D112<>\"\",IF(Tool!$D$98<>0,Tool!E111-Tool!$D$98,Tool!E111),\"\"))),\"\")","v":""},{"$f":"IF(S52=\"\",\"\",IF(R23=\"\",\"\",IF(Tool!E111<>\"\",IF(AND($C$2>=(Tool!E112-Tool!$D$98),(Tool!E113-Tool!$D$98)>=(Tool!E112-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E112-Tool!$D$98,Tool!E112),$C$2),\"\")))","v":""},{"$f":"IF(R52<>\"\",IF(Tool!H112=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U52=\"Rolling\",Tool!I112>0),Tool!I112,\"\")","v":""},{"$f":"IF(U52=\"Rolling\",IF(Tool!J112>0,IF(Tool!F112=\"Barrier Wall\",3,IF(Tool!F112=\"Depressed Grass\",Tool!J112*0.5,Tool!J112)),\"\"),\"\")","v":""},{"$f":"IF(R23<>\"\",IF(U52=\"Rolling\",Tool!F112,\"\"),\"\")","v":""},"",null,"HM  (125% Factor)",{"$f":"IF(SUM($AI$25:$AI$28)>0,(AI28/SUM($AI$25:$AI$28))*1.25,0)","v":0},null,{"$f":"\"2:1\"","v":"2:1"}]
[null,{"$f":"IF(AND(E46>=6,E46<=30),6,\"\")","v":""},{"$f":"IF(D13>=$C$2,\"\",IF($C$2<(Tool!E68-Tool!$D$64),\"\",IF(Tool!D69<>\"\",IF(Tool!$D$64<>0,Tool!E68-Tool!$D$64,Tool!E68),\"\")))","v":""},{"$f":"IF(C14=\"\",\"\",IF(B15=\"\",$C$2,IF((D13-$C$9)>=$C$2,\"\",IF(Tool!E68<>\"\",IF(AND($C$2>=(Tool!E69-Tool!$D$64),(Tool!E70-Tool!$D$64)>=(Tool!E69-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E69-Tool!$D$64,Tool!E69),$C$2),\"\"))))","v":""},{"$f":"IF(C53=\"\",\"\",IF(B53<>\"\",IF(Tool!N69=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E53=\"Rolling\",IF(Tool!I69>Tool!G69,0,IF(Tool!G69>0,Tool!G69+J53,\"\")),\"\")","v":""},{"$f":"IF(E53=\"Rolling\",IF(Tool!H69>0,Tool!H69,\"\"),\"\")","v":""},{"$f":"IF(E53=\"Rolling\",IF(Tool!I69>Tool!G69,Tool!G69,IF(Tool!I69>=0,Tool!I69)),\"\")","v":""},{"$f":"IF(E53=\"Rolling\",Tool!O69,\"\")","v":""},{"$f":"IF(AND(K53=\"Urban/C&G\",E53=\"Rolling\",Tool!L69=\"Both Sides\",Tool!M69=\"Both Sides\"),Tool!$M$62*2,IF(AND(K53=\"Urban/C&G\",E53=\"Rolling\",Tool!L69=\"Both Sides\",Tool!M69=\"One Side\"),Tool!$M$62,IF(AND(K53=\"Urban/C&G\",E53=\"Rolling\",Tool!L69=\"One Side\",Tool!M69=\"Both Sides\"),Tool!$M$62,IF(AND(K53=\"Urban/C&G\",E53=\"Rolling\",Tool!L69=\"One Side\",Tool!M69=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E53=\"Rolling\",Tool!K69,\"\")","v":""},{"$f":"IF(E53<>\"\",Drainage!G51,\"\")","v":""},"",{"$f":"IF(AND(F53=H53,G53=\"\"),\"\",VLOOKUP(Tool!P69,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S36>=16,S36<=20),16,\"\")","v":""},{"$f":"IF(R24<>\"\",IF(T23>=$C$2,\"\",IF($C$2<(Tool!E112-Tool!$D$98),\"\",IF(Tool!D113<>\"\",IF(Tool!$D$98<>0,Tool!E112-Tool!$D$98,Tool!E112),\"\"))),\"\")","v":""},{"$f":"IF(S53=\"\",\"\",IF(R24=\"\",\"\",IF(Tool!E112<>\"\",IF(AND($C$2>=(Tool!E113-Tool!$D$98),(Tool!E114-Tool!$D$98)>=(Tool!E113-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E113-Tool!$D$98,Tool!E113),$C$2),\"\")))","v":""},{"$f":"IF(R53<>\"\",IF(Tool!H113=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U53=\"Rolling\",Tool!I113>0),Tool!I113,\"\")","v":""},{"$f":"IF(U53=\"Rolling\",IF(Tool!J113>0,IF(Tool!F113=\"Barrier Wall\",3,IF(Tool!F113=\"Depressed Grass\",Tool!J113*0.5,Tool!J113)),\"\"),\"\")","v":""},{"$f":"IF(R24<>\"\",IF(U53=\"Rolling\",Tool!F113,\"\"),\"\")","v":""},"",null,"Guardrail Factor:",{"$f":"SUM(AB50:AB52)","v":0},null,{"$f":"\"1:1\"","v":"1:1"}]
[null,{"$f":"IF(AND(E46>=7,E46<=30),7,\"\")","v":""},{"$f":"IF(D14>=$C$2,\"\",IF($C$2<(Tool!E69-Tool!$D$64),\"\",IF(Tool!D70<>\"\",IF(Tool!$D$64<>0,Tool!E69-Tool!$D$64,Tool!E69),\"\")))","v":""},{"$f":"IF(C15=\"\",\"\",IF(B16=\"\",$C$2,IF((D14-$C$9)>=$C$2,\"\",IF(Tool!E69<>\"\",IF(AND($C$2>=(Tool!E70-Tool!$D$64),(Tool!E71-Tool!$D$64)>=(Tool!E70-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E70-Tool!$D$64,Tool!E70),$C$2),\"\"))))","v":""},{"$f":"IF(C54=\"\",\"\",IF(B54<>\"\",IF(Tool!N70=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E54=\"Rolling\",IF(Tool!I70>Tool!G70,0,IF(Tool!G70>0,Tool!G70+J54,\"\")),\"\")","v":""},{"$f":"IF(E54=\"Rolling\",IF(Tool!H70>0,Tool!H70,\"\"),\"\")","v":""},{"$f":"IF(E54=\"Rolling\",IF(Tool!I70>Tool!G70,Tool!G70,IF(Tool!I70>=0,Tool!I70)),\"\")","v":""},{"$f":"IF(E54=\"Rolling\",Tool!O70,\"\")","v":""},{"$f":"IF(AND(K54=\"Urban/C&G\",E54=\"Rolling\",Tool!L70=\"Both Sides\",Tool!M70=\"Both Sides\"),Tool!$M$62*2,IF(AND(K54=\"Urban/C&G\",E54=\"Rolling\",Tool!L70=\"Both Sides\",Tool!M70=\"One Side\"),Tool!$M$62,IF(AND(K54=\"Urban/C&G\",E54=\"Rolling\",Tool!L70=\"One Side\",Tool!M70=\"Both Sides\"),Tool!$M$62,IF(AND(K54=\"Urban/C&G\",E54=\"Rolling\",Tool!L70=\"One Side\",Tool!M70=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E54=\"Rolling\",Tool!K70,\"\")","v":""},{"$f":"IF(E54<>\"\",Drainage!G52,\"\")","v":""},"",{"$f":"IF(AND(F54=H54,G54=\"\"),\"\",VLOOKUP(Tool!P70,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S36>=17,S36<=20),17,\"\")","v":""},{"$f":"IF(R25<>\"\",IF(T24>=$C$2,\"\",IF($C$2<(Tool!E113-Tool!$D$98),\"\",IF(Tool!D114<>\"\",IF(Tool!$D$98<>0,Tool!E113-Tool!$D$98,Tool!E113),\"\"))),\"\")","v":""},{"$f":"IF(S54=\"\",\"\",IF(R25=\"\",\"\",IF(Tool!E113<>\"\",IF(AND($C$2>=(Tool!E114-Tool!$D$98),(Tool!E115-Tool!$D$98)>=(Tool!E114-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E114-Tool!$D$98,Tool!E114),$C$2),\"\")))","v":""},{"$f":"IF(R54<>\"\",IF(Tool!H114=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U54=\"Rolling\",Tool!I114>0),Tool!I114,\"\")","v":""},{"$f":"IF(U54=\"Rolling\",IF(Tool!J114>0,IF(Tool!F114=\"Barrier Wall\",3,IF(Tool!F114=\"Depressed Grass\",Tool!J114*0.5,Tool!J114)),\"\"),\"\")","v":""},{"$f":"IF(R25<>\"\",IF(U54=\"Rolling\",Tool!F114,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E46>=8,E46<=30),8,\"\")","v":""},{"$f":"IF(D15>=$C$2,\"\",IF($C$2<(Tool!E70-Tool!$D$64),\"\",IF(Tool!D71<>\"\",IF(Tool!$D$64<>0,Tool!E70-Tool!$D$64,Tool!E70),\"\")))","v":""},{"$f":"IF(C16=\"\",\"\",IF(B17=\"\",$C$2,IF((D15-$C$9)>=$C$2,\"\",IF(Tool!E70<>\"\",IF(AND($C$2>=(Tool!E71-Tool!$D$64),(Tool!E72-Tool!$D$64)>=(Tool!E71-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E71-Tool!$D$64,Tool!E71),$C$2),\"\"))))","v":""},{"$f":"IF(C55=\"\",\"\",IF(B55<>\"\",IF(Tool!N71=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E55=\"Rolling\",IF(Tool!I71>Tool!G71,0,IF(Tool!G71>0,Tool!G71+J55,\"\")),\"\")","v":""},{"$f":"IF(E55=\"Rolling\",IF(Tool!H71>0,Tool!H71,\"\"),\"\")","v":""},{"$f":"IF(E55=\"Rolling\",IF(Tool!I71>Tool!G71,Tool!G71,IF(Tool!I71>=0,Tool!I71)),\"\")","v":""},{"$f":"IF(E55=\"Rolling\",Tool!O71,\"\")","v":""},{"$f":"IF(AND(K55=\"Urban/C&G\",E55=\"Rolling\",Tool!L71=\"Both Sides\",Tool!M71=\"Both Sides\"),Tool!$M$62*2,IF(AND(K55=\"Urban/C&G\",E55=\"Rolling\",Tool!L71=\"Both Sides\",Tool!M71=\"One Side\"),Tool!$M$62,IF(AND(K55=\"Urban/C&G\",E55=\"Rolling\",Tool!L71=\"One Side\",Tool!M71=\"Both Sides\"),Tool!$M$62,IF(AND(K55=\"Urban/C&G\",E55=\"Rolling\",Tool!L71=\"One Side\",Tool!M71=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E55=\"Rolling\",Tool!K71,\"\")","v":""},{"$f":"IF(E55<>\"\",Drainage!G53,\"\")","v":""},"",{"$f":"IF(AND(F55=H55,G55=\"\"),\"\",VLOOKUP(Tool!P71,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S36>=18,S36<=20),18,\"\")","v":""},{"$f":"IF(R26<>\"\",IF(T25>=$C$2,\"\",IF($C$2<(Tool!E114-Tool!$D$98),\"\",IF(Tool!D115<>\"\",IF(Tool!$D$98<>0,Tool!E114-Tool!$D$98,Tool!E114),\"\"))),\"\")","v":""},{"$f":"IF(S55=\"\",\"\",IF(R26=\"\",\"\",IF(Tool!E114<>\"\",IF(AND($C$2>=(Tool!E115-Tool!$D$98),(Tool!E116-Tool!$D$98)>=(Tool!E115-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E115-Tool!$D$98,Tool!E115),$C$2),\"\")))","v":""},{"$f":"IF(R55<>\"\",IF(Tool!H115=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U55=\"Rolling\",Tool!I115>0),Tool!I115,\"\")","v":""},{"$f":"IF(U55=\"Rolling\",IF(Tool!J115>0,IF(Tool!F115=\"Barrier Wall\",3,IF(Tool!F115=\"Depressed Grass\",Tool!J115*0.5,Tool!J115)),\"\"),\"\")","v":""},{"$f":"IF(R26<>\"\",IF(U55=\"Rolling\",Tool!F115,\"\"),\"\")","v":""},"",null,"Slopes Calculations"]
[null,{"$f":"IF(AND(E46>=9,F46<=20),9,\"\")","v":""},{"$f":"IF(D16>=$C$2,\"\",IF($C$2<(Tool!E71-Tool!$D$64),\"\",IF(Tool!D72<>\"\",IF(Tool!$D$64<>0,Tool!E71-Tool!$D$64,Tool!E71),\"\")))","v":""},{"$f":"IF(C17=\"\",\"\",IF(B18=\"\",$C$2,IF((D16-$C$9)>=$C$2,\"\",IF(Tool!E71<>\"\",IF(AND($C$2>=(Tool!E72-Tool!$D$64),(Tool!E73-Tool!$D$64)>=(Tool!E72-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E72-Tool!$D$64,Tool!E72),$C$2),\"\"))))","v":""},{"$f":"IF(C56=\"\",\"\",IF(B56<>\"\",IF(Tool!N72=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E56=\"Rolling\",IF(Tool!I72>Tool!G72,0,IF(Tool!G72>0,Tool!G72+J56,\"\")),\"\")","v":""},{"$f":"IF(E56=\"Rolling\",IF(Tool!H72>0,Tool!H72,\"\"),\"\")","v":""},{"$f":"IF(E56=\"Rolling\",IF(Tool!I72>Tool!G72,Tool!G72,IF(Tool!I72>=0,Tool!I72)),\"\")","v":""},{"$f":"IF(E56=\"Rolling\",Tool!O72,\"\")","v":""},{"$f":"IF(AND(K56=\"Urban/C&G\",E56=\"Rolling\",Tool!L72=\"Both Sides\",Tool!M72=\"Both Sides\"),Tool!$M$62*2,IF(AND(K56=\"Urban/C&G\",E56=\"Rolling\",Tool!L72=\"Both Sides\",Tool!M72=\"One Side\"),Tool!$M$62,IF(AND(K56=\"Urban/C&G\",E56=\"Rolling\",Tool!L72=\"One Side\",Tool!M72=\"Both Sides\"),Tool!$M$62,IF(AND(K56=\"Urban/C&G\",E56=\"Rolling\",Tool!L72=\"One Side\",Tool!M72=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E56=\"Rolling\",Tool!K72,\"\")","v":""},{"$f":"IF(E56<>\"\",Drainage!G54,\"\")","v":""},"",{"$f":"IF(AND(F56=H56,G56=\"\"),\"\",VLOOKUP(Tool!P72,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S36>=19,S36<=20),19,\"\")","v":""},{"$f":"IF(R27<>\"\",IF(T26>=$C$2,\"\",IF($C$2<(Tool!E115-Tool!$D$98),\"\",IF(Tool!D116<>\"\",IF(Tool!$D$98<>0,Tool!E115-Tool!$D$98,Tool!E115),\"\"))),\"\")","v":""},{"$f":"IF(S56=\"\",\"\",IF(R27=\"\",\"\",IF(Tool!E115<>\"\",IF(AND($C$2>=(Tool!E116-Tool!$D$98),(Tool!E117-Tool!$D$98)>=(Tool!E116-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E116-Tool!$D$98,Tool!E116),$C$2),\"\")))","v":""},{"$f":"IF(R56<>\"\",IF(Tool!H116=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U56=\"Rolling\",Tool!I116>0),Tool!I116,\"\")","v":""},{"$f":"IF(U56=\"Rolling\",IF(Tool!J116>0,IF(Tool!F116=\"Barrier Wall\",3,IF(Tool!F116=\"Depressed Grass\",Tool!J116*0.5,Tool!J116)),\"\"),\"\")","v":""},{"$f":"IF(R27<>\"\",IF(U56=\"Rolling\",Tool!F116,\"\"),\"\")","v":""},"",null,"Rural Types","Slope Length","Width","Volume","Urban Slope Types","Slope Length","Width","Volume"]
[null,{"$f":"IF(AND(E46>=10,E46<=30),10,\"\")","v":""},{"$f":"IF(D17>=$C$2,\"\",IF($C$2<(Tool!E72-Tool!$D$64),\"\",IF(Tool!D73<>\"\",IF(Tool!$D$64<>0,Tool!E72-Tool!$D$64,Tool!E72),\"\")))","v":""},{"$f":"IF(C18=\"\",\"\",IF(B19=\"\",$C$2,IF((D17-$C$9)>=$C$2,\"\",IF(Tool!E72<>\"\",IF(AND($C$2>=(Tool!E73-Tool!$D$64),(Tool!E74-Tool!$D$64)>=(Tool!E73-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E73-Tool!$D$64,Tool!E73),$C$2),\"\"))))","v":""},{"$f":"IF(C57=\"\",\"\",IF(B57<>\"\",IF(Tool!N73=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E57=\"Rolling\",IF(Tool!I73>Tool!G73,0,IF(Tool!G73>0,Tool!G73+J57,\"\")),\"\")","v":""},{"$f":"IF(E57=\"Rolling\",IF(Tool!H73>0,Tool!H73,\"\"),\"\")","v":""},{"$f":"IF(E57=\"Rolling\",IF(Tool!I73>Tool!G73,Tool!G73,IF(Tool!I73>=0,Tool!I73)),\"\")","v":""},{"$f":"IF(E57=\"Rolling\",Tool!O73,\"\")","v":""},{"$f":"IF(AND(K57=\"Urban/C&G\",E57=\"Rolling\",Tool!L73=\"Both Sides\",Tool!M73=\"Both Sides\"),Tool!$M$62*2,IF(AND(K57=\"Urban/C&G\",E57=\"Rolling\",Tool!L73=\"Both Sides\",Tool!M73=\"One Side\"),Tool!$M$62,IF(AND(K57=\"Urban/C&G\",E57=\"Rolling\",Tool!L73=\"One Side\",Tool!M73=\"Both Sides\"),Tool!$M$62,IF(AND(K57=\"Urban/C&G\",E57=\"Rolling\",Tool!L73=\"One Side\",Tool!M73=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E57=\"Rolling\",Tool!K73,\"\")","v":""},{"$f":"IF(E57<>\"\",Drainage!G55,\"\")","v":""},"",{"$f":"IF(AND(F57=H57,G57=\"\"),\"\",VLOOKUP(Tool!P73,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S36=20),20,\"\")","v":""},{"$f":"IF(R28<>\"\",IF(T27>=$C$2,\"\",IF($C$2<(Tool!E116-Tool!$D$98),\"\",IF(Tool!D117<>\"\",IF(Tool!$D$98<>0,Tool!E116-Tool!$D$98,Tool!E116),\"\"))),\"\")","v":""},{"$f":"IF(S57=\"\",\"\",IF(R28=\"\",\"\",IF(Tool!E116<>\"\",IF(AND($C$2>=(Tool!E117-Tool!$D$98),(Tool!E118-Tool!$D$98)>=(Tool!E117-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E117-Tool!$D$98,Tool!E117),$C$2),\"\")))","v":""},{"$f":"IF(R57<>\"\",IF(Tool!H117=\"Rolling\",\"Rolling\",\"\"),\"\")","v":""},{"$f":"IF(AND(U57=\"Rolling\",Tool!I117>0),Tool!I117,\"\")","v":""},{"$f":"IF(U57=\"Rolling\",IF(Tool!J117>0,IF(Tool!F117=\"Barrier Wall\",3,IF(Tool!F117=\"Depressed Grass\",Tool!J117*0.5,Tool!J117)),\"\"),\"\")","v":""},{"$f":"IF(R28<>\"\",IF(U57=\"Rolling\",Tool!F117,\"\"),\"\")","v":""},"",null,"Flat - One Side",{"$f":"F41","v":0},{"$f":"M40*AG25","v":0},{"$f":"(AB57*AG25*5280*AC57)*0.5/27","v":0},"Flat - One Side",{"$f":"F43","v":0},{"$f":"M42*AG25","v":0},{"$f":"(AF57*AG25*5280*AG57)*0.5/27","v":0}]
[null,{"$f":"IF(AND(E46>=11,E46<=30),11,\"\")","v":""},{"$f":"IF(D18>=$C$2,\"\",IF($C$2<(Tool!E73-Tool!$D$64),\"\",IF(Tool!D74<>\"\",IF(Tool!$D$64<>0,Tool!E73-Tool!$D$64,Tool!E73),\"\")))","v":""},{"$f":"IF(C19=\"\",\"\",IF(B20=\"\",$C$2,IF((D18-$C$9)>=$C$2,\"\",IF(Tool!E73<>\"\",IF(AND($C$2>=(Tool!E74-Tool!$D$64),(Tool!E75-Tool!$D$64)>=(Tool!E74-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E74-Tool!$D$64,Tool!E74),$C$2),\"\"))))","v":""},{"$f":"IF(C58=\"\",\"\",IF(B58<>\"\",IF(Tool!N74=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E58=\"Rolling\",IF(Tool!I74>Tool!G74,0,IF(Tool!G74>0,Tool!G74+J58,\"\")),\"\")","v":""},{"$f":"IF(E58=\"Rolling\",IF(Tool!H74>0,Tool!H74,\"\"),\"\")","v":""},{"$f":"IF(E58=\"Rolling\",IF(Tool!I74>Tool!G74,Tool!G74,IF(Tool!I74>=0,Tool!I74)),\"\")","v":""},{"$f":"IF(E58=\"Rolling\",Tool!O74,\"\")","v":""},{"$f":"IF(AND(K58=\"Urban/C&G\",E58=\"Rolling\",Tool!L74=\"Both Sides\",Tool!M74=\"Both Sides\"),Tool!$M$62*2,IF(AND(K58=\"Urban/C&G\",E58=\"Rolling\",Tool!L74=\"Both Sides\",Tool!M74=\"One Side\"),Tool!$M$62,IF(AND(K58=\"Urban/C&G\",E58=\"Rolling\",Tool!L74=\"One Side\",Tool!M74=\"Both Sides\"),Tool!$M$62,IF(AND(K58=\"Urban/C&G\",E58=\"Rolling\",Tool!L74=\"One Side\",Tool!M74=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E58=\"Rolling\",Tool!K74,\"\")","v":""},{"$f":"IF(E58<>\"\",Drainage!G56,\"\")","v":""},"",{"$f":"IF(AND(F58=H58,G58=\"\"),\"\",VLOOKUP(Tool!P74,$AM$4:$AN$9,2,0))","v":""},"","","",null,null,null,null,null,null,null,null,null,"Rolling - One Side",{"$f":"F80","v":0},{"$f":"M79*AG26","v":0},{"$f":"(AB58*AG26*5280*AC58)*0.5/27","v":0},"Rolling - One Side",{"$f":"F82","v":0},{"$f":"M81*AG26","v":0},{"$f":"(AF58*AG26*5280*AG58)*0.5/27","v":0}]
[null,{"$f":"IF(AND(E46>=12,F46<=30),12,\"\")","v":""},{"$f":"IF(D19>=$C$2,\"\",IF($C$2<(Tool!E74-Tool!$D$64),\"\",IF(Tool!D75<>\"\",IF(Tool!$D$64<>0,Tool!E74-Tool!$D$64,Tool!E74),\"\")))","v":""},{"$f":"IF(C20=\"\",\"\",IF(B21=\"\",$C$2,IF((D19-$C$9)>=$C$2,\"\",IF(Tool!E74<>\"\",IF(AND($C$2>=(Tool!E75-Tool!$D$64),(Tool!E76-Tool!$D$64)>=(Tool!E75-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E75-Tool!$D$64,Tool!E75),$C$2),\"\"))))","v":""},{"$f":"IF(C59=\"\",\"\",IF(B59<>\"\",IF(Tool!N75=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E59=\"Rolling\",IF(Tool!I75>Tool!G75,0,IF(Tool!G75>0,Tool!G75+J59,\"\")),\"\")","v":""},{"$f":"IF(E59=\"Rolling\",IF(Tool!H75>0,Tool!H75,\"\"),\"\")","v":""},{"$f":"IF(E59=\"Rolling\",IF(Tool!I75>Tool!G75,Tool!G75,IF(Tool!I75>=0,Tool!I75)),\"\")","v":""},{"$f":"IF(E59=\"Rolling\",Tool!O75,\"\")","v":""},{"$f":"IF(AND(K59=\"Urban/C&G\",E59=\"Rolling\",Tool!L75=\"Both Sides\",Tool!M75=\"Both Sides\"),Tool!$M$62*2,IF(AND(K59=\"Urban/C&G\",E59=\"Rolling\",Tool!L75=\"Both Sides\",Tool!M75=\"One Side\"),Tool!$M$62,IF(AND(K59=\"Urban/C&G\",E59=\"Rolling\",Tool!L75=\"One Side\",Tool!M75=\"Both Sides\"),Tool!$M$62,IF(AND(K59=\"Urban/C&G\",E59=\"Rolling\",Tool!L75=\"One Side\",Tool!M75=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E59=\"Rolling\",Tool!K75,\"\")","v":""},{"$f":"IF(E59<>\"\",Drainage!G57,\"\")","v":""},"",{"$f":"IF(AND(F59=H59,G59=\"\"),\"\",VLOOKUP(Tool!P75,$AM$4:$AN$9,2,0))","v":""},"","","",null,null,null,null,null,null,"Avg. Inside Shldr. Width:",{"$f":"IF(SUM(Y38:Y57),SUMPRODUCT(V38:V57,Y38:Y57)/SUM(Y38:Y57),0)","v":0},null,"Mountainous - One Side",{"$f":"F120","v":0},{"$f":"M119*AG27","v":0},{"$f":"(AB59*AG27*5280*AC59)*0.5/27","v":0},"Mountainous - One Side",{"$f":"F122","v":0},{"$f":"M121*AG27","v":0},{"$f":"(AF59*AG27*5280*AG59)*0.5/27","v":0}]
[null,{"$f":"IF(AND(E46>=13,E46<=30),13,\"\")","v":""},{"$f":"IF(D20>=$C$2,\"\",IF($C$2<(Tool!E75-Tool!$D$64),\"\",IF(Tool!D76<>\"\",IF(Tool!$D$64<>0,Tool!E75-Tool!$D$64,Tool!E75),\"\")))","v":""},{"$f":"IF(C21=\"\",\"\",IF(B22=\"\",$C$2,IF((D20-$C$9)>=$C$2,\"\",IF(Tool!E75<>\"\",IF(AND($C$2>=(Tool!E76-Tool!$D$64),(Tool!E77-Tool!$D$64)>=(Tool!E76-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E76-Tool!$D$64,Tool!E76),$C$2),\"\"))))","v":""},{"$f":"IF(C60=\"\",\"\",IF(B60<>\"\",IF(Tool!N76=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E60=\"Rolling\",IF(Tool!I76>Tool!G76,0,IF(Tool!G76>0,Tool!G76+J60,\"\")),\"\")","v":""},{"$f":"IF(E60=\"Rolling\",IF(Tool!H76>0,Tool!H76,\"\"),\"\")","v":""},{"$f":"IF(E60=\"Rolling\",IF(Tool!I76>Tool!G76,Tool!G76,IF(Tool!I76>=0,Tool!I76)),\"\")","v":""},{"$f":"IF(E60=\"Rolling\",Tool!O76,\"\")","v":""},{"$f":"IF(AND(K60=\"Urban/C&G\",E60=\"Rolling\",Tool!L76=\"Both Sides\",Tool!M76=\"Both Sides\"),Tool!$M$62*2,IF(AND(K60=\"Urban/C&G\",E60=\"Rolling\",Tool!L76=\"Both Sides\",Tool!M76=\"One Side\"),Tool!$M$62,IF(AND(K60=\"Urban/C&G\",E60=\"Rolling\",Tool!L76=\"One Side\",Tool!M76=\"Both Sides\"),Tool!$M$62,IF(AND(K60=\"Urban/C&G\",E60=\"Rolling\",Tool!L76=\"One Side\",Tool!M76=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E60=\"Rolling\",Tool!K76,\"\")","v":""},{"$f":"IF(E60<>\"\",Drainage!G58,\"\")","v":""},"",{"$f":"IF(AND(F60=H60,G60=\"\"),\"\",VLOOKUP(Tool!P76,$AM$4:$AN$9,2,0))","v":""},"","","",null,null,null,null,null,null,"Avg. Interior Width:",{"$f":"IF(SUM(Y38:Y57)>0,SUMPRODUCT(W38:W57,Y38:Y57)/SUM(Y38:Y57),0)","v":0},null,"Heavy Mountainous - One Side",{"$f":"F160","v":0},{"$f":"M159*AG28","v":0},{"$f":"(AB60*AG28*5280*AC60)*0.5/27","v":0},"Heavy Mountainous - One Side",{"$f":"F162","v":0},{"$f":"M161*AG28","v":0},{"$f":"(AF60*AG28*5280*AG60)*0.5/27","v":0}]
[null,{"$f":"IF(AND(E46>=14,E46<=30),14,\"\")","v":""},{"$f":"IF(D21>=$C$2,\"\",IF($C$2<(Tool!E76-Tool!$D$64),\"\",IF(Tool!D77<>\"\",IF(Tool!$D$64<>0,Tool!E76-Tool!$D$64,Tool!E76),\"\")))","v":""},{"$f":"IF(C22=\"\",\"\",IF(B23=\"\",$C$2,IF((D21-$C$9)>=$C$2,\"\",IF(Tool!E76<>\"\",IF(AND($C$2>=(Tool!E77-Tool!$D$64),(Tool!E78-Tool!$D$64)>=(Tool!E77-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E77-Tool!$D$64,Tool!E77),$C$2),\"\"))))","v":""},{"$f":"IF(C61=\"\",\"\",IF(B61<>\"\",IF(Tool!N77=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E61=\"Rolling\",IF(Tool!I77>Tool!G77,0,IF(Tool!G77>0,Tool!G77+J61,\"\")),\"\")","v":""},{"$f":"IF(E61=\"Rolling\",IF(Tool!H77>0,Tool!H77,\"\"),\"\")","v":""},{"$f":"IF(E61=\"Rolling\",IF(Tool!I77>Tool!G77,Tool!G77,IF(Tool!I77>=0,Tool!I77)),\"\")","v":""},{"$f":"IF(E61=\"Rolling\",Tool!O77,\"\")","v":""},{"$f":"IF(AND(K61=\"Urban/C&G\",E61=\"Rolling\",Tool!L77=\"Both Sides\",Tool!M77=\"Both Sides\"),Tool!$M$62*2,IF(AND(K61=\"Urban/C&G\",E61=\"Rolling\",Tool!L77=\"Both Sides\",Tool!M77=\"One Side\"),Tool!$M$62,IF(AND(K61=\"Urban/C&G\",E61=\"Rolling\",Tool!L77=\"One Side\",Tool!M77=\"Both Sides\"),Tool!$M$62,IF(AND(K61=\"Urban/C&G\",E61=\"Rolling\",Tool!L77=\"One Side\",Tool!M77=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E61=\"Rolling\",Tool!K77,\"\")","v":""},{"$f":"IF(E61<>\"\",Drainage!G59,\"\")","v":""},"",{"$f":"IF(AND(F61=H61,G61=\"\"),\"\",VLOOKUP(Tool!P77,$AM$4:$AN$9,2,0))","v":""},"","","",null,null,null,null,null,null,"Avg. Fill Width:",{"$f":"Y59+Y60","v":0},null,"Flat - Both Sides",{"$f":"F42","v":0},{"$f":"M41*AG25","v":0},{"$f":"(AB61*AG25*5280*AC61)*0.5/27","v":0},"Flat - Both Sides",{"$f":"F44","v":0},{"$f":"M43*AG25","v":0},{"$f":"(AF61*AG25*5280*AG61)*0.5/27","v":0}]
[null,{"$f":"IF(AND(E46>=15,E46<=30),15,\"\")","v":""},{"$f":"IF(D22>=$C$2,\"\",IF($C$2<(Tool!E77-Tool!$D$64),\"\",IF(Tool!D78<>\"\",IF(Tool!$D$64<>0,Tool!E77-Tool!$D$64,Tool!E77),\"\")))","v":""},{"$f":"IF(C23=\"\",\"\",IF(B24=\"\",$C$2,IF((D22-$C$9)>=$C$2,\"\",IF(Tool!E77<>\"\",IF(AND($C$2>=(Tool!E78-Tool!$D$64),(Tool!E79-Tool!$D$64)>=(Tool!E78-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E78-Tool!$D$64,Tool!E78),$C$2),\"\"))))","v":""},{"$f":"IF(C62=\"\",\"\",IF(B62<>\"\",IF(Tool!N78=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E62=\"Rolling\",IF(Tool!I78>Tool!G78,0,IF(Tool!G78>0,Tool!G78+J62,\"\")),\"\")","v":""},{"$f":"IF(E62=\"Rolling\",IF(Tool!H78>0,Tool!H78,\"\"),\"\")","v":""},{"$f":"IF(E62=\"Rolling\",IF(Tool!I78>Tool!G78,Tool!G78,IF(Tool!I78>=0,Tool!I78)),\"\")","v":""},{"$f":"IF(E62=\"Rolling\",Tool!O78,\"\")","v":""},{"$f":"IF(AND(K62=\"Urban/C&G\",E62=\"Rolling\",Tool!L78=\"Both Sides\",Tool!M78=\"Both Sides\"),Tool!$M$62*2,IF(AND(K62=\"Urban/C&G\",E62=\"Rolling\",Tool!L78=\"Both Sides\",Tool!M78=\"One Side\"),Tool!$M$62,IF(AND(K62=\"Urban/C&G\",E62=\"Rolling\",Tool!L78=\"One Side\",Tool!M78=\"Both Sides\"),Tool!$M$62,IF(AND(K62=\"Urban/C&G\",E62=\"Rolling\",Tool!L78=\"One Side\",Tool!M78=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E62=\"Rolling\",Tool!K78,\"\")","v":""},{"$f":"IF(E62<>\"\",Drainage!G60,\"\")","v":""},"",{"$f":"IF(AND(F62=H62,G62=\"\"),\"\",VLOOKUP(Tool!P78,$AM$4:$AN$9,2,0))","v":""},"","","",null,null,null,null,null,null,"Avg. Fill Area:",{"$f":"Y61*SUM(Y38:Y57)*5280","v":0},null,"Rolling - Both Sides",{"$f":"F81","v":0},{"$f":"M80*AG26","v":0},{"$f":"(AB62*AG26*5280*AC62)*0.5/27","v":0},"Rolling - Both Sides",{"$f":"F83","v":0},{"$f":"M82*AG26","v":0},{"$f":"(AF62*AG26*5280*AG62)*0.5/27","v":0}]
[null,{"$f":"IF(AND(E46>=16,E46<=30),16,\"\")","v":""},{"$f":"IF(D23>=$C$2,\"\",IF($C$2<(Tool!E78-Tool!$D$64),\"\",IF(Tool!D79<>\"\",IF(Tool!$D$64<>0,Tool!E78-Tool!$D$64,Tool!E78),\"\")))","v":""},{"$f":"IF(C24=\"\",\"\",IF(B25=\"\",$C$2,IF((D23-$C$9)>=$C$2,\"\",IF(Tool!E78<>\"\",IF(AND($C$2>=(Tool!E79-Tool!$D$64),(Tool!E80-Tool!$D$64)>=(Tool!E79-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E79-Tool!$D$64,Tool!E79),$C$2),\"\"))))","v":""},{"$f":"IF(C63=\"\",\"\",IF(B63<>\"\",IF(Tool!N79=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E63=\"Rolling\",IF(Tool!I79>Tool!G79,0,IF(Tool!G79>0,Tool!G79+J63,\"\")),\"\")","v":""},{"$f":"IF(E63=\"Rolling\",IF(Tool!H79>0,Tool!H79,\"\"),\"\")","v":""},{"$f":"IF(E63=\"Rolling\",IF(Tool!I79>Tool!G79,Tool!G79,IF(Tool!I79>=0,Tool!I79)),\"\")","v":""},{"$f":"IF(E63=\"Rolling\",Tool!O79,\"\")","v":""},{"$f":"IF(AND(K63=\"Urban/C&G\",E63=\"Rolling\",Tool!L79=\"Both Sides\",Tool!M79=\"Both Sides\"),Tool!$M$62*2,IF(AND(K63=\"Urban/C&G\",E63=\"Rolling\",Tool!L79=\"Both Sides\",Tool!M79=\"One Side\"),Tool!$M$62,IF(AND(K63=\"Urban/C&G\",E63=\"Rolling\",Tool!L79=\"One Side\",Tool!M79=\"Both Sides\"),Tool!$M$62,IF(AND(K63=\"Urban/C&G\",E63=\"Rolling\",Tool!L79=\"One Side\",Tool!M79=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E63=\"Rolling\",Tool!K79,\"\")","v":""},{"$f":"IF(E63<>\"\",Drainage!G61,\"\")","v":""},"",{"$f":"IF(AND(F63=H63,G63=\"\"),\"\",VLOOKUP(Tool!P79,$AM$4:$AN$9,2,0))","v":""},"","","",null,null,null,null,null,null,"Length:",{"$f":"SUM(Y38:Y57)","v":0},null,"Mountainous - Both Sides",{"$f":"F121","v":0},{"$f":"M120*AG27","v":0},{"$f":"(AB63*AG27*5280*AC63)*0.5/27","v":0},"Mountainous - Both Sides",{"$f":"F123","v":0},{"$f":"M122*AG27","v":0},{"$f":"(AF63*AG27*5280*AG63)*0.5/27","v":0}]
[null,{"$f":"IF(AND(E46>=17,E46<=30),17,\"\")","v":""},{"$f":"IF(D24>=$C$2,\"\",IF($C$2<(Tool!E79-Tool!$D$64),\"\",IF(Tool!D80<>\"\",IF(Tool!$D$64<>0,Tool!E79-Tool!$D$64,Tool!E79),\"\")))","v":""},{"$f":"IF(C25=\"\",\"\",IF(B26=\"\",$C$2,IF((D24-$C$9)>=$C$2,\"\",IF(Tool!E79<>\"\",IF(AND($C$2>=(Tool!E80-Tool!$D$64),(Tool!E81-Tool!$D$64)>=(Tool!E80-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E80-Tool!$D$64,Tool!E80),$C$2),\"\"))))","v":""},{"$f":"IF(C64=\"\",\"\",IF(B64<>\"\",IF(Tool!N80=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E64=\"Rolling\",IF(Tool!I80>Tool!G80,0,IF(Tool!G80>0,Tool!G80+J64,\"\")),\"\")","v":""},{"$f":"IF(E64=\"Rolling\",IF(Tool!H80>0,Tool!H80,\"\"),\"\")","v":""},{"$f":"IF(E64=\"Rolling\",IF(Tool!I80>Tool!G80,Tool!G80,IF(Tool!I80>=0,Tool!I80)),\"\")","v":""},{"$f":"IF(E64=\"Rolling\",Tool!O80,\"\")","v":""},{"$f":"IF(AND(K64=\"Urban/C&G\",E64=\"Rolling\",Tool!L80=\"Both Sides\",Tool!M80=\"Both Sides\"),Tool!$M$62*2,IF(AND(K64=\"Urban/C&G\",E64=\"Rolling\",Tool!L80=\"Both Sides\",Tool!M80=\"One Side\"),Tool!$M$62,IF(AND(K64=\"Urban/C&G\",E64=\"Rolling\",Tool!L80=\"One Side\",Tool!M80=\"Both Sides\"),Tool!$M$62,IF(AND(K64=\"Urban/C&G\",E64=\"Rolling\",Tool!L80=\"One Side\",Tool!M80=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E64=\"Rolling\",Tool!K80,\"\")","v":""},{"$f":"IF(E64<>\"\",Drainage!G62,\"\")","v":""},"",{"$f":"IF(AND(F64=H64,G64=\"\"),\"\",VLOOKUP(Tool!P80,$AM$4:$AN$9,2,0))","v":""},"","","",null,null,null,null,null,null,null,null,null,"Heavy Mountainous - Both Sides",{"$f":"F161","v":0},{"$f":"M160*AG28","v":0},{"$f":"(AB64*AG28*5280*AC64)*0.5/27","v":0},"Heavy Mountainous - Both Sides",{"$f":"F163","v":0},{"$f":"M162*AG28","v":0},{"$f":"(AF64*AG28*5280*AG64)*0.5/27","v":0}]
[null,{"$f":"IF(AND(E46>=18,E46<=30),18,\"\")","v":""},{"$f":"IF(D25>=$C$2,\"\",IF($C$2<(Tool!E80-Tool!$D$64),\"\",IF(Tool!D81<>\"\",IF(Tool!$D$64<>0,Tool!E80-Tool!$D$64,Tool!E80),\"\")))","v":""},{"$f":"IF(C26=\"\",\"\",IF(B27=\"\",$C$2,IF((D25-$C$9)>=$C$2,\"\",IF(Tool!E80<>\"\",IF(AND($C$2>=(Tool!E81-Tool!$D$64),(Tool!E82-Tool!$D$64)>=(Tool!E81-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E81-Tool!$D$64,Tool!E81),$C$2),\"\"))))","v":""},{"$f":"IF(C65=\"\",\"\",IF(B65<>\"\",IF(Tool!N81=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E65=\"Rolling\",IF(Tool!I81>Tool!G81,0,IF(Tool!G81>0,Tool!G81+J65,\"\")),\"\")","v":""},{"$f":"IF(E65=\"Rolling\",IF(Tool!H81>0,Tool!H81,\"\"),\"\")","v":""},{"$f":"IF(E65=\"Rolling\",IF(Tool!I81>Tool!G81,Tool!G81,IF(Tool!I81>=0,Tool!I81)),\"\")","v":""},{"$f":"IF(E65=\"Rolling\",Tool!O81,\"\")","v":""},{"$f":"IF(AND(K65=\"Urban/C&G\",E65=\"Rolling\",Tool!L81=\"Both Sides\",Tool!M81=\"Both Sides\"),Tool!$M$62*2,IF(AND(K65=\"Urban/C&G\",E65=\"Rolling\",Tool!L81=\"Both Sides\",Tool!M81=\"One Side\"),Tool!$M$62,IF(AND(K65=\"Urban/C&G\",E65=\"Rolling\",Tool!L81=\"One Side\",Tool!M81=\"Both Sides\"),Tool!$M$62,IF(AND(K65=\"Urban/C&G\",E65=\"Rolling\",Tool!L81=\"One Side\",Tool!M81=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E65=\"Rolling\",Tool!K81,\"\")","v":""},{"$f":"IF(E65<>\"\",Drainage!G63,\"\")","v":""},"",{"$f":"IF(AND(F65=H65,G65=\"\"),\"\",VLOOKUP(Tool!P81,$AM$4:$AN$9,2,0))","v":""},"","","","Mountainous Terrain"]
[null,{"$f":"IF(AND(E46>=19,E46<=30),19,\"\")","v":""},{"$f":"IF(D26>=$C$2,\"\",IF($C$2<(Tool!E81-Tool!$D$64),\"\",IF(Tool!D82<>\"\",IF(Tool!$D$64<>0,Tool!E81-Tool!$D$64,Tool!E81),\"\")))","v":""},{"$f":"IF(C27=\"\",\"\",IF(B28=\"\",$C$2,IF((D26-$C$9)>=$C$2,\"\",IF(Tool!E81<>\"\",IF(AND($C$2>=(Tool!E82-Tool!$D$64),(Tool!E83-Tool!$D$64)>=(Tool!E82-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E82-Tool!$D$64,Tool!E82),$C$2),\"\"))))","v":""},{"$f":"IF(C66=\"\",\"\",IF(B66<>\"\",IF(Tool!N82=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E66=\"Rolling\",IF(Tool!I82>Tool!G82,0,IF(Tool!G82>0,Tool!G82+J66,\"\")),\"\")","v":""},{"$f":"IF(E66=\"Rolling\",IF(Tool!H82>0,Tool!H82,\"\"),\"\")","v":""},{"$f":"IF(E66=\"Rolling\",IF(Tool!I82>Tool!G82,Tool!G82,IF(Tool!I82>=0,Tool!I82)),\"\")","v":""},{"$f":"IF(E66=\"Rolling\",Tool!O82,\"\")","v":""},{"$f":"IF(AND(K66=\"Urban/C&G\",E66=\"Rolling\",Tool!L82=\"Both Sides\",Tool!M82=\"Both Sides\"),Tool!$M$62*2,IF(AND(K66=\"Urban/C&G\",E66=\"Rolling\",Tool!L82=\"Both Sides\",Tool!M82=\"One Side\"),Tool!$M$62,IF(AND(K66=\"Urban/C&G\",E66=\"Rolling\",Tool!L82=\"One Side\",Tool!M82=\"Both Sides\"),Tool!$M$62,IF(AND(K66=\"Urban/C&G\",E66=\"Rolling\",Tool!L82=\"One Side\",Tool!M82=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E66=\"Rolling\",Tool!K82,\"\")","v":""},{"$f":"IF(E66<>\"\",Drainage!G64,\"\")","v":""},"",{"$f":"IF(AND(F66=H66,G66=\"\"),\"\",VLOOKUP(Tool!P82,$AM$4:$AN$9,2,0))","v":""},"","","","Segments:",{"$f":"Tool!$J$96","v":1},null,null,null,null,null,null,null,"Sidewalks"]
[null,{"$f":"IF(AND(E46>=20,E46<=30),20,\"\")","v":""},{"$f":"IF(D27>=$C$2,\"\",IF($C$2<(Tool!E82-Tool!$D$64),\"\",IF(Tool!D83<>\"\",IF(Tool!$D$64<>0,Tool!E82-Tool!$D$64,Tool!E82),\"\")))","v":""},{"$f":"IF(C28=\"\",\"\",IF(B29=\"\",$C$2,IF((D27-$C$9)>=$C$2,\"\",IF(Tool!E82<>\"\",IF(AND($C$2>=(Tool!E83-Tool!$D$64),(Tool!E84-Tool!$D$64)>=(Tool!E83-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E83-Tool!$D$64,Tool!E83),$C$2),\"\"))))","v":""},{"$f":"IF(C67=\"\",\"\",IF(B67<>\"\",IF(Tool!N83=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E67=\"Rolling\",IF(Tool!I83>Tool!G83,0,IF(Tool!G83>0,Tool!G83+J67,\"\")),\"\")","v":""},{"$f":"IF(E67=\"Rolling\",IF(Tool!H83>0,Tool!H83,\"\"),\"\")","v":""},{"$f":"IF(E67=\"Rolling\",IF(Tool!I83>Tool!G83,Tool!G83,IF(Tool!I83>=0,Tool!I83)),\"\")","v":""},{"$f":"IF(E67=\"Rolling\",Tool!O83,\"\")","v":""},{"$f":"IF(AND(K67=\"Urban/C&G\",E67=\"Rolling\",Tool!L83=\"Both Sides\",Tool!M83=\"Both Sides\"),Tool!$M$62*2,IF(AND(K67=\"Urban/C&G\",E67=\"Rolling\",Tool!L83=\"Both Sides\",Tool!M83=\"One Side\"),Tool!$M$62,IF(AND(K67=\"Urban/C&G\",E67=\"Rolling\",Tool!L83=\"One Side\",Tool!M83=\"Both Sides\"),Tool!$M$62,IF(AND(K67=\"Urban/C&G\",E67=\"Rolling\",Tool!L83=\"One Side\",Tool!M83=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E67=\"Rolling\",Tool!K83,\"\")","v":""},{"$f":"IF(E67<>\"\",Drainage!G65,\"\")","v":""},"",{"$f":"IF(AND(F67=H67,G67=\"\"),\"\",VLOOKUP(Tool!P83,$AM$4:$AN$9,2,0))","v":""},"","","","Segments","Begin (mi)","End (mi)","Terrain Type","Inside Shldr. Width (ft)","Interior Width (ft)","Median Type","Length",null,"Description","Length","Depth","Width","Volume"]
[null,{"$f":"IF(AND(E46>=21,E46<=30),21,\"\")","v":""},{"$f":"IF(D28>=$C$2,\"\",IF($C$2<(Tool!E83-Tool!$D$64),\"\",IF(Tool!D84<>\"\",IF(Tool!$D$64<>0,Tool!E83-Tool!$D$64,Tool!E83),\"\")))","v":""},{"$f":"IF(C29=\"\",\"\",IF(B30=\"\",$C$2,IF((D28-$C$9)>=$C$2,\"\",IF(Tool!E83<>\"\",IF(AND($C$2>=(Tool!E84-Tool!$D$64),(Tool!E85-Tool!$D$64)>=(Tool!E84-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E84-Tool!$D$64,Tool!E84),$C$2),\"\"))))","v":""},{"$f":"IF(C68=\"\",\"\",IF(B68<>\"\",IF(Tool!N84=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E68=\"Rolling\",IF(Tool!I84>Tool!G84,0,IF(Tool!G84>0,Tool!G84+J68,\"\")),\"\")","v":""},{"$f":"IF(E68=\"Rolling\",IF(Tool!H84>0,Tool!H84,\"\"),\"\")","v":""},{"$f":"IF(E68=\"Rolling\",IF(Tool!I84>Tool!G84,Tool!G84,IF(Tool!I84>=0,Tool!I84)),\"\")","v":""},{"$f":"IF(E68=\"Rolling\",Tool!O84,\"\")","v":""},{"$f":"IF(AND(K68=\"Urban/C&G\",E68=\"Rolling\",Tool!L84=\"Both Sides\",Tool!M84=\"Both Sides\"),Tool!$M$62*2,IF(AND(K68=\"Urban/C&G\",E68=\"Rolling\",Tool!L84=\"Both Sides\",Tool!M84=\"One Side\"),Tool!$M$62,IF(AND(K68=\"Urban/C&G\",E68=\"Rolling\",Tool!L84=\"One Side\",Tool!M84=\"Both Sides\"),Tool!$M$62,IF(AND(K68=\"Urban/C&G\",E68=\"Rolling\",Tool!L84=\"One Side\",Tool!M84=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E68=\"Rolling\",Tool!K84,\"\")","v":""},{"$f":"IF(E68<>\"\",Drainage!G66,\"\")","v":""},"",{"$f":"IF(AND(F68=H68,G68=\"\"),\"\",VLOOKUP(Tool!P84,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S66>=1,S66<=20),1,\"\")","v":1},{"$f":"IF(Tool!D98<>\"\",IF(R9<>\"\",IF(Tool!D98=0,Tool!D98,Tool!D98-Tool!D98),\"\"),\"\")","v":""},{"$f":"IF(Tool!E98<>\"\",IF(R68=1,IF($C$2<(Tool!E98-Tool!$D$98),$C$2,IF(Tool!D98<>0,(Tool!E98-Tool!D98),Tool!E98)),\"\"),\"\")","v":""},{"$f":"IF(R68<>\"\",IF(Tool!H98=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U68=\"Mountainous\",Tool!I98>0),Tool!I98,\"\")","v":""},{"$f":"IF(U68=\"Mountainous\",IF(Tool!J98>0,IF(Tool!F98=\"Barrier Wall\",3,IF(Tool!F98=\"Depressed Grass\",Tool!J98*0.5,Tool!J98)),\"\"),\"\")","v":""},{"$f":"IF(R9<>\"\",IF(U68=\"Mountainous\",Tool!F98,\"\"),\"\")","v":""},{"$f":"IF(U68=\"Mountainous\",T68-S68,\"\")","v":""},null,"Sidewalk Length - Flat:",{"$f":"F40","v":0},{"$f":"AG25","v":3},5,{"$f":"((AB68*5280)*AC68*AD68)/27","v":0}]
[null,{"$f":"IF(AND(E46>=22,E46<=30),22,\"\")","v":""},{"$f":"IF(D29>=$C$2,\"\",IF($C$2<(Tool!E84-Tool!$D$64),\"\",IF(Tool!D85<>\"\",IF(Tool!$D$64<>0,Tool!E84-Tool!$D$64,Tool!E84),\"\")))","v":""},{"$f":"IF(C30=\"\",\"\",IF(B31=\"\",$C$2,IF((D29-$C$9)>=$C$2,\"\",IF(Tool!E84<>\"\",IF(AND($C$2>=(Tool!E85-Tool!$D$64),(Tool!E86-Tool!$D$64)>=(Tool!E85-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E85-Tool!$D$64,Tool!E85),$C$2),\"\"))))","v":""},{"$f":"IF(C69=\"\",\"\",IF(B69<>\"\",IF(Tool!N85=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E69=\"Rolling\",IF(Tool!I85>Tool!G85,0,IF(Tool!G85>0,Tool!G85+J69,\"\")),\"\")","v":""},{"$f":"IF(E69=\"Rolling\",IF(Tool!H85>0,Tool!H85,\"\"),\"\")","v":""},{"$f":"IF(E69=\"Rolling\",IF(Tool!I85>Tool!G85,Tool!G85,IF(Tool!I85>=0,Tool!I85)),\"\")","v":""},{"$f":"IF(E69=\"Rolling\",Tool!O85,\"\")","v":""},{"$f":"IF(AND(K69=\"Urban/C&G\",E69=\"Rolling\",Tool!L85=\"Both Sides\",Tool!M85=\"Both Sides\"),Tool!$M$62*2,IF(AND(K69=\"Urban/C&G\",E69=\"Rolling\",Tool!L85=\"Both Sides\",Tool!M85=\"One Side\"),Tool!$M$62,IF(AND(K69=\"Urban/C&G\",E69=\"Rolling\",Tool!L85=\"One Side\",Tool!M85=\"Both Sides\"),Tool!$M$62,IF(AND(K69=\"Urban/C&G\",E69=\"Rolling\",Tool!L85=\"One Side\",Tool!M85=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E69=\"Rolling\",Tool!K85,\"\")","v":""},{"$f":"IF(E69<>\"\",Drainage!G67,\"\")","v":""},"",{"$f":"IF(AND(F69=H69,G69=\"\"),\"\",VLOOKUP(Tool!P85,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S66>=2,S66<=20),2,\"\")","v":""},{"$f":"IF(R10<>\"\",IF(T9>=$C$2,\"\",IF($C$2<(Tool!E98-Tool!$D$98),\"\",IF(Tool!D99<>\"\",IF(Tool!$D$98<>0,Tool!E98-Tool!$D$98,Tool!E98),\"\"))),\"\")","v":""},{"$f":"IF(S69=\"\",\"\",IF(R10=\"\",\"\",IF(Tool!E98<>\"\",IF(AND($C$2>=(Tool!E99-Tool!$D$98),(Tool!E100-Tool!$D$98)>=(Tool!E99-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E99-Tool!$D$98,Tool!E99),$C$2),\"\")))","v":""},{"$f":"IF(R69<>\"\",IF(Tool!H99=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U69=\"Mountainous\",Tool!I99>0),Tool!I99,\"\")","v":""},{"$f":"IF(U69=\"Mountainous\",IF(Tool!J99>0,IF(Tool!F99=\"Barrier Wall\",3,IF(Tool!F99=\"Depressed Grass\",Tool!J99*0.5,Tool!J99)),\"\"),\"\")","v":""},{"$f":"IF(R10<>\"\",IF(U69=\"Mountainous\",Tool!F99,\"\"),\"\")","v":""},{"$f":"IF(U69=\"Mountainous\",T69-S69,\"\")","v":""},null,"Sidewalk Length - Rolling:",{"$f":"F79","v":0},{"$f":"AG26","v":4.9804691576092077},5,{"$f":"((AB69*5280)*AC69*AD69)/27","v":0}]
[null,{"$f":"IF(AND(E46>=23,E46<=30),23,\"\")","v":""},{"$f":"IF(D30>=$C$2,\"\",IF($C$2<(Tool!E85-Tool!$D$64),\"\",IF(Tool!D86<>\"\",IF(Tool!$D$64<>0,Tool!E85-Tool!$D$64,Tool!E85),\"\")))","v":""},{"$f":"IF(C31=\"\",\"\",IF(B32=\"\",$C$2,IF((D30-$C$9)>=$C$2,\"\",IF(Tool!E85<>\"\",IF(AND($C$2>=(Tool!E86-Tool!$D$64),(Tool!E87-Tool!$D$64)>=(Tool!E86-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E86-Tool!$D$64,Tool!E86),$C$2),\"\"))))","v":""},{"$f":"IF(C70=\"\",\"\",IF(B70<>\"\",IF(Tool!N86=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E70=\"Rolling\",IF(Tool!I86>Tool!G86,0,IF(Tool!G86>0,Tool!G86+J70,\"\")),\"\")","v":""},{"$f":"IF(E70=\"Rolling\",IF(Tool!H86>0,Tool!H86,\"\"),\"\")","v":""},{"$f":"IF(E70=\"Rolling\",IF(Tool!I86>Tool!G86,Tool!G86,IF(Tool!I86>=0,Tool!I86)),\"\")","v":""},{"$f":"IF(E70=\"Rolling\",Tool!O86,\"\")","v":""},{"$f":"IF(AND(K70=\"Urban/C&G\",E70=\"Rolling\",Tool!L86=\"Both Sides\",Tool!M86=\"Both Sides\"),Tool!$M$62*2,IF(AND(K70=\"Urban/C&G\",E70=\"Rolling\",Tool!L86=\"Both Sides\",Tool!M86=\"One Side\"),Tool!$M$62,IF(AND(K70=\"Urban/C&G\",E70=\"Rolling\",Tool!L86=\"One Side\",Tool!M86=\"Both Sides\"),Tool!$M$62,IF(AND(K70=\"Urban/C&G\",E70=\"Rolling\",Tool!L86=\"One Side\",Tool!M86=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E70=\"Rolling\",Tool!K86,\"\")","v":""},{"$f":"IF(E70<>\"\",Drainage!G68,\"\")","v":""},"",{"$f":"IF(AND(F70=H70,G70=\"\"),\"\",VLOOKUP(Tool!P86,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S66>=3,S66<=20),3,\"\")","v":""},{"$f":"IF(R11<>\"\",IF(T10>=$C$2,\"\",IF($C$2<(Tool!E99-Tool!$D$98),\"\",IF(Tool!D100<>\"\",IF(Tool!$D$98<>0,Tool!E99-Tool!$D$98,Tool!E99),\"\"))),\"\")","v":""},{"$f":"IF(S70=\"\",\"\",IF(R11=\"\",\"\",IF(Tool!E99<>\"\",IF(AND($C$2>=(Tool!E100-Tool!$D$98),(Tool!E101-Tool!$D$98)>=(Tool!E100-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E100-Tool!$D$98,Tool!E100),$C$2),\"\")))","v":""},{"$f":"IF(R70<>\"\",IF(Tool!H100=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U70=\"Mountainous\",Tool!I100>0),Tool!I100,\"\")","v":""},{"$f":"IF(U70=\"Mountainous\",IF(Tool!J100>0,IF(Tool!F100=\"Barrier Wall\",3,IF(Tool!F100=\"Depressed Grass\",Tool!J100*0.5,Tool!J100)),\"\"),\"\")","v":""},{"$f":"IF(R11<>\"\",IF(U70=\"Mountainous\",Tool!F100,\"\"),\"\")","v":""},"",null,"Sidewalk Length - Mountainous:",{"$f":"F119","v":0},{"$f":"AG27","v":9},5,0]
[null,{"$f":"IF(AND(E46>=24,E46<=30),24,\"\")","v":""},{"$f":"IF(D31>=$C$2,\"\",IF($C$2<(Tool!E86-Tool!$D$64),\"\",IF(Tool!D87<>\"\",IF(Tool!$D$64<>0,Tool!E86-Tool!$D$64,Tool!E86),\"\")))","v":""},{"$f":"IF(C32=\"\",\"\",IF(B33=\"\",$C$2,IF((D31-$C$9)>=$C$2,\"\",IF(Tool!E86<>\"\",IF(AND($C$2>=(Tool!E87-Tool!$D$64),(Tool!E88-Tool!$D$64)>=(Tool!E87-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E87-Tool!$D$64,Tool!E87),$C$2),\"\"))))","v":""},{"$f":"IF(C71=\"\",\"\",IF(B71<>\"\",IF(Tool!N87=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E71=\"Rolling\",IF(Tool!I87>Tool!G87,0,IF(Tool!G87>0,Tool!G87+J71,\"\")),\"\")","v":""},{"$f":"IF(E71=\"Rolling\",IF(Tool!H87>0,Tool!H87,\"\"),\"\")","v":""},{"$f":"IF(E71=\"Rolling\",IF(Tool!I87>Tool!G87,Tool!G87,IF(Tool!I87>=0,Tool!I87)),\"\")","v":""},{"$f":"IF(E71=\"Rolling\",Tool!O87,\"\")","v":""},{"$f":"IF(AND(K71=\"Urban/C&G\",E71=\"Rolling\",Tool!L87=\"Both Sides\",Tool!M87=\"Both Sides\"),Tool!$M$62*2,IF(AND(K71=\"Urban/C&G\",E71=\"Rolling\",Tool!L87=\"Both Sides\",Tool!M87=\"One Side\"),Tool!$M$62,IF(AND(K71=\"Urban/C&G\",E71=\"Rolling\",Tool!L87=\"One Side\",Tool!M87=\"Both Sides\"),Tool!$M$62,IF(AND(K71=\"Urban/C&G\",E71=\"Rolling\",Tool!L87=\"One Side\",Tool!M87=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E71=\"Rolling\",Tool!K87,\"\")","v":""},{"$f":"IF(E71<>\"\",Drainage!G69,\"\")","v":""},"",{"$f":"IF(AND(F71=H71,G71=\"\"),\"\",VLOOKUP(Tool!P87,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S66>=4,S66<=20),4,\"\")","v":""},{"$f":"IF(R12<>\"\",IF(T11>=$C$2,\"\",IF($C$2<(Tool!E100-Tool!$D$98),\"\",IF(Tool!D101<>\"\",IF(Tool!$D$98<>0,Tool!E100-Tool!$D$98,Tool!E100),\"\"))),\"\")","v":""},{"$f":"IF(S71=\"\",\"\",IF(R12=\"\",\"\",IF(Tool!E100<>\"\",IF(AND($C$2>=(Tool!E101-Tool!$D$98),(Tool!E102-Tool!$D$98)>=(Tool!E101-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E101-Tool!$D$98,Tool!E101),$C$2),\"\")))","v":""},{"$f":"IF(R71<>\"\",IF(Tool!H101=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U71=\"Mountainous\",Tool!I101>0),Tool!I101,\"\")","v":""},{"$f":"IF(U71=\"Mountainous\",IF(Tool!J101>0,IF(Tool!F101=\"Barrier Wall\",3,IF(Tool!F101=\"Depressed Grass\",Tool!J101*0.5,Tool!J101)),\"\"),\"\")","v":""},{"$f":"IF(R12<>\"\",IF(U71=\"Mountainous\",Tool!F101,\"\"),\"\")","v":""},"",null,"Sidewalk Length - HM:",{"$f":"F159","v":0},{"$f":"AG28","v":16.018039252929434},5,0]
[null,{"$f":"IF(AND(E46>=25,E46<=30),25,\"\")","v":""},{"$f":"IF(D32>=$C$2,\"\",IF($C$2<(Tool!E87-Tool!$D$64),\"\",IF(Tool!D88<>\"\",IF(Tool!$D$64<>0,Tool!E87-Tool!$D$64,Tool!E87),\"\")))","v":""},{"$f":"IF(C33=\"\",\"\",IF(B34=\"\",$C$2,IF((D32-$C$9)>=$C$2,\"\",IF(Tool!E87<>\"\",IF(AND($C$2>=(Tool!E88-Tool!$D$64),(Tool!E89-Tool!$D$64)>=(Tool!E88-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E88-Tool!$D$64,Tool!E88),$C$2),\"\"))))","v":""},{"$f":"IF(C72=\"\",\"\",IF(B72<>\"\",IF(Tool!N88=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E72=\"Rolling\",IF(Tool!I88>Tool!G88,0,IF(Tool!G88>0,Tool!G88+J72,\"\")),\"\")","v":""},{"$f":"IF(E72=\"Rolling\",IF(Tool!H88>0,Tool!H88,\"\"),\"\")","v":""},{"$f":"IF(E72=\"Rolling\",IF(Tool!I88>Tool!G88,Tool!G88,IF(Tool!I88>=0,Tool!I88)),\"\")","v":""},{"$f":"IF(E72=\"Rolling\",Tool!O88,\"\")","v":""},{"$f":"IF(AND(K72=\"Urban/C&G\",E72=\"Rolling\",Tool!L88=\"Both Sides\",Tool!M88=\"Both Sides\"),Tool!$M$62*2,IF(AND(K72=\"Urban/C&G\",E72=\"Rolling\",Tool!L88=\"Both Sides\",Tool!M88=\"One Side\"),Tool!$M$62,IF(AND(K72=\"Urban/C&G\",E72=\"Rolling\",Tool!L88=\"One Side\",Tool!M88=\"Both Sides\"),Tool!$M$62,IF(AND(K72=\"Urban/C&G\",E72=\"Rolling\",Tool!L88=\"One Side\",Tool!M88=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E72=\"Rolling\",Tool!K88,\"\")","v":""},{"$f":"IF(E72<>\"\",Drainage!G70,\"\")","v":""},"",{"$f":"IF(AND(F72=H72,G72=\"\"),\"\",VLOOKUP(Tool!P88,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S66>=5,S66<=20),5,\"\")","v":""},{"$f":"IF(R13<>\"\",IF(T12>=$C$2,\"\",IF($C$2<(Tool!E101-Tool!$D$98),\"\",IF(Tool!D102<>\"\",IF(Tool!$D$98<>0,Tool!E101-Tool!$D$98,Tool!E101),\"\"))),\"\")","v":""},{"$f":"IF(S72=\"\",\"\",IF(R13=\"\",\"\",IF(Tool!E101<>\"\",IF(AND($C$2>=(Tool!E102-Tool!$D$98),(Tool!E103-Tool!$D$98)>=(Tool!E102-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E102-Tool!$D$98,Tool!E102),$C$2),\"\")))","v":""},{"$f":"IF(R72<>\"\",IF(Tool!H102=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U72=\"Mountainous\",Tool!I102>0),Tool!I102,\"\")","v":""},{"$f":"IF(U72=\"Mountainous\",IF(Tool!J102>0,IF(Tool!F102=\"Barrier Wall\",3,IF(Tool!F102=\"Depressed Grass\",Tool!J102*0.5,Tool!J102)),\"\"),\"\")","v":""},{"$f":"IF(R13<>\"\",IF(U72=\"Mountainous\",Tool!F102,\"\"),\"\")","v":""},"",null,"Total:",null,null,null,{"$f":"SUM(AE68:AE71)","v":0}]
[null,{"$f":"IF(AND(E46>=26,E46<=30),26,\"\")","v":""},{"$f":"IF(D33>=$C$2,\"\",IF($C$2<(Tool!E88-Tool!$D$64),\"\",IF(Tool!D89<>\"\",IF(Tool!$D$64<>0,Tool!E88-Tool!$D$64,Tool!E88),\"\")))","v":""},{"$f":"IF(C34=\"\",\"\",IF(B35=\"\",$C$2,IF((D33-$C$9)>=$C$2,\"\",IF(Tool!E88<>\"\",IF(AND($C$2>=(Tool!E89-Tool!$D$64),(Tool!E90-Tool!$D$64)>=(Tool!E89-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E89-Tool!$D$64,Tool!E89),$C$2),\"\"))))","v":""},{"$f":"IF(C73=\"\",\"\",IF(B73<>\"\",IF(Tool!N89=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E73=\"Rolling\",IF(Tool!I89>Tool!G89,0,IF(Tool!G89>0,Tool!G89+J73,\"\")),\"\")","v":""},{"$f":"IF(E73=\"Rolling\",IF(Tool!H89>0,Tool!H89,\"\"),\"\")","v":""},{"$f":"IF(E73=\"Rolling\",IF(Tool!I89>Tool!G89,Tool!G89,IF(Tool!I89>=0,Tool!I89)),\"\")","v":""},{"$f":"IF(E73=\"Rolling\",Tool!O89,\"\")","v":""},{"$f":"IF(AND(K73=\"Urban/C&G\",E73=\"Rolling\",Tool!L89=\"Both Sides\",Tool!M89=\"Both Sides\"),Tool!$M$62*2,IF(AND(K73=\"Urban/C&G\",E73=\"Rolling\",Tool!L89=\"Both Sides\",Tool!M89=\"One Side\"),Tool!$M$62,IF(AND(K73=\"Urban/C&G\",E73=\"Rolling\",Tool!L89=\"One Side\",Tool!M89=\"Both Sides\"),Tool!$M$62,IF(AND(K73=\"Urban/C&G\",E73=\"Rolling\",Tool!L89=\"One Side\",Tool!M89=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E73=\"Rolling\",Tool!K89,\"\")","v":""},{"$f":"IF(E73<>\"\",Drainage!G71,\"\")","v":""},"",{"$f":"IF(AND(F73=H73,G73=\"\"),\"\",VLOOKUP(Tool!P89,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S66>=6,S66<=20),6,\"\")","v":""},{"$f":"IF(R14<>\"\",IF(T13>=$C$2,\"\",IF($C$2<(Tool!E102-Tool!$D$98),\"\",IF(Tool!D103<>\"\",IF(Tool!$D$98<>0,Tool!E102-Tool!$D$98,Tool!E102),\"\"))),\"\")","v":""},{"$f":"IF(S73=\"\",\"\",IF(R14=\"\",\"\",IF(Tool!E102<>\"\",IF(AND($C$2>=(Tool!E103-Tool!$D$98),(Tool!E104-Tool!$D$98)>=(Tool!E103-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E103-Tool!$D$98,Tool!E103),$C$2),\"\")))","v":""},{"$f":"IF(R73<>\"\",IF(Tool!H103=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U73=\"Mountainous\",Tool!I103>0),Tool!I103,\"\")","v":""},{"$f":"IF(U73=\"Mountainous\",IF(Tool!J103>0,IF(Tool!F103=\"Barrier Wall\",3,IF(Tool!F103=\"Depressed Grass\",Tool!J103*0.5,Tool!J103)),\"\"),\"\")","v":""},{"$f":"IF(R14<>\"\",IF(U73=\"Mountainous\",Tool!F103,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E46>=27,E46<=30),27,\"\")","v":""},{"$f":"IF(D34>=$C$2,\"\",IF($C$2<(Tool!E89-Tool!$D$64),\"\",IF(Tool!D90<>\"\",IF(Tool!$D$64<>0,Tool!E89-Tool!$D$64,Tool!E89),\"\")))","v":""},{"$f":"IF(C35=\"\",\"\",IF(B36=\"\",$C$2,IF((D34-$C$9)>=$C$2,\"\",IF(Tool!E89<>\"\",IF(AND($C$2>=(Tool!E90-Tool!$D$64),(Tool!E91-Tool!$D$64)>=(Tool!E90-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E90-Tool!$D$64,Tool!E90),$C$2),\"\"))))","v":""},{"$f":"IF(C74=\"\",\"\",IF(B74<>\"\",IF(Tool!N90=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E74=\"Rolling\",IF(Tool!I90>Tool!G90,0,IF(Tool!G90>0,Tool!G90+J74,\"\")),\"\")","v":""},{"$f":"IF(E74=\"Rolling\",IF(Tool!H90>0,Tool!H90,\"\"),\"\")","v":""},{"$f":"IF(E74=\"Rolling\",IF(Tool!I90>Tool!G90,Tool!G90,IF(Tool!I90>=0,Tool!I90)),\"\")","v":""},{"$f":"IF(E74=\"Rolling\",Tool!O90,\"\")","v":""},{"$f":"IF(AND(K74=\"Urban/C&G\",E74=\"Rolling\",Tool!L90=\"Both Sides\",Tool!M90=\"Both Sides\"),Tool!$M$62*2,IF(AND(K74=\"Urban/C&G\",E74=\"Rolling\",Tool!L90=\"Both Sides\",Tool!M90=\"One Side\"),Tool!$M$62,IF(AND(K74=\"Urban/C&G\",E74=\"Rolling\",Tool!L90=\"One Side\",Tool!M90=\"Both Sides\"),Tool!$M$62,IF(AND(K74=\"Urban/C&G\",E74=\"Rolling\",Tool!L90=\"One Side\",Tool!M90=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E74=\"Rolling\",Tool!K90,\"\")","v":""},{"$f":"IF(E74<>\"\",Drainage!G72,\"\")","v":""},"",{"$f":"IF(AND(F74=H74,G74=\"\"),\"\",VLOOKUP(Tool!P90,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S66>=7,S66<=20),7,\"\")","v":""},{"$f":"IF(R15<>\"\",IF(T14>=$C$2,\"\",IF($C$2<(Tool!E103-Tool!$D$98),\"\",IF(Tool!D104<>\"\",IF(Tool!$D$98<>0,Tool!E103-Tool!$D$98,Tool!E103),\"\"))),\"\")","v":""},{"$f":"IF(S74=\"\",\"\",IF(R15=\"\",\"\",IF(Tool!E103<>\"\",IF(AND($C$2>=(Tool!E104-Tool!$D$98),(Tool!E105-Tool!$D$98)>=(Tool!E104-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E104-Tool!$D$98,Tool!E104),$C$2),\"\")))","v":""},{"$f":"IF(R74<>\"\",IF(Tool!H104=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U74=\"Mountainous\",Tool!I104>0),Tool!I104,\"\")","v":""},{"$f":"IF(U74=\"Mountainous\",IF(Tool!J104>0,IF(Tool!F104=\"Barrier Wall\",3,IF(Tool!F104=\"Depressed Grass\",Tool!J104*0.5,Tool!J104)),\"\"),\"\")","v":""},{"$f":"IF(R15<>\"\",IF(U74=\"Mountainous\",Tool!F104,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E46>=28,E46<=30),28,\"\")","v":""},{"$f":"IF(D35>=$C$2,\"\",IF($C$2<(Tool!E90-Tool!$D$64),\"\",IF(Tool!D91<>\"\",IF(Tool!$D$64<>0,Tool!E90-Tool!$D$64,Tool!E90),\"\")))","v":""},{"$f":"IF(C36=\"\",\"\",IF(B37=\"\",$C$2,IF((D35-$C$9)>=$C$2,\"\",IF(Tool!E90<>\"\",IF(AND($C$2>=(Tool!E91-Tool!$D$64),(Tool!E92-Tool!$D$64)>=(Tool!E91-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E91-Tool!$D$64,Tool!E91),$C$2),\"\"))))","v":""},{"$f":"IF(C75=\"\",\"\",IF(B75<>\"\",IF(Tool!N91=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E75=\"Rolling\",IF(Tool!I91>Tool!G91,0,IF(Tool!G91>0,Tool!G91+J75,\"\")),\"\")","v":""},{"$f":"IF(E75=\"Rolling\",IF(Tool!H91>0,Tool!H91,\"\"),\"\")","v":""},{"$f":"IF(E75=\"Rolling\",IF(Tool!I91>Tool!G91,Tool!G91,IF(Tool!I91>=0,Tool!I91)),\"\")","v":""},{"$f":"IF(E75=\"Rolling\",Tool!O91,\"\")","v":""},{"$f":"IF(AND(K75=\"Urban/C&G\",E75=\"Rolling\",Tool!L91=\"Both Sides\",Tool!M91=\"Both Sides\"),Tool!$M$62*2,IF(AND(K75=\"Urban/C&G\",E75=\"Rolling\",Tool!L91=\"Both Sides\",Tool!M91=\"One Side\"),Tool!$M$62,IF(AND(K75=\"Urban/C&G\",E75=\"Rolling\",Tool!L91=\"One Side\",Tool!M91=\"Both Sides\"),Tool!$M$62,IF(AND(K75=\"Urban/C&G\",E75=\"Rolling\",Tool!L91=\"One Side\",Tool!M91=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E75=\"Rolling\",Tool!K91,\"\")","v":""},{"$f":"IF(E75<>\"\",Drainage!G73,\"\")","v":""},"",{"$f":"IF(AND(F75=H75,G75=\"\"),\"\",VLOOKUP(Tool!P91,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S66>=8,S66<=20),8,\"\")","v":""},{"$f":"IF(R16<>\"\",IF(T15>=$C$2,\"\",IF($C$2<(Tool!E104-Tool!$D$98),\"\",IF(Tool!D105<>\"\",IF(Tool!$D$98<>0,Tool!E104-Tool!$D$98,Tool!E104),\"\"))),\"\")","v":""},{"$f":"IF(S75=\"\",\"\",IF(R16=\"\",\"\",IF(Tool!E104<>\"\",IF(AND($C$2>=(Tool!E105-Tool!$D$98),(Tool!E106-Tool!$D$98)>=(Tool!E105-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E105-Tool!$D$98,Tool!E105),$C$2),\"\")))","v":""},{"$f":"IF(R75<>\"\",IF(Tool!H105=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U75=\"Mountainous\",Tool!I105>0),Tool!I105,\"\")","v":""},{"$f":"IF(U75=\"Mountainous\",IF(Tool!J105>0,IF(Tool!F105=\"Barrier Wall\",3,IF(Tool!F105=\"Depressed Grass\",Tool!J105*0.5,Tool!J105)),\"\"),\"\")","v":""},{"$f":"IF(R16<>\"\",IF(U75=\"Mountainous\",Tool!F105,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E46>=29,E46<=30),29,\"\")","v":""},{"$f":"IF(D36>=$C$2,\"\",IF($C$2<(Tool!E91-Tool!$D$64),\"\",IF(Tool!D92<>\"\",IF(Tool!$D$64<>0,Tool!E91-Tool!$D$64,Tool!E91),\"\")))","v":""},{"$f":"IF(C37=\"\",\"\",IF(B38=\"\",$C$2,IF((D36-$C$9)>=$C$2,\"\",IF(Tool!E91<>\"\",IF(AND($C$2>=(Tool!E92-Tool!$D$64),(Tool!E93-Tool!$D$64)>=(Tool!E92-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E92-Tool!$D$64,Tool!E92),$C$2),\"\"))))","v":""},{"$f":"IF(C76=\"\",\"\",IF(B76<>\"\",IF(Tool!N92=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E76=\"Rolling\",IF(Tool!I92>Tool!G92,0,IF(Tool!G92>0,Tool!G92+J76,\"\")),\"\")","v":""},{"$f":"IF(E76=\"Rolling\",IF(Tool!H92>0,Tool!H92,\"\"),\"\")","v":""},{"$f":"IF(E76=\"Rolling\",IF(Tool!I92>Tool!G92,Tool!G92,IF(Tool!I92>=0,Tool!I92)),\"\")","v":""},{"$f":"IF(E76=\"Rolling\",Tool!O92,\"\")","v":""},{"$f":"IF(AND(K76=\"Urban/C&G\",E76=\"Rolling\",Tool!L92=\"Both Sides\",Tool!M92=\"Both Sides\"),Tool!$M$62*2,IF(AND(K76=\"Urban/C&G\",E76=\"Rolling\",Tool!L92=\"Both Sides\",Tool!M92=\"One Side\"),Tool!$M$62,IF(AND(K76=\"Urban/C&G\",E76=\"Rolling\",Tool!L92=\"One Side\",Tool!M92=\"Both Sides\"),Tool!$M$62,IF(AND(K76=\"Urban/C&G\",E76=\"Rolling\",Tool!L92=\"One Side\",Tool!M92=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E76=\"Rolling\",Tool!K92,\"\")","v":""},{"$f":"IF(E76<>\"\",Drainage!G74,\"\")","v":""},"",{"$f":"IF(AND(F76=H76,G76=\"\"),\"\",VLOOKUP(Tool!P92,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S66>=9,S66<=20),9,\"\")","v":""},{"$f":"IF(R17<>\"\",IF(T16>=$C$2,\"\",IF($C$2<(Tool!E105-Tool!$D$98),\"\",IF(Tool!D106<>\"\",IF(Tool!$D$98<>0,Tool!E105-Tool!$D$98,Tool!E105),\"\"))),\"\")","v":""},{"$f":"IF(S76=\"\",\"\",IF(R17=\"\",\"\",IF(Tool!E105<>\"\",IF(AND($C$2>=(Tool!E106-Tool!$D$98),(Tool!E107-Tool!$D$98)>=(Tool!E106-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E106-Tool!$D$98,Tool!E106),$C$2),\"\")))","v":""},{"$f":"IF(R76<>\"\",IF(Tool!H106=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U76=\"Mountainous\",Tool!I106>0),Tool!I106,\"\")","v":""},{"$f":"IF(U76=\"Mountainous\",IF(Tool!J106>0,IF(Tool!F106=\"Barrier Wall\",3,IF(Tool!F106=\"Depressed Grass\",Tool!J106*0.5,Tool!J106)),\"\"),\"\")","v":""},{"$f":"IF(R17<>\"\",IF(U76=\"Mountainous\",Tool!F106,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(E46=30,30,\"\")","v":""},{"$f":"IF(D37>=$C$2,\"\",IF($C$2<(Tool!E92-Tool!$D$64),\"\",IF(Tool!D93<>\"\",IF(Tool!$D$64<>0,Tool!E92-Tool!$D$64,Tool!E92),\"\")))","v":""},{"$f":"IF(C38=\"\",\"\",IF(B39=\"\",$C$2,IF((D37-$C$9)>=$C$2,\"\",IF(Tool!E92<>\"\",IF(AND($C$2>=(Tool!E93-Tool!$D$64),(Tool!E94-Tool!$D$64)>=(Tool!E93-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E93-Tool!$D$64,Tool!E93),$C$2),\"\"))))","v":""},{"$f":"IF(C77=\"\",\"\",IF(B77<>\"\",IF(Tool!N93=Tool!$E$8,\"Rolling\",\"\"),\"\"))","v":""},{"$f":"IF(E77=\"Rolling\",IF(Tool!I93>Tool!G93,0,IF(Tool!G93>0,Tool!G93+J77,\"\")),\"\")","v":""},{"$f":"IF(E77=\"Rolling\",IF(Tool!H93>0,Tool!H93,\"\"),\"\")","v":""},{"$f":"IF(E77=\"Rolling\",IF(Tool!I93>Tool!G93,Tool!G93,IF(Tool!I93>=0,Tool!I93)),\"\")","v":""},{"$f":"IF(E77=\"Rolling\",Tool!O93,\"\")","v":""},{"$f":"IF(AND(K77=\"Urban/C&G\",E77=\"Rolling\",Tool!L93=\"Both Sides\",Tool!M93=\"Both Sides\"),Tool!$M$62*2,IF(AND(K77=\"Urban/C&G\",E77=\"Rolling\",Tool!L93=\"Both Sides\",Tool!M93=\"One Side\"),Tool!$M$62,IF(AND(K77=\"Urban/C&G\",E77=\"Rolling\",Tool!L93=\"One Side\",Tool!M93=\"Both Sides\"),Tool!$M$62,IF(AND(K77=\"Urban/C&G\",E77=\"Rolling\",Tool!L93=\"One Side\",Tool!M93=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E77=\"Rolling\",Tool!K93,\"\")","v":""},{"$f":"IF(E77<>\"\",Drainage!G75,\"\")","v":""},"",{"$f":"IF(AND(F77=H77,G77=\"\"),\"\",VLOOKUP(Tool!P93,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S66>=10,S66<=20),10,\"\")","v":""},{"$f":"IF(R18<>\"\",IF(T17>=$C$2,\"\",IF($C$2<(Tool!E106-Tool!$D$98),\"\",IF(Tool!D107<>\"\",IF(Tool!$D$98<>0,Tool!E106-Tool!$D$98,Tool!E106),\"\"))),\"\")","v":""},{"$f":"IF(S77=\"\",\"\",IF(R18=\"\",\"\",IF(Tool!E106<>\"\",IF(AND($C$2>=(Tool!E107-Tool!$D$98),(Tool!E108-Tool!$D$98)>=(Tool!E107-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E107-Tool!$D$98,Tool!E107),$C$2),\"\")))","v":""},{"$f":"IF(R77<>\"\",IF(Tool!H107=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U77=\"Mountainous\",Tool!I107>0),Tool!I107,\"\")","v":""},{"$f":"IF(U77=\"Mountainous\",IF(Tool!J107>0,IF(Tool!F107=\"Barrier Wall\",3,IF(Tool!F107=\"Depressed Grass\",Tool!J107*0.5,Tool!J107)),\"\"),\"\")","v":""},{"$f":"IF(R18<>\"\",IF(U77=\"Mountainous\",Tool!F107,\"\"),\"\")","v":""},""]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(S66>=11,S66<=20),11,\"\")","v":""},{"$f":"IF(R19<>\"\",IF(T18>=$C$2,\"\",IF($C$2<(Tool!E107-Tool!$D$98),\"\",IF(Tool!D108<>\"\",IF(Tool!$D$98<>0,Tool!E107-Tool!$D$98,Tool!E107),\"\"))),\"\")","v":""},{"$f":"IF(S78=\"\",\"\",IF(R19=\"\",\"\",IF(Tool!E107<>\"\",IF(AND($C$2>=(Tool!E108-Tool!$D$98),(Tool!E109-Tool!$D$98)>=(Tool!E108-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E108-Tool!$D$98,Tool!E108),$C$2),\"\")))","v":""},{"$f":"IF(R78<>\"\",IF(Tool!H108=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U78=\"Mountainous\",Tool!I108>0),Tool!I108,\"\")","v":""},{"$f":"IF(U78=\"Mountainous\",IF(Tool!J108>0,IF(Tool!F108=\"Barrier Wall\",3,IF(Tool!F108=\"Depressed Grass\",Tool!J108*0.5,Tool!J108)),\"\"),\"\")","v":""},{"$f":"IF(R19<>\"\",IF(U78=\"Mountainous\",Tool!F108,\"\"),\"\")","v":""},""]
[null,"Rural - Length - One Side",{"$f":"SUMIFS(Q48:Q77,K48:K77,\"Rural/Ditch\",I48:I77,\"One Side\")","v":0},null,"Sidewalk Length - Rolling:",{"$f":"SUMPRODUCT(L48:L77,Q48:Q77)","v":0},null,"Avg. Rd. Width:",{"$f":"IF(SUM(Q48:Q77),SUMPRODUCT(F48:F77,Q48:Q77)/SUM(Q48:Q77),0)","v":0},null,null,"Rural - Slope Rate - One Side:",{"$f":"IFERROR(SUMIFS(O48:O77,I48:I77,\"One Side\",K48:K77,\"Rural/Ditch\")/SUMIFS(M48:M77,I48:I77,\"One Side\",K48:K77,\"Rural/Ditch\"),0)","v":0},null,"Guardrail Length",{"$f":"SUM(P48:P77)","v":0},null,{"$f":"IF(AND(S66>=12,S66<=20),12,\"\")","v":""},{"$f":"IF(R20<>\"\",IF(T19>=$C$2,\"\",IF($C$2<(Tool!E108-Tool!$D$98),\"\",IF(Tool!D109<>\"\",IF(Tool!$D$98<>0,Tool!E108-Tool!$D$98,Tool!E108),\"\"))),\"\")","v":""},{"$f":"IF(S79=\"\",\"\",IF(R20=\"\",\"\",IF(Tool!E108<>\"\",IF(AND($C$2>=(Tool!E109-Tool!$D$98),(Tool!E110-Tool!$D$98)>=(Tool!E109-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E109-Tool!$D$98,Tool!E109),$C$2),\"\")))","v":""},{"$f":"IF(R79<>\"\",IF(Tool!H109=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U79=\"Mountainous\",Tool!I109>0),Tool!I109,\"\")","v":""},{"$f":"IF(U79=\"Mountainous\",IF(Tool!J109>0,IF(Tool!F109=\"Barrier Wall\",3,IF(Tool!F109=\"Depressed Grass\",Tool!J109*0.5,Tool!J109)),\"\"),\"\")","v":""},{"$f":"IF(R20<>\"\",IF(U79=\"Mountainous\",Tool!F109,\"\"),\"\")","v":""},""]
[null,"Rural - Length - Both Sides",{"$f":"SUMIFS(Q48:Q77,K48:K77,\"Rural/Ditch\",I48:I77,\"Both Sides\")","v":0},null,"Rural Slope Length - One Sides:",{"$f":"SUMIFS(M48:M77,I48:I77,\"One Side\",K48:K77,\"Rural/Ditch\")","v":0},null,"Avg. Retained Width:",{"$f":"IF(SUM(Q48:Q77)>0,SUMPRODUCT(H48:H77,Q48:Q77)/SUM(Q48:Q77),0)","v":0},null,null,"Rural - Slope Rate - Both Sides:",{"$f":"IFERROR(SUMIFS(O48:O77,I48:I77,\"Both Sides\",K48:K77,\"Rural/Ditch\")/SUMIFS(M48:M77,I48:I77,\"Both Sides\",K48:K77,\"Rural/Ditch\"),0)","v":0},null,null,null,null,{"$f":"IF(AND(S66>=13,S66<=20),13,\"\")","v":""},{"$f":"IF(R21<>\"\",IF(T20>=$C$2,\"\",IF($C$2<(Tool!E109-Tool!$D$98),\"\",IF(Tool!D110<>\"\",IF(Tool!$D$98<>0,Tool!E109-Tool!$D$98,Tool!E109),\"\"))),\"\")","v":""},{"$f":"IF(S80=\"\",\"\",IF(R21=\"\",\"\",IF(Tool!E109<>\"\",IF(AND($C$2>=(Tool!E110-Tool!$D$98),(Tool!E111-Tool!$D$98)>=(Tool!E110-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E110-Tool!$D$98,Tool!E110),$C$2),\"\")))","v":""},{"$f":"IF(R80<>\"\",IF(Tool!H110=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U80=\"Mountainous\",Tool!I110>0),Tool!I110,\"\")","v":""},{"$f":"IF(U80=\"Mountainous\",IF(Tool!J110>0,IF(Tool!F110=\"Barrier Wall\",3,IF(Tool!F110=\"Depressed Grass\",Tool!J110*0.5,Tool!J110)),\"\"),\"\")","v":""},{"$f":"IF(R21<>\"\",IF(U80=\"Mountainous\",Tool!F110,\"\"),\"\")","v":""},""]
[null,"Urban - Length - One Side",{"$f":"SUMIFS(Q48:Q77,K48:K77,\"Urban/C&G\",I48:I77,\"One Side\")","v":0},null,"Rural Slope Length - Both Sides:",{"$f":"SUMIFS(M48:M77,I48:I77,\"Both Sides\",K48:K77,\"Rural/Ditch\")*2","v":0},null,"Avg. Shoulder Width:",{"$f":"IF(SUM(Q48:Q77),SUMPRODUCT(G48:G77,Q48:Q77)/SUM(Q48:Q77),0)","v":0},null,null,"Urban - Slope Rate - One Side:",{"$f":"IFERROR(SUMIFS(O48:O77,I48:I77,\"One Side\",K48:K77,\"Urban/C&G\")/SUMIFS(M48:M77,I48:I77,\"One Side\",K48:K77,\"Urban/C&G\"),0)","v":0},null,null,null,null,{"$f":"IF(AND(S66>=14,S66<=20),14,\"\")","v":""},{"$f":"IF(R22<>\"\",IF(T21>=$C$2,\"\",IF($C$2<(Tool!E110-Tool!$D$98),\"\",IF(Tool!D111<>\"\",IF(Tool!$D$98<>0,Tool!E110-Tool!$D$98,Tool!E110),\"\"))),\"\")","v":""},{"$f":"IF(S81=\"\",\"\",IF(R22=\"\",\"\",IF(Tool!E110<>\"\",IF(AND($C$2>=(Tool!E111-Tool!$D$98),(Tool!E112-Tool!$D$98)>=(Tool!E111-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E111-Tool!$D$98,Tool!E111),$C$2),\"\")))","v":""},{"$f":"IF(R81<>\"\",IF(Tool!H111=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U81=\"Mountainous\",Tool!I111>0),Tool!I111,\"\")","v":""},{"$f":"IF(U81=\"Mountainous\",IF(Tool!J111>0,IF(Tool!F111=\"Barrier Wall\",3,IF(Tool!F111=\"Depressed Grass\",Tool!J111*0.5,Tool!J111)),\"\"),\"\")","v":""},{"$f":"IF(R22<>\"\",IF(U81=\"Mountainous\",Tool!F111,\"\"),\"\")","v":""},""]
[null,"Urban - Length - Both Sides",{"$f":"SUMIFS(Q48:Q77,K48:K77,\"Urban/C&G\",I48:I77,\"Both Sides\")","v":0},null,"Urban Slope Length - One Sides:",{"$f":"SUMIFS(M48:M77,I48:I77,\"One Side\",K48:K77,\"Urban/C&G\")","v":0},null,"Avg. Fill Width:",{"$f":"IF(I79>=I80,(I79+I81*2)-I80,0)","v":0},null,null,"Urban - Slope Rate - Both Sides:",{"$f":"IFERROR(SUMIFS(O48:O77,I48:I77,\"Both Sides\",K48:K77,\"Urban/C&G\")/SUMIFS(M48:M77,I48:I77,\"Both Sides\",K48:K77,\"Urban/C&G\"),0)","v":0},null,null,null,null,{"$f":"IF(AND(S66>=15,S66<=20),15,\"\")","v":""},{"$f":"IF(R23<>\"\",IF(T22>=$C$2,\"\",IF($C$2<(Tool!E111-Tool!$D$98),\"\",IF(Tool!D112<>\"\",IF(Tool!$D$98<>0,Tool!E111-Tool!$D$98,Tool!E111),\"\"))),\"\")","v":""},{"$f":"IF(S82=\"\",\"\",IF(R23=\"\",\"\",IF(Tool!E111<>\"\",IF(AND($C$2>=(Tool!E112-Tool!$D$98),(Tool!E113-Tool!$D$98)>=(Tool!E112-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E112-Tool!$D$98,Tool!E112),$C$2),\"\")))","v":""},{"$f":"IF(R82<>\"\",IF(Tool!H112=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U82=\"Mountainous\",Tool!I112>0),Tool!I112,\"\")","v":""},{"$f":"IF(U82=\"Mountainous\",IF(Tool!J112>0,IF(Tool!F112=\"Barrier Wall\",3,IF(Tool!F112=\"Depressed Grass\",Tool!J112*0.5,Tool!J112)),\"\"),\"\")","v":""},{"$f":"IF(R23<>\"\",IF(U82=\"Mountainous\",Tool!F112,\"\"),\"\")","v":""},""]
[null,null,null,null,"Urban Slope Length - Both Sides:",{"$f":"SUMIFS(M48:M77,I48:I77,\"Both Sides\",K48:K77,\"Urban/C&G\")*2","v":0},null,"Avg. Fill Area:",{"$f":"I82*SUM(Q48:Q77)*5280","v":0},null,null,null,null,null,null,null,null,{"$f":"IF(AND(S66>=16,S66<=20),16,\"\")","v":""},{"$f":"IF(R24<>\"\",IF(T23>=$C$2,\"\",IF($C$2<(Tool!E112-Tool!$D$98),\"\",IF(Tool!D113<>\"\",IF(Tool!$D$98<>0,Tool!E112-Tool!$D$98,Tool!E112),\"\"))),\"\")","v":""},{"$f":"IF(S83=\"\",\"\",IF(R24=\"\",\"\",IF(Tool!E112<>\"\",IF(AND($C$2>=(Tool!E113-Tool!$D$98),(Tool!E114-Tool!$D$98)>=(Tool!E113-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E113-Tool!$D$98,Tool!E113),$C$2),\"\")))","v":""},{"$f":"IF(R83<>\"\",IF(Tool!H113=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U83=\"Mountainous\",Tool!I113>0),Tool!I113,\"\")","v":""},{"$f":"IF(U83=\"Mountainous\",IF(Tool!J113>0,IF(Tool!F113=\"Barrier Wall\",3,IF(Tool!F113=\"Depressed Grass\",Tool!J113*0.5,Tool!J113)),\"\"),\"\")","v":""},{"$f":"IF(R24<>\"\",IF(U83=\"Mountainous\",Tool!F113,\"\"),\"\")","v":""},""]
[null,null,null,null,null,null,null,"Length:",{"$f":"SUM(Q48:Q77)","v":0},null,null,null,null,null,null,null,null,{"$f":"IF(AND(S66>=17,S66<=20),17,\"\")","v":""},{"$f":"IF(R25<>\"\",IF(T24>=$C$2,\"\",IF($C$2<(Tool!E113-Tool!$D$98),\"\",IF(Tool!D114<>\"\",IF(Tool!$D$98<>0,Tool!E113-Tool!$D$98,Tool!E113),\"\"))),\"\")","v":""},{"$f":"IF(S84=\"\",\"\",IF(R25=\"\",\"\",IF(Tool!E113<>\"\",IF(AND($C$2>=(Tool!E114-Tool!$D$98),(Tool!E115-Tool!$D$98)>=(Tool!E114-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E114-Tool!$D$98,Tool!E114),$C$2),\"\")))","v":""},{"$f":"IF(R84<>\"\",IF(Tool!H114=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U84=\"Mountainous\",Tool!I114>0),Tool!I114,\"\")","v":""},{"$f":"IF(U84=\"Mountainous\",IF(Tool!J114>0,IF(Tool!F114=\"Barrier Wall\",3,IF(Tool!F114=\"Depressed Grass\",Tool!J114*0.5,Tool!J114)),\"\"),\"\")","v":""},{"$f":"IF(R25<>\"\",IF(U84=\"Mountainous\",Tool!F114,\"\"),\"\")","v":""},""]
[null,"Mountainous Terrain",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(S66>=18,S66<=20),18,\"\")","v":""},{"$f":"IF(R26<>\"\",IF(T25>=$C$2,\"\",IF($C$2<(Tool!E114-Tool!$D$98),\"\",IF(Tool!D115<>\"\",IF(Tool!$D$98<>0,Tool!E114-Tool!$D$98,Tool!E114),\"\"))),\"\")","v":""},{"$f":"IF(S85=\"\",\"\",IF(R26=\"\",\"\",IF(Tool!E114<>\"\",IF(AND($C$2>=(Tool!E115-Tool!$D$98),(Tool!E116-Tool!$D$98)>=(Tool!E115-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E115-Tool!$D$98,Tool!E115),$C$2),\"\")))","v":""},{"$f":"IF(R85<>\"\",IF(Tool!H115=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U85=\"Mountainous\",Tool!I115>0),Tool!I115,\"\")","v":""},{"$f":"IF(U85=\"Mountainous\",IF(Tool!J115>0,IF(Tool!F115=\"Barrier Wall\",3,IF(Tool!F115=\"Depressed Grass\",Tool!J115*0.5,Tool!J115)),\"\"),\"\")","v":""},{"$f":"IF(R26<>\"\",IF(U85=\"Mountainous\",Tool!F115,\"\"),\"\")","v":""},""]
[null,"Segments:",null,null,{"$f":"Tool!$J$61","v":1},null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(AND(S66>=19,S66<=20),19,\"\")","v":""},{"$f":"IF(R27<>\"\",IF(T26>=$C$2,\"\",IF($C$2<(Tool!E115-Tool!$D$98),\"\",IF(Tool!D116<>\"\",IF(Tool!$D$98<>0,Tool!E115-Tool!$D$98,Tool!E115),\"\"))),\"\")","v":""},{"$f":"IF(S86=\"\",\"\",IF(R27=\"\",\"\",IF(Tool!E115<>\"\",IF(AND($C$2>=(Tool!E116-Tool!$D$98),(Tool!E117-Tool!$D$98)>=(Tool!E116-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E116-Tool!$D$98,Tool!E116),$C$2),\"\")))","v":""},{"$f":"IF(R86<>\"\",IF(Tool!H116=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U86=\"Mountainous\",Tool!I116>0),Tool!I116,\"\")","v":""},{"$f":"IF(U86=\"Mountainous\",IF(Tool!J116>0,IF(Tool!F116=\"Barrier Wall\",3,IF(Tool!F116=\"Depressed Grass\",Tool!J116*0.5,Tool!J116)),\"\"),\"\")","v":""},{"$f":"IF(R27<>\"\",IF(U86=\"Mountainous\",Tool!F116,\"\"),\"\")","v":""},""]
[null,"Segments","Begin (mi)","End (mi)","Terrain Type","Total Pavement Width (ft)","Outside Shldr Width (ft)","Existing Pavement Width","Widen to One Side or Both?","Grass Strip","Rural/Urban","Sidewalks","Slope Length","Slope Rate","Slope Area (ft-mi)","Guardrail Length","Length",{"$f":"IF(AND(S66=20),20,\"\")","v":""},{"$f":"IF(R28<>\"\",IF(T27>=$C$2,\"\",IF($C$2<(Tool!E116-Tool!$D$98),\"\",IF(Tool!D117<>\"\",IF(Tool!$D$98<>0,Tool!E116-Tool!$D$98,Tool!E116),\"\"))),\"\")","v":""},{"$f":"IF(S87=\"\",\"\",IF(R28=\"\",\"\",IF(Tool!E116<>\"\",IF(AND($C$2>=(Tool!E117-Tool!$D$98),(Tool!E118-Tool!$D$98)>=(Tool!E117-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E117-Tool!$D$98,Tool!E117),$C$2),\"\")))","v":""},{"$f":"IF(R87<>\"\",IF(Tool!H117=\"Mountainous\",\"Mountainous\",\"\"),\"\")","v":""},{"$f":"IF(AND(U87=\"Mountainous\",Tool!I117>0),Tool!I117,\"\")","v":""},{"$f":"IF(U87=\"Mountainous\",IF(Tool!J117>0,IF(Tool!F117=\"Barrier Wall\",3,IF(Tool!F117=\"Depressed Grass\",Tool!J117*0.5,Tool!J117)),\"\"),\"\")","v":""},{"$f":"IF(R28<>\"\",IF(U87=\"Mountainous\",Tool!F117,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E86>=1,E86<=30),1,\"\")","v":1},{"$f":"IF(Tool!D64<>\"\",IF(B9<>\"\",IF(Tool!D64=0,Tool!D64,Tool!D64-Tool!D64),\"\"),\"\")","v":""},{"$f":"IF(C88=\"\",\"\",IF((Tool!E65-Tool!D64)<(Tool!E64-Tool!D64),C2,IF(B9<>\"\",IF(Tool!E64<>\"\",IF(AND(B10=\"\",Tool!E64-Tool!D64<$C$2),$C$2,IF(B9=1,IF($C$2<(Tool!E64-Tool!$D$64),$C$2,IF(Tool!D64<>0,(Tool!E64-Tool!D64),Tool!E64)),\"\")),\"\"),\"\")))","v":""},{"$f":"IF(C88=\"\",\"\",IF(B88<>\"\",IF(Tool!N64=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E88=\"Mountainous\",IF(Tool!I64>Tool!G64,0,IF(Tool!G64>0,Tool!G64+J88,\"\")),\"\")","v":""},{"$f":"IF(E88=\"Mountainous\",IF(Tool!H64>0,Tool!H64,\"\"),\"\")","v":""},{"$f":"IF(E88=\"Mountainous\",IF(Tool!I64>Tool!G64,Tool!G64,IF(Tool!I64>=0,Tool!I64)),\"\")","v":""},{"$f":"IF(E88=\"Mountainous\",Tool!O64,\"\")","v":""},{"$f":"IF(AND(K88=\"Urban/C&G\",E88=\"Mountainous\",Tool!L64=\"Both Sides\",Tool!M64=\"Both Sides\"),Tool!$M$62*2,IF(AND(K88=\"Urban/C&G\",E88=\"Mountainous\",Tool!L64=\"Both Sides\",Tool!M64=\"One Side\"),Tool!$M$62,IF(AND(K88=\"Urban/C&G\",E88=\"Mountainous\",Tool!L64=\"One Side\",Tool!M64=\"Both Sides\"),Tool!$M$62,IF(AND(K88=\"Urban/C&G\",E88=\"Mountainous\",Tool!L64=\"One Side\",Tool!M64=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E88=\"Mountainous\",Tool!K64,\"\")","v":""},{"$f":"IF(E88<>\"\",Drainage!G46,\"\")","v":""},{"$f":"IF(AND(F88=H88,G88=\"\"),\"\",D88-C88)","v":""},{"$f":"IF(AND(F88=H88,G88=\"\"),\"\",VLOOKUP(Tool!P64,$AM$4:$AN$9,2,0))","v":""},{"$f":"IF(AND(F88=H88,G88=\"\"),\"\",M88*N88)","v":""},{"$f":"IF(AND(N88=4,I88=\"Both Sides\"),M88*0.2,IF(AND(N88=4,I88=\"One Side\"),M88*0.1,IF(AND(N88=3,I88=\"One Side\"),M88*0.3,IF(AND(N88=3,I88=\"Both Sides\"),M88*0.5,IF(AND(N88=2,I88=\"One Side\"),M88*0.5,IF(AND(N88=2,I88=\"Both Sides\"),M88,IF(AND(N88=1,I88=\"One Side\"),M88*0.75,IF(AND(N88=1,I88=\"Both Sides\"),M88,\"\"))))))))","v":""},{"$f":"IF(E88=\"Mountainous\",D88-C88,\"\")","v":""}]
[null,{"$f":"IF(AND(E86>=2,E86<=30),2,\"\")","v":""},{"$f":"IF(D9>=$C$2,\"\",IF($C$2<(Tool!E64-Tool!$D$64),\"\",IF(Tool!D65<>\"\",IF(Tool!$D$64<>0,Tool!E64-Tool!$D$64,Tool!E64),\"\")))","v":""},{"$f":"IF(C10=\"\",\"\",IF(B90=\"\",$C$2,IF((D9-$C$9)>=$C$2,\"\",IF(Tool!E64<>\"\",IF(AND($C$2>=(Tool!E65-Tool!$D$64),(Tool!E66-Tool!$D$64)>=(Tool!E65-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E65-Tool!$D$64,Tool!E65),$C$2),\"\"))))","v":""},{"$f":"IF(C89=\"\",\"\",IF(B89<>\"\",IF(Tool!N65=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E89=\"Mountainous\",IF(Tool!I65>Tool!G65,0,IF(Tool!G65>0,Tool!G65+J89,\"\")),\"\")","v":""},{"$f":"IF(E89=\"Mountainous\",IF(Tool!H65>0,Tool!H65,\"\"),\"\")","v":""},{"$f":"IF(E89=\"Mountainous\",IF(Tool!I65>Tool!G65,Tool!G65,IF(Tool!I65>=0,Tool!I65)),\"\")","v":""},{"$f":"IF(E89=\"Mountainous\",Tool!O65,\"\")","v":""},{"$f":"IF(AND(K89=\"Urban/C&G\",E89=\"Mountainous\",Tool!L65=\"Both Sides\",Tool!M65=\"Both Sides\"),Tool!$M$62*2,IF(AND(K89=\"Urban/C&G\",E89=\"Mountainous\",Tool!L65=\"Both Sides\",Tool!M65=\"One Side\"),Tool!$M$62,IF(AND(K89=\"Urban/C&G\",E89=\"Mountainous\",Tool!L65=\"One Side\",Tool!M65=\"Both Sides\"),Tool!$M$62,IF(AND(K89=\"Urban/C&G\",E89=\"Mountainous\",Tool!L65=\"One Side\",Tool!M65=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E89=\"Mountainous\",Tool!K65,\"\")","v":""},{"$f":"IF(E89<>\"\",Drainage!G47,\"\")","v":""},{"$f":"IF(AND(F89=H89,G89=\"\"),\"\",D89-C89)","v":""},{"$f":"IF(AND(F89=H89,G89=\"\"),\"\",VLOOKUP(Tool!P65,$AM$4:$AN$9,2,0))","v":""},"",{"$f":"IF(AND(N89=4,I89=\"Both Sides\"),M89*0.2,IF(AND(N89=4,I89=\"One Side\"),M89*0.1,IF(AND(N89=3,I89=\"One Side\"),M89*0.3,IF(AND(N89=3,I89=\"Both Sides\"),M89*0.5,IF(AND(N89=2,I89=\"One Side\"),M89*0.5,IF(AND(N89=2,I89=\"Both Sides\"),M89,IF(AND(N89=1,I89=\"One Side\"),M89*0.75,IF(AND(N89=1,I89=\"Both Sides\"),M89,\"\"))))))))","v":""},"",null,null,null,null,null,null,"Avg. Inside Shldr. Width:",{"$f":"IF(SUM(Y68:Y87),SUMPRODUCT(V68:V87,Y68:Y87)/SUM(Y68:Y87),0)","v":0}]
[null,{"$f":"IF(AND(E86>=3,E86<=30),3,\"\")","v":""},{"$f":"IF(D10>=$C$2,\"\",IF($C$2<(Tool!E65-Tool!$D$64),\"\",IF(Tool!D66<>\"\",IF(Tool!$D$64<>0,Tool!E65-Tool!$D$64,Tool!E65),\"\")))","v":""},{"$f":"IF(C11=\"\",\"\",IF(B91=\"\",$C$2,IF((D10-$C$9)>=$C$2,\"\",IF(Tool!E65<>\"\",IF(AND($C$2>=(Tool!E66-Tool!$D$64),(Tool!E67-Tool!$D$64)>=(Tool!E66-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E66-Tool!$D$64,Tool!E66),$C$2),\"\"))))","v":""},{"$f":"IF(C90=\"\",\"\",IF(B90<>\"\",IF(Tool!N66=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E90=\"Mountainous\",IF(Tool!I66>Tool!G66,0,IF(Tool!G66>0,Tool!G66+J90,\"\")),\"\")","v":""},{"$f":"IF(E90=\"Mountainous\",IF(Tool!H66>0,Tool!H66,\"\"),\"\")","v":""},{"$f":"IF(E90=\"Mountainous\",IF(Tool!I66>Tool!G66,Tool!G66,IF(Tool!I66>=0,Tool!I66)),\"\")","v":""},{"$f":"IF(E90=\"Mountainous\",Tool!O66,\"\")","v":""},{"$f":"IF(AND(K90=\"Urban/C&G\",E90=\"Mountainous\",Tool!L66=\"Both Sides\",Tool!M66=\"Both Sides\"),Tool!$M$62*2,IF(AND(K90=\"Urban/C&G\",E90=\"Mountainous\",Tool!L66=\"Both Sides\",Tool!M66=\"One Side\"),Tool!$M$62,IF(AND(K90=\"Urban/C&G\",E90=\"Mountainous\",Tool!L66=\"One Side\",Tool!M66=\"Both Sides\"),Tool!$M$62,IF(AND(K90=\"Urban/C&G\",E90=\"Mountainous\",Tool!L66=\"One Side\",Tool!M66=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E90=\"Mountainous\",Tool!K66,\"\")","v":""},{"$f":"IF(E90<>\"\",Drainage!G48,\"\")","v":""},"",{"$f":"IF(AND(F90=H90,G90=\"\"),\"\",VLOOKUP(Tool!P66,$AM$4:$AN$9,2,0))","v":""},"","","",null,null,null,null,null,null,"Avg. Interior Width:",{"$f":"IF(SUM(Y68:Y87)>0,SUMPRODUCT(W68:W87,Y68:Y87)/SUM(Y68:Y87),0)","v":0}]
[null,{"$f":"IF(AND(E86>=4,E86<=30),4,\"\")","v":""},{"$f":"IF(D11>=$C$2,\"\",IF($C$2<(Tool!E66-Tool!$D$64),\"\",IF(Tool!D67<>\"\",IF(Tool!$D$64<>0,Tool!E66-Tool!$D$64,Tool!E66),\"\")))","v":""},{"$f":"IF(C12=\"\",\"\",IF(B92=\"\",$C$2,IF((D11-$C$9)>=$C$2,\"\",IF(Tool!E66<>\"\",IF(AND($C$2>=(Tool!E67-Tool!$D$64),(Tool!E68-Tool!$D$64)>=(Tool!E67-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E67-Tool!$D$64,Tool!E67),$C$2),\"\"))))","v":""},{"$f":"IF(C91=\"\",\"\",IF(B91<>\"\",IF(Tool!N67=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E91=\"Mountainous\",IF(Tool!I67>Tool!G67,0,IF(Tool!G67>0,Tool!G67+J91,\"\")),\"\")","v":""},{"$f":"IF(E91=\"Mountainous\",IF(Tool!H67>0,Tool!H67,\"\"),\"\")","v":""},{"$f":"IF(E91=\"Mountainous\",IF(Tool!I67>Tool!G67,Tool!G67,IF(Tool!I67>=0,Tool!I67)),\"\")","v":""},{"$f":"IF(E91=\"Mountainous\",Tool!O67,\"\")","v":""},{"$f":"IF(AND(K91=\"Urban/C&G\",E91=\"Mountainous\",Tool!L67=\"Both Sides\",Tool!M67=\"Both Sides\"),Tool!$M$62*2,IF(AND(K91=\"Urban/C&G\",E91=\"Mountainous\",Tool!L67=\"Both Sides\",Tool!M67=\"One Side\"),Tool!$M$62,IF(AND(K91=\"Urban/C&G\",E91=\"Mountainous\",Tool!L67=\"One Side\",Tool!M67=\"Both Sides\"),Tool!$M$62,IF(AND(K91=\"Urban/C&G\",E91=\"Mountainous\",Tool!L67=\"One Side\",Tool!M67=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E91=\"Mountainous\",Tool!K67,\"\")","v":""},{"$f":"IF(E91<>\"\",Drainage!G49,\"\")","v":""},"",{"$f":"IF(AND(F91=H91,G91=\"\"),\"\",VLOOKUP(Tool!P67,$AM$4:$AN$9,2,0))","v":""},"","","",null,null,null,null,null,null,"Avg. Fill Width:",{"$f":"Y89+Y90","v":0}]
[null,{"$f":"IF(AND(E86>=5,E86<=30),5,\"\")","v":""},{"$f":"IF(D12>=$C$2,\"\",IF($C$2<(Tool!E67-Tool!$D$64),\"\",IF(Tool!D68<>\"\",IF(Tool!$D$64<>0,Tool!E67-Tool!$D$64,Tool!E67),\"\")))","v":""},{"$f":"IF(C13=\"\",\"\",IF(B93=\"\",$C$2,IF((D12-$C$9)>=$C$2,\"\",IF(Tool!E67<>\"\",IF(AND($C$2>=(Tool!E68-Tool!$D$64),(Tool!E69-Tool!$D$64)>=(Tool!E68-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E68-Tool!$D$64,Tool!E68),$C$2),\"\"))))","v":""},{"$f":"IF(C92=\"\",\"\",IF(B92<>\"\",IF(Tool!N68=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E92=\"Mountainous\",IF(Tool!I68>Tool!G68,0,IF(Tool!G68>0,Tool!G68+J92,\"\")),\"\")","v":""},{"$f":"IF(E92=\"Mountainous\",IF(Tool!H68>0,Tool!H68,\"\"),\"\")","v":""},{"$f":"IF(E92=\"Mountainous\",IF(Tool!I68>Tool!G68,Tool!G68,IF(Tool!I68>=0,Tool!I68)),\"\")","v":""},{"$f":"IF(E92=\"Mountainous\",Tool!O68,\"\")","v":""},{"$f":"IF(AND(K92=\"Urban/C&G\",E92=\"Mountainous\",Tool!L68=\"Both Sides\",Tool!M68=\"Both Sides\"),Tool!$M$62*2,IF(AND(K92=\"Urban/C&G\",E92=\"Mountainous\",Tool!L68=\"Both Sides\",Tool!M68=\"One Side\"),Tool!$M$62,IF(AND(K92=\"Urban/C&G\",E92=\"Mountainous\",Tool!L68=\"One Side\",Tool!M68=\"Both Sides\"),Tool!$M$62,IF(AND(K92=\"Urban/C&G\",E92=\"Mountainous\",Tool!L68=\"One Side\",Tool!M68=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E92=\"Mountainous\",Tool!K68,\"\")","v":""},{"$f":"IF(E92<>\"\",Drainage!G50,\"\")","v":""},"",{"$f":"IF(AND(F92=H92,G92=\"\"),\"\",VLOOKUP(Tool!P68,$AM$4:$AN$9,2,0))","v":""},"","","",null,null,null,null,null,null,"Avg. Fill Area:",{"$f":"Y91*SUM(Y68:Y87)*5280","v":0}]
[null,{"$f":"IF(AND(E86>=6,E86<=30),6,\"\")","v":""},{"$f":"IF(D13>=$C$2,\"\",IF($C$2<(Tool!E68-Tool!$D$64),\"\",IF(Tool!D69<>\"\",IF(Tool!$D$64<>0,Tool!E68-Tool!$D$64,Tool!E68),\"\")))","v":""},{"$f":"IF(C14=\"\",\"\",IF(B94=\"\",$C$2,IF((D13-$C$9)>=$C$2,\"\",IF(Tool!E68<>\"\",IF(AND($C$2>=(Tool!E69-Tool!$D$64),(Tool!E70-Tool!$D$64)>=(Tool!E69-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E69-Tool!$D$64,Tool!E69),$C$2),\"\"))))","v":""},{"$f":"IF(C93=\"\",\"\",IF(B93<>\"\",IF(Tool!N69=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E93=\"Mountainous\",IF(Tool!I69>Tool!G69,0,IF(Tool!G69>0,Tool!G69+J93,\"\")),\"\")","v":""},{"$f":"IF(E93=\"Mountainous\",IF(Tool!H69>0,Tool!H69,\"\"),\"\")","v":""},{"$f":"IF(E93=\"Mountainous\",IF(Tool!I69>Tool!G69,Tool!G69,IF(Tool!I69>=0,Tool!I69)),\"\")","v":""},{"$f":"IF(E93=\"Mountainous\",Tool!O69,\"\")","v":""},{"$f":"IF(AND(K93=\"Urban/C&G\",E93=\"Mountainous\",Tool!L69=\"Both Sides\",Tool!M69=\"Both Sides\"),Tool!$M$62*2,IF(AND(K93=\"Urban/C&G\",E93=\"Mountainous\",Tool!L69=\"Both Sides\",Tool!M69=\"One Side\"),Tool!$M$62,IF(AND(K93=\"Urban/C&G\",E93=\"Mountainous\",Tool!L69=\"One Side\",Tool!M69=\"Both Sides\"),Tool!$M$62,IF(AND(K93=\"Urban/C&G\",E93=\"Mountainous\",Tool!L69=\"One Side\",Tool!M69=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E93=\"Mountainous\",Tool!K69,\"\")","v":""},{"$f":"IF(E93<>\"\",Drainage!G51,\"\")","v":""},"",{"$f":"IF(AND(F93=H93,G93=\"\"),\"\",VLOOKUP(Tool!P69,$AM$4:$AN$9,2,0))","v":""},"","","",null,null,null,null,null,null,"Length:",{"$f":"SUM(Y68:Y87)","v":0}]
[null,{"$f":"IF(AND(E86>=7,E86<=30),7,\"\")","v":""},{"$f":"IF(D14>=$C$2,\"\",IF($C$2<(Tool!E69-Tool!$D$64),\"\",IF(Tool!D70<>\"\",IF(Tool!$D$64<>0,Tool!E69-Tool!$D$64,Tool!E69),\"\")))","v":""},{"$f":"IF(C15=\"\",\"\",IF(B95=\"\",$C$2,IF((D14-$C$9)>=$C$2,\"\",IF(Tool!E69<>\"\",IF(AND($C$2>=(Tool!E70-Tool!$D$64),(Tool!E71-Tool!$D$64)>=(Tool!E70-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E70-Tool!$D$64,Tool!E70),$C$2),\"\"))))","v":""},{"$f":"IF(C94=\"\",\"\",IF(B94<>\"\",IF(Tool!N70=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E94=\"Mountainous\",IF(Tool!I70>Tool!G70,0,IF(Tool!G70>0,Tool!G70+J94,\"\")),\"\")","v":""},{"$f":"IF(E94=\"Mountainous\",IF(Tool!H70>0,Tool!H70,\"\"),\"\")","v":""},{"$f":"IF(E94=\"Mountainous\",IF(Tool!I70>Tool!G70,Tool!G70,IF(Tool!I70>=0,Tool!I70)),\"\")","v":""},{"$f":"IF(E94=\"Mountainous\",Tool!O70,\"\")","v":""},{"$f":"IF(AND(K94=\"Urban/C&G\",E94=\"Mountainous\",Tool!L70=\"Both Sides\",Tool!M70=\"Both Sides\"),Tool!$M$62*2,IF(AND(K94=\"Urban/C&G\",E94=\"Mountainous\",Tool!L70=\"Both Sides\",Tool!M70=\"One Side\"),Tool!$M$62,IF(AND(K94=\"Urban/C&G\",E94=\"Mountainous\",Tool!L70=\"One Side\",Tool!M70=\"Both Sides\"),Tool!$M$62,IF(AND(K94=\"Urban/C&G\",E94=\"Mountainous\",Tool!L70=\"One Side\",Tool!M70=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E94=\"Mountainous\",Tool!K70,\"\")","v":""},{"$f":"IF(E94<>\"\",Drainage!G52,\"\")","v":""},"",{"$f":"IF(AND(F94=H94,G94=\"\"),\"\",VLOOKUP(Tool!P70,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E86>=8,E86<=30),8,\"\")","v":""},{"$f":"IF(D15>=$C$2,\"\",IF($C$2<(Tool!E70-Tool!$D$64),\"\",IF(Tool!D71<>\"\",IF(Tool!$D$64<>0,Tool!E70-Tool!$D$64,Tool!E70),\"\")))","v":""},{"$f":"IF(C16=\"\",\"\",IF(B96=\"\",$C$2,IF((D15-$C$9)>=$C$2,\"\",IF(Tool!E70<>\"\",IF(AND($C$2>=(Tool!E71-Tool!$D$64),(Tool!E72-Tool!$D$64)>=(Tool!E71-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E71-Tool!$D$64,Tool!E71),$C$2),\"\"))))","v":""},{"$f":"IF(C95=\"\",\"\",IF(B95<>\"\",IF(Tool!N71=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E95=\"Mountainous\",IF(Tool!I71>Tool!G71,0,IF(Tool!G71>0,Tool!G71+J95,\"\")),\"\")","v":""},{"$f":"IF(E95=\"Mountainous\",IF(Tool!H71>0,Tool!H71,\"\"),\"\")","v":""},{"$f":"IF(E95=\"Mountainous\",IF(Tool!I71>Tool!G71,Tool!G71,IF(Tool!I71>=0,Tool!I71)),\"\")","v":""},{"$f":"IF(E95=\"Mountainous\",Tool!O71,\"\")","v":""},{"$f":"IF(AND(K95=\"Urban/C&G\",E95=\"Mountainous\",Tool!L71=\"Both Sides\",Tool!M71=\"Both Sides\"),Tool!$M$62*2,IF(AND(K95=\"Urban/C&G\",E95=\"Mountainous\",Tool!L71=\"Both Sides\",Tool!M71=\"One Side\"),Tool!$M$62,IF(AND(K95=\"Urban/C&G\",E95=\"Mountainous\",Tool!L71=\"One Side\",Tool!M71=\"Both Sides\"),Tool!$M$62,IF(AND(K95=\"Urban/C&G\",E95=\"Mountainous\",Tool!L71=\"One Side\",Tool!M71=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E95=\"Mountainous\",Tool!K71,\"\")","v":""},{"$f":"IF(E95<>\"\",Drainage!G53,\"\")","v":""},"",{"$f":"IF(AND(F95=H95,G95=\"\"),\"\",VLOOKUP(Tool!P71,$AM$4:$AN$9,2,0))","v":""},"","","","Heavy Mountainous Terrain"]
[null,{"$f":"IF(AND(E86>=9,F86<=20),9,\"\")","v":""},{"$f":"IF(D16>=$C$2,\"\",IF($C$2<(Tool!E71-Tool!$D$64),\"\",IF(Tool!D72<>\"\",IF(Tool!$D$64<>0,Tool!E71-Tool!$D$64,Tool!E71),\"\")))","v":""},{"$f":"IF(C17=\"\",\"\",IF(B97=\"\",$C$2,IF((D16-$C$9)>=$C$2,\"\",IF(Tool!E71<>\"\",IF(AND($C$2>=(Tool!E72-Tool!$D$64),(Tool!E73-Tool!$D$64)>=(Tool!E72-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E72-Tool!$D$64,Tool!E72),$C$2),\"\"))))","v":""},{"$f":"IF(C96=\"\",\"\",IF(B96<>\"\",IF(Tool!N72=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E96=\"Mountainous\",IF(Tool!I72>Tool!G72,0,IF(Tool!G72>0,Tool!G72+J96,\"\")),\"\")","v":""},{"$f":"IF(E96=\"Mountainous\",IF(Tool!H72>0,Tool!H72,\"\"),\"\")","v":""},{"$f":"IF(E96=\"Mountainous\",IF(Tool!I72>Tool!G72,Tool!G72,IF(Tool!I72>=0,Tool!I72)),\"\")","v":""},{"$f":"IF(E96=\"Mountainous\",Tool!O72,\"\")","v":""},{"$f":"IF(AND(K96=\"Urban/C&G\",E96=\"Mountainous\",Tool!L72=\"Both Sides\",Tool!M72=\"Both Sides\"),Tool!$M$62*2,IF(AND(K96=\"Urban/C&G\",E96=\"Mountainous\",Tool!L72=\"Both Sides\",Tool!M72=\"One Side\"),Tool!$M$62,IF(AND(K96=\"Urban/C&G\",E96=\"Mountainous\",Tool!L72=\"One Side\",Tool!M72=\"Both Sides\"),Tool!$M$62,IF(AND(K96=\"Urban/C&G\",E96=\"Mountainous\",Tool!L72=\"One Side\",Tool!M72=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E96=\"Mountainous\",Tool!K72,\"\")","v":""},{"$f":"IF(E96<>\"\",Drainage!G54,\"\")","v":""},"",{"$f":"IF(AND(F96=H96,G96=\"\"),\"\",VLOOKUP(Tool!P72,$AM$4:$AN$9,2,0))","v":""},"","","","Segments:",{"$f":"Tool!$J$96","v":1}]
[null,{"$f":"IF(AND(E86>=10,E86<=30),10,\"\")","v":""},{"$f":"IF(D17>=$C$2,\"\",IF($C$2<(Tool!E72-Tool!$D$64),\"\",IF(Tool!D73<>\"\",IF(Tool!$D$64<>0,Tool!E72-Tool!$D$64,Tool!E72),\"\")))","v":""},{"$f":"IF(C18=\"\",\"\",IF(B98=\"\",$C$2,IF((D17-$C$9)>=$C$2,\"\",IF(Tool!E72<>\"\",IF(AND($C$2>=(Tool!E73-Tool!$D$64),(Tool!E74-Tool!$D$64)>=(Tool!E73-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E73-Tool!$D$64,Tool!E73),$C$2),\"\"))))","v":""},{"$f":"IF(C97=\"\",\"\",IF(B97<>\"\",IF(Tool!N73=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E97=\"Mountainous\",IF(Tool!I73>Tool!G73,0,IF(Tool!G73>0,Tool!G73+J97,\"\")),\"\")","v":""},{"$f":"IF(E97=\"Mountainous\",IF(Tool!H73>0,Tool!H73,\"\"),\"\")","v":""},{"$f":"IF(E97=\"Mountainous\",IF(Tool!I73>Tool!G73,Tool!G73,IF(Tool!I73>=0,Tool!I73)),\"\")","v":""},{"$f":"IF(E97=\"Mountainous\",Tool!O73,\"\")","v":""},{"$f":"IF(AND(K97=\"Urban/C&G\",E97=\"Mountainous\",Tool!L73=\"Both Sides\",Tool!M73=\"Both Sides\"),Tool!$M$62*2,IF(AND(K97=\"Urban/C&G\",E97=\"Mountainous\",Tool!L73=\"Both Sides\",Tool!M73=\"One Side\"),Tool!$M$62,IF(AND(K97=\"Urban/C&G\",E97=\"Mountainous\",Tool!L73=\"One Side\",Tool!M73=\"Both Sides\"),Tool!$M$62,IF(AND(K97=\"Urban/C&G\",E97=\"Mountainous\",Tool!L73=\"One Side\",Tool!M73=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E97=\"Mountainous\",Tool!K73,\"\")","v":""},{"$f":"IF(E97<>\"\",Drainage!G55,\"\")","v":""},"",{"$f":"IF(AND(F97=H97,G97=\"\"),\"\",VLOOKUP(Tool!P73,$AM$4:$AN$9,2,0))","v":""},"","","","Segments","Begin (mi)","End (mi)","Terrain Type","Inside Shldr. Width (ft)","Interior Width (ft)","Median Type","Length"]
[null,{"$f":"IF(AND(E86>=11,E86<=30),11,\"\")","v":""},{"$f":"IF(D18>=$C$2,\"\",IF($C$2<(Tool!E73-Tool!$D$64),\"\",IF(Tool!D74<>\"\",IF(Tool!$D$64<>0,Tool!E73-Tool!$D$64,Tool!E73),\"\")))","v":""},{"$f":"IF(C19=\"\",\"\",IF(B99=\"\",$C$2,IF((D18-$C$9)>=$C$2,\"\",IF(Tool!E73<>\"\",IF(AND($C$2>=(Tool!E74-Tool!$D$64),(Tool!E75-Tool!$D$64)>=(Tool!E74-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E74-Tool!$D$64,Tool!E74),$C$2),\"\"))))","v":""},{"$f":"IF(C98=\"\",\"\",IF(B98<>\"\",IF(Tool!N74=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E98=\"Mountainous\",IF(Tool!I74>Tool!G74,0,IF(Tool!G74>0,Tool!G74+J98,\"\")),\"\")","v":""},{"$f":"IF(E98=\"Mountainous\",IF(Tool!H74>0,Tool!H74,\"\"),\"\")","v":""},{"$f":"IF(E98=\"Mountainous\",IF(Tool!I74>Tool!G74,Tool!G74,IF(Tool!I74>=0,Tool!I74)),\"\")","v":""},{"$f":"IF(E98=\"Mountainous\",Tool!O74,\"\")","v":""},{"$f":"IF(AND(K98=\"Urban/C&G\",E98=\"Mountainous\",Tool!L74=\"Both Sides\",Tool!M74=\"Both Sides\"),Tool!$M$62*2,IF(AND(K98=\"Urban/C&G\",E98=\"Mountainous\",Tool!L74=\"Both Sides\",Tool!M74=\"One Side\"),Tool!$M$62,IF(AND(K98=\"Urban/C&G\",E98=\"Mountainous\",Tool!L74=\"One Side\",Tool!M74=\"Both Sides\"),Tool!$M$62,IF(AND(K98=\"Urban/C&G\",E98=\"Mountainous\",Tool!L74=\"One Side\",Tool!M74=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E98=\"Mountainous\",Tool!K74,\"\")","v":""},{"$f":"IF(E98<>\"\",Drainage!G56,\"\")","v":""},"",{"$f":"IF(AND(F98=H98,G98=\"\"),\"\",VLOOKUP(Tool!P74,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=1,S96<=20),1,\"\")","v":1},{"$f":"IF(Tool!D98<>\"\",IF(R9<>\"\",IF(Tool!D98=0,Tool!D98,Tool!D98-Tool!D98),\"\"),\"\")","v":""},{"$f":"IF(Tool!E98<>\"\",IF(R98=1,IF($C$2<(Tool!E98-Tool!$D$98),$C$2,IF(Tool!D98<>0,(Tool!E98-Tool!D98),Tool!E98)),\"\"),\"\")","v":""},{"$f":"IF(R98<>\"\",IF(Tool!H98=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U98=\"HM\",Tool!I98>0),Tool!I98,\"\")","v":""},{"$f":"IF(U98=\"HM\",IF(Tool!J98>0,IF(Tool!F98=\"Barrier Wall\",3,IF(Tool!F98=\"Depressed Grass\",Tool!J98*0.5,Tool!J98)),\"\"),\"\")","v":""},{"$f":"IF(R98<>\"\",IF(U98=\"HM\",Tool!F98,\"\"),\"\")","v":""},{"$f":"IF(U98=\"HM\",T98-S98,\"\")","v":""}]
[null,{"$f":"IF(AND(E86>=12,F86<=30),12,\"\")","v":""},{"$f":"IF(D19>=$C$2,\"\",IF($C$2<(Tool!E74-Tool!$D$64),\"\",IF(Tool!D75<>\"\",IF(Tool!$D$64<>0,Tool!E74-Tool!$D$64,Tool!E74),\"\")))","v":""},{"$f":"IF(C20=\"\",\"\",IF(B100=\"\",$C$2,IF((D19-$C$9)>=$C$2,\"\",IF(Tool!E74<>\"\",IF(AND($C$2>=(Tool!E75-Tool!$D$64),(Tool!E76-Tool!$D$64)>=(Tool!E75-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E75-Tool!$D$64,Tool!E75),$C$2),\"\"))))","v":""},{"$f":"IF(C99=\"\",\"\",IF(B99<>\"\",IF(Tool!N75=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E99=\"Mountainous\",IF(Tool!I75>Tool!G75,0,IF(Tool!G75>0,Tool!G75+J99,\"\")),\"\")","v":""},{"$f":"IF(E99=\"Mountainous\",IF(Tool!H75>0,Tool!H75,\"\"),\"\")","v":""},{"$f":"IF(E99=\"Mountainous\",IF(Tool!I75>Tool!G75,Tool!G75,IF(Tool!I75>=0,Tool!I75)),\"\")","v":""},{"$f":"IF(E99=\"Mountainous\",Tool!O75,\"\")","v":""},{"$f":"IF(AND(K99=\"Urban/C&G\",E99=\"Mountainous\",Tool!L75=\"Both Sides\",Tool!M75=\"Both Sides\"),Tool!$M$62*2,IF(AND(K99=\"Urban/C&G\",E99=\"Mountainous\",Tool!L75=\"Both Sides\",Tool!M75=\"One Side\"),Tool!$M$62,IF(AND(K99=\"Urban/C&G\",E99=\"Mountainous\",Tool!L75=\"One Side\",Tool!M75=\"Both Sides\"),Tool!$M$62,IF(AND(K99=\"Urban/C&G\",E99=\"Mountainous\",Tool!L75=\"One Side\",Tool!M75=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E99=\"Mountainous\",Tool!K75,\"\")","v":""},{"$f":"IF(E99<>\"\",Drainage!G57,\"\")","v":""},"",{"$f":"IF(AND(F99=H99,G99=\"\"),\"\",VLOOKUP(Tool!P75,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=2,S96<=20),2,\"\")","v":""},{"$f":"IF(R10<>\"\",IF(T9>=$C$2,\"\",IF($C$2<(Tool!E98-Tool!$D$98),\"\",IF(Tool!D99<>\"\",IF(Tool!$D$98<>0,Tool!E98-Tool!$D$98,Tool!E98),\"\"))),\"\")","v":""},{"$f":"IF(S99=\"\",\"\",IF(R10=\"\",\"\",IF(Tool!E98<>\"\",IF(AND($C$2>=(Tool!E99-Tool!$D$98),(Tool!E100-Tool!$D$98)>=(Tool!E99-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E99-Tool!$D$98,Tool!E99),$C$2),\"\")))","v":""},{"$f":"IF(R99<>\"\",IF(Tool!H99=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U99=\"HM\",Tool!I99>0),Tool!I99,\"\")","v":""},{"$f":"IF(U99=\"HM\",IF(Tool!J99>0,IF(Tool!F99=\"Barrier Wall\",3,IF(Tool!F99=\"Depressed Grass\",Tool!J99*0.5,Tool!J99)),\"\"),\"\")","v":""},{"$f":"IF(R99<>\"\",IF(U99=\"HM\",Tool!F99,\"\"),\"\")","v":""},{"$f":"IF(U99=\"HM\",T99-S99,\"\")","v":""}]
[null,{"$f":"IF(AND(E86>=13,E86<=30),13,\"\")","v":""},{"$f":"IF(D20>=$C$2,\"\",IF($C$2<(Tool!E75-Tool!$D$64),\"\",IF(Tool!D76<>\"\",IF(Tool!$D$64<>0,Tool!E75-Tool!$D$64,Tool!E75),\"\")))","v":""},{"$f":"IF(C21=\"\",\"\",IF(B101=\"\",$C$2,IF((D20-$C$9)>=$C$2,\"\",IF(Tool!E75<>\"\",IF(AND($C$2>=(Tool!E76-Tool!$D$64),(Tool!E77-Tool!$D$64)>=(Tool!E76-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E76-Tool!$D$64,Tool!E76),$C$2),\"\"))))","v":""},{"$f":"IF(C100=\"\",\"\",IF(B100<>\"\",IF(Tool!N76=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E100=\"Mountainous\",IF(Tool!I76>Tool!G76,0,IF(Tool!G76>0,Tool!G76+J100,\"\")),\"\")","v":""},{"$f":"IF(E100=\"Mountainous\",IF(Tool!H76>0,Tool!H76,\"\"),\"\")","v":""},{"$f":"IF(E100=\"Mountainous\",IF(Tool!I76>Tool!G76,Tool!G76,IF(Tool!I76>=0,Tool!I76)),\"\")","v":""},{"$f":"IF(E100=\"Mountainous\",Tool!O76,\"\")","v":""},{"$f":"IF(AND(K100=\"Urban/C&G\",E100=\"Mountainous\",Tool!L76=\"Both Sides\",Tool!M76=\"Both Sides\"),Tool!$M$62*2,IF(AND(K100=\"Urban/C&G\",E100=\"Mountainous\",Tool!L76=\"Both Sides\",Tool!M76=\"One Side\"),Tool!$M$62,IF(AND(K100=\"Urban/C&G\",E100=\"Mountainous\",Tool!L76=\"One Side\",Tool!M76=\"Both Sides\"),Tool!$M$62,IF(AND(K100=\"Urban/C&G\",E100=\"Mountainous\",Tool!L76=\"One Side\",Tool!M76=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E100=\"Mountainous\",Tool!K76,\"\")","v":""},{"$f":"IF(E100<>\"\",Drainage!G58,\"\")","v":""},"",{"$f":"IF(AND(F100=H100,G100=\"\"),\"\",VLOOKUP(Tool!P76,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=3,S96<=20),3,\"\")","v":""},{"$f":"IF(R11<>\"\",IF(T10>=$C$2,\"\",IF($C$2<(Tool!E99-Tool!$D$98),\"\",IF(Tool!D100<>\"\",IF(Tool!$D$98<>0,Tool!E99-Tool!$D$98,Tool!E99),\"\"))),\"\")","v":""},{"$f":"IF(S100=\"\",\"\",IF(R11=\"\",\"\",IF(Tool!E99<>\"\",IF(AND($C$2>=(Tool!E100-Tool!$D$98),(Tool!E101-Tool!$D$98)>=(Tool!E100-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E100-Tool!$D$98,Tool!E100),$C$2),\"\")))","v":""},{"$f":"IF(R100<>\"\",IF(Tool!H100=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U100=\"HM\",Tool!I100>0),Tool!I100,\"\")","v":""},{"$f":"IF(U100=\"HM\",IF(Tool!J100>0,IF(Tool!F100=\"Barrier Wall\",3,IF(Tool!F100=\"Depressed Grass\",Tool!J100*0.5,Tool!J100)),\"\"),\"\")","v":""},{"$f":"IF(R100<>\"\",IF(U100=\"HM\",Tool!F100,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E86>=14,E86<=30),14,\"\")","v":""},{"$f":"IF(D21>=$C$2,\"\",IF($C$2<(Tool!E76-Tool!$D$64),\"\",IF(Tool!D77<>\"\",IF(Tool!$D$64<>0,Tool!E76-Tool!$D$64,Tool!E76),\"\")))","v":""},{"$f":"IF(C22=\"\",\"\",IF(B102=\"\",$C$2,IF((D21-$C$9)>=$C$2,\"\",IF(Tool!E76<>\"\",IF(AND($C$2>=(Tool!E77-Tool!$D$64),(Tool!E78-Tool!$D$64)>=(Tool!E77-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E77-Tool!$D$64,Tool!E77),$C$2),\"\"))))","v":""},{"$f":"IF(C101=\"\",\"\",IF(B101<>\"\",IF(Tool!N77=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E101=\"Mountainous\",IF(Tool!I77>Tool!G77,0,IF(Tool!G77>0,Tool!G77+J101,\"\")),\"\")","v":""},{"$f":"IF(E101=\"Mountainous\",IF(Tool!H77>0,Tool!H77,\"\"),\"\")","v":""},{"$f":"IF(E101=\"Mountainous\",IF(Tool!I77>Tool!G77,Tool!G77,IF(Tool!I77>=0,Tool!I77)),\"\")","v":""},{"$f":"IF(E101=\"Mountainous\",Tool!O77,\"\")","v":""},{"$f":"IF(AND(K101=\"Urban/C&G\",E101=\"Mountainous\",Tool!L77=\"Both Sides\",Tool!M77=\"Both Sides\"),Tool!$M$62*2,IF(AND(K101=\"Urban/C&G\",E101=\"Mountainous\",Tool!L77=\"Both Sides\",Tool!M77=\"One Side\"),Tool!$M$62,IF(AND(K101=\"Urban/C&G\",E101=\"Mountainous\",Tool!L77=\"One Side\",Tool!M77=\"Both Sides\"),Tool!$M$62,IF(AND(K101=\"Urban/C&G\",E101=\"Mountainous\",Tool!L77=\"One Side\",Tool!M77=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E101=\"Mountainous\",Tool!K77,\"\")","v":""},{"$f":"IF(E101<>\"\",Drainage!G59,\"\")","v":""},"",{"$f":"IF(AND(F101=H101,G101=\"\"),\"\",VLOOKUP(Tool!P77,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=4,S96<=20),4,\"\")","v":""},{"$f":"IF(R12<>\"\",IF(T11>=$C$2,\"\",IF($C$2<(Tool!E100-Tool!$D$98),\"\",IF(Tool!D101<>\"\",IF(Tool!$D$98<>0,Tool!E100-Tool!$D$98,Tool!E100),\"\"))),\"\")","v":""},{"$f":"IF(S101=\"\",\"\",IF(R12=\"\",\"\",IF(Tool!E100<>\"\",IF(AND($C$2>=(Tool!E101-Tool!$D$98),(Tool!E102-Tool!$D$98)>=(Tool!E101-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E101-Tool!$D$98,Tool!E101),$C$2),\"\")))","v":""},{"$f":"IF(R101<>\"\",IF(Tool!H101=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U101=\"HM\",Tool!I101>0),Tool!I101,\"\")","v":""},{"$f":"IF(U101=\"HM\",IF(Tool!J101>0,IF(Tool!F101=\"Barrier Wall\",3,IF(Tool!F101=\"Depressed Grass\",Tool!J101*0.5,Tool!J101)),\"\"),\"\")","v":""},{"$f":"IF(R101<>\"\",IF(U101=\"HM\",Tool!F101,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E86>=15,E86<=30),15,\"\")","v":""},{"$f":"IF(D22>=$C$2,\"\",IF($C$2<(Tool!E77-Tool!$D$64),\"\",IF(Tool!D78<>\"\",IF(Tool!$D$64<>0,Tool!E77-Tool!$D$64,Tool!E77),\"\")))","v":""},{"$f":"IF(C23=\"\",\"\",IF(B103=\"\",$C$2,IF((D22-$C$9)>=$C$2,\"\",IF(Tool!E77<>\"\",IF(AND($C$2>=(Tool!E78-Tool!$D$64),(Tool!E79-Tool!$D$64)>=(Tool!E78-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E78-Tool!$D$64,Tool!E78),$C$2),\"\"))))","v":""},{"$f":"IF(C102=\"\",\"\",IF(B102<>\"\",IF(Tool!N78=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E102=\"Mountainous\",IF(Tool!I78>Tool!G78,0,IF(Tool!G78>0,Tool!G78+J102,\"\")),\"\")","v":""},{"$f":"IF(E102=\"Mountainous\",IF(Tool!H78>0,Tool!H78,\"\"),\"\")","v":""},{"$f":"IF(E102=\"Mountainous\",IF(Tool!I78>Tool!G78,Tool!G78,IF(Tool!I78>=0,Tool!I78)),\"\")","v":""},{"$f":"IF(E102=\"Mountainous\",Tool!O78,\"\")","v":""},{"$f":"IF(AND(K102=\"Urban/C&G\",E102=\"Mountainous\",Tool!L78=\"Both Sides\",Tool!M78=\"Both Sides\"),Tool!$M$62*2,IF(AND(K102=\"Urban/C&G\",E102=\"Mountainous\",Tool!L78=\"Both Sides\",Tool!M78=\"One Side\"),Tool!$M$62,IF(AND(K102=\"Urban/C&G\",E102=\"Mountainous\",Tool!L78=\"One Side\",Tool!M78=\"Both Sides\"),Tool!$M$62,IF(AND(K102=\"Urban/C&G\",E102=\"Mountainous\",Tool!L78=\"One Side\",Tool!M78=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E102=\"Mountainous\",Tool!K78,\"\")","v":""},{"$f":"IF(E102<>\"\",Drainage!G60,\"\")","v":""},"",{"$f":"IF(AND(F102=H102,G102=\"\"),\"\",VLOOKUP(Tool!P78,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=5,S96<=20),5,\"\")","v":""},{"$f":"IF(R13<>\"\",IF(T12>=$C$2,\"\",IF($C$2<(Tool!E101-Tool!$D$98),\"\",IF(Tool!D102<>\"\",IF(Tool!$D$98<>0,Tool!E101-Tool!$D$98,Tool!E101),\"\"))),\"\")","v":""},{"$f":"IF(S102=\"\",\"\",IF(R13=\"\",\"\",IF(Tool!E101<>\"\",IF(AND($C$2>=(Tool!E102-Tool!$D$98),(Tool!E103-Tool!$D$98)>=(Tool!E102-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E102-Tool!$D$98,Tool!E102),$C$2),\"\")))","v":""},{"$f":"IF(R102<>\"\",IF(Tool!H102=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U102=\"HM\",Tool!I102>0),Tool!I102,\"\")","v":""},{"$f":"IF(U102=\"HM\",IF(Tool!J102>0,IF(Tool!F102=\"Barrier Wall\",3,IF(Tool!F102=\"Depressed Grass\",Tool!J102*0.5,Tool!J102)),\"\"),\"\")","v":""},{"$f":"IF(R102<>\"\",IF(U102=\"HM\",Tool!F102,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E86>=16,E86<=30),16,\"\")","v":""},{"$f":"IF(D23>=$C$2,\"\",IF($C$2<(Tool!E78-Tool!$D$64),\"\",IF(Tool!D79<>\"\",IF(Tool!$D$64<>0,Tool!E78-Tool!$D$64,Tool!E78),\"\")))","v":""},{"$f":"IF(C24=\"\",\"\",IF(B104=\"\",$C$2,IF((D23-$C$9)>=$C$2,\"\",IF(Tool!E78<>\"\",IF(AND($C$2>=(Tool!E79-Tool!$D$64),(Tool!E80-Tool!$D$64)>=(Tool!E79-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E79-Tool!$D$64,Tool!E79),$C$2),\"\"))))","v":""},{"$f":"IF(C103=\"\",\"\",IF(B103<>\"\",IF(Tool!N79=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E103=\"Mountainous\",IF(Tool!I79>Tool!G79,0,IF(Tool!G79>0,Tool!G79+J103,\"\")),\"\")","v":""},{"$f":"IF(E103=\"Mountainous\",IF(Tool!H79>0,Tool!H79,\"\"),\"\")","v":""},{"$f":"IF(E103=\"Mountainous\",IF(Tool!I79>Tool!G79,Tool!G79,IF(Tool!I79>=0,Tool!I79)),\"\")","v":""},{"$f":"IF(E103=\"Mountainous\",Tool!O79,\"\")","v":""},{"$f":"IF(AND(K103=\"Urban/C&G\",E103=\"Mountainous\",Tool!L79=\"Both Sides\",Tool!M79=\"Both Sides\"),Tool!$M$62*2,IF(AND(K103=\"Urban/C&G\",E103=\"Mountainous\",Tool!L79=\"Both Sides\",Tool!M79=\"One Side\"),Tool!$M$62,IF(AND(K103=\"Urban/C&G\",E103=\"Mountainous\",Tool!L79=\"One Side\",Tool!M79=\"Both Sides\"),Tool!$M$62,IF(AND(K103=\"Urban/C&G\",E103=\"Mountainous\",Tool!L79=\"One Side\",Tool!M79=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E103=\"Mountainous\",Tool!K79,\"\")","v":""},{"$f":"IF(E103<>\"\",Drainage!G61,\"\")","v":""},"",{"$f":"IF(AND(F103=H103,G103=\"\"),\"\",VLOOKUP(Tool!P79,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=6,S96<=20),6,\"\")","v":""},{"$f":"IF(R14<>\"\",IF(T13>=$C$2,\"\",IF($C$2<(Tool!E102-Tool!$D$98),\"\",IF(Tool!D103<>\"\",IF(Tool!$D$98<>0,Tool!E102-Tool!$D$98,Tool!E102),\"\"))),\"\")","v":""},{"$f":"IF(S103=\"\",\"\",IF(R14=\"\",\"\",IF(Tool!E102<>\"\",IF(AND($C$2>=(Tool!E103-Tool!$D$98),(Tool!E104-Tool!$D$98)>=(Tool!E103-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E103-Tool!$D$98,Tool!E103),$C$2),\"\")))","v":""},{"$f":"IF(R103<>\"\",IF(Tool!H103=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U103=\"HM\",Tool!I103>0),Tool!I103,\"\")","v":""},{"$f":"IF(U103=\"HM\",IF(Tool!J103>0,IF(Tool!F103=\"Barrier Wall\",3,IF(Tool!F103=\"Depressed Grass\",Tool!J103*0.5,Tool!J103)),\"\"),\"\")","v":""},{"$f":"IF(R103<>\"\",IF(U103=\"HM\",Tool!F103,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E86>=17,E86<=30),17,\"\")","v":""},{"$f":"IF(D24>=$C$2,\"\",IF($C$2<(Tool!E79-Tool!$D$64),\"\",IF(Tool!D80<>\"\",IF(Tool!$D$64<>0,Tool!E79-Tool!$D$64,Tool!E79),\"\")))","v":""},{"$f":"IF(C25=\"\",\"\",IF(B105=\"\",$C$2,IF((D24-$C$9)>=$C$2,\"\",IF(Tool!E79<>\"\",IF(AND($C$2>=(Tool!E80-Tool!$D$64),(Tool!E81-Tool!$D$64)>=(Tool!E80-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E80-Tool!$D$64,Tool!E80),$C$2),\"\"))))","v":""},{"$f":"IF(C104=\"\",\"\",IF(B104<>\"\",IF(Tool!N80=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E104=\"Mountainous\",IF(Tool!I80>Tool!G80,0,IF(Tool!G80>0,Tool!G80+J104,\"\")),\"\")","v":""},{"$f":"IF(E104=\"Mountainous\",IF(Tool!H80>0,Tool!H80,\"\"),\"\")","v":""},{"$f":"IF(E104=\"Mountainous\",IF(Tool!I80>Tool!G80,Tool!G80,IF(Tool!I80>=0,Tool!I80)),\"\")","v":""},{"$f":"IF(E104=\"Mountainous\",Tool!O80,\"\")","v":""},{"$f":"IF(AND(K104=\"Urban/C&G\",E104=\"Mountainous\",Tool!L80=\"Both Sides\",Tool!M80=\"Both Sides\"),Tool!$M$62*2,IF(AND(K104=\"Urban/C&G\",E104=\"Mountainous\",Tool!L80=\"Both Sides\",Tool!M80=\"One Side\"),Tool!$M$62,IF(AND(K104=\"Urban/C&G\",E104=\"Mountainous\",Tool!L80=\"One Side\",Tool!M80=\"Both Sides\"),Tool!$M$62,IF(AND(K104=\"Urban/C&G\",E104=\"Mountainous\",Tool!L80=\"One Side\",Tool!M80=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E104=\"Mountainous\",Tool!K80,\"\")","v":""},{"$f":"IF(E104<>\"\",Drainage!G62,\"\")","v":""},"",{"$f":"IF(AND(F104=H104,G104=\"\"),\"\",VLOOKUP(Tool!P80,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=7,S96<=20),7,\"\")","v":""},{"$f":"IF(R15<>\"\",IF(T14>=$C$2,\"\",IF($C$2<(Tool!E103-Tool!$D$98),\"\",IF(Tool!D104<>\"\",IF(Tool!$D$98<>0,Tool!E103-Tool!$D$98,Tool!E103),\"\"))),\"\")","v":""},{"$f":"IF(S104=\"\",\"\",IF(R15=\"\",\"\",IF(Tool!E103<>\"\",IF(AND($C$2>=(Tool!E104-Tool!$D$98),(Tool!E105-Tool!$D$98)>=(Tool!E104-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E104-Tool!$D$98,Tool!E104),$C$2),\"\")))","v":""},{"$f":"IF(R104<>\"\",IF(Tool!H104=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U104=\"HM\",Tool!I104>0),Tool!I104,\"\")","v":""},{"$f":"IF(U104=\"HM\",IF(Tool!J104>0,IF(Tool!F104=\"Barrier Wall\",3,IF(Tool!F104=\"Depressed Grass\",Tool!J104*0.5,Tool!J104)),\"\"),\"\")","v":""},{"$f":"IF(R104<>\"\",IF(U104=\"HM\",Tool!F104,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E86>=18,E86<=30),18,\"\")","v":""},{"$f":"IF(D25>=$C$2,\"\",IF($C$2<(Tool!E80-Tool!$D$64),\"\",IF(Tool!D81<>\"\",IF(Tool!$D$64<>0,Tool!E80-Tool!$D$64,Tool!E80),\"\")))","v":""},{"$f":"IF(C26=\"\",\"\",IF(B106=\"\",$C$2,IF((D25-$C$9)>=$C$2,\"\",IF(Tool!E80<>\"\",IF(AND($C$2>=(Tool!E81-Tool!$D$64),(Tool!E82-Tool!$D$64)>=(Tool!E81-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E81-Tool!$D$64,Tool!E81),$C$2),\"\"))))","v":""},{"$f":"IF(C105=\"\",\"\",IF(B105<>\"\",IF(Tool!N81=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E105=\"Mountainous\",IF(Tool!I81>Tool!G81,0,IF(Tool!G81>0,Tool!G81+J105,\"\")),\"\")","v":""},{"$f":"IF(E105=\"Mountainous\",IF(Tool!H81>0,Tool!H81,\"\"),\"\")","v":""},{"$f":"IF(E105=\"Mountainous\",IF(Tool!I81>Tool!G81,Tool!G81,IF(Tool!I81>=0,Tool!I81)),\"\")","v":""},{"$f":"IF(E105=\"Mountainous\",Tool!O81,\"\")","v":""},{"$f":"IF(AND(K105=\"Urban/C&G\",E105=\"Mountainous\",Tool!L81=\"Both Sides\",Tool!M81=\"Both Sides\"),Tool!$M$62*2,IF(AND(K105=\"Urban/C&G\",E105=\"Mountainous\",Tool!L81=\"Both Sides\",Tool!M81=\"One Side\"),Tool!$M$62,IF(AND(K105=\"Urban/C&G\",E105=\"Mountainous\",Tool!L81=\"One Side\",Tool!M81=\"Both Sides\"),Tool!$M$62,IF(AND(K105=\"Urban/C&G\",E105=\"Mountainous\",Tool!L81=\"One Side\",Tool!M81=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E105=\"Mountainous\",Tool!K81,\"\")","v":""},{"$f":"IF(E105<>\"\",Drainage!G63,\"\")","v":""},"",{"$f":"IF(AND(F105=H105,G105=\"\"),\"\",VLOOKUP(Tool!P81,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=8,S96<=20),8,\"\")","v":""},{"$f":"IF(R16<>\"\",IF(T15>=$C$2,\"\",IF($C$2<(Tool!E104-Tool!$D$98),\"\",IF(Tool!D105<>\"\",IF(Tool!$D$98<>0,Tool!E104-Tool!$D$98,Tool!E104),\"\"))),\"\")","v":""},{"$f":"IF(S105=\"\",\"\",IF(R16=\"\",\"\",IF(Tool!E104<>\"\",IF(AND($C$2>=(Tool!E105-Tool!$D$98),(Tool!E106-Tool!$D$98)>=(Tool!E105-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E105-Tool!$D$98,Tool!E105),$C$2),\"\")))","v":""},{"$f":"IF(R105<>\"\",IF(Tool!H105=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U105=\"HM\",Tool!I105>0),Tool!I105,\"\")","v":""},{"$f":"IF(U105=\"HM\",IF(Tool!J105>0,IF(Tool!F105=\"Barrier Wall\",3,IF(Tool!F105=\"Depressed Grass\",Tool!J105*0.5,Tool!J105)),\"\"),\"\")","v":""},{"$f":"IF(R105<>\"\",IF(U105=\"HM\",Tool!F105,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E86>=19,E86<=30),19,\"\")","v":""},{"$f":"IF(D26>=$C$2,\"\",IF($C$2<(Tool!E81-Tool!$D$64),\"\",IF(Tool!D82<>\"\",IF(Tool!$D$64<>0,Tool!E81-Tool!$D$64,Tool!E81),\"\")))","v":""},{"$f":"IF(C27=\"\",\"\",IF(B107=\"\",$C$2,IF((D26-$C$9)>=$C$2,\"\",IF(Tool!E81<>\"\",IF(AND($C$2>=(Tool!E82-Tool!$D$64),(Tool!E83-Tool!$D$64)>=(Tool!E82-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E82-Tool!$D$64,Tool!E82),$C$2),\"\"))))","v":""},{"$f":"IF(C106=\"\",\"\",IF(B106<>\"\",IF(Tool!N82=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E106=\"Mountainous\",IF(Tool!I82>Tool!G82,0,IF(Tool!G82>0,Tool!G82+J106,\"\")),\"\")","v":""},{"$f":"IF(E106=\"Mountainous\",IF(Tool!H82>0,Tool!H82,\"\"),\"\")","v":""},{"$f":"IF(E106=\"Mountainous\",IF(Tool!I82>Tool!G82,Tool!G82,IF(Tool!I82>=0,Tool!I82)),\"\")","v":""},{"$f":"IF(E106=\"Mountainous\",Tool!O82,\"\")","v":""},{"$f":"IF(AND(K106=\"Urban/C&G\",E106=\"Mountainous\",Tool!L82=\"Both Sides\",Tool!M82=\"Both Sides\"),Tool!$M$62*2,IF(AND(K106=\"Urban/C&G\",E106=\"Mountainous\",Tool!L82=\"Both Sides\",Tool!M82=\"One Side\"),Tool!$M$62,IF(AND(K106=\"Urban/C&G\",E106=\"Mountainous\",Tool!L82=\"One Side\",Tool!M82=\"Both Sides\"),Tool!$M$62,IF(AND(K106=\"Urban/C&G\",E106=\"Mountainous\",Tool!L82=\"One Side\",Tool!M82=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E106=\"Mountainous\",Tool!K82,\"\")","v":""},{"$f":"IF(E106<>\"\",Drainage!G64,\"\")","v":""},"",{"$f":"IF(AND(F106=H106,G106=\"\"),\"\",VLOOKUP(Tool!P82,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=9,S96<=20),9,\"\")","v":""},{"$f":"IF(R17<>\"\",IF(T16>=$C$2,\"\",IF($C$2<(Tool!E105-Tool!$D$98),\"\",IF(Tool!D106<>\"\",IF(Tool!$D$98<>0,Tool!E105-Tool!$D$98,Tool!E105),\"\"))),\"\")","v":""},{"$f":"IF(S106=\"\",\"\",IF(R17=\"\",\"\",IF(Tool!E105<>\"\",IF(AND($C$2>=(Tool!E106-Tool!$D$98),(Tool!E107-Tool!$D$98)>=(Tool!E106-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E106-Tool!$D$98,Tool!E106),$C$2),\"\")))","v":""},{"$f":"IF(R106<>\"\",IF(Tool!H106=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U106=\"HM\",Tool!I106>0),Tool!I106,\"\")","v":""},{"$f":"IF(U106=\"HM\",IF(Tool!J106>0,IF(Tool!F106=\"Barrier Wall\",3,IF(Tool!F106=\"Depressed Grass\",Tool!J106*0.5,Tool!J106)),\"\"),\"\")","v":""},{"$f":"IF(R106<>\"\",IF(U106=\"HM\",Tool!F106,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E86>=20,E86<=30),20,\"\")","v":""},{"$f":"IF(D27>=$C$2,\"\",IF($C$2<(Tool!E82-Tool!$D$64),\"\",IF(Tool!D83<>\"\",IF(Tool!$D$64<>0,Tool!E82-Tool!$D$64,Tool!E82),\"\")))","v":""},{"$f":"IF(C28=\"\",\"\",IF(B108=\"\",$C$2,IF((D27-$C$9)>=$C$2,\"\",IF(Tool!E82<>\"\",IF(AND($C$2>=(Tool!E83-Tool!$D$64),(Tool!E84-Tool!$D$64)>=(Tool!E83-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E83-Tool!$D$64,Tool!E83),$C$2),\"\"))))","v":""},{"$f":"IF(C107=\"\",\"\",IF(B107<>\"\",IF(Tool!N83=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E107=\"Mountainous\",IF(Tool!I83>Tool!G83,0,IF(Tool!G83>0,Tool!G83+J107,\"\")),\"\")","v":""},{"$f":"IF(E107=\"Mountainous\",IF(Tool!H83>0,Tool!H83,\"\"),\"\")","v":""},{"$f":"IF(E107=\"Mountainous\",IF(Tool!I83>Tool!G83,Tool!G83,IF(Tool!I83>=0,Tool!I83)),\"\")","v":""},{"$f":"IF(E107=\"Mountainous\",Tool!O83,\"\")","v":""},{"$f":"IF(AND(K107=\"Urban/C&G\",E107=\"Mountainous\",Tool!L83=\"Both Sides\",Tool!M83=\"Both Sides\"),Tool!$M$62*2,IF(AND(K107=\"Urban/C&G\",E107=\"Mountainous\",Tool!L83=\"Both Sides\",Tool!M83=\"One Side\"),Tool!$M$62,IF(AND(K107=\"Urban/C&G\",E107=\"Mountainous\",Tool!L83=\"One Side\",Tool!M83=\"Both Sides\"),Tool!$M$62,IF(AND(K107=\"Urban/C&G\",E107=\"Mountainous\",Tool!L83=\"One Side\",Tool!M83=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E107=\"Mountainous\",Tool!K83,\"\")","v":""},{"$f":"IF(E107<>\"\",Drainage!G65,\"\")","v":""},"",{"$f":"IF(AND(F107=H107,G107=\"\"),\"\",VLOOKUP(Tool!P83,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=10,S96<=20),10,\"\")","v":""},{"$f":"IF(R18<>\"\",IF(T17>=$C$2,\"\",IF($C$2<(Tool!E106-Tool!$D$98),\"\",IF(Tool!D107<>\"\",IF(Tool!$D$98<>0,Tool!E106-Tool!$D$98,Tool!E106),\"\"))),\"\")","v":""},{"$f":"IF(S107=\"\",\"\",IF(R18=\"\",\"\",IF(Tool!E106<>\"\",IF(AND($C$2>=(Tool!E107-Tool!$D$98),(Tool!E108-Tool!$D$98)>=(Tool!E107-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E107-Tool!$D$98,Tool!E107),$C$2),\"\")))","v":""},{"$f":"IF(R107<>\"\",IF(Tool!H107=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U107=\"HM\",Tool!I107>0),Tool!I107,\"\")","v":""},{"$f":"IF(U107=\"HM\",IF(Tool!J107>0,IF(Tool!F107=\"Barrier Wall\",3,IF(Tool!F107=\"Depressed Grass\",Tool!J107*0.5,Tool!J107)),\"\"),\"\")","v":""},{"$f":"IF(R107<>\"\",IF(U107=\"HM\",Tool!F107,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E86>=21,E86<=30),21,\"\")","v":""},{"$f":"IF(D28>=$C$2,\"\",IF($C$2<(Tool!E83-Tool!$D$64),\"\",IF(Tool!D84<>\"\",IF(Tool!$D$64<>0,Tool!E83-Tool!$D$64,Tool!E83),\"\")))","v":""},{"$f":"IF(C29=\"\",\"\",IF(B109=\"\",$C$2,IF((D28-$C$9)>=$C$2,\"\",IF(Tool!E83<>\"\",IF(AND($C$2>=(Tool!E84-Tool!$D$64),(Tool!E85-Tool!$D$64)>=(Tool!E84-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E84-Tool!$D$64,Tool!E84),$C$2),\"\"))))","v":""},{"$f":"IF(C108=\"\",\"\",IF(B108<>\"\",IF(Tool!N84=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E108=\"Mountainous\",IF(Tool!I84>Tool!G84,0,IF(Tool!G84>0,Tool!G84+J108,\"\")),\"\")","v":""},{"$f":"IF(E108=\"Mountainous\",IF(Tool!H84>0,Tool!H84,\"\"),\"\")","v":""},{"$f":"IF(E108=\"Mountainous\",IF(Tool!I84>Tool!G84,Tool!G84,IF(Tool!I84>=0,Tool!I84)),\"\")","v":""},{"$f":"IF(E108=\"Mountainous\",Tool!O84,\"\")","v":""},{"$f":"IF(AND(K108=\"Urban/C&G\",E108=\"Mountainous\",Tool!L84=\"Both Sides\",Tool!M84=\"Both Sides\"),Tool!$M$62*2,IF(AND(K108=\"Urban/C&G\",E108=\"Mountainous\",Tool!L84=\"Both Sides\",Tool!M84=\"One Side\"),Tool!$M$62,IF(AND(K108=\"Urban/C&G\",E108=\"Mountainous\",Tool!L84=\"One Side\",Tool!M84=\"Both Sides\"),Tool!$M$62,IF(AND(K108=\"Urban/C&G\",E108=\"Mountainous\",Tool!L84=\"One Side\",Tool!M84=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E108=\"Mountainous\",Tool!K84,\"\")","v":""},{"$f":"IF(E108<>\"\",Drainage!G66,\"\")","v":""},"",{"$f":"IF(AND(F108=H108,G108=\"\"),\"\",VLOOKUP(Tool!P84,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=11,S96<=20),11,\"\")","v":""},{"$f":"IF(R19<>\"\",IF(T18>=$C$2,\"\",IF($C$2<(Tool!E107-Tool!$D$98),\"\",IF(Tool!D108<>\"\",IF(Tool!$D$98<>0,Tool!E107-Tool!$D$98,Tool!E107),\"\"))),\"\")","v":""},{"$f":"IF(S108=\"\",\"\",IF(R19=\"\",\"\",IF(Tool!E107<>\"\",IF(AND($C$2>=(Tool!E108-Tool!$D$98),(Tool!E109-Tool!$D$98)>=(Tool!E108-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E108-Tool!$D$98,Tool!E108),$C$2),\"\")))","v":""},{"$f":"IF(R108<>\"\",IF(Tool!H108=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U108=\"HM\",Tool!I108>0),Tool!I108,\"\")","v":""},{"$f":"IF(U108=\"HM\",IF(Tool!J108>0,IF(Tool!F108=\"Barrier Wall\",3,IF(Tool!F108=\"Depressed Grass\",Tool!J108*0.5,Tool!J108)),\"\"),\"\")","v":""},{"$f":"IF(R108<>\"\",IF(U108=\"HM\",Tool!F108,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E86>=22,E86<=30),22,\"\")","v":""},{"$f":"IF(D29>=$C$2,\"\",IF($C$2<(Tool!E84-Tool!$D$64),\"\",IF(Tool!D85<>\"\",IF(Tool!$D$64<>0,Tool!E84-Tool!$D$64,Tool!E84),\"\")))","v":""},{"$f":"IF(C30=\"\",\"\",IF(B110=\"\",$C$2,IF((D29-$C$9)>=$C$2,\"\",IF(Tool!E84<>\"\",IF(AND($C$2>=(Tool!E85-Tool!$D$64),(Tool!E86-Tool!$D$64)>=(Tool!E85-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E85-Tool!$D$64,Tool!E85),$C$2),\"\"))))","v":""},{"$f":"IF(C109=\"\",\"\",IF(B109<>\"\",IF(Tool!N85=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E109=\"Mountainous\",IF(Tool!I85>Tool!G85,0,IF(Tool!G85>0,Tool!G85+J109,\"\")),\"\")","v":""},{"$f":"IF(E109=\"Mountainous\",IF(Tool!H85>0,Tool!H85,\"\"),\"\")","v":""},{"$f":"IF(E109=\"Mountainous\",IF(Tool!I85>Tool!G85,Tool!G85,IF(Tool!I85>=0,Tool!I85)),\"\")","v":""},{"$f":"IF(E109=\"Mountainous\",Tool!O85,\"\")","v":""},{"$f":"IF(AND(K109=\"Urban/C&G\",E109=\"Mountainous\",Tool!L85=\"Both Sides\",Tool!M85=\"Both Sides\"),Tool!$M$62*2,IF(AND(K109=\"Urban/C&G\",E109=\"Mountainous\",Tool!L85=\"Both Sides\",Tool!M85=\"One Side\"),Tool!$M$62,IF(AND(K109=\"Urban/C&G\",E109=\"Mountainous\",Tool!L85=\"One Side\",Tool!M85=\"Both Sides\"),Tool!$M$62,IF(AND(K109=\"Urban/C&G\",E109=\"Mountainous\",Tool!L85=\"One Side\",Tool!M85=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E109=\"Mountainous\",Tool!K85,\"\")","v":""},{"$f":"IF(E109<>\"\",Drainage!G67,\"\")","v":""},"",{"$f":"IF(AND(F109=H109,G109=\"\"),\"\",VLOOKUP(Tool!P85,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=12,S96<=20),12,\"\")","v":""},{"$f":"IF(R20<>\"\",IF(T19>=$C$2,\"\",IF($C$2<(Tool!E108-Tool!$D$98),\"\",IF(Tool!D109<>\"\",IF(Tool!$D$98<>0,Tool!E108-Tool!$D$98,Tool!E108),\"\"))),\"\")","v":""},{"$f":"IF(S109=\"\",\"\",IF(R20=\"\",\"\",IF(Tool!E108<>\"\",IF(AND($C$2>=(Tool!E109-Tool!$D$98),(Tool!E110-Tool!$D$98)>=(Tool!E109-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E109-Tool!$D$98,Tool!E109),$C$2),\"\")))","v":""},{"$f":"IF(R109<>\"\",IF(Tool!H109=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U109=\"HM\",Tool!I109>0),Tool!I109,\"\")","v":""},{"$f":"IF(U109=\"HM\",IF(Tool!J109>0,IF(Tool!F109=\"Barrier Wall\",3,IF(Tool!F109=\"Depressed Grass\",Tool!J109*0.5,Tool!J109)),\"\"),\"\")","v":""},{"$f":"IF(R109<>\"\",IF(U109=\"HM\",Tool!F109,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E86>=23,E86<=30),23,\"\")","v":""},{"$f":"IF(D30>=$C$2,\"\",IF($C$2<(Tool!E85-Tool!$D$64),\"\",IF(Tool!D86<>\"\",IF(Tool!$D$64<>0,Tool!E85-Tool!$D$64,Tool!E85),\"\")))","v":""},{"$f":"IF(C31=\"\",\"\",IF(B111=\"\",$C$2,IF((D30-$C$9)>=$C$2,\"\",IF(Tool!E85<>\"\",IF(AND($C$2>=(Tool!E86-Tool!$D$64),(Tool!E87-Tool!$D$64)>=(Tool!E86-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E86-Tool!$D$64,Tool!E86),$C$2),\"\"))))","v":""},{"$f":"IF(C110=\"\",\"\",IF(B110<>\"\",IF(Tool!N86=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E110=\"Mountainous\",IF(Tool!I86>Tool!G86,0,IF(Tool!G86>0,Tool!G86+J110,\"\")),\"\")","v":""},{"$f":"IF(E110=\"Mountainous\",IF(Tool!H86>0,Tool!H86,\"\"),\"\")","v":""},{"$f":"IF(E110=\"Mountainous\",IF(Tool!I86>Tool!G86,Tool!G86,IF(Tool!I86>=0,Tool!I86)),\"\")","v":""},{"$f":"IF(E110=\"Mountainous\",Tool!O86,\"\")","v":""},{"$f":"IF(AND(K110=\"Urban/C&G\",E110=\"Mountainous\",Tool!L86=\"Both Sides\",Tool!M86=\"Both Sides\"),Tool!$M$62*2,IF(AND(K110=\"Urban/C&G\",E110=\"Mountainous\",Tool!L86=\"Both Sides\",Tool!M86=\"One Side\"),Tool!$M$62,IF(AND(K110=\"Urban/C&G\",E110=\"Mountainous\",Tool!L86=\"One Side\",Tool!M86=\"Both Sides\"),Tool!$M$62,IF(AND(K110=\"Urban/C&G\",E110=\"Mountainous\",Tool!L86=\"One Side\",Tool!M86=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E110=\"Mountainous\",Tool!K86,\"\")","v":""},{"$f":"IF(E110<>\"\",Drainage!G68,\"\")","v":""},"",{"$f":"IF(AND(F110=H110,G110=\"\"),\"\",VLOOKUP(Tool!P86,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=13,S96<=20),13,\"\")","v":""},{"$f":"IF(R21<>\"\",IF(T20>=$C$2,\"\",IF($C$2<(Tool!E109-Tool!$D$98),\"\",IF(Tool!D110<>\"\",IF(Tool!$D$98<>0,Tool!E109-Tool!$D$98,Tool!E109),\"\"))),\"\")","v":""},{"$f":"IF(S110=\"\",\"\",IF(R21=\"\",\"\",IF(Tool!E109<>\"\",IF(AND($C$2>=(Tool!E110-Tool!$D$98),(Tool!E111-Tool!$D$98)>=(Tool!E110-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E110-Tool!$D$98,Tool!E110),$C$2),\"\")))","v":""},{"$f":"IF(R110<>\"\",IF(Tool!H110=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U110=\"HM\",Tool!I110>0),Tool!I110,\"\")","v":""},{"$f":"IF(U110=\"HM\",IF(Tool!J110>0,IF(Tool!F110=\"Barrier Wall\",3,IF(Tool!F110=\"Depressed Grass\",Tool!J110*0.5,Tool!J110)),\"\"),\"\")","v":""},{"$f":"IF(R110<>\"\",IF(U110=\"HM\",Tool!F110,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E86>=24,E86<=30),24,\"\")","v":""},{"$f":"IF(D31>=$C$2,\"\",IF($C$2<(Tool!E86-Tool!$D$64),\"\",IF(Tool!D87<>\"\",IF(Tool!$D$64<>0,Tool!E86-Tool!$D$64,Tool!E86),\"\")))","v":""},{"$f":"IF(C32=\"\",\"\",IF(B112=\"\",$C$2,IF((D31-$C$9)>=$C$2,\"\",IF(Tool!E86<>\"\",IF(AND($C$2>=(Tool!E87-Tool!$D$64),(Tool!E88-Tool!$D$64)>=(Tool!E87-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E87-Tool!$D$64,Tool!E87),$C$2),\"\"))))","v":""},{"$f":"IF(C111=\"\",\"\",IF(B111<>\"\",IF(Tool!N87=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E111=\"Mountainous\",IF(Tool!I87>Tool!G87,0,IF(Tool!G87>0,Tool!G87+J111,\"\")),\"\")","v":""},{"$f":"IF(E111=\"Mountainous\",IF(Tool!H87>0,Tool!H87,\"\"),\"\")","v":""},{"$f":"IF(E111=\"Mountainous\",IF(Tool!I87>Tool!G87,Tool!G87,IF(Tool!I87>=0,Tool!I87)),\"\")","v":""},{"$f":"IF(E111=\"Mountainous\",Tool!O87,\"\")","v":""},{"$f":"IF(AND(K111=\"Urban/C&G\",E111=\"Mountainous\",Tool!L87=\"Both Sides\",Tool!M87=\"Both Sides\"),Tool!$M$62*2,IF(AND(K111=\"Urban/C&G\",E111=\"Mountainous\",Tool!L87=\"Both Sides\",Tool!M87=\"One Side\"),Tool!$M$62,IF(AND(K111=\"Urban/C&G\",E111=\"Mountainous\",Tool!L87=\"One Side\",Tool!M87=\"Both Sides\"),Tool!$M$62,IF(AND(K111=\"Urban/C&G\",E111=\"Mountainous\",Tool!L87=\"One Side\",Tool!M87=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E111=\"Mountainous\",Tool!K87,\"\")","v":""},{"$f":"IF(E111<>\"\",Drainage!G69,\"\")","v":""},"",{"$f":"IF(AND(F111=H111,G111=\"\"),\"\",VLOOKUP(Tool!P87,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=14,S96<=20),14,\"\")","v":""},{"$f":"IF(R22<>\"\",IF(T21>=$C$2,\"\",IF($C$2<(Tool!E110-Tool!$D$98),\"\",IF(Tool!D111<>\"\",IF(Tool!$D$98<>0,Tool!E110-Tool!$D$98,Tool!E110),\"\"))),\"\")","v":""},{"$f":"IF(S111=\"\",\"\",IF(R22=\"\",\"\",IF(Tool!E110<>\"\",IF(AND($C$2>=(Tool!E111-Tool!$D$98),(Tool!E112-Tool!$D$98)>=(Tool!E111-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E111-Tool!$D$98,Tool!E111),$C$2),\"\")))","v":""},{"$f":"IF(R111<>\"\",IF(Tool!H111=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U111=\"HM\",Tool!I111>0),Tool!I111,\"\")","v":""},{"$f":"IF(U111=\"HM\",IF(Tool!J111>0,IF(Tool!F111=\"Barrier Wall\",3,IF(Tool!F111=\"Depressed Grass\",Tool!J111*0.5,Tool!J111)),\"\"),\"\")","v":""},{"$f":"IF(R111<>\"\",IF(U111=\"HM\",Tool!F111,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E86>=25,E86<=30),25,\"\")","v":""},{"$f":"IF(D32>=$C$2,\"\",IF($C$2<(Tool!E87-Tool!$D$64),\"\",IF(Tool!D88<>\"\",IF(Tool!$D$64<>0,Tool!E87-Tool!$D$64,Tool!E87),\"\")))","v":""},{"$f":"IF(C33=\"\",\"\",IF(B113=\"\",$C$2,IF((D32-$C$9)>=$C$2,\"\",IF(Tool!E87<>\"\",IF(AND($C$2>=(Tool!E88-Tool!$D$64),(Tool!E89-Tool!$D$64)>=(Tool!E88-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E88-Tool!$D$64,Tool!E88),$C$2),\"\"))))","v":""},{"$f":"IF(C112=\"\",\"\",IF(B112<>\"\",IF(Tool!N88=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E112=\"Mountainous\",IF(Tool!I88>Tool!G88,0,IF(Tool!G88>0,Tool!G88+J112,\"\")),\"\")","v":""},{"$f":"IF(E112=\"Mountainous\",IF(Tool!H88>0,Tool!H88,\"\"),\"\")","v":""},{"$f":"IF(E112=\"Mountainous\",IF(Tool!I88>Tool!G88,Tool!G88,IF(Tool!I88>=0,Tool!I88)),\"\")","v":""},{"$f":"IF(E112=\"Mountainous\",Tool!O88,\"\")","v":""},{"$f":"IF(AND(K112=\"Urban/C&G\",E112=\"Mountainous\",Tool!L88=\"Both Sides\",Tool!M88=\"Both Sides\"),Tool!$M$62*2,IF(AND(K112=\"Urban/C&G\",E112=\"Mountainous\",Tool!L88=\"Both Sides\",Tool!M88=\"One Side\"),Tool!$M$62,IF(AND(K112=\"Urban/C&G\",E112=\"Mountainous\",Tool!L88=\"One Side\",Tool!M88=\"Both Sides\"),Tool!$M$62,IF(AND(K112=\"Urban/C&G\",E112=\"Mountainous\",Tool!L88=\"One Side\",Tool!M88=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E112=\"Mountainous\",Tool!K88,\"\")","v":""},{"$f":"IF(E112<>\"\",Drainage!G70,\"\")","v":""},"",{"$f":"IF(AND(F112=H112,G112=\"\"),\"\",VLOOKUP(Tool!P88,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=15,S96<=20),15,\"\")","v":""},{"$f":"IF(R23<>\"\",IF(T22>=$C$2,\"\",IF($C$2<(Tool!E111-Tool!$D$98),\"\",IF(Tool!D112<>\"\",IF(Tool!$D$98<>0,Tool!E111-Tool!$D$98,Tool!E111),\"\"))),\"\")","v":""},{"$f":"IF(S112=\"\",\"\",IF(R23=\"\",\"\",IF(Tool!E111<>\"\",IF(AND($C$2>=(Tool!E112-Tool!$D$98),(Tool!E113-Tool!$D$98)>=(Tool!E112-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E112-Tool!$D$98,Tool!E112),$C$2),\"\")))","v":""},{"$f":"IF(R112<>\"\",IF(Tool!H112=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U112=\"HM\",Tool!I112>0),Tool!I112,\"\")","v":""},{"$f":"IF(U112=\"HM\",IF(Tool!J112>0,IF(Tool!F112=\"Barrier Wall\",3,IF(Tool!F112=\"Depressed Grass\",Tool!J112*0.5,Tool!J112)),\"\"),\"\")","v":""},{"$f":"IF(R112<>\"\",IF(U112=\"HM\",Tool!F112,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E86>=26,E86<=30),26,\"\")","v":""},{"$f":"IF(D33>=$C$2,\"\",IF($C$2<(Tool!E88-Tool!$D$64),\"\",IF(Tool!D89<>\"\",IF(Tool!$D$64<>0,Tool!E88-Tool!$D$64,Tool!E88),\"\")))","v":""},{"$f":"IF(C34=\"\",\"\",IF(B114=\"\",$C$2,IF((D33-$C$9)>=$C$2,\"\",IF(Tool!E88<>\"\",IF(AND($C$2>=(Tool!E89-Tool!$D$64),(Tool!E90-Tool!$D$64)>=(Tool!E89-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E89-Tool!$D$64,Tool!E89),$C$2),\"\"))))","v":""},{"$f":"IF(C113=\"\",\"\",IF(B113<>\"\",IF(Tool!N89=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E113=\"Mountainous\",IF(Tool!I89>Tool!G89,0,IF(Tool!G89>0,Tool!G89+J113,\"\")),\"\")","v":""},{"$f":"IF(E113=\"Mountainous\",IF(Tool!H89>0,Tool!H89,\"\"),\"\")","v":""},{"$f":"IF(E113=\"Mountainous\",IF(Tool!I89>Tool!G89,Tool!G89,IF(Tool!I89>=0,Tool!I89)),\"\")","v":""},{"$f":"IF(E113=\"Mountainous\",Tool!O89,\"\")","v":""},{"$f":"IF(AND(K113=\"Urban/C&G\",E113=\"Mountainous\",Tool!L89=\"Both Sides\",Tool!M89=\"Both Sides\"),Tool!$M$62*2,IF(AND(K113=\"Urban/C&G\",E113=\"Mountainous\",Tool!L89=\"Both Sides\",Tool!M89=\"One Side\"),Tool!$M$62,IF(AND(K113=\"Urban/C&G\",E113=\"Mountainous\",Tool!L89=\"One Side\",Tool!M89=\"Both Sides\"),Tool!$M$62,IF(AND(K113=\"Urban/C&G\",E113=\"Mountainous\",Tool!L89=\"One Side\",Tool!M89=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E113=\"Mountainous\",Tool!K89,\"\")","v":""},{"$f":"IF(E113<>\"\",Drainage!G71,\"\")","v":""},"",{"$f":"IF(AND(F113=H113,G113=\"\"),\"\",VLOOKUP(Tool!P89,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=16,S96<=20),16,\"\")","v":""},{"$f":"IF(R24<>\"\",IF(T23>=$C$2,\"\",IF($C$2<(Tool!E112-Tool!$D$98),\"\",IF(Tool!D113<>\"\",IF(Tool!$D$98<>0,Tool!E112-Tool!$D$98,Tool!E112),\"\"))),\"\")","v":""},{"$f":"IF(S113=\"\",\"\",IF(R24=\"\",\"\",IF(Tool!E112<>\"\",IF(AND($C$2>=(Tool!E113-Tool!$D$98),(Tool!E114-Tool!$D$98)>=(Tool!E113-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E113-Tool!$D$98,Tool!E113),$C$2),\"\")))","v":""},{"$f":"IF(R113<>\"\",IF(Tool!H113=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U113=\"HM\",Tool!I113>0),Tool!I113,\"\")","v":""},{"$f":"IF(U113=\"HM\",IF(Tool!J113>0,IF(Tool!F113=\"Barrier Wall\",3,IF(Tool!F113=\"Depressed Grass\",Tool!J113*0.5,Tool!J113)),\"\"),\"\")","v":""},{"$f":"IF(R113<>\"\",IF(U113=\"HM\",Tool!F113,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E86>=27,E86<=30),27,\"\")","v":""},{"$f":"IF(D34>=$C$2,\"\",IF($C$2<(Tool!E89-Tool!$D$64),\"\",IF(Tool!D90<>\"\",IF(Tool!$D$64<>0,Tool!E89-Tool!$D$64,Tool!E89),\"\")))","v":""},{"$f":"IF(C35=\"\",\"\",IF(B115=\"\",$C$2,IF((D34-$C$9)>=$C$2,\"\",IF(Tool!E89<>\"\",IF(AND($C$2>=(Tool!E90-Tool!$D$64),(Tool!E91-Tool!$D$64)>=(Tool!E90-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E90-Tool!$D$64,Tool!E90),$C$2),\"\"))))","v":""},{"$f":"IF(C114=\"\",\"\",IF(B114<>\"\",IF(Tool!N90=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E114=\"Mountainous\",IF(Tool!I90>Tool!G90,0,IF(Tool!G90>0,Tool!G90+J114,\"\")),\"\")","v":""},{"$f":"IF(E114=\"Mountainous\",IF(Tool!H90>0,Tool!H90,\"\"),\"\")","v":""},{"$f":"IF(E114=\"Mountainous\",IF(Tool!I90>Tool!G90,Tool!G90,IF(Tool!I90>=0,Tool!I90)),\"\")","v":""},{"$f":"IF(E114=\"Mountainous\",Tool!O90,\"\")","v":""},{"$f":"IF(AND(K114=\"Urban/C&G\",E114=\"Mountainous\",Tool!L90=\"Both Sides\",Tool!M90=\"Both Sides\"),Tool!$M$62*2,IF(AND(K114=\"Urban/C&G\",E114=\"Mountainous\",Tool!L90=\"Both Sides\",Tool!M90=\"One Side\"),Tool!$M$62,IF(AND(K114=\"Urban/C&G\",E114=\"Mountainous\",Tool!L90=\"One Side\",Tool!M90=\"Both Sides\"),Tool!$M$62,IF(AND(K114=\"Urban/C&G\",E114=\"Mountainous\",Tool!L90=\"One Side\",Tool!M90=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E114=\"Mountainous\",Tool!K90,\"\")","v":""},{"$f":"IF(E114<>\"\",Drainage!G72,\"\")","v":""},"",{"$f":"IF(AND(F114=H114,G114=\"\"),\"\",VLOOKUP(Tool!P90,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=17,S96<=20),17,\"\")","v":""},{"$f":"IF(R25<>\"\",IF(T24>=$C$2,\"\",IF($C$2<(Tool!E113-Tool!$D$98),\"\",IF(Tool!D114<>\"\",IF(Tool!$D$98<>0,Tool!E113-Tool!$D$98,Tool!E113),\"\"))),\"\")","v":""},{"$f":"IF(S114=\"\",\"\",IF(R25=\"\",\"\",IF(Tool!E113<>\"\",IF(AND($C$2>=(Tool!E114-Tool!$D$98),(Tool!E115-Tool!$D$98)>=(Tool!E114-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E114-Tool!$D$98,Tool!E114),$C$2),\"\")))","v":""},{"$f":"IF(R114<>\"\",IF(Tool!H114=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U114=\"HM\",Tool!I114>0),Tool!I114,\"\")","v":""},{"$f":"IF(U114=\"HM\",IF(Tool!J114>0,IF(Tool!F114=\"Barrier Wall\",3,IF(Tool!F114=\"Depressed Grass\",Tool!J114*0.5,Tool!J114)),\"\"),\"\")","v":""},{"$f":"IF(R114<>\"\",IF(U114=\"HM\",Tool!F114,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E86>=28,E86<=30),28,\"\")","v":""},{"$f":"IF(D35>=$C$2,\"\",IF($C$2<(Tool!E90-Tool!$D$64),\"\",IF(Tool!D91<>\"\",IF(Tool!$D$64<>0,Tool!E90-Tool!$D$64,Tool!E90),\"\")))","v":""},{"$f":"IF(C36=\"\",\"\",IF(B116=\"\",$C$2,IF((D35-$C$9)>=$C$2,\"\",IF(Tool!E90<>\"\",IF(AND($C$2>=(Tool!E91-Tool!$D$64),(Tool!E92-Tool!$D$64)>=(Tool!E91-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E91-Tool!$D$64,Tool!E91),$C$2),\"\"))))","v":""},{"$f":"IF(C115=\"\",\"\",IF(B115<>\"\",IF(Tool!N91=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E115=\"Mountainous\",IF(Tool!I91>Tool!G91,0,IF(Tool!G91>0,Tool!G91+J115,\"\")),\"\")","v":""},{"$f":"IF(E115=\"Mountainous\",IF(Tool!H91>0,Tool!H91,\"\"),\"\")","v":""},{"$f":"IF(E115=\"Mountainous\",IF(Tool!I91>Tool!G91,Tool!G91,IF(Tool!I91>=0,Tool!I91)),\"\")","v":""},{"$f":"IF(E115=\"Mountainous\",Tool!O91,\"\")","v":""},{"$f":"IF(AND(K115=\"Urban/C&G\",E115=\"Mountainous\",Tool!L91=\"Both Sides\",Tool!M91=\"Both Sides\"),Tool!$M$62*2,IF(AND(K115=\"Urban/C&G\",E115=\"Mountainous\",Tool!L91=\"Both Sides\",Tool!M91=\"One Side\"),Tool!$M$62,IF(AND(K115=\"Urban/C&G\",E115=\"Mountainous\",Tool!L91=\"One Side\",Tool!M91=\"Both Sides\"),Tool!$M$62,IF(AND(K115=\"Urban/C&G\",E115=\"Mountainous\",Tool!L91=\"One Side\",Tool!M91=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E115=\"Mountainous\",Tool!K91,\"\")","v":""},{"$f":"IF(E115<>\"\",Drainage!G73,\"\")","v":""},"",{"$f":"IF(AND(F115=H115,G115=\"\"),\"\",VLOOKUP(Tool!P91,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=18,S96<=20),18,\"\")","v":""},{"$f":"IF(R26<>\"\",IF(T25>=$C$2,\"\",IF($C$2<(Tool!E114-Tool!$D$98),\"\",IF(Tool!D115<>\"\",IF(Tool!$D$98<>0,Tool!E114-Tool!$D$98,Tool!E114),\"\"))),\"\")","v":""},{"$f":"IF(S115=\"\",\"\",IF(R26=\"\",\"\",IF(Tool!E114<>\"\",IF(AND($C$2>=(Tool!E115-Tool!$D$98),(Tool!E116-Tool!$D$98)>=(Tool!E115-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E115-Tool!$D$98,Tool!E115),$C$2),\"\")))","v":""},{"$f":"IF(R115<>\"\",IF(Tool!H115=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U115=\"HM\",Tool!I115>0),Tool!I115,\"\")","v":""},{"$f":"IF(U115=\"HM\",IF(Tool!J115>0,IF(Tool!F115=\"Barrier Wall\",3,IF(Tool!F115=\"Depressed Grass\",Tool!J115*0.5,Tool!J115)),\"\"),\"\")","v":""},{"$f":"IF(R115<>\"\",IF(U115=\"HM\",Tool!F115,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(AND(E86>=29,E86<=30),29,\"\")","v":""},{"$f":"IF(D36>=$C$2,\"\",IF($C$2<(Tool!E91-Tool!$D$64),\"\",IF(Tool!D92<>\"\",IF(Tool!$D$64<>0,Tool!E91-Tool!$D$64,Tool!E91),\"\")))","v":""},{"$f":"IF(C37=\"\",\"\",IF(B117=\"\",$C$2,IF((D36-$C$9)>=$C$2,\"\",IF(Tool!E91<>\"\",IF(AND($C$2>=(Tool!E92-Tool!$D$64),(Tool!E93-Tool!$D$64)>=(Tool!E92-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E92-Tool!$D$64,Tool!E92),$C$2),\"\"))))","v":""},{"$f":"IF(C116=\"\",\"\",IF(B116<>\"\",IF(Tool!N92=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E116=\"Mountainous\",IF(Tool!I92>Tool!G92,0,IF(Tool!G92>0,Tool!G92+J116,\"\")),\"\")","v":""},{"$f":"IF(E116=\"Mountainous\",IF(Tool!H92>0,Tool!H92,\"\"),\"\")","v":""},{"$f":"IF(E116=\"Mountainous\",IF(Tool!I92>Tool!G92,Tool!G92,IF(Tool!I92>=0,Tool!I92)),\"\")","v":""},{"$f":"IF(E116=\"Mountainous\",Tool!O92,\"\")","v":""},{"$f":"IF(AND(K116=\"Urban/C&G\",E116=\"Mountainous\",Tool!L92=\"Both Sides\",Tool!M92=\"Both Sides\"),Tool!$M$62*2,IF(AND(K116=\"Urban/C&G\",E116=\"Mountainous\",Tool!L92=\"Both Sides\",Tool!M92=\"One Side\"),Tool!$M$62,IF(AND(K116=\"Urban/C&G\",E116=\"Mountainous\",Tool!L92=\"One Side\",Tool!M92=\"Both Sides\"),Tool!$M$62,IF(AND(K116=\"Urban/C&G\",E116=\"Mountainous\",Tool!L92=\"One Side\",Tool!M92=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E116=\"Mountainous\",Tool!K92,\"\")","v":""},{"$f":"IF(E116<>\"\",Drainage!G74,\"\")","v":""},"",{"$f":"IF(AND(F116=H116,G116=\"\"),\"\",VLOOKUP(Tool!P92,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96>=19,S96<=20),19,\"\")","v":""},{"$f":"IF(R27<>\"\",IF(T26>=$C$2,\"\",IF($C$2<(Tool!E115-Tool!$D$98),\"\",IF(Tool!D116<>\"\",IF(Tool!$D$98<>0,Tool!E115-Tool!$D$98,Tool!E115),\"\"))),\"\")","v":""},{"$f":"IF(S116=\"\",\"\",IF(R27=\"\",\"\",IF(Tool!E115<>\"\",IF(AND($C$2>=(Tool!E116-Tool!$D$98),(Tool!E117-Tool!$D$98)>=(Tool!E116-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E116-Tool!$D$98,Tool!E116),$C$2),\"\")))","v":""},{"$f":"IF(R116<>\"\",IF(Tool!H116=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U116=\"HM\",Tool!I116>0),Tool!I116,\"\")","v":""},{"$f":"IF(U116=\"HM\",IF(Tool!J116>0,IF(Tool!F116=\"Barrier Wall\",3,IF(Tool!F116=\"Depressed Grass\",Tool!J116*0.5,Tool!J116)),\"\"),\"\")","v":""},{"$f":"IF(R116<>\"\",IF(U116=\"HM\",Tool!F116,\"\"),\"\")","v":""},""]
[null,{"$f":"IF(E86=30,30,\"\")","v":""},{"$f":"IF(D37>=$C$2,\"\",IF($C$2<(Tool!E92-Tool!$D$64),\"\",IF(Tool!D93<>\"\",IF(Tool!$D$64<>0,Tool!E92-Tool!$D$64,Tool!E92),\"\")))","v":""},{"$f":"IF(C38=\"\",\"\",IF(B118=\"\",$C$2,IF((D37-$C$9)>=$C$2,\"\",IF(Tool!E92<>\"\",IF(AND($C$2>=(Tool!E93-Tool!$D$64),(Tool!E94-Tool!$D$64)>=(Tool!E93-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E93-Tool!$D$64,Tool!E93),$C$2),\"\"))))","v":""},{"$f":"IF(C117=\"\",\"\",IF(B117<>\"\",IF(Tool!N93=Tool!$E$9,\"Mountainous\",\"\"),\"\"))","v":""},{"$f":"IF(E117=\"Mountainous\",IF(Tool!I93>Tool!G93,0,IF(Tool!G93>0,Tool!G93+J117,\"\")),\"\")","v":""},{"$f":"IF(E117=\"Mountainous\",IF(Tool!H93>0,Tool!H93,\"\"),\"\")","v":""},{"$f":"IF(E117=\"Mountainous\",IF(Tool!I93>Tool!G93,Tool!G93,IF(Tool!I93>=0,Tool!I93)),\"\")","v":""},{"$f":"IF(E117=\"Mountainous\",Tool!O93,\"\")","v":""},{"$f":"IF(AND(K117=\"Urban/C&G\",E117=\"Mountainous\",Tool!L93=\"Both Sides\",Tool!M93=\"Both Sides\"),Tool!$M$62*2,IF(AND(K117=\"Urban/C&G\",E117=\"Mountainous\",Tool!L93=\"Both Sides\",Tool!M93=\"One Side\"),Tool!$M$62,IF(AND(K117=\"Urban/C&G\",E117=\"Mountainous\",Tool!L93=\"One Side\",Tool!M93=\"Both Sides\"),Tool!$M$62,IF(AND(K117=\"Urban/C&G\",E117=\"Mountainous\",Tool!L93=\"One Side\",Tool!M93=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E117=\"Mountainous\",Tool!K93,\"\")","v":""},{"$f":"IF(E117<>\"\",Drainage!G75,\"\")","v":""},"",{"$f":"IF(AND(F117=H117,G117=\"\"),\"\",VLOOKUP(Tool!P93,$AM$4:$AN$9,2,0))","v":""},"","","",{"$f":"IF(AND(S96=20),20,\"\")","v":""},{"$f":"IF(R28<>\"\",IF(T27>=$C$2,\"\",IF($C$2<(Tool!E116-Tool!$D$98),\"\",IF(Tool!D117<>\"\",IF(Tool!$D$98<>0,Tool!E116-Tool!$D$98,Tool!E116),\"\"))),\"\")","v":""},{"$f":"IF(S117=\"\",\"\",IF(R28=\"\",\"\",IF(Tool!E116<>\"\",IF(AND($C$2>=(Tool!E117-Tool!$D$98),(Tool!E118-Tool!$D$98)>=(Tool!E117-Tool!$D$98)),IF(Tool!$D$98<>\"\",Tool!E117-Tool!$D$98,Tool!E117),$C$2),\"\")))","v":""},{"$f":"IF(R117<>\"\",IF(Tool!H117=\"Heavy Mountainous\",\"HM\",\"\"),\"\")","v":""},{"$f":"IF(AND(U117=\"HM\",Tool!I117>0),Tool!I117,\"\")","v":""},{"$f":"IF(U117=\"HM\",IF(Tool!J117>0,IF(Tool!F117=\"Barrier Wall\",3,IF(Tool!F117=\"Depressed Grass\",Tool!J117*0.5,Tool!J117)),\"\"),\"\")","v":""},{"$f":"IF(R117<>\"\",IF(U117=\"HM\",Tool!F117,\"\"),\"\")","v":""},""]
[]
[null,"Rural - Length - One Side",{"$f":"SUMIFS(Q88:Q117,K88:K117,\"Rural/Ditch\",I88:I117,\"One Side\")","v":0},null,"Sidewalk Length - Mountainous:",{"$f":"SUMPRODUCT(L88:L117,Q88:Q117)","v":0},null,"Avg. Rd. Width:",{"$f":"IF(SUM(Q88:Q117),SUMPRODUCT(F88:F117,Q88:Q117)/SUM(Q88:Q117),0)","v":0},null,null,"Rural - Slope Rate - One Side:",{"$f":"IFERROR(SUMIFS(O88:O117,I88:I117,\"One Side\",K88:K117,\"Rural/Ditch\")/SUMIFS(M88:M117,I88:I117,\"One Side\",K88:K117,\"Rural/Ditch\"),0)","v":0},null,"Guardrail Length",{"$f":"SUM(P88:P117)","v":0},null,null,null,null,null,null,null,"Avg. Inside Shldr. Width:",{"$f":"IF(SUM(Y98:Y117),SUMPRODUCT(V98:V117,Y98:Y117)/SUM(Y98:Y117),0)","v":0}]
[null,"Rural - Length - Both Sides",{"$f":"SUMIFS(Q88:Q117,K88:K117,\"Rural/Ditch\",I88:I117,\"Both Sides\")","v":0},null,"Rural Slope Length - One Sides:",{"$f":"SUMIFS(M88:M117,I88:I117,\"One Side\",K88:K117,\"Rural/Ditch\")","v":0},null,"Avg. Retained Width:",{"$f":"IF(SUM(Q88:Q117)>0,SUMPRODUCT(H88:H117,Q88:Q117)/SUM(Q88:Q117),0)","v":0},null,null,"Rural - Slope Rate - Both Sides:",{"$f":"IFERROR(SUMIFS(O88:O117,I88:I117,\"Both Sides\",K88:K117,\"Rural/Ditch\")/SUMIFS(M88:M117,I88:I117,\"Both Sides\",K88:K117,\"Rural/Ditch\"),0)","v":0},null,null,null,null,null,null,null,null,null,null,"Avg. Interior Width:",{"$f":"IF(SUM(Y98:Y117)>0,SUMPRODUCT(W98:W117,Y98:Y117)/SUM(Y98:Y117),0)","v":0}]
[null,"Urban - Length - One Side",{"$f":"SUMIFS(Q88:Q117,K88:K117,\"Urban/C&G\",I88:I117,\"One Side\")","v":0},null,"Rural Slope Length - Both Sides:",{"$f":"SUMIFS(M88:M117,I88:I117,\"Both Sides\",K88:K117,\"Rural/Ditch\")*2","v":0},null,"Avg. Shoulder Width:",{"$f":"IF(SUM(Q88:Q117),SUMPRODUCT(G88:G117,Q88:Q117)/SUM(Q88:Q117),0)","v":0},null,null,"Urban - Slope Rate - One Side:",{"$f":"IFERROR(SUMIFS(O88:O117,I88:I117,\"One Side\",K88:K117,\"Urban/C&G\")/SUMIFS(M88:M117,I88:I117,\"One Side\",K88:K117,\"Urban/C&G\"),0)","v":0},null,null,null,null,null,null,null,null,null,null,"Avg. Fill Width:",{"$f":"Y119+Y120","v":0}]
[null,"Urban - Length - Both Sides",{"$f":"SUMIFS(Q88:Q117,K88:K117,\"Urban/C&G\",I88:I117,\"Both Sides\")","v":0},null,"Urban Slope Length - One Sides:",{"$f":"SUMIFS(M88:M117,I88:I117,\"One Side\",K88:K117,\"Urban/C&G\")","v":0},null,"Avg. Fill Width:",{"$f":"IF(I119>=I120,(I119+I121*2)-I120,0)","v":0},null,null,"Urban - Slope Rate - Both Sides:",{"$f":"IFERROR(SUMIFS(O88:O117,I88:I117,\"Both Sides\",K88:K117,\"Urban/C&G\")/SUMIFS(M88:M117,I88:I117,\"Both Sides\",K88:K117,\"Urban/C&G\"),0)","v":0},null,null,null,null,null,null,null,null,null,null,"Avg. Fill Area:",{"$f":"Y121*SUM(Y98:Y117)*5280","v":0},null,null,null,null,null,"TERRAIN"]
[null,null,null,null,"Urban Slope Length - Both Sides:",{"$f":"SUMIFS(M88:M117,I88:I117,\"Both Sides\",K88:K117,\"Urban/C&G\")*2","v":0},null,"Avg. Fill Area:",{"$f":"I122*SUM(Q88:Q117)*5280","v":0},null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Length:",{"$f":"SUM(Y98:Y117)","v":0}]
[null,null,null,null,null,null,null,"Length:",{"$f":"SUM(Q88:Q117)","v":0}]
[null,"Heavy Mountainous Terrain"]
[null,"Segments:",null,null,{"$f":"Tool!$J$61","v":1}]
[null,"Segments","Begin (mi)","End (mi)","Terrain Type","Total Pavement Width (ft)","Outside Shldr Width (ft)","Existing Pavement Width","Widen to One Side or Both?","Grass Strip","Rural/Urban","Sidewalks","Slope Length","Slope Rate","Slope Area (ft-mi)","Guardrail Length","Length"]
[null,{"$f":"IF(AND(E126>=1,E126<=30),1,\"\")","v":1},{"$f":"IF(Tool!D64<>\"\",IF(B9<>\"\",IF(Tool!D64=0,Tool!D64,Tool!D64-Tool!D64),\"\"),\"\")","v":""},{"$f":"IF(C128=\"\",\"\",IF((Tool!E65-Tool!D64)<(Tool!E64-Tool!D64),C2,IF(B9<>\"\",IF(Tool!E64<>\"\",IF(AND(B10=\"\",Tool!E64-Tool!D64<$C$2),$C$2,IF(B9=1,IF($C$2<(Tool!E64-Tool!$D$64),$C$2,IF(Tool!D64<>0,(Tool!E64-Tool!D64),Tool!E64)),\"\")),\"\"),\"\")))","v":""},{"$f":"IF(C128=\"\",\"\",IF(B128<>\"\",IF(Tool!N64=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E128=\"HM\",IF(Tool!I64>Tool!G64,0,IF(Tool!G64>0,Tool!G64+J128,\"\")),\"\")","v":""},{"$f":"IF(E128=\"HM\",IF(Tool!H64>0,Tool!H64,\"\"),\"\")","v":""},{"$f":"IF(E128=\"HM\",IF(Tool!I64>Tool!G64,Tool!G64,IF(Tool!I64>=0,Tool!I64)),\"\")","v":""},{"$f":"IF(E128=\"HM\",Tool!O64,\"\")","v":""},{"$f":"IF(AND(K128=\"Urban/C&G\",E128=\"HM\",Tool!L64=\"Both Sides\",Tool!M64=\"Both Sides\"),Tool!$M$62*2,IF(AND(K128=\"Urban/C&G\",E128=\"HM\",Tool!L64=\"Both Sides\",Tool!M64=\"One Side\"),Tool!$M$62,IF(AND(K128=\"Urban/C&G\",E128=\"HM\",Tool!L64=\"One Side\",Tool!M64=\"Both Sides\"),Tool!$M$62,IF(AND(K128=\"Urban/C&G\",E128=\"HM\",Tool!L64=\"One Side\",Tool!M64=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E128=\"HM\",Tool!K64,\"\")","v":""},{"$f":"IF(E128<>\"\",Drainage!G46,\"\")","v":""},{"$f":"IF(AND(F128=H128,G128=\"\"),\"\",D128-C128)","v":""},{"$f":"IF(AND(F128=H128,G128=\"\"),\"\",VLOOKUP(Tool!P64,$AM$4:$AN$9,2,0))","v":""},{"$f":"IF(AND(F128=H128,G128=\"\"),\"\",M128*N128)","v":""},{"$f":"IF(AND(N128=4,I128=\"Both Sides\"),M128*0.2,IF(AND(N128=4,I128=\"One Side\"),M128*0.1,IF(AND(N128=3,I128=\"One Side\"),M128*0.3,IF(AND(N128=3,I128=\"Both Sides\"),M128*0.5,IF(AND(N128=2,I128=\"One Side\"),M128*0.5,IF(AND(N128=2,I128=\"Both Sides\"),M128,IF(AND(N128=1,I128=\"One Side\"),M128*0.75,IF(AND(N128=1,I128=\"Both Sides\"),M128,\"\"))))))))","v":""},{"$f":"IF(E128=\"HM\",D128-C128,\"\")","v":""}]
[null,{"$f":"IF(AND(E126>=2,E126<=30),2,\"\")","v":""},{"$f":"IF(D9>=$C$2,\"\",IF($C$2<(Tool!E64-Tool!$D$64),\"\",IF(Tool!D65<>\"\",IF(Tool!$D$64<>0,Tool!E64-Tool!$D$64,Tool!E64),\"\")))","v":""},{"$f":"IF(C10=\"\",\"\",IF(B11=\"\",$C$2,IF((D9-$C$9)>=$C$2,\"\",IF(Tool!E64<>\"\",IF(AND($C$2>=(Tool!E65-Tool!$D$64),(Tool!E66-Tool!$D$64)>=(Tool!E65-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E65-Tool!$D$64,Tool!E65),$C$2),\"\"))))","v":""},{"$f":"IF(C129=\"\",\"\",IF(B129<>\"\",IF(Tool!N65=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E129=\"HM\",IF(Tool!I65>Tool!G65,0,IF(Tool!G65>0,Tool!G65+J129,\"\")),\"\")","v":""},{"$f":"IF(E129=\"HM\",IF(Tool!H65>0,Tool!H65,\"\"),\"\")","v":""},{"$f":"IF(E129=\"HM\",IF(Tool!I65>Tool!G65,Tool!G65,IF(Tool!I65>=0,Tool!I65)),\"\")","v":""},{"$f":"IF(E129=\"HM\",Tool!O65,\"\")","v":""},{"$f":"IF(AND(K129=\"Urban/C&G\",E129=\"HM\",Tool!L65=\"Both Sides\",Tool!M65=\"Both Sides\"),Tool!$M$62*2,IF(AND(K129=\"Urban/C&G\",E129=\"HM\",Tool!L65=\"Both Sides\",Tool!M65=\"One Side\"),Tool!$M$62,IF(AND(K129=\"Urban/C&G\",E129=\"HM\",Tool!L65=\"One Side\",Tool!M65=\"Both Sides\"),Tool!$M$62,IF(AND(K129=\"Urban/C&G\",E129=\"HM\",Tool!L65=\"One Side\",Tool!M65=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E129=\"HM\",Tool!K65,\"\")","v":""},{"$f":"IF(E129<>\"\",Drainage!G47,\"\")","v":""},"",{"$f":"IF(AND(F129=H129,G129=\"\"),\"\",VLOOKUP(Tool!P65,$AM$4:$AN$9,2,0))","v":""},"",{"$f":"IF(AND(N129=4,I129=\"Both Sides\"),M129*0.2,IF(AND(N129=4,I129=\"One Side\"),M129*0.1,IF(AND(N129=3,I129=\"One Side\"),M129*0.3,IF(AND(N129=3,I129=\"Both Sides\"),M129*0.5,IF(AND(N129=2,I129=\"One Side\"),M129*0.5,IF(AND(N129=2,I129=\"Both Sides\"),M129,IF(AND(N129=1,I129=\"One Side\"),M129*0.75,IF(AND(N129=1,I129=\"Both Sides\"),M129,\"\"))))))))","v":""},{"$f":"IF(E129=\"HM\",D129-C129,\"\")","v":""}]
[null,{"$f":"IF(AND(E126>=3,E126<=30),3,\"\")","v":""},{"$f":"IF(D10>=$C$2,\"\",IF($C$2<(Tool!E65-Tool!$D$64),\"\",IF(Tool!D66<>\"\",IF(Tool!$D$64<>0,Tool!E65-Tool!$D$64,Tool!E65),\"\")))","v":""},{"$f":"IF(C11=\"\",\"\",IF(B12=\"\",$C$2,IF((D10-$C$9)>=$C$2,\"\",IF(Tool!E65<>\"\",IF(AND($C$2>=(Tool!E66-Tool!$D$64),(Tool!E67-Tool!$D$64)>=(Tool!E66-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E66-Tool!$D$64,Tool!E66),$C$2),\"\"))))","v":""},{"$f":"IF(C130=\"\",\"\",IF(B130<>\"\",IF(Tool!N66=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E130=\"HM\",IF(Tool!I66>Tool!G66,0,IF(Tool!G66>0,Tool!G66+J130,\"\")),\"\")","v":""},{"$f":"IF(E130=\"HM\",IF(Tool!H66>0,Tool!H66,\"\"),\"\")","v":""},{"$f":"IF(E130=\"HM\",IF(Tool!I66>Tool!G66,Tool!G66,IF(Tool!I66>=0,Tool!I66)),\"\")","v":""},{"$f":"IF(E130=\"HM\",Tool!O66,\"\")","v":""},{"$f":"IF(AND(K130=\"Urban/C&G\",E130=\"HM\",Tool!L66=\"Both Sides\",Tool!M66=\"Both Sides\"),Tool!$M$62*2,IF(AND(K130=\"Urban/C&G\",E130=\"HM\",Tool!L66=\"Both Sides\",Tool!M66=\"One Side\"),Tool!$M$62,IF(AND(K130=\"Urban/C&G\",E130=\"HM\",Tool!L66=\"One Side\",Tool!M66=\"Both Sides\"),Tool!$M$62,IF(AND(K130=\"Urban/C&G\",E130=\"HM\",Tool!L66=\"One Side\",Tool!M66=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E130=\"HM\",Tool!K66,\"\")","v":""},{"$f":"IF(E130<>\"\",Drainage!G48,\"\")","v":""},"",{"$f":"IF(AND(F130=H130,G130=\"\"),\"\",VLOOKUP(Tool!P66,$AM$4:$AN$9,2,0))","v":""},"","",{"$f":"IF(E130=\"HM\",D130-C130,\"\")","v":""}]
[null,{"$f":"IF(AND(E126>=4,E126<=30),4,\"\")","v":""},{"$f":"IF(D11>=$C$2,\"\",IF($C$2<(Tool!E66-Tool!$D$64),\"\",IF(Tool!D67<>\"\",IF(Tool!$D$64<>0,Tool!E66-Tool!$D$64,Tool!E66),\"\")))","v":""},{"$f":"IF(C12=\"\",\"\",IF(B13=\"\",$C$2,IF((D11-$C$9)>=$C$2,\"\",IF(Tool!E66<>\"\",IF(AND($C$2>=(Tool!E67-Tool!$D$64),(Tool!E68-Tool!$D$64)>=(Tool!E67-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E67-Tool!$D$64,Tool!E67),$C$2),\"\"))))","v":""},{"$f":"IF(C131=\"\",\"\",IF(B131<>\"\",IF(Tool!N67=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E131=\"HM\",IF(Tool!I67>Tool!G67,0,IF(Tool!G67>0,Tool!G67+J131,\"\")),\"\")","v":""},{"$f":"IF(E131=\"HM\",IF(Tool!H67>0,Tool!H67,\"\"),\"\")","v":""},{"$f":"IF(E131=\"HM\",IF(Tool!I67>Tool!G67,Tool!G67,IF(Tool!I67>=0,Tool!I67)),\"\")","v":""},{"$f":"IF(E131=\"HM\",Tool!O67,\"\")","v":""},{"$f":"IF(AND(K131=\"Urban/C&G\",E131=\"HM\",Tool!L67=\"Both Sides\",Tool!M67=\"Both Sides\"),Tool!$M$62*2,IF(AND(K131=\"Urban/C&G\",E131=\"HM\",Tool!L67=\"Both Sides\",Tool!M67=\"One Side\"),Tool!$M$62,IF(AND(K131=\"Urban/C&G\",E131=\"HM\",Tool!L67=\"One Side\",Tool!M67=\"Both Sides\"),Tool!$M$62,IF(AND(K131=\"Urban/C&G\",E131=\"HM\",Tool!L67=\"One Side\",Tool!M67=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E131=\"HM\",Tool!K67,\"\")","v":""},{"$f":"IF(E131<>\"\",Drainage!G49,\"\")","v":""},"",{"$f":"IF(AND(F131=H131,G131=\"\"),\"\",VLOOKUP(Tool!P67,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=5,E126<=30),5,\"\")","v":""},{"$f":"IF(D12>=$C$2,\"\",IF($C$2<(Tool!E67-Tool!$D$64),\"\",IF(Tool!D68<>\"\",IF(Tool!$D$64<>0,Tool!E67-Tool!$D$64,Tool!E67),\"\")))","v":""},{"$f":"IF(C13=\"\",\"\",IF(B14=\"\",$C$2,IF((D12-$C$9)>=$C$2,\"\",IF(Tool!E67<>\"\",IF(AND($C$2>=(Tool!E68-Tool!$D$64),(Tool!E69-Tool!$D$64)>=(Tool!E68-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E68-Tool!$D$64,Tool!E68),$C$2),\"\"))))","v":""},{"$f":"IF(C132=\"\",\"\",IF(B132<>\"\",IF(Tool!N68=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E132=\"HM\",IF(Tool!I68>Tool!G68,0,IF(Tool!G68>0,Tool!G68+J132,\"\")),\"\")","v":""},{"$f":"IF(E132=\"HM\",IF(Tool!H68>0,Tool!H68,\"\"),\"\")","v":""},{"$f":"IF(E132=\"HM\",IF(Tool!I68>Tool!G68,Tool!G68,IF(Tool!I68>=0,Tool!I68)),\"\")","v":""},{"$f":"IF(E132=\"HM\",Tool!O68,\"\")","v":""},{"$f":"IF(AND(K132=\"Urban/C&G\",E132=\"HM\",Tool!L68=\"Both Sides\",Tool!M68=\"Both Sides\"),Tool!$M$62*2,IF(AND(K132=\"Urban/C&G\",E132=\"HM\",Tool!L68=\"Both Sides\",Tool!M68=\"One Side\"),Tool!$M$62,IF(AND(K132=\"Urban/C&G\",E132=\"HM\",Tool!L68=\"One Side\",Tool!M68=\"Both Sides\"),Tool!$M$62,IF(AND(K132=\"Urban/C&G\",E132=\"HM\",Tool!L68=\"One Side\",Tool!M68=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E132=\"HM\",Tool!K68,\"\")","v":""},{"$f":"IF(E132<>\"\",Drainage!G50,\"\")","v":""},"",{"$f":"IF(AND(F132=H132,G132=\"\"),\"\",VLOOKUP(Tool!P68,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=6,E126<=30),6,\"\")","v":""},{"$f":"IF(D13>=$C$2,\"\",IF($C$2<(Tool!E68-Tool!$D$64),\"\",IF(Tool!D69<>\"\",IF(Tool!$D$64<>0,Tool!E68-Tool!$D$64,Tool!E68),\"\")))","v":""},{"$f":"IF(C14=\"\",\"\",IF(B15=\"\",$C$2,IF((D13-$C$9)>=$C$2,\"\",IF(Tool!E68<>\"\",IF(AND($C$2>=(Tool!E69-Tool!$D$64),(Tool!E70-Tool!$D$64)>=(Tool!E69-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E69-Tool!$D$64,Tool!E69),$C$2),\"\"))))","v":""},{"$f":"IF(C133=\"\",\"\",IF(B133<>\"\",IF(Tool!N69=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E133=\"HM\",IF(Tool!I69>Tool!G69,0,IF(Tool!G69>0,Tool!G69+J133,\"\")),\"\")","v":""},{"$f":"IF(E133=\"HM\",IF(Tool!H69>0,Tool!H69,\"\"),\"\")","v":""},{"$f":"IF(E133=\"HM\",IF(Tool!I69>Tool!G69,Tool!G69,IF(Tool!I69>=0,Tool!I69)),\"\")","v":""},{"$f":"IF(E133=\"HM\",Tool!O69,\"\")","v":""},{"$f":"IF(AND(K133=\"Urban/C&G\",E133=\"HM\",Tool!L69=\"Both Sides\",Tool!M69=\"Both Sides\"),Tool!$M$62*2,IF(AND(K133=\"Urban/C&G\",E133=\"HM\",Tool!L69=\"Both Sides\",Tool!M69=\"One Side\"),Tool!$M$62,IF(AND(K133=\"Urban/C&G\",E133=\"HM\",Tool!L69=\"One Side\",Tool!M69=\"Both Sides\"),Tool!$M$62,IF(AND(K133=\"Urban/C&G\",E133=\"HM\",Tool!L69=\"One Side\",Tool!M69=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E133=\"HM\",Tool!K69,\"\")","v":""},{"$f":"IF(E133<>\"\",Drainage!G51,\"\")","v":""},"",{"$f":"IF(AND(F133=H133,G133=\"\"),\"\",VLOOKUP(Tool!P69,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=7,E126<=30),7,\"\")","v":""},{"$f":"IF(D14>=$C$2,\"\",IF($C$2<(Tool!E69-Tool!$D$64),\"\",IF(Tool!D70<>\"\",IF(Tool!$D$64<>0,Tool!E69-Tool!$D$64,Tool!E69),\"\")))","v":""},{"$f":"IF(C15=\"\",\"\",IF(B16=\"\",$C$2,IF((D14-$C$9)>=$C$2,\"\",IF(Tool!E69<>\"\",IF(AND($C$2>=(Tool!E70-Tool!$D$64),(Tool!E71-Tool!$D$64)>=(Tool!E70-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E70-Tool!$D$64,Tool!E70),$C$2),\"\"))))","v":""},{"$f":"IF(C134=\"\",\"\",IF(B134<>\"\",IF(Tool!N70=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E134=\"HM\",IF(Tool!I70>Tool!G70,0,IF(Tool!G70>0,Tool!G70+J134,\"\")),\"\")","v":""},{"$f":"IF(E134=\"HM\",IF(Tool!H70>0,Tool!H70,\"\"),\"\")","v":""},{"$f":"IF(E134=\"HM\",IF(Tool!I70>Tool!G70,Tool!G70,IF(Tool!I70>=0,Tool!I70)),\"\")","v":""},{"$f":"IF(E134=\"HM\",Tool!O70,\"\")","v":""},{"$f":"IF(AND(K134=\"Urban/C&G\",E134=\"HM\",Tool!L70=\"Both Sides\",Tool!M70=\"Both Sides\"),Tool!$M$62*2,IF(AND(K134=\"Urban/C&G\",E134=\"HM\",Tool!L70=\"Both Sides\",Tool!M70=\"One Side\"),Tool!$M$62,IF(AND(K134=\"Urban/C&G\",E134=\"HM\",Tool!L70=\"One Side\",Tool!M70=\"Both Sides\"),Tool!$M$62,IF(AND(K134=\"Urban/C&G\",E134=\"HM\",Tool!L70=\"One Side\",Tool!M70=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E134=\"HM\",Tool!K70,\"\")","v":""},{"$f":"IF(E134<>\"\",Drainage!G52,\"\")","v":""},"",{"$f":"IF(AND(F134=H134,G134=\"\"),\"\",VLOOKUP(Tool!P70,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=8,E126<=30),8,\"\")","v":""},{"$f":"IF(D15>=$C$2,\"\",IF($C$2<(Tool!E70-Tool!$D$64),\"\",IF(Tool!D71<>\"\",IF(Tool!$D$64<>0,Tool!E70-Tool!$D$64,Tool!E70),\"\")))","v":""},{"$f":"IF(C16=\"\",\"\",IF(B17=\"\",$C$2,IF((D15-$C$9)>=$C$2,\"\",IF(Tool!E70<>\"\",IF(AND($C$2>=(Tool!E71-Tool!$D$64),(Tool!E72-Tool!$D$64)>=(Tool!E71-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E71-Tool!$D$64,Tool!E71),$C$2),\"\"))))","v":""},{"$f":"IF(C135=\"\",\"\",IF(B135<>\"\",IF(Tool!N71=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E135=\"HM\",IF(Tool!I71>Tool!G71,0,IF(Tool!G71>0,Tool!G71+J135,\"\")),\"\")","v":""},{"$f":"IF(E135=\"HM\",IF(Tool!H71>0,Tool!H71,\"\"),\"\")","v":""},{"$f":"IF(E135=\"HM\",IF(Tool!I71>Tool!G71,Tool!G71,IF(Tool!I71>=0,Tool!I71)),\"\")","v":""},{"$f":"IF(E135=\"HM\",Tool!O71,\"\")","v":""},{"$f":"IF(AND(K135=\"Urban/C&G\",E135=\"HM\",Tool!L71=\"Both Sides\",Tool!M71=\"Both Sides\"),Tool!$M$62*2,IF(AND(K135=\"Urban/C&G\",E135=\"HM\",Tool!L71=\"Both Sides\",Tool!M71=\"One Side\"),Tool!$M$62,IF(AND(K135=\"Urban/C&G\",E135=\"HM\",Tool!L71=\"One Side\",Tool!M71=\"Both Sides\"),Tool!$M$62,IF(AND(K135=\"Urban/C&G\",E135=\"HM\",Tool!L71=\"One Side\",Tool!M71=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E135=\"HM\",Tool!K71,\"\")","v":""},{"$f":"IF(E135<>\"\",Drainage!G53,\"\")","v":""},"",{"$f":"IF(AND(F135=H135,G135=\"\"),\"\",VLOOKUP(Tool!P71,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=9,F126<=20),9,\"\")","v":""},{"$f":"IF(D16>=$C$2,\"\",IF($C$2<(Tool!E71-Tool!$D$64),\"\",IF(Tool!D72<>\"\",IF(Tool!$D$64<>0,Tool!E71-Tool!$D$64,Tool!E71),\"\")))","v":""},{"$f":"IF(C17=\"\",\"\",IF(B18=\"\",$C$2,IF((D16-$C$9)>=$C$2,\"\",IF(Tool!E71<>\"\",IF(AND($C$2>=(Tool!E72-Tool!$D$64),(Tool!E73-Tool!$D$64)>=(Tool!E72-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E72-Tool!$D$64,Tool!E72),$C$2),\"\"))))","v":""},{"$f":"IF(C136=\"\",\"\",IF(B136<>\"\",IF(Tool!N72=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E136=\"HM\",IF(Tool!I72>Tool!G72,0,IF(Tool!G72>0,Tool!G72+J136,\"\")),\"\")","v":""},{"$f":"IF(E136=\"HM\",IF(Tool!H72>0,Tool!H72,\"\"),\"\")","v":""},{"$f":"IF(E136=\"HM\",IF(Tool!I72>Tool!G72,Tool!G72,IF(Tool!I72>=0,Tool!I72)),\"\")","v":""},{"$f":"IF(E136=\"HM\",Tool!O72,\"\")","v":""},{"$f":"IF(AND(K136=\"Urban/C&G\",E136=\"HM\",Tool!L72=\"Both Sides\",Tool!M72=\"Both Sides\"),Tool!$M$62*2,IF(AND(K136=\"Urban/C&G\",E136=\"HM\",Tool!L72=\"Both Sides\",Tool!M72=\"One Side\"),Tool!$M$62,IF(AND(K136=\"Urban/C&G\",E136=\"HM\",Tool!L72=\"One Side\",Tool!M72=\"Both Sides\"),Tool!$M$62,IF(AND(K136=\"Urban/C&G\",E136=\"HM\",Tool!L72=\"One Side\",Tool!M72=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E136=\"HM\",Tool!K72,\"\")","v":""},{"$f":"IF(E136<>\"\",Drainage!G54,\"\")","v":""},"",{"$f":"IF(AND(F136=H136,G136=\"\"),\"\",VLOOKUP(Tool!P72,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=10,E126<=30),10,\"\")","v":""},{"$f":"IF(D17>=$C$2,\"\",IF($C$2<(Tool!E72-Tool!$D$64),\"\",IF(Tool!D73<>\"\",IF(Tool!$D$64<>0,Tool!E72-Tool!$D$64,Tool!E72),\"\")))","v":""},{"$f":"IF(C18=\"\",\"\",IF(B19=\"\",$C$2,IF((D17-$C$9)>=$C$2,\"\",IF(Tool!E72<>\"\",IF(AND($C$2>=(Tool!E73-Tool!$D$64),(Tool!E74-Tool!$D$64)>=(Tool!E73-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E73-Tool!$D$64,Tool!E73),$C$2),\"\"))))","v":""},{"$f":"IF(C137=\"\",\"\",IF(B137<>\"\",IF(Tool!N73=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E137=\"HM\",IF(Tool!I73>Tool!G73,0,IF(Tool!G73>0,Tool!G73+J137,\"\")),\"\")","v":""},{"$f":"IF(E137=\"HM\",IF(Tool!H73>0,Tool!H73,\"\"),\"\")","v":""},{"$f":"IF(E137=\"HM\",IF(Tool!I73>Tool!G73,Tool!G73,IF(Tool!I73>=0,Tool!I73)),\"\")","v":""},{"$f":"IF(E137=\"HM\",Tool!O73,\"\")","v":""},{"$f":"IF(AND(K137=\"Urban/C&G\",E137=\"HM\",Tool!L73=\"Both Sides\",Tool!M73=\"Both Sides\"),Tool!$M$62*2,IF(AND(K137=\"Urban/C&G\",E137=\"HM\",Tool!L73=\"Both Sides\",Tool!M73=\"One Side\"),Tool!$M$62,IF(AND(K137=\"Urban/C&G\",E137=\"HM\",Tool!L73=\"One Side\",Tool!M73=\"Both Sides\"),Tool!$M$62,IF(AND(K137=\"Urban/C&G\",E137=\"HM\",Tool!L73=\"One Side\",Tool!M73=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E137=\"HM\",Tool!K73,\"\")","v":""},{"$f":"IF(E137<>\"\",Drainage!G55,\"\")","v":""},"",{"$f":"IF(AND(F137=H137,G137=\"\"),\"\",VLOOKUP(Tool!P73,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=11,E126<=30),11,\"\")","v":""},{"$f":"IF(D18>=$C$2,\"\",IF($C$2<(Tool!E73-Tool!$D$64),\"\",IF(Tool!D74<>\"\",IF(Tool!$D$64<>0,Tool!E73-Tool!$D$64,Tool!E73),\"\")))","v":""},{"$f":"IF(C19=\"\",\"\",IF(B20=\"\",$C$2,IF((D18-$C$9)>=$C$2,\"\",IF(Tool!E73<>\"\",IF(AND($C$2>=(Tool!E74-Tool!$D$64),(Tool!E75-Tool!$D$64)>=(Tool!E74-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E74-Tool!$D$64,Tool!E74),$C$2),\"\"))))","v":""},{"$f":"IF(C138=\"\",\"\",IF(B138<>\"\",IF(Tool!N74=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E138=\"HM\",IF(Tool!I74>Tool!G74,0,IF(Tool!G74>0,Tool!G74+J138,\"\")),\"\")","v":""},{"$f":"IF(E138=\"HM\",IF(Tool!H74>0,Tool!H74,\"\"),\"\")","v":""},{"$f":"IF(E138=\"HM\",IF(Tool!I74>Tool!G74,Tool!G74,IF(Tool!I74>=0,Tool!I74)),\"\")","v":""},{"$f":"IF(E138=\"HM\",Tool!O74,\"\")","v":""},{"$f":"IF(AND(K138=\"Urban/C&G\",E138=\"HM\",Tool!L74=\"Both Sides\",Tool!M74=\"Both Sides\"),Tool!$M$62*2,IF(AND(K138=\"Urban/C&G\",E138=\"HM\",Tool!L74=\"Both Sides\",Tool!M74=\"One Side\"),Tool!$M$62,IF(AND(K138=\"Urban/C&G\",E138=\"HM\",Tool!L74=\"One Side\",Tool!M74=\"Both Sides\"),Tool!$M$62,IF(AND(K138=\"Urban/C&G\",E138=\"HM\",Tool!L74=\"One Side\",Tool!M74=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E138=\"HM\",Tool!K74,\"\")","v":""},{"$f":"IF(E138<>\"\",Drainage!G56,\"\")","v":""},"",{"$f":"IF(AND(F138=H138,G138=\"\"),\"\",VLOOKUP(Tool!P74,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=12,F126<=30),12,\"\")","v":""},{"$f":"IF(D19>=$C$2,\"\",IF($C$2<(Tool!E74-Tool!$D$64),\"\",IF(Tool!D75<>\"\",IF(Tool!$D$64<>0,Tool!E74-Tool!$D$64,Tool!E74),\"\")))","v":""},{"$f":"IF(C20=\"\",\"\",IF(B21=\"\",$C$2,IF((D19-$C$9)>=$C$2,\"\",IF(Tool!E74<>\"\",IF(AND($C$2>=(Tool!E75-Tool!$D$64),(Tool!E76-Tool!$D$64)>=(Tool!E75-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E75-Tool!$D$64,Tool!E75),$C$2),\"\"))))","v":""},{"$f":"IF(C139=\"\",\"\",IF(B139<>\"\",IF(Tool!N75=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E139=\"HM\",IF(Tool!I75>Tool!G75,0,IF(Tool!G75>0,Tool!G75+J139,\"\")),\"\")","v":""},{"$f":"IF(E139=\"HM\",IF(Tool!H75>0,Tool!H75,\"\"),\"\")","v":""},{"$f":"IF(E139=\"HM\",IF(Tool!I75>Tool!G75,Tool!G75,IF(Tool!I75>=0,Tool!I75)),\"\")","v":""},{"$f":"IF(E139=\"HM\",Tool!O75,\"\")","v":""},{"$f":"IF(AND(K139=\"Urban/C&G\",E139=\"HM\",Tool!L75=\"Both Sides\",Tool!M75=\"Both Sides\"),Tool!$M$62*2,IF(AND(K139=\"Urban/C&G\",E139=\"HM\",Tool!L75=\"Both Sides\",Tool!M75=\"One Side\"),Tool!$M$62,IF(AND(K139=\"Urban/C&G\",E139=\"HM\",Tool!L75=\"One Side\",Tool!M75=\"Both Sides\"),Tool!$M$62,IF(AND(K139=\"Urban/C&G\",E139=\"HM\",Tool!L75=\"One Side\",Tool!M75=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E139=\"HM\",Tool!K75,\"\")","v":""},{"$f":"IF(E139<>\"\",Drainage!G57,\"\")","v":""},"",{"$f":"IF(AND(F139=H139,G139=\"\"),\"\",VLOOKUP(Tool!P75,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=13,E126<=30),13,\"\")","v":""},{"$f":"IF(D20>=$C$2,\"\",IF($C$2<(Tool!E75-Tool!$D$64),\"\",IF(Tool!D76<>\"\",IF(Tool!$D$64<>0,Tool!E75-Tool!$D$64,Tool!E75),\"\")))","v":""},{"$f":"IF(C21=\"\",\"\",IF(B22=\"\",$C$2,IF((D20-$C$9)>=$C$2,\"\",IF(Tool!E75<>\"\",IF(AND($C$2>=(Tool!E76-Tool!$D$64),(Tool!E77-Tool!$D$64)>=(Tool!E76-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E76-Tool!$D$64,Tool!E76),$C$2),\"\"))))","v":""},{"$f":"IF(C140=\"\",\"\",IF(B140<>\"\",IF(Tool!N76=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E140=\"HM\",IF(Tool!I76>Tool!G76,0,IF(Tool!G76>0,Tool!G76+J140,\"\")),\"\")","v":""},{"$f":"IF(E140=\"HM\",IF(Tool!H76>0,Tool!H76,\"\"),\"\")","v":""},{"$f":"IF(E140=\"HM\",IF(Tool!I76>Tool!G76,Tool!G76,IF(Tool!I76>=0,Tool!I76)),\"\")","v":""},{"$f":"IF(E140=\"HM\",Tool!O76,\"\")","v":""},{"$f":"IF(AND(K140=\"Urban/C&G\",E140=\"HM\",Tool!L76=\"Both Sides\",Tool!M76=\"Both Sides\"),Tool!$M$62*2,IF(AND(K140=\"Urban/C&G\",E140=\"HM\",Tool!L76=\"Both Sides\",Tool!M76=\"One Side\"),Tool!$M$62,IF(AND(K140=\"Urban/C&G\",E140=\"HM\",Tool!L76=\"One Side\",Tool!M76=\"Both Sides\"),Tool!$M$62,IF(AND(K140=\"Urban/C&G\",E140=\"HM\",Tool!L76=\"One Side\",Tool!M76=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E140=\"HM\",Tool!K76,\"\")","v":""},{"$f":"IF(E140<>\"\",Drainage!G58,\"\")","v":""},"",{"$f":"IF(AND(F140=H140,G140=\"\"),\"\",VLOOKUP(Tool!P76,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=14,E126<=30),14,\"\")","v":""},{"$f":"IF(D21>=$C$2,\"\",IF($C$2<(Tool!E76-Tool!$D$64),\"\",IF(Tool!D77<>\"\",IF(Tool!$D$64<>0,Tool!E76-Tool!$D$64,Tool!E76),\"\")))","v":""},{"$f":"IF(C22=\"\",\"\",IF(B23=\"\",$C$2,IF((D21-$C$9)>=$C$2,\"\",IF(Tool!E76<>\"\",IF(AND($C$2>=(Tool!E77-Tool!$D$64),(Tool!E78-Tool!$D$64)>=(Tool!E77-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E77-Tool!$D$64,Tool!E77),$C$2),\"\"))))","v":""},{"$f":"IF(C141=\"\",\"\",IF(B141<>\"\",IF(Tool!N77=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E141=\"HM\",IF(Tool!I77>Tool!G77,0,IF(Tool!G77>0,Tool!G77+J141,\"\")),\"\")","v":""},{"$f":"IF(E141=\"HM\",IF(Tool!H77>0,Tool!H77,\"\"),\"\")","v":""},{"$f":"IF(E141=\"HM\",IF(Tool!I77>Tool!G77,Tool!G77,IF(Tool!I77>=0,Tool!I77)),\"\")","v":""},{"$f":"IF(E141=\"HM\",Tool!O77,\"\")","v":""},{"$f":"IF(AND(K141=\"Urban/C&G\",E141=\"HM\",Tool!L77=\"Both Sides\",Tool!M77=\"Both Sides\"),Tool!$M$62*2,IF(AND(K141=\"Urban/C&G\",E141=\"HM\",Tool!L77=\"Both Sides\",Tool!M77=\"One Side\"),Tool!$M$62,IF(AND(K141=\"Urban/C&G\",E141=\"HM\",Tool!L77=\"One Side\",Tool!M77=\"Both Sides\"),Tool!$M$62,IF(AND(K141=\"Urban/C&G\",E141=\"HM\",Tool!L77=\"One Side\",Tool!M77=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E141=\"HM\",Tool!K77,\"\")","v":""},{"$f":"IF(E141<>\"\",Drainage!G59,\"\")","v":""},"",{"$f":"IF(AND(F141=H141,G141=\"\"),\"\",VLOOKUP(Tool!P77,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=15,E126<=30),15,\"\")","v":""},{"$f":"IF(D22>=$C$2,\"\",IF($C$2<(Tool!E77-Tool!$D$64),\"\",IF(Tool!D78<>\"\",IF(Tool!$D$64<>0,Tool!E77-Tool!$D$64,Tool!E77),\"\")))","v":""},{"$f":"IF(C23=\"\",\"\",IF(B24=\"\",$C$2,IF((D22-$C$9)>=$C$2,\"\",IF(Tool!E77<>\"\",IF(AND($C$2>=(Tool!E78-Tool!$D$64),(Tool!E79-Tool!$D$64)>=(Tool!E78-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E78-Tool!$D$64,Tool!E78),$C$2),\"\"))))","v":""},{"$f":"IF(C142=\"\",\"\",IF(B142<>\"\",IF(Tool!N78=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E142=\"HM\",IF(Tool!I78>Tool!G78,0,IF(Tool!G78>0,Tool!G78+J142,\"\")),\"\")","v":""},{"$f":"IF(E142=\"HM\",IF(Tool!H78>0,Tool!H78,\"\"),\"\")","v":""},{"$f":"IF(E142=\"HM\",IF(Tool!I78>Tool!G78,Tool!G78,IF(Tool!I78>=0,Tool!I78)),\"\")","v":""},{"$f":"IF(E142=\"HM\",Tool!O78,\"\")","v":""},{"$f":"IF(AND(K142=\"Urban/C&G\",E142=\"HM\",Tool!L78=\"Both Sides\",Tool!M78=\"Both Sides\"),Tool!$M$62*2,IF(AND(K142=\"Urban/C&G\",E142=\"HM\",Tool!L78=\"Both Sides\",Tool!M78=\"One Side\"),Tool!$M$62,IF(AND(K142=\"Urban/C&G\",E142=\"HM\",Tool!L78=\"One Side\",Tool!M78=\"Both Sides\"),Tool!$M$62,IF(AND(K142=\"Urban/C&G\",E142=\"HM\",Tool!L78=\"One Side\",Tool!M78=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E142=\"HM\",Tool!K78,\"\")","v":""},{"$f":"IF(E142<>\"\",Drainage!G60,\"\")","v":""},"",{"$f":"IF(AND(F142=H142,G142=\"\"),\"\",VLOOKUP(Tool!P78,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=16,E126<=30),16,\"\")","v":""},{"$f":"IF(D23>=$C$2,\"\",IF($C$2<(Tool!E78-Tool!$D$64),\"\",IF(Tool!D79<>\"\",IF(Tool!$D$64<>0,Tool!E78-Tool!$D$64,Tool!E78),\"\")))","v":""},{"$f":"IF(C24=\"\",\"\",IF(B25=\"\",$C$2,IF((D23-$C$9)>=$C$2,\"\",IF(Tool!E78<>\"\",IF(AND($C$2>=(Tool!E79-Tool!$D$64),(Tool!E80-Tool!$D$64)>=(Tool!E79-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E79-Tool!$D$64,Tool!E79),$C$2),\"\"))))","v":""},{"$f":"IF(C143=\"\",\"\",IF(B143<>\"\",IF(Tool!N79=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E143=\"HM\",IF(Tool!I79>Tool!G79,0,IF(Tool!G79>0,Tool!G79+J143,\"\")),\"\")","v":""},{"$f":"IF(E143=\"HM\",IF(Tool!H79>0,Tool!H79,\"\"),\"\")","v":""},{"$f":"IF(E143=\"HM\",IF(Tool!I79>Tool!G79,Tool!G79,IF(Tool!I79>=0,Tool!I79)),\"\")","v":""},{"$f":"IF(E143=\"HM\",Tool!O79,\"\")","v":""},{"$f":"IF(AND(K143=\"Urban/C&G\",E143=\"HM\",Tool!L79=\"Both Sides\",Tool!M79=\"Both Sides\"),Tool!$M$62*2,IF(AND(K143=\"Urban/C&G\",E143=\"HM\",Tool!L79=\"Both Sides\",Tool!M79=\"One Side\"),Tool!$M$62,IF(AND(K143=\"Urban/C&G\",E143=\"HM\",Tool!L79=\"One Side\",Tool!M79=\"Both Sides\"),Tool!$M$62,IF(AND(K143=\"Urban/C&G\",E143=\"HM\",Tool!L79=\"One Side\",Tool!M79=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E143=\"HM\",Tool!K79,\"\")","v":""},{"$f":"IF(E143<>\"\",Drainage!G61,\"\")","v":""},"",{"$f":"IF(AND(F143=H143,G143=\"\"),\"\",VLOOKUP(Tool!P79,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=17,E126<=30),17,\"\")","v":""},{"$f":"IF(D24>=$C$2,\"\",IF($C$2<(Tool!E79-Tool!$D$64),\"\",IF(Tool!D80<>\"\",IF(Tool!$D$64<>0,Tool!E79-Tool!$D$64,Tool!E79),\"\")))","v":""},{"$f":"IF(C25=\"\",\"\",IF(B26=\"\",$C$2,IF((D24-$C$9)>=$C$2,\"\",IF(Tool!E79<>\"\",IF(AND($C$2>=(Tool!E80-Tool!$D$64),(Tool!E81-Tool!$D$64)>=(Tool!E80-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E80-Tool!$D$64,Tool!E80),$C$2),\"\"))))","v":""},{"$f":"IF(C144=\"\",\"\",IF(B144<>\"\",IF(Tool!N80=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E144=\"HM\",IF(Tool!I80>Tool!G80,0,IF(Tool!G80>0,Tool!G80+J144,\"\")),\"\")","v":""},{"$f":"IF(E144=\"HM\",IF(Tool!H80>0,Tool!H80,\"\"),\"\")","v":""},{"$f":"IF(E144=\"HM\",IF(Tool!I80>Tool!G80,Tool!G80,IF(Tool!I80>=0,Tool!I80)),\"\")","v":""},{"$f":"IF(E144=\"HM\",Tool!O80,\"\")","v":""},{"$f":"IF(AND(K144=\"Urban/C&G\",E144=\"HM\",Tool!L80=\"Both Sides\",Tool!M80=\"Both Sides\"),Tool!$M$62*2,IF(AND(K144=\"Urban/C&G\",E144=\"HM\",Tool!L80=\"Both Sides\",Tool!M80=\"One Side\"),Tool!$M$62,IF(AND(K144=\"Urban/C&G\",E144=\"HM\",Tool!L80=\"One Side\",Tool!M80=\"Both Sides\"),Tool!$M$62,IF(AND(K144=\"Urban/C&G\",E144=\"HM\",Tool!L80=\"One Side\",Tool!M80=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E144=\"HM\",Tool!K80,\"\")","v":""},{"$f":"IF(E144<>\"\",Drainage!G62,\"\")","v":""},"",{"$f":"IF(AND(F144=H144,G144=\"\"),\"\",VLOOKUP(Tool!P80,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=18,E126<=30),18,\"\")","v":""},{"$f":"IF(D25>=$C$2,\"\",IF($C$2<(Tool!E80-Tool!$D$64),\"\",IF(Tool!D81<>\"\",IF(Tool!$D$64<>0,Tool!E80-Tool!$D$64,Tool!E80),\"\")))","v":""},{"$f":"IF(C26=\"\",\"\",IF(B27=\"\",$C$2,IF((D25-$C$9)>=$C$2,\"\",IF(Tool!E80<>\"\",IF(AND($C$2>=(Tool!E81-Tool!$D$64),(Tool!E82-Tool!$D$64)>=(Tool!E81-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E81-Tool!$D$64,Tool!E81),$C$2),\"\"))))","v":""},{"$f":"IF(C145=\"\",\"\",IF(B145<>\"\",IF(Tool!N81=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E145=\"HM\",IF(Tool!I81>Tool!G81,0,IF(Tool!G81>0,Tool!G81+J145,\"\")),\"\")","v":""},{"$f":"IF(E145=\"HM\",IF(Tool!H81>0,Tool!H81,\"\"),\"\")","v":""},{"$f":"IF(E145=\"HM\",IF(Tool!I81>Tool!G81,Tool!G81,IF(Tool!I81>=0,Tool!I81)),\"\")","v":""},{"$f":"IF(E145=\"HM\",Tool!O81,\"\")","v":""},{"$f":"IF(AND(K145=\"Urban/C&G\",E145=\"HM\",Tool!L81=\"Both Sides\",Tool!M81=\"Both Sides\"),Tool!$M$62*2,IF(AND(K145=\"Urban/C&G\",E145=\"HM\",Tool!L81=\"Both Sides\",Tool!M81=\"One Side\"),Tool!$M$62,IF(AND(K145=\"Urban/C&G\",E145=\"HM\",Tool!L81=\"One Side\",Tool!M81=\"Both Sides\"),Tool!$M$62,IF(AND(K145=\"Urban/C&G\",E145=\"HM\",Tool!L81=\"One Side\",Tool!M81=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E145=\"HM\",Tool!K81,\"\")","v":""},{"$f":"IF(E145<>\"\",Drainage!G63,\"\")","v":""},"",{"$f":"IF(AND(F145=H145,G145=\"\"),\"\",VLOOKUP(Tool!P81,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=19,E126<=30),19,\"\")","v":""},{"$f":"IF(D26>=$C$2,\"\",IF($C$2<(Tool!E81-Tool!$D$64),\"\",IF(Tool!D82<>\"\",IF(Tool!$D$64<>0,Tool!E81-Tool!$D$64,Tool!E81),\"\")))","v":""},{"$f":"IF(C27=\"\",\"\",IF(B28=\"\",$C$2,IF((D26-$C$9)>=$C$2,\"\",IF(Tool!E81<>\"\",IF(AND($C$2>=(Tool!E82-Tool!$D$64),(Tool!E83-Tool!$D$64)>=(Tool!E82-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E82-Tool!$D$64,Tool!E82),$C$2),\"\"))))","v":""},{"$f":"IF(C146=\"\",\"\",IF(B146<>\"\",IF(Tool!N82=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E146=\"HM\",IF(Tool!I82>Tool!G82,0,IF(Tool!G82>0,Tool!G82+J146,\"\")),\"\")","v":""},{"$f":"IF(E146=\"HM\",IF(Tool!H82>0,Tool!H82,\"\"),\"\")","v":""},{"$f":"IF(E146=\"HM\",IF(Tool!I82>Tool!G82,Tool!G82,IF(Tool!I82>=0,Tool!I82)),\"\")","v":""},{"$f":"IF(E146=\"HM\",Tool!O82,\"\")","v":""},{"$f":"IF(AND(K146=\"Urban/C&G\",E146=\"HM\",Tool!L82=\"Both Sides\",Tool!M82=\"Both Sides\"),Tool!$M$62*2,IF(AND(K146=\"Urban/C&G\",E146=\"HM\",Tool!L82=\"Both Sides\",Tool!M82=\"One Side\"),Tool!$M$62,IF(AND(K146=\"Urban/C&G\",E146=\"HM\",Tool!L82=\"One Side\",Tool!M82=\"Both Sides\"),Tool!$M$62,IF(AND(K146=\"Urban/C&G\",E146=\"HM\",Tool!L82=\"One Side\",Tool!M82=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E146=\"HM\",Tool!K82,\"\")","v":""},{"$f":"IF(E146<>\"\",Drainage!G64,\"\")","v":""},"",{"$f":"IF(AND(F146=H146,G146=\"\"),\"\",VLOOKUP(Tool!P82,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=20,E126<=30),20,\"\")","v":""},{"$f":"IF(D27>=$C$2,\"\",IF($C$2<(Tool!E82-Tool!$D$64),\"\",IF(Tool!D83<>\"\",IF(Tool!$D$64<>0,Tool!E82-Tool!$D$64,Tool!E82),\"\")))","v":""},{"$f":"IF(C28=\"\",\"\",IF(B29=\"\",$C$2,IF((D27-$C$9)>=$C$2,\"\",IF(Tool!E82<>\"\",IF(AND($C$2>=(Tool!E83-Tool!$D$64),(Tool!E84-Tool!$D$64)>=(Tool!E83-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E83-Tool!$D$64,Tool!E83),$C$2),\"\"))))","v":""},{"$f":"IF(C147=\"\",\"\",IF(B147<>\"\",IF(Tool!N83=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E147=\"HM\",IF(Tool!I83>Tool!G83,0,IF(Tool!G83>0,Tool!G83+J147,\"\")),\"\")","v":""},{"$f":"IF(E147=\"HM\",IF(Tool!H83>0,Tool!H83,\"\"),\"\")","v":""},{"$f":"IF(E147=\"HM\",IF(Tool!I83>Tool!G83,Tool!G83,IF(Tool!I83>=0,Tool!I83)),\"\")","v":""},{"$f":"IF(E147=\"HM\",Tool!O83,\"\")","v":""},{"$f":"IF(AND(K147=\"Urban/C&G\",E147=\"HM\",Tool!L83=\"Both Sides\",Tool!M83=\"Both Sides\"),Tool!$M$62*2,IF(AND(K147=\"Urban/C&G\",E147=\"HM\",Tool!L83=\"Both Sides\",Tool!M83=\"One Side\"),Tool!$M$62,IF(AND(K147=\"Urban/C&G\",E147=\"HM\",Tool!L83=\"One Side\",Tool!M83=\"Both Sides\"),Tool!$M$62,IF(AND(K147=\"Urban/C&G\",E147=\"HM\",Tool!L83=\"One Side\",Tool!M83=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E147=\"HM\",Tool!K83,\"\")","v":""},{"$f":"IF(E147<>\"\",Drainage!G65,\"\")","v":""},"",{"$f":"IF(AND(F147=H147,G147=\"\"),\"\",VLOOKUP(Tool!P83,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=21,E126<=30),21,\"\")","v":""},{"$f":"IF(D28>=$C$2,\"\",IF($C$2<(Tool!E83-Tool!$D$64),\"\",IF(Tool!D84<>\"\",IF(Tool!$D$64<>0,Tool!E83-Tool!$D$64,Tool!E83),\"\")))","v":""},{"$f":"IF(C29=\"\",\"\",IF(B30=\"\",$C$2,IF((D28-$C$9)>=$C$2,\"\",IF(Tool!E83<>\"\",IF(AND($C$2>=(Tool!E84-Tool!$D$64),(Tool!E85-Tool!$D$64)>=(Tool!E84-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E84-Tool!$D$64,Tool!E84),$C$2),\"\"))))","v":""},{"$f":"IF(C148=\"\",\"\",IF(B148<>\"\",IF(Tool!N84=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E148=\"HM\",IF(Tool!I84>Tool!G84,0,IF(Tool!G84>0,Tool!G84+J148,\"\")),\"\")","v":""},{"$f":"IF(E148=\"HM\",IF(Tool!H84>0,Tool!H84,\"\"),\"\")","v":""},{"$f":"IF(E148=\"HM\",IF(Tool!I84>Tool!G84,Tool!G84,IF(Tool!I84>=0,Tool!I84)),\"\")","v":""},{"$f":"IF(E148=\"HM\",Tool!O84,\"\")","v":""},{"$f":"IF(AND(K148=\"Urban/C&G\",E148=\"HM\",Tool!L84=\"Both Sides\",Tool!M84=\"Both Sides\"),Tool!$M$62*2,IF(AND(K148=\"Urban/C&G\",E148=\"HM\",Tool!L84=\"Both Sides\",Tool!M84=\"One Side\"),Tool!$M$62,IF(AND(K148=\"Urban/C&G\",E148=\"HM\",Tool!L84=\"One Side\",Tool!M84=\"Both Sides\"),Tool!$M$62,IF(AND(K148=\"Urban/C&G\",E148=\"HM\",Tool!L84=\"One Side\",Tool!M84=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E148=\"HM\",Tool!K84,\"\")","v":""},{"$f":"IF(E148<>\"\",Drainage!G66,\"\")","v":""},"",{"$f":"IF(AND(F148=H148,G148=\"\"),\"\",VLOOKUP(Tool!P84,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=22,E126<=30),22,\"\")","v":""},{"$f":"IF(D29>=$C$2,\"\",IF($C$2<(Tool!E84-Tool!$D$64),\"\",IF(Tool!D85<>\"\",IF(Tool!$D$64<>0,Tool!E84-Tool!$D$64,Tool!E84),\"\")))","v":""},{"$f":"IF(C30=\"\",\"\",IF(B31=\"\",$C$2,IF((D29-$C$9)>=$C$2,\"\",IF(Tool!E84<>\"\",IF(AND($C$2>=(Tool!E85-Tool!$D$64),(Tool!E86-Tool!$D$64)>=(Tool!E85-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E85-Tool!$D$64,Tool!E85),$C$2),\"\"))))","v":""},{"$f":"IF(C149=\"\",\"\",IF(B149<>\"\",IF(Tool!N85=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E149=\"HM\",IF(Tool!I85>Tool!G85,0,IF(Tool!G85>0,Tool!G85+J149,\"\")),\"\")","v":""},{"$f":"IF(E149=\"HM\",IF(Tool!H85>0,Tool!H85,\"\"),\"\")","v":""},{"$f":"IF(E149=\"HM\",IF(Tool!I85>Tool!G85,Tool!G85,IF(Tool!I85>=0,Tool!I85)),\"\")","v":""},{"$f":"IF(E149=\"HM\",Tool!O85,\"\")","v":""},{"$f":"IF(AND(K149=\"Urban/C&G\",E149=\"HM\",Tool!L85=\"Both Sides\",Tool!M85=\"Both Sides\"),Tool!$M$62*2,IF(AND(K149=\"Urban/C&G\",E149=\"HM\",Tool!L85=\"Both Sides\",Tool!M85=\"One Side\"),Tool!$M$62,IF(AND(K149=\"Urban/C&G\",E149=\"HM\",Tool!L85=\"One Side\",Tool!M85=\"Both Sides\"),Tool!$M$62,IF(AND(K149=\"Urban/C&G\",E149=\"HM\",Tool!L85=\"One Side\",Tool!M85=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E149=\"HM\",Tool!K85,\"\")","v":""},{"$f":"IF(E149<>\"\",Drainage!G67,\"\")","v":""},"",{"$f":"IF(AND(F149=H149,G149=\"\"),\"\",VLOOKUP(Tool!P85,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=23,E126<=30),23,\"\")","v":""},{"$f":"IF(D30>=$C$2,\"\",IF($C$2<(Tool!E85-Tool!$D$64),\"\",IF(Tool!D86<>\"\",IF(Tool!$D$64<>0,Tool!E85-Tool!$D$64,Tool!E85),\"\")))","v":""},{"$f":"IF(C31=\"\",\"\",IF(B32=\"\",$C$2,IF((D30-$C$9)>=$C$2,\"\",IF(Tool!E85<>\"\",IF(AND($C$2>=(Tool!E86-Tool!$D$64),(Tool!E87-Tool!$D$64)>=(Tool!E86-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E86-Tool!$D$64,Tool!E86),$C$2),\"\"))))","v":""},{"$f":"IF(C150=\"\",\"\",IF(B150<>\"\",IF(Tool!N86=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E150=\"HM\",IF(Tool!I86>Tool!G86,0,IF(Tool!G86>0,Tool!G86+J150,\"\")),\"\")","v":""},{"$f":"IF(E150=\"HM\",IF(Tool!H86>0,Tool!H86,\"\"),\"\")","v":""},{"$f":"IF(E150=\"HM\",IF(Tool!I86>Tool!G86,Tool!G86,IF(Tool!I86>=0,Tool!I86)),\"\")","v":""},{"$f":"IF(E150=\"HM\",Tool!O86,\"\")","v":""},{"$f":"IF(AND(K150=\"Urban/C&G\",E150=\"HM\",Tool!L86=\"Both Sides\",Tool!M86=\"Both Sides\"),Tool!$M$62*2,IF(AND(K150=\"Urban/C&G\",E150=\"HM\",Tool!L86=\"Both Sides\",Tool!M86=\"One Side\"),Tool!$M$62,IF(AND(K150=\"Urban/C&G\",E150=\"HM\",Tool!L86=\"One Side\",Tool!M86=\"Both Sides\"),Tool!$M$62,IF(AND(K150=\"Urban/C&G\",E150=\"HM\",Tool!L86=\"One Side\",Tool!M86=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E150=\"HM\",Tool!K86,\"\")","v":""},{"$f":"IF(E150<>\"\",Drainage!G68,\"\")","v":""},"",{"$f":"IF(AND(F150=H150,G150=\"\"),\"\",VLOOKUP(Tool!P86,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=24,E126<=30),24,\"\")","v":""},{"$f":"IF(D31>=$C$2,\"\",IF($C$2<(Tool!E86-Tool!$D$64),\"\",IF(Tool!D87<>\"\",IF(Tool!$D$64<>0,Tool!E86-Tool!$D$64,Tool!E86),\"\")))","v":""},{"$f":"IF(C32=\"\",\"\",IF(B33=\"\",$C$2,IF((D31-$C$9)>=$C$2,\"\",IF(Tool!E86<>\"\",IF(AND($C$2>=(Tool!E87-Tool!$D$64),(Tool!E88-Tool!$D$64)>=(Tool!E87-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E87-Tool!$D$64,Tool!E87),$C$2),\"\"))))","v":""},{"$f":"IF(C151=\"\",\"\",IF(B151<>\"\",IF(Tool!N87=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E151=\"HM\",IF(Tool!I87>Tool!G87,0,IF(Tool!G87>0,Tool!G87+J151,\"\")),\"\")","v":""},{"$f":"IF(E151=\"HM\",IF(Tool!H87>0,Tool!H87,\"\"),\"\")","v":""},{"$f":"IF(E151=\"HM\",IF(Tool!I87>Tool!G87,Tool!G87,IF(Tool!I87>=0,Tool!I87)),\"\")","v":""},{"$f":"IF(E151=\"HM\",Tool!O87,\"\")","v":""},{"$f":"IF(AND(K151=\"Urban/C&G\",E151=\"HM\",Tool!L87=\"Both Sides\",Tool!M87=\"Both Sides\"),Tool!$M$62*2,IF(AND(K151=\"Urban/C&G\",E151=\"HM\",Tool!L87=\"Both Sides\",Tool!M87=\"One Side\"),Tool!$M$62,IF(AND(K151=\"Urban/C&G\",E151=\"HM\",Tool!L87=\"One Side\",Tool!M87=\"Both Sides\"),Tool!$M$62,IF(AND(K151=\"Urban/C&G\",E151=\"HM\",Tool!L87=\"One Side\",Tool!M87=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E151=\"HM\",Tool!K87,\"\")","v":""},{"$f":"IF(E151<>\"\",Drainage!G69,\"\")","v":""},"",{"$f":"IF(AND(F151=H151,G151=\"\"),\"\",VLOOKUP(Tool!P87,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=25,E126<=30),25,\"\")","v":""},{"$f":"IF(D32>=$C$2,\"\",IF($C$2<(Tool!E87-Tool!$D$64),\"\",IF(Tool!D88<>\"\",IF(Tool!$D$64<>0,Tool!E87-Tool!$D$64,Tool!E87),\"\")))","v":""},{"$f":"IF(C33=\"\",\"\",IF(B34=\"\",$C$2,IF((D32-$C$9)>=$C$2,\"\",IF(Tool!E87<>\"\",IF(AND($C$2>=(Tool!E88-Tool!$D$64),(Tool!E89-Tool!$D$64)>=(Tool!E88-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E88-Tool!$D$64,Tool!E88),$C$2),\"\"))))","v":""},{"$f":"IF(C152=\"\",\"\",IF(B152<>\"\",IF(Tool!N88=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E152=\"HM\",IF(Tool!I88>Tool!G88,0,IF(Tool!G88>0,Tool!G88+J152,\"\")),\"\")","v":""},{"$f":"IF(E152=\"HM\",IF(Tool!H88>0,Tool!H88,\"\"),\"\")","v":""},{"$f":"IF(E152=\"HM\",IF(Tool!I88>Tool!G88,Tool!G88,IF(Tool!I88>=0,Tool!I88)),\"\")","v":""},{"$f":"IF(E152=\"HM\",Tool!O88,\"\")","v":""},{"$f":"IF(AND(K152=\"Urban/C&G\",E152=\"HM\",Tool!L88=\"Both Sides\",Tool!M88=\"Both Sides\"),Tool!$M$62*2,IF(AND(K152=\"Urban/C&G\",E152=\"HM\",Tool!L88=\"Both Sides\",Tool!M88=\"One Side\"),Tool!$M$62,IF(AND(K152=\"Urban/C&G\",E152=\"HM\",Tool!L88=\"One Side\",Tool!M88=\"Both Sides\"),Tool!$M$62,IF(AND(K152=\"Urban/C&G\",E152=\"HM\",Tool!L88=\"One Side\",Tool!M88=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E152=\"HM\",Tool!K88,\"\")","v":""},{"$f":"IF(E152<>\"\",Drainage!G70,\"\")","v":""},"",{"$f":"IF(AND(F152=H152,G152=\"\"),\"\",VLOOKUP(Tool!P88,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=26,E126<=30),26,\"\")","v":""},{"$f":"IF(D33>=$C$2,\"\",IF($C$2<(Tool!E88-Tool!$D$64),\"\",IF(Tool!D89<>\"\",IF(Tool!$D$64<>0,Tool!E88-Tool!$D$64,Tool!E88),\"\")))","v":""},{"$f":"IF(C34=\"\",\"\",IF(B35=\"\",$C$2,IF((D33-$C$9)>=$C$2,\"\",IF(Tool!E88<>\"\",IF(AND($C$2>=(Tool!E89-Tool!$D$64),(Tool!E90-Tool!$D$64)>=(Tool!E89-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E89-Tool!$D$64,Tool!E89),$C$2),\"\"))))","v":""},{"$f":"IF(C153=\"\",\"\",IF(B153<>\"\",IF(Tool!N89=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E153=\"HM\",IF(Tool!I89>Tool!G89,0,IF(Tool!G89>0,Tool!G89+J153,\"\")),\"\")","v":""},{"$f":"IF(E153=\"HM\",IF(Tool!H89>0,Tool!H89,\"\"),\"\")","v":""},{"$f":"IF(E153=\"HM\",IF(Tool!I89>Tool!G89,Tool!G89,IF(Tool!I89>=0,Tool!I89)),\"\")","v":""},{"$f":"IF(E153=\"HM\",Tool!O89,\"\")","v":""},{"$f":"IF(AND(K153=\"Urban/C&G\",E153=\"HM\",Tool!L89=\"Both Sides\",Tool!M89=\"Both Sides\"),Tool!$M$62*2,IF(AND(K153=\"Urban/C&G\",E153=\"HM\",Tool!L89=\"Both Sides\",Tool!M89=\"One Side\"),Tool!$M$62,IF(AND(K153=\"Urban/C&G\",E153=\"HM\",Tool!L89=\"One Side\",Tool!M89=\"Both Sides\"),Tool!$M$62,IF(AND(K153=\"Urban/C&G\",E153=\"HM\",Tool!L89=\"One Side\",Tool!M89=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E153=\"HM\",Tool!K89,\"\")","v":""},{"$f":"IF(E153<>\"\",Drainage!G71,\"\")","v":""},"",{"$f":"IF(AND(F153=H153,G153=\"\"),\"\",VLOOKUP(Tool!P89,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=27,E126<=30),27,\"\")","v":""},{"$f":"IF(D34>=$C$2,\"\",IF($C$2<(Tool!E89-Tool!$D$64),\"\",IF(Tool!D90<>\"\",IF(Tool!$D$64<>0,Tool!E89-Tool!$D$64,Tool!E89),\"\")))","v":""},{"$f":"IF(C35=\"\",\"\",IF(B36=\"\",$C$2,IF((D34-$C$9)>=$C$2,\"\",IF(Tool!E89<>\"\",IF(AND($C$2>=(Tool!E90-Tool!$D$64),(Tool!E91-Tool!$D$64)>=(Tool!E90-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E90-Tool!$D$64,Tool!E90),$C$2),\"\"))))","v":""},{"$f":"IF(C154=\"\",\"\",IF(B154<>\"\",IF(Tool!N90=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E154=\"HM\",IF(Tool!I90>Tool!G90,0,IF(Tool!G90>0,Tool!G90+J154,\"\")),\"\")","v":""},{"$f":"IF(E154=\"HM\",IF(Tool!H90>0,Tool!H90,\"\"),\"\")","v":""},{"$f":"IF(E154=\"HM\",IF(Tool!I90>Tool!G90,Tool!G90,IF(Tool!I90>=0,Tool!I90)),\"\")","v":""},{"$f":"IF(E154=\"HM\",Tool!O90,\"\")","v":""},{"$f":"IF(AND(K154=\"Urban/C&G\",E154=\"HM\",Tool!L90=\"Both Sides\",Tool!M90=\"Both Sides\"),Tool!$M$62*2,IF(AND(K154=\"Urban/C&G\",E154=\"HM\",Tool!L90=\"Both Sides\",Tool!M90=\"One Side\"),Tool!$M$62,IF(AND(K154=\"Urban/C&G\",E154=\"HM\",Tool!L90=\"One Side\",Tool!M90=\"Both Sides\"),Tool!$M$62,IF(AND(K154=\"Urban/C&G\",E154=\"HM\",Tool!L90=\"One Side\",Tool!M90=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E154=\"HM\",Tool!K90,\"\")","v":""},{"$f":"IF(E154<>\"\",Drainage!G72,\"\")","v":""},"",{"$f":"IF(AND(F154=H154,G154=\"\"),\"\",VLOOKUP(Tool!P90,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=28,E126<=30),28,\"\")","v":""},{"$f":"IF(D35>=$C$2,\"\",IF($C$2<(Tool!E90-Tool!$D$64),\"\",IF(Tool!D91<>\"\",IF(Tool!$D$64<>0,Tool!E90-Tool!$D$64,Tool!E90),\"\")))","v":""},{"$f":"IF(C36=\"\",\"\",IF(B37=\"\",$C$2,IF((D35-$C$9)>=$C$2,\"\",IF(Tool!E90<>\"\",IF(AND($C$2>=(Tool!E91-Tool!$D$64),(Tool!E92-Tool!$D$64)>=(Tool!E91-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E91-Tool!$D$64,Tool!E91),$C$2),\"\"))))","v":""},{"$f":"IF(C155=\"\",\"\",IF(B155<>\"\",IF(Tool!N91=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E155=\"HM\",IF(Tool!I91>Tool!G91,0,IF(Tool!G91>0,Tool!G91+J155,\"\")),\"\")","v":""},{"$f":"IF(E155=\"HM\",IF(Tool!H91>0,Tool!H91,\"\"),\"\")","v":""},{"$f":"IF(E155=\"HM\",IF(Tool!I91>Tool!G91,Tool!G91,IF(Tool!I91>=0,Tool!I91)),\"\")","v":""},{"$f":"IF(E155=\"HM\",Tool!O91,\"\")","v":""},{"$f":"IF(AND(K155=\"Urban/C&G\",E155=\"HM\",Tool!L91=\"Both Sides\",Tool!M91=\"Both Sides\"),Tool!$M$62*2,IF(AND(K155=\"Urban/C&G\",E155=\"HM\",Tool!L91=\"Both Sides\",Tool!M91=\"One Side\"),Tool!$M$62,IF(AND(K155=\"Urban/C&G\",E155=\"HM\",Tool!L91=\"One Side\",Tool!M91=\"Both Sides\"),Tool!$M$62,IF(AND(K155=\"Urban/C&G\",E155=\"HM\",Tool!L91=\"One Side\",Tool!M91=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E155=\"HM\",Tool!K91,\"\")","v":""},{"$f":"IF(E155<>\"\",Drainage!G73,\"\")","v":""},"",{"$f":"IF(AND(F155=H155,G155=\"\"),\"\",VLOOKUP(Tool!P91,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(AND(E126>=29,E126<=30),29,\"\")","v":""},{"$f":"IF(D36>=$C$2,\"\",IF($C$2<(Tool!E91-Tool!$D$64),\"\",IF(Tool!D92<>\"\",IF(Tool!$D$64<>0,Tool!E91-Tool!$D$64,Tool!E91),\"\")))","v":""},{"$f":"IF(C37=\"\",\"\",IF(B38=\"\",$C$2,IF((D36-$C$9)>=$C$2,\"\",IF(Tool!E91<>\"\",IF(AND($C$2>=(Tool!E92-Tool!$D$64),(Tool!E93-Tool!$D$64)>=(Tool!E92-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E92-Tool!$D$64,Tool!E92),$C$2),\"\"))))","v":""},{"$f":"IF(C156=\"\",\"\",IF(B156<>\"\",IF(Tool!N92=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E156=\"HM\",IF(Tool!I92>Tool!G92,0,IF(Tool!G92>0,Tool!G92+J156,\"\")),\"\")","v":""},{"$f":"IF(E156=\"HM\",IF(Tool!H92>0,Tool!H92,\"\"),\"\")","v":""},{"$f":"IF(E156=\"HM\",IF(Tool!I92>Tool!G92,Tool!G92,IF(Tool!I92>=0,Tool!I92)),\"\")","v":""},{"$f":"IF(E156=\"HM\",Tool!O92,\"\")","v":""},{"$f":"IF(AND(K156=\"Urban/C&G\",E156=\"HM\",Tool!L92=\"Both Sides\",Tool!M92=\"Both Sides\"),Tool!$M$62*2,IF(AND(K156=\"Urban/C&G\",E156=\"HM\",Tool!L92=\"Both Sides\",Tool!M92=\"One Side\"),Tool!$M$62,IF(AND(K156=\"Urban/C&G\",E156=\"HM\",Tool!L92=\"One Side\",Tool!M92=\"Both Sides\"),Tool!$M$62,IF(AND(K156=\"Urban/C&G\",E156=\"HM\",Tool!L92=\"One Side\",Tool!M92=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E156=\"HM\",Tool!K92,\"\")","v":""},{"$f":"IF(E156<>\"\",Drainage!G74,\"\")","v":""},"",{"$f":"IF(AND(F156=H156,G156=\"\"),\"\",VLOOKUP(Tool!P92,$AM$4:$AN$9,2,0))","v":""},"","",""]
[null,{"$f":"IF(E126=30,30,\"\")","v":""},{"$f":"IF(D37>=$C$2,\"\",IF($C$2<(Tool!E92-Tool!$D$64),\"\",IF(Tool!D93<>\"\",IF(Tool!$D$64<>0,Tool!E92-Tool!$D$64,Tool!E92),\"\")))","v":""},{"$f":"IF(C38=\"\",\"\",IF(B39=\"\",$C$2,IF((D37-$C$9)>=$C$2,\"\",IF(Tool!E92<>\"\",IF(AND($C$2>=(Tool!E93-Tool!$D$64),(Tool!E94-Tool!$D$64)>=(Tool!E93-Tool!$D$64)),IF(Tool!$D$64<>\"\",Tool!E93-Tool!$D$64,Tool!E93),$C$2),\"\"))))","v":""},{"$f":"IF(C157=\"\",\"\",IF(B157<>\"\",IF(Tool!N93=Tool!$E$10,\"HM\",\"\"),\"\"))","v":""},{"$f":"IF(E157=\"HM\",IF(Tool!I93>Tool!G93,0,IF(Tool!G93>0,Tool!G93+J157,\"\")),\"\")","v":""},{"$f":"IF(E157=\"HM\",IF(Tool!H93>0,Tool!H93,\"\"),\"\")","v":""},{"$f":"IF(E157=\"HM\",IF(Tool!I93>Tool!G93,Tool!G93,IF(Tool!I93>=0,Tool!I93)),\"\")","v":""},{"$f":"IF(E157=\"HM\",Tool!O93,\"\")","v":""},{"$f":"IF(AND(K157=\"Urban/C&G\",E157=\"HM\",Tool!L93=\"Both Sides\",Tool!M93=\"Both Sides\"),Tool!$M$62*2,IF(AND(K157=\"Urban/C&G\",E157=\"HM\",Tool!L93=\"Both Sides\",Tool!M93=\"One Side\"),Tool!$M$62,IF(AND(K157=\"Urban/C&G\",E157=\"HM\",Tool!L93=\"One Side\",Tool!M93=\"Both Sides\"),Tool!$M$62,IF(AND(K157=\"Urban/C&G\",E157=\"HM\",Tool!L93=\"One Side\",Tool!M93=\"One Side\"),Tool!$M$62,0))))","v":0},{"$f":"IF(E157=\"HM\",Tool!K93,\"\")","v":""},{"$f":"IF(E157<>\"\",Drainage!G75,\"\")","v":""},"",{"$f":"IF(AND(F157=H157,G157=\"\"),\"\",VLOOKUP(Tool!P93,$AM$4:$AN$9,2,0))","v":""},"","",""]
[]
[null,"Rural - Length - One Side",{"$f":"SUMIFS(Q128:Q157,K128:K157,\"Rural/Ditch\",I128:I157,\"One Side\")","v":0},null,"Sidewalk Length - HM:",{"$f":"SUMPRODUCT(L128:L157,Q128:Q157)","v":0},null,"Avg. Rd. Width:",{"$f":"IF(SUM(Q128:Q157),SUMPRODUCT(F128:F157,Q128:Q157)/SUM(Q128:Q157),0)","v":0},null,null,"Rural - Slope Rate - One Side:",{"$f":"IFERROR(SUMIFS(O128:O157,I128:I157,\"One Side\",K128:K157,\"Rural/Ditch\")/SUMIFS(M128:M157,I128:I157,\"One Side\",K128:K157,\"Rural/Ditch\"),0)","v":0},null,"Guardrail Length",{"$f":"SUM(P128:P157)","v":0}]
[null,"Rural - Length - Both Sides",{"$f":"SUMIFS(Q128:Q157,K128:K157,\"Rural/Ditch\",I128:I157,\"Both Sides\")","v":0},null,"Rural Slope Length - One Sides:",{"$f":"SUMIFS(M128:M157,I128:I157,\"One Side\",K128:K157,\"Rural/Ditch\")","v":0},null,"Avg. Retained Width:",{"$f":"IF(SUM(Q128:Q157)>0,SUMPRODUCT(H128:H157,Q128:Q157)/SUM(Q128:Q157),0)","v":0},null,null,"Rural - Slope Rate - Both Sides:",{"$f":"IFERROR(SUMIFS(O128:O157,I128:I157,\"Both Sides\",K128:K157,\"Rural/Ditch\")/SUMIFS(M128:M157,I128:I157,\"Both Sides\",K128:K157,\"Rural/Ditch\"),0)","v":0}]
[null,"Urban - Length - One Side",{"$f":"SUMIFS(Q128:Q157,K128:K157,\"Urban/C&G\",I128:I157,\"One Side\")","v":0},null,"Rural Slope Length - Both Sides:",{"$f":"SUMIFS(M128:M157,I128:I157,\"Both Sides\",K128:K157,\"Rural/Ditch\")*2","v":0},null,"Avg. Shoulder Width:",{"$f":"IF(SUM(Q128:Q157),SUMPRODUCT(G128:G157,Q128:Q157)/SUM(Q128:Q157),0)","v":0},null,null,"Urban - Slope Rate - One Side:",{"$f":"IFERROR(SUMIFS(O128:O157,I128:I157,\"One Side\",K128:K157,\"Urban/C&G\")/SUMIFS(M128:M157,I128:I157,\"One Side\",K128:K157,\"Urban/C&G\"),0)","v":0}]
[null,"Urban - Length - Both Sides",{"$f":"SUMIFS(Q128:Q157,K128:K157,\"Urban/C&G\",I128:I157,\"Both Sides\")","v":0},null,"Urban Slope Length - One Sides:",{"$f":"SUMIFS(M128:M157,I128:I157,\"One Side\",K128:K157,\"Urban/C&G\")","v":0},null,"Avg. Fill Width:",{"$f":"IF(I159>=I160,(I159+I161*2)-I160,0)","v":0},null,null,"Urban - Slope Rate - Both Sides:",{"$f":"IFERROR(SUMIFS(O128:O157,I128:I157,\"Both Sides\",K128:K157,\"Urban/C&G\")/SUMIFS(M128:M157,I128:I157,\"Both Sides\",K128:K157,\"Urban/C&G\"),0)","v":0}]
[null,null,null,null,"Urban Slope Length - Both Sides:",{"$f":"SUMIFS(M128:M157,I128:I157,\"Both Sides\",K128:K157,\"Urban/C&G\")*2","v":0},null,"Avg. Fill Area:",{"$f":"I162*SUM(Q128:Q157)*5280","v":0}]
[null,null,null,null,null,null,null,"Length:",{"$f":"SUM(Q128:Q157)","v":0}]

{"sheet":"Bridges","index":34,"n_rows":98,"n_cols":47,"rows_kept":98,"cut":false,"hidden":true,"merged":[[18,2,18,3],[19,2,19,3],[14,2,14,3],[20,2,20,3],[21,2,21,3],[17,2,17,3],[5,1,5,4],[6,1,6,4],[7,2,7,3],[8,2,8,3],[9,2,9,3],[10,2,10,3],[12,2,12,3],[13,2,13,3],[15,2,15,3],[16,2,16,3],[11,2,11,3],[1,6,1,25],[29,6,29,25],[4,6,4,7],[3,6,3,9],[3,15,3,18],[4,15,4,16],[95,43,101,48],[3,27,3,30],[4,27,4,28],[59,6,59,25],[62,6,62,7],[31,6,31,9],[61,36,61,39],[61,26,61,29],[61,16,61,19],[61,6,61,9],[32,6,32,7],[32,36,32,37]]}
[]
[null,null,null,null,null,null,"Bridge Removals"]
[]
[null,null,null,null,null,null,"Type = Box Bridges",null,null,null,null,null,null,null,null,"Type = Concrete",null,null,null,null,null,null,null,null,null,null,null,"Type = Steel"]
[null,null,null,null,null,null,"Segments:",null,{"$f":"Tool!F131","v":1},null,null,null,null,null,null,"Segments:",null,{"$f":"Tool!F131","v":1},null,null,null,null,null,null,null,null,null,"Segments:",null,{"$f":"Tool!F131","v":1}]
[null,"Bridge & Structure Summary",null,null,null,null,"Segments","Length","Width","Type","Area (sqft)",null,null,null,null,"Segments","Length","Width","Type","Area (sqft)",null,null,null,null,null,null,null,"Segments","Length","Width","Type","Area (sqft)"]
[null,"Summary Table",null,null,null,null,{"$f":"IF(AND(I5>=1,I5<=20),1,\"\")","v":1},{"$f":"IF(J7=1,Tool!D133,\"\")","v":""},{"$f":"IF(J7=1,Tool!E133,\"\")","v":""},{"$f":"IF(Tool!D133=\"\",\"\",IF(G7<>\"\",IF(Tool!F133=Tool!$H$7,1,\"\"),\"\"))","v":""},{"$f":"IF(J7=1,H7*I7,\"\")","v":""},null,null,null,null,{"$f":"IF(AND(R5>=1,R5<=20),1,\"\")","v":1},{"$f":"IF(S7=1,Tool!D133,\"\")","v":""},{"$f":"IF(S7=1,Tool!E133,\"\")","v":""},{"$f":"IF(Tool!D133=\"\",\"\",IF(P7<>\"\",IF(OR(Tool!F133=Tool!$H$9,Tool!F133=Tool!$H$8),1,\"\"),\"\"))","v":""},{"$f":"IF(S7=1,Q7*R7,\"\")","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=1,AD5<=20),1,\"\")","v":1},{"$f":"IF(AE7=1,Tool!D133,\"\")","v":""},{"$f":"IF(AE7=1,Tool!E133,\"\")","v":""},{"$f":"IF(Tool!D133=\"\",\"\",IF(AB7<>\"\",IF(Tool!F133=Tool!$H$10,1,\"\"),\"\"))","v":""},{"$f":"IF(AE7=1,AC7*AD7,\"\")","v":""}]
[null,"Number","Description",null,"Area (SF)",null,{"$f":"IF(AND(I5>=2,I5<=20),2,\"\")","v":""},{"$f":"IF(J8=1,Tool!D134,\"\")","v":""},{"$f":"IF(J8=1,Tool!E134,\"\")","v":""},{"$f":"IF(Tool!D134=\"\",\"\",IF(G8<>\"\",IF(Tool!F134=Tool!$H$7,1,\"\"),\"\"))","v":""},{"$f":"IF(J8=1,H8*I8,\"\")","v":""},null,null,null,null,{"$f":"IF(AND(R5>=2,R5<=20),2,\"\")","v":""},{"$f":"IF(S8=1,Tool!D134,\"\")","v":""},{"$f":"IF(S8=1,Tool!E134,\"\")","v":""},{"$f":"IF(Tool!D134=\"\",\"\",IF(P8<>\"\",IF(OR(Tool!F134=Tool!$H$9,Tool!F134=Tool!$H$8),1,\"\"),\"\"))","v":""},{"$f":"IF(S8=1,Q8*R8,\"\")","v":""},null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=2,AD5<=20),2,\"\")","v":""},{"$f":"IF(AE8=1,Tool!D134,\"\")","v":""},{"$f":"IF(AE8=1,Tool!E134,\"\")","v":""},{"$f":"IF(Tool!D134=\"\",\"\",IF(AB8<>\"\",IF(Tool!F134=Tool!$H$10,1,\"\"),\"\"))","v":""},{"$f":"IF(AE8=1,AC8*AD8,\"\")","v":""}]
[null,{"$f":"K27+T27+AF27","v":0},"Bridge Removal:",null,{"$f":"K28+T28+AF28","v":0},null,{"$f":"IF(AND(I5>=3,I5<=20),3,\"\")","v":""},{"$f":"IF(J9=1,Tool!D135,\"\")","v":""},{"$f":"IF(J9=1,Tool!E135,\"\")","v":""},{"$f":"IF(Tool!D135=\"\",\"\",IF(G9<>\"\",IF(Tool!F135=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5>=3,R5<=20),3,\"\")","v":""},{"$f":"IF(S9=1,Tool!D135,\"\")","v":""},{"$f":"IF(S9=1,Tool!E135,\"\")","v":""},{"$f":"IF(Tool!D135=\"\",\"\",IF(P9<>\"\",IF(OR(Tool!F135=Tool!$H$9,Tool!F135=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=3,AD5<=20),3,\"\")","v":""},{"$f":"IF(AE9=1,Tool!D135,\"\")","v":""},{"$f":"IF(AE9=1,Tool!E135,\"\")","v":""},{"$f":"IF(Tool!D135=\"\",\"\",IF(AB9<>\"\",IF(Tool!F135=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,{"$f":"K55","v":0},"Widen Existing Bridge (Box):",null,{"$f":"K56","v":0},null,{"$f":"IF(AND(I5>=4,I5<=20),4,\"\")","v":""},{"$f":"IF(J10=1,Tool!D136,\"\")","v":""},{"$f":"IF(J10=1,Tool!E136,\"\")","v":""},{"$f":"IF(Tool!D136=\"\",\"\",IF(G10<>\"\",IF(Tool!F136=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5>=4,R5<=20),4,\"\")","v":""},{"$f":"IF(S10=1,Tool!D136,\"\")","v":""},{"$f":"IF(S10=1,Tool!E136,\"\")","v":""},{"$f":"IF(Tool!D136=\"\",\"\",IF(P10<>\"\",IF(OR(Tool!F136=Tool!$H$9,Tool!F136=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=4,AD5<=20),4,\"\")","v":""},{"$f":"IF(AE10=1,Tool!D136,\"\")","v":""},{"$f":"IF(AE10=1,Tool!E136,\"\")","v":""},{"$f":"IF(Tool!D136=\"\",\"\",IF(AB10<>\"\",IF(Tool!F136=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,{"$f":"U55","v":0},"Widen Existing Bridge (Concrete I-Beam & Bulb-T):",null,{"$f":"U56","v":0},null,{"$f":"IF(AND(I5>=5,I5<=20),5,\"\")","v":""},{"$f":"IF(J11=1,Tool!D137,\"\")","v":""},{"$f":"IF(J11=1,Tool!E137,\"\")","v":""},{"$f":"IF(Tool!D137=\"\",\"\",IF(G11<>\"\",IF(Tool!F137=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5>=5,R5<=20),5,\"\")","v":""},{"$f":"IF(S11=1,Tool!D137,\"\")","v":""},{"$f":"IF(S11=1,Tool!E137,\"\")","v":""},{"$f":"IF(Tool!D137=\"\",\"\",IF(P11<>\"\",IF(OR(Tool!F137=Tool!$H$9,Tool!F137=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=5,AD5<=20),5,\"\")","v":""},{"$f":"IF(AE11=1,Tool!D137,\"\")","v":""},{"$f":"IF(AE11=1,Tool!E137,\"\")","v":""},{"$f":"IF(Tool!D137=\"\",\"\",IF(AB11<>\"\",IF(Tool!F137=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,null,"Widen Existing Bridge (Concrete Box Beam):",null,{"$f":"AE56","v":0},null,{"$f":"IF(AND(I5>=6,I5<=20),6,\"\")","v":""},{"$f":"IF(J12=1,Tool!D138,\"\")","v":""},{"$f":"IF(J12=1,Tool!E138,\"\")","v":""},{"$f":"IF(Tool!D138=\"\",\"\",IF(G12<>\"\",IF(Tool!F138=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5>=6,R5<=20),6,\"\")","v":""},{"$f":"IF(S12=1,Tool!D138,\"\")","v":""},{"$f":"IF(S12=1,Tool!E138,\"\")","v":""},{"$f":"IF(Tool!D138=\"\",\"\",IF(P12<>\"\",IF(OR(Tool!F138=Tool!$H$9,Tool!F138=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=6,AD5<=20),6,\"\")","v":""},{"$f":"IF(AE12=1,Tool!D138,\"\")","v":""},{"$f":"IF(AE12=1,Tool!E138,\"\")","v":""},{"$f":"IF(Tool!D138=\"\",\"\",IF(AB12<>\"\",IF(Tool!F138=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,{"$f":"AO55","v":0},"Widen Existing Bridge (Steel Girder):",null,{"$f":"AO56","v":0},null,{"$f":"IF(AND(I5>=7,I5<=20),7,\"\")","v":""},{"$f":"IF(J13=1,Tool!D139,\"\")","v":""},{"$f":"IF(J13=1,Tool!E139,\"\")","v":""},{"$f":"IF(Tool!D139=\"\",\"\",IF(G13<>\"\",IF(Tool!F139=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5>=7,R5<=20),7,\"\")","v":""},{"$f":"IF(S13=1,Tool!D139,\"\")","v":""},{"$f":"IF(S13=1,Tool!E139,\"\")","v":""},{"$f":"IF(Tool!D139=\"\",\"\",IF(P13<>\"\",IF(OR(Tool!F139=Tool!$H$9,Tool!F139=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=7,AD5<=20),7,\"\")","v":""},{"$f":"IF(AE13=1,Tool!D139,\"\")","v":""},{"$f":"IF(AE13=1,Tool!E139,\"\")","v":""},{"$f":"IF(Tool!D139=\"\",\"\",IF(AB13<>\"\",IF(Tool!F139=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,{"$f":"K85","v":0},"New Bridge (Box):",null,{"$f":"K86+K57","v":0},null,{"$f":"IF(AND(I5>=8,I5<=20),8,\"\")","v":""},{"$f":"IF(J14=1,Tool!D140,\"\")","v":""},{"$f":"IF(J14=1,Tool!E140,\"\")","v":""},{"$f":"IF(Tool!D140=\"\",\"\",IF(G14<>\"\",IF(Tool!F140=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5>=8,R5<=20),8,\"\")","v":""},{"$f":"IF(S14=1,Tool!D140,\"\")","v":""},{"$f":"IF(S14=1,Tool!E140,\"\")","v":""},{"$f":"IF(Tool!D140=\"\",\"\",IF(P14<>\"\",IF(OR(Tool!F140=Tool!$H$9,Tool!F140=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=8,AD5<=20),8,\"\")","v":""},{"$f":"IF(AE14=1,Tool!D140,\"\")","v":""},{"$f":"IF(AE14=1,Tool!E140,\"\")","v":""},{"$f":"IF(Tool!D140=\"\",\"\",IF(AB14<>\"\",IF(Tool!F140=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,{"$f":"U85","v":0},"New Bridge (Concrete I-Beam & Bulb-T):",null,{"$f":"U86+U57","v":0},null,{"$f":"IF(AND(I5>=9,I5<=20),9,\"\")","v":""},{"$f":"IF(J15=1,Tool!D141,\"\")","v":""},{"$f":"IF(J15=1,Tool!E141,\"\")","v":""},{"$f":"IF(Tool!D141=\"\",\"\",IF(G15<>\"\",IF(Tool!F141=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5>=9,R5<=20),9,\"\")","v":""},{"$f":"IF(S15=1,Tool!D141,\"\")","v":""},{"$f":"IF(S15=1,Tool!E141,\"\")","v":""},{"$f":"IF(Tool!D141=\"\",\"\",IF(P15<>\"\",IF(OR(Tool!F141=Tool!$H$9,Tool!F141=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=9,AD5<=20),9,\"\")","v":""},{"$f":"IF(AE15=1,Tool!D141,\"\")","v":""},{"$f":"IF(AE15=1,Tool!E141,\"\")","v":""},{"$f":"IF(Tool!D141=\"\",\"\",IF(AB15<>\"\",IF(Tool!F141=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,{"$f":"AE85","v":0},"New Bridge (Concrete Box Beam):",null,{"$f":"AE86","v":0},null,{"$f":"IF(AND(I5>=10,I5<=20),10,\"\")","v":""},{"$f":"IF(J16=1,Tool!D142,\"\")","v":""},{"$f":"IF(J16=1,Tool!E142,\"\")","v":""},{"$f":"IF(Tool!D142=\"\",\"\",IF(G16<>\"\",IF(Tool!F142=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5>=10,R5<=20),10,\"\")","v":""},{"$f":"IF(S16=1,Tool!D142,\"\")","v":""},{"$f":"IF(S16=1,Tool!E142,\"\")","v":""},{"$f":"IF(Tool!D142=\"\",\"\",IF(P16<>\"\",IF(OR(Tool!F142=Tool!$H$9,Tool!F142=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=10,AD5<=20),10,\"\")","v":""},{"$f":"IF(AE16=1,Tool!D142,\"\")","v":""},{"$f":"IF(AE16=1,Tool!E142,\"\")","v":""},{"$f":"IF(Tool!D142=\"\",\"\",IF(AB16<>\"\",IF(Tool!F142=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,{"$f":"AO85","v":0},"New Bridge (Steel Girder):",null,{"$f":"AO86+AO57","v":0},null,{"$f":"IF(AND(I5>=11,I5<=20),11,\"\")","v":""},{"$f":"IF(J17=1,Tool!D143,\"\")","v":""},{"$f":"IF(J17=1,Tool!E143,\"\")","v":""},{"$f":"IF(Tool!D143=\"\",\"\",IF(G17<>\"\",IF(Tool!F143=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5>=11,R5<=20),11,\"\")","v":""},{"$f":"IF(S17=1,Tool!D143,\"\")","v":""},{"$f":"IF(S17=1,Tool!E143,\"\")","v":""},{"$f":"IF(Tool!D143=\"\",\"\",IF(P17<>\"\",IF(OR(Tool!F143=Tool!$H$9,Tool!F143=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=11,AD5<=20),11,\"\")","v":""},{"$f":"IF(AE17=1,Tool!D143,\"\")","v":""},{"$f":"IF(AE17=1,Tool!E143,\"\")","v":""},{"$f":"IF(Tool!D143=\"\",\"\",IF(AB17<>\"\",IF(Tool!F143=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,null,"New Bridge (Box):",null,{"$f":"K88","v":0},null,{"$f":"IF(AND(I5>=12,I5<=20),12,\"\")","v":""},{"$f":"IF(J18=1,Tool!D144,\"\")","v":""},{"$f":"IF(J18=1,Tool!E144,\"\")","v":""},{"$f":"IF(Tool!D144=\"\",\"\",IF(G18<>\"\",IF(Tool!F144=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5>=12,R5<=20),12,\"\")","v":""},{"$f":"IF(S18=1,Tool!D144,\"\")","v":""},{"$f":"IF(S18=1,Tool!E144,\"\")","v":""},{"$f":"IF(Tool!D144=\"\",\"\",IF(P18<>\"\",IF(OR(Tool!F144=Tool!$H$9,Tool!F144=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=12,AD5<=20),12,\"\")","v":""},{"$f":"IF(AE18=1,Tool!D144,\"\")","v":""},{"$f":"IF(AE18=1,Tool!E144,\"\")","v":""},{"$f":"IF(Tool!D144=\"\",\"\",IF(AB18<>\"\",IF(Tool!F144=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,null,"New Bridge (Concrete I-Beam & Bulb-T):",null,{"$f":"U88","v":0},null,{"$f":"IF(AND(I5>=13,I5<=20),13,\"\")","v":""},{"$f":"IF(J19=1,Tool!D145,\"\")","v":""},{"$f":"IF(J19=1,Tool!E145,\"\")","v":""},{"$f":"IF(Tool!D145=\"\",\"\",IF(G19<>\"\",IF(Tool!F145=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5>=13,R5<=20),13,\"\")","v":""},{"$f":"IF(S19=1,Tool!D145,\"\")","v":""},{"$f":"IF(S19=1,Tool!E145,\"\")","v":""},{"$f":"IF(Tool!D145=\"\",\"\",IF(P19<>\"\",IF(OR(Tool!F145=Tool!$H$9,Tool!F145=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=13,AD5<=20),13,\"\")","v":""},{"$f":"IF(AE19=1,Tool!D145,\"\")","v":""},{"$f":"IF(AE19=1,Tool!E145,\"\")","v":""},{"$f":"IF(Tool!D145=\"\",\"\",IF(AB19<>\"\",IF(Tool!F145=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,null,"New Bridge (Concrete Box Beam):",null,{"$f":"AE88","v":0},null,{"$f":"IF(AND(I5>=14,I5<=20),14,\"\")","v":""},{"$f":"IF(J20=1,Tool!D146,\"\")","v":""},{"$f":"IF(J20=1,Tool!E146,\"\")","v":""},{"$f":"IF(Tool!D146=\"\",\"\",IF(G20<>\"\",IF(Tool!F146=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5>=14,R5<=20),14,\"\")","v":""},{"$f":"IF(S20=1,Tool!D146,\"\")","v":""},{"$f":"IF(S20=1,Tool!E146,\"\")","v":""},{"$f":"IF(Tool!D146=\"\",\"\",IF(P20<>\"\",IF(OR(Tool!F146=Tool!$H$9,Tool!F146=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=14,AD5<=20),14,\"\")","v":""},{"$f":"IF(AE20=1,Tool!D146,\"\")","v":""},{"$f":"IF(AE20=1,Tool!E146,\"\")","v":""},{"$f":"IF(Tool!D146=\"\",\"\",IF(AB20<>\"\",IF(Tool!F146=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,null,"New Bridge (Steel Girder):",null,{"$f":"AO88","v":0},null,{"$f":"IF(AND(I5>=15,I5<=20),15,\"\")","v":""},{"$f":"IF(J21=1,Tool!D147,\"\")","v":""},{"$f":"IF(J21=1,Tool!E147,\"\")","v":""},{"$f":"IF(Tool!D147=\"\",\"\",IF(G21<>\"\",IF(Tool!F147=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5>=15,R5<=20),15,\"\")","v":""},{"$f":"IF(S21=1,Tool!D147,\"\")","v":""},{"$f":"IF(S21=1,Tool!E147,\"\")","v":""},{"$f":"IF(Tool!D147=\"\",\"\",IF(P21<>\"\",IF(OR(Tool!F147=Tool!$H$9,Tool!F147=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=15,AD5<=20),15,\"\")","v":""},{"$f":"IF(AE21=1,Tool!D147,\"\")","v":""},{"$f":"IF(AE21=1,Tool!E147,\"\")","v":""},{"$f":"IF(Tool!D147=\"\",\"\",IF(AB21<>\"\",IF(Tool!F147=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,null,"Retaining Wall",null,{"$f":"IF(Tool!D203*Tool!D204>0,Tool!D203*Tool!D204,0)","v":0},null,{"$f":"IF(AND(I5>=16,I5<=20),16,\"\")","v":""},{"$f":"IF(J22=1,Tool!D148,\"\")","v":""},{"$f":"IF(J22=1,Tool!E148,\"\")","v":""},{"$f":"IF(Tool!D148=\"\",\"\",IF(G22<>\"\",IF(Tool!F148=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5>=16,R5<=20),16,\"\")","v":""},{"$f":"IF(S22=1,Tool!D148,\"\")","v":""},{"$f":"IF(S22=1,Tool!E148,\"\")","v":""},{"$f":"IF(Tool!D148=\"\",\"\",IF(P22<>\"\",IF(OR(Tool!F148=Tool!$H$9,Tool!F148=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=16,AD5<=20),16,\"\")","v":""},{"$f":"IF(AE22=1,Tool!D148,\"\")","v":""},{"$f":"IF(AE22=1,Tool!E148,\"\")","v":""},{"$f":"IF(Tool!D148=\"\",\"\",IF(AB22<>\"\",IF(Tool!F148=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,"Additional Guardrail for Bridges",null,null,null,null,{"$f":"IF(AND(I5>=17,I5<=20),17,\"\")","v":""},{"$f":"IF(J23=1,Tool!D149,\"\")","v":""},{"$f":"IF(J23=1,Tool!E149,\"\")","v":""},{"$f":"IF(Tool!D149=\"\",\"\",IF(G23<>\"\",IF(Tool!F149=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5>=17,R5<=20),17,\"\")","v":""},{"$f":"IF(S23=1,Tool!D149,\"\")","v":""},{"$f":"IF(S23=1,Tool!E149,\"\")","v":""},{"$f":"IF(Tool!D149=\"\",\"\",IF(P23<>\"\",IF(OR(Tool!F149=Tool!$H$9,Tool!F149=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=17,AD5<=20),17,\"\")","v":""},{"$f":"IF(AE23=1,Tool!D149,\"\")","v":""},{"$f":"IF(AE23=1,Tool!E149,\"\")","v":""},{"$f":"IF(Tool!D149=\"\",\"\",IF(AB23<>\"\",IF(Tool!F149=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,"Item Number","Description",null,"Quantity",null,{"$f":"IF(AND(I5>=18,I5<=20),18,\"\")","v":""},{"$f":"IF(J24=1,Tool!D150,\"\")","v":""},{"$f":"IF(J24=1,Tool!E150,\"\")","v":""},{"$f":"IF(Tool!D150=\"\",\"\",IF(G24<>\"\",IF(Tool!F150=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5>=18,R5<=20),18,\"\")","v":""},{"$f":"IF(S24=1,Tool!D150,\"\")","v":""},{"$f":"IF(S24=1,Tool!E150,\"\")","v":""},{"$f":"IF(Tool!D150=\"\",\"\",IF(P24<>\"\",IF(OR(Tool!F150=Tool!$H$9,Tool!F150=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=18,AD5<=20),18,\"\")","v":""},{"$f":"IF(AE24=1,Tool!D150,\"\")","v":""},{"$f":"IF(AE24=1,Tool!E150,\"\")","v":""},{"$f":"IF(Tool!D150=\"\",\"\",IF(AB24<>\"\",IF(Tool!F150=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,"705-01.01","Guardrail @ Bridge Ends (LF)",null,{"$f":"25*4*SUM(B10:B17)","v":0},null,{"$f":"IF(AND(I5>=19,I5<=20),19,\"\")","v":""},{"$f":"IF(J25=1,Tool!D151,\"\")","v":""},{"$f":"IF(J25=1,Tool!E151,\"\")","v":""},{"$f":"IF(Tool!D151=\"\",\"\",IF(G25<>\"\",IF(Tool!F151=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5>=19,R5<=20),19,\"\")","v":""},{"$f":"IF(S25=1,Tool!D151,\"\")","v":""},{"$f":"IF(S25=1,Tool!E151,\"\")","v":""},{"$f":"IF(Tool!D151=\"\",\"\",IF(P25<>\"\",IF(OR(Tool!F151=Tool!$H$9,Tool!F151=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5>=19,AD5<=20),19,\"\")","v":""},{"$f":"IF(AE25=1,Tool!D151,\"\")","v":""},{"$f":"IF(AE25=1,Tool!E151,\"\")","v":""},{"$f":"IF(Tool!D151=\"\",\"\",IF(AB25<>\"\",IF(Tool!F151=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,"705-04.07","Type 38 Guadrail End Treatment (EACH)",null,{"$f":"4*SUM(B10:B17)","v":0},null,{"$f":"IF(AND(I5=20),20,\"\")","v":""},{"$f":"IF(J26=1,Tool!D152,\"\")","v":""},{"$f":"IF(J26=1,Tool!E152,\"\")","v":""},{"$f":"IF(Tool!D152=\"\",\"\",IF(G26<>\"\",IF(Tool!F152=Tool!$H$7,1,\"\"),\"\"))","v":""},"",null,null,null,null,{"$f":"IF(AND(R5=20),20,\"\")","v":""},{"$f":"IF(S26=1,Tool!D152,\"\")","v":""},{"$f":"IF(S26=1,Tool!E152,\"\")","v":""},{"$f":"IF(Tool!D152=\"\",\"\",IF(P26<>\"\",IF(OR(Tool!F152=Tool!$H$9,Tool!F152=Tool!$H$8),1,\"\"),\"\"))","v":""},"",null,null,null,null,null,null,null,{"$f":"IF(AND(AD5=20),20,\"\")","v":""},{"$f":"IF(AE26=1,Tool!D152,\"\")","v":""},{"$f":"IF(AE26=1,Tool!E152,\"\")","v":""},{"$f":"IF(Tool!D152=\"\",\"\",IF(AB26<>\"\",IF(Tool!F152=Tool!$H$10,1,\"\"),\"\"))","v":""},""]
[null,"705-04.09","Earth Pad-Type 38 Guadrail End Treatment (EACH)",null,{"$f":"4*SUM(B10:B17)","v":0},null,null,null,null,"Number:",{"$f":"SUM(J7:J26)","v":0},null,null,null,null,null,null,null,"Number:",{"$f":"SUM(S7:S26)","v":0},null,null,null,null,null,null,null,null,null,null,"Number:",{"$f":"SUM(AE7:AE26)","v":0}]
[null,"709-05.05","Machined Rip-Rap (Class A-3)",null,{"$f":"800*SUM(B10:B17)","v":0},null,null,null,null,"Total Area:",{"$f":"SUM(K7:K26)","v":0},null,null,null,null,null,null,null,"Total Area:",{"$f":"SUM(T7:T26)","v":0},null,null,null,null,null,null,null,null,null,null,"Total Area:",{"$f":"SUM(AF7:AF26)","v":0}]
[]
[null,null,null,"Type 38",{"$f":"SUM(B10:B17)*4","v":0},null,"Bridge Widenings"]
[]
[null,null,null,null,null,null,"Type = Box Bridges",null,null,null,null,null,null,null,null,null,"Type = Concrete I-Beam & Bulb-T",null,null,null,null,null,null,null,null,null,"Type = Concrete I-Beam & Bulb-T",null,null,null,null,null,null,null,null,null,"Type = Steel"]
[null,null,null,null,null,null,"Bridges:",null,{"$f":"Tool!H179","v":1},null,null,null,null,null,null,null,"Bridges:",null,{"$f":"Tool!H179","v":1},null,null,null,null,null,null,null,"Bridges:",null,{"$f":"Tool!H179","v":1},null,null,null,null,null,null,null,"Bridges:",null,{"$f":"Tool!H179","v":1}]
[null,null,null,null,null,null,"Segments","Length","Width","Type","Area (sqft)","Area Additional","CM","Foundation","Contingency",null,"Segments","Length","Width","Type","Area (sqft)","Area Additional","CM","Foundation","Contingency",null,"Segments","Length","Width","Type","Area (sqft)","Area Additional","CM","Foundation","Contingency",null,"Segments","Length","Width","Type","Area (sqft)","Area Additional","CM","Foundation","Contingency",null,"Contingency"]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=1,I33<=20),1,\"\")","v":1},{"$f":"IF(Bridges!$G35<>\"\",Tool!$D181,\"\")","v":0},{"$f":"IF(Bridges!G35<>\"\",Tool!$E181,\"\")","v":0},{"$f":"IF(Tool!$D181=\"\",\"\",IF(G35<>\"\",IF(Tool!$F181=Tool!$H$7,1,\"\"),\"\"))","v":""},{"$f":"IF(J35=1,H35*I35,\"\")","v":""},{"$f":"IF(Bridges!J35=1,Tool!$G181*Tool!$D181,\"\")","v":""},{"$f":"IF($J35=1,Tool!$H181,\"\")","v":""},{"$f":"IF(J35=1,IF(Tool!$I181=\"Yes\",$I$98,0),\"\")","v":""},{"$f":"IF(J35=1,IFERROR(VLOOKUP(M35,$H$94:$I$96,2,0)+N35,0),\"\")","v":""},{"$f":"H35*L35","v":{"$error":"#VALUE!"}},{"$f":"IF(AND(S33>=1,S33<=20),1,\"\")","v":1},{"$f":"IF(Bridges!$G35<>\"\",Tool!$D181,\"\")","v":0},{"$f":"IF(Bridges!Q35<>\"\",Tool!$E181,\"\")","v":0},{"$f":"IF(Tool!$D181=\"\",\"\",IF(Q35<>\"\",IF(Tool!$F181=Tool!$H$8,1,\"\"),\"\"))","v":""},{"$f":"IF(T35=1,R35*S35,\"\")","v":""},{"$f":"IF(Bridges!T35=1,Tool!$G181*Tool!$D181,\"\")","v":""},{"$f":"IF($T35=1,Tool!$H181,\"\")","v":""},{"$f":"IF(T35=1,IF(Tool!$I181=\"Yes\",$I$98,0),\"\")","v":""},{"$f":"IF(T35=1,IFERROR(VLOOKUP(W35,$H$94:$I$96,2,0)+X35,0),\"\")","v":""},null,{"$f":"IF(AND(AC33>=1,AC33<=20),1,\"\")","v":1},{"$f":"IF(Bridges!$G35<>\"\",Tool!$D181,\"\")","v":0},{"$f":"IF(Bridges!AA35<>\"\",Tool!$E181,\"\")","v":0},{"$f":"IF(Tool!$D181=\"\",\"\",IF(AA35<>\"\",IF(Tool!$F181=Tool!$H$9,1,\"\"),\"\"))","v":""},{"$f":"IF(AD35=1,AB35*AC35,\"\")","v":""},{"$f":"IF(Bridges!AD35=1,Tool!$G181*Tool!$D181,\"\")","v":""},{"$f":"IF($AD35=1,Tool!$H181,\"\")","v":""},{"$f":"IF(AD35=1,IF(Tool!$I181=\"Yes\",$I$98,0),\"\")","v":""},{"$f":"IF(AD35=1,IFERROR(VLOOKUP(AG35,$H$94:$I$96,2,0)+AH35,0),\"\")","v":""},null,{"$f":"IF(AND(AM33>=1,AM33<=20),1,\"\")","v":1},{"$f":"IF(Bridges!$G35<>\"\",Tool!$D181,\"\")","v":0},{"$f":"IF(Bridges!AK35<>\"\",Tool!$E181,\"\")","v":0},{"$f":"IF(Tool!$D181=\"\",\"\",IF(AK35<>\"\",IF(Tool!$F181=Tool!$H$10,1,\"\"),\"\"))","v":""},{"$f":"IF(AN35=1,AL35*AM35,\"\")","v":""},{"$f":"IF(Bridges!AN35=1,Tool!$G181*Tool!$D181,\"\")","v":""},{"$f":"IF($AN35=1,Tool!$H181,\"\")","v":""},{"$f":"IF(AN35=1,IF(Tool!$I181=\"Yes\",$I$98,0),\"\")","v":""},{"$f":"IF(AN35=1,IFERROR(VLOOKUP(AQ35,$H$94:$I$96,2,0)+AR35,0),\"\")","v":""},null,{"$f":"SUM(O35,Y35,AI35,AS35)","v":0}]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=2,I33<=20),2,\"\")","v":""},{"$f":"IF(Bridges!$G36<>\"\",Tool!$D182,\"\")","v":""},{"$f":"IF(Bridges!G36<>\"\",Tool!$E182,\"\")","v":""},{"$f":"IF(Tool!$D182=\"\",\"\",IF(G36<>\"\",IF(Tool!$F182=Tool!$H$7,1,\"\"),\"\"))","v":""},{"$f":"IF(J36=1,H36*I36,\"\")","v":""},{"$f":"IF(Bridges!J36=1,Tool!$G182*Tool!$D182,\"\")","v":""},{"$f":"IF($J36=1,Tool!$H182,\"\")","v":""},{"$f":"IF(J36=1,IF(Tool!$I182=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=2,S33<=20),2,\"\")","v":""},{"$f":"IF(Bridges!$G36<>\"\",Tool!$D182,\"\")","v":""},{"$f":"IF(Bridges!Q36<>\"\",Tool!$E182,\"\")","v":""},{"$f":"IF(Tool!$D182=\"\",\"\",IF(Q36<>\"\",IF(Tool!$F182=Tool!$H$8,1,\"\"),\"\"))","v":""},{"$f":"IF(T36=1,R36*S36,\"\")","v":""},{"$f":"IF(Bridges!T36=1,Tool!$G182*Tool!$D182,\"\")","v":""},{"$f":"IF($T36=1,Tool!$H182,\"\")","v":""},{"$f":"IF(T36=1,IF(Tool!$I182=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=2,AC33<=20),2,\"\")","v":""},{"$f":"IF(Bridges!$G36<>\"\",Tool!$D182,\"\")","v":""},{"$f":"IF(Bridges!AA36<>\"\",Tool!$E182,\"\")","v":""},{"$f":"IF(Tool!$D182=\"\",\"\",IF(AA36<>\"\",IF(Tool!$F182=Tool!$H$9,1,\"\"),\"\"))","v":""},{"$f":"IF(AD36=1,AB36*AC36,\"\")","v":""},{"$f":"IF(Bridges!AD36=1,Tool!$G182*Tool!$D182,\"\")","v":""},{"$f":"IF($AD36=1,Tool!$H182,\"\")","v":""},{"$f":"IF(AD36=1,IF(Tool!$I182=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=2,AM33<=20),2,\"\")","v":""},{"$f":"IF(Bridges!$G36<>\"\",Tool!$D182,\"\")","v":""},{"$f":"IF(Bridges!AK36<>\"\",Tool!$E182,\"\")","v":""},{"$f":"IF(Tool!$D182=\"\",\"\",IF(AK36<>\"\",IF(Tool!$F182=Tool!$H$10,1,\"\"),\"\"))","v":""},{"$f":"IF(AN36=1,AL36*AM36,\"\")","v":""},{"$f":"IF(Bridges!AN36=1,Tool!$G182*Tool!$D182,\"\")","v":""},{"$f":"IF($AN36=1,Tool!$H182,\"\")","v":""},{"$f":"IF(AN36=1,IF(Tool!$I182=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"SUM(O36,Y36,AI36,AS36)","v":0}]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=3,I33<=20),3,\"\")","v":""},{"$f":"IF(Bridges!$G37<>\"\",Tool!$D183,\"\")","v":""},{"$f":"IF(Bridges!G37<>\"\",Tool!$E183,\"\")","v":""},{"$f":"IF(Tool!$D183=\"\",\"\",IF(G37<>\"\",IF(Tool!$F183=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J37=1,Tool!$G183*Tool!$D183,\"\")","v":""},{"$f":"IF($J37=1,Tool!$H183,\"\")","v":""},{"$f":"IF(J37=1,IF(Tool!$I183=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=3,S33<=20),3,\"\")","v":""},{"$f":"IF(Bridges!$G37<>\"\",Tool!$D183,\"\")","v":""},{"$f":"IF(Bridges!Q37<>\"\",Tool!$E183,\"\")","v":""},{"$f":"IF(Tool!$D183=\"\",\"\",IF(Q37<>\"\",IF(Tool!$F183=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T37=1,Tool!$G183*Tool!$D183,\"\")","v":""},{"$f":"IF($T37=1,Tool!$H183,\"\")","v":""},{"$f":"IF(T37=1,IF(Tool!$I183=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=3,AC33<=20),3,\"\")","v":""},{"$f":"IF(Bridges!$G37<>\"\",Tool!$D183,\"\")","v":""},{"$f":"IF(Bridges!AA37<>\"\",Tool!$E183,\"\")","v":""},{"$f":"IF(Tool!$D183=\"\",\"\",IF(AA37<>\"\",IF(Tool!$F183=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD37=1,Tool!$G183*Tool!$D183,\"\")","v":""},{"$f":"IF($AD37=1,Tool!$H183,\"\")","v":""},{"$f":"IF(AD37=1,IF(Tool!$I183=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=3,AM33<=20),3,\"\")","v":""},{"$f":"IF(Bridges!$G37<>\"\",Tool!$D183,\"\")","v":""},{"$f":"IF(Bridges!AK37<>\"\",Tool!$E183,\"\")","v":""},{"$f":"IF(Tool!$D183=\"\",\"\",IF(AK37<>\"\",IF(Tool!$F183=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN37=1,Tool!$G183*Tool!$D183,\"\")","v":""},{"$f":"IF($AN37=1,Tool!$H183,\"\")","v":""},{"$f":"IF(AN37=1,IF(Tool!$I183=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=4,I33<=20),4,\"\")","v":""},{"$f":"IF(Bridges!$G38<>\"\",Tool!$D184,\"\")","v":""},{"$f":"IF(Bridges!G38<>\"\",Tool!$E184,\"\")","v":""},{"$f":"IF(Tool!$D184=\"\",\"\",IF(G38<>\"\",IF(Tool!$F184=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J38=1,Tool!$G184*Tool!$D184,\"\")","v":""},{"$f":"IF($J38=1,Tool!$H184,\"\")","v":""},{"$f":"IF(J38=1,IF(Tool!$I184=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=4,S33<=20),4,\"\")","v":""},{"$f":"IF(Bridges!$G38<>\"\",Tool!$D184,\"\")","v":""},{"$f":"IF(Bridges!Q38<>\"\",Tool!$E184,\"\")","v":""},{"$f":"IF(Tool!$D184=\"\",\"\",IF(Q38<>\"\",IF(Tool!$F184=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T38=1,Tool!$G184*Tool!$D184,\"\")","v":""},{"$f":"IF($T38=1,Tool!$H184,\"\")","v":""},{"$f":"IF(T38=1,IF(Tool!$I184=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=4,AC33<=20),4,\"\")","v":""},{"$f":"IF(Bridges!$G38<>\"\",Tool!$D184,\"\")","v":""},{"$f":"IF(Bridges!AA38<>\"\",Tool!$E184,\"\")","v":""},{"$f":"IF(Tool!$D184=\"\",\"\",IF(AA38<>\"\",IF(Tool!$F184=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD38=1,Tool!$G184*Tool!$D184,\"\")","v":""},{"$f":"IF($AD38=1,Tool!$H184,\"\")","v":""},{"$f":"IF(AD38=1,IF(Tool!$I184=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=4,AM33<=20),4,\"\")","v":""},{"$f":"IF(Bridges!$G38<>\"\",Tool!$D184,\"\")","v":""},{"$f":"IF(Bridges!AK38<>\"\",Tool!$E184,\"\")","v":""},{"$f":"IF(Tool!$D184=\"\",\"\",IF(AK38<>\"\",IF(Tool!$F184=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN38=1,Tool!$G184*Tool!$D184,\"\")","v":""},{"$f":"IF($AN38=1,Tool!$H184,\"\")","v":""},{"$f":"IF(AN38=1,IF(Tool!$I184=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=5,I33<=20),5,\"\")","v":""},{"$f":"IF(Bridges!$G39<>\"\",Tool!$D185,\"\")","v":""},{"$f":"IF(Bridges!G39<>\"\",Tool!$E185,\"\")","v":""},{"$f":"IF(Tool!$D185=\"\",\"\",IF(G39<>\"\",IF(Tool!$F185=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J39=1,Tool!$G185*Tool!$D185,\"\")","v":""},{"$f":"IF($J39=1,Tool!$H185,\"\")","v":""},{"$f":"IF(J39=1,IF(Tool!$I185=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=5,S33<=20),5,\"\")","v":""},{"$f":"IF(Bridges!$G39<>\"\",Tool!$D185,\"\")","v":""},{"$f":"IF(Bridges!Q39<>\"\",Tool!$E185,\"\")","v":""},{"$f":"IF(Tool!$D185=\"\",\"\",IF(Q39<>\"\",IF(Tool!$F185=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T39=1,Tool!$G185*Tool!$D185,\"\")","v":""},{"$f":"IF($T39=1,Tool!$H185,\"\")","v":""},{"$f":"IF(T39=1,IF(Tool!$I185=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=5,AC33<=20),5,\"\")","v":""},{"$f":"IF(Bridges!$G39<>\"\",Tool!$D185,\"\")","v":""},{"$f":"IF(Bridges!AA39<>\"\",Tool!$E185,\"\")","v":""},{"$f":"IF(Tool!$D185=\"\",\"\",IF(AA39<>\"\",IF(Tool!$F185=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD39=1,Tool!$G185*Tool!$D185,\"\")","v":""},{"$f":"IF($AD39=1,Tool!$H185,\"\")","v":""},{"$f":"IF(AD39=1,IF(Tool!$I185=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=5,AM33<=20),5,\"\")","v":""},{"$f":"IF(Bridges!$G39<>\"\",Tool!$D185,\"\")","v":""},{"$f":"IF(Bridges!AK39<>\"\",Tool!$E185,\"\")","v":""},{"$f":"IF(Tool!$D185=\"\",\"\",IF(AK39<>\"\",IF(Tool!$F185=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN39=1,Tool!$G185*Tool!$D185,\"\")","v":""},{"$f":"IF($AN39=1,Tool!$H185,\"\")","v":""},{"$f":"IF(AN39=1,IF(Tool!$I185=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=6,I33<=20),6,\"\")","v":""},{"$f":"IF(Bridges!$G40<>\"\",Tool!$D186,\"\")","v":""},{"$f":"IF(Bridges!G40<>\"\",Tool!$E186,\"\")","v":""},{"$f":"IF(Tool!$D186=\"\",\"\",IF(G40<>\"\",IF(Tool!$F186=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J40=1,Tool!$G186*Tool!$D186,\"\")","v":""},{"$f":"IF($J40=1,Tool!$H186,\"\")","v":""},{"$f":"IF(J40=1,IF(Tool!$I186=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=6,S33<=20),6,\"\")","v":""},{"$f":"IF(Bridges!$G40<>\"\",Tool!$D186,\"\")","v":""},{"$f":"IF(Bridges!Q40<>\"\",Tool!$E186,\"\")","v":""},{"$f":"IF(Tool!$D186=\"\",\"\",IF(Q40<>\"\",IF(Tool!$F186=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T40=1,Tool!$G186*Tool!$D186,\"\")","v":""},{"$f":"IF($T40=1,Tool!$H186,\"\")","v":""},{"$f":"IF(T40=1,IF(Tool!$I186=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=6,AC33<=20),6,\"\")","v":""},{"$f":"IF(Bridges!$G40<>\"\",Tool!$D186,\"\")","v":""},{"$f":"IF(Bridges!AA40<>\"\",Tool!$E186,\"\")","v":""},{"$f":"IF(Tool!$D186=\"\",\"\",IF(AA40<>\"\",IF(Tool!$F186=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD40=1,Tool!$G186*Tool!$D186,\"\")","v":""},{"$f":"IF($AD40=1,Tool!$H186,\"\")","v":""},{"$f":"IF(AD40=1,IF(Tool!$I186=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=6,AM33<=20),6,\"\")","v":""},{"$f":"IF(Bridges!$G40<>\"\",Tool!$D186,\"\")","v":""},{"$f":"IF(Bridges!AK40<>\"\",Tool!$E186,\"\")","v":""},{"$f":"IF(Tool!$D186=\"\",\"\",IF(AK40<>\"\",IF(Tool!$F186=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN40=1,Tool!$G186*Tool!$D186,\"\")","v":""},{"$f":"IF($AN40=1,Tool!$H186,\"\")","v":""},{"$f":"IF(AN40=1,IF(Tool!$I186=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=7,I33<=20),7,\"\")","v":""},{"$f":"IF(Bridges!$G41<>\"\",Tool!$D187,\"\")","v":""},{"$f":"IF(Bridges!G41<>\"\",Tool!$E187,\"\")","v":""},{"$f":"IF(Tool!$D187=\"\",\"\",IF(G41<>\"\",IF(Tool!$F187=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J41=1,Tool!$G187*Tool!$D187,\"\")","v":""},{"$f":"IF($J41=1,Tool!$H187,\"\")","v":""},{"$f":"IF(J41=1,IF(Tool!$I187=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=7,S33<=20),7,\"\")","v":""},{"$f":"IF(Bridges!$G41<>\"\",Tool!$D187,\"\")","v":""},{"$f":"IF(Bridges!Q41<>\"\",Tool!$E187,\"\")","v":""},{"$f":"IF(Tool!$D187=\"\",\"\",IF(Q41<>\"\",IF(Tool!$F187=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T41=1,Tool!$G187*Tool!$D187,\"\")","v":""},{"$f":"IF($T41=1,Tool!$H187,\"\")","v":""},{"$f":"IF(T41=1,IF(Tool!$I187=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=7,AC33<=20),7,\"\")","v":""},{"$f":"IF(Bridges!$G41<>\"\",Tool!$D187,\"\")","v":""},{"$f":"IF(Bridges!AA41<>\"\",Tool!$E187,\"\")","v":""},{"$f":"IF(Tool!$D187=\"\",\"\",IF(AA41<>\"\",IF(Tool!$F187=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD41=1,Tool!$G187*Tool!$D187,\"\")","v":""},{"$f":"IF($AD41=1,Tool!$H187,\"\")","v":""},{"$f":"IF(AD41=1,IF(Tool!$I187=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=7,AM33<=20),7,\"\")","v":""},{"$f":"IF(Bridges!$G41<>\"\",Tool!$D187,\"\")","v":""},{"$f":"IF(Bridges!AK41<>\"\",Tool!$E187,\"\")","v":""},{"$f":"IF(Tool!$D187=\"\",\"\",IF(AK41<>\"\",IF(Tool!$F187=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN41=1,Tool!$G187*Tool!$D187,\"\")","v":""},{"$f":"IF($AN41=1,Tool!$H187,\"\")","v":""},{"$f":"IF(AN41=1,IF(Tool!$I187=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=8,I33<=20),8,\"\")","v":""},{"$f":"IF(Bridges!$G42<>\"\",Tool!$D188,\"\")","v":""},{"$f":"IF(Bridges!G42<>\"\",Tool!$E188,\"\")","v":""},{"$f":"IF(Tool!$D188=\"\",\"\",IF(G42<>\"\",IF(Tool!$F188=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J42=1,Tool!$G188*Tool!$D188,\"\")","v":""},{"$f":"IF($J42=1,Tool!$H188,\"\")","v":""},{"$f":"IF(J42=1,IF(Tool!$I188=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=8,S33<=20),8,\"\")","v":""},{"$f":"IF(Bridges!$G42<>\"\",Tool!$D188,\"\")","v":""},{"$f":"IF(Bridges!Q42<>\"\",Tool!$E188,\"\")","v":""},{"$f":"IF(Tool!$D188=\"\",\"\",IF(Q42<>\"\",IF(Tool!$F188=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T42=1,Tool!$G188*Tool!$D188,\"\")","v":""},{"$f":"IF($T42=1,Tool!$H188,\"\")","v":""},{"$f":"IF(T42=1,IF(Tool!$I188=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=8,AC33<=20),8,\"\")","v":""},{"$f":"IF(Bridges!$G42<>\"\",Tool!$D188,\"\")","v":""},{"$f":"IF(Bridges!AA42<>\"\",Tool!$E188,\"\")","v":""},{"$f":"IF(Tool!$D188=\"\",\"\",IF(AA42<>\"\",IF(Tool!$F188=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD42=1,Tool!$G188*Tool!$D188,\"\")","v":""},{"$f":"IF($AD42=1,Tool!$H188,\"\")","v":""},{"$f":"IF(AD42=1,IF(Tool!$I188=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=8,AM33<=20),8,\"\")","v":""},{"$f":"IF(Bridges!$G42<>\"\",Tool!$D188,\"\")","v":""},{"$f":"IF(Bridges!AK42<>\"\",Tool!$E188,\"\")","v":""},{"$f":"IF(Tool!$D188=\"\",\"\",IF(AK42<>\"\",IF(Tool!$F188=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN42=1,Tool!$G188*Tool!$D188,\"\")","v":""},{"$f":"IF($AN42=1,Tool!$H188,\"\")","v":""},{"$f":"IF(AN42=1,IF(Tool!$I188=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=9,I33<=20),9,\"\")","v":""},{"$f":"IF(Bridges!$G43<>\"\",Tool!$D189,\"\")","v":""},{"$f":"IF(Bridges!G43<>\"\",Tool!$E189,\"\")","v":""},{"$f":"IF(Tool!$D189=\"\",\"\",IF(G43<>\"\",IF(Tool!$F189=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J43=1,Tool!$G189*Tool!$D189,\"\")","v":""},{"$f":"IF($J43=1,Tool!$H189,\"\")","v":""},{"$f":"IF(J43=1,IF(Tool!$I189=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=9,S33<=20),9,\"\")","v":""},{"$f":"IF(Bridges!$G43<>\"\",Tool!$D189,\"\")","v":""},{"$f":"IF(Bridges!Q43<>\"\",Tool!$E189,\"\")","v":""},{"$f":"IF(Tool!$D189=\"\",\"\",IF(Q43<>\"\",IF(Tool!$F189=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T43=1,Tool!$G189*Tool!$D189,\"\")","v":""},{"$f":"IF($T43=1,Tool!$H189,\"\")","v":""},{"$f":"IF(T43=1,IF(Tool!$I189=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=9,AC33<=20),9,\"\")","v":""},{"$f":"IF(Bridges!$G43<>\"\",Tool!$D189,\"\")","v":""},{"$f":"IF(Bridges!AA43<>\"\",Tool!$E189,\"\")","v":""},{"$f":"IF(Tool!$D189=\"\",\"\",IF(AA43<>\"\",IF(Tool!$F189=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD43=1,Tool!$G189*Tool!$D189,\"\")","v":""},{"$f":"IF($AD43=1,Tool!$H189,\"\")","v":""},{"$f":"IF(AD43=1,IF(Tool!$I189=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=9,AM33<=20),9,\"\")","v":""},{"$f":"IF(Bridges!$G43<>\"\",Tool!$D189,\"\")","v":""},{"$f":"IF(Bridges!AK43<>\"\",Tool!$E189,\"\")","v":""},{"$f":"IF(Tool!$D189=\"\",\"\",IF(AK43<>\"\",IF(Tool!$F189=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN43=1,Tool!$G189*Tool!$D189,\"\")","v":""},{"$f":"IF($AN43=1,Tool!$H189,\"\")","v":""},{"$f":"IF(AN43=1,IF(Tool!$I189=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=10,I33<=20),10,\"\")","v":""},{"$f":"IF(Bridges!$G44<>\"\",Tool!$D190,\"\")","v":""},{"$f":"IF(Bridges!G44<>\"\",Tool!$E190,\"\")","v":""},{"$f":"IF(Tool!$D190=\"\",\"\",IF(G44<>\"\",IF(Tool!$F190=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J44=1,Tool!$G190*Tool!$D190,\"\")","v":""},{"$f":"IF($J44=1,Tool!$H190,\"\")","v":""},{"$f":"IF(J44=1,IF(Tool!$I190=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=10,S33<=20),10,\"\")","v":""},{"$f":"IF(Bridges!$G44<>\"\",Tool!$D190,\"\")","v":""},{"$f":"IF(Bridges!Q44<>\"\",Tool!$E190,\"\")","v":""},{"$f":"IF(Tool!$D190=\"\",\"\",IF(Q44<>\"\",IF(Tool!$F190=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T44=1,Tool!$G190*Tool!$D190,\"\")","v":""},{"$f":"IF($T44=1,Tool!$H190,\"\")","v":""},{"$f":"IF(T44=1,IF(Tool!$I190=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=10,AC33<=20),10,\"\")","v":""},{"$f":"IF(Bridges!$G44<>\"\",Tool!$D190,\"\")","v":""},{"$f":"IF(Bridges!AA44<>\"\",Tool!$E190,\"\")","v":""},{"$f":"IF(Tool!$D190=\"\",\"\",IF(AA44<>\"\",IF(Tool!$F190=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD44=1,Tool!$G190*Tool!$D190,\"\")","v":""},{"$f":"IF($AD44=1,Tool!$H190,\"\")","v":""},{"$f":"IF(AD44=1,IF(Tool!$I190=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=10,AM33<=20),10,\"\")","v":""},{"$f":"IF(Bridges!$G44<>\"\",Tool!$D190,\"\")","v":""},{"$f":"IF(Bridges!AK44<>\"\",Tool!$E190,\"\")","v":""},{"$f":"IF(Tool!$D190=\"\",\"\",IF(AK44<>\"\",IF(Tool!$F190=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN44=1,Tool!$G190*Tool!$D190,\"\")","v":""},{"$f":"IF($AN44=1,Tool!$H190,\"\")","v":""},{"$f":"IF(AN44=1,IF(Tool!$I190=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=11,I33<=20),11,\"\")","v":""},{"$f":"IF(Bridges!$G45<>\"\",Tool!$D191,\"\")","v":""},{"$f":"IF(Bridges!G45<>\"\",Tool!$E191,\"\")","v":""},{"$f":"IF(Tool!$D191=\"\",\"\",IF(G45<>\"\",IF(Tool!$F191=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J45=1,Tool!$G191*Tool!$D191,\"\")","v":""},{"$f":"IF($J45=1,Tool!$H191,\"\")","v":""},{"$f":"IF(J45=1,IF(Tool!$I191=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=11,S33<=20),11,\"\")","v":""},{"$f":"IF(Bridges!$G45<>\"\",Tool!$D191,\"\")","v":""},{"$f":"IF(Bridges!Q45<>\"\",Tool!$E191,\"\")","v":""},{"$f":"IF(Tool!$D191=\"\",\"\",IF(Q45<>\"\",IF(Tool!$F191=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T45=1,Tool!$G191*Tool!$D191,\"\")","v":""},{"$f":"IF($T45=1,Tool!$H191,\"\")","v":""},{"$f":"IF(T45=1,IF(Tool!$I191=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=11,AC33<=20),11,\"\")","v":""},{"$f":"IF(Bridges!$G45<>\"\",Tool!$D191,\"\")","v":""},{"$f":"IF(Bridges!AA45<>\"\",Tool!$E191,\"\")","v":""},{"$f":"IF(Tool!$D191=\"\",\"\",IF(AA45<>\"\",IF(Tool!$F191=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD45=1,Tool!$G191*Tool!$D191,\"\")","v":""},{"$f":"IF($AD45=1,Tool!$H191,\"\")","v":""},{"$f":"IF(AD45=1,IF(Tool!$I191=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=11,AM33<=20),11,\"\")","v":""},{"$f":"IF(Bridges!$G45<>\"\",Tool!$D191,\"\")","v":""},{"$f":"IF(Bridges!AK45<>\"\",Tool!$E191,\"\")","v":""},{"$f":"IF(Tool!$D191=\"\",\"\",IF(AK45<>\"\",IF(Tool!$F191=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN45=1,Tool!$G191*Tool!$D191,\"\")","v":""},{"$f":"IF($AN45=1,Tool!$H191,\"\")","v":""},{"$f":"IF(AN45=1,IF(Tool!$I191=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=12,I33<=20),12,\"\")","v":""},{"$f":"IF(Bridges!$G46<>\"\",Tool!$D192,\"\")","v":""},{"$f":"IF(Bridges!G46<>\"\",Tool!$E192,\"\")","v":""},{"$f":"IF(Tool!$D192=\"\",\"\",IF(G46<>\"\",IF(Tool!$F192=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J46=1,Tool!$G192*Tool!$D192,\"\")","v":""},{"$f":"IF($J46=1,Tool!$H192,\"\")","v":""},{"$f":"IF(J46=1,IF(Tool!$I192=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=12,S33<=20),12,\"\")","v":""},{"$f":"IF(Bridges!$G46<>\"\",Tool!$D192,\"\")","v":""},{"$f":"IF(Bridges!Q46<>\"\",Tool!$E192,\"\")","v":""},{"$f":"IF(Tool!$D192=\"\",\"\",IF(Q46<>\"\",IF(Tool!$F192=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T46=1,Tool!$G192*Tool!$D192,\"\")","v":""},{"$f":"IF($T46=1,Tool!$H192,\"\")","v":""},{"$f":"IF(T46=1,IF(Tool!$I192=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=12,AC33<=20),12,\"\")","v":""},{"$f":"IF(Bridges!$G46<>\"\",Tool!$D192,\"\")","v":""},{"$f":"IF(Bridges!AA46<>\"\",Tool!$E192,\"\")","v":""},{"$f":"IF(Tool!$D192=\"\",\"\",IF(AA46<>\"\",IF(Tool!$F192=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD46=1,Tool!$G192*Tool!$D192,\"\")","v":""},{"$f":"IF($AD46=1,Tool!$H192,\"\")","v":""},{"$f":"IF(AD46=1,IF(Tool!$I192=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=12,AM33<=20),12,\"\")","v":""},{"$f":"IF(Bridges!$G46<>\"\",Tool!$D192,\"\")","v":""},{"$f":"IF(Bridges!AK46<>\"\",Tool!$E192,\"\")","v":""},{"$f":"IF(Tool!$D192=\"\",\"\",IF(AK46<>\"\",IF(Tool!$F192=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN46=1,Tool!$G192*Tool!$D192,\"\")","v":""},{"$f":"IF($AN46=1,Tool!$H192,\"\")","v":""},{"$f":"IF(AN46=1,IF(Tool!$I192=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=13,I33<=20),13,\"\")","v":""},{"$f":"IF(Bridges!$G47<>\"\",Tool!$D193,\"\")","v":""},{"$f":"IF(Bridges!G47<>\"\",Tool!$E193,\"\")","v":""},{"$f":"IF(Tool!$D193=\"\",\"\",IF(G47<>\"\",IF(Tool!$F193=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J47=1,Tool!$G193*Tool!$D193,\"\")","v":""},{"$f":"IF($J47=1,Tool!$H193,\"\")","v":""},{"$f":"IF(J47=1,IF(Tool!$I193=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=13,S33<=20),13,\"\")","v":""},{"$f":"IF(Bridges!$G47<>\"\",Tool!$D193,\"\")","v":""},{"$f":"IF(Bridges!Q47<>\"\",Tool!$E193,\"\")","v":""},{"$f":"IF(Tool!$D193=\"\",\"\",IF(Q47<>\"\",IF(Tool!$F193=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T47=1,Tool!$G193*Tool!$D193,\"\")","v":""},{"$f":"IF($T47=1,Tool!$H193,\"\")","v":""},{"$f":"IF(T47=1,IF(Tool!$I193=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=13,AC33<=20),13,\"\")","v":""},{"$f":"IF(Bridges!$G47<>\"\",Tool!$D193,\"\")","v":""},{"$f":"IF(Bridges!AA47<>\"\",Tool!$E193,\"\")","v":""},{"$f":"IF(Tool!$D193=\"\",\"\",IF(AA47<>\"\",IF(Tool!$F193=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD47=1,Tool!$G193*Tool!$D193,\"\")","v":""},{"$f":"IF($AD47=1,Tool!$H193,\"\")","v":""},{"$f":"IF(AD47=1,IF(Tool!$I193=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=13,AM33<=20),13,\"\")","v":""},{"$f":"IF(Bridges!$G47<>\"\",Tool!$D193,\"\")","v":""},{"$f":"IF(Bridges!AK47<>\"\",Tool!$E193,\"\")","v":""},{"$f":"IF(Tool!$D193=\"\",\"\",IF(AK47<>\"\",IF(Tool!$F193=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN47=1,Tool!$G193*Tool!$D193,\"\")","v":""},{"$f":"IF($AN47=1,Tool!$H193,\"\")","v":""},{"$f":"IF(AN47=1,IF(Tool!$I193=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=14,I33<=20),14,\"\")","v":""},{"$f":"IF(Bridges!$G48<>\"\",Tool!$D194,\"\")","v":""},{"$f":"IF(Bridges!G48<>\"\",Tool!$E194,\"\")","v":""},{"$f":"IF(Tool!$D194=\"\",\"\",IF(G48<>\"\",IF(Tool!$F194=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J48=1,Tool!$G194*Tool!$D194,\"\")","v":""},{"$f":"IF($J48=1,Tool!$H194,\"\")","v":""},{"$f":"IF(J48=1,IF(Tool!$I194=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=14,S33<=20),14,\"\")","v":""},{"$f":"IF(Bridges!$G48<>\"\",Tool!$D194,\"\")","v":""},{"$f":"IF(Bridges!Q48<>\"\",Tool!$E194,\"\")","v":""},{"$f":"IF(Tool!$D194=\"\",\"\",IF(Q48<>\"\",IF(Tool!$F194=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T48=1,Tool!$G194*Tool!$D194,\"\")","v":""},{"$f":"IF($T48=1,Tool!$H194,\"\")","v":""},{"$f":"IF(T48=1,IF(Tool!$I194=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=14,AC33<=20),14,\"\")","v":""},{"$f":"IF(Bridges!$G48<>\"\",Tool!$D194,\"\")","v":""},{"$f":"IF(Bridges!AA48<>\"\",Tool!$E194,\"\")","v":""},{"$f":"IF(Tool!$D194=\"\",\"\",IF(AA48<>\"\",IF(Tool!$F194=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD48=1,Tool!$G194*Tool!$D194,\"\")","v":""},{"$f":"IF($AD48=1,Tool!$H194,\"\")","v":""},{"$f":"IF(AD48=1,IF(Tool!$I194=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=14,AM33<=20),14,\"\")","v":""},{"$f":"IF(Bridges!$G48<>\"\",Tool!$D194,\"\")","v":""},{"$f":"IF(Bridges!AK48<>\"\",Tool!$E194,\"\")","v":""},{"$f":"IF(Tool!$D194=\"\",\"\",IF(AK48<>\"\",IF(Tool!$F194=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN48=1,Tool!$G194*Tool!$D194,\"\")","v":""},{"$f":"IF($AN48=1,Tool!$H194,\"\")","v":""},{"$f":"IF(AN48=1,IF(Tool!$I194=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=15,I33<=20),15,\"\")","v":""},{"$f":"IF(Bridges!$G49<>\"\",Tool!$D195,\"\")","v":""},{"$f":"IF(Bridges!G49<>\"\",Tool!$E195,\"\")","v":""},{"$f":"IF(Tool!$D195=\"\",\"\",IF(G49<>\"\",IF(Tool!$F195=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J49=1,Tool!$G195*Tool!$D195,\"\")","v":""},{"$f":"IF($J49=1,Tool!$H195,\"\")","v":""},{"$f":"IF(J49=1,IF(Tool!$I195=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=15,S33<=20),15,\"\")","v":""},{"$f":"IF(Bridges!$G49<>\"\",Tool!$D195,\"\")","v":""},{"$f":"IF(Bridges!Q49<>\"\",Tool!$E195,\"\")","v":""},{"$f":"IF(Tool!$D195=\"\",\"\",IF(Q49<>\"\",IF(Tool!$F195=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T49=1,Tool!$G195*Tool!$D195,\"\")","v":""},{"$f":"IF($T49=1,Tool!$H195,\"\")","v":""},{"$f":"IF(T49=1,IF(Tool!$I195=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=15,AC33<=20),15,\"\")","v":""},{"$f":"IF(Bridges!$G49<>\"\",Tool!$D195,\"\")","v":""},{"$f":"IF(Bridges!AA49<>\"\",Tool!$E195,\"\")","v":""},{"$f":"IF(Tool!$D195=\"\",\"\",IF(AA49<>\"\",IF(Tool!$F195=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD49=1,Tool!$G195*Tool!$D195,\"\")","v":""},{"$f":"IF($AD49=1,Tool!$H195,\"\")","v":""},{"$f":"IF(AD49=1,IF(Tool!$I195=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=15,AM33<=20),15,\"\")","v":""},{"$f":"IF(Bridges!$G49<>\"\",Tool!$D195,\"\")","v":""},{"$f":"IF(Bridges!AK49<>\"\",Tool!$E195,\"\")","v":""},{"$f":"IF(Tool!$D195=\"\",\"\",IF(AK49<>\"\",IF(Tool!$F195=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN49=1,Tool!$G195*Tool!$D195,\"\")","v":""},{"$f":"IF($AN49=1,Tool!$H195,\"\")","v":""},{"$f":"IF(AN49=1,IF(Tool!$I195=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=16,I33<=20),16,\"\")","v":""},{"$f":"IF(Bridges!$G50<>\"\",Tool!$D196,\"\")","v":""},{"$f":"IF(Bridges!G50<>\"\",Tool!$E196,\"\")","v":""},{"$f":"IF(Tool!$D196=\"\",\"\",IF(G50<>\"\",IF(Tool!$F196=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J50=1,Tool!$G196*Tool!$D196,\"\")","v":""},{"$f":"IF($J50=1,Tool!$H196,\"\")","v":""},{"$f":"IF(J50=1,IF(Tool!$I196=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=16,S33<=20),16,\"\")","v":""},{"$f":"IF(Bridges!$G50<>\"\",Tool!$D196,\"\")","v":""},{"$f":"IF(Bridges!Q50<>\"\",Tool!$E196,\"\")","v":""},{"$f":"IF(Tool!$D196=\"\",\"\",IF(Q50<>\"\",IF(Tool!$F196=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T50=1,Tool!$G196*Tool!$D196,\"\")","v":""},{"$f":"IF($T50=1,Tool!$H196,\"\")","v":""},{"$f":"IF(T50=1,IF(Tool!$I196=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=16,AC33<=20),16,\"\")","v":""},{"$f":"IF(Bridges!$G50<>\"\",Tool!$D196,\"\")","v":""},{"$f":"IF(Bridges!AA50<>\"\",Tool!$E196,\"\")","v":""},{"$f":"IF(Tool!$D196=\"\",\"\",IF(AA50<>\"\",IF(Tool!$F196=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD50=1,Tool!$G196*Tool!$D196,\"\")","v":""},{"$f":"IF($AD50=1,Tool!$H196,\"\")","v":""},{"$f":"IF(AD50=1,IF(Tool!$I196=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=16,AM33<=20),16,\"\")","v":""},{"$f":"IF(Bridges!$G50<>\"\",Tool!$D196,\"\")","v":""},{"$f":"IF(Bridges!AK50<>\"\",Tool!$E196,\"\")","v":""},{"$f":"IF(Tool!$D196=\"\",\"\",IF(AK50<>\"\",IF(Tool!$F196=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN50=1,Tool!$G196*Tool!$D196,\"\")","v":""},{"$f":"IF($AN50=1,Tool!$H196,\"\")","v":""},{"$f":"IF(AN50=1,IF(Tool!$I196=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=17,I33<=20),17,\"\")","v":""},{"$f":"IF(Bridges!$G51<>\"\",Tool!$D197,\"\")","v":""},{"$f":"IF(Bridges!G51<>\"\",Tool!$E197,\"\")","v":""},{"$f":"IF(Tool!$D197=\"\",\"\",IF(G51<>\"\",IF(Tool!$F197=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J51=1,Tool!$G197*Tool!$D197,\"\")","v":""},{"$f":"IF($J51=1,Tool!$H197,\"\")","v":""},{"$f":"IF(J51=1,IF(Tool!$I197=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=17,S33<=20),17,\"\")","v":""},{"$f":"IF(Bridges!$G51<>\"\",Tool!$D197,\"\")","v":""},{"$f":"IF(Bridges!Q51<>\"\",Tool!$E197,\"\")","v":""},{"$f":"IF(Tool!$D197=\"\",\"\",IF(Q51<>\"\",IF(Tool!$F197=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T51=1,Tool!$G197*Tool!$D197,\"\")","v":""},{"$f":"IF($T51=1,Tool!$H197,\"\")","v":""},{"$f":"IF(T51=1,IF(Tool!$I197=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=17,AC33<=20),17,\"\")","v":""},{"$f":"IF(Bridges!$G51<>\"\",Tool!$D197,\"\")","v":""},{"$f":"IF(Bridges!AA51<>\"\",Tool!$E197,\"\")","v":""},{"$f":"IF(Tool!$D197=\"\",\"\",IF(AA51<>\"\",IF(Tool!$F197=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD51=1,Tool!$G197*Tool!$D197,\"\")","v":""},{"$f":"IF($AD51=1,Tool!$H197,\"\")","v":""},{"$f":"IF(AD51=1,IF(Tool!$I197=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=17,AM33<=20),17,\"\")","v":""},{"$f":"IF(Bridges!$G51<>\"\",Tool!$D197,\"\")","v":""},{"$f":"IF(Bridges!AK51<>\"\",Tool!$E197,\"\")","v":""},{"$f":"IF(Tool!$D197=\"\",\"\",IF(AK51<>\"\",IF(Tool!$F197=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN51=1,Tool!$G197*Tool!$D197,\"\")","v":""},{"$f":"IF($AN51=1,Tool!$H197,\"\")","v":""},{"$f":"IF(AN51=1,IF(Tool!$I197=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=18,I33<=20),18,\"\")","v":""},{"$f":"IF(Bridges!$G52<>\"\",Tool!$D198,\"\")","v":""},{"$f":"IF(Bridges!G52<>\"\",Tool!$E198,\"\")","v":""},{"$f":"IF(Tool!$D198=\"\",\"\",IF(G52<>\"\",IF(Tool!$F198=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J52=1,Tool!$G198*Tool!$D198,\"\")","v":""},{"$f":"IF($J52=1,Tool!$H198,\"\")","v":""},{"$f":"IF(J52=1,IF(Tool!$I198=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=18,S33<=20),18,\"\")","v":""},{"$f":"IF(Bridges!$G52<>\"\",Tool!$D198,\"\")","v":""},{"$f":"IF(Bridges!Q52<>\"\",Tool!$E198,\"\")","v":""},{"$f":"IF(Tool!$D198=\"\",\"\",IF(Q52<>\"\",IF(Tool!$F198=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T52=1,Tool!$G198*Tool!$D198,\"\")","v":""},{"$f":"IF($T52=1,Tool!$H198,\"\")","v":""},{"$f":"IF(T52=1,IF(Tool!$I198=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=18,AC33<=20),18,\"\")","v":""},{"$f":"IF(Bridges!$G52<>\"\",Tool!$D198,\"\")","v":""},{"$f":"IF(Bridges!AA52<>\"\",Tool!$E198,\"\")","v":""},{"$f":"IF(Tool!$D198=\"\",\"\",IF(AA52<>\"\",IF(Tool!$F198=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD52=1,Tool!$G198*Tool!$D198,\"\")","v":""},{"$f":"IF($AD52=1,Tool!$H198,\"\")","v":""},{"$f":"IF(AD52=1,IF(Tool!$I198=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=18,AM33<=20),18,\"\")","v":""},{"$f":"IF(Bridges!$G52<>\"\",Tool!$D198,\"\")","v":""},{"$f":"IF(Bridges!AK52<>\"\",Tool!$E198,\"\")","v":""},{"$f":"IF(Tool!$D198=\"\",\"\",IF(AK52<>\"\",IF(Tool!$F198=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN52=1,Tool!$G198*Tool!$D198,\"\")","v":""},{"$f":"IF($AN52=1,Tool!$H198,\"\")","v":""},{"$f":"IF(AN52=1,IF(Tool!$I198=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I33>=19,I33<=20),19,\"\")","v":""},{"$f":"IF(Bridges!$G53<>\"\",Tool!$D199,\"\")","v":""},{"$f":"IF(Bridges!G53<>\"\",Tool!$E199,\"\")","v":""},{"$f":"IF(Tool!$D199=\"\",\"\",IF(G53<>\"\",IF(Tool!$F199=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J53=1,Tool!$G199*Tool!$D199,\"\")","v":""},{"$f":"IF($J53=1,Tool!$H199,\"\")","v":""},{"$f":"IF(J53=1,IF(Tool!$I199=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33>=19,S33<=20),19,\"\")","v":""},{"$f":"IF(Bridges!$G53<>\"\",Tool!$D199,\"\")","v":""},{"$f":"IF(Bridges!Q53<>\"\",Tool!$E199,\"\")","v":""},{"$f":"IF(Tool!$D199=\"\",\"\",IF(Q53<>\"\",IF(Tool!$F199=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T53=1,Tool!$G199*Tool!$D199,\"\")","v":""},{"$f":"IF($T53=1,Tool!$H199,\"\")","v":""},{"$f":"IF(T53=1,IF(Tool!$I199=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33>=19,AC33<=20),19,\"\")","v":""},{"$f":"IF(Bridges!$G53<>\"\",Tool!$D199,\"\")","v":""},{"$f":"IF(Bridges!AA53<>\"\",Tool!$E199,\"\")","v":""},{"$f":"IF(Tool!$D199=\"\",\"\",IF(AA53<>\"\",IF(Tool!$F199=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD53=1,Tool!$G199*Tool!$D199,\"\")","v":""},{"$f":"IF($AD53=1,Tool!$H199,\"\")","v":""},{"$f":"IF(AD53=1,IF(Tool!$I199=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33>=19,AM33<=20),19,\"\")","v":""},{"$f":"IF(Bridges!$G53<>\"\",Tool!$D199,\"\")","v":""},{"$f":"IF(Bridges!AK53<>\"\",Tool!$E199,\"\")","v":""},{"$f":"IF(Tool!$D199=\"\",\"\",IF(AK53<>\"\",IF(Tool!$F199=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN53=1,Tool!$G199*Tool!$D199,\"\")","v":""},{"$f":"IF($AN53=1,Tool!$H199,\"\")","v":""},{"$f":"IF(AN53=1,IF(Tool!$I199=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I33=20),20,\"\")","v":""},{"$f":"IF(Bridges!$G54<>\"\",Tool!$D200,\"\")","v":""},{"$f":"IF(Bridges!G54<>\"\",Tool!$E200,\"\")","v":""},{"$f":"IF(Tool!$D200=\"\",\"\",IF(G54<>\"\",IF(Tool!$F200=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!J54=1,Tool!$G200*Tool!$D200,\"\")","v":""},{"$f":"IF($J54=1,Tool!$H200,\"\")","v":""},{"$f":"IF(J54=1,IF(Tool!$I200=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(S33=20),20,\"\")","v":""},{"$f":"IF(Bridges!$G54<>\"\",Tool!$D200,\"\")","v":""},{"$f":"IF(Bridges!Q54<>\"\",Tool!$E200,\"\")","v":""},{"$f":"IF(Tool!$D200=\"\",\"\",IF(Q54<>\"\",IF(Tool!$F200=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!T54=1,Tool!$G200*Tool!$D200,\"\")","v":""},{"$f":"IF($T54=1,Tool!$H200,\"\")","v":""},{"$f":"IF(T54=1,IF(Tool!$I200=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AC33=20),20,\"\")","v":""},{"$f":"IF(Bridges!$G54<>\"\",Tool!$D200,\"\")","v":""},{"$f":"IF(Bridges!AA54<>\"\",Tool!$E200,\"\")","v":""},{"$f":"IF(Tool!$D200=\"\",\"\",IF(AA54<>\"\",IF(Tool!$F200=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AD54=1,Tool!$G200*Tool!$D200,\"\")","v":""},{"$f":"IF($AD54=1,Tool!$H200,\"\")","v":""},{"$f":"IF(AD54=1,IF(Tool!$I200=\"Yes\",$I$98,0),\"\")","v":""},"",null,{"$f":"IF(AND(AM33=20),20,\"\")","v":""},{"$f":"IF(Bridges!$G54<>\"\",Tool!$D200,\"\")","v":""},{"$f":"IF(Bridges!AK54<>\"\",Tool!$E200,\"\")","v":""},{"$f":"IF(Tool!$D200=\"\",\"\",IF(AK54<>\"\",IF(Tool!$F200=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(Bridges!AN54=1,Tool!$G200*Tool!$D200,\"\")","v":""},{"$f":"IF($AN54=1,Tool!$H200,\"\")","v":""},{"$f":"IF(AN54=1,IF(Tool!$I200=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,null,null,null,"Number:",{"$f":"SUM(J35:J54)","v":0},null,null,null,null,null,null,null,null,"Number:",{"$f":"SUM(T35:T54)","v":0},null,null,null,null,null,null,null,null,"Number:",{"$f":"SUM(AD35:AD54)","v":0},null,null,null,null,null,null,null,null,"Number:",{"$f":"SUM(AN35:AN54)","v":0}]
[null,null,null,null,null,null,null,null,null,"Area Exist:",{"$f":"SUM(K35:K54)","v":0},null,null,null,null,null,null,null,null,"Area Exist:",{"$f":"SUM(U35:U54)","v":0},null,null,null,null,null,null,null,null,"Area Exist:",{"$f":"SUM(AE35:AE54)","v":0},null,null,null,null,null,null,null,null,"Area Exist:",{"$f":"SUM(AO35:AO54)","v":0}]
[null,null,null,null,null,null,null,null,null,"Area New:",{"$f":"SUM(L35:L54)","v":0},null,null,null,null,null,null,null,null,"Area New:",{"$f":"SUM(V35:V54)","v":0},null,null,null,null,null,null,null,null,"Area New:",{"$f":"SUM(AF35:AF54)","v":0},null,null,null,null,null,null,null,null,"Area New:",{"$f":"SUM(AP35:AP54)","v":0}]
[null,null,null,null,null,null,null,null,null,"Contingency:",{"$f":"IFERROR(SUMPRODUCT(L35:L54,O35:O54)/SUM(L35:L54),0)","v":0},null,null,null,null,null,null,null,null,"Contingency:",{"$f":"IFERROR(SUMPRODUCT(V35:V54,Y35:Y54)/SUM(V35:V54),0)","v":0},null,null,null,null,null,null,null,null,"Contingency:",{"$f":"IFERROR(SUMPRODUCT(AF35:AF54,AI35:AI54)/SUM(AF35:AF54),0)","v":0},null,null,null,null,null,null,null,null,"Contingency:",{"$f":"IFERROR(SUMPRODUCT(AP35:AP54,AS35:AS54)/SUM(AP35:AP54),0)","v":0}]
[]
[null,null,null,null,null,null,"New Bridges"]
[]
[null,null,null,null,null,null,"Type = Box Bridges",null,null,null,null,null,null,null,null,null,"Type = Concrete I-Beam & Bulb-T",null,null,null,null,null,null,null,null,null,"Type = Concrete Box Beam",null,null,null,null,null,null,null,null,null,"Type = Steel Bridges"]
[null,null,null,null,null,null,"Bridges:",null,{"$f":"Tool!G155","v":1},null,null,null,null,null,null,null,"Bridges:",null,{"$f":"Tool!G155","v":1},null,null,null,null,null,null,null,"Bridges:",null,{"$f":"Tool!G155","v":1},null,null,null,null,null,null,null,"Bridges:",null,{"$f":"Tool!G155","v":1}]
[null,null,null,null,null,null,"Segments","Length","Width","Type","Area (sqft)","CM","Foundation","Contingency",null,null,"Segments","Length","Width","Type","Area (sqft)","CM","Foundation","Contingency 1","Contingency 2",null,"Segments","Length","Width","Type","Area (sqft)","CM","Foundation","Contingency",null,null,"Segments","Length","Width","Type","Area (sqft)","CM","Foundation","Contingency",null,"Contingency"]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=1,I63<=20),1,\"\")","v":1},{"$f":"IF(Bridges!G65<>\"\",Tool!$D157,\"\")","v":0},{"$f":"IF(Bridges!G65<>\"\",Tool!$E157,\"\")","v":0},{"$f":"IF(Tool!D157=\"\",\"\",IF(G65<>\"\",IF(Tool!F157=Tool!$H$7,1,\"\"),\"\"))","v":""},{"$f":"IF(J65=1,H65*I65,\"\")","v":""},{"$f":"IF(J65=1,Tool!G157,\"\")","v":""},{"$f":"IF(J65=1,IF(Tool!$H157=\"Yes\",$I$98,0),\"\")","v":""},{"$f":"IF(J65=1,IFERROR(VLOOKUP(L65,$H$94:$I$96,2,0)+M65,0),\"\")","v":""},null,null,{"$f":"IF(AND(S63>=1,S63<=20),1,\"\")","v":1},{"$f":"IF(Bridges!Q65<>\"\",Tool!$D157,\"\")","v":0},{"$f":"IF(Bridges!Q65<>\"\",Tool!$E157,\"\")","v":0},{"$f":"IF(Tool!D157=\"\",\"\",IF(Q65<>\"\",IF(Tool!F157=Tool!$H$8,1,\"\"),\"\"))","v":""},{"$f":"IF(T65=1,R65*S65,\"\")","v":""},{"$f":"IF(T65=1,Tool!$G157,\"\")","v":""},{"$f":"IF(T65=1,IF(Tool!$H157=\"Yes\",$I$98,0),\"\")","v":""},{"$f":"IF(T65=1,IFERROR(VLOOKUP(V65,$H$94:$I$96,2,0),0),\"\")","v":""},{"$f":"IF(T65=1,IFERROR(VLOOKUP(V65,$H$94:$I$96,2,0)+W65,0),\"\")","v":""},null,{"$f":"IF(AND(AC63>=1,AC63<=20),1,\"\")","v":1},{"$f":"IF(Bridges!AA65<>\"\",Tool!$D157,\"\")","v":0},{"$f":"IF(Bridges!AA65<>\"\",Tool!$E157,\"\")","v":0},{"$f":"IF(Tool!D157=\"\",\"\",IF(AA65<>\"\",IF(Tool!F157=Tool!$H$9,1,\"\"),\"\"))","v":""},{"$f":"IF(AD65=1,AB65*AC65,\"\")","v":""},{"$f":"IF(AD65=1,Tool!$G157,\"\")","v":""},{"$f":"IF(AD65=1,IF(Tool!$H157=\"Yes\",$I$98,0),\"\")","v":""},{"$f":"IF(AD65=1,IFERROR(VLOOKUP(AF65,$H$94:$I$96,2,0)+AG65,0),\"\")","v":""},null,null,{"$f":"IF(AND(AM63>=1,AM63<=20),1,\"\")","v":1},{"$f":"IF(Bridges!AK65<>\"\",Tool!$D157,\"\")","v":0},{"$f":"IF(Bridges!AK65<>\"\",Tool!$E157,\"\")","v":0},{"$f":"IF(Tool!D157=\"\",\"\",IF(AK65<>\"\",IF(Tool!F157=Tool!$H$10,1,\"\"),\"\"))","v":""},{"$f":"IF(AN65=1,AL65*AM65,\"\")","v":""},{"$f":"IF(AN65=1,Tool!$G157,\"\")","v":""},{"$f":"IF(AN65=1,IF(Tool!$H157=\"Yes\",$I$98,0),\"\")","v":""},{"$f":"IF(AN65=1,IFERROR(VLOOKUP(AP65,$H$94:$I$96,2,0)+AQ65,0),\"\")","v":""},null,{"$f":"SUM(N65,AH65,Y65,AR65)","v":0}]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=2,I63<=20),2,\"\")","v":""},{"$f":"IF(Bridges!G66<>\"\",Tool!$D158,\"\")","v":""},{"$f":"IF(Bridges!G66<>\"\",Tool!$E158,\"\")","v":""},{"$f":"IF(Tool!D158=\"\",\"\",IF(G66<>\"\",IF(Tool!F158=Tool!$H$7,1,\"\"),\"\"))","v":""},{"$f":"IF(J66=1,H66*I66,\"\")","v":""},{"$f":"IF(J66=1,Tool!G158,\"\")","v":""},{"$f":"IF(J66=1,IF(Tool!$H158=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=2,S63<=20),2,\"\")","v":""},{"$f":"IF(Bridges!Q66<>\"\",Tool!$D158,\"\")","v":""},{"$f":"IF(Bridges!Q66<>\"\",Tool!$E158,\"\")","v":""},{"$f":"IF(Tool!D158=\"\",\"\",IF(Q66<>\"\",IF(Tool!F158=Tool!$H$8,1,\"\"),\"\"))","v":""},{"$f":"IF(T66=1,R66*S66,\"\")","v":""},{"$f":"IF(T66=1,Tool!$G158,\"\")","v":""},{"$f":"IF(T66=1,IF(Tool!$H158=\"Yes\",$I$98,0),\"\")","v":""},{"$f":"IF(T66=1,IFERROR(VLOOKUP(V66,$H$94:$I$96,2,0),0),\"\")","v":""},"",null,{"$f":"IF(AND(AC63>=2,AC63<=20),2,\"\")","v":""},{"$f":"IF(Bridges!AA66<>\"\",Tool!$D158,\"\")","v":""},{"$f":"IF(Bridges!AA66<>\"\",Tool!$E158,\"\")","v":""},{"$f":"IF(Tool!D158=\"\",\"\",IF(AA66<>\"\",IF(Tool!F158=Tool!$H$9,1,\"\"),\"\"))","v":""},{"$f":"IF(AD66=1,AB66*AC66,\"\")","v":""},{"$f":"IF(AD66=1,Tool!$G158,\"\")","v":""},{"$f":"IF(AD66=1,IF(Tool!$H158=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=2,AM63<=20),2,\"\")","v":""},{"$f":"IF(Bridges!AK66<>\"\",Tool!$D158,\"\")","v":""},{"$f":"IF(Bridges!AK66<>\"\",Tool!$E158,\"\")","v":""},{"$f":"IF(Tool!D158=\"\",\"\",IF(AK66<>\"\",IF(Tool!F158=Tool!$H$10,1,\"\"),\"\"))","v":""},{"$f":"IF(AN66=1,AL66*AM66,\"\")","v":""},{"$f":"IF(AN66=1,Tool!$G158,\"\")","v":""},{"$f":"IF(AN66=1,IF(Tool!$H158=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=3,I63<=20),3,\"\")","v":""},{"$f":"IF(Bridges!G67<>\"\",Tool!$D159,\"\")","v":""},{"$f":"IF(Bridges!G67<>\"\",Tool!$E159,\"\")","v":""},{"$f":"IF(Tool!D159=\"\",\"\",IF(G67<>\"\",IF(Tool!F159=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J67=1,Tool!G159,\"\")","v":""},{"$f":"IF(J67=1,IF(Tool!$H159=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=3,S63<=20),3,\"\")","v":""},{"$f":"IF(Bridges!Q67<>\"\",Tool!$D159,\"\")","v":""},{"$f":"IF(Bridges!Q67<>\"\",Tool!$E159,\"\")","v":""},{"$f":"IF(Tool!D159=\"\",\"\",IF(Q67<>\"\",IF(Tool!F159=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T67=1,Tool!$G159,\"\")","v":""},{"$f":"IF(T67=1,IF(Tool!$H159=\"Yes\",$I$98,0),\"\")","v":""},{"$f":"IF(T67=1,IFERROR(VLOOKUP(V67,$H$94:$I$96,2,0),0),\"\")","v":""},"",null,{"$f":"IF(AND(AC63>=3,AC63<=20),3,\"\")","v":""},{"$f":"IF(Bridges!AA67<>\"\",Tool!$D159,\"\")","v":""},{"$f":"IF(Bridges!AA67<>\"\",Tool!$E159,\"\")","v":""},{"$f":"IF(Tool!D159=\"\",\"\",IF(AA67<>\"\",IF(Tool!F159=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD67=1,Tool!$G159,\"\")","v":""},{"$f":"IF(AD67=1,IF(Tool!$H159=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=3,AM63<=20),3,\"\")","v":""},{"$f":"IF(Bridges!AK67<>\"\",Tool!$D159,\"\")","v":""},{"$f":"IF(Bridges!AK67<>\"\",Tool!$E159,\"\")","v":""},{"$f":"IF(Tool!D159=\"\",\"\",IF(AK67<>\"\",IF(Tool!F159=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN67=1,Tool!$G159,\"\")","v":""},{"$f":"IF(AN67=1,IF(Tool!$H159=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=4,I63<=20),4,\"\")","v":""},{"$f":"IF(Bridges!G68<>\"\",Tool!$D160,\"\")","v":""},{"$f":"IF(Bridges!G68<>\"\",Tool!$E160,\"\")","v":""},{"$f":"IF(Tool!D160=\"\",\"\",IF(G68<>\"\",IF(Tool!F160=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J68=1,Tool!G160,\"\")","v":""},{"$f":"IF(J68=1,IF(Tool!$H160=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=4,S63<=20),4,\"\")","v":""},{"$f":"IF(Bridges!Q68<>\"\",Tool!$D160,\"\")","v":""},{"$f":"IF(Bridges!Q68<>\"\",Tool!$E160,\"\")","v":""},{"$f":"IF(Tool!D160=\"\",\"\",IF(Q68<>\"\",IF(Tool!F160=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T68=1,Tool!$G160,\"\")","v":""},{"$f":"IF(T68=1,IF(Tool!$H160=\"Yes\",$I$98,0),\"\")","v":""},"","",null,{"$f":"IF(AND(AC63>=4,AC63<=20),4,\"\")","v":""},{"$f":"IF(Bridges!AA68<>\"\",Tool!$D160,\"\")","v":""},{"$f":"IF(Bridges!AA68<>\"\",Tool!$E160,\"\")","v":""},{"$f":"IF(Tool!D160=\"\",\"\",IF(AA68<>\"\",IF(Tool!F160=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD68=1,Tool!$G160,\"\")","v":""},{"$f":"IF(AD68=1,IF(Tool!$H160=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=4,AM63<=20),4,\"\")","v":""},{"$f":"IF(Bridges!AK68<>\"\",Tool!$D160,\"\")","v":""},{"$f":"IF(Bridges!AK68<>\"\",Tool!$E160,\"\")","v":""},{"$f":"IF(Tool!D160=\"\",\"\",IF(AK68<>\"\",IF(Tool!F160=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN68=1,Tool!$G160,\"\")","v":""},{"$f":"IF(AN68=1,IF(Tool!$H160=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=5,I63<=20),5,\"\")","v":""},{"$f":"IF(Bridges!G69<>\"\",Tool!$D161,\"\")","v":""},{"$f":"IF(Bridges!G69<>\"\",Tool!$E161,\"\")","v":""},{"$f":"IF(Tool!D161=\"\",\"\",IF(G69<>\"\",IF(Tool!F161=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J69=1,Tool!G161,\"\")","v":""},{"$f":"IF(J69=1,IF(Tool!$H161=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=5,S63<=20),5,\"\")","v":""},{"$f":"IF(Bridges!Q69<>\"\",Tool!$D161,\"\")","v":""},{"$f":"IF(Bridges!Q69<>\"\",Tool!$E161,\"\")","v":""},{"$f":"IF(Tool!D161=\"\",\"\",IF(Q69<>\"\",IF(Tool!F161=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T69=1,Tool!$G161,\"\")","v":""},{"$f":"IF(T69=1,IF(Tool!$H161=\"Yes\",$I$98,0),\"\")","v":""},"","",null,{"$f":"IF(AND(AC63>=5,AC63<=20),5,\"\")","v":""},{"$f":"IF(Bridges!AA69<>\"\",Tool!$D161,\"\")","v":""},{"$f":"IF(Bridges!AA69<>\"\",Tool!$E161,\"\")","v":""},{"$f":"IF(Tool!D161=\"\",\"\",IF(AA69<>\"\",IF(Tool!F161=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD69=1,Tool!$G161,\"\")","v":""},{"$f":"IF(AD69=1,IF(Tool!$H161=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=5,AM63<=20),5,\"\")","v":""},{"$f":"IF(Bridges!AK69<>\"\",Tool!$D161,\"\")","v":""},{"$f":"IF(Bridges!AK69<>\"\",Tool!$E161,\"\")","v":""},{"$f":"IF(Tool!D161=\"\",\"\",IF(AK69<>\"\",IF(Tool!F161=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN69=1,Tool!$G161,\"\")","v":""},{"$f":"IF(AN69=1,IF(Tool!$H161=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=6,I63<=20),6,\"\")","v":""},{"$f":"IF(Bridges!G70<>\"\",Tool!$D162,\"\")","v":""},{"$f":"IF(Bridges!G70<>\"\",Tool!$E162,\"\")","v":""},{"$f":"IF(Tool!D162=\"\",\"\",IF(G70<>\"\",IF(Tool!F162=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J70=1,Tool!G162,\"\")","v":""},{"$f":"IF(J70=1,IF(Tool!$H162=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=6,S63<=20),6,\"\")","v":""},{"$f":"IF(Bridges!Q70<>\"\",Tool!$D162,\"\")","v":""},{"$f":"IF(Bridges!Q70<>\"\",Tool!$E162,\"\")","v":""},{"$f":"IF(Tool!D162=\"\",\"\",IF(Q70<>\"\",IF(Tool!F162=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T70=1,Tool!$G162,\"\")","v":""},{"$f":"IF(T70=1,IF(Tool!$H162=\"Yes\",$I$98,0),\"\")","v":""},"","",null,{"$f":"IF(AND(AC63>=6,AC63<=20),6,\"\")","v":""},{"$f":"IF(Bridges!AA70<>\"\",Tool!$D162,\"\")","v":""},{"$f":"IF(Bridges!AA70<>\"\",Tool!$E162,\"\")","v":""},{"$f":"IF(Tool!D162=\"\",\"\",IF(AA70<>\"\",IF(Tool!F162=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD70=1,Tool!$G162,\"\")","v":""},{"$f":"IF(AD70=1,IF(Tool!$H162=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=6,AM63<=20),6,\"\")","v":""},{"$f":"IF(Bridges!AK70<>\"\",Tool!$D162,\"\")","v":""},{"$f":"IF(Bridges!AK70<>\"\",Tool!$E162,\"\")","v":""},{"$f":"IF(Tool!D162=\"\",\"\",IF(AK70<>\"\",IF(Tool!F162=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN70=1,Tool!$G162,\"\")","v":""},{"$f":"IF(AN70=1,IF(Tool!$H162=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=7,I63<=20),7,\"\")","v":""},{"$f":"IF(Bridges!G71<>\"\",Tool!$D163,\"\")","v":""},{"$f":"IF(Bridges!G71<>\"\",Tool!$E163,\"\")","v":""},{"$f":"IF(Tool!D163=\"\",\"\",IF(G71<>\"\",IF(Tool!F163=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J71=1,Tool!G163,\"\")","v":""},{"$f":"IF(J71=1,IF(Tool!$H163=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=7,S63<=20),7,\"\")","v":""},{"$f":"IF(Bridges!Q71<>\"\",Tool!$D163,\"\")","v":""},{"$f":"IF(Bridges!Q71<>\"\",Tool!$E163,\"\")","v":""},{"$f":"IF(Tool!D163=\"\",\"\",IF(Q71<>\"\",IF(Tool!F163=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T71=1,Tool!$G163,\"\")","v":""},{"$f":"IF(T71=1,IF(Tool!$H163=\"Yes\",$I$98,0),\"\")","v":""},"","",null,{"$f":"IF(AND(AC63>=7,AC63<=20),7,\"\")","v":""},{"$f":"IF(Bridges!AA71<>\"\",Tool!$D163,\"\")","v":""},{"$f":"IF(Bridges!AA71<>\"\",Tool!$E163,\"\")","v":""},{"$f":"IF(Tool!D163=\"\",\"\",IF(AA71<>\"\",IF(Tool!F163=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD71=1,Tool!$G163,\"\")","v":""},{"$f":"IF(AD71=1,IF(Tool!$H163=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=7,AM63<=20),7,\"\")","v":""},{"$f":"IF(Bridges!AK71<>\"\",Tool!$D163,\"\")","v":""},{"$f":"IF(Bridges!AK71<>\"\",Tool!$E163,\"\")","v":""},{"$f":"IF(Tool!D163=\"\",\"\",IF(AK71<>\"\",IF(Tool!F163=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN71=1,Tool!$G163,\"\")","v":""},{"$f":"IF(AN71=1,IF(Tool!$H163=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=8,I63<=20),8,\"\")","v":""},{"$f":"IF(Bridges!G72<>\"\",Tool!$D164,\"\")","v":""},{"$f":"IF(Bridges!G72<>\"\",Tool!$E164,\"\")","v":""},{"$f":"IF(Tool!D164=\"\",\"\",IF(G72<>\"\",IF(Tool!F164=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J72=1,Tool!G164,\"\")","v":""},{"$f":"IF(J72=1,IF(Tool!$H164=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=8,S63<=20),8,\"\")","v":""},{"$f":"IF(Bridges!Q72<>\"\",Tool!$D164,\"\")","v":""},{"$f":"IF(Bridges!Q72<>\"\",Tool!$E164,\"\")","v":""},{"$f":"IF(Tool!D164=\"\",\"\",IF(Q72<>\"\",IF(Tool!F164=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T72=1,Tool!$G164,\"\")","v":""},{"$f":"IF(T72=1,IF(Tool!$H164=\"Yes\",$I$98,0),\"\")","v":""},"","",null,{"$f":"IF(AND(AC63>=8,AC63<=20),8,\"\")","v":""},{"$f":"IF(Bridges!AA72<>\"\",Tool!$D164,\"\")","v":""},{"$f":"IF(Bridges!AA72<>\"\",Tool!$E164,\"\")","v":""},{"$f":"IF(Tool!D164=\"\",\"\",IF(AA72<>\"\",IF(Tool!F164=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD72=1,Tool!$G164,\"\")","v":""},{"$f":"IF(AD72=1,IF(Tool!$H164=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=8,AM63<=20),8,\"\")","v":""},{"$f":"IF(Bridges!AK72<>\"\",Tool!$D164,\"\")","v":""},{"$f":"IF(Bridges!AK72<>\"\",Tool!$E164,\"\")","v":""},{"$f":"IF(Tool!D164=\"\",\"\",IF(AK72<>\"\",IF(Tool!F164=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN72=1,Tool!$G164,\"\")","v":""},{"$f":"IF(AN72=1,IF(Tool!$H164=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=9,I63<=20),9,\"\")","v":""},{"$f":"IF(Bridges!G73<>\"\",Tool!$D165,\"\")","v":""},{"$f":"IF(Bridges!G73<>\"\",Tool!$E165,\"\")","v":""},{"$f":"IF(Tool!D165=\"\",\"\",IF(G73<>\"\",IF(Tool!F165=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J73=1,Tool!G165,\"\")","v":""},{"$f":"IF(J73=1,IF(Tool!$H165=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=9,S63<=20),9,\"\")","v":""},{"$f":"IF(Bridges!Q73<>\"\",Tool!$D165,\"\")","v":""},{"$f":"IF(Bridges!Q73<>\"\",Tool!$E165,\"\")","v":""},{"$f":"IF(Tool!D165=\"\",\"\",IF(Q73<>\"\",IF(Tool!F165=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T73=1,Tool!$G165,\"\")","v":""},{"$f":"IF(T73=1,IF(Tool!$H165=\"Yes\",$I$98,0),\"\")","v":""},"","",null,{"$f":"IF(AND(AC63>=9,AC63<=20),9,\"\")","v":""},{"$f":"IF(Bridges!AA73<>\"\",Tool!$D165,\"\")","v":""},{"$f":"IF(Bridges!AA73<>\"\",Tool!$E165,\"\")","v":""},{"$f":"IF(Tool!D165=\"\",\"\",IF(AA73<>\"\",IF(Tool!F165=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD73=1,Tool!$G165,\"\")","v":""},{"$f":"IF(AD73=1,IF(Tool!$H165=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=9,AM63<=20),9,\"\")","v":""},{"$f":"IF(Bridges!AK73<>\"\",Tool!$D165,\"\")","v":""},{"$f":"IF(Bridges!AK73<>\"\",Tool!$E165,\"\")","v":""},{"$f":"IF(Tool!D165=\"\",\"\",IF(AK73<>\"\",IF(Tool!F165=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN73=1,Tool!$G165,\"\")","v":""},{"$f":"IF(AN73=1,IF(Tool!$H165=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=10,I63<=20),10,\"\")","v":""},{"$f":"IF(Bridges!G74<>\"\",Tool!$D166,\"\")","v":""},{"$f":"IF(Bridges!G74<>\"\",Tool!$E166,\"\")","v":""},{"$f":"IF(Tool!D166=\"\",\"\",IF(G74<>\"\",IF(Tool!F166=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J74=1,Tool!G166,\"\")","v":""},{"$f":"IF(J74=1,IF(Tool!$H166=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=10,S63<=20),10,\"\")","v":""},{"$f":"IF(Bridges!Q74<>\"\",Tool!$D166,\"\")","v":""},{"$f":"IF(Bridges!Q74<>\"\",Tool!$E166,\"\")","v":""},{"$f":"IF(Tool!D166=\"\",\"\",IF(Q74<>\"\",IF(Tool!F166=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T74=1,Tool!$G166,\"\")","v":""},{"$f":"IF(T74=1,IF(Tool!$H166=\"Yes\",$I$98,0),\"\")","v":""},"","",null,{"$f":"IF(AND(AC63>=10,AC63<=20),10,\"\")","v":""},{"$f":"IF(Bridges!AA74<>\"\",Tool!$D166,\"\")","v":""},{"$f":"IF(Bridges!AA74<>\"\",Tool!$E166,\"\")","v":""},{"$f":"IF(Tool!D166=\"\",\"\",IF(AA74<>\"\",IF(Tool!F166=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD74=1,Tool!$G166,\"\")","v":""},{"$f":"IF(AD74=1,IF(Tool!$H166=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=10,AM63<=20),10,\"\")","v":""},{"$f":"IF(Bridges!AK74<>\"\",Tool!$D166,\"\")","v":""},{"$f":"IF(Bridges!AK74<>\"\",Tool!$E166,\"\")","v":""},{"$f":"IF(Tool!D166=\"\",\"\",IF(AK74<>\"\",IF(Tool!F166=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN74=1,Tool!$G166,\"\")","v":""},{"$f":"IF(AN74=1,IF(Tool!$H166=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=11,I63<=20),11,\"\")","v":""},{"$f":"IF(Bridges!G75<>\"\",Tool!$D167,\"\")","v":""},{"$f":"IF(Bridges!G75<>\"\",Tool!$E167,\"\")","v":""},{"$f":"IF(Tool!D167=\"\",\"\",IF(G75<>\"\",IF(Tool!F167=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J75=1,Tool!G167,\"\")","v":""},{"$f":"IF(J75=1,IF(Tool!$H167=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=11,S63<=20),11,\"\")","v":""},{"$f":"IF(Bridges!Q75<>\"\",Tool!$D167,\"\")","v":""},{"$f":"IF(Bridges!Q75<>\"\",Tool!$E167,\"\")","v":""},{"$f":"IF(Tool!D167=\"\",\"\",IF(Q75<>\"\",IF(Tool!F167=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T75=1,Tool!$G167,\"\")","v":""},{"$f":"IF(T75=1,IF(Tool!$H167=\"Yes\",$I$98,0),\"\")","v":""},"","",null,{"$f":"IF(AND(AC63>=11,AC63<=20),11,\"\")","v":""},{"$f":"IF(Bridges!AA75<>\"\",Tool!$D167,\"\")","v":""},{"$f":"IF(Bridges!AA75<>\"\",Tool!$E167,\"\")","v":""},{"$f":"IF(Tool!D167=\"\",\"\",IF(AA75<>\"\",IF(Tool!F167=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD75=1,Tool!$G167,\"\")","v":""},{"$f":"IF(AD75=1,IF(Tool!$H167=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=11,AM63<=20),11,\"\")","v":""},{"$f":"IF(Bridges!AK75<>\"\",Tool!$D167,\"\")","v":""},{"$f":"IF(Bridges!AK75<>\"\",Tool!$E167,\"\")","v":""},{"$f":"IF(Tool!D167=\"\",\"\",IF(AK75<>\"\",IF(Tool!F167=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN75=1,Tool!$G167,\"\")","v":""},{"$f":"IF(AN75=1,IF(Tool!$H167=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=12,I63<=20),12,\"\")","v":""},{"$f":"IF(Bridges!G76<>\"\",Tool!$D168,\"\")","v":""},{"$f":"IF(Bridges!G76<>\"\",Tool!$E168,\"\")","v":""},{"$f":"IF(Tool!D168=\"\",\"\",IF(G76<>\"\",IF(Tool!F168=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J76=1,Tool!G168,\"\")","v":""},{"$f":"IF(J76=1,IF(Tool!$H168=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=12,S63<=20),12,\"\")","v":""},{"$f":"IF(Bridges!Q76<>\"\",Tool!$D168,\"\")","v":""},{"$f":"IF(Bridges!Q76<>\"\",Tool!$E168,\"\")","v":""},{"$f":"IF(Tool!D168=\"\",\"\",IF(Q76<>\"\",IF(Tool!F168=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T76=1,Tool!$G168,\"\")","v":""},{"$f":"IF(T76=1,IF(Tool!$H168=\"Yes\",$I$98,0),\"\")","v":""},"","",null,{"$f":"IF(AND(AC63>=12,AC63<=20),12,\"\")","v":""},{"$f":"IF(Bridges!AA76<>\"\",Tool!$D168,\"\")","v":""},{"$f":"IF(Bridges!AA76<>\"\",Tool!$E168,\"\")","v":""},{"$f":"IF(Tool!D168=\"\",\"\",IF(AA76<>\"\",IF(Tool!F168=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD76=1,Tool!$G168,\"\")","v":""},{"$f":"IF(AD76=1,IF(Tool!$H168=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=12,AM63<=20),12,\"\")","v":""},{"$f":"IF(Bridges!AK76<>\"\",Tool!$D168,\"\")","v":""},{"$f":"IF(Bridges!AK76<>\"\",Tool!$E168,\"\")","v":""},{"$f":"IF(Tool!D168=\"\",\"\",IF(AK76<>\"\",IF(Tool!F168=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN76=1,Tool!$G168,\"\")","v":""},{"$f":"IF(AN76=1,IF(Tool!$H168=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=13,I63<=20),13,\"\")","v":""},{"$f":"IF(Bridges!G77<>\"\",Tool!$D169,\"\")","v":""},{"$f":"IF(Bridges!G77<>\"\",Tool!$E169,\"\")","v":""},{"$f":"IF(Tool!D169=\"\",\"\",IF(G77<>\"\",IF(Tool!F169=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J77=1,Tool!G169,\"\")","v":""},{"$f":"IF(J77=1,IF(Tool!$H169=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=13,S63<=20),13,\"\")","v":""},{"$f":"IF(Bridges!Q77<>\"\",Tool!$D169,\"\")","v":""},{"$f":"IF(Bridges!Q77<>\"\",Tool!$E169,\"\")","v":""},{"$f":"IF(Tool!D169=\"\",\"\",IF(Q77<>\"\",IF(Tool!F169=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T77=1,Tool!$G169,\"\")","v":""},{"$f":"IF(T77=1,IF(Tool!$H169=\"Yes\",$I$98,0),\"\")","v":""},"","",null,{"$f":"IF(AND(AC63>=13,AC63<=20),13,\"\")","v":""},{"$f":"IF(Bridges!AA77<>\"\",Tool!$D169,\"\")","v":""},{"$f":"IF(Bridges!AA77<>\"\",Tool!$E169,\"\")","v":""},{"$f":"IF(Tool!D169=\"\",\"\",IF(AA77<>\"\",IF(Tool!F169=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD77=1,Tool!$G169,\"\")","v":""},{"$f":"IF(AD77=1,IF(Tool!$H169=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=13,AM63<=20),13,\"\")","v":""},{"$f":"IF(Bridges!AK77<>\"\",Tool!$D169,\"\")","v":""},{"$f":"IF(Bridges!AK77<>\"\",Tool!$E169,\"\")","v":""},{"$f":"IF(Tool!D169=\"\",\"\",IF(AK77<>\"\",IF(Tool!F169=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN77=1,Tool!$G169,\"\")","v":""},{"$f":"IF(AN77=1,IF(Tool!$H169=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=14,I63<=20),14,\"\")","v":""},{"$f":"IF(Bridges!G78<>\"\",Tool!$D170,\"\")","v":""},{"$f":"IF(Bridges!G78<>\"\",Tool!$E170,\"\")","v":""},{"$f":"IF(Tool!D170=\"\",\"\",IF(G78<>\"\",IF(Tool!F170=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J78=1,Tool!G170,\"\")","v":""},{"$f":"IF(J78=1,IF(Tool!$H170=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=14,S63<=20),14,\"\")","v":""},{"$f":"IF(Bridges!Q78<>\"\",Tool!$D170,\"\")","v":""},{"$f":"IF(Bridges!Q78<>\"\",Tool!$E170,\"\")","v":""},{"$f":"IF(Tool!D170=\"\",\"\",IF(Q78<>\"\",IF(Tool!F170=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T78=1,Tool!$G170,\"\")","v":""},{"$f":"IF(T78=1,IF(Tool!$H170=\"Yes\",$I$98,0),\"\")","v":""},"","",null,{"$f":"IF(AND(AC63>=14,AC63<=20),14,\"\")","v":""},{"$f":"IF(Bridges!AA78<>\"\",Tool!$D170,\"\")","v":""},{"$f":"IF(Bridges!AA78<>\"\",Tool!$E170,\"\")","v":""},{"$f":"IF(Tool!D170=\"\",\"\",IF(AA78<>\"\",IF(Tool!F170=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD78=1,Tool!$G170,\"\")","v":""},{"$f":"IF(AD78=1,IF(Tool!$H170=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=14,AM63<=20),14,\"\")","v":""},{"$f":"IF(Bridges!AK78<>\"\",Tool!$D170,\"\")","v":""},{"$f":"IF(Bridges!AK78<>\"\",Tool!$E170,\"\")","v":""},{"$f":"IF(Tool!D170=\"\",\"\",IF(AK78<>\"\",IF(Tool!F170=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN78=1,Tool!$G170,\"\")","v":""},{"$f":"IF(AN78=1,IF(Tool!$H170=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=15,I63<=20),15,\"\")","v":""},{"$f":"IF(Bridges!G79<>\"\",Tool!$D171,\"\")","v":""},{"$f":"IF(Bridges!G79<>\"\",Tool!$E171,\"\")","v":""},{"$f":"IF(Tool!D171=\"\",\"\",IF(G79<>\"\",IF(Tool!F171=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J79=1,Tool!G171,\"\")","v":""},{"$f":"IF(J79=1,IF(Tool!$H171=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=15,S63<=20),15,\"\")","v":""},{"$f":"IF(Bridges!Q79<>\"\",Tool!$D171,\"\")","v":""},{"$f":"IF(Bridges!Q79<>\"\",Tool!$E171,\"\")","v":""},{"$f":"IF(Tool!D171=\"\",\"\",IF(Q79<>\"\",IF(Tool!F171=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T79=1,Tool!$G171,\"\")","v":""},{"$f":"IF(T79=1,IF(Tool!$H171=\"Yes\",$I$98,0),\"\")","v":""},"","",null,{"$f":"IF(AND(AC63>=15,AC63<=20),15,\"\")","v":""},{"$f":"IF(Bridges!AA79<>\"\",Tool!$D171,\"\")","v":""},{"$f":"IF(Bridges!AA79<>\"\",Tool!$E171,\"\")","v":""},{"$f":"IF(Tool!D171=\"\",\"\",IF(AA79<>\"\",IF(Tool!F171=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD79=1,Tool!$G171,\"\")","v":""},{"$f":"IF(AD79=1,IF(Tool!$H171=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=15,AM63<=20),15,\"\")","v":""},{"$f":"IF(Bridges!AK79<>\"\",Tool!$D171,\"\")","v":""},{"$f":"IF(Bridges!AK79<>\"\",Tool!$E171,\"\")","v":""},{"$f":"IF(Tool!D171=\"\",\"\",IF(AK79<>\"\",IF(Tool!F171=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN79=1,Tool!$G171,\"\")","v":""},{"$f":"IF(AN79=1,IF(Tool!$H171=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=16,I63<=20),16,\"\")","v":""},{"$f":"IF(Bridges!G80<>\"\",Tool!$D172,\"\")","v":""},{"$f":"IF(Bridges!G80<>\"\",Tool!$E172,\"\")","v":""},{"$f":"IF(Tool!D172=\"\",\"\",IF(G80<>\"\",IF(Tool!F172=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J80=1,Tool!G172,\"\")","v":""},{"$f":"IF(J80=1,IF(Tool!$H172=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=16,S63<=20),16,\"\")","v":""},{"$f":"IF(Bridges!Q80<>\"\",Tool!$D172,\"\")","v":""},{"$f":"IF(Bridges!Q80<>\"\",Tool!$E172,\"\")","v":""},{"$f":"IF(Tool!D172=\"\",\"\",IF(Q80<>\"\",IF(Tool!F172=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T80=1,Tool!$G172,\"\")","v":""},{"$f":"IF(T80=1,IF(Tool!$H172=\"Yes\",$I$98,0),\"\")","v":""},"","",null,{"$f":"IF(AND(AC63>=16,AC63<=20),16,\"\")","v":""},{"$f":"IF(Bridges!AA80<>\"\",Tool!$D172,\"\")","v":""},{"$f":"IF(Bridges!AA80<>\"\",Tool!$E172,\"\")","v":""},{"$f":"IF(Tool!D172=\"\",\"\",IF(AA80<>\"\",IF(Tool!F172=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD80=1,Tool!$G172,\"\")","v":""},{"$f":"IF(AD80=1,IF(Tool!$H172=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=16,AM63<=20),16,\"\")","v":""},{"$f":"IF(Bridges!AK80<>\"\",Tool!$D172,\"\")","v":""},{"$f":"IF(Bridges!AK80<>\"\",Tool!$E172,\"\")","v":""},{"$f":"IF(Tool!D172=\"\",\"\",IF(AK80<>\"\",IF(Tool!F172=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN80=1,Tool!$G172,\"\")","v":""},{"$f":"IF(AN80=1,IF(Tool!$H172=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=17,I63<=20),17,\"\")","v":""},{"$f":"IF(Bridges!G81<>\"\",Tool!$D173,\"\")","v":""},{"$f":"IF(Bridges!G81<>\"\",Tool!$E173,\"\")","v":""},{"$f":"IF(Tool!D173=\"\",\"\",IF(G81<>\"\",IF(Tool!F173=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J81=1,Tool!G173,\"\")","v":""},{"$f":"IF(J81=1,IF(Tool!$H173=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=17,S63<=20),17,\"\")","v":""},{"$f":"IF(Bridges!Q81<>\"\",Tool!$D173,\"\")","v":""},{"$f":"IF(Bridges!Q81<>\"\",Tool!$E173,\"\")","v":""},{"$f":"IF(Tool!D173=\"\",\"\",IF(Q81<>\"\",IF(Tool!F173=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T81=1,Tool!$G173,\"\")","v":""},{"$f":"IF(T81=1,IF(Tool!$H173=\"Yes\",$I$98,0),\"\")","v":""},"","",null,{"$f":"IF(AND(AC63>=17,AC63<=20),17,\"\")","v":""},{"$f":"IF(Bridges!AA81<>\"\",Tool!$D173,\"\")","v":""},{"$f":"IF(Bridges!AA81<>\"\",Tool!$E173,\"\")","v":""},{"$f":"IF(Tool!D173=\"\",\"\",IF(AA81<>\"\",IF(Tool!F173=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD81=1,Tool!$G173,\"\")","v":""},{"$f":"IF(AD81=1,IF(Tool!$H173=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=17,AM63<=20),17,\"\")","v":""},{"$f":"IF(Bridges!AK81<>\"\",Tool!$D173,\"\")","v":""},{"$f":"IF(Bridges!AK81<>\"\",Tool!$E173,\"\")","v":""},{"$f":"IF(Tool!D173=\"\",\"\",IF(AK81<>\"\",IF(Tool!F173=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN81=1,Tool!$G173,\"\")","v":""},{"$f":"IF(AN81=1,IF(Tool!$H173=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=18,I63<=20),18,\"\")","v":""},{"$f":"IF(Bridges!G82<>\"\",Tool!$D174,\"\")","v":""},{"$f":"IF(Bridges!G82<>\"\",Tool!$E174,\"\")","v":""},{"$f":"IF(Tool!D174=\"\",\"\",IF(G82<>\"\",IF(Tool!F174=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J82=1,Tool!G174,\"\")","v":""},{"$f":"IF(J82=1,IF(Tool!$H174=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=18,S63<=20),18,\"\")","v":""},{"$f":"IF(Bridges!Q82<>\"\",Tool!$D174,\"\")","v":""},{"$f":"IF(Bridges!Q82<>\"\",Tool!$E174,\"\")","v":""},{"$f":"IF(Tool!D174=\"\",\"\",IF(Q82<>\"\",IF(Tool!F174=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T82=1,Tool!$G174,\"\")","v":""},{"$f":"IF(T82=1,IF(Tool!$H174=\"Yes\",$I$98,0),\"\")","v":""},"","",null,{"$f":"IF(AND(AC63>=18,AC63<=20),18,\"\")","v":""},{"$f":"IF(Bridges!AA82<>\"\",Tool!$D174,\"\")","v":""},{"$f":"IF(Bridges!AA82<>\"\",Tool!$E174,\"\")","v":""},{"$f":"IF(Tool!D174=\"\",\"\",IF(AA82<>\"\",IF(Tool!F174=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD82=1,Tool!$G174,\"\")","v":""},{"$f":"IF(AD82=1,IF(Tool!$H174=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=18,AM63<=20),18,\"\")","v":""},{"$f":"IF(Bridges!AK82<>\"\",Tool!$D174,\"\")","v":""},{"$f":"IF(Bridges!AK82<>\"\",Tool!$E174,\"\")","v":""},{"$f":"IF(Tool!D174=\"\",\"\",IF(AK82<>\"\",IF(Tool!F174=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN82=1,Tool!$G174,\"\")","v":""},{"$f":"IF(AN82=1,IF(Tool!$H174=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63>=19,I63<=20),19,\"\")","v":""},{"$f":"IF(Bridges!G83<>\"\",Tool!$D175,\"\")","v":""},{"$f":"IF(Bridges!G83<>\"\",Tool!$E175,\"\")","v":""},{"$f":"IF(Tool!D175=\"\",\"\",IF(G83<>\"\",IF(Tool!F175=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J83=1,Tool!G175,\"\")","v":""},{"$f":"IF(J83=1,IF(Tool!$H175=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63>=19,S63<=20),19,\"\")","v":""},{"$f":"IF(Bridges!Q83<>\"\",Tool!$D175,\"\")","v":""},{"$f":"IF(Bridges!Q83<>\"\",Tool!$E175,\"\")","v":""},{"$f":"IF(Tool!D175=\"\",\"\",IF(Q83<>\"\",IF(Tool!F175=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T83=1,Tool!$G175,\"\")","v":""},{"$f":"IF(T83=1,IF(Tool!$H175=\"Yes\",$I$98,0),\"\")","v":""},"","",null,{"$f":"IF(AND(AC63>=19,AC63<=20),19,\"\")","v":""},{"$f":"IF(Bridges!AA83<>\"\",Tool!$D175,\"\")","v":""},{"$f":"IF(Bridges!AA83<>\"\",Tool!$E175,\"\")","v":""},{"$f":"IF(Tool!D175=\"\",\"\",IF(AA83<>\"\",IF(Tool!F175=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD83=1,Tool!$G175,\"\")","v":""},{"$f":"IF(AD83=1,IF(Tool!$H175=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63>=19,AM63<=20),19,\"\")","v":""},{"$f":"IF(Bridges!AK83<>\"\",Tool!$D175,\"\")","v":""},{"$f":"IF(Bridges!AK83<>\"\",Tool!$E175,\"\")","v":""},{"$f":"IF(Tool!D175=\"\",\"\",IF(AK83<>\"\",IF(Tool!F175=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN83=1,Tool!$G175,\"\")","v":""},{"$f":"IF(AN83=1,IF(Tool!$H175=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,{"$f":"IF(AND(I63=20),20,\"\")","v":""},{"$f":"IF(Bridges!G84<>\"\",Tool!$D176,\"\")","v":""},{"$f":"IF(Bridges!G84<>\"\",Tool!$E176,\"\")","v":""},{"$f":"IF(Tool!D176=\"\",\"\",IF(G84<>\"\",IF(Tool!F176=Tool!$H$7,1,\"\"),\"\"))","v":""},"",{"$f":"IF(J84=1,Tool!G176,\"\")","v":""},{"$f":"IF(J84=1,IF(Tool!$H176=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(S63=20),20,\"\")","v":""},{"$f":"IF(Bridges!Q84<>\"\",Tool!$D176,\"\")","v":""},{"$f":"IF(Bridges!Q84<>\"\",Tool!$E176,\"\")","v":""},{"$f":"IF(Tool!D176=\"\",\"\",IF(Q84<>\"\",IF(Tool!F176=Tool!$H$8,1,\"\"),\"\"))","v":""},"",{"$f":"IF(T84=1,Tool!$G176,\"\")","v":""},{"$f":"IF(T84=1,IF(Tool!$H176=\"Yes\",$I$98,0),\"\")","v":""},"","",null,{"$f":"IF(AND(AC63=20),20,\"\")","v":""},{"$f":"IF(Bridges!AA84<>\"\",Tool!$D176,\"\")","v":""},{"$f":"IF(Bridges!AA84<>\"\",Tool!$E176,\"\")","v":""},{"$f":"IF(Tool!D176=\"\",\"\",IF(AA84<>\"\",IF(Tool!F176=Tool!$H$9,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AD84=1,Tool!$G176,\"\")","v":""},{"$f":"IF(AD84=1,IF(Tool!$H176=\"Yes\",$I$98,0),\"\")","v":""},"",null,null,{"$f":"IF(AND(AM63=20),20,\"\")","v":""},{"$f":"IF(Bridges!AK84<>\"\",Tool!$D176,\"\")","v":""},{"$f":"IF(Bridges!AK84<>\"\",Tool!$E176,\"\")","v":""},{"$f":"IF(Tool!D176=\"\",\"\",IF(AK84<>\"\",IF(Tool!F176=Tool!$H$10,1,\"\"),\"\"))","v":""},"",{"$f":"IF(AN84=1,Tool!$G176,\"\")","v":""},{"$f":"IF(AN84=1,IF(Tool!$H176=\"Yes\",$I$98,0),\"\")","v":""},"",null,0]
[null,null,null,null,null,null,null,null,null,"Number:",{"$f":"SUM(J65:J84)","v":0},null,null,null,null,null,null,null,null,"Number:",{"$f":"SUM(T65:T84)","v":0},null,null,null,null,null,null,null,null,"Number:",{"$f":"SUM(AD65:AD84)","v":0},null,null,null,null,null,null,null,null,"Number:",{"$f":"SUM(AN65:AN84)","v":0}]
[null,null,null,null,null,null,null,null,null,"Total Area:",{"$f":"SUM(K65:K84)","v":0},null,null,null,null,null,null,null,null,"Total Area:",{"$f":"SUM(U65:U84)","v":0},null,null,null,null,null,null,null,null,"Total Area:",{"$f":"SUM(AE65:AE84)","v":0},null,null,null,null,null,null,null,null,"Total Area:",{"$f":"SUM(AO65:AO84)","v":0}]
[null,null,null,null,null,null,null,null,null,"Contingency",{"$f":"IFERROR(SUMPRODUCT(K65:K84,N65:N84)/SUM(K65:K84),0)","v":0},null,null,null,null,null,null,null,null,"Contingency",{"$f":"IFERROR(SUMPRODUCT(U65:U84,Y65:Y84)/SUM(U65:U84),0)","v":0},null,null,null,null,null,null,null,null,"Contingency",{"$f":"IFERROR(SUMPRODUCT(AE65:AE84,AH65:AH84)/SUM(AE65:AE84),0)","v":0},null,null,null,null,null,null,null,null,"Contingency",{"$f":"IFERROR(SUMPRODUCT(AO65:AO84,AR65:AR84)/SUM(AO65:AO84),0)","v":0}]
[null,null,null,null,null,null,null,null,null,"Contingency Final:",{"$f":"IFERROR(((K87*K86)+(K57*K58))/(K57+K86),0)","v":0},null,null,null,null,null,null,null,null,"Contingency Final:",{"$f":"IFERROR(((U87*U86)+(U57*U58))/(U57+U86),0)","v":0},null,null,null,null,null,null,null,null,"Contingency Final:",{"$f":"IFERROR(((AE87*AE86)+(AE57*AE58))/(AE57+AE86),0)","v":0},null,null,null,null,null,null,null,null,"Contingency Final:",{"$f":"IFERROR(((AO87*AO86)+(AO57*AO58))/(AO57+AO86),0)","v":0}]
[]
[null,null,null,null,null,null,null,null,"Bridge Widenings:",{"$f":"SUM(L35:L54)+SUM(V35:V54)+SUM(AP35:AP54)","v":0}]
[null,null,null,null,null,null,null,null,"New Bridges:",{"$f":"SUM(L65:L84)+SUM(V65:V84)+SUM(AF65:AF84)","v":0}]
[null,null,null,null,null,null,null,null,"Total:",{"$f":"J90+J91","v":0}]
[]
[null,null,null,null,null,null,null,"Detour/New Location",0]
[null,null,null,null,null,null,null,"ABC/CMGC",1]
[null,null,null,null,null,null,null,"Stage Construction",0.25,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"BRIDGES"]
[]
[null,null,null,null,null,null,null,"Foundation",0.25]

{"sheet":"Utilities","index":35,"n_rows":78,"n_cols":17,"rows_kept":78,"cut":false,"hidden":true,"merged":[]}
[]
["ROW Impacts","Average Project Length","Average"]
["Very Low Impacts",{"$f":"AVERAGEIF($P$17:$P$78,1,$H$17:$H$78)","v":2.3735833333333329},{"$f":"(SUMPRODUCT(IF($P$17:$P$78=1,1,0),$O$17:$O$78,$H$17:$H$78))/SUMIF($P$17:$P$78,1,$H$17:$H$78)","v":102822.83716237367}]
["Low Impacts",{"$f":"AVERAGEIF($P$17:$P$78,2,$H$17:$H$78)","v":2.1921666666666666},{"$f":"(SUMPRODUCT(IF($P$17:$P$78=2,1,0),$O$17:$O$78,$H$17:$H$78))/SUMIF($P$17:$P$78,2,$H$17:$H$78)","v":574276.89136055252}]
["Moderate Impacts",{"$f":"AVERAGEIF($P$17:$P$78,3,$H$17:$H$78)","v":2.718461538461538},{"$f":"(SUMPRODUCT(IF($P$17:$P$78=3,1,0),$O$17:$O$78,$H$17:$H$78))/SUMIF($P$17:$P$78,3,$H$17:$H$78)","v":1670674.9128553781}]
["High Impacts",{"$f":"AVERAGEIF($P$17:$P$78,4,$H$17:$H$78)","v":1.3207692307692309},{"$f":"(SUMPRODUCT(IF($P$17:$P$78=4,1,0),$O$17:$O$78,$H$17:$H$78))/SUMIF($P$17:$P$78,4,$H$17:$H$78)","v":4393285.7384400507}]
["Very High Impacts",{"$f":"AVERAGEIF($P$17:$P$78,5,$H$17:$H$78)","v":1.7585833333333334},{"$f":"(SUMPRODUCT(IF($P$17:$P$78=5,1,0),$O$17:$O$78,$H$17:$H$78))/SUMIF($P$17:$P$78,5,$H$17:$H$78)","v":8739749.7168796733}]
[]
["Utility Impacts","Average Project Length","Distressed"]
["Very Low",{"$f":"B3","v":2.3735833333333329},{"$f":"MROUND(C3,10000)","v":100000}]
["Low",{"$f":"B4","v":2.1921666666666666},{"$f":"MROUND(C4,10000)","v":570000}]
["Moderate",{"$f":"B5","v":2.718461538461538},1670000]
["High",{"$f":"B6","v":1.3207692307692309},4390000]
["Very High",{"$f":"B7","v":1.7585833333333334},8740000]
[]
["PIN","County","Route","Project Description","PPRM SCOPE OF WORK","Project Type Work","Program Type","Length","ROW Estimate Date","Years","Utility Estimate","Utility Estimate Date","Years","Inflated Utility Estimate","Utility Cost/Mile","Group","Cumulative Length"]
[100286,"Sumner","SR-109 ","North of the Cumberland River Bridge to SR-109 Bypass South of Gallatin","Widen from 2-ln to 4/5-ln","Widen","Legislative",1.3,"2014-04-24",{"$f":"IFERROR(YEAR(TODAY())-YEAR(I17),\"\")","v":11},7516166,"2011-10-24",{"$f":"IFERROR(YEAR(TODAY())-YEAR(L17),\"\")","v":14},{"$f":"IFERROR(((VLOOKUP(M17,'Const Index'!C:E,3,0)*(M17)+1)*K17),K17)","v":15407588.801653968},{"$f":"N17/H17","v":11851991.385887668},5]
[112152.03,"Hamilton","SR-317 ","(Bonny Oaks Drive), From Near Adamson Circle to West of Bonnyshire Drive (IA) (#2 Priority)~","Widen to 4-ln and 12' lanes with a 12' continuous center turn lane and  5' sidewalks on either side or a single 10' multiuse path.","Widen","Legislative",0.95099999999999996,"2020-08-13",5,7392000,"2020-08-13",5,{"$f":"IFERROR(((VLOOKUP(M18,'Const Index'!C:E,3,0)*(M18)+1)*K18),K18)","v":11106377.495248172},11678630.38406748,5]
[112152.04,"Hamilton","SR-317 ","(Bonny Oaks Drive), From West of Bonnyshire Drive to Near I-75 (IA) (#1 Priority)~","Upgrading the existing two (2) lane sections of Bonny Oaks Drive to an improved five (5) lane urban section including sidewalks, curb and gutters and bike lanes. The typical section would consist of five (5) twelve (12) foot lanes with six (6) foot bike lanes, two (2) foot curb and gutter and five (5) foot sidewalks on both sides.","Widen","Legislative",2.11,"2022-04-08",3,20180000,"2022-04-08",3,{"$f":"IFERROR(((VLOOKUP(M19,'Const Index'!C:E,3,0)*(M19)+1)*K19),K19)","v":23433087.204896972},11105728.533126527,5]
[101419.03,"Hamblen","SR-34 ","From SR-32 in Morristown to Near East Morris Boulevard (IA)","Widen from 2-ln to 5-ln","Widen","Legislative",3.8,"2016-02-04",9,23000000,"2016-02-04",9,{"$f":"IFERROR(((VLOOKUP(M20,'Const Index'!C:E,3,0)*(M20)+1)*K20),K20)","v":40527485.531730175},10665127.771507941,5]
[101589.01,"Coffee","SR-55 ","From First Avenue to SR-16 (US-41A, N Jackson Street) in Tullahoma (IA)","Widen from 2-ln to 4-ln at 11' lanes with a 11' continuous center turn lane with 10' paved shoulder; bike lanes and 5' sidewalks on each side.","Widen","Legislative",0.64,"2016-07-26",9,3830300,"2016-07-26",9,{"$f":"IFERROR(((VLOOKUP(M21,'Const Index'!C:E,3,0)*(M21)+1)*K21),K21)","v":6749235.9927037433},10545681.238599598,5]
[124077,"Hamilton","SR-320 ","From near Bel-Air Road to near SR-321 (Ooltewah-Ringgold Road) (IA)","Widen existing 2-lane to 4 12' travel lanes with a continuous 12' center turn lane along with curb and gutter, including pedestrian facilities.","Widen","Legislative",1.51,"2020-10-01",5,9263600,"2020-10-01",5,{"$f":"IFERROR(((VLOOKUP(M22,'Const Index'!C:E,3,0)*(M22)+1)*K22),K22)","v":13918430.541799374},9217503.6700658109,5]
[107777,"Knox","SR-332 ","(Concord Road), Turkey Creek to Northshore Drive","Widen roadway, curb and gutter, sidewalks and bike lanes. New Termini: Concord Rd (SR-332) from north of Turkey Crk Rd to Northshore Dr and revised length (0.93 miles).","Widen","Local Programs",0.93,"2014-12-05",11,4386000,"2014-12-05",11,{"$f":"IFERROR(((VLOOKUP(M23,'Const Index'!C:E,3,0)*(M23)+1)*K23),K23)","v":8188357.0416767178},8804684.9910502341,5]
[118596,"Scott","SR-63 ","From Water Plant Road to Park Road in Huntsville",null,"Widen","Other",0.156,"2014-12-26",11,629400,"2014-12-10",11,{"$f":"IFERROR(((VLOOKUP(M24,'Const Index'!C:E,3,0)*(M24)+1)*K24),K24)","v":1175046.0378548396},7532346.3965053819,5]
[124885,"Wilson","SR-171 ","(South Mt. Juliet Road), From south of SR-265 (Central Pike) to near Providence Way (IA)","Widen South Mt. Juliet Road from 2 lanes to 5 lanes","Widen","Legislative",1.46,"2022-05-10",3,9312025.9100000001,"2022-05-10",3,{"$f":"IFERROR(((VLOOKUP(M25,'Const Index'!C:E,3,0)*(M25)+1)*K25),K25)","v":10813157.344067894},7406272.1534711607,5]
[100339.02,"Shelby","SR-4 ","(Lamar Ave.) From South of Shelby Drive to Near Raines/Perkins Road Interchange (IA)","Widen from 4 lanes to 6 lanes divided.","Widen","Legislative",1.9,"2019-01-28",6,8167910,"2019-01-30",6,{"$f":"IFERROR(((VLOOKUP(M26,'Const Index'!C:E,3,0)*(M26)+1)*K26),K26)","v":12526705.438345643},6593002.8622871805,5]
[101599.01,"Madison","SR-18 ","From North of Medon-Malesus Road to  SR-5 (US-45) in Jackson (EPD) (IA)~","Widen from current 2 lanes without shoulders to 2 lanes with shoulders and to 3 lanes with sidewalks","Construction-New","Legislative",4.99,"2017-05-15",8,16650000,"2013-01-02",12,{"$f":"IFERROR(((VLOOKUP(M27,'Const Index'!C:E,3,0)*(M27)+1)*K27),K27)","v":32127298.313196901},6438336.33531,5]
[119830,"Montgomery","SR-13 ","From Cracker Barrel Drive to International Boulevard (serving Hankook Tire)","Widen from 2-ln to 5-ln rural section","Widen","Legislative",1.3560000000000001,"2015-06-12",10,4532664,"2014-11-20",11,{"$f":"IFERROR(((VLOOKUP(M28,'Const Index'!C:E,3,0)*(M28)+1)*K28),K28)","v":8462168.5321373828},6240537.2655880395,5]
[112538,"Putnam","SR-136 ","SR-111 to I-40 (IA)","WIDEN EXISTING 2-LN TO 5-LN WITH CENTER TURN LANE, SHOULDERS, CURB AND GUTTER, AND SIDEWALK","Widen","Legislative",2.2400000000000002,"2017-08-31",8,7914500,"2017-08-31",8,{"$f":"IFERROR(((VLOOKUP(M29,'Const Index'!C:E,3,0)*(M29)+1)*K29),K29)","v":13398516.530379046},5981480.5939192167,4]
[127967,"Warren","SIA ","State Industrial Access Serving Motlow Advanced Robotics in McMinnville","Pavement removal and scarification in the vicinity of SR-1 at SR-380; and construction of an extension to Magness Drive: SIA: Magness Drive: STA 100+40   STA 107+01 (LEFT) and SR380/Mall Entrance: STA 303+13   STA 305+50 (LEFT).  MMAG: SR 380 and SR 1: SR380 STA 201+41   STA 206+28 (LEFT).   SR380 STA 207+50   SR 1 STA 61+93 (RIGHT).","Construction-New","Economic Development",0.2,"2020-09-30",5,764500,"2020-09-30",5,{"$f":"IFERROR(((VLOOKUP(M30,'Const Index'!C:E,3,0)*(M30)+1)*K30),K30)","v":1148650.6486901012},5743253.2434505057,4]
[119831,"Montgomery","SR-237 ","From West of I-24 to East of International Boulevard Serving Hankook Tire (Includes I-24 Ramp Modifications)",null,"Widen","Legislative",1.02,"2014-02-26",11,3101354,"2014-02-13",11,{"$f":"IFERROR(((VLOOKUP(M31,'Const Index'!C:E,3,0)*(M31)+1)*K31),K31)","v":5790012.2810379062},5676482.6284685358,4]
[10766.01,"Sumner",null,"Walton Ferry Road/Old Shackle Island Road, From Nokes Drive to Volunteer Drive in Hendersonville (Section 2)","Widen from 2 lanes to 3 lanes with turn lanes.","Widen","Local Programs",1.1000000000000001,"2021-11-23",4,4741171,"2021-11-23",4,{"$f":"IFERROR(((VLOOKUP(M32,'Const Index'!C:E,3,0)*(M32)+1)*K32),K32)","v":5863944.5600099079},5330858.6909180973,4]
[100339.01,"Shelby","SR-4 ","From Mississippi State Line to South of Shelby Drive (IA)","Widen from 4-ln to 6-ln on existing alignment.","Widen","Legislative",1.48,"2014-10-06",11,3912530,"2014-09-29",11,{"$f":"IFERROR(((VLOOKUP(M33,'Const Index'!C:E,3,0)*(M33)+1)*K33),K33)","v":7304421.472018105},4935419.9135257462,4]
[101651.03,"Blount","SR-115 ","(Relocated Alcoa Highway), From SR-162(Pellissippi Parkway) to existing SR-115 at South Singleton Station Road (IA)","Construct new 4-ln","Construction-New","Legislative",1.3,"2017-08-28",8,3708081.5,"2017-08-28",8,{"$f":"IFERROR(((VLOOKUP(M34,'Const Index'!C:E,3,0)*(M34)+1)*K34),K34)","v":6277439.0389465829},4828799.2607281404,4]
[100241.03,"Knox","SR-115 ","From Woodson Drive to Cherokee Trail Interchange (IA)","Widening from 4-ln to 6-ln including pedestrian and bicycle facilities.","Widen","Legislative",1.6,"2017-07-11",8,4253166.25,"2017-07-17",8,{"$f":"IFERROR(((VLOOKUP(M35,'Const Index'!C:E,3,0)*(M35)+1)*K35),K35)","v":7200217.1087340023},4500135.6929587508,4]
[124788,"Sevier","SR-449 EXT","(Veterans Blvd), From SR-35 to Robert Henderson Road (IA)","Construct new 5 lane facility.","Construction-New","Legislative",0.7,"2022-10-26",3,2630992,"2022-10-26",3,{"$f":"IFERROR(((VLOOKUP(M36,'Const Index'!C:E,3,0)*(M36)+1)*K36),K36)","v":3055117.1938248905},4364453.1340355584,4]
[100241.01,"Blount","SR-115 ","(Alcoa Highway), Pellissippi Parkway to South of Little River (IA)~","Reconstruct 4-lanes and 6-lanes, including a frontage road system, new interchanges at Singleton Station Road and Topside Road (SR-333), modify the existing SR-115 and SR-162 interchange, and build a multi-use path.","Widen","Legislative",2.71,"2019-12-14",6,7038860,"2019-12-14",6,{"$f":"IFERROR(((VLOOKUP(M37,'Const Index'!C:E,3,0)*(M37)+1)*K37),K37)","v":10795139.251259333},3983446.2181768757,4]
[121394,"Maury","SR-247 ","Industrial Access Road Serving Project Shotgun in Spring Hill",null,"Widen and Resurfacing","Economic Development",0.52,"2015-09-09",10,1081308,"2015-09-09",10,{"$f":"IFERROR(((VLOOKUP(M38,'Const Index'!C:E,3,0)*(M38)+1)*K38),K38)","v":1965555.8206008058},3779915.039616934,4]
[101244.03,"Roane","SR-1 ","From SR-382 to near Ruritan Road (IA)~","Widen 2-ln to 5 ln with center turn lane","Widen","Legislative",3.5,"2017-06-19",8,6116000,"2017-06-19",8,{"$f":"IFERROR(((VLOOKUP(M39,'Const Index'!C:E,3,0)*(M39)+1)*K39),K39)","v":10353822.363989923},2958234.9611399779,4]
[126525,"Grundy","SR-108 ","From near 40th Avenue (LM 8.05) to near 32nd Avenue (LM 8.35) in Gruetli-Laager","Widen from 2-Lane with 12' travel lanes to 3-Lane with 12' travel lanes and 2' shoulders on both sides (business area frontage improvement)","Widen","Other",0.3,"2020-08-21",5,578700,"2020-08-21",5,{"$f":"IFERROR(((VLOOKUP(M40,'Const Index'!C:E,3,0)*(M40)+1)*K40),K40)","v":869488.72517588164},2898295.7505862722,4]
[125204,"Lawrence","Weakly Creek Road","Weakley Creek Road, From SR-6/US-43 (North Locust Ave) to Springer Road; (05958) Old Military Road, From Weakley Creek Road/Hicks St to SR-6/US-43 (North Locust Ave)","Widen and Resurfacing of Weakley Creek Road, From SR-6 (North Locust Ave) to Springer Road ;Old North Military Ave from Weakley Creek Road to SR-6 (North Locust Ave) a distance of 1,535 feet","Widen and Resurfacing","Local Programs",0.5,"2023-03-28",2,1243205,"2023-03-28",2,{"$f":"IFERROR(((VLOOKUP(M41,'Const Index'!C:E,3,0)*(M41)+1)*K41),K41)","v":1410391.1343492002},2820782.2686984004,4]
[103899,"Loudon","SR-73 ","From Simpson Road East to North of SR-2(US-11) in Lenoir City","Widen from 4-lanes to 6-lanes","Widen","Legislative",1.2809999999999999,"2017-05-15",8,1921518,"2017-05-15",8,{"$f":"IFERROR(((VLOOKUP(M42,'Const Index'!C:E,3,0)*(M42)+1)*K42),K42)","v":3252952.2631146484},2539385.0609794292,3]
[100260.04,"Cumberland","SR-28 ","From near Hollow Lane to near Lowe Road (EPD) (IA)~","Widen from existing 2 lane to a 4 lane facility.","Widen","Legislative",3.05,"2020-04-27",5,4780560,"2020-04-27",5,{"$f":"IFERROR(((VLOOKUP(M43,'Const Index'!C:E,3,0)*(M43)+1)*K43),K43)","v":7182725.1080470243},2354991.8387039425,3]
[107774.01,"Fentress","SR-28 ","(South York Highway), From Near Little Road to North of Kilby Road (IA)~","Widen from existing 2 lane to a 3 lane facility.","Widen","Legislative",3.23,"2019-09-19",6,4457125,"2019-09-26",6,{"$f":"IFERROR(((VLOOKUP(M44,'Const Index'!C:E,3,0)*(M44)+1)*K44),K44)","v":6835664.444990986},2116304.7817309555,3]
[123070,"Moore","SR-55 ","From near Goodbranch Road to near Moore County High School (IA)","Widen from 2-lanes to a 3 lane facility.","Widen","Legislative",0.56999999999999995,"2020-08-14",5,673813.57,"2020-08-14",5,{"$f":"IFERROR(((VLOOKUP(M45,'Const Index'!C:E,3,0)*(M45)+1)*K45),K45)","v":1012395.5451624497},1776132.5353727189,3]
[132406,"Maury","SIA ","State Industrial Access serving Project Leeward","Section 1: New SIA access road from Oakland Blvd. to serve Project Leeward with cul-de-sac and connection to SR-6/US-43,  Section 2: right-in only entrance with deceleration lane to Columbia Tennessee Rail Site from SR-6/US-43, Section 3: dual left lanes on Oakland Blvd to SR-6/US-43, extend the right turn lane on SR-6/US-43 toward Oakland Blvd and installation of traffic signals on intersections of Hampshire Pike/SR-99 and on SR-6/US-43.","Construction-New","Economic Development",1.32,"2022-07-14",3,1897609.66,"2022-07-14",3,{"$f":"IFERROR(((VLOOKUP(M46,'Const Index'!C:E,3,0)*(M46)+1)*K46),K46)","v":2203511.0328857726},1669326.5400649791,3]
[101409,"Claiborne","SR-63 ","From Campbell County Line to Hall Lane (IA)","Widen From 2-LN to 5-LN","Widen","Legislative",5.35,"2019-05-29",6,5786950,"2019-05-29",6,{"$f":"IFERROR(((VLOOKUP(M47,'Const Index'!C:E,3,0)*(M47)+1)*K47),K47)","v":8875148.9715771005},1658906.3498274956,3]
[100260.03,"Cumberland","SR-28 ","Near Potato Farm Road to near Hollow Lane (EPD)","Widen from existing 2-ln to super 2-lane facility","Widen","Legislative",3.45,"2019-11-19",6,3522500,"2019-11-19",6,{"$f":"IFERROR(((VLOOKUP(M48,'Const Index'!C:E,3,0)*(M48)+1)*K48),K48)","v":5402277.9274713518},1565877.6601366235,3]
[101410.01,"Grainger","SR-1 ","From West of Helton Road to Bean Station (IA)~","Widen 2-ln to 5-ln","Widen","Legislative",4.62,"2017-08-28",{"$f":"IFERROR(YEAR(TODAY())-YEAR(I49),\"\")","v":8},4182264.74,"2017-08-28",{"$f":"IFERROR(YEAR(TODAY())-YEAR(L49),\"\")","v":8},{"$f":"IFERROR(((VLOOKUP(M49,'Const Index'!C:E,3,0)*(M49)+1)*K49),K49)","v":7080187.4096040716},{"$f":"N49/H49","v":1532508.0973168986},3]
[101423,"Blount","SR-162 EXT","(Pellissippi Parkway), From near SR-33 to SR-73 (US-321)~","Construct new 4 lane","Stage Construction-New","Legislative",4.9000000000000004,"2023-02-22",2,6575765,"2023-02-22",2,{"$f":"IFERROR(((VLOOKUP(M50,'Const Index'!C:E,3,0)*(M50)+1)*K50),K50)","v":7460073.4855182916},1522463.976636386,3]
[101407.01,"Campbell","SR-63 ","(General Carl W. Stiner Hwy.), From Near Myers Lane (LaFollette City Limits) to Near Frontier Road/Woodson Lane (IA)","Widen 2-ln to 5-ln","Widen","Legislative",4.92,"2018-06-20",7,4399898.57,"2018-06-20",7,{"$f":"IFERROR(((VLOOKUP(M51,'Const Index'!C:E,3,0)*(M51)+1)*K51),K51)","v":6964574.8611616623},1415563.9961710696,3]
[112219,"Franklin","SR-97 ","Intersection at Beans Creek Road, LM 4.70","Widen the curve of SR-97 to the inside at the intersection of Beans Creek Road to permit large vehicles to turn without crossing the center line.","Widen","Local Programs",8.8999999999999996E-2,"2014-02-04",11,61500,"2013-11-07",12,{"$f":"IFERROR(((VLOOKUP(M52,'Const Index'!C:E,3,0)*(M52)+1)*K52),K52)","v":118668.39917487143},1333352.7997176566,3]
[126523,"Sumner","SIA ","Industrial Access Road Serving Project Cardinal",null,"Construction-New","Economic Development",0.16,"2019-02-11",6,114310,"2019-02-11",6,{"$f":"IFERROR(((VLOOKUP(M53,'Const Index'!C:E,3,0)*(M53)+1)*K53),K53)","v":175311.39528438615},1095696.2205274133,3]
[101651.02,"Blount","SR-115 ","(Relocated Alcoa Highway), From Proposed Interchange at Tyson Blvd to SR-162 (Pellissippi Parkway) (IA)","New alignment, new four lane divided facility, construct an interchange at Pellissippi Parkway (SR-162)","Construction-New","Legislative",2.4,"2018-01-10",7,1565588.05,"2018-01-10",7,{"$f":"IFERROR(((VLOOKUP(M54,'Const Index'!C:E,3,0)*(M54)+1)*K54),K54)","v":2478160.5763164461},1032566.9067985192,3]
[128962,"Anderson","SIA ","State Industrial Access Serving Norris Industrial Park","Constructing a new two lane access road connecting SR-71 to Sawmill Rd, approximately .25 miles, including a tie-in to the existing church, and a box culvert on the new roadway for  stream mitigation.","Construction-New","Economic Development",0.25,"2022-05-04",3,206080,"2022-05-04",3,{"$f":"IFERROR(((VLOOKUP(M55,'Const Index'!C:E,3,0)*(M55)+1)*K55),K55)","v":239300.82315090031},957203.29260360124,2]
[128996,"Giles","SIA ","State Industrial Access Serving Integrity Mold and Murco Wall Products","Widen Tarpley Shop Road 0.78 miles","Construction-New","Economic Development",0.78,"2021-06-22",4,517465.4,"2021-06-22",4,{"$f":"IFERROR(((VLOOKUP(M56,'Const Index'!C:E,3,0)*(M56)+1)*K56),K56)","v":640008.22103302134},820523.36029874533,2]
[101410.02,"Grainger","SR-1 ","From Rutledge to West of Helton Road (IA)~","Widen 2-ln to 5-ln","Widen","Legislative",5.7,"2017-09-26",8,2711637.2,"2017-09-26",8,{"$f":"IFERROR(((VLOOKUP(M57,'Const Index'!C:E,3,0)*(M57)+1)*K57),K57)","v":4590550.994831102},805359.82365457923,2]
[119592,"Sumner","SIA ","Industrial Access Road serving ABC and other industries in Gallatin","SIA will serve: ABC Fuels, ABC Tech, Salga, Hoeganeas, Servpro and ITW CIP industries located on Airport Rd between Coles Ferry and Steam Plant Rd.","Widen and Resurfacing","Economic Development",1.17,"2015-09-17",10,505260,"2015-09-17",10,{"$f":"IFERROR(((VLOOKUP(M58,'Const Index'!C:E,3,0)*(M58)+1)*K58),K58)","v":918440.19827538787},784991.62245759647,2]
[101407.02,"Campbell","SR-63 ","(General Carl W. Stiner Highway), From Near Frontier Road/Woodson Lane to Near Claiborne County Line (IA)","Widen From 2-LN to 5-LN","Widen","Legislative",5.26,"2019-09-13",6,2203000,"2019-09-13",6,{"$f":"IFERROR(((VLOOKUP(M59,'Const Index'!C:E,3,0)*(M59)+1)*K59),K59)","v":3378628.3248316217},642324.77658395853,2]
[132132.03,"Tipton","SR-194 EXT","New route from Northern Interchange to SR-1 (Project Blue Oval, G2 North)","2-Lane from Northern Interchange to SR-1","Construction-New","Legislative",2.5,"2022-09-27",3,1200000,"2022-09-27",3,{"$f":"IFERROR(((VLOOKUP(M60,'Const Index'!C:E,3,0)*(M60)+1)*K60),K60)","v":1393444.2341861431},557377.69367445726,2]
[101885.01,"Hardin","SR-128 ","From Pyburns Drive to SR-226 (Airport Road) (IA)","Left-turn lane at Pyburns Drive and SR-226, Truck Climbing Lane for steep vertical curve just north of Hatley Creek. re-align two(2) intersections.","Widen","Legislative",3.4,"2015-04-09",10,745500,"2014-09-04",11,{"$f":"IFERROR(((VLOOKUP(M61,'Const Index'!C:E,3,0)*(M61)+1)*K61),K61)","v":1391796.665428635},409351.96042018675,2]
[101419.04,"Hamblen","SR-34 ","(E. Andrew Johnson Hwy.), From Near Morris Blvd to West of Old Stagecoach Road in Russellville (***) (IA)~","Widen to 5-Lane w/ Ditches.","Construction-New","Legislative",1.56,"2017-08-29",8,355993.45,"2017-08-30",8,{"$f":"IFERROR(((VLOOKUP(M62,'Const Index'!C:E,3,0)*(M62)+1)*K62),K62)","v":602663.98692673782},386323.06854278065,2]
[126690,"Gibson","SIA ","Industrial Access Road Serving Project Phoenix (Tyson Foods)",null,"Construction-New","Economic Development",0.33,"2019-04-26",6,82000,"2019-04-26",6,{"$f":"IFERROR(((VLOOKUP(M63,'Const Index'!C:E,3,0)*(M63)+1)*K63),K63)","v":125759.20228606128},381088.49177594326,2]
[115906,"Rutherford","SR-268 ","From SR-1(US 41/70S) to SR-10 (IA)","Widen SR-268 (Thompson Lane) from 2 to 5 lanes including sidewalks and bike lanes. Interconnect traffic signals into existing fiber optic to provide for coordinated arterial signal system.","Widen","Legislative",4.3,"2017-06-20",8,908823.49,"2017-11-27",8,{"$f":"IFERROR(((VLOOKUP(M64,'Const Index'!C:E,3,0)*(M64)+1)*K64),K64)","v":1538554.1163638607},357803.28287531645,2]
[101406.04,"Campbell","SR-63 ","(Howard Baker Hwy.) From Near the Intersection of SR-297 and West of Old SR-63 to West of Stinking Creek Road (Truck Climbing Lane) (***) (IA)","Construct truck climbing lane and intersection improvements at the intersection of SR-297 and SR-63.","Widen","Legislative",0.876,"2017-01-10",8,141484.79999999999,"2017-01-10",8,{"$f":"IFERROR(((VLOOKUP(M65,'Const Index'!C:E,3,0)*(M65)+1)*K65),K65)","v":239520.68123032071},273425.43519443006,2]
[128559,"Cheatham","SIA ","State Industrial Access Road serving Caymas Boats and Nashville Fabrication",null,"Construction-New","Economic Development",0.18,"2020-09-16",5,32120.400000000001,"2020-09-16",5,{"$f":"IFERROR(((VLOOKUP(M66,'Const Index'!C:E,3,0)*(M66)+1)*K66),K66)","v":48260.455586900622},268113.64214944793,2]
[100241.02,"Knox","SR-115 ","From South of Topside Road to North of Maloney Road (IA)","Widen 4-ln to 6-ln including pedestrian & bicycle facilities","Widen","Legislative",2.2000000000000002,"2017-05-11",8,293749.15000000002,"2019-03-25",6,{"$f":"IFERROR(((VLOOKUP(M67,'Const Index'!C:E,3,0)*(M67)+1)*K67),K67)","v":450508.03385620192},204776.37902554631,1]
[101419.02,"Hamblen","SR-34 ","From West of Old Stagecoach Road  in Russellville to Steadman Road (EPD) (IA)~","Construct 5 lane roadway in a 5 lane ROW on new alignment","Construction-New","Legislative",3.7,"2017-08-29",8,439200,"2017-08-29",8,{"$f":"IFERROR(((VLOOKUP(M68,'Const Index'!C:E,3,0)*(M68)+1)*K68),K68)","v":743524.98074957065},200952.69749988394,1]
[127751,"Weakley","SIA ","State Industrial Access serving Project Dove",null,"Construction-New","Economic Development",1.7,"2022-05-19",3,286400,"2022-05-19",3,{"$f":"IFERROR(((VLOOKUP(M69,'Const Index'!C:E,3,0)*(M69)+1)*K69),K69)","v":332568.69055909279},195628.6415053487,1]
[117511,"Fentress","SIA ","Industrial Access Road serving Clarkrange Regional Business Park",null,"Construction-New","Economic Development",0.99299999999999999,"2014-02-06",11,78000,"2013-11-11",12,{"$f":"IFERROR(((VLOOKUP(M70,'Const Index'!C:E,3,0)*(M70)+1)*K70),K70)","v":150506.26236812962},151567.23299912349,1]
[106634.03,"Sumner","SR-109 PROP","(Portland Bypass), from existing SR-109, south of Portland, to SR-52, west of Portland (IA)","Construct new 4-ln divided roadway.","Construction-New","Legislative",3.75,"2020-06-22",5,351434,"2020-06-22",5,{"$f":"IFERROR(((VLOOKUP(M71,'Const Index'!C:E,3,0)*(M71)+1)*K71),K71)","v":528024.71167005494},140806.58977868131,1]
[120852,"Sumner","SIA ","Industrial Access Road serving Beretta USA in Gallatin","Extend Gateway Blvd. 1060 ft. and a 1750 ft. connection between Gateway Blvd. and Commerce Drive","Construction-New","Economic Development",0.53,"2016-01-25",9,39805.199999999997,"2015-11-24",10,{"$f":"IFERROR(((VLOOKUP(M72,'Const Index'!C:E,3,0)*(M72)+1)*K72),K72)","v":72356.204291634931},136521.14017289609,1]
[121356,"Madison","SR-223 ","From 0.74 Miles North of Old Denmark-Jackson Road to near Golden Drive","Extend the right turn lane on SR-223 in front of Nexus Corp., and add a center turn lane on SR-223 in front of Pacific Industries. Project now shows on contract as: Serving Pacific Industries and Project Nexus.","Widen and Resurfacing","Safety",0.23,"2016-12-09",9,16000,"2016-12-09",9,{"$f":"IFERROR(((VLOOKUP(M73,'Const Index'!C:E,3,0)*(M73)+1)*K73),K73)","v":28193.033413377514},122578.40614511962,1]
[101463.03,"Montgomery","SR-374 PROP","SR-76 (US-79) to Dotsonville Road in Clarksville (Re-Budgeted ROW & Stage Const.) (IA)~","Construct Four-Lane Divided.","Construction-New","Legislative",2.9,"2022-08-05",3,293045,"2022-08-05",3,{"$f":"IFERROR(((VLOOKUP(M74,'Const Index'!C:E,3,0)*(M74)+1)*K74),K74)","v":340284.88800589857},117339.61655375813,1]
[120361,"Hamilton","SIA ","Industrial Access Road serving Volkswagen Group of America Supplier Park in Chattanooga","Construction of a four-lane Roadway with bicycle and pedestrian facilities.","Construction-New","Economic Development",1.34,"2016-06-20",9,57000,"2016-04-22",9,{"$f":"IFERROR(((VLOOKUP(M75,'Const Index'!C:E,3,0)*(M75)+1)*K75),K75)","v":100437.68153515739},74953.493682953267,1]
[128975,"Carroll","SIA ","State Industrial Access Serving Pottery Direct International","SIA standard of two 12' lanes with 4' gravel   shoulders. The proposed road will be constructed on a 10\" stone base with 3\" of base   (\"A\" mix), 2\" of binder (\"BM-2\" mix) and 1.25\" of asphalt surface (\"D\" mix).","Construction-New","Economic Development",0.6,"2021-07-07",4,21929.16,"2021-07-07",4,{"$f":"IFERROR(((VLOOKUP(M76,'Const Index'!C:E,3,0)*(M76)+1)*K76),K76)","v":27122.282340710102},45203.803901183506,1]
[124081,"Hamilton","I-75 ","From North of SR-2 in Hamilton County to near SR-311 in Bradley County (IA)~","WIDEN I-75 FROM 4 TO 6 LANES FROM APD-40/SR 311 (EXIT 20) TO HAMILTON COUNTY LINE. FULL PROJECT EXTENDS TO US 64 IN HAMILTON COUNTY; DETAILS ON THE PORTION IN HAMILTON COUNTY CAN BE FOUND IN THE TIP FOR THE CHATTANOOGA/HAMILTON COUNTY/NORTH GEORGIA TRANSPORTATION PLANNING ORGANIZATION.","Widen","Legislative",8.5299999999999994,"2022-08-31",3,124900,"2022-08-31",3,{"$f":"IFERROR(((VLOOKUP(M77,'Const Index'!C:E,3,0)*(M77)+1)*K77),K77)","v":145034.32070820773},17002.85119674182,1]
[124789,"Sevier",null,"Jake Thomas Connector, From SR-71 / 73 (US-321 / 441) to SR-449 (IA)","Jake Thomas Road Extension-Between Teaster and New Ripkin Experience Ballpark, widening existing 2-lane road to 4-lane median divided section. From Ballpark to Veterans Blvd-constructing 5-lane on new alignment.","Construction-New","Legislative",2.0099999999999998,"2020-03-16",5,6750,"2020-03-16",5,{"$f":"IFERROR(((VLOOKUP(M78,'Const Index'!C:E,3,0)*(M78)+1)*K78),K78)","v":10141.78139785243},5045.6623869912592,1]

{"sheet":"Traffic Control","index":36,"n_rows":5,"n_cols":4,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
[null,"Project Type","Average","High"]
[null,"Resurfacing",0.05,7.4999999999999997E-2]
[null,"Bridge Construction",0.04,0.08]
[null,"Grade and Drain",0.05,0.1]
[null,"Safety",0.06,0.115]

{"sheet":"Corridor_Proj_ROW","index":37,"n_rows":84,"n_cols":18,"rows_kept":84,"cut":false,"hidden":true,"merged":[]}
[]
["ROW Impacts","Average Project Length","Average"]
["Very Low Impacts",{"$f":"AVERAGEIF($Q$17:$Q$84,1,$I$17:$I$84)","v":2.641833333333333},{"$f":"(SUMPRODUCT(IF($Q$17:$Q$84=1,1,0),$P$17:$P$84,$I$17:$I$84))/SUMIF($Q$17:$Q$84,1,$I$17:$I$84)","v":74502.00224044612},{"$f":"COUNTIF(Q:Q,1)/COUNTA($Q$17:$Q$84)","v":8.8235294117647065E-2}]
["Low Impacts",{"$f":"AVERAGEIF($Q$17:$Q$84,2,$I$17:$I$84)","v":1.9090666666666665},{"$f":"(SUMPRODUCT(IF($Q$17:$Q$84=2,1,0),$P$17:$P$84,$I$17:$I$84))/SUMIF($Q$17:$Q$84,2,$I$17:$I$84)","v":327064.06033423496},{"$f":"COUNTIF(Q:Q,2)/COUNTA($Q$17:$Q$84)","v":0.22058823529411764}]
["Moderate Impacts",{"$f":"AVERAGEIF($Q$17:$Q$84,3,$I$17:$I$84)","v":2.1468928571428569},{"$f":"(SUMPRODUCT(IF($Q$17:$Q$84=3,1,0),$P$17:$P$84,$I$17:$I$84))/SUMIF($Q$17:$Q$84,3,$I$17:$I$84)","v":3784432.01920657},{"$f":"COUNTIF(Q:Q,3)/COUNTA($Q$17:$Q$84)","v":0.41176470588235292}]
["High Impacts",{"$f":"AVERAGEIF($Q$17:$Q$84,4,$I$17:$I$84)","v":1.8234166666666667},{"$f":"(SUMPRODUCT(IF($Q$17:$Q$84=4,1,0),$P$17:$P$84,$I$17:$I$84))/SUMIF($Q$17:$Q$84,4,$I$17:$I$84)","v":9973410.5259714369},{"$f":"COUNTIF(Q:Q,4)/COUNTA($Q$17:$Q$84)","v":0.17647058823529413}]
["Very High Impacts",{"$f":"AVERAGEIF($Q$17:$Q$84,5,$I$17:$I$84)","v":1.6779999999999997},{"$f":"(SUMPRODUCT(IF($Q$17:$Q$84=5,1,0),$P$17:$P$84,$I$17:$I$84))/SUMIF($Q$17:$Q$84,5,$I$17:$I$84)","v":28317726.154310387},{"$f":"COUNTIF(Q:Q,5)/COUNTA($Q$17:$Q$84)","v":0.10294117647058823}]
[]
["ROW Impacts","Average Project Length","Distressed"]
["Very Low",{"$f":"B3","v":2.641833333333333},{"$f":"MROUND(C3,5000)","v":75000}]
["Low",{"$f":"B4","v":1.9090666666666665},{"$f":"MROUND(C4,5000)","v":325000}]
["Moderate",{"$f":"B5","v":2.1468928571428569},{"$f":"MROUND(C5,5000)","v":3785000}]
["High",{"$f":"B6","v":1.8234166666666667},{"$f":"MROUND(C6,1000)","v":9973000}]
["Very High",{"$f":"B7","v":1.6779999999999997},{"$f":"MROUND(C7,1000)","v":28318000}]
[]
["PIN","County","Route","Project Description","PPRM SCOPE OF WORK","Project Type Work","Program Type","HVI","Length","ROW Estimate Date","Years","Utility Estimate","Utility Estimate Date","ROW Cost","Inflated ROW","ROW/Mile","Group","Cumulative Length"]
[100339.02,"Shelby","SR-4 ","(Lamar Ave.) From South of Shelby Drive to Near Raines/Perkins Road Interchange (IA)","Widen from 4 lanes to 6 lanes divided.","Widen","Legislative",{"$f":"VLOOKUP(B17,ROW_Zillow!B:F,5,0)","v":1.2460347206491074},1.9,"2019-01-28",{"$f":"IFERROR(YEAR(TODAY())-YEAR(J17),\"\")","v":6},8167910,"2019-01-30",45201198,{"$f":"IFERROR(((VLOOKUP(K17,'Housing Index'!C:F,4,0)*(K17)+1)*N17),N17)","v":80357035.274398133},{"$f":"O17/(I17*H17)","v":33942213.454675965},5,{"$f":"SUM($I$17:I17)","v":1.9}]
[100339.01,"Shelby","SR-4 ","From Mississippi State Line to South of Shelby Drive (IA)","Widen from 4-ln to 6-ln on existing alignment.","Widen","Legislative",{"$f":"VLOOKUP(B18,ROW_Zillow!B:F,5,0)","v":1.2460347206491074},1.48,"2014-10-06",11,3912530,"2014-09-29",26489000,{"$f":"IFERROR(((VLOOKUP(K18,'Housing Index'!C:F,4,0)*(K18)+1)*N18),N18)","v":63164308.159722224},34251522.760275885,5,{"$f":"SUM($I$17:I18)","v":3.38}]
[100241.01,"Blount","SR-115 ","(Alcoa Highway), Pellissippi Parkway to South of Little River (IA)~","Reconstruct 4-lanes and 6-lanes, including a frontage road system, new interchanges at Singleton Station Road and Topside Road (SR-333), modify the existing SR-115 and SR-162 interchange, and build a multi-use path.","Widen","Legislative",{"$f":"VLOOKUP(B19,ROW_Zillow!B:F,5,0)","v":1.0793158837702588},2.71,"2019-12-14",6,7038860,"2019-12-14",48921623.219999999,{"$f":"IFERROR(((VLOOKUP(K19,'Housing Index'!C:F,4,0)*(K19)+1)*N19),N19)","v":86971071.049275175},29734247.986361664,5,{"$f":"SUM($I$17:I19)","v":6.09}]
[101651.03,"Blount","SR-115 ","(Relocated Alcoa Highway), From SR-162(Pellissippi Parkway) to existing SR-115 at South Singleton Station Road (IA)","Construct new 4-ln","Construction-New","Legislative",{"$f":"VLOOKUP(B20,ROW_Zillow!B:F,5,0)","v":1.0793158837702588},1.3,"2017-08-28",8,3708081.5,"2017-08-28",20500794.809999999,{"$f":"IFERROR(((VLOOKUP(K20,'Housing Index'!C:F,4,0)*(K20)+1)*N20),N20)","v":41502581.834647588},29578980.009270784,5,{"$f":"SUM($I$17:I20)","v":7.39}]
[101725.02,"Blount","SR-336 ","Montvale Station Road to SR-73(Lamar Alexander Parkway) (IA)","Widen existing roadway to 2 - 12 foot travel lanes with a 12 foot center turn lane including curb and gutter, sidewalk, and a multiuse path. Close SR-73 EB and WB access to Highland Avenue to construct EB right-turn lane on to SR-336; lengthen WB SR-73 left-turn lane near Highland Avenue","Widen","Legislative",{"$f":"VLOOKUP(B21,ROW_Zillow!B:F,5,0)","v":1.0793158837702588},0.6,"2019-09-01",6,"",null,9300000,{"$f":"IFERROR(((VLOOKUP(K21,'Housing Index'!C:F,4,0)*(K21)+1)*N21),N21)","v":16533199.585814133},25530368.872889612,5,{"$f":"SUM($I$17:I21)","v":7.9899999999999993}]
[101651.02,"Blount","SR-115 ","(Relocated Alcoa Highway), From Proposed Interchange at Tyson Blvd to SR-162 (Pellissippi Parkway) (IA)","New alignment, new four lane divided facility, construct an interchange at Pellissippi Parkway (SR-162)","Construction-New","Legislative",{"$f":"VLOOKUP(B22,ROW_Zillow!B:F,5,0)","v":1.0793158837702588},2.4,"2018-01-10",7,1565588.05,"2018-01-10",30418669.510000002,{"$f":"IFERROR(((VLOOKUP(K22,'Housing Index'!C:F,4,0)*(K22)+1)*N22),N22)","v":57265882.524171442},22107322.558546167,5,{"$f":"SUM($I$17:I22)","v":10.389999999999999}]
[119830,"Montgomery","SR-13 ","From Cracker Barrel Drive to International Boulevard (serving Hankook Tire)","Widen from 2-ln to 5-ln rural section","Widen","Legislative",{"$f":"VLOOKUP(B23,ROW_Zillow!B:F,5,0)","v":0.97854843249105894},1.3560000000000001,"2015-06-12",10,4532664,"2014-11-20",12967524,{"$f":"IFERROR(((VLOOKUP(K23,'Housing Index'!C:F,4,0)*(K23)+1)*N23),N23)","v":29385095.713720053},22145479.823082913,5,{"$f":"SUM($I$17:I23)","v":11.745999999999999}]
[127967,"Warren","SIA ","State Industrial Access Serving Motlow Advanced Robotics in McMinnville","Pavement removal and scarification in the vicinity of SR-1 at SR-380; and construction of an extension to Magness Drive: SIA: Magness Drive: STA 100+40   STA 107+01 (LEFT) and SR380/Mall Entrance: STA 303+13   STA 305+50 (LEFT).  MMAG: SR 380 and SR 1: SR380 STA 201+41   STA 206+28 (LEFT).   SR380 STA 207+50   SR 1 STA 61+93 (RIGHT).","Construction-New","Economic Development",{"$f":"VLOOKUP(B24,ROW_Zillow!B:F,5,0)","v":0.67264221531195723},0.2,"2020-09-30",5,764500,"2020-09-30",987450,{"$f":"IFERROR(((VLOOKUP(K24,'Housing Index'!C:F,4,0)*(K24)+1)*N24),N24)","v":1652084.8965819669},12280562.080212025,4,{"$f":"SUM($I$17:I24)","v":11.945999999999998}]
[101419.03,"Hamblen","SR-34 ","From SR-32 in Morristown to Near East Morris Boulevard (IA)","Widen from 2-ln to 5-ln","Widen","Legislative",{"$f":"VLOOKUP(B25,ROW_Zillow!B:F,5,0)","v":0.67698744482656836},3.8,"2016-02-04",9,23000000,"2016-02-04",14800000,{"$f":"IFERROR(((VLOOKUP(K25,'Housing Index'!C:F,4,0)*(K25)+1)*N25),N25)","v":31859758.008902259},12384493.846257115,4,{"$f":"SUM($I$17:I25)","v":15.745999999999999}]
[107777,"Knox","SR-332 ","(Concord Road), Turkey Creek to Northshore Drive","Widen roadway, curb and gutter, sidewalks and bike lanes. New Termini: Concord Rd (SR-332) from north of Turkey Crk Rd to Northshore Dr and revised length (0.93 miles).","Widen","Local Programs",{"$f":"VLOOKUP(B26,ROW_Zillow!B:F,5,0)","v":1.0314909011031255},0.93,"2014-12-05",11,4386000,"2014-12-05",4900000,{"$f":"IFERROR(((VLOOKUP(K26,'Housing Index'!C:F,4,0)*(K26)+1)*N26),N26)","v":11684288.194444444},12180185.722703112,4,{"$f":"SUM($I$17:I26)","v":16.675999999999998}]
[112538,"Putnam","SR-136 ","SR-111 to I-40 (IA)","WIDEN EXISTING 2-LN TO 5-LN WITH CENTER TURN LANE, SHOULDERS, CURB AND GUTTER, AND SIDEWALK","Widen","Legislative",{"$f":"VLOOKUP(B27,ROW_Zillow!B:F,5,0)","v":0.92302147902551535},2.2400000000000002,"2017-08-31",8,7914500,"2017-08-31",10963500,{"$f":"IFERROR(((VLOOKUP(K27,'Housing Index'!C:F,4,0)*(K27)+1)*N27),N27)","v":22194922.692568466},10734796.378814301,4,{"$f":"SUM($I$17:I27)","v":18.915999999999997}]
[124077,"Hamilton","SR-320 ","From near Bel-Air Road to near SR-321 (Ooltewah-Ringgold Road) (IA)","Widen existing 2-lane to 4 12' travel lanes with a continuous 12' center turn lane along with curb and gutter, including pedestrian facilities.","Widen","Legislative",{"$f":"VLOOKUP(B28,ROW_Zillow!B:F,5,0)","v":1.5713238877791278},1.51,"2020-10-01",5,9263600,"2020-10-01",15855750,{"$f":"IFERROR(((VLOOKUP(K28,'Housing Index'!C:F,4,0)*(K28)+1)*N28),N28)","v":26527971.13674568},11180503.868379621,4,{"$f":"SUM($I$17:I28)","v":20.425999999999998}]
[107774.01,"Fentress","SR-28 ","(South York Highway), From Near Little Road to North of Kilby Road (IA)~","Widen from existing 2 lane to a 3 lane facility.","Widen","Legislative",{"$f":"VLOOKUP(B29,ROW_Zillow!B:F,5,0)","v":0.55337836446384814},3.23,"2019-09-19",6,4457125,"2019-09-26",10225110,{"$f":"IFERROR(((VLOOKUP(K29,'Housing Index'!C:F,4,0)*(K29)+1)*N29),N29)","v":18177826.281387523},10169913.31001934,4,{"$f":"SUM($I$17:I29)","v":23.655999999999999}]
[124788,"Sevier","SR-449 EXT","(Veterans Blvd), From SR-35 to Robert Henderson Road (IA)","Construct new 5 lane facility.","Construction-New","Legislative",{"$f":"VLOOKUP(B30,ROW_Zillow!B:F,5,0)","v":1.1919966775812243},0.7,"2022-10-26",3,2630992,"2022-10-26",7475198,{"$f":"IFERROR(((VLOOKUP(K30,'Housing Index'!C:F,4,0)*(K30)+1)*N30),N30)","v":9186157.4448858332},11009327.719563542,4,{"$f":"SUM($I$17:I30)","v":24.355999999999998}]
[101419.04,"Hamblen","SR-34 ","(E. Andrew Johnson Hwy.), From Near Morris Blvd to West of Old Stagecoach Road in Russellville (***) (IA)~","Widen to 5-Lane w/ Ditches.","Construction-New","Legislative",{"$f":"VLOOKUP(B31,ROW_Zillow!B:F,5,0)","v":0.67698744482656836},1.56,"2017-08-29",8,355993.45,"2017-08-30",4800829.75,{"$f":"IFERROR(((VLOOKUP(K31,'Housing Index'!C:F,4,0)*(K31)+1)*N31),N31)","v":9718980.7234398499},9202705.1549750939,4,{"$f":"SUM($I$17:I31)","v":25.915999999999997}]
[112152.03,"Hamilton","SR-317 ","(Bonny Oaks Drive), From Near Adamson Circle to West of Bonnyshire Drive (IA) (#2 Priority)~","Widen to 4-ln and 12' lanes with a 12' continuous center turn lane and  5' sidewalks on either side or a single 10' multiuse path.","Widen","Legislative",{"$f":"VLOOKUP(B32,ROW_Zillow!B:F,5,0)","v":1.5713238877791278},0.95099999999999996,"2020-08-13",5,7392000,"2020-08-13",8191200,{"$f":"IFERROR(((VLOOKUP(K32,'Housing Index'!C:F,4,0)*(K32)+1)*N32),N32)","v":13704549.906205082},9171039.1404759753,4,{"$f":"SUM($I$17:I32)","v":26.866999999999997}]
[124789,"Sevier",null,"Jake Thomas Connector, From SR-71 / 73 (US-321 / 441) to SR-449 (IA)","Jake Thomas Road Extension-Between Teaster and New Ripkin Experience Ballpark, widening existing 2-lane road to 4-lane median divided section. From Ballpark to Veterans Blvd-constructing 5-lane on new alignment.","Construction-New","Legislative",{"$f":"VLOOKUP(B33,ROW_Zillow!B:F,5,0)","v":1.1919966775812243},2.0099999999999998,"2020-03-16",5,6750,"2020-03-16",11005478.52,{"$f":"IFERROR(((VLOOKUP(K33,'Housing Index'!C:F,4,0)*(K33)+1)*N33),N33)","v":18413068.856700853},7685198.2449035076,4,{"$f":"SUM($I$17:I33)","v":28.876999999999995}]
[100260.03,"Cumberland","SR-28 ","Near Potato Farm Road to near Hollow Lane (EPD)","Widen from existing 2-ln to super 2-lane facility","Widen","Legislative",{"$f":"VLOOKUP(B34,ROW_Zillow!B:F,5,0)","v":0.85118446975157369},3.45,"2019-11-19",6,3522500,"2019-11-19",12940450,{"$f":"IFERROR(((VLOOKUP(K34,'Housing Index'!C:F,4,0)*(K34)+1)*N34),N34)","v":23005058.341962203},7833945.6248406712,4,{"$f":"SUM($I$17:I34)","v":32.326999999999998}]
[100286,"Sumner","SR-109 ","North of the Cumberland River Bridge to SR-109 Bypass South of Gallatin","Widen from 2-ln to 4/5-ln","Widen","Legislative",{"$f":"VLOOKUP(B35,ROW_Zillow!B:F,5,0)","v":1.0072592104450255},1.3,"2014-04-24",11,7516166,"2011-10-24",4370829,{"$f":"IFERROR(((VLOOKUP(K35,'Housing Index'!C:F,4,0)*(K35)+1)*N35),N35)","v":10422454.221354166},7959492.8443717733,4,{"$f":"SUM($I$17:I35)","v":33.626999999999995}]
[101410.02,"Grainger","SR-1 ","From Rutledge to West of Helton Road (IA)~","Widen 2-ln to 5-ln","Widen","Legislative",{"$f":"VLOOKUP(B36,ROW_Zillow!B:F,5,0)","v":0.53198171296773},5.7,"2017-09-26",8,2711637.2,"2017-09-26",10170302.08,{"$f":"IFERROR(((VLOOKUP(K36,'Housing Index'!C:F,4,0)*(K36)+1)*N36),N36)","v":20589142.922029305},6789952.0775768384,3,{"$f":"SUM($I$17:I36)","v":39.326999999999998}]
[10766.01,"Sumner",null,"Walton Ferry Road/Old Shackle Island Road, From Nokes Drive to Volunteer Drive in Hendersonville (Section 2)","Widen from 2 lanes to 3 lanes with turn lanes.","Widen","Local Programs",{"$f":"VLOOKUP(B37,ROW_Zillow!B:F,5,0)","v":1.0072592104450255},1.1000000000000001,"2021-11-23",4,4741171,"2021-11-23",4334493.12,{"$f":"IFERROR(((VLOOKUP(K37,'Housing Index'!C:F,4,0)*(K37)+1)*N37),N37)","v":6666024.2977494122},6016348.1515206732,3,{"$f":"SUM($I$17:I37)","v":40.427}]
[119831,"Montgomery","SR-237 ","From West of I-24 to East of International Boulevard Serving Hankook Tire (Includes I-24 Ramp Modifications)",null,"Widen","Legislative",{"$f":"VLOOKUP(B38,ROW_Zillow!B:F,5,0)","v":0.97854843249105894},1.02,"2014-02-26",11,3101354,"2014-02-13",2795051,{"$f":"IFERROR(((VLOOKUP(K38,'Housing Index'!C:F,4,0)*(K38)+1)*N38),N38)","v":6664934.980034722},6677492.6651225323,3,{"$f":"SUM($I$17:I38)","v":41.447000000000003}]
[101599.01,"Madison","SR-18 ","From North of Medon-Malesus Road to  SR-5 (US-45) in Jackson (EPD) (IA)~","Widen from current 2 lanes without shoulders to 2 lanes with shoulders and to 3 lanes with sidewalks","Construction-New","Legislative",{"$f":"VLOOKUP(B39,ROW_Zillow!B:F,5,0)","v":0.63833343630085737},4.99,"2017-05-15",8,16650000,"2013-01-02",9892000,{"$f":"IFERROR(((VLOOKUP(K39,'Housing Index'!C:F,4,0)*(K39)+1)*N39),N39)","v":20025737.700085491},6286955.4680529162,3,{"$f":"SUM($I$17:I39)","v":46.437000000000005}]
[124885,"Wilson","SR-171 ","(South Mt. Juliet Road), From south of SR-265 (Central Pike) to near Providence Way (IA)","Widen South Mt. Juliet Road from 2 lanes to 5 lanes","Widen","Legislative",{"$f":"VLOOKUP(B40,ROW_Zillow!B:F,5,0)","v":1.4167027053000816},1.46,"2022-05-10",3,9312025.9100000001,"2022-05-10",10785416.1,{"$f":"IFERROR(((VLOOKUP(K40,'Housing Index'!C:F,4,0)*(K40)+1)*N40),N40)","v":13254034.261461239},6407911.5714063663,3,{"$f":"SUM($I$17:I40)","v":47.897000000000006}]
[126690,"Gibson","SIA ","Industrial Access Road Serving Project Phoenix (Tyson Foods)",null,"Construction-New","Economic Development",{"$f":"VLOOKUP(B41,ROW_Zillow!B:F,5,0)","v":0.32247712404840845},0.33,"2019-04-26",6,82000,"2019-04-26",334080,{"$f":"IFERROR(((VLOOKUP(K41,'Housing Index'!C:F,4,0)*(K41)+1)*N41),N41)","v":593915.19544395548},5580994.3784622299,3,{"$f":"SUM($I$17:I41)","v":48.227000000000004}]
[100260.04,"Cumberland","SR-28 ","From near Hollow Lane to near Lowe Road (EPD) (IA)~","Widen from existing 2 lane to a 4 lane facility.","Widen","Legislative",{"$f":"VLOOKUP(B42,ROW_Zillow!B:F,5,0)","v":0.85118446975157369},3.05,"2020-04-27",5,4780560,"2020-04-27",8239150,{"$f":"IFERROR(((VLOOKUP(K42,'Housing Index'!C:F,4,0)*(K42)+1)*N42),N42)","v":13784774.191780154},5309775.0913908379,3,{"$f":"SUM($I$17:I42)","v":51.277000000000001}]
[100241.03,"Knox","SR-115 ","From Woodson Drive to Cherokee Trail Interchange (IA)","Widening from 4-ln to 6-ln including pedestrian and bicycle facilities.","Widen","Legislative",{"$f":"VLOOKUP(B43,ROW_Zillow!B:F,5,0)","v":1.0314909011031255},1.6,"2017-07-11",8,4253166.25,"2017-07-17",4125000.61,{"$f":"IFERROR(((VLOOKUP(K43,'Housing Index'!C:F,4,0)*(K43)+1)*N43),N43)","v":8350806.7355997413},5059912.9901854871,3,{"$f":"SUM($I$17:I43)","v":52.877000000000002}]
[101423,"Blount","SR-162 EXT","(Pellissippi Parkway), From near SR-33 to SR-73 (US-321)~","Construct new 4 lane","Stage Construction-New","Legislative",{"$f":"VLOOKUP(B44,ROW_Zillow!B:F,5,0)","v":1.0793158837702588},4.9000000000000004,"2023-02-22",2,6575765,"2023-02-22",23230764.219999999,{"$f":"IFERROR(((VLOOKUP(K44,'Housing Index'!C:F,4,0)*(K44)+1)*N44),N44)","v":25589425.500176437},4838557.2873135824,3,{"$f":"SUM($I$17:I44)","v":57.777000000000001}]
[128962,"Anderson","SIA ","State Industrial Access Serving Norris Industrial Park","Constructing a new two lane access road connecting SR-71 to Sawmill Rd, approximately .25 miles, including a tie-in to the existing church, and a box culvert on the new roadway for  stream mitigation.","Construction-New","Economic Development",{"$f":"VLOOKUP(B45,ROW_Zillow!B:F,5,0)","v":0.84670195020490535},0.25,"2022-05-04",3,206080,"2022-05-04",905431.84,{"$f":"IFERROR(((VLOOKUP(K45,'Housing Index'!C:F,4,0)*(K45)+1)*N45),N45)","v":1112671.4553718416},5256496.4807395115,3,{"$f":"SUM($I$17:I45)","v":58.027000000000001}]
[101589.01,"Coffee","SR-55 ","From First Avenue to SR-16 (US-41A, N Jackson Street) in Tullahoma (IA)","Widen from 2-ln to 4-ln at 11' lanes with a 11' continuous center turn lane with 10' paved shoulder; bike lanes and 5' sidewalks on each side.","Widen","Legislative",{"$f":"VLOOKUP(B46,ROW_Zillow!B:F,5,0)","v":0.84801993451265467},0.64,"2016-07-26",9,3830300,"2016-07-26",1188957.6599999999,{"$f":"IFERROR(((VLOOKUP(K46,'Housing Index'!C:F,4,0)*(K46)+1)*N46),N46)","v":2559452.9277318032},4715862.253732509,3,{"$f":"SUM($I$17:I46)","v":58.667000000000002}]
[126525,"Grundy","SR-108 ","From near 40th Avenue (LM 8.05) to near 32nd Avenue (LM 8.35) in Gruetli-Laager","Widen from 2-Lane with 12' travel lanes to 3-Lane with 12' travel lanes and 2' shoulders on both sides (business area frontage improvement)","Widen","Other",{"$f":"VLOOKUP(B47,ROW_Zillow!B:F,5,0)","v":0.76640959108163953},0.3,"2020-08-21",5,578700,"2020-08-21",528700,{"$f":"IFERROR(((VLOOKUP(K47,'Housing Index'!C:F,4,0)*(K47)+1)*N47),N47)","v":884558.49392160203},3847196.5217850772,3,{"$f":"SUM($I$17:I47)","v":58.966999999999999}]
[101410.01,"Grainger","SR-1 ","From West of Helton Road to Bean Station (IA)~","Widen 2-ln to 5-ln","Widen","Legislative",{"$f":"VLOOKUP(B48,ROW_Zillow!B:F,5,0)","v":0.53198171296773},4.62,"2017-08-28",8,4182264.74,"2017-08-28",3600418.87,{"$f":"IFERROR(((VLOOKUP(K48,'Housing Index'!C:F,4,0)*(K48)+1)*N48),N48)","v":7288823.6859136876},2965642.2881197487,3,{"$f":"SUM($I$17:I48)","v":63.586999999999996}]
[112152.04,"Hamilton","SR-317 ","(Bonny Oaks Drive), From West of Bonnyshire Drive to Near I-75 (IA) (#1 Priority)~","Upgrading the existing two (2) lane sections of Bonny Oaks Drive to an improved five (5) lane urban section including sidewalks, curb and gutters and bike lanes. The typical section would consist of five (5) twelve (12) foot lanes with six (6) foot bike lanes, two (2) foot curb and gutter and five (5) foot sidewalks on both sides.","Widen","Legislative",{"$f":"VLOOKUP(B49,ROW_Zillow!B:F,5,0)","v":1.5713238877791278},2.11,"2022-04-08",{"$f":"IFERROR(YEAR(TODAY())-YEAR(J49),\"\")","v":3},20180000,"2022-04-08",9063650,{"$f":"IFERROR(((VLOOKUP(K49,'Housing Index'!C:F,4,0)*(K49)+1)*N49),N49)","v":11138182.015424807},{"$f":"O49/(I49*H49)","v":3359434.2261781371},3,{"$f":"SUM($I$17:I49)","v":65.697000000000003}]
[101419.02,"Hamblen","SR-34 ","From West of Old Stagecoach Road  in Russellville to Steadman Road (EPD) (IA)~","Construct 5 lane roadway in a 5 lane ROW on new alignment","Construction-New","Legislative",{"$f":"VLOOKUP(B50,ROW_Zillow!B:F,5,0)","v":0.67698744482656836},3.7,"2017-08-29",8,439200,"2017-08-29",3125003.84,{"$f":"IFERROR(((VLOOKUP(K50,'Housing Index'!C:F,4,0)*(K50)+1)*N50),N50)","v":6326375.5773958676},2525646.8937500683,3,{"$f":"SUM($I$17:I50)","v":69.397000000000006}]
[115906,"Rutherford","SR-268 ","From SR-1(US 41/70S) to SR-10 (IA)","Widen SR-268 (Thompson Lane) from 2 to 5 lanes including sidewalks and bike lanes. Interconnect traffic signals into existing fiber optic to provide for coordinated arterial signal system.","Widen","Legislative",{"$f":"VLOOKUP(B51,ROW_Zillow!B:F,5,0)","v":1.2396786497982979},4.3,"2017-06-20",8,908823.49,"2017-11-27",6542526.1500000004,{"$f":"IFERROR(((VLOOKUP(K51,'Housing Index'!C:F,4,0)*(K51)+1)*N51),N51)","v":13244936.572568761},2484690.5349828345,3,{"$f":"SUM($I$17:I51)","v":73.697000000000003}]
[132132.03,"Tipton","SR-194 EXT","New route from Northern Interchange to SR-1 (Project Blue Oval, G2 North)","2-Lane from Northern Interchange to SR-1","Construction-New","Legislative",{"$f":"VLOOKUP(B52,ROW_Zillow!B:F,5,0)","v":0.52846708814706511},2.5,"2022-09-27",3,1200000,"2022-09-27",2703664.2,{"$f":"IFERROR(((VLOOKUP(K52,'Housing Index'!C:F,4,0)*(K52)+1)*N52),N52)","v":3322491.9285484212},2514814.6426282786,3,{"$f":"SUM($I$17:I52)","v":76.197000000000003}]
[106634.03,"Sumner","SR-109 PROP","(Portland Bypass), from existing SR-109, south of Portland, to SR-52, west of Portland (IA)","Construct new 4-ln divided roadway.","Construction-New","Legislative",{"$f":"VLOOKUP(B53,ROW_Zillow!B:F,5,0)","v":1.0072592104450255},3.75,"2020-06-22",5,351434,"2020-06-22",4994415.96,{"$f":"IFERROR(((VLOOKUP(K53,'Housing Index'!C:F,4,0)*(K53)+1)*N53),N53)","v":8356067.8259799741},2212225.7413860359,3,{"$f":"SUM($I$17:I53)","v":79.947000000000003}]
[100241.02,"Knox","SR-115 ","From South of Topside Road to North of Maloney Road (IA)","Widen 4-ln to 6-ln including pedestrian & bicycle facilities","Widen","Legislative",{"$f":"VLOOKUP(B54,ROW_Zillow!B:F,5,0)","v":1.0314909011031255},2.2000000000000002,"2017-05-11",8,293749.15000000002,"2019-03-25",2285000.14,{"$f":"IFERROR(((VLOOKUP(K54,'Housing Index'!C:F,4,0)*(K54)+1)*N54),N54)","v":4625840.421380775},2038461.7399364184,3,{"$f":"SUM($I$17:I54)","v":82.147000000000006}]
[101244.03,"Roane","SR-1 ","From SR-382 to near Ruritan Road (IA)~","Widen 2-ln to 5 ln with center turn lane","Widen","Legislative",{"$f":"VLOOKUP(B55,ROW_Zillow!B:F,5,0)","v":0.90934052733101312},3.5,"2017-06-19",8,6116000,"2017-06-19",2972616,{"$f":"IFERROR(((VLOOKUP(K55,'Housing Index'!C:F,4,0)*(K55)+1)*N55),N55)","v":6017875.8895144891},1890813.2427974036,3,{"$f":"SUM($I$17:I55)","v":85.647000000000006}]
[125204,"Lawrence","Weakly Creek Road","Weakley Creek Road, From SR-6/US-43 (North Locust Ave) to Springer Road; (05958) Old Military Road, From Weakley Creek Road/Hicks St to SR-6/US-43 (North Locust Ave)","Widen and Resurfacing of Weakley Creek Road, From SR-6 (North Locust Ave) to Springer Road ;Old North Military Ave from Weakley Creek Road to SR-6 (North Locust Ave) a distance of 1,535 feet","Widen and Resurfacing","Local Programs",{"$f":"VLOOKUP(B56,ROW_Zillow!B:F,5,0)","v":0.63126643190071186},0.5,"2023-03-28",2,1243205,"2023-03-28",518995.02,{"$f":"IFERROR(((VLOOKUP(K56,'Housing Index'!C:F,4,0)*(K56)+1)*N56),N56)","v":571689.51798059186},1811246.3742425307,3,{"$f":"SUM($I$17:I56)","v":86.147000000000006}]
[101463.03,"Montgomery","SR-374 PROP","SR-76 (US-79) to Dotsonville Road in Clarksville (Re-Budgeted ROW & Stage Const.) (IA)~","Construct Four-Lane Divided.","Construction-New","Legislative",{"$f":"VLOOKUP(B57,ROW_Zillow!B:F,5,0)","v":0.97854843249105894},2.9,"2022-08-05",3,293045,"2022-08-05",4588390.4400000004,{"$f":"IFERROR(((VLOOKUP(K57,'Housing Index'!C:F,4,0)*(K57)+1)*N57),N57)","v":5638603.4189929133},1986969.6194797656,3,{"$f":"SUM($I$17:I57)","v":89.047000000000011}]
[112219,"Franklin","SR-97 ","Intersection at Beans Creek Road, LM 4.70","Widen the curve of SR-97 to the inside at the intersection of Beans Creek Road to permit large vehicles to turn without crossing the center line.","Widen","Local Programs",{"$f":"VLOOKUP(B58,ROW_Zillow!B:F,5,0)","v":0.56362020085531694},8.8999999999999996E-2,"2014-02-04",11,61500,"2013-11-07",32500,{"$f":"IFERROR(((VLOOKUP(K58,'Housing Index'!C:F,4,0)*(K58)+1)*N58),N58)","v":77497.829861111109},1544944.8617162653,3,{"$f":"SUM($I$17:I58)","v":89.13600000000001}]
[126523,"Sumner","SIA ","Industrial Access Road Serving Project Cardinal",null,"Construction-New","Economic Development",{"$f":"VLOOKUP(B59,ROW_Zillow!B:F,5,0)","v":1.0072592104450255},0.16,"2019-02-11",6,114310,"2019-02-11",132236.51999999999,{"$f":"IFERROR(((VLOOKUP(K59,'Housing Index'!C:F,4,0)*(K59)+1)*N59),N59)","v":235085.24491327981},1458693.8153276779,3,{"$f":"SUM($I$17:I59)","v":89.296000000000006}]
[117459,"Lincoln","SIA ","Industrial Access Road serving PepsiCo Frito-Lay in Fayetteville",null,"Construction-New","Other",{"$f":"VLOOKUP(B60,ROW_Zillow!B:F,5,0)","v":0.68707826218277424},0.56399999999999995,"2014-07-17",11,"","00:00:00",242054,{"$f":"IFERROR(((VLOOKUP(K60,'Housing Index'!C:F,4,0)*(K60)+1)*N60),N60)","v":577189.52951388888},1489474.7031819574,3,{"$f":"SUM($I$17:I60)","v":89.86}]
[101885.01,"Hardin","SR-128 ","From Pyburns Drive to SR-226 (Airport Road) (IA)","Left-turn lane at Pyburns Drive and SR-226, Truck Climbing Lane for steep vertical curve just north of Hatley Creek. re-align two(2) intersections.","Widen","Legislative",{"$f":"VLOOKUP(B61,ROW_Zillow!B:F,5,0)","v":0.51020064938185161},3.4,"2015-04-09",10,745500,"2014-09-04",984300,{"$f":"IFERROR(((VLOOKUP(K61,'Housing Index'!C:F,4,0)*(K61)+1)*N61),N61)","v":2230475.8958622054},1285812.4016643965,3,{"$f":"SUM($I$17:I61)","v":93.26}]
[132365,"Maury","SR-99 ","Industrial Access Support for State Route 99 (Hampshire Pike)","turn lane addition and bridge replacement (Bridge No. 60SR0990023 over East Fork Greenlick Creek)","Widen","Economic Development",{"$f":"VLOOKUP(B62,ROW_Zillow!B:F,5,0)","v":1.1169779718143564},0.3,"2023-04-10",2,263333,"2023-04-10",365530.5,{"$f":"IFERROR(((VLOOKUP(K62,'Housing Index'!C:F,4,0)*(K62)+1)*N62),N62)","v":402643.46920362499},1201585.8246204371,3,{"$f":"SUM($I$17:I62)","v":93.56}]
[128559,"Cheatham","SIA ","State Industrial Access Road serving Caymas Boats and Nashville Fabrication",null,"Construction-New","Economic Development",{"$f":"VLOOKUP(B63,ROW_Zillow!B:F,5,0)","v":1.0109042607961449},0.18,"2020-09-16",5,32120.400000000001,"2020-09-16",115691.1,{"$f":"IFERROR(((VLOOKUP(K63,'Housing Index'!C:F,4,0)*(K63)+1)*N63),N63)","v":193560.70583721099},1063737.9783168414,3,{"$f":"SUM($I$17:I63)","v":93.740000000000009}]
[128975,"Carroll","SIA ","State Industrial Access Serving Pottery Direct International","SIA standard of two 12' lanes with 4' gravel   shoulders. The proposed road will be constructed on a 10\" stone base with 3\" of base   (\"A\" mix), 2\" of binder (\"BM-2\" mix) and 1.25\" of asphalt surface (\"D\" mix).","Construction-New","Economic Development",{"$f":"VLOOKUP(B64,ROW_Zillow!B:F,5,0)","v":0.47069544265738589},0.6,"2021-07-07",4,21929.16,"2021-07-07",165300,{"$f":"IFERROR(((VLOOKUP(K64,'Housing Index'!C:F,4,0)*(K64)+1)*N64),N64)","v":254215.14947934161},900140.25503812544,2,{"$f":"SUM($I$17:I64)","v":94.34}]
[121356,"Madison","SR-223 ","From 0.74 Miles North of Old Denmark-Jackson Road to near Golden Drive","Extend the right turn lane on SR-223 in front of Nexus Corp., and add a center turn lane on SR-223 in front of Pacific Industries. Project now shows on contract as: Serving Pacific Industries and Project Nexus.","Widen and Resurfacing","Safety",{"$f":"VLOOKUP(B65,ROW_Zillow!B:F,5,0)","v":0.63833343630085737},0.23,"2016-12-09",9,16000,"2016-12-09",42630,{"$f":"IFERROR(((VLOOKUP(K65,'Housing Index'!C:F,4,0)*(K65)+1)*N65),N65)","v":91769.019183750221},625058.49277409504,2,{"$f":"SUM($I$17:I65)","v":94.570000000000007}]
[118596,"Scott","SR-63 ","From Water Plant Road to Park Road in Huntsville",null,"Widen","Other",{"$f":"VLOOKUP(B66,ROW_Zillow!B:F,5,0)","v":0.4859483652189433},0.156,"2014-12-26",11,629400,"2014-12-10",17100,{"$f":"IFERROR(((VLOOKUP(K66,'Housing Index'!C:F,4,0)*(K66)+1)*N66),N66)","v":40775.78125},537882.68846888666,2,{"$f":"SUM($I$17:I66)","v":94.726000000000013}]
[101406.04,"Campbell","SR-63 ","(Howard Baker Hwy.) From Near the Intersection of SR-297 and West of Old SR-63 to West of Stinking Creek Road (Truck Climbing Lane) (***) (IA)","Construct truck climbing lane and intersection improvements at the intersection of SR-297 and SR-63.","Widen","Legislative",{"$f":"VLOOKUP(B67,ROW_Zillow!B:F,5,0)","v":0.56782814033787077},0.876,"2017-01-10",8,141484.79999999999,"2017-01-10",120000.84,{"$f":"IFERROR(((VLOOKUP(K67,'Housing Index'!C:F,4,0)*(K67)+1)*N67),N67)","v":242934.22418418183},488391.03599413356,2,{"$f":"SUM($I$17:I67)","v":95.602000000000018}]
[101409,"Claiborne","SR-63 ","From Campbell County Line to Hall Lane (IA)","Widen From 2-LN to 5-LN","Widen","Legislative",{"$f":"VLOOKUP(B68,ROW_Zillow!B:F,5,0)","v":0.49524976489082012},5.35,"2019-05-29",6,5786950,"2019-05-29",636112.19999999995,{"$f":"IFERROR(((VLOOKUP(K68,'Housing Index'!C:F,4,0)*(K68)+1)*N68),N68)","v":1130856.9851151954},426805.12418074132,2,{"$f":"SUM($I$17:I68)","v":100.95200000000001}]
[121394,"Maury","SR-247 ","Industrial Access Road Serving Project Shotgun in Spring Hill",null,"Widen and Resurfacing","Economic Development",{"$f":"VLOOKUP(B69,ROW_Zillow!B:F,5,0)","v":1.1169779718143564},0.52,"2015-09-09",10,1081308,"2015-09-09",110072.4,{"$f":"IFERROR(((VLOOKUP(K69,'Housing Index'!C:F,4,0)*(K69)+1)*N69),N69)","v":249429.88418135021},429438.06082025997,2,{"$f":"SUM($I$17:I69)","v":101.47200000000001}]
[119592,"Sumner","SIA ","Industrial Access Road serving ABC and other industries in Gallatin","SIA will serve: ABC Fuels, ABC Tech, Salga, Hoeganeas, Servpro and ITW CIP industries located on Airport Rd between Coles Ferry and Steam Plant Rd.","Widen and Resurfacing","Economic Development",{"$f":"VLOOKUP(B70,ROW_Zillow!B:F,5,0)","v":1.0072592104450255},1.17,"2015-09-17",10,505260,"2015-09-17",201710,{"$f":"IFERROR(((VLOOKUP(K70,'Housing Index'!C:F,4,0)*(K70)+1)*N70),N70)","v":457085.53586748498},387855.87078894203,2,{"$f":"SUM($I$17:I70)","v":102.64200000000001}]
[128996,"Giles","SIA ","State Industrial Access Serving Integrity Mold and Murco Wall Products","Widen Tarpley Shop Road 0.78 miles","Construction-New","Economic Development",{"$f":"VLOOKUP(B71,ROW_Zillow!B:F,5,0)","v":0.68010736080506873},0.78,"2021-06-22",4,517465.4,"2021-06-22",103701,{"$f":"IFERROR(((VLOOKUP(K71,'Housing Index'!C:F,4,0)*(K71)+1)*N71),N71)","v":159481.94323144105},300634.9314347473,2,{"$f":"SUM($I$17:I71)","v":103.42200000000001}]
[101407.01,"Campbell","SR-63 ","(General Carl W. Stiner Hwy.), From Near Myers Lane (LaFollette City Limits) to Near Frontier Road/Woodson Lane (IA)","Widen 2-ln to 5-ln","Widen","Legislative",{"$f":"VLOOKUP(B72,ROW_Zillow!B:F,5,0)","v":0.56782814033787077},4.92,"2018-06-20",7,4399898.57,"2018-06-20",380000.34,{"$f":"IFERROR(((VLOOKUP(K72,'Housing Index'!C:F,4,0)*(K72)+1)*N72),N72)","v":715384.83372625348},256069.41812104901,2,{"$f":"SUM($I$17:I72)","v":108.34200000000001}]
[124081,"Hamilton","I-75 ","From North of SR-2 in Hamilton County to near SR-311 in Bradley County (IA)~","WIDEN I-75 FROM 4 TO 6 LANES FROM APD-40/SR 311 (EXIT 20) TO HAMILTON COUNTY LINE. FULL PROJECT EXTENDS TO US 64 IN HAMILTON COUNTY; DETAILS ON THE PORTION IN HAMILTON COUNTY CAN BE FOUND IN THE TIP FOR THE CHATTANOOGA/HAMILTON COUNTY/NORTH GEORGIA TRANSPORTATION PLANNING ORGANIZATION.","Widen","Legislative",{"$f":"VLOOKUP(B73,ROW_Zillow!B:F,5,0)","v":1.5713238877791278},8.5299999999999994,"2022-08-31",3,124900,"2022-08-31",3361325,{"$f":"IFERROR(((VLOOKUP(K73,'Housing Index'!C:F,4,0)*(K73)+1)*N73),N73)","v":4130681.3108403115},308181.7703886322,2,{"$f":"SUM($I$17:I73)","v":116.87200000000001}]
[120361,"Hamilton","SIA ","Industrial Access Road serving Volkswagen Group of America Supplier Park in Chattanooga","Construction of a four-lane Roadway with bicycle and pedestrian facilities.","Construction-New","Economic Development",{"$f":"VLOOKUP(B74,ROW_Zillow!B:F,5,0)","v":1.5713238877791278},1.34,"2016-06-20",9,57000,"2016-04-22",235000,{"$f":"IFERROR(((VLOOKUP(K74,'Housing Index'!C:F,4,0)*(K74)+1)*N74),N74)","v":505881.29270892101},240258.13882422048,2,{"$f":"SUM($I$17:I74)","v":118.21200000000002}]
[132406,"Maury","SIA ","State Industrial Access serving Project Leeward","Section 1: New SIA access road from Oakland Blvd. to serve Project Leeward with cul-de-sac and connection to SR-6/US-43,  Section 2: right-in only entrance with deceleration lane to Columbia Tennessee Rail Site from SR-6/US-43, Section 3: dual left lanes on Oakland Blvd to SR-6/US-43, extend the right turn lane on SR-6/US-43 toward Oakland Blvd and installation of traffic signals on intersections of Hampshire Pike/SR-99 and on SR-6/US-43.","Construction-New","Economic Development",{"$f":"VLOOKUP(B75,ROW_Zillow!B:F,5,0)","v":1.1169779718143564},1.32,"2022-07-14",3,1897609.66,"2022-07-14",262327.62,{"$f":"IFERROR(((VLOOKUP(K75,'Housing Index'!C:F,4,0)*(K75)+1)*N75),N75)","v":322370.43346038216},218643.54670493372,2,{"$f":"SUM($I$17:I75)","v":119.53200000000001}]
[117511,"Fentress","SIA ","Industrial Access Road serving Clarkrange Regional Business Park",null,"Construction-New","Economic Development",{"$f":"VLOOKUP(B76,ROW_Zillow!B:F,5,0)","v":0.55337836446384814},0.99299999999999999,"2014-02-06",11,78000,"2013-11-11",47500,{"$f":"IFERROR(((VLOOKUP(K76,'Housing Index'!C:F,4,0)*(K76)+1)*N76),N76)","v":113266.05902777778},206123.9071254718,2,{"$f":"SUM($I$17:I76)","v":120.52500000000001}]
[123070,"Moore","SR-55 ","From near Goodbranch Road to near Moore County High School (IA)","Widen from 2-lanes to a 3 lane facility.","Widen","Legislative",{"$f":"VLOOKUP(B77,ROW_Zillow!B:F,5,0)","v":0.92590113744791558},0.56999999999999995,"2020-08-14",5,673813.57,"2020-08-14",60478.92,{"$f":"IFERROR(((VLOOKUP(K77,'Housing Index'!C:F,4,0)*(K77)+1)*N77),N77)","v":101186.19706677709},191726.34830766462,2,{"$f":"SUM($I$17:I77)","v":121.095}]
[103899,"Loudon","SR-73 ","From Simpson Road East to North of SR-2(US-11) in Lenoir City","Widen from 4-lanes to 6-lanes","Widen","Legislative",{"$f":"VLOOKUP(B78,ROW_Zillow!B:F,5,0)","v":1.1243882012946449},1.2809999999999999,"2017-05-15",8,1921518,"2017-05-15",90000.63,{"$f":"IFERROR(((VLOOKUP(K78,'Housing Index'!C:F,4,0)*(K78)+1)*N78),N78)","v":182200.66813813639},126498.26116005916,2,{"$f":"SUM($I$17:I78)","v":122.376}]
[101407.02,"Campbell","SR-63 ","(General Carl W. Stiner Highway), From Near Frontier Road/Woodson Lane to Near Claiborne County Line (IA)","Widen From 2-LN to 5-LN","Widen","Legislative",{"$f":"VLOOKUP(B79,ROW_Zillow!B:F,5,0)","v":0.56782814033787077},5.26,"2019-09-13",6,2203000,"2019-09-13",206233.85,{"$f":"IFERROR(((VLOOKUP(K79,'Housing Index'!C:F,4,0)*(K79)+1)*N79),N79)","v":366634.98961299506},122752.75661170896,1,{"$f":"SUM($I$17:I79)","v":127.63600000000001}]
[127751,"Weakley","SIA ","State Industrial Access serving Project Dove",null,"Construction-New","Economic Development",{"$f":"VLOOKUP(B80,ROW_Zillow!B:F,5,0)","v":0.5682709006912553},1.7,"2022-05-19",3,286400,"2022-05-19",104400,{"$f":"IFERROR(((VLOOKUP(K80,'Housing Index'!C:F,4,0)*(K80)+1)*N80),N80)","v":128295.57655142793},132802.83420270446,1,{"$f":"SUM($I$17:I80)","v":129.33600000000001}]
[117211,"Lincoln","SIA ","Industrial Access Road serving General Products Partners, LLC","Grading, base, drainage, paving, guardrail, striping and signs for relocating approximately 3,250 linear feet of McDougal Road and extending the current Industrial park entrance approximately 1000 feet to tie into the newly relocated McDougal Road.  (New business moving in instead of General Products-Hirotec).","Construction-New","Economic Development",{"$f":"VLOOKUP(B81,ROW_Zillow!B:F,5,0)","v":0.68707826218277424},0.75,"2014-07-17",{"$f":"IFERROR(YEAR(TODAY())-YEAR(J81),\"\")","v":11},"",null,20615,{"$f":"IFERROR(((VLOOKUP(K81,'Housing Index'!C:F,4,0)*(K81)+1)*N81),N81)","v":49157.469618055555},{"$f":"O81/(I81*H81)","v":95394.216978790791},1,{"$f":"SUM($I$17:I81)","v":130.08600000000001}]
[114152,"Benton","I-40 ","West of SR-191 to West of Tennessee River (WB Truck Climbing Lane)","I-40, West of SR-191 to West of Tennessee River (WB Truck Climbing Lane) - Widen","Widen","Legislative",{"$f":"VLOOKUP(B82,ROW_Zillow!B:F,5,0)","v":0.51043061018554747},2.1110000000000002,"2014-10-30",11,"",null,29200,{"$f":"IFERROR(((VLOOKUP(K82,'Housing Index'!C:F,4,0)*(K82)+1)*N82),N82)","v":69628.819444444453},64619.57355250432,1,{"$f":"SUM($I$17:I82)","v":132.197}]
[120852,"Sumner","SIA ","Industrial Access Road serving Beretta USA in Gallatin","Extend Gateway Blvd. 1060 ft. and a 1750 ft. connection between Gateway Blvd. and Commerce Drive","Construction-New","Economic Development",{"$f":"VLOOKUP(B83,ROW_Zillow!B:F,5,0)","v":1.0072592104450255},0.53,"2016-01-25",9,39805.199999999997,"2015-11-24",13050,{"$f":"IFERROR(((VLOOKUP(K83,'Housing Index'!C:F,4,0)*(K83)+1)*N83),N83)","v":28092.556892984761},52622.824171513748,1,{"$f":"SUM($I$17:I83)","v":132.727}]
[114149.01,"Madison","I-40 ","From East of SR-5(US-45) to East of SR-1(US-70) in Jackson (IA)","Widen 4-ln to 6-ln on existing alignment.","Widen","Legislative",{"$f":"VLOOKUP(B84,ROW_Zillow!B:F,5,0)","v":0.63833343630085737},5.5,"2018-06-28",7,"",null,24969,{"$f":"IFERROR(((VLOOKUP(K84,'Housing Index'!C:F,4,0)*(K84)+1)*N84),N84)","v":47006.389292469641},13388.95277759869,1,{"$f":"SUM($I$17:I84)","v":138.227}]

{"sheet":"Bridges_Projects_ROW","index":38,"n_rows":97,"n_cols":15,"rows_kept":97,"cut":false,"hidden":true,"merged":[]}
["ROW Impacts","Average",null,null,null,null,null,null,null,null,null,"Max","Min","Count"]
["Very Low",{"$f":"AVERAGEIF($J$9:$J$97,1,$I$9:$I$97)","v":52831.502722448291},{"$f":"COUNTIF(J:J,1)","v":21},{"$f":"C2/$C$7","v":0.23595505617977527},null,null,null,null,null,null,null,10000000,1380000,{"$f":"COUNTIFS(I9:I97,\">=\"&M2,I9:I97,\"<=\"&L2)","v":9},5]
["Low",{"$f":"AVERAGEIF($J$9:$J$97,2,$I$9:$I$97)","v":119021.94117333644},{"$f":"COUNTIF(J:J,2)","v":21},{"$f":"C3/$C$7","v":0.23595505617977527},null,null,null,null,null,null,null,{"$f":"M2","v":1380000},617108.375510204,{"$f":"COUNTIFS(I10:I98,\">=\"&M3,I10:I98,\"<=\"&L3)","v":10},4]
["Moderate",{"$f":"AVERAGEIF($J$9:$J$97,3,$I$9:$I$97)","v":225947.871462298},{"$f":"COUNTIF(J:J,3)","v":19},{"$f":"C4/$C$7","v":0.21348314606741572},null,null,null,null,null,null,null,{"$f":"M3","v":617108.375510204},369421.39076923078,{"$f":"COUNTIFS(I11:I99,\">=\"&M4,I11:I99,\"<=\"&L4)","v":3},4]
["High",{"$f":"AVERAGEIF($J$9:$J$97,4,$I$9:$I$97)","v":685720.14286045008},{"$f":"COUNTIF(J:J,4)","v":21},{"$f":"C5/$C$7","v":0.23595505617977527},null,null,null,null,null,null,null,{"$f":"M4","v":369421.39076923078},275000,10,3]
["Very High",{"$f":"AVERAGEIF($J$9:$J$97,5,$I$9:$I$97)","v":3448973.3166555995},{"$f":"COUNTIF(J:J,5)","v":7},{"$f":"C6/$C$7","v":7.8651685393258425E-2},null,null,null,null,null,null,null,275000,212000,7,3]
[null,null,{"$f":"SUM(C2:C6)","v":89},null,null,null,null,"Calibration Factor",1,null,null,212000,168300,9,3]
["PIN","Description","County","Route","Estimate Date","HVI","Years","ROW Cost","Inflated ROW","Group",null,168300,122200,7,3]
[124238,"(Broadway), Bridge over 11th Ave South and CSX R/R, LM 17.29 (IA)","Davidson","SR-1 ","2022-02-09",{"$f":"VLOOKUP(C9,ROW_Zillow!B:F,5,0)","v":1.4256299896346025},{"$f":"IFERROR(YEAR(TODAY())-YEAR(E9),\"\")","v":3},8973133.0199999996,{"$f":"IFERROR(((VLOOKUP(G9,'Housing Index'!C:F,4,0)*(G9)+1)*H9*$I$7),H9*$I$7)/F9","v":7734788.9366525281},5,null,122200,95000,8,3]
[83910.01,"Bridge over Clinch River in Clinton, LM 10.71","Anderson","SR-9 ","2016-04-15",{"$f":"VLOOKUP(C10,ROW_Zillow!B:F,5,0)","v":0.84670195020490535},9,2206474.86,{"$f":"IFERROR(((VLOOKUP(G10,'Housing Index'!C:F,4,0)*(G10)+1)*H10*$I$7),H10*$I$7)/F10","v":5609823.2865763502},5,null,95000,77000,7,3]
[124362,"(Main Street), Bridge over Greasy Rock Creek, LM 11.77 (IA)","Hancock","SR-33 ","2019-11-25",{"$f":"VLOOKUP(C11,ROW_Zillow!B:F,5,0)","v":0.39568360139212094},6,676054.92,{"$f":"IFERROR(((VLOOKUP(G11,'Housing Index'!C:F,4,0)*(G11)+1)*H11*$I$7),H11*$I$7)/F11","v":3037441.2446013242},5,null,77000,60000,4,2]
[124490,"(South Main Street) Bridge over Sweetwater Creek, LM 2.28  (IA)","Monroe","SR-2 ","2022-06-07",{"$f":"VLOOKUP(C12,ROW_Zillow!B:F,5,0)","v":0.67276920859161016},3,1356505.26,{"$f":"IFERROR(((VLOOKUP(G12,'Housing Index'!C:F,4,0)*(G12)+1)*H12*$I$7),H12*$I$7)/F12","v":2477801.7757523227},5,null,60000,40000,11,2]
[124424,"(East Meeting Street) Bridge over Rimmer Creek, LM 13.23 (IA)","Jefferson","SR-9 ","2019-07-10",{"$f":"VLOOKUP(C13,ROW_Zillow!B:F,5,0)","v":1.0377307330601262},6,1112622.6000000001,{"$f":"IFERROR(((VLOOKUP(G13,'Housing Index'!C:F,4,0)*(G13)+1)*H13*$I$7),H13*$I$7)/F13","v":1906062.5932992839},5,null,40000,0,4,1]
[124331,"Bridge over Williams Creek, LM 7.73 (IA)","Grainger","SR-131 ","2019-10-27",{"$f":"VLOOKUP(C14,ROW_Zillow!B:F,5,0)","v":0.53198171296773},6,516056.76,{"$f":"IFERROR(((VLOOKUP(G14,'Housing Index'!C:F,4,0)*(G14)+1)*H14*$I$7),H14*$I$7)/F14","v":1724545.7804096779},5]
[122156,"Fort Robinson Drive, Bridge over Dry Hollow, LM 0.39 in Kingsport (IA)","Sullivan",null,"2019-05-29",{"$f":"VLOOKUP(C15,ROW_Zillow!B:F,5,0)","v":0.64268038194086918},6,597341.96,{"$f":"IFERROR(((VLOOKUP(G15,'Housing Index'!C:F,4,0)*(G15)+1)*H15*$I$7),H15*$I$7)/F15","v":1652349.5992977107},5]
[124721,"(Nashville Pike) Bridge over East Fork Station Camp Creek, LM 11.91 in Gallatin (IA)","Sumner","SR-6 ","2022-09-13",{"$f":"VLOOKUP(C16,ROW_Zillow!B:F,5,0)","v":1.0072592104450255},3,1295028.06,{"$f":"IFERROR(((VLOOKUP(G16,'Housing Index'!C:F,4,0)*(G16)+1)*H16*$I$7),H16*$I$7)/F16","v":1579970.9990931244},4]
[124076,"(East Brainerd Rd.), Bridge over CSX R/R, LM 0.86 in Chattanooga (IA)","Hamilton","SR-320 ","2022-02-14",{"$f":"VLOOKUP(C17,ROW_Zillow!B:F,5,0)","v":1.5713238877791278},3,1938360,{"$f":"IFERROR(((VLOOKUP(G17,'Housing Index'!C:F,4,0)*(G17)+1)*H17*$I$7),H17*$I$7)/F17","v":1515932.6623646456},4]
[124722,"(Nashville Pike) Bridge over West Fork Station Camp Creek, LM 9.84 in Gallatin (IA)","Sumner","SR-6 ","2021-08-27",{"$f":"VLOOKUP(C18,ROW_Zillow!B:F,5,0)","v":1.0072592104450255},4,662752.07999999996,{"$f":"IFERROR(((VLOOKUP(G18,'Housing Index'!C:F,4,0)*(G18)+1)*H18*$I$7),H18*$I$7)/F18","v":1011901.9352756359},4]
[115687,"Bridge over Kerns Branch, LM 23.80 in Harbison Crossroads","Knox","SR-131 ","2015-01-28",{"$f":"VLOOKUP(C19,ROW_Zillow!B:F,5,0)","v":1.0314909011031255},10,514000,{"$f":"IFERROR(((VLOOKUP(G19,'Housing Index'!C:F,4,0)*(G19)+1)*H19*$I$7),H19*$I$7)/F19","v":1129191.9328966741},4]
[100494,"Bridge over French Broad River, LM 9.16 in Dandridge","Jefferson","SR-92 ","2014-07-23",{"$f":"VLOOKUP(C20,ROW_Zillow!B:F,5,0)","v":1.0377307330601262},11,375000,{"$f":"IFERROR(((VLOOKUP(G20,'Housing Index'!C:F,4,0)*(G20)+1)*H20*$I$7),H20*$I$7)/F20","v":861693.40531119867},4]
[10716,"Forge Road, Bridge over Forge Creek, LM 1.86","Johnson","Old Forge Creek Rd.","2015-07-31",{"$f":"VLOOKUP(C21,ROW_Zillow!B:F,5,0)","v":0.54094675206106657},10,178700,{"$f":"IFERROR(((VLOOKUP(G21,'Housing Index'!C:F,4,0)*(G21)+1)*H21*$I$7),H21*$I$7)/F21","v":748583.21355777443},4]
[124631,"(Unicoi Drive), Bridge over North Indian Creek, LM 5.22 in Erwin. (IA)","Unicoi","SR-107 ","2019-11-10",{"$f":"VLOOKUP(C22,ROW_Zillow!B:F,5,0)","v":0.52493530207239303},6,209783.44,{"$f":"IFERROR(((VLOOKUP(G22,'Housing Index'!C:F,4,0)*(G22)+1)*H22*$I$7),H22*$I$7)/F22","v":710459.59247663792},4]
[124040,"00918-7.67 Wattendorf Memorial Highway/A.E.D.C. Road, Bridge over I-24, LM 7.67 (IA)","Coffee","Wattendorf Memorial Hwy","2022-05-16",{"$f":"VLOOKUP(C23,ROW_Zillow!B:F,5,0)","v":0.84801993451265467},3,522825,{"$f":"IFERROR(((VLOOKUP(G23,'Housing Index'!C:F,4,0)*(G23)+1)*H23*$I$7),H23*$I$7)/F23","v":757637.51133219176},4]
[124125,"Bridge over Brushy Creek, LM 3.98 (IA)","Anderson","SR-61 ","2019-10-03",{"$f":"VLOOKUP(C24,ROW_Zillow!B:F,5,0)","v":0.84670195020490535},6,320228.58,{"$f":"IFERROR(((VLOOKUP(G24,'Housing Index'!C:F,4,0)*(G24)+1)*H24*$I$7),H24*$I$7)/F24","v":672362.50943212456},4]
[115684,"Bridge over Brush Creek, LM 16.39","Polk","SR-68 ","2014-10-20",{"$f":"VLOOKUP(C25,ROW_Zillow!B:F,5,0)","v":0.74666900059721164},11,203150,{"$f":"IFERROR(((VLOOKUP(G25,'Housing Index'!C:F,4,0)*(G25)+1)*H25*$I$7),H25*$I$7)/F25","v":648776.16448488634},4]
[117923,"Boanerges Church Road, Bridge over Old Fort Creek, LM 3.29 (IA)","Polk","Boanerges Church Road","2016-08-17",{"$f":"VLOOKUP(C26,ROW_Zillow!B:F,5,0)","v":0.74666900059721164},9,220105,{"$f":"IFERROR(((VLOOKUP(G26,'Housing Index'!C:F,4,0)*(G26)+1)*H26*$I$7),H26*$I$7)/F26","v":634574.39523752558},4]
[115677,"Bridge over Elk Fork Creek, LM 14.79","Campbell","SR-297 ","2014-07-23",{"$f":"VLOOKUP(C27,ROW_Zillow!B:F,5,0)","v":0.56782814033787077},11,150000,{"$f":"IFERROR(((VLOOKUP(G27,'Housing Index'!C:F,4,0)*(G27)+1)*H27*$I$7),H27*$I$7)/F27","v":629912.93713241746},4]
[124519,"Caney Creek Road, Bridge over Caney Creek, LM 3.94 (IA)","Roane","Caney Creek Road","2021-01-29",{"$f":"VLOOKUP(C28,ROW_Zillow!B:F,5,0)","v":0.90934052733101312},4,294277.08,{"$f":"IFERROR(((VLOOKUP(G28,'Housing Index'!C:F,4,0)*(G28)+1)*H28*$I$7),H28*$I$7)/F28","v":497689.4851551287},4]
[82443.009999999995,"Bridge over Doe Creek, LM 10.06","Hardin","SR-69 ","2017-03-01",{"$f":"VLOOKUP(C29,ROW_Zillow!B:F,5,0)","v":0.51020064938185161},8,138660.6,{"$f":"IFERROR(((VLOOKUP(G29,'Housing Index'!C:F,4,0)*(G29)+1)*H29*$I$7),H29*$I$7)/F29","v":550194.80294238124},4]
[115691,"Bridge over Limestone Creek (SBL), LM 1.72","Washington","SR-34 ","2015-07-31",{"$f":"VLOOKUP(C30,ROW_Zillow!B:F,5,0)","v":0.79939180515798647},10,147900,{"$f":"IFERROR(((VLOOKUP(G30,'Housing Index'!C:F,4,0)*(G30)+1)*H30*$I$7),H30*$I$7)/F30","v":419255.27096119215},4]
[124493,"Kidd Lane, Bridge over Elk River, LM 2.00 (IA)","Lincoln","Kidd Lane","2021-08-03",{"$f":"VLOOKUP(C31,ROW_Zillow!B:F,5,0)","v":0.68707826218277424},4,163608.72,{"$f":"IFERROR(((VLOOKUP(G31,'Housing Index'!C:F,4,0)*(G31)+1)*H31*$I$7),H31*$I$7)/F31","v":366208.83086662571},4]
[124052,"Bridge over Obed River, LM 12.72 in Crossville (IA)","Cumberland","SR-1 ","2020-01-30",{"$f":"VLOOKUP(C32,ROW_Zillow!B:F,5,0)","v":0.85118446975157369},5,173425,{"$f":"IFERROR(((VLOOKUP(G32,'Housing Index'!C:F,4,0)*(G32)+1)*H32*$I$7),H32*$I$7)/F32","v":340882.93366847199},4]
[124456,"(North Church Street) Bridge over Trace Creek, LM 19.35 in Waverly (IA)","Humphreys","SR-13 ","2021-10-18",{"$f":"VLOOKUP(C33,ROW_Zillow!B:F,5,0)","v":0.57099267557678979},4,118447.02,{"$f":"IFERROR(((VLOOKUP(G33,'Housing Index'!C:F,4,0)*(G33)+1)*H33*$I$7),H33*$I$7)/F33","v":319023.13306754653},4]
[124411,"(East Main Street) Bridge over Wells Creek, LM 5.87 in Erin (IA)","Houston","SR-49 ","2019-09-03",{"$f":"VLOOKUP(C34,ROW_Zillow!B:F,5,0)","v":0.50758527427116151},6,97514.82,{"$f":"IFERROR(((VLOOKUP(G34,'Housing Index'!C:F,4,0)*(G34)+1)*H34*$I$7),H34*$I$7)/F34","v":341535.27768128691},4]
[124563,"Bridge over West Prong Fork Little Pigeon River, LM 21.04 in Pigeon Forge","Sevier","SR-71 ","2020-09-24",{"$f":"VLOOKUP(C35,ROW_Zillow!B:F,5,0)","v":1.1919966775812243},5,230820.48000000001,{"$f":"IFERROR(((VLOOKUP(G35,'Housing Index'!C:F,4,0)*(G35)+1)*H35*$I$7),H35*$I$7)/F35","v":323978.76208343264},4]
[115673,"Bridges over Branch at LM's 4.77, 5.45, 9.83 and Bridge over Sugar Creek, LM 8.30","Bedford","SR-130 ","2014-08-13",{"$f":"VLOOKUP(C36,ROW_Zillow!B:F,5,0)","v":0.88120979976248826},11,125779,{"$f":"IFERROR(((VLOOKUP(G36,'Housing Index'!C:F,4,0)*(G36)+1)*H36*$I$7),H36*$I$7)/F36","v":340357.24504854949},4]
[124677,"Old Lower River Road, Bridge over South Mouse Creek, LM 13.09","Bradley","Old Lower River Road","2021-01-19",{"$f":"VLOOKUP(C37,ROW_Zillow!B:F,5,0)","v":0.85442451450812418},4,155575,{"$f":"IFERROR(((VLOOKUP(G37,'Housing Index'!C:F,4,0)*(G37)+1)*H37*$I$7),H37*$I$7)/F37","v":280023.63166584796},3]
[124053,"Bridge over Obed River, LM 15.37 in Crossville (IA)","Cumberland","SR-24 ","2021-01-19",{"$f":"VLOOKUP(C38,ROW_Zillow!B:F,5,0)","v":0.85118446975157369},4,145000,{"$f":"IFERROR(((VLOOKUP(G38,'Housing Index'!C:F,4,0)*(G38)+1)*H38*$I$7),H38*$I$7)/F38","v":261982.86397589071},3]
[117282,"Rotten Fork Road, Bridge over Rotten Fork Wolf River, LM 0.135 (IA)","Fentress","Rotten Fork Road","2016-12-20",{"$f":"VLOOKUP(C39,ROW_Zillow!B:F,5,0)","v":0.55337836446384814},9,75124.5,{"$f":"IFERROR(((VLOOKUP(G39,'Housing Index'!C:F,4,0)*(G39)+1)*H39*$I$7),H39*$I$7)/F39","v":292240.34807354183},3]
[124425,"Bridge over Koontz Creek, LM 14.24  (IA)","Jefferson","SR-9 ","2019-10-27",{"$f":"VLOOKUP(C40,ROW_Zillow!B:F,5,0)","v":1.0377307330601262},6,161665.74,{"$f":"IFERROR(((VLOOKUP(G40,'Housing Index'!C:F,4,0)*(G40)+1)*H40*$I$7),H40*$I$7)/F40","v":276953.76638228254},3]
[116956,"Creekwood Road, Bridges over Branch of Sugar Creek, LM 0.50 and Sugar Creek, LM 0.56","Gibson","Creekwood Road","2015-01-20",{"$f":"VLOOKUP(C41,ROW_Zillow!B:F,5,0)","v":0.32247712404840845},{"$f":"IFERROR(YEAR(TODAY())-YEAR(E41),\"\")","v":10},39700,{"$f":"IFERROR(((VLOOKUP(G41,'Housing Index'!C:F,4,0)*(G41)+1)*H41*$I$7),H41*$I$7)/F41","v":278972.66033970925},3]
[105360.01,"Bridge over Buffalo River, LM 28.33","Perry","SR-13 ","2019-07-26",{"$f":"VLOOKUP(C42,ROW_Zillow!B:F,5,0)","v":0.44142520782278605},6,62068,{"$f":"IFERROR(((VLOOKUP(G42,'Housing Index'!C:F,4,0)*(G42)+1)*H42*$I$7),H42*$I$7)/F42","v":249968.09544991393},3]
[115678,"Bridges over Grassy Hollow Creek, LM 7.67, and Branch, LM 8.94","Carroll","SR-104 ","2014-08-13",{"$f":"VLOOKUP(C43,ROW_Zillow!B:F,5,0)","v":0.47069544265738589},11,49000,{"$f":"IFERROR(((VLOOKUP(G43,'Housing Index'!C:F,4,0)*(G43)+1)*H43*$I$7),H43*$I$7)/F43","v":248234.57241223624},3]
[125402,"(Yellow Creek Road) Bridge over Yellow Creek, LM 19.06 (IA)","Dickson","SR-46 ","2021-05-18",{"$f":"VLOOKUP(C44,ROW_Zillow!B:F,5,0)","v":0.99387000006864501},4,137556,{"$f":"IFERROR(((VLOOKUP(G44,'Housing Index'!C:F,4,0)*(G44)+1)*H44*$I$7),H44*$I$7)/F44","v":212852.39010819976},3]
[124128,"Bridge over Bull Run Creek, LM 16.10 (IA)","Anderson","SR-9 ","2022-11-07",{"$f":"VLOOKUP(C45,ROW_Zillow!B:F,5,0)","v":0.84670195020490535},3,171736.56,{"$f":"IFERROR(((VLOOKUP(G45,'Housing Index'!C:F,4,0)*(G45)+1)*H45*$I$7),H45*$I$7)/F45","v":249254.71564328627},3]
[124161,"Smalling Road, Bridge over Watauga River, LM 1.99 (IA)","Carter","Smalling Road","2022-04-08",{"$f":"VLOOKUP(C46,ROW_Zillow!B:F,5,0)","v":0.59732490372536506},3,120743.03999999999,{"$f":"IFERROR(((VLOOKUP(G46,'Housing Index'!C:F,4,0)*(G46)+1)*H46*$I$7),H46*$I$7)/F46","v":248406.33565582157},3]
[124063,"Old Decherd Road, Bridge over Wagner Creek, LM 0.25 (IA)","Franklin","Old Decherd Road","2020-08-21",{"$f":"VLOOKUP(C47,ROW_Zillow!B:F,5,0)","v":0.56362020085531694},5,72350,{"$f":"IFERROR(((VLOOKUP(G47,'Housing Index'!C:F,4,0)*(G47)+1)*H47*$I$7),H47*$I$7)/F47","v":214767.83135431944},3]
[124369,"AFG Road, Bridge over Southern Railway, LM 0.45 (IA)","Hawkins","AFG Road","2021-11-23",{"$f":"VLOOKUP(C48,ROW_Zillow!B:F,5,0)","v":0.57636414808102854},4,72796.14,{"$f":"IFERROR(((VLOOKUP(G48,'Housing Index'!C:F,4,0)*(G48)+1)*H48*$I$7),H48*$I$7)/F48","v":194240.58064349857},3]
[124383,"Bridge over Norfolk Southern Railroad, LM 6.19 (IA)","Hawkins","SR-70 ","2020-09-22",{"$f":"VLOOKUP(C49,ROW_Zillow!B:F,5,0)","v":0.57636414808102854},5,66325.63,{"$f":"IFERROR(((VLOOKUP(G49,'Housing Index'!C:F,4,0)*(G49)+1)*H49*$I$7),H49*$I$7)/F49","v":192531.44586555878},3]
[124428,"A375-0.34 Slimp Branch Road, Bridge over Roan Creek, LM 0.34 (IA)","Johnson","Slimp Branch Road","2021-10-25",{"$f":"VLOOKUP(C50,ROW_Zillow!B:F,5,0)","v":0.54094675206106657},4,63334.98,{"$f":"IFERROR(((VLOOKUP(G50,'Housing Index'!C:F,4,0)*(G50)+1)*H50*$I$7),H50*$I$7)/F50","v":180060.1860605976},3]
[124089,"Bridge over Middle Creek, LM 13.35 (IA)","McMinn","SR-39 ","2019-07-25",{"$f":"VLOOKUP(C51,ROW_Zillow!B:F,5,0)","v":0.70460676702568015},6,77300,{"$f":"IFERROR(((VLOOKUP(G51,'Housing Index'!C:F,4,0)*(G51)+1)*H51*$I$7),H51*$I$7)/F51","v":195032.34565279799},3]
[124377,"S. Armstrong Road, Bridge over Crockett Creek, LM 0.27 (IA)","Hawkins","S. Armstrong Road","2020-01-20",{"$f":"VLOOKUP(C52,ROW_Zillow!B:F,5,0)","v":0.57636414808102854},5,62625.9,{"$f":"IFERROR(((VLOOKUP(G52,'Housing Index'!C:F,4,0)*(G52)+1)*H52*$I$7),H52*$I$7)/F52","v":181791.79113160176},3]
[124540,"Lawrenceburg Hwy, Bridge over Tennessee Southern Railroad, LM 3.18 (IA)","Maury","Lawrenceburg Hwy","2021-01-13",{"$f":"VLOOKUP(C53,ROW_Zillow!B:F,5,0)","v":1.1169779718143564},4,123952.38,{"$f":"IFERROR(((VLOOKUP(G53,'Housing Index'!C:F,4,0)*(G53)+1)*H53*$I$7),H53*$I$7)/F53","v":170662.78797210168},3]
[101895.01,"Bridges over Shaw Creek, LM 6.80 and Overflow, LM 7.11","Fayette","SR-196 ","2017-03-23",{"$f":"VLOOKUP(C54,ROW_Zillow!B:F,5,0)","v":1.3164586722681},8,121104,{"$f":"IFERROR(((VLOOKUP(G54,'Housing Index'!C:F,4,0)*(G54)+1)*H54*$I$7),H54*$I$7)/F54","v":186232.58598142094},3]
[124605,"(Snow Creek Road), Bridge over Leipers Creek, LM 1.05 (IA)","Maury","SR-247 ","2019-09-03",{"$f":"VLOOKUP(C55,ROW_Zillow!B:F,5,0)","v":1.1169779718143564},6,112341.36,{"$f":"IFERROR(((VLOOKUP(G55,'Housing Index'!C:F,4,0)*(G55)+1)*H55*$I$7),H55*$I$7)/F55","v":178800.62341503511},3]
[123826,"Grassy Branch Rd over Middle Prong of Little Pigeon River","Sevier","Grassy Branch rd","2022-06-07",{"$f":"VLOOKUP(C56,ROW_Zillow!B:F,5,0)","v":1.1919966775812243},3,174765.9,{"$f":"IFERROR(((VLOOKUP(G56,'Housing Index'!C:F,4,0)*(G56)+1)*H56*$I$7),H56*$I$7)/F56","v":180174.29733809445},2]
[117328,"Hatchett Hollow Road, Bridge over Hatchett Creek, LM 0.12 in Cornersville (IA)","Marshall","Hatchett Hollow Road","2015-05-01",{"$f":"VLOOKUP(C57,ROW_Zillow!B:F,5,0)","v":0.84467005773045845},10,59087,{"$f":"IFERROR(((VLOOKUP(G57,'Housing Index'!C:F,4,0)*(G57)+1)*H57*$I$7),H57*$I$7)/F57","v":158516.65163362134},2]
[115692,"Bridges over Branch, LM 8.56 and LM 8.66","Madison","SR-197 ","2014-06-23",{"$f":"VLOOKUP(C58,ROW_Zillow!B:F,5,0)","v":0.63833343630085737},11,42000,{"$f":"IFERROR(((VLOOKUP(G58,'Housing Index'!C:F,4,0)*(G58)+1)*H58*$I$7),H58*$I$7)/F58","v":156894.5569372678},2]
[124227,"Gap Creek Road, Bridge over Gap Creek, LM 2.73 (IA)","Carter","Gap Creek Rd.","2022-04-07",{"$f":"VLOOKUP(C59,ROW_Zillow!B:F,5,0)","v":0.59732490372536506},3,73962.899999999994,{"$f":"IFERROR(((VLOOKUP(G59,'Housing Index'!C:F,4,0)*(G59)+1)*H59*$I$7),H59*$I$7)/F59","v":152164.90294991716},2]
[124514,"(Petros Hwy.), Bridge over Stockstill Creek, LM 2.60 (IA)","Morgan","SR-116 ","2019-10-16",{"$f":"VLOOKUP(C60,ROW_Zillow!B:F,5,0)","v":0.54028775990719191},6,41208.67,{"$f":"IFERROR(((VLOOKUP(G60,'Housing Index'!C:F,4,0)*(G60)+1)*H60*$I$7),H60*$I$7)/F60","v":135593.04980328112},2]
[122332,"Easley Ford Road, Bridge over Conasauga River, LM 1.53 (IA)","Polk","Easley Ford Road","2022-08-22",{"$f":"VLOOKUP(C61,ROW_Zillow!B:F,5,0)","v":0.74666900059721164},3,87000,{"$f":"IFERROR(((VLOOKUP(G61,'Housing Index'!C:F,4,0)*(G61)+1)*H61*$I$7),H61*$I$7)/F61","v":143186.57982855936},2]
[124660,"(Old SR-34), Bridge over Little Limestone Creek, LM 11.72 (IA)","Washington","SR-353 ","2019-10-27",{"$f":"VLOOKUP(C62,ROW_Zillow!B:F,5,0)","v":0.79939180515798647},6,57641.32,{"$f":"IFERROR(((VLOOKUP(G62,'Housing Index'!C:F,4,0)*(G62)+1)*H62*$I$7),H62*$I$7)/F62","v":128188.24029795038},2]
[124671,"South Mill Street, Bridge over Buffalo River, LM 0.22 in Linden (IA)","Perry","South Mill Street","2022-04-14",{"$f":"VLOOKUP(C63,ROW_Zillow!B:F,5,0)","v":0.44142520782278605},3,49727.46,{"$f":"IFERROR(((VLOOKUP(G63,'Housing Index'!C:F,4,0)*(G63)+1)*H63*$I$7),H63*$I$7)/F63","v":138436.4107171405},2]
[121363,"Bridges over Hurricane Creek at LM's 8.17 and 8.33","Humphreys","SR-230 ","2021-04-28",{"$f":"VLOOKUP(C64,ROW_Zillow!B:F,5,0)","v":0.57099267557678979},4,41039.64,{"$f":"IFERROR(((VLOOKUP(G64,'Housing Index'!C:F,4,0)*(G64)+1)*H64*$I$7),H64*$I$7)/F64","v":110535.44895231814},2]
[11845,"John Butler Road, Bridge Over Proctor Branch, LM 0.16 (IA)","Clay","John Butler Rd.","2015-10-09",{"$f":"VLOOKUP(C65,ROW_Zillow!B:F,5,0)","v":0.50110175250725919},10,26275,{"$f":"IFERROR(((VLOOKUP(G65,'Housing Index'!C:F,4,0)*(G65)+1)*H65*$I$7),H65*$I$7)/F65","v":118819.26246337278},2]
[124012,"Tunnel Hill Road, Bridge over Black Fox Creek, LM 6.157 (IA)","Bradley","Tunnel Hill Road","2020-05-26",{"$f":"VLOOKUP(C66,ROW_Zillow!B:F,5,0)","v":0.85442451450812418},5,56050,{"$f":"IFERROR(((VLOOKUP(G66,'Housing Index'!C:F,4,0)*(G66)+1)*H66*$I$7),H66*$I$7)/F66","v":109753.69831221757},2]
[124154,"Bridge over South Fork Forked Deer River, LM 14.16 (IA)","Chester","SR-100 ","2022-07-21",{"$f":"VLOOKUP(C67,ROW_Zillow!B:F,5,0)","v":0.42745937931176509},3,41760,{"$f":"IFERROR(((VLOOKUP(G67,'Housing Index'!C:F,4,0)*(G67)+1)*H67*$I$7),H67*$I$7)/F67","v":120054.05216092477},2]
[124442,"Tatum Lane, Bridge over Blue Creek, LM 0.09 (IA)","Humphreys","Tatum Lane","2021-05-03",{"$f":"VLOOKUP(C68,ROW_Zillow!B:F,5,0)","v":0.57099267557678979},4,35670,{"$f":"IFERROR(((VLOOKUP(G68,'Housing Index'!C:F,4,0)*(G68)+1)*H68*$I$7),H68*$I$7)/F68","v":96072.954444268718},2]
[124602,"(North Main Street), Bridge over Sugar Creek, LM 2.06 (IA)","Maury","SR-243 ","2021-06-11",{"$f":"VLOOKUP(C69,ROW_Zillow!B:F,5,0)","v":1.1169779718143564},4,68790.899999999994,{"$f":"IFERROR(((VLOOKUP(G69,'Housing Index'!C:F,4,0)*(G69)+1)*H69*$I$7),H69*$I$7)/F69","v":94714.169918399683},2]
[124085,"Orme Road, Bridge over Dry Creek, LM 0.58 (IA)","Marion","Orme Road","2021-04-01",{"$f":"VLOOKUP(C70,ROW_Zillow!B:F,5,0)","v":0.69570694069757066},4,42175,{"$f":"IFERROR(((VLOOKUP(G70,'Housing Index'!C:F,4,0)*(G70)+1)*H70*$I$7),H70*$I$7)/F70","v":93230.353202930157},2]
[115674,"Bridge Over Lick Fork Creek, LM 5.25","Campbell","SR-297 ","2014-07-23",{"$f":"VLOOKUP(C71,ROW_Zillow!B:F,5,0)","v":0.56782814033787077},11,25000,{"$f":"IFERROR(((VLOOKUP(G71,'Housing Index'!C:F,4,0)*(G71)+1)*H71*$I$7),H71*$I$7)/F71","v":104985.48952206958},2]
[124513,"(Petros Hwy), Bridge over Stockstill Creek, LM 2.26 (IA)","Morgan","SR-116 ","2019-11-12",{"$f":"VLOOKUP(C72,ROW_Zillow!B:F,5,0)","v":0.54028775990719191},6,30102.3,{"$f":"IFERROR(((VLOOKUP(G72,'Housing Index'!C:F,4,0)*(G72)+1)*H72*$I$7),H72*$I$7)/F72","v":99048.638626126718},2]
[117922,"Columbus Road, Bridge over CSX Railroad, LM 1.13 (IA)","Polk","Columbus Road","2017-06-26",{"$f":"VLOOKUP(C73,ROW_Zillow!B:F,5,0)","v":0.74666900059721164},{"$f":"IFERROR(YEAR(TODAY())-YEAR(E73),\"\")","v":8},33475,{"$f":"IFERROR(((VLOOKUP(G73,'Housing Index'!C:F,4,0)*(G73)+1)*H73*$I$7),H73*$I$7)/F73","v":90760.500111132395},2]
[115682,"Bridge over Muddy Creek, LM 1.15","Madison","SR-138 ","2015-07-23",{"$f":"VLOOKUP(C74,ROW_Zillow!B:F,5,0)","v":0.63833343630085737},10,25750,{"$f":"IFERROR(((VLOOKUP(G74,'Housing Index'!C:F,4,0)*(G74)+1)*H74*$I$7),H74*$I$7)/F74","v":91411.258673182572},2]
[103939,"Hoot Owl Lane, Bridge over Middle Fork Goose Creek, LM 0.06","Macon","Hoot Owl Lane","2022-02-22",{"$f":"VLOOKUP(C75,ROW_Zillow!B:F,5,0)","v":0.71034205811487061},3,55944.480000000003,{"$f":"IFERROR(((VLOOKUP(G75,'Housing Index'!C:F,4,0)*(G75)+1)*H75*$I$7),H75*$I$7)/F75","v":96783.404796755378},2]
[103801,"Brymer Creek Road, Bridge over Brymer Creek, LM 2.98 (IA)","Bradley","Brymer Creek Road","2020-03-05",{"$f":"VLOOKUP(C76,ROW_Zillow!B:F,5,0)","v":0.85442451450812418},5,40925,{"$f":"IFERROR(((VLOOKUP(G76,'Housing Index'!C:F,4,0)*(G76)+1)*H76*$I$7),H76*$I$7)/F76","v":80136.843950535331},2]
[124572,"Ashwood Road, Bridge over Big Bigby Creek, LM 1.31 (IA)","Maury","Ashwood Road","2020-07-09",{"$f":"VLOOKUP(C77,ROW_Zillow!B:F,5,0)","v":1.1169779718143564},5,52871.64,{"$f":"IFERROR(((VLOOKUP(G77,'Housing Index'!C:F,4,0)*(G77)+1)*H77*$I$7),H77*$I$7)/F77","v":79194.572748000326},1]
[83843.009999999995,"Bridge over Hatchie River, LM 8.98","Haywood","SR-76 ","2014-08-28",{"$f":"VLOOKUP(C78,ROW_Zillow!B:F,5,0)","v":0.40729147360255907},11,13700,{"$f":"IFERROR(((VLOOKUP(G78,'Housing Index'!C:F,4,0)*(G78)+1)*H78*$I$7),H78*$I$7)/F78","v":80208.691046894935},1]
[103937,"Purtle Road, Bridge over Puncheon Creek, LM 0.10","Macon","Purtle Road","2021-08-10",{"$f":"VLOOKUP(C79,ROW_Zillow!B:F,5,0)","v":0.71034205811487061},4,32433.599999999999,{"$f":"IFERROR(((VLOOKUP(G79,'Housing Index'!C:F,4,0)*(G79)+1)*H79*$I$7),H79*$I$7)/F79","v":70219.252410818925},1]
[114379.01,"Bridge over Piney River, LM 11.46","Hickman","SR-230 ","2021-06-07",{"$f":"VLOOKUP(C80,ROW_Zillow!B:F,5,0)","v":0.56193496571181445},4,23843,{"$f":"IFERROR(((VLOOKUP(G80,'Housing Index'!C:F,4,0)*(G80)+1)*H80*$I$7),H80*$I$7)/F80","v":65253.440788950204},1]
[124717,"(Old US-31 East) Bridge over Little Trammel Creek, LM 39.41 (IA)","Sumner","SR-174 ","2020-06-22",{"$f":"VLOOKUP(C81,ROW_Zillow!B:F,5,0)","v":1.0072592104450255},5,37418.699999999997,{"$f":"IFERROR(((VLOOKUP(G81,'Housing Index'!C:F,4,0)*(G81)+1)*H81*$I$7),H81*$I$7)/F81","v":62153.371894860393},1]
[124692,"Webster Road, Bridge over Little Indian Creek, LM 0.86 (IA)","Putnam","Webster Road","2022-11-23",{"$f":"VLOOKUP(C82,ROW_Zillow!B:F,5,0)","v":0.92302147902551535},3,51157.74,{"$f":"IFERROR(((VLOOKUP(G82,'Housing Index'!C:F,4,0)*(G82)+1)*H82*$I$7),H82*$I$7)/F82","v":68109.975984720309},1]
[124142,"(Sams Creek Road) Bridge over Dry Creek, LM 11.54 (IA)","Cheatham","SR-249 ","2021-04-28",{"$f":"VLOOKUP(C83,ROW_Zillow!B:F,5,0)","v":1.0109042607961449},4,37245,{"$f":"IFERROR(((VLOOKUP(G83,'Housing Index'!C:F,4,0)*(G83)+1)*H83*$I$7),H83*$I$7)/F83","v":56661.298891454979},1]
[124509,"(Nashville Highway) Bridge over Rock Creek, LM 13.18 in Lewisburg (IA)","Marshall","SR-11 ","2020-07-24",{"$f":"VLOOKUP(C84,ROW_Zillow!B:F,5,0)","v":0.84467005773045845},5,30032.400000000001,{"$f":"IFERROR(((VLOOKUP(G84,'Housing Index'!C:F,4,0)*(G84)+1)*H84*$I$7),H84*$I$7)/F84","v":59486.742425327961},1]
[124675,"Experiment Station Road (05353), Bridge over Wartrace Creek, LM 0.61 in Springfield (IA)","Robertson","Experiment Station Road","2021-01-21",{"$f":"VLOOKUP(C85,ROW_Zillow!B:F,5,0)","v":0.98784639991213441},4,32129.1,{"$f":"IFERROR(((VLOOKUP(G85,'Housing Index'!C:F,4,0)*(G85)+1)*H85*$I$7),H85*$I$7)/F85","v":50019.311925774411},1]
[124460,"Busby Road, Bridge over Shoal Creek, LM 6.24 (IA)","Lawrence","Busby Rd","2021-05-06",{"$f":"VLOOKUP(C86,ROW_Zillow!B:F,5,0)","v":0.63126643190071186},4,20048.28,{"$f":"IFERROR(((VLOOKUP(G86,'Housing Index'!C:F,4,0)*(G86)+1)*H86*$I$7),H86*$I$7)/F86","v":48841.950324519603},1]
[115676,"Bridge over Meridian Creek, LM 4.70","Madison","SR-18 ","2015-01-20",{"$f":"VLOOKUP(C87,ROW_Zillow!B:F,5,0)","v":0.63833343630085737},10,15200,{"$f":"IFERROR(((VLOOKUP(G87,'Housing Index'!C:F,4,0)*(G87)+1)*H87*$I$7),H87*$I$7)/F87","v":53959.267255626219},1]
[124242,"Bridge over South Fork Sycamore Creek, LM 20.56 (IA)","Claiborne","SR-33 ","2022-12-22",{"$f":"VLOOKUP(C88,ROW_Zillow!B:F,5,0)","v":0.49524976489082012},3,21142.74,{"$f":"IFERROR(((VLOOKUP(G88,'Housing Index'!C:F,4,0)*(G88)+1)*H88*$I$7),H88*$I$7)/F88","v":52462.402515226211},1]
[124501,"Macedonia Road, Bridge over Emory River, LM 7.80 (IA)","Morgan","Macedonia Road","2020-05-12",{"$f":"VLOOKUP(C89,ROW_Zillow!B:F,5,0)","v":0.54028775990719191},5,14775.48,{"$f":"IFERROR(((VLOOKUP(G89,'Housing Index'!C:F,4,0)*(G89)+1)*H89*$I$7),H89*$I$7)/F89","v":45754.489729798835},1]
[123388,"S. Harpeth Road (0A372), Bridge over Brush Creek, LM 1.27 in Kingston Springs (IA)","Cheatham","South Harpeth Road","2020-10-23",{"$f":"VLOOKUP(C90,ROW_Zillow!B:F,5,0)","v":1.0109042607961449},5,26047.8,{"$f":"IFERROR(((VLOOKUP(G90,'Housing Index'!C:F,4,0)*(G90)+1)*H90*$I$7),H90*$I$7)/F90","v":43110.024367373597},1]
[124046,"(Winchester Highway), Bridge over Bradley Creek, LM 4.66 (IA)","Coffee","SR-127 ","2020-01-30",{"$f":"VLOOKUP(C91,ROW_Zillow!B:F,5,0)","v":0.84801993451265467},5,21427,{"$f":"IFERROR(((VLOOKUP(G91,'Housing Index'!C:F,4,0)*(G91)+1)*H91*$I$7),H91*$I$7)/F91","v":42273.923285600256},1]
[101878.01,"Bridge over Earthman Fork Creek, LM 6.05","Davidson","SR-65 ","2014-02-24",{"$f":"VLOOKUP(C92,ROW_Zillow!B:F,5,0)","v":1.4256299896346025},11,26260,{"$f":"IFERROR(((VLOOKUP(G92,'Housing Index'!C:F,4,0)*(G92)+1)*H92*$I$7),H92*$I$7)/F92","v":43923.210779135763},1]
[124444,"Weed Lane, Bridge over Blue Creek, LM 0.17 (IA)","Humphreys","Weed Lane","2022-02-09",{"$f":"VLOOKUP(C93,ROW_Zillow!B:F,5,0)","v":0.57099267557678979},3,21257.279999999999,{"$f":"IFERROR(((VLOOKUP(G93,'Housing Index'!C:F,4,0)*(G93)+1)*H93*$I$7),H93*$I$7)/F93","v":45749.709405014859},1]
[107719,"Lays Road, Bridge Over Straight Fork Creek LM 0.01","Scott","Lays Rd.","2016-11-07",{"$f":"VLOOKUP(C94,ROW_Zillow!B:F,5,0)","v":0.4859483652189433},9,8500,{"$f":"IFERROR(((VLOOKUP(G94,'Housing Index'!C:F,4,0)*(G94)+1)*H94*$I$7),H94*$I$7)/F94","v":37653.864692713199},1]
[124092,"W. Memorial Drive, Bridge over Decatur Branch, LM 0.37 in Decatur (IA)","Meigs","W. Memorial Drive","2022-02-08",{"$f":"VLOOKUP(C95,ROW_Zillow!B:F,5,0)","v":0.6907404737879006},3,22360,{"$f":"IFERROR(((VLOOKUP(G95,'Housing Index'!C:F,4,0)*(G95)+1)*H95*$I$7),H95*$I$7)/F95","v":39780.302306952595},1]
[124319,"(Lewisburg Highway) Bridge over Pigeon Roost Creek, LM 23.38 (IA)","Giles","SR-11 ","2021-01-25",{"$f":"VLOOKUP(C96,ROW_Zillow!B:F,5,0)","v":0.68010736080506873},4,14424.6,{"$f":"IFERROR(((VLOOKUP(G96,'Housing Index'!C:F,4,0)*(G96)+1)*H96*$I$7),H96*$I$7)/F96","v":32617.815960689401},1]
[124507,"WMA Road, Bridge over Island Creek, LM 10.271 (IA)","Morgan","WMA","2020-02-03",{"$f":"VLOOKUP(C97,ROW_Zillow!B:F,5,0)","v":0.54028775990719191},5,10342.77,{"$f":"IFERROR(((VLOOKUP(G97,'Housing Index'!C:F,4,0)*(G97)+1)*H97*$I$7),H97*$I$7)/F97","v":32027.938431961025},1]

{"sheet":"ROW_Zillow","index":39,"n_rows":116,"n_cols":9,"rows_kept":116,"cut":false,"hidden":true,"merged":[]}
["City","County","Region","Home Value Index - 2023","HVI County Average","Factor",null,"TN Average",291354]
["Oak Ridge","Anderson",1,246690,{"$f":"AVERAGEIF(B:B,B2,D:D)","v":246690},{"$f":"E2/$I$1","v":0.84670195020490535}]
["Shelbyville","Bedford",3,256744,{"$f":"AVERAGEIF(B:B,B3,D:D)","v":256744},0.88120979976248826]
["Camden","Benton",4,148716,148716,0.51043061018554747]
["Pikeville","Bledsoe",2,158567,158567,0.54424171283043998]
["Maryville","Blount",1,314463,314463,1.0793158837702588]
["Cleveland","Bradley",2,248940,248940,0.85442451450812418]
["LaFollette","Campbell",1,165439,165439,0.56782814033787077]
["Woodbury","Cannon",2,244943,244943,0.84070580805480621]
["Huntingdon","Carroll",4,137139,137139,0.47069544265738589]
["Elizabethton","Carter",1,174033,174033,0.59732490372536506]
["Ashland City","Cheatham",3,294531,294531,1.0109042607961449]
["Henderson","Chester",4,124542,124542,0.42745937931176509]
["Tazewell","Claiborne",1,144293,144293,0.49524976489082012]
["Celina","Clay",2,145998,145998,0.50110175250725919]
["Newport","Cocke",1,155244,155244,0.53283634341728614]
["Manchester","Coffee",2,260540,247074,0.84801993451265467]
["Tullahoma","Coffee",2,233608,247074,0.84801993451265467]
["Alamo","Crockett",4,119900,119900,0.41152687109152442]
["Crossville","Cumberland",2,247996,247996,0.85118446975157369]
["Nashville","Davidson",3,415363,415363,1.4256299896346025]
["Parsons","Decatur",4,115356,115356,0.39593072344982394]
["Smithville","Dekalb",2,230014,230014,0.78946573584024937]
["Dickson","Dickson",3,289568,289568,0.99387000006864501]
["Dyersburg","Dyer",4,120952,113689,0.39020916136383915]
["Dyersburg","Dyer",4,106426,113689,0.39020916136383915]
["Rossville","Fayette",4,513660,383555.5,1.3164586722681]
["Somerville","Fayette",4,253451,383555.5,1.3164586722681]
["Jamestown","Fentress",2,161229,161229,0.55337836446384814]
["Winchester","Franklin",2,164213,164213,0.56362020085531694]
["Trenton","Gibson",4,93955,93955,0.32247712404840845]
["Pulaski","Giles",3,198152,198152,0.68010736080506873]
["Rutledge","Grainger",1,154995,154995,0.53198171296773]
["Greeneville","Greene",1,170937,170937,{"$f":"E34/$I$1","v":0.586698655244136}]
["Monteagle","Grundy",2,282380,223296.5,0.76640959108163953]
["Pelham","Grundy",2,164213,223296.5,0.76640959108163953]
["Morristown","Hamblen",1,197243,197243,0.67698744482656836]
["Lookout Mountain","Hamilton",2,797625,457811.5,1.5713238877791278]
["Signal Mountain","Hamilton",2,480127,457811.5,1.5713238877791278]
["Chattanooga","Hamilton",2,262140,457811.5,1.5713238877791278]
["East Ridge","Hamilton",2,291354,457811.5,1.5713238877791278]
["Sneedville","Hancock",1,115284,115284,0.39568360139212094]
["Bolivar","Hardeman",4,107995,107995,0.37066592530049358]
["Savannah","Hardin",4,148649,148649,0.51020064938185161]
["Rogersville","Hawkins",1,167926,167926,0.57636414808102854]
["Brownsville","Haywood",4,118666,118666,0.40729147360255907]
["Lexington","Henderson",4,165789,165789,0.56902942811837143]
["Paris","Henry",4,158670,158670,0.54459523466298732]
["Centerville","Hickman",3,163722,163722,0.56193496571181445]
["Erin","Houston",3,147887,147887,0.50758527427116151]
["Waverly","Humphreys",3,166361,166361,0.57099267557678979]
["Gainesboro","Jackson",2,155742,155742,0.53454560431639864]
["Dandridge","Jefferson",1,302347,302347,1.0377307330601262]
["Mountain City","Johnson",1,157607,157607,0.54094675206106657]
["Knoxville","Knox",1,300529,300529,1.0314909011031255]
["Tiptonville","Lake",4,65748,65748,0.2256636256924566]
["Ripley","Lauderdale",4,110782,110782,0.38023160828408054]
["Lawerenceburg","Lawrence",3,183922,183922,0.63126643190071186]
["Hohenwald","Lewis",3,183544,183544,0.62996904109777108]
["Fayetteville","Lincoln",3,200183,200183,0.68707826218277424]
["Lenoir City","Loudon",1,327595,327595,1.1243882012946449]
["Lafayette","Macon",3,206961,206961,0.71034205811487061]
["Jackson","Madison",4,185981,185981,0.63833343630085737]
["Kimball","Marion",2,202697,202697,0.69570694069757066]
["Lewisburg","Marshall",3,246098,246098,0.84467005773045845]
["Columbia","Maury",3,325436,325436,1.1169779718143564]
["Athens","McMinn",2,205290,{"$f":"AVERAGEIF(B:B,B67,D:D)","v":205290},{"$f":"E67/$I$1","v":0.70460676702568015}]
["Selmer","McNairy",4,119102,119102,0.40878793495198279]
["Decatur","Meigs",2,201250,201250,0.6907404737879006]
["Sweetwater","Monroe",1,196014,196014,0.67276920859161016]
["Clarksville","Montgomery",3,285104,285104,0.97854843249105894]
["Lynchburg","Moore",3,269765,269765,0.92590113744791558]
["Wartburg","Morgan",1,157415,157415,0.54028775990719191]
["Union City","Obion",4,120852,120852,0.41479437385448631]
["Livingston","Overton",2,177041,177041,0.60764911413606815]
["Linden","Perry",3,128611,128611,0.44142520782278605]
["Byrdstown","Pickett",2,178491,178491,0.61262587779814248]
["Ocoee","Polk",2,217545,217545,0.74666900059721164]
["Cookeville","Putnam",2,268926,268926,0.92302147902551535]
["Dayton","Rhea",2,197646,197646,0.67837064189954488]
["Kingston","Roane",1,264940,264940,0.90934052733101312]
["Springfield","Robertson",3,287813,287813,0.98784639991213441]
["Murfreesboro","Rutherford",3,388894,361185.33333333331,1.2396786497982979]
["Smyrna","Rutherford",3,377254,361185.33333333331,1.2396786497982979]
["LaVergne","Rutherford",3,317408,361185.33333333331,1.2396786497982979]
["Oneida","Scott",1,141583,141583,0.4859483652189433]
["Dunlap","Sequathchie",2,180601,180601,0.61986792698916093]
["Sevierville","Sevier",1,347293,347293,1.1919966775812243]
["Collierville","Shelby",4,486414,363037.2,1.2460347206491074]
["Germantown","Shelby",4,471688,363037.2,1.2460347206491074]
["Arlington","Shelby",4,394862,363037.2,1.2460347206491074]
["Bartlett","Shelby",4,319823,363037.2,1.2460347206491074]
["Memphis","Shelby",4,142399,363037.2,1.2460347206491074]
["Carthage","Smith",3,225405,225405,0.77364649189645585]
["Dover","Stewart",3,197732,197732,0.67866581546846794]
["Kingsport","Sullivan",1,196262,187247.5,0.64268038194086918]
["Bristol","Sullivan",1,178233,187247.5,0.64268038194086918]
["Gallatin","Sumner",3,402313,293469,1.0072592104450255]
["Goodlettsville","Sumner",3,370017,293469,{"$f":"E99/$I$1","v":1.0072592104450255}]
["Portland","Sumner",3,277004,293469,1.0072592104450255]
["Henderson","Sumner",3,124542,293469,1.0072592104450255]
["Covington","Tipton",4,153971,153971,0.52846708814706511]
["Hartsville","Trousdale",3,235734,235734,0.80909821042443208]
["Erwin","Unicoi",1,152942,152942,0.52493530207239303]
["Maynardville","Union",1,212012,212012,0.72767835691289628]
["Spencer","Van Buren",2,145780,145780,0.50035352183254733]
["McMinnville","Warren",2,195977,195977,0.67264221531195723]
["Johnson City","Washington",1,232906,232906,0.79939180515798647]
["Waynesboro","Wayne",3,123644,123644,0.4243772180920804]
["Martin","Weakley",4,165568,165568,0.5682709006912553]
["Sparta","White",2,200260,200260,0.68734254549448437]
["Brentwood","Williamson",3,1156986,771541.75,2.6481247897746383]
["Franklin","Williamson",3,805711,771541.75,2.6481247897746383]
["Thompson Station","Williamson",3,637859,771541.75,2.6481247897746383]
["Spring Hill","Williamson",3,485611,771541.75,2.6481247897746383]
["Lebanon","Wilson",3,412762,412762,1.4167027053000816]

{"sheet":"Const Index","index":40,"n_rows":35,"n_cols":16,"rows_kept":35,"cut":false,"hidden":true,"merged":[[0,0,0,2],[0,3,0,5]]}
["Mortenson Construction Cost Index",null,null,"https://www.mortenson.com/cost-index",null,null,"Current Year",{"$f":"YEAR(TODAY())","v":2025},null,null,149.26518911208811]
["Year","# Years (inflation)","# Years (since last estimate)","Index Value","Year-over-Year Increase to Current Year"]
[2008,0,{"$f":"IF((YEAR(TODAY())-A3)<0,0,(YEAR(TODAY())-A3))","v":17},91,{"$f":"IF(A3>($H$1-1),\"\",((VLOOKUP($H$1,$A$4:$D$35,4,0)-D3)/($H$1-A3))/D3)","v":7.5011369831603822E-2}]
[2009,1,{"$f":"IF((YEAR(TODAY())-A4)<0,0,(YEAR(TODAY())-A4))","v":16},93.8,{"$f":"IF(A4>($H$1-1),\"\",((VLOOKUP($H$1,$A$4:$D$35,4,0)-D4)/($H$1-A4))/D4)","v":7.545481685067372E-2},null,{"$f":"93.8*((1+(E4*C4)))","v":207.04258912949112},null,"2014-01-01",{"$f":"YEAR(I4)","v":2014},{"$f":"VLOOKUP(J4,A:F,5,0)","v":7.8811860914411919E-2}]
[2010,2,{"$f":"IF((YEAR(TODAY())-A5)<0,0,(YEAR(TODAY())-A5))","v":15},96.4,{"$f":"IF(A5>($H$1-1),\"\",((VLOOKUP($H$1,$A$4:$D$35,4,0)-D5)/($H$1-A5))/D5)","v":7.6516313367559555E-2},null,null,null,null,null,null,null,null,null,null,{"$f":"1+E4","v":1.0754548168506737}]
[2011,3,14,101,7.4994758931747604E-2]
[2012,4,13,103.6,7.6806199234846398E-2]
[2013,5,12,107.3,7.7463955521506006E-2]
[2014,6,11,110.9,7.8811860914411919E-2]
[2015,7,10,113.9,8.1775758673828886E-2]
[2016,8,9,117.5,8.4673843148454955E-2]
[2017,9,8,122.3,8.6613439420984387E-2]
[2018,10,7,130.80000000000001,8.3270630329282544E-2]
[2019,11,6,135,{"$f":"IF(A14>($H$1-1),\"\",((VLOOKUP($H$1,$A$4:$D$35,4,0)-D14)/($H$1-A14))/D14)","v":8.8941468061100148E-2}]
[2020,12,5,137.80000000000001,0.10049722660303498]
[2021,13,4,167.4,5.9203388783588877E-2]
[2022,14,3,178.3,5.3734509496150884E-2]
[2023,15,2,182.5,6.7239970217783884E-2]
[2024,16,1,183.1,0.1307623655351782]
[2025,17,0,{"$f":"87.709*EXP(0.0409*(B20+4))","v":207.04258912949112}]
[2026,18,0,215.68618772490856]
[2027,19,0,224.69063863091984]
[2028,20,0,234.07100668291994]
[2029,21,0,243.84298564193037]
[2030,22,0,254.02292445093926]
[2031,23,0,264.62785458738927]
[2032,24,0,275.67551855757517]
[2033,25,0,287.18439958062368]
[2034,26,0,299.17375251171728]
[2035,27,0,311.66363605629914]
[2036,28,0,324.67494632915356]
[2037,29,0,338.2294518145091]
[2038,30,0,352.34982978565318]
[2039,31,0,367.05970424498986]
[2040,32,0,382.38368544801676]