## Sheet1
TDOT Estimating Process within PDN Stages
|  | Stage 1 Cost Validation | Line and Grade Package | Functional Design Plans | Plan-in-Hand Plans | Plans, Specification & Estimate Plans/Letting
BID ITEMS | CONSTRUCTION ITEMS | Validate Concept Report Estimate. - Scoping information - Statewide averages | Focus on major Items that include 80% of the costs (see below) and considers a realistic inflation % for the year the project will be let. *For Highway Program or High-Risk/High-Profile Projects, Headquarters Construction will estimate based on quantities. | Estimate all Project Items. | Estimate all Project Items based on inflation, market, etc. | Estimate Final Review and Update based on inflation, market, etc.
|  | Concept Report Estimate updated by Concept Design Lead and/or Roadway Design Lead Engineer through Scoping Process. | Major items quantified and estimated by Discipline - Compiled by Roadway Design Lead Engineer. • Major Removals • Pavement (conservative pavement section assumptions) • Earthwork (excavation, borrow, geotech recommendation [e.g., graded solid rock, geotextiles], rock cuts) • Barrier/Guardrail • Drainage System • Structures (hydraulic and non-hydraulic) • Walls (retaining, sound) • Sign structures • TSMO (ITS, signals, and lighting) | All Items quantified and estimated by Discipline - Compiled by Roadway Design Lead Engineer. | All Items quantified and estimated by Disciplines, Headquarters and 3rd Party - Compiled by Roadway Design Lead Engineer. | Completed by Headquarters Construction.
Statewide and Regional Averages for Unit Prices
| % BASED ITEMS |  | Recommended Values: Mobilization 8% of Construction - Highway Program 10% of Construction - All other Programs Traffic Control 5% of Construction - Highway Program, New Bridge, ITS 15% of Construction - Bridge Repair 25% of Construction - Safety Program | Utilize production based unit price estimate process. |  | Completed by Headquarters Construction.
| CONTINGENCY FOR CONSTURCTION ITEMS |  | Add Contingency to Bid Items Total - Recommended Values: • 15% Rural minor pavement preservation without complications. • 20% Urban minor pavement preservation without complications. • 25% New construction, reconstruction, rehabilitation, widening, trails, landscaping, and enhancement. - Adjust per understanding of project Level of Detail (LOD). | Lower Contingency Based on LOD - Recommended Values: • 10% Rural minor pavement preservation without complications. • 15% Urban minor pavement preservation without complications. • 20% New construction, reconstruction, rehabilitation, widening, trails, landscaping, and enhancement. - Adjust per understanding of project Level of Detail (LOD). | Lowest Level of Contingency - Recommended Values: • 5% Rural minor pavement preservation without complications. • 8% Urban minor pavement preservation without complications. • 10% New construction, reconstruction, rehabilitation, widening, trails, landscaping, and enhancement. | No Contingency - All items should be estimated with limited risk of project changes.
NON-BID | OTHER |  | • ROW funded amount • Utilities and Railroad Estimate (1RR2 & 1UT2) • Environmental mitigation (streams and wetland design or credits) • Incentives 2% of construction | • ROW funded amount (2RW1) • Utilities and Railroad updated estimate (2UT1/3RR1) • Final environmental mitigation (streams and wetland design or credit costs) • Incentives 2% of construction | • Final ROW costs • Final utility costs • Final incentive costs • Final environmental mitigation (streams and wetland design or credit costs)
| PRELMINARY ENGINEERING |  | PE Recommendations (as applicable): 6% - Rural or Urban Pavement Rehab, and safety projects. 10% - New construction, reconstruction, roadway and bridge rehabilitation, widening, trails, landscaping, and enhancement. 20% - Local Government - Percentage is based on the design complexity vs. construction costs. Adjust the recommendations to fit the anticipated needs of the project. PE costs can range higher than 20% depending on design complexity and the size of the project. Small projects generally have a higher PE % than large projects. |  | Include actual PE costs | Completed by Headquarters Construction.
| CONSTRUCTION ENGINEERING |  | CE Recommended Values: Construction, Reconstruction, Rehabilitation: $500K - $1M: 8.0% $1M - $5M: 7.5% $5M - $15M: 7.0% >$15M: 6.5% Signals or TSMO only: 13.5% | Spot Improvement, Safety, Enhancements: $0 - $500K: 12.0% $500K - $5M: 8.5% $5M - $15M: 7.5% >$15M: 6.5% Local Goverment:16% | Included actual CE costs (as coordinated with Construction) in the estimate. | Completed by Headquarters Construction.
| INFLATION FACTOR | 3.5% per year until Programmed Construction Year
Update Project File at each stage of the project.

## Sheet2
CE Recommended Values: Construction, Reconstruction, Rehabilitation: $500K - $1M: 8.0% $1M - $5M: 7.5% $5M - $15M: 7.0% >$15M: 6.5% Signals or TSMO only: 13.5% | Spot Improvement, Safety, Enhancements: $0 - $500K: 12.0% $500K - $5M: 8.5% $5M - $15M: 7.5% >$15M: 6.5% Local Goverment:16%
CE Recommended Values: Construction, Reconstruction, Rehabilitation: <$50M: 8.5% $50M - $100M: 10% >$100M: 14% Signals or TSMO only: 13.5% | Spot Improvement, Safety, Enhancements: $0 - $500K: 12.0% $500K - $5M: 8.5% $5M - $15M: 7.5% >$15M: 6.5% Local Goverment: 16%