## Slide 1: CMGC04
Broadway Bridge

## Slide 2: Project Overview
Project Status Update
Broadway Full Closure
Detour Routes
Renderings

## Slide 3: Project Status
Schedule
  Currently trending on schedule
  Adjusted closure date to September 8th
Construction
  Setting bridge deck panels
  Beam/diaphragm bolt up
  Drainage on Broadway

## Slide 4: Project Pictures

## Slide 5: Current Progress Picture

## Slide 6: Remaining Work
  Concrete closure pours
  Drainage
  Paving
  Parapets/Fencing
  Sidewalk
  Lighting

## Slide 7: Closure Details
An 8-week full closure
Detour Routes
Maintain access to adjacent businesses
At the end of the closure, at least two lanes in each direction (4 lanes total) must be opened to traffic

## Slide 8: Traffic Management Adjustments
BlueTOAD (camera and CCTV)
Signal timing
Increased signage
Modified detour on Porter and 11th Ave.
Additional security presence
DMS utilization and local message boards

## Slide 9: Schedule – Post Closure Construction
Post Closure Work (September 2023 – October 2023)
  Maintain four (4) lanes traffic
  Erect sidewalks, fencing, lighting and parapets
Project Complete: October 31, 2023

## Slide 13: Stay Connected
Project Website
Email Newsletter Signup
Rebekah Hammonds Contact

## Slide 14: Comments and Questions?
https://www.tn.gov/tdot/projects/region-3/nashville-broadway-viaduct.html