## Sheet1
FileNet Project Deliverables and Plan Sets (PDN)
Deliverable Plan Set | File Naming Convention and File Format (nnnnnn-nn is the project PIN) | Comments | PPRM Activity | PDN | RDG
Line and Grade Field Review | nnnnnn-nn-LineandGradePlans.pdf nnnnnn-nn-LineandGradePlans.zip | See PDN 1RD1 for submittal packet requirements. | 375 | 1RD1 | 1-105.01
Line and Grade Estimate | nnnnnn-nn-LineandGradeEstimate.xlsm | See Roadway Design Guidelines Chapter 1-401.00, Creating the Roadway Quantities Estimate and 1-402.01, Submittal of the Line and Grade Estimate. | 390 | 1RD1 | 1-402.01
Public Meeting Plans | nnnnnn-nn-PublicMeeting.pdf | See Footnotes and Roadway Design Guidelines Chapter 1-105.01 for submittal packet requirements. | 390 |  | 1-105.05
Incidentals | nnnnnn-nn-Incidentals.pdf | See PDN 1PM1 for submittal packet requirements. | 425
Functional Design Plans Field Review | nnnnnn-nn-FunctionalDesignPlansFieldReview.pdf nnnnnn-nn-FunctionalDesignPlansFieldReview.zip | See Footnotes and Roadway Design Guidelines Chapter 1-105.02 for submittal packet requirements. See PDN 2RD1. For other divisions that may be submitting Functional Design Plans Field Review documents for inclusion in the submittal packet, please use the following naming convention when placing files on FileNet: nnnnnn-nn-FunctionalDesignPlansFieldReview-Bridge.pdf nnnnnn-nn-FunctionalDesignPlansFieldReview-ITS.pdf nnnnnn-nn-FunctionalDesignPlansFieldReview-Lighting.pdf nnnnnn-nn-FunctionalDesignPlansFieldReview-NaturalStreamDesign.pdf nnnnnn-nn-FunctionalDesignPlansFieldReview-Wall.pdf nnnnnn-nn-FunctionalDesignPlansFieldReview-Signal.pdf nnnnnn-nn-FunctionalDesignPlansFieldReview-Geotech.pdf nnnnnn-nn-FunctionalDesignPlansFieldReview-Hydraulic.pdf | 540 | 2RD1 | 1-105.02
Functional Design Plans Estimate | nnnnnn-nn-FunctionalDesignPlansEstimate.xlsm | See Roadway Design Guidelines Chapter 1-401.00, Creating the Roadway Quantities Estimate and 1-402.02, Submittal of R.O.W. Estimate for R.O.W. or Utilities Only Funding. |  | 2RD1 | 1-402.02
Functional Design Plans Submittal | nnnnnn-nn-FunctionalDesignPlans.pdf nnnnnn-nn-FunctionalDesignPlans.zip | See PDN 2RD1 for submittal packet requirements. For other divisions that may be submitting Functional Design Plans Field Review documents for inclusion in the submittal packet, please use the following naming convention when placing files on FileNet: nnnnnn-nn-FunctionalDesignPlans-Bridge.pdf nnnnnn-nn-FunctionalDesignPlans-ITS.pdf nnnnnn-nn-FunctionalDesignPlans-Lighting.pdf nnnnnn-nn-FunctionalDesignPlans-NaturalStreamDesign.pdf nnnnnn-nn-FunctionalDesignPlans-Wall.pdf nnnnnn-nn-FunctionalDesignPlans-Signal.pdf nnnnnn-nn-FunctionalDesignPlans-Geotech.pdf nnnnnn-nn-FunctionalDesignPlans-Hydraulic.pdf |  | 2RD1 | 1-503.03
Permit Sketches | nnnnnn-nn-PermitSketches.pdf | See Roadway Design Guidelines Chapter 5-404.00 Environmental Permit Requirements. See also PDN 2RD1 | 575 | 2RD1
Natural Stream Design Plan | nnnnnn-nn-NSD.pdf | Final sealed plan set submitted by Environmental Division and added to the Environmental FileNet folder. See Roadway Design Guidelines Chapter 5-407.00, Addition of Natural Stream Design Sheets to Functional Design Plans for required information. |  | 1EN1 - 4EN1
SWPPP | nnnnnn-nn-SWPPP.pdf | Final signed SWPPP submitted by Environmental Division or Regional Environmental Tech group. See TDOT Environmental Guide and PDN 3EN3 for additional information about SWPPP Sheets required information |  | 1EN1 - 4EN1
Utility Plans | nnnnnn-nn-Construction-Utility.pdf or nnnnnn-nn-Construction-Utility-Rev-mm-dd-yy.pdf nnnnnn-nn-UtilityConstruction.zip or nnnnnn-nn-UtilityConstruction-Rev-mm-dd-yy.zip nnnnnn-nn-UtilityConstructionEstimate.xlsm or nnnnnn-nn-UtilityConstructionEstimate-Rev-mm-dd-yy.xlsm nnnnnn-nn-UtilitySpecs.pdf or nnnnnn-nn-UtilitySpecs-Rev-mm-dd-yy.pdf | See Footnotes. These plans will be the final sealed plan set. Utility Plans revisions, if any, will necessitate another uploaded plan set in entirety. See naming convention for revisions. Utility Plans, CADD, Specifications, and Estimate Files Will Be Loaded onto FileNet by the Utility Section of the R.O.W. Division. |  | 1UT1 - 3UT3
Right-of-Way Estimate | nnnnnn-nn-RoadwayROWEstimate.xlsm | See Roadway Design Guidelines Chapter 1-402.02 Submittal of R.O.W. Estimate for R.O.W. or Utilities Only Funding. | 585 | 2RD1 | 1-402.02
Plan-in-Hand Plans Field Reveiw | nnnnnn-nn-PIHFieldReview.pdf nnnnnn-nn-PIHFieldReview.zip | See Footnotes and Roadway Design Guidelines Chapter 1-105.0d for submittal packet requirements. See 3RD1 for related info. For other divisions that may be submitting Plan-in-Hand documents for inclusion in the submittal packet, please use the following naming convention when placing files on FileNet: nnnnnn-nn-PIHFieldReview-Roadway.pdf nnnnnn-nn-PIHFieldReview-Bridge.pdf nnnnnn-nn-PIHFieldReview-Geotech.pdf nnnnnn-nn-PIHFieldReview-ITS.pdf nnnnnn-nn-PIHFieldReview-Lighting.pdf nnnnnn-nn-PIHFieldReview-NaturalStreamDesign.pdf nnnnnn-nn-PIHFieldReview-Walls.pdf nnnnnn-nn-PIHFieldReview-Signal.pdf nnnnnn-nn-PIHFieldReview-UtilityRainbows.pdf | 600 | 3RD1, 3PM2 | 1-105.06
Plan-in-Hand Plans Submittal | nnnnnn-nn-Plan-in-HandPlans.pdf nnnnnn-nn-Plan-in-HandPlans.zip | See Footnotes and Roadway Design Guidelines Chapter 1-105.0d for submittal packet requirements. See 3RD1 for related info. For other divisions that may be submitting Plan-in-Hand documents for inclusion in the submittal packet, please use the following naming convention when placing files on FileNet: nnnnnn-nn-PIH-Roadway.pdf nnnnnn-nn-PIH-Bridge.pdf nnnnnn-nn-PIH-Geotech.pdf nnnnnn-nn-PIH-ITS.pdf nnnnnn-nn-PIH-Lighting.pdf nnnnnn-nn-PIH-NaturalStreamDesign.pdf nnnnnn-nn-PIH-Walls.pdf nnnnnn-nn-PIH-Signal.pdf nnnnnn-nn-PIH-UtilityRainbows.pdf |  | 3RD1 | 1-105.07
Plan-in-Hand Estimate | nnnnnn-nn-RoadwayPIHFieldReviewEstimate.xlsm | See Roadway Design Guidelines Chapter 1-402.04 Submittal of Plan-in-Hand Estimate for Field Review. |  | 3RD1 | 1-402.04
NPDES | nnnnnn-nn-NPDES.pdf | This plan set shall be updated immediately following the Plan-in-Hand Field Review and include all updates as defined in the PS&E Field Review from the SWPPP Consultant. This plan set will be used for NPDES application. See PDN 3EN3. |  | 1EN1 - 4EN1
Draft Traffic Control Sheets | nnnnnn-nn-TrafficControl.pdf | These are updated traffic control plans based on items discussed at the Functional Design Plans Field Review. See Roadway Design Guidelines Chapter 1-105.02 | 600 | 3RD1
Work Zone Significance Determination & Traffic Management Plan | nnnnnn-nn-PIH-TMP.pdf nnnnnn-nn-TMP.pdf | See TDOT Work Zone Safety and Mobility manual and Traffic Management Plan Workbook. A signed copy shall be turned in with Functional plans submittal. It shall be re-evaluated at the Plan-in-Hand Field Review submittal and a Plan-in-Hand TMP shall be developed. If changes are made at the Plan-in-Hand or PS&E phase, revise the associated document and replace original on FileNet with the same name. See Roadway Design Guidelines Chapter 1-105.05, 1-105.06, 1-105.07, or 1-105.08 | 600 & 695 | 3RD1
Utility Rainbow Plans | nnnnnn-nn-UtilityRainbows.pdf nnnnnn-nn-UtilityRainbows-Rev-mm-dd-yy.pdf | These plans are submitted by the utility companies approximately 120 days after the Functional Design plans are turned in. The Regional R.O.W. offices are responsible for uploading the plans to the FileNet Folder. See Roadway Design Guidelines Chapter 1-105.07 and 1-105.08 for submittal packet requirements and 1-500.00 for Field Review requirements. | N/A | 3UT1
Constructability Review | nnnnnn-nn-ConstructabilityReview.pdf nnnnnn-nn-ConstructabilityReview.zip | See PDN 3PM2 for more information. | 690 | 3PM2
PS&E Field Review | nnnnnn-nn-PS&EFieldReview.pdf nnnnnn-nn-PS&EFieldReview.zip | See Footnotes and Roadway Design Guidelines Chapter 1-105.06 for submittal packet requirements. This plan set will be used for NEPA Re-evaluation and for obtaining SWPPP comments. For other divisions that may be submitting PS&E Field Review documents for inclusion in the submittal packet, please use the following naming convention when placing files on FileNet: nnnnnn-nn-PS&EFieldReview-Roadway.pdf nnnnnn-nn-PS&EFieldReview-Bridge.pdf nnnnnn-nn-PS&EFieldReview-Geotech.pdf nnnnnn-nn-PS&EFieldReview-ITS.pdf nnnnnn-nn-PS&EFieldReview-Lighting.pdf nnnnnn-nn-PS&EFieldReview-NaturalStreamDesign.pdf nnnnnn-nn-PS&EFieldReview-Walls.pdf nnnnnn-nn-PS&EFieldReview-Signal.pdf nnnnnn-nn-Utility.pdf | 695 | 4RD1, 4PM2 | 1-105.06
PS&E Field Review Estimates | nnnnnn-nn-RoadwayPS&EEstimate.xlsm nnnnnn-nn-RoadwayPS&EEstimate.xlsm nnnnnn-nn-StructuresPS&EEstimate.xlsm nnnnnn-nn-TrafficOpsITSPS&EEstimate.xlsm nnnnnn-nn-TrafficOpsSignalsPS&EEstimate.xlsm nnnnnn-nn-TrafficOpsLightingPS&EEstimate.xlsm nnnnnn-nn-UtilityPS&EEstimate.xlsm | Send updated Roadway, Structure, and Utility estimate to Bid Analysis & Estimating Office. See Roadway Design Guidelines Chapter 1-402.04 See Chapter 1-402.04 and 1-402.05 for Utility Estimate requirements. |  | 4RD1 | 1-402.05
Roadway Plans Final PS&E | nnnnnn-nn-PS&E-Roadway.pdf nnnnnn-nn-PS&E-Roadway.zip | See Footnotes and Roadway Design Guidelines Chapter 1-105.07 for submittal packet requirements. For other divisions that may be submitting Final Construction Plans Review documents for inclusion in the submittal packet, please use the following naming convention when placing files on FileNet: nnnnnn-nn-TitleSheet.pdf nnnnnn-nn-TMP.pdf nnnnnn-nn-PS&E-Roadway.pdf nnnnnn-nn-GradingReport.pdf nnnnnn-nn-SpecialProvisionOrder.pdf nnnnnn-nn-PS&E-Checklist.pdf | 695 | 4RD1 | 1-105.09
PS&E Final Plans | nnnnnn-nn-FinalPS&E.pdf | See Footnotes and Roadway Design Guidelines Chapter 1-105.08 for submittal packet requirements. For other divisions that may be submitting PS&E Field Review documents for inclusion in the submittal packet, please use the following naming convention when placing files on FileNet: nnnnnn-nn-PS&E-Roadway.pdf nnnnnn-nn-PS&E-Bridge.pdf nnnnnn-nn-PS&E-Geotech.pdf nnnnnn-nn-PS&E-ITS.pdf nnnnnn-nn-PS&E-Lighting.pdf nnnnnn-nn-PS&E-NaturalStreamDesign.pdf nnnnnn-nn-PS&E-Walls.pdf nnnnnn-nn-PS&E-Signal.pdf nnnnnn-nn-PS&E-SWPPP.pdf nnnnnn-nn-PS&E-Utility.pdf |  | 4RD1 | 1-105.10
Construction Letting Files | nnnnnn-nn-ConstructionLettingFiles.zip | See Roadway Design Guidelines Chapter 1-105.09 for submittal requirements. |  | 4RD1 | 1-105.10
Complete Package | nnnnnn-nn-FinalPS&EPackage.zip | See PDN 4RD1 for submittal packet requirements. Include a copy of Request for Comments Notification For other divisions that may be submitting Final Construction Plans Review documents for inclusion in the submittal packet, please use the following naming convention when placing files on FileNet: nnnnnn-nn-TitleSheet.pdf nnnnnn-nn-TMP.pdf nnnnnn-nn-PS&E-Roadway.pdf nnnnnn-nn-GradingReport.pdf nnnnnn-nn-PS&E-Bridge.pdf nnnnnn-nn-PS&E-Geotech.pdf nnnnnn-nn-PS&E-ITS.pdf nnnnnn-nn-PS&E-Lighting.pdf nnnnnn-nn-PS&E-NaturalStreamDesign.pdf nnnnnn-nn-PS&E-Walls.pdf nnnnnn-nn-PS&E-Signal.pdf nnnnnn-nn-PS&E-SWPPP.pdf nnnnnn-nn-PS&E-Utility.pdf | 710 | 4RD1 | 1-105.10
Resurfacing PS&E Submittal | nnnnnn-nn-PS&E.pdf | Place PS&E document on FileNet when submitting the resurfacing plan set for review.
Roadway Letting Revision | nnnnnn-nn-RoadwayConstruction-LettingRev-mm-dd-yy.pdf nnnnnn-nn-ConstructionLettingFiles-Rev-XX.XX.XX.zip | See Footnotes and Roadway Design Guidelines Chapter 1-105.09 for submittal packet requirements. Letting and/or Construction Plan revisions, if any, will necessitate another uploaded plan set in its ENTIRETY. If the proposed revision impacts any cross sections and/or the proposed terrain (.tin) file of the Contractor Letting Files, an updated submittal shall be uploaded to Filenet. For other divisions that may be submitting construction letting documents, please follow the naming convention shown and substitute your division’s name where “Roadway” is shown under the File Naming and File Format column. [Geotech, Structures, TrafficOpsITS, TrafficOpsSignals, TrafficOpsLighting, Utility] | 715 |  | 1-105.11
Roadway Construction Revision | nnnnnn-nn-RoadwayConstruction-Rev-mm-dd-yy.pdf | See Footnotes and Roadway Design Guidelines Chapter 1-105.10 for submittal packet requirements. Letting and/or Construction Plan revisions, if any, will necessitate another uploaded plan set in its ENTIRETY. If the proposed revision impacts any cross sections and/or the proposed terrain (.tin) file of the Contractor Letting Files, an updated submittal shall be uploaded to Filenet. For other divisions that may be submitting construction letting documents, please follow the naming convention shown and substitute your division’s name where “Roadway” is shown under the File Naming and File Format column. [Geotech, Structures, TrafficOpsITS, TrafficOpsSignals, TrafficOpsLighting, Utility] |  |  | 1-105.12
PS&E Estimate | nnnnnn-nn-RoadwayLettingEstimate.xlsm nnnnnn-nn-RoadwayConstructionEstimate.xlsm nnnnnn-nn-StructuresConstructionEstimate.xlsm nnnnnn-nn-TrafficOpsITSConstructionEstimate.xlsm nnnnnn-nn-TrafficOpsSignalsConstructionEstimate.xlsm nnnnnn-nn-TrafficOpsLightingConstructionEstimate.xlsm nnnnnn-nn-UtilityConstructionEstimate.xlsm | Turned in with final submittal for letting. See Roadway Design Guidelines Chapter 1-402.05, Submittal of PS&E Estimate for Letting Process for additional information | 715 | 4RD1 | 1-402.06
Project Folder | nnnnnn-nn-ProjectFolder.pdf or nnnnnn-nn-ProjectFolder.zip nnnnnn-nn-ProjectFolder-Addendum.pdf or nnnnnn-nn-ProjectFolder-Addendum.zip | See Roadway Design Guidelines Chapter 1-102.00, Project Folder for required information. | 715 |  | 1-102.00
PS&E Estimate for Letting Revision | nnnnnn-nn-PS&EEstimate-Rev-mm-dd-yy.xlsm nnnnnn-nn-RoadwayConstructionEstimate-Rev-mm-dd-yy.xlsm nnnnnn-nn-StructuresConstructionEstimate-Rev-mm-dd-yy.xlsm nnnnnn-nn-TrafficOpsITSConstructionEstimate-Rev-mm-dd-yy.xlsm nnnnnn-nn-TrafficOpsSignalsConstructionEstimate-Rev-mm-dd-yy.xlsm nnnnnn-nn-TrafficOpsLightingConstructionEstimate-Rev-mm-dd-yy.xlsm nnnnnn-nn-UtilityConstructionEstimate-Rev-mm-dd-yy.xlsm | If a Letting Revision consists of changes, additions, or deletions of quantities, an "Estimate Revision Request" form must be submitted as part of the revision. If a Letting Revision is issued but no quantities were revised the Designer shall state “No Quantities Affected” in the body of the Letting revision email. Estimate revisions are not needed after the project is let to construction. See Roadway Design Guidelines Chapter 1-402.06, Revision of PS&E Estimate for Letting Process for additional information. |  |  | 1-402.07
Footnotes | The Zip file placed on FileNet includes the following: • Required Bentley MicroStation files are sheet files (*.sht) that make up a plan set and all reference DGN files to those sheet files including, but not limited to, the *Survey.dgn, * Alignments.dgn, *Proposed.dgn, and *MainlineXSections.dgn files. • Required Bentley GEOPAK *.tin files are the existing ground surface and all proposed surfaces for the project. Required Bentley GEOPAK *.gpk file is the project GEOPAK file containing all project geometry including, but not limited to, all existing and proposed alignments, existing and proposed profiles, and proposed R.O.W. and easements. R.O.W. Acquisition Excel file.