## Module 1
TDOT - Subsurface Utility Engineering (SUE) Decision Tool
This decision support tool is not a discrete deciding factor for the type of utility investigation to be implemented within a TDOT project. This tool is intended to be a collaborative framework led by the project manager (PM) to consider various aspects of risk in determining if a procedural subsurface utility investigation is warranted for a project and provide assistance in determining the extent of that investigation. The decision tool includes three modules. - Module 1 is intended to help the PM determine if using the remainder of the tool is necessary, i.e., is a procedural utility investigation needed for a project? - Module 2 assists the PM in determining the type of investigation to consider, and - Module 3 provides a framework or checklist for the PM and collaborators to assess varying utility-related project risks and utility risks. These assessments and the associated scoring rubric provide guidance for the PM to use in making a final determination in regard to the utility investigation needs for a project.
When & How to Use this Tool:
The SUE decision support tool may be revisited through the development of a project to re-evaluate the utility investigation approach applied. Initial use of the tool should begin early in the PDN, at Stage 0 – Planning, by completing at least Module 1. After the Utility Inventory is completed—led by the Regional Utility Office or a consultant—the information gathered will support the completion of Modules 2 and 3. If needed, the first full iteration of the tool should be completed by Stage 1 – Context/Scoping. To initiate the Utility Inventory, the lead utility coordinator should begin collecting relevant utility information using the following items as a starting point.
|  | ☑ | Use Google Earth and Google Street View within the project area to visually identify utility features. On a case-by-case basis, a field visit may be prudent.
|  | ☑ | Gather historical IRIS data, permits, One-Call records, available survey information, local knowledge, and professional judgment that identifies or indicates the presence and location of utility features.
|  | ☑ | Make a not-to-scale sketch of major suspected utilities synthesized from the above observations on a background kmz file.
|  | ☑ | Highlight any probable electric and telecom vaults.
|  | ☑ | Review data and sketch with the Project Point of Contact (PPOC) for inclusion into the Utility Risk Register and a SUM versus SUE decision for the project.
Module 1 is an initial screening process; Module 2 allows a deeper evaluation to determine the type of investigation; and Module 3 begins the evaluation of the project to assist in scoping the SUE services needed.
Module 1: Project Information
Project Name and PIN:
County/Route/Section:
Project Description: (General Summary)
Project Scope: (Actual Work Scope Note: If the scope of the project changes, it is recommended that utility impact analysis be done again.)
No. | Module 01: Screening Questions |  |  | Column 1 |  | Column 2
1 | Does the project require excavation, demolition, or significant underground disturbances (e.g., vibration, weight/compression, etc.)? |  |  |  | NO |  | YES or Unknown | 3 | 0 | 0
2 | Is there evidence of underground utilities in the project area and is there a likelihood that the project will have an impact on the existing utilities (above or below ground) [e.g., utility congestion, areas sensitive to utility risks or outages, large, expensive, or hard to relocate items, etc.]? |  |  |  | NO |  | YES or Unknown
3 | Is the project being delivered using alternative delivery contracts? Some projects are proposed to be delivered through alternative delivery contracts, such as Design Build (DB), Progressive DB, Construction Manager/General Contractor (CMGC), and P3, rather than the traditional Design Bid Build (DBB). This may cause a need for greater utility awareness to reduce contractor-perceived risks to the demands of the project schedule. |  |  |  | NO |  | YES or Unknown | 10 | 0 | 0
[9 empty] | 0 | 0
Instructions:
- If there are no boxes checked in Column 2, then it is generally not necessary to evaluate the project for implementation of a SUE investigation. Module 2 may still be used to assess the project if desired. - If any of the boxes in Column 2 are checked, please proceed with Module 2 to consider appropriate utility investigation levels.

## Module 2
Module 2: General Risk Considerations
Module 2 will assist the Project Manager (PM) and team with an early decision regarding the utility investigation type. If the results of Module 2 indicate the need for a utility investigation, the use of Module 3 will help the PM and project team consider additional risks that can aid in scoping the utility investigation. Using the Utility Inventory and your knowledge of the project characteristics, answer the questions below. NOTE: For a detailed explanation of each question, refer to Module 2 – Details, or hover over the corresponding cell in the spreadsheet to view the description.
Weight Factor | General Risk Considerations - Questions | Column 1 |  | Column 2 |  | Column 3 |  | Reset Line
1 | Which of the responses provides the best project area description? |  | Rural |  | Suburban |  | Commercial/ Urban |  | 4 | 0 | 0 | 0
0.75 | What type of project is being developed for construction? |  | Minimal |  | Minor |  | Major |  | 4 | 0 | 0 | 0
1 | What is the depth of excavation or height of fill (embankment) involved in the project? |  | None |  | Shallow |  | Deep |  | 4 | 0 | 0 | 0
0.75 | What number of utilities (underground) is expected within the project footprint? |  | Low |  | Average |  | High |  | 4 | 0 | 0 | 0
0.5 | Based on anticipated coordination and relocation challenges, what type of utility service represents the greatest potential risk within the project footprint? |  | Energy |  | Municipal |  | Telecomm |  | 1 | 1 | 1 | 0.5
0.75 | What is the pattern of utilities found within the project footprint? |  | Simple |  | Moderate |  | Complex |  | 4 | 0 | 0 | 0
0.5 | To what extent can reliable utility information help manage or resolve the identified utility-related risks on this project? |  | Low |  | Medium |  | High |  | 4 | 0 | 0 | 0
[9 empty] | 25 | 1 | 1 | 0.5
| Utility Investigation Level |  | Assessment Not Complete | [5 empty] | 2 |  | 1
| SUE Consulting Services (ASCE 38-22) obtain comprehensive and reliable utility location and attribute information and engineering |  |  | Above 2.3
| Hybrid Approach |  |  | 1.7 to 2.3
| Subsurface Utility Mapping (SUM) obtain some utility location information |  |  | 1.2 to 1.7
| No field investigations |  |  | Below 1.2
Note on B6: Project area description indicates the location or nature of the project. This factor is separated into three different categories: (1) rural, (2) suburban, and (3) commercial/urban. In general, urban/commercial areas have more complex and congested roadways and utilities because of higher building and infrastructure density. Therefore, a more urbanized or commercialized area usually means more risks associated with utilities, so increased investigation levels are recommended.
Note on B7: Type of project often indicates whether a more intense utility investigation is needed. As an example, a project that is primarily pavement resurfacing may only need minimal areas of investigation. The types of projects identified include (1) Minimal (i.e., Pavement Surface Repairs, Bridge Deck or Joint Repairs), (2) Minor (i.e., Signal or Lighting Projects, Pedestrian and Bike Projects, Noise Barriers, or Structure Replacements), and (3) Major (i.e., New alignments, Widening or Realignments, Intersection or Interchange Improvements, or Drainage Systems). This can also be thought of as how likely this type of project will impact utilities if present from low (1) to high (3).
Note on B8: Depth of excavation required can also present varying risk levels for encountering utilities and associated risks. This factor is separated into three different categories: (1) without excavation, (2) shallow excavation (i.e., less than 3 feet), and (3) deep excavation (i.e., anything over 3 feet).
Note on B9: Number of utilities indicates the number of subsurface utilities that can be expected to be encountered on the project. If there are many utilities expected within the project, more reliable data/information will be required to successfully locate the utilities. A higher density of utilities means more utility complexity, which requires getting better information related to underground utilities on the project.The categories for this risk are a Low number of utilities (i.e. 0-2), an Average number of utilities (i.e. 3-6), or a High number of utilities (i.e. >6).
Note on B10: Utility service type refers to the category of subsurface utility facilities anticipated within the project footprint. Utilities can generally be grouped into three categories: (1) energy (e.g., gas and electric), (2) municipal (e.g., water and sewer), and (3) telecommunications (e.g., fiber optics, cable, and telephone). The anticipated coordination and relocation risk associated with each utility type may vary based on factors such as the reliability and availability of utility records, the utility owner’s technical capabilities, responsiveness during coordination, and ability to support design and relocation efforts within the project schedule. When multiple utility types are present, select the utility category representing the greatest anticipated risk. Do not select all utility types present. While telecommunications utilities are often associated with higher coordination and relocation challenges due to complex networks, multiple service providers, and relocation constraints, municipal utilities may also present significant risks due to outdated or incomplete records, difficulty locating facilities, and limited resources to support design and relocation efforts. This risk assessment should be refined based on project-specific knowledge and the project team’s prior experience coordinating with local utility owners.
Note on B11: Pattern of utilities indicates the configuration of subsurface utilities that can be expected to be encountered on the project. For instance, an intersection in a downtown area may have a more complex pattern of utilities than other areas. Select the most complex pattern present. The categories are: (1) Simple (consists of a few parallel or crossing utilities) , (2) Moderate (Much of the project is simple but a complex area appears to be probable), and (3) Complex (consists of many parallel and crossing utilities).
Note on B12: Project teams led by utility coordinators need to identify and provide solution-oriented management of utility related risks. A component of risk management is establishing a foundation of reliable data. When an accurate representation of the utility locations and attributes assists in identifying and managing risks, SUE services should be considered as a critical resource. This response should be a subjective estimate of the percentage of the identified utility risks that can be managed or even resolved with dependable utility information based upon the project scope and other pertinent information in assessing utility risks. Low- Less than 20% improvement in managing utility related risks by using SUE services, Medium- 20% to 50% improvement in identifying and managing utility risks using SUE services., High- Greater than 50% improvement in identifying and managing utility risks with reliable utility investigation and utility engineering services.

## Module 2 - Details
This section presents detailed descriptions of each question presented in Module 2.
1. Which of the responses provides the best project area description?
Project area description indicates the location or nature of the project. This factor is separated into three different categories: (1) rural, (2) suburban, and (3) commercial/urban. In general, urban/commercial areas have more complex and congested roadways and utilities because of higher building and infrastructure density. Therefore, a more urbanized or commercialized area usually means more risks associated with utilities, so increased investigation levels are recommended. | Rural
Suburban
Commercial/Urban
2. What type of project is being developed for constuction?
Type of project often indicates whether a more intense utility investigation is needed. As an example, a project that is primarily pavement resurfacing may only need minimal areas of investigation. The types of projects identified include (1) Minimal, (2) Minor, and (3) Major. This can also be thought of as how likely this type of project will impact utilities if present from low (1) to high (3). | Repair | (i.e., Pavement Surface Repairs, Bridge Deck or Joint Repairs)
| Rehab | (i.e., Signal or Lighting Projects, Pedestrian and Bike Projects, Noise Barriers, or Structure Replacements)
| New | (i.e., New Alignments, Widening or Realignments, Intersection or Interchange Improvements, or Drainage Systems)
3.What is the depth of excavation (or embankment) involved in the project?
Depth of excavation required can also present varying risk levels for encountering utilities and associated risks. This factor is separated into three different categories: (1) without excavation, (2) shallow excavation, and (3) deep excavation. | None | No excavation
| Shallow | (i.e., less than 3 feet)
| Deep | (i.e., anything over 3 feet)
4. What number of utilities (underground) is expected in the project footprint?
Number of utilities indicates the number of subsurface utilities that can be expected to be encountered on the project. If there are many utilities expected within the project, more reliable data/information will be required to successfully locate the utilities. A higher density of utilities means more utility complexity, which requires getting better information related to underground utilities on the project. | Low | (i.e. 0-2)
| Average | (i.e. 3-6)
| High | (i.e. >6)
5. Based on anticipated coordination and relocation challenges, what type of utility service represents the greatest potential risk within the project footprint?
Utility service type refers to the category of subsurface utility facilities anticipated within the project footprint. Utilities can generally be grouped into three categories: (1) energy (e.g., gas and electric), (2) municipal (e.g., water and sewer), and (3) telecommunications (e.g., fiber optics, cable, and telephone). The anticipated coordination and relocation risk associated with each utility type may vary based on factors such as the reliability and availability of utility records, the utility owner’s technical capabilities, responsiveness during coordination, and ability to support design and relocation efforts within the project schedule. When multiple utility types are present, select the utility category representing the greatest anticipated risk. Do not select all utility types present. While telecommunications utilities are often associated with higher coordination and relocation challenges due to complex networks, multiple service providers, and relocation constraints, municipal utilities may also present significant risks due to outdated or incomplete records, difficulty locating facilities, and limited resources to support design and relocation efforts. This risk assessment should be refined based on project-specific knowledge and the project team’s prior experience coordinating with local utility owners. | Energy | Gas and electric
| Municipal | Water, sewer, etc.
| Telecommunications | Fiber optics, cable, telephone
6. What is the pattern of utilities found within the project footprint?
The pattern of utilities indicates the configuration of subsurface utilities that can be expected to be encountered on the project. For instance, an intersection in a downtown area may have a more complex pattern of utilities than other areas. Select the most complex pattern present. | Simple | A simple pattern of utilities consists of a parallel or crossing utilities.
| Moderate | Much of the project is simple but a complex area appears to be probable.
| Complex | A complex pattern of utilities consists of many parallel and crossing utilities.
7. To what extent can reliable utility information help manage or resolve the identified utility-related risks on this project?
Project teams led by utility coordinators need to identify and provide solution-oriented management of utility-related risks. A component of risk management is establishing a foundation of reliable data. When an accurate representation of the utility locations and attributes assists in identifying and managing risks, SUE services should be considered as a critical resource. This response should be a subjective estimate of the percentage of the identified utility risks that can be managed or even resolved with dependable utility information based upon the project scope and other pertinent information in assessing utility risks. | Low | Less than 20% improvement in managing utility related risks by using SUE services.
| Medium | 20% to 50% improvement in identifying and managing utility risks using SUE services.
| High | Greater than 50% improvement in identifying and managing utility risks with reliable utility investigation and utility engineering services.

## Module 3
Module 3: Detailed Risk Considerations for Setting Utility Investigation Scope
- Each of the following questions should be interpreted with the concept: Will SUE or SUM consulting services reduce or eliminate this concern? Answering these questions does not provide a score, but allows the project team to develop a scope for the utility investigation to align data certainty/accuracy needs with the associated project risks. - NOTE: For a detailed explanation of each question and answer, refer to Module 3 – Details, or hover over the corresponding cell in the spreadsheet to view the description.
No. | Detailed Risk Considerations - Questions | Column 1 |  | Column 2 |  | Column 3 |  | Reset Line
1 | Account for the project’s critical factors/goals, such as an early open-to-traffic date, politically sensitive, or for a major event? |  | Low |  | Medium |  | High |  | 4 | 0 | 0 | 0
2 | For this scope of work, what utility location and attribute confidence level does the project team need to make the correct project decisions? |  | Low |  | Medium |  | High |  | 4 | 0 | 0 | 0
3 | Does the utility risk assessment identify a number of risks that SUE services would assist in reducing? |  | Low |  | Medium |  | High |  | 4 | 0 | 0 | 0
4 | Does the project propose to acquire new ROW that utilities might relocate to? |  | Low |  | Medium |  | High |  | 4 | 0 | 0 | 0
5 | What is the density of the project area regarding real estate and ROW? Are there clusters of businesses or residences? |  | Low |  | Medium |  | High |  | 4 | 0 | 0 | 0
6 | What is the traffic density of the project area? Is it rural, urbanizing, or urban? |  | Low |  | Medium |  | High |  | 4 | 0 | 0 | 0
7 | What is the density of existing utilities within the project area? How many utilities are probable? |  | Low |  | Medium |  | High |  | 4 | 0 | 0 | 0
8 | Does the project scope propose enclosed drainage or open ditches? |  | Low |  | Medium |  | High |  | 4 | 0 | 0 | 0
9 | Are there environmental concerns that restrict design and potential utility relocations? |  | Low |  | Medium |  | High |  | 4 | 0 | 0 | 0
10 | Are there utilities involved that represent a high cost to the citizens to relocate the facility? |  | Low |  | Medium |  | High |  | 4 | 0 | 0 | 0
11 | Are utility service disruptions a significant concern for residents and businesses in this project area? |  | Low |  | Medium |  | High |  | 4 | 0 | 0 | 0
12 | Does the Utility Conflict Matrix (UCM) have a number of potential design conflicts identified? |  | Low |  | Medium |  | High |  | 4 | 0 | 0 | 0
13 | As the project is scoped, what level of risk is likely to be realized during construction to experience unexpected utilities, inaccurate utility relocations, or delays due to relocations? |  | Low |  | Medium |  | High |  | 4 | 0 | 0 | 0
[9 empty] | 52 | 0 | 0 | 0
| Utility Investigation Level |  | Assessment Not Complete | [5 empty] | #DIV/0! |  | #DIV/0!
| SUE Consulting Services (ASCE 38-22) obtain comprehensive and reliable utility location and attribute information and engineering |  |  | Above 2.7
| Hybrid Approach |  |  | 2.1 to 2.7
| Subsurface Utility Mapping (SUM) obtain some utility location information |  |  | 1.5 to 2.1
| No field investigations |  |  | Below 1.5
Note on B6: Some projects do not follow the typical PDN flow due to factors such as having a section of the project open to traffic or an event schedule, or other sensitive factors. These factors may drive a decision to obtain comprehensive and reliable utility data.
Note on D6: No factors.
Note on F6: Factors involved but likely not sufficient to change the PDN flow and schedule.
Note on H6: Factors that will directly affect the development plan and schedule and will have an effect on utility impact determinations and resolutions
Note on B7: Some project scopes are very unlikely to involve utilities in any significant way such as overlays, while others are very likely to have high involvement pointing to the need for comprehensive and reliable data that will greatly reduce TDOT risk.
Note on D7: Project, as scoped, is not likely to impact any utilities (overlays, maintenance, pipe liners, etc.)
Note on F7: Project as scoped may involve utilities – rural culvert or bridge replacements, minor or spot reconstruction of existing pavements, scour protection, etc.
Note on H7: The project, as scoped, anticipates excavation, widening, or added lanes, urban or interstate bridge replacements.
Note on B8: The project team should have conducted a utility red flag and Risk Assessment at initial scoping. Does the risk assessment include risks that SUE consulting services can mitigate?
Note on D8: No risks that SUE would mitigate.
Note on F8: 0-3 risks that SUE would mitigate.
Note on H8: More than 3 identified risks that SUE consulting would mitigate.
Note on B9: Some projects have been scoped not to acquire new ROW. This decision may make it difficult to relocate utilities without risk of delays if the utility has to acquire sufficient room to relocate. Designing to avoid these utilities may require more comprehensive and reliable utility data to achieve the project goals.
Note on D9: Sufficient ROW exists or will be acquired.
Note on F9: New ROW will be acquired for a minimal area such as in urban settings yet there may be utility relocations to address.
Note on H9: Project is scoped to not acquire ROW and there are anticipated utility relocations.
Note on B10: Projects in highly developed areas are likely to encounter a greater number of utilities. The more commercialized the area, the higher the probability of encountering larger and higher-capacity utility infrastructure. In such cases, comprehensive and reliable utility data is essential for effective decision-making.
Note on D10: Any residences or businesses are spaced out, mostly rural.
Note on F10: There are a few residential clusters or a few businesses in the project.
Note on H10: Mostly commercial area with very little vacant space in the project.
Note on B11: Traffic density has a considerable effect on projects, particularly when maintaining traffic flow during construction. High-traffic urban areas are especially challenging to construct in, so minimizing unnecessary utility relocations is highly beneficial. Eliminating such relocations is extremely important and requires comprehensive and reliable utility information.
Note on D11: Rural low traffic (such as-less than 8,000 AADT)
Note on F11: Urbanized with modest traffic (generally 8,000-50,000 AADT)
Note on H11: Complex area with high traffic volumes (more than 50,000 AADT)
Note on B12: If the evaluation happens after a utility inventory has been accomplished there may be a sense of how many utilities are likely to be involved in the project. The more dense the utilities, the more comprehensive and reliable utility data will be needed.
Note on D12: All utilities are aerial; therefore, they are visible and identifiable.
Note on F12: Less than 3 utilities are likely underground in the project area.
Note on H12: More than 3 utilities are likely underground in the project area.
Note on B13: One of the most important design features for utility impacts is the project’s drainage. Enclosed gravity systems are likely to have impacts to existing utilities, but careful consideration of the design may reduce design impacts to existing utilities. This design requires accurate and reliable utility data.
Note on D13: Existing drainage is sufficient for the project.
Note on F13: Drainage will be enhanced without significant new drainage infrastructure or ditch grades can be modified to avoid unnecessary relocations of utilities.
Note on H13: The project will require substantial drainage design with a high probability of impact to utilities.
Note on B14: There are times when environmental features -such as historic properties and buildings, parks, mitigation sites, protected streams, and wetlands- can restrict design. These same restrictions are likely to also affect utility designs and relocations. In such cases, it may be more important to design to avoid utilities, which require more reliable utility data.
Note on D14: No environmental restrictions are anticipated.
Note on F14: Environmental concerns are expected to have little to no impact on utility relocations.
Note on H14: The project is located in a historic area with no additional space for utility relocation, or in a location with environmental constraints, such as wetlands or other sensitive areas, that impact utility placement.
Note on B15: The cost of relocating utilities is realized by the end users. Therefore, the cost of relocation is a factor in determining the feasibility of designing to avoid that utility. When a utility relocation cost is high, the analysis to determine whether the utility should be designed around is prudent. Therefore, accurate location and attribute information provided by a SUE consultant will be essential for decision-making.
Note on D15: The relocation costs are less than $75,000
Note on F15: Relocation costs are likely in the range of $75,000-$300,000
Note on H15: The cost to relocate the facility is more than $300,000
Note on B16: Sometimes disconnecting utility services can be very serious. In areas of health care, for example, it may be dangerous to disconnect energy or communication to systems necessary for healthcare services. This may apply in certain commercial areas as well. This question involves both the disconnection of the main and the adjustments for service lines that are impacted by construction. It is important to know what situations and constraints are in place for disconnecting utility infrastructure, such as notices, timing, and more. SUE consulting services may be scoped to assist with identifying these situations and provide accurate and reliable utility information.
Note on D16: It is unlikely that service disruptions will have any significant impact.
Note on F16: Service disruptions will be a nuisance but not significant to business.
Note on H16: The project may have disruptions to health care and other important businesses should there be any abnormal disconnection of services.
Note on B17: If the UCM has been populated with a high number of utility impacts that might be avoidable if reliable utility data is provided, then it is important to raise the level of investigations and utility engineering appropriately.
Note on D17: No utility impacts are identified.
Note on F17: A few utility impacts are identified with a mix of aerial and underground utilities that are not likely to be resolved by SUE services.
Note on H17: Underground utility impacts that are likely to have detrimental effects on the project's success are identified.
Note on B18: Identifying risks that utilities will have an adverse effect on construction is important. One mitigation strategy is to have a comprehensive review of all utilities within the project limits to reduce the risk of unknowns. Any time a utility is to relocate, there is a risk of schedule concerns and potentially second relocations due to not moving to the correct location. Another common risk is that utility contractors are often slow to mobilize and perform as planned. When having accurate and reliable data during project development can minimize or eliminate some of this risk, SUE consultants should be a part of the project team.
Note on D18: The project has little to no risk of utility relocations and/or encountering unknown utility facilities during construction.
Note on F18: There could be utilities impacted which may lead to relocations, but the relocations are easily identifiable and managed as Move Priors or work in state.
Note on H18: There will be multiple utility facilities and likely significant relocations of underground facilities within the project area.

## Page 1 (B) (hidden)
TDOT SUE Decision Tool
- Each of the following questions should be interpreted with the concept: Will SUE consulting services reduce or eliminate this concern? - Refer to PAGE 2 for a more detailed description of each question. - Place the cursor over the cell on the spreadsheet for a detailed description of each question and answer option.
Weight Factor | Complexity Factors | Column 1 |  | Column 2 |  | Column 3 |  | Reset Line
0.75 | Account for the project’s critical factors/goals such as an early open to traffic date, politically sensitive, or for a major event? |  | Low |  | Medium |  | High |  | 1 | 1 | 1 | 0.75
0.75 | Account for the project delivery method? |  | Low |  | Medium |  | High |  | 1 | 1 | 1 | 0.75
0.5 | For this scope of work, what utility location and attribute confidence level does the project team need to make the correct project decisions? |  | Low |  | Medium |  | High |  | 1 | 1 | 1 | 0.5
0.5 | Does the Utility Risk Assessment identify a number of risks that SUE services would assist in reducing? |  | Low |  | Medium |  | High |  | 1 | 1 | 1 | 0.5
0.75 | Does the project propose to acquire new rights-of-way that utilities might relocate to? |  | Low |  | Medium |  | High |  | 1 | 1 | 1 | 0.75
1.25 | What is the density of the project area regarding real estate and ROW, are there clusters of businesses or residences? |  | Low |  | Medium |  | High |  | 1 | 1 | 1 | 1.25
1.25 | What is the traffic density of the project area? Is it rural, urbanizing, or urban? |  | Low |  | Medium |  | High |  | 1 | 1 | 1 | 1.25
0.5 | What is the density of existing utilities within the project area-how many utilities are probable? |  | Low |  | Medium |  | High |  | 1 | 1 | 1 | 0.5
0.5 | Does the project scope propose enclosed drainage or open ditches? |  | Low |  | Medium |  | High |  | 1 | 1 | 1 | 0.5
0.5 | Are there environmental concerns that restrict design and potential utility relocations? |  | Low |  | Medium |  | High |  | 1 | 1 | 1 | 0.5
0.75 | Are there utilities involved that represent a high cost to the citizens to relocate the facility? |  | Low |  | Medium |  | High |  | 1 | 1 | 1 | 0.75
0.25 | Are utility service disruptions a significant concern for residents and businesses in this project area? |  | Low |  | Medium |  | High |  | 1 | 1 | 1 | 0.25
0.75 | Does the UCM have a number of potential design conflicts identified? |  | Low |  | Medium |  | High |  | 1 | 1 | 1 | 0.75
0.25 | As the project is scoped, what level of risk is likely to be realized during construction to experience unexpected utilities, inaccurate utility relocations, or delays due to relocations? |  | Low |  | Medium |  | High |  | 1 | 1 | 1 | 0.25
[9 empty] | 14 | 14 | 14 | 9.25
| Utility Investigation Level |  | 2.018 | [5 empty] | 1.5135 |  | 2.018
| SUE Consulting Services (ASCE 38-22) obtain comprehensive and reliable utility location and attribute information and engineering |  |  | Above 2.7
| Hybrid Approach |  |  | 2.1 to 2.7
| Subsurface Utility Mapping (SUM) obtain some utility location information |  |  | 1.5 to 2.1
| No field investigations |  |  | Below 1.5
Note on B6: Some projects do not follow the typical PDN flow due to factors such as having a section of the project open to traffic or an event schedule or other sensitive factors. These factors may drive a decision to obtain comprehensive and reliable utility data.
Note on D6: No factors.
Note on F6: Factors involved but likely not sufficient to change the PDN flow and schedule.
Note on H6: Factors that will directly affect the development plan and schedule and will have an effect on utility impact determinations and resolutions.
Note on B7: Some projects are proposed as Alternative Contracting Methods (ACM), such as Design Build (DB), Progressive DB, CMGC, and P3 rather than the traditional design bid build (DBB). This may cause a need for greater utility awareness early to reduce contractors perceived risk, and the ability to meet the demands of the project schedule.
Note on D7: Traditional project delivery method.
Note on F7: ACM but project scope is very unlikely to have significant utility involvement.
Note on H7: ACM with utility involvement.
Note on B8: Some project scopes are very unlikely to involve utilities in any significant way such as overlays, while others are very likely to have high involvement pointing to the need for comprehensive and reliable data that will greatly reduce TDOT risk.
Note on D8: Project as scoped is not likely to impact any utilities, (overlays, maintenance, pipe liners, etc.
Note on F8: Project as scoped may involve utilities – rural culvert or bridge replacements, minor or spot reconstruction of existing pavements, scour protection, etc.
Note on H8: The project as scopes anticipates excavation, widening, or added lanes, urban or interstate bridge replacements.
Note on B9: A project should have conducted a utility red flag and Risk Assessment at initial scoping. Does the risk assessment include risks that SUE consulting services can mitigate.
Note on D9: No risks that SUE would mitigate.
Note on F9: 0-3 risks that SUE would mitigate.
Note on H9: More than 3 identified risks that SUE consulting would mitigate.
Note on B10: Some projects have been scoped to not acquire new right-of-way. This decision may make it difficult to relocate utilities without risk of delays if the utility has to acquire sufficient room to relocate. Designing to avoid these utilities may require more comprehensive and reliable utility data to achieve the project goals.
Note on D10: Sufficient ROW exists or will be acquired.
Note on F10: Sufficient ROW exists and utilities that must be relocated have room.
Note on H10: Project is scoped to not acquire ROW and there are complex utilities involved.
Note on B11: A project within an area that is highly developed is likely to have more utilities. The more commercialized the area, the higher probability of more and larger utility infrastructure. A project in these areas will need comprehensive and reliable utility data for decision making.
Note on D11: Any residences or businesses are spaced out, mostly rural
Note on F11: There are a few residential clusters or a few businesses in the project.
Note on H11: Mostly commercial area with very little vacant space in the project.
Note on B12: Project traffic density has a considerable effect on projects especially for maintaining traffic during construction. High traffic urban areas will be especially difficult to construct and any reduction in unnecessary utility relocations is extremely helpful.
Note on D12: Rural low traffic.
Note on F12: Urbanized with modest traffic.
Note on H12: Complex area with high traffic volumes.
Note on B13: If the evaluation happens after a utility inventory has been accomplished there may be a sense of how many utilities are likely to be involved in the project. The more dense the utilities, the more comprehensive and reliable utility data will be needed.
Note on D13: All utilities are aerial.
Note on F13: Less than 3 utilities are likely underground in the project area.
Note on H13: More than 3 utilities are likely underground in the project area.
Note on B14: One of the most important design features for utility impacts is the project’s drainage. Enclosed gravity systems are likely to have impacts to existing utilities but careful consideration of the design may reduce design impacts to existing utilities. This design requires accurate and reliable utility data.
Note on D14: Existing drainage is sufficient for the project.
Note on F14: Drainage will be enhanced without significant new drainage infrastructure or ditch grades can be modified to avoid unnecessary relocations of utilities.
Note on H14: The project will require substantial drainage design with a high probability of impact to utilities.
Note on B15: There are times that environmental features such as historic properties and buildings, parks, wetlands, etc that restrict design. These same restrictions are likely to also affect utility designs and relocations. It may be more important to design to avoid utilities in this circumstance which requires more reliable utility data.
Note on D15: No environmental restrictions are anticipated.
Note on F15: Any environmental concerns will have no to little effect on utility relocations.
Note on H15: The project is in an historic area with no additional areas to relocate utilities or the area has other environmental concerns that affect utility placement
Note on B16: All utility relocations have a cost to the taxpayer or the ratepayers. The citizens will always pay for relocations. When a utility cost is high, the decision to avoid relocating that line may be necessary, therefore accurate location and attribute information provided by a SUE consultant will be beneficial for decision making.
Note on D16: The relocation costs are less than $75,000.
Note on F16: Relocation costs are likely in a range of $75,000-$300,000.
Note on H16: The costs to relocate the facility is more than $300,000.
Note on B17: Sometimes disconnecting utility services can be very serious. In areas of health care for example it may be dangerous to disconnect energy or communication to systems necessary for healthcare services. This may apply in certain commercial areas as well. This question involves both the disconnection of the main and the adjustments for service lines that are impacted by construction. It is important to know what situations and constraints are in place for disconnecting utility infrastructure such as notices, timing, and more. SUE consulting services may be scoped to assist with identifying these situations and provide accurate and reliable utility information.
Note on D17: It is unlikely that service disruptions will have any significant impact.
Note on F17: Service disruptions will be a nuisance but not significant to business.
Note on H17: The project may have disruptions to health care and other important businesses should there be any abnormal disconnection of services.
Note on B18: If the UCM has been populated with a high number of utility impacts that might be avoidable if reliable utility data is provided, then it is important to raise the level of investigations and utility engineering appropriately.
Note on D18: No utility impacts are identified.
Note on F18: A few utility impacts are identified with a mix of aerial and underground that are not likely to be resolved by SUE services.
Note on H18: Underground utility impacts are identified that have probable detrimental affects on the projects success.
Note on B19: Identifying risks that utilities will have an adverse affect on construction is important. One mitigation strategy is to have a comprehensive review of all utilities within the project limits to reduce the risk of unknowns. Any time a utility is to relocate there is risk of schedule concerns and potentially second relocations due to not moving to the correct location. Another common risk is that utility contractors are often slow to mobilize and perform as planned. When having accurate and reliable data during project development can minimize or eliminate some of this risk, SUE consultants should be a part of the project team.
Note on D19: The project has little risk of utility relocations.
Note on F19: Relocations of aerial facilities will be likely but no or managed underground relocations.
Note on H19: There will be multiple relocations of underground facilities within the project area.

## Module 3 - Details
This section presents detailed descriptions of each question presented in Module 3.
1. Account for the project’s critical factors/goals such as an early open to traffic date, politically sensitive, or for a major event?
Some projects do not follow the typical PDN flow due to factors such as having a section of the project open to traffic or an event schedule, or other sensitive factors. These factors may drive a decision to obtain comprehensive and reliable utility data. | Low | No factors.
| Medium | Factors involved but likely not sufficient to change the PDN flow and schedule.
| High | Factors that will directly affect the development plan and schedule and will have an effect on utility impact determinations and resolutions
2. For this scope of work, what utility location and attribute confidence level does the project team need to make the correct project decisions?
Some project scopes are very unlikely to involve utilities in any significant way such as overlays, while others are very likely to have high involvement pointing to the need for comprehensive and reliable data that will greatly reduce TDOT risk. | Low | Project, as scoped, is not likely to impact any utilities (overlays, maintenance, pipe liners, etc.)
| Medium | Project, as scoped, may involve utilities – rural culvert or bridge replacements, minor or spot reconstruction of existing pavements, scour protection, etc.
| High | The project, as scoped, anticipates excavation, widening, adding lanes, and urban or interstate bridge replacements.
3. Does the Utility Risk Assessment identify a number of risks that SUE services would assist in reducing?
The project team should have conducted a utility red flag and Risk Assessment at initial scoping. Does the risk assessment include risks that SUE consulting services can mitigate? | Low | No risks that SUE would mitigate.
| Medium | 0-3 risks that SUE would mitigate.
| High | More than 3 identified risks that SUE consulting would mitigate.
4. Does the project propose to acquire new ROW that utilities might relocate to?
Some projects have been scoped not to acquire new ROW. This decision may make it difficult to relocate utilities without risk of delays if the utility has to acquire sufficient room to relocate. Designing to avoid these utilities may require more comprehensive and reliable utility data to achieve the project goals. | Low | Sufficient ROW exists or will be acquired.
| Medium | Sufficient ROW exists and utilities that must be relocated have room.
| High | Project is scoped to not acquire ROW and there are complex utilities involved.
5. What is the density of the project area regarding real estate and ROW? Are there clusters of businesses or residences?
Projects in highly developed areas are likely to encounter a greater number of utilities. The more commercialized the area, the higher the probability of encountering larger and higher-capacity utility infrastructure. In such cases, comprehensive and reliable utility data is essential for effective decision-making. | Low | Any residences or businesses are spaced out, mostly rural.
| Medium | There are a few residential clusters or a few businesses in the project.
| High | Mostly commercial area with very little vacant space in the project.
6. What is the traffic density of the project area? Is it rural, urbanizing, or urban?
Traffic density has a considerable effect on projects, particularly when maintaining traffic flow during construction. High-traffic urban areas are especially challenging to construct in, so minimizing unnecessary utility relocations is highly beneficial. Eliminating such relocations is extremely important and requires comprehensive and reliable utility information. | Low | Rural low traffic (such as less than 8,000 AADT)
| Medium | Urbanized with modest traffic (generally 8,000-50,000 AADT)
| High | Complex area with high traffic volumes (more than 50,000 AADT)
7. What is the density of existing utilities within the project area? How many utilities are probable?
If the evaluation happens after a utility inventory has been accomplished there may be a sense of how many utilities are likely to be involved in the project. The more dense the utilities, the more comprehensive and reliable utility data will be needed. | Low | All utilities are aerial; therefore, they are visible and identifiable.
| Medium | Less than 3 utilities are likely underground in the project area.
| High | More than 3 utilities are likely underground in the project area.
8. Does the project scope propose enclosed drainage or open ditches?
One of the most important design features for utility impacts is the project’s drainage. Enclosed gravity systems are likely to have impacts to existing utilities, but careful consideration of the design may reduce design impacts to existing utilities. This design requires accurate and reliable utility data. | Low | Existing drainage is sufficient for the project.
| Medium | Drainage will be enhanced without significant new drainage infrastructure or ditch grades can be modified to avoid unnecessary relocations of utilities.
| High | The project will require substantial drainage design with a high probability of impact to utilities.
9. Are there environmental concerns that restrict design and potential utility relocations?
There are times when environmental features -such as historic properties and buildings, parks, mitigation sites, protected streams, and wetlands- can restrict design. These same restrictions are likely to also affect utility designs and relocations. In such cases, it may be more important to design to avoid utilities, which require more reliable utility data. | Low | No environmental restrictions are anticipated.
| Medium | Environmental concerns are expected to have little to no impact on utility relocations.
| High | The project is located in a historic area with no additional space for utility relocation, or in a location with environmental constraints, such as wetlands or other sensitive areas, that impact utility placement.
10. Are there utilities involved that represent a high cost to the citizens to relocate the facility?
The cost of relocating utilities is realized by the end users. Therefore, the cost of relocation is a factor in determining the feasibility of designing to avoid that utility. When a utility relocation cost is high, the analysis to determine whether the utility should be designed around is prudent. Therefore, accurate location and attribute information provided by a SUE consultant will be essential for decision-making. | Low | The relocation costs are less than $75,000
| Medium | Relocation costs are likely in a range of $75,000-$300,000
| High | The costs to relocate the facility is more than $300,000
11. Are utility service disruptions a significant concern for residents and businesses in this project area?
Sometimes disconnecting utility services can be very serious. In areas of health care, for example, it may be dangerous to disconnect energy or communication to systems necessary for healthcare services. This may apply in certain commercial areas as well. This question involves both the disconnection of the main and the adjustments for service lines that are impacted by construction. It is important to know what situations and constraints are in place for disconnecting utility infrastructure, such as notices, timing, and more. SUE consulting services may be scoped to assist with identifying these situations and provide accurate and reliable utility information. | Low | It is unlikely that service disruptions will have any significant impact.
| Medium | Service disruptions will be a nuisance but not significant to business.
| High | The project may have disruptions to health care and other important businesses should there be any abnormal disconnection of services.
12. Does the Utility Conflict Matrix (UCM) have a number of potential design conflicts identified?
If the UCM has been populated with a high number of utility impacts that might be avoidable if reliable utility data is provided, then it is important to raise the level of investigations and utility engineering appropriately. | Low | No utility impacts are identified.
| Medium | A few utility impacts are identified with a mix of aerial and underground utilities that are not likely to be resolved by SUE services.
| High | Underground utility impacts that are likely to have detrimental effects on the project's success are identified.
13. As the project is scoped, what level of risk is likely to be realized during construction to experience unexpected utilities, inaccurate utility relocations, or delays due to relocations?
Identifying risks that utilities will have an adverse effect on construction is important. One mitigation strategy is to have a comprehensive review of all utilities within the project limits to reduce the risk of unknowns. Any time a utility is to relocate, there is a risk of schedule concerns and potentially second relocations due to not moving to the correct location. Another common risk is that utility contractors are often slow to mobilize and perform as planned. When having accurate and reliable data during project development can minimize or eliminate some of this risk, SUE consultants should be a part of the project team. | Low | The project has little to no risk of utility relocations and/or encountering unknown utility facilities during construction.
| Medium | There could be utilities impacted which may lead to relocations, but the relocations are easily identifiable and managed as Move Priors or work in state.
| High | There will be multiple utility facilities and likely significant relocations of underground facilities within the project area.